## Federal Permits
Item | Task Name | Status | Regulatory Citation | Background | Time Frame | Regulatory Agency
Duke Energy
Duke Energy Requirement for Property Sale or Lease
A04.01 | Phase I Environmental Site Assessment (ESA) |  | 40 CFR 312 and ADMP-ERM-EVS-00002 | Evaluation of environmental liability associated with a real estate asset of any type. Can be stand alone effort or could lead to a ESA Phase II. | 3 - 4 weeks | EPA
A04.01.01 | Phase II Environmental Site Assessment (ESA) |  | 39 CFR 312 and ADMP-ERM-EVS-00002 | More in depth evaluation of environmental liability associated with a real estate asset of any type. | 3 - 4 weeks | EPA
A04.01.01.02 | Federal
A04.01.02 | Federal NEPA
A04.01.02.01 | Federal Nexus Evaluation for NEPA Compliance |  | 42 U.S.C. §§4321 et seq.(NEPA) | Projects that require federal action generally must conduct a study to determine if there will be significant impacts to the environment. |  | Federal Agency
A04.01.02.02 | Environmental Impact Statement (EIS)/Environmental Assessment (EA)/Finding of No Significant Impact (FONSI)/Record of Decision (ROD)/Categorical Exclusion (CE) or CE with Documentation |  | 42 U.S.C. §§4321 et seq.(NEPA) | Complete EIS, EA, or CE if nexus evaluation determines NEPA is triggered. | 3 - 4 months | Federal Agency
A04.01.02.03 | Federal Streams and Wetlands
A04.01.02.04 | Preliminary stream and wetland determination investigation |  | 33 U.S.C. §1251 et seq. (1972) | National Wetlands Inventory (NWI) review and preliminary survey. |  | USACE
A04.01.02.05 | Wetland/stream delineation and isolated waters/upland ditches evaluation. |  | 33 U.S.C. §1251 et seq. (1972), USACE 1987 Wetland Delineation Manual | Permit is required to dredge and fill or otherwise disturb wetland or stream areas. It is required prior to the disturbance of any wetland or stream areas. Complete a significant nexus evaluation for isolated waters/upland ditches. Only USACE can determine if a water body is jurisdictional. | 1 day | USACE
A04.01.02.06 | Formal or Preliminary USACE Jurisdictional Determination based on wetland delineation |  | 33 U.S.C. §1251 et seq. (1972) | Formal Jurisdictional Determination (JD) verification request must come from landowner. Preliminary Jurisdictional Determination (PJD) request can be submitted without landowner authorization form. JD or PJD will be used to delineate waters as well as document waters that were previously identified on NWI maps as non-jurisdictional. | 45 days | USACE
A04.01.03 | USACE Permit (Section 10 and/or Nationwide Permit, Regional General Permit, or Individual Permit) |  | 33 U.S.C. §403 33 U.S.C. §§404 (404 permit) | Structures in Navigable Waters/Work Affecting the Course, Location, Condition, or Physical Capacities of Navigable Waters requires Section 10 Permit. Nationwide Permit (NWP), Regional General Permit (RGP), or Individual Permit (IP) is required to dredge and fill or otherwise disturb wetland or stream areas. It is required prior to the disturbance of any wetland or stream areas. Complete a significant nexus evaluation for isolated waters/upland ditches. | 1 day for NWP that has no Pre-Construction Notification (PCN) to 18 months for IP | USACE
A04.01.03.05 | Refuse Act of 1899 |  | 33 U.S.C. §407 | It is unlawful to discharge or dispose of any refuse or pollutant into U.S. navigable waters or tributaries of the US. |  | EPA
A04.01.03.01 | Coastal Barrier & Zone Permitting |  | 16 U.S.C.§§ 3501, 1451 | Relates to coastal waters, shores, and areas near the coast. Refer to the State Coastal Management Plan for map of affected areas. |  | NOAA/State Agency
A04.01.03.07 | Federal Wildlife
A04.01.03.08 | Informal Consultation with USFWS |  | - | Discuss potential project impacts to Threatened & Endangered Species/Migratory Birds/NWRs and seek approval of plans for data gathering and initial mitigation measure plans. |  | USFWS
| U.S. Fish and Wildlife Service Land-Based Wind Energy Guidelines |  | expires 11/20/2021 | Tier 1 preliminary site evaluation, Tier 2 site characterization, Tier 3 field studies to document site wildlife and habitat and predict project impacts, Tier 3 post-construction studies to estimate impacts, Tier 5 other post-construction studies, bmps, mitigation, and advancing use, cooperation, and effective implementation. | multi-year process | USFWS
A04.01.03.06 | Threatened & Endangered (T & E) Species and Habitat Surveys |  | 16 U.S.C. §§ 1531 et seq. | Before the issuance of a federal permit, the permittee must receive clearance for potential impacts on endangered or threatened species. Habitat Survey could lead to a Biological Assessment (BA) or Biological Evaluation (BE). |  | USFWS
| Section 7 Interagency Formal Consultation - T & E Species Impacts Review |  | 16 U.S.C. §§ 1531 et seq. | Submit to and discuss findings with USFWS. USFWS prepares a biological opinion (BO) about the proposed project, whether the species will likely be affected, and whether the proposed project activity will jeopardize the continued existence of a listed species. | 90 days | USFWS
| Section 10 T & E Habitat Conservation Plan (HCP) and Incidental Take Permit (ITP) |  |  | May be required if an activity results in the direct take, result in the capture or handling, or significantly modify the behavior of a listed species. Will include mitigation. | 15 months to 4 years | USFWS
A04.01.03.03 | Avian Preconstruction Survey |  | 16 U.S.C. §§703-712 | It is unlawful to take or otherwise affect a migratory bird or its egg or nest. Desktop review and pre-construction avian field survey necessary. USFWS typically requests 2 years of pre-construction avian surveys but is often willing to accept one year preconstruction with follow up post-construction monitoring. Evaluation of habitat. Adhere to the 2012 USFWS Land Based Wind Energy Guidelines. |  | USFWS
| Bird and Bat Conservation Strategy (BBCS) |  | 16 U.S.C. §§703-712 | Prepare plan for operations. Nearly 1,000 species of birds and bats are protected under the Migratory Bird Treaty Act (MBTA), Endangered Species Act (ESA), and local State regulations. Take of these bird and bat species, whether direct or incidental, is prohibited. Creation of a BBCS required if impacts to avian and bat resources are unavoidable. |  | USFWS
A04.01.04.01 | Bald and Golden Eagle Take Permit |  | 16 U.S.C. §§ 668-668(d) | The knowing or wanton taking (which includes wounding or disturbing) of a bald or golden eagle is a criminal offense. Protection of these species may be addressed in Eagle Conservation Plan (ECP), APP, or BBCS. |  | USFWS
A04.01.04.02 | Eagle Conservation Plan (ECP) |  | 16 U.S.C. 668-668d | Bald and golden eagles are protected under the Bald and Golden Protection Act and the Lacey Act. Take of this species would require a permit. |  | USFWS
A04.01.04.03 | Federal Stormwater and Water Quality
A04.01.04.04 | SPCC Plan: Construction |  | 40 CFR 112 | SPCC required for total capacity of ASTs greater than 1,320 gal and with a reasonable likelihood of impacting water bodies. Likely not needed until construction. | 15 days | EPA
A04.01.04.05 | SPCC Plan: Operations |  | 40 CFR 112 | Spill plan for areas in which large fuel tanks may be used. A separate plan will likely be needed for operations. | 15 days | EPA
A04.01.04.06 | Stormwater Permit: Construction |  | 40 CFR 122.26 | A permit is required for any construction activities that disturb an area greater than 5 acres. Notice of Intent must be submitted prior to construction activities. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.04.07 | Stormwater Pollution Prevention Plan: Construction |  | 40 CFR 122.44 | A plan to address stormwater impacts resulting from construction activities must be prepared. Coverage under NPDES General Permit is required, The plan must be developed prior to the submission of the related NOI. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.04.08 | Stormwater Permit: Operations |  | 40 CFR 122.26 | Operational stormwater discharges authorized under NPDES General permit for industrial facilities, NOI must be submitted prior to the conversion from construction phase to full operation phase. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.04.09 | Stormwater Pollution Prevention Plan: Operations |  | 40 CFR 122.44 | This plan is to address stormwater impacts resulting from facility operations. It must be developed and implemented, kept on site, and updated periodically. It must be developed and implemented prior to submission of the related NOI. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.05 | NPDES Permit |  | 33 U.S.C. §301 | A discharge permit for direct, non-stormwater (i.e., process) discharges to waters of the state must be secured. It is required to be issued before discharges commence. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.05.01 | Publicly Owned Treatment Works Permit |  | 33 U.S.C. §§1281, 1381 | Discharge of industrial effluents to POTW requires compliance with local pretreatment plans. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.05.02 | Safe Drinking Water Act |  | 42 U.S.C. §§ 300, 40 CFR Parts 142-143 (SDWA) | Compliance with the SDWA is required for facilities where drinking water is obtained through an onsite well, or where it is obtained from a municipal source but is further treated before being provided to workers. Compliance consists of monitoring, recordkeeping, reporting, and certain equipment and maintenance requirements. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
Federal Air
A04.01.05 | New Source Performance Standards |  | 40 CFR Part 60, Subparts IIII and JJJJ. | The only air emission sources potentially subject to a New Source Performance Standard (NSPS) would be any stationary compression ignition or spark ignition internal combustion engine for normal or emergency operations. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.05.01 | National Emission Standards for Hazardous Air Pollutants [Maximum Achievable Control Technology (MACT)] |  | 40 CFR Part 63 Subpart ZZZZ | The only air emission sources potentially subject to a National Emission Standard for hazardous Air Pollutants (NESHAP) would be any new stationary reciprocating internal combustion engine (RICE) for normal or emergency operations. State agency may be the authorized and EPA delegated authority for this program. |  | EPA
A04.01.06 | Federal Cultural Resources
A04.01.06.01 | Review of National Register of Historic Places and State Databases |  | 16 U.S.C. §470 | Projects receiving federal permits must receive clearance from the applicable state historical preservation body. Review literature and request concurrence from State Historic Preservation Office (SHPO)/Tribal Historic Preservation Office (THPO) if no impacts anticipated. | 1 day | NPS/SHPO/THPO
A04.01.06.02 | On-site (Phase II) Cultural Resources Survey |  | 16 U.S.C. §470 | Complete on-site survey if impacts are possible. Avoid impacts or mitigate as necessary. Request concurrence from SHPO/THPO. | 3 - 4 weeks | NPS/SHPO/THPO
A04.01.06.03 | Federal Floodplain
A04.01.06.04 | Flood Zone Map Review |  | 44 CFR 60.2 | Certain requirements may exist for facilities located within a 100-year floodplain where there is a floodplain management district. Floodplain development permit or notification may be required if construction occurs in the floodplain. |  | FEMA
A04.01.06.05 | Hydraulics and Hydrology Study for unavoidable floodplain impacts |  | 44 CFR 60.2 |  |  | FEMA
A04.01.07 | Development of Conditional Letter of Map Revision |  | 44 CFR 60.2 |  |  | FEMA
| Submittal of Certification of No Net Rise or Conditional Letter of Map Revision |  | 44 CFR 60.2 |  |  | FEMA
| Receipt of Concurrence of No Net Rise or Letter of Map Revision |  | 44 CFR 60.2 |  |  | FEMA
A04.01.07.02 | Federal Other
A04.01.07.03 | FAA Determination |  | 14 CFR 77 | A project located within 20,000 feet of a public airport and/or which contains elements with an elevation of 200 feet above the ground level (such as cranes or communication towers) must receive clearance from the Federal Aviation Administration (FAA). | 1 day | FAA
A04.01.07.04 | FAA Notice of Proposed Construction or Alteration Application (Form 7460-1) |  | 14 CFR 77 | A Notice of Proposed Construction or Alteration (FAA Form 7460-1) must be filed for each turbine or meteorological tower in order to obtain FAA Determination of No Hazard to Air Navigation. |  | FAA
A04.01.07.05 | FAA Form 7460-2 Part II |  | - | FAA Form 7460-2 Part II must be submitted for each turbine within 5 days of reaching their greatest height. |  | FAA
A04.01.07.06 | Microwave Line of Sight Transmission Paths Analysis |  | - | Potentially a concern for any tall structures associated with project, such as communications equipment or CSP towers. |  | FCC
A04.01.07.07 | NEXRAD and other Radar Proximity Interference Analysis |  | - | Review project plans for NOAA, DOD, FAA for possible interference with their operations. |  | DOD, NOAA, FAA
A04.01.07.07 | Self Certification Notice for Exempt Wholesale Generators |  | 18 CFR 366.7(a) | A facility must register with the Federal Energy Regulatory Commission (FERC) to sell power. |  | FERC
A04.01.08 | Use and occupancy agreement - utility crossing federal highway |  | 23 CFR 645 |  |  | DOT
A04.01.08.01 | Coordination with NRCS |  | - | Review for prior converted wetlands, farmed wetlands, agricultural exemptions, conservation easements, important farm lands. |  | USACE, NRCS
A04.01.08.02 | Seismic Requirements |  | 40 CFR 264, 18 CFR 380 | State and federal regulations restrict the siting of liquefied natural gas facilities and hazardous waste treatment, storage, and disposal facilities |  | EPA
A04.01.08.03 | EPA Noise Standards |  | 42 U.S.C. §7641 | EPA’s noise regulations apply to specific sources and do not provide a uniform level of exposure for all facilities. |  | EPA
A04.01.08.04 | Sites on or Near Public or Tribal Lands
A04.01.08.05 | Consultation w/ Federal Land Owners - BLM, NPS, USFS, etc. |  |  | Consult with appropriate agencies if project on or near federal land |  | BLM, NPS, USFS, etc.
| Consultation w/ State/Tribal Land Owners if on or near project |  |  | Consult with appropriate agencies if project on or near state/tribal land. |  | State or Tribal agency
A04.01.08.06 | Forest Service Organic Legislation |  | 16 U.S.C. §§473 et seq. | Restricts the use of land, water, timber and stone found in national forests, as well as construction. |  | USFS
A04.01.08.07 | National Wildlife Refuge Lands |  | 16 U.S.C. §668d | Restricts disturbance of any property, including natural growth, on National Wildlife Refuge System lands. Evaluate whether project will involve these lands. |  | USFWS
A04.01.08.08 | Taylor Grazing Act |  | 43 U.S.C. §315 et. seq. | Grazing districts may be established from certain lands within the public domain. Restrictions then apply to their use. |  | BLM, NPS
A04.02 | Wilderness Act |  | 16 U.S.C. §1131 | The National Wilderness Preservation System protects designated wilderness areas. |  | FS, BLM, USFWS, NPS
| Wild and Scenic Rivers Act |  | 16 U.S.C. §1271 | The national wild and scenic rivers system is designed to protect identified rivers. Identify if protected rivers are in project area. |  | FS, BLM, USFWS, NPS
A04.02.01 | Land Reclamation Plan |  |  | Determine if needed. |  | FS, BLM, USFWS, NPS
| Land Reclamation Annual Report |  |  | Determine if needed. |  | FS, BLM, USFWS, NPS