## Sheet1
Date | Form of Contact | Persons Present | Document or Description
December 2015 | Phone | Carroll Browning/Greg Hale | Commissioner Browning called to tell LTC that it needed to stay out of its easements. LTC reviewed and confirmed ELWD had non-excusive easements.
December 2015 | Phone | Carroll Browning/Greg Hale | LTC called Commissioner Browning back to let him know that ELWD had non-exclusive easements.
January 2016 | Phone | Carroll Browning/Greg Hale | LTC send letter to ELWD notifying it that it had non-exclusive easements and ELWD would be responsible if it damages LTC's fiber without following proper 811 laws and LTC and its contractors were trying to avoid ELWD's lines but it is nearly impossible when ELWD's marks are off by so much.
June 16, 2016 | Reply Letter from LTC | To ELWD Attorney | LTC sent Letter replying to East Logan Attorney, Joe Hendricks. See attached.
June 17, 2016 | In-Person | Carroll Browning/Linda Alexander/Greg Hale | After a couple of water line were hit due to highly inaccurate locates by ELWD, LTC visited the sites then went to ELWD's office. LTC and ELWD made site vists to discuss and the parties agreed they would get together to resolve issues.
June 20, 2016 | Legal Document |  | LTC received formal complaint in which ELWD sought injunction preventing FTTH deployment and the removal of fiber anywhere within 10 feet of ELWD's water lines.
June 24, 2016 | In-Person | Greg Hale/Thadd Kistler/Electricom/Joe Gran Clark/East Logan Commissioners and Attorney Joe Hendricks | This communication has been redacted due to confidentiality agreement between the parties.
October 26, 2017 | In-Person Pre Design | Carroll Browning/Linda Alexander/Daniel Brown/Greg Hale/Thadd Kistler | The parties met at LTC headquarters and LTC showed ELWD where contractors would be excavating in 2018. Commissioner Browning claimed that ELWD should not have to locate its facilities.
March 15, 2018 | In-Person Pre Construction | Linda Alexander/Daniel Brown/Greg Hale/Thad Kistler | LTC meet with ELWD to discuss contractor excavations for 2018. ELWD agreed it would locate its facilities.
May-June, 2018 | Emails | Thadd Kistler/Daniel Brown | LTC shared its maps and information to ELWD to assist with design work for 2019 Builds.
October 25th, 2019 | In-Person | Carroll Browning/Greg Hale/Thadd Kistler/Other LTC Staff | Commissioner Browning entered LTC's building and threatened to shoot LTC's General Manager after North Central hit a water line that was not located by ELWD.
November 8th, 2019 | Phone/Email | Hamp Moore Secretary/LTC Attorney Joe Gran Calrk | LTC was notified that Hamp Moore will be acting as new attorney for ELWD and wanted to set up a call
November 2019 | Phone | Greg Hale/Harris Dockins | LTC called Commissioner Dockins to discuss locate issues and requested resolution of these issues.
November 2019 | Phone | Greg Hale/Lloyd Houchens | LTC called Commissioner Houchens to discuss locate issues and requested resolution of these issues.
February 27th, 2020 | Letter | Greg Hale | LTC sent letter to Commissioner Dockins, copied to other commissioners, that outlined locate issues, the inconsistency of ELWD's responses, and asked it to confirm that it will follow the law going forward. See letter attached.
April 24th, 2020 | Phone | Hamp Moore/Greg Hale/Joe Gran Clark | The parties discussed ELWD's failure to mark and locate its lines.
May 11th, 2022 | Microsoft Teams | Greg Hale/Christopher Zelli/Stephen Taylor/Gerald Wuetcher/John Park | Informal Conference with PSC Commission Staff
May - July 2022 | Various | Christopher Zelli/Gerald Wuetcher | Proposals for settlement were shared but no agreement was reached.