## (6a) Schedule C1
Schedule C1
Jackson Purchase Energy Corporation
Case No. 2021-00358
Construction Projects
For Five Years Ended December 31, 2020
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Vaiance In Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
506 | Kansas Substation Rebuild | 1614652.99 | 1453000 | 161652.99 | 11.13% | 111.1% | 1614652.99 | 161652.99 | 2016-01-01 | 2019-12-31 | 2019-03-21 | 2020-07-22
1301 | Construction of New Headquarters | 9780984.92 | 9780984.92 | 0 | 0% | 100% | 9780984.92 | 0 | 2020-01-01 | 2020-12-31 | 2020-02-12 | 2020-12-31

## (6b) Schedule C2
Schedule C2
Jackson Purchase Energy Corporation
Case No. 2021-00358
Calculation of Capital Construction Project Slippage Factor
Source: Schedule 10a - Construction Projects
Year | Annual Actual Cost | Annual Original Budget | Variance In Dollars | Variance As Percent | Slippage Factor
2016 | 0 | 0 | 0 | 0% | 0%
2017 | 0 | 0 | 0 | 0% | 0%
2018 | 0 | 0 | 0 | 0% | 0%
2019 | 0 | 0 | 0 | 0% | 0%
2020 | 11395637.91 | 11233984.92 | 161652.99 | 1.439% | 101.4%
Totals | 11395637.91 | 11233984.92 | 161652.99 | 1.439% | 101.4%
Five Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 5 years) |  |  |  |  | 20.29%