## Sheet1
Schedule C2
South Kentucky Rural Electric Cooperative Corporation Case No. 2021-00407
Calculation of Capital Construction Project Slippage Factor
Source: Schedule 10a – Construction Projects
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars Over/(Under) | Variance as Percent | Slippage Factor
2016 | 256410.1 | 214000 | 42410.1 | 19.82% | 119.8%
2017 | 458673.49 | 300500 | 158173.49 | 52.64% | 152.6%
2018 | 144790.51 | 89750 | 55040.51 | 61.33% | 161.3%
2019 | 200101.99 | 191750 | 8351.99 | 4.356% | 104.4%
2020 | 89604.93 | 26660 | 62944.93 | 236.1% | 336.1%
Totals | 1149581.02 | 822660 | 326921.02 | 39.74% | 139.7%
Five Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 5 years) |  |  |  |  | 27.95%
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule 10a.
Total all projects for a given year.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor
for each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.