## Sheet1
Schedule C1
South Kentucky Rural Electric Cooperative Corporation Case No. 2021-00407
Construction Projects
For Five Years ended December 31, __2020__________________
|  |  |  | Variance |  |  | Total | Total | Variance | Date | Date
|  | Annual Actual Cost | Annual Original Budget | In | Variance | Percent | Actual | Budget | In | Original | Original | Date | Date
Project | Project |  |  | Dollars | As | Of | Project | Project | Dollars | Budget | Budget | Actual | Actual
No. | Title/Description |  |  | Under/(Over) | Percent | Budget | Cost | Cost | Under/(Over) | Start | End | Start | End
15-033855 | 121264 - APPLE TREE PARK | 5096.6 | 5500 | 403.4 | -7.335% |  | 5096.6 | 5500 | 403.4 | 2015-01-01 | 2018-12-31 | 2016-01-29 | 2016-05-31
15-033812 | 121263 - APPLE TREE PARK | 14449.16 | 10500 | -3949.16 | 37.61% |  | 14449.16 | 10500 | -3949.16 | 2015-01-01 | 2018-12-31 | 2016-01-29 | 2016-05-31
15-031853 | 121368 - MINE 18 PART B | 23688.01 | 33000 | 9311.99 | -28.22% |  | 23688.01 | 33000 | 9311.99 | 2015-01-01 | 2018-12-31 | 2016-02-18 | 2016-06-30
15-031852 | 121318 - MINE 18 PART A | 45007.96 | 41250 | -3757.96 | 9.11% |  | 45007.96 | 41250 | -3757.96 | 2015-01-01 | 2018-12-31 | 2016-02-04 | 2016-06-30
15-030152 | 121357 - OLD CLEAR SPRINGS ROAD | 16888.95 | 8250 | -8638.95 | 104.7% |  | 16888.95 | 8250 | -8638.95 | 2015-01-01 | 2018-12-31 | 2016-02-11 | 2016-06-30
15-030151 | 121218 - LOVELESS ROAD | 11120.73 | 8250 | -2870.73 | 34.8% |  | 11120.73 | 8250 | -2870.73 | 2015-01-01 | 2018-12-31 | 2016-01-20 | 2016-07-31
15-030253 | 122221 - LUTTRELL ROAD | 10578.6 | 13750 | 3171.4 | -23.06% |  | 10578.6 | 13750 | 3171.4 | 2015-01-01 | 2018-12-31 | 2016-05-18 | 2016-09-30
15-030252 | 122222 - FINIS BEASLEY ROAD | 9718.08 | 13750 | 4031.92 | -29.32% |  | 9718.08 | 13750 | 4031.92 | 2015-01-01 | 2018-12-31 | 2016-05-16 | 2016-09-30
15-031651 | 121613 - DENTON PHELPS | 15553.03 | 22000 | 6446.97 | -29.3% |  | 15553.03 | 22000 | 6446.97 | 2015-01-01 | 2018-12-31 | 2016-03-21 | 2016-10-31
15-031253 | 121824 - MERVIN LAWLESS LINE | 9854.66 | 11000 | 1145.34 | -10.41% |  | 9854.66 | 11000 | 1145.34 | 2015-01-01 | 2018-12-31 | 2016-04-13 | 2016-10-31
15-031252 | 121859 - MILLER'S CREEK | 5660.76 | 8250 | 2589.24 | -31.38% |  | 5660.76 | 8250 | 2589.24 | 2015-01-01 | 2018-12-31 | 2016-04-18 | 2016-10-31
15-031251 | 121815 - VETERANS MEMORIAL PARK ROAD | 3888.46 | 5500 | 1611.54 | -29.3% |  | 3888.46 | 5500 | 1611.54 | 2015-01-01 | 2018-12-31 | 2016-04-13 | 2016-10-31
15-030751 | 121659 - ACORN ANO | 61969.54 | 13750 | -48219.54 | 350.7% |  | 61969.54 | 13750 | -48219.54 | 2015-01-01 | 2018-12-31 | 2016-03-30 | 2016-10-31
15-030153 | 122220 - C W HALE ROAD | 15359.94 | 13750 | -1609.94 | 11.71% |  | 15359.94 | 13750 | -1609.94 | 2015-01-01 | 2018-12-31 | 2016-05-18 | 2016-10-31
15-033854 | 122491 - CLAY STREET | 7575.62 | 5500 | -2075.62 | 37.74% |  | 7575.62 | 5500 | -2075.62 | 2015-01-01 | 2018-12-31 | 2016-06-16 | 2016-12-31
15-032753 | 123198 - KENNETT LANE | 10049.97 | 8250 | -1799.97 | 21.82% |  | 10049.97 | 8250 | -1799.97 | 2015-01-01 | 2018-12-31 | 2016-08-17 | 2017-01-31
15-031452 | 122622 - BELL HILL RD | 50830.59 | 57750 | 6919.41 | -11.98% |  | 50830.59 | 57750 | 6919.41 | 2015-01-01 | 2018-12-31 | 2016-07-06 | 2017-02-28
15-031551 | 124134 - ISLAND VIEW DRIVE/TWIN RIVER | 38245.71 | 22000 | -16245.71 | 73.84% |  | 38245.71 | 22000 | -16245.71 | 2015-01-01 | 2018-12-31 | 2016-12-06 | 2017-03-31
15-032752 | 123637 - NEW HOPE CHURCH ROAD | 81077.83 | 13750 | -67327.83 | 489.7% |  | 81077.83 | 13750 | -67327.83 | 2015-01-01 | 2018-12-31 | 2016-10-10 | 2017-04-30
15-031751 | 122796 - SKULL BONE | 31018.25 | 13750 | -17268.25 | 125.6% |  | 31018.25 | 13750 | -17268.25 | 2015-01-01 | 2018-12-31 | 2016-07-25 | 2017-05-31
15-030251 | 124614 - COMBEST LANE OFF HWY 837 | 17723.03 | 30250 | 12526.97 | -41.41% |  | 17723.03 | 30250 | 12526.97 | 2015-01-01 | 2018-12-31 | 2017-02-16 | 2017-06-30
15-033152 | 124165 - HAMMONDS CAMP | 71967.22 | 35750 | -36217.22 | 101.3% |  | 71967.22 | 35750 | -36217.22 | 2015-01-01 | 2018-12-31 | 2016-12-07 | 2017-07-31
15-039992 | 126350 - CLUB HEIGHTS | 10464.01 | 8000 | -2464.01 | 30.8% | 1550 | 10464.01 | 8000 | -2464.01 | 2015-01-01 | 2018-12-31 | 2017-09-18 | 2017-10-31
15-039992 | 126609 - DUGAN STREET | 2604.8 | 1500 | -1104.8 | 73.65% | 257 | 2604.8 | 1500 | -1104.8 | 2015-01-01 | 2018-12-31 | 2017-10-18 | 2017-11-30
15-039992 | 126656 - BLEVINS STREET | 9183.97 | 2750 | -6433.97 | 234% | 496 | 9183.97 | 2750 | -6433.97 | 2015-01-01 | 2018-12-31 | 2017-10-20 | 2017-11-30
15-031754 | 125592 - HICKORY KNOB CHURCH ROAD | 86020.97 | 90750 | 4729.03 | -5.211% |  | 86020.97 | 90750 | 4729.03 | 2015-01-01 | 2018-12-31 | 2017-06-23 | 2017-11-30
15-039992 | 126896 - CHERRY AND WEST ST | 11565.39 | 1250 | -10315.39 | 825.2% | 228 | 11565.39 | 1250 | -10315.39 | 2015-01-01 | 2018-12-31 | 2017-11-15 | 2017-12-31
15-039992 | 125559 - RAMSEY ST WIRE CHANGE | 37921.75 | 14750 | -23171.75 | 157.1% | 2801 | 37921.75 | 14750 | -23171.75 | 2015-01-01 | 2018-12-31 | 2017-05-26 | 2017-12-31
15-039992 | 127109 - CHERRY STREET | 14143.85 | 4500 | -9643.85 | 214.3% | 842 | 14143.85 | 4500 | -9643.85 | 2015-01-01 | 2018-12-31 | 2017-12-07 | 2018-02-28
15-039992 | 126219 - VIRGINIA AVE | 10870.9 | 3000 | -7870.9 | 262.4% | 542 | 10870.9 | 3000 | -7870.9 | 2015-01-01 | 2018-12-31 | 2017-08-28 | 2018-03-31
15-039992 | 127500 - EAST HIGH STREET | 9327.02 | 1250 | -8077.02 | 646.2% | 199 | 9327.02 | 1250 | -8077.02 | 2015-01-01 | 2018-12-31 | 2018-02-12 | 2018-03-31
15-039992 | 127582 - VINE STREET | 22875.16 | 6750 | -16125.16 | 238.9% | 1274 | 22875.16 | 6750 | -16125.16 | 2015-01-01 | 2018-12-31 | 2018-02-26 | 2018-04-30
15-039992 | 127476 - TRADEWAY DR AND LEE ST | 13743.73 | 3250 | -10493.73 | 322.9% | 610 | 13743.73 | 3250 | -10493.73 | 2015-01-01 | 2018-12-31 | 2018-02-06 | 2018-04-30
15-039992 | 128236 - ABBOTT STEVEN | 8526.66 | 15500 | 6973.34 | -44.99% | 2980 | 8526.66 | 15500 | 6973.34 | 2015-01-01 | 2018-12-31 | 2018-05-16 | 2018-05-31
15-039992 | 128266 - EAST COLUMBIA AVE | 26326.47 | 6000 | -20326.47 | 338.8% | 1127 | 26326.47 | 6000 | -20326.47 | 2015-01-01 | 2018-12-31 | 2018-05-15 | 2018-06-30
15-039992 | 124846 - SHADY GROVE CHURCH WIRE | 36134.94 | 44750 | 8615.06 | -19.25% | 8558 | 36134.94 | 44750 | 8615.06 | 2015-01-01 | 2018-12-31 | 2017-03-17 | 2018-07-31
15-039992 | 128089 - W HWY 80 | 2841.78 | 4750 | 1908.22 | -40.17% | 879 | 2841.78 | 4750 | 1908.22 | 2015-01-01 | 2018-12-31 | 2018-02-07 | 2018-08-31
15-039992 | 127367 - FAUBUSH NORFLEET RD | 16240.3 | 32000 | 15759.7 | -49.25% | 6125 | 16240.3 | 32000 | 15759.7 | 2015-01-01 | 2018-12-31 | 2018-01-23 | 2019-01-31
15-039992 | 130759 - SYSTEM INSPECTION 2019 | 30415.92 | 19500 | -10915.92 | 55.98% | 3725 | 30415.92 | 19500 | -10915.92 | 2015-01-01 | 2018-12-31 | 2019-01-15 | 2019-05-31
15-033451 | 125894 - HEGNARER-DUNCAN RAMSEY ROAD | 26600.56 | 16500 | -10100.56 | 61.22% |  | 26600.56 | 16500 | -10100.56 | 2015-01-01 | 2018-12-31 | 2017-03-01 | 2019-05-31
15-033154 | 128036 - GUS SKINNER WIRE CHANGE | 79540.26 | 68750 | -10790.26 | 15.69% |  | 79540.26 | 68750 | -10790.26 | 2015-01-01 | 2018-12-31 | 2018-04-23 | 2019-07-31
15-033153 | 127516 - DON HORN TAP | 47304.95 | 55000 | 7695.05 | -13.99% |  | 47304.95 | 55000 | 7695.05 | 2015-01-01 | 2018-12-31 | 2018-02-06 | 2019-10-31
20-060829 | 131105 - WILLA DR | 24078.27 | 15660 | -8418.27 | 53.76% |  | 24078.27 | 15660 | -8418.27 | 2020-01-01 | 2023-12-31 | 2020-01-06 | 2020-08-31
15-033853 | 124390 - DON PATTON ROAD | 65526.66 | 11000 | -54526.66 | 495.7% |  | 65526.66 | 11000 | -54526.66 | 2015-01-01 | 2018-12-31 | 2017-01-24 | 2020-09-30
|  | 1149581.02 | 822660 | -326921.02 |  |  | 1149581.02 | 822660 | -326921.02
Note: As part of the CWP development, a cost per mile estimate is used for each project type. For each of the jobs listed in table C1, the variances are a combination of the job length being more or less than estimated, the cost
running higher than expected due to more than average poles needing to be changed out, etc., and finally right of way costs being more than expected for the specific job.