## DR-01-15
Unit Name | Event Type | Month | Scheduled Hours | Forced Hours | Actual Hours | Event Duration Hours | Event Start | Event End | Description
East Bend 2 | PE | May | 159.07 |  | 159.07 | 159.07 | 2021-05-03 06:00 | 2021-05-09 21:04 | 2021 Spring Planned Outage Extension: 2-2 PA Fan Shaft and Bearing Repairs
East Bend 2 | U1 | July |  | 40.6 | 40.6 | 40.6 | 2021-07-29 03:14 | 2021-07-30 19:50 | SFC Unable to Pull Ash
East Bend 2 | U1 | August |  | 63.13 | 63.13 | 63.13 | 2021-08-02 19:06 | 2021-08-05 10:14 | 2-1 BFPT Manual Valve Leaking
East Bend 2 | U1 | August |  | 183.5 | 183.5 | 183.5 | 2021-08-28 19:00 | 2021-09-05 10:30 | Generator Flex Links and A-phase Bushing
East Bend 2 | U1 | September |  | 1.73 | 1.73 | 1.73 | 2021-09-05 11:14 | 2021-09-05 12:58 | Trip on boiler drum level.
East Bend 2 | U1 | September |  | 1.6 | 1.6 | 1.6 | 2021-09-05 13:06 | 2021-09-05 14:42 | Trip on boiler drum level.
East Bend 2 | PO | September | 1705.97 |  | 1705.97 | 1705.97 | 2021-09-10 23:02 | 2021-11-21 | Planned Fall Outage
Woodsdale CT1 | MO | May | 33.53 |  | 33.53 | 33.53 | 2021-05-04 06:30 | 2021-05-05 16:02 | <OMC!> Replace Switchyard Breaker 1521
Woodsdale CT1 | U1 | June |  | 1561.23 | 1561.23 | 1561.23 | 2021-06-10 10:15 | 2021-08-14 11:29 | Forced Outage-Turbine Blade Damage
Woodsdale CT1 | PO | September | 105.5 |  | 105.5 | 105.5 | 2021-09-13 06:00 | 2021-09-17 15:30 | Replace Annunciator on Transformer Bank 39.
Woodsdale CT2 | MO | May | 33.53 |  | 33.53 | 33.53 | 2021-05-04 06:30 | 2021-05-05 16:02 | <OMC!> Replace Switchyard Breaker 1521
Woodsdale CT2 | SF | June |  | 0.73 | 0.73 | 0.73 | 2021-06-04 15:56 | 2021-06-04 16:40 | Syncronizer Failure
Woodsdale CT2 | MO | July | 0.68 |  | 0.68 | 0.68 | 2021-07-01 11:35 | 2021-07-01 12:16 | Made unit unavailable to safely lift GT1 parts over units
Woodsdale CT2 | SF | August |  | 21.47 | 21.47 | 21.47 | 2021-08-17 13:50 | 2021-08-18 11:18 | Power Oil Breaker won`t close
Woodsdale CT2 | PO | September | 103 |  | 103 | 103 | 2021-09-13 06:00 | 2021-09-17 13:00 | Transformer Bank 39 Annunciator Outage
Woodsdale CT3 | MO | May | 33.53 |  | 33.53 | 33.53 | 2021-05-04 06:30 | 2021-05-05 16:02 | <OMC!> Replace Switchyard Breaker 1521
Woodsdale CT3 | PO | May | 171.85 |  | 171.85 | 171.85 | 2021-05-15 06:00 | 2021-05-22 09:51 | Spring Prep and Boroscope Inspection
Woodsdale CT3 | PO | May | 1.55 |  | 1.55 | 1.55 | 2021-05-22 09:57 | 2021-05-22 11:30 | Spring Prep and Boroscope Inspection
Woodsdale CT3 | MO | July | 0.68 |  | 0.68 | 0.68 | 2021-07-01 11:35 | 2021-07-01 12:16 | Made unit unavailable to safely lift GT1 parts over units
Woodsdale CT3 | PO | September | 177.05 |  | 177.05 | 177.05 | 2021-09-18 06:00 | 2021-09-25 15:03 | TB40 annunciator outage, replace fuel valve
Woodsdale CT3 | U1 | September |  | 18.03 | 18.03 | 18.03 | 2021-09-27 18:00 | 2021-09-28 12:02 | Leak on NG Stop Valve Relief Valve
Woodsdale CT4 | MO | May | 33.53 |  | 33.53 | 33.53 | 2021-05-04 06:30 | 2021-05-05 16:02 | <OMC!> Replace Switchyard Breaker 1521
Woodsdale CT4 | PO | May | 171.15 |  | 171.15 | 171.15 | 2021-05-15 06:00 | 2021-05-22 09:09 | Spring Prep and Boroscope Inspection
Woodsdale CT4 | MO | July | 0.68 |  | 0.68 | 0.68 | 2021-07-01 11:35 | 2021-07-01 12:16 | Made unit unavailable to safely lift GT1 parts over units
Woodsdale CT4 | PO | September | 176.42 |  | 176.42 | 176.42 | 2021-09-18 06:00 | 2021-09-25 14:25 | TB40 annunciator outage, stack repairs
Woodsdale CT5 | PO | May | 1.63 |  | 1.63 | 1.63 | 2021-05-27 09:15 | 2021-05-27 10:53 | Generator Rewind Outage
Woodsdale CT5 | MO | June | 2.58 |  | 2.58 | 2.58 | 2021-06-07 06:30 | 2021-06-07 09:05 | Made GT5 unavailable to finish SFC work on GT6
Woodsdale CT5 | SF | June |  | 0.95 | 0.95 | 0.95 | 2021-06-27 16:47 | 2021-06-27 17:44 | Gen Breaker SF6 Gas Low
Woodsdale CT5 | MO | July | 0.68 |  | 0.68 | 0.68 | 2021-07-01 11:35 | 2021-07-01 12:16 | Made unit unavailable to safely lift GT1 parts over units
Woodsdale CT5 | U1 | July |  | 3.8 | 3.8 | 3.8 | 2021-07-27 17:24 | 2021-07-27 21:12 | Tripped; faulty exhause Thermocouple
Woodsdale CT5 | U1 | August |  | 163.02 | 163.02 | 163.02 | 2021-08-27 12:41 | 2021-09-03 07:42 | Fire Alarm-Heat Detected Trip-Unit Unavailable.
Woodsdale CT6 | MO | July | 0.68 |  | 0.68 | 0.68 | 2021-07-01 11:35 | 2021-07-01 12:16 | Made unit unavailable to safely lift GT1 parts over units
Woodsdale CT6 | SF | October |  | 15.08 | 15.08 | 15.08 | 2021-10-18 19:04 | 2021-10-19 10:09 | Failed start; Synchronizer blocked
Event Type Legend:
PO | Planned Outage
PE | Planned Outage Extension
MO | Maintenance Outage
ME | Maintenance Outage Extension
U1 | Unplanned (Forced) Outage – Immediate
U2 | Unplanned (Forced) Outage – Delayed
U3 | Unplanned (Forced) Outage – Postponed
SF | Startup Failure