## 2019IRP
Table 8.(2)(a)-1
($100,000 and Above)
Bluegrass Station
Description | Est. Cost | Operating Unit | Date
Generator Inspections | 840000 | OC01-03 | 2022
Relocate GSU Protection Panel | 170000 | OC00 | 2022
Enclosure Doors | 113000 | OC00 | 2023
Demin Tank - Strip and Re-coat interior | 358500 | OC00 | 2023
Stack Repair | 1200000 | OC01-02 | 2023
Bluegrass Peak Shave Battery Storage (Project #1) | 5555580 | OC00 | 2024
Inlet Filter Change-out | 204295 | OC01 | 2028
Inlet Filter Change-out | 204295 | OC02 | 2028
Inlet Filter Change-out | 204295 | OC03 | 2028
Generator Inspections | 840000 | OC01-03 | 2031
OC00 - Common
OC01 - Bluegrass 1
OC02 - Bluegrass 2
OC03 - Bluegrass 3
Table 8.(2)(a)-2
($100,000 and Above)
Cooper Power Station
Description |  | Operating Unit | Date
Temporary Landfill Cap | 180000 | CP00 | 2022
ABB Symphony Plus Operations Rev. Upg | 274395 | CP01 | 2022
ABB Symphony Plus Operations Rev. Upg | 374545 | CP02 | 2022
U2 AQCS FD Fan Hub Swap | 343000 | CP02 | 2022
U2 AQCS FD Fan Motor Swap | 120000 | CP02 | 2022
U1 Boiler Economizer Tubes Installation | 850000 | CP01 | 2023
Boiler Economizer Tubes Matl Purchase | 550000 | CP01 | 2023
U1 Boiler Weld Overlay In Firebox | 186000 | CP01 | 2023
1A Hyd Turb Rebuild | 200000 | CP01 | 2023
Turbine Valve Rebuild | 647680 | CP01 | 2025
High Energy Piping Assessment | 242545 | CP01 | 2025
PJFF Bag Replacement | 650000 | CP02 | 2025
Boiler Assessment | 466695 | CP01 | 2026
C.W.P. And Motor Rebuild A | 190000 | CP01 | 2026
C.W.P., Fluid Drive, and Motor Rebuild B | 193000 | CP01 | 2027
Boiler Assessment | 475000 | CP02 | 2027
Turbine Valve Overhaul | 700000 | CP02 | 2027
ID Fan Hub Swap | 465000 | CP00 | 2028
C.W.P., Fluid drive, and Motor Rebuild B | 150000 | CP02 | 2029
High Energy Piping Assessment | 266800 | CP01 | 2030
C.W.P., Fluid Drive, and Motor Rebuild A | 152000 | CP02 | 2030
Boiler assessment | 513365 | CP01 | 2031
CP00 - Common
CP01 - Cooper 1
CP02 - Cooper 2
Table 8.(2)(a)-3
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
Resurface Existing Blacktop | 150000 | SP00 | 2022
Painting Structural Steel - Select Areas | 2000000 | SP00 | 2022
Ash Haul Bridge Repairs | 150000 | SP00 | 2022
Add Concrete Pad At Rock Pile | 185000 | SP00 | 2022
Clean & Inspect River Intake | 145000 | SP00 | 2022
Clean , Test & Repair Well Pumps | 165000 | SP00 | 2022
Water Services Building Piping Replacement | 150000 | SP00 | 2022
Clean & Inspect River Intake | 145000 | SP00 | 2022
Boiler Ignition Fuel Oil Tank Repairs | 250000 | SP00 | 2022
Overhaul (4) Pulverizers | 400000 | SP01 | 2022
Outage Boiler & Air heater Repair | 400000 | SP01 | 2022
Outage Boiler & Air heater Inspection | 350000 | SP01 | 2022
High Energy Piping Assessment | 200000 | SP01 | 2022
Air Heater Wash (2) | 122000 | SP01 | 2022
Refractory Repairs Boiler | 100000 | SP01 | 2022
Expansion Joint Repairs | 225000 | SP01 | 2022
1A BFP 5Yr Overhaul | 175000 | SP01 | 2022
BFW-Medium Piping Assessment | 200000 | SP01 | 2022
Tube Alignment Castings | 150000 | SP01 | 2022
ID Fan Outlet Duct SS Overlay | 400000 | SP01 | 2022
ID Fan Outlet Duct Expansion Joints D6-A & D6-B Replacement | 100000 | SP01 | 2022
Sootblowing Air Receiver Tank 5 Year Inspection (Scafffold,Insulation,Nde,Painting) | 150000 | SP01 | 2022
DA Tank Internal Repairs And Shell NDE | 100000 | SP01 | 2022
HMI Operators S+ Upgrade - Comp/Software/Graphics | 850000 | SP01 | 2022
Outage Boiler & Air heater Inspection And Repair | 900000 | SP02 | 2022
Boiler Deslags-2 | 100000 | SP02 | 2022
Air Heater Wash 2 (TR) | 100000 | SP02 | 2022
High Energy Piping Assessments | 600000 | SP02 | 2022
Replace 2A BWCP Heat Exchanger | 250000 | SP02 | 2022
Pulverizer Overhauls | 600000 | SP02 | 2022
Rebuild Pulverizer Journals (3) | 175000 | SP02 | 2022
Expansion Joint Repairs | 200000 | SP02 | 2022
FD Fan Rotor Replacement | 100000 | SP02 | 2022
Table 8.(2)(a)-4
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
2B FD Fan Rotor Rebuild | 180000 | SP02 | 2022
BFP Rotating Element Rebuild | 125000 | SP02 | 2022
ID Fan Rebuild | 500000 | SP02 | 2022
Condensate Pump Rebuild | 175000 | SP02 | 2022
BFP Rebuild | 175000 | SP02 | 2022
Lower Waterwall Remediation | 750000 | SP02 | 2022
BFW-Medium Piping Assessment | 200000 | SP02 | 2022
RH Leading Edge Replacement | 475000 | SP02 | 2022
Amstar Flame Spray Repairs | 220000 | SP03 | 2022
Boiler & Air heater Inspection | 150000 | SP03 | 2022
Boiler & Air heater Repairs | 325000 | SP03 | 2022
13.8 Switchgear Block I/O Replacement | 300000 | SP03 | 2022
Plenum Expansion Joint Repairs | 100000 | SP03 | 2022
SRD Constant Support Hanger Replacement | 315000 | SP03 | 2022
Power Roof Exhauster Complete Replacement | 150000 | SP04 | 2022
Amstar Flame Spray Repairs | 220000 | SP04 | 2022
Boiler & Air heater Repairs | 325000 | SP04 | 2022
4A Voith Drive Rebuild 5 Yr PM | 125000 | SP04 | 2022
Plenum Expansion Joint Repairs | 100000 | SP04 | 2022
Rebuild Limestone Mill Journals | 125000 | SP03 | 2022
Refractory | 1400000 | SP03 | 2022
Rebuild Limestone Mill Journals | 125000 | SP04 | 2022
Refractory (MP) | 1400000 | SP04 | 2022
SH & RH Floors | 385000 | SP04 | 2022
SH & RH Walls | 100000 | SP04 | 2022
Outage- Precipitator Inspection And Repairs | 300000 | SP01 | 2022
Outage- Precipitator Inspection And Repairs | 450000 | SP02 | 2022
Tube Sheet Modules / Wall Repair | 200000 | SP03 | 2022
Replace Baghouse Bags/Filters | 700000 | SP04 | 2022
Replace The Cone Liners In The UC4 Surge Bin | 120000 | SP04 | 2022
Install Actuators On Coal Slide Inlet Chute Isolation Valves | 130000 | SP01 | 2022
Overhaul U3 Crushers | 100000 | SP03 | 2022
Replace The Chain And Sprockets On SR#3 | 113000 | SP03 | 2022
Table 8.(2)(a)-5
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
Replace The Rotor In U3 Crusher | 206012 | SP03 | 2022
Install Dust Suppression On PC3 And BC3 Conveyors | 125000 | SP03 | 2022
Overhaul U4 Crushers | 100000 | SP04 | 2022
Install Dust Suppression on PC4 and BC4 Conveyors | 125000 | SP04 | 2022
SCR Catalyst Replacement | 1200000 | SP01 | 2022
SCR Inlet Expansion Joint D10-F Replacement | 100000 | SP01 | 2022
Lagoon / Coal Pile Runoff Cleaning | 100000 | SP00 | 2022
Reagent Line Replacement | 300000 | SP20 | 2022
Filter Feed Line | 240000 | SP20 | 2022
Scrubber Inlet Duct Repairs | 125000 | SP21 | 2022
WESP SIRS Clean/Inspect/Repair | 200000 | SP21 | 2022
Replace Kirk Keys | 150000 | SP21 | 2022
WESP - Collecting Plate Replacement | 175000 | SP21 | 2022
WESP SIRS Clean/Inspect/Repair | 300000 | SP22 | 2022
2A Vacuum Pump - Refurbishment | 100000 | SP22 | 2022
WESP - Collecting Plate Replacement | 175000 | SP22 | 2022
FWH7 Extraction Steam NRV Relocation/Replacement | 200000 | SP01 | 2022
Extraction Steam Secondary NRV Inspection | 100000 | SP01 | 2022
Unit 1 MCC Essential 1A and 1B | 250000 | SP01 | 2022
Asbestos Abatement for Condenser Water Boxes/Piping | 350000 | SP01 | 2022
Turbine Valves | 600000 | SP02 | 2022
Circ water line repair | 400000 | SP02 | 2022
Bottle Replacement for Switchgear | 100000 | SP02 | 2022
Cooling Tower Inspection & Repair | 100000 | SP03 | 2022
Unit 3 Cooling Tower Fill Replacement - 3 cells | 950000 | SP03 | 2022
Turbine and Exciter Controls | 600000 | SP03 | 2022
Cooling Tower Inspection & Repair | 100000 | SP04 | 2022
Cooling Tower Rain Zone Repair | 200000 | SP04 | 2022
Turbine and Exciter Controls | 600000 | SP04 | 2022
Spurlock 1 / 2 Bottom Ash Silo Elevator | 2310760 | SP01/02 | 2022
Air Heater Wash Water Pumping System | 2057259 | SP00 | 2022
Ash Pond Closure - CCR / ELG Compliance | 3050000 | SP00 | 2022
CCR/ELG Compliance WMB Pond | 7750000 | SP00 | 2022
Table 8.(2)(a)-6
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
Ignition Fuel Oil Pipe Replacement | 1455998 | SP00 | 2022
Landfill - Area D Phase 2 Construction | 157500 | SP00 | 2022
Landfill - Area D Phase 1 Construction | 7875293 | SP00 | 2022
Landfill Area D Construction - Ponds and Stream Mitigation | 4426585 | SP00 | 2022
SSR-2 Compressor Replacement | 53992 | SP00 | 2022
Unit 1 Blowdown Flash Tank | 608366 | SP01 | 2022
Unit 1 Condenser Retube | 1750000 | SP01 | 2022
Unit 1 Superheat Outlet Replacement | 67821 | SP01 | 2022
Unit 2 Cooling Tower Replacement Project | 1559219 | SP02 | 2022
Unit 3 Blowdown Flash Tank | 609215 | SP03 | 2022
Unit 3 Boiler Turn-Down Modifications | 2302000 | SP03 | 2022
Unit 4 Blowdown Flash Tank | 609366 | SP04 | 2022
WWT and Ash System Platforms and Foggers | 751579 | SP00 | 2022
Well 2R | 400000 | SP00 | 2022
Resurface Existing Blacktop | 150000 | SP00 | 2023
Chiller Replacement - 3rd of 3 | 100000 | SP00 | 2023
Day/Night Lighting Control | 100000 | SP00 | 2023
Structural Painting | 2000000 | SP00 | 2023
Ash Haul Bridge Repairs | 150000 | SP00 | 2023
Clean & Inspect River Intake | 145000 | SP00 | 2023
Clean , Test & Repair Well Pumps | 165000 | SP00 | 2023
Water Services Building Piping Replacement | 150000 | SP00 | 2023
PLC to DCS RO and Pretreatment | 500000 | SP00 | 2023
Transfer Tower 2 & 3 Controller Replacement | 160000 | SP00 | 2023
4A IAC Overhaul | 130000 | SP04 | 2023
4B IAC Overhaul | 130000 | SP04 | 2023
Boiler Ignition Fuel Oil Tank Repairs | 250000 | SP00 | 2023
Overhaul (4) Pulverizers | 400000 | SP01 | 2023
Outage Boiler & Air heater Repair | 400000 | SP01 | 2023
Outage Boiler & Air heater Inspection | 350000 | SP01 | 2023
High Energy Piping Assessment | 200000 | SP01 | 2023
Air Heater Wash (2) | 122000 | SP01 | 2023
Boiler Chemical Clean | 200000 | SP01 | 2023
Table 8.(2)(a)-7
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
Expansion Joint Repairs | 225000 | SP01 | 2023
Condensate Pump 1B Rebuild | 100000 | SP01 | 2023
BFW-Medium Piping Assessment | 200000 | SP01 | 2023
HMI Operators S+ Upgrade - Comp/Software/Graphics - Finalize | 150000 | SP01 | 2023
Pulverizer Maintenance | 100000 | SP02 | 2023
Outage Boiler & Air heater Inspection and Repair | 900000 | SP02 | 2023
Misc. Scaffolding Boiler | 250000 | SP02 | 2023
Boiler Deslags-2 | 100000 | SP02 | 2023
Air Heater Wash 2 (TR) | 100000 | SP02 | 2023
FD Fan Rotor Rebuild | 225000 | SP02 | 2023
High Energy Piping Assessments | 200000 | SP02 | 2023
Pulverizer Overhauls | 600000 | SP02 | 2023
Rebuild Pulverizer Journals (6) | 175000 | SP02 | 2023
Boiler Chemical Clean | 525000 | SP02 | 2023
Expansion Joint Repairs | 200000 | SP02 | 2023
HMI Operators S+ Upgrade - Comp/Software/Graphics - Finalize | 150000 | SP02 | 2023
U2 Pulverizer Inching Drive | 200000 | SP02 | 2023
GECKO UT Inspection of Boiler Tubing | 225000 | SP02 | 2023
2A ID Fan - Hydraulic Unit and Feedback Changeout | 100000 | SP02 | 2023
ID Fan Stall Protection System | 195000 | SP02 | 2023
Amstar Flame Spray Repairs | 220000 | SP03 | 2023
Robotic Ut Inspection | 150000 | SP03 | 2023
Boiler & Air heater Inspection | 150000 | SP03 | 2023
Boiler & Air heater Repairs | 325000 | SP03 | 2023
Boiler Chemical Clean | 535000 | SP03 | 2023
3A FP volute replacement (2014 last) | 150000 | SP03 | 2023
NO. 1 Sector Plate Replacement (Hot PA to GAS) | 125000 | SP03 | 2023
Buy & install new condensate pump then rebuild for spare | 180000 | SP03 | 2023
Air Preheater Sensorless Leakage Control System Upgrade (SLCS) | 165000 | SP03 | 2023
CCW Heat Exchanger 5 yr PM | 240000 | SP04 | 2023
Amstar Flame Spray Repairs | 220000 | SP04 | 2023
Robotic Ut Inspection | 150000 | SP04 | 2023
Boiler & Air heater Inspection | 150000 | SP04 | 2023
Boiler & Air heater Repairs | 325000 | SP04 | 2023
Air Preheater Sensorless Leakage Control System Upgrade (SLCS) | 165000 | SP04 | 2023
Rebuild Limestone Mill Journals | 125000 | SP03 | 2023
Refractory | 1400000 | SP03 | 2023
Rebuild Limestone Mill Journals | 125000 | SP04 | 2023
Table 8.(2)(a)-8
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
Refractory (MP) | 1400000 | SP04 | 2023
Outage- Precipitator Inspection And Repairs | 300000 | SP01 | 2023
Outage- Precipitator Inspection And Repairs | 450000 | SP02 | 2023
Tube Sheet Modules / Wall Repair | 200000 | SP03 | 2023
Baghouse bag/filter membrane replacement | 700000 | SP03 | 2023
Inspect & Repair Cells | 175000 | SP00 | 2023
Dredge River around Unloading Cells | 200000 | SP00 | 2023
Inspect & Repair Cells | 250000 | SP00 | 2023
Dredge River around Unloading Cells | 200000 | SP00 | 2023
Paint Barge Unloader | 250000 | SP00 | 2023
Paint CH Structural Steel | 250000 | SP00 | 2023
Overhaul U3 Crushers | 100000 | SP03 | 2023
Overhaul U4 Crushers | 125000 | SP04 | 2023
#3 Dozer Powertrain Rebuild | 451100 | SP00 | 2023
Ammonia Tuning Grid Pipe Replacement | 1250000 | SP02 | 2023
Lagoon / Coal Pile Runoff Cleaning | 100000 | SP00 | 2023
WMB Pond Dredging | 250000 | SP00 | 2023
Replace Horizontal Run of NUVALY Piping | 250000 | SP01 | 2023
Replace Horizontal Run of NUVALY Piping | 300000 | SP02 | 2023
HMI Operators S+ Upgrade - Comp/Software/Graphics | 1400000 | SP20 | 2023
Scrubber Inlet Duct Repairs | 125000 | SP21 | 2023
WESP SIRS Clean/Inspect/Repair | 200000 | SP21 | 2023
WESP SIRS Clean/Inspect/Repair | 300000 | SP22 | 2023
Brine Concentrator Tube cleaning | 150000 | SP20 | 2023
Chemical Clean Evaporator Heat Exchanger | 120000 | SP20 | 2023
Replace Filter Press Cloths | 150000 | SP20 | 2023
Insulation/Heat Trace | 500000 | SP20 | 2023
Electrical Instrumentation | 100000 | SP20 | 2023
DSI Building Electrical Upgrade | 125000 | SP21 | 2023
DSI Building Electrical Upgrade | 125000 | SP22 | 2023
MCC Essential Service Upgrade | 286750 | SP01 | 2023
Unit 1 Generator Relay Panel Replacement | 920000 | SP01 | 2023
Stator Leak Monitoring System Replacement | 350000 | SP02 | 2023
Cooling Tower Inspection & Repair | 100000 | SP03 | 2023
Turbine valve repairs | 100000 | SP03 | 2023
CT Lilly Pads | 360000 | SP03 | 2023
Unit 3 Cooling Tower Fill Replacement | 950000 | SP03 | 2023
Cooling Tower Inspection & Repair | 100000 | SP04 | 2023
Table 8.(2)(a)-9
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
Cooling Tower Rain Zone Repair | 200000 | SP04 | 2023
CCR/ELG Compliance WMB Pond | 500000 | SP00 | 2023
Ignition Fuel Oil Pipe Replacement | 50 | SP00 | 2023
Landfill - Area D Phase 2 Construction | 7895000 | SP00 | 2023
Unit 1 Condenser Retube | 3750000 | SP01 | 2023
Unit 1 Superheat Outlet Replacement | 6555677 | SP01 | 2023
Unit 3 Boiler Turn-Down Modifications | 2124100 | SP03 | 2023
Boiler Assessment | 1133000 | SP01 | 2024
"B" Feed Pump 5yr PM | 260000 | SP01 | 2024
Boiler Assessment | 1540000 | SP02 | 2024
"B" Feed Pump 5yr PM | 260000 | SP02 | 2024
FD Fan Overhaul A | 200000 | SP02 | 2024
Boiler Assessment | 2546500 | SP03 | 2024
"B" Feed Pump 9yr PM | 150000 | SP03 | 2024
"B" Voith Drive 5yr PM | 132000 | SP03 | 2024
Limestone Mill 3-4yr PM | 300000 | SP03 | 2024
Boiler Assessment | 2315000 | SP04 | 2024
Turbine Valves 5yr PM | 440000 | SP04 | 2024
Baghouse filter replacement 2yr PM | 750000 | SP04 | 2024
Ash Pond Closure - CCR / ELG Compliance | 5100000 | SP00 | 2024
Boiler Assessment | 1133000 | SP01 | 2025
"A" Feed Pump 5yr PM | 260000 | SP01 | 2025
Boiler Assessment | 1540000 | SP02 | 2025
"A" Feed Pump 5yr PM | 260000 | SP02 | 2025
ID Fan Overhaul B | 400000 | SP02 | 2025
Boiler Assessment | 2546500 | SP03 | 2025
Major Turbine 10yr PM | 5500000 | SP03 | 2025
Generator Field & Stator | 7000000 | SP03 | 2025
Baghouse filter replacement 2yr PM | 700000 | SP03 | 2025
Boiler Assessment | 2315000 | SP04 | 2025
Ash Pond Closure - CCR / ELG Compliance | 1500000 | SP00 | 2025
Boiler Assessment | 1133000 | SP01 | 2026
C.W.P. and Motor Rebuild A | 350000 | SP01 | 2026
Boiler Assessment | 1540000 | SP02 | 2026
C.W.P. and Motor Rebuild A | 350000 | SP02 | 2026
Table 8.(2)(a)-10
($100,000 and Above)
Spurlock Power Station
Description |  | Operating Unit | Date
ID Fan Overhaul A | 400000 | SP02 | 2026
Boiler Assessment | 2546500 | SP03 | 2026
Boiler Assessment | 2546500 | SP04 | 2026
"A" Voith Drive 5yr PM | 132000 | SP04 | 2026
Limestone Mill 3-4yr PM | 330000 | SP04 | 2026
Baghouse filter replacement 2yr PM | 700000 | SP04 | 2026
Boiler Assessment | 1133000 | SP01 | 2027
Boiler Assessment | 1540000 | SP02 | 2027
Major Turbine 10yr PM | 6000000 | SP02 | 2027
Turbine Valves | 550000 | SP02 | 2027
WESP Plates | 800000 | SP02 | 2027
Precipitator Major | 1000000 | SP02 | 2027
Boiler Assessment | 2546500 | SP03 | 2027
Limestone Mill 3-4 yr PM | 330000 | SP03 | 2027
Boiler Assessment | 2546500 | SP04 | 2027
"A" Feed Pump 9yr PM | 150000 | SP04 | 2027
"B" Voith Drive 5yr PM | 132000 | SP04 | 2027
Baghouse filter replacement 3yr PM | 825000 | SP04 | 2027
Boiler Assessment | 1133000 | SP01 | 2028
Turbine Valves | 550000 | SP01 | 2028
Boiler Assessment | 1540000 | SP02 | 2028
Boiler Assessment | 2546500 | SP03 | 2028
"A" Voith Drive 5yr PM | 145200 | SP03 | 2028
Boiler Assessment | 2546500 | SP04 | 2028
"B" Feed Pump 9yr PM | 150000 | SP04 | 2028
Boiler Assessment | 1030000 | SP01 | 2029
"B" Feed Pump 5yr PM | 270000 | SP01 | 2029
Boiler Assessment | 1694000 | SP02 | 2029
"B" Feed Pump 5yr PM | 270000 | SP02 | 2029
Boiler Assessment | 2801150 | SP03 | 2029
"B" Voith Drive 5yr PM | 145200 | SP03 | 2029
Baghouse filter replacement 3yr PM | 825000 | SP03 | 2029
Baghouse cage replacement 6yr PM | 770000 | SP03 | 2029
Boiler Assessment | 2546500 | SP04 | 2029
Major Turbine 10yr PM | 5500000 | SP04 | 2029
Generator & Stator 20yr PM | 7000000 | SP04 | 2029
Limestone Mill 3-4yr PM | 330000 | SP04 | 2029
Boiler Assessment | 1246300 | SP01 | 2030
"A" Feed Pump 5yr PM | 270000 | SP01 | 2030
C.W.P. and Motor Rebuild B | 350000 | SP01 | 2030
Boiler Assessment | 1694000 | SP02 | 2030
"A" Feed Pump 5yr PM | 270000 | SP02 | 2030
C.W.P. and Motor Rebuild B | 350000 | SP02 | 2030
ID Fan Overhaul B | 400000 | SP02 | 2030
13.8kV Motor Overhaul | 700000 | SP02 | 2030
Boiler Assessment | 2801150 | SP03 | 2030
Turbine Valves 5yr PM | 440000 | SP03 | 2030
Limestone Mill 3-4yr PM | 330000 | SP03 | 2030
Boiler Assessment | 2546500 | SP04 | 2030
Baghouse filter replacement 3yr PM | 825000 | SP04 | 2030
Baghouse cage replacement 6yr PM | 770000 | SP04 | 2030
Boiler Assessment | 1246300 | SP01 | 2031
Boiler Assessment | 1694000 | SP02 | 2031
ID Fan Overhaul A | 400000 | SP02 | 2031
FD Fan Overhaul A | 200000 | SP02 | 2031
Boiler Assessment | 2801150 | SP03 | 2031
Boiler Assessment | 2546500 | SP04 | 2031
"A" Voith Drive 5yr PM | 145200 | SP04 | 2031
SP00- Common
SP01- Spurlock 1
SP02- Spurlock 2
SP03- Spurlock 3
SP04- Spurlock 4
SP20- Spurlock Scrubber Common
SP21- Spurlock Scrubber Unit 1
SP22- Spurlock Scrubber Unit 2
Table 8.(2)(a)-11
Smith CTs - Station
Description |  | Operating Unit | Date
Structure Painting- Units 2 and 4 and bay | 462198 | SM52/54 | 2022
Structure Painting- Units 1 and 3 | 552862 | SM51/53 | 2022
Site Blacktop repair | 465000 | SM50 | 2022
U1-3 Camera replacement | 170000 | SM51-53 | 2022
Rebuild liquid fuel pump- #1 (Unit 2) | 120000 | SM52 | 2022
15 Yr Breaker Maintenance Units 1 & 3 | 300000 | SM51/53 | 2022
Retrofill ABB AdVac Breakers | 199192 | SM50 | 2022
Unit No. 6 CI | 200000 | SM56 | 2022
Unit No. 6 Parts Refurbishment | 125000 | SM56 | 2022
Unit No. 7 CI Inspection | 200000 | SM57 | 2022
Unit 10 Row 3-5 HPC Blade | 450000 | SM60 | 2022
Gas Line Inspection from Bybee to Plant | 442152 | SM50 | 2022
Intake Fan PLC Replacements on U1, 2, & 3 | 213060 | SM51-53 | 2022
Unit 1 Exhaust Repairs | 274370 | SM51 | 2022
Waterwash CO or NOX | 267800 | SM50 | 2022
Restack catalyst for LMS | 105280 | SM50 | 2022
J.K. Smith Electrical Infrastructure Upgrades | 6509869 | SM50 | 2022
Smith New Water Intake | 7494776 | SM50 | 2022
Rebuild liquid fuel pump- #1 (Unit 1) | 120000 | SM51 | 2023
Gas Compressor Overhaul | 170000 | SM50 | 2023
Gas Compressor Overhaul | 170000 | SM50 | 2023
Retrofit 5000A 13.8 KV Generator Breakers 4-7 | 1838399 | SM54-57 | 2023
Unit No. 7 Parts Refurbishment | 125000 | SM57 | 2023
Waterwash CO or NOX | 267800 | SM50 | 2023
Restack catalyst for LMS | 105280 | SM50 | 2023
Smith New Demineralized Water Storage Tank | 4771803 | SM50 | 2023
Smith New Water Intake | 6221218 | SM50 | 2023
Table 8.(2)(a)-12
Smith CTs - Station
Description |  | Operating Unit | Date
Generator Ckt Bkr 12 yr Maintenance | 200000 | SM60 | 2024
Catalyst Replace | 150000 | SM60 | 2025
Smith BOP DEMIN #1 Resin | 260000 | SM50 | 2028
Smith BOP DEMIN #2 Resin | 260000 | SM50 | 2028
DCS HMI Upgrades | 173000 | SM50 | 2028
Gas Compressor Overhaul | 215000 | SM59 | 2028
HMI Upgrade | 104000 | SM59 | 2028
Gas Compressor Overhaul | 215000 | SM60 | 2028
HMI Upgrade | 104000 | SM60 | 2028
Major and Gen Major | 12390000 | SM54 | 2029
Major and Gen Major | 12761700 | SM55 | 2030
Catalyst Replace | 390000 | SM59 | 2030
Catalyst Replace | 390000 | SM60 | 2030
Major and Gen Major | 13144551 | SM56 | 2030
SM50 - Smith Units Common
SM51 - Smith Unit 1
SM52 - Smith Unit 2
SM53 - Smith Unit 3
SM54 - Smith Unit 4
SM55 - Smith Unit 5
SM56 - Smith Unit 6
SM57 - Smith Unit 7
SM59 - Smith Unit 9
SM60 - Smith Unit 10
Table 8.(2)(a)-13
Landfill Gas
Description |  | Operating Unit | Date
Green Valley- Major Overhaul- Unit 2 | 185000 | LF01 | 2022
Laurel Ridge- Fuel skid upgrade | 101000 | LF02 | 2022
Laurel Ridge - Major Overhaul- Unit 1 | 185000 | LF02 | 2022
Bavarian- Major Overhaul- Unit 4 | 185000 | LF03 | 2022
Pendleton- Major Overhaul- Unit 3 | 185000 | LF05 | 2022
Glasgow- Major Overhaul- Unit 1 | 185000 | LF07 | 2022
Green Valley- Major Overhaul- Unit 2 & 3 | 370000 | LF01 | 2023
Bavarian- Major Overhaul- Unit 1 & 3 | 370000 | LF03 | 2023
Hardin- Major Overhaul- Unit 2 | 185000 | LF04 | 2023
Pendleton- Major Overhaul- Unit 1 & 4 | 370000 | LF05 | 2023
Laurel Ridge - Major Overhaul- Unit 4 | 199000 | LF02 | 2024
Hardin- Major Overhaul- Unit 3 | 199000 | LF04 | 2024
Laurel Ridge - Major Overhaul- Unit 2 | 199000 | LF02 | 2025
Bavarian- Major Overhaul- Unit 2 | 199000 | LF03 | 2025
Laurel Ridge - Major Overhaul- Unit 3 | 199000 | LF02 | 2026
Pendleton- Major Overhaul- Unit 4 | 199000 | LF05 | 2026