## G
Schedule G
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Projects
As of Forecast period annual 2023
|  |  | Accumulated Costs |  |  |  | Estimated Physical Percent Complete
Line No. | Project No. | Description of Project | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost
(A) | (B) | (C) | (D) | (E) | (F)* | (G = D + E + F)
2 | None Assigned | AMI project | 504458.19 | 18358.4702 |  | 522816.6602 | 0
3 | None Assigned | Clinton Main | 546550 | 7790.5141 |  | 554340.5141 | 0
Total |  |  | 1051008.19 | 26148.9843 | 0 | 1077157.1743 | 0
*Explain the nature of all other indirect costs in footnotes.
Schedule G
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Projects
As of Base period Sept 2022
|  |  | Accumulated Costs |  |  |  | Estimated Physical Percent Complete
Line No. | Project No. | Description of Project | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost
(A) | (B) | (C) | (D) | (E) | (F)* | (G = D + E + F)
Not Applicable
Total |  |  |  | #REF! | #REF!
*Explain the nature of all other indirect costs in footnotes.
Schedule G
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Projects
As of period Sept 2021
|  |  | Accumulated Costs |  |  |  | Estimated Physical Percent Complete
Line No. | Project No. | Description of Project | Construction Amount | AFUDC Capitalized | Indirect Costs Other | Total Cost
(A) | (B) | (C) | (D) | (E) | (F)* | (G = D + E + F)
Not Applicable
Total |  |  |  | #REF! | #REF!
*Explain the nature of all other indirect costs in footnotes.

## H
Schedule H
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Work in Progress – Percent Complete*
As of Forecasted period annual 2023
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (G/H)
2 | AMI project | 2023-01-01 | 2023-12-30 | 0% | 522816.6602 | 522816.6602 | 0 | 0%
3 | Clinton Main | 2023-01-01 | 2023-12-30 | 0 | 554340.5141 | 554340.5141 | 3567.98 | 0.6436%
Schedule H
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Work in Progress – Percent Complete*
As of Base period ending Sept 2022 CWIP as of May 31 ,2022
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (G/H)
Not Applicable
* Should be based on expenditures including AFUDC.
Schedule H
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Work in Progress – Percent Complete*
As of period ending Sept 2021
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (G/H)
Not Applicable
* Should be based on expenditures including AFUDC.

## I1
Schedule I1
Water Service Corporation of Kentucky
Case No. 2022-00147
Construction Projects
For 5 Years Ended December 31, _______2021______
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
None Assigned | GL projects 2021 | 253858 | 239722 | 14136 | 5.568% | 5.897% | 253858 | 239722 | 14136 | 2021-01-01 | 2021-12-31 | 2021-01-01 | 2021-12-31
None Assigned | GL projects 2020 | 307149 | 352265 | -45116 | -14.69% | -12.81% | 307149 | 352265 | -45116 | 2020-01-01 | 2020-12-31 | 2020-01-01 | 2020-12-31
None Assigned | GL projects 2019 | 150701.77 | 101255 | 49446.77 | 32.81% | 48.83% | 150701.77 | 101255 | 49446.77 | 2019-01-01 | 2019-12-31 | 2019-01-01 | 2019-12-31
None Assigned | GL projects 2018 | 219722.86 | 128770.47 | 90952.39 | 41.39% | 70.63% | 219722.86 | 128770.47 | 90952.39 | 2018-01-01 | 2018-12-31 | 2018-01-01 | 2018-12-31
None Assigned | GL projects 2017 | 357654.13 | 243667.0991 | 113987.0309 | 31.87% | 46.78% | 357654.13 | 243667.0991 | 113987.0309 | 2017-01-01 | 2017-12-31 | 2017-01-01 | 2017-12-31
Formulas:
Date Actual Start = [Date Original Budget Start]
Date Actual End = [Date Original Budget End]

## I2
Schedule I2
Water Service Corporation of Kentucky
Case No. 2022-00147
Calculation of Capital Construction Project Slippage Factor
Source: Schedule I1 – Construction Projects
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
1 | 253858 | 239722 | 14136 | 5.897% | 1.059
2 | 307149 | 352265 | -45116 | -12.81% | 0.87193
3 | 150701.77 | 101255 | 49446.77 | 48.83% | 1.4883
4 | 219722.86 | 128770.47 | 90952.39 | 70.63% | 1.7063
5 | 357654.13 | 243667.0991 | 113987.0309 | 46.78% | 1.4678
Totals | 1289085.76 | 1065679.5691 | 223406.1909 | 20.96% | 1.2096
5 Year Average Slippage Factor (Mathematic Average of the Yearly Slippage Factors / 5 years) |  |  |  |  | 1.3187
The Annual Actual Cost, Annual Original Budget, Variance in Dollars, and Variance as Percent are to be taken from Schedule I1. Total all projects for a given year.
The Slippage Factor is calculated by dividing the Annual Actual Cost by the Annual Original Budget. Calculate a Slippage Factor for each year and the Totals line. Carry Slippage Factor percentages to 3 decimal places.