## Sheet1
Project Number | Project Title/ Description | Notice to Proceed/ Originial Start Date | Contract Duration- Substantial | Contract Duration- Final | Substantial Completion on Notice to Proceed | Final Completion on Notice to Proceed | Actual Substantial Completion | Additional Change Order Days | Original Construction Bid Amount | Change Order Total/ Variance in Dollars | Total Actual Construction Cost | Board Approved Budget | Notes
184-0478 | FTTP Lab Standy Power | 2018-09-05 | 270 | 300 | 2019-06-02 | 2019-07-02 | 2019-06-25 | 30- U, C | 72202 | 6347 | 78549 | 237000
184-0488 | TMTP Belt Filter Press Replacement | 2017-06-08 | 380 | 430 | 2018-06-23 | 2018-08-12 | 2018-10-31 | 120- C, P | 886800 | 24829.46 | 911629.46 | 1075000
184-0493 | Richardson Road Pump 2 | 2021-09-21 | 210 | 240 | 2022-04-19 | 2022-05-19 | 2022-04-19 | no | 57275 | 17843 | 75118 | 165000
184-0498 | ORPS1 Pump 4 Upgrade | 2019-07-02 | 180 | 210 | 2019-12-29 | 2020-01-28 | 2020-04-03 | 102- A | 385000 | 91557.98 | 476557.98 | 503000
184-0521 | Bromley Tank Gravity Wall | 2017-05-01 | 25 | 30 | 2017-05-26 | 2017-05-31 | 2017-05-22 | no | 33543.45 | 0 | 33543.45 | 50000
184-0532 | Bromley Tank Drainage Channel | 2018-09-24 | 30 | 40 | 2018-10-24 | 2018-11-03 | 2018-10-01 | no | 25676 | 0 | 25676 | 30000
184-0534 | TMTP and Tank Security Upgrades | 2021-04-07 |  |  | 2021-06-25 | 2021-06-30 | 2021-06-25 | 30- C/P | 61204.71 |  | 61240.71 | 65000
184-0536 | Automated Meter System | 2021-10-07 | 20 years | 20 years | 2041-10-07 | 2041-10-07 | not complete | no | 16712733.71 |  |  | 13500000
184-0613 | Cox Road and Oliver Road WMR | 2019-04-01 | 205 | 230 | 2019-10-23 | 2019-11-17 | 2019-10-29 | 21- A | 940926.6 | 5784.35 | 946710.95 | 1300000
184-0721 | St. Joseph Lane WMR | 2021-01-25 | 60 | 75 | 2021-03-26 | 2021-04-10 | 2021-04-26 | no | 241308 | 1536 | 242844 | 290000
184-0742 | Church Street and Faye Drive WMR | 2018-06-20 | 50 | 65 | 2018-08-09 | 2018-08-24 | 2018-08-20 | 7- A | 208664 | 12381.2 | 221045.2 | 260000
184-0750 | Sub-District M Phase 2 |  | 150 |  |  |  | 2018-04-19 | 58- A, W, H, LD | 953445 | 80863.35 | 1034308.35 | 3400000 | *Phase 1 included in budget
184-0767 | 8" & 12" Water Main Connection- Phase 1 | 2019-05-13 | 60 | 90 | 2019-07-12 | 2019-08-11 | 2019-07-15 | 9- A | 246271 | -518 | 245753 | 335000
184-0776 | 24inch Cross Country WMR project | 2019-04-08 | 90 | 120 | 2019-07-02 | 2019-09-05 | 2019-08-12 | 39- W, H | 980040 | 12300 | 992340 | 1200000
184-0795 | Madison Pike Phase 2 WMR | 2017-10-11 | 120 | 150 | 2018-02-07 | 2018-03-09 | 2018-01-29 | no | 1270875 | 39390.74 | 1231484.26 | 1675000
184-0807 | Edgewood WMR (Phase 1) | 2017-06-26 | 170 | 200 | 2017-12-13 | 2018-01-12 | 2017-11-07 | 1- U | 785328 | 65472.3 | 719855.7 | 900000
184-0812 | Parker and Ridge WMR | 2019-03-18 | 120 | 150 | 2019-07-16 | 2019-08-15 | 2019-07-29 | 24- W | 521127.02 | 5272.7 | 526399.72 | 640000
184-0826 | Lincoln Avenue WMR (Bellevue) | 2017-02-13 | 180 | 210 | 2017-08-12 | 2017-09-11 | 2017-07-06 | 1- A | 958399 | 17862.39 | 976261.39 | 1075000
184-0830 | Riggs Avenue Phase 2 WMR | 2017-08-28 | 75 | 90 | 2017-11-11 | 2017-11-26 | 2017-11-20 | 10- A | 303348.5 | -4505.5 | 298483 | 375000
184-0836 | Blossom Lane WMR | 2017-07-17 | 120 | 150 | 2017-11-14 | 2017-12-14 | 2017-10-31 | no | 755783 | -58481.3 | 697301.7 | 895000
184-0837 | Ervin Terrace & 10th Ave WMR | 2019-09-16 | 65 | 95 | 2019-11-20 | 2019-12-20 | 2019-12-04 | 168 (final)- C | 414113 | 24563.5 | 438676 | 470000
184-0838 | Echo Hills and Licking Pike WMR | 2018-05-14 | 130 | 160 | 2018-09-21 | 2018-10-21 | 2018-12-10 | 61- A, LD | 679720 | 705.98 | 680425.98 | 790000
184-0839 | Latonia Avenue WMR | 2017-04-24 | 60 | 75 | 2017-06-23 | 2017-07-08 | 2017-06-23 | no | 172250 | -6134.5 | 166115.5 | 215000
184-0840 | Ann Street WMR | 2019-04-10 | 125 | 140 | 2019-08-13 | 2019-08-28 | 2019-09-06 | 34- U, A | 447518 | -8129 | 439389 | 530000
184-0842 | Perimeter Dr- Phase 1 WMR | 2017-05-15 | 60 | 75 | 2017-07-14 | 2017-07-29 | 2017-07-17 | 2- U | 213216 | -1452.26 | 211763.74 | 255000
184-0843 | Perimeter Dr- Phase 2 WMR | 2017-11-13 | 75 | 90 | 2018-01-27 | 2018-02-11 | 2018-02-02 | 24- W | 229756 | -7049 | 222707 | 270000
184-0846 | ORPS2 Rehabilitation | 2017-02-01 | 365 | 395 | 2018-02-01 | 2018-03-03 | 2018-01-17 | no | 1564000 | -130931.27 | 1433068.73 | 2000000
184-0848 | Dudley Road and Lyndale Court WMR | 2018-05-07 | 110 | 140 | 2018-08-25 | 2018-09-24 | 2018-11-12 | 57- A, LD | 636524 | 70338 | 706862 | 831490
184-0849 | Wedgewood Drive and Clubhouse Drive WMR | 2017-03-13 | 110 | 130 | 2017-07-01 | 2017-07-21 | 2017-06-28 | no | 333000 | 1911.17 | 334911.17 | 415000
184-0850 | Brookwood Drive WMR - Central Phase | 2017-06-14 | 35 | 42 | 2017-07-19 | 2017-07-26 | 2017-07-25 | 9- U, W, H | 134610 | 5246 | 139856 | 175000
184-0851 | Hudson Avenue WMR | 2017-02-27 | 28 | 35 | 2017-03-27 | 2017-04-03 | 2017-03-27 | no | 97375 | 1765 | 99140 | 130000
184-0852 | Buttermilk Pike WMR | 2018-01-22 | 85 | 100 | 2018-04-17 | 2018-05-02 | 2018-05-08 | 21- A | 403786.3 | 24734.5 | 428520.8 | 485000
184-0853 | McHenry Street and Clifton Avenue WMR | 2017-04-26 | 28 | 35 | 2017-05-24 | 2017-05-31 | 2017-05-31 | 11- U | 72000 | 8476.07 | 80476.07 | 90000
184-0854 | McKinney St and 9th Ave WMR | 2017-08-09 | 21 | 28 | 2017-08-30 | 2017-09-06 | 2017-08-30 | no | 81590 | -12.37 | 81577.63 | 110000
184-0855 | Arlington Road WMR | 2018-07-16 | 40 | 50 | 2018-08-25 | 2018-09-04 | 2018-09-18 | 28- C | 172736 | -8888.5 | 163847.5 | 210000
184-0856 | Lorup Avenue WMR | 2017-07-05 | 40 | 50 | 2017-08-14 | 2017-08-24 | 2017-08-18 | 7- W | 159191 | -1761.1 | 157429.9 | 195000
184-0857 | Caldwell Drive MWR | 2018-04-09 | 35 | 45 | 2018-05-14 | 2018-05-24 | 2018-05-07 | no | 108082 | -1930 | 106152 | 130000
184-0858 | Erlanger Road Phase 2 WMR | 2018-06-04 | 50 | 70 | 2018-07-24 | 2018-08-13 | 2018-07-30 | 7- A | 260558.22 | -10205.14 | 250353.08 | 325000
184-0859 | Birch Drive WMR | 2018-04-16 | 45 | 60 | 2018-05-31 | 6/15/20118 | 2018-05-15 | no | 126096 | -11700.68 | 114395.32 | 160000
184-0860 | Amsterdam Road WMR- HDPE | 2020-04-13 | 90 | 120 | 2020-07-12 | 2020-08-11 | 2020-07-08 | 2- A | 329521.25 | -4632.42 | 324888.83 | 400000
184-0861 | Stonehouse Road WMR | 2019-08-05 | 100 | 130 | 2019-11-13 | 2019-12-13 | 2019-10-10 | no | 661170 | 664.5 | 661834.5 | 770000
184-0862 | Highland Ave WMR | 2018-03-05 | 35 | 45 | 2018-04-09 | 2018-04-19 | 2018-04-06 | no | 108454 | 4485.21 | 112939.21 | 135000
184-0863 | Amsterdam Road WMR (Morris to Redwood) | 2018-03-13 | 40 | 55 | 2018-04-22 | 2018-05-07 | 2018-04-20 | no | 151075 | 181 | 151256 | 180000
184-0864 | Winters Lane WMR | 2018-05-14 | 135 | 165 | 2018-09-26 | 2018-10-26 | 2018-08-29 | no | 761680 | -5875.9 | 755804.1 | 870000
184-0865 | Ripple Creek Road WMR | 2018-05-29 | 40 | 55 | 2018-07-08 | 2018-07-23 | 2018-07-09 | 4- U, A | 185260 | -13624.1 | 171635.9 | 235000
184-0866 | Pentland Place WMR | [5 empty] | 2018-09-26 |  |  |  |  | 255000 | *coordinated with city
184-0867 | Alexander Circle (Cochran Avenue) WMR | 2018-11-01 | 70 | 90 | 2019-01-10 | 2019-01-30 | 2019-07-26 | 176- C | 290641.6 | -4959.5 | 285682.1 | 355000
184-0868 | Brookwood Drive WMR - North Phase | 2018-03-26 | 35 | 42 | 2018-04-30 | 2018-05-07 | 2018-04-30 | no | 93075 | 1156 | 94231 | 120000
184-0869 | Highland Ave WMR (Oak to Floral) | 2018-07-09 | 35 | 45 | 2018-08-13 | 2018-08-23 | 2018-08-17 | 3- A | 111040 | -1710.25 | 109329.75 | 135000
184-0870 | Sunset Drive WMR | 2018-08-20 | 40 | 50 | 2018-08-29 | 2018-08-09 | 2018-10-03 | 4- W, H | 153516.45 | 91.65 | 153608.1 | 185000
184-0871 | N. Ft. Thomas Ave WMR (Covert to Lincoln) | 2019-04-01 | 100 | 120 | 2019-07-10 | 2019-07-30 | 2019-07-08 | no | 549575 | -16988 | 532587 | 665000
184-0872 | Narrows and Nelson WMR Relocation | [10 empty] | 75000 | *coordinated with city
184-0873 | Jackson Road WMR | 2020-01-06 | 40 | 60 | 2020-02-15 | 2020-03-03 | 2020-03-11 | no | 168373 | 2487 | 170860 | 205000
184-0874 | Janet Drive WMR | 2019-05-20 | 50 | 65 | 2019-07-09 | 2019-07-24 | 2019-07-15 | 11- U, A | 181055 | 5534.5 | 186539.5 | 220000
184-0875 | Hillview Drive WMR (Dixie to Longmeadow) | 2019-08-05 | 50 | 70 | 2019-09-24 | 2019-10-14 | 2019-09-18 | no | 243393.5 | -649.25 | 242744.25 | 300000
184-0876 | Brookwood and Oakridge Drive WMR | 2019-11-18 | 65 | 90 | 2020-01-22 | 2020-02-16 | 2020-02-07 | 26- A | 178352.1 | 835.35 | 179187.45 | 230000
184-0877 | Valleywood Court & Hickory Lane WMR | 2020-06-15 | 45 | 60 | 2020-07-30 | 2020-08-14 | 2020-07-22 | no | 154630 | -5382 | 149248 | 200000
184-0878 | Covert Run to Lincoln WMR | 2020-11-02 | 60 | 90 | 2021-01-01 | 2021-01-31 | 2021-01-21 | no | 282969.1 | 2948.07 | 285917.17 | 360000
184-0879 | Rossmoyne, Druid, Warwick WMR | 2019-03-18 | 50 | 70 | 2019-05-07 | 2019-05-27 | 2019-04-18 | no | 267911 | -6757 | 261154 | 300000
184-0880 | Parkway Dr WMR | 2019-04-30 | 30 | 40 | 2019-05-29 | 2019-06-08 | 2019-06-04 | 8- W | 124944 | 2212.3 | 127156.3 | 155000
184-0881 | Ash Street WMR | 2019-07-15 | 28 | 35 | 2019-08-12 | 2019-08-19 | 2019-08-09 | no | 114318 | 310 | 114628 | 140000
184-0882 | Pieck Drive and West Henry Clay Ave WMR | 2019-05-28 | 40 | 50 | 2019-07-07 | 2019-07-17 | 2019-06-27 | no | 162805.4 | 5359.4 | 168164.8 | 200000
184-0883 | Sunset Drive & Allen Court WMR | 2019-08-08 | 45 | 55 | 2019-09-22 | 2019-10-02 | 2019-09-24 | 2- W | 172758.6 | 671.1 | 173429.7 | 210000
184-0884 | Thornton & Tower View WMR | 2020-07-15 | 45 | 60 | 2020-08-29 | 2020-09-13 | 2020-09-14 | no | 117589 | 5661 | 123250 | 155000
184-0885 | Amsterdam Road WMR (Arlington to Montauge) | 2020-01-06 | 45 | 60 | 2020-02-20 | 2020-03-06 | 2020-03-09 | 1- A | 302690 | -1601.07 | 301088.93 | 370000
184-0886 | Highland Avenue WMR | 2019-07-15 | 80 | 100 | 2019-10-03 | 2019-10-23 | 2019-10-10 | 7- W | 389360 | -4244 | 385116 | 430000
184-0887 | Wayskin, Marnoam, Sipple, & Dave WMR | 2019-10-28 | 120 | 150 | 2020-02-25 | 2020-03-26 | 2020-02-12 | no | 444996.2 | -12096 | 432900.2 | 540000
184-0888 | Fourth Street MWR (Scott to Greenup) | 2019-06-17 | 45 | 60 | 2019-08-01 | 2019-08-16 | 2019-07-31 | 2- A | 257295.6 | 1033.6 | 258329.2 | 300000
184-0889 | Old Alexandria Pike (CR1557) WMR | 2019-12-03 | 30 | 45 | 2020-01-01 | 2020-01-16 | 2019-12-20 | 2- A | 132175 | 3659 | 135834 | 160000
184-0890 | E. Main St WMR | 2020-06-01 | 90 | 120 | 2020-08-30 | 2020-09-29 | 2020-07-20 | no | 565009.5 | 4000 | 569009.5 | 650000
184-0891 | Ridge and W. Orchard Road WMR | [5 empty] | 2020-07-16 |  |  |  |  | 270000 | *coordinated with city
184-0892 | Barma Drive WMR | 2019-10-21 | 30 | 45 | 2019-11-20 | 2019-12-05 | 2019-11-11 | no | 61984.8 | -860 | 61124.8 | 90000
184-0893 | Crowell & Eustace WMR | 2020-08-10 | 90 | 105 | 2020-11-08 | 2020-11-23 | 2020-11-09 | 11- A | 405396.95 | -1256.4 | 404140.55 | 470000
184-0894 | Thatcher Ct & Paul Ln WMR | 2020-06-30 | 55 | 70 | 2020-08-24 | 2020-09-08 | 2020-08-21 | no | 188724.7 | 3761.15 | 192485.85 | 240000
184-0895 | Persimmon, etc WMR | 2020-10-05 | 140 | 160 | 2021-02-22 | 2021-03-14 | 2021-02-26 | no | 472992.5 | -12107.38 | 460815.12 | 545000
184-0896 | Lexington & Woodward WMR | 2021-04-12 | 100 | 120 | 2021-07-21 | 2021-08-10 | 2021-08-04 | 14- W, H, A | 441707 | -2817 | 438890 | 510000
184-0897 | E. Main St WMR - Phase 2 | 2021-06-14 | 90 | 120 | 2021-09-12 | 2021-10-12 | 2021-09-10 | no | 417598.56 | 3114.3 | 420712.86 | 490000
184-0899 | Greenup Street WMR | 2020-10-14 | 30 | 45 | 2020-11-13 | 2020-11-28 | 2020-11-03 | no | 52015 | -325 | 51690 | 65000
184-0900 | Robin Ln WMR | 2021-03-15 | 40 | 60 | 2021-04-24 | 2021-05-14 | 2021-04-20 | no | 114484 | -5840 | 108644 | 140000
184-0901 | Wayman Branch WMR | 2021-08-30 | 60 | 80 | 2021-10-29 | 2021-11-18 | 2021-11-17 | 19- A | 434310 | -1265 | 433045 | 500000
184-0902 | Sagebrush & Shadyside WMR | 2021-03-15 | 80 | 100 | 2021-06-03 | 2021-06-23 | 2021-06-08 | 6- W, H | 362029.85 | -17693.64 | 344336.21 | 420000
184-0904 | Chapman Lane WMR | 2021-08-16 | 30 | 40 | 2021-09-15 | 2021-09-25 | 2021-09-30 | no | 151916 | 1858 | 153774 | 190000
184-0905 | Willowbrook Lane WMR | 2021-08-16 | 30 | 40 | 2021-09-15 | 2021-09-25 | 2021-09-20 | no | 169520 | -1530 | 167990 | 210000
184-0907 | Joyce Avenue WMR | 2021-10-18 | 28 | 35 | 2021-11-15 | 2021-11-22 | 2021-11-17 | no | 84141 | 1685 | 85826 | 110000
184-4003 | SCADA improvements- Phase 1 | 2020-07-06 | 180 | 210 | 2021-01-02 | 2021-02-01 | 2021-04-03 | 456- C, P | 671031 | 2500 | 673531 | 900000
184-4005 | TMTP Concrete Flow Meter Pit | 2018-01-08 | 30 | 45 | 2018-02-22 | 2018-03-09 | 2018-01-29 | no | 39210 | 0 | 39210 | 60000
184-4006 | FTTP Phase 2 Basin Improvements | 2021-06-01 | 660 | 730 | 2023-03-23 | 2023-06-01 | not complete |  | 5584000 |  |  | 6000000 | *project not complete
184-4008 | FTTP Residuals Handling Improvements | 2021-01-04 | 420 | 450 | 2022-02-28 | 2022-03-30 | 2022-06-13 | 169- C | 2177000 | 232302.33 | 2409302.33 | 3000000
184-4012 | MPTP Clearwell Rehab and Painting | 2020-03-16 | 90 | 105 | 2020-06-14 | 2020-06-29 | 2020-07-10 | 26- A | 647000 | 35418.59 | 682418.59 | 743923
184-4014 | Central Facility Standby Power | 2019-06-05 | 270 | 300 | 2020-03-01 | 2020-03-31 | 2020-03-27 | 150- C, P | 375620 | 1463.05 | 377083.5 | 400000
*U= unmarked items on original plans,
*W= weather
*H= holiday
*A= additional work for adjusted quantities
*LD= liquidated damages assessed
*C= Duke, City coordination, NKWD coordination
*P= COVID Pandemic related

## Schedule E
|  |  | contractor final cost or current with approved Cos | Ask Gerry | difference Column O and Column L | Get $ from Tracy
Line No. (A) | Project Number (B) | Description of Project (C) | Construction Amount (D) | AFUDC Capitalized (E) | Indirect Costs Other (F)* | Total Cost (G=D+E+F) | Estimated Physical Percent Complete | Most Recent Budget Estimate (G) | Total Project Expenditures (H)
| 184-0872 | Narrows and Nelson WMR Relocation
| 184-0866 | Pentland Place WMR
| 184-0750 | Sub-District M Phase 2 | 953445
| 162-003 | Dayton Tank Painting | 261000
| 162-003 | Dudley 1080 Tank Painting | 623900
| 184-0846 | ORPS2 Rehabilitation | 1564000
| 184-0826 | Lincoln Avenue WMR (Bellevue) | 958399
| 184-0851 | Hudson Avenue WMR | 97375
| 184-0849 | Wedgewood Drive and Clubhouse Drive WMR | 333000
| 184-0839 | Latonia Avenue WMR | 172250
| 184-0853 | McHenry Street and Clifton Avenue WMR | 72000
| 184-0521 | Bromley Tank Gravity Wall | 33543.45
| 184-0842 | Perimeter Dr- Phase 1 WMR | 213216
| 184-0488 | TMTP Belt Filter Press Replacement | 886800
| 184-0850 | Brookwood Drive WMR - Central Phase | 134610
| 184-0807 | Edgewood WMR (Phase 1) | 785328
| 184-0856 | Lorup Avenue WMR | 159191
| 184-0836 | Blossom Lane WMR | 755783
| 184-0854 | McKinney St and 9th Ave WMR | 81590
| 184-0830 | Riggs Avenue Phase 2 WMR | 303348.5
| 184-0795 | Madison Pike Phase 2 WMR | 1270875
| 184-0843 | Perimeter Dr- Phase 2 WMR | 229756
| 184-4005 | TMTP Concrete Flow Meter Pit | 39210
| 184-0852 | Buttermilk Pike WMR | 403786.3
| 184-0862 | Highland Ave WMR | 108454
| 184-0863 | Amsterdam Road WMR (Morris to Redwood) | 151075
| 184-0868 | Brookwood Drive WMR - North Phase | 93075
| 184-0857 | Caldwell Drive MWR | 108082
| 184-0859 | Birch Drive WMR | 126096
| 184-0848 | Dudley Road and Lyndale Court WMR | 636524
| 184-0838 | Echo Hills and Licking Pike WMR | 679720
| 184-0864 | Winters Lane WMR | 761680
| 184-0865 | Ripple Creek Road WMR | 185260
| 184-0858 | Erlanger Road Phase 2 WMR | 260558.22
| 162-003 | Harrison Tank Painting | 65100
| 162-003 | South Newport Tank Repairs | 15600
| 184-0742 | Church Street and Faye Drive WMR | 208664
| 184-0869 | Highland Ave WMR (Oak to Floral) | 111040
| 184-0855 | Arlington Road WMR | 172736
| 184-0870 | Sunset Drive WMR | 153516.45
| 162-003 | Devon Tank Painting | 578820
| 184-0532 | Bromley Tank Drainage Channel | 25676
| 184-0867 | Alexander Circle (Cochran Avenue) WMR | 290641.6
| 184-0812 | Parker and Ridge WMR | 521127.02
| 184-0879 | Rossmoyne, Druid, Warwick WMR | 267911
| 184-0613 | Cox Road and Oliver Road WMR | 940926.6
| 184-0871 | N. Ft. Thomas Ave WMR (Covert to Lincoln) | 549575
| 184-0776 | 24inch Cross Country WMR project | 980040
| 184-0840 | Ann Street WMR | 447518
| 162-003 | Rossford Tank Painting | 299200
| 184-0880 | Parkway Dr WMR | 124944
| 184-0767 | 8" & 12" Water Main Connection- Phase 1 | 246271
| 184-0874 | Janet Drive WMR | 181055
| 184-0882 | Pieck Drive and West Henry Clay Ave WMR | 162805.4
| 184-4014 | Central Facility Standby Power | 375620
| 184-0888 | Fourth Street MWR (Scott to Greenup) | 257295.6
| 184-0498 | ORPS1 Pump 4 Upgrade | 385000
| 184-0881 | Ash Street WMR | 114318
| 184-0886 | Highland Avenue WMR | 389360
| 184-0861 | Stonehouse Road WMR | 661170
| 184-0875 | Hillview Drive WMR (Dixie to Longmeadow) | 243393.5
| 184-0883 | Sunset Drive & Allen Court WMR | 172758.6
| 184-0837 | Ervin Terrace & 10th Ave WMR | 414113
| 184-0892 | Barma Drive WMR | 61984.8
| 184-0887 | Wayskin, Marnoam, Sipple, & Dave WMR | 444996.2
| 184-0876 | Brookwood and Oakridge Drive WMR | 178352.1
| 184-0889 | Old Alexandria Pike (CR1557) WMR | 132175
1 | 184-0534 | TMTP Security Camera Upgrade | 61204.71 | N/A | 2538.2 | 63742.91 | 100
2 | 184-0536 | Automated Meter System | 12890000 | N/A | 610000 | 13500000 | 5 | 6000000
3 | 184-0478 | FTTP Lab Standby Power | 78549 | N/A | 54679.25 | 133228.25 | 100
4 | 184-0721 | St. Joseph Lane WMR | 242844 | N/A | 47605.32 | 290449.32 | 100
5 | 184-0860 | Amsterdam Road WMR- HDPE | 324888.83 | N/A | 40708.38 | 365597.21 | 100
6 | 184-0873 | Jackson Road WMR | 170860 | N/A | 27173.28 | 198033.28 | 100
7 | 184-0877 | Valleywood Court & Hickory Lane WMR | 149248 | N/A | 32489.58 | 181737.58 | 100
8 | 184-0878 | Covert Run to Lincoln WMR | 285917.17 | N/A | 70254.76 | 356171.93 | 100
9 | 184-0884 | Thornton & Tower View WMR | 123250 | N/A | 29100.93 | 152350.93 | 100
10 | 184-0885 | Amsterdam Road WMR (Arlington to Montauge) | 301088.93 | N/A | 32880.36 | 333969.29 | 100
11 | 184-0890 | E. Main St WMR | 569009.5 | N/A | 54533.09 | 623542.59 | 100
12 | 184-0891 | Ridge and W. Orchard Road WMR | 222863 | N/A | 33331.45 | 256194.45 | 100
13 | 184-0893 | Crowell & Eustace WMR | 404140.55 | N/A | 60935.87 | 465076.42 | 100
14 | 184-0894 | Thatcher Ct & Paul Ln WMR | 192485.85 | N/A | 33190.44 | 225676.29 | 100
15 | 184-0895 | Persimmon, etc WMR | 460815.12 | N/A | 58114.73 | 518929.85 | 100
16 | 184-0896 | Lexington & Woodward WMR | 438890 | N/A | 71590.95 | 510480.95 | 100
17 | 184-0897 | E. Main St WMR - Phase 2 | 420712.86 | N/A | 26780.52 | 447493.38 | 100
18 | 184-0899 | Greenup Street WMR | 51690 | N/A | 11952.89 | 63642.89 | 100
19 | 184-0900 | Robin Ln WMR | 108644 | N/A | 21961.57 | 130605.57 | 100
20 | 184-0901 | Wayman Branch WMR | 433045 | N/A | 38635.43 | 471680.43 | 100
21 | 184-0902 | Sagebrush & Shadyside WMR | 344336.21 | N/A | 50148.99 | 394485.2 | 100
22 | 184-0904 | Chapman Lane WMR | 153774 | N/A | 23377.09 | 177151.09 | 100
23 | 184-0905 | Willowbrook Lane WMR | 167990 | N/A | 26076.03 | 194066.03 | 100
24 | 184-0907 | Joyce Avenue WMR | 85826 | N/A | 14086.61 | 99912.61 | 100
25 | 184-4003 | SCADA improvements | 673531 | N/A | 439821.22 | 3938969 | 35
26 | 184-4006 | FTTP Phase 2 Basin Improvements | 5680250 | N/A | 319750 | 6000000 | 35
27 | 184-4008 | FTTP Residuals Handling Improvements | 2409302.33 | N/A | 590697.67 | 3000000 | 95
28 | 184-4012 | MPTP Clearwell Rehab and Painting | 682418.59 | N/A | 79566.02 | 761984.61 | 100

## Schedule F
[7 empty] | same as Schedule E column G if project is complete | same as Schedule E column G if complete or current cost from Tracy
Line No. (A) | Project Number (B) | Project Title/ Description | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H)
| 184-0872 | Narrows and Nelson WMR Relocation |  |  |  | 75000
| 184-0866 | Pentland Place WMR |  |  |  | 255000
| 184-0750 | Sub-District M Phase 2 |  |  |  | 3400000
| 162-003 | Dayton Tank Painting |  | 2017-10-27 |  | 350000
| 162-003 | Dudley 1080 Tank Painting |  |  |  | 700000
| 184-0846 | ORPS2 Rehabilitation | 2017-02-01 | 2018-02-01 |  | 2000000
| 184-0826 | Lincoln Avenue WMR (Bellevue) | 2017-02-13 | 2017-08-12 |  | 1075000
| 184-0851 | Hudson Avenue WMR | 2017-02-27 | 2017-03-27 |  | 130000
| 184-0849 | Wedgewood Drive and Clubhouse Drive WMR | 2017-03-13 | 2017-07-01 |  | 415000
| 184-0839 | Latonia Avenue WMR | 2017-04-24 | 2017-06-23 |  | 215000
| 184-0853 | McHenry Street and Clifton Avenue WMR | 2017-04-26 | 2017-05-24 |  | 90000
| 184-0521 | Bromley Tank Gravity Wall | 2017-05-01 | 2017-05-26 |  | 50000
| 184-0842 | Perimeter Dr- Phase 1 WMR | 2017-05-15 | 2017-07-14 |  | 255000
| 184-0488 | TMTP Belt Filter Press Replacement | 2017-06-08 | 2018-06-23 |  | 1075000
| 184-0850 | Brookwood Drive WMR - Central Phase | 2017-06-14 | 2017-07-19 |  | 175000
| 184-0807 | Edgewood WMR (Phase 1) | 2017-06-26 | 2017-12-13 |  | 900000
| 184-0856 | Lorup Avenue WMR | 2017-07-05 | 2017-08-14 |  | 195000
| 184-0836 | Blossom Lane WMR | 2017-07-17 | 2017-11-14 |  | 895000
| 184-0854 | McKinney St and 9th Ave WMR | 2017-08-09 | 2017-08-30 |  | 110000
| 184-0830 | Riggs Avenue Phase 2 WMR | 2017-08-28 | 2017-11-11 |  | 375000
| 184-0795 | Madison Pike Phase 2 WMR | 2017-10-11 | 2018-02-07 |  | 1675000
| 184-0843 | Perimeter Dr- Phase 2 WMR | 2017-11-13 | 2018-01-27 |  | 270000
| 184-4005 | TMTP Concrete Flow Meter Pit | 2018-01-08 | 2018-02-22 |  | 60000
| 184-0852 | Buttermilk Pike WMR | 2018-01-22 | 2018-04-17 |  | 485000
| 184-0862 | Highland Ave WMR | 2018-03-05 | 2018-04-09 |  | 135000
| 184-0863 | Amsterdam Road WMR (Morris to Redwood) | 2018-03-13 | 2018-04-22 |  | 180000
| 184-0868 | Brookwood Drive WMR - North Phase | 2018-03-26 | 2018-04-30 |  | 120000
| 184-0857 | Caldwell Drive MWR | 2018-04-09 | 2018-05-14 |  | 130000
| 184-0859 | Birch Drive WMR | 2018-04-16 | 2018-05-31 |  | 160000
| 184-0848 | Dudley Road and Lyndale Court WMR | 2018-05-07 | 2018-08-25 |  | 831490
| 184-0838 | Echo Hills and Licking Pike WMR | 2018-05-14 | 2018-09-21 |  | 790000
| 184-0864 | Winters Lane WMR | 2018-05-14 | 2018-09-26 |  | 870000
| 184-0865 | Ripple Creek Road WMR | 2018-05-29 | 2018-07-08 |  | 235000
| 184-0858 | Erlanger Road Phase 2 WMR | 2018-06-04 | 2018-07-24 |  | 325000
| 162-003 | Harrison Tank Painting | 2018-06-18 | 2018-07-13 |  | 300000
| 162-003 | South Newport Tank Repairs | 2018-06-18 | 2018-07-09 |  | 300000
| 184-0742 | Church Street and Faye Drive WMR | 2018-06-20 | 2018-08-09 |  | 260000
| 184-0869 | Highland Ave WMR (Oak to Floral) | 2018-07-09 | 2018-08-13 |  | 135000
| 184-0855 | Arlington Road WMR | 2018-07-16 | 2018-08-25 |  | 210000
| 184-0870 | Sunset Drive WMR | 2018-08-20 | 2018-08-29 |  | 185000
| 162-003 | Devon Tank Painting | 2018-09-10 | 2018-11-19 |  | 800000
| 184-0532 | Bromley Tank Drainage Channel | 2018-09-24 | 2018-10-24 |  | 30000
| 184-0867 | Alexander Circle (Cochran Avenue) WMR | 2018-11-01 | 2019-01-10 |  | 355000
| 184-0812 | Parker and Ridge WMR | 2019-03-18 | 2019-07-16 |  | 640000
| 184-0879 | Rossmoyne, Druid, Warwick WMR | 2019-03-18 | 2019-05-07 |  | 300000
| 184-0613 | Cox Road and Oliver Road WMR | 2019-04-01 | 2019-10-23 |  | 1300000
| 184-0871 | N. Ft. Thomas Ave WMR (Covert to Lincoln) | 2019-04-01 | 2019-07-10 |  | 665000
| 184-0776 | 24inch Cross Country WMR project | 2019-04-08 | 2019-07-02 |  | 1200000
| 184-0840 | Ann Street WMR | 2019-04-10 | 2019-08-13 |  | 530000
| 162-003 | Rossford Tank Painting | 2019-04-15 | 2019-05-30 |  | 360000
| 184-0880 | Parkway Dr WMR | 2019-04-30 | 2019-05-29 |  | 155000
| 184-0767 | 8" & 12" Water Main Connection- Phase 1 | 2019-05-13 | 2019-07-12 |  | 335000
| 184-0874 | Janet Drive WMR | 2019-05-20 | 2019-07-09 |  | 220000
| 184-0882 | Pieck Drive and West Henry Clay Ave WMR | 2019-05-28 | 2019-07-07 |  | 200000
| 184-4014 | Central Facility Standby Power | 2019-06-05 | 2020-03-01 |  | 400000
| 184-0888 | Fourth Street MWR (Scott to Greenup) | 2019-06-17 | 2019-08-01 |  | 300000
| 184-0498 | ORPS1 Pump 4 Upgrade | 2019-07-02 | 2019-12-29 |  | 503000
| 184-0881 | Ash Street WMR | 2019-07-15 | 2019-08-12 |  | 140000
| 184-0886 | Highland Avenue WMR | 2019-07-15 | 2019-10-03 |  | 430000
| 184-0861 | Stonehouse Road WMR | 2019-08-05 | 2019-11-13 |  | 770000
| 184-0875 | Hillview Drive WMR (Dixie to Longmeadow) | 2019-08-05 | 2019-09-24 |  | 300000
| 184-0883 | Sunset Drive & Allen Court WMR | 2019-08-08 | 2019-09-22 |  | 210000
| 184-0837 | Ervin Terrace & 10th Ave WMR | 2019-09-16 | 2019-11-20 |  | 470000
| 184-0892 | Barma Drive WMR | 2019-10-21 | 2019-11-20 |  | 90000
| 184-0887 | Wayskin, Marnoam, Sipple, & Dave WMR | 2019-10-28 | 2020-02-25 |  | 540000
| 184-0876 | Brookwood and Oakridge Drive WMR | 2019-11-18 | 2020-01-22 |  | 230000
| 184-0889 | Old Alexandria Pike (CR1557) WMR | 2019-12-03 | 2020-01-01 |  | 160000
1 | 184-0534 |  | 2021-04-07 | 2021-06-25 | 100 | 65000 | 63742.91 | 63742.91
2 | 184-0536 |  | 2021-10-07 | 2023-10-07 | 5 | 13500000 | 13500000 | 157500
3 | 184-0478 |  | 2018-09-05 | 2019-07-25 | 100 | 237000 | 133228.25 | 133228.25
4 | 184-0721 | St. Joseph Lane WMR | 2021-01-25 | 2021-04-26 | 100 | 290000 | 290449.32 | 290449.32
5 | 184-0860 | Amsterdam Road WMR- HDPE | 2020-04-13 | 2020-07-08 | 100 | 400000 | 365597.21 | 365597.21
6 | 184-0873 | Jackson Road WMR | 2020-01-06 | 2020-03-11 | 100 | 205000 | 198033.28 | 198033.28
7 | 184-0877 | Valleywood Court & Hickory Lane WMR | 2020-06-15 | 2020-07-22 | 100 | 200000 | 181737.58 | 181737.58
8 | 184-0878 | Covert Run to Lincoln WMR | 2020-11-02 | 2021-01-21 | 100 | 360000 | 356171.93 | 356171.93
9 | 184-0884 | Thornton & Tower View WMR | 2020-07-15 | 2020-09-14 | 100 | 155000 | 152350.93 | 152350.93
10 | 184-0885 | Amsterdam Road WMR (Arlington to Montauge) | 2020-01-06 | 2020-03-09 | 100 | 370000 | 333969.29 | 333969.29
11 | 184-0890 | E. Main St WMR | 2020-06-01 | 2020-07-20 | 100 | 650000 | 623542.59 | 623542.59
12 | 184-0891 | Ridge and W. Orchard Road WMR | 2020-06-01 | 2020-07-16 | 100 | 270000 | 256194.45 | 256194.45
13 | 184-0893 | Crowell & Eustace WMR | 2020-08-10 | 2020-11-09 | 100 | 470000 | 465076.42 | 465076.42
14 | 184-0894 | Thatcher Ct & Paul Ln WMR | 2020-06-30 | 2020-08-21 | 100 | 240000 | 225676.29 | 225676.29
15 | 184-0895 | Persimmon, etc WMR | 2020-10-05 | 2021-02-26 | 100 | 545000 | 518929.85 | 518929.85
16 | 184-0896 | Lexington & Woodward WMR | 2021-04-12 | 2021-08-04 | 100 | 510000 | 510480.95 | 510480.95
17 | 184-0897 | E. Main St WMR - Phase 2 | 2021-06-14 | 2021-09-10 | 100 | 490000 | 447493.38 | 447493.38
18 | 184-0899 | Greenup Street WMR | 2020-10-14 | 2020-11-03 | 100 | 65000 | 63642.89 | 63642.89
19 | 184-0900 | Robin Ln WMR | 2021-03-15 | 2021-04-20 | 100 | 140000 | 130605.57 | 130605.57
20 | 184-0901 | Wayman Branch WMR | 2021-08-30 | 2021-11-17 | 100 | 500000 | 471680.43 | 471680.43
21 | 184-0902 | Sagebrush & Shadyside WMR | 2021-03-15 | 2021-06-08 | 100 | 420000 | 394485.2 | 394485.2
22 | 184-0904 | Chapman Lane WMR | 2021-08-16 | 2021-09-30 | 100 | 190000 | 177151.09 | 177151.09
23 | 184-0905 | Willowbrook Lane WMR | 2021-08-16 | 2021-09-20 | 100 | 210000 | 194066.03 | 194066.03
24 | 184-0907 | Joyce Avenue WMR | 2021-10-18 | 2021-11-17 | 100 | 110000 | 99912.61 | 99912.61
25 | 184-4003 | SCADA improvements- Phase 1 | 2020-07-06 | Ph 2- not bid | 35 | 3938969 | 3938969 | 1113352.22
26 | 184-4006 | FTTP Phase 2 Basin Improvements | 2021-06-01 | 2023-03-23 | 35 | 6000000 | 6000000 | 4553618.08
27 | 184-4008 | FTTP Residuals Handling Improvements | 2021-01-04 | 2020-06-13 | 95 | 3000000 | 3000000 | 2705485.24
28 | 184-4012 | MPTP Clearwell Rehab and Painting | 2020-03-16 | 2020-07-10 | 100 | 743923 | 743923 | 761984.61
[6 empty] | board approved budget | if complete: this is the actual budget spent
if not complete: board approved budget

## Schedule G1
[9 empty] | For Date Original Budget Started | 2021-03-18 | BAN 2021
[10 empty] | 2017-04-19 | BAN 2017
[10 empty] | 2011-09-22 | BAN 2011
| need to add unbid 184 projects where we've incurred expenses between 1/1/2017 and 12/31/21 | defer until further evaluation |  |  |  |  | From Tracy, will be total project cost if completed or projected cost if in progress- completed on 7.27 | board approved total project cost |  | Use earliest of: 1) date of BAN issuance; first year in blue section of approved budget; or date of first expense | Use 2 years from date of BAN; or date of last expense if IR&R | use Tracy's first bill | use SC or date of last bill, which of is later
Project Number | Project Title/ Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End | Substantial completion | date of last bill | Funding Source | Original Date of Funding Source | Notice to Proceed/ Originial Start Date | Contract Duration- Substantial | Contract Duration- Final | Substantial Completion on Notice to Proceed | Final Completion on Notice to Proceed | Actual Substantial Completion | Additional Change Order Days | Original Construction Bid Amount | Change Order Total/ Variance in Dollars | Total Actual Construction Cost | Board Approved Budget | Notes
184-0475 | MPTP Raw Water Line | 1 | 1 | 0 | 0% |  | 189498.18 | 1000000 | -810501.82 | 2013-01-01 | on hold | 2013-12-31 | not complete | not complete | 2018-06-30 | BAN 2017- 545,910, SRF 2014- 454,090
184-0477 | FTTP Floc/Sed Basins 2 & 3 | 1 | 1 | 0 | 0% |  | 2423261.12 | 2700000 | -276738.88 | 2011-09-22 | 2013-09-22 | 2013-06-01 | 2017-05-31 | 2016-03-29 | 2017-05-31 | IR &R, SRF loan 2014
184-0478 | FTTP Laboratory Generator | 1 | 1 | 0 | 0% |  | 132228.25 | 237000 | -104771.75 | 2011-09-22 | 2013-09-22 | 2013-10-07 | 2019-12-31 | 2019-06-25 | 2019-12-31 | BAN 2011 |  | 2018-09-05 | 270 | 300 | 2019-06-02 | 2019-07-02 | 2019-06-25 | 30- U, C | 72202 | 6347 | 78549 | 237000
184-0486 | ORPS2 Rehabilitation | 1 | 1 | 0 | 0% |  | 1805455.68 | 2000000 | -194544.32 | 2017-04-19 | 2019-04-19 | 2016-07-01 | 2018-01-17 | 2018-01-17 | 2016-12-31 | BAN 2017 |  | 2017-02-01 | 365 | 395 | 2018-02-01 | 2018-03-03 | 2018-01-17 | no | 1564000 | -130931.27 | 1433068.73 | 2000000
184-0487 | Replace Lumley Tank | 1 | 1 | 0 | 0% |  | 1846222.39 | 2000000 | -153777.61 | 2015-01-01 | 2018-12-31 | 2014-12-31 | 2017-12-31 | 2017-02-27 | 2017-12-31 | IR&R, SRF 2015
184-0488 | TMTP Belt Filter Press Replacement | 1 | 1 | 0 | 0% |  | 1042668.57 | 1075000 | -32331.43 | 2017-04-19 | 2019-04-19 | 2015-04-01 | 2019-12-31 | 2018-10-31 | 2019-12-31 | BAN 2017 |  | 2017-06-08 | 380 | 430 | 2018-06-23 | 2018-08-12 | 2018-10-31 | 120- C, P | 886800 | 24829.46 | 911629.46 | 1075000
184-0493 | Richardson Road and Ripple Creek Pump Stations | 1 | 1 | 0 | 0% |  | 273733.56 | 415000 | -141266.44 | 2016-01-01 | 2022-12-31 | 2015-12-31 | 2022-06-01 | 2022-04-19 | 2022-06-01 | IR &R |  | 2021-09-21 | 210 | 240 | 2022-04-19 | 2022-05-19 | 2022-04-19 | no | 57275 | 17843 | 75118 | 165000
184-0498 | ORPS1 Pump 4 Upgrade | 1 | 1 | 0 | 0% |  | 406115.18 | 503000 | -96884.82 | 2017-01-01 | 2020-12-31 | 2017-12-31 | 2020-06-30 | 2020-04-03 | 2020-06-30 | IR &R |  | 2019-07-02 | 180 | 210 | 2019-12-29 | 2020-01-28 | 2020-04-03 | 102- A | 385000 | 91557.98 | 476557.98 | 503000
184-0521 | Bromley Tank Gravity Wall | 1 | 1 | 0 | 0% |  | 36640.18 | 50000 | -13359.82 | 2015-01-01 | 2015-12-31 | 2014-12-31 | 2017-12-31 | 2017-05-22 | 2017-12-31 | O&M |  | 2017-05-01 | 25 | 30 | 2017-05-26 | 2017-05-31 | 2017-05-22 | no | 33543.45 | 0 | 33543.45 | 50000
184-0528 | Piner Water Hauling Station Drainage | 1 | 1 | 0 | 0% |  | 33395.87 | 27000 | 6395.87 | 2014-01-01 | 2019-12-31 | 2014-12-31 | 2019-05-31 | 2019-03-29 | 2019-05-31 | IR &R |  | 2019-03-05 |  |  | 2019-03-29
184-0532 | Bromley Tank Drainage Channel | 1 | 1 | 0 | 0% |  | 26804.48 | 30000 | -3195.52 | 2018-01-01 | 2018-12-31 | 2018-09-01 | 2018-12-31 | 2018-10-01 | 2018-12-31 |  |  | 2018-09-24 | 30 | 40 | 2018-10-24 | 2018-11-03 | 2018-10-01 | no | 25676 | 0 | 25676 | 30000
185-0533 | Old Siry Rd Landslide Mitigation | 1 | 1 | 0 | 0% |  | 14597.32 | 151000 | -136402.68 | 2019-01-01 | on hold | 2019-05-31 | not complete |  | 2020-05-31 | OCB
184-0534 | TMTP and Tank Security Upgrades | 1 | 1 | 0 | 0% |  | 63742.91 | 65000 | -1257.09 | 2020-01-01 | 2021-12-31 | 2020-10-30 | 2021-07-01 | 2021-06-25 | 2021-07-01 | OCB |  | 2021-04-07 |  |  | 2021-06-25 | 2021-06-30 | 2021-06-25 | 30- C/P | 61204.71 |  | 61240.71 | 65000
184-0535 | CF Material Bins | 1 | 1 | 0 | 0% |  | 2734 | 175000 | -172266 | 2021-01-01 | 2021-12-31 | 2021-03-01 | not complete | not complete | 2021-10-31
184-0536 | Automated Meter System | 1 | 1 | 0 | 0% |  | 1149266 | 13500000 | -12350734 | 2021-01-01 | 2023-10-06 | 2021-10-22 | not complete | not complete | 2022-06-30 |  |  | 2021-10-07 | 20 years | 20 years | 107/2023 | 2041-10-07 | not complete | no | 16712733.71 |  |  | 13500000 | *project not complete
184-0613 | Cox Road and Oliver Road WMR | 1 | 1 | 0 | 0% |  | 1432700 | 1300000 | 132700 | 2013-01-01 | 2020-12-31 | 2007-05-01 | 2020-12-31 | 2019-10-29 | 2020-12-31 | IR &R |  | 2019-04-01 | 205 | 230 | 2019-10-23 | 2019-11-17 | 2019-10-29 | 21- A | 940926.6 | 5784.35 | 946710.95 | 1300000
184-0721 | St. Joseph Lane WMR | 1 | 1 | 0 | 0% |  | 274647.44 | 290000 | -15352.56 | 2011-01-01 | 2021-12-31 | 2012-03-19 | 2021-06-30 | 2021-04-26 | 2021-06-30 | IR &R |  | 2021-01-25 | 60 | 75 | 2021-03-26 | 2021-04-10 | 2021-04-26 | no | 241308 | 1536 | 242844 | 290000
184-0742 | Church Street and Faye Drive WMR | 1 | 1 | 0 | 0% |  | 250787.57 | 260000 | -9212.43 | 2013-01-01 | 2018-12-31 | 2012-12-01 | 2018-08-20 | 2018-08-20 | 2013-05-01 | IR &R |  | 2018-06-20 | 50 | 65 | 2018-08-09 | 2018-08-24 | 2018-08-20 | 7- A | 208664 | 12381.2 | 221045.2 | 260000
184-0749 | 36" Licking River Crossing Wilder | 1 | 1 | 0 | 0% |  | 435174 | 5708000 | -5272826 | 2013-01-01 | 2024-12-31 | 2012-12-29 | not complete | not complete | 2022-07-11 | IR &R- 2,200,000, SRF 2013-3,488,040
184-0750 | Sub-District M Phase 2 | 1 | 1 | 0 | 0% |  | 3405865.08 | 3400000 | 5865.08 | 2013-01-01 | 2018-12-31 | 2013-04-01 | 2018-12-31 | 2018-04-19 | 2018-12-31 |  |  |  | 150 |  |  |  | 2018-04-19 | 58- A, W, H, LD | 953445 | 80863.35 | 1034308.35 | 3400000 | *Phase 1 included in budget
184-0754 | 16" Cross Country WMR C County | 1 | 1 | 0 | 0% |  | 56567 | 850000 | -793433 | 2019-01-01 | 2024-12-31 | 2014-12-31 | not complete | not complete | 2022-06-30
184-0767 | 8" & 12" Water Main Connection- Phase 1 | 1 | 1 | 0 | 0% |  | 311787.08 | 335000 | -23212.92 | 2013-01-01 | 2019-12-31 | 2013-08-16 | 2019-12-31 | 2019-07-15 | 2019-12-31 | IR &R |  | 2019-05-13 | 60 | 90 | 2019-07-12 | 2019-08-11 | 2019-07-15 | 9- A | 246271 | -518 | 245753 | 335000
184-0776 | 24inch Cross Country WMR project | 1 | 1 | 0 | 0% |  | 1094763.59 | 1200000 | -105236.41 | 2021-03-18 | 2023-03-18 | 2014-10-08 | 2020-02-28 | 2019-08-12 | 2020-02-28 | BAN 2021- 200,00, SRF 2016 |  | 2019-04-08 | 90 | 120 | 2019-07-02 | 2019-09-05 | 2019-08-12 | 39- W, H | 980040 | 12300 | 992340 | 1200000
184-0795 | Madison Pike Phase 2 WMR | 1 | 1 | 0 | 0% |  | 1384999.5 | 1675000 | -290000.5 | 2017-04-19 | 2019-04-19 | 2014-04-01 | 2018-12-31 | 2018-01-29 | 2018-12-31 | BAN 2017- 1,350,000 |  | 2017-10-11 | 120 | 150 | 2018-02-07 | 2018-03-09 | 2018-01-29 | no | 1270875 | 39390.74 | 1231484.26 | 1675000
184-0807 | Edgewood WMR Beech, Buckner Wildrose & Elmwood | 1 | 1 | 0 | 0% |  | 809449.05 | 900000 | -90550.95 | 2017-04-19 | 2019-04-19 | 2014-12-31 | 2018-01-31 | 2017-11-07 | 2018-01-31 | BAN 2017 & SRF 2015 |  | 2017-06-26 | 170 | 200 | 2017-12-13 | 2018-01-12 | 2017-11-07 | 1- U | 785328 | 65472.3 | 719855.7 | 900000
184-0811 | Newport WMR 15th,16th, 17th, Parkview & Main | 1 | 1 | 0 | 0% |  | 23155.8 | 830000 | -806844.2 | 2015-11-01 | on hold | 2014-11-30 | on hold |  | 2018-11-30 | BAN 2017 & SRF
184-0812 | Parker and Ridge WMR | 1 | 1 | 0 | 0% |  | 622001.63 | 640000 | -17998.37 | 2017-04-19 | 2019-04-19 | 2014-12-01 | 2020-03-01 | 2019-07-29 | 2020-03-01 | BAN 2017 |  | 2019-03-18 | 120 | 150 | 2019-07-16 | 2019-08-15 | 2019-07-29 | 24- W | 521127.02 | 5272.7 | 526399.72 | 640000
184-0813 | N. Ft Thomas Phase II 2015 WMR | 1 | 1 | 0 | 0% |  | 487476.62 | 510000 | -22523.38 | 2015-01-01 | 2015-12-31 | 2014-12-31 | 2019-08-31 | 2015-08-21 | 2019-08-31
184-0824 | Latonia Lakes | 1 | 1 | 0 | 0% |  | 1583143.88 | 1856415 | -273271.12 | 2015-01-01 | 2018-12-31 | 2015-06-30 | 2018-06-30 |  | 2018-06-30 | SRF & OCB
184-0826 | Lincoln Avenue WMR (Bellevue) | 1 | 1 | 0 | 0% |  | 1060977.1 | 1075000 | -14022.9 | 2017-04-19 | 2019-04-19 | 2015-10-14 | 2017-12-31 | 2017-07-06 | 2017-12-31 | BAN 2017 |  | 2017-02-13 | 180 | 210 | 2017-08-12 | 2017-09-11 | 2017-07-06 | 1- A | 958399 | 17862.39 | 976261.39 | 1075000
184-0830 | Riggs Avenue Phase 2 WMR | 1 | 1 | 0 | 0% |  | 348251.7 | 375000 | -26748.3 | 2017-04-19 | 2019-04-19 | 2015-12-31 | 2018-02-16 | 2017-11-20 | 2018-02-16 | BAN 2017 |  | 2017-08-28 | 75 | 90 | 2017-11-11 | 2017-11-26 | 2017-11-20 | 10- A | 303348.5 | -4505.5 | 298483 | 375000
184-0836 | Blossom Lane WMR | 1 | 1 | 0 | 0% |  | 779110.75 | 895000 | -115889.25 | 2016-01-01 | 2016-12-31 | 2016-03-07 | 2018-08-01 | 2017-10-31 | 2018-08-01 | BAN 2017 |  | 2017-07-17 | 120 | 150 | 2017-11-14 | 2017-12-14 | 2017-10-31 | no | 755783 | -58481.3 | 697301.7 | 895000
184-0837 | Ervin Terrace & 10th Ave WMR | 1 | 1 | 0 | 0% |  | 478851.34 | 470000 | 8851.34 | 2017-04-19 | 2019-04-19 | 2016-10-07 | 2020-06-30 | 2019-12-04 | 2020-06-30 | BAN 2017 |  | 2019-09-16 | 65 | 95 | 2019-11-20 | 2019-12-20 | 2019-12-04 | 168 (final)- C | 414113 | 24563.5 | 438676 | 470000
184-0838 | Echo Hills and Licking Pike WMR | 1 | 1 | 0 | 0% |  | 771044 | 790000 | -18956 | 2017-04-19 | 2019-04-19 | 2016-07-31 | 2019-12-31 | 2018-12-10 | 2019-12-31 | BAN 2017 |  | 2018-05-14 | 130 | 160 | 2018-09-21 | 2018-10-21 | 2018-12-10 | 61- A, LD | 679720 | 705.98 | 680425.98 | 790000
184-0839 | Latonia Avenue WMR | 1 | 1 | 0 | 0% |  | 197668.87 | 215000 | -17331.13 | 2017-04-19 | 2019-04-19 | 2016-07-12 | 2017-12-31 | 2017-06-23 | 2017-12-31 | BAN 2017 |  | 2017-04-24 | 60 | 75 | 2017-06-23 | 2017-07-08 | 2017-06-23 | no | 172250 | -6134.5 | 166115.5 | 215000
184-0840 | Ann Street WMR | 1 | 1 | 0 | 0% |  | 524259.08 | 530000 | -5740.92 | 2021-03-18 | 2023-03-18 | 2016-03-07 | 2020-01-07 | 2019-09-06 | 2020-01-07 | BAN 2021 |  | 2019-04-10 | 125 | 140 | 2019-08-13 | 2019-08-28 | 2019-09-06 | 34- U, A | 447518 | -8129 | 439389 | 530000
184-0842 | Perimeter Dr- Phase 1 WMR | 1 | 1 | 0 | 0% |  | 251739.49 | 255000 | -3260.51 | 2017-04-19 | 2019-04-19 | 2016-07-01 | 2018-02-01 | 2017-07-17 | 2018-02-01 | BAN 2017 |  | 2017-05-15 | 60 | 75 | 2017-07-14 | 2017-07-29 | 2017-07-17 | 2- U | 213216 | -1452.26 | 211763.74 | 255000
184-0843 | Perimeter Dr- Phase 2 WMR | 1 | 1 | 0 | 0% |  | 255518.25 | 270000 | -14481.75 | 2017-04-19 | 2019-04-19 | 2016-07-01 | 2018-06-30 | 2018-02-02 | 2018-06-30 | BAN 2017 |  | 2017-11-13 | 75 | 90 | 2018-01-27 | 2018-02-11 | 2018-02-02 | 24- W | 229756 | -7049 | 222707 | 270000
184-0848 | Dudley Road and Lyndale Court WMR | 1 | 1 | 0 | 0% |  | 772048.69 | 831490 | -59441.31 | 2011-09-22 | 2013-09-22 | 2016-10-14 | 2019-06-30 | 2018-11-12 | 2019-06-30 | BAN 2017 |  | 2018-05-07 | 110 | 140 | 2018-08-25 | 2018-09-24 | 2018-11-12 | 57- A, LD | 636524 | 70338 | 706862 | 831490
184-0849 | Wedgewood Drive and Clubhouse Drive WMR | 1 | 1 | 0 | 0% |  | 397238.69 | 415000 | -17761.31 | 2017-04-19 | 2019-04-19 | 2016-11-01 | 2017-12-31 | 2017-06-28 | 2017-12-31 | BAN 2017 |  | 2017-03-13 | 110 | 130 | 2017-07-01 | 2017-07-21 | 2017-06-28 | no | 333000 | 1911.17 | 334911.17 | 415000
184-0850 | Brookwood Drive WMR - Central Phase | 1 | 1 | 0 | 0% |  | 171664.15 | 175000 | -3335.85 | 2017-04-19 | 2019-04-19 | 2016-12-01 | 2017-12-31 | 2017-07-25 | 2017-12-31 | BAN 2017 |  | 2017-06-14 | 35 | 42 | 2017-07-19 | 2017-07-26 | 2017-07-25 | 9- U, W, H | 134610 | 5246 | 139856 | 175000
184-0851 | Hudson Avenue WMR | 1 | 1 | 0 | 0% |  | 119903.96 | 130000 | -10096.04 | 2017-04-19 | 2019-04-19 | 2016-12-15 | 2017-12-31 | 2017-03-27 | 2017-12-31 | BAN 2017 |  | 2017-02-27 | 28 | 35 | 2017-03-27 | 2017-04-03 | 2017-03-27 | no | 97375 | 1765 | 99140 | 130000
184-0852 | Buttermilk Pike WMR | 1 | 1 | 0 | 0% |  | 477179.52 | 485000 | -7820.48 | 2017-04-19 | 2019-04-19 | 2016-12-23 | 2018-06-30 | 2018-05-08 | 2018-06-30 | BAN 2017 |  | 2018-01-22 | 85 | 100 | 2018-04-17 | 2018-05-02 | 2018-05-08 | 21- A | 403786.3 | 24734.5 | 428520.8 | 485000
184-0853 | McHenry Street and Clifton Avenue WMR | 1 | 1 | 0 | 0% |  | 91361.2 | 90000 | 1361.2 | 2017-04-19 | 2019-04-19 | 2017-03-01 | 2017-12-31 | 2017-05-31 | 2017-12-31 | BAN 2017 |  | 2017-04-26 | 28 | 35 | 2017-05-24 | 2017-05-31 | 2017-05-31 | 11- U | 72000 | 8476.07 | 80476.07 | 90000
184-0854 | McKinney St and 9th Ave WMR | 1 | 1 | 0 | 0% |  | 100952.81 | 110000 | -9047.19 | 2017-04-19 | 2019-04-19 | 2017-03-31 | 2017-12-31 | 2017-08-30 | 2017-12-31 | BAN 2017 |  | 2017-08-09 | 21 | 28 | 2017-08-30 | 2017-09-06 | 2017-08-30 | no | 81590 | -12.37 | 81577.63 | 110000
184-0855 | Arlington Road WMR | 1 | 1 | 0 | 0% |  | 206881.96 | 210000 | -3118.04 | 2017-04-19 | 2019-04-19 | 2017-07-01 | 2020-06-30 | 2018-09-18 | 2020-06-30 | BAN 2017 |  | 2018-07-16 | 40 | 50 | 2018-08-25 | 2018-09-04 | 2018-09-18 | 28- C | 172736 | -8888.5 | 163847.5 | 210000
184-0856 | Lorup Avenue WMR | 1 | 1 | 0 | 0% |  | 181050.71 | 195000 | -13949.29 | 2017-04-19 | 2019-04-19 | 2017-04-14 | 2017-12-31 | 2017-08-18 | 2017-12-31 | BAN 2017 |  | 2017-07-05 | 40 | 50 | 2017-08-14 | 2017-08-24 | 2017-08-18 | 7- W | 159191 | -1761.1 | 157429.9 | 195000
184-0857 | Caldwell Drive MWR | 1 | 1 | 0 | 0% |  | 122740.67 | 130000 | -7259.33 | 2017-04-19 | 2019-04-19 | 2017-12-31 | 2018-06-30 | 2018-05-07 | 2018-06-30 | BAN 2017 |  | 2018-04-09 | 35 | 45 | 2018-05-14 | 2018-05-24 | 2018-05-07 | no | 108082 | -1930 | 106152 | 130000
184-0858 | Erlanger Road Phase 2 WMR | 1 | 1 | 0 | 0% |  | 282886.7 | 325000 | -42113.3 | 2017-04-19 | 2019-04-19 | 2017-08-01 | 2018-12-31 | 2018-07-30 | 2018-12-31 | BAN 2017 |  | 2018-06-04 | 50 | 70 | 2018-07-24 | 2018-08-13 | 2018-07-30 | 7- A | 260558.22 | -10205.14 | 250353.08 | 325000
184-0859 | Birch Drive WMR | 1 | 1 | 0 | 0% |  | 134075.67 | 160000 | -25924.33 | 2017-04-19 | 2019-04-19 | 2017-08-02 | 2018-12-31 | 2018-05-15 | 2018-12-31 | BAN 2017 |  | 2018-04-16 | 45 | 60 | 2018-05-31 | 6/15/20118 | 2018-05-15 | no | 126096 | -11700.68 | 114395.32 | 160000
184-0860 | Amsterdam Road WMR- HDPE | 1 | 1 | 0 | 0% |  | 365597.21 | 400000 | -34402.79 | 2017-04-19 | 2019-04-19 | 2017-10-31 | 2020-12-31 | 2020-07-08 | 2020-12-31 | BAN 2017 |  | 2020-04-13 | 90 | 120 | 2020-07-12 | 2020-08-11 | 2020-07-08 | 2- A | 329521.25 | -4632.42 | 324888.83 | 400000
184-0861 | Stonehouse Road WMR | 1 | 1 | 0 | 0% |  | 731576.42 | 770000 | -38423.58 | 2017-04-19 | 2019-04-19 | 2017-09-29 | 2020-07-01 | 2019-10-10 | 2020-07-01 | BAN 2017 |  | 2019-08-05 | 100 | 130 | 2019-11-13 | 2019-12-13 | 2019-10-10 | no | 661170 | 664.5 | 661834.5 | 770000
184-0862 | Highland Ave WMR | 1 | 1 | 0 | 0% |  | 132335.33 | 135000 | -2664.67 | 2017-04-19 | 2019-04-19 | 2017-12-01 | 2018-12-31 | 2018-04-06 | 2018-12-31 | BAN 2017 |  | 2018-03-05 | 35 | 45 | 2018-04-09 | 2018-04-19 | 2018-04-06 | no | 108454 | 4485.21 | 112939.21 | 135000
184-0863 | Amsterdam Road WMR (Morris to Redwood) | 1 | 1 | 0 | 0% |  | 168443.17 | 180000 | -11556.83 | 2017-04-19 | 2019-04-19 | 2017-11-10 | 2018-12-31 | 2018-04-20 | 2018-12-31 | BAN 2017 |  | 2018-03-13 | 40 | 55 | 2018-04-22 | 2018-05-07 | 2018-04-20 | no | 151075 | 181 | 151256 | 180000
184-0864 | Winters Lane WMR | 1 | 1 | 0 | 0% |  | 835220.16 | 870000 | -34779.84 | 2017-04-19 | 2019-04-19 | 2017-12-31 | 2018-12-31 | 2018-08-29 | 2018-12-31 | BAN 2017 |  | 2018-05-14 | 135 | 165 | 2018-09-26 | 2018-10-26 | 2018-08-29 | no | 761680 | -5875.9 | 755804.1 | 870000
184-0865 | Ripple Creek Road WMR | 1 | 1 | 0 | 0% |  | 196942.87 | 235000 | -38057.13 | 2017-04-19 | 2019-04-19 | 2018-02-01 | 2018-12-31 | 2018-07-09 | 2018-12-31 | BAN 2017 |  | 2018-05-29 | 40 | 55 | 2018-07-08 | 2018-07-23 | 2018-07-09 | 4- U, A | 185260 | -13624.1 | 171635.9 | 235000
184-0866 | Pentland Place WMR | 1 | 1 | 0 | 0% |  | 222811.29 | 255000 | -32188.71 | 2017-04-19 | 2019-04-19 | 2018-03-16 | 2018-12-31 | 2018-09-26 | 2018-12-31 | BAN 2017 | [6 empty] | 2018-09-26 |  |  |  |  | 255000 | *coordinated with city
184-0867 | Alexander Circle (Cochran Avenue) WMR | 1 | 1 | 0 | 0% |  | 205311.13 | 355000 | -149688.87 | 2017-04-19 | 2019-04-19 | 2018-05-18 | 2020-11-30 | 2019-07-26 | 2020-11-30 | BAN 2017 |  | 2018-11-01 | 70 | 90 | 2019-01-10 | 2019-01-30 | 2019-07-26 | 176- C | 290641.6 | -4959.5 | 285682.1 | 355000
184-0868 | Brookwood Drive WMR - North Phase | 1 | 1 | 0 | 0% |  | 105962.87 | 120000 | -14037.13 | 2017-04-19 | 2019-04-19 | 2018-03-01 | 2018-12-31 | 2018-04-30 | 2018-12-31 | BAN 2017 |  | 2018-03-26 | 35 | 42 | 2018-04-30 | 2018-05-07 | 2018-04-30 | no | 93075 | 1156 | 94231 | 120000
184-0869 | Highland Ave WMR (Oak to Floral) | 1 | 1 | 0 | 0% |  | 67450.23 | 135000 | -67549.77 | 2017-04-19 | 2019-04-19 | 2018-05-01 | 2018-12-31 | 2018-08-17 | 2018-12-31 | BAN 2017 |  | 2018-07-09 | 35 | 45 | 2018-08-13 | 2018-08-23 | 2018-08-17 | 3- A | 111040 | -1710.25 | 109329.75 | 135000
184-0870 | Sunset Drive WMR | 1 | 1 | 0 | 0% |  | 178270.51 | 185000 | -6729.49 | 2017-04-19 | 2019-04-19 | 2018-06-30 | 2018-12-31 | 2018-10-03 | 2018-12-31 | BAN 2017 |  | 2018-08-20 | 40 | 50 | 2018-08-29 | 2018-08-09 | 2018-10-03 | 4- W, H | 153516.45 | 91.65 | 153608.1 | 185000
184-0871 | N. Ft. Thomas Ave WMR (Covert to Lincoln) | 1 | 1 | 0 | 0% |  | 603432.2 | 665000 | -61567.8 | 2017-04-19 | 2019-04-19 | 2018-08-17 | 2020-01-31 | 2019-07-08 | 2020-01-31 | BAN 2017 |  | 2019-04-01 | 100 | 120 | 2019-07-10 | 2019-07-30 | 2019-07-08 | no | 549575 | -16988 | 532587 | 665000
184-0872 | Narrows and Nelson WMR Relocation | 1 | 1 | 0 | 0% |  | 53029.56 | 75000 | -21970.44 | 2017-04-19 | 2019-04-19 | 2018-09-01 | 2018-09-01 |  | 2019-03-05 | BAN 2017 | [11 empty] | 75000 | *coordinated with city
184-0873 | Jackson Road WMR | 1 | 1 | 0 | 0% |  | 198033.28 | 205000 | -6966.72 | 2017-04-19 | 2019-04-19 | 2018-12-13 | 2020-06-30 | 2020-03-11 | 2020-06-30 | BAN 2017 |  | 2020-01-06 | 40 | 60 | 2020-02-15 | 2020-03-03 | 2020-03-11 | no | 168373 | 2487 | 170860 | 205000
184-0874 | Janet Drive WMR | 1 | 1 | 0 | 0% |  | 224671.86 | 220000 | 4671.86 | 2017-04-19 | 2019-04-19 | 2018-09-30 | 2019-12-31 | 2019-07-15 | 2019-12-31 | BAN 2017 |  | 2019-05-20 | 50 | 65 | 2019-07-09 | 2019-07-24 | 2019-07-15 | 11- U, A | 181055 | 5534.5 | 186539.5 | 220000
184-0875 | Hillview Drive WMR (Dixie to Longmeadow) | 1 | 1 | 0 | 0% |  | 235735.54 | 300000 | -64264.46 | 2017-04-19 | 2019-04-19 | 2018-11-08 | 2019-12-31 | 2019-09-18 | 2019-12-31 | BAN 2017 |  | 2019-08-05 | 50 | 70 | 2019-09-24 | 2019-10-14 | 2019-09-18 | no | 243393.5 | -649.25 | 242744.25 | 300000
184-0876 | Brookwood and Oakridge Drive WMR | 1 | 1 | 0 | 0% |  | 208943.56 | 230000 | -21056.44 | 2017-04-19 | 2019-04-19 | 2019-06-19 | 2020-06-30 | 2020-02-07 | 2020-06-30 | BAN 2017 |  | 2019-11-18 | 65 | 90 | 2020-01-22 | 2020-02-16 | 2020-02-07 | 26- A | 178352.1 | 835.35 | 179187.45 | 230000
184-0877 | Valleywood Court & Hickory Lane WMR | 1 | 1 | 0 | 0% |  | 181446.8 | 200000 | -18553.2 | 2017-04-19 | 2019-04-19 | 2019-12-31 | 2020-12-31 | 2020-07-22 | 2020-12-31 | BAN 2017 |  | 2020-06-15 | 45 | 60 | 2020-07-30 | 2020-08-14 | 2020-07-22 | no | 154630 | -5382 | 149248 | 200000
184-0878 | Covert Run to Lincoln WMR | 1 | 1 | 0 | 0% |  | 356171.93 | 360000 | -3828.07 | 2017-04-19 | 2019-04-19 | 2018-12-31 | 2021-06-30 | 2021-01-21 | 2021-06-30 | BAN 2017 |  | 2020-11-02 | 60 | 90 | 2021-01-01 | 2021-01-31 | 2021-01-21 | no | 282969.1 | 2948.07 | 285917.17 | 360000
184-0879 | Rossmoyne, Druid, Warwick WMR | 1 | 1 | 0 | 0% |  | 261460.04 | 300000 | -38539.96 | 2021-03-18 | 2023-03-18 | 2018-12-31 | 2020-01-31 | 2019-04-18 | 2020-01-31 | BAN 2021 |  | 2019-03-18 | 50 | 70 | 2019-05-07 | 2019-05-27 | 2019-04-18 | no | 267911 | -6757 | 261154 | 300000
184-0880 | Parkway Dr WMR | 1 | 1 | 0 | 0% |  | 460665.35 | 155000 | 305665.35 | 2017-04-19 | 2019-04-19 | 2019-03-04 | 2019-06-30 | 2019-06-04 | 2019-06-30 | BAN 2017 |  | 2019-04-30 | 30 | 40 | 2019-05-29 | 2019-06-08 | 2019-06-04 | 8- W | 124944 | 2212.3 | 127156.3 | 155000
184-0881 | Ash Street WMR | 1 | 1 | 0 | 0% |  | 128564.54 | 140000 | -11435.46 | 2021-03-18 | 2023-03-18 | 2019-05-01 | 2019-12-31 | 2019-08-09 | 2019-12-31 | BAN 2021 |  | 2019-07-15 | 28 | 35 | 2019-08-12 | 2019-08-19 | 2019-08-09 | no | 114318 | 310 | 114628 | 140000
184-0882 | Pieck Drive and West Henry Clay Ave WMR | 1 | 1 | 0 | 0% |  | 197223.46 | 200000 | -2776.54 | 2021-03-18 | 2023-03-18 | 2019-04-19 | 2021-01-22 | 2019-06-27 | 2021-01-22 | BAN 2021 |  | 2019-05-28 | 40 | 50 | 2019-07-07 | 2019-07-17 | 2019-06-27 | no | 162805.4 | 5359.4 | 168164.8 | 200000
184-0883 | Sunset Drive & Allen Court WMR | 1 | 1 | 0 | 0% |  | 198805.31 | 210000 | -11194.69 | 2021-03-18 | 2023-03-18 | 2019-06-01 | 2020-01-31 | 2019-09-24 | 2020-01-31 | BAN 2021 |  | 2019-08-08 | 45 | 55 | 2019-09-22 | 2019-10-02 | 2019-09-24 | 2- W | 172758.6 | 671.1 | 173429.7 | 210000
184-0884 | Thornton & Tower View WMR | 1 | 1 | 0 | 0% |  | 152350.93 | 155000 | -2649.07 | 2021-03-18 | 2023-03-18 | 2019-05-01 | 2020-12-31 | 2020-09-14 | 2020-12-31 | BAN 2021 |  | 2020-07-15 | 45 | 60 | 2020-08-29 | 2020-09-13 | 2020-09-14 | no | 117589 | 5661 | 123250 | 155000
184-0885 | Amsterdam Road WMR (Arlington to Montauge) | 1 | 1 | 0 | 0% |  | 329969.79 | 370000 | -40030.21 | 2021-03-18 | 2023-03-18 | 2019-06-01 | 2020-06-30 | 2020-03-09 | 2020-06-30 | BAN 2021 |  | 2020-01-06 | 45 | 60 | 2020-02-20 | 2020-03-06 | 2020-03-09 | 1- A | 302690 | -1601.07 | 301088.93 | 370000
184-0886 | Highland Avenue WMR | 1 | 1 | 0 | 0% |  | 290542.53 | 430000 | -139457.47 | 2021-03-18 | 2023-03-18 | 2019-05-31 | 2020-01-31 | 2019-10-10 | 2020-01-31 | BAN 2021 |  | 2019-07-15 | 80 | 100 | 2019-10-03 | 2019-10-23 | 2019-10-10 | 7- W | 389360 | -4244 | 385116 | 430000
184-0887 | Wayskin, Marnoam, Sipple, & Dave WMR | 1 | 1 | 0 | 0% |  | 501611.05 | 540000 | -38388.95 | 2019-01-01 | 2021-12-31 | 2019-06-30 | 2020-08-01 | 2020-02-12 | 2020-08-01 | IR &R |  | 2019-10-28 | 120 | 150 | 2020-02-25 | 2020-03-26 | 2020-02-12 | no | 444996.2 | -12096 | 432900.2 | 540000
184-0888 | Fourth Street MWR (Scott to Greenup) | 1 | 1 | 0 | 0% |  | 229237.19 | 300000 | -70762.81 | 2021-03-18 | 2023-03-18 | 2019-04-01 | 2019-12-31 | 2019-07-31 | 2019-12-31 | BAN 2021 |  | 2019-06-17 | 45 | 60 | 2019-08-01 | 2019-08-16 | 2019-07-31 | 2- A | 257295.6 | 1033.6 | 258329.2 | 300000
184-0889 | Old Alexandria Pike (CR1557) WMR | 1 | 1 | 0 | 0% |  | 128592.29 | 160000 | -31407.71 | 2021-03-18 | 2023-03-18 | 2019-05-31 | 2020-05-31 | 2019-12-20 | 2020-05-31 | BAN 2021 |  | 2019-12-03 | 30 | 45 | 2020-01-01 | 2020-01-16 | 2019-12-20 | 2- A | 132175 | 3659 | 135834 | 160000
184-0890 | E. Main St WMR | 1 | 1 | 0 | 0% |  | 622877.95 | 650000 | -27122.05 | 2021-03-18 | 2023-03-18 | 2019-06-30 | 2020-12-31 | 2020-07-20 | 2020-12-31 | BAN 2021 |  | 2020-06-01 | 90 | 120 | 2020-08-30 | 2020-09-29 | 2020-07-20 | no | 565009.5 | 4000 | 569009.5 | 650000
184-0891 | Ridge and W. Orchard Road WMR | 1 | 1 | 0 | 0% |  | 256194.45 | 270000 | -13805.55 | 2021-03-18 | 2023-03-18 | 2019-06-30 | 2020-12-31 | 2020-07-16 | 2020-12-31 | BAN 2021 | [6 empty] | 2020-07-16 |  |  |  |  | 270000 | *coordinated with city
184-0892 | Barma Drive WMR | 1 | 1 | 0 | 0% |  | 74384.52 | 90000 | -15615.48 | 2021-03-18 | 2023-03-18 | 2019-10-01 | 2020-04-01 | 2019-11-11 | 2020-04-01 | BAN 2021 |  | 2019-10-21 | 30 | 45 | 2019-11-20 | 2019-12-05 | 2019-11-11 | no | 61984.8 | -860 | 61124.8 | 90000
184-0893 | Crowell & Eustace WMR | 1 | 1 | 0 | 0% |  | 463036.62 | 470000 | -6963.38 | 2021-03-18 | 2023-03-18 | 2020-04-16 | 2020-12-31 | 2020-11-09 | 2020-12-31 | BAN 2021 |  | 2020-08-10 | 90 | 105 | 2020-11-08 | 2020-11-23 | 2020-11-09 | 11- A | 405396.95 | -1256.4 | 404140.55 | 470000
184-0894 | Thatcher Ct & Paul Ln WMR | 1 | 1 | 0 | 0% |  | 225676.29 | 240000 | -14323.71 | 2017-04-19 | 2019-04-19 | 2020-05-04 | 2020-12-31 | 2020-08-21 | 2020-12-31 | BAN 2017 |  | 2020-06-30 | 55 | 70 | 2020-08-24 | 2020-09-08 | 2020-08-21 | no | 188724.7 | 3761.15 | 192485.85 | 240000
184-0895 | Persimmon, etc WMR | 1 | 1 | 0 | 0% |  | 518929.85 | 545000 | -26070.15 | 2021-03-18 | 2023-03-18 | 2020-06-01 | 2021-06-30 | 2021-02-26 | 2021-06-30 | BAN 2021 |  | 2020-10-05 | 140 | 160 | 2021-02-22 | 2021-03-14 | 2021-02-26 | no | 472992.5 | -12107.38 | 460815.12 | 545000
184-0896 | Lexington & Woodward WMR | 1 | 1 | 0 | 0% |  | 509998.96 | 510000 | -1.04 | 2021-03-18 | 2023-03-18 | 2020-06-30 | 2021-12-31 | 2021-08-04 | 2021-12-31 | BAN 2021 |  | 2021-04-12 | 100 | 120 | 2021-07-21 | 2021-08-10 | 2021-08-04 | 14- W, H, A | 441707 | -2817 | 438890 | 510000
184-0897 | E. Main St WMR - Phase 2 | 1 | 1 | 0 | 0% |  | 447493.38 | 490000 | -42506.62 | 2021-03-18 | 2023-03-18 | 2020-06-30 | 2021-12-31 | 2021-09-10 | 2021-12-31 | BAN 2021 |  | 2021-06-14 | 90 | 120 | 2021-09-12 | 2021-10-12 | 2021-09-10 | no | 417598.56 | 3114.3 | 420712.86 | 490000
184-0899 | Greenup Street WMR | 1 | 1 | 0 | 0% |  | 60292.47 | 65000 | -4707.53 | 2017-04-19 | 2019-04-19 | 2020-09-01 | 2020-12-31 | 2020-11-03 | 2020-12-31 | BAN 2017 |  | 2020-10-14 | 30 | 45 | 2020-11-13 | 2020-11-28 | 2020-11-03 | no | 52015 | -325 | 51690 | 65000
184-0900 | Robin Ln WMR | 1 | 1 | 0 | 0% |  | 128515.53 | 140000 | -11484.47 | 2017-04-19 | 2019-04-19 | 2020-11-30 | 2021-06-30 | 2021-04-20 | 2021-06-30 | BAN 2017 |  | 2021-03-15 | 40 | 60 | 2021-04-24 | 2021-05-14 | 2021-04-20 | no | 114484 | -5840 | 108644 | 140000
184-0901 | Wayman Branch WMR | 1 | 1 | 0 | 0% |  | 471680.43 | 500000 | -28319.57 | 2021-01-01 | 2023-03-28 | 2021-01-07 | 2022-06-30 | 2021-11-17 | 2022-06-30 | BAN 2021 |  | 2021-08-30 | 60 | 80 | 2021-10-29 | 2021-11-18 | 2021-11-17 | 19- A | 434310 | -1265 | 433045 | 500000
184-0902 | Sagebrush & Shadyside WMR | 1 | 1 | 0 | 0% |  | 394485.2 | 420000 | -25514.8 | 2021-03-18 | 2023-03-18 | 2020-12-31 | 2021-12-31 | 2021-06-08 | 2021-12-31 | BAN 2021 |  | 2021-03-15 | 80 | 100 | 2021-06-03 | 2021-06-23 | 2021-06-08 | 6- W, H | 362029.85 | -17693.64 | 344336.21 | 420000
184-0903 | Darlas Dr WMR | 1 | 1 | 0 | 0% |  | 19383 | 285000 | -265617 | 2021-03-18 | 2023-03-18 | 2021-05-07 | not complete | not complete | 2022-06-06 | BAN 2021
184-0904 | Chapman Lane WMR | 1 | 1 | 0 | 0% |  | 177151.09 | 190000 | -12848.91 | 2021-01-01 | 2021-12-31 | 2021-05-07 | 2021-12-31 | 2021-09-30 | 2021-12-31 | BAN 2017 |  | 2021-08-16 | 30 | 40 | 2021-09-15 | 2021-09-25 | 2021-09-30 | no | 151916 | 1858 | 153774 | 190000
184-0905 | Willowbrook Lane WMR | 1 | 1 | 0 | 0% |  | 194066.03 | 210000 | -15933.97 | 2021-03-18 | 2023-03-18 | 2021-05-17 | 2021-12-31 | 2021-09-20 | 2021-12-31 | BAN 2021 |  | 2021-08-16 | 30 | 40 | 2021-09-15 | 2021-09-25 | 2021-09-20 | no | 169520 | -1530 | 167990 | 210000
184-0907 | Joyce Avenue WMR | 1 | 1 | 0 | 0% |  | 99912.61 | 110000 | -10087.39 | 2021-03-18 | 2023-03-18 | 2021-09-01 | 2021-12-31 | 2021-11-17 | 2021-12-31 | BAN 2021 |  | 2021-10-18 | 28 | 35 | 2021-11-15 | 2021-11-22 | 2021-11-17 | no | 84141 | 1685 | 85826 | 110000
184-4002 | Plant Metering Upgrades | 1 | 1 | 0 | 0% |  | 46553 | 300000 | -253447 | 2021-03-18 | 2023-03-18 | 2018-06-30 | not complete | not complete | 2022-05-01 | BAN 2021
184-4003 | SCADA improvements | 1 | 1 | 0 | 0% |  | 1113352 | 3938969 | -2825617 | 2021-03-18 | 2023-03-18 | 2016-12-06 | not complete | not complete | 2022-06-29 | BAN 2021- 710,000, SRF 2016 |  | 2020-07-06 | 180 | 210 | 2021-01-02 | 2021-02-01 | 2021-04-03 | 456- C, P | 671031 | 2500 | 673531 | 900000
184-4005 | TMTP Concrete Flow Meter Pit | 1 | 1 | 0 | 0% |  | 51450.73 | 60000 | -8549.27 | 2017-04-19 | 2019-04-19 | 2017-11-01 | 2018-06-30 | 2018-01-29 | 2018-06-30 | BAN 2017 |  | 2018-01-08 | 30 | 45 | 2018-02-22 | 2018-03-09 | 2018-01-29 | no | 39210 | 0 | 39210 | 60000
184-4006 | FTTP Phase 2 Basin Improvements | 1 | 1 | 0 | 0% |  | 4553618 | 6000000 | -1446382 | 2021-03-18 | 2023-03-18 | 2018-06-30 | not complete | not complete | 2022-06-01 | BAN 2021- 2,065,000, SRF- 3,935,000 |  | 2021-06-01 | 660 | 730 | 2023-03-23 | 2023-06-01 | not complete |  | 5584000 |  |  | 6000000 | *project not complete
184-4008 | FTTP Residuals Handling Improvements | 1 | 1 | 0 | 0% |  | 2705485 | 3000000 | -294515 | 2021-03-18 | 2023-03-18 | 2018-06-30 | not complete | 2022-06-13 | 2022-06-29 | BAN 2021 |  | 2021-01-04 | 420 | 450 | 2022-02-28 | 2022-03-30 | 2022-06-13 | 169- C | 2177000 | 232302.33 | 2409302.33 | 3000000
184-4010 | TMTP - PAC & UV Replacement | 1 | 1 | 0 | 0% |  | 123838 | 1615000 | -1491162 | 2018-01-01 | 2024-12-31 | 2018-06-30 | not complete | not complete | 2022-03-22 | future BAN
184-4012 | MPTP Clearwell Rehab and Painting | 1 | 1 | 0 | 0% |  | 761984.61 | 743923 | 18061.61 | 2017-04-19 | 2019-04-19 | 2018-06-30 | 2022-06-30 | 2020-07-10 | 2022-06-30 | BAN 2017 |  | 2020-03-16 | 90 | 105 | 2020-06-14 | 2020-06-29 | 2020-07-10 | 26- A | 647000 | 35418.59 | 682418.59 | 743923
184-4013 | Taylor Mill Pump Station Backup Generator | 1 | 1 | 0 | 0% |  | 87497 | 6600000 | -6512503 | 2018-01-01 | 2020-12-31 | 2018-11-01 | not complete | not complete | 2021-06-30 | future BAN- 1,535,000, SRF 2020- 4,065,000
184-4014 | Central Facility Standby Power | 1 | 1 | 0 | 0% |  | 420130.89 | 400000 | 20130.89 | 2011-09-22 | 2013-09-22 | 2018-12-31 | 2020-12-31 | 2020-03-27 | 2020-12-31 | BAN 2011 |  | 2019-06-05 | 270 | 300 | 2020-03-01 | 2020-03-31 | 2020-03-27 | 150- C, P | 375620 | 1463.05 | 377083.5 | 400000
184-4016 | MPTP Actiflo Upgrades | 1 | 1 | 0 | 0% |  | 103359 | 828000 | -724641 | 2020-01-01 | 2024-12-31 | 2020-11-30 | not complete | not complete | 2022-06-01
184-4017 | FTTP Old Clearwell Baffle Replacement | 1 | 1 | 0 | 0% |  | 97463 | 750000 | -652537 | 2021-01-01 | 2024-12-31 | 2020-12-31 | not complete | not complete | 2022-06-30
90089797
Note on R6: Stacey Kampsen: Future BAN - took out of BAn 2017 in 2018
Note on R31: Stacey Kampsen: Future BAN - moved out of BAn 2017 in 2018
Note on R37: Stacey Kampsen: moved to BAN 2009 in 2018
Note on R99: Stacey Kampsen: future BAN

## Schedule G1 Final
Project Number | Project Title/ Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
184-0475 | MPTP Raw Water Line | [5 empty] | 189498.18 | 1000000 | -810501.82 | 2013-01-01 | on hold | 2013-12-31 | on hold
184-0477 | FTTP Floc/Sed Basins 2 & 3 | [5 empty] | 2423261.12 | 2423261.12 | 0 | 2011-09-22 | 2013-09-22 | 2013-06-01 | 2017-05-31
184-0478 | FTTP Laboratory Generator | [5 empty] | 132228.25 | 132228.25 | 0 | 2011-09-22 | 2013-09-22 | 2013-10-07 | 2019-12-31
184-0486 | ORPS2 Rehabilitation | [5 empty] | 1805455.68 | 1805455.68 | 0 | 2016-07-01 | 2019-04-19 | 2016-07-01 | 2018-01-17
184-0487 | Replace Lumley Tank | [5 empty] | 1846222.39 | 1846222.39 | 0 | 2014-12-31 | 2018-12-31 | 2014-12-31 | 2017-12-31
184-0488 | TMTP Belt Filter Press Replacement | [5 empty] | 1042668.57 | 1042668.57 | 0 | 2015-04-01 | 2019-04-19 | 2015-04-01 | 2019-12-31
184-0493 | Richardson Road and Ripple Creek Pump Stations | [5 empty] | 273733.56 | 273733.56 | 0 | 2015-12-31 | 2022-12-31 | 2015-12-31 | 2022-06-01
184-0498 | ORPS1 Pump 4 Upgrade | [5 empty] | 406115.18 | 406115.18 | 0 | 2017-12-31 | 2020-12-31 | 2017-12-31 | 2020-06-30
184-0521 | Bromley Tank Gravity Wall | [5 empty] | 36640.18 | 36640.18 | 0 | 2014-12-31 | 2015-12-31 | 2014-12-31 | 2017-12-31
184-0528 | Piner Water Hauling Station Drainage | [5 empty] | 33395.87 | 33395.87 | 0 | 2014-01-01 | 2019-12-31 | 2014-12-31 | 2019-05-31
184-0532 | Bromley Tank Drainage Channel | [5 empty] | 26804.48 | 26804.48 | 0 | 2018-01-01 | 2018-12-31 | 2018-09-01 | 2018-12-31
185-0533 | Old Siry Rd Landslide Mitigation | [5 empty] | 14597.32 | 151000 | -136402.68 | 2019-01-01 | on hold | 2019-05-31 | on hold
184-0534 | TMTP and Tank Security Upgrades | [5 empty] | 63742.91 | 63742.91 | 0 | 2020-01-01 | 2021-12-31 | 2020-10-30 | 2021-07-01
184-0535 | Central Facility Material Bins | [5 empty] | 2734 | 175000 | -172266 | 2021-01-01 | 2021-12-31 | 2021-03-01 | under design
184-0536 | Automated Meter System | [5 empty] | 1149266 | 13500000 | -12350734 | 2021-01-01 | 2023-10-06 | 2021-10-22 | under construction
184-0613 | Cox Road and Oliver Road WMR | [5 empty] | 1432700 | 1432700 | 0 | 2007-05-01 | 2020-12-31 | 2007-05-01 | 2020-12-31
184-0721 | St. Joseph Lane WMR | [5 empty] | 274647.44 | 274647.44 | 0 | 2011-01-01 | 2021-12-31 | 2012-03-19 | 2021-06-30
184-0742 | Church Street and Faye Drive WMR | [5 empty] | 250787.57 | 250787.57 | 0 | 2012-12-01 | 2018-12-31 | 2012-12-01 | 2018-08-20
184-0749 | 36" Licking River Crossing Wilder | [5 empty] | 435174 | 5708000 | -5272826 | 2012-12-29 | 2024-12-31 | 2012-12-29 | accepted bids
184-0750 | Sub-District M Phase 2 | [5 empty] | 3405865.08 | 3405865.08 | 0 | 2013-01-01 | 2018-12-31 | 2013-04-01 | 2018-12-31
184-0754 | 16" Cross Country WMR C County | [5 empty] | 56567 | 850000 | -793433 | 2014-12-31 | 2024-12-31 | 2014-12-31 | under design
184-0767 | 8" & 12" Water Main Connection- Phase 1 | [5 empty] | 311787.08 | 311787.08 | 0 | 2013-01-01 | 2019-12-31 | 2013-08-16 | 2019-12-31
184-0776 | 24inch Cross Country WMR project | [5 empty] | 1094763.59 | 1094763.59 | 0 | 2014-10-08 | 2023-03-18 | 2014-10-08 | 2020-02-28
184-0795 | Madison Pike Phase 2 WMR | [5 empty] | 1384999.5 | 1384999.5 | 0 | 2014-04-01 | 2019-04-19 | 2014-04-01 | 2018-12-31
184-0807 | Edgewood WMR Beech, Buckner Wildrose & Elmwood | [5 empty] | 809449.05 | 809449.05 | 0 | 2014-12-31 | 2019-04-19 | 2014-12-31 | 2018-01-31
184-0811 | Newport WMR 15th,16th, 17th, Parkview & Main | [5 empty] | 23155.8 | 830000 | -806844.2 | 2014-11-30 | on hold | 2014-11-30 | on hold
184-0812 | Parker and Ridge WMR | [5 empty] | 622001.63 | 622001.63 | 0 | 2014-12-01 | 2019-04-19 | 2014-12-01 | 2020-03-01
184-0813 | N. Ft Thomas Phase II 2015 WMR | [5 empty] | 487476.62 | 487476.62 | 0 | 2014-12-31 | 2015-12-31 | 2014-12-31 | 2019-08-31
184-0824 | Latonia Lakes | [5 empty] | 1583143.88 | 1583143.88 | 0 | 2015-01-01 | 2018-12-31 | 2015-06-30 | 2018-06-30
184-0826 | Lincoln Avenue WMR (Bellevue) | [5 empty] | 1060977.1 | 1060977.1 | 0 | 2015-10-14 | 2019-04-19 | 2015-10-14 | 2017-12-31
184-0830 | Riggs Avenue Phase 2 WMR | [5 empty] | 348251.7 | 348251.7 | 0 | 2015-12-31 | 2019-04-19 | 2015-12-31 | 2018-02-16
184-0836 | Blossom Lane WMR | [5 empty] | 779110.75 | 779110.75 | 0 | 2016-01-01 | 2016-12-31 | 2016-03-07 | 2018-08-01
184-0837 | Ervin Terrace & 10th Ave WMR | [5 empty] | 478851.34 | 478851.34 | 0 | 2016-10-07 | 2019-04-19 | 2016-10-07 | 2020-06-30
184-0838 | Echo Hills and Licking Pike WMR | [5 empty] | 771044 | 771044 | 0 | 2016-07-31 | 2019-04-19 | 2016-07-31 | 2019-12-31
184-0839 | Latonia Avenue WMR | [5 empty] | 197668.87 | 197668.87 | 0 | 2016-07-12 | 2019-04-19 | 2016-07-12 | 2017-12-31
184-0840 | Ann Street WMR | [5 empty] | 524259.08 | 524259.08 | 0 | 2016-03-07 | 2023-03-18 | 2016-03-07 | 2020-01-07
184-0842 | Perimeter Dr- Phase 1 WMR | [5 empty] | 251739.49 | 251739.49 | 0 | 2016-07-01 | 2019-04-19 | 2016-07-01 | 2018-02-01
184-0843 | Perimeter Dr- Phase 2 WMR | [5 empty] | 255518.25 | 255518.25 | 0 | 2016-07-01 | 2019-04-19 | 2016-07-01 | 2018-06-30
184-0848 | Dudley Road and Lyndale Court WMR | [5 empty] | 772048.69 | 772048.69 | 0 | 2011-09-22 | 2013-09-22 | 2016-10-14 | 2019-06-30
184-0849 | Wedgewood Drive and Clubhouse Drive WMR | [5 empty] | 397238.69 | 397238.69 | 0 | 2016-11-01 | 2019-04-19 | 2016-11-01 | 2017-12-31
184-0850 | Brookwood Drive WMR - Central Phase | [5 empty] | 171664.15 | 171664.15 | 0 | 2016-12-01 | 2019-04-19 | 2016-12-01 | 2017-12-31
184-0851 | Hudson Avenue WMR | [5 empty] | 119903.96 | 119903.96 | 0 | 2016-12-15 | 2019-04-19 | 2016-12-15 | 2017-12-31
184-0852 | Buttermilk Pike WMR | [5 empty] | 477179.52 | 477179.52 | 0 | 2016-12-23 | 2019-04-19 | 2016-12-23 | 2018-06-30
184-0853 | McHenry Street and Clifton Avenue WMR | [5 empty] | 91361.2 | 91361.2 | 0 | 2017-03-01 | 2019-04-19 | 2017-03-01 | 2017-12-31
184-0854 | McKinney St and 9th Ave WMR | [5 empty] | 100952.81 | 100952.81 | 0 | 2017-03-31 | 2019-04-19 | 2017-03-31 | 2017-12-31
184-0855 | Arlington Road WMR | [5 empty] | 206881.96 | 206881.96 | 0 | 2017-04-19 | 2019-04-19 | 2017-07-01 | 2020-06-30
184-0856 | Lorup Avenue WMR | [5 empty] | 181050.71 | 181050.71 | 0 | 2017-04-14 | 2019-04-19 | 2017-04-14 | 2017-12-31
184-0857 | Caldwell Drive MWR | [5 empty] | 122740.67 | 122740.67 | 0 | 2017-04-19 | 2019-04-19 | 2017-12-31 | 2018-06-30
184-0858 | Erlanger Road Phase 2 WMR | [5 empty] | 282886.7 | 282886.7 | 0 | 2017-04-19 | 2019-04-19 | 2017-08-01 | 2018-12-31
184-0859 | Birch Drive WMR | [5 empty] | 134075.67 | 134075.67 | 0 | 2017-04-19 | 2019-04-19 | 2017-08-02 | 2018-12-31
184-0860 | Amsterdam Road WMR- HDPE | [5 empty] | 365597.21 | 365597.21 | 0 | 2017-04-19 | 2019-04-19 | 2017-10-31 | 2020-12-31
184-0861 | Stonehouse Road WMR | [5 empty] | 731576.42 | 731576.42 | 0 | 2017-04-19 | 2019-04-19 | 2017-09-29 | 2020-07-01
184-0862 | Highland Ave WMR | [5 empty] | 132335.33 | 132335.33 | 0 | 2017-04-19 | 2019-04-19 | 2017-12-01 | 2018-12-31
184-0863 | Amsterdam Road WMR (Morris to Redwood) | [5 empty] | 168443.17 | 168443.17 | 0 | 2017-04-19 | 2019-04-19 | 2017-11-10 | 2018-12-31
184-0864 | Winters Lane WMR | [5 empty] | 835220.16 | 835220.16 | 0 | 2017-04-19 | 2019-04-19 | 2017-12-31 | 2018-12-31
184-0865 | Ripple Creek Road WMR | [5 empty] | 196942.87 | 196942.87 | 0 | 2017-04-19 | 2019-04-19 | 2018-02-01 | 2018-12-31
184-0866 | Pentland Place WMR | [5 empty] | 222811.29 | 222811.29 | 0 | 2017-04-19 | 2019-04-19 | 2018-03-16 | 2018-12-31
184-0867 | Alexander Circle (Cochran Avenue) WMR | [5 empty] | 205311.13 | 205311.13 | 0 | 2017-04-19 | 2019-04-19 | 2018-05-18 | 2020-11-30
184-0868 | Brookwood Drive WMR - North Phase | [5 empty] | 105962.87 | 105962.87 | 0 | 2017-04-19 | 2019-04-19 | 2018-03-01 | 2018-12-31
184-0869 | Highland Ave WMR (Oak to Floral) | [5 empty] | 67450.23 | 67450.23 | 0 | 2017-04-19 | 2019-04-19 | 2018-05-01 | 2018-12-31
184-0870 | Sunset Drive WMR | [5 empty] | 178270.51 | 178270.51 | 0 | 2017-04-19 | 2019-04-19 | 2018-06-30 | 2018-12-31
184-0871 | N. Ft. Thomas Ave WMR (Covert to Lincoln) | [5 empty] | 603432.2 | 603432.2 | 0 | 2017-04-19 | 2019-04-19 | 2018-08-17 | 2020-01-31
184-0872 | Narrows and Nelson WMR Relocation | [5 empty] | 53029.56 | 53029.56 | 0 | 2017-04-19 | 2019-04-19 | 2018-09-01 | 2018-09-01
184-0873 | Jackson Road WMR | [5 empty] | 198033.28 | 198033.28 | 0 | 2017-04-19 | 2019-04-19 | 2018-12-13 | 2020-06-30
184-0874 | Janet Drive WMR | [5 empty] | 224671.86 | 224671.86 | 0 | 2017-04-19 | 2019-04-19 | 2018-09-30 | 2019-12-31
184-0875 | Hillview Drive WMR (Dixie to Longmeadow) | [5 empty] | 235735.54 | 235735.54 | 0 | 2017-04-19 | 2019-04-19 | 2018-11-08 | 2019-12-31
184-0876 | Brookwood and Oakridge Drive WMR | [5 empty] | 208943.56 | 208943.56 | 0 | 2017-04-19 | 2019-04-19 | 2019-06-19 | 2020-06-30
184-0877 | Valleywood Court & Hickory Lane WMR | [5 empty] | 181446.8 | 181446.8 | 0 | 2017-04-19 | 2019-04-19 | 2019-12-31 | 2020-12-31
184-0878 | Covert Run to Lincoln WMR | [5 empty] | 356171.93 | 356171.93 | 0 | 2017-04-19 | 2019-04-19 | 2018-12-31 | 2021-06-30
184-0879 | Rossmoyne, Druid, Warwick WMR | [5 empty] | 261460.04 | 261460.04 | 0 | 2018-12-31 | 2023-03-18 | 2018-12-31 | 2020-01-31
184-0880 | Parkway Dr WMR | [5 empty] | 460665.35 | 460665.35 | 0 | 2017-04-19 | 2019-04-19 | 2019-03-04 | 2019-06-30
184-0881 | Ash Street WMR | [5 empty] | 128564.54 | 128564.54 | 0 | 2019-05-01 | 2023-03-18 | 2019-05-01 | 2019-12-31
184-0882 | Pieck Drive and West Henry Clay Ave WMR | [5 empty] | 197223.46 | 197223.46 | 0 | 2019-04-19 | 2023-03-18 | 2019-04-19 | 2021-01-22
184-0883 | Sunset Drive & Allen Court WMR | [5 empty] | 198805.31 | 198805.31 | 0 | 2019-06-01 | 2023-03-18 | 2019-06-01 | 2020-01-31
184-0884 | Thornton & Tower View WMR | [5 empty] | 152350.93 | 152350.93 | 0 | 2019-05-01 | 2023-03-18 | 2019-05-01 | 2020-12-31
184-0885 | Amsterdam Road WMR (Arlington to Montauge) | [5 empty] | 329969.79 | 329969.79 | 0 | 2019-06-01 | 2023-03-18 | 2019-06-01 | 2020-06-30
184-0886 | Highland Avenue WMR | [5 empty] | 290542.53 | 290542.53 | 0 | 2019-05-31 | 2023-03-18 | 2019-05-31 | 2020-01-31
184-0887 | Wayskin, Marnoam, Sipple, & Dave WMR | [5 empty] | 501611.05 | 501611.05 | 0 | 2019-01-01 | 2021-12-31 | 2019-06-30 | 2020-08-01
184-0888 | Fourth Street MWR (Scott to Greenup) | [5 empty] | 229237.19 | 229237.19 | 0 | 2019-04-01 | 2023-03-18 | 2019-04-01 | 2019-12-31
184-0889 | Old Alexandria Pike (CR1557) WMR | [5 empty] | 128592.29 | 128592.29 | 0 | 2019-05-31 | 2023-03-18 | 2019-05-31 | 2020-05-31
184-0890 | E. Main St WMR | [5 empty] | 622877.95 | 622877.95 | 0 | 2019-06-30 | 2023-03-18 | 2019-06-30 | 2020-12-31
184-0891 | Ridge and W. Orchard Road WMR | [5 empty] | 256194.45 | 256194.45 | 0 | 2019-06-30 | 2023-03-18 | 2019-06-30 | 2020-12-31
184-0892 | Barma Drive WMR | [5 empty] | 74384.52 | 74384.52 | 0 | 2019-10-01 | 2023-03-18 | 2019-10-01 | 2020-04-01
184-0893 | Crowell & Eustace WMR | [5 empty] | 463036.62 | 463036.62 | 0 | 2020-04-16 | 2023-03-18 | 2020-04-16 | 2020-12-31
184-0894 | Thatcher Ct & Paul Ln WMR | [5 empty] | 225676.29 | 225676.29 | 0 | 2017-04-19 | 2019-04-19 | 2020-05-04 | 2020-12-31
184-0895 | Persimmon, etc WMR | [5 empty] | 518929.85 | 518929.85 | 0 | 2020-06-01 | 2023-03-18 | 2020-06-01 | 2021-06-30
184-0896 | Lexington & Woodward WMR | [5 empty] | 509998.96 | 509998.96 | 0 | 2020-06-30 | 2023-03-18 | 2020-06-30 | 2021-12-31
184-0897 | E. Main St WMR - Phase 2 | [5 empty] | 447493.38 | 447493.38 | 0 | 2020-06-30 | 2023-03-18 | 2020-06-30 | 2021-12-31
184-0899 | Greenup Street WMR | [5 empty] | 60292.47 | 60292.47 | 0 | 2017-04-19 | 2019-04-19 | 2020-09-01 | 2020-12-31
184-0900 | Robin Ln WMR | [5 empty] | 128515.53 | 128515.53 | 0 | 2017-04-19 | 2019-04-19 | 2020-11-30 | 2021-06-30
184-0901 | Wayman Branch WMR | [5 empty] | 471680.43 | 471680.43 | 0 | 2021-01-01 | 2023-03-28 | 2021-01-07 | 2022-06-30
184-0902 | Sagebrush & Shadyside WMR | [5 empty] | 394485.2 | 394485.2 | 0 | 2020-12-31 | 2023-03-18 | 2020-12-31 | 2021-12-31
184-0903 | Darlas Dr WMR | [5 empty] | 19383 | 285000 | -265617 | 2021-03-18 | 2023-03-18 | 2021-05-07 | under construction
184-0904 | Chapman Lane WMR | [5 empty] | 177151.09 | 177151.09 | 0 | 2021-01-01 | 2021-12-31 | 2021-05-07 | 2021-12-31
184-0905 | Willowbrook Lane WMR | [5 empty] | 194066.03 | 194066.03 | 0 | 2021-03-18 | 2023-03-18 | 2021-05-17 | 2021-12-31
184-0907 | Joyce Avenue WMR | [5 empty] | 99912.61 | 99912.61 | 0 | 2021-03-18 | 2023-03-18 | 2021-09-01 | 2021-12-31
184-4002 | Plant Metering Upgrades | [5 empty] | 46553 | 300000 | -253447 | 2018-06-30 | 2023-03-18 | 2018-06-30 | preliminary design
184-4003 | SCADA improvements | [5 empty] | 1113352 | 3938969 | -2825617 | 2016-12-06 | 2023-03-18 | 2016-12-06 | under design
184-4005 | TMTP Concrete Flow Meter Pit | [5 empty] | 51450.73 | 51450.73 | 0 | 2017-04-19 | 2019-04-19 | 2017-11-01 | 2018-06-30
184-4006 | FTTP Phase 2 Basin Improvements | [5 empty] | 4553618 | 6000000 | -1446382 | 2018-06-30 | 2023-03-18 | 2018-06-30 | under construction
184-4008 | FTTP Residuals Handling Improvements | [5 empty] | 2705485 | 3000000 | -294515 | 2018-06-30 | 2023-03-18 | 2018-06-30 | under construction
184-4010 | TMTP - PAC & UV Replacement | [5 empty] | 123838 | 1615000 | -1491162 | 2018-01-01 | 2024-12-31 | 2018-06-30 | under design
184-4012 | MPTP Clearwell Rehab and Painting | [5 empty] | 761984.61 | 761984.61 | 0 | 2017-04-19 | 2019-04-19 | 2018-06-30 | 2022-06-30
184-4013 | Taylor Mill Pump Station Backup Generator | [5 empty] | 87497 | 6600000 | -6512503 | 2018-01-01 | 2020-12-31 | 2018-11-01 | under design
184-4014 | Central Facility Standby Power | [5 empty] | 420130.89 | 420130.89 | 0 | 2011-09-22 | 2013-09-22 | 2018-12-31 | 2020-12-31
184-4016 | MPTP Actiflo Upgrades | [5 empty] | 103359 | 828000 | -724641 | 2020-01-01 | 2024-12-31 | 2020-11-30 | under design
184-4017 | FTTP Old Clearwell Baffle Replacement | [5 empty] | 97463 | 750000 | -652537 | 2020-12-31 | 2024-12-31 | 2020-12-31 | under design

## Schedule G2
Year | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2017
2018
2019
2020
2021
Totals | 52223505.25 | 87032933.95 | 34809428.7 | 40% | 1.6665
5 Year Average Slippage Factor (Mathematic Avergae of the Yearly Slippage Factors / 5 years)

## 2017-2021
| need to add unbid 184 projects where we've incurred expenses between 1/1/2017 and 12/31/21 | used net change on Tracy's tracking sheet
Project Number | Project Title/ Description | 2017 | 2018 | 2019 | 2020 | 2021 |  | Total Budget Project Cost
184-0475 | MPTP Raw Water Line | 14776.28 | 10290.28 |  |  |  |  | 1000000
184-0477 | FTTP Floc/Sed Basins 2 & 3 | 4801.01 | [5 empty] | 2700000
184-0478 | FTTP Laboratory Generator | 1103.49 | 13423.32 | 86967.1 |  |  |  | 237000
184-0486 | ORPS # 2 Rehabilitation Project | 1473250.97 | [5 empty] | 2000000
184-0487 | Replace Lumley Tank | 24329.99 | [5 empty] | 1075000
184-0488 | TMTP Belt Filter Press Replacement | 32306.65 | 907236.07 | 1082.19 |  |  |  | 165000
184-0493 | Richardson Road Pump 2 | 8623.2 | 259.62 |  | 11484.67 | 6967.43 |  | 503000
184-0498 | ORPS1 Pump 4 Upgrade | 9682.09 | 8181.01 | 216745.38 | 171506.7 |  |  | 50000
184-0521 | Bromley Tank Gravity Wall | 33543.45 |  |  |  |  | *numbers pulled from 184 tracking sheet | 27000
184-0528 | Piner Water Hauling Station Drainage |  | 8071.9 |  |  |  |  | 30000
184-0532 | Bromley Tank Drainage Channel |  | 26804.48 |  |  |  |  | 151000
185-0533 | Old Siry Rd Landslide Mitigation |  |  | 11837.12 | 2760.2 |  |  | 65000
184-0534 | TMTP Security Camera Upgrade |  |  |  | 2118.88 | -2118.88 |  | 65000
184-0535 | CF Mateiral Bins |  |  |  |  | 2734.48 |  | 175000
184-0536 | Automated Meter System |  |  |  |  | 295015 |  | 13500000
184-0613 | Cox Road and Oliver Road WMR | 102.6 | 7048.37 | 964807.64 |  |  |  | 1300000
184-0721 | St. Joseph Lane WMR |  |  |  | 6927.96 |  |  | 290000
184-0742 | Church Street and Faye Drive WMR | 6097 | 221934.32 |  |  |  | *numbers pulled from 184 tracking sheet | 260000
184-0749 | 36" Licking River Crossing Wilder | 854 | 1119.55 | 55878.29 | 45510.92 | 228.24 |  | 5708000
184-0750 | Sub-District M Phase 2 | 839502.46 | [5 empty] | 3400000
184-0754 | 16" Cross Country WMR C County |  |  | 80.28 | 1393 | 54623.38 |  | 850000
184-0767 | 8" & 12" Water Main Connection- Phase 1 | 179.55 | 13584.79 | 254831.77 |  |  |  | 335000
184-0776 | 24inch Cross Country WMR project | 72859.57 | 38604.23 | 962995.19 | 1249.01 |  |  | 1200000
184-0795 | Madison Pike Phase 2 WMR | 993172.14 | [5 empty] | 1675000
184-0807 | Edgewood WMR Beech, Buckner Wildrose & Elmwood | 775968.28 | [5 empty] | 900000
184-0811 | Newport WMR 15th,16th, 17th, Parkview & Main | 337.39 | 52.84 |  |  |  |  | 830000
184-0812 | Parker and Ridge WMR | 281.64 | 554.82 | 566533.32 |  |  |  | 640000
184-0813 | N. Ft Thomas Phase II 2015 WMR |  |  | 123.65 |  |  |  | 510000
184-0824 | Latonia Lakes | 1363488.98 | [5 empty] | 1856415
184-0826 | Lincoln Avenue WMR (Bellevue) | 991431.3 | 492 |  |  |  | *numbers pulled from 184 tracking sheet | 1075000
184-0830 | Riggs Avenue Phase 2 WMR | 334652.54 | [5 empty] | 375000
184-0836 | Blossom Lane WMR | 748200.13 | [5 empty] | 895000
184-0837 | Ervin Terrace & 10th Ave WMR | 321.39 | 823.28 | 393506.34 |  |  |  | 470000
184-0838 | Echo Hills and Licking Pike WMR | 20448.76 | 692133.67 |  |  |  |  | 790000
184-0839 | Latonia Avenue WMR | 172300.02 |  |  |  |  | *numbers pulled from 184 tracking sheet | 215000
184-0840 | Ann Street WMR | 346.19 | 599.8 | 491669.57 |  |  |  | 530000
184-0842 | Perimeter Dr- Phase 1 WMR | 237699.93 | [5 empty] | 255000
184-0843 | Perimeter Dr- Phase 2 WMR | 209199.07 | [5 empty] | 270000
184-0848 | Dudley Road and Lyndale Court WMR | 2477.02 | 774205.28 |  |  |  |  | 2000000
184-0849 | Wedgewood Drive and Clubhouse Drive WMR | 340537.03 |  |  |  |  | *numbers pulled from 184 tracking sheet | 831490
184-0850 | Brookwood Drive WMR - Central Phase | 155256.01 |  |  |  |  | *numbers pulled from 184 tracking sheet | 415000
184-0851 | Hudson Avenue WMR | 107752.45 |  |  |  |  | *numbers pulled from 184 tracking sheet | 175000
184-0852 | Buttermilk Pike WMR | 14403.78 | [5 empty] | 130000
184-0853 | McHenry Street and Clifton Avenue WMR | 91361.2 | [5 empty] | 485000
184-0854 | McKinney St and 9th Ave WMR | 96200.31 |  |  |  |  | *numbers pulled from 184 tracking sheet | 90000
184-0855 | Arlington Road WMR | 9041.81 | 195324.21 | 2349.78 |  |  |  | 110000
184-0856 | Lorup Avenue WMR | 169286.57 |  |  |  |  | *numbers pulled from 184 tracking sheet | 210000
184-0857 | Caldwell Drive MWR | 204.35 | [5 empty] | 195000
184-0858 | Erlanger Road Phase 2 WMR | 13671.01 | [5 empty] | 130000
184-0859 | Birch Drive WMR | 7168.3 | [5 empty] | 325000
184-0860 | Amsterdam Road WMR- HDPE | 664.35 | 23227.84 | 2582.52 | 339122.5 |  |  | 160000
184-0861 | Stonehouse Road WMR | 8911.68 | 27904.64 | 612500.1 |  |  |  | 400000
184-0862 | Highland Ave WMR | 7947.59 | [5 empty] | 770000
184-0863 | Amsterdam Road WMR (Morris to Redwood) | 6821.92 | [5 empty] | 135000
184-0864 | Winters Lane WMR | 204.35 | [5 empty] | 180000
184-0865 | Ripple Creek Road WMR |  | 189178.83 |  |  |  | *numbers pulled from 184 tracking sheet | 870000
184-0866 | Pentland Place WMR |  | 222811.29 |  |  |  |  | 235000
184-0867 | Alexander Circle (Cochran Avenue) WMR |  | 186223.17 | 12074.96 | 7013 |  |  | 255000
184-0868 | Brookwood Drive WMR - North Phase |  | 96290.46 |  |  |  | *numbers pulled from 184 tracking sheet | 355000
184-0869 | Highland Ave WMR (Oak to Floral) |  | 110036.7 |  |  |  | *numbers pulled from 184 tracking sheet | 120000
184-0870 | Sunset Drive WMR |  | 161633.41 |  |  |  | *numbers pulled from 184 tracking sheet | 135000
184-0871 | N. Ft. Thomas Ave WMR (Covert to Lincoln) |  | 29722.14 | 573163.4 |  |  |  | 185000
184-0872 | Narrows and Nelson WMR Relocation |  | 1589.56 |  |  |  |  | 665000
184-0873 | Jackson Road WMR |  | 2183.08 | 10176.8 |  |  |  | 75000
184-0874 | Janet Drive WMR |  | 3244.24 | 221427.62 |  |  |  | 205000
184-0875 | Hillview Drive WMR (Dixie to Longmeadow) |  | 971.42 |  |  |  |  | 220000
184-0876 | Brookwood and Oakridge Drive WMR |  |  | 127053.92 | 81889.64 |  |  | 300000
184-0877 | Valleywood Court & Hickory Lane WMR |  |  | 246.51 |  |  |  | 230000
184-0878 | Covert Run to Lincoln WMR |  | 369.73 | 27581.18 | 188850.9 |  |  | 200000
184-0879 | Rossmoyne, Druid, Warwick WMR |  | 1298.1 | 259164.67 |  |  |  | 360000
184-0880 | Parkway Dr WMR |  |  | 130749.8 |  |  | *numbers pulled from 184 tracking sheet | 300000
184-0881 | Ash Street WMR |  |  | 122044.48 |  |  | *numbers pulled from 184 tracking sheet | 155000
184-0882 | Pieck Drive and West Henry Clay Ave WMR |  |  | 186321.56 |  |  |  | 140000
184-0883 | Sunset Drive & Allen Court WMR |  |  | 198038.94 |  |  |  | 200000
184-0884 | Thornton & Tower View WMR |  |  | 6333.22 | 146017.71 |  |  | 210000
184-0885 | Amsterdam Road WMR (Arlington to Montauge) |  |  | 19904.07 | 310065.72 |  |  | 155000
184-0886 | Highland Avenue WMR |  |  | 289556.09 |  |  |  | 370000
184-0887 | Wayskin, Marnoam, Sipple, & Dave WMR |  |  | 234101.55 |  |  |  | 430000
184-0888 | Fourth Street MWR (Scott to Greenup) |  |  | 220754.75 |  |  | *numbers pulled from 184 tracking sheet | 540000
184-0889 | Old Alexandria Pike (CR1557) WMR |  |  | 128404.06 |  |  |  | 300000
184-0890 | E. Main St WMR |  |  | 16292.14 |  |  |  | 160000
184-0891 | Ridge and W. Orchard Road WMR |  |  | 11673.24 | 244521.21 |  |  | 650000
184-0892 | Barma Drive WMR |  |  | 74114.52 |  |  |  | 270000
184-0893 | Crowell & Eustace WMR |  |  |  | 425401.54 |  | *numbers pulled from 184 tracking sheet | 90000
184-0894 | Thatcher Ct & Paul Ln WMR |  |  |  | 225676.29 |  |  | 470000
184-0895 | Persimmon, etc WMR |  |  |  | 352528.54 | 166401.31 |  | 240000
184-0896 | Lexington & Woodward WMR |  |  |  | 20943.38 |  |  | 545000
184-0897 | E. Main St WMR - Phase 2 |  |  |  | 431.94 | 447061.44 |  | 510000
184-0899 | Greenup Street WMR |  |  |  | 21748.99 |  |  | 490000
184-0900 | Robin Ln WMR |  |  |  | 2495.44 |  |  | 65000
184-0901 | Wayman Branch WMR |  |  |  |  | 471019.57 |  | 140000
184-0902 | Sagebrush & Shadyside WMR |  |  |  | 374.4 | 394110.8 |  | 500000
184-0903 | Darlas Dr WMR |  |  |  |  | 17498.38 |  | 420000
184-0904 | Chapman Lane WMR |  |  |  |  | 177151.09 |  | 285000
184-0905 | Willowbrook Lane WMR |  |  |  |  | 194066.03 |  | 190000
184-0907 | Joyce Avenue WMR |  |  |  |  | 99912.61 |  | 210000
184-4002 | Plant Metering Upgrades |  | 2593.34 | 893.09 | 29906.82 | 909.36 |  | 110000
184-4003 | SCADA improvements- Phase 1 | 11836.92 | 104131.44 | 14160.77 | 526251.64 | 320714.98 |  | 300000
184-4005 | TMTP Concrete Flow Meter Pit | 11905.37 | [5 empty] | 900000
184-4006 | FTTP Phase 2 Basin Improvements |  | 1027.68 | 72332.2 | 163575.48 | 818666.44 |  | 60000
184-4008 | FTTP Residuals Handling Improvements |  | 38947.82 | 63868.75 | 97594.06 | 1267591.43 |  | 6000000
184-4010 | TMTP - PAC & UV Replacement |  | 782.95 |  | 50991.51 | 67896.77 |  | 3000000
184-4012 | MPTP Clearwell Rehab and Painting |  | 1435.68 | 30608.12 | 722938 | 6372.21 |  | 1615000
184-4013 | Taylor Mill Pump Station Backup Generator |  | 1474.54 | 46564.72 | 39220.81 | 236.84 |  | 743923
184-4014 | Central Facility Standby Power |  | 2104.4 | 245086.22 | 172940.27 |  |  | 6600000
184-4015 | Meter Reading Study |  |  | 13020.92 | 87294.06 | 8800 |  | 400000
184-4016 | MPTP Actiflo Upgrades |  |  |  | 25810.59 | 69598.13 |  | 828000
184-4017 | FTTP Old Clearwell Baffle Replacement |  |  |  | 669.35 | 66865.62 |  | 750000
|  | 9425512.09 | 4129926.3 | 7980202.51 | 4527225.13 | 4952322.66
|  | 9425512.09 | 4129926.3 | 7980202.51 | 4527225.13 | 4952322.66