## SCHEDULE H
| DUKE ENERGY KENTUCKY | [6 empty] | SCHEDULE H
CASE NO. 2022-00372
CONSTRUCTION WORK IN PROGRESS - PERCENT COMPLETE
AS OF FEBRUARY 28, 2022
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (H/G)
1 | 35035 | 2000-06-01 | 2000-04-13 | 100% | 0 | 0 | -856
2 | 78906 | 1999-12-01 | 2000-04-13 | 100% | 0 | 0 | -472.79
3 | 307482003 | 2022-01-01 | 2023-03-31 | 12.78% | 49782 | 49782 | 6378.78 | 12.81%
4 | 344598001 | 2018-04-01 | 2020-02-12 | 100% | 282698 | 282698 | 1456.65 | 0.5153%
5 | 346954001 | 2018-05-01 | 2024-09-30 | 59.68% | 128275 | 139345 | 29826.83 | 21.41%
6 | 349395006 | 2020-05-01 | 2022-10-28 | 73.41% | 120275 | 5497 | 28840.38 | 524.7%
7 | 349472008 | 2021-02-01 | 2022-05-30 | 81.16% | 84630 | 13541 | -4062.82 | -30%
8 | 349472018 | 2022-01-01 | 2023-05-30 | 11.28% | 13250 | 13250 | 1046.16 | 7.896%
9 | 359140001 | 2019-01-01 | 2023-03-29 | 74.55% | 169292 | 169292 | 5322.23 | 3.144%
10 | 400051013 | 2021-06-01 | 2024-03-31 | 26.31% | 91312 | 91312 | 25033.23 | 27.42%
11 | 400052001 | 2021-02-01 | 2022-03-31 | 92.67% | 1367991 | 1367991 | 85075.64 | 6.219%
12 | 400052002 | 2021-09-01 | 2022-06-30 | 59.6% | 29783 | 29783 | 6573.41 | 22.07%
13 | 400055004 | 2022-01-01 | 2023-03-31 | 12.78% | 8753 | 12665 | 3786.48 | 29.9%
14 | 400055005 | 2021-01-01 | 2023-03-30 | 51.71% | 11224 | 26435 | 15487.85 | 58.59%
15 | 400055007 | 2021-03-01 | 2023-03-31 | 47.89% | 28581 | 47004 | 28767.56 | 61.2%
16 | 400055009 | 2021-06-01 | 2022-09-30 | 55.97% | 6330 | 11775 | 6868.1 | 58.33%
17 | 400055010 | 2021-10-01 | 2022-03-15 | 90.91% | 6670 | 6670 | 3326.03 | 49.87%
18 | 400055011 | 2021-11-01 | 2022-03-31 | 79.33% | 3153 | 3153 | 3978.86 | 126.2%
19 | 400055012 | 2021-10-01 | 2022-03-31 | 82.87% | 8909 | 8909 | 1483.87 | 16.66%
20 | 400055015 | 2022-01-01 | 2023-03-31 | 12.78% | 16675 | 16675 | 2276.32 | 13.65%
21 | 400055016 | 2022-01-01 | 2023-03-31 | 12.78% | 14885 | 14885 | 2198.67 | 14.77%
22 | 400055017 | 2022-01-01 | 2023-03-31 | 12.78% | 25942 | 25942 | 3709.92 | 14.3%
23 | 400098001 | 2022-02-01 | 2023-02-28 | 6.888% | 30621 | 30621 | 463.7 | 1.514%
24 | 400098002 | 2022-01-01 | 2023-03-31 | 12.78% | 410225 | 380661 | 65228.16 | 17.14%
25 | 400098003 | 2022-01-01 | 2023-03-31 | 12.78% | 138775 | 138775 | 4843.99 | 3.491%
26 | 315986A | 2017-08-01 | 2022-12-05 | 85.66% | 3313201.21 | 3313201.21 | 5364882.09 | 161.9%
27 | 315986F | 2021-04-01 | 2022-06-30 | 73.19% | 76898 | 76898 | 459787.55 | 597.9%
28 | 315986HW7 | 2021-04-01 | 2021-12-31 | 100% | 89586 | 89586 | 39718.06 | 44.34%
29 | 315986HW8 | 2021-10-01 | 2022-06-30 | 55.15% | 96250 | 96250 | 42055.89 | 43.69%
30 | 349395SW6 | 2021-12-01 | 2022-10-28 | 26.89% | 58192 | 71164 | 17318.44 | 24.34%
31 | 349472S13 | 2021-06-01 | 2022-07-30 | 64.15% | 21856 | 4607.94 | 5167.89 | 112.2%
32 | 349472S14 | 2021-03-01 | 2023-10-01 | 38.56% | 32423 | 9998.76 | 8782.56 | 87.84%
33 | 349472SW6 | 2021-01-01 | 2022-07-29 | 73.69% | 242915 | 24420 | 20027.5 | 82.01%
34 | 8SFYTOOLS | 2020-11-01 | 2022-06-30 | 79.87% | 2001 | 1155.68 | 3897.29 | 337.2%
35 | ARCOSSW | 2018-07-01 | 2022-03-31 | 97.74% | 129249 | 129249 | 148237.89 | 114.7%
36 | BKYTOOL | 2020-04-01 | 2050-12-31 | 6.215% | 50000 | 50000 | 62821.03 | 125.6%
37 | CAPAUTOKY | 2014-03-01 | 2020-12-31 | 100% | 49 | 49 | 2610.33 | 5327%
38 | CEB020297 | 2016-07-01 | 2019-12-31 | 100% | 0 | 0 | 4951.04
39 | CEB020813 | 2019-07-01 | 2022-12-31 | 76.08% | 114305.77 | 114305.77 | 86028.53 | 75.26%
40 | CMU060004 | 2016-07-01 | 2025-03-31 | 64.73% | 0 | 0 | 12459.69
41 | CPADEK | 2018-03-01 | 2050-12-31 | 12.17% | 1 | 1 | 7179.27
42 | CS2100003 | 2021-06-01 | 2021-08-29 | 100% | 8343 | 8343 | 8347.36 | 100.1%
43 | CS2100007 | 2021-09-01 | 2021-12-29 | 100% | 25285 | 25285 | 14495.755 | 57.33%
44 | CS2100008 | 2021-08-01 | 2022-08-31 | 53.42% | 5958 | 5958 | 4195.76 | 70.42%
45 | CWDVLV21 | 2021-06-01 | 2022-03-30 | 90.07% | 44961 | 44961 | 36627.87 | 81.47%
46 | CY190HW13 | 2019-12-01 | 2022-10-28 | 77.21% | 8893269 | 2784426 | 2631908.75 | 94.52%
47 | CY190SW13 | 2019-12-01 | 2022-10-28 | 77.21% | 952370 | 70000 | 18817.81 | 26.88%
48 | CY190SW16 | 2020-12-01 | 2022-10-28 | 65.23% | 50484 | 50484 | 42883.72 | 84.95%
49 | D2017DL5 | 2017-12-01 | 2023-04-30 | 78.44% | 49 | 29216.85 | 18738.66 | 64.14%
50 | DISOHDK | 2018-01-01 | 2026-03-31 | 50.45% | 0 | 0 | 8419.055
51 | DKETKYE21 | 2021-05-01 | 2021-12-31 | 100% | 1 | 1 | 9106.53
52 | DKY213501 | 2021-06-01 | 2025-01-18 | 20.5% | 1245722 | 1245722 | 2575.78 | 0.2068%
53 | DKY213502 | 2021-06-01 | 2025-01-18 | 20.5% | 6087134 | 6087134 | 22137.14 | 0.3637%
54 | DKY213503 | 2021-07-01 | 2025-01-26 | 18.54% | 1507486 | 1507486 | 2050.6 | 0.136%
55 | E1214 | 2008-09-01 | 2050-12-31 | 31.87% | 0 | 0 | 97000
56 | EB020818X | 2020-07-01 | 2022-09-30 | 73.93% | 158414.95 | 261776.21 | 238593.01 | 91.14%
57 | EB021199X | 2021-10-01 | 2022-06-30 | 55.15% | 185057.23 | 185057.23 | 93420.64 | 50.48%
58 | EB021371X | 2021-06-01 | 2023-12-31 | 28.84% | 34661.94 | 34661.94 | 429.1 | 1.238%
59 | EB021604X | 2022-02-01 | 2025-06-01 | 2.22% | 265300.08 | 265300.08 | 12105.38 | 4.563%
60 | EB021688X | 2022-02-01 | 2022-10-31 | 9.926% | 635973.21 | 816057.48 | 20110.81 | 2.464%
61 | EB021722X | 2021-10-01 | 2022-12-31 | 32.89% | 1636560.19 | 2672404.4 | 54161.53 | 2.027%
62 | EB021751X | 2021-06-01 | 2022-11-30 | 49.73% | 104214.83 | 216857.16 | 155123.38 | 71.53%
63 | EB021785X | 2021-11-01 | 2022-11-30 | 30.2% | 45209.18 | 45209.18 | 70965.28 | 157%
64 | EB021799X | 2021-12-01 | 2022-12-31 | 22.53% | 59085.12 | 59085.12 | 18371.81 | 31.09%
65 | EB021895X | 2022-02-01 | 2022-05-28 | 23.28% | 225852.1 | 225852.1 | 177545.55 | 78.61%
66 | EDUKEKY22 | 2022-02-01 | 2025-12-15 | 1.911% | 50000 | 50000 | 138498.15 | 277%
67 | ETSFHCAPK | 2008-07-01 | 2050-12-31 | 32.15% | 0 | 0 | 257.925
68 | GPACCRUAL | 2005-03-01 | 2051-03-31 | 36.88% | 1 | 1 | 44618.99
69 | INCENTIVE | 2009-12-01 | 2050-12-31 | 29.8% | 0 | 0 | 499083.565
70 | IT2000019 | 2020-06-01 | 2022-07-30 | 80.74% | 21707 | 21707 | 52199.25 | 240.5%
71 | IT2000050 | 2020-08-01 | 2021-12-30 | 100% | 6071 | 11583 | 15536.63 | 134.1%
72 | IT2100108 | 2021-11-01 | 2023-03-31 | 23.11% | 22221 | 22221 | 13150.64 | 59.18%
73 | IT2100120 | 2021-12-01 | 2022-06-29 | 42.38% | 30225 | 30225 | 30057.87 | 99.45%
74 | K2055SURK | 2021-11-01 | 2023-03-31 | 23.11% | 77.69 | 77.69 | 28980.73 | 37303%
75 | K2152SURK | 2022-02-01 | 2025-03-31 | 2.34% | 77.69 | 77.69 | 2172.68 | 2797%
76 | K2210SURK | 2022-02-01 | 2023-03-31 | 6.383% | 77.69 | 77.69 | 11626.35 | 14965%
77 | K2241SURK | 2021-11-01 | 2024-03-31 | 13.51% | 77.69 | 77.69 | 51818.88 | 66700%
78 | KBANNER | 2019-09-01 | 2067-04-01 | 5.242% | 0 | 0 | 2006.59
79 | KCSL | 2021-11-01 | 2067-04-01 | 0.7174% | 97 | 97 | 105.31 | 108.6%
80 | KFPLOMX | 2017-09-01 | 2067-12-31 | 8.927% | 0 | 0 | 9922.49
81 | KMHR | 2019-12-01 | 2067-12-31 | 4.669% | 0 | 0 | 1344.44
82 | KMW3CEB80 | 2021-02-01 | 2023-11-08 | 38.81% | 298262 | 9223149 | 25157.31 | 0.2728%
83 | KPOLRNF | 2020-10-01 | 2067-12-31 | 2.984% | 93 | 93 | 10746.03 | 11555%
84 | KPPL | 2017-12-01 | 2067-12-31 | 8.474% | 2 | 2 | 37650.91 | 1882546%
85 | KPPLLGT | 2021-07-01 | 2069-12-31 | 1.366% | 440 | 440 | 24960.65 | 5673%
86 | KRFSCM | 2021-05-01 | 2068-03-31 | 1.768% | 89 | 89 | 9292.8 | 10441%
87 | KROC | 2018-11-01 | 2067-12-31 | 6.766% | 0 | 0 | 137333.13
88 | KRXRCM | 2020-01-01 | 2068-03-31 | 4.477% | 84 | 84 | 72473.95 | 86279%
89 | KSBDUG | 2020-01-01 | 2028-04-01 | 26.19% | 2 | 2 | 945281.59 | 47264080%
90 | KSCDL | 2021-07-01 | 2067-12-31 | 1.425% | 93 | 93 | 1767.06 | 1900%
91 | KSLNOLE | 2018-02-01 | 2067-04-01 | 8.287% | 58 | 58 | 42401.1 | 73105%
92 | KSMCELL | 2019-03-01 | 2067-04-01 | 6.235% | 0 | 0 | 12716.94
93 | KSTMOH | 2017-12-01 | 2067-12-31 | 8.474% | 93 | 93 | 123520.64 | 132818%
94 | KSVDTUG | 2018-08-01 | 2068-03-31 | 7.205% | 0 | 0 | -568.7
95 | KUC348450 | 2017-10-01 | 2022-06-30 | 92.96% | 90 | 90 | 2566.64 | 2852%
96 | KUC348474 | 2017-07-01 | 2022-07-29 | 91.86% | 190407.95 | 190407.95 | 649.31 | 0.341%
97 | KYGLPR5 | 2016-07-01 | 2024-12-31 | 66.6% | 160000 | 160000 | 56225.27 | 35.14%
98 | KYGLT2001 | 2020-09-01 | 2023-08-29 | 49.91% | 694336 | 398290.5 | 66797.69 | 16.77%
99 | KYGLT2102 | 2022-02-01 | 2024-02-03 | 3.689% | 624145.67 | 624145.67 | 798.33 | 0.1279%
100 | KYGLT2103 | 2022-02-01 | 2023-10-17 | 4.334% | 0 | 0 | 370.12
101 | LTHITTAMO | 2020-08-01 | 2022-12-30 | 65.38% | 96831 | 96831 | 68833.76 | 71.09%
102 | LTHRROBTS | 2021-03-01 | 2024-03-30 | 32.36% | 152888.02 | 152888.02 | 28523.09 | 18.66%
103 | LTHTASDBS | 2021-09-01 | 2023-03-31 | 31.25% | 9159 | 9159 | 312.12 | 3.408%
104 | LTHTRLIVS | 2021-07-01 | 2025-12-31 | 14.72% | 29192 | 29192 | 1161.44 | 3.979%
105 | LTHTRMTLS | 2021-03-01 | 2023-05-01 | 46.02% | 25480 | 25480 | 4010.56 | 15.74%
106 | M18009501 | 2019-03-01 | 2023-12-29 | 62.07% | 2336966 | 2336966 | 155324.26 | 6.646%
107 | M18037501 | 2021-11-01 | 2024-06-28 | 12.27% | 8574167 | 8574167 | 11716.99 | 0.1367%
108 | M18037502 | 2021-12-01 | 2024-06-28 | 9.468% | 0 | 0 | 663.02
109 | M18037503 | 2022-01-01 | 2024-06-28 | 6.381% | 0 | 0 | 487.01
110 | M18037801 | 2019-10-01 | 2023-07-21 | 63.43% | 2360214.13 | 2360214.13 | 385436.4 | 16.33%
111 | M18037802 | 2019-10-01 | 2023-08-04 | 62.79% | 523888.35 | 523888.35 | 125524.43 | 23.96%
112 | M18037803 | 2020-06-01 | 2023-07-10 | 56.17% | 0 | 0 | 5223.88
113 | M18038701 | 2021-03-01 | 2023-01-16 | 53.06% | 814576.06 | 117253.42 | 135047.73 | 115.2%
114 | M18043901 | 2021-05-01 | 2027-07-20 | 13.34% | 0 | 0 | 838.44
115 | M19016706 | 2020-01-01 | 2027-02-08 | 30.4% | 85275 | 85275 | 303.61 | 0.356%
116 | M19019401 | 2020-12-01 | 2028-06-19 | 16.47% | 0 | 0 | 4087.72
117 | M19022601 | 2019-11-01 | 2023-03-04 | 69.73% | 5133016 | 5133016 | 9043876.77 | 176.2%
118 | M19022602 | 2020-01-01 | 2023-01-06 | 71.66% | 1992002 | 7486323 | 7195574.05 | 96.12%
119 | M19029701 | 2020-11-01 | 2023-07-18 | 48.94% | 6743234 | 6331544 | 332338.1 | 5.249%
120 | M19029702 | 2021-03-01 | 2022-12-31 | 54.33% | 307328 | 307328 | 251.03 | 0.08168%
121 | M19029801 | 2021-06-01 | 2023-07-04 | 35.65% | 763550.75 | 23140666.42 | 50332.58 | 0.2175%
122 | M19029803 | 2021-08-01 | 2023-03-13 | 35.82% | 1438798 | 998899.36 | 17446.45 | 1.747%
123 | M19029901 | 2021-07-01 | 2026-02-13 | 14.34% | 984733.98 | 25354607.12 | 34333.87 | 0.1354%
124 | M19030001 | 2021-07-01 | 2025-07-07 | 16.5% | 814497.49 | 17599527.47 | 31371.2 | 0.1783%
125 | M20005601 | 2020-12-01 | 2024-01-26 | 39.44% | 480208 | 33230.58 | 78152.96 | 235.2%
126 | M20005602 | 2020-12-01 | 2024-02-25 | 38.44% | 74678.82 | 74678.82 | 865.64 | 1.159%
127 | M20005603 | 2020-12-01 | 2024-02-18 | 38.67% | 192603.93 | 192603.93 | 4828.6 | 2.507%
128 | M20005604 | 2021-02-01 | 2023-12-10 | 37.62% | 114396 | 114396 | 1015.21 | 0.8875%
129 | M20032601 | 2021-02-01 | 2023-11-20 | 38.36% | 167211 | 168205.24 | 46240.96 | 27.49%
130 | M20032701 | 2020-12-01 | 2021-05-28 | 100% | 0 | 0 | 491.43
131 | M20038201 | 2021-03-01 | 2022-10-21 | 60.77% | 54602 | 54602 | 17095.63 | 31.31%
132 | M21025101 | 2021-07-01 | 2023-02-07 | 41.3% | 128087 | 128087 | 24635.87 | 19.23%
133 | M21025701 | 2018-08-01 | 2022-07-30 | 89.58% | 2407350 | 2407350 | 61327.13 | 2.547%
134 | M21025801 | 2021-06-01 | 2023-06-10 | 36.81% | 0 | 0 | 725.13
135 | M21028001 | 2021-06-01 | 2022-06-17 | 71.39% | 105658 | 105658 | 12828.74 | 12.14%
136 | M21032301 | 2021-12-01 | 2022-08-29 | 32.84% | 139856 | 139856 | 35987.48 | 25.73%
137 | M21037401 | 2021-08-01 | 2024-03-10 | 22.16% | 160173 | 160173 | 3193.43 | 1.994%
138 | M21037402 | 2021-08-01 | 2024-03-10 | 22.16% | 2253809 | 2253809 | 55709.95 | 2.472%
139 | M21042801 | 2021-11-01 | 2022-08-05 | 42.96% | 104596 | 104596 | 14733.09 | 14.09%
140 | M21042901 | 2022-02-01 | 2022-05-29 | 23.08% | 45532 | 45532 | 25497.79 | 56%
141 | M21050401 | 2022-01-01 | 2023-07-10 | 10.45% | 724878 | 724878 | -85879.97 | -11.85%
142 | MWEMSKY | 2019-07-01 | 2023-03-30 | 71.13% | 679701.48 | 679701.48 | 554959.42 | 81.65%
143 | MWEMSKY2 | 2020-12-01 | 2024-12-31 | 30.45% | 1646591 | 1646591 | 380774.71 | 23.13%
144 | MX0000476 | 2019-07-01 | 2022-10-20 | 80.61% | 228.31 | 228.31 | 7861.18 | 3443%
145 | MX0000477 | 2019-08-01 | 2022-11-10 | 78.7% | 228.31 | 228.31 | 2749.06 | 1204%
146 | MX0000632 | 2019-08-01 | 2022-09-01 | 83.58% | 228.31 | 228.31 | 847.75 | 371.3%
147 | MX0000704 | 2019-09-01 | 2030-10-07 | 22.47% | 228.31 | 228.31 | 14026.65 | 6144%
148 | MX0000778 | 2019-09-01 | 2030-10-18 | 22.41% | 228.31 | 228.31 | 5258.14 | 2303%
149 | MX0000780 | 2019-09-01 | 2030-10-18 | 22.41% | 228.31 | 228.31 | 6360.14 | 2786%
150 | MX0000782 | 2019-09-01 | 2030-11-15 | 22.26% | 228.31 | 228.31 | 5576.35 | 2442%
151 | MX0002133 | 2022-02-01 | 2023-06-15 | 5.411% | 228.31 | 287654.23 | 2390.57 | 0.8311%
152 | MX0002522 | 2021-12-01 | 2024-03-30 | 10.47% | 228.31 | 228.31 | 6814.87 | 2985%
153 | MX0002524 | 2021-12-01 | 2024-03-30 | 10.47% | 228.31 | 228.31 | 9047.12 | 3963%
154 | MX0002526 | 2022-01-01 | 2024-03-30 | 7.082% | 228.31 | 228.31 | 2845.07 | 1246%
155 | MX0240701 | 2021-03-01 | 2023-01-29 | 52.07% | 228.31 | 285971.02 | 22702.84 | 7.939%
156 | MX0291269 | 2021-06-01 | 2023-02-16 | 43.52% | 288352.06 | 297921.33 | 296889.65 | 99.65%
157 | MX0319569 | 2021-08-01 | 2024-03-30 | 21.71% | 228.31 | 14762.51 | 1236.3 | 8.375%
158 | MX0319570 | 2021-08-01 | 2024-03-30 | 21.71% | 228.31 | 16439.26 | 1273.2 | 7.745%
159 | MX0319571 | 2021-08-01 | 2024-03-30 | 21.71% | 228.31 | 14384.29 | 1043.06 | 7.251%
160 | MX0319572 | 2021-08-01 | 2024-03-30 | 21.71% | 12341.72 | 21002.93 | 1773.9 | 8.446%
161 | MX0319573 | 2021-08-01 | 2024-03-30 | 21.71% | 23077.95 | 16539.05 | 1849.23 | 11.18%
162 | MX0319574 | 2021-08-01 | 2024-03-30 | 21.71% | 24462.8 | 14639.02 | 1810.75 | 12.37%
163 | MX0494865 | 2019-11-01 | 2022-12-29 | 73.66% | 209984.34 | 104991.78 | 745.97 | 0.7105%
164 | MX0675382 | 2018-03-01 | 2023-06-29 | 75.03% | 228.31 | 10800.23 | 1423.05 | 13.18%
165 | MX0705679 | 2020-04-01 | 2022-09-01 | 79.05% | 76144.29 | 79086.82 | 9283.29 | 11.74%
166 | MX0705681 | 2020-04-01 | 2022-09-01 | 79.05% | 59525.72 | 61400.33 | 3492.66 | 5.688%
167 | MX1006763 | 2021-06-01 | 2023-02-28 | 42.7% | 228.31 | 11657.67 | 17466.8 | 149.8%
168 | MX1064765 | 2021-11-01 | 2023-06-15 | 20.14% | 228.31 | 228.31 | 20723.54 | 9077%
169 | MX1089667 | 2021-11-01 | 2025-03-31 | 9.551% | 228.31 | 591554.32 | 49417.04 | 8.354%
170 | MX1089713 | 2021-11-01 | 2024-08-29 | 11.53% | 589991.61 | 589991.61 | 33190.42 | 5.626%
171 | MX1089758 | 2021-11-01 | 2024-08-29 | 11.53% | 403119.11 | 403119.11 | 41677.25 | 10.34%
172 | MX1204044 | 2022-02-01 | 2022-10-18 | 10.42% | 27912.1 | 27912.1 | 9150.98 | 32.78%
173 | MX1261517 | 2021-10-01 | 2022-07-27 | 50.17% | 48426.64 | 48426.64 | 51563.01 | 106.5%
174 | MX1264145 | 2021-06-01 | 2022-03-31 | 89.77% | 5235.15 | 5235.15 | 618.59 | 11.82%
175 | MX1264996 | 2021-07-01 | 2022-03-31 | 88.64% | 5509.56 | 5509.56 | 965.18 | 17.52%
176 | MX1266171 | 2021-07-01 | 2022-03-31 | 88.64% | 985.6 | 985.6 | 880.93 | 89.38%
177 | MX1277606 | 2021-11-01 | 2023-01-29 | 26.21% | 47359.32 | 47359.32 | 61085.91 | 129%
178 | MX1278018 | 2021-11-01 | 2023-01-29 | 26.21% | 46482.63 | 46482.63 | 63191.37 | 135.9%
179 | MX1278081 | 2021-11-01 | 2023-01-29 | 26.21% | 46603.9 | 46603.9 | 15571.79 | 33.41%
180 | MX1296858 | 2021-06-01 | 2022-03-31 | 89.77% | 11201.12 | 11201.12 | 13514.46 | 120.7%
181 | MX1325365 | 2019-07-01 | 2023-03-30 | 71.13% | 76917.35 | 78426.11 | 9538.14 | 12.16%
182 | MX1393376 | 2022-01-01 | 2024-03-30 | 7.082% | 228.31 | 43183.35 | 3833.64 | 8.878%
183 | MX1393377 | 2021-11-01 | 2023-02-02 | 25.98% | 45214.57 | 45214.57 | 12700.43 | 28.09%
184 | MX1393379 | 2021-10-01 | 2023-02-02 | 30.67% | 51507.07 | 51507.07 | 42342.86 | 82.21%
185 | MX1393380 | 2021-10-01 | 2023-02-02 | 30.67% | 45129.26 | 44782.02 | 48385.18 | 108%
186 | MX1393381 | 2021-10-01 | 2023-02-02 | 30.67% | 43388.09 | 43388.09 | 40959.4 | 94.4%
187 | MX1393382 | 2021-10-01 | 2023-02-02 | 30.67% | 43289.81 | 43289.81 | 15690.44 | 36.25%
188 | MX1393383 | 2021-10-01 | 2023-02-02 | 30.67% | 45647.76 | 45647.76 | 15485.55 | 33.92%
189 | MX1393384 | 2021-10-01 | 2023-02-02 | 30.67% | 47387.16 | 47387.16 | 14316.14 | 30.21%
190 | MX1393385 | 2021-10-01 | 2023-02-02 | 30.67% | 44274.37 | 44274.37 | 15688.13 | 35.43%
191 | MX1450766 | 2019-04-01 | 2022-03-31 | 97.17% | 3795.57 | 3795.57 | 3536.46 | 93.17%
192 | MX1464324 | 2019-06-01 | 2022-03-31 | 97% | 2837.22 | 2837.22 | 1534.61 | 54.09%
193 | MX1473561 | 2021-12-01 | 2023-06-15 | 15.86% | 228.31 | 45686.85 | 921.28 | 2.017%
194 | MX1473566 | 2021-12-01 | 2024-03-30 | 10.47% | 228.31 | 44184.22 | 3264.34 | 7.388%
195 | MX1478604 | 2021-07-01 | 2022-06-23 | 67.79% | 228.31 | 9623.67 | -2143.31 | -22.27%
196 | MX1488550 | 2019-03-01 | 2022-03-31 | 97.25% | 17460.92 | 17460.92 | 21788.26 | 124.8%
197 | MX1518649 | 2021-11-01 | 2023-05-23 | 20.95% | 228.31 | 59637.34 | 9154.85 | 15.35%
198 | MX1518718 | 2021-11-01 | 2023-03-31 | 23.11% | 228.31 | 258069.85 | 2324.37 | 0.9007%
199 | MX1561891 | 2021-08-01 | 2022-11-29 | 43.51% | 228.31 | 914832.76 | 55467.91 | 6.063%
200 | MX1593217 | 2021-10-01 | 2022-03-31 | 82.87% | 69980.49 | 69980.49 | 1916.73 | 2.739%
201 | MX1601008 | 2022-02-01 | 2023-03-31 | 6.383% | 228.31 | 34548.66 | 1143.38 | 3.309%
202 | MX1601017 | 2022-02-01 | 2023-06-15 | 5.411% | 16718.93 | 17486.11 | 18815.55 | 107.6%
203 | MX1601025 | 2022-02-01 | 2023-06-15 | 5.411% | 19330.73 | 17461.9 | 2000.82 | 11.46%
204 | MX1601026 | 2022-02-01 | 2024-03-30 | 3.426% | 228.31 | 25431.13 | 518.89 | 2.04%
205 | MX1601027 | 2022-02-01 | 2024-03-30 | 3.426% | 20599.15 | 20599.15 | 171.03 | 0.8303%
206 | MX1601030 | 2022-02-01 | 2024-03-30 | 3.426% | 17156.03 | 17156.03 | 119.58 | 0.697%
207 | MX1601032 | 2022-02-01 | 2023-02-02 | 7.377% | 16333.77 | 16333.77 | 538.55 | 3.297%
208 | MX1701449 | 2021-10-01 | 2023-02-02 | 30.67% | 40620.48 | 40620.48 | 13528.61 | 33.3%
209 | MX1701450 | 2021-10-01 | 2023-02-02 | 30.67% | 228.31 | 89359.68 | 671.13 | 0.751%
210 | MX1701451 | 2021-10-01 | 2023-02-02 | 30.67% | 44442.98 | 44442.98 | 13704.38 | 30.84%
211 | MX1701452 | 2021-11-01 | 2023-02-02 | 25.98% | 228.31 | 228.31 | 106.33 | 46.57%
212 | MX1701453 | 2021-10-01 | 2023-02-02 | 30.67% | 46702.95 | 46702.95 | 13368.77 | 28.63%
213 | MX1701455 | 2021-10-01 | 2023-02-02 | 30.67% | 44820.96 | 41765.51 | 39611.33 | 94.84%
214 | MX1701461 | 2021-10-01 | 2023-02-02 | 30.67% | 44901.57 | 44901.57 | 12586.3 | 28.03%
215 | MX1701462 | 2021-10-01 | 2023-02-02 | 30.67% | 44552.1 | 44552.1 | 40669.55 | 91.29%
216 | MX1701463 | 2021-10-01 | 2023-02-02 | 30.67% | 44985.64 | 44985.64 | 36112.34 | 80.28%
217 | MX1701467 | 2021-10-01 | 2023-02-02 | 30.67% | 44567.74 | 44567.74 | 42999.71 | 96.48%
218 | MX1701468 | 2021-10-01 | 2023-02-02 | 30.67% | 43947.82 | 43947.82 | 15338.11 | 34.9%
219 | MX1701479 | 2021-12-01 | 2024-03-30 | 10.47% | 228.31 | 43634.32 | 4316.21 | 9.892%
220 | MX1701480 | 2021-12-01 | 2024-03-30 | 10.47% | 0 | 0 | 4652.81
221 | MX1701481 | 2021-12-01 | 2024-03-30 | 10.47% | 43414.29 | 45195.49 | 48745.76 | 107.9%
222 | MX1701482 | 2021-12-01 | 2023-06-15 | 15.86% | 44819.16 | 53063.26 | 47333.3 | 89.2%
223 | MX1701483 | 2021-12-01 | 2023-03-31 | 18.35% | 228.31 | 41130.11 | 4297.99 | 10.45%
224 | MX1701485 | 2021-12-01 | 2023-03-31 | 18.35% | 228.31 | 43167.24 | 5441.48 | 12.61%
225 | MX1701486 | 2021-10-01 | 2023-02-02 | 30.67% | 44820.84 | 44820.84 | 14980.42 | 33.42%
226 | MX1701487 | 2021-10-01 | 2023-02-02 | 30.67% | 43932.67 | 43932.67 | 13358.01 | 30.41%
227 | MX1701488 | 2021-10-01 | 2023-02-02 | 30.67% | 45212.76 | 45212.76 | 13152.42 | 29.09%
228 | MX1793644 | 2021-11-01 | 2023-03-30 | 23.15% | 53485.55 | 53485.55 | 2289.39 | 4.28%
229 | MX1848370 | 2019-06-01 | 2022-09-01 | 84.43% | 116060.84 | 69933.97 | 2243.59 | 3.208%
230 | MX1848383 | 2018-08-01 | 2022-09-01 | 87.6% | 56431.9 | 57824.65 | 33190.84 | 57.4%
231 | MX1898562 | 2022-01-01 | 2022-08-27 | 24.37% | 55287.54 | 55287.54 | 41891.27 | 75.77%
232 | MX1975019 | 2019-10-01 | 2023-03-31 | 68.99% | 228.31 | 256821.89 | 64045.58 | 24.94%
233 | MX1975744 | 2021-06-01 | 2023-03-30 | 40.78% | 228.31 | 311628.4 | 18864.39 | 6.053%
234 | MX1977350 | 2021-10-01 | 2023-03-23 | 27.88% | 228.31 | 72693.64 | 4014.53 | 5.523%
235 | MX2158154 | 2021-12-01 | 2023-02-02 | 20.79% | 21526.42 | 21526.42 | 21723.23 | 100.9%
236 | MX2158161 | 2021-12-01 | 2023-02-02 | 20.79% | 19560.85 | 19560.85 | 22240.65 | 113.7%
237 | MX2158176 | 2022-02-01 | 2023-02-02 | 7.377% | 26548.65 | 26548.65 | 702.27 | 2.645%
238 | MX2158190 | 2021-12-01 | 2024-03-30 | 10.47% | 15692.92 | 15692.92 | 25636.07 | 163.4%
239 | MX2158204 | 2021-12-01 | 2024-03-30 | 10.47% | 20181.62 | 20181.62 | 20380.05 | 101%
240 | MX2158210 | 2021-12-01 | 2024-03-30 | 10.47% | 23199.72 | 23199.72 | 32208.68 | 138.8%
241 | MX2278295 | 2022-01-01 | 2023-06-15 | 10.94% | 201579.18 | 201579.18 | 60481.4 | 30%
242 | MX2506723 | 2021-10-01 | 2022-07-28 | 50% | 228.31 | 173052.3 | 125111.78 | 72.3%
243 | MX2636418 | 2022-01-01 | 2022-07-28 | 27.88% | 35816.35 | 35816.35 | -57078.24 | -159.4%
244 | MX2831125 | 2021-11-01 | 2023-03-31 | 23.11% | 6546.64 | 6546.64 | 12194.77 | 186.3%
245 | MX2866326 | 2020-10-01 | 2022-11-29 | 65.27% | 8023.11 | 8023.11 | 384.51 | 4.793%
246 | MX3045963 | 2019-11-01 | 2031-02-27 | 20.55% | 628843.53 | 628843.53 | 149118.79 | 23.71%
247 | MX3062206 | 2021-11-01 | 2023-02-28 | 24.59% | 10342.05 | 10342.05 | 480.26 | 4.644%
248 | MX3170570 | 2022-01-01 | 2022-07-29 | 27.75% | 13640.52 | 13640.52 | 10206.19 | 74.82%
249 | MX3192862 | 2021-12-01 | 2023-03-31 | 18.35% | 4853.76 | 4853.76 | 108.47 | 2.235%
250 | MX3999738 | 2022-02-01 | 2023-06-15 | 5.411% | 228.31 | 858671.15 | 369.47 | 0.04303%
251 | MX4154470 | 2021-12-01 | 2023-02-07 | 20.55% | 63412.35 | 74076.7 | 185076.19 | 249.8%
252 | MX4412975 | 2020-07-01 | 2022-12-15 | 67.67% | 55117.03 | 55221.15 | 99486.86 | 180.2%
253 | MX4497255 | 2021-12-01 | 2022-06-29 | 42.38% | 57496.83 | 57496.83 | 6797.31 | 11.82%
254 | MX4517175 | 2020-07-01 | 2022-10-13 | 72.78% | 228.31 | 89534.31 | 62201.49 | 69.47%
255 | MX4546275 | 2021-04-01 | 2022-12-29 | 52.28% | 40247.01 | 53891.15 | 63353.43 | 117.6%
256 | MX4864988 | 2020-12-01 | 2023-01-29 | 57.54% | 228.31 | 222076.22 | 215198.7 | 96.9%
257 | MX4877019 | 2020-10-01 | 2022-07-29 | 77.33% | 228.31 | 33025.21 | 23826.5 | 72.15%
258 | MX4946544 | 2020-08-01 | 2022-03-31 | 94.89% | 7569.04 | 7569.04 | 2716 | 35.88%
259 | MX5358828 | 2020-10-01 | 2023-03-31 | 56.53% | 228.31 | 925015.26 | 1536358.87 | 166.1%
260 | MX5764593 | 2020-06-01 | 2023-03-31 | 61.67% | 228.31 | 89329.35 | 14025.28 | 15.7%
261 | MX5931078 | 2020-09-01 | 2022-12-29 | 64.19% | 77608.13 | 86459.21 | -108308.76 | -125.3%
262 | MX5977873 | 2021-01-01 | 2023-05-01 | 49.76% | 228.31 | 412012.18 | 249391.29 | 60.53%
263 | MX5977890 | 2021-01-01 | 2023-03-31 | 51.65% | 228.31 | 12338.21 | 24459.56 | 198.2%
264 | MX6240781 | 2020-04-01 | 2022-06-30 | 85.12% | 160184.27 | 185360.78 | 287095.55 | 154.9%
265 | MX6277290 | 2020-04-01 | 2023-09-03 | 55.84% | 228.31 | 228.31 | 24619.18 | 10783%
266 | MX6321063 | 2021-04-01 | 2023-02-16 | 48.54% | 218837.74 | 279083.39 | 328861.46 | 117.8%
267 | MX6321718 | 2020-12-01 | 2023-01-29 | 57.54% | 228.31 | 377643.13 | 535797.77 | 141.9%
268 | MX6322062 | 2021-03-01 | 2023-03-31 | 47.89% | 228.31 | 472926.98 | 33225.16 | 7.025%
269 | MX6491994 | 2022-01-01 | 2023-03-31 | 12.78% | 228.31 | 5682.78 | 5982.9 | 105.3%
270 | MX7372041 | 2021-10-01 | 2023-06-15 | 24.12% | 228.31 | 38388.05 | 4123.24 | 10.74%
271 | MX7372045 | 2021-10-01 | 2024-03-30 | 16.47% | 228.31 | 41067.84 | 2224.5 | 5.417%
272 | MX7372047 | 2021-10-01 | 2022-11-29 | 35.38% | 228.31 | 43984.74 | 2966.47 | 6.744%
273 | MX7372048 | 2021-10-01 | 2022-11-29 | 35.38% | 228.31 | 48817.22 | 4647.02 | 9.519%
274 | MX7372051 | 2021-10-01 | 2024-03-30 | 16.47% | 228.31 | 56141.81 | 2537.77 | 4.52%
275 | MX7372054 | 2021-10-01 | 2023-06-15 | 24.12% | 228.31 | 43253.26 | 4953.02 | 11.45%
276 | MX7372055 | 2021-12-01 | 2023-06-15 | 15.86% | 228.31 | 44205.38 | 3434.45 | 7.769%
277 | MX7372056 | 2021-10-01 | 2023-06-15 | 24.12% | 228.31 | 44441.08 | 2274.83 | 5.119%
278 | MX7372063 | 2021-10-01 | 2023-02-02 | 30.67% | 47524.19 | 47524.19 | 14797.68 | 31.14%
279 | MX7372064 | 2021-11-01 | 2023-02-02 | 25.98% | 44050.59 | 44050.59 | 13106.73 | 29.75%
280 | MX7372065 | 2021-09-01 | 2023-02-02 | 34.68% | 41759.97 | 41759.97 | 12383.05 | 29.65%
281 | MX7372067 | 2021-10-01 | 2023-02-02 | 30.67% | 45568.45 | 45568.45 | 14814.17 | 32.51%
282 | MX7372068 | 2021-11-01 | 2023-02-02 | 25.98% | 41285.61 | 41285.61 | 15787.53 | 38.24%
283 | MX7473884 | 2020-10-01 | 2022-12-29 | 62.88% | 81317.73 | 81818.3 | 146371.04 | 178.9%
284 | MX7488839 | 2020-09-01 | 2023-06-29 | 52.86% | 228.31 | 5697.77 | 3108.11 | 54.55%
285 | MX7488872 | 2020-09-01 | 2023-06-29 | 52.86% | 228.31 | 184107.64 | 11914.86 | 6.472%
286 | MX7791895 | 2022-01-01 | 2022-08-07 | 26.61% | 82809.53 | 82809.53 | 92118.55 | 111.2%
287 | MX7890923 | 2020-11-01 | 2022-11-24 | 64.28% | 243913.75 | 246708.65 | 360102.32 | 146%
288 | MX7891191 | 2021-11-01 | 2024-08-29 | 11.53% | 228.31 | 4968.19 | 1448.39 | 29.15%
289 | MX7891201 | 2022-01-01 | 2024-03-30 | 7.082% | 19631.86 | 19631.86 | 2249.37 | 11.46%
290 | MX7891216 | 2021-11-01 | 2024-08-29 | 11.53% | 5005.02 | 5005.02 | 1208.34 | 24.14%
291 | MX7891217 | 2021-11-01 | 2024-08-29 | 11.53% | 0 | 0 | 1632.43
292 | MX7891218 | 2021-11-01 | 2024-08-29 | 11.53% | 228.31 | 4505.46 | 1036.76 | 23.01%
293 | MX7891230 | 2021-12-01 | 2024-03-30 | 10.47% | 228.31 | 11695.81 | 1680.41 | 14.37%
294 | MX8022852 | 2021-06-01 | 2022-08-08 | 62.82% | 23793.81 | 23793.81 | -1458.52 | -6.13%
295 | MX8203329 | 2021-01-01 | 2022-12-29 | 58.18% | 228.31 | 36544.94 | 6699.09 | 18.33%
296 | MX8204271 | 2021-03-01 | 2023-09-28 | 38.68% | 228.31 | 25351.75 | 11247.37 | 44.37%
297 | MX8250982 | 2021-04-01 | 2022-12-01 | 54.68% | 496269.57 | 508337.93 | 713559.21 | 140.4%
298 | MX8452455 | 2020-01-01 | 2022-10-01 | 78.59% | 76145.04 | 76145.04 | 833.68 | 1.095%
299 | MX8564271 | 2021-08-01 | 2024-03-30 | 21.71% | 228.31 | 18984.91 | 2243.58 | 11.82%
300 | MX8566565 | 2021-08-01 | 2022-10-27 | 46.68% | 56317.69 | 58280.63 | -98639.81 | -169.2%
301 | MX8693627 | 2018-10-01 | 2022-03-31 | 97.57% | 3280.81 | 5552.31 | 8780.7 | 158.1%
302 | MX8701723 | 2021-08-01 | 2022-11-01 | 46.17% | 75038.83 | 75038.83 | -5080.19 | -6.77%
303 | MX8762998 | 2020-06-01 | 2022-06-29 | 84.04% | 228.31 | 90094.12 | 143002.62 | 158.7%
304 | MX8763054 | 2020-06-01 | 2023-03-31 | 61.67% | 228.31 | 181991.33 | 574747.98 | 315.8%
305 | MX9015414 | 2020-06-01 | 2022-11-29 | 69.92% | 228.31 | 529298.87 | 412583.7 | 77.95%
306 | MX9048687 | 2021-01-01 | 2022-11-30 | 60.6% | 138788.98 | 138788.98 | 191452.09 | 137.9%
307 | MX9064744 | 2021-06-01 | 2023-03-16 | 41.65% | 228.31 | 29880.79 | 12578.36 | 42.1%
308 | MX9210584 | 2021-08-01 | 2022-08-04 | 57.34% | 228.31 | 13934.21 | 8246.82 | 59.18%
309 | MX9365045 | 2021-03-01 | 2023-05-01 | 46.02% | 228.31 | 945276.15 | 25696.92 | 2.718%
310 | MX9545158 | 2019-11-01 | 2022-06-29 | 87.54% | 228.31 | 260622.82 | 226365.38 | 86.86%
311 | MX9649928 | 2021-02-01 | 2022-03-31 | 92.67% | 9873.3 | 9873.3 | 5666.7 | 57.39%
312 | MX9918857 | 2021-03-01 | 2023-05-01 | 46.02% | 26594.21 | 42388.14 | 19622.36 | 46.29%
313 | MX9919639 | 2021-08-01 | 2023-02-02 | 38.36% | 21366.89 | 14661.57 | 1835.71 | 12.52%
314 | MX9919640 | 2021-08-01 | 2023-02-02 | 38.36% | 228.31 | 18001.27 | 1416.34 | 7.868%
315 | MX9919641 | 2021-08-01 | 2023-02-02 | 38.36% | 228.31 | 14787.19 | 1281.15 | 8.664%
316 | MX9919642 | 2021-08-01 | 2023-02-02 | 38.36% | 228.31 | 16604.23 | 1300.12 | 7.83%
317 | MX9919684 | 2021-08-01 | 2023-06-15 | 30.89% | 228.31 | 14257.76 | 1307.05 | 9.167%
318 | MX9919685 | 2021-08-01 | 2023-06-15 | 30.89% | 228.31 | 17251.93 | 3829.94 | 22.2%
319 | MX9992812 | 2021-03-01 | 2022-11-29 | 57.05% | 228.31 | 156473.13 | 265890.72 | 169.9%
320 | MX9998915 | 2018-05-01 | 2023-07-29 | 73.05% | 228.31 | 228.31 | 16452.82 | 7206%
321 | MX9998916 | 2018-05-01 | 2023-10-29 | 69.71% | 228.31 | 228.31 | 236.08 | 103.4%
322 | MXA701477 | 2021-10-01 | 2024-03-30 | 16.47% | 72821.71 | 73972.87 | 3089.51 | 4.177%
323 | OLEKY | 2015-01-01 | 2020-12-31 | 100% | 10 | 10 | 2656.09 | 26561%
324 | RWT055A | 2021-07-01 | 2023-03-31 | 37.93% | 5000 | 5000 | 1088.01 | 21.76%
325 | SG001117 | 2021-09-01 | 2024-07-30 | 16.93% | 2998104 | 874447 | 748210.58 | 85.56%
326 | SG001145 | 2021-07-01 | 2022-11-30 | 46.81% | 5173 | 5173 | 5098.35 | 98.56%
327 | SG1001SW | 2020-09-01 | 2022-12-31 | 64.04% | 27663.6 | 27663.6 | 6028.33 | 21.79%
328 | SG1010B2T | 2020-06-01 | 2021-09-01 | 100% | 1777260 | 1777260 | 85146.45 | 4.791%
329 | SG1010Z1L | 2019-11-01 | 2024-03-31 | 52.73% | 5597208.53 | 5597208.53 | 1572026.455 | 28.09%
330 | SG1010Z1O | 2019-11-01 | 2024-03-31 | 52.73% | 1399302.13 | 1399302.13 | 383714.811 | 27.42%
331 | SG1037SW | 2022-01-01 | 2024-01-31 | 7.632% | 77982 | 77982 | 276.98 | 0.3552%
332 | SG1041SW | 2020-06-01 | 2021-12-31 | 100% | 32007.13 | 32007.13 | 140.94 | 0.4403%
333 | SG1057SVR | 2020-09-01 | 2023-10-31 | 47.19% | 7291 | 7291 | 13136.66 | 180.2%
334 | SG1057SW | 2020-09-01 | 2023-10-31 | 47.19% | 150716 | 150716 | 52470.01 | 34.81%
335 | SG1069GDQ | 2020-11-01 | 2024-03-31 | 38.84% | 195874 | 195874 | 91024.46 | 46.47%
336 | SG1076OCT | 2020-11-01 | 2023-03-31 | 55% | 231176 | 231176 | 558.52 | 0.2416%
337 | SG1081SW | 2021-05-01 | 2022-04-30 | 83.24% | 1215071 | 1215071 | 1275662.17 | 105%
338 | SG1092SLR | 2021-03-01 | 2022-10-15 | 61.38% | 4976446 | 4976446 | 4630775.02 | 93.05%
339 | SG1093SW | 2021-11-01 | 2026-03-31 | 7.387% | 56870 | 56870 | 31826.89 | 55.96%
340 | SG1094OTA | 2021-12-01 | 2023-01-31 | 20.89% | 34685 | 34685 | 5232.14 | 15.08%
341 | SG223SW | 2017-05-01 | 2023-02-28 | 82.86% | 1016639 | 1016639 | 124840.211 | 12.28%
342 | SG336SW | 2016-09-01 | 2024-07-30 | 69.44% | 1049863.37 | 1049863.37 | 1478585.001 | 140.8%
343 | SG359SW | 2018-09-01 | 2022-12-01 | 82.22% | 229797.94 | 227863.84 | 125554.94 | 55.1%
344 | SG359SW2 | 2019-09-01 | 2022-12-01 | 76.75% | 227863.84 | 227863.84 | 77216.32 | 33.89%
345 | SG438DOTS | 2019-10-01 | 2021-09-30 | 100% | 1 | 1 | 16226.01
346 | SG459FB01 | 2018-02-01 | 2023-03-01 | 80.26% | 37132 | 37132 | 23641.45 | 63.67%
347 | SG459FB02 | 2018-02-01 | 2023-03-01 | 80.26% | 37132 | 37132 | 8069.07 | 21.73%
348 | SG551NOK | 2020-12-01 | 2023-03-31 | 53.41% | 11880 | 17998 | 12241.83 | 68.02%
349 | SG601SW | 2017-06-01 | 2025-03-31 | 60.59% | 42090 | 42090 | 361233.48 | 858.2%
350 | SG723SW | 2020-01-01 | 2022-07-30 | 83.85% | 38014 | 38014 | 44317.04 | 116.6%
351 | SG732TR01 | 2018-09-01 | 2021-09-30 | 100% | 968336.2 | 968336.2 | 1574772.38 | 162.6%
352 | SG732TR02 | 2019-02-01 | 2022-03-31 | 97.31% | 968336 | 968336 | 20539.82 | 2.121%
353 | SG732TR03 | 2020-12-01 | 2023-03-31 | 53.41% | 1519055 | 1519055 | 83094.65 | 5.47%
354 | SG732TR04 | 2021-02-01 | 2024-03-31 | 33.97% | 1519055 | 1519055 | 8188.59 | 0.5391%
355 | SG732TR05 | 2021-05-01 | 2025-03-31 | 21.19% | 1519055 | 1519055 | 15314.48 | 1.008%
356 | SG732TR06 | 2021-06-01 | 2022-11-15 | 51.13% | 1777260 | 1777260 | 1273583.28 | 71.66%
357 | SG744BLK | 2018-11-01 | 2031-03-31 | 26.8% | 248821.93 | 248821.93 | 255890.75 | 102.8%
358 | SG744MTR | 2018-07-01 | 2021-12-31 | 100% | 248821.93 | 248821.93 | 2998.81 | 1.205%
359 | SG764BLK1 | 2019-04-01 | 2028-03-31 | 32.37% | 217462.26 | 217462.26 | 1505341.78 | 692.2%
360 | SG764MAT1 | 2019-10-01 | 2028-03-31 | 28.38% | 217462.26 | 217462.26 | 445408.27 | 204.8%
361 | SG776MTR | 2018-03-01 | 2028-03-31 | 39.64% | 1 | 1 | 326096.59
362 | SG794ETOS | 2021-01-01 | 2024-03-31 | 35.7% | 11229.12 | 11229.12 | 11699.44 | 104.2%
363 | SG960DASH | 2021-09-01 | 2026-03-31 | 10.77% | 179000 | 179000 | 5144.44 | 2.874%
364 | SG960ORCH | 2021-09-01 | 2026-03-31 | 10.77% | 939747 | 939747 | 23905.13 | 2.544%
365 | SGCAPATKY | 2017-01-01 | 2025-12-31 | 57.33% | 83 | 83 | 211.73 | 255.1%
366 | SGDLSKY | 2017-05-01 | 2025-12-31 | 55.72% | 94 | 94 | 240.45 | 255.8%
367 | SGHYDRKY | 2016-10-01 | 2025-12-31 | 58.5% | 83 | 83 | 130.38 | 157.1%
368 | SGKAMIMGT | 2016-01-01 | 2023-02-01 | 86.94% | 603878 | 603878 | 5945.01 | 0.9845%
369 | SGRFSKY | 2017-01-01 | 2025-12-31 | 57.33% | 83 | 83 | 244.79 | 294.9%
370 | SGRXRKY | 2019-02-01 | 2050-12-31 | 9.635% | 1 | 1 | 159
371 | SGSELFKY | 2017-12-01 | 2025-12-31 | 52.51% | 1 | 1 | 258.2
372 | SKY1904DC | 2019-07-01 | 2020-03-31 | 100% | 7238.08 | 7238.08 | 7864.52 | 108.7%
373 | SKY1905DC | 2019-06-01 | 2020-03-31 | 100% | 4414.23 | 4414.23 | 4809.63 | 109%
374 | SKY1906DC | 2019-07-01 | 2020-03-31 | 100% | 16289.14 | 16289.14 | 17771.06 | 109.1%
375 | SKY1907DC | 2019-08-01 | 2020-03-31 | 100% | 17651.28 | 17651.28 | 18643.2 | 105.6%
376 | SKY1908DC | 2019-08-01 | 2020-03-31 | 100% | 4194.01 | 4194.01 | 4355.54 | 103.9%
377 | SKY1909DC | 2019-12-01 | 2020-03-31 | 100% | 20266.74 | 20266.74 | 20949.17 | 103.4%
378 | SKY2001DC | 2020-01-01 | 2020-12-31 | 100% | 11079.32 | 11079.32 | 11692.22 | 105.5%
379 | SKY2007DC | 2020-08-01 | 2021-03-31 | 100% | 27 | 27 | 2935.3 | 10871%
380 | SKY2105DC | 2021-06-01 | 2022-03-31 | 89.77% | 5176.57 | 5176.57 | 6564.89 | 126.8%
381 | SKY2109DC | 2021-12-01 | 2022-03-31 | 74.17% | 18008.29 | 18008.29 | 19099.32 | 106.1%
382 | SKY2201DC | 2022-02-01 | 2022-09-30 | 11.2% | 27 | 27 | 46767.34 | 173212%
383 | SMODEMKY | 2019-03-01 | 2068-12-31 | 6.015% | 1 | 1 | 121154.06
384 | TC210SW57 | 2022-02-01 | 2024-03-31 | 3.422% | 16982 | 16982 | 120.85 | 0.7116%
385 | TCPRLFKY | 2020-06-01 | 2021-06-30 | 100% | 10299 | 10299 | 3945.54 | 38.31%
386 | TKY190401 | 2019-01-01 | 2025-06-20 | 48.86% | 0 | 0 | 15900.22
387 | TKY190402 | 2018-12-01 | 2025-12-08 | 46.22% | 0 | 0 | 10598.14
388 | TKY199902 | 2019-02-01 | 2024-06-10 | 57.41% | 0 | 0 | 16883.6
389 | TKY199903 | 2019-02-01 | 2024-06-21 | 57.09% | 2390612 | 2390612 | 85012.53 | 3.556%
390 | TKYTOOL | 2017-11-01 | 2050-12-31 | 13.04% | 100 | 100 | -6779.76 | -6780%
391 | TOOLKTY | 2019-09-01 | 2050-12-31 | 7.961% | 100 | 100 | 8398.56 | 8399%
392 | UIRATEDES | 2021-02-01 | 2023-09-01 | 41.61% | 213693 | 213693 | 95644.92 | 44.76%
393 | URDSTSP | 2015-07-01 | 2050-12-31 | 18.77% | 49 | 49 | 1082.56 | 2209%
394 | WD010053X | 2021-06-01 | 2023-12-31 | 28.84% | 6824.07 | 6824.07 | 219.56 | 3.217%
395 | WD020008X | 2021-09-01 | 2022-06-04 | 65.22% | 30620.34 | 30620.34 | 1231.01 | 4.02%
396 | WD020021X | 2021-06-01 | 2023-12-31 | 28.84% | 6824.07 | 6824.07 | 225.85 | 3.31%
397 | WD030008X | 2022-01-01 | 2023-09-30 | 9.105% | 1191034.1 | 1243270.06 | 17188.97 | 1.383%
398 | WD030013X | 2021-06-01 | 2023-12-31 | 28.84% | 6824.07 | 6824.07 | 149.83 | 2.196%
399 | WD040020X | 2021-06-01 | 2023-12-31 | 28.84% | 6824.07 | 6824.07 | 139.42 | 2.043%
400 | WD050019X | 2021-06-01 | 2023-12-31 | 28.84% | 6824.07 | 6824.07 | 149.83 | 2.196%
401 | WD060018X | 2021-06-01 | 2023-12-31 | 28.84% | 6824.07 | 6824.07 | 204.16 | 2.992%
402 | WEBFG | 2019-10-01 | 2022-03-31 | 96.6% | 86692 | 79688 | 22369 | 28.07%
403 | Blank Project ID | [5 empty] | -163810.5
57803994.678