## STAFF-DR-01-004
Status Update for Duke Energy Kentucky Energy Efficiency and Demand Response Programs; 2021-2023
Planned1 Evaluation, Measurement and Verification Activities and Evaluation Reports
Residential Customer Programs | Program/Measure | Last Evaluation completion | Next Evaluation ==> | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023
Low Income Neighborhood | Neighborhood | 2015-02-27 |  |  | M&V | M&V | M&V | Report
Low Income Services | Refrigerator Replace |  | TBD
| Weatherization/Payment Plus | 2013-07-31
My Home Energy Report | MyHER | 2014-02-01 | [8 empty] | M&V | M&V | Report
Residential Energy Assessments | HEHC | 8/7/2020
Residential Smart Saver® | HVAC | 2015-09-21 |  |  |  |  | M&V | M&V | M&V | M&V | Report
| Specialty Bulbs/Online Savings Store | 2015-06-22 |  |  |  | M&V | M&V | M&V | Report
| Water Measures | 9/25/2020*
| Multi-Family | 2019-12-26 | [5 empty] | M&V | M&V | M&V | M&V | M&V | Report
Power Manager |  | 2020-08-13 | [6 empty] | M&V | M&V | M&V | Report
Peak Time Rebate Pilot | Peak Time Rebate | N/A |  | M&V | M&V | M&V | M&V | Report
Non-Residential Customer Programs | Program/Measure |  |  | Q1 2021 | Q2 2021 | Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022 | Q1 2023 | Q2 2023 | Q3 2023 | Q4 2023
Small Business Energy Saver |  | 2017-04-07 | [6 empty] | M&V | Report
Smart $aver® Non-Res, Custom |  | 2016-03-01 |  | M&V | M&V | Report
Smart $aver® Non-Res, Prescriptive |  | 2019-07-24 | [9 empty] | M&V | M&V | M&V | M&V
PowerShare |  | 2017-02-14 |  |  |  |  | M&V | M&V | Report
Pay For Performance |  | N/A | TBD
1 Future Evaluation Report dates are projections only. Actual report dates will vary depending on program participation, time to achieve a significant sample and the time needed to collect adequate data.
* Revised report
LEGEND
M&V | Data collection (surveys, interviews, onsite visits, billing data) and analysis
Report | Evaluation Report