## Exhibit 20
Bluegrass Water Utility Operating Company, Inc.
KY PSC Case No. 2022-00432
Information About Plant Additions for Pro Forma Adjustment
Line Number | NARUC Account | Project Description | Asset Description | Actual or Estimated Start Up Date | Estimated Completion Date | Total Estimated Cost | Estimated Costs by Year |  |  | Costs Incurred to Date
[7 empty] | 2023 | 2024 | 2025
(A) | (B) | (C) | (D) | (E) | (E) | (F) | (G) | (H) | (I) | (J)
1
2 |  | WOODLAND ACRES
3 | 372.000 | MBBR | Blowers and controls for MBBRs | 2023-08-31 | 2024-06-30 | 74300 | 29720 | 44580 | 0 | 0
4 | 311.000 | MBBR | Blower Pad | 2023-08-31 | 2024-06-30 | 1500 | 600 | 900 | 0 | 0
5 | 372.000 | MBBR | Blower discharge header piping, calves, appurtenances | 2023-08-31 | 2024-06-30 | 10000 | 4000 | 6000 | 0 | 0
6 | 372.000 | MBBR | MBBR assemblies (complete) | 2023-08-31 | 2024-06-30 | 98500 | 39400 | 59100 | 0 | 0
7 | 311.000 | MBBR | Electrical distribution for MBBR | 2023-08-31 | 2024-06-30 | 20000 | 8000 | 12000 | 0 | 0
8 | 372.000 | Peracetic Acid Disinfection | Peracetic acid equipment and pad | 2023-08-31 | 2024-06-30 | 17250 | 6900 | 10350 | 0 | 0
9 | 311.000 | Peracetic Acid Disinfection | Electrical distribution for PAA | 2023-08-31 | 2024-06-30 | 5000 | 2000 | 3000 | 0 | 0
10 | 311.000 | Wet Weather Overflow Prevention | Wet Weather Tank and Pad | 2023-08-31 | 2024-06-30 | 16700 | 6680 | 10020 | 0 | 0
11 | 311.000 | Wet Weather Overflow Prevention | Wet Weather Valves, Grinder piping, return piping | 2023-08-31 | 2024-06-30 | 15000 | 6000 | 9000 | 0 | 0
12 | 372.000 | Wet Weather Overflow Prevention | Wet Weather Diffusers | 2023-08-31 | 2024-06-30 | 6000 | 2400 | 3600 | 0 | 0
13 | 372.000 | Wet Weather Overflow Prevention | Wet Weather Blower and Pad | 2023-08-31 | 2024-06-30 | 10000 | 4000 | 6000 | 0 | 0
14 | 311.000 | Wet Weather Overflow Prevention | Wet Weather air piping | 2023-08-31 | 2024-06-30 | 3000 | 1200 | 1800 | 0 | 0
15 | 363.000 | Wet Weather Overflow Prevention | Wet Weather Grinder pump and control | 2023-08-31 | 2024-06-30 | 5000 | 2000 | 3000 | 0 | 0
16 | 311.000 | Wet Weather Overflow Prevention | Electrical distribution for WWOP | 2023-08-31 | 2024-06-30 | 15000 | 6000 | 9000 | 0 | 0
17
18 |  | PERSIMMON RIDGE
19 | 372.000 | MBBR | Airlifts, Blowers, Diffusers, Sieves, Controls | 2023-08-31 | 2024-06-30 | 175000 | 70000 | 105000 | 0 | 0
20 | 372.000 | MBBR | Lagoon Penetrations for MBBR, Suction and Discharge | 2023-08-31 | 2024-06-30 | 20000 | 8000 | 12000 | 0 | 0
21 | 311.000 | MBBR | MBBR Suction and Discharge yard piping | 2023-08-31 | 2024-06-30 | 15000 | 6000 | 9000 | 0 | 0
22 | 311.000 | MBBR | Air piping to Chlorine contact Tank | 2023-08-31 | 2024-06-30 | 10500 | 4200 | 6300 | 0 | 0
23 | 372.000 | MBBR | Airlifts, Blowers, Diffusers, Sieves, Controls | 2023-08-31 | 2024-06-30 | 7500 | 3000 | 4500 | 0 | 0
24 | 311.000 | Site Work | Miscellaneous Electrical Distribution | 2023-08-31 | 2024-06-30 | 25000 | 10000 | 15000 | 0 | 0
25
26 |  | HERRINGTON HAVEN
27 | 372.000 | MBBR | Blowers and Controls for New MBBR Assemblies (2 each) | 2023-08-31 | 2024-06-30 | 30400 | 12160 | 18240 | 0 | 0
28 | 311.000 | MBBR | Blower Pad | 2023-08-31 | 2024-06-30 | 1500 | 600 | 900 | 0 | 0
29 | 372.000 | MBBR | Blower Discharge Header Piping, Valves, Appurtenances | 2023-08-31 | 2024-06-30 | 3500 | 1400 | 2100 | 0 | 0
30 | 372.000 | MBBR | MBBR Assemblies Complete (3 each) | 2023-08-31 | 2024-06-30 | 68450 | 27380 | 41070 | 0 | 0
31 | 311.000 | MBBR | Electrical Distribution for MBBR Treatment System | 2023-08-31 | 2024-06-30 | 7500 | 3000 | 4500 | 0 | 0
32 | 372.000 | Peracetic Acid Disinfection | PAA Equipment and Pad | 2023-08-31 | 2024-06-30 | 17250 | 6900 | 10350 | 0 | 0
33 | 311.000 | Peracetic Acid Disinfection | Electrical Distribution for PAA Disinfection System | 2023-08-31 | 2024-06-30 | 5000 | 2000 | 3000 | 0 | 0
34 | 311.000 | Solids Processing (Digester) System | Digester Tank and Pad | 2023-08-31 | 2024-06-30 | 16450 | 6580 | 9870 | 0 | 0
35 | 311.000 | Solids Processing (Digester) System | Digester Valves, Decant Piping, Grinder FM Piping, Air Piping | 2023-08-31 | 2024-06-30 | 15000 | 6000 | 9000 | 0 | 0
36 | 372.000 | Solids Processing (Digester) System | Digester Diffusers | 2023-08-31 | 2024-06-30 | 6000 | 2400 | 3600 | 0 | 0
37 | 372.000 | Solids Processing (Digester) System | Digester Blower and Blower Pad | 2023-08-31 | 2024-06-30 | 10000 | 4000 | 6000 | 0 | 0
38 | 311.000 | Solids Processing (Digester) System | Digester WAS/RAS Piping | 2023-08-31 | 2024-06-30 | 5000 | 2000 | 3000 | 0 | 0
39 | 363.000 | Solids Processing (Digester) System | Digester System Grinder Pump and Control Panel | 2023-08-31 | 2024-06-30 | 5000 | 2000 | 3000 | 0 | 0
40 | 311.000 | Solids Processing (Digester) System | Electrical Distribution for Digester System | 2023-08-31 | 2024-06-30 | 12500 | 5000 | 7500 | 0 | 0
41 | 311.000 | General Plant | All Weather Gravel Access Road for All Three New Systems | 2023-08-31 | 2024-06-30 | 3000 | 1200 | 1800 | 0 | 0
42
43
44
45 |  |  | TOTAL PROPOSED PLANT ADDITIONS |  |  | 756800 | 302720 | 454080 | 0 | 0
46
47
48