## Attachment 1
Reconciliation
| 8737865.3846 |  | Original QIP 3 plant additions forecast based on 13-month average as of June 30, 2023.
| 9170834.6154 | A | Update QIP 3 plant additions from 13-month average to terminal balance as of June 30, 2023.
| 3570364.63 | B | Update QIP 3 plant additions for July 2022 to January 2023 with actuals and update forecast for February to June 2023.
| 7908526.73 | C | Add QIP 1 / QIP 2 post-in-service spend for July 2022 to January 2023.
| 29387591.36 | D | Total plant additions during QIP 3 period.
A | Update QIP 3 plant additions from 13-month average to terminal balance as of June 30, 2023:
13-month
| Terminal | Average
| 2023-06-30 | 2023-06-30 | Update
| 46214742.92 | 37043908.3046 | 9170834.6154 | A
B | Update QIP 3 plant additions for July 2022 to January 2023 with actuals and update forecast for February to June 2023:
|  |  |  | 2022 | [5 empty] | 2023
|  |  |  | July | August | September | October | November | December | January | February | March | April | May | June | Total
|  |  | Original QIP 3 forecast for July 2022 to June 2023 | 511450 | 1794050 | 2862000 | 1547600 | 1391250 | 834750 | 641300 | 954000 | 1799350 | 2544000 | 1722500 | 1306450 | 17908700
|  |  | Actuals for July 2022 to January 2023 & | 0 | 603291.99 | 1242542.25 | 1397990.76 | 1870611.77 | 1050232.84 | 1232219.02 | 642750 | 2183105 | 4545917 | 3792106 | 2918298 | 21479064.63
Forecast update for July 2022 to June 2023
|  |  |  | 2023 June: Update | 3570364.63 | B
C | Add QIP 1 / QIP 2 post-in-service spend for July 2022 to January 2023:
|  |  |  | 2022 | [5 empty] | 2023
|  |  |  | July | August | September | October | November | December | January
|  |  | QIP 1 | 0 | 0 | -2731.24 | -18217.46 | 0 | 0 | 0
|  |  | QIP 2 | 1495115 | 1915566.25 | 1834249.57 | 1743878.28 | 212462.6 | 449708.93 | 278494.8
|  |  | Total | 1495115 | 1915566.25 | 1831518.33 | 1725660.82 | 212462.6 | 449708.93 | 278494.8 |  |  |  |  | 0 | 7908526.73 | C
D | Total plant additions during QIP 3 period:
|  |  |  | 2022 | [5 empty] | 2023
|  |  |  | July | August | September | October | November | December | January | February | March | April | May | June | Total
|  |  | Actuals for July 2022 to January 2023 & | 1495115 | 2518858.24 | 3074060.58 | 3123651.58 | 2083074.37 | 1499941.77 | 1510713.82 | 642750 | 2183105 | 4545917 | 3792106 | 2918298 | 29387591.36 | D
Forecast update for July 2022 to June 2023