## DR Exhibit August 2023 Year 2
[5 empty] | End of QIP 2 Period |  | QIP 3 Midyear Reconciliation (Post-In-Service Spend) |  | End of QIP 3 Period (Post-In-Service Spend) |  |  | Reason for Variance
QIP Year | Project Name | WBS Number(s) | Total Linear Feet | Estimated Project Cost in QIP Application filed March 26, 2021 | Total Project Cost as of June 30, 2022 | Variance as of June 30, 2022 | Plant Additions July 2022-January 2023 | Variance including July 2022-January 2023 | Plant Additions February 2023-June 2023 | Variance including February 2023-June 2023 | Total Project Cost as of June 30, 2023
2 | Thistleton Circle | R12-02B2.20-P-0020 | 276 | 73140 | 32019 | -41121 | 0 | -41121 | 0 | -41121 | 32019 | Reason for Variance: Actual linear footage installed was less than estimated. Water main installation work performed by Kentucky American Water crews.
2 | Crosskeys Court | R12-02B2.20-P-0021 | 230 | 60950 | 50800.63 | -10149.37 | 0 | -10149.37 | 0 | -10149.37 | 50800.63 | Reason for Variance: Water main installation work was performed by Kentucky American Water crews. Actual linear footage installed was less than estimated, and the water main was able to be installed largely in the utility strip rather than under pavement, both of which resulted in cost savings.
2 | Croyden Court | R12-02B2.20-P-0022 | 482 | 127730 | 159471.45 | 31741.45 | 0 | 31741.45 | 0 | 31741.45 | 159471.45 | Reason for Variance: Estimated cost included 4' paving width; actual pavement required was full curb-to-curb width plus all cul-de-sacs. Water main installation work performed by Kentucky American Water crews.
2 | Fairway - Phase I | R12-02B2.20-P-0010 R12-02B2.21-P-0050 R12-02B2.21-P-0051 | 2940 | 775000 | 1191831.69 | 416831.69 | 84591 | 501422.69 | 0 | 501422.69 | 1276422.69 | Reason for Variance: Additional cold patch (temporary asphalt) was required along the entire length of the project prior to final pavement restoration. Proposed connection points along Henry Clay Blvd required full intersection pavement restoration. More service lines required replacement compared to estimated.
2 | Wyatt Avenue | R12-02B2.20-P-0024 R12-02B2.21-P-0028 R12-02B2.21-P-0029 R12-02B2.21-P-0030 | 4050 | 1532500 | 1134089.59 | -398410.41 | -1941 | -400351.41 | 222828 | -177523.41 | 1354976.59 | Reason for Variance: Actual linear footage installed was less than estimated. Amount of pavement restoration required was in line with pavement restoration estimates.
2 | Bluegrass/Highlawn | R12-02B2.20-P-0026 | 1017 | 625000 | 359422.62 | -265577.38 | -2762 | -268339.38 | 0 | -268339.38 | 356660.62 | Reason for Variance: Actual linear footage installed was less than estimated. The paving for this project was being cost-shared with LFUCG resulting in cost savings.
2 | Codell Drive | R12-02B2.20-P-0027 R12-02B2.21-P-0036 R12-02B2.21-P-0037 | 5476 | 1312500 | 1408343.25 | 95843.25 | 251917 | 347760.25 | 7919 | 355679.25 | 1668179.25 | Reason for Variance: Approximately 250 additional linear feet of main were installed compared to estimated. Amount of pavement restoration required was in line with pavement restoration estimates.
2 | N Ashland/Aurora | R12-02B2.20-P-0028 R12-02B2.21-P-0034 R12-02B2.21-P-0035 | 5255 | 1000000 | 698858.18 | -301141.82 | 791595 | 490453.18 | 24858 | 515311.18 | 1515311.18 | Reason for Variance: Approximately 800 additional linear feet of main were installed compared to estimated.
2 | National Avenue | R12-02B2.20-P-0029 | 3100 | 875000 | 806460.65 | -68539.35 | -59034 | -127573.35 | 201033 | 73459.65 | 948459.65 | Reason for Variance: Final restoration was delayed until spring 2023, and the contractor was required to maintain temporary cold patch that was not included in their original bid price.
2 | Whitney/Ash | R12-02B2.20-P-0030 R12-02B2.21-P-0039 R12-02B2.21-P-0040 R12-02B2.21-P-0041 R12-02B2.21-P-0042 R12-02B2.21-P-0043 | 6720 | 1650000 | 2017587 | 367587 | 1002936 | 1370523 | -176664 | 1193859 | 2843859 | Reason for Variance: Approximately 120 additional linear feet of main were installed compared to estimated. Additional cold patch (temporary asphalt) was required along the entire length of the project prior to final pavement restoration. Nearly all service lines required replacement compared to estimated.
2 | Clays Mill Road - Phase II | R12-02B2.21-P-0018 R12-02B2.21-P-0019 R12-02B2.21-P-0020 | 7220 | 1575000 | 1804892.25 | 229892.25 | 259317 | 489209.25 | 81 | 489290.25 | 2064290.25 | Reason for Variance: Additional main installation costs required due to a storm sewer alignment change. Additional costs incurred on project to uncover valve boxes covered by LFUCG's roadway contractor during project. The paving for this project is being cost-shared with LFUCG.
2 | Montclair Drive | R12-02B2.21-P-0002 | 2200 | 550000 | 527191.68 | -22808.32 | 245670 | 222861.68 | 0 | 222861.68 | 772861.68 | Reason for Variance: Curb-to-curb paving was required, although the paving for this project was cost-shared with LFUCG.
2 | Summit Drive | R12-02B2.21-P-0003 R12-02B2.21-P-0052 R12-02B2.21-P-0053 | 2850 | 725000 | 788951.81 | 63951.81 | 148250 | 212201.81 | 0 | 212201.81 | 937201.81 | Reason for Variance: Kentucky American Water encountered several brittle house service lines that failed upon re-connection. Curb-to-curb paving was required, although the paving for this project was cost-shared with LFUCG.
2 | Valley Farm | R12-02B2.21-P-0015 | 5306 | 1350000 | 1437053.61 | 87053.61 | 181753 | 268806.61 | 0 | 268806.61 | 1618806.61 | Reason for Variance: Estimated cost included 5' paving width; actual pavement required was full lane width (~8').
2 | Colchester/Barksdale | R12-02B2.21-P-0016 R12-02B2.21-P-0031 R12-02B2.21-P-0032 R12-02B2.21-P-0033 | 3555 | 925000 | 911958.46 | -13041.54 | 284044 | 271002.46 | 0 | 271002.46 | 1196002.46 | Reason for Variance: Actual linear footage installed was less than estimated. Estimated paving cost included 5' paving width; actual pavement required was full lane width (~8').
2 | Campbell Lane | R12-02B2.21-P-0004 | 507 | 275000 | 222708 | -52292 | 25405.32 | -26886.68 | -6155 | -33041.68 | 241958.32 | Reason for Variance: Actual linear footage installed was less than estimated.
2 | Westgate/Hamilton Park | R12-02B2.21-P-0005 R12-02B2.21-P-0054 | 3600 | 900000 | 609346.69 | -290653.31 | 1288405 | 997751.69 | 6477 | 1004228.69 | 1904228.69 | Reason for Variance: Estimated paving cost included 5' paving width; actual pavement required was full curb-to-curb in most areas.
2 | Lancelot | R12-02B2.21-P-0007 R12-02B2.21-P-0055 | 2500 | 617500 | 612821.53 | -4678.47 | 497688 | 493009.53 | -9199 | 483810.53 | 1101310.53 | Reason for Variance: Estimated paving cost included 5' paving width; actual pavement required was full curb-to-curb in most areas.
2 | Kilrush/Caywood | R12-02B2.21-P-0008 R12-02B2.21-P-0056 R12-02B2.21-P-0057 R12-02B2.21-P-0058 | 5239 | 1567500 | 1012319 | -555181 | 1155123.39 | 599942.39 | -13180 | 586762.39 | 2154262.39 | Reason for Variance: Estimated paving cost included 5' paving width; actual pavement required "parking lane widths" of ~6' plus all intersections and full cul-de-sac bulbs.
2 | Merrimac/Fogo/Crewe | R12-02B2.21-P-0012 R12-02B2.21-P-0044 R12-02B2.21-P-0045 | 3041 | 860000 | 484693.25 | -375306.75 | 966571 | 591264.25 | -68966 | 522298.25 | 1382298.25 | Reason for Variance: Estimated paving cost included 5' paving width; actual pavement required "parking lane widths" of ~6' plus all intersections and full cul-de-sac bulbs.
2 | Tisdale/Fraserdale | R12-02B2.21-P-0013 R12-02B2.21-P-0059 R12-02B2.21-P-0060 | 5056 | 1322500 | 1575172.62 | 252672.62 | 128819 | 381491.62 | 0 | 381491.62 | 1703991.62 | Reason for Variance: Estimated paving cost included 5' paving width; actual pavement required "parking lane widths" of ~6' plus all intersections and full cul-de-sac bulbs.
2 | Montavesta Road | R12-02B2.21-P-0009 R12-02B2.21-P-0046 R12-02B2.21-P-0047 R12-02B2.21-P-0048 R12-02B2.21-P-0049 | 3904 | 1087500 | 374877.99 | -712622.01 | 443507 | -269115.01 | 78315 | -190800.01 | 896699.99 | Reason for Variance: Water main installation work was performed by Kentucky American Water crews. Some parts of this project were pavement cost-shared with LFUCG.
[5 empty] | End of QIP 2 Period |  | QIP 3 Midyear Reconciliation (Post-In-Service Spend) |  | End of QIP 3 Period (Post-In-Service Spend)
|  |  | Total Linear Feet / Total Miles | Estimated Project Cost in QIP Application filed March 26, 2021 | Total Project Cost as of June 30, 2022 | Variance as of June 30, 2022 | Plant Additions July 2022-January 2023 | Variance including July 2022-January 2023 | Plant Additions February 2023-June 2023 | Variance including February 2023-June 2023 | Total Project Cost as of June 30, 2023
|  |  | 74524 | 19786820 | 18220870.95 | -1565949.05 | 7691854.71 | 6125905.66 | 267347 | 6393252.66 | 26180072.66
14.1144

## DR Exhibit August 2023 Year 3
[5 empty] | QIP 3 Midyear Reconciliation |  | End of QIP 3 Period |  |  | QIP 3 Midyear Reforecast |  | Reason for Variance
QIP Year | Project Name | WBS Number(s) | Total Linear Feet | Estimated Project Cost in QIP Application filed March 1, 2022 | Plant Additions July 2022-January 2023 | Variance including July 2022-January 2023 | Plant Additions February 2023-June 2023 | Variance including February 2023-June 2023 | Total Project Cost as of June 30, 2023 | Estimated Project Cost in QIP 3 Midyear Reconciliation filed March 1, 2023 | Variance including February 2023-June 2023
3 | Aylesford | R12-02B2.21-P-0006 | 1500 | 397500 | 0 | -397500 | 360060.22 | -37439.78 | 360060.22 | 455816 | -95755.78 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Linden Walk/Rose | R12-02B2.21-P-0061 | 1900 | 503500 | 0 | -503500 | 425129.51 | -78370.49 | 425129.51 | 549210 | -124080.49 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Birkenhead Dr/Ct | R12-02B2.21-P-0014 | 1700 | 450500 | 694794.89 | 244294.89 | -7104.14 | 237190.75 | 687690.75 | 450500 | 237190.75 | Reason for Variance: Estimated paving cost included 8' paving width; actual pavement required was in line with widths but also included intersections and full cul-de-sac bulbs.
3 | Cardiff Dr | R12-02B2.21-P-0062 | 1100 | 291500 | 307524.01 | 16024.01 | -5356.26 | 10667.75 | 302167.75 | 291500 | 10667.75 | Reason for Variance: Estimated paving cost included 8' paving width; actual pavement required was in line with widths but also included intersections and full cul-de-sac bulbs.
3 | Aldershot Dr | R12-02B2.21-P-0063 | 1200 | 318000 | 389413.88 | 71413.88 | -4320.32 | 67093.56 | 385093.56 | 318000 | 67093.56 | Reason for Variance: Estimated paving cost included 8' paving width; actual pavement required was in line with widths but also included intersections and full cul-de-sac bulbs.
3 | Cardigan Ct | R12-02B2.21-P-0064 | 500 | 132500 | 195817.09 | 63317.09 | -12909.01 | 50408.08 | 182908.08 | 132500 | 50408.08 | Reason for Variance: Estimated paving cost included 8' paving width; actual pavement required was in line with widths but also included intersections and full cul-de-sac bulbs.
3 | Colonial Dr | R12-02B2.21-P-0010 | 2400 | 636000 | 538911.38 | -97088.62 | 44084.11 | -53004.51 | 582995.49 | 636000 | -53004.51 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023. Columbia Gas and LFUCG sanitary sewer initiated projects in this area and paving coordination will occur.
3 | Standish Way | R12-02B2.21-P-0065 | 2200 | 583000 | 266133.53 | -316866.47 | 33497.41 | -283369.06 | 299630.94 | 583000 | -283369.06 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023. Columbia Gas and LFUCG sanitary sewer initiated projects in this area and paving coordination will occur.
3 | Bryanwood Pkwy | R12-02B2.21-P-0017 | 3100 | 821500 | 0 | -821500 | 696820.72 | -124679.28 | 696820.72 | 905627 | -208806.28 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Gaines Village Dr | R12-30B2.22-P-0002 | 2550 | 675750 | 0 | -675750 | 395641.13 | -280108.87 | 395641.13 | 629080 | -233438.87 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Grace Dr | R12-02B2.21-P-0067 | 700 | 185500 | 0 | -185500 | 239750.5 | 54250.5 | 239750.5 | 185500 | 54250.5 | Reason for Variance: Estimated paving cost included 8' paving width; actual pavement required was in line with widths but also included intersection and full cul-de-sac bulb.
3 | Ox Hill Dr | R12-02B2.21-P-0068 | 700 | 185500 | 0 | -185500 | 169278.6 | -16221.4 | 169278.6 | 235055 | -65776.4 | Reason for Variance: Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Stephen Foster Dr/Versie Ct/Jannelle Ct | R12-02B2.21-P-0069 | 2420 | 641300 | 0 | -641300 | 545965.7 | -95334.3 | 545965.7 | 672255 | -126289.3 | Reason for Variance: Project is still underway, pending completion of service line and restoration work in summer 2023. One additional valve was required when an existing valve broke in the closed position.
3 | River Park Dr | R12-02B2.21-P-0070 | 1950 | 516750 | 525863.95 | 9113.95 | 503417.45 | 512531.4 | 1029281.4 | 516750 | 512531.4 | Reason for Variance: Pavement extents and temporary restoration greater than planned. This area is a potential paving cost-share with LFUCG.
3 | Golden Gate Park | R12-02B2.21-P-0071 | 500 | 132500 | 74704.83 | -57795.17 | 131734.34 | 73939.17 | 206439.17 | 132500 | 73939.17 | Reason for Variance: Pavement extents and temporary restoration greater than planned. This area is a potential paving cost-share with LFUCG.
3 | Atokad Park | R12-02B2.21-P-0072 | 650 | 172250 | 96973.49 | -75276.51 | 160471.86 | 85195.35 | 257445.35 | 172250 | 85195.35 | Reason for Variance: Pavement extents and temporary restoration greater than planned. This area is a potential paving cost-share with LFUCG.
3 | Beulah Park Ct | R12-02B2.21-P-0073 | 350 | 92750 | 71897.22 | -20852.78 | 100474.37 | 79621.59 | 172371.59 | 92750 | 79621.59 | Reason for Variance: Additional 8" tap not included in original estimate. Pavement extents and temporary restoration greater than planned. This area is a potential paving cost-share with LFUCG.
3 | Ak Sar Ben Park | R12-02B2.21-P-0074 | 800 | 212000 | 105421.37 | -106578.63 | 196722.68 | 90144.05 | 302144.05 | 212000 | 90144.05 | Reason for Variance: Pavement extents and temporary restoration greater than planned. This area is a potential paving cost-share with LFUCG.
3 | Ascot Park | R12-02B2.21-P-0075 | 750 | 198750 | 102259.91 | -96490.09 | 172394.26 | 75904.17 | 274654.17 | 198750 | 75904.17 | Reason for Variance: Pavement extents and temporary restoration greater than planned. This area is a potential paving cost-share with LFUCG.
3 | Kentucky Ave South | R12-02B2.21-P-0076 | 1500 | 397500 | 888523.24 | 491023.24 | 126320.33 | 617343.57 | 1014843.57 | 397500 | 617343.57 | Reason for Variance: Contractor bids were higher than originally estimated. Nearly all service lines along this road required full replacement and additional plumbing services. This area served as a temporary concrete restoration pilot project with LFUCG.
3 | Kentucky Ave North | R12-02B2.21-P-0077 | 1570 | 416050 | 513729.84 | 97679.84 | 236934.24 | 334614.08 | 750664.08 | 416050 | 334614.08 | Reason for Variance: Contractor bids were higher than originally estimated. Nearly all service lines along this road required full replacement and additional plumbing services. This area served as a temporary concrete restoration pilot project with LFUCG.
3 | Woodland Ave North | R12-02B2.21-P-0078 | 1600 | 424000 | 628073.25 | 204073.25 | 153724.36 | 357797.61 | 781797.61 | 424000 | 357797.61 | Reason for Variance: Contractor bids were higher than originally estimated. Nearly all service lines along this road required full replacement and additional plumbing services. This area served as a temporary concrete restoration pilot project with LFUCG.
3 | American Ave | R12-02B2.21-P-0079 | 2100 | 556500 | 329109.71 | -227390.29 | 326310.08 | 98919.79 | 655419.79 | 556500 | 98919.79 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Southern Ave | R12-02B2.21-P-0080 | 650 | 172250 | 64033.44 | -108216.56 | 68103.52 | -40113.04 | 132136.96 | 172250 | -40113.04 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Camden Ave | R12-02B2.21-P-0081 | 550 | 145750 | 53525.65 | -92224.35 | 67131.72 | -25092.63 | 120657.37 | 145750 | -25092.63 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Stanley Ave | R12-02B2.21-P-0082 | 400 | 106000 | 55201.05 | -50798.95 | 26416.5 | -24382.45 | 81617.55 | 106000 | -24382.45 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Lone Oak Dr/Southbend Dr | R12-02B2.21-P-0083 | 1750 | 463750 | 244907.92 | -218842.08 | 99141.03 | -119701.05 | 344048.95 | 463750 | -119701.05 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Greenwood Ave | R12-02B2.21-P-0084 | 750 | 198750 | 0 | -198750 | 0 | -198750 | 0 | 198750 | -198750 | Reason for Variance: Project was delayed to future QIP period due to LFUCG roadway access restrictions.
3 | Bradley Ct | R12-02B2.21-P-0085 | 840 | 222600 | 0 | -222600 | 0 | -222600 | 0 | 222600 | -222600 | Reason for Variance: Project was delayed to future QIP period due to LFUCG roadway access restrictions.
3 | Douglas Ave | R12-02B2.21-P-0086 | 1450 | 384250 | 0 | -384250 | 382975.25 | -1274.75 | 382975.25 | 451873 | -68897.75 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Chiles Ave | R12-02B2.21-P-0087 | 1200 | 318000 | 0 | -318000 | 294667.95 | -23332.05 | 294667.95 | 359985 | -65317.05 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023. An unplanned storm sewer conflict also added cost.
3 | Breathitt Ave | R12-02B2.21-P-0088 | 1200 | 318000 | 0 | -318000 | 310719.83 | -7280.17 | 310719.83 | 366218 | -55498.17 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Florence Ave | R12-02B2.21-P-0089 | 1300 | 344500 | 0 | -344500 | 236914.23 | -107585.77 | 236914.23 | 234233 | 2681.23 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Woodstock Cir | R12-02B2.21-P-0090 | 500 | 132500 | 0 | -132500 | 108719.57 | -23780.43 | 108719.57 | 172975 | -64255.43 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Woodside Way/Ct | R12-02B2.21-P-0091 | 600 | 159000 | 0 | -159000 | 153541.46 | -5458.54 | 153541.46 | 143230 | 10311.46 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Malabu Cir | R12-02B2.21-P-0092 | 900 | 238500 | 0 | -238500 | 202221.84 | -36278.16 | 202221.84 | 271987 | -69765.16 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Tanforan Dr/Ct | R12-02B2.21-P-0093 | 2200 | 583000 | 0 | -583000 | 455710.53 | -127289.47 | 455710.53 | 633005 | -177294.47 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Waterford Park | R12-02B2.21-P-0094 | 600 | 159000 | 0 | -159000 | 131918.38 | -27081.62 | 131918.38 | 169711 | -37792.62 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Narragansett Park | R12-02B2.21-P-0095 | 350 | 92750 | 0 | -92750 | 103238.68 | 10488.68 | 103238.68 | 112660 | -9421.32 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Oaklawn/Maywood Park | R12-02B2.21-P-0096 | 650 | 172250 | 0 | -172250 | 198383.06 | 26133.06 | 198383.06 | 195077 | 3306.06 | Reason for Variance: Contractor bids were higher than originally estimated. Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Canonero/Gunbow/Personality | R12-02B2.21-P-0097 | 1340 | 355100 | 370590 | 15490 | 495291.68 | 510781.68 | 865881.68 | 355100 | 510781.68 | Reason for Variance: Contractor bids were higher than originally estimated. Pavement extents greater than planned.
3 | Moundview Ct | R12-02B2.21-P-0098 | 920 | 243800 | 0 | -243800 | 220168.58 | -23631.42 | 220168.58 | 262798 | -42629.42 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Wood Valley Ct | R12-02B2.21-P-0099 | 910 | 241150 | 0 | -241150 | 241815.14 | 665.14 | 241815.14 | 262071 | -20255.86 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Derby Dr | R12-02B2.21-P-0100 | 890 | 235850 | 39668 | -196182 | 207999.25 | 11817.25 | 247667.25 | 235850 | 11817.25 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Headley Ave | R12-02B2.21-P-0101 | 1520 | 402800 | 0 | -402800 | 485743.06 | 82943.06 | 485743.06 | 462821 | 22922.06 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023. Change order item for an additional valve excavation and change in connection type (from cut/cap to use of tee fittings).
3 | Jane St | R12-02B2.22-P-0002 | 700 | 185500 | 0 | -185500 | 243562.39 | 58062.39 | 243562.39 | 266007 | -22444.61 | Reason for Variance: Additional cast iron main found in the area and added to scope of work. Additional 8" tap required. Project is still underway, pending completion of restoration work in summer 2023.
3 | Ferguson St/Martin St | R12-02B2.22-P-0003 | 860 | 227900 | 0 | -227900 | 185397.71 | -42502.29 | 185397.71 | 286055 | -100657.29 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Coolidge St | R12-02B2.22-P-0004 | 500 | 132500 | 0 | -132500 | 111448.24 | -21051.76 | 111448.24 | 153192 | -41743.76 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Anderson St | R12-02B2.22-P-0005 | 680 | 180200 | 0 | -180200 | 136929.03 | -43270.97 | 136929.03 | 358409 | -221479.97 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Warren Ct | R12-02B2.22-P-0006 | 350 | 92750 | 0 | -92750 | 103510.23 | 10760.23 | 103510.23 | 92750 | 10760.23 | Reason for Variance: Slight additions to materials and pavement quantities.
3 | Chrysalis Ct | R12-02B2.22-P-0007 | 350 | 92750 | 106679 | 13929 | -513.06 | 13415.94 | 106165.94 | 92750 | 13415.94 | Reason for Variance: Slight additions to materials and pavement quantities.
3 | Kenton St | R12-02B2.22-P-0008 | 800 | 212000 | 0 | -212000 | 228992.15 | 16992.15 | 228992.15 | 238198 | -9205.85 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Campbell St | R12-02B2.22-P-0009 | 800 | 212000 | 0 | -212000 | 225831.29 | 13831.29 | 225831.29 | 247559 | -21727.71 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
3 | Toner St/Sheila Ct/Harken Ct | R12-02B2.22-P-0010 | 900 | 238500 | 330838 | 92338 | -1959.77 | 90378.23 | 328878.23 | 238500 | 90378.23 | Reason for Variance: Nearly all service lines along this road required full replacement and additional plumbing services. This area is a historic area and additional protection measures were needed during restoration.
3 | Elsmere Park | R12-02B2.22-P-0011 | 850 | 225250 | 402293 | 177043 | 219928.56 | 396971.56 | 622221.56 | 225250 | 396971.56 | Reason for Variance: Nearly all service lines along this road required full replacement and additional plumbing services. This area is a historic area and additional protection measures were needed during restoration. Specialty curb sections and concrete pavement were required per LFUCG Historic Preservation.
3 | Briarwood Dr | R12-02B2.22-P-0012 | 2250 | 596250 | 0 | -596250 | 596189.78 | -60.22 | 596189.78 | 743795 | -147605.22 | Reason for Variance: Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Redwood Dr/Cir | R12-02B2.22-P-0013 | 3000 | 795000 | 0 | -795000 | 533937.63 | -261062.37 | 533937.63 | 752072 | -218134.37 | Reason for Variance: Project is still underway, pending completion of service line and restoration work in summer 2023.
3 | Edinburgh Ct | R12-02B2.20-P-0023 | 330 | 87450 | 0 | -87450 | 52113.6 | -35336.4 | 52113.6 | 87450 | -35336.4 | Reason for Variance: Project is still underway, pending completion of restoration work in summer 2023.
[5 empty] | QIP 3 Midyear Reconciliation |  | End of QIP 3 Period |  |  | QIP 3 Midyear Reforecast
|  |  | Total Linear Feet / Total Miles | Estimated Project Cost in QIP Application filed March 1, 2022 | Plant Additions July 2022-January 2023 | Variance including July 2022-January 2023 | Plant Additions February 2023-June 2023 | Variance including February 2023-June 2023 | Total Project Cost as of June 30, 2023 | Estimated Project Cost in QIP 3 Midyear Reconciliation filed March 1, 2023 | Variance including February 2023-June 2023
|  |  | 67580 | 17908700 | 7396887.65 | -10511812.35 | 12115231.18 | 1603418.83 | 19512118.83 | 18943774 | 568344.83
12.7992