## Sheet1
Schedule C
Taylor County Rural Electric Cooperative Corporation
Case No. 2023-00147
Construction Projects
For Five Years ended December 31, 2022
|  |  |  | Variance |  |  | Total | Total | Variance | Date | Date
|  | Annual Actual Cost | Annual Original Budget | In | Variance | Percent | Actual | Budget | In | Original | Original | Date | Date
Project | Project |  |  | Dollars | As | Of | Project | Project | Dollars | Budget | Budget | Actual | Actual
No. | Title/Description |  |  | Under/(Over) | Percent | Budget | Cost | Cost | Under/(Over) | Start | End | Start | End
19-030201 | DC 3PH 3/0ACSR-336ASCR VAUGH CRV
| 123099 Work Plan 302.01 Vaughn Crv | 156721.67 | 105000 | -51721.67 | 49.26% |  | 156721.67 | 105000 | -51721.67 | 2019-01-01 | 2021-12-31 | 2019-07-24 | 2020-01-31
19-030301 | SVILLE OLD MIX - 3PH 336ACSR
| 122134 Summersville Sub Ret RECC | -1297.5 |  |  |  |  | -1297.5 |  |  | 2019-01-01 | 2021-12-31 | 2019-03-15 | 2020-01-31
| 122150 Summersville Sub Ret Part I | 3579.97 |  |  |  |  | 3579.97 |  |  | 2019-01-01 | 2021-12-31 | 2019-03-07 | 2019-10-31
| 122153 Summersville Sub OH Part II | 172.79 |  |  |  |  | 172.79 |  |  | 2019-01-01 | 2021-12-31 | 2019-03-07 | 2020-07-31
| 122993 Summersville Sub Prep Mobil | 2151.53 |  |  |  |  | 2151.53 |  |  | 2019-01-01 | 2021-12-31 | 2019-07-08 | 2019-07-31
| 123043 AMR Sville Sub Equipment | 10380.07 |  |  |  |  | 10380.07 |  |  | 2019-01-01 | 2021-12-31 | 2019-07-17 | 2020-10-31
|  | 14986.86 | 149600 | 134613.14 | -89.98% |  | 14986.86 | 149600 | 134613.14
19-030401 | MCKNNY MIXED OLD - 3PH 336ACSR
| 125283 Work Plan 304.01 Mcknny Pl | 6446.2 |  |  |  |  | 6446.2 |  |  | 2019-01-01 | 2021-12-31 | 2020-07-28 | 2021-04-30
| 125284 Work Plan 304.01 Mcknny UG | 59863.31 |  |  |  |  | 59863.31 |  |  | 2019-01-01 | 2021-12-31 | 2020-07-28 | 2021-04-30
| 125285 Work Plan 304.01 Mcknny RET | 5840.24 |  |  |  |  | 5840.24 |  |  | 2019-01-01 | 2021-12-31 | 2020-07-28 | 2021-06-30
|  | 72149.75 | 102000 | 29850.25 | -29.26% |  | 72149.75 | 102000 | 29850.25
19-030901 | DNNVLL 3PH 4ACSR - 3PH 336ACSR
| 123490 Work Plan 309.01 Dnnvll | 177587.18 | 136000 | -41587.18 | 30.58% |  | 177587.18 | 136000 | -41587.18 | 2019-01-01 | 2021-12-31 | 2019-09-23 | 2021-02-28
19-031302 | NEW CONRD 4ACSR - 3 PH 1/0ACSR
| 127103 Work Plan 313.02 | 92595.22 | 45000 | -47595.22 | 105.8% |  | 92595.22 | 45000 | -47595.22 | 2019-01-01 | 2021-12-31 | 2021-06-24 | 2022-12-31
19-031401 | CONTOWN - CKT1&2 - 3PH336ACSR
| 121861 Work Plan 314,01, 314.02 UG Contown | 42918.07 |  |  |  |  | 42918.07 |  |  | 2019-01-01 | 2021-12-31 | 2018-12-28 | 2019-08-31
| 121863 Work Plan 314.02 Contown 1&2 | 391028.39 |  |  |  |  | 391028.39 |  |  | 2019-01-01 | 2021-12-31 | 2018-12-28 | 2020-05-31
|  | 433946.46 | 315000 | -118946.46 | 37.76% |  | 433946.46 | 315000 | -118946.46
|  | 947987.14 | 852600 | -95387.14 | 11.19% |  | 947987.14 | 852600 | -95387.14