## DRR Projected Projects
Description | District | 5 yr Estimate | 2024 | 2025 | 2026 | 2027 | 2028
Total DRR Projects | Total | 165908800 | 19000000 | 35288300 | 32881000 | 38733000 | 40006500
TOR Enhanced ROW Widening | Total | 60000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000
Additional Tie Lines | Total | 10580000 | 1000000 | 3325000 | 3192000 | 1463000 | 1600000
DACR Projects and Recloser Modernization | Total | 27812800 | 1000000 | 4003300 | 8911000 | 0 | 13898500
Additional New Distribution Substation Sources | Total | 52476000 | 3000000 | 11970000 | 4788000 | 22610000 | 10108000
Asset Renewal/Storm Hardening or Resiliency | Total | 15040000 | 2000000 | 3990000 | 3990000 | 2660000 | 2400000
Additional Tie Lines (List of Larger Projects) | Total | 10580000.241 | 1000000 | 3325000 | 3192000 | 1463000 | 1600000.241
Additional Tie Lines - Ashland | Sub-total | 1000000 | 1000000 | 0 | 0 | 0 | 0
Hayward Haldeman to Olive Hill Globe along Trumbo Rd and Hwy60 | Ashland | 1000000 | 1000000 | 0 | 0 | 0 | 0
Additional Tie Lines- Hazard | Sub-total | 7316999.921 | 0 | 2500000 | 2400000 | 0 | 601503.7
Talcum - Dline 12m 34.5kV Conversion for ties to Beckham Hindman and Haddix Troublesome Cr. | Hazard | 6517000 | 0 | 2500000 | 2400000 | 0 | 0
Various Smaller Rural Ties |  | 799999.921 | 0 | 0 | 0 | 0 | 601503.7
Additional Tie Lines - Pikeville | Sub-total | 2263000.32 | 0 | 0 | 0 | 1100000 | 601504
Johns Creek - Coleman Calloway Tie | Pikeville | 1463000 | 0 | 0 | 0 | 1100000 | 0
Various Smaller Rural Ties |  | 800000.32 | 0 | 0 | 0 | 0 | 601504
DACR/Recloser Moderization - Total | Total | 27812800 | 1000000 | 4003300 | 8911000 | 0 | 13898500
DACR - Ashland | Sub-total | 3005800 | 0 | 2010000 | 250000 | 0 | 0
Hayward - Lawton | Ashland | 1330000 | 0 | 1000000 | 0 | 0 | 0
OliveHill - Globe | Ashland | 1343300 | 0 | 1010000 | 0 | 0 | 0
Princess - US Cannonsburg | Ashland | 332500 | 0 | 0 | 250000 | 0 | 0
Hitchins - Denton | Ashland | 0 | 0 | 0 | 0 | 0 | 0
Hitchins - Grayson | Ashland | 0 | 0 | 0 | 0 | 0 | 0
Hitchins - EK Road | Ashland | 0 | 0 | 0 | 0 | 0 | 0
Grayson - Landsdown | Ashland | 0 | 0 | 0 | 0 | 0 | 0
Grayson - Dixie Park | Ashland | 0 | 0 | 0 | 0 | 0 | 0
DACR - Hazard | Subtotal | 14098000 | 0 | 0 | 3750000 | 0 | 6850000
BECKHAM - CARR CREEK | Hazard | 731500 | 0 | 0 | 550000 | 0 | 0
VICCO - REDFOX | Hazard | 665000 | 0 | 0 | 500000 | 0 | 0
SOFT SHELL - VEST | Hazard | 731500 | 0 | 0 | 550000 | 0 | 0
SOFT SHELL - LEBURN | Hazard | 665000 | 0 | 0 | 500000 | 0 | 0
COLLIER - UPPER ROCKHOUSE | Hazard | 731500 | 0 | 0 | 550000 | 0 | 0
COLLIER - LOWER ROCKHOUSE | Hazard | 133000 | 0 | 0 | 100000 | 0 | 0
REEDY - DEANE | Hazard | 1330000 | 0 | 0 | 1000000 | 0 | 0
BECKHAM - HINDMAN | Hazard | 665000 | 0 | 0 | 0 | 0 | 500000
TALCUM - CIRCUIT 1 | Hazard | 665000 | 0 | 0 | 0 | 0 | 500000
BLUEGRASS - WALKERTOWN | Hazard | 1330000 | 0 | 0 | 0 | 0 | 1000000
BLUEGRASS - HAZARD | Hazard | 665000 | 0 | 0 | 0 | 0 | 500000
COMBS - AIRPORT GARDENS | Hazard | 1330000 | 0 | 0 | 0 | 0 | 1000000
HAZARD - HAZARD | Hazard | 997500 | 0 | 0 | 0 | 0 | 750000
BULAN - ARY-HEINER | Hazard | 731500 | 0 | 0 | 0 | 0 | 550000
BULAN - AJAX-DWARF | Hazard | 665000 | 0 | 0 | 0 | 0 | 500000
BULAN - LOTTS CR. | Hazard | 665000 | 0 | 0 | 0 | 0 | 500000
JACKSON - S.JACKSON | Hazard | 731500 | 0 | 0 | 0 | 0 | 550000
JACKSON - PANBOWL | Hazard | 665000 | 0 | 0 | 0 | 0 | 500000
DACR - Pikeville | Subtotal | 5719000 | 0 | 0 | 1700000 | 0 | 2600000
ELWOOD -DORTON | Pikeville | 931000 | 0 | 0 | 700000 | 0 | 0
ELWOOD - VIRGIE - IN | Pikeville | 665000 | 0 | 0 | 500000 | 0 | 0
FORDSBRANCH - ROBINSON CR. | Pikeville | 665000 | 0 | 0 | 500000 | 0 | 0
TOMWATKIN - DISTRIBUTION | Pikeville | 2128000 | 0 | 0 | 0 | 0 | 1600000
SIDNEY - COBURN MTN. | Pikeville | 1330000 | 0 | 0 | 0 | 0 | 1000000
FALCON - FALCO OIL SPRINGS | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
FALCON - BURNING FK. | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
INDEX - WEST LIBERTY | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
INDEX - HOSPITAL | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
W.PAINTSVILLE - PAINTSVILLE | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
W.PAINTSVILLE - STAFFORDSVILLE | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
W.PAINTSVILLE - PLAZA | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
KENWOOD | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
KENWOOD - AUXIER | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
KENWOOD - HAGERHILL | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
MAYO TRAIL - NIPPA | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
MAYO TRAIL - EUCLID | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
KIMPER - GRAPEVINE | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
FISHTRAP - DISTRIBUTION | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
KEYSER - STONECOAL | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
PIKEVILLE - CITY | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
PIKEVILLE - MAIN ST. | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
PIKEVILLE - CEDAR CR. | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
S.PIKEVILL - PIKEVILLE | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
S.PIKEVILLE - ISLAND CR. | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
S.PIKEVILLE - HOSPITAL | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
BELFRY - BELFRY | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
BELFRY - TOLER | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
NEW CAMP - SOUTH SIDE | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
MCKINNEY - GIBSON | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
SALISBURY - PRINTER | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
ALLEN - DISTRIBUTION | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
BETSYLAYNE _ TRAM | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
Recloser Modernization | Subtotal | 4990000 | 1000000 | 1000000 | 1000000 | 0 | 1000000
Additional New Substation Projects - Total | Total | 52476000 | 3000000 | 11970000 | 4788000 | 22610000 | 10108000
Substation Projects - Ashland | Subtotal | 23807000 | 0 | 0 | 2300000 | 12000000 | 3600000
Grays Br.-Increase Bank Size to 20MVA (2) Breakers | Ashland | 9975000 | 0 | 0 | 300000 | 3600000 | 3600000
Ramey Sta. - Relieve loading Howard Collins\ Mobile Issue | Ashland | 12236000 | 0 | 0 | 2000000 | 7200000 | 0
Ramey Sta. - D line Exits | Ashland | 1596000 | 0 | 0 | 0 | 1200000 | 0
RT. 645 Station Near Lawrence Co. Martin Co. Line (2030 -2031) | Ashland | 0 | 0 | 0 | 0 | 0 | 0
Substation Projects - Hazard | Subtotal | 14970000 | 3000000 | 9000000 | 0 | 0 | 0
Talcum - Land | Hazard | 500000 | 500000 | 0 | 0 | 0 | 0
Talcum - New Station | Hazard | 14470000 | 2500000 | 9000000 | 0 | 0 | 0
Substation Projects - Pikeville | Subtotal | 13699000 | 0 | 0 | 1300000 | 5000000 | 4000000
Dorton 34kV Distribution Bank | Pikeville | 6650000 | 0 | 0 | 1000000 | 4000000 | 0
Dorton 34kV to Elwood (Future Myra) 18kFT Rebuild | Pikeville | 0 | 0 | 0 | 0 | 0 | 0
Stone 12kV Distribution Bank with 3-12kV CBs and Circuit Ties | Pikeville | 6650000 | 0 | 0 | 0 | 1000000 | 4000000
Tom Watkins - purchase addl property | Pikeville | 399000 | 0 | 0 | 300000 | 0 | 0
Asset Renewal/Storm Hardening/Resiliency-Total | Total | 15039999.63 | 2000000 | 3990000 | 3990000 | 2660000 | 2399999.63

## DRR 5 Year Cost vs Reliability
|  | 2024 |  |  | 2025 |  |  | 2026 |  |  | 2027 |  |  | 2028 |  |  | 2029 |  |  | Total 5 yr DRR
DRR Category |  | Cap Ex ($M) | O&M ($M) | SAIDI Savings* (minutes) | Cap Ex ($M) | O&M ($M) | SAIDI Savings* (minutes) | Cap Ex ($M) | O&M ($M) | SAIDI Savings* (minutes) | Cap Ex ($M) | O&M ($M) | SAIDI Savings* (minutes) | Cap Ex ($M) | O&M ($M) | SAIDI Savings* (minutes) | Cap Ex ($M) | O&M ($M) | SAIDI Savings* (minutes) | Cap Ex ($M) | O&M ($M) | SAIDI Min Savings* (min) | Overview of Investment to Projected Reliability Improvement - 5 Year DRR Plan
[23 empty] | Total DRR Projects | Total Spend | Minutes Saved | Projected $M/Min | Projected Bandwidth
TOR Enhanced ROW Widening |  | 12 | 0 | 0 | 12 | 0 | 6 | 12 | 0 | 6 | 12 | 0 | 6 | 12 | 0 | 6 | 0 | 0 | 6 |  |  | 30 | TOR Enhanced ROW Widening | 60000000 | 30 | 2 | + / - 5%
Additional Tie Lines |  | 1 | 0.1 | 0 | 3.325 | 0.3 | 0.42373 | 3.2 | 0.3 | 1.4089 | 1.5 | 0.2 | 1.3559 | 1.6 | 0.16 | 0.63559 | 0 | 0 | 0.67797 | 10.625 | 1.06 | 4.5021 | Additional Tie Lines | 10580000 | 4.5 | 2.36 | + / - 5%
DACR Projects and Recloser Modernization |  | 1 | 0.05 | 0 | 4.0033 | 0.2 | 0.42735 | 8.9 | 0.4 | 1.7108 | 0 | 0 | 3.8034 | 13.9 | 0.695 | 0 | 0 | 0 | 5.9402 | 27.8033 | 1.345 | 11.8818 | DACR Projects and Recloser Modernization | 27812800 | 11.9 | 2.34 | + / - 5%
Additional New Distribution Substation Sources |  | 3 | 0 | 0 | 11.97 | 0 | 0.4 | 4.8 | 0 | 1.596 | 22.6 | 0 | 0.64 | 10.1 | 0 | 3.0133 | 0 | 0 | 1.3467 | 52.47 | 0 | 6.996 | Additional New Distribution Substation Sources | 52476000 | 7 | 7.5 | + / - 5%
Asset Renewal/Storm Hardening or Resiliency |  | 2 | 0.2 | 0 | 3.99 | 0.4 | 0.39216 | 4 | 0.4 | 0.78235 | 2.7 | 0.3 | 0.78431 | 2.4 | 0.24 | 0.52941 | 0 | 0 | 0.47059 | 15.09 | 1.54 | 2.9588 | Asset Renewal/Storm Hardening or Resiliency | 15040000 | 2.9 | 5.1 | + / - 5%
Totals |  | 19 | 0.35 | 0 | 35.2883 | 0.9 | 7.6432 | 32.9 | 1.1 | 11.4981 | 38.8 | 0.5 | 12.5837 | 40 | 1.095 | 10.1783 | 0 | 0 | 14.4354 | 165.9883 | 3.945 | 56.3387 | Total | 165908800 | 56.3 | $2.95M/Min
*Note - SAIDI Savings will begin the year following the Cap Ex
*Note - SAIDI Savings will begin the year following the Cap Ex
Kentucky SAIDI - Historical Performance and Proposed Glidepath for Total DRR Program | [22 empty] | DRR - TOR Enhanced Widening
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | [6 empty] | YEAR | SPEND | Est SAIDI Minutes Saved (@ 1min/$2.0M) | Three Year Average | PROJECTED SAIDI Improvements | ESTIMATED CUSTOMERS | Targeted CMI saved ($2.0M)
| 12-'14 | 13-'15 | 14-'16 | 15-'17 | 16-'18 | 17-'19 | 18-'20 | 19-'21 | 20-'22 | 21-'23 | 22-'24 | 23-'25 | 24-'26 | 25-'27 | 26-'28 | 27-'29 | [6 empty] | 2020 |  |  | 217.4
Historical Annual SAIDI | 505.3 | 468.1 | 445.8 | 406.3 | 484.2 | 485.1 | 397.4 | 402.1 | 490.6 | 426 | [12 empty] | 2021 |  |  | 206.4
Three Year Average |  |  |  | 440.0667 | 445.4333 | 458.5333 | 455.5667 | 428.2 | 430.0333 | 426.3233 | 422.6133 | 415 | [10 empty] | 2022 |  |  | 198.1
[23 empty] | 2023 | 7420000 |  | 194.39 | 194.39
Total DRR Projection | [11 empty] | 414.9701 | 403.472 | 390.8884 | 380.71 | 366.2746 | [6 empty] | 2024 | 12000000 | 3.71 |  | 190.68 | 162018 | 601086.78
[23 empty] | 2025 | 12000000 | 9.71 |  | 184.68 | 162018 | 1573194.78
Total DRR +5% Projection | [11 empty] | 435.7186 | 423.6456 | 410.4328 | 399.7455 | 384.5884 | [6 empty] | 2026 | 12000000 | 15.71 |  | 178.68 | 162018 | 2545302.78
[23 empty] | 2027 | 12000000 | 21.71 |  | 172.68 | 162018 | 3517410.78
Total DRR -5% Projection | [11 empty] | 394.2216 | 383.2984 | 371.344 | 361.6745 | 347.9609 | [6 empty] | 2028 | 12000000 | 27.71 |  | 166.68 | 162018 | 4489518.78
[23 empty] | 2029 |  | 33.71 |  | 160.68 | 162018 | 5461626.78
[24 empty] | 60000000 | 30 |  |  | 162018 | 4860540
[23 empty] | 1 Minute Saved | 2000000

## Projected Reliability - Graphs
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029
| 12-'14 | 13-'15 | 14-'16 | 15-'17 | 16-'18 | 17-'19 | 18-'20 | 19-'21 | 20-'22 | 21-'23 | 22-'24 | 23-'25 | 24-'26 | 25-'27 | 26-'28 | 27-'29
Total DRR 5-Year Plan
Historical SAIDI | 505 | 468 | 446 | 406 | 484 | 485 | 397 | 402 | 491
3 Year Average |  |  |  | 440 | 445.3333 | 458.3333 | 455.3333 | 428 | 430 | 426 | 422.6133
DRR Glidepath Projected | [10 empty] | 422.6133 | 414.9701 | 403.472 | 390.8884 | 380.71 | 366.2746
DRR Variance Over Projected | [9 empty] | 447.3 | 443.744 | 445.2509 | 433.178 | 419.9651 | 409.2779 | 394.1207
DRR Variance Under Projected | [9 empty] | 404.7 | 401.4827 | 384.6893 | 373.7661 | 361.8116 | 352.1422 | 338.4286
DRR Enhanced ROW (TOR SAIDI only)
Historical SAIDI | 207 | 167 | 186 | 177 | 219 | 250 | 183 | 186 | 225
3 Year Average |  |  |  | 176.6667 | 194 | 215.3333 | 217.3333 | 206.3333 | 198 | 194.39 | 190.68
DRR (only TOR) Glidepath Projected | [10 empty] | 190.68 | 184.68 | 178.68 | 172.68 | 166.68 | 160.68
DRR (only TOR) Over Projected | [9 empty] | 204.1095 | 200.214 | 193.914 | 187.614 | 181.314 | 175.014 | 168.714
DRR (only TOR) Under Projected | [9 empty] | 184.6705 | 181.146 | 175.446 | 169.746 | 164.046 | 158.346 | 152.646
DRR no TOR
Historical SAIDI | 505 | 468 | 446 | 406 | 484 | 485 | 397 | 402 | 491 | 426
3 Year Average |  |  |  | 440 | 445.3333 | 458.3333 | 455.3333 | 428 | 430 | 426.29 | 422.58
DRR (no TOR) Glidepath Projected | [10 empty] | 422.58 | 420.9368 | 415.4387 | 408.855 | 404.6767 | 396.2413
DRR (no TOR) Over Projection | [11 empty] | 441.9836 | 436.2106 | 429.2978 | 424.9105 | 416.0534
DRR (no TOR) Under Projected | [11 empty] | 399.8899 | 394.6668 | 388.4123 | 384.4429 | 376.4292