## Schedule C1
Kentucky Power Company
Case No. 2023-00159
Construction Projects
For the Five Years Ended December 31, 2022
Schedule C1
Budget to Actual Variance Information - 2018 through 2022 - (Under)/Over Budget
| Project Information |  |  |  |  | Actual Information - 2018 through 2022 | [5 empty] | Budget Information - 2018 through 2022 | [5 empty] | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | Total
Line No. | GLBU | PROJECT_ID | Project DESCR | Date Actual Start (1) | Date Actual End (2) | 2018 | 2019 | 2020 | 2021 | 2022 | Total | 2018 | 2019 | 2020 | 2021 | 2022 | Total | $ | % of Budget | $ | % of Budget | $ | % of Budget | $ | % of Budget | $ | % of Budget | $ | % of Budget
1 | 110 | 000007818 | KP/Small Local Asset Improv | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 4089610.38 | 9196871.74 | 6309480.46 | 2359909.32 | 4289567.35 | 26245439.25 | 4343289.557 | 6897992.969 | 3158320.567 | 3148245.459 | 9476418.536 | 27024267.088 | -253679.177 | -5.841% | 2298878.771 | 33.33% | 3151159.893 | 99.77% | -788336.139 | -25.04% | -5186851.186 | -54.73% | -778827.838 | -2.882%
2 | 110 | EON011326 | Line Transformer/Kp | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 3292740.4 | 4169778.13 | 4182121.32 | 3795573.49 | 3467184.6 | 18907397.94 | 2380838.487 | 2454911.058 | 2691865.096 | 2827803.644 | 4912723.602 | 15268141.887 | 911901.913 | 38.3% | 1714867.072 | 69.85% | 1490256.224 | 55.36% | 967769.846 | 34.22% | -1445539.002 | -29.42% | 3639256.053 | 23.84%
3 | 110 | 000009160 | Forestry KP D Base R W | Charges Began Prior to Jan 2015 | 6/1/2019 | 3124617.13 | 145069.9 | 0 | 0 | 0 | 3269687.03 | 3526110.35 | 36914.711 | 7.559 | 0 | 0 | 3563032.62 | -401493.22 | -11.39% | 108155.189 | 293% | -7.559 | -100% | 0 | n.m. | 0 | n.m. | -293345.59 | -8.233%
4 | 110 | EDN014651 | Ds/Kp/Cs-New Customers | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 2799137.59 | 3205327.67 | 4055207.96 | 3918394.36 | 4037898.57 | 18015966.15 | 2494504.405 | 3576105.638 | 1660533.412 | 3089044.865 | 7180104.096 | 18000292.416 | 304633.185 | 12.21% | -370777.968 | -10.37% | 2394674.548 | 144.2% | 829349.495 | 26.85% | -3142205.526 | -43.76% | 15673.734 | 0.08707%
5 | 110 | 000001818 | KY/Svc Restoration NonMjr Evt | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 3735553.75 | 4814165.52 | 5718061.56 | 4734352.05 | 5605015.93 | 24607148.81 | 1877153.48 | 3112051.825 | 2601477.46 | 3291533.994 | 10388731.552 | 21270948.311 | 1858400.27 | 99% | 1702113.695 | 54.69% | 3116584.1 | 119.8% | 1442818.056 | 43.83% | -4783715.622 | -46.05% | 3336200.499 | 15.68%
6 | 110 | 000005234 | KyPCo-D Capital Software Dev | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 3570402.201 | 3166476.01 | 4467541.18 | 5154906.61 | 4907911.09 | 21267237.091 | 0 | 0 | 0 | 185626.154 | 485831.698 | 671457.852 | 3570402.201 | n.m. | 3166476.01 | n.m. | 4467541.18 | n.m. | 4969280.456 | 2677% | 4422079.392 | 910.2% | 20595779.239 | 3067%
7 | 110 | 000007599 | KP-Failed Equip No Outage | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 2226747.2 | 3059416.88 | 3953676.63 | 4060981.08 | 3808761.1 | 17109582.89 | 1318943.214 | 2939318.98 | 2094303.165 | 1450293.672 | 6700297.582 | 14503156.613 | 907803.986 | 68.83% | 120097.9 | 4.086% | 1859373.465 | 88.78% | 2610687.408 | 180% | -2891536.482 | -43.16% | 2606426.277 | 17.97%
8 | 110 | EDN100033 | Ds/Kp/C&I New | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 2314915.6 | 2646558.92 | 2774305.5 | 2297727.16 | 2069431.57 | 12102938.75 | 993903.006 | 2238818.64 | 1377111.093 | 1324593.631 | 3672789.13 | 9607215.5 | 1321012.594 | 132.9% | 407740.28 | 18.21% | 1397194.407 | 101.5% | 973133.529 | 73.47% | -1603357.56 | -43.66% | 2495723.25 | 25.98%
9 | 110 | TREEREL19 | ROW Capital widening & removal | 1/1/2019 | 2020-10-01 |  | 11096862.67 | 1039801.24 | 0 | 0 | 12136663.91 | 0 | 7352444.605 | 7398240.872 | -0.036 | 0 | 14750685.441 | 0 | n.m. | 3744418.065 | 50.93% | -6358439.632 | -85.95% | 0.036 | -100% | 0 | n.m. | -2614021.531 | -17.72%
10 | 110 | EDN014680 | Ds-Kp-Ai Pole Replacement | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 3274647.1 | 2154427.2 | 1487079.71 | 1739379.59 | 1618330.97 | 10273864.57 | 3882678.298 | 2758626.902 | 3193818.064 | 1376567.522 | 2339088.226 | 13550779.012 | -608031.198 | -15.66% | -604199.702 | -21.9% | -1706738.354 | -53.44% | 362812.068 | 26.36% | -720757.256 | -30.81% | -3276914.442 | -24.18%
11 | 110 | ITCW11004 | KY Next Generation Radio Sys | 4/1/2017 | Charges Continued After Dec 2022 | 35132.57 | 5423767.51 | 6072401.93 | 4424166.36 | 1541222.99 | 17496691.36 | 0 | 562245.572 | 12340311.959 | 8459805.661 | 0 | 21362363.192 | 35132.57 | n.m. | 4861521.938 | 864.7% | -6267910.029 | -50.79% | -4035639.301 | -47.7% | 1541222.99 | n.m. | -3865671.832 | -18.1%
12 | 110 | 000016528 | KYCutout-Arrester | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1965461.66 | 2055322.59 | 625365.04 | 497805.69 | 541732.45 | 5685687.43 | 1374553.911 | 1538902.771 | 1557350.006 | 627295.793 | 1160130.868 | 6258233.349 | 590907.749 | 42.99% | 516419.819 | 33.56% | -931984.966 | -59.84% | -129490.103 | -20.64% | -618398.418 | -53.3% | -572545.919 | -9.149%
13 | 110 | TREEREL18 | ROW Capital widening & removal | 2/1/2018 | 2020-02-01 | 5800827.92 | 207427.86 | -8808.9 | 0 | 0 | 5999446.88 | 0 | 4115.233 | 0 | 0 | 0 | 4115.233 | 5800827.92 | n.m. | 203312.627 | 4940% | -8808.9 | n.m. | 0 | n.m. | 0 | n.m. | 5995331.647 | 145686%
14 | 110 | DR15K02B0 | KP/Princess Station DStation | 5/1/2018 | 2021-12-01 | 823609.81 | 4921431.416 | 926016.73 | 190038.69 | 0 | 6861096.646 | 0 | 0 | 0 | 0 | 0 | 0 | 823609.81 | n.m. | 4921431.416 | n.m. | 926016.73 | n.m. | 190038.69 | n.m. | 0 | n.m. | 6861096.646 | n.m.
15 | 110 | EDN014720 | Ds-Kp-Ai Recloser Replacement | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1125173.25 | 1191423.86 | 713328.97 | 610835.6 | 705241.38 | 4346003.06 | 712458.459 | 1279494.251 | 994891.708 | 771400.796 | 1753659.514 | 5511904.728 | 412714.791 | 57.93% | -88070.391 | -6.883% | -281562.738 | -28.3% | -160565.196 | -20.81% | -1048418.134 | -59.78% | -1165901.668 | -21.15%
16 | 110 | EDN100577 | Ds-Kp-Ai Ckt Inspections | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1002217.69 | 1233400.35 | 1019497.99 | 584665.14 | 637741.2 | 4477522.37 | 1514221.493 | 1340203.582 | 934475.661 | 1585323.985 | 1550119.62 | 6924344.341 | -512003.803 | -33.81% | -106803.232 | -7.969% | 85022.329 | 9.098% | -1000658.845 | -63.12% | -912378.42 | -58.86% | -2446821.971 | -35.34%
17 | 110 | EDN011333 | Customer Meter/Kp | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 616111.64 | 659050.63 | 482792.02 | 289920.78 | 424443.82 | 2472318.89 | 890049.815 | 821050.012 | 732419.25 | 777389.165 | 1362738.144 | 4583646.386 | -273938.175 | -30.78% | -161999.382 | -19.73% | -249627.23 | -34.08% | -487468.385 | -62.71% | -938294.324 | -68.85% | -2111327.496 | -46.06%
18 | 110 | ITCB11000 | KENTUCKY POWER - DIST | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1122604.55 | 638681.62 | 856854.33 | 2478388.96 | 1681243.06 | 6777772.52 | 649157.138 | 628717.637 | 636778.296 | 650747.237 | 4656907.682 | 7222307.99 | 473447.412 | 72.93% | 9963.983 | 1.585% | 220076.034 | 34.56% | 1827641.723 | 280.9% | -2975664.622 | -63.9% | -444535.47 | -6.155%
19 | 110 | IT110BILL | Corp Prgrm Billing - KP Distri | 7/1/2017 | 2020-12-01 | 431990.74 | 1219442.56 | 98175.6 | 0 | 0 | 1749608.9 | 0 | 0 | 0 | 0 | 0 | 0 | 431990.74 | n.m. | 1219442.56 | n.m. | 98175.6 | n.m. | 0 | n.m. | 0 | n.m. | 1749608.9 | n.m.
20 | 110 | P18025001 | Kewanee Station - Baseline Wor | 3/1/2018 | Charges Continued After Dec 2022 | 483499.47 | 2564136.48 | 224314.82 | 2909569.49 | 4652630.81 | 10834151.07 | 0 | 42.239 | 197394.262 | 2693544.951 | 589455.186 | 3480436.638 | 483499.47 | n.m. | 2564094.241 | 6070443% | 26920.558 | 13.64% | 216024.539 | 8.02% | 4063175.624 | 689.3% | 7353714.432 | 211.3%
21 | 110 | P11161006 | D/KP Stanville Station KPCo | 7/1/2015 | 8/1/2019 | 2657028.76 | 86497.01 | -6164.89 | 0 | 0 | 2737360.88 | 2775961.244 | 9753.921 | 0 | 0 | 0 | 2785715.165 | -118932.484 | -4.284% | 76743.089 | 786.8% | -6164.89 | n.m. | 0 | n.m. | 0 | n.m. | -48354.285 | -1.736%
22 | 110 | 000025229 | 2018 Gen Plt Cap Blkt - KYPC-D | 1/1/2018 | Charges Continued After Dec 2022 | 1096100.6 | 1866210.29 | 980184.8 | 359730.23 | 175943.77 | 4478169.69 | 176034.918 | 177550.368 | 178737.033 | 205374.463 | 410231.208 | 1147927.99 | 920065.682 | 522.7% | 1688659.922 | 951.1% | 801447.767 | 448.4% | 154355.767 | 75.16% | -234287.438 | -57.11% | 3330241.7 | 290.1%
23 | 110 | KY5YCYCLE | KY D 2017-00179 | 1/1/2019 | Charges Continued After Dec 2022 |  | 2952531.33 | -28958.86 | 5910790.14 | 2749936.16 | 11584298.77 | 0 | 3853204.675 | 2993487.675 | 2813719.58 | 5508121.96 | 15168533.89 | 0 | n.m. | -900673.345 | -23.37% | -3022446.535 | -101% | 3097070.56 | 110.1% | -2758185.8 | -50.07% | -3584235.12 | -23.63%
24 | 110 | EDN014694 | Ds-Kp-Ai Other Make Ready | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1475972.9 | 713622.11 | 389948.48 | -532895.87 | 214916.88 | 2261564.5 | 249649.572 | 404136.78 | 509621.981 | 331798.246 | 1655112.834 | 3150319.413 | 1226323.328 | 491.2% | 309485.33 | 76.58% | -119673.501 | -23.48% | -864694.116 | -260.6% | -1440195.954 | -87.01% | -888754.913 | -28.21%
25 | 110 | P11063003 | TKYVicco Station Improvement | Charges Began Prior to Jan 2015 | 3/1/2019 | 17038.49 | 2189.15 | 0 | 0 | 0 | 19227.64 | 0 | 0 | 0 | 0 | 0 | 0 | 17038.49 | n.m. | 2189.15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19227.64 | n.m.
26 | 110 | A16928013 | Mobile KPCo 118 Purchase | 7/1/2017 | 3/1/2019 | 1108482.28 | 109282.22 | 0 | 0 | 0 | 1217764.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1108482.28 | n.m. | 109282.22 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1217764.5 | n.m.
27 | 110 | 000004737 | KPSectionalizing Program | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 785162.79 | 831334.8 | 483652.27 | 210338.38 | 192497.24 | 2502985.48 | 0 | 679153.406 | 694392.113 | 27.024 | 774031.526 | 2147604.069 | 785162.79 | n.m. | 152181.394 | 22.41% | -210739.843 | -30.35% | 210311.356 | 778239% | -581534.286 | -75.13% | 355381.411 | 16.55%
28 | 110 | B110KYSRR | D/KY/Non-Specific Work - Sta | 11/1/2016 | Charges Continued After Dec 2022 | 694499.54 | 912988.96 | 1771964.71 | 1176190.18 | 2351716.16 | 6907359.55 | 1085772.628 | 723564.163 | 637074.234 | 663358.948 | 1191143.094 | 4300913.067 | -391273.088 | -36.04% | 189424.797 | 26.18% | 1134890.476 | 178.1% | 512831.232 | 77.31% | 1160573.066 | 97.43% | 2606446.483 | 60.6%
29 | 110 | EDN012370 | Ds/Kp/Public Relocation | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 752217.3 | 486999.36 | 574425.54 | 564504.88 | 298717.55 | 2676864.63 | 2100540.12 | 2394095.554 | 878883.102 | 2015281.325 | 1597929.112 | 8986729.213 | -1348322.82 | -64.19% | -1907096.194 | -79.66% | -304457.562 | -34.64% | -1450776.445 | -71.99% | -1299211.562 | -81.31% | -6309864.583 | -70.21%
30 | 110 | DCTSUVLKY | KY CATS Monthly Unvouch Liab | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1735717.14 | 259951.18 | -617775.43 | -397307.76 | 631423.59 | 1612008.72 | 0 | 0 | 0 | 0 | 0 | 0 | 1735717.14 | n.m. | 259951.18 | n.m. | -617775.43 | n.m. | -397307.76 | n.m. | 631423.59 | n.m. | 1612008.72 | n.m.
31 | 110 | 000025820 | Kentucky Power State Office | 11/1/2018 | 2020-06-01 | 984.2 | 1842610.84 | 159881.05 | 0 | 0 | 2003476.09 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 984.2 | n.m. | 1842610.84 | n.m. | 159881.05 | n.m. | 0 | n.m. | -410231.208 | -100% | 1593244.882 | 388.4%
32 | 110 | A15702051 | Pikeville Stn RepBank#1 | 12/1/2017 | 2020-11-01 | 765874.35 | 999432.22 | 34620.23 | 0 | 0 | 1799926.8 | 0 | 1301.685 | 0 | 0 | 0 | 1301.685 | 765874.35 | n.m. | 998130.535 | 76680% | 34620.23 | n.m. | 0 | n.m. | 0 | n.m. | 1798625.115 | 138177%
33 | 110 | A16928014 | Skid Station KPCo 1002 Purchas | 11/1/2017 | 2020-01-01 | 980687.65 | 232200.47 | 2160.71 | 0 | 0 | 1215048.83 | 0 | 0 | 0 | 0 | 0 | 0 | 980687.65 | n.m. | 232200.47 | n.m. | 2160.71 | n.m. | 0 | n.m. | 0 | n.m. | 1215048.83 | n.m.
34 | 110 | IT1101421 | Maximo Imp - KYP - D | 3/1/2016 | 2020-08-01 | 547153.3 | 605026.08 | 9968.62 | 0 | 0 | 1162148 | 0 | 0 | 1366.536 | 0 | 0 | 1366.536 | 547153.3 | n.m. | 605026.08 | n.m. | 8602.084 | 629.5% | 0 | n.m. | 0 | n.m. | 1160781.464 | 84943%
35 | 110 | DR18K03B5 | Breaker Rpl - S Pikeville | 5/1/2018 | 2020-05-01 | 1283232.09 | 202700.73 | -106934.65 | 0 | 0 | 1378998.17 | 0 | 0 | 0 | 0 | 0 | 0 | 1283232.09 | n.m. | 202700.73 | n.m. | -106934.65 | n.m. | 0 | n.m. | 0 | n.m. | 1378998.17 | n.m.
36 | 110 | 000024101 | KYPCo-D General Plt Cap Blkt | 3/1/2016 | 1/1/2018 | 6168.57 |  | 0 | 0 | 0 | 6168.57 | 159.014 | -66.276 | 0 | 0 | 3307757.578 | 3307850.316 | 6009.556 | 3779% | 66.276 | -100% | 0 | n.m. | 0 | n.m. | -3307757.578 | -100% | -3301681.746 | -99.81%
37 | 110 | EDN015042 | Ds-Kp-Small Wire Repl Ovhd | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 383665.93 | 463033.17 | 912622.24 | 784812.81 | 361942.5 | 2906076.65 | 0 | 430168.281 | 1082070.137 | 21.665 | 1435538.9 | 2947798.983 | 383665.93 | n.m. | 32864.889 | 7.64% | -169447.897 | -15.66% | 784791.145 | 3622392% | -1073596.4 | -74.79% | -41722.333 | -1.415%
38 | 110 | EDN014658 | Ds/Kp/Cs-Upgrades | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 172256.35 | 261639.36 | 333578.48 | 358015.04 | 247982.78 | 1373472.01 | 42298.937 | 165936.356 | 175126.398 | 59845.883 | 155873.558 | 599081.132 | 129957.413 | 307.2% | 95703.004 | 57.67% | 158452.082 | 90.48% | 298169.157 | 498.2% | 92109.222 | 59.09% | 774390.878 | 129.3%
39 | 110 | 000002241 | KP-Damage Claims-Reimburse | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 237814.74 | 234703.53 | 329561.9 | 277802.17 | 448374.93 | 1528257.27 | -26892.034 | 111634.272 | 35079.736 | -24224.478 | 413955.9 | 509553.396 | 264706.774 | -984.3% | 123069.258 | 110.2% | 294482.164 | 839.5% | 302026.648 | -1247% | 34419.03 | 8.315% | 1018703.874 | 199.9%
40 | 110 | DR18K04B0 | Pikeville Sta - Trans upgrade | 8/1/2018 | 2020-09-01 | 341023.98 | 863555.66 | -36756.56 | 0 | 0 | 1167823.08 | 0 | 0 | 0 | 0 | 0 | 0 | 341023.98 | n.m. | 863555.66 | n.m. | -36756.56 | n.m. | 0 | n.m. | 0 | n.m. | 1167823.08 | n.m.
41 | 110 | DR15K02A0 | KP/Princess Station D Line | 4/1/2018 | 2022-10-01 | 737337.68 | 403072.35 | 186189.36 | 12373.48 | -20611.39 | 1318361.48 | 0 | 0 | 0 | 0 | 0 | 0 | 737337.68 | n.m. | 403072.35 | n.m. | 186189.36 | n.m. | 12373.48 | n.m. | -20611.39 | n.m. | 1318361.48 | n.m.
42 | 110 | KYCR012DL | KP/VoltVar Circ Reconfig DLine | Charges Began Prior to Jan 2015 | 2022-02-01 | 185457.02 | 81473.15 | 24489.87 | 8124.32 | 1799.29 | 301343.65 | 0 | 0 | 0 | 0 | 0 | 0 | 185457.02 | n.m. | 81473.15 | n.m. | 24489.87 | n.m. | 8124.32 | n.m. | 1799.29 | n.m. | 301343.65 | n.m.
43 | 110 | A15710004 | Ashland SC Tele Modernization | 9/1/2016 | 5/1/2018 | 23114.04 |  | 0 | 0 | 0 | 23114.04 | 42373.74 | 0 | 0 | 0 | 0 | 42373.74 | -19259.7 | -45.45% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -19259.7 | -45.45%
44 | 110 | P12057001 | T/KP/BECKHAM-(KPCo) | Charges Began Prior to Jan 2015 | 11/1/2018 | 33137.79 |  | 0 | 0 | 0 | 33137.79 | -1.49 | 0 | 0 | 0 | 0 | -1.49 | 33139.28 | -2224113% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33139.28 | -2224113%
45 | 110 | SI110KYRE | DB/SI/KyP-KENTUCKY SYS REHAB | Charges Began Prior to Jan 2015 | 2020-01-01 | -11732.42 | 1755.18 | -22.09 | 0 | 0 | -9999.33 | 0 | 0 | 0 | 0 | 0 | 0 | -11732.42 | n.m. | 1755.18 | n.m. | -22.09 | n.m. | 0 | n.m. | 0 | n.m. | -9999.33 | n.m.
46 | 110 | DR19K02A0 | Ashland DA 2019 - D line | 3/1/2019 | 2021-08-01 |  | 1001143.91 | 211076.13 | 77484.68 | 0 | 1289704.72 | 0 | 0 | 0 | 8.823 | 0 | 8.823 | 0 | n.m. | 1001143.91 | n.m. | 211076.13 | n.m. | 77475.857 | 878112% | 0 | n.m. | 1289695.897 | 14617431%
47 | 110 | 000024645 | KYPCo-D General Plt Cap Blkt | 3/1/2017 | Charges Continued After Dec 2022 | 173478.84 | 396.9 | 3883.96 | 3013 | 94.04 | 180866.74 | 23220.541 | 22638.545 | 22814.029 | 0 | 0 | 68673.115 | 150258.299 | 647.1% | -22241.645 | -98.25% | -18930.069 | -82.98% | 3013 | n.m. | 94.04 | n.m. | 112193.625 | 163.4%
48 | 110 | A13002031 | D/KP/S.Pikeville-ReplTrf Bank1 | 5/1/2015 | 1/1/2018 | -6795.75 |  | 0 | 0 | 0 | -6795.75 | 0 | 0 | 0 | 0 | 0 | 0 | -6795.75 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -6795.75 | n.m.
49 | 110 | P11161002 | D/KP/S.PIKEV -Remote End | 9/1/2015 | 8/1/2019 | 585543.55 | 67952.08 | 10301.72 | 0 | 0 | 663797.35 | 495743.786 | 0 | 0 | 0 | 0 | 495743.786 | 89799.764 | 18.11% | 67952.08 | n.m. | 10301.72 | n.m. | 0 | n.m. | 0 | n.m. | 168053.564 | 33.9%
50 | 110 | DR18K02A0 | Hazard 2018 DA Plan | 3/1/2019 | Charges Continued After Dec 2022 |  | 782023.02 | 268757.54 | 15632.71 | 34195.61 | 1100608.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 782023.02 | n.m. | 268757.54 | n.m. | 15632.71 | n.m. | 34195.61 | n.m. | 1100608.88 | n.m.
51 | 110 | 000025522 | Lovely\Lovely Sectionalizing | 6/1/2018 | 2020-03-01 | 344446.15 | 430200.15 | 7628.87 | 0 | 0 | 782275.17 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 344446.15 | n.m. | 430200.15 | n.m. | 7628.87 | n.m. | 0 | n.m. | -410231.208 | -100% | 372043.962 | 90.69%
52 | 110 | A13212036 | Ashland (KY) Telecom Pilot Wir | 11/1/2015 | 5/1/2019 | 13923.97 | 3998.69 | 0 | 0 | 0 | 17922.66 | 0 | 0 | 0 | 0 | 0 | 0 | 13923.97 | n.m. | 3998.69 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17922.66 | n.m.
53 | 110 | 000007615 | KP-Cust Req Relocate | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 46726.92 | 134290.16 | 139680.55 | 117786.5 | 102929.07 | 541413.2 | 107797.162 | 234362.779 | 177623.956 | 114959.609 | 430471.298 | 1065214.804 | -61070.242 | -56.65% | -100072.619 | -42.7% | -37943.406 | -21.36% | 2826.891 | 2.459% | -327542.228 | -76.09% | -523801.604 | -49.17%
54 | 110 | DP14K02B0 | KP/Raccoon Sta - 30 MVA 138-34 | 3/1/2018 | Charges Continued After Dec 2022 | 64563.59 | 639872.63 | 3877249.6 | 2098237.98 | 68700.13 | 6748623.93 | 0 | 0 | 0 | 0 | 0 | 0 | 64563.59 | n.m. | 639872.63 | n.m. | 3877249.6 | n.m. | 2098237.98 | n.m. | 68700.13 | n.m. | 6748623.93 | n.m.
55 | 110 | DP15K05L0 | Raccoon Station site purchase | 12/1/2015 | 2021-12-01 | 812.37 |  | 24774.02 | -3566.36 | 0 | 22020.03 | 0 | 0 | 0 | 0 | 0 | 0 | 812.37 | n.m. | 0 | n.m. | 24774.02 | n.m. | -3566.36 | n.m. | 0 | n.m. | 22020.03 | n.m.
56 | 110 | A15710030 | Beavercreek TS TTMP | 3/1/2018 | 2020-07-01 | 467454.47 | 212242.63 | 6693.69 | 0 | 0 | 686390.79 | 0 | 0 | 0 | 0 | 0 | 0 | 467454.47 | n.m. | 212242.63 | n.m. | 6693.69 | n.m. | 0 | n.m. | 0 | n.m. | 686390.79 | n.m.
57 | 110 | EDN100044 | Ds/Kp/C&I Upgrades | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 131836.06 | 106813.27 | 113888.81 | 187030.42 | 98379.52 | 637948.08 | 0 | 86822.798 | 102376.033 | 8.628 | 0 | 189207.459 | 131836.06 | n.m. | 19990.472 | 23.02% | 11512.777 | 11.25% | 187021.792 | 2167615% | 98379.52 | n.m. | 448740.621 | 237.2%
58 | 110 | P11161021 | Stanville DLINE Components | 7/1/2017 | 11/1/2019 | 471649.68 | 96611.17 | 0 | 0 | 0 | 568260.85 | 0 | 0 | 0 | 0 | 0 | 0 | 471649.68 | n.m. | 96611.17 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 568260.85 | n.m.
59 | 110 | A13212028 | Second Fork - Telecom Legacy | 8/1/2015 | 4/1/2018 | 242 |  | 0 | 0 | 0 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 242 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 242 | n.m.
60 | 110 | A13212029 | Elwood (KP) - Telecom Legacy | 9/1/2015 | 8/1/2018 | 49400.99 |  | 0 | 0 | 0 | 49400.99 | 0 | 0 | 0 | 0 | 0 | 0 | 49400.99 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49400.99 | n.m.
61 | 110 | 000025473 | Purchase Hazard Service Center | 12/1/2017 | 7/1/2018 | 5684.59 |  | 0 | 0 | 0 | 5684.59 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 5684.59 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -404546.618 | -98.61%
62 | 110 | A16928010 | Ashland Srvc Purch Sp Transf | 12/1/2017 | 1/1/2019 | 249639.95 | 2672.51 | 0 | 0 | 0 | 252312.46 | 0 | 0 | 0 | 0 | 0 | 0 | 249639.95 | n.m. | 2672.51 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 252312.46 | n.m.
63 | 110 | DR19K04A0 | Pikeville DA 2019 - D line | 7/1/2019 | 2020-12-01 |  | 556826.61 | 337678.48 | 0 | 0 | 894505.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 556826.61 | n.m. | 337678.48 | n.m. | 0 | n.m. | 0 | n.m. | 894505.09 | n.m.
64 | 110 | DMS19KK01 | KP/ME/Wind Storm 02/24/19 | 2/1/2019 | 2020-04-01 |  | 534591.08 | -15938.18 | 0 | 0 | 518652.9 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 534591.08 | n.m. | -15938.18 | n.m. | 0 | n.m. | -0.01 | -100% | 518652.89 | 5186528900%
65 | 110 | A16928012 | Pikeville Purchase Spare | 8/1/2017 | 1/1/2019 | 394738.33 | 3.09 | 0 | 0 | 0 | 394741.42 | 0 | 0 | 0 | 0 | 0 | 0 | 394738.33 | n.m. | 3.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 394741.42 | n.m.
66 | 110 | DR19K06B0 | Breaker Repl - Ashland | 4/1/2019 | 2020-06-01 |  | 481201.09 | 10526.5 | 0 | 0 | 491727.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 481201.09 | n.m. | 10526.5 | n.m. | 0 | n.m. | 0 | n.m. | 491727.59 | n.m.
67 | 110 | A17212002 | Hayward RTU Replacement | 7/1/2018 | 2022-08-01 | 23803.41 | 456749.66 | 187427.83 | 0 | 4442.49 | 672423.39 | 0 | 241746.308 | 0 | 0 | 0 | 241746.308 | 23803.41 | n.m. | 215003.352 | 88.94% | 187427.83 | n.m. | 0 | n.m. | 4442.49 | n.m. | 430677.082 | 178.2%
68 | 110 | P16113007 | Coalton Line Relaying | 12/1/2016 | 2022-03-01 | 180930.76 | 284568.3 | -49834.87 | 5144.69 | 144.74 | 420953.62 | 205.33 | 42663.519 | 0 | 0 | 0 | 42868.849 | 180725.43 | 88017% | 241904.781 | 567% | -49834.87 | n.m. | 5144.69 | n.m. | 144.74 | n.m. | 378084.771 | 882%
69 | 110 | DX16K02A0 | Coalton Sta - US RT 60 PPR | 2/1/2017 | 2022-02-01 | 52701.02 | 146866.72 | -45155.52 | 46958.23 | -177258.1 | 24112.35 | 0 | 0 | 0 | 0 | 0 | 0 | 52701.02 | n.m. | 146866.72 | n.m. | -45155.52 | n.m. | 46958.23 | n.m. | -177258.1 | n.m. | 24112.35 | n.m.
70 | 110 | A15702009 | Prestonsburg Rpl OCB C | 5/1/2017 | 10/1/2018 | 49550.29 |  | 0 | 0 | 0 | 49550.29 | 0 | 0 | 0 | 0 | 0 | 0 | 49550.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49550.29 | n.m.
71 | 110 | DR19K06B1 | Breaker Repl - Lovely | 4/1/2019 | 2021-01-01 |  | 451477.36 | 49166.34 | -1114.38 | 0 | 499529.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 451477.36 | n.m. | 49166.34 | n.m. | -1114.38 | n.m. | 0 | n.m. | 499529.32 | n.m.
72 | 110 | A13212039 | Argentum Telecom Legacy Circui | 9/1/2016 | 1/1/2018 | 173.49 |  | 0 | 0 | 0 | 173.49 | 0 | 0 | 0 | 0 | 0 | 0 | 173.49 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 173.49 | n.m.
73 | 110 | A13002034 | D/KP/Kimper-ReplFailedTrf 1B | 9/1/2015 | 1/1/2018 | -16141.83 |  | 0 | 0 | 0 | -16141.83 | 0 | 0 | 579470.428 | 0 | 0 | 579470.428 | -16141.83 | n.m. | 0 | n.m. | -579470.428 | -100% | 0 | n.m. | 0 | n.m. | -595612.258 | -102.8%
74 | 110 | DR19K02B0 | Ashland DA 2019 - Busseyville | 5/1/2019 | 2020-09-01 |  | 365765.98 | 46768.93 | 0 | 0 | 412534.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 365765.98 | n.m. | 46768.93 | n.m. | 0 | n.m. | 0 | n.m. | 412534.91 | n.m.
75 | 110 | DP16K02A0 | Add Two D circuits-Cedar Ck | 6/1/2019 | 2020-11-01 |  | 342442.72 | 91973.57 | 0 | 0 | 434416.29 | 0 | 0 | 60.538 | 0 | 0 | 60.538 | 0 | n.m. | 342442.72 | n.m. | 91913.032 | 151827% | 0 | n.m. | 0 | n.m. | 434355.752 | 717493%
76 | 110 | 000007558 | KP-PQ-QOS Mitigation | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 49820.07 | 115860.03 | 40636.16 | 31358.26 | 7861.39 | 245535.91 | 1042545.271 | 593202.504 | 100869.928 | 1177655.085 | 1124398.524 | 4038671.312 | -992725.201 | -95.22% | -477342.474 | -80.47% | -60233.768 | -59.71% | -1146296.825 | -97.34% | -1116537.134 | -99.3% | -3793135.402 | -93.92%
77 | 110 | A15710011 | Hagler Hill TS Tele Modernizat | 1/1/2017 | 5/1/2019 | 95835.73 | 1171.92 | 0 | 0 | 0 | 97007.65 | 2139.5 | 1169.575 | 0 | 0 | 0 | 3309.075 | 93696.23 | 4379% | 2.345 | 0.2005% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 93698.575 | 2832%
78 | 110 | A15702050 | Tenth St.-Transformer 2 Failur | 6/1/2017 | 6/1/2018 | -116197.76 |  | 0 | 0 | 0 | -116197.76 | 0 | 0 | 0 | 0 | 0 | 0 | -116197.76 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -116197.76 | n.m.
79 | 110 | 000014717 | KY/DOP/Copper Theft | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 2913.04 | 52986.21 | 139511.82 | 21260.14 | 1020.45 | 217691.66 | 132168.628 | 166275.978 | 63818.056 | 135529.086 | 270669.18 | 768460.928 | -129255.588 | -97.8% | -113289.768 | -68.13% | 75693.764 | 118.6% | -114268.946 | -84.31% | -269648.73 | -99.62% | -550769.268 | -71.67%
80 | 110 | 000023644 | General Plant Blanket KYPCo-D | 8/1/2015 | 1/1/2018 | 989.7 |  | 0 | 0 | 0 | 989.7 | 0 | 0 | 0 | 0 | 3307757.578 | 3307757.578 | 989.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -3307757.578 | -100% | -3306767.878 | -99.97%
81 | 110 | A13002025 | /DKP/RussellFork-RetiningWall | 2/1/2015 | 1/1/2018 | 28.74 |  | 0 | 0 | 0 | 28.74 | 0 | 0 | 0 | 0 | 0 | 0 | 28.74 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28.74 | n.m.
82 | 110 | A15710010 | Catalpa TS Shelter upgradeTTMP | 12/1/2016 | 3/1/2019 | 87274.66 | 1170.26 | 0 | 0 | 0 | 88444.92 | 5237.44 | 0 | 0 | 0 | 0 | 5237.44 | 82037.22 | 1566% | 1170.26 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 83207.48 | 1589%
83 | 110 | DMS18KK03 | KY/ME/Wind Storm 04/04/18 | 4/1/2018 | 3/1/2019 | 276983.7 | 578.75 | 0 | 0 | 0 | 277562.45 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 276983.7 | n.m. | 578.75 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 277562.44 | 2775624400%
84 | 110 | DR18K02B0 | Jeff Sta - Add DRTU | 9/1/2018 | 2020-08-01 | 25497.33 | 250106.49 | 3123.13 | 0 | 0 | 278726.95 | 0 | 0 | 0 | 0 | 0 | 0 | 25497.33 | n.m. | 250106.49 | n.m. | 3123.13 | n.m. | 0 | n.m. | 0 | n.m. | 278726.95 | n.m.
85 | 110 | A17750006 | Cannonsburg Failed TR1 | 8/1/2018 | 9/1/2019 | 231357.56 | 41478.7 | 0 | 0 | 0 | 272836.26 | 0 | 0 | 0 | 0 | 0 | 0 | 231357.56 | n.m. | 41478.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 272836.26 | n.m.
86 | 110 | KYCAPTOOL | KY Purch. Cap Tools | 3/1/2019 | Charges Continued After Dec 2022 |  | 266473.3 | 171508.92 | 152457.4 | 216101.61 | 806541.23 | 0 | 0 | 113785.355 | 132539.668 | 34112.776 | 280437.799 | 0 | n.m. | 266473.3 | n.m. | 57723.565 | 50.73% | 19917.732 | 15.03% | 181988.834 | 533.5% | 526103.431 | 187.6%
87 | 110 | 000025595 | Fords Br. Shelby Circuit. | 3/1/2018 | 1/1/2019 | 261404.04 | 1.65 | 0 | 0 | 0 | 261405.69 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 261404.04 | n.m. | 1.65 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -148825.518 | -36.28%
88 | 110 | 000025514 | Mayking Milstone SH | 7/1/2018 | 2/1/2019 | 200602.18 | 55876.95 | 0 | 0 | 0 | 256479.13 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 200602.18 | n.m. | 55876.95 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -153752.078 | -37.48%
89 | 110 | DR18K02B3 | Vicco Sta - Add DRTU | 10/1/2018 | 2020-10-01 | 22963.94 | 228128.8 | 24603.74 | 0 | 0 | 275696.48 | 0 | 0 | 0 | 0 | 0 | 0 | 22963.94 | n.m. | 228128.8 | n.m. | 24603.74 | n.m. | 0 | n.m. | 0 | n.m. | 275696.48 | n.m.
90 | 110 | DP18K03L0 | Tygart Sta - Purchase property | 6/1/2019 | Charges Continued After Dec 2022 |  | 243336.09 | 364353.1 | 10046.14 | 4745.9 | 622481.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 243336.09 | n.m. | 364353.1 | n.m. | 10046.14 | n.m. | 4745.9 | n.m. | 622481.23 | n.m.
91 | 110 | 000007577 | KP-UG Cable Repl Failure | Charges Began Prior to Jan 2015 | 2020-03-01 | 10277.53 | 54149.1 | 5140.32 | 0 | 0 | 69566.95 | 0 | 46213.604 | 11.081 | 0 | 1124398.524 | 1170623.209 | 10277.53 | n.m. | 7935.496 | 17.17% | 5129.239 | 46289% | 0 | n.m. | -1124398.524 | -100% | -1101056.259 | -94.06%
92 | 110 | P11161003 | Allen Remote End | 2/1/2016 | 7/1/2019 | 180007.18 | 2623.95 | 0 | 0 | 0 | 182631.13 | 153734.81 | 0 | 0 | 0 | 0 | 153734.81 | 26272.37 | 17.09% | 2623.95 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28896.32 | 18.8%
93 | 110 | EDN014701 | Ds Kp Ai Support Cs Res | Charges Began Prior to Jan 2015 | 2022-03-01 | 26050.37 | 17236.03 | 22093.76 | 30456.03 | 758.11 | 96594.3 | 0 | 29024.341 | 6.146 | 0 | 0 | 29030.487 | 26050.37 | n.m. | -11788.311 | -40.62% | 22087.614 | 359382% | 30456.03 | n.m. | 758.11 | n.m. | 67563.813 | 232.7%
94 | 110 | EDN103175 | Ds Kp Anda | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 65599.8 | 116372.3 | 23888.05 | -11878.47 | 2075.43 | 196057.11 | -0.018 | 0.003 | 0.02 | -0.045 | -0.008 | -0.048 | 65599.818 | -364443433% | 116372.297 | 3879076567% | 23888.03 | 119440150% | -11878.425 | 26396500% | 2075.438 | -25942975% | 196057.158 | -408452412%
95 | 110 | KYCR30009 | KY CR Highland Sta | 5/1/2016 | 10/1/2018 | 28466.29 |  | 0 | 0 | 0 | 28466.29 | 0 | 0 | 0 | 0 | 0 | 0 | 28466.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28466.29 | n.m.
96 | 110 | DX17K01B0 | Elwood Sta - Repl Brkr R | 2/1/2018 | 2021-10-01 | 188239.79 | 17214.79 | 11853.84 | 569.82 | 0 | 217878.24 | 0 | 0 | 0 | 0 | 0 | 0 | 188239.79 | n.m. | 17214.79 | n.m. | 11853.84 | n.m. | 569.82 | n.m. | 0 | n.m. | 217878.24 | n.m.
97 | 110 | A13002013 | D/KP/Highland-Repl BPLC Rly | 5/1/2017 | 9/1/2019 | 79878.37 | 39683.16 | 0 | 0 | 0 | 119561.53 | 10.96 | 0 | 0 | 0 | 0 | 10.96 | 79867.41 | 728717% | 39683.16 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 119550.57 | 1090790%
98 | 110 | DMS18KK05 | KY/ME/Wind Storm 7/20/18 | 7/1/2018 | 3/1/2019 | 191048.05 | 1778.53 | 0 | 0 | 0 | 192826.58 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 191048.05 | n.m. | 1778.53 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 192826.57 | 1928265700%
99 | 110 | DMS19KK05 | KY Pre/Valid Major Storm 5 | 10/1/2019 | 2020-09-01 |  | 191864.87 | -6941.65 | 0 | 0 | 184923.22 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 191864.87 | n.m. | -6941.65 | n.m. | 0 | n.m. | -0.01 | -100% | 184923.21 | 1849232100%
100 | 110 | A13002014 | D/KP/Raceland-Repl BPLC Rly | 5/1/2017 | 9/1/2019 | 75459.01 | 27366.05 | 0 | 0 | 0 | 102825.06 | 109.71 | 0 | 0 | 0 | 0 | 109.71 | 75349.3 | 68680% | 27366.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 102715.35 | 93624%
101 | 110 | EDN101114 | Ds Kp Ai Support Cs C I | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 4737.05 | 4350.89 | 38475.62 | 6823.23 | 11164.79 | 65551.58 | 0 | 42451.412 | 10.063 | 0 | 0 | 42461.475 | 4737.05 | n.m. | -38100.522 | -89.75% | 38465.557 | 382247% | 6823.23 | n.m. | 11164.79 | n.m. | 23090.105 | 54.38%
102 | 110 | DMS19KK02 | KY Pre/Valid Major Storm 2 | 5/1/2019 | 2020-04-01 |  | 179885.64 | 486.07 | 0 | 0 | 180371.71 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 179885.64 | n.m. | 486.07 | n.m. | 0 | n.m. | -0.01 | -100% | 180371.7 | 1803717000%
103 | 110 | KYCR33111 | KY CR Stinnett Sta | 12/1/2015 | 9/1/2018 | 24704.68 |  | 0 | 0 | 0 | 24704.68 | 0 | 0 | 0 | 0 | 0 | 0 | 24704.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24704.68 | n.m.
104 | 110 | A15702012 | Combs - Rpl Failed RTU | 1/1/2017 | 1/1/2018 | 1.46 |  | 0 | 0 | 0 | 1.46 | 0 | 0 | 0 | 0 | 0 | 0 | 1.46 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1.46 | n.m.
105 | 110 | 000025524 | Feds Cr. Exit Relocation | 5/1/2018 | 7/1/2019 | 100656.97 | 65337.49 | 0 | 0 | 0 | 165994.46 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 100656.97 | n.m. | 65337.49 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -244236.748 | -59.54%
106 | 110 | DMS19KK06 | KY Pre/Valid Major Storm 6 | 11/1/2019 | 2020-08-01 |  | 164826.4 | 15793.14 | 0 | 0 | 180619.54 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 164826.4 | n.m. | 15793.14 | n.m. | 0 | n.m. | -0.01 | -100% | 180619.53 | 1806195300%
107 | 110 | KYCR31167 | KY CR Belhaven Sta | 5/1/2016 | 2021-12-01 | -64580.53 | 6.55 | 5.7 | -366.59 | 0 | -64934.87 | 0 | 0 | 0 | 0 | 0 | 0 | -64580.53 | n.m. | 6.55 | n.m. | 5.7 | n.m. | -366.59 | n.m. | 0 | n.m. | -64934.87 | n.m.
108 | 110 | P18216001 | Hoods Creek Land Purchase | 4/1/2019 | 2022-02-01 |  | 160314.63 | 76408.61 | 8709.49 | 93.1 | 245525.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 160314.63 | n.m. | 76408.61 | n.m. | 8709.49 | n.m. | 93.1 | n.m. | 245525.83 | n.m.
109 | 110 | A15710005 | Ashland POP Tele Modernization | 9/1/2016 | 2020-04-01 | 20302.14 | 23554.35 | 4598.69 | 0 | 0 | 48455.18 | 4938.59 | 7592.589 | 0 | 0 | 0 | 12531.179 | 15363.55 | 311.1% | 15961.761 | 210.2% | 4598.69 | n.m. | 0 | n.m. | 0 | n.m. | 35924.001 | 286.7%
110 | 110 | DMS18KK02 | KY/Pre Valid Major Event | 3/1/2018 | 11/1/2018 | 143091.85 |  | 0 | 0 | 0 | 143091.85 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 143091.85 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 143091.84 | 1430918400%
111 | 110 | DR19K06B2 | Breaker Repl - 47th St | 4/1/2019 | 2020-07-01 |  | 139188.306 | 8238.12 | 0 | 0 | 147426.426 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 139188.306 | n.m. | 8238.12 | n.m. | 0 | n.m. | 0 | n.m. | 147426.426 | n.m.
112 | 110 | KYCR30106 | KY CR Russell Sta | 5/1/2016 | 10/1/2018 | 35481.85 |  | 0 | 0 | 0 | 35481.85 | 0 | 0 | 0 | 0 | 0 | 0 | 35481.85 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35481.85 | n.m.
113 | 110 | KYCR31109 | KY CR Wurtland Sta | 5/1/2016 | 1/1/2019 | 26366.16 | 0.42 | 0 | 0 | 0 | 26366.58 | 0 | 0 | 0 | 0 | 0 | 0 | 26366.16 | n.m. | 0.42 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 26366.58 | n.m.
114 | 110 | KYCR34119 | KY CR Fords Branch Sta | 1/1/2016 | 1/1/2019 | 18108.32 | 7.61 | 0 | 0 | 0 | 18115.93 | 0 | 0 | 0 | 0 | 0 | 0 | 18108.32 | n.m. | 7.61 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 18115.93 | n.m.
115 | 110 | P17076002 | Kenwood Station | 9/1/2017 | Charges Continued After Dec 2022 | 74909.04 | 14613.37 | 77655.37 | 20765.21 | 6339.59 | 194282.58 | 0 | 39569.124 | 481537.321 | 6101.858 | 501101.398 | 1028309.701 | 74909.04 | n.m. | -24955.754 | -63.07% | -403881.951 | -83.87% | 14663.352 | 240.3% | -494761.808 | -98.73% | -834027.121 | -81.11%
116 | 110 | A20212001 | Lovely RTU Reliability | 10/1/2018 | 2021-03-01 | 6463.43 | 115260.03 | 159959.62 | 2076.79 | 0 | 283759.87 | 0 | 0 | 429154.835 | 0 | 3.436 | 429158.271 | 6463.43 | n.m. | 115260.03 | n.m. | -269195.215 | -62.73% | 2076.79 | n.m. | -3.436 | -100% | -145398.401 | -33.88%
117 | 110 | A15710017 | West Paintsville Telecom Moder | 1/1/2017 | 2020-07-01 | 47661.86 | 46007.19 | 22444.21 | 0 | 0 | 116113.26 | 0 | 0 | 0 | 0 | 0 | 0 | 47661.86 | n.m. | 46007.19 | n.m. | 22444.21 | n.m. | 0 | n.m. | 0 | n.m. | 116113.26 | n.m.
118 | 110 | 000025570 | BlueGrass\Walker Town Tie | 4/1/2018 | 10/1/2018 | 114855.51 |  | 0 | 0 | 0 | 114855.51 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 114855.51 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -295375.698 | -72%
119 | 110 | DX17K02B0 | Second Fork Sta - add SCADA | 2/1/2018 | 2022-05-01 | 98845.51 | 14277.65 | 7534.47 | 9071.15 | 3197.93 | 132926.71 | 0 | 0 | 0 | 0 | 0 | 0 | 98845.51 | n.m. | 14277.65 | n.m. | 7534.47 | n.m. | 9071.15 | n.m. | 3197.93 | n.m. | 132926.71 | n.m.
120 | 110 | P18025002 | Kewanee Station Land Purchase | 3/1/2018 | Charges Continued After Dec 2022 | 105184.23 | 4031.76 | 3856.71 | 185362.5 | 6499.25 | 304934.45 | 0 | 87.091 | 0 | 0 | 0 | 87.091 | 105184.23 | n.m. | 3944.669 | 4529% | 3856.71 | n.m. | 185362.5 | n.m. | 6499.25 | n.m. | 304847.359 | 350033%
121 | 110 | DMS18KK08 | KP/Pre Valid Major Event 8 | 10/1/2018 | 6/1/2019 | 114623.46 | -16055.64 | 0 | 0 | 0 | 98567.82 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 114623.46 | n.m. | -16055.64 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 98567.81 | 985678100%
122 | 110 | TA1807312 | D/KPCO/SEL GE Relay | 3/1/2019 | 2021-05-01 |  | 98563.372 | 157021.6 | 8198.5 | 0 | 263783.472 | 0 | 0 | 0 | 0 | -2921656.574 | -2921656.574 | 0 | n.m. | 98563.372 | n.m. | 157021.6 | n.m. | 8198.5 | n.m. | 2921656.574 | -100% | 3185440.046 | -109%
123 | 110 | EDN100296 | Ds-Kp-Ai Small Wire Repl Urd | Charges Began Prior to Jan 2015 | 2021-08-01 |  |  | 0 | 10462.52 | 0 | 10462.52 | 336323.209 | 299920.12 | 381729.507 | 0 | 8457.348 | 1026430.184 | -336323.209 | -100% | -299920.12 | -100% | -381729.507 | -100% | 10462.52 | n.m. | -8457.348 | -100% | -1015967.664 | -98.98%
124 | 110 | DMS17KK03 | KY/ME/Thunder 6/23/17 | 6/1/2017 | 3/1/2018 | -3487.38 |  | 0 | 0 | 0 | -3487.38 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | -3487.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | -3487.39 | -34873900%
125 | 110 | 000008154 | KP Cust Serv Eng Support | Charges Began Prior to Jan 2015 | 6/1/2019 |  | 0 | 0 | 0 | 0 | 0 | 1953522.54 | 2229813.265 | 20498.131 | 1992281.191 | -258029.924 | 5938085.203 | -1953522.54 | -100% | -2229813.265 | -100% | -20498.131 | -100% | -1992281.191 | -100% | 258029.924 | -100% | -5938085.203 | -100%
126 | 110 | P17084024 | DO NOT USE | 10/1/2017 | 2021-03-01 | 70833.52 | 6914.06 | -44344.51 | -34614.94 | 0 | -1211.87 | 0 | 87.122 | 3874.977 | -1610.343 | 0 | 2351.756 | 70833.52 | n.m. | 6826.938 | 7836% | -48219.487 | -1244% | -33004.597 | 2050% | 0 | n.m. | -3563.626 | -151.5%
127 | 110 | EDN014687 | Ds-Kp-Ai Aepc Make Ready | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 55887.42 | -26443.85 | -3366.61 | 100136.3 | -48791.55 | 77421.71 | 16893.868 | 8.319 | 0 | 17492.606 | -36240.368 | -1845.575 | 38993.552 | 230.8% | -26452.169 | -317973% | -3366.61 | n.m. | 82643.694 | 472.4% | -12551.182 | 34.63% | 79267.285 | -4295%
128 | 110 | A15710039 | Pikeville TTMP | 11/1/2018 | 2021-01-01 | 21422.42 | 46064.98 | 24283.28 | 20.82 | 0 | 91791.5 | 0 | 38867.844 | 0 | 0 | 0 | 38867.844 | 21422.42 | n.m. | 7197.136 | 18.52% | 24283.28 | n.m. | 20.82 | n.m. | 0 | n.m. | 52923.656 | 136.2%
129 | 110 | A15710040 | South PIkeville TTMP | 3/1/2018 | 2021-01-01 | 33633.56 | 32801.13 | 14791.99 | 26.15 | 0 | 81252.83 | 0 | 38895.597 | 0 | 0 | 0 | 38895.597 | 33633.56 | n.m. | -6094.467 | -15.67% | 14791.99 | n.m. | 26.15 | n.m. | 0 | n.m. | 42357.233 | 108.9%
130 | 110 | A15710012 | Busseyville Telecom Modernizat | 1/1/2017 | 6/1/2019 | 42112.1 | 3765.19 | 0 | 0 | 0 | 45877.29 | 0 | 0 | 0 | 0 | 0 | 0 | 42112.1 | n.m. | 3765.19 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45877.29 | n.m.
131 | 110 | DMS18KK04 | KY/Pre Valid Major Event | 7/1/2018 | 10/1/2018 | 62537.37 |  | 0 | 0 | 0 | 62537.37 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 62537.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 62537.36 | 625373600%
132 | 110 | DMS17KK04 | KY/Pre Valid Major Event 4 | 11/1/2017 | 2/1/2018 | 670.35 |  | 0 | 0 | 0 | 670.35 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 670.35 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 670.34 | 6703400%
133 | 110 | DMS19KK03 | KY Pre/Valid Major Storm 3 | 6/1/2019 | 10/1/2019 |  | 57887.79 | 0 | 0 | 0 | 57887.79 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 57887.79 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 57887.78 | 578877800%
134 | 110 | P19091002 | Cancel Middle Creek Stn Land | 7/1/2019 | 2022-02-01 |  | 55537.35 | -42405.25 | -12677.78 | -454.32 | -9.3792e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 55537.35 | n.m. | -42405.25 | n.m. | -12677.78 | n.m. | -454.32 | n.m. | -9.3792e-12 | n.m.
135 | 110 | DMS18KK01 | KY/ME/Snow Storm 3/12/18 | 3/1/2018 | 1/1/2019 | 55271.19 | 6.68 | 0 | 0 | 0 | 55277.87 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 55271.19 | n.m. | 6.68 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 55277.86 | 552778600%
136 | 110 | P17076003 | Prestonsburg Remote End Work | 9/1/2017 | Charges Continued After Dec 2022 | 28795.27 | 2467.63 | 35506.25 | 8911.87 | 2686.85 | 78367.87 | 0 | 16310.266 | 572879.293 | 2307.716 | -1852.592 | 589644.683 | 28795.27 | n.m. | -13842.636 | -84.87% | -537373.043 | -93.8% | 6604.154 | 286.2% | 4539.442 | -245% | -511276.813 | -86.71%
137 | 110 | A15710026 | Jenkins Station TTMP | 2/1/2018 | 2020-02-01 | 17308.58 | 30551.35 | 2120.03 | 0 | 0 | 49979.96 | 20675.638 | 0 | 0 | 0 | 0 | 20675.638 | -3367.058 | -16.29% | 30551.35 | n.m. | 2120.03 | n.m. | 0 | n.m. | 0 | n.m. | 29304.322 | 141.7%
138 | 110 | DR19K05A0 | Hazard DA 2019 - D line | 5/1/2019 | Charges Continued After Dec 2022 |  | 47657.63 | 2382772.04 | 1315461.03 | 111403.6 | 3857294.3 | 0 | 0 | 0 | 250.183 | 103.986 | 354.169 | 0 | n.m. | 47657.63 | n.m. | 2382772.04 | n.m. | 1315210.847 | 525700% | 111299.614 | 107033% | 3856940.131 | 1089011%
139 | 110 | 000025516 | Lilly Cornett Woods SH | 4/1/2018 | 10/1/2018 | 47547.76 |  | 0 | 0 | 0 | 47547.76 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 47547.76 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -362683.448 | -88.41%
140 | 110 | DP16K03B0 | Tygart Sta - Dist Station | 10/1/2019 | Charges Continued After Dec 2022 |  | 43569.35 | 158804.25 | 17417.62 | 748199.76 | 967990.98 | 0 | 0 | 0 | 626998.173 | 0 | 626998.173 | 0 | n.m. | 43569.35 | n.m. | 158804.25 | n.m. | -609580.553 | -97.22% | 748199.76 | n.m. | 340992.807 | 54.38%
141 | 110 | P19091009 | Cancel Mid Crk Station (KP D) | 7/1/2019 | 2020-07-01 |  | 42325.42 | -42325.42 | 0 | 0 | 7.276e-12 | 0 | 0 | 686.283 | 492.51 | 0 | 1178.793 | 0 | n.m. | 42325.42 | n.m. | -43011.703 | -6267% | -492.51 | -100% | 0 | n.m. | -1178.793 | -100%
142 | 110 | A15710021 | Allen Station TTMP | 1/1/2017 | 2020-02-01 | 19883.95 | 10527.1 | 2901.12 | 0 | 0 | 33312.17 | 0 | 0 | 0 | 0 | 0 | 0 | 19883.95 | n.m. | 10527.1 | n.m. | 2901.12 | n.m. | 0 | n.m. | 0 | n.m. | 33312.17 | n.m.
143 | 110 | A15710016 | Oakland TS Telecom Modernizati | 1/1/2017 | 8/1/2019 | 19197.69 | 4043.09 | 0 | 0 | 0 | 23240.78 | 0 | 0 | 0 | 0 | 0 | 0 | 19197.69 | n.m. | 4043.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23240.78 | n.m.
144 | 110 | DR19K05B0 | Hazard DA 2019 - Shamrock | 6/1/2019 | Charges Continued After Dec 2022 |  | 35878.69 | 95449.34 | 343997.68 | 383738.22 | 859063.93 | 0 | 0 | 0 | 44.052 | 0 | 44.052 | 0 | n.m. | 35878.69 | n.m. | 95449.34 | n.m. | 343953.628 | 780790% | 383738.22 | n.m. | 859019.878 | 1950013%
145 | 110 | P17084005 | Myra Station | 11/1/2017 | Charges Continued After Dec 2022 | 7433.68 | 11508.2 | 54188.42 | 53534.52 | 105190.27 | 231855.09 | 0 | 481626.355 | 300774.067 | 3428.669 | -1312311.326 | -526482.235 | 7433.68 | n.m. | -470118.155 | -97.61% | -246585.647 | -81.98% | 50105.851 | 1461% | 1417501.596 | -108% | 758337.325 | -144%
146 | 110 | DMS18KK09 | KP/Pre Valid Major Event 9 | 12/1/2018 | 2/1/2019 | 51612.43 | -16293.02 | 0 | 0 | 0 | 35319.41 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 51612.43 | n.m. | -16293.02 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 35319.4 | 353194000%
147 | 110 | A15710019 | Coalton Station TTMP | 1/1/2017 | 8/1/2019 | 5765.99 | 13991.56 | 0 | 0 | 0 | 19757.55 | 0 | 0 | 0 | 0 | 0 | 0 | 5765.99 | n.m. | 13991.56 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19757.55 | n.m.
148 | 110 | 000025521 | Bishop Knobb SH | 8/1/2018 | 9/1/2018 | 33931.76 |  | 0 | 0 | 0 | 33931.76 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 33931.76 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -376299.448 | -91.73%
149 | 110 | A15710020 | Prestonburg Station TTMP | 1/1/2017 | 2020-07-01 | 11676.44 | 9321.53 | 3651.2 | 0 | 0 | 24649.17 | 295.86 | 0 | 0 | 0 | 0 | 295.86 | 11380.58 | 3847% | 9321.53 | n.m. | 3651.2 | n.m. | 0 | n.m. | 0 | n.m. | 24353.31 | 8231%
150 | 110 | DR19K05B2 | Hazard DA 2019 - Slemp | 6/1/2019 | Charges Continued After Dec 2022 |  | 33526.33 | 497362.67 | 759251.2 | 54808.22 | 1344948.42 | 0 | 0 | 0 | 56.703 | 0 | 56.703 | 0 | n.m. | 33526.33 | n.m. | 497362.67 | n.m. | 759194.497 | 1338897% | 54808.22 | n.m. | 1344891.717 | 2371818%
151 | 110 | DR19K05B1 | Hazard DA 2019 - Engle | 6/1/2019 | 2021-08-01 |  | 30740.71 | 725300.78 | 26727.06 | 0 | 782768.55 | 0 | 0 | 0 | 32.711 | 0 | 32.711 | 0 | n.m. | 30740.71 | n.m. | 725300.78 | n.m. | 26694.349 | 81607% | 0 | n.m. | 782735.839 | 2392883%
152 | 110 | DMS18KK06 | KP/Pre Valid Major Event 6 | 9/1/2018 | 1/1/2019 | 27714.93 | 1494.35 | 0 | 0 | 0 | 29209.28 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 27714.93 | n.m. | 1494.35 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 29209.27 | 292092700%
153 | 110 | P17084014 | Henry Clay Station Retirement | 9/1/2017 | 2021-08-01 | 5826.03 | 1554.45 | 1735.94 | -29617.06 | 0 | -20500.64 | 0 | 1373.546 | 1379.138 | 1731.772 | 0 | 4484.456 | 5826.03 | n.m. | 180.904 | 13.17% | 356.802 | 25.87% | -31348.832 | -1810% | 0 | n.m. | -24985.096 | -557.1%
154 | 110 | A15710038 | Grayson TTMP | 3/1/2018 | 2020-01-01 | 10749.3 | 15080.74 | 307.02 | 0 | 0 | 26137.06 | 0 | 24313.116 | 0 | 0 | 0 | 24313.116 | 10749.3 | n.m. | -9232.376 | -37.97% | 307.02 | n.m. | 0 | n.m. | 0 | n.m. | 1823.944 | 7.502%
155 | 110 | P17084009 | Burton Station Retirement | 9/1/2017 | 2020-07-01 | -462.3 | 4475.54 | -25678.98 | 0 | 0 | -21665.74 | 0 | 1159547.264 | 2568422.047 | -648.819 | 911830.746 | 4639151.238 | -462.3 | n.m. | -1155071.724 | -99.61% | -2594101.027 | -101% | 648.819 | -100% | -911830.746 | -100% | -4660816.978 | -100.5%
156 | 110 | A15710013 | Cannonsburg Telecom Modernizat | 1/1/2018 | 3/1/2019 | 19217.07 | 3057.88 | 0 | 0 | 0 | 22274.95 | 0 | 0 | 0 | 0 | 0 | 0 | 19217.07 | n.m. | 3057.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22274.95 | n.m.
157 | 110 | P17084025 | Elwood Station Retirement | 9/1/2017 | Charges Continued After Dec 2022 | 1946.45 | 1517.48 | 6573.61 | 2919.22 | 893.7 | 13850.46 | 0 | 1194.116 | 1070.101 | 1116.399 | -968.352 | 2412.264 | 1946.45 | n.m. | 323.364 | 27.08% | 5503.509 | 514.3% | 1802.821 | 161.5% | 1862.052 | -192.3% | 11438.196 | 474.2%
158 | 110 | P14030009 | Stinnett Station & Telecom | 11/1/2016 | Charges Continued After Dec 2022 | 3353.69 | 2130.05 | 5705.88 | 43842.6 | 23245.6 | 78277.82 | 834.96 | 78506.966 | 30483.294 | 2586.355 | 219511.262 | 331922.837 | 2518.73 | 301.7% | -76376.916 | -97.29% | -24777.414 | -81.28% | 41256.245 | 1595% | -196265.662 | -89.41% | -253645.017 | -76.42%
159 | 110 | A19442001 | Grayson Meter Mod | 5/1/2019 | 2021-05-01 |  | 20045.12 | 388547.93 | 19066.6 | 0 | 427659.65 | 0 | 0 | 151796.409 | 0 | 0 | 151796.409 | 0 | n.m. | 20045.12 | n.m. | 236751.521 | 156% | 19066.6 | n.m. | 0 | n.m. | 275863.241 | 181.7%
160 | 110 | DMS19KK04 | KY Pre/Valid Major Storm 4 | 10/1/2019 | 11/1/2019 |  | 17278.42 | 0 | 0 | 0 | 17278.42 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 17278.42 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | 17278.41 | 172784100%
161 | 110 | A20705033 | Barrenshe Station Pre-Eng | 7/1/2019 | Charges Continued After Dec 2022 |  | 16770.15 | 681.15 | 615.49 | -18112.72 | -45.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 16770.15 | n.m. | 681.15 | n.m. | 615.49 | n.m. | -18112.72 | n.m. | -45.93 | n.m.
162 | 110 | P17225006 | Ramey Station | 12/1/2017 | Charges Continued After Dec 2022 | 12437.46 | 1579.12 | 663.25 | -14709.5 | 1325.91 | 1296.24 | 0 | 3528326.199 | 2234291.359 | 478.132 | 0 | 5763095.69 | 12437.46 | n.m. | -3526747.079 | -99.96% | -2233628.109 | -99.97% | -15187.632 | -3176% | 1325.91 | n.m. | -5761799.45 | -99.98%
163 | 110 | P19092002 | Cancel Allen Station (Dist) | 9/1/2019 | Charges Continued After Dec 2022 |  | 15212.19 | 17590.2 | 16762.05 | 623099.14 | 672663.58 | 0 | 0 | 6381.141 | 1114.18 | 495873.16 | 503368.481 | 0 | n.m. | 15212.19 | n.m. | 11209.059 | 175.7% | 15647.87 | 1404% | 127225.98 | 25.66% | 169295.099 | 33.63%
164 | 110 | A15710002 | Princess Tele. Moderniz. Stati | 12/1/2016 | 5/1/2018 | 10376.59 |  | 0 | 0 | 0 | 10376.59 | 490.35 | 27.779 | 0 | 0 | 0 | 518.129 | 9886.24 | 2016% | -27.779 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9858.461 | 1903%
165 | 110 | A20705058 | Falcon Station 46kV removal | 9/1/2019 | 2021-03-01 |  | 12176.27 | 9728.54 | -21904.81 | 0 | 7.276e-12 | 0 | 0 | 0 | 218505.903 | 0 | 218505.903 | 0 | n.m. | 12176.27 | n.m. | 9728.54 | n.m. | -240410.713 | -110% | 0 | n.m. | -218505.903 | -100%
166 | 110 | P17083016 | McKinney Station Work | 3/1/2019 | Charges Continued After Dec 2022 |  | 9341.56 | 44789.34 | 17239.98 | 13176.85 | 84547.73 | 0 | 0 | 103757.669 | 103307.577 | -3832.696 | 203232.55 | 0 | n.m. | 9341.56 | n.m. | -58968.329 | -56.83% | -86067.597 | -83.31% | 17009.546 | -443.8% | -118684.82 | -58.4%
167 | 110 | B110KYCSV | D/KY/Customer Service | 9/1/2017 | 12/1/2018 | 689.7 |  | 0 | 0 | 0 | 689.7 | 0 | 0 | 0 | 0 | 0 | 0 | 689.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 689.7 | n.m.
168 | 110 | P18025003 | DO NOT USE | 3/1/2018 | 2022-03-01 | 1213.43 | 6787.34 | 324.95 | 293.66 | -8619.38 | 0 | 0 | 4.572 | 12559.577 | 359.489 | 0 | 12923.638 | 1213.43 | n.m. | 6782.768 | 148355% | -12234.627 | -97.41% | -65.829 | -18.31% | -8619.38 | n.m. | -12923.638 | -100%
169 | 110 | P17083030 | Garrett Station (Distribution) | 4/1/2019 | Charges Continued After Dec 2022 |  | 7740.45 | 60185.75 | 16210.02 | 133010.54 | 217146.76 | 0 | 0 | 39825.99 | 632841.715 | -283.338 | 672384.367 | 0 | n.m. | 7740.45 | n.m. | 20359.76 | 51.12% | -616631.695 | -97.44% | 133293.878 | -47044% | -455237.607 | -67.7%
170 | 110 | A20705084 | Belfry Needs Assessment | 11/1/2019 | 2020-08-01 |  | 7626.92 | -7626.92 | 0 | 0 | 0 | 0 | 0 | 0 | 243.836 | 0 | 243.836 | 0 | n.m. | 7626.92 | n.m. | -7626.92 | n.m. | -243.836 | -100% | 0 | n.m. | -243.836 | -100%
171 | 110 | 000025515 | Long Span Rehab 2018 | 8/1/2019 | 10/1/2019 |  | 7494.87 | 0 | 0 | 0 | 7494.87 | 0 | 0 | 0 | 0 | 410231.208 | 410231.208 | 0 | n.m. | 7494.87 | n.m. | 0 | n.m. | 0 | n.m. | -410231.208 | -100% | -402736.338 | -98.17%
172 | 110 | A20705085 | Tom Watkins Station Needs Asmt | 11/1/2019 | Charges Continued After Dec 2022 |  | 6985.08 | 2337.53 | 328.8 | 274.36 | 9925.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6985.08 | n.m. | 2337.53 | n.m. | 328.8 | n.m. | 274.36 | n.m. | 9925.77 | n.m.
173 | 110 | A20705068 | Coleman Stn Needs Assessment | 9/1/2019 | Charges Continued After Dec 2022 |  | 6725.33 | 2680.56 | 331.74 | 276.81 | 10014.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6725.33 | n.m. | 2680.56 | n.m. | 331.74 | n.m. | 276.81 | n.m. | 10014.44 | n.m.
174 | 110 | P17076011 | Distribution work at Kenwood | 4/1/2018 | Charges Continued After Dec 2022 | 4433.95 | 1242.45 | 230.56 | 208.32 | 173.85 | 6289.13 | 0 | 0 | 1867111.475 | 254.938 | 0 | 1867366.413 | 4433.95 | n.m. | 1242.45 | n.m. | -1866880.915 | -99.99% | -46.618 | -18.29% | 173.85 | n.m. | -1861077.283 | -99.66%
175 | 110 | P18221011 | Collier Remote End | 5/1/2019 | Charges Continued After Dec 2022 |  | 5200.66 | 1526.7 | 7418.25 | 18959.12 | 33104.73 | 0 | 0 | 195.297 | 24156.139 | 187965.158 | 212316.594 | 0 | n.m. | 5200.66 | n.m. | 1331.403 | 681.7% | -16737.889 | -69.29% | -169006.038 | -89.91% | -179211.864 | -84.41%
176 | 110 | DP18K01L0 | Lloyd Sta - Purchase property | 6/1/2019 | 2022-07-01 |  | 3668.09 | 275.26 | 58.6 | -4001.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 3668.09 | n.m. | 275.26 | n.m. | 58.6 | n.m. | -4001.95 | n.m. | 0 | n.m.
177 | 110 | KYVVO12DS | KP/KY VoltVar Opt D Station | Charges Began Prior to Jan 2015 | 1/1/2018 | 1737.12 |  | 0 | 0 | 0 | 1737.12 | 0 | 0 | 0 | 0 | 0 | 0 | 1737.12 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1737.12 | n.m.
178 | 110 | EDN014673 | Ds-Kp-Ai Pole Reinforcement | 4/1/2014 | 5/1/2018 | 3380.07 |  | 1245.26 | 2563.66 | 0 | 7188.99 | 0 | 0 | 0 | 0 | 155873.558 | 155873.558 | 3380.07 | n.m. | 0 | n.m. | 1245.26 | n.m. | 2563.66 | n.m. | -155873.558 | -100% | -148684.568 | -95.39%
179 | 110 | A15710086 | Hayward Station TTMP | 7/1/2019 | Charges Continued After Dec 2022 |  | 3039.53 | 1152.61 | 13365.68 | 6706.64 | 24264.46 | 0 | 0 | 29.824 | 17720.231 | 4526.706 | 22276.761 | 0 | n.m. | 3039.53 | n.m. | 1122.786 | 3765% | -4354.551 | -24.57% | 2179.934 | 48.16% | 1987.699 | 8.923%
180 | 110 | A15710076 | Russell Station TTMP | 7/1/2019 | Charges Continued After Dec 2022 |  | 2893.26 | 6336.71 | 36138.22 | 23319.92 | 68688.11 | 0 | 0 | 21.728 | 70781.187 | 0 | 70802.915 | 0 | n.m. | 2893.26 | n.m. | 6314.982 | 29064% | -34642.967 | -48.94% | 23319.92 | n.m. | -2114.805 | -2.987%
181 | 110 | A15710075 | Belhaven Station TTMP | 6/1/2019 | 2022-10-01 |  | 2719.9 | 26276.89 | 50634.54 | 36994.76 | 116626.09 | 0 | 0 | 14.796 | 80854.586 | 2938.726 | 83808.108 | 0 | n.m. | 2719.9 | n.m. | 26262.094 | 177495% | -30220.046 | -37.38% | 34056.034 | 1159% | 32817.982 | 39.16%
182 | 110 | A15710080 | Tenth Street Station TTMP | 6/1/2019 | 2022-08-01 |  | 2711.45 | 22154.88 | 21655.92 | 51728.64 | 98250.89 | 0 | 0 | 15.316 | 81762.488 | 0 | 81777.804 | 0 | n.m. | 2711.45 | n.m. | 22139.564 | 144552% | -60106.568 | -73.51% | 51728.64 | n.m. | 16473.086 | 20.14%
183 | 110 | A15710079 | Hitchins Station TTMP | 7/1/2019 | 2021-10-01 |  | 2556.72 | 12758.05 | 35893.89 | 0 | 51208.66 | 0 | 0 | 30.252 | 59783.652 | 0 | 59813.904 | 0 | n.m. | 2556.72 | n.m. | 12727.798 | 42073% | -23889.762 | -39.96% | 0 | n.m. | -8605.244 | -14.39%
184 | 110 | DX16K01A0 | Falcon Sta - Mtn Parkway PPR | 4/1/2016 | 2022-11-01 |  |  | 0 | 0 | 604.18 | 604.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 604.18 | n.m. | 604.18 | n.m.
185 | 110 | P19092014 | Prestonsburg Remote End | 5/1/2019 | Charges Continued After Dec 2022 |  | 2215.6 | 403.31 | 1999.92 | 36589.88 | 41208.71 | 0 | 0 | 45.458 | 99.546 | 330453.158 | 330598.162 | 0 | n.m. | 2215.6 | n.m. | 357.852 | 787.2% | 1900.374 | 1909% | -293863.278 | -88.93% | -289389.452 | -87.54%
186 | 110 | A15710072 | Raccoon Station TTMP | 9/1/2019 | Charges Continued After Dec 2022 |  | 1963.97 | 79.77 | 23416.56 | 11377.03 | 36837.33 | 0 | 0 | 0 | 17655.4 | 0 | 17655.4 | 0 | n.m. | 1963.97 | n.m. | 79.77 | n.m. | 5761.16 | 32.63% | 11377.03 | n.m. | 19181.93 | 108.6%
187 | 110 | P17083025 | Soft Shell Station Work (KPCo) | 3/1/2019 | Charges Continued After Dec 2022 |  | 1756.78 | -1756.78 | 50642.68 | 3722.88 | 54365.56 | 0 | 0 | 90.075 | 0 | 21349.018 | 21439.093 | 0 | n.m. | 1756.78 | n.m. | -1846.855 | -2050% | 50642.68 | n.m. | -17626.138 | -82.56% | 32926.467 | 153.6%
188 | 110 | A15710085 | Olive Hill Station TTMP | 7/1/2019 | Charges Continued After Dec 2022 |  | 1605.89 | 21589.25 | 21494.95 | 5817.3 | 50507.39 | 0 | 0 | 9.91 | 81178.288 | 105438.456 | 186626.654 | 0 | n.m. | 1605.89 | n.m. | 21579.34 | 217753% | -59683.338 | -73.52% | -99621.156 | -94.48% | -136119.264 | -72.94%
189 | 110 | P19092016 | McKinney Remote End Work | 5/1/2019 | Charges Continued After Dec 2022 |  | 1569.96 | 472.73 | 3675.16 | 35193.79 | 40911.64 | 0 | 0 | 49.983 | 83.236 | 166190.426 | 166323.645 | 0 | n.m. | 1569.96 | n.m. | 422.747 | 845.8% | 3591.924 | 4315% | -130996.636 | -78.82% | -125412.005 | -75.4%
190 | 110 | P13064028 | D Line Work | 11/1/2019 | 2021-04-01 |  | 1488.42 | 84256.81 | 45580.39 | 0 | 131325.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1488.42 | n.m. | 84256.81 | n.m. | 45580.39 | n.m. | 0 | n.m. | 131325.62 | n.m.
191 | 110 | P17225007 | Ramey Station - Distribution | 12/1/2017 | 2021-11-01 | 53.42 | 55.72 | 45.95 | -1177.47 | 0 | -1022.38 | 0 | 2022123.542 | 1397360.292 | 38.712 | 0 | 3419522.546 | 53.42 | n.m. | -2022067.822 | -100% | -1397314.342 | -100% | -1216.182 | -3142% | 0 | n.m. | -3420544.926 | -100%
192 | 110 | P18221016 | Jackhorn Distribution work | 9/1/2019 | 2021-05-01 |  | 904.11 | 3356.18 | -4260.29 | 0 | 9.0949e-13 | 0 | 0 | 0 | 2031758.371 | 0 | 2031758.371 | 0 | n.m. | 904.11 | n.m. | 3356.18 | n.m. | -2036018.661 | -100.2% | 0 | n.m. | -2031758.371 | -100%
193 | 110 | A13212004 | D/KP/McKinney - Telecom Legacy | Charges Began Prior to Jan 2015 | 10/1/2018 | -5.62 |  | 0 | 0 | 0 | -5.62 | 0 | 0 | 0 | 0 | 0 | 0 | -5.62 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -5.62 | n.m.
194 | 110 | P18025004 | DO NOT USE | 3/1/2018 | 2022-03-01 | 520.72 | 26.97 | 22.24 | 20.1 | -590.03 | 0 | 0 | 2.736 | 3415.741 | 24.547 | 0 | 3443.024 | 520.72 | n.m. | 24.234 | 885.7% | -3393.501 | -99.35% | -4.447 | -18.12% | -590.03 | n.m. | -3443.024 | -100%
195 | 110 | DR19K04B2 | Pikeville DA 2019 - Stanv. D | 11/1/2019 | 2020-01-01 |  | 344.26 | 226.62 | 0 | 0 | 570.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 344.26 | n.m. | 226.62 | n.m. | 0 | n.m. | 0 | n.m. | 570.88 | n.m.
196 | 110 | A15710060 | Pikesville SC TTMP | 2/1/2019 | 2020-05-01 |  | 136 | -136 | 0 | 0 | 0 | 0 | 0 | 33849.551 | 0 | 0 | 33849.551 | 0 | n.m. | 136 | n.m. | -33985.551 | -100.4% | 0 | n.m. | 0 | n.m. | -33849.551 | -100%
197 | 110 | DR20K02B3 | Breaker Repl - Jenkins | 12/1/2019 | 2022-09-01 |  | 78.69 | 60309.55 | 6600.61 | -66988.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 78.69 | n.m. | 60309.55 | n.m. | 6600.61 | n.m. | -66988.85 | n.m. | 0 | n.m.
198 | 110 | DR20K02B1 | Breaker Repl - Sidney | 12/1/2019 | 2022-09-01 |  | 78.69 | 117203.47 | 9833.49 | -127115.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 78.69 | n.m. | 117203.47 | n.m. | 9833.49 | n.m. | -127115.65 | n.m. | 0 | n.m.
199 | 110 | DR20K02B0 | Breaker Repl - E Prestonsburg | 12/1/2019 | 2022-09-01 |  | 78.69 | 64140.56 | 6577.71 | -70796.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 78.69 | n.m. | 64140.56 | n.m. | 6577.71 | n.m. | -70796.96 | n.m. | 0 | n.m.
200 | 110 | P17084001 | Cancel: DO NOT USE | 11/1/2017 | 2021-03-01 | 38121.92 | -71822.63 | -21.48 | 17.46 | 0 | -33704.73 | 0 | 52899.064 | 3762.683 | 0 | 22007.54 | 78669.287 | 38121.92 | n.m. | -124721.694 | -235.8% | -3784.163 | -100.6% | 17.46 | n.m. | -22007.54 | -100% | -112374.017 | -142.8%
201 | 110 | A18702002 | CANCELLED | 4/1/2018 | 7/1/2018 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m.
202 | 110 | DMS18KK07 | KP/Pre Valid Major Event 7 | 9/1/2018 | 12/1/2018 | -6.0507e-15 |  | 0 | 0 | 0 | -6.0507e-15 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | -6.0507e-15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -0.01 | -100% | -0.01 | -100%
203 | 110 | A15702008 | CANCELLED | 12/1/2016 | 10/1/2018 | -58403.55 |  | 0 | 0 | 0 | -58403.55 | 0 | 0 | 0 | 0 | 0 | 0 | -58403.55 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -58403.55 | n.m.
204 | 110 | P17225011 | Hoods Creek Land Purchase | 2/1/2018 | 8/1/2019 | 27503.24 | -27503.24 | 0 | 0 | 0 | 3.638e-12 | 0 | 524.403 | 1659.471 | 0.006 | 0 | 2183.88 | 27503.24 | n.m. | -28027.643 | -5345% | -1659.471 | -100% | -0.006 | -100% | 0 | n.m. | -2183.88 | -100%
205 | 110 | ETN000110 | T Kp D Anda | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 7.6398e-11 | -1.5007e-11 | -8.7839e-11 | -6.9946e-11 | 6.3608e-11 | -3.2786e-11 | 0 | 0 | 0 | 0 | 0 | 0 | 7.6398e-11 | n.m. | -1.5007e-11 | n.m. | -8.7839e-11 | n.m. | -6.9946e-11 | n.m. | 6.3608e-11 | n.m. | -3.2786e-11 | n.m.
206 | 110 | P19091007 | Cancel Prestonsburg Remote End | 8/1/2019 | 10/1/2019 |  | -1146.23 | 1146.23 | 0 | 0 | -1.819e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | -1146.23 | n.m. | 1146.23 | n.m. | 0 | n.m. | 0 | n.m. | -1.819e-12 | n.m.
207 | 110 | P12124003 | DKPLOVELY Station SCADA Upgr | Charges Began Prior to Jan 2015 | 2/1/2019 | -120644.7 | 16935.77 | 0 | 0 | 0 | -103708.93 | 0 | 0 | 0 | 0 | 0 | 0 | -120644.7 | n.m. | 16935.77 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -103708.93 | n.m.
208 | 110 | TREEREL20 | ROW Capital widening & removal | 2020-02-01 | 2021-06-01 |  |  | 7437385.51 | 116467.62 |  | 7553853.13 | 0 | 0 | 0 | 518.946 | 0 | 518.946 | 0 | n.m. | 0 | n.m. | 7437385.51 | n.m. | 115948.674 | 22343% | 0 | n.m. | 7553334.184 | 1455514%
209 | 110 | P19036005 | Osborne 69kV Station | 2020-07-01 | Charges Continued After Dec 2022 |  |  | 22039 | 437479.77 | 2645706.41 | 3105225.18 | 0 | 0 | 0 | 10.397 | 3704516.27 | 3704526.667 | 0 | n.m. | 0 | n.m. | 22039 | n.m. | 437469.373 | 4207650% | -1058809.86 | -28.58% | -599301.487 | -16.18%
210 | 110 | DMS20KK04 | KY/ME/ Wind Storm 04/12/2020 | 2020-04-01 | 2021-11-01 |  |  | 4086839.05 | 471.79 |  | 4087310.84 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 4086839.05 | n.m. | 471.79 | n.m. | -0.01 | -100% | 4087310.83 | 40873108300%
211 | 110 | IT1101725 | CIS-Common Deployment-KYP D | 2020-11-01 | Charges Continued After Dec 2022 |  |  | 64722.17 | 138382.43 | 590752.91 | 793857.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 64722.17 | n.m. | 138382.43 | n.m. | 590752.91 | n.m. | 793857.51 | n.m.
212 | 110 | DP14K02A0 | KP/Raccoon Sta - D line exits | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 559101.64 | 286058.08 | 149555.87 | 994715.59 | 0 | 0 | 0 | 153.151 | 0 | 153.151 | 0 | n.m. | 0 | n.m. | 559101.64 | n.m. | 285904.929 | 186682% | 149555.87 | n.m. | 994562.439 | 649400%
213 | 110 | IT110CCIC | Cloud Comp Imp Cost - KyP D | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 364523.55 | 166373.05 | 154435.93 | 685332.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 364523.55 | n.m. | 166373.05 | n.m. | 154435.93 | n.m. | 685332.53 | n.m.
214 | 110 | P19036011 | Osborne 69kV Land Purchase | 2020-08-01 | Charges Continued After Dec 2022 |  |  | 2724.43 | 399968.79 | 401171.7 | 803864.92 | 0 | 0 | 0 | 58.945 | 0 | 58.945 | 0 | n.m. | 0 | n.m. | 2724.43 | n.m. | 399909.845 | 678446% | 401171.7 | n.m. | 803805.975 | 1363654%
215 | 110 | P19305013 | Orinoco KPCO D | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 38058.38 | 131176.81 | 264421.74 | 433656.93 | 0 | 0 | 0 | 340378.609 | 2155737.024 | 2496115.633 | 0 | n.m. | 0 | n.m. | 38058.38 | n.m. | -209201.799 | -61.46% | -1891315.284 | -87.73% | -2062458.703 | -82.63%
216 | 110 | A16928017 | Purchase Spare 69-12 20MVA | 2020-12-01 | 2022-04-01 |  |  | 281484.81 | 390627.99 | 62939.71 | 735052.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 281484.81 | n.m. | 390627.99 | n.m. | 62939.71 | n.m. | 735052.51 | n.m.
217 | 110 | P19215015 | Coalton Remote End | 2020-11-01 | 2022-10-01 |  |  | 16204.5 | 613699.75 | 16647.89 | 646552.14 | 0 | 0 | 0 | 236475.21 | 10764.216 | 247239.426 | 0 | n.m. | 0 | n.m. | 16204.5 | n.m. | 377224.54 | 159.5% | 5883.674 | 54.66% | 399312.714 | 161.5%
218 | 110 | DMS20KK11 | KY Pre\Valid Major Storm 11 | 2020-12-01 | 2021-03-01 |  |  | 199497.33 | 403760.66 |  | 603257.99 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 199497.33 | n.m. | 403760.66 | n.m. | -0.01 | -100% | 603257.98 | 6032579800%
219 | 110 | DX20K01A0 | Breaks Russell Fork KY | 2020-11-01 | 2022-05-01 |  |  | 7072.35 | 336502.2 | 53020.92 | 396595.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7072.35 | n.m. | 336502.2 | n.m. | 53020.92 | n.m. | 396595.47 | n.m.
220 | 110 | P19305022 | New Camp Station | 2020-08-01 | Charges Continued After Dec 2022 |  |  | 124.36 | 78988.37 | 174713.3 | 253826.03 | 0 | 0 | 0 | 5.304 | 1407528.354 | 1407533.658 | 0 | n.m. | 0 | n.m. | 124.36 | n.m. | 78983.066 | 1489123% | -1232815.054 | -87.59% | -1153707.628 | -81.97%
221 | 110 | P19092022 | Allen Station Land Purchase | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 4265.65 | 125819.94 | 103174.73 | 233260.32 | 0 | 0 | 0 | 352155.798 | 441048.138 | 793203.936 | 0 | n.m. | 0 | n.m. | 4265.65 | n.m. | -226335.858 | -64.27% | -337873.408 | -76.61% | -559943.616 | -70.59%
222 | 110 | DMS20KK01 | KY/ME/Wind Storm 01/11/2020 | 2020-01-01 | 2020-09-01 |  |  | 224448.85 |  |  | 224448.85 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 224448.85 | n.m. | 0 | n.m. | -0.01 | -100% | 224448.84 | 2244488400%
223 | 110 | IT1101722 | CIS-Net Meter/Spc Bill-KYP D | 2020-12-01 | Charges Continued After Dec 2022 |  |  | 1553.67 | 29353.6 | 107313.68 | 138220.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1553.67 | n.m. | 29353.6 | n.m. | 107313.68 | n.m. | 138220.95 | n.m.
224 | 110 | DMS20KK03 | KY/ME/Thunderstorm 04/09/2020 | 2020-04-01 | 2021-01-01 |  |  | 179165.29 | 8.6 |  | 179173.89 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 179165.29 | n.m. | 8.6 | n.m. | -0.01 | -100% | 179173.88 | 1791738800%
225 | 110 | P19215016 | Cannonsburg Station Work | 2020-10-01 | 2022-04-01 |  |  | 7939.42 | 85845.49 | -118.05 | 93666.86 | 0 | 0 | 0 | 43356.608 | 6845.662 | 50202.27 | 0 | n.m. | 0 | n.m. | 7939.42 | n.m. | 42488.882 | 98% | -6963.712 | -101.7% | 43464.59 | 86.58%
226 | 110 | P17083033 | Garrett Land Purchase | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 24411.37 | 63083.15 | 1420.26 | 88914.78 | 0 | 0 | 159.107 | 151012.968 | 94596.812 | 245768.887 | 0 | n.m. | 0 | n.m. | 24252.263 | 15243% | -87929.818 | -58.23% | -93176.552 | -98.5% | -156854.107 | -63.82%
227 | 110 | A15710057 | Daisy Station TTMP | 2020-01-01 | 2021-11-01 |  |  | 50517.95 | 21786.6 |  | 72304.55 | 0 | 0 | 9024.651 | 8608.455 | 0 | 17633.106 | 0 | n.m. | 0 | n.m. | 41493.299 | 459.8% | 13178.145 | 153.1% | 0 | n.m. | 54671.444 | 310%
228 | 110 | A15710053 | Topmost Station TTMP | 2020-01-01 | 2021-06-01 |  |  | 65341.73 | 6520.74 |  | 71862.47 | 0 | 0 | 33842.778 | 0 | 0 | 33842.778 | 0 | n.m. | 0 | n.m. | 31498.952 | 93.07% | 6520.74 | n.m. | 0 | n.m. | 38019.692 | 112.3%
229 | 110 | A15710063 | Falcon Station TTMP | 2020-03-01 | 2021-02-01 |  |  | 67445.72 | 1317.58 |  | 68763.3 | 0 | 0 | 42867.456 | 0 | 0 | 42867.456 | 0 | n.m. | 0 | n.m. | 24578.264 | 57.34% | 1317.58 | n.m. | 0 | n.m. | 25895.844 | 60.41%
230 | 110 | A15710062 | Coleman Station TTMP | 2020-01-01 | 2021-09-01 |  |  | 50766.51 | 12666.19 |  | 63432.7 | 0 | 0 | 33842.778 | 0 | 0 | 33842.778 | 0 | n.m. | 0 | n.m. | 16923.732 | 50.01% | 12666.19 | n.m. | 0 | n.m. | 29589.922 | 87.43%
231 | 110 | DMS20KK09 | KY Pre\Valid Major Storm 09 | 2020-11-01 | 2021-01-01 |  |  | 55356.61 | 49.59 |  | 55406.2 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 55356.61 | n.m. | 49.59 | n.m. | -0.01 | -100% | 55406.19 | 554061900%
232 | 110 | IT1101724 | CIS-Meter Enhancements-KYP D | 2020-12-01 | Charges Continued After Dec 2022 |  |  | 6343.95 | 6634.52 | 26692.38 | 39670.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 6343.95 | n.m. | 6634.52 | n.m. | 26692.38 | n.m. | 39670.85 | n.m.
233 | 110 | DMS20KK05 | KY Pre\Valid Major Storm 05 | 2020-05-01 | 2020-07-01 |  |  | 45980.33 |  |  | 45980.33 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 45980.33 | n.m. | 0 | n.m. | -0.01 | -100% | 45980.32 | 459803200%
234 | 110 | DMS20KK02 | KY Pre\Valid Major Storm 02 | 2020-03-01 | 2020-10-01 |  |  | 45107.11 |  |  | 45107.11 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 45107.11 | n.m. | 0 | n.m. | -0.01 | -100% | 45107.1 | 451071000%
235 | 110 | DMS20KK06 | KY Pre\Valid Major Storm 06 | 2020-06-01 | 2020-09-01 |  |  | 43549.85 | -0.01 |  | 43549.84 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 43549.85 | n.m. | -0.01 | n.m. | -0.01 | -100% | 43549.83 | 435498300%
236 | 110 | A21222010 | Wurtland Station TTMP | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 2515.18 | 9863.82 | 18292.49 | 30671.49 | 0 | 0 | 0 | 0 | 5080.408 | 5080.408 | 0 | n.m. | 0 | n.m. | 2515.18 | n.m. | 9863.82 | n.m. | 13212.082 | 260.1% | 25591.082 | 503.7%
237 | 110 | A15710056 | Jeff Station TTMP | 2020-01-01 | 2021-06-01 |  |  | 25313.91 | 6055.15 |  | 31369.06 | 0 | 0 | 33842.778 | 4934.164 | 0 | 38776.942 | 0 | n.m. | 0 | n.m. | -8528.868 | -25.2% | 1120.986 | 22.72% | 0 | n.m. | -7407.882 | -19.1%
238 | 110 | A15710055 | Vicco Station TTMP | 2020-01-01 | 2021-06-01 |  |  | 21038.14 | 4719.56 |  | 25757.7 | 0 | 0 | 33842.778 | 0 | 0 | 33842.778 | 0 | n.m. | 0 | n.m. | -12804.638 | -37.84% | 4719.56 | n.m. | 0 | n.m. | -8085.078 | -23.89%
239 | 110 | P19036002 | Burton Station Retirement | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 14344.13 | 5269.07 | 1567.28 | 21180.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 14344.13 | n.m. | 5269.07 | n.m. | 1567.28 | n.m. | 21180.48 | n.m.
240 | 110 | A15710059 | Keyser Station TTMP | 2020-03-01 | 2021-11-01 |  |  | 14975.8 | 4281.42 |  | 19257.22 | 0 | 0 | 9024.651 | 0 | 0 | 9024.651 | 0 | n.m. | 0 | n.m. | 5951.149 | 65.94% | 4281.42 | n.m. | 0 | n.m. | 10232.569 | 113.4%
241 | 110 | A21222011 | Highland Station TTMP | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 1549.56 | 8971.49 | 8332.24 | 18853.29 | 0 | 0 | 0 | 0 | 6694.902 | 6694.902 | 0 | n.m. | 0 | n.m. | 1549.56 | n.m. | 8971.49 | n.m. | 1637.338 | 24.46% | 12158.388 | 181.6%
242 | 110 | A15710054 | Beckham Station TTMP | 2020-01-01 | 2021-06-01 |  |  | 17343.93 | 1454.97 |  | 18798.9 | 0 | 0 | 33842.778 | 0 | 0 | 33842.778 | 0 | n.m. | 0 | n.m. | -16498.848 | -48.75% | 1454.97 | n.m. | 0 | n.m. | -15043.878 | -44.45%
243 | 110 | P20035008 | Middle Creek Station | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 4277.79 | 968.04 | 2686.85 | 7932.68 | 0 | 0 | 0 | 45.671 | 19003.758 | 19049.429 | 0 | n.m. | 0 | n.m. | 4277.79 | n.m. | 922.369 | 2020% | -16316.908 | -85.86% | -11116.749 | -58.36%
244 | 110 | EDN100232 | Ds-Kp-Ai Urd Program | 2020-11-01 | 2021-04-01 |  |  | 14127.47 | 1074.11 |  | 15201.58 | 8308.519 | 4.089 | 0 | 8648.883 | 8457.348 | 25418.839 | -8308.519 | -100% | -4.089 | -100% | 14127.47 | n.m. | -7574.773 | -87.58% | -8457.348 | -100% | -10217.259 | -40.2%
245 | 110 | P20035005 | Remote End at Prestonsburg | 2020-12-01 | Charges Continued After Dec 2022 |  |  | 106.65 | 3.75 | 3961.82 | 4072.22 | 0 | 0 | 0 | 0 | 11181.936 | 11181.936 | 0 | n.m. | 0 | n.m. | 106.65 | n.m. | 3.75 | n.m. | -7220.116 | -64.57% | -7109.716 | -63.58%
246 | 110 | A21222015 | Jackson Sta TTMP | 2020-08-01 | Charges Continued After Dec 2022 |  |  | 1584.36 | 4479.74 | 5835.86 | 11899.96 | 0 | 0 | 0 | 0 | 102775.024 | 102775.024 | 0 | n.m. | 0 | n.m. | 1584.36 | n.m. | 4479.74 | n.m. | -96939.164 | -94.32% | -90875.064 | -88.42%
247 | 110 | DMS20KK10 | KY Pre\Valid Major Storm 10 | 2020-11-01 | 2021-03-01 |  |  | 105895.45 | -93418.41 |  | 12477.04 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 105895.45 | n.m. | -93418.41 | n.m. | -0.01 | -100% | 12477.03 | 124770300%
248 | 110 | DR20K02B2 | Breaker Repl - Grayson | 2020-04-01 | Charges Continued After Dec 2022 |  |  | 39406.23 | 10220.59 | 19878.11 | 69504.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 39406.23 | n.m. | 10220.59 | n.m. | 19878.11 | n.m. | 69504.93 | n.m.
249 | 110 | A21222009 | Tygart Station | 2020-08-01 | Charges Continued After Dec 2022 |  |  | 1577.14 | 980.11 | 6047.66 | 8604.91 | 0 | 0 | 0 | 0 | 12150.132 | 12150.132 | 0 | n.m. | 0 | n.m. | 1577.14 | n.m. | 980.11 | n.m. | -6102.472 | -50.23% | -3545.222 | -29.18%
250 | 110 | A20045031 | South Pikeville Station NIP | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 8648.91 | 305.06 | 254.55 | 9208.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 8648.91 | n.m. | 305.06 | n.m. | 254.55 | n.m. | 9208.52 | n.m.
251 | 110 | DMS20KK07 | KY Pre\Valid Major Storm 07 | 2020-08-01 | 2020-12-01 |  |  | 7701.14 | 0.26 |  | 7701.4 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 7701.14 | n.m. | 0.26 | n.m. | -0.01 | -100% | 7701.39 | 77013900%
252 | 110 | A20045087 | Daisy Station NIP | 2020-11-01 | Charges Continued After Dec 2022 |  |  | 4848.31 | 2001.78 | 194.75 | 7044.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 4848.31 | n.m. | 2001.78 | n.m. | 194.75 | n.m. | 7044.84 | n.m.
253 | 110 | A20045075 | Prestonsburg NIP Track 6 | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 4767.31 | 1370.33 | 174.47 | 6312.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 4767.31 | n.m. | 1370.33 | n.m. | 174.47 | n.m. | 6312.11 | n.m.
254 | 110 | A20077019 | Collier Sta TTMP | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 652.26 | 4822.59 | 799.53 | 6274.38 | 0 | 0 | 0 | 0 | 34.318 | 34.318 | 0 | n.m. | 0 | n.m. | 652.26 | n.m. | 4822.59 | n.m. | 765.212 | 2230% | 6240.062 | 18183%
255 | 110 | A20077010 | Haddix Sta TTMP | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 652.26 | 2626 | 912.55 | 4190.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 652.26 | n.m. | 2626 | n.m. | 912.55 | n.m. | 4190.81 | n.m.
256 | 110 | A20077017 | Whitesburg Sta TTMP | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 652.26 | 1990.13 | 941.41 | 3583.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 652.26 | n.m. | 1990.13 | n.m. | 941.41 | n.m. | 3583.8 | n.m.
257 | 110 | A20077008 | Bulan Sta TTMP | 2020-12-01 | Charges Continued After Dec 2022 |  |  | 142.8 | 2109.91 | 1060.04 | 3312.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 142.8 | n.m. | 2109.91 | n.m. | 1060.04 | n.m. | 3312.75 | n.m.
258 | 110 | A20045086 | Olive Hill Station NIP | 2020-11-01 | Charges Continued After Dec 2022 |  |  | 116.84 | 1642.16 | 50 | 1809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 116.84 | n.m. | 1642.16 | n.m. | 50 | n.m. | 1809 | n.m.
259 | 110 | IT1101723 | CIS-Smart Grid Gateway-KYP D | 2020-12-01 | 2021-05-01 |  |  | 650.1 | 8.44 |  | 658.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 650.1 | n.m. | 8.44 | n.m. | 0 | n.m. | 658.54 | n.m.
260 | 110 | IT1101721 | Cust Info Trnsfrm Imp-KYP D | 2020-05-01 | 2022-02-01 |  |  | 1529.93 | 19.87 | -1549.8 | 4.7748e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1529.93 | n.m. | 19.87 | n.m. | -1549.8 | n.m. | 4.7748e-12 | n.m.
261 | 110 | DMS20KK08 | KY Pre\Valid Major Storm 08 | 2020-08-01 | 2021-02-01 |  |  | 22275.84 | -24547.15 |  | -2271.31 | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0 | n.m. | 0 | n.m. | 22275.84 | n.m. | -24547.15 | n.m. | -0.01 | -100% | -2271.32 | -22713200%
262 | 110 | DMS21KK01 | KY/ME/Ice Storm 02/10/2021 | 2021-02-01 | 2022-04-01 |  |  |  | 15733429.8 | 22900.14 | 15756329.94 | 0 | 0 | 0 | 0 | 6556.792 | 6556.792 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15733429.8 | n.m. | 16343.348 | 249.3% | 15749773.148 | 240205%
263 | 110 | TREEREL21 | ROW Capital widening & removal | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 6726648.01 | 6694133.18 | 13420781.19 | 0 | 0 | 0 | 7306292.815 | 10124469.474 | 17430762.289 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -579644.805 | -7.934% | -3430336.294 | -33.88% | -4009981.099 | -23.01%
264 | 110 | P18025018 | Kewanee Transco to KPCo | 2021-05-01 | Charges Continued After Dec 2022 |  |  |  | 1280257.47 | 2659903.15 | 3940160.62 | 0 | 0 | 0 | 0 | 946459.558 | 946459.558 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1280257.47 | n.m. | 1713443.592 | 181% | 2993701.062 | 316.3%
265 | 110 | P19092023 | Allen Station | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 342299.14 | 2677036.28 | 3019335.42 | 0 | 0 | 0 | 0 | 6494481.018 | 6494481.018 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 342299.14 | n.m. | -3817444.738 | -58.78% | -3475145.598 | -53.51%
266 | 110 | ITCW11006 | NGUCS Weddington & Leatherwood | 2021-12-01 | Charges Continued After Dec 2022 |  |  |  | 1047839.55 | 1615384.25 | 2663223.8 | 0 | 0 | 0 | 0 | 4069664 | 4069664 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1047839.55 | n.m. | -2454279.75 | -60.31% | -1406440.2 | -34.56%
267 | 110 | ITCT11004 | Ashland-Lynchburg MW Upgrade ( | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 576562.26 | 1170626.31 | 1747188.57 | 0 | 0 | 0 | 0 | 713859.464 | 713859.464 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 576562.26 | n.m. | 456766.846 | 63.99% | 1033329.106 | 144.8%
268 | 110 | A19750112 | Wurtland Sta Transformer Fail | 2021-03-01 | Charges Continued After Dec 2022 |  |  |  | 1661315.38 | 76752.87 | 1738068.25 | 0 | 0 | 0 | 0 | 0.104 | 0.104 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1661315.38 | n.m. | 76752.766 | 73800737% | 1738068.146 | 1671219371%
269 | 110 | P17083040 | Garrett Station | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 166307.49 | 463152.86 | 629460.35 | 0 | 0 | 0 | 0 | 22007.54 | 22007.54 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 166307.49 | n.m. | 441145.32 | 2005% | 607452.81 | 2760%
270 | 110 | DMS21KK02 | KY/ME/Thunderstorm 02/28/21 | 2021-03-01 | Charges Continued After Dec 2022 |  |  |  | 758649.68 |  | 758649.68 | 0 | 0 | 0 | 0 | 6556.792 | 6556.792 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 758649.68 | n.m. | -6556.792 | -100% | 752092.888 | 11470%
271 | 110 | A19750115 | Falcon TR-2 Failure | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 575802.03 | 834.05 | 576636.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 575802.03 | n.m. | 834.05 | n.m. | 576636.08 | n.m.
272 | 110 | P19305020 | Orinoco Station Land Purchase | 2021-05-01 | Charges Continued After Dec 2022 |  |  |  | 553262.24 | 7966.7 | 561228.94 | 0 | 0 | 0 | 0 | 2057888.392 | 2057888.392 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 553262.24 | n.m. | -2049921.692 | -99.61% | -1496659.452 | -72.73%
273 | 110 | P17084006 | Myra Land Purchase | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 10873.97 | 547267.13 | 558141.1 | 0 | 0 | 0 | 0 | 911830.746 | 911830.746 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10873.97 | n.m. | -364563.616 | -39.98% | -353689.646 | -38.79%
274 | 110 | P19036012 | Osborne Station T | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 138485.11 | 203531.04 | 342016.15 | 0 | 0 | 0 | 0 | 13732.082 | 13732.082 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 138485.11 | n.m. | 189798.958 | 1382% | 328284.068 | 2391%
275 | 110 | DX21K0003 | Dewey DA Coms Upgrade | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 5879.45 | 93951.68 | 99831.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5879.45 | n.m. | 93951.68 | n.m. | 99831.13 | n.m.
276 | 110 | DMS21KK03 | KY Pre\Valid Major Storm 03 | 2021-05-01 | Charges Continued After Dec 2022 |  |  |  | 86968.32 | -3467.02 | 83501.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 86968.32 | n.m. | -3467.02 | n.m. | 83501.3 | n.m.
277 | 110 | DX21K0002 | Buckhorn DA Comm. Upgrade | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 12120.31 | 69216.21 | 81336.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12120.31 | n.m. | 69216.21 | n.m. | 81336.52 | n.m.
278 | 110 | DMS21KK07 | KY Pre\Valid Major Storm 07 | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 78668.27 | 254.46 | 78922.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 78668.27 | n.m. | 254.46 | n.m. | 78922.73 | n.m.
279 | 110 | DMS21KK09 | KY Pre\Valid Major Storm 09 | 2021-12-01 | Charges Continued After Dec 2022 |  |  |  | 50618.93 | 5312.1 | 55931.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50618.93 | n.m. | 5312.1 | n.m. | 55931.03 | n.m.
280 | 110 | A20072072 | Jackson 2021 Relay Upgrade | 2021-02-01 | Charges Continued After Dec 2022 |  |  |  | 50057.87 | 170.81 | 50228.68 | 0 | 0 | 0 | 0 | 11346.092 | 11346.092 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50057.87 | n.m. | -11175.282 | -98.49% | 38882.588 | 342.7%
281 | 110 | P21043006 | Kenwood Station | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 16519.57 | 1215.23 | 17734.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16519.57 | n.m. | 1215.23 | n.m. | 17734.8 | n.m.
282 | 110 | DMS21KK05 | KY Pre\Valid Major Storm 05 | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 50095.39 |  | 50095.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50095.39 | n.m. | 0 | n.m. | 50095.39 | n.m.
283 | 110 | P19037016 | New Draffin 69kV Station | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 6470.07 | 30970.76 | 37440.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6470.07 | n.m. | 30970.76 | n.m. | 37440.83 | n.m.
284 | 110 | DMS21KK08 | KY Pre\Valid Major Storm 08 | 2021-09-01 | Charges Continued After Dec 2022 |  |  |  | 38005.75 | 69.22 | 38074.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 38005.75 | n.m. | 69.22 | n.m. | 38074.97 | n.m.
285 | 110 | A20072067 | Haddix 2021 Relay Upgrade | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 34803.26 |  | 34803.26 | 0 | 0 | 0 | 0 | 10119.042 | 10119.042 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 34803.26 | n.m. | -10119.042 | -100% | 24684.218 | 243.9%
286 | 110 | DMS21KK06 | KY Pre\Valid Major Storm 06 | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 31555.79 |  | 31555.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 31555.79 | n.m. | 0 | n.m. | 31555.79 | n.m.
287 | 110 | A21222016 | Belhaven Station TTMP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 9284.4 | 20315.18 | 29599.58 | 0 | 0 | 0 | 0 | 38817.676 | 38817.676 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9284.4 | n.m. | -18502.496 | -47.67% | -9218.096 | -23.75%
288 | 110 | EVCHRG110 | EV Chargers for GL BU 110 | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 15378.66 | 8634.03 | 24012.69 | 0 | 0 | 0 | 0 | 902215.072 | 902215.072 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15378.66 | n.m. | -893581.042 | -99.04% | -878202.382 | -97.34%
289 | 110 | A20934001 | Falcon Elim Cust DC System | 2021-03-01 | Charges Continued After Dec 2022 |  |  |  | 4104.31 | 20261.12 | 24365.43 | 0 | 0 | 0 | 0 | 314162.13 | 314162.13 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4104.31 | n.m. | -293901.01 | -93.55% | -289796.7 | -92.24%
290 | 110 | P19037003 | Poor Bottom Land Purchase | 2021-12-01 | Charges Continued After Dec 2022 |  |  |  | 425 | 10166.06 | 10591.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 425 | n.m. | 10166.06 | n.m. | 10591.06 | n.m.
291 | 110 | A21505006 | Jackson Station NIP | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 11278.14 | 355.59 | 11633.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11278.14 | n.m. | 355.59 | n.m. | 11633.73 | n.m.
292 | 110 | EDNANDA | Distribution Anda Project | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 1599.05 | 3416.07 | 5015.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1599.05 | n.m. | 3416.07 | n.m. | 5015.12 | n.m.
293 | 110 | A24112002 | Argentum Sta TTMP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 3435.39 | 1275.75 | 4711.14 | 0 | 0 | 0 | 44.568 | 10.304 | 54.872 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3390.822 | 7608% | 1265.446 | 12281% | 4656.268 | 8486%
294 | 110 | A20077007 | Soft Shell Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 1906.51 | 2522.58 | 4429.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1906.51 | n.m. | 2522.58 | n.m. | 4429.09 | n.m.
295 | 110 | A24112012 | New Camp Sta TTMP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 1655.57 | 2467.09 | 4122.66 | 0 | 0 | 0 | 0 | 10.304 | 10.304 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1655.57 | n.m. | 2456.786 | 23843% | 4112.356 | 39910%
296 | 110 | A20077018 | Mayking Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 1835.7 | 1837.44 | 3673.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1835.7 | n.m. | 1837.44 | n.m. | 3673.14 | n.m.
297 | 110 | A20077022 | South Pikeville Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 1056.69 | 2218.55 | 3275.24 | 0 | 0 | 0 | 0 | 3.436 | 3.436 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1056.69 | n.m. | 2215.114 | 64468% | 3271.804 | 95221%
298 | 110 | A20077023 | Elwood Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 1838.97 | 1328.12 | 3167.09 | 0 | 0 | 0 | 0 | 3.436 | 3.436 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1838.97 | n.m. | 1324.684 | 38553% | 3163.654 | 92074%
299 | 110 | A21505009 | Coalton NIP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 3037.3 | 95.76 | 3133.06 | 0 | 0 | 0 | 50.874 | 0 | 50.874 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2986.426 | 5870% | 95.76 | n.m. | 3082.186 | 6058%
300 | 110 | A20077013 | Engle Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 2518.05 | 399.51 | 2917.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2518.05 | n.m. | 399.51 | n.m. | 2917.56 | n.m.
301 | 110 | A20077011 | Jackson Sta TTMP | 2021-06-01 | Charges Continued After Dec 2022 |  |  |  | 1282.83 | 1489.3 | 2772.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1282.83 | n.m. | 1489.3 | n.m. | 2772.13 | n.m.
302 | 110 | A24112010 | Lovely Sta TTMP | 2021-06-01 | Charges Continued After Dec 2022 |  |  |  | 2227.02 | 173.11 | 2400.13 | 0 | 0 | 0 | 0 | 10.304 | 10.304 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2227.02 | n.m. | 162.806 | 1580% | 2389.826 | 23193%
303 | 110 | A21505010 | McKinney Station NIP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 898.14 | 28.3 | 926.44 | 0 | 0 | 0 | 68.275 | 0 | 68.275 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 829.865 | 1215% | 28.3 | n.m. | 858.165 | 1257%
304 | 110 | DMS21KK04 | KY Pre\Valid Major Storm 04 | 2021-06-01 | 2022-02-01 |  |  |  | 5448.12 | -5448.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5448.12 | n.m. | -5448.12 | n.m. | 0 | n.m.
305 | 110 | 110KYLSBO | Dist KY Lease BO | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 22121355.79 | 22121355.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22121355.79 | n.m. | 22121355.79 | n.m.
306 | 110 | DMS22KK14 | KY/ME/Flood 14 07/28/22 | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 6514673.21 | 6514673.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6514673.21 | n.m. | 6514673.21 | n.m.
307 | 110 | TP1708310 | T Funded D Garret Area Imp | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 1866348.21 | 1866348.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1866348.21 | n.m. | 1866348.21 | n.m.
308 | 110 | TP1802510 | KEWANEE DLINE WORK | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 783365 | 783365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 783365 | n.m. | 783365 | n.m.
309 | 110 | TP1403006 | T Funded D Work | 2022-10-01 | Charges Continued After Dec 2022 |  |  |  |  | 566402.78 | 566402.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 566402.78 | n.m. | 566402.78 | n.m.
310 | 110 | DMS22KK09 | KY/ME/Thunderstorm 09 06/17/22 | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 1609424.3 | 1609424.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1609424.3 | n.m. | 1609424.3 | n.m.
311 | 110 | KEPDS2201 | KPCo Storm - Distribution | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 299975.35 | 299975.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 299975.35 | n.m. | 299975.35 | n.m.
312 | 110 | A21750003 | Beefhide TR-1 Failure | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 398444.78 | 398444.78 | 0 | 0 | 0 | 82.187 | 0 | 82.187 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -82.187 | -100% | 398444.78 | n.m. | 398362.593 | 484703%
313 | 110 | DMS22KK15 | KY Pre/Valid Major Storm 15 | 2022-12-01 | Charges Continued After Dec 2022 |  |  |  |  | 121221.23 | 121221.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 121221.23 | n.m. | 121221.23 | n.m.
314 | 110 | DMS22KK02 | KY Pre\Valid Major Storm 02 | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 228650.82 | 228650.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 228650.82 | n.m. | 228650.82 | n.m.
315 | 110 | DMS22KK10 | KY Pre-valid Storm Event | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 215853.04 | 215853.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 215853.04 | n.m. | 215853.04 | n.m.
316 | 110 | DMS22KK03 | KY Pre\Valid Major Storm 03 | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 151068.54 | 151068.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 151068.54 | n.m. | 151068.54 | n.m.
317 | 110 | DMS22KK01 | KY Pre\Valid Major Storm 01 | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 138981.25 | 138981.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 138981.25 | n.m. | 138981.25 | n.m.
318 | 110 | DMS22KK11 | KY Pre/Valid Major Storm 11 | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 130457.69 | 130457.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 130457.69 | n.m. | 130457.69 | n.m.
319 | 110 | DMS22KK08 | KY Pre/Valid Major Storm 08 | 2022-05-01 | Charges Continued After Dec 2022 |  |  |  |  | 114295.94 | 114295.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 114295.94 | n.m. | 114295.94 | n.m.
320 | 110 | P22005001 | 47th Street Station | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 51455.54 | 51455.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 51455.54 | n.m. | 51455.54 | n.m.
321 | 110 | DMS22KK13 | KY Pre/Valid Major Storm 13 | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 94325.18 | 94325.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 94325.18 | n.m. | 94325.18 | n.m.
322 | 110 | DMS22KK05 | KY Pre\Valid Major Storm 05 | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 61676.23 | 61676.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 61676.23 | n.m. | 61676.23 | n.m.
323 | 110 | DMS22KK04 | KY Pre\Valid Major Storm 04 | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 47504.15 | 47504.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 47504.15 | n.m. | 47504.15 | n.m.
324 | 110 | DMS22KK12 | KY Pre/Valid Major Storm 12 | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 45389.69 | 45389.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45389.69 | n.m. | 45389.69 | n.m.
325 | 110 | TP1822105 | Fleming T-Funded D | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 40495.82 | 40495.82 | 0 | 0 | 0 | 0 | 79165.066 | 79165.066 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -38669.246 | -48.85% | -38669.246 | -48.85%
326 | 110 | P22012002 | Peter Creek Station Work | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | 35262.46 | 35262.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35262.46 | n.m. | 35262.46 | n.m.
327 | 110 | DMS22KK06 | KY Pre\Valid Major Storm 06 | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 36653.23 | 36653.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 36653.23 | n.m. | 36653.23 | n.m.
328 | 110 | DMS22KK07 | KY Pre\Valid Major Storm 07 | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 30155.89 | 30155.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30155.89 | n.m. | 30155.89 | n.m.
329 | 110 | P21720003 | Coalton Remote End | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 6440.61 | 6440.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6440.61 | n.m. | 6440.61 | n.m.
330 | 110 | A21050053 | Howard Collins GE/SEL Relay Up | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 18518.86 | 18518.86 | 0 | 0 | 0 | 0 | 42908.372 | 42908.372 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -24389.512 | -56.84% | -24389.512 | -56.84%
331 | 110 | A21050054 | Tenth St GE/SEL Relay | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 11358.76 | 11358.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11358.76 | n.m. | 11358.76 | n.m.
332 | 110 | TP1910410 | KPCo D FAA Light Work | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 17114.5 | 17114.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17114.5 | n.m. | 17114.5 | n.m.
333 | 110 | P19037017 | New Draffin Land Purchase | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 10372.44 | 10372.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10372.44 | n.m. | 10372.44 | n.m.
334 | 110 | P22012001 | Coleman Station Work | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | 11629.37 | 11629.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11629.37 | n.m. | 11629.37 | n.m.
335 | 110 | TP1903604 | T Funded D | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 10568.45 | 10568.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10568.45 | n.m. | 10568.45 | n.m.
336 | 110 | P17084055 | Myra Station | 2022-10-01 | Charges Continued After Dec 2022 |  |  |  |  | 7135.52 | 7135.52 | 0 | 0 | 0 | 0 | 67161.554 | 67161.554 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -60026.034 | -89.38% | -60026.034 | -89.38%
337 | 110 | TP1909210 | Allen Distribution Feeder Work | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 6824.09 | 6824.09 | 0 | 0 | 0 | 0 | 46552.366 | 46552.366 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -39728.276 | -85.34% | -39728.276 | -85.34%
338 | 110 | P21753003 | Stanville Remote End Work | 2022-05-01 | Charges Continued After Dec 2022 |  |  |  |  | 3682.3 | 3682.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3682.3 | n.m. | 3682.3 | n.m.
339 | 110 | A25101001 | 47th St Sta TTMP | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 2020.52 | 2020.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2020.52 | n.m. | 2020.52 | n.m.
340 | 110 | A25101003 | Argentum Sta TTMP | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 1161.73 | 1161.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1161.73 | n.m. | 1161.73 | n.m.
341 | 110 | A25101006 | Second Fork Sta TTMP | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 1089.02 | 1089.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1089.02 | n.m. | 1089.02 | n.m.
342 | 110 | A25101002 | Ashland (25th St) Sta TTMP | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 1085.96 | 1085.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1085.96 | n.m. | 1085.96 | n.m.
343 | 110 | A25101005 | Tygart Sta TTMP | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 389.36 | 389.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 389.36 | n.m. | 389.36 | n.m.
344 | 110 | Other Budgeted Projects |  | Other | Other | 0 | 0 | 0 | 0 | 0 | 0 | 28519401.393 | 27915035.267 | 21003299.162 | 26460664.528 | 32091888.918 | 135990289.268 | -28519401.393 | -100% | -27915035.267 | -100% | -21003299.162 | -100% | -26460664.528 | -100% | -32091888.918 | -100% | -135990289.268 | -100%
345 | 110 Total |  |  |  |  | 64555463.901 | 88614408.034 | 76107842.41 | 88686021.68 | 107164361.46 | 425128097.485 | 65228356.309 | 85935621.527 | 81798334.916 | 80874350.254 | 148629554.586 | 462466217.592 | -672892.408 | -1.032% | 2678786.507 | 3.117% | -5690492.506 | -6.957% | 7811671.426 | 9.659% | -41465193.126 | -27.9% | -37338120.107 | -8.074%
346 | 117 | 000005237 | KyPCo-G Capital Software Dev | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 3951851.2 | 2434708.91 | 3219101.12 | 4103342.66 | 2998343.87 | 16707347.76 | 7849.761 | 0 | 0 | 444423.467 | 446540.92 | 898814.148 | 3944001.439 | 50244% | 2434708.91 | n.m. | 3219101.12 | n.m. | 3658919.193 | 823.3% | 2551802.95 | 571.5% | 15808533.612 | 1759%
347 | 117 | 000022392 | ML LANDFILL EXPANSION - PH 3 | 9/1/2016 | 2022-05-01 | 5001223.22 | 4075206.479 | 317355.65 | 275014.77 | 11.32 | 9668811.439 | 6548798.546 | 6639060.198 | 691703.716 | 279161.894 | 0.031372 | 14158724.3854 | -1547575.326 | -23.63% | -2563853.719 | -38.62% | -374348.066 | -54.12% | -4147.124 | -1.486% | 11.2886 | 35983% | -4489912.9464 | -31.71%
348 | 117 | 000021737 | BS Repurpose BAP | 1/1/2018 | 2022-08-01 | 806782.14 | 5604089.6 | 1353166.07 | 10170.2 | -1982.59 | 7772225.42 | 3204614.575 | 63986.64 | 0 | 0 | 0 | 3268601.215 | -2397832.435 | -74.82% | 5540102.96 | 8658% | 1353166.07 | n.m. | 10170.2 | n.m. | -1982.59 | n.m. | 4503624.205 | 137.8%
349 | 117 | BSPPB0013 | Other Costs PPB<$100k | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 822841.17 | 1025412.4 | 824459.16 | 562958.27 | 601797.47 | 3837468.47 | 6152.041 | 41464.751 | 368578.644 | 37574.693 | 174741.5 | 628511.629 | 816689.129 | 13275% | 983947.649 | 2373% | 455880.516 | 123.7% | 525383.577 | 1398% | 427055.97 | 244.4% | 3208956.841 | 510.6%
350 | 117 | IT1171421 | Maximo Imp - KYP - G | 3/1/2016 | 2020-08-01 | 1378551.17 | 1452005.5 | 22688.92 | 0 | 0 | 2853245.59 | 0 | 0 | 3458.04 | 0 | 0 | 3458.04 | 1378551.17 | n.m. | 1452005.5 | n.m. | 19230.88 | 556.1% | 0 | n.m. | 0 | n.m. | 2849787.55 | 82410%
351 | 117 | IT117BILL | Corp Prgrm Billing - KYPCO Gen | 7/1/2017 | 2020-12-01 | 457878.61 | 1193125.32 | 86361.3 | 0 | 0 | 1737365.23 | 0 | 0 | 0 | 0 | 0 | 0 | 457878.61 | n.m. | 1193125.32 | n.m. | 86361.3 | n.m. | 0 | n.m. | 0 | n.m. | 1737365.23 | n.m.
352 | 117 | BS0000038 | Big Sandy U1 HP IPSFLP Overha | 1/1/2018 | 11/1/2018 | 3563720.16 |  | 0 | 0 | 0 | 3563720.16 | 2117803.537 | 1884.65 | 0 | 0 | 0 | 2119688.187 | 1445916.623 | 68.27% | -1884.65 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1444031.973 | 68.12%
353 | 117 | KMLFALFCI | ML U0 New Landfill | Charges Began Prior to Jan 2015 | 4/1/2018 | 5967.71 |  | 0 | 0 | 0 | 5967.71 | 0 | 0 | 0 | 0 | 0 | 0 | 5967.71 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5967.71 | n.m.
354 | 117 | ML119SC02 | ML U1 ECON PARTITION WALL RPL | 8/1/2018 | 2020-01-01 | 115498.38 | 2854954.9 | 4.68 | 0 | 0 | 2970457.96 | 0 | 1328078.491 | 0 | 0 | 0 | 1328078.491 | 115498.38 | n.m. | 1526876.409 | 115% | 4.68 | n.m. | 0 | n.m. | 0 | n.m. | 1642379.469 | 123.7%
355 | 117 | 000022308 | ML U1 ESP Project | 11/1/2018 | 2020-01-01 | 110827.14 | 2422707.58 | 302.92 | 0 | 0 | 2533837.64 | 0 | 3810922.273 | 0 | 0 | 0 | 3810922.273 | 110827.14 | n.m. | -1388214.693 | -36.43% | 302.92 | n.m. | 0 | n.m. | 0 | n.m. | -1277084.633 | -33.51%
356 | 117 | ML1EC1302 | ML1 E PHASE 1 GSU TRANSFORMER | 5/1/2018 | 2020-06-01 | 1016323.31 | 982086.07 | 11191.15 | 0 | 0 | 2009600.53 | -1153.63 | 1926700.328 | 107.008 | 0 | 0 | 1925653.706 | 1017476.94 | -88198% | -944614.258 | -49.03% | 11084.142 | 10358% | 0 | n.m. | 0 | n.m. | 83946.824 | 4.359%
357 | 117 | NRCCPKPCO | NERC CIP KYPCO | 9/1/2016 | 2022-07-01 | 1310014.19 | 31983.25 | 932.5 | 228131.03 | 9612.57 | 1580673.54 | 1364112.891 | 83130.097 | 184408.107 | 143938.42 | 0 | 1775589.515 | -54098.701 | -3.966% | -51146.847 | -61.53% | -183475.607 | -99.49% | 84192.61 | 58.49% | 9612.57 | n.m. | -194915.975 | -10.98%
358 | 117 | ML1VC1601 | ML1 V CATALYST REPLACEMENT 3 L | 12/1/2016 | 2021-04-01 | 486935.82 | 104662.13 | 5432.69 | -1729.22 | 0 | 595301.42 | 1238690.003 | 0 | 0 | 0 | 0 | 1238690.003 | -751754.183 | -60.69% | 104662.13 | n.m. | 5432.69 | n.m. | -1729.22 | n.m. | 0 | n.m. | -643388.583 | -51.94%
359 | 117 | ML2VC1601 | ML2 V CATALYST REPLACEMENT 3 L | 7/1/2017 | 2020-10-01 | 495998.88 | 2173.81 | 49247.01 | 0 | 0 | 547419.7 | 1182821.549 | 0 | 0 | 0 | 0 | 1182821.549 | -686822.669 | -58.07% | 2173.81 | n.m. | 49247.01 | n.m. | 0 | n.m. | 0 | n.m. | -635401.849 | -53.72%
360 | 117 | ML1E18C05 | MLU1 LP TURBINE ROTOR REPAIR | 9/1/2017 | 11/1/2019 | 562669.49 | 219858.11 | 0 | 0 | 0 | 782527.6 | 520848.41 | 0 | 0 | 0 | 0 | 520848.41 | 41821.08 | 8.029% | 219858.11 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 261679.19 | 50.24%
361 | 117 | ML1SC1810 | ML1 S BREECHING DUCT RPL | 12/1/2018 | 2020-01-01 | 6215.14 | 1050781.52 | 4.68 | 0 | 0 | 1057001.34 | 0 | 1074746.662 | 0 | 0 | 0 | 1074746.662 | 6215.14 | n.m. | -23965.142 | -2.23% | 4.68 | n.m. | 0 | n.m. | 0 | n.m. | -17745.322 | -1.651%
362 | 117 | BSPPBOUT1 | Unit 1PPB Outage<100k | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 621388.14 | -2967.15 | 766578.093 | 4596.59 | 127870.4 | 1517466.073 | 949600.069 | 690285.217 | 910693.182 | 513434.007 | 388070.158 | 3452082.633 | -328211.929 | -34.56% | -693252.367 | -100.4% | -144115.089 | -15.82% | -508837.417 | -99.1% | -260199.758 | -67.05% | -1934616.56 | -56.04%
363 | 117 | ML016VP11 | ML - 2016 FGD NON OUTAGE PPB | 11/1/2016 | 8/1/2019 | 36063.64 | 9119.91 | 0 | 0 | 0 | 45183.55 | 0 | 0 | 0 | 0 | 0 | 0 | 36063.64 | n.m. | 9119.91 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45183.55 | n.m.
364 | 117 | BSPPB0002 | Boiler & Auxiliaries PPB<100k | Charges Began Prior to Jan 2015 | 2021-08-01 | 232591.6 | 110441.28 | -46581.47 | 15211.64 | 0 | 311663.05 | 167583.019 | 181633.254 | 0 | 167570.217 | 143793.024 | 660579.514 | 65008.581 | 38.79% | -71191.974 | -39.2% | -46581.47 | n.m. | -152358.577 | -90.92% | -143793.024 | -100% | -348916.464 | -52.82%
365 | 117 | ARCFLA117 | Arc Flash Protection Swi KYPCo | Charges Began Prior to Jan 2015 | 8/1/2019 | 57261.68 | 56433.93 | 0 | 0 | 0 | 113695.61 | 0 | 0 | 0 | 0 | 0 | 0 | 57261.68 | n.m. | 56433.93 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 113695.61 | n.m.
366 | 117 | BS2DCOM20 | Big Sandy U1 CEMS Building | 11/1/2017 | 1/1/2019 | 643384.91 | 62.82 | 0 | 0 | 0 | 643447.73 | 234258.77 | 0 | 0 | 0 | 0 | 234258.77 | 409126.14 | 174.6% | 62.82 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 409188.96 | 174.7%
367 | 117 | ML018VP01 | ML - NON OUTAGE PPB FGD | 1/1/2018 | 2020-03-01 | 590253.77 | 69582.83 | -14.32 | 0 | 0 | 659822.28 | 0 | 0 | 0 | 0 | 0 | 0 | 590253.77 | n.m. | 69582.83 | n.m. | -14.32 | n.m. | 0 | n.m. | 0 | n.m. | 659822.28 | n.m.
368 | 117 | MLP17EP04 | MLP E LIGHTING PANEL REPLACE | 10/1/2016 | 1/1/2019 | 20621.47 | 27.24 | 0 | 0 | 0 | 20648.71 | 108684.395 | 7.053 | 0 | 0 | 0 | 108691.448 | -88062.925 | -81.03% | 20.187 | 286.2% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -88042.738 | -81%
369 | 117 | ML018MP05 | ML 2018 PLANT CAPITAL PAVING | 8/1/2018 | 3/1/2019 | 606985.67 | -519.08 | 0 | 0 | 0 | 606466.59 | 0 | 0 | 0 | 0 | 0 | 0 | 606985.67 | n.m. | -519.08 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 606466.59 | n.m.
370 | 117 | ML018NP01 | ML CAPITAL TOOLS | 3/1/2018 | 10/1/2019 | 497621.6 | 53554.48 | 0 | 0 | 0 | 551176.08 | 0 | 167679.091 | 154617.382 | 55261.389 | 89062.4776 | 466620.3396 | 497621.6 | n.m. | -114124.611 | -68.06% | -154617.382 | -100% | -55261.389 | -100% | -89062.4776 | -100% | 84555.7404 | 18.12%
371 | 117 | ML1E18C02 | ML1 2nd RH TURBINE REPLACEMENT | 7/1/2017 | 4/1/2018 | 3901.58 |  | 0 | 0 | 0 | 3901.58 | 680.58 | 0 | 0 | 0 | 0 | 680.58 | 3221 | 473.3% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3221 | 473.3%
372 | 117 | BSPPB0016 | Turb & Support Sys PPB<100k | Charges Began Prior to Jan 2015 | 2018-07-01 | 113389.93 |  | 0 | 0 | 0 | 113389.93 | 0 | 0 | 0 | 0 | 0 | 0 | 113389.93 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 113389.93 | n.m.
373 | 117 | ML017MP01 | ML 2017 PLANT CAPITAL PAVING | 10/1/2017 | 5/1/2018 | 37737.09 |  | 0 | 0 | 0 | 37737.09 | 96.56 | 0 | 0 | 0 | 0 | 96.56 | 37640.53 | 38981% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 37640.53 | 38981%
374 | 117 | ML0M18C01 | ML COAL YARD PLC REPLACEMENT | 9/1/2017 | 8/1/2018 | 230688.63 |  | 0 | 0 | 0 | 230688.63 | 250943.379 | 0 | 0 | 0 | 0 | 250943.379 | -20254.749 | -8.071% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -20254.749 | -8.071%
375 | 117 | BSPPBS347 | REP U1 BFPT Rotor with Spare | 11/1/2018 | 3/1/2019 | 297879.73 | 88890.82 | 0 | 0 | 0 | 386770.55 | 0 | 0 | 0 | 0 | 0 | 0 | 297879.73 | n.m. | 88890.82 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 386770.55 | n.m.
376 | 117 | ML018VP04 | ML ID FAN DRIVE END HUB PURCHA | 7/1/2018 | 8/1/2019 | 390173.51 | -29288.6 | 0 | 0 | 0 | 360884.91 | 0 | 0 | 0 | 0 | 0 | 0 | 390173.51 | n.m. | -29288.6 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 360884.91 | n.m.
377 | 117 | ML1E18C03 | MLU1 LPB TURBINE REPLACEMENT | 7/1/2017 | 4/1/2018 | 2529.58 |  | 0 | 0 | 0 | 2529.58 | 308.23 | 0 | 0 | 0 | 0 | 308.23 | 2221.35 | 720.7% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2221.35 | 720.7%
378 | 117 | ML016NP06 | MLP CAPITAL TOOLS | 1/1/2016 | 3/1/2019 | 2056.83 | -9.25 | 0 | 0 | 0 | 2047.58 | 0 | 0 | 0 | 0 | 0 | 0 | 2056.83 | n.m. | -9.25 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2047.58 | n.m.
379 | 117 | MLP17SP01 | INSTALL R3/R4 FIRE HEADER CTIE | 5/1/2017 | 8/1/2019 | 70358.15 | 8635.15 | 0 | 0 | 0 | 78993.3 | 0 | 0 | 0 | 0 | 0 | 0 | 70358.15 | n.m. | 8635.15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 78993.3 | n.m.
380 | 117 | ML018MP03 | ML MH CONVEYOR BELT REPLACE | 1/1/2018 | 2020-02-01 | 321529.07 | 4107.27 | -137.53 | 0 | 0 | 325498.81 | 0 | 0 | 0 | 0 | 0 | 0 | 321529.07 | n.m. | 4107.27 | n.m. | -137.53 | n.m. | 0 | n.m. | 0 | n.m. | 325498.81 | n.m.
381 | 117 | ML017NP01 | Capital Tools | 1/1/2017 | 11/1/2019 | 47179.63 | 365.07 | 0 | 0 | 0 | 47544.7 | 164970.598 | 92.956 | 0 | 0 | 0 | 165063.554 | -117790.968 | -71.4% | 272.114 | 292.7% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -117518.854 | -71.2%
382 | 117 | BSPPBS341 | Replace Bushings on 102 Transf | 4/1/2018 | 3/1/2019 | 290044.94 | 5852.52 | 0 | 0 | 0 | 295897.46 | 0 | 0 | 0 | 0 | 0 | 0 | 290044.94 | n.m. | 5852.52 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 295897.46 | n.m.
383 | 117 | ML2E18C05 | ML Unit 2 High Energy Piping | 12/1/2017 | 9/1/2018 | 239551.2 |  | 0 | 0 | 0 | 239551.2 | 361099.519 | 0 | 0 | 0 | 0 | 361099.519 | -121548.319 | -33.66% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -121548.319 | -33.66%
384 | 117 | MLP18EP04 | ML E LIGHTING PANEL REPLACE | 2/1/2018 | 7/1/2019 | 283802.77 | -111.56 | 0 | 0 | 0 | 283691.21 | 0 | 114120.294 | 79044.086 | 66326.674 | 51310.7842 | 310801.8382 | 283802.77 | n.m. | -114231.854 | -100.1% | -79044.086 | -100% | -66326.674 | -100% | -51310.7842 | -100% | -27110.6282 | -8.723%
385 | 117 | ML019SP01 | ML PULVERIZER REBUILD CAP (#xx | 5/1/2019 | 2020-06-01 |  | 262170.25 | 12074.84 | 0 | 0 | 274245.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 262170.25 | n.m. | 12074.84 | n.m. | 0 | n.m. | 0 | n.m. | 274245.09 | n.m.
386 | 117 | ML218EP05 | ML U2 CT SHELL MONITORING SYST | 3/1/2018 | 7/1/2019 | 261469.98 | -58.67 | 0 | 0 | 0 | 261411.31 | 0 | 0 | 0 | 0 | 0 | 0 | 261469.98 | n.m. | -58.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 261411.31 | n.m.
387 | 117 | ML018NP12 | ML SERVICE BUILDING ROOF | 9/1/2018 | 2020-06-01 | 244165.04 | 15120.12 | 26983.52 | 0 | 0 | 286268.68 | 0 | 0 | 0 | 0 | 0 | 0 | 244165.04 | n.m. | 15120.12 | n.m. | 26983.52 | n.m. | 0 | n.m. | 0 | n.m. | 286268.68 | n.m.
388 | 117 | ML120SP01 | ML U1 Lime Inj Rig and Pig Buy | 12/1/2019 | 2020-07-01 |  | 258792.11 | 1164.88 | 0 | 0 | 259956.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 258792.11 | n.m. | 1164.88 | n.m. | 0 | n.m. | 0 | n.m. | 259956.99 | n.m.
389 | 117 | ML118SP22 | ML U1 BOILER CAMERA UPGRADE | 11/1/2018 | 2021-03-01 | 185551.79 | 67516 | 8224.61 | -1061.27 | 0 | 260231.13 | 0 | 0 | 0 | 0 | 0 | 0 | 185551.79 | n.m. | 67516 | n.m. | 8224.61 | n.m. | -1061.27 | n.m. | 0 | n.m. | 260231.13 | n.m.
390 | 117 | ML015VP01 | MLU0 CCR COMPLIANCE | 6/1/2015 | 2020-07-01 | 36797.72 | 12230.74 | 6170.36 | 0 | 0 | 55198.82 | 0 | 0 | 0 | 0 | 0 | 0 | 36797.72 | n.m. | 12230.74 | n.m. | 6170.36 | n.m. | 0 | n.m. | 0 | n.m. | 55198.82 | n.m.
391 | 117 | ML219SP06 | MLU2 21 PULVERIZER REBUILD | 10/1/2019 | 2020-07-01 |  | 230994.26 | 913.46 | 0 | 0 | 231907.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 230994.26 | n.m. | 913.46 | n.m. | 0 | n.m. | 0 | n.m. | 231907.72 | n.m.
392 | 117 | ML0E17C02 | ML REPLACE AMMONIA TANK | 9/1/2017 | 3/1/2018 | 30413.77 |  | 0 | 0 | 0 | 30413.77 | 0 | 0 | 0 | 0 | 0 | 0 | 30413.77 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30413.77 | n.m.
393 | 117 | ML018MP06 | ML HIGH SULFUR STAMLER REBUILD | 9/1/2018 | 2020-06-01 | 144645.08 | 68880.38 | 4294.37 | 0 | 0 | 217819.83 | 0 | 0 | 0 | 0 | 0 | 0 | 144645.08 | n.m. | 68880.38 | n.m. | 4294.37 | n.m. | 0 | n.m. | 0 | n.m. | 217819.83 | n.m.
394 | 117 | ML017VP04 | ML-NON OUTAGE PPB FGD | 3/1/2017 | 2020-06-01 | 12751.9 | 77.33 | 1.56 | 0 | 0 | 12830.79 | 0 | 0 | 0 | 0 | 0 | 0 | 12751.9 | n.m. | 77.33 | n.m. | 1.56 | n.m. | 0 | n.m. | 0 | n.m. | 12830.79 | n.m.
395 | 117 | MLP19EP04 | ML E LIGHTING PANEL REPLACE | 2/1/2019 | 2021-01-01 |  | 209318.24 | 97069.93 | 173.59 | 0 | 306561.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 209318.24 | n.m. | 97069.93 | n.m. | 173.59 | n.m. | 0 | n.m. | 306561.76 | n.m.
396 | 117 | BSPPBS348 | Replace 4KV Brkr Racking Mech | 8/1/2019 | 2020-02-01 |  | 208359.69 | 421.81 | 0 | 0 | 208781.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 208359.69 | n.m. | 421.81 | n.m. | 0 | n.m. | 0 | n.m. | 208781.5 | n.m.
397 | 117 | ML219VP06 | ML 21 ID FAN DE HUB REPLACE | 10/1/2019 | 2020-03-01 |  | 201875.99 | 13800.75 | 0 | 0 | 215676.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 201875.99 | n.m. | 13800.75 | n.m. | 0 | n.m. | 0 | n.m. | 215676.74 | n.m.
398 | 117 | ML017MP03 | ML MH LANDFILL FACILITY | 7/1/2017 | 3/1/2018 | 28402.68 |  | 0 | 0 | 0 | 28402.68 | 0 | 0 | 0 | 0 | 0 | 0 | 28402.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28402.68 | n.m.
399 | 117 | MLP19MP03 | ML MH R4 COAL CHUTE REPLACEMT | 3/1/2019 | 2020-01-01 |  | 199325.51 | -3013.11 | 0 | 0 | 196312.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 199325.51 | n.m. | -3013.11 | n.m. | 0 | n.m. | 0 | n.m. | 196312.4 | n.m.
400 | 117 | MLP19EP03 | ML E PUMP REPLACEMENT DR 10 HP | 2/1/2019 | 2021-12-01 |  | 194707.38 | 119224.25 | 10506.91 | 0 | 324438.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 194707.38 | n.m. | 119224.25 | n.m. | 10506.91 | n.m. | 0 | n.m. | 324438.54 | n.m.
401 | 117 | ML018SP01 | PULVERIZER REBUILD CAPITAL(#xx | 3/1/2018 | 8/1/2018 | 190972.11 |  | 0 | 0 | 0 | 190972.11 | 0 | 188086.783 | 230463.715 | 0 | 253348.7926 | 671899.2906 | 190972.11 | n.m. | -188086.783 | -100% | -230463.715 | -100% | 0 | n.m. | -253348.7926 | -100% | -480927.1806 | -71.58%
402 | 117 | ML019VP01 | ML - NON OUTAGE PPB FGD | 1/1/2019 | 2021-07-01 |  | 189928.63 | 20917.8 | -481.65 | 0 | 210364.78 | 0 | 219507.56 | 43.066 | 0 | 0 | 219550.626 | 0 | n.m. | -29578.93 | -13.48% | 20874.734 | 48471% | -481.65 | n.m. | 0 | n.m. | -9185.846 | -4.184%
403 | 117 | ML217SP08 | ML U2 PRECIP ROOF BAY BOX VVV | 12/1/2017 | 9/1/2018 | 181716.27 |  | 0 | 0 | 0 | 181716.27 | 228940.317 | 0 | 0 | 0 | 0 | 228940.317 | -47224.047 | -20.63% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -47224.047 | -20.63%
404 | 117 | ML117SP09 | ML S PULVERIZER GEARBOX | 7/1/2017 | 1/1/2018 | -2517 |  | 0 | 0 | 0 | -2517 | 352068.549 | 0 | 0 | 0 | 0 | 352068.549 | -354585.549 | -100.7% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -354585.549 | -100.7%
405 | 117 | MLP18EP02 | ML E MOTOR REWIND / REPL +10HP | 7/1/2018 | 2020-06-01 | 123699.65 | 59760.74 | 3192.85 | 0 | 0 | 186653.24 | 0 | 36584.593 | 46382.698 | 33154.313 | 26718.4665 | 142840.0705 | 123699.65 | n.m. | 23176.147 | 63.35% | -43189.848 | -93.12% | -33154.313 | -100% | -26718.4665 | -100% | 43813.1695 | 30.67%
406 | 117 | ML118EP07 | ML REPAIR U1 2nd RH ROTOR @CMS | 10/1/2017 | 3/1/2018 | 25894.11 |  | 902.42 | 0 | 0 | 26796.53 | 158742.579 | 0 | 0 | 0 | 0 | 158742.579 | -132848.469 | -83.69% | 0 | n.m. | 902.42 | n.m. | 0 | n.m. | 0 | n.m. | -131946.049 | -83.12%
407 | 117 | ML219SP05 | MLU2 PRECIP ROOF BAY BOX4ROW7 | 10/1/2019 | 2020-07-01 |  | 178925.45 | -29526.15 | 0 | 0 | 149399.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 178925.45 | n.m. | -29526.15 | n.m. | 0 | n.m. | 0 | n.m. | 149399.3 | n.m.
408 | 117 | ML218SP10 | ML U2 PRECIP EJ REPLACEMENT | 1/1/2018 | 2020-01-01 | 171607.89 | 1125.42 | -1019.41 | 0 | 0 | 171713.9 | 240963.106 | 134.281 | 0 | 0 | 0 | 241097.387 | -69355.216 | -28.78% | 991.139 | 738.1% | -1019.41 | n.m. | 0 | n.m. | 0 | n.m. | -69383.487 | -28.78%
409 | 117 | MLP19MP02 | MLP MH CONVEYOR BELT REPLACE | 1/1/2019 | 2020-10-01 |  | 172014.78 | 18953.12 | 0 | 0 | 190967.9 | 0 | 213409.83 | 41.852 | 0 | 0 | 213451.682 | 0 | n.m. | -41395.05 | -19.4% | 18911.268 | 45186% | 0 | n.m. | 0 | n.m. | -22483.782 | -10.53%
410 | 117 | 000020310 | ML U0 ELG Compliance | 12/1/2019 | 2022-09-01 |  | 170487.51 | 1547924.793 | 3748459.12 | -5466871.423 | -3.3528e-08 | 2423.2 | 338277.705 | 737479.442 | 9382989.739 | 0 | 10461170.086 | -2423.2 | -100% | -167790.195 | -49.6% | 810445.351 | 109.9% | -5634530.619 | -60.05% | -5466871.423 | n.m. | -10461170.086 | -100%
411 | 117 | MLP17EP03 | MLP E PUMP REPLACEMENT DR 10 H | 1/1/2017 | 4/1/2018 | 2332.35 |  | 0 | 0 | 0 | 2332.35 | 181224.389 | 56.652 | 0 | 0 | 0 | 181281.041 | -178892.039 | -98.71% | -56.652 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -178948.691 | -98.71%
412 | 117 | ML119EP04 | ML UNIT 1 HIGH ENERGY PIPING | 1/1/2019 | 11/1/2019 |  | 154923.07 | 0 | 0 | 0 | 154923.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 154923.07 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 154923.07 | n.m.
413 | 117 | ML018MP01 | REPLACE COALCONVEYOR SAMPLERS | 9/1/2017 | 11/1/2018 | 112106.85 |  | 0 | 0 | 0 | 112106.85 | 147165.015 | 42.802 | 0 | 0 | 0 | 147207.817 | -35058.165 | -23.82% | -42.802 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -35100.967 | -23.84%
414 | 117 | MLP18EP07 | ML #12 CIRCULATOR PUMP ELEMENT | 7/1/2018 | 8/1/2019 | 129151.55 | 21117.15 | 0 | 0 | 0 | 150268.7 | 0 | 0 | 0 | 0 | 0 | 0 | 129151.55 | n.m. | 21117.15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 150268.7 | n.m.
415 | 117 | ML118VP07 | ML #12 ID FAN HUBS PPB PORTION | 4/1/2018 | 6/1/2018 | 149614.49 |  | 0 | 0 | 0 | 149614.49 | 0 | 0 | 0 | 0 | 0 | 0 | 149614.49 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 149614.49 | n.m.
416 | 117 | ML217SP09 | ML U2 PRECIP ROOF BAY BOX WWW | 12/1/2017 | 9/1/2018 | 141853.25 |  | 0 | 0 | 0 | 141853.25 | 228940.317 | 0 | 0 | 0 | 0 | 228940.317 | -87087.067 | -38.04% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -87087.067 | -38.04%
417 | 117 | BSPPBS338 | Repl 7 Banks Combustion Coils | 5/1/2018 | 9/1/2018 | 146250.98 |  | 0 | 0 | 0 | 146250.98 | 0 | 0 | 0 | 0 | 0 | 0 | 146250.98 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 146250.98 | n.m.
418 | 117 | ML0VP1603 | ML REPL SCAFFOLDING w/PLATFORM | 10/1/2016 | 3/1/2018 | -4410.51 |  | 0 | 0 | 0 | -4410.51 | 27247.494 | 0 | 0 | 0 | 0 | 27247.494 | -31658.004 | -116.2% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -31658.004 | -116.2%
419 | 117 | ML217SP06 | ML U2 PRECIP ROOF BAY BOX YYY | 12/1/2017 | 9/1/2018 | 141081.15 |  | 0 | 0 | 0 | 141081.15 | 228828.157 | 0 | 0 | 0 | 0 | 228828.157 | -87747.007 | -38.35% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -87747.007 | -38.35%
420 | 117 | BSPPBS342 | REPL CATHODIC PROT TEST STA | 4/1/2018 | 8/1/2018 | 144648.43 |  | 0 | 0 | 0 | 144648.43 | 0 | 0 | 0 | 0 | 0 | 0 | 144648.43 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 144648.43 | n.m.
421 | 117 | ML018EP14 | ML SEWAGE TREATMNT PLANT COVER | 9/1/2018 | 2020-03-01 | 32182.6 | 111888.79 | 901.6 | 0 | 0 | 144972.99 | 0 | 0 | 0 | 0 | 0 | 0 | 32182.6 | n.m. | 111888.79 | n.m. | 901.6 | n.m. | 0 | n.m. | 0 | n.m. | 144972.99 | n.m.
422 | 117 | ML017MP06 | ML MH CONVEYOR BELT REPLACE | 3/1/2017 | 4/1/2018 | 88682.44 |  | 0 | 0 | 0 | 88682.44 | 0 | 0 | 0 | 0 | 0 | 0 | 88682.44 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 88682.44 | n.m.
423 | 117 | MLP17EP05 | MLP E POWER CABLE REPLACEMENT | 2/1/2017 | 1/1/2019 | 22579.84 | -1594.32 | 0 | 0 | 0 | 20985.52 | 28794.932 | 16.229 | 0 | 0 | 0 | 28811.161 | -6215.092 | -21.58% | -1610.549 | -9924% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -7825.641 | -27.16%
424 | 117 | ML217SP05 | ML U2 PRECIP ROOF BAY BOX XXX | 12/1/2017 | 9/1/2018 | 133839.65 |  | 0 | 0 | 0 | 133839.65 | 228828.157 | 0 | 0 | 0 | 0 | 228828.157 | -94988.507 | -41.51% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -94988.507 | -41.51%
425 | 117 | ML119EP01 | RPL MAIN TURB OIL TANK VALVE | 2/1/2019 | 11/1/2019 |  | 134147.92 | 0 | 0 | 0 | 134147.92 | 0 | 140974.649 | 0 | 0 | 0 | 140974.649 | 0 | n.m. | -6826.729 | -4.843% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -6826.729 | -4.843%
426 | 117 | BSPPB0003 | Boiler MU Water Supply PPB<100 | Charges Began Prior to Jan 2015 | 2/1/2019 | 3188.81 | 258.98 | 0 | 20877.58 | 3052.31 | 27377.68 | 175002.489 | 0 | 209162.386 | 0 | 156092.583 | 540257.458 | -171813.679 | -98.18% | 258.98 | n.m. | -209162.386 | -100% | 20877.58 | n.m. | -153040.273 | -98.04% | -512879.778 | -94.93%
427 | 117 | ML018EP04 | ML HVAC REPLACEMENT | 2/1/2018 | 3/1/2019 | 129725.41 | 4104.19 | 0 | 0 | 0 | 133829.6 | 0 | 0 | 0 | 0 | 0 | 0 | 129725.41 | n.m. | 4104.19 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 133829.6 | n.m.
428 | 117 | ML219SP04 | MLU2 PRECIP ROOF BAY BOX3ROW7 | 10/1/2019 | 2020-07-01 |  | 131813.08 | -1764.98 | 0 | 0 | 130048.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 131813.08 | n.m. | -1764.98 | n.m. | 0 | n.m. | 0 | n.m. | 130048.1 | n.m.
429 | 117 | ML018NP10 | ML GUARD RAIL UPGRADES | 10/1/2018 | 3/1/2019 | 108006.88 | 18016.09 | 0 | 0 | 0 | 126022.97 | 0 | 0 | 0 | 0 | 0 | 0 | 108006.88 | n.m. | 18016.09 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 126022.97 | n.m.
430 | 117 | ITCB11700 | KENTUCKY POWER - GEN | Charges Began Prior to Jan 2015 | 3/1/2019 | 6323.97 | 615.43 | 0 | 51324.73 | -27734.45 | 30529.68 | 0 | 0 | 0 | 0 | 0 | 0 | 6323.97 | n.m. | 615.43 | n.m. | 0 | n.m. | 51324.73 | n.m. | -27734.45 | n.m. | 30529.68 | n.m.
431 | 117 | ML119SP08 | ML U1 DEMINERALIZER RESIN RPL | 11/1/2018 | 2020-02-01 | 6.7 | 121997.79 | 239.92 | 0 | 0 | 122244.41 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7 | n.m. | 121997.79 | n.m. | 239.92 | n.m. | 0 | n.m. | 0 | n.m. | 122244.41 | n.m.
432 | 117 | ML217SP07 | ML U2 PRECIP ROOF BAY BOX ZZZ | 12/1/2017 | 9/1/2018 | 116972.32 |  | 0 | 0 | 0 | 116972.32 | 228828.157 | 0 | 0 | 0 | 0 | 228828.157 | -111855.837 | -48.88% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -111855.837 | -48.88%
433 | 117 | ML017SP02 | PULVERIZER REBUILD CAPITAL(#YY | 8/1/2017 | 1/1/2018 | -4802.5 |  | 0 | 0 | 0 | -4802.5 | 191225.297 | 0 | 0 | 0 | 0 | 191225.297 | -196027.797 | -102.5% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -196027.797 | -102.5%
434 | 117 | ML219EP03 | ML UNIT2 ACID LINE REPLACEMENT | 7/1/2019 | 2021-06-01 |  | 118896.84 | 6760.45 | 19.33 | 0 | 125676.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 118896.84 | n.m. | 6760.45 | n.m. | 19.33 | n.m. | 0 | n.m. | 125676.62 | n.m.
435 | 117 | ML018NP04 | ML STOREROOM SECURITY SYSTEM | 7/1/2018 | 6/1/2019 | 96213.52 | 18104.38 | 0 | 0 | 0 | 114317.9 | 0 | 0 | 0 | 0 | 0 | 0 | 96213.52 | n.m. | 18104.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 114317.9 | n.m.
436 | 117 | ML218SP08 | ML2 LONGER O2 PROBE REPLACEMN | 10/1/2017 | 5/1/2018 | 30336.21 |  | 0 | 0 | 0 | 30336.21 | 100240.072 | 56.173 | 0 | 0 | 0 | 100296.245 | -69903.862 | -69.74% | -56.173 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -69960.035 | -69.75%
437 | 117 | MLP18EP06 | MLP E VALVE REPLACEMENT 6 IN G | 1/1/2018 | 9/1/2019 | 101505.8 | 11604.92 | 0 | 0 | 0 | 113110.72 | 0 | 110180.444 | 136986.592 | 99310.564 | 80429.2813 | 426906.8813 | 101505.8 | n.m. | -98575.524 | -89.47% | -136986.592 | -100% | -99310.564 | -100% | -80429.2813 | -100% | -313796.1613 | -73.5%
438 | 117 | ML017EP04 | ML HVAC REPLACEMENT | 5/1/2017 | 3/1/2018 | 9341.29 |  | 0 | 0 | 0 | 9341.29 | 0 | 0 | 0 | 0 | 0 | 0 | 9341.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9341.29 | n.m.
439 | 117 | ML219VP07 | ML 22 ID FAN DE HUB REPLACEMEN | 10/1/2019 | 2020-03-01 |  | 112115.88 | 7685.98 | 0 | 0 | 119801.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 112115.88 | n.m. | 7685.98 | n.m. | 0 | n.m. | 0 | n.m. | 119801.86 | n.m.
440 | 117 | ML117EP10 | ML1 RPL FEEDWATER CHEM PUMPS | 8/1/2017 | 1/1/2019 | 54966.6 | -584.97 | 0 | 0 | 0 | 54381.63 | 0 | 0 | 0 | 0 | 0 | 0 | 54966.6 | n.m. | -584.97 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 54381.63 | n.m.
441 | 117 | MLP19MP01 | MLP MH COAL CHUTE REPLACEMENT | 10/1/2019 | 2021-03-01 |  | 109504.57 | 206708.78 | 1518.81 | 0 | 317732.16 | 0 | 44389.673 | 0 | 0 | 0 | 44389.673 | 0 | n.m. | 65114.897 | 146.7% | 206708.78 | n.m. | 1518.81 | n.m. | 0 | n.m. | 273342.487 | 615.8%
442 | 117 | 000025231 | 2018 Gen Plt Cap Blkt - KYPC-G | 3/1/2018 | 2022-09-01 | 39895.79 | 66042.98 | 39430.49 | 27652.84 | -4894.77 | 168127.33 | 0 | 0 | 0 | 0 | 0 | 0 | 39895.79 | n.m. | 66042.98 | n.m. | 39430.49 | n.m. | 27652.84 | n.m. | -4894.77 | n.m. | 168127.33 | n.m.
443 | 117 | ML117EP03 | REPLACE U1 WELL WATER TANK PPB | 1/1/2017 | 3/1/2018 | -17892.41 |  | 0 | 0 | 0 | -17892.41 | 0 | 0 | 0 | 0 | 0 | 0 | -17892.41 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -17892.41 | n.m.
444 | 117 | ML018EP16 | ML CEMS HG SORBENT BU SYSTEM | 10/1/2018 | 10/1/2019 | 10154.14 | 91389.28 | 0 | 0 | 0 | 101543.42 | 0 | 0 | 0 | 0 | 0 | 0 | 10154.14 | n.m. | 91389.28 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 101543.42 | n.m.
445 | 117 | ML118SP01 | ML U1 PRECIP EJ REPLACEMENT | 3/1/2018 | 7/1/2019 | 101112.26 | -280.98 | 0 | 0 | 0 | 100831.28 | 0 | 0 | 0 | 0 | 0 | 0 | 101112.26 | n.m. | -280.98 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 100831.28 | n.m.
446 | 117 | MLP19EP01 | ML E MOTORS GREATER THAN 10 HP | 1/1/2019 | 2020-07-01 |  | 100699.74 | 17576.21 | 0 | 0 | 118275.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 100699.74 | n.m. | 17576.21 | n.m. | 0 | n.m. | 0 | n.m. | 118275.95 | n.m.
447 | 117 | ML018VP02 | ML0 V BALL MILL REBUILD | 10/1/2018 | 6/1/2019 | 96636.49 | 1920.67 | 0 | 0 | 0 | 98557.16 | 0 | 0 | 0 | 0 | 0 | 0 | 96636.49 | n.m. | 1920.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 98557.16 | n.m.
448 | 117 | MLP18SP01 | ML SAFETY VALVES ( 4 ) | 4/1/2019 | 2022-01-01 |  | 96297.65 | 41094.71 | 893.36 | 262.19 | 138547.91 | 89917.761 | 13.035 | 0 | 0 | 0 | 89930.796 | -89917.761 | -100% | 96284.615 | 738662% | 41094.71 | n.m. | 893.36 | n.m. | 262.19 | n.m. | 48617.114 | 54.06%
449 | 117 | ML018EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 2/1/2018 | 7/1/2019 | 96189.96 | -209.01 | 0 | 0 | 0 | 95980.95 | 0 | 0 | 0 | 0 | 0 | 0 | 96189.96 | n.m. | -209.01 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 95980.95 | n.m.
450 | 117 | ML019NP01 | ML CAPITAL TOOLS | 2/1/2019 | 2022-04-01 |  | 95839.41 | 19687.68 | 66.77 | -4415.48 | 111178.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 95839.41 | n.m. | 19687.68 | n.m. | 66.77 | n.m. | -4415.48 | n.m. | 111178.38 | n.m.
451 | 117 | ML019VP02 | ML0 V BALL MILL REBUILD | 11/1/2018 | 11/1/2019 | 430.74 | 95205.44 | 0 | 0 | 0 | 95636.18 | 0 | 0 | 0 | 0 | 0 | 0 | 430.74 | n.m. | 95205.44 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 95636.18 | n.m.
452 | 117 | MLP15MP02 | MLP MH CONVEYOR BELT REPLACE | 2/1/2015 | 5/1/2018 | 298.62 |  | 0 | 0 | 0 | 298.62 | 0 | 0 | 0 | 0 | 0 | 0 | 298.62 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 298.62 | n.m.
453 | 117 | BSPPBS351 | Replace Auto Voltage Regulator | 6/1/2019 | 2021-03-01 |  | 91562.77 | 546635.68 | 20993.21 | 0 | 659191.66 | 0 | 0 | 315300.655 | 0 | 0 | 315300.655 | 0 | n.m. | 91562.77 | n.m. | 231335.025 | 73.37% | 20993.21 | n.m. | 0 | n.m. | 343891.005 | 109.1%
454 | 117 | ML118EP08 | ML U1 RPL PLANT CONTRL BATTERY | 12/1/2017 | 6/1/2018 | 19218.11 |  | 0 | 0 | 0 | 19218.11 | 0 | 0 | 0 | 0 | 0 | 0 | 19218.11 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19218.11 | n.m.
455 | 117 | ML017EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 5/1/2017 | 8/1/2018 | 13035.23 |  | 0 | 0 | 0 | 13035.23 | 0 | 0 | 0 | 0 | 0 | 0 | 13035.23 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13035.23 | n.m.
456 | 117 | BSPPBS363 | BS1 BFPT (SPARE) BLADE REPLACE | 12/1/2019 | 2021-05-01 |  | 87715.37 | 88237.47 | -66730.34 | 0 | 109222.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 87715.37 | n.m. | 88237.47 | n.m. | -66730.34 | n.m. | 0 | n.m. | 109222.5 | n.m.
457 | 117 | ML218EP07 | ML #21A CIRC WATER PUMP REPLAC | 9/1/2018 | 3/1/2019 | 66189.37 | 20322.96 | 0 | 0 | 0 | 86512.33 | 0 | 0 | 0 | 0 | 0 | 0 | 66189.37 | n.m. | 20322.96 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 86512.33 | n.m.
458 | 117 | ML218SP06 | REPLACE 26E BURNERTUBE OPENING | 12/1/2017 | 7/1/2018 | 72951.4 |  | 0 | 0 | 0 | 72951.4 | 124713.087 | 0 | 0 | 0 | 0 | 124713.087 | -51761.687 | -41.5% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -51761.687 | -41.5%
459 | 117 | ML017NP04 | ML UPGRADE RSO BREAK AREA | 11/1/2017 | 2/1/2018 | 14012.14 |  | 0 | 0 | 0 | 14012.14 | 0 | 0 | 0 | 0 | 0 | 0 | 14012.14 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14012.14 | n.m.
460 | 117 | ML219VP08 | ML 22 ID FAN DCHG VLV EJ | 10/1/2019 | 2020-03-01 |  | 84840.09 | 3969.85 | 0 | 0 | 88809.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 84840.09 | n.m. | 3969.85 | n.m. | 0 | n.m. | 0 | n.m. | 88809.94 | n.m.
461 | 117 | ML018EP11 | ML CIRCULATING WATERPMP MOTORS | 10/1/2018 | 11/1/2019 | 51113.76 | 33148.37 | 0 | 0 | 0 | 84262.13 | 0 | 0 | 0 | 0 | 0 | 0 | 51113.76 | n.m. | 33148.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 84262.13 | n.m.
462 | 117 | ML218SP20 | ML REPLACE U2 PULVERIZER YOKE | 4/1/2018 | 2020-09-01 | 86610.09 | -2473.46 | 36078.46 | 0 | 0 | 120215.09 | 0 | 59751.963 | 140133.627 | 0 | 48338.679 | 248224.269 | 86610.09 | n.m. | -62225.423 | -104.1% | -104055.167 | -74.25% | 0 | n.m. | -48338.679 | -100% | -128009.179 | -51.57%
463 | 117 | ML016VP08 | UPS ON FGD | 12/1/2016 | 1/1/2019 | 27113.22 | -1731.93 | 0 | 0 | 0 | 25381.29 | 0 | 0 | 0 | 0 | 0 | 0 | 27113.22 | n.m. | -1731.93 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25381.29 | n.m.
464 | 117 | ML119EP07 | ML UNIT1 ACID LINE REPLACEMENT | 7/1/2019 | 2021-06-01 |  | 81852.43 | 6926.78 | 5.82 | 0 | 88785.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 81852.43 | n.m. | 6926.78 | n.m. | 5.82 | n.m. | 0 | n.m. | 88785.03 | n.m.
465 | 117 | MLP17EP01 | MLP E MOTORS GREATER THAN 10 H | 3/1/2017 | 7/1/2018 | 2708.04 |  | 0 | 0 | 0 | 2708.04 | 70.56 | 0 | 0 | 0 | 0 | 70.56 | 2637.48 | 3738% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2637.48 | 3738%
466 | 117 | BSPPB0017 | Turb Valves & Ctrls PPB<100k | 12/1/2016 | 4/1/2018 | 2636.25 |  | 0 | 0 | 0 | 2636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 2636.25 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2636.25 | n.m.
467 | 117 | ML218SP07 | REPLACE 26F BURNERTUBE OPENING | 12/1/2017 | 9/1/2018 | 67132.66 |  | 0 | 0 | 0 | 67132.66 | 124713.087 | 0 | 0 | 0 | 0 | 124713.087 | -57580.427 | -46.17% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -57580.427 | -46.17%
468 | 117 | ML017EP11 | ML WASTE TANK CATHODIC PROTECT | 12/1/2017 | 7/1/2018 | 331395.96 |  | 0 | 0 | 0 | 331395.96 | 0 | 0 | 0 | 0 | 0 | 0 | 331395.96 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 331395.96 | n.m.
469 | 117 | ML018NP07 | ML NEW GATE FOR GATE 3 | 8/1/2018 | 2020-03-01 | 61295.05 | 15746.09 | 21.11 | 0 | 0 | 77062.25 | 0 | 0 | 0 | 0 | 0 | 0 | 61295.05 | n.m. | 15746.09 | n.m. | 21.11 | n.m. | 0 | n.m. | 0 | n.m. | 77062.25 | n.m.
470 | 117 | ML218SP05 | REPLACE 26D BURNERTUBE OPENING | 12/1/2017 | 9/1/2018 | 61586.52 |  | 0 | 0 | 0 | 61586.52 | 124713.087 | 0 | 0 | 0 | 0 | 124713.087 | -63126.567 | -50.62% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -63126.567 | -50.62%
471 | 117 | MLP18EP08 | ML #12 CIRCULATOR PUMP MOTOR | 8/1/2018 | 11/1/2019 | 50006.17 | 24310.06 | 0 | 0 | 0 | 74316.23 | 0 | 0 | 0 | 0 | 0 | 0 | 50006.17 | n.m. | 24310.06 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 74316.23 | n.m.
472 | 117 | ML017EP06 | GATE1 LIGHTS & GUARDGATE POWER | 3/1/2017 | 1/1/2018 | 1803.27 |  | 0 | 0 | 0 | 1803.27 | 0 | 0 | 0 | 0 | 0 | 0 | 1803.27 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1803.27 | n.m.
473 | 117 | ML117EP11 | ML U1 1st RH EXH PIPING SPRING | 12/1/2017 | 5/1/2018 | 69372.38 |  | 0 | 0 | 0 | 69372.38 | 0 | 0 | 0 | 0 | 0 | 0 | 69372.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 69372.38 | n.m.
474 | 117 | MLP18EP03 | ML E PUMP REPLACEMENT DR 10 HP | 1/1/2018 | 2020-01-01 | 68223.93 | 38.85 | 2.3 | 0 | 0 | 68265.08 | 0 | 183716.278 | 151711.714 | 110428.959 | 90059.2 | 535916.151 | 68223.93 | n.m. | -183677.428 | -99.98% | -151709.414 | -100% | -110428.959 | -100% | -90059.2 | -100% | -467651.071 | -87.26%
475 | 117 | ML118EP04 | REP RFL9300 PILOT WIRE SYSTEM | 2/1/2019 | 11/1/2019 |  | 67456.46 | 0 | 0 | 0 | 67456.46 | 90361.153 | 117880.6 | 21.121 | 0 | 0 | 208262.874 | -90361.153 | -100% | -50424.14 | -42.78% | -21.121 | -100% | 0 | n.m. | 0 | n.m. | -140806.414 | -67.61%
476 | 117 | ML019EP02 | ML TRANSFORMER REPLACEMENT | 2/1/2019 | 2021-09-01 |  | 67033.21 | 104522.11 | 11965.71 | 0 | 183521.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 67033.21 | n.m. | 104522.11 | n.m. | 11965.71 | n.m. | 0 | n.m. | 183521.03 | n.m.
477 | 117 | ML117EP04 | REPLACE #11 RDV to NASH PUMP | 2/1/2019 | 11/1/2019 |  | 66949.39 | 0 | 0 | 0 | 66949.39 | 0 | 145001.883 | 0 | 0 | 0 | 145001.883 | 0 | n.m. | -78052.493 | -53.83% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -78052.493 | -53.83%
478 | 117 | ML118SP19 | ML U1 TURBINE BASEMENT FIRE SY | 11/1/2018 | 1/1/2019 | 66806.57 | -187.27 | 0 | 0 | 0 | 66619.3 | 0 | 0 | 0 | 0 | 0 | 0 | 66806.57 | n.m. | -187.27 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 66619.3 | n.m.
479 | 117 | MLP19EP02 | ML E MOTOR REWINDSOVER 10HP | 2/1/2019 | 2021-06-01 |  | 65591.32 | 11484.89 | 0.95 | 0 | 77077.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 65591.32 | n.m. | 11484.89 | n.m. | 0.95 | n.m. | 0 | n.m. | 77077.16 | n.m.
480 | 117 | ML217VP05 | INSTALL 2nd RH BLADES 3rd ROW | 5/1/2017 | 7/1/2018 | 1809.67 |  | 0 | 0 | 0 | 1809.67 | 0 | 0 | 0 | 0 | 0 | 0 | 1809.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1809.67 | n.m.
481 | 117 | ML018NP08 | ML TURNSTILE ROOFS AND GRATING | 8/1/2018 | 2020-01-01 | 51275.75 | 10793.78 | 75.1 | 0 | 0 | 62144.63 | 0 | 0 | 0 | 0 | 0 | 0 | 51275.75 | n.m. | 10793.78 | n.m. | 75.1 | n.m. | 0 | n.m. | 0 | n.m. | 62144.63 | n.m.
482 | 117 | ML016VP09 | SELF CONTAINED RESTROOM SYSTEM | 12/1/2016 | 3/1/2018 | 296.19 |  | 0 | 0 | 0 | 296.19 | 0 | 0 | 0 | 0 | 0 | 0 | 296.19 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 296.19 | n.m.
483 | 117 | ML219EP14 | ML219 21 CIRC MTR DIODE RING | 11/1/2019 | 2020-06-01 |  | 60390.91 | 21693.76 | 0 | 0 | 82084.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 60390.91 | n.m. | 21693.76 | n.m. | 0 | n.m. | 0 | n.m. | 82084.67 | n.m.
484 | 117 | MLP18EP01 | ML E MOTORS GREATER THAN 10 HP | 1/1/2018 | 6/1/2019 | 55492.12 | 4648.15 | 0 | 0 | 0 | 60140.27 | 0 | 0 | 0 | 0 | 0 | 0 | 55492.12 | n.m. | 4648.15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 60140.27 | n.m.
485 | 117 | ML116EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 4/1/2016 | 4/1/2018 | 9751.38 |  | 0 | 0 | 0 | 9751.38 | 0 | 0 | 0 | 0 | 0 | 0 | 9751.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9751.38 | n.m.
486 | 117 | ML018EP06 | ML #12 RIVER WATER MU PUMP RPL | 8/1/2018 | 10/1/2018 | 59009.28 |  | 0 | 0 | 0 | 59009.28 | 0 | 0 | 0 | 0 | 0 | 0 | 59009.28 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 59009.28 | n.m.
487 | 117 | ML018NP11 | ML GATE 3 EMPLOYEE STAIRS | 9/1/2018 | 4/1/2019 | 27112.12 | 30771.7 | 0 | 0 | 0 | 57883.82 | 0 | 0 | 0 | 0 | 0 | 0 | 27112.12 | n.m. | 30771.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 57883.82 | n.m.
488 | 117 | ML216SP12 | ML2 #5 PRECIP EXPJOINT REPLACE | 12/1/2016 | 9/1/2018 | 48814.58 |  | 0 | 0 | 0 | 48814.58 | 0 | 0 | 0 | 0 | 0 | 0 | 48814.58 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 48814.58 | n.m.
489 | 117 | ML017EP02 | REPLACE AMMONIA TANK | 10/1/2016 | 8/1/2019 | 9225.69 | 9343.95 | 0 | 0 | 0 | 18569.64 | 0 | 0 | 0 | 0 | 0 | 0 | 9225.69 | n.m. | 9343.95 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 18569.64 | n.m.
490 | 117 | ML117VP06 | RPL #11 ID FAN HYDRAULIC CYL | 3/1/2018 | 6/1/2019 | 58724.84 | -2504.21 | 0 | 0 | 0 | 56220.63 | 0 | 0 | 0 | 0 | 0 | 0 | 58724.84 | n.m. | -2504.21 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 56220.63 | n.m.
491 | 117 | ML118SP05 | RPL AUMA TEMPER AIR DAMPER DRV | 12/1/2017 | 5/1/2018 | 10708.76 |  | 0 | 0 | 0 | 10708.76 | 0 | 50077.912 | 8.95 | 0 | 0 | 50086.862 | 10708.76 | n.m. | -50077.912 | -100% | -8.95 | -100% | 0 | n.m. | 0 | n.m. | -39378.102 | -78.62%
492 | 117 | ML119EP05 | ML #11B CIRC WATER PUMP REPLMT | 3/1/2019 | 7/1/2019 |  | 53357.1 | 0 | 0 | 0 | 53357.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 53357.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 53357.1 | n.m.
493 | 117 | ML1VP1704 | ML1 ID FAN GUILLOTINE DAMPER | 8/1/2017 | 7/1/2018 | 474.23 |  | 0 | 0 | 0 | 474.23 | 0 | 0 | 0 | 0 | 0 | 0 | 474.23 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 474.23 | n.m.
494 | 117 | MLP19EP06 | LP E VALVE REPLACEMENT 6 IN + | 1/1/2019 | 2020-11-01 |  | 52345.57 | 7371.21 | 0 | 0 | 59716.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 52345.57 | n.m. | 7371.21 | n.m. | 0 | n.m. | 0 | n.m. | 59716.78 | n.m.
495 | 117 | ML018EP01 | ML REPLACEMENT OF TRANSMITTERS | 2/1/2018 | 2021-06-01 | 50480.49 | 1279.78 | 9235.63 | 6905.28 | 0 | 67901.18 | 0 | 64091.052 | 81461.059 | 58183.305 | 47935.5766 | 251670.9926 | 50480.49 | n.m. | -62811.272 | -98% | -72225.429 | -88.66% | -51278.025 | -88.13% | -47935.5766 | -100% | -183769.8126 | -73.02%
496 | 117 | ML0VP1702 | REDUNDANT HDR SLURRY FEED TNK | 12/1/2017 | 7/1/2018 | 42956.13 |  | 0 | 0 | 0 | 42956.13 | 0 | 0 | 0 | 0 | 0 | 0 | 42956.13 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 42956.13 | n.m.
497 | 117 | ML218SP04 | REPLACE FD INLET VANE DRIVES | 3/1/2018 | 5/1/2018 | 50404.09 |  | 0 | 0 | 0 | 50404.09 | 66264.917 | 36.929 | 0 | 0 | 0 | 66301.846 | -15860.827 | -23.94% | -36.929 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -15897.756 | -23.98%
498 | 117 | ML018EP17 | ML R3 TRANSFORMER REPLACEMENT | 10/1/2018 | 2020-08-01 | 20609.8 | 29085.31 | 813.24 | 0 | 0 | 50508.35 | 0 | 0 | 0 | 0 | 0 | 0 | 20609.8 | n.m. | 29085.31 | n.m. | 813.24 | n.m. | 0 | n.m. | 0 | n.m. | 50508.35 | n.m.
499 | 117 | MLP18EP09 | ML1 2019 HIGH ENERGY PIPE MAT | 9/1/2018 | 6/1/2019 | 603.23 | 49010.5 | 0 | 0 | 0 | 49613.73 | 0 | 0 | 0 | 0 | 0 | 0 | 603.23 | n.m. | 49010.5 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49613.73 | n.m.
500 | 117 | ML119SP07 | ML1 E PRECIPITATOR EJ REPLACE | 1/1/2019 | 11/1/2019 |  | 49348.05 | 0 | 0 | 0 | 49348.05 | 0 | 176745.429 | 31.652 | 0 | 0 | 176777.081 | 0 | n.m. | -127397.379 | -72.08% | -31.652 | -100% | 0 | n.m. | 0 | n.m. | -127429.031 | -72.08%
501 | 117 | MLP17EP06 | MLP E VALVE REPLACEMENT 6 IN G | 1/1/2017 | 1/1/2019 | 13103.46 | -288.9 | 0 | 0 | 0 | 12814.56 | 108224.814 | 15.431 | 0 | 0 | 0 | 108240.245 | -95121.354 | -87.89% | -304.331 | -1972% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -95425.685 | -88.16%
502 | 117 | ML218SP03 | RPL AUMA TEMPER AIR DAMPER DRV | 12/1/2017 | 6/1/2018 | 15037.97 |  | 0 | 0 | 0 | 15037.97 | 51204.698 | 28.536 | 0 | 0 | 0 | 51233.234 | -36166.728 | -70.63% | -28.536 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -36195.264 | -70.65%
503 | 117 | MLP17EP20 | MLP E CARBONE FILTER BUILDING | 9/1/2017 | 3/1/2018 | 4934.18 |  | 0 | 0 | 0 | 4934.18 | 0 | 0 | 0 | 0 | 0 | 0 | 4934.18 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4934.18 | n.m.
504 | 117 | ML1NP1911 | ML1 INSULATION & LAGGING RPL | 3/1/2019 | 11/1/2019 |  | 45133.97 | 0 | 0 | 0 | 45133.97 | 0 | 118871.889 | 19.778 | 0 | 0 | 118891.667 | 0 | n.m. | -73737.919 | -62.03% | -19.778 | -100% | 0 | n.m. | 0 | n.m. | -73757.697 | -62.04%
505 | 117 | ML119SP14 | ML U1 SCR INLET EXP JOINT | 4/1/2019 | 11/1/2019 |  | 45023.69 | 0 | 0 | 0 | 45023.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 45023.69 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45023.69 | n.m.
506 | 117 | ML018SP03 | ML U1&2 WATER CANNON UPGRADE | 4/1/2018 | 4/1/2019 | 44892.44 | 15.1 | 0 | 0 | 0 | 44907.54 | 0 | 0 | 0 | 0 | 0 | 0 | 44892.44 | n.m. | 15.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 44907.54 | n.m.
507 | 117 | ML119SP13 | REPLACE U1 PULVERIZER YOKE | 5/1/2019 | 2020-06-01 |  | 44589.82 | -497.14 | 0 | 0 | 44092.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 44589.82 | n.m. | -497.14 | n.m. | 0 | n.m. | 0 | n.m. | 44092.68 | n.m.
508 | 117 | ML019EP08 | ML- UNIT 0 INSTRUMENTATION PPB | 7/1/2019 | 2020-06-01 |  | 40984.97 | 1236.72 | 0 | 0 | 42221.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 40984.97 | n.m. | 1236.72 | n.m. | 0 | n.m. | 0 | n.m. | 42221.69 | n.m.
509 | 117 | ML017MP05 | ML MH COAL CHUTE REPLACEMENT | 9/1/2017 | 7/1/2018 | 10208.59 |  | 0 | 0 | 0 | 10208.59 | 0 | 0 | 0 | 0 | 0 | 0 | 10208.59 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10208.59 | n.m.
510 | 117 | ML217VP04 | U2 PRECIPITATOR PLC UPGRADE | 12/1/2017 | 2018-06-01 | 19881.88 |  | 0 | 0 | 0 | 19881.88 | 0 | 0 | 0 | 0 | 0 | 0 | 19881.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19881.88 | n.m.
511 | 117 | ML017EP01 | Replacement of Transmitters | 6/1/2017 | 5/1/2018 | 85.68 |  | 0 | 0 | 0 | 85.68 | 65843.532 | 10.953 | 0 | 0 | 0 | 65854.485 | -65757.852 | -99.87% | -10.953 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -65768.805 | -99.87%
512 | 117 | ML118EP10 | ML U1 STATOR DO & CONDUCTIVITY | 9/1/2018 | 11/1/2019 | 16825.37 | 22977.3 | 0 | 0 | 0 | 39802.67 | 0 | 0 | 0 | 0 | 0 | 0 | 16825.37 | n.m. | 22977.3 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 39802.67 | n.m.
513 | 117 | ML118EP12 | ML UNIT 1 INSTRUMENTATION PPB | 1/1/2018 | 2020-11-01 | 35446.03 | 3222.13 | 1626.74 | 0 | 0 | 40294.9 | 0 | 0 | 0 | 0 | 0 | 0 | 35446.03 | n.m. | 3222.13 | n.m. | 1626.74 | n.m. | 0 | n.m. | 0 | n.m. | 40294.9 | n.m.
514 | 117 | ML218SP02 | RPL AUMA HOT AIR DAMPER DRIVES | 12/1/2017 | 5/1/2018 | 6768.76 |  | 0 | 0 | 0 | 6768.76 | 29980.269 | 0 | 0 | 0 | 0 | 29980.269 | -23211.509 | -77.42% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -23211.509 | -77.42%
515 | 117 | ML216EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 3/1/2016 | 5/1/2018 | 507.29 |  | 0 | 0 | 0 | 507.29 | 0 | 0 | 0 | 0 | 0 | 0 | 507.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 507.29 | n.m.
516 | 117 | ML217SP11 | ML2 CROSSOVER PIPE @ CMS | 6/1/2017 | 2/1/2018 | 847.55 |  | 0 | 0 | 0 | 847.55 | 0 | 0 | 0 | 0 | 0 | 0 | 847.55 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 847.55 | n.m.
517 | 117 | ML219SP07 | MLU2 PRECIP EXP JOINT #1 | 11/1/2019 | 2020-06-01 |  | 37034.1 | 6566.96 | 0 | 0 | 43601.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 37034.1 | n.m. | 6566.96 | n.m. | 0 | n.m. | 0 | n.m. | 43601.06 | n.m.
518 | 117 | ML219EP01 | ML U2 555 LEAK DECTECT HP HEAT | 12/1/2018 | 2020-01-01 | 7225.96 | 29272.29 | 300.18 | 0 | 0 | 36798.43 | 0 | 0 | 0 | 0 | 0 | 0 | 7225.96 | n.m. | 29272.29 | n.m. | 300.18 | n.m. | 0 | n.m. | 0 | n.m. | 36798.43 | n.m.
519 | 117 | ML018EP12 | ML HIGH WIND WARNING LIGHTS | 9/1/2018 | 2/1/2019 | 31688.11 | 3995.95 | 0 | 0 | 0 | 35684.06 | 0 | 0 | 0 | 0 | 0 | 0 | 31688.11 | n.m. | 3995.95 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35684.06 | n.m.
520 | 117 | ML019EP01 | ML REPLACEMENT OF TRANSMITTER | 4/1/2019 | 2020-06-01 |  | 35046.52 | 19.08 | 0 | 0 | 35065.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 35046.52 | n.m. | 19.08 | n.m. | 0 | n.m. | 0 | n.m. | 35065.6 | n.m.
521 | 117 | ML218SP11 | ML U2 #21 PA DUCT EJ REPLACEMT | 1/1/2018 | 7/1/2018 | 35019.76 |  | 0 | 0 | 0 | 35019.76 | 0 | 0 | 0 | 0 | 0 | 0 | 35019.76 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 35019.76 | n.m.
522 | 117 | ML218SP16 | ML U2 #26 PA DUCT EJ REPLACEMT | 1/1/2018 | 6/1/2018 | 34667.68 |  | 0 | 0 | 0 | 34667.68 | 0 | 0 | 0 | 0 | 0 | 0 | 34667.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 34667.68 | n.m.
523 | 117 | ML219EP02 | ML INTERTEK HIGH ENERGY PIPING | 4/1/2019 | 2020-05-01 |  | 32875.13 | 7260.09 | 0 | 0 | 40135.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 32875.13 | n.m. | 7260.09 | n.m. | 0 | n.m. | 0 | n.m. | 40135.22 | n.m.
524 | 117 | 000025026 | Gen Plt Blkt KY-G Mitchell117 | 10/1/2017 | 2022-09-01 | 130.68 | 2133.39 | 19.3 | 3131.45 | -3131.45 | 2283.37 | 0 | 0 | 0 | 0 | 0 | 0 | 130.68 | n.m. | 2133.39 | n.m. | 19.3 | n.m. | 3131.45 | n.m. | -3131.45 | n.m. | 2283.37 | n.m.
525 | 117 | ML218EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 2/1/2018 | 2020-01-01 | 22502.24 | 8671.47 | 10.03 | 0 | 0 | 31183.74 | 0 | 0 | 0 | 0 | 0 | 0 | 22502.24 | n.m. | 8671.47 | n.m. | 10.03 | n.m. | 0 | n.m. | 0 | n.m. | 31183.74 | n.m.
526 | 117 | ML218EP03 | ML REPLACE#24 NASH VACUUM PUMP | 3/1/2018 | 1/1/2019 | 31290.93 | -296.89 | 0 | 0 | 0 | 30994.04 | 0 | 0 | 0 | 0 | 0 | 0 | 31290.93 | n.m. | -296.89 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30994.04 | n.m.
527 | 117 | ML119EP03 | ML U1 555 LEAK DECTECT HP HEAT | 12/1/2018 | 12/1/2019 | 7225.96 | 23641.13 | 0 | 0 | 0 | 30867.09 | 0 | 0 | 0 | 0 | 0 | 0 | 7225.96 | n.m. | 23641.13 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30867.09 | n.m.
528 | 117 | ML218SP15 | ML U2 #25 PA DUCT EJ REPLACEMT | 1/1/2018 | 5/1/2018 | 30338.29 |  | 0 | 0 | 0 | 30338.29 | 0 | 0 | 0 | 0 | 0 | 0 | 30338.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30338.29 | n.m.
529 | 117 | ML218SP14 | ML U2 #24 PA DUCT EJ REPLACEMT | 12/1/2017 | 5/1/2018 | 21591.56 |  | 0 | 0 | 0 | 21591.56 | 0 | 0 | 0 | 0 | 0 | 0 | 21591.56 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21591.56 | n.m.
530 | 117 | ML017EP13 | ML PROTECTOWIRE 1600 PANEL RPL | 9/1/2017 | 3/1/2018 | 588.62 |  | 0 | 0 | 0 | 588.62 | 0 | 0 | 0 | 0 | 0 | 0 | 588.62 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 588.62 | n.m.
531 | 117 | ML217EP02 | U2 SLAG BLOWER PLC UPGRADE | 11/1/2017 | 8/1/2018 | 13504.96 |  | 0 | 0 | 0 | 13504.96 | 0 | 0 | 0 | 0 | 0 | 0 | 13504.96 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13504.96 | n.m.
532 | 117 | ML218SP13 | ML U2 #23 PA DUCT EJ REPLACEMT | 12/1/2017 | 6/1/2018 | 20071.11 |  | 0 | 0 | 0 | 20071.11 | 0 | 0 | 0 | 0 | 0 | 0 | 20071.11 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20071.11 | n.m.
533 | 117 | ML018NP05 | ML FIRE HOUSE UPGRADES | 9/1/2018 | 2/1/2019 | 20663.25 | 6018.3 | 0 | 0 | 0 | 26681.55 | 0 | 0 | 0 | 0 | 0 | 0 | 20663.25 | n.m. | 6018.3 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 26681.55 | n.m.
534 | 117 | ML218SP12 | ML U2 #22 PA DUCT EJ REPLACEMT | 12/1/2017 | 6/1/2018 | 17880.7 |  | 0 | 0 | 0 | 17880.7 | 0 | 0 | 0 | 0 | 0 | 0 | 17880.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17880.7 | n.m.
535 | 117 | ML018EP10 | ML CIRCULATING WATER PUMP | 10/1/2018 | 3/1/2019 | 32231.88 | -6117.11 | 0 | 0 | 0 | 26114.77 | 0 | 0 | 0 | 0 | 0 | 0 | 32231.88 | n.m. | -6117.11 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 26114.77 | n.m.
536 | 117 | ML019EP10 | ML MH UPGRADE SCALE ELECTRONIC | 8/1/2019 | 2020-02-01 |  | 25677.18 | 1661.59 | 0 | 0 | 27338.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 25677.18 | n.m. | 1661.59 | n.m. | 0 | n.m. | 0 | n.m. | 27338.77 | n.m.
537 | 117 | ML119SP10 | ML #12 CLINKER GRINDER REPLACE | 3/1/2019 | 7/1/2019 |  | 24685.34 | 0 | 0 | 0 | 24685.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 24685.34 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24685.34 | n.m.
538 | 117 | ML119SP16 | ML PENTHOUSE ROOF INSULATION | 4/1/2019 | 11/1/2019 |  | 24577.97 | 0 | 0 | 0 | 24577.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 24577.97 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24577.97 | n.m.
539 | 117 | ML018EP15 | ML CPS POTABLE WATER PUMP | 9/1/2018 | 3/1/2019 | 16867.23 | 7131.86 | 0 | 0 | 0 | 23999.09 | 0 | 0 | 0 | 0 | 0 | 0 | 16867.23 | n.m. | 7131.86 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23999.09 | n.m.
540 | 117 | ML017VP06 | ML U1&2 IDFAN INST ACCESS BRID | 8/1/2017 | 2/1/2018 | 620.24 |  | 0 | 0 | 0 | 620.24 | 0 | 0 | 0 | 0 | 0 | 0 | 620.24 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 620.24 | n.m.
541 | 117 | ML219EP16 | ML219 21B CIRC WTR PMP REBUILD | 11/1/2019 | 2020-01-01 |  | 23833.86 | 105.46 | 0 | 0 | 23939.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 23833.86 | n.m. | 105.46 | n.m. | 0 | n.m. | 0 | n.m. | 23939.32 | n.m.
542 | 117 | ML118EP01 | RFP9300 PILOT to GE190 SEL411L | 2/1/2019 | 11/1/2019 |  | 23106.78 | 0 | 0 | 0 | 23106.78 | 84745.884 | 120139.412 | 0 | 0 | 0 | 204885.296 | -84745.884 | -100% | -97032.632 | -80.77% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -181778.516 | -88.72%
543 | 117 | ML219VP05 | 21 ID FAN DISCHARGE EJ REPLACE | 11/1/2019 | 2020-03-01 |  | 22933.56 | 2827.69 | 0 | 0 | 25761.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 22933.56 | n.m. | 2827.69 | n.m. | 0 | n.m. | 0 | n.m. | 25761.25 | n.m.
544 | 117 | ML218SP17 | ML #22 CLINKER GRINDER REPLACE | 4/1/2018 | 5/1/2018 | 22828.62 |  | 0 | 0 | 0 | 22828.62 | 0 | 0 | 0 | 0 | 0 | 0 | 22828.62 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 22828.62 | n.m.
545 | 117 | ML018EP07 | ML HVAC CFB BLUE BUILDING REP | 11/1/2018 | 1/1/2019 | 14767.2 | 7041.41 | 0 | 0 | 0 | 21808.61 | 0 | 0 | 0 | 0 | 0 | 0 | 14767.2 | n.m. | 7041.41 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21808.61 | n.m.
546 | 117 | ML219SP03 | REPL DFA FILTER SEPARATOR BAGS | 2/1/2019 | 2020-06-01 |  | 21515.41 | 5167.67 | 0 | 0 | 26683.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 21515.41 | n.m. | 5167.67 | n.m. | 0 | n.m. | 0 | n.m. | 26683.08 | n.m.
547 | 117 | ML218EP04 | ML U2 COOL TOWER VALVE REPL | 3/1/2018 | 6/1/2018 | 21189.05 |  | 0 | 0 | 0 | 21189.05 | 0 | 0 | 0 | 0 | 0 | 0 | 21189.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21189.05 | n.m.
548 | 117 | ML118EP09 | MLU1 COOL TOWER VALVE REPL | 3/1/2018 | 5/1/2018 | 21102.24 |  | 0 | 0 | 0 | 21102.24 | 0 | 0 | 0 | 0 | 0 | 0 | 21102.24 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21102.24 | n.m.
549 | 117 | ML219EP13 | ML- UNIT 2 INSTRUMENTATION PPB | 1/1/2019 | 2020-06-01 |  | 19825.42 | 975.88 | 0 | 0 | 20801.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 19825.42 | n.m. | 975.88 | n.m. | 0 | n.m. | 0 | n.m. | 20801.3 | n.m.
550 | 117 | ML019NP06 | ML U0 Gate 4 Automatic Gate | 12/1/2019 | 2021-03-01 |  | 19496.65 | 77053.48 | 2253.83 | 0 | 98803.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 19496.65 | n.m. | 77053.48 | n.m. | 2253.83 | n.m. | 0 | n.m. | 98803.96 | n.m.
551 | 117 | ML219VP11 | ML2 STACK FLUE EJ @ ELE 250 | 11/1/2019 | 2020-07-01 |  | 18519.63 | -925.96 | 0 | 0 | 17593.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 18519.63 | n.m. | -925.96 | n.m. | 0 | n.m. | 0 | n.m. | 17593.67 | n.m.
552 | 117 | ML119SP15 | ML #51 SAFETY VALVE REPLACEMNT | 4/1/2019 | 11/1/2019 |  | 17556.68 | 0 | 0 | 0 | 17556.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 17556.68 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17556.68 | n.m.
553 | 117 | ML018EP13 | ML1 CONVEYOR 7 FIREDELUGE VALV | 9/1/2018 | 3/1/2019 | 17416.63 | -22.45 | 0 | 0 | 0 | 17394.18 | 0 | 0 | 0 | 0 | 0 | 0 | 17416.63 | n.m. | -22.45 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 17394.18 | n.m.
554 | 117 | ML119SP17 | ML U1 Purge Air Heater Pnchlst | 12/1/2019 | 2020-08-01 |  | 17149.22 | 21626.25 | 0 | 0 | 38775.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 17149.22 | n.m. | 21626.25 | n.m. | 0 | n.m. | 0 | n.m. | 38775.47 | n.m.
555 | 117 | ML218SP09 | REPL DFA FILTER SEPARATOR BAGS | 7/1/2018 | 4/1/2019 | 8070.99 | 7767.21 | 0 | 0 | 0 | 15838.2 | 20586.523 | 21256.207 | 0 | 19472.302 | 17989.552 | 79304.584 | -12515.533 | -60.79% | -13488.997 | -63.46% | 0 | n.m. | -19472.302 | -100% | -17989.552 | -100% | -63466.384 | -80.03%
556 | 117 | BSPPB0011 | Generator & Support PPB<100k | Charges Began Prior to Jan 2015 | 9/1/2018 | 12901.66 |  | 7621.58 | 13464.5 | 10822.49 | 44810.23 | 0 | 0 | 0 | 0 | 0 | 0 | 12901.66 | n.m. | 0 | n.m. | 7621.58 | n.m. | 13464.5 | n.m. | 10822.49 | n.m. | 44810.23 | n.m.
557 | 117 | ML018MP04 | ML MH TOWBOAT UPGRADE REPLACE | 7/1/2018 | 4/1/2019 | 25506.44 | -10956.22 | 0 | 0 | 0 | 14550.22 | 0 | 0 | 0 | 0 | 0 | 0 | 25506.44 | n.m. | -10956.22 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14550.22 | n.m.
558 | 117 | ML016VP10 | GAS PUMP & FUEL MANAGEMENT | 12/1/2016 | 1/1/2018 | 72.63 |  | 0 | 0 | 0 | 72.63 | 0 | 0 | 0 | 0 | 0 | 0 | 72.63 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 72.63 | n.m.
559 | 117 | ML018MP09 | ML MH DFA SCALE UPGRADES | 12/1/2018 | 7/1/2019 | 13207.57 | 957.87 | 0 | 0 | 0 | 14165.44 | 0 | 0 | 0 | 0 | 0 | 0 | 13207.57 | n.m. | 957.87 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14165.44 | n.m.
560 | 117 | ML119EP12 | ML- UNIT 1 INSTRUMENTATION PPB | 2/1/2019 | 2020-06-01 |  | 14112.19 | 533.56 | 0 | 0 | 14645.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 14112.19 | n.m. | 533.56 | n.m. | 0 | n.m. | 0 | n.m. | 14645.75 | n.m.
561 | 117 | ML018EP02 | ML UNIT 1 & UNIT 2 PI SERVERS | 7/1/2018 | 10/1/2019 | 11150.9 | 2153.58 | 0 | 0 | 0 | 13304.48 | 0 | 0 | 0 | 0 | 0 | 0 | 11150.9 | n.m. | 2153.58 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13304.48 | n.m.
562 | 117 | BSPPB0007 | Condenser & Aux. PPB<100k | Charges Began Prior to Jan 2015 | 3/1/2019 |  | 11911.9 | 0 | 0 | 30952.35 | 42864.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 11911.9 | n.m. | 0 | n.m. | 0 | n.m. | 30952.35 | n.m. | 42864.25 | n.m.
563 | 117 | ML119SP09 | REPL DFA FILTER SEPARTOR BAGS | 2/1/2019 | 2020-06-01 |  | 11490.78 | 129.05 | 0 | 0 | 11619.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 11490.78 | n.m. | 129.05 | n.m. | 0 | n.m. | 0 | n.m. | 11619.83 | n.m.
564 | 117 | ML217VP08 | ML RPL#22 ID FAN HYDRAULIC CYL | 12/1/2017 | 7/1/2018 | 252.65 |  | 0 | 0 | 0 | 252.65 | 0 | 0 | 0 | 0 | 0 | 0 | 252.65 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 252.65 | n.m.
565 | 117 | ML218SP27 | ML U2 FOAM SYSTEM DELUGE VALVE | 4/1/2018 | 6/1/2018 | 9696.72 |  | 0 | 0 | 0 | 9696.72 | 0 | 0 | 0 | 0 | 0 | 0 | 9696.72 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9696.72 | n.m.
566 | 117 | ML019EP11 | SULFURIC ACID LEAK DETECTION | 11/1/2019 | 2020-08-01 |  | 8869.5 | 3910.24 | 0 | 0 | 12779.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 8869.5 | n.m. | 3910.24 | n.m. | 0 | n.m. | 0 | n.m. | 12779.74 | n.m.
567 | 117 | ITCB11701 | Kentucky Power - Gen-Miitchell | 11/1/2017 | 3/1/2019 | 6326.74 | 660.68 | 0 | 0 | 14780.78 | 21768.2 | 0 | 0 | 0 | 0 | 0 | 0 | 6326.74 | n.m. | 660.68 | n.m. | 0 | n.m. | 0 | n.m. | 14780.78 | n.m. | 21768.2 | n.m.
568 | 117 | ML219EP23 | MLU2 EXCITER BRUSH RIGGING | 11/1/2019 | 2020-06-01 |  | 8598.74 | 2708.21 | 0 | 0 | 11306.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 8598.74 | n.m. | 2708.21 | n.m. | 0 | n.m. | 0 | n.m. | 11306.95 | n.m.
569 | 117 | ML119EP22 | REPLACE DEMINERALIZER HMI | 12/1/2019 | 2020-03-01 |  | 8279.22 | 754.04 | 0 | 0 | 9033.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 8279.22 | n.m. | 754.04 | n.m. | 0 | n.m. | 0 | n.m. | 9033.26 | n.m.
570 | 117 | ML018MP08 | ML BARGE UNLOADER NETWORK UPGR | 9/1/2018 | 1/1/2019 | 8142.51 | -28.51 | 0 | 0 | 0 | 8114 | 0 | 0 | 0 | 0 | 0 | 0 | 8142.51 | n.m. | -28.51 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8114 | n.m.
571 | 117 | ML018EP18 | ML OUTFALL HEATED SAMPLERS | 11/1/2018 | 1/1/2019 | 7791.16 | -11.01 | 0 | 0 | 0 | 7780.15 | 0 | 0 | 0 | 0 | 0 | 0 | 7791.16 | n.m. | -11.01 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7780.15 | n.m.
572 | 117 | ML218SP26 | ML U2 TURBINE BASEMENT FIRE SY | 12/1/2018 | 3/1/2019 | 19523.31 | -11932.98 | 0 | 0 | 0 | 7590.33 | 0 | 0 | 0 | 0 | 0 | 0 | 19523.31 | n.m. | -11932.98 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7590.33 | n.m.
573 | 117 | ML118SP20 | ML U1 FOAM SYSTEM DELUGE VALVE | 4/1/2018 | 7/1/2018 | 7335.84 |  | 0 | 0 | 0 | 7335.84 | 0 | 0 | 0 | 0 | 0 | 0 | 7335.84 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7335.84 | n.m.
574 | 117 | ML118SP07 | REPL DFA FILTER SEPARTOR BAGS | 11/1/2018 | 4/1/2019 | 7328.23 | -37.51 | 0 | 0 | 0 | 7290.72 | 20586.523 | 21256.207 | 0 | 19472.302 | 17989.552 | 79304.584 | -13258.293 | -64.4% | -21293.717 | -100.2% | 0 | n.m. | -19472.302 | -100% | -17989.552 | -100% | -72013.864 | -90.81%
575 | 117 | MLP19EP05 | ML E POWER CABLE REPLACEMENT | 7/1/2019 | 2020-01-01 |  | 6324.76 | 26.33 | 0 | 0 | 6351.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6324.76 | n.m. | 26.33 | n.m. | 0 | n.m. | 0 | n.m. | 6351.09 | n.m.
576 | 117 | ML218EP06 | ML REPLACE #22 ECH PUMP | 3/1/2018 | 6/1/2018 | 6302.74 |  | 0 | 0 | 0 | 6302.74 | 0 | 0 | 0 | 0 | 0 | 0 | 6302.74 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6302.74 | n.m.
577 | 117 | ML119SP12 | RPL PULVERIZER CLASSIFIER ASBY | 1/1/2019 | 11/1/2019 |  | 6218.19 | 0 | 0 | 0 | 6218.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6218.19 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6218.19 | n.m.
578 | 117 | ML017VP03 | RPL CHEMICAL INJ SKID CPS CLAR | 8/1/2017 | 7/1/2019 | 478.82 | 98.92 | 0 | 0 | 0 | 577.74 | 0 | 0 | 0 | 0 | 0 | 0 | 478.82 | n.m. | 98.92 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 577.74 | n.m.
579 | 117 | ML018MP11 | ML MH BARGE UNLDR AUTO GREASE | 11/1/2018 | 2020-07-01 | 5411.8 | 187.8 | -8414.61 | 0 | 0 | -2815.01 | 0 | 0 | 0 | 0 | 0 | 0 | 5411.8 | n.m. | 187.8 | n.m. | -8414.61 | n.m. | 0 | n.m. | 0 | n.m. | -2815.01 | n.m.
580 | 117 | ML118SP18 | RPL 6" HSO-AUX STEAM-CHEM STA | 3/1/2018 | 7/1/2018 | 5435.17 |  | 0 | 0 | 0 | 5435.17 | 0 | 0 | 0 | 0 | 0 | 0 | 5435.17 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5435.17 | n.m.
581 | 117 | ML219EP19 | MLU2 22B CIRC WTR PMP EJ | 10/1/2019 | 2020-04-01 |  | 5352.45 | 22.66 | 0 | 0 | 5375.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 5352.45 | n.m. | 22.66 | n.m. | 0 | n.m. | 0 | n.m. | 5375.11 | n.m.
582 | 117 | ML019EP04 | ML E HVAC UNIT REPLACEMENTS | 12/1/2019 | 2020-10-01 |  | 5092.33 | 9002.7 | 0 | 0 | 14095.03 | 0 | 24685.287 | 0 | 0 | 0 | 24685.287 | 0 | n.m. | -19592.957 | -79.37% | 9002.7 | n.m. | 0 | n.m. | 0 | n.m. | -10590.257 | -42.9%
583 | 117 | ML118SP21 | ML #12F BURNER LINE SLIP JOINT | 4/1/2018 | 10/1/2018 | 5090.81 |  | 0 | 0 | 0 | 5090.81 | 0 | 0 | 0 | 0 | 0 | 0 | 5090.81 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5090.81 | n.m.
584 | 117 | ML020SP01 | ML MITCHELL DSI PROJECT | 12/1/2019 | 2022-09-01 |  | 4797.62 | 37378.57 | 492740.15 | -511091.48 | 23824.86 | 0 | 0 | 3241167.06 | 4777.559 | 2213596.8054 | 5459541.4244 | 0 | n.m. | 4797.62 | n.m. | -3203788.49 | -98.85% | 487962.591 | 10214% | -2724688.2854 | -123.1% | -5435716.5644 | -99.56%
585 | 117 | ML019EP09 | ML AMMONIA TANK N2 BLANKETING | 3/1/2019 | 2020-01-01 |  | 4076.62 | -40.6 | 0 | 0 | 4036.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 4076.62 | n.m. | -40.6 | n.m. | 0 | n.m. | 0 | n.m. | 4036.02 | n.m.
586 | 117 | ML218SP18 | ML #22 RECEIVING HOPPER REPLAC | 4/1/2018 | 5/1/2018 | 4075.1 |  | 0 | 0 | 0 | 4075.1 | 0 | 0 | 0 | 0 | 0 | 0 | 4075.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4075.1 | n.m.
587 | 117 | ML118VP06 | ML RPL #12 ID FAN OUTLET EJ | 4/1/2018 | 6/1/2018 | 4049.74 |  | 0 | 0 | 0 | 4049.74 | 0 | 0 | 0 | 0 | 0 | 0 | 4049.74 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4049.74 | n.m.
588 | 117 | ML018VP06 | ML SILICON CARBIDE AR PUMP | 12/1/2018 | 2020-03-01 | 3372.28 | 380.05 | 10.31 | 0 | 0 | 3762.64 | 0 | 0 | 0 | 0 | 0 | 0 | 3372.28 | n.m. | 380.05 | n.m. | 10.31 | n.m. | 0 | n.m. | 0 | n.m. | 3762.64 | n.m.
589 | 117 | ML219EP15 | ML219 22 CIRC MTR DIODE RING | 10/1/2019 | 2020-06-01 |  | 3664.13 | 431.32 | 0 | 0 | 4095.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 3664.13 | n.m. | 431.32 | n.m. | 0 | n.m. | 0 | n.m. | 4095.45 | n.m.
590 | 117 | ML219EP22 | REPLACE DEMINERALIZER HMI | 9/1/2019 | 2020-10-01 |  | 3566.42 | 8648.48 | 0 | 0 | 12214.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 3566.42 | n.m. | 8648.48 | n.m. | 0 | n.m. | 0 | n.m. | 12214.9 | n.m.
591 | 117 | ML018MP10 | ML MT HANDLING MOBILE HEATERS | 11/1/2018 | 4/1/2019 | 3102.67 | 210.07 | 0 | 0 | 0 | 3312.74 | 0 | 0 | 0 | 0 | 0 | 0 | 3102.67 | n.m. | 210.07 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3312.74 | n.m.
592 | 117 | ML018NP03 | ML HAUL ROAD RELOCATION PRELIM | 11/1/2018 | 2022-09-01 | 234.49 | 2939.48 | 2009.55 | 112.3 | -5295.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 234.49 | n.m. | 2939.48 | n.m. | 2009.55 | n.m. | 112.3 | n.m. | -5295.82 | n.m. | 0 | n.m.
593 | 117 | BSPPBS333 | VOLT VAR PROJECT | 8/1/2017 | 7/1/2018 | 71.07 |  | 0 | 0 | 0 | 71.07 | 0 | 0 | 0 | 0 | 0 | 0 | 71.07 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 71.07 | n.m.
594 | 117 | ML118SP11 | DFA EXHAUST BLOWER REPLACEMENT | 10/1/2018 | 4/1/2019 | 2262.25 | -29.27 | 0 | 0 | 0 | 2232.98 | 0 | 0 | 0 | 0 | 0 | 0 | 2262.25 | n.m. | -29.27 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2232.98 | n.m.
595 | 117 | ML017EP09 | ML U1/U2 VOLT / VAR COMPLIANCE | 7/1/2017 | 7/1/2018 | 168.32 |  | 0 | 0 | 0 | 168.32 | 0 | 0 | 0 | 0 | 0 | 0 | 168.32 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 168.32 | n.m.
596 | 117 | ML117SP14 | ML UNIT 1 ECONOMIZER EJ | 10/1/2017 | 5/1/2018 | 38.08 |  | 0 | 0 | 0 | 38.08 | 0 | 0 | 0 | 0 | 0 | 0 | 38.08 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 38.08 | n.m.
597 | 117 | ML119SP11 | ML #12 RECEIVING HOPPER REPLAC | 4/1/2019 | 10/1/2019 |  | 1510.43 | 0 | 0 | 0 | 1510.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1510.43 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1510.43 | n.m.
598 | 117 | BSPPBS340 | REPLACE 15 BREAKERS "B" BUS | 11/1/2018 | 11/1/2019 | 337.41 | -337.41 | 0 | 0 | 177859.53 | 177859.53 | 0 | 0 | 720573.915 | 0 | 541493.22 | 1262067.135 | 337.41 | n.m. | -337.41 | n.m. | -720573.915 | -100% | 0 | n.m. | -363633.69 | -67.15% | -1084207.605 | -85.91%
599 | 117 | ML118VP08 | ML RPL#12 ID FAN HYDRAULIC CYL | 4/1/2018 | 11/1/2018 | -1.7764e-15 |  | 0 | 0 | 0 | -1.7764e-15 | 0 | 0 | 0 | 0 | 0 | 0 | -1.7764e-15 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1.7764e-15 | n.m.
600 | 117 | BSPPBS339 | REPLACE 15 BREAKERS "A" BUS | 11/1/2018 | 11/1/2019 | 253.06 | -253.06 | 0 | 0 | 179475.82 | 179475.82 | 0 | 0 | 720573.915 | 0 | 541493.22 | 1262067.135 | 253.06 | n.m. | -253.06 | n.m. | -720573.915 | -100% | 0 | n.m. | -362017.4 | -66.86% | -1082591.315 | -85.78%
601 | 117 | GENREB117 | Generation Rebate Program | 1/1/2018 | 1/1/2018 | -1292.95 |  | 0 | 0 | 0 | -1292.95 | 0 | 0 | 0 | 0 | 0 | 0 | -1292.95 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1292.95 | n.m.
602 | 117 | BSPPBS367 | Replace TR 2SCR-2F Transformer | 2020-12-01 | 2022-05-01 |  |  | 313531.47 | 409690.95 | 21363.7 | 744586.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 313531.47 | n.m. | 409690.95 | n.m. | 21363.7 | n.m. | 744586.12 | n.m.
603 | 117 | ML020VP01 | ML - NON OUTAGE PPB FGD | 2020-01-01 | 2021-09-01 |  |  | 298289.01 | 191104.79 |  | 489393.8 | 0 | 0 | 278251.826 | 0 | 0 | 278251.826 | 0 | n.m. | 0 | n.m. | 20037.184 | 7.201% | 191104.79 | n.m. | 0 | n.m. | 211141.974 | 75.88%
604 | 117 | MLP20EP20 | ML E U2 Cooling Tower Monitors | 2020-06-01 | 2021-01-01 |  |  | 365708.84 | 16.04 |  | 365724.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 365708.84 | n.m. | 16.04 | n.m. | 0 | n.m. | 365724.88 | n.m.
605 | 117 | MLPMPBELT | ML M Conveyor Belt Rplcmts | 2020-12-01 | 2022-09-01 |  |  | 59225 | 171301.29 | 84040.51 | 314566.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 59225 | n.m. | 171301.29 | n.m. | 84040.51 | n.m. | 314566.8 | n.m.
606 | 117 | MLPEPPUMP | ML E Pump Replacements | 2020-12-01 | 2022-09-01 |  |  | 31830.32 | 215952.54 | 46467.2 | 294250.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 31830.32 | n.m. | 215952.54 | n.m. | 46467.2 | n.m. | 294250.06 | n.m.
607 | 117 | MLP20SP06 | ML S Coal Burner Replacements | 2020-07-01 | 2021-09-01 |  |  | 158031.76 | 112259.11 |  | 270290.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 158031.76 | n.m. | 112259.11 | n.m. | 0 | n.m. | 270290.87 | n.m.
608 | 117 | IT117CCIC | Cloud Computing Imp Cost-KyP G | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 52536.79 | 69545.76 | 77415.75 | 199498.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 52536.79 | n.m. | 69545.76 | n.m. | 77415.75 | n.m. | 199498.3 | n.m.
609 | 117 | ML220VP01 | ML U2 ID Fan Hub Shell Replace | 2020-01-01 | 2021-03-01 |  |  | 250626.75 | -2500.9 |  | 248125.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 250626.75 | n.m. | -2500.9 | n.m. | 0 | n.m. | 248125.85 | n.m.
610 | 117 | ML018SP02 | PULVERIZER REBUILD CAPITAL(#YY | 2020-05-01 | 2020-10-01 |  |  | 247823.14 |  |  | 247823.14 | 0 | 182838.616 | 225842.187 | 188053.648 | 86355.967 | 683090.418 | 0 | n.m. | -182838.616 | -100% | 21980.953 | 9.733% | -188053.648 | -100% | -86355.967 | -100% | -435267.278 | -63.72%
611 | 117 | MLPNPTOOL | ML N Capital Tool Purchases | 2020-11-01 | 2022-09-01 |  |  | 28611.95 | 127103.11 | 38238.84 | 193953.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 28611.95 | n.m. | 127103.11 | n.m. | 38238.84 | n.m. | 193953.9 | n.m.
612 | 117 | BSPPB0009 | Effluent WW Treating PPB<100k | 2020-03-01 | Charges Continued After Dec 2022 |  |  | 2372.86 | 17236.19 | 65649.67 | 85258.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2372.86 | n.m. | 17236.19 | n.m. | 65649.67 | n.m. | 85258.72 | n.m.
613 | 117 | MLP20MP06 | ML M Pump Replacements MH Cap | 2020-02-01 | 2021-06-01 |  |  | 48490.27 | 47933.04 |  | 96423.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 48490.27 | n.m. | 47933.04 | n.m. | 0 | n.m. | 96423.31 | n.m.
614 | 117 | MLP20EP12 | ML E Control Replacements | 2020-07-01 | 2022-04-01 |  |  | 12763.4 | 67225.95 | 8482.98 | 88472.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 12763.4 | n.m. | 67225.95 | n.m. | 8482.98 | n.m. | 88472.33 | n.m.
615 | 117 | MLPVPPUMP | ML V FGD CPS Pumps | 2020-11-01 | 2022-09-01 |  |  | 7534.48 | 103798.83 | -23364.12 | 87969.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7534.48 | n.m. | 103798.83 | n.m. | -23364.12 | n.m. | 87969.19 | n.m.
616 | 117 | MLP20VP01 | ML V FGD Non Outage Capital | 2020-02-01 | 2022-09-01 |  |  | 108567.3 | 4959.75 | -27877.28 | 85649.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 108567.3 | n.m. | 4959.75 | n.m. | -27877.28 | n.m. | 85649.77 | n.m.
617 | 117 | MLP20SP09 | ML S U2 Up Blr Vent Fan Rplc | 2020-10-01 | 2022-02-01 |  |  | 53688.48 | 16971.97 | 7272.58 | 77933.03 | 0 | 0 | 0 | 11.351 | 0 | 11.351 | 0 | n.m. | 0 | n.m. | 53688.48 | n.m. | 16960.619 | 149420% | 7272.58 | n.m. | 77921.679 | 686474%
618 | 117 | MLP20EP06 | ML E Valve Replacements Cptl | 2020-01-01 | 2021-06-01 |  |  | 50420.08 | 26726.64 |  | 77146.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 50420.08 | n.m. | 26726.64 | n.m. | 0 | n.m. | 77146.72 | n.m.
619 | 117 | MLP20EP02 | ML-E-MOTOR REWINDS/REPLACEMENT | 2020-02-01 | 2021-08-01 |  |  | 71095.69 | 2645.52 |  | 73741.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 71095.69 | n.m. | 2645.52 | n.m. | 0 | n.m. | 73741.21 | n.m.
620 | 117 | MLP20EP07 | ML E Carbon Filter Replacement | 2020-09-01 | 2021-04-01 |  |  | 67056.05 | 5150.55 |  | 72206.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 67056.05 | n.m. | 5150.55 | n.m. | 0 | n.m. | 72206.6 | n.m.
621 | 117 | MLP20MP08 | ML M Gypsum Trn Hse Walkways | 2020-08-01 | 2021-04-01 |  |  | 61058.42 | 10866.33 |  | 71924.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 61058.42 | n.m. | 10866.33 | n.m. | 0 | n.m. | 71924.75 | n.m.
622 | 117 | MLP20MP02 | MLP MH CONVEYOR BELT REPLACE | 2020-04-01 | 2021-06-01 |  |  | 56785.97 | -575.02 |  | 56210.95 | 0 | 0 | 270522.629 | 14.746 | 0 | 270537.375 | 0 | n.m. | 0 | n.m. | -213736.659 | -79.01% | -589.766 | -3999% | 0 | n.m. | -214326.425 | -79.22%
623 | 117 | ML020MP01 | ML U0 Conveyor Belt Rplcmts | 2020-03-01 | 2021-03-01 |  |  | 11594.87 | 36624.73 |  | 48219.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 11594.87 | n.m. | 36624.73 | n.m. | 0 | n.m. | 48219.6 | n.m.
624 | 117 | MLP20EP03 | ML E Pump Replacements (Cap) | 2020-02-01 | 2021-11-01 |  |  | 17786.25 | 28947.54 |  | 46733.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 17786.25 | n.m. | 28947.54 | n.m. | 0 | n.m. | 46733.79 | n.m.
625 | 117 | MLP20EP13 | ML E Monitoring Systems | 2020-09-01 | 2021-06-01 |  |  | 34264.19 | 652.43 |  | 34916.62 | 0 | 0 | 0 | 0 | 11579.2557 | 11579.2557 | 0 | n.m. | 0 | n.m. | 34264.19 | n.m. | 652.43 | n.m. | -11579.2557 | -100% | 23337.3643 | 201.5%
626 | 117 | MLP20NP01 | ML CAPITAL TOOLS | 2020-03-01 | 2022-04-01 |  |  | 23634.94 | 11202.6 | 78.02 | 34915.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 23634.94 | n.m. | 11202.6 | n.m. | 78.02 | n.m. | 34915.56 | n.m.
627 | 117 | MLP20VP03 | ML V FGD and CPS Pumps Capital | 2020-03-01 | 2021-03-01 |  |  | 34595.13 | -19.34 |  | 34575.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 34595.13 | n.m. | -19.34 | n.m. | 0 | n.m. | 34575.79 | n.m.
628 | 117 | MLP20SP05 | ML S Coal Silo Load Cells | 2020-07-01 | 2021-02-01 |  |  | 31667.65 | -159.45 |  | 31508.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 31667.65 | n.m. | -159.45 | n.m. | 0 | n.m. | 31508.2 | n.m.
629 | 117 | MLPEPTANK | ML E Tank Replacements | 2020-11-01 | 2021-06-01 |  |  | 16047.93 | 15100.81 |  | 31148.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 16047.93 | n.m. | 15100.81 | n.m. | 0 | n.m. | 31148.74 | n.m.
630 | 117 | MLP20SP04 | ML S Lime Inj Load Cell U1 | 2020-03-01 | 2020-06-01 |  |  | 29671.07 |  |  | 29671.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 29671.07 | n.m. | 0 | n.m. | 0 | n.m. | 29671.07 | n.m.
631 | 117 | ML019SP02 | ML PULVERIZER REBUILD CAP(#YY | 2020-03-01 | 2020-08-01 |  |  | 25207.21 |  |  | 25207.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 25207.21 | n.m. | 0 | n.m. | 0 | n.m. | 25207.21 | n.m.
632 | 117 | MLP20NP02 | ML N Security Gates | 2020-03-01 | 2021-02-01 |  |  | 19208.76 | 4121.63 |  | 23330.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 19208.76 | n.m. | 4121.63 | n.m. | 0 | n.m. | 23330.39 | n.m.
633 | 117 | MLP20EP09 | ML E Transmitter Replcmts Cap | 2020-03-01 | 2022-09-01 |  |  | 14058.61 | 20589.19 | -12214.95 | 22432.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 14058.61 | n.m. | 20589.19 | n.m. | -12214.95 | n.m. | 22432.85 | n.m.
634 | 117 | MLP20VP04 | ML V CO2 Monitors | 2020-06-01 | 2021-02-01 |  |  | 22588.1 | -305.13 |  | 22282.97 | 0 | 0 | 0 | 13813.231 | 0 | 13813.231 | 0 | n.m. | 0 | n.m. | 22588.1 | n.m. | -14118.361 | -102.2% | 0 | n.m. | 8469.739 | 61.32%
635 | 117 | ML119VP07 | RPL 11 ID FAN INLET HORIZ EJ | 2020-10-01 | 2021-01-01 |  |  | 19952.45 | 747.43 |  | 20699.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 19952.45 | n.m. | 747.43 | n.m. | 0 | n.m. | 20699.88 | n.m.
636 | 117 | MLP20SP07 | ML S Expansion Joint Replcmts | 2020-04-01 | 2021-06-01 |  |  | 18771.11 | 1610.74 |  | 20381.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 18771.11 | n.m. | 1610.74 | n.m. | 0 | n.m. | 20381.85 | n.m.
637 | 117 | MLP20MP05 | ML U0 Limestone Stamler Cap | 2020-02-01 | 2020-06-01 |  |  | 12708.31 |  |  | 12708.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 12708.31 | n.m. | 0 | n.m. | 0 | n.m. | 12708.31 | n.m.
638 | 117 | MLP20EP10 | ML E Battery Charger Replace | 2020-02-01 | 2021-08-01 |  |  | 2922.86 | 8669.44 |  | 11592.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2922.86 | n.m. | 8669.44 | n.m. | 0 | n.m. | 11592.3 | n.m.
639 | 117 | MLP20MP09 | ML M Control Replacements | 2020-08-01 | 2021-01-01 |  |  | 11565.5 | 16.03 |  | 11581.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 11565.5 | n.m. | 16.03 | n.m. | 0 | n.m. | 11581.53 | n.m.
640 | 117 | MLPSPLIME | ML S Lime Injection Equipment | 2020-12-01 | 2021-01-01 |  |  | 10261.02 | 274.09 |  | 10535.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 10261.02 | n.m. | 274.09 | n.m. | 0 | n.m. | 10535.11 | n.m.
641 | 117 | MLP20SP01 | ML SAFETY VALVES (4) | 2020-07-01 | 2021-03-01 |  |  | 8561.68 | -90.2 |  | 8471.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 8561.68 | n.m. | -90.2 | n.m. | 0 | n.m. | 8471.48 | n.m.
642 | 117 | MLP20VP02 | ML V Oxidation Air Blower Cap | 2020-03-01 | 2021-06-01 |  |  | 7133.13 | 1329.31 |  | 8462.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7133.13 | n.m. | 1329.31 | n.m. | 0 | n.m. | 8462.44 | n.m.
643 | 117 | MLP800MHZ | ML E 800MHz Radios | 2020-12-01 | 2021-01-01 |  |  | 7445.05 | 31.21 |  | 7476.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 7445.05 | n.m. | 31.21 | n.m. | 0 | n.m. | 7476.26 | n.m.
644 | 117 | MLP20SP08 | ML S Burner Drive Replacements | 2020-07-01 | 2020-10-01 |  |  | 6444.87 |  |  | 6444.87 | 0 | 0 | 0 | 14.767 | 0 | 14.767 | 0 | n.m. | 0 | n.m. | 6444.87 | n.m. | -14.767 | -100% | 0 | n.m. | 6430.103 | 43544%
645 | 117 | MLP20MP07 | ML M Control Upgrades Matl Han | 2020-03-01 | 2021-01-01 |  |  | 3090.25 | -33.23 |  | 3057.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 3090.25 | n.m. | -33.23 | n.m. | 0 | n.m. | 3057.02 | n.m.
646 | 117 | MLP19SP01 | ML SAFETY VALVES ( 4 ) | 2020-03-01 | 2020-08-01 |  |  | 2432.05 |  |  | 2432.05 | 0 | 91461.481 | 17.911 | 0 | 0 | 91479.392 | 0 | n.m. | -91461.481 | -100% | 2414.139 | 13479% | 0 | n.m. | 0 | n.m. | -89047.342 | -97.34%
647 | 117 | MLP20SP03 | ML S Pump Replacements (Cap) | 2020-02-01 | 2020-06-01 |  |  | 1221.64 |  |  | 1221.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1221.64 | n.m. | 0 | n.m. | 0 | n.m. | 1221.64 | n.m.
648 | 117 | MLPVPIDFB | ML V ID FAN BLADES | 2020-12-01 | 2021-02-01 |  |  | 1770 | -1769.49 | 0 | 0.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 1770 | n.m. | -1769.49 | n.m. | 0 | n.m. | 0.51 | n.m.
649 | 117 | ML119VP04 | RPL #11 ID FAN OUTLET HUB CYL | 2020-12-01 | 2022-04-01 |  |  | 3802 | -3800.93 | -1.07 | -2.9088e-13 | 0 | 33243.385 | 22449.833 | 0 | 0 | 55693.218 | 0 | n.m. | -33243.385 | -100% | -18647.833 | -83.06% | -3800.93 | n.m. | -1.07 | n.m. | -55693.218 | -100%
650 | 117 | ML1GSUF1C | ML1 Ph 1 GSU Repl w Amos Spare | 2021-04-01 | 2022-04-01 |  |  |  | 1233464.587 | 4646.06 | 1238110.647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1233464.587 | n.m. | 4646.06 | n.m. | 1238110.647 | n.m.
651 | 117 | MLPSPPULV | ML S Pulverizer Rebuilds | 2021-03-01 | 2022-09-01 |  |  |  | 640142.42 | -162208.52 | 477933.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 640142.42 | n.m. | -162208.52 | n.m. | 477933.9 | n.m.
652 | 117 | MLPEPCTRL | ML E Control Upgds Rplcmts | 2021-02-01 | 2022-09-01 |  |  |  | 275314.62 | 20423.84 | 295738.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 275314.62 | n.m. | 20423.84 | n.m. | 295738.46 | n.m.
653 | 117 | BSPPBS369 | HEP Reheat Steam Line Insul | 2021-10-01 | 2022-02-01 |  |  |  | 252128.17 | 10331.58 | 262459.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 252128.17 | n.m. | 10331.58 | n.m. | 262459.75 | n.m.
654 | 117 | MLPEPVALV | ML E Valve Replacements | 2021-03-01 | 2022-09-01 |  |  |  | 109612.3 | 27606.31 | 137218.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 109612.3 | n.m. | 27606.31 | n.m. | 137218.61 | n.m.
655 | 117 | MLPSPEJNT | ML S Expansion Joint Repl | 2021-06-01 | 2022-09-01 |  |  |  | 106646.01 | 773.4 | 107419.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 106646.01 | n.m. | 773.4 | n.m. | 107419.41 | n.m.
656 | 117 | MLPMPECRN | ML M ECrane Capital Work | 2021-03-01 | 2022-09-01 |  |  |  | 104471.76 | -6.62 | 104465.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 104471.76 | n.m. | -6.62 | n.m. | 104465.14 | n.m.
657 | 117 | ML2EP1701 | ML2 HIGH ENERGY PIPING | 2021-02-01 | 2021-06-01 |  |  |  | 94366.55 |  | 94366.55 | 204728.09 | 0 | 0 | 210442.855 | 0 | 415170.945 | -204728.09 | -100% | 0 | n.m. | 0 | n.m. | -116076.305 | -55.16% | 0 | n.m. | -320804.395 | -77.27%
658 | 117 | MLPVPCNTM | ML V Containment Systems | 2021-04-01 | 2022-01-01 |  |  |  | 87819.68 | -1250.58 | 86569.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 87819.68 | n.m. | -1250.58 | n.m. | 86569.1 | n.m.
659 | 117 | MLPSPBRNE | ML S Coal Burner Exp Joint Rpl | 2021-06-01 | 2022-02-01 |  |  |  | 73963.64 | 265.36 | 74229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 73963.64 | n.m. | 265.36 | n.m. | 74229 | n.m.
660 | 117 | MLPEPMOTR | ML E Motor Rewind/Rplc >10HP | 2021-07-01 | 2022-09-01 |  |  |  | 53242.22 | 8463.96 | 61706.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 53242.22 | n.m. | 8463.96 | n.m. | 61706.18 | n.m.
661 | 117 | MLPMPDRNG | ML M Drainage Projects (Cap) | 2021-11-01 | 2022-01-01 |  |  |  | 60490.8 | -382.65 | 60108.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 60490.8 | n.m. | -382.65 | n.m. | 60108.15 | n.m.
662 | 117 | MLPSPBRNN | ML S Burner Nozzle Rplcmt | 2021-04-01 | 2022-09-01 |  |  |  | 114884.97 | -65340 | 49544.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 114884.97 | n.m. | -65340 | n.m. | 49544.97 | n.m.
663 | 117 | MLPEPSWGR | ML E Switchgear Breaker Rplcmt | 2021-07-01 | 2022-09-01 |  |  |  | 45791.93 | 2780.98 | 48572.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45791.93 | n.m. | 2780.98 | n.m. | 48572.91 | n.m.
664 | 117 | MLPSPCLGR | ML S Clinker Grinder Replace | 2021-01-01 | 2021-03-01 |  |  |  | 46005.93 |  | 46005.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 46005.93 | n.m. | 0 | n.m. | 46005.93 | n.m.
665 | 117 | MLPVPEJNT | ML V FGD CPS Expansion Joints | 2021-03-01 | 2022-09-01 |  |  |  | 45131.93 | 57.25 | 45189.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 45131.93 | n.m. | 57.25 | n.m. | 45189.18 | n.m.
666 | 117 | MLPSPDUCT | ML S Duct Lag Insul Replace | 2021-04-01 | 2021-06-01 |  |  |  | 40527.65 |  | 40527.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 40527.65 | n.m. | 0 | n.m. | 40527.65 | n.m.
667 | 117 | MLPMPPUMP | ML M CY Pump Replace Cap >10HP | 2021-05-01 | 2022-09-01 |  |  |  | 26891.08 | 12804.6 | 39695.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 26891.08 | n.m. | 12804.6 | n.m. | 39695.68 | n.m.
668 | 117 | MLPEPTRMT | ML E Transmitter Replacements | 2021-02-01 | 2022-09-01 |  |  |  | 25384.46 | 4923.68 | 30308.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 25384.46 | n.m. | 4923.68 | n.m. | 30308.14 | n.m.
669 | 117 | MLPEPSERV | ML E Server Replacements | 2021-02-01 | 2022-09-01 |  |  |  | 29237.51 | 62.84 | 29300.35 | 0 | 0 | 0 | 0 | 36153.348 | 36153.348 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 29237.51 | n.m. | -36090.508 | -99.83% | -6852.998 | -18.96%
670 | 117 | MLPEPLGHT | ML E LIGHTING REPLACEMENTS | 2021-11-01 | 2022-01-01 |  |  |  | 20225.69 | 3523.57 | 23749.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20225.69 | n.m. | 3523.57 | n.m. | 23749.26 | n.m.
671 | 117 | MLPSPDFAF | ML S Dry Fly Ash Fltr Sep Bags | 2021-04-01 | 2022-09-01 |  |  |  | 15103.85 | 2884.98 | 17988.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15103.85 | n.m. | 2884.98 | n.m. | 17988.83 | n.m.
672 | 117 | MLPSPVALV | ML S Blr Brnr Steam Valve Repl | 2021-04-01 | 2022-09-01 |  |  |  | 23428.18 | -5526.57 | 17901.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23428.18 | n.m. | -5526.57 | n.m. | 17901.61 | n.m.
673 | 117 | MLPVPTRMT | ML V FGD CPS Env Transmitters | 2021-05-01 | 2022-09-01 |  |  |  | 11078.23 | 5896.27 | 16974.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11078.23 | n.m. | 5896.27 | n.m. | 16974.5 | n.m.
674 | 117 | MLPVPVALV | ML V FGD CPS Valve Replace | 2021-03-01 | 2022-09-01 |  |  |  | 7174.35 | 5217.97 | 12392.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7174.35 | n.m. | 5217.97 | n.m. | 12392.32 | n.m.
675 | 117 | MLPSPASHL | ML S Ash Line Remove Replace | 2021-11-01 | 2022-09-01 |  |  |  | 12330.22 | 15.94 | 12346.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 12330.22 | n.m. | 15.94 | n.m. | 12346.16 | n.m.
676 | 117 | MLPEPCABL | ML E Cable Replacements | 2021-04-01 | 2022-07-01 |  |  |  | 7190.88 | 3115.46 | 10306.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7190.88 | n.m. | 3115.46 | n.m. | 10306.34 | n.m.
677 | 117 | MLPNPSECU | ML N Security Projects (Cap) | 2021-11-01 | 2022-09-01 |  |  |  | 33342.56 | -24612.89 | 8729.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33342.56 | n.m. | -24612.89 | n.m. | 8729.67 | n.m.
678 | 117 | MLPVPHEAT | ML V FGD CPS Heaters | 2021-03-01 | 2021-09-01 |  |  |  | 6702.58 |  | 6702.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6702.58 | n.m. | 0 | n.m. | 6702.58 | n.m.
679 | 117 | BSP800MHZ | Upgrades to 800MHz Radio Equip | 2021-06-01 | 2022-01-01 |  |  |  | 661.14 | 0.99 | 662.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 661.14 | n.m. | 0.99 | n.m. | 662.13 | n.m.
680 | 117 | MLPEPBLWR | ML E Blower Vent Fan Repl | 2021-08-01 | 2022-01-01 |  |  |  | 485.65 | -8.45 | 477.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 485.65 | n.m. | -8.45 | n.m. | 477.2 | n.m.
681 | 117 | ML2E24C04 | ML2 E COOLING TOWER COMPONENTS | 2021-10-01 | 2022-09-01 |  |  |  | 701312.84 | -701312.84 | 1.1642e-09 | 0 | 0 | 348603.978 | 2112225.343 | 2356213.2165 | 4817042.5375 | 0 | n.m. | 0 | n.m. | -348603.978 | -100% | -1410912.503 | -66.8% | -3057526.0565 | -129.8% | -4817042.5375 | -100%
682 | 117 | ML1VC1801 | Mitchell Catalyst Replacement | 2021-01-01 | 2022-09-01 |  |  |  | 1350365.43 | -1350365.43 | 0 | 0 | 323676.019 | 399759.816 | 1001599.263 | 0 | 1725035.098 | 0 | n.m. | -323676.019 | -100% | -399759.816 | -100% | 348766.167 | 34.82% | -1350365.43 | n.m. | -1725035.098 | -100%
683 | 117 | ML2VC1801 | ML2 V CATALYST REPLACEMENT 4 L | 2021-08-01 | 2022-09-01 |  |  |  | 295585.75 | -295585.75 | 0 | 0 | 0 | 0 | 240565.921 | 817535.1645 | 1058101.0855 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 55019.829 | 22.87% | -1113120.9145 | -136.2% | -1058101.0855 | -100%
684 | 117 | 000022309 | ML U2 ESP Upgrades | 2021-08-01 | 2022-09-01 |  |  |  | 653384.84 | -653384.84 | 0 | 0 | 39617.141 | 545630.944 | 74366.303 | 3351569.4703 | 4011183.8583 | 0 | n.m. | -39617.141 | -100% | -545630.944 | -100% | 579018.537 | 778.6% | -4004954.3103 | -119.5% | -4011183.8583 | -100%
685 | 117 | ML220SC01 | AIR HEATER BASKET REPLACEMENT | 2021-08-01 | 2022-09-01 |  |  |  | 1111730.68 | -1111730.68 | 0 | 0 | 0 | 258800.446 | 197483.405 | 1603173.411 | 2059457.262 | 0 | n.m. | 0 | n.m. | -258800.446 | -100% | 914247.275 | 462.9% | -2714904.091 | -169.3% | -2059457.262 | -100%
686 | 117 | MLPVPAIRC | ML V FGD AIR COMPRESSOR REPLAC | 2021-12-01 | 2022-09-01 |  |  |  | 49943.37 | -49943.37 | -1.6735e-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49943.37 | n.m. | -49943.37 | n.m. | -1.6735e-10 | n.m.
687 | 117 | MLP20EP01 | ML INST NEW NOSE LINER PA FANS | 2021-12-01 | 2022-09-01 |  |  |  | 399.23 | -399.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 399.23 | n.m. | -399.23 | n.m. | 0 | n.m.
688 | 117 | MLLPC0ELG | ML PCC U0 ELG Compliance - 117 | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 10010726.583 | 10010726.583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10010726.583 | n.m. | 10010726.583 | n.m.
689 | 117 | MLLPPBSHD | ML Minor PPB Liberty Shadow | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 4763845.21 | 4763845.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4763845.21 | n.m. | 4763845.21 | n.m.
690 | 117 | MLLPC0LIM | ML PCC U0 Lime Conversion 117 | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 2484613.87 | 2484613.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2484613.87 | n.m. | 2484613.87 | n.m.
691 | 117 | MLLPC2CTC | ML PCC U2 Cooling Twr Cmp 117 | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 2830874.35 | 2830874.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2830874.35 | n.m. | 2830874.35 | n.m.
692 | 117 | MLLPC2ESP | ML PCC U2 ESP Upgrades 117 | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 2026569.4 | 2026569.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2026569.4 | n.m. | 2026569.4 | n.m.
693 | 117 | MLLSC2AHB | ML S U2 Air Htr Bskt Rplc Lbty | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 2091455.35 | 2091455.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2091455.35 | n.m. | 2091455.35 | n.m.
694 | 117 | MLLPC1CL4 | ML PCC U1 SCR Cat Layer 4 117 | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 1357439.4 | 1357439.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1357439.4 | n.m. | 1357439.4 | n.m.
695 | 117 | MLLVC2CL4 | ML V U2 Cat Layer 4 Rplc Lbty | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 1284801.81 | 1284801.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1284801.81 | n.m. | 1284801.81 | n.m.
696 | 117 | BS0000040 | Rewedge Generator U1 | 2022-10-01 | Charges Continued After Dec 2022 |  |  |  |  | 944205.4 | 944205.4 | 0 | 0 | 0 | 0 | 286217.845 | 286217.845 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 657987.555 | 229.9% | 657987.555 | 229.9%
697 | 117 | MLLSC1AHB | ML S U1 Air Htr Bskt Rplc Lbty | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 918461.41 | 918461.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 918461.41 | n.m. | 918461.41 | n.m.
698 | 117 | 117KYLSBO | Gen KY Lease Buyout | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 451756.11 | 451756.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 451756.11 | n.m. | 451756.11 | n.m.
699 | 117 | MLLEP2LAI | ML E U2 LPA Turb Insp Liberty | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 408194.38 | 408194.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 408194.38 | n.m. | 408194.38 | n.m.
700 | 117 | MLLEP2LBI | ML E U2 LPB Turb Insp Liberty | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 347125.58 | 347125.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 347125.58 | n.m. | 347125.58 | n.m.
701 | 117 | MLLSP2LSO | ML S U2 Lwr Sdwl Weld Ovly Lby | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 236083.66 | 236083.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 236083.66 | n.m. | 236083.66 | n.m.
702 | 117 | MLPMPHEAT | ML U0 LS TUNNEL HEAT TRACE HTR | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 49303.8 | 49303.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 49303.8 | n.m. | 49303.8 | n.m.
703 | 117 | ITCBLBRTY | KENTUCKY POWER LIBERTY | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 42280.1 | 42280.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 42280.1 | n.m. | 42280.1 | n.m.
704 | 117 | BSPPBS358 | BS1 REPL BLR COMBUSTION COILS | 2022-11-01 | Charges Continued After Dec 2022 |  |  |  |  | 39087.88 | 39087.88 | 0 | 0 | 113532.33 | 0 | 77534.819 | 191067.149 | 0 | n.m. | 0 | n.m. | -113532.33 | -100% | 0 | n.m. | -38446.939 | -49.59% | -151979.269 | -79.54%
705 | 117 | MLPSPFANS | ML S BLOWERS FANS ETC | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 13617.6 | 13617.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13617.6 | n.m. | 13617.6 | n.m.
706 | 117 | MLLSHSVB | 2021 Gen Plt Cap Blkt - KYPC-G | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 6075.85 | 6075.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6075.85 | n.m. | 6075.85 | n.m.
707 | 117 | MLPVPOTHR | FGD OTHER NON OUTAGE CAPITAL | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 4781.09 | 4781.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4781.09 | n.m. | 4781.09 | n.m.
708 | 117 | MLLSTORB | Gen Plt Blkt KY-G Mitchell117 | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 694.05 | 694.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 694.05 | n.m. | 694.05 | n.m.
709 | 117 | Other Budgeted Projects |  | Other | Other | 0 | 0 | 0 | 0 | 0 | 0 | 16588325.68 | 14893555.841 | 16823112.79 | 16074007.68 | 20567965.803 | 84946967.794 | -16588325.68 | -100% | -14893555.841 | -100% | -16823112.79 | -100% | -16074007.68 | -100% | -20567965.803 | -100% | -84946967.794 | -100%
710 | 117 Total |  |  |  |  | 32001996.29 | 29935961.239 | 12568377.776 | 19029604.457 | 24418704.97 | 117954644.732 | 38973204.694 | 34083480.815 | 28410698.052 | 31548078.317 | 34523302.1236 | 167538764.0016 | -6971208.404 | -17.89% | -4147519.576 | -12.17% | -15842320.276 | -55.76% | -12518473.86 | -39.68% | -10104597.1536 | -29.27% | -49584119.2696 | -29.6%
711 | 180 | P16113009 | Cannonsburg - S.NEAL TL KPCo | 11/1/2017 | 2022-08-01 | 4320320.91 | 7004790.82 | 1649849.17 | 149872.53 | 32172.7 | 13157006.13 | 0 | 8578467.821 | 0 | 0 | 0 | 8578467.821 | 4320320.91 | n.m. | -1573677.001 | -18.34% | 1649849.17 | n.m. | 149872.53 | n.m. | 32172.7 | n.m. | 4578538.309 | 53.37%
712 | 180 | P13064029 | Hazard-Wooton Change to KPCo | 8/1/2017 | Charges Continued After Dec 2022 | 675391.51 | 6595819.03 | 7759601.47 | 929158.47 | 31122.11 | 15991092.59 | 0 | 5206319.775 | 4740944.623 | 50.264 | 0 | 9947314.662 | 675391.51 | n.m. | 1389499.255 | 26.69% | 3018656.847 | 63.67% | 929108.206 | 1848457% | 31122.11 | n.m. | 6043777.928 | 60.76%
713 | 180 | B180KYLRC | T/KY/Non-Specific Work - Line | 2/1/2017 | Charges Continued After Dec 2022 | 2010328 | 2127355.99 | 3895557.4 | 5272577.27 | 4991667.58 | 18297486.24 | 450790.158 | 59761.599 | 2130907.368 | 2292232.424 | 4375672.444 | 9309363.993 | 1559537.842 | 346% | 2067594.391 | 3460% | 1764650.032 | 82.81% | 2980344.846 | 130% | 615995.136 | 14.08% | 8988122.247 | 96.55%
714 | 180 | A15702033 | Jackson - Helech Str. Replace | 5/1/2017 | 2022-04-01 | 259941.49 | 5306860.72 | 672595.75 | 54309.39 | 19736.5 | 6313443.85 | 330.68 | 13213566.954 | 0 | 0 | 0 | 13213897.634 | 259610.81 | 78508% | -7906706.234 | -59.84% | 672595.75 | n.m. | 54309.39 | n.m. | 19736.5 | n.m. | -6900453.784 | -52.22%
715 | 180 | 000005273 | KyPCo-T Capital Software Dev | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 1189138.17 | 969627.8 | 1168885.58 | 1491211.43 | 1708697.85 | 6527560.83 | 0 | 0 | 77613.765 | 366038.178 | 181343.93 | 624995.873 | 1189138.17 | n.m. | 969627.8 | n.m. | 1091271.815 | 1406% | 1125173.252 | 307.4% | 1527353.92 | 842.2% | 5902564.957 | 944.4%
716 | 180 | A14068001 | Baker 765kV Improvements | 6/1/2015 | Charges Continued After Dec 2022 | 1009283.18 | 669643.87 | 1574464.8 | 9504583.22 | 356890.09 | 13114865.16 | 104344.73 | 0 | 5768479.145 | 4255913.971 | 0 | 10128737.846 | 904938.45 | 867.3% | 669643.87 | n.m. | -4194014.345 | -72.71% | 5248669.249 | 123.3% | 356890.09 | n.m. | 2986127.314 | 29.48%
717 | 180 | P11161025 | Betsy Layne - Allen TLINE KPCo | 8/1/2017 | 11/1/2019 | 3478613.48 | 4349.29 | 0 | 0 | 0 | 3482962.77 | 0 | 0 | 0 | 0 | 0 | 0 | 3478613.48 | n.m. | 4349.29 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3482962.77 | n.m.
718 | 180 | DP16K02B0 | Cedar Creek add D trans | 4/1/2018 | 2020-11-01 | 174338.2 | 3351786.76 | 127831.7 | 0 | 0 | 3653956.66 | 0 | 0 | 0 | 1.459 | 0 | 1.459 | 174338.2 | n.m. | 3351786.76 | n.m. | 127831.7 | n.m. | -1.459 | -100% | 0 | n.m. | 3653955.201 | 250442440%
719 | 180 | A15702028 | Dorton 138/46 XF Replacement | 5/1/2017 | 2020-05-01 | 300657.27 | 2724152.33 | 27498.73 | 0 | 0 | 3052308.33 | 0 | 1191933.61 | 0 | 0 | 0 | 1191933.61 | 300657.27 | n.m. | 1532218.72 | 128.5% | 27498.73 | n.m. | 0 | n.m. | 0 | n.m. | 1860374.72 | 156.1%
720 | 180 | 000012898 | Forestry KP T non-NERC | Charges Began Prior to Jan 2015 | 2021-12-01 | 602604.59 | 571002.63 | 2658289.59 | 78987.72 | 0 | 3910884.53 | 459954.064 | 556308.951 | 1970204.418 | 94.591 | 0 | 2986562.024 | 142650.526 | 31.01% | 14693.679 | 2.641% | 688085.172 | 34.92% | 78893.129 | 83404% | 0 | n.m. | 924322.506 | 30.95%
721 | 180 | A15702027 | Johns Creek 138/34 kV XF | 5/1/2017 | 2022-01-01 | 311674.8 | 2650274.174 | 2544172.2 | 30584.95 | 0.92 | 5536707.044 | -177321.971 | 2123516.143 | 2664711.244 | 0 | 0 | 4610905.416 | 488996.771 | -275.8% | 526758.031 | 24.81% | -120539.044 | -4.524% | 30584.95 | n.m. | 0.92 | n.m. | 925801.628 | 20.08%
722 | 180 | P10115014 | Stone Change to KPCo | 7/1/2017 | 2022-02-01 | 318182.17 | 2296332.66 | 266821.52 | -11286.96 | -109909.37 | 2760140.02 | 0 | 1876865.534 | 0 | 0 | 0 | 1876865.534 | 318182.17 | n.m. | 419467.126 | 22.35% | 266821.52 | n.m. | -11286.96 | n.m. | -109909.37 | n.m. | 883274.486 | 47.06%
723 | 180 | 000010377 | Forestry KY T NERC | Charges Began Prior to Jan 2015 | 2022-01-01 |  | 2554140.67 | 362457.77 | 140415.33 | 1325.48 | 3058339.25 | 97070.915 | 98072.528 | 410389.613 | 58.185 | 0 | 605591.241 | -97070.915 | -100% | 2456068.142 | 2504% | -47931.843 | -11.68% | 140357.145 | 241226% | 1325.48 | n.m. | 2452748.009 | 405%
724 | 180 | B180KYSRR | T/KY/Non-Specific Work - Stati | 10/1/2016 | Charges Continued After Dec 2022 | 523423.37 | 352442.93 | 1196028.13 | 124658.05 | 1076570.76 | 3273123.24 | 244907.148 | 162522.894 | 538107.93 | 808466.396 | 1543278.6 | 3297282.968 | 278516.222 | 113.7% | 189920.036 | 116.9% | 657920.2 | 122.3% | -683808.346 | -84.58% | -466707.84 | -30.24% | -24159.728 | -0.7327%
725 | 180 | A15702007 | Beaver Creek- Repl Cap Bk AACC | 6/1/2017 | Charges Continued After Dec 2022 | 1962726.31 | 112955.25 | 17240.09 | 6138.8 | 3781.09 | 2102841.54 | 388.31 | 0 | 0 | 0 | 0 | 388.31 | 1962338 | 505353% | 112955.25 | n.m. | 17240.09 | n.m. | 6138.8 | n.m. | 3781.09 | n.m. | 2102453.23 | 541437%
726 | 180 | P13064030 | Hazard Station Change to KPCo | 9/1/2017 | Charges Continued After Dec 2022 | 500058.38 | 886589.15 | 2222368.98 | 2478689.61 | 463876.45 | 6551582.57 | 0 | 3073601.288 | 4044446.644 | 2076661.535 | 1195941.766 | 10390651.233 | 500058.38 | n.m. | -2187012.138 | -71.15% | -1822077.664 | -45.05% | 402028.075 | 19.36% | -732065.316 | -61.21% | -3839068.663 | -36.95%
727 | 180 | A15042010 | Stone Station Incr. KPCo | 6/1/2017 | 2020-11-01 | 1036651.52 | 939832.72 | 31390.82 | 0 | 0 | 2007875.06 | 651.14 | 1093822.817 | 0 | 0 | 0 | 1094473.957 | 1036000.38 | 159106% | -153990.097 | -14.08% | 31390.82 | n.m. | 0 | n.m. | 0 | n.m. | 913401.103 | 83.46%
728 | 180 | SI180KYLR | TB/SI/KyP/KY - LINE REHAB | Charges Began Prior to Jan 2015 | 11/1/2018 | -2550.21 |  | 0 | 0 | 0 | -2550.21 | 0 | 0 | 0 | 0 | 0 | 0 | -2550.21 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -2550.21 | n.m.
729 | 180 | A15702034 | Hazard-Jackson Str Rep Part 2 | 5/1/2017 | 2022-04-01 | 197411.94 | 1725260.08 | 2231041.98 | 897183.32 | 3934.41 | 5054831.73 | 699.48 | 3729.871 | 0 | 0 | 0 | 4429.351 | 196712.46 | 28123% | 1721530.209 | 46155% | 2231041.98 | n.m. | 897183.32 | n.m. | 3934.41 | n.m. | 5050402.379 | 114021%
730 | 180 | P11063002 | TKYHazard Station Improvemen | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 | 131011.07 | 63677.51 | 190781.66 | 163208.89 | 750338.15 | 1299017.28 | 490415.882 | 0 | 110960.903 | 164479.456 | 2990477.042 | 3756333.283 | -359404.812 | -73.29% | 63677.51 | n.m. | 79820.757 | 71.94% | -1270.566 | -0.7725% | -2240138.892 | -74.91% | -2457316.003 | -65.42%
731 | 180 | P11161023 | Stanville Ext TLINE KPCo | 8/1/2017 | Charges Continued After Dec 2022 | 1512509.76 | 53324.31 | -5405.03 | 1335.1 | 1157.5 | 1562921.64 | 0 | 0 | 0 | 0 | 0 | 0 | 1512509.76 | n.m. | 53324.31 | n.m. | -5405.03 | n.m. | 1335.1 | n.m. | 1157.5 | n.m. | 1562921.64 | n.m.
732 | 180 | A15702041 | Hazard CB/XF Replacements | 6/1/2017 | Charges Continued After Dec 2022 | 1518203.93 | -571646.29 | -409986.8 | 1658639.89 | 4484340.71 | 6679551.44 | 517292.887 | 1175823.82 | 1673016.891 | 168727 | 15048669.244 | 18583529.842 | 1000911.043 | 193.5% | -1747470.11 | -148.6% | -2083003.691 | -124.5% | 1489912.89 | 883% | -10564328.534 | -70.2% | -11903978.402 | -64.06%
733 | 180 | A18730015 | Spring Fork Tap Str 2 Failure | 6/1/2018 | 2022-02-01 | 791072.28 | 1022812.5 | 25631.85 | 3212.22 | 5391.69 | 1848120.54 | 0 | 0 | 0 | 0 | 0 | 0 | 791072.28 | n.m. | 1022812.5 | n.m. | 25631.85 | n.m. | 3212.22 | n.m. | 5391.69 | n.m. | 1848120.54 | n.m.
734 | 180 | A15702029 | Leslie 161/69kV XF Replacement | 6/1/2017 | Charges Continued After Dec 2022 | 1013743.01 | -256968.03 | 562667.62 | 201841.75 | 508365.3 | 2029649.65 | 7.01 | 2686855.333 | 507280.616 | 1466686.867 | 3732671.034 | 8393500.86 | 1013736 | 14461284% | -2943823.363 | -109.6% | 55387.004 | 10.92% | -1264845.117 | -86.24% | -3224305.734 | -86.38% | -6363851.21 | -75.82%
735 | 180 | A18730013 | Baker - Don Marquis STR 162-26 | 4/1/2018 | 11/1/2019 | 1549100.86 | 126248.27 | 19567.91 | 109099.23 | 1028235.31 | 2832251.58 | 0 | 0 | 0 | 0 | 0.086 | 0.086 | 1549100.86 | n.m. | 126248.27 | n.m. | 19567.91 | n.m. | 109099.23 | n.m. | 1028235.224 | 1195622353% | 2832251.494 | 3293315691%
736 | 180 | A16928011 | Chadwick Spare Purchase XF | 6/1/2017 | 1/1/2019 | 1036398.4 | 1656.08 | 0 | 0 | 0 | 1038054.48 | 28.33 | 0 | 0 | 0 | 0 | 28.33 | 1036370.07 | 3658207% | 1656.08 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1038026.15 | 3664053%
737 | 180 | P10115002 | TKPStone-RetRem Switches | 3/1/2017 | 2020-10-01 | 16879.4 | 1467356.49 | 26273.19 | 0 | 0 | 1510509.08 | 0 | 429782.812 | 0 | 0 | 0 | 429782.812 | 16879.4 | n.m. | 1037573.678 | 241.4% | 26273.19 | n.m. | 0 | n.m. | 0 | n.m. | 1080726.268 | 251.5%
738 | 180 | P13064031 | Hazard 161/138 Spare KPCo | 12/1/2017 | Charges Continued After Dec 2022 | 364898.71 | 563347.92 | 380808.61 | 771314.29 | 2824.48 | 2083194.01 | 0 | 35835.218 | 141643.967 | 77886.354 | 0 | 255365.539 | 364898.71 | n.m. | 527512.702 | 1472% | 239164.643 | 168.8% | 693427.936 | 890.3% | 2824.48 | n.m. | 1827828.471 | 715.8%
739 | 180 | A15702053 | Beaver Creek-Betsy Lane Remedi | 5/1/2017 | Charges Continued After Dec 2022 | 196614.2 | 54298.25 | 1950.82 | 1824.36 | 1581.71 | 256269.34 | 0 | 0 | 0 | 0 | 0 | 0 | 196614.2 | n.m. | 54298.25 | n.m. | 1950.82 | n.m. | 1824.36 | n.m. | 1581.71 | n.m. | 256269.34 | n.m.
740 | 180 | A15702010 | Thelma Rpl CB "B, D, BB" | 12/1/2016 | 3/1/2019 | 652950.46 | -926.04 | 0 | 0 | 0 | 652024.42 | 2221.5 | 0 | 0 | 0 | 0 | 2221.5 | 650728.96 | 29292% | -926.04 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 649802.92 | 29251%
741 | 180 | A16902001 | Big Sandy Remote End Relaying | 11/1/2016 | 2020-07-01 | 894180.08 | 61986.96 | 0.09 | 0 | 0 | 956167.13 | 539197.146 | 0 | 0 | 0 | 0 | 539197.146 | 354982.934 | 65.84% | 61986.96 | n.m. | 0.09 | n.m. | 0 | n.m. | 0 | n.m. | 416969.984 | 77.33%
742 | 180 | A19750001 | B Sandy - Broadf KP 765 Slide | 5/1/2019 | 2020-09-01 |  | 1303628.53 | 79958.69 | 0 | 0 | 1383587.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 1303628.53 | n.m. | 79958.69 | n.m. | 0 | n.m. | 0 | n.m. | 1383587.22 | n.m.
743 | 180 | P10115010 | T/KP/Inez: replace 138kV Bus # | Charges Began Prior to Jan 2015 | 2020-08-01 | 394397.7 | 465488.27 | 54323.24 | 0 | 0 | 914209.21 | 1640.335 | 384340.491 | 0 | 0 | 0 | 385980.826 | 392757.365 | 23944% | 81147.779 | 21.11% | 54323.24 | n.m. | 0 | n.m. | 0 | n.m. | 528228.384 | 136.9%
744 | 180 | P11161012 | B.Layne-S.Pikeville 69kV KPCo | 12/1/2015 | 8/1/2019 | 978802.07 | 21464.08 | 0 | 0 | 0 | 1000266.15 | 348588.782 | 151456.388 | 0 | 0 | 0 | 500045.17 | 630213.288 | 180.8% | -129992.308 | -85.83% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 500220.98 | 100%
745 | 180 | P13064025 | Hazard - Wooton ROW KPCo | 4/1/2017 | Charges Continued After Dec 2022 | 622675.89 | 383495.28 | 119628.6 | 29872.65 | 6465.02 | 1162137.44 | 1807.32 | 344668.4 | 107831.051 | 0 | 0 | 454306.771 | 620868.57 | 34353% | 38826.88 | 11.26% | 11797.549 | 10.94% | 29872.65 | n.m. | 6465.02 | n.m. | 707830.669 | 155.8%
746 | 180 | P11028016 | TKPBreaks 69kV Extension - C | Charges Began Prior to Jan 2015 | 7/1/2018 | 30228.86 |  | 0 | 0 | 0 | 30228.86 | 0 | 0 | 0 | 0 | 0 | 0 | 30228.86 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 30228.86 | n.m.
747 | 180 | IT1801421 | Maximo Imp - KYP - T | 3/1/2016 | 2020-08-01 | 376600.48 | 414418.06 | 6803.1 | 0 | 0 | 797821.64 | 0 | 0 | 936.628 | 0 | 0 | 936.628 | 376600.48 | n.m. | 414418.06 | n.m. | 5866.472 | 626.3% | 0 | n.m. | 0 | n.m. | 796885.012 | 85080%
748 | 180 | P11161007 | T/KP Line Work Betsy-Dewey | 4/1/2016 | 8/1/2019 | 924496.22 | 105926.81 | 0 | 0 | 0 | 1030423.03 | 430922.601 | 0 | 0 | 0 | 0 | 430922.601 | 493573.619 | 114.5% | 105926.81 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 599500.429 | 139.1%
749 | 180 | A13212035 | Bellefonte Telecom Legacy Pilo | 11/1/2015 | 7/1/2019 | 707745.35 | 16006.67 | 0 | 0 | 0 | 723752.02 | 0 | 0 | 0 | 0 | 0 | 0 | 707745.35 | n.m. | 16006.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 723752.02 | n.m.
750 | 180 | P13121005 | Leach: Breaker Replace/Retire | 6/1/2015 | 3/1/2018 | 1069.61 |  | 0 | 0 | 0 | 1069.61 | 0 | 0 | 0 | 0 | 0 | 0 | 1069.61 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1069.61 | n.m.
751 | 180 | SI180KYRE | TBSIKyP-KENTUCKY SYS REHAB | Charges Began Prior to Jan 2015 | 2021-02-01 | -15663.8 | 2309.96 | 8148.71 | -498.39 | 0 | -5703.52 | 634.096 | 0 | 0 | 0 | 0 | 634.096 | -16297.896 | -2570% | 2309.96 | n.m. | 8148.71 | n.m. | -498.39 | n.m. | 0 | n.m. | -6337.616 | -999.5%
752 | 180 | A15710034 | Coalton-Leon Fiber TelModFib | 8/1/2018 | 2022-08-01 | 313203.45 | 637154.24 | 14352.96 | 0 | -231452.54 | 733258.11 | 0 | 808636.615 | 0 | 0 | 0 | 808636.615 | 313203.45 | n.m. | -171482.375 | -21.21% | 14352.96 | n.m. | 0 | n.m. | -231452.54 | n.m. | -75378.505 | -9.322%
753 | 180 | P10115013 | Johns Creek Change to KPCo | 7/1/2017 | 2021-11-01 | 205629.86 | 552392.63 | 1016529.87 | 30238.68 | 0 | 1804791.04 | 0 | 1554087.688 | 15239.766 | 313.38 | 0 | 1569640.834 | 205629.86 | n.m. | -1001695.058 | -64.46% | 1001290.104 | 6570% | 29925.3 | 9549% | 0 | n.m. | 235150.206 | 14.98%
754 | 180 | IT180BILL | Corp Prgrm Billing-KYPCO Trans | 7/1/2017 | Charges Continued After Dec 2022 | 87242.76 | 356624.46 | 145910.11 | 157179.15 | 186285.15 | 933241.63 | 0 | 0 | 0 | 0 | 0 | 0 | 87242.76 | n.m. | 356624.46 | n.m. | 145910.11 | n.m. | 157179.15 | n.m. | 186285.15 | n.m. | 933241.63 | n.m.
755 | 180 | P17225004 | Moore Hollow 138kV Ext ROW | 12/1/2017 | 2021-11-01 | 693594.62 | 127433.91 | 11387.14 | -838479.48 | 0 | -6063.81 | 0 | 0 | 40058.572 | 36201.649 | 0 | 76260.221 | 693594.62 | n.m. | 127433.91 | n.m. | -28671.432 | -71.57% | -874681.129 | -2416% | 0 | n.m. | -82324.031 | -108%
756 | 180 | A19750002 | Betsy Layne- Allen 138kV Slide | 5/1/2019 | 2022-01-01 |  | 823087.88 | 679640.7 | 4515.88 | -1020 | 1506224.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 823087.88 | n.m. | 679640.7 | n.m. | 4515.88 | n.m. | -1020 | n.m. | 1506224.46 | n.m.
757 | 180 | P13121006 | Bellefonte Remote for Chadwick | 1/1/2016 | 5/1/2018 | 14731.28 |  | 0 | 0 | 0 | 14731.28 | 0 | 0 | 0 | 0 | 0 | 0 | 14731.28 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14731.28 | n.m.
758 | 180 | A17750008 | Prestonsburg-Mid Creek46kVSlid | 3/1/2019 | 2020-11-01 |  | 743577.65 | 284359.8 | 0 | 0 | 1027937.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 743577.65 | n.m. | 284359.8 | n.m. | 0 | n.m. | 0 | n.m. | 1027937.45 | n.m.
759 | 180 | P18025005 | Kewanee 138 Ext TLINE | 3/1/2018 | Charges Continued After Dec 2022 | 612822.72 | 118175.72 | 353886.19 | 2439862.5 | 12680322.12 | 16205069.25 | 0 | 9687373.959 | 30334.55 | 5228954.294 | 94954.388 | 15041617.191 | 612822.72 | n.m. | -9569198.239 | -98.78% | 323551.64 | 1067% | -2789091.794 | -53.34% | 12585367.732 | 13254% | 1163452.059 | 7.735%
760 | 180 | P10115015 | Inez Change to KPCo | 7/1/2017 | 2020-08-01 | 170485.39 | 256169.66 | 81055.42 | 0 | 0 | 507710.47 | 0 | 250460.836 | 0 | 0 | 0 | 250460.836 | 170485.39 | n.m. | 5708.824 | 2.279% | 81055.42 | n.m. | 0 | n.m. | 0 | n.m. | 257249.634 | 102.7%
761 | 180 | P11161008 | Dewey Remote ends | 1/1/2016 | 8/1/2019 | 534468.83 | 5667.65 | 0 | 0 | 0 | 540136.48 | 443064.81 | 9778.922 | 0 | 0 | 0 | 452843.732 | 91404.02 | 20.63% | -4111.272 | -42.04% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 87292.748 | 19.28%
762 | 180 | P16113003 | Cannonsburg-SNeal ROW (KY) | 12/1/2016 | 2021-11-01 | 638478.47 | 35478.57 | 129437.85 | 244.46 | 0 | 803639.35 | 487.76 | 335736.994 | 0 | 0 | 0 | 336224.754 | 637990.71 | 130800% | -300258.424 | -89.43% | 129437.85 | n.m. | 244.46 | n.m. | 0 | n.m. | 467414.596 | 139%
763 | 180 | P11161010 | B.Layne - Allen 46 kV KPCo | 7/1/2015 | Charges Continued After Dec 2022 | 519715.5 | 26585.13 | 2216.6 | 1996.73 | 1731.12 | 552245.08 | 278409.472 | 0 | 0 | 0 | 0 | 278409.472 | 241306.028 | 86.67% | 26585.13 | n.m. | 2216.6 | n.m. | 1996.73 | n.m. | 1731.12 | n.m. | 273835.608 | 98.36%
764 | 180 | TP0921005 | T/KY/Line: Conxt: Bonnyman-Sof | Charges Began Prior to Jan 2015 | 5/1/2019 | 64673.03 | 207547.41 | 0 | 0 | 0 | 272220.44 | 0 | 0 | 0 | 0 | 0 | 0 | 64673.03 | n.m. | 207547.41 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 272220.44 | n.m.
765 | 180 | A17959001 | KPCO/StormRcvry/BarrensheCole | 5/1/2017 | 10/1/2018 | 33851.27 |  | 0 | 0 | 0 | 33851.27 | 0 | 0 | 0 | 0 | 0 | 0 | 33851.27 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 33851.27 | n.m.
766 | 180 | A17750007 | Prestonsburg-Thelma 69kV Slide | 2/1/2019 | 2021-11-01 |  | 645803.49 | 352699.13 | 181012.62 | 0 | 1179515.24 | 0 | 0 | 9160.062 | 0 | 0 | 9160.062 | 0 | n.m. | 645803.49 | n.m. | 343539.068 | 3750% | 181012.62 | n.m. | 0 | n.m. | 1170355.178 | 12777%
767 | 180 | P10115001 | TKPJohns Creek-RetRem MOABs | Charges Began Prior to Jan 2015 | 2021-05-01 | 6820.96 | 555075.19 | 367362.02 | 5655.21 | 0 | 934913.38 | 414973.055 | 963549.405 | 14368.076 | 0 | 0 | 1392890.536 | -408152.095 | -98.36% | -408474.215 | -42.39% | 352993.944 | 2457% | 5655.21 | n.m. | 0 | n.m. | -457977.156 | -32.88%
768 | 180 | P11028010 | TKPLine work at Elkhorn City | Charges Began Prior to Jan 2015 | 1/1/2018 | 747.53 |  | 0 | 0 | 0 | 747.53 | 0 | 0 | 0 | 0 | 0 | 0 | 747.53 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 747.53 | n.m.
769 | 180 | P17225003 | Moore Hollow 138kV Extension | 11/1/2017 | Charges Continued After Dec 2022 | 407881.71 | 86371.57 | 33312.7 | -531539.09 | 1314.21 | -2658.9 | 0 | 1849.336 | 4296127.759 | 25163.696 | 0 | 4323140.791 | 407881.71 | n.m. | 84522.234 | 4570% | -4262815.059 | -99.22% | -556702.786 | -2212% | 1314.21 | n.m. | -4325799.691 | -100.1%
770 | 180 | KEPCS1701 | KPCo Storm - Transmission | 3/1/2017 | 2/1/2019 | 13927.23 | -15776.97 | 0 | 0 | 0 | -1849.74 | 0 | 0 | 0 | 0 | 0 | 0 | 13927.23 | n.m. | -15776.97 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1849.74 | n.m.
771 | 180 | A15702055 | Hazard Stn Rplc Fld Bnk #4 | 6/1/2017 | 11/1/2018 | 202565.77 |  | 0 | 0 | 0 | 202565.77 | 0 | 0 | 0 | 0 | 0 | 0 | 202565.77 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 202565.77 | n.m.
772 | 180 | P18221017 | Jackhorn Land Purchase | 8/1/2019 | Charges Continued After Dec 2022 |  | 508480.8 | 9803.71 | 18818.09 | 111300.48 | 648403.08 | 0 | 0 | 0 | 22361.846 | 0 | 22361.846 | 0 | n.m. | 508480.8 | n.m. | 9803.71 | n.m. | -3543.756 | -15.85% | 111300.48 | n.m. | 626041.234 | 2800%
773 | 180 | P11161024 | Stanville Ext ROW KPCo | 8/1/2017 | 4/1/2019 | 188306.53 | -1508.67 | 0 | 0 | 0 | 186797.86 | 0 | 0 | 0 | 0 | 0 | 0 | 188306.53 | n.m. | -1508.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 186797.86 | n.m.
774 | 180 | A15710033 | Morgan Fork Fiber TelModFib | 12/1/2017 | 2020-05-01 | 264457.51 | 236448.82 | 13034.64 | 0 | 0 | 513940.97 | 0 | 0 | 0 | 0 | 0 | 0 | 264457.51 | n.m. | 236448.82 | n.m. | 13034.64 | n.m. | 0 | n.m. | 0 | n.m. | 513940.97 | n.m.
775 | 180 | P13121013 | TLINE work @ Chadwick: KES | 4/1/2016 | 1/1/2018 | 0.48 |  | 0 | 0 | 0 | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0.48 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0.48 | n.m.
776 | 180 | A17042001 | Big Sandy-Baker 138kV Tie | 2/1/2018 | 2020-07-01 | 498449.3 | -28657.28 | 0.2 | 0 | 0 | 469792.22 | 0 | 0 | 0 | 0 | 0 | 0 | 498449.3 | n.m. | -28657.28 | n.m. | 0.2 | n.m. | 0 | n.m. | 0 | n.m. | 469792.22 | n.m.
777 | 180 | A17938021 | KPCO-Trans-Security AccSys-Est | 10/1/2017 | 2020-08-01 | 209512.37 | 56579.02 | 35485.02 | 0 | 0 | 301576.41 | 1779.663 | 0 | 0 | 0 | 0 | 1779.663 | 207732.707 | 11673% | 56579.02 | n.m. | 35485.02 | n.m. | 0 | n.m. | 0 | n.m. | 299796.747 | 16846%
778 | 180 | P11161009 | Morgan Fork Remote End | 7/1/2015 | 8/1/2019 | 295810.42 | 3153.62 | 0 | 0 | 0 | 298964.04 | 373166.672 | 0 | 0 | 0 | 0 | 373166.672 | -77356.252 | -20.73% | 3153.62 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -74202.632 | -19.88%
779 | 180 | A15042007 | Highland-Raceland FC ADSS | 10/1/2017 | 2022-06-01 | 289721.06 | 124459.48 | 18.66 | 0 | 28913.28 | 443112.48 | 0 | 0 | 0 | 0 | 0 | 0 | 289721.06 | n.m. | 124459.48 | n.m. | 18.66 | n.m. | 0 | n.m. | 28913.28 | n.m. | 443112.48 | n.m.
780 | 180 | A19750003 | Hazard - Pineville 161kV Fail | 6/1/2019 | 2020-09-01 |  | 432150.41 | 57527.51 | 0 | 0 | 489677.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 432150.41 | n.m. | 57527.51 | n.m. | 0 | n.m. | 0 | n.m. | 489677.92 | n.m.
781 | 180 | A15702002 | T/KY/BigSandy-Inez138kv:Lights | 8/1/2016 | 1/1/2019 | 136452.58 | 93.83 | 0 | 0 | 0 | 136546.41 | 0 | 0 | 0 | 0 | 0 | 0 | 136452.58 | n.m. | 93.83 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 136546.41 | n.m.
782 | 180 | A17212001 | Big Sandy 138KV RTU Replacemen | 7/1/2018 | 2020-04-01 | 21816.23 | 398626.29 | 40914.09 | 0 | 0 | 461356.61 | 0 | 0 | 0 | 0 | 0 | 0 | 21816.23 | n.m. | 398626.29 | n.m. | 40914.09 | n.m. | 0 | n.m. | 0 | n.m. | 461356.61 | n.m.
783 | 180 | A18730016 | Bonnyman-Softshell St 88 Failr | 6/1/2018 | 2020-07-01 | 54508.75 | 365512.83 | 17165.79 | 0 | 0 | 437187.37 | 0 | 0 | 0 | 0 | 0 | 0 | 54508.75 | n.m. | 365512.83 | n.m. | 17165.79 | n.m. | 0 | n.m. | 0 | n.m. | 437187.37 | n.m.
784 | 180 | P13121002 | D/KP/Chadwick: remove 138kV eq | 6/1/2015 | 3/1/2018 | 1160.98 |  | 0 | 0 | 0 | 1160.98 | 0 | 0 | 0 | 0 | 0 | 0 | 1160.98 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1160.98 | n.m.
785 | 180 | A15702030 | Morehead: Replace CB B | 5/1/2017 | Charges Continued After Dec 2022 | 141796.29 | 214606.12 | 657467.34 | 101609.79 | 736488.9 | 1851968.44 | 396.03 | 1604.348 | 460343.979 | 34574.45 | 1310890.874 | 1807809.681 | 141400.26 | 35704% | 213001.772 | 13277% | 197123.361 | 42.82% | 67035.34 | 193.9% | -574401.974 | -43.82% | 44158.759 | 2.443%
786 | 180 | A16928002 | Baker Station: Purchase 69/13k | 12/1/2017 | 9/1/2018 | 89757.4 |  | 0 | 0 | 0 | 89757.4 | 0 | 0 | 0 | 0 | 0 | 0 | 89757.4 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 89757.4 | n.m.
787 | 180 | A15702013 | T/KP/Leach:S.Neal pilot wire | 12/1/2016 | 8/1/2019 | 42436.91 | 5191.51 | 0 | 0 | 0 | 47628.42 | 0 | 0 | 0 | 0 | 0 | 0 | 42436.91 | n.m. | 5191.51 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 47628.42 | n.m.
788 | 180 | B180KYSRC | T/KY/Non-Specific Work-Station | 12/1/2016 | 2021-05-01 | 176022.82 | 8350.25 | 468.19 | -9277.3 | 0 | 175563.96 | 216196.539 | 135458.423 | 215341.223 | 288320.883 | 550404.176 | 1405721.244 | -40173.719 | -18.58% | -127108.173 | -93.84% | -214873.033 | -99.78% | -297598.183 | -103.2% | -550404.176 | -100% | -1230157.284 | -87.51%
789 | 180 | ITCW18001 | KY Next Generation Radio Sys | 4/1/2017 | 12/1/2018 | 25745.3 |  | 0 | 0 | 0 | 25745.3 | 0 | 0 | 43246.375 | 0 | 0 | 43246.375 | 25745.3 | n.m. | 0 | n.m. | -43246.375 | -100% | 0 | n.m. | 0 | n.m. | -17501.075 | -40.47%
790 | 180 | P12088002 | Bellefonte: 69kV SUPP Work | 9/1/2015 | 10/1/2018 | 171950.34 |  | 0 | 0 | 0 | 171950.34 | 0 | 0 | 0 | 0 | 0 | 0 | 171950.34 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 171950.34 | n.m.
791 | 180 | B180KYTRE | T/KP/Transmission Region Tools | 3/1/2017 | 1/1/2019 | 129816.33 | 117.59 | 118297.41 | 0 | 318566.37 | 566797.7 | 0 | 0 | 0 | 0 | 0 | 0 | 129816.33 | n.m. | 117.59 | n.m. | 118297.41 | n.m. | 0 | n.m. | 318566.37 | n.m. | 566797.7 | n.m.
792 | 180 | A15710035 | Pikeville Fiber TelModFib | 1/1/2019 | 2021-06-01 |  | 313088.78 | 961822.1 | 15275.57 | 0 | 1290186.45 | 0 | 468153.839 | 0 | 0 | 0 | 468153.839 | 0 | n.m. | -155065.059 | -33.12% | 961822.1 | n.m. | 15275.57 | n.m. | 0 | n.m. | 822032.611 | 175.6%
793 | 180 | P17110001 | Chadwick Station Work | 10/1/2017 | 2022-11-01 | 153194.94 | 120071.61 | 577726.28 | 2053926.99 | 146160.25 | 3051080.07 | 0 | 10761557.491 | 2071315.594 | 1110458.975 | 106826.956 | 14050159.016 | 153194.94 | n.m. | -10641485.881 | -98.88% | -1493589.314 | -72.11% | 943468.015 | 84.96% | 39333.294 | 36.82% | -10999078.946 | -78.28%
794 | 180 | A15042011 | Coleman-Stone 69kV reconfig | 6/1/2017 | 11/1/2019 | 14283.08 | 277568.61 | 1648.99 | 0 | 0 | 293500.68 | 14.68 | 183752.859 | 0 | 0 | 0 | 183767.539 | 14268.4 | 97196% | 93815.751 | 51.06% | 1648.99 | n.m. | 0 | n.m. | 0 | n.m. | 109733.141 | 59.71%
795 | 180 | A15702035 | Hazard - Fleming Str. Replace | 5/1/2017 | Charges Continued After Dec 2022 | 42152.55 | 155338.27 | 33864.94 | 5496.2 | 6118.42 | 242970.38 | 959.61 | 6887.7 | 14687.865 | 14501.142 | 0 | 37036.317 | 41192.94 | 4293% | 148450.57 | 2155% | 19177.075 | 130.6% | -9004.942 | -62.1% | 6118.42 | n.m. | 205934.063 | 556%
796 | 180 | A15010001 | Ashland-Kenova69kV-Relocate | 2/1/2015 | 10/1/2018 | 160985 |  | 0 | 0 | 0 | 160985 | 0 | 0 | 0 | 0 | 0 | 0 | 160985 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 160985 | n.m.
797 | 180 | A15705185 | Johns Creek 69kV Breaker Failu | 12/1/2016 | 4/1/2019 | -15369.17 | 240.88 | 0 | 0 | 0 | -15128.29 | 0 | 0 | 0 | 0 | 0 | 0 | -15369.17 | n.m. | 240.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -15128.29 | n.m.
798 | 180 | A15702054 | Stone TF Failre Rplcment | 6/1/2017 | 11/1/2019 | 13164.15 | 29096.05 | 324.46 | 0 | 256720.95 | 299305.61 | 0 | 0 | 0 | 0 | 0 | 0 | 13164.15 | n.m. | 29096.05 | n.m. | 324.46 | n.m. | 0 | n.m. | 256720.95 | n.m. | 299305.61 | n.m.
799 | 180 | P11161026 | Betsy Layne - Allen ROW KPCo | 11/1/2017 | 9/1/2019 | 80143.03 | -3132.22 | 0 | 0 | 0 | 77010.81 | 0 | 0 | 0 | 0 | 0 | 0 | 80143.03 | n.m. | -3132.22 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 77010.81 | n.m.
800 | 180 | P13064021 | T/KP/Hazard - Jackson 69kV Lin | 5/1/2016 | Charges Continued After Dec 2022 | 68845.73 | 170634.35 | 199742.44 | 11828.07 | 19761.62 | 470812.21 | 106014.07 | 8703.071 | 508222.691 | 0 | 0 | 622939.832 | -37168.34 | -35.06% | 161931.279 | 1861% | -308480.251 | -60.7% | 11828.07 | n.m. | 19761.62 | n.m. | -152127.622 | -24.42%
801 | 180 | P12104006 | T/KP/Bellefonte 138kV Remote R | 10/1/2015 | 9/1/2018 | 21678.83 |  | 0 | 0 | 0 | 21678.83 | 0 | 0 | 0 | 0 | 0 | 0 | 21678.83 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21678.83 | n.m.
802 | 180 | P11161022 | Beaver Cr - Betsy L TLINE KPCo | 3/1/2017 | 2020-12-01 | 237458.83 | 11037.43 | 141.67 | 0 | 0 | 248637.93 | 320.19 | 0 | 0 | 0 | 0 | 320.19 | 237138.64 | 74062% | 11037.43 | n.m. | 141.67 | n.m. | 0 | n.m. | 0 | n.m. | 248317.74 | 77553%
803 | 180 | A16905009 | Cancelled - DO NOT USE | 3/1/2017 | 2020-11-01 | 191240.08 | 21020.17 | -266738.74 | 0 | 0 | -54478.49 | 757562.963 | 252889.975 | 480560.886 | 0 | 0 | 1491013.824 | -566322.883 | -74.76% | -231869.805 | -91.69% | -747299.626 | -155.5% | 0 | n.m. | 0 | n.m. | -1545492.314 | -103.7%
804 | 180 | P13064002 | T/KP/Hazard Station / OPCO | 8/1/2016 | Charges Continued After Dec 2022 | 97377.45 | 87526.79 | 454889.5 | 2468027.99 | 508877.25 | 3616698.98 | 19976.261 | 199395.079 | 3308317.126 | 3780787.995 | 1606694.534 | 8915170.995 | 77401.189 | 387.5% | -111868.289 | -56.1% | -2853427.626 | -86.25% | -1312760.005 | -34.72% | -1097817.284 | -68.33% | -5298472.015 | -59.43%
805 | 180 | A15702047 | Leon KY Remote End Work | 5/1/2017 | 2022-12-01 | 46892.46 | 171661.77 | 372725.25 | 113729.98 | -748630.83 | -43621.37 | 286079.568 | 6711.384 | 631384.236 | 11687.59 | 956318.76 | 1892181.538 | -239187.108 | -83.61% | 164950.386 | 2458% | -258658.986 | -40.97% | 102042.39 | 873.1% | -1704949.59 | -178.3% | -1935802.908 | -102.3%
806 | 180 | A15042005 | Baker-Big Sandy Fiber Cable | 2/1/2018 | 7/1/2019 | 164733.23 | 92470.61 | 0 | 0 | 0 | 257203.84 | 0 | 0 | 0 | 0 | 0 | 0 | 164733.23 | n.m. | 92470.61 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 257203.84 | n.m.
807 | 180 | P16116005 | Stinnett -Pineville TL to KPCo | 7/1/2017 | Charges Continued After Dec 2022 | 46889.45 | 8507.52 | -256.81 | 53079.71 | 15225.76 | 123445.63 | 0 | 20184.124 | 1341509.859 | 114408.46 | 72574.706 | 1548677.149 | 46889.45 | n.m. | -11676.604 | -57.85% | -1341766.669 | -100% | -61328.75 | -53.61% | -57348.946 | -79.02% | -1425231.519 | -92.03%
808 | 180 | KYCR34118 | KY CR Johns Creek Sta | 1/1/2016 | 7/1/2018 | 10395.37 |  | 0 | 0 | 0 | 10395.37 | 0 | 0 | 0 | 0 | 0 | 0 | 10395.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10395.37 | n.m.
809 | 180 | DR18K02B1 | Bonnyman Sta - Add DRTU | 9/1/2018 | 2020-09-01 | 25128.3 | 223313.576 | 3932.08 | 0 | 0 | 252373.956 | 0 | 0 | 0 | 0 | 0 | 0 | 25128.3 | n.m. | 223313.576 | n.m. | 3932.08 | n.m. | 0 | n.m. | 0 | n.m. | 252373.956 | n.m.
810 | 180 | A14068005 | Ashland to Coalton Fiber Build | 8/1/2018 | 7/1/2019 | 175518.61 | 72690.9 | 0 | 14180.39 | 437.27 | 262827.17 | 0 | 0 | 0 | 0 | 0 | 0 | 175518.61 | n.m. | 72690.9 | n.m. | 0 | n.m. | 14180.39 | n.m. | 437.27 | n.m. | 262827.17 | n.m.
811 | 180 | P10115003 | TKPStone Tap - Retire | Charges Began Prior to Jan 2015 | 2020-11-01 | 6676.93 | 234792.99 | 189477.93 | 0 | 0 | 430947.85 | 197236.433 | 366127.501 | 0.129 | 0 | 0 | 563364.063 | -190559.503 | -96.61% | -131334.511 | -35.87% | 189477.801 | 146882016% | 0 | n.m. | 0 | n.m. | -132416.213 | -23.5%
812 | 180 | P18025006 | Kewanee 138 Ext ROW | 5/1/2018 | Charges Continued After Dec 2022 | 183103.49 | 43342.38 | 280899.12 | 976874.26 | 368923.53 | 1853142.78 | 0 | 0 | 14200.471 | 2032448.464 | 3211833.212 | 5258482.147 | 183103.49 | n.m. | 43342.38 | n.m. | 266698.649 | 1878% | -1055574.204 | -51.94% | -2842909.682 | -88.51% | -3405339.367 | -64.76%
813 | 180 | P17225001 | Moore Hollow 138kV Station | 11/1/2017 | Charges Continued After Dec 2022 | 129797.23 | 61988.87 | 30897.51 | -235215.62 | 3898.96 | -8633.05 | 0 | 1844.685 | 3673380.068 | 254.028 | 0 | 3675478.781 | 129797.23 | n.m. | 60144.185 | 3260% | -3642482.558 | -99.16% | -235469.648 | -92694% | 3898.96 | n.m. | -3684111.831 | -100.2%
814 | 180 | DR18K02B2 | Leslie Sta - breaker control | 10/1/2018 | 2020-02-01 | 23524.05 | 186915.484 | -3413.88 | 0 | 0 | 207025.654 | 0 | 0 | 0 | 0 | 0 | 0 | 23524.05 | n.m. | 186915.484 | n.m. | -3413.88 | n.m. | 0 | n.m. | 0 | n.m. | 207025.654 | n.m.
815 | 180 | KYCR33039 | KY CR Leslie Sta | 1/1/2016 | 7/1/2018 | 8656.31 |  | 0 | 0 | 0 | 8656.31 | 0 | 0 | 0 | 0 | 0 | 0 | 8656.31 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8656.31 | n.m.
816 | 180 | P12088005 | Bellefonte Rem/Rep XF (KPCo) | 5/1/2016 | 9/1/2018 | 153218.39 |  | 0 | 0 | 0 | 153218.39 | 0 | 0 | 0 | 0 | 0 | 0 | 153218.39 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 153218.39 | n.m.
817 | 180 | P14030102 | Leslie - Wooton TL to KPCo | 12/1/2017 | Charges Continued After Dec 2022 | 9354.36 | 3255.84 | 29237.79 | 150437.62 | 323771.57 | 516057.18 | 0 | 517186.892 | 44354.525 | 121819.225 | 2859.004 | 686219.646 | 9354.36 | n.m. | -513931.052 | -99.37% | -15116.735 | -34.08% | 28618.395 | 23.49% | 320912.566 | 11225% | -170162.466 | -24.8%
818 | 180 | DR19K04B0 | Pikeville DA 2019 - Beaver Ck | 5/1/2019 | 2020-09-01 |  | 184594.808 | 16768.41 | 0 | 0 | 201363.218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 184594.808 | n.m. | 16768.41 | n.m. | 0 | n.m. | 0 | n.m. | 201363.218 | n.m.
819 | 180 | DR19K04B1 | Pikeville DA 2019 - Stanville | 6/1/2019 | 2020-09-01 |  | 180747.28 | 15426.49 | 0 | 0 | 196173.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 180747.28 | n.m. | 15426.49 | n.m. | 0 | n.m. | 0 | n.m. | 196173.77 | n.m.
820 | 180 | KYCR30003 | KY CR Bellefonte Sta | 12/1/2015 | 8/1/2019 | 62344.13 | 31701.54 | 0 | 0 | 0 | 94045.67 | 0 | 0 | 0 | 0 | 0 | 0 | 62344.13 | n.m. | 31701.54 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 94045.67 | n.m.
821 | 180 | A13212037 | South Portsmouth Telecom Legac | 5/1/2016 | 5/1/2018 | 560.56 |  | 0 | 0 | 0 | 560.56 | 60960.177 | 0 | 0 | 0 | 0 | 60960.177 | -60399.617 | -99.08% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -60399.617 | -99.08%
822 | 180 | A18730009 | T/KY/EngleTapLighting:Failure | 2/1/2018 | 3/1/2019 | 153717.73 | 3013.63 | 0 | 0 | 0 | 156731.36 | 0 | 0 | 0 | 0 | 0 | 0 | 153717.73 | n.m. | 3013.63 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 156731.36 | n.m.
823 | 180 | A15702014 | Thelma-2017GEUpgrade | 2/1/2017 | 6/1/2018 | 3176.93 |  | 0 | 0 | 0 | 3176.93 | 0 | 0 | 0 | 0 | 0 | 0 | 3176.93 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3176.93 | n.m.
824 | 180 | P13064003 | T/KP/Wooton Station - Station | 5/1/2016 | Charges Continued After Dec 2022 | 50469.33 | 8722.14 | 234870.58 | 313894.05 | 55581.48 | 663537.58 | 147849.324 | 13015.81 | 324485.003 | 237756.89 | 0 | 723107.027 | -97379.994 | -65.86% | -4293.67 | -32.99% | -89614.423 | -27.62% | 76137.16 | 32.02% | 55581.48 | n.m. | -59569.447 | -8.238%
825 | 180 | A15702036 | Daisy-Clover Fork Str. Replace | 5/1/2017 | Charges Continued After Dec 2022 | 32286.6 | 52416.61 | 14331.93 | 2431.67 | 2706.96 | 104173.77 | 79487.542 | 44847.471 | 6389.059 | 7140.06 | 0 | 137864.132 | -47200.942 | -59.38% | 7569.139 | 16.88% | 7942.871 | 124.3% | -4708.39 | -65.94% | 2706.96 | n.m. | -33690.362 | -24.44%
826 | 180 | O17EST025 | SCADA - SERVERS - KPCO | 6/1/2017 | 3/1/2018 | 3565.04 |  | 0 | 0 | 0 | 3565.04 | 14929.207 | 14.204 | 0 | 0 | 0 | 14943.411 | -11364.167 | -76.12% | -14.204 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -11378.371 | -76.14%
827 | 180 | A18730002 | Jackson-Helech Str Rplc ROW | 8/1/2017 | 11/1/2019 | 54126.39 | 35180.46 | 270.75 | 0 | 0 | 89577.6 | 0 | 939.498 | 0.49 | 0 | 0 | 939.988 | 54126.39 | n.m. | 34240.962 | 3645% | 270.26 | 55155% | 0 | n.m. | 0 | n.m. | 88637.612 | 9430%
828 | 180 | A18730003 | Hazard-Jackson Str. Replc ROW | 8/1/2017 | 2021-07-01 | 63942.18 | 27961.35 | 7687.16 | 1499.16 | 0 | 101089.85 | 0 | 1308.12 | 0 | 0 | 0 | 1308.12 | 63942.18 | n.m. | 26653.23 | 2038% | 7687.16 | n.m. | 1499.16 | n.m. | 0 | n.m. | 99781.73 | 7628%
829 | 180 | P14030008 | T/KP/Leslie Station Work | 6/1/2016 | Charges Continued After Dec 2022 | 7293.75 | 9273.34 | 11958.02 | 52596.46 | 78813.35 | 159934.92 | 480394.065 | 205026.257 | 21844.556 | 5039.745 | 0 | 712304.623 | -473100.315 | -98.48% | -195752.917 | -95.48% | -9886.536 | -45.26% | 47556.715 | 943.6% | 78813.35 | n.m. | -552369.703 | -77.55%
830 | 180 | A15710041 | Grayson Fiber Ext TelModFib | 12/1/2018 | 2020-03-01 | 615.08 | 101515.23 | 2206.63 | 0 | 0 | 104336.94 | 0 | 23654.589 | 0 | 0 | 0 | 23654.589 | 615.08 | n.m. | 77860.641 | 329.2% | 2206.63 | n.m. | 0 | n.m. | 0 | n.m. | 80682.351 | 341.1%
831 | 180 | A15702032 | Hazard-Bonnyman Str. Replace | 5/1/2017 | Charges Continued After Dec 2022 | 11917.2 | 40290.91 | 19510.29 | 2043.24 | 2274.55 | 76036.19 | 279.39 | 3333.858 | 4892.401 | 6038.854 | 0 | 14544.503 | 11637.81 | 4165% | 36957.052 | 1109% | 14617.889 | 298.8% | -3995.614 | -66.17% | 2274.55 | n.m. | 61491.687 | 422.8%
832 | 180 | P17076001 | Kenwood Extension TLINE | 9/1/2017 | Charges Continued After Dec 2022 | 42179.34 | 18155.44 | 31941.83 | 18316.14 | 4754.83 | 115347.58 | 0 | 192719.151 | 1069210.686 | 4959.904 | 853100.466 | 2119990.207 | 42179.34 | n.m. | -174563.711 | -90.58% | -1037268.856 | -97.01% | 13356.236 | 269.3% | -848345.636 | -99.44% | -2004642.627 | -94.56%
833 | 180 | P17225013 | Ramey 138 kV Extension TLINE | 11/1/2017 | Charges Continued After Dec 2022 | 8134.21 | 79063.44 | 3594.93 | -94139.63 | 84.6 | -3262.45 | 0 | 3234515.937 | 3666547.67 | 4264.172 | 0 | 6905327.779 | 8134.21 | n.m. | -3155452.497 | -97.56% | -3662952.74 | -99.9% | -98403.802 | -2308% | 84.6 | n.m. | -6908590.229 | -100%
834 | 180 | P18221013 | Beaver Creek Remote End | 5/1/2019 | Charges Continued After Dec 2022 |  | 90105.69 | 25220.47 | 246267.46 | 376773.79 | 738367.41 | 0 | 0 | 329.096 | 473223.945 | 1547104.902 | 2020657.943 | 0 | n.m. | 90105.69 | n.m. | 24891.374 | 7564% | -226956.485 | -47.96% | -1170331.112 | -75.65% | -1282290.533 | -63.46%
835 | 180 | P17084003 | Cancel - DO NOT USE | 10/1/2017 | 2020-07-01 | 68946.52 | 5762.35 | -81144.87 | 0 | 0 | -6436 | 0 | 3206760.447 | -19248.128 | -1274.364 | 0 | 3186237.955 | 68946.52 | n.m. | -3200998.097 | -99.82% | -61896.742 | 321.6% | 1274.364 | -100% | 0 | n.m. | -3192673.955 | -100.2%
836 | 180 | A15702006 | KYPCo BAT HCP | 4/1/2016 | Charges Continued After Dec 2022 | 39897.95 | 29581.08 | 22576.07 | 26986.74 | 28964.45 | 148006.29 | 0 | 0 | 0 | 4175.463 | 0 | 4175.463 | 39897.95 | n.m. | 29581.08 | n.m. | 22576.07 | n.m. | 22811.277 | 546.3% | 28964.45 | n.m. | 143830.827 | 3445%
837 | 180 | A15042012 | Stone-Sprigg 46kV Reconfig | 6/1/2017 | 2020-10-01 | 10080.79 | 64395.24 | 102650.29 | 0 | 0 | 177126.32 | 7.34 | 54651.858 | 0 | 0 | 0 | 54659.198 | 10073.45 | 137240% | 9743.382 | 17.83% | 102650.29 | n.m. | 0 | n.m. | 0 | n.m. | 122467.122 | 224.1%
838 | 180 | P17110003 | Bellefonte Remote end Work | 11/1/2017 | Charges Continued After Dec 2022 | 51699.85 | 15626.41 | 194702.32 | 325344.59 | 7085.31 | 594458.48 | 0 | 385.557 | 421086.578 | 418618.114 | 27611.162 | 867701.411 | 51699.85 | n.m. | 15240.853 | 3953% | -226384.258 | -53.76% | -93273.524 | -22.28% | -20525.852 | -74.34% | -273242.931 | -31.49%
839 | 180 | SI180KYUN | TB SI KYPCO - KENTUCKY UNCAT | Charges Began Prior to Jan 2015 | 2021-05-01 | 3125.6 | 2228.26 | 1985.32 | 1575.48 | 0 | 8914.66 | 0 | 0 | 0 | 0 | 0 | 0 | 3125.6 | n.m. | 2228.26 | n.m. | 1985.32 | n.m. | 1575.48 | n.m. | 0 | n.m. | 8914.66 | n.m.
840 | 180 | A15702003 | Inez Station - UPFC Retirement | 4/1/2017 | 6/1/2018 | 29983.79 |  | 0 | 0 | 0 | 29983.79 | 0 | 0 | 0 | 0 | 0 | 0 | 29983.79 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 29983.79 | n.m.
841 | 180 | P17083001 | Garrett-Soft Shell 138kV TLINE | 3/1/2019 | Charges Continued After Dec 2022 |  | 71239.76 | 135864.15 | 380619.92 | 696202.52 | 1283926.35 | 0 | 0 | 5873883.229 | 916761.059 | -3598.27 | 6787046.018 | 0 | n.m. | 71239.76 | n.m. | -5738019.079 | -97.69% | -536141.139 | -58.48% | 699800.79 | -19448% | -5503119.668 | -81.08%
842 | 180 | A15710024 | Beaver Creek TTMP | 8/1/2017 | 2020-06-01 | 37260.08 | 29772.29 | 6010.83 | 0 | 0 | 73043.2 | 21340.364 | 0 | 0 | 0 | 0 | 21340.364 | 15919.716 | 74.6% | 29772.29 | n.m. | 6010.83 | n.m. | 0 | n.m. | 0 | n.m. | 51702.836 | 242.3%
843 | 180 | P17084026 | Beaver Creek - Fleming Cut in | 9/1/2017 | 2021-01-01 | 52732.61 | 7092.29 | -67895.12 | -152 | 0 | -8222.22 | 0 | 1228.177 | 3410.346 | -358.36 | 0 | 4280.163 | 52732.61 | n.m. | 5864.113 | 477.5% | -71305.466 | -2091% | 206.36 | -57.58% | 0 | n.m. | -12502.383 | -292.1%
844 | 180 | P17084016 | DO NOT USE | 9/1/2017 | 2021-03-01 | 35173.91 | 2953.17 | -62251.79 | -4015.02 | 0 | -28139.73 | 0 | 3492.349 | 0 | 0 | 0 | 3492.349 | 35173.91 | n.m. | -539.179 | -15.44% | -62251.79 | n.m. | -4015.02 | n.m. | 0 | n.m. | -31632.079 | -905.8%
845 | 180 | A15702016 | BeaverCreek-2017GEUpgrade | 1/1/2017 | 6/1/2018 | -361.9 |  | 0 | 0 | 0 | -361.9 | 0 | 0 | 0 | 0 | 0 | 0 | -361.9 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -361.9 | n.m.
846 | 180 | ITCB18000 | KENTUCKY POWER - TRANSM | Charges Began Prior to Jan 2015 | Charges Continued After Dec 2022 |  | 10464.66 | 148.7 | 145383.43 | 18475.97 | 174472.76 | 69692.176 | 63456.271 | 62917.633 | 68849.216 | 137290.846 | 402206.142 | -69692.176 | -100% | -52991.611 | -83.51% | -62768.933 | -99.76% | 76534.214 | 111.2% | -118814.876 | -86.54% | -227733.382 | -56.62%
847 | 180 | DP14K02C0 | KP/Raccoon Sta - T line in & o | 8/1/2018 | 2022-06-01 | 7775.82 | 56643.65 | 542528.94 | 599121.21 | -11533.26 | 1194536.36 | 0 | 0 | 0 | 0 | 0 | 0 | 7775.82 | n.m. | 56643.65 | n.m. | 542528.94 | n.m. | 599121.21 | n.m. | -11533.26 | n.m. | 1194536.36 | n.m.
848 | 180 | A18730011 | T/KY/EngleTapLighting: ROW | 3/1/2018 | 3/1/2019 | 62081.16 | 65.05 | 0 | 0 | 0 | 62146.21 | 0 | 0 | 0 | 0 | 0 | 0 | 62081.16 | n.m. | 65.05 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 62146.21 | n.m.
849 | 180 | A15702060 | Wooton-2018Geupgrade | 1/1/2018 | 3/1/2019 | 54911.46 | -1101.7 | 0 | 0 | 0 | 53809.76 | 0 | 0 | 0 | 0 | 0 | 0 | 54911.46 | n.m. | -1101.7 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 53809.76 | n.m.
850 | 180 | P19215003 | Chadwick - England Hill TLINE | 11/1/2019 | 2022-07-01 |  | 50615.36 | 746699.39 | 2036656.57 | 485111.76 | 3319083.08 | 0 | 0 | 0 | 2644581.514 | 25916.774 | 2670498.288 | 0 | n.m. | 50615.36 | n.m. | 746699.39 | n.m. | -607924.944 | -22.99% | 459194.986 | 1772% | 648584.792 | 24.29%
851 | 180 | P17225015 | East Park - Princess 138kV TL | 11/1/2017 | Charges Continued After Dec 2022 | 16833.87 | 6560.95 | 1812.16 | -52087.45 | 76.94 | -26803.53 | 0 | 3795362.354 | 3528002.173 | 2229.187 | 0 | 7325593.714 | 16833.87 | n.m. | -3788801.404 | -99.83% | -3526190.013 | -99.95% | -54316.637 | -2437% | 76.94 | n.m. | -7352397.244 | -100.4%
852 | 180 | DR19K06D0 | Breaker Repl - Bellefonte | 4/1/2019 | 2021-04-01 |  | 48563.4 | 75217.4 | -2784.9 | 0 | 120995.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 48563.4 | n.m. | 75217.4 | n.m. | -2784.9 | n.m. | 0 | n.m. | 120995.9 | n.m.
853 | 180 | DP14K02C1 | Sprigg-Beaver Creek-Tower Rplc | 10/1/2018 | 2022-08-01 | 756 | 46430.2 | 133064.05 | 570664.34 | 4288.01 | 755202.6 | 0 | 0 | 0 | 0 | 0 | 0 | 756 | n.m. | 46430.2 | n.m. | 133064.05 | n.m. | 570664.34 | n.m. | 4288.01 | n.m. | 755202.6 | n.m.
854 | 180 | A15702023 | Leslie-2017GEUpgrade | 3/1/2017 | 1/1/2018 | -623.89 |  | 0 | 0 | 0 | -623.89 | 0 | 0 | 0 | 0 | 0 | 0 | -623.89 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -623.89 | n.m.
855 | 180 | A15702045 | Morgan Fork 2017 GE Upgrade | 3/1/2017 | 3/1/2018 | 905.38 |  | 0 | 0 | 0 | 905.38 | 0 | 0 | 0 | 0 | 0 | 0 | 905.38 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 905.38 | n.m.
856 | 180 | P17084007 | Myra 138kV Extension TLINE | 10/1/2017 | Charges Continued After Dec 2022 | 33774.11 | 4315.53 | 84532.61 | 124009.41 | 114763.22 | 361394.88 | 0 | 1577738.167 | 1918166 | 4597.241 | 3949616.302 | 7450117.71 | 33774.11 | n.m. | -1573422.637 | -99.73% | -1833633.39 | -95.59% | 119412.169 | 2597% | -3834853.082 | -97.09% | -7088722.83 | -95.15%
857 | 180 | P13121012 | TLINE work @ Chadwick: Bellfnt | 4/1/2016 | 1/1/2018 | 0.41 |  | 0 | 0 | 0 | 0.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0.41 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0.41 | n.m.
858 | 180 | P14030013 | Wooton Relaying Work & Telecom | 9/1/2016 | Charges Continued After Dec 2022 | 1763.39 | 1863.26 | 7457.47 | 61548.71 | 15317.72 | 87950.55 | 193780.405 | 182839.966 | 11002.447 | 2043.007 | 11845.216 | 401511.041 | -192017.015 | -99.09% | -180976.706 | -98.98% | -3544.977 | -32.22% | 59505.703 | 2913% | 3472.504 | 29.32% | -313560.491 | -78.1%
859 | 180 | A15702022 | LeeCity-2017GEUpgrade | 3/1/2017 | 2/1/2018 | -1625.16 |  | 0 | 0 | 0 | -1625.16 | 0 | 0 | 0 | 0 | 0 | 0 | -1625.16 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1625.16 | n.m.
860 | 180 | A15702019 | BigSandy138kv-2017GEUpgrade | 1/1/2017 | 1/1/2018 | 614.12 |  | 0 | 0 | 0 | 614.12 | 0 | 0 | 0 | 0 | 0 | 0 | 614.12 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 614.12 | n.m.
861 | 180 | A15710001 | Bellefonte 138KV Tele. Moderni | 12/1/2016 | 5/1/2018 | 4327.59 |  | 0 | 0 | 0 | 4327.59 | 1377.48 | 1.065 | 0 | 0 | 0 | 1378.545 | 2950.11 | 214.2% | -1.065 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2949.045 | 213.9%
862 | 180 | A15702020 | Dewey-2017GEUpgrade | 3/1/2017 | 6/1/2018 | 16.67 |  | 0 | 0 | 0 | 16.67 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16.67 | n.m.
863 | 180 | DR19K05D0 | Hazard DA 2019 - Hazard Sta | 6/1/2019 | 2021-11-01 |  | 35353.96 | 570818.15 | 31419.83 | 0 | 637591.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 35353.96 | n.m. | 570818.15 | n.m. | 31419.83 | n.m. | 0 | n.m. | 637591.94 | n.m.
864 | 180 | A18730012 | S Neal - Leach: Hdware & Gnd | 4/1/2018 | 2/1/2019 | 29422.26 | 2735.82 | 0 | 0 | 0 | 32158.08 | 0 | 0 | 0 | 0 | 0 | 0 | 29422.26 | n.m. | 2735.82 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 32158.08 | n.m.
865 | 180 | P16116003 | Stinnett - Pineville ROW KPCo | 11/1/2016 | Charges Continued After Dec 2022 | 12427.87 | 498.93 | 1027.85 | 7846.63 | 1364.16 | 23165.44 | 14.85 | 9222.044 | 1061065.107 | 397.778 | 1638219.052 | 2708918.831 | 12413.02 | 83589% | -8723.114 | -94.59% | -1060037.257 | -99.9% | 7448.852 | 1873% | -1636854.892 | -99.92% | -2685753.391 | -99.14%
866 | 180 | A15710036 | Hays Branch TTMP | 12/1/2017 | 2020-09-01 | 20639.75 | 9390.32 | 8175.24 | 0 | 0 | 38205.31 | 0 | 0 | 0 | 0 | 0 | 0 | 20639.75 | n.m. | 9390.32 | n.m. | 8175.24 | n.m. | 0 | n.m. | 0 | n.m. | 38205.31 | n.m.
867 | 180 | A15702018 | BetsyLayne-2017GEUpgrade | 2/1/2017 | 1/1/2018 | 481.24 |  | 0 | 0 | 0 | 481.24 | 0 | 0 | 0 | 0 | 0 | 0 | 481.24 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 481.24 | n.m.
868 | 180 | B180KYCSV | T/KY/Customer Service | 9/1/2019 | 2022-09-01 |  | 29394.28 | 5674.28 | 2098.9 | -34912.37 | 2255.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 29394.28 | n.m. | 5674.28 | n.m. | 2098.9 | n.m. | -34912.37 | n.m. | 2255.09 | n.m.
869 | 180 | A18730004 | Hazard-Fleming Str. Replc ROW | 8/1/2017 | Charges Continued After Dec 2022 | 1863.65 | 12801.85 | 1035.02 | 983.12 | 852.38 | 17536.02 | 0 | 0 | 0 | 1245.956 | 0 | 1245.956 | 1863.65 | n.m. | 12801.85 | n.m. | 1035.02 | n.m. | -262.836 | -21.1% | 852.38 | n.m. | 16290.064 | 1307%
870 | 180 | A18502002 | Baker 765 Firewall Install | 12/1/2018 | 8/1/2019 | 2107.25 | 26217.54 | 0 | 0 | 0 | 28324.79 | 0 | 0 | 0 | 0 | 0 | 0 | 2107.25 | n.m. | 26217.54 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28324.79 | n.m.
871 | 180 | P17225017 | Bellefonte - Coalton 138 kV TL | 12/1/2017 | Charges Continued After Dec 2022 | 6147.35 | 1708.24 | 966.51 | -27712.4 | 1.27 | -18889.03 | 0 | 877678.433 | 1041257.751 | 1199.368 | 0 | 1920135.552 | 6147.35 | n.m. | -875970.193 | -99.81% | -1040291.241 | -99.91% | -28911.768 | -2411% | 1.27 | n.m. | -1939024.582 | -101%
872 | 180 | A18730001 | Hazard-Bonnyman Str Replce ROW | 8/1/2017 | Charges Continued After Dec 2022 | 1702.44 | 13156.93 | 958.7 | 910.65 | 789.5 | 17518.22 | 0 | 626.261 | 1307.627 | 1154.096 | 0 | 3087.984 | 1702.44 | n.m. | 12530.669 | 2001% | -348.927 | -26.68% | -243.446 | -21.09% | 789.5 | n.m. | 14430.236 | 467.3%
873 | 180 | DR19K06D1 | RTU Repl - Bonnyman | 5/1/2019 | 2020-06-01 |  | 26376.5 | 950.72 | 0 | 0 | 27327.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 26376.5 | n.m. | 950.72 | n.m. | 0 | n.m. | 0 | n.m. | 27327.22 | n.m.
874 | 180 | P18221005 | Beaver Creek - Fleming 69kV | 5/1/2019 | Charges Continued After Dec 2022 |  | 25976.7 | 8954.64 | 3401.44 | 173497.81 | 211830.59 | 0 | 0 | 930.82 | 242747.904 | 2566146.376 | 2809825.1 | 0 | n.m. | 25976.7 | n.m. | 8023.82 | 862% | -239346.464 | -98.6% | -2392648.566 | -93.24% | -2597994.51 | -92.46%
875 | 180 | 000025230 | 2018 Gen Plt Cap Blkt - KYPC-T | 4/1/2018 | Charges Continued After Dec 2022 | 6403.03 | 19382.74 | 46.98 | 27874.16 | 2098.91 | 55805.82 | 0 | 0 | 0 | 0 | 0 | 0 | 6403.03 | n.m. | 19382.74 | n.m. | 46.98 | n.m. | 27874.16 | n.m. | 2098.91 | n.m. | 55805.82 | n.m.
876 | 180 | P13064020 | T/KP/Hazard - Jackson 69kV ROW | 5/1/2017 | 2020-01-01 | 12940.82 | 9400.05 | 409.48 | 0 | 0 | 22750.35 | 40198.462 | 2493.216 | 44722.761 | 0 | 0 | 87414.439 | -27257.642 | -67.81% | 6906.834 | 277% | -44313.281 | -99.08% | 0 | n.m. | 0 | n.m. | -64664.089 | -73.97%
877 | 180 | A18730005 | Daisy - Clover Fork ROW | 8/1/2017 | Charges Continued After Dec 2022 | 999.85 | 11865.28 | 917.86 | 871.83 | 755.85 | 15410.67 | 0 | 678.83 | 1251.88 | 1104.897 | 0 | 3035.607 | 999.85 | n.m. | 11186.45 | 1648% | -334.02 | -26.68% | -233.067 | -21.09% | 755.85 | n.m. | 12375.063 | 407.7%
878 | 180 | A20705052 | Coleman - Stone 69kV Pre Eng | 9/1/2019 | Charges Continued After Dec 2022 |  | 24020.59 | 1097.6 | 830.03 | 719.65 | 26667.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 24020.59 | n.m. | 1097.6 | n.m. | 830.03 | n.m. | 719.65 | n.m. | 26667.87 | n.m.
879 | 180 | P17110002 | Bellefonte - Grangston Cut in | 11/1/2017 | Charges Continued After Dec 2022 | 12603.7 | 8658.6 | 8015.27 | 1013325.41 | 1390.82 | 1043993.8 | 0 | 327.835 | 970685.908 | 291322.823 | 160594.558 | 1422931.124 | 12603.7 | n.m. | 8330.765 | 2541% | -962670.638 | -99.17% | 722002.587 | 247.8% | -159203.738 | -99.13% | -378937.324 | -26.63%
880 | 180 | A15702044 | INEZ 2017 GE Upgrade | 3/1/2017 | 6/1/2018 | -231.66 |  | 0 | 0 | 0 | -231.66 | 0 | 0 | 0 | 0 | 0 | 0 | -231.66 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -231.66 | n.m.
881 | 180 | P11161001 | T/KY/Betsy Layne: Retirement | 10/1/2018 | 1/1/2019 | 21780.93 | 21.14 | 0 | 0 | 0 | 21802.07 | 19187.726 | 0 | 0 | 0 | 0 | 19187.726 | 2593.204 | 13.51% | 21.14 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2614.344 | 13.63%
882 | 180 | A15702021 | Fleming-2017GEUpgrade | 3/1/2017 | 1/1/2018 | -431.08 |  | 0 | 0 | 0 | -431.08 | 0 | 0 | 0 | 0 | 0 | 0 | -431.08 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -431.08 | n.m.
883 | 180 | A15702025 | Baker 765 kV PK Removals | 11/1/2016 | 7/1/2019 | 2665.67 | 8774.67 | 681.78 | 0 | 0 | 12122.12 | 1288726.835 | 0 | 0 | 0 | 0 | 1288726.835 | -1286061.165 | -99.79% | 8774.67 | n.m. | 681.78 | n.m. | 0 | n.m. | 0 | n.m. | -1276604.715 | -99.06%
884 | 180 | A15710022 | Morgan Fork TTMP | 1/1/2017 | 2020-04-01 | 9983.9 | 9731.57 | 2635.66 | 0 | 0 | 22351.13 | 0 | 0 | 0 | 0 | 0 | 0 | 9983.9 | n.m. | 9731.57 | n.m. | 2635.66 | n.m. | 0 | n.m. | 0 | n.m. | 22351.13 | n.m.
885 | 180 | A20705037 | Big Sandy - Thelma Pre Eng | 8/1/2019 | Charges Continued After Dec 2022 |  | 20945.85 | 754.96 | 717.13 | 621.72 | 23039.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 20945.85 | n.m. | 754.96 | n.m. | 717.13 | n.m. | 621.72 | n.m. | 23039.66 | n.m.
886 | 180 | A15702015 | MorganCounty-2017GEUpgrade | 3/1/2017 | 1/1/2018 | 327.24 |  | 0 | 0 | 0 | 327.24 | 694.23 | 0 | 0 | 0 | 0 | 694.23 | -366.99 | -52.86% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -366.99 | -52.86%
887 | 180 | P17084019 | Elwood - Cedar Cr. Reconfig. | 9/1/2017 | Charges Continued After Dec 2022 | 12573.1 | 1680.75 | 1535.09 | 704.49 | 610.8 | 17104.23 | 0 | 1021.207 | 982.483 | 923.582 | 1302607.3 | 1305534.572 | 12573.1 | n.m. | 659.543 | 64.58% | 552.607 | 56.25% | -219.092 | -23.72% | -1301996.5 | -99.95% | -1288430.342 | -98.69%
888 | 180 | P18025013 | Sprigg - Beaver Cr. TLINE Work | 6/1/2018 | Charges Continued After Dec 2022 | 12715.99 | 7004.4 | 65635.38 | 142501.56 | 1169733.66 | 1397590.99 | 0 | 0 | 2645.237 | 341813.655 | 1235712.934 | 1580171.826 | 12715.99 | n.m. | 7004.4 | n.m. | 62990.143 | 2381% | -199312.095 | -58.31% | -65979.274 | -5.339% | -182580.836 | -11.55%
889 | 180 | P19104010 | Bellefonte Ext (KY) Line work | 5/1/2019 | Charges Continued After Dec 2022 |  | 19091.71 | 40060.75 | 1416436.82 | 2890630.3 | 4366219.58 | 0 | 0 | 158.894 | 2501917.417 | 4105365.242 | 6607441.553 | 0 | n.m. | 19091.71 | n.m. | 39901.856 | 25112% | -1085480.597 | -43.39% | -1214734.942 | -29.59% | -2241221.973 | -33.92%
890 | 180 | A15710037 | Leon TTMP | 12/1/2017 | 11/1/2019 | 564.19 | 17862.24 | 0 | 0 | 0 | 18426.43 | 0 | 37838.688 | 0 | 0 | 0 | 37838.688 | 564.19 | n.m. | -19976.448 | -52.79% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -19412.258 | -51.3%
891 | 180 | P17084036 | DO NOT USE | 11/1/2017 | 2020-12-01 | 5017.52 | 790.4 | -17735.64 | 0 | 0 | -11927.72 | 0 | 917.939 | 883.332 | 843.193 | 0 | 2644.464 | 5017.52 | n.m. | -127.539 | -13.89% | -18618.972 | -2108% | -843.193 | -100% | 0 | n.m. | -14572.184 | -551%
892 | 180 | P17076005 | Prestonsburg - Thelma 69kV | 9/1/2017 | Charges Continued After Dec 2022 | 10949.16 | 1785.54 | 624.44 | 3324.95 | 656.02 | 17340.11 | 0 | 705.75 | 518447.986 | 1229687.597 | 679656.474 | 2428497.807 | 10949.16 | n.m. | 1079.79 | 153% | -517823.546 | -99.88% | -1226362.647 | -99.73% | -679000.454 | -99.9% | -2411157.697 | -99.29%
893 | 180 | P17110005 | Chadwick - Leach Relocation | 10/1/2017 | 2022-05-01 | 9126.53 | 6289.94 | 15627.95 | 729940.17 | -12454.73 | 748529.86 | 0 | 322.409 | 442713.48 | 288105.994 | 117438.566 | 848580.449 | 9126.53 | n.m. | 5967.531 | 1851% | -427085.53 | -96.47% | 441834.176 | 153.4% | -129893.296 | -110.6% | -100050.589 | -11.79%
894 | 180 | A20705028 | Sprigg-Barrenshe 69kV Pre Eng | 7/1/2019 | Charges Continued After Dec 2022 |  | 16952.39 | 611.05 | 580.4 | 3343.45 | 21487.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 16952.39 | n.m. | 611.05 | n.m. | 580.4 | n.m. | 3343.45 | n.m. | 21487.29 | n.m.
895 | 180 | P17084037 | Beaver Creek Remote End | 11/1/2017 | 2022-02-01 | 3958.39 | 738.1 | 2255.36 | -16384.89 | -2432.94 | -11865.98 | 0 | 327.527 | 824.901 | 188.401 | 0.046 | 1340.875 | 3958.39 | n.m. | 410.573 | 125.4% | 1430.459 | 173.4% | -16573.291 | -8797% | -2432.986 | -5289100% | -13206.855 | -984.9%
896 | 180 | P14030103 | Leslie - Stinnett TL to KPCo | 12/1/2017 | Charges Continued After Dec 2022 | 693.21 | 732.48 | 12135.89 | 96676.91 | 282198.8 | 392437.29 | 0 | 981810.301 | 10015.681 | 403320.354 | 1087646.68 | 2482793.016 | 693.21 | n.m. | -981077.821 | -99.93% | 2120.209 | 21.17% | -306643.444 | -76.03% | -805447.88 | -74.05% | -2090355.726 | -84.19%
897 | 180 | A18702003 | Leach RE Work | 5/1/2018 | 10/1/2018 | 16387.34 |  | 0 | 0 | 0 | 16387.34 | 0 | 0 | 0 | 0 | 0 | 0 | 16387.34 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16387.34 | n.m.
898 | 180 | TA1807311 | T/KPCO/SEL GE Relay | 7/1/2019 | 2020-12-01 |  | 15656.27 | 22879.42 | 0 | 0 | 38535.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 15656.27 | n.m. | 22879.42 | n.m. | 0 | n.m. | 0 | n.m. | 38535.69 | n.m.
899 | 180 | A17016001 | T/KY/Hazard-Jackson69kv:Reloc | 10/1/2017 | 2/1/2019 | 73200.01 | -86747.85 | 0 | 0 | 0 | -13547.84 | 0 | 0 | 0 | 0 | 0 | 0 | 73200.01 | n.m. | -86747.85 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -13547.84 | n.m.
900 | 180 | P18025007 | Cedar Creek Remote End | 5/1/2018 | Charges Continued After Dec 2022 | 11429.84 | 3974.25 | 19608.38 | 8463.99 | 125386.13 | 168862.59 | 0 | 0 | 1282.278 | 125252.305 | 329372.728 | 455907.311 | 11429.84 | n.m. | 3974.25 | n.m. | 18326.102 | 1429% | -116788.315 | -93.24% | -203986.598 | -61.93% | -287044.721 | -62.96%
901 | 180 | B180KYRMB | Reimbursable-DOP-180 Kentucky | 7/1/2019 | 9/1/2019 |  | 15117.27 | 0 | 55951.7 | 19118.65 | 90187.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 15117.27 | n.m. | 0 | n.m. | 55951.7 | n.m. | 19118.65 | n.m. | 90187.62 | n.m.
902 | 180 | A15702061 | Johnscreek-2018Geupgrade | 1/1/2018 | 12/1/2018 | 14295.31 |  | 0 | 0 | 0 | 14295.31 | 0 | 0 | 0 | 0 | 0 | 0 | 14295.31 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14295.31 | n.m.
903 | 180 | P17225016 | East Park - Princess 138kV ROW | 12/1/2017 | 2021-11-01 | 7679.82 | 207.29 | 195.44 | -13949.88 | 0 | -5867.33 | 0 | 487805.282 | 523874.715 | 587.476 | 0 | 1012267.473 | 7679.82 | n.m. | -487597.992 | -99.96% | -523679.275 | -99.96% | -14537.356 | -2475% | 0 | n.m. | -1018134.803 | -100.6%
904 | 180 | A20705029 | Barrenshe-Coleman Pre Eng | 7/1/2019 | Charges Continued After Dec 2022 |  | 13276.96 | 478.55 | 454.55 | -15004.5 | -794.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 13276.96 | n.m. | 478.55 | n.m. | 454.55 | n.m. | -15004.5 | n.m. | -794.44 | n.m.
905 | 180 | P14030104 | Leslie Ext Install to KPCo | 12/1/2017 | Charges Continued After Dec 2022 | 453.07 | 2617.29 | 905.45 | 455.59 | 10861.88 | 15293.28 | 0 | 104030.999 | 11130.228 | 589.303 | 342168.506 | 457919.036 | 453.07 | n.m. | -101413.709 | -97.48% | -10224.778 | -91.86% | -133.713 | -22.69% | -331306.626 | -96.83% | -442625.756 | -96.66%
906 | 180 | A17750109 | Allen-Prestonsburg Fld sliding | 6/1/2019 | 2022-03-01 |  | 12573.39 | 7555.35 | -20098.14 | -30.6 | 2.1778e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 12573.39 | n.m. | 7555.35 | n.m. | -20098.14 | n.m. | -30.6 | n.m. | 2.1778e-12 | n.m.
907 | 180 | P19215005 | Chadwick - Leach TLINE | 12/1/2019 | Charges Continued After Dec 2022 |  | 12434 | 121204.16 | 794177.22 | 126735.14 | 1054550.52 | 0 | 0 | 0 | 549422.235 | 119896.184 | 669318.419 | 0 | n.m. | 12434 | n.m. | 121204.16 | n.m. | 244754.985 | 44.55% | 6838.956 | 5.704% | 385232.101 | 57.56%
908 | 180 | P19092020 | Cancel -Dwale Extension T Line | 9/1/2019 | 2021-08-01 |  | 12351.3 | -2006.93 | -10344.37 | 0 | -1.819e-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 12351.3 | n.m. | -2006.93 | n.m. | -10344.37 | n.m. | 0 | n.m. | -1.819e-12 | n.m.
909 | 180 | A15702057 | Fleming-2018Geupgrade | 1/1/2018 | 3/1/2019 | 11221.28 | 524.01 | 0 | 0 | 0 | 11745.29 | 0 | 0 | 0 | 0 | 0 | 0 | 11221.28 | n.m. | 524.01 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11745.29 | n.m.
910 | 180 | P17225018 | Bellefonte - Coalton 138kV ROW | 12/1/2017 | 2021-11-01 | 5431.12 | 172.88 | 163 | -11634.45 | 0 | -5867.45 | 0 | 3565517.424 | 2777748.451 | 484.846 | 0 | 6343750.721 | 5431.12 | n.m. | -3565344.544 | -100% | -2777585.451 | -99.99% | -12119.296 | -2500% | 0 | n.m. | -6349618.171 | -100.1%
911 | 180 | P17225014 | Ramey 138 kV Extension ROW | 12/1/2017 | 2021-11-01 | 5373.62 | 172 | 162.17 | -12837.69 | 0 | -7129.9 | 0 | 487632.337 | 533178.043 | 331.533 | 0 | 1021141.913 | 5373.62 | n.m. | -487460.337 | -99.96% | -533015.873 | -99.97% | -13169.223 | -3972% | 0 | n.m. | -1028271.813 | -100.7%
912 | 180 | P18221002 | Dorton - Fleming 138kV | 5/1/2019 | Charges Continued After Dec 2022 |  | 10913.72 | 37511.57 | 22601.79 | 108252.75 | 179279.83 | 0 | 0 | 46.375 | 47293.03 | 819672.754 | 867012.159 | 0 | n.m. | 10913.72 | n.m. | 37465.195 | 80787% | -24691.24 | -52.21% | -711420.004 | -86.79% | -687732.329 | -79.32%
913 | 180 | A19750104 | Daisy-Cloverfork Failure | 9/1/2019 | 2022-04-01 |  | 10840.75 | 491870.21 | 0 | 3843.43 | 506554.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 10840.75 | n.m. | 491870.21 | n.m. | 0 | n.m. | 3843.43 | n.m. | 506554.39 | n.m.
914 | 180 | P17083003 | Garrett Switch (Removal) | 3/1/2019 | Charges Continued After Dec 2022 |  | 10549.74 | 22502.04 | 8270.9 | 3888.49 | 45211.17 | 0 | 0 | 325.686 | 3449.282 | 2851.356 | 6626.324 | 0 | n.m. | 10549.74 | n.m. | 22176.354 | 6809% | 4821.618 | 139.8% | 1037.134 | 36.37% | 38584.846 | 582.3%
915 | 180 | A20705035 | Middle Creek-Falcon 46kV Remvl | 9/1/2019 | Charges Continued After Dec 2022 |  | 10380.62 | 12076.51 | -18091.47 | 8586.96 | 12952.62 | 0 | 0 | 0 | 454746.874 | 287757.512 | 742504.386 | 0 | n.m. | 10380.62 | n.m. | 12076.51 | n.m. | -472838.344 | -104% | -279170.552 | -97.02% | -729551.766 | -98.26%
916 | 180 | P14030002 | Stinnett Loop Install OPGW | 3/1/2017 | Charges Continued After Dec 2022 | 1452.67 | 442.63 | 2501.96 | 3693.69 | 6514.11 | 14605.06 | 21852.325 | 18552.732 | 1131.263 | 58936.311 | 778.998 | 101251.629 | -20399.655 | -93.35% | -18110.102 | -97.61% | 1370.697 | 121.2% | -55242.621 | -93.73% | 5735.112 | 736.2% | -86646.569 | -85.58%
917 | 180 | 000025076 | Pikeville Transmission SC | 6/1/2017 | 2020-12-01 | -225829.77 | -1922035.03 | -9863.08 | 0 | 0 | -2157727.88 | 42.38 | 38010.524 | 25899.359 | 0 | 0 | 63952.263 | -225872.15 | -532969% | -1960045.554 | -5157% | -35762.439 | -138.1% | 0 | n.m. | 0 | n.m. | -2221680.143 | -3474%
918 | 180 | A21212002 | Bellefonte 34kV - RTU Replacem | 6/1/2019 | 2020-03-01 |  | 9441.19 | -9441.19 | 0 | 0 | 0 | 0 | 0 | 73.228 | 0 | 0 | 73.228 | 0 | n.m. | 9441.19 | n.m. | -9514.418 | -12993% | 0 | n.m. | 0 | n.m. | -73.228 | -100%
919 | 180 | A20705082 | Bellefonte138kV&69kV Needs Asm | 10/1/2019 | Charges Continued After Dec 2022 |  | 9363.66 | 7460.62 | 4255.05 | 4488.49 | 25567.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 9363.66 | n.m. | 7460.62 | n.m. | 4255.05 | n.m. | 4488.49 | n.m. | 25567.82 | n.m.
920 | 180 | P17110007 | Chadwick - Tri State #2 Reloca | 2/1/2018 | 2022-04-01 | 5058.04 | 4284.06 | 336.74 | 72574.22 | 3392.36 | 85645.42 | 0 | 179.653 | 5342.74 | 15569.874 | 8386.404 | 29478.671 | 5058.04 | n.m. | 4104.407 | 2285% | -5006 | -93.7% | 57004.346 | 366.1% | -4994.044 | -59.55% | 56166.749 | 190.5%
921 | 180 | A20705083 | Bellefonte 34.5kV St Needs Asm | 10/1/2019 | Charges Continued After Dec 2022 |  | 9234.02 | 6732.07 | 4422.5 | 628.73 | 21017.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 9234.02 | n.m. | 6732.07 | n.m. | 4422.5 | n.m. | 628.73 | n.m. | 21017.32 | n.m.
922 | 180 | A17750107 | Prestonsburg-Thelma69kVSlidROW | 4/1/2019 | 2020-01-01 |  | 9198.34 | 2.21 | 0 | 0 | 9200.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 9198.34 | n.m. | 2.21 | n.m. | 0 | n.m. | 0 | n.m. | 9200.55 | n.m.
923 | 180 | P17110006 | Chadwick - Tri State #1 Reloca | 7/1/2018 | 2022-01-01 | 2935.16 | 5917.58 | 319.1 | 6084.08 | 1.88 | 15257.8 | 0 | 0 | 21098.759 | 28455.764 | 9653.666 | 59208.189 | 2935.16 | n.m. | 5917.58 | n.m. | -20779.659 | -98.49% | -22371.684 | -78.62% | -9651.786 | -99.98% | -43950.389 | -74.23%
924 | 180 | P19092007 | Allen -East Prestonsburg TLINE | 5/1/2019 | Charges Continued After Dec 2022 |  | 8048.73 | 24537.13 | 66420.25 | 377277.78 | 476283.89 | 0 | 0 | 116.903 | 52991.262 | 0 | 53108.165 | 0 | n.m. | 8048.73 | n.m. | 24420.227 | 20889% | 13428.988 | 25.34% | 377277.78 | n.m. | 423175.725 | 796.8%
925 | 180 | P17084017 | Beaver Creek - Fremont Cut in | 9/1/2017 | Charges Continued After Dec 2022 | 3222.55 | 350.44 | 283.42 | 269.23 | 233.42 | 4359.06 | 0 | 370.69 | 409.036 | 290.516 | 392506.862 | 393577.104 | 3222.55 | n.m. | -20.25 | -5.463% | -125.616 | -30.71% | -21.286 | -7.327% | -392273.442 | -99.94% | -389218.044 | -98.89%
926 | 180 | A19750101 | B Sandy - Broadf 765 Slide ROW | 6/1/2019 | 12/1/2019 |  | 7780.32 | 0 | 0 | 0 | 7780.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 7780.32 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7780.32 | n.m.
927 | 180 | P16113004 | Cannonsburg-SNeal KY Remove | 12/1/2016 | 2022-03-01 | 2766.67 | 3221.92 | 314.24 | 174.5 | 494.27 | 6971.6 | 46.668 | 108.792 | 0 | 0 | 0 | 155.46 | 2720.002 | 5828% | 3113.128 | 2862% | 314.24 | n.m. | 174.5 | n.m. | 494.27 | n.m. | 6816.14 | 4384%
928 | 180 | P19092013 | Allen - Prestonsburg TLINE | 5/1/2019 | Charges Continued After Dec 2022 |  | 7132.98 | 51058.71 | 117738.58 | 405784.27 | 581714.54 | 0 | 0 | 47.375 | 1699.018 | 1057831.822 | 1059578.215 | 0 | n.m. | 7132.98 | n.m. | 51011.335 | 107676% | 116039.562 | 6830% | -652047.552 | -61.64% | -477863.675 | -45.1%
929 | 180 | A20705036 | Middle Creek-Prestonsburg Rebu | 9/1/2019 | Charges Continued After Dec 2022 |  | 6943.39 | 30659.97 | 45673.62 | 159685.82 | 242962.8 | 0 | 0 | 0 | 641110.918 | 361506.26 | 1002617.178 | 0 | n.m. | 6943.39 | n.m. | 30659.97 | n.m. | -595437.298 | -92.88% | -201820.44 | -55.83% | -759654.378 | -75.77%
930 | 180 | P17084022 | Henry Clay - Dorton Reconfig. | 9/1/2017 | 2021-12-01 | 1270.34 | 2432.88 | 243.1 | -6987.22 | 0 | -3040.9 | 0 | 261.146 | 423.461 | 0 | 0 | 684.607 | 1270.34 | n.m. | 2171.734 | 831.6% | -180.361 | -42.59% | -6987.22 | n.m. | 0 | n.m. | -3725.507 | -544.2%
931 | 180 | P19092021 | Cancel - Dwale Extension ROW | 11/1/2019 | 2020-05-01 |  | 6738.62 | -6738.62 | 0 | 0 | 9.0949e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 6738.62 | n.m. | -6738.62 | n.m. | 0 | n.m. | 0 | n.m. | 9.0949e-13 | n.m.
932 | 180 | O18EST033 | SCADA - SERVERS - KPCO | 10/1/2018 | 1/1/2019 | 6389.51 | 154.74 | 0 | 0 | 0 | 6544.25 | 0 | 0 | 10764.192 | 4.652 | 0 | 10768.844 | 6389.51 | n.m. | 154.74 | n.m. | -10764.192 | -100% | -4.652 | -100% | 0 | n.m. | -4224.594 | -39.23%
933 | 180 | P19092019 | Allen - Prestonsburg ROW | 11/1/2019 | Charges Continued After Dec 2022 |  | 6503.47 | 9789.38 | 51077.03 | 29644.38 | 97014.26 | 0 | 0 | 0 | 756.427 | 83419.564 | 84175.991 | 0 | n.m. | 6503.47 | n.m. | 9789.38 | n.m. | 50320.603 | 6652% | -53775.184 | -64.46% | 12838.269 | 15.25%
934 | 180 | A17016002 | T/KY/Hazard-Jkson69kv:RelocROW | 11/1/2017 | 3/1/2019 | 73809.07 | -89640.16 | 0 | 0 | 0 | -15831.09 | 0 | 0 | 0 | 0 | 0 | 0 | 73809.07 | n.m. | -89640.16 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -15831.09 | n.m.
935 | 180 | P18025008 | Beaver Creek Remote End Work | 5/1/2018 | Charges Continued After Dec 2022 | 5985.62 | 279.21 | 225.82 | 1111.34 | 28434.29 | 36036.28 | 0 | 0 | 0 | 0 | 0 | 0 | 5985.62 | n.m. | 279.21 | n.m. | 225.82 | n.m. | 1111.34 | n.m. | 28434.29 | n.m. | 36036.28 | n.m.
936 | 180 | P19215004 | Chadwick - England Hill ROW | 12/1/2019 | 2022-01-01 |  | 6145 | 49689.52 | 30549.09 | 1455.76 | 87839.37 | 0 | 0 | 0 | 168804.16 | -10562.33 | 158241.83 | 0 | n.m. | 6145 | n.m. | 49689.52 | n.m. | -138255.07 | -81.9% | 12018.09 | -113.8% | -70402.46 | -44.49%
937 | 180 | A15702056 | Topmost SS Failure | 8/1/2017 | 2020-10-01 | -84483.3 | 24033.04 | 5571.77 | 0 | 0 | -54878.49 | 0 | 0 | 0 | 0 | 0 | 0 | -84483.3 | n.m. | 24033.04 | n.m. | 5571.77 | n.m. | 0 | n.m. | 0 | n.m. | -54878.49 | n.m.
938 | 180 | A15710050 | 2BCXLD Pikesville SC-Johns Cr | 4/1/2019 | 2020-06-01 |  | 6000 | -6000 | 0 | 0 | 0 | 0 | 0 | 682102.481 | 0 | 0 | 682102.481 | 0 | n.m. | 6000 | n.m. | -688102.481 | -100.9% | 0 | n.m. | 0 | n.m. | -682102.481 | -100%
939 | 180 | P17083005 | Hays Branch S.S | 4/1/2019 | Charges Continued After Dec 2022 |  | 5860.03 | 19603.73 | 27791.61 | 2907.28 | 56162.65 | 0 | 0 | 244.67 | 29902.444 | 5844.224 | 35991.338 | 0 | n.m. | 5860.03 | n.m. | 19359.06 | 7912% | -2110.834 | -7.059% | -2936.944 | -50.25% | 20171.312 | 56.04%
940 | 180 | A20705073 | Sprigg-StoneKP 46kV KY | 10/1/2019 | 2020-07-01 |  | 5818.65 | -5818.65 | 0 | 0 | -9.0949e-13 | 0 | 0 | 0 | 104.984 | 0 | 104.984 | 0 | n.m. | 5818.65 | n.m. | -5818.65 | n.m. | -104.984 | -100% | 0 | n.m. | -104.984 | -100%
941 | 180 | P18221003 | Hazard - Fleming 69kV | 5/1/2019 | Charges Continued After Dec 2022 |  | 5365.09 | 2146.77 | 2641.11 | 123809.83 | 133962.8 | 0 | 0 | 50.296 | 236968.218 | 1257002.402 | 1494020.916 | 0 | n.m. | 5365.09 | n.m. | 2096.474 | 4168% | -234327.108 | -98.89% | -1133192.572 | -90.15% | -1360058.116 | -91.03%
942 | 180 | P19215006 | Chadwick - Leach ROW | 12/1/2019 | 2022-01-01 |  | 5355 | 48354.22 | 15467.41 | 1165.79 | 70342.42 | 0 | 0 | 0 | 162897.295 | 7031.194 | 169928.489 | 0 | n.m. | 5355 | n.m. | 48354.22 | n.m. | -147429.885 | -90.5% | -5865.404 | -83.42% | -99586.069 | -58.6%
943 | 180 | A15710044 | 2 BCXLD Beckham - Vicco TelMod | 4/1/2019 | 2020-06-01 |  | 4775.02 | -4775.02 | 0 | 0 | -1.819e-12 | 0 | 0 | 28574.161 | 0 | 0 | 28574.161 | 0 | n.m. | 4775.02 | n.m. | -33349.181 | -116.7% | 0 | n.m. | 0 | n.m. | -28574.161 | -100%
944 | 180 | P19092011 | McKinney -Allen reconfigure | 7/1/2019 | Charges Continued After Dec 2022 |  | 4328.28 | 24578.55 | 99815.46 | 463091.94 | 591814.23 | 0 | 0 | 36.032 | 553.99 | 1062433.698 | 1063023.72 | 0 | n.m. | 4328.28 | n.m. | 24542.518 | 68113% | 99261.47 | 17918% | -599341.758 | -56.41% | -471209.49 | -44.33%
945 | 180 | P17084023 | Henry Clay - Elk. City Reconfi | 9/1/2017 | 2021-12-01 | 1577.5 | 192.6 | 155.78 | -4477.5 | 0 | -2551.62 | 0 | 250.115 | 324.822 | 70.911 | 0 | 645.848 | 1577.5 | n.m. | -57.515 | -23% | -169.042 | -52.04% | -4548.411 | -6414% | 0 | n.m. | -3197.468 | -495.1%
946 | 180 | P18221004 | Fleming - Fremont 69kV | 5/1/2019 | Charges Continued After Dec 2022 |  | 4246.65 | 1485.88 | 4546.75 | 13071.14 | 23350.42 | 0 | 0 | 46.375 | 356661.114 | 2156935.73 | 2513643.219 | 0 | n.m. | 4246.65 | n.m. | 1439.505 | 3104% | -352114.364 | -98.73% | -2143864.59 | -99.39% | -2490292.799 | -99.07%
947 | 180 | P19092017 | McKinney - Allen ROW | 11/1/2019 | Charges Continued After Dec 2022 |  | 4214.9 | 784.89 | 37585.66 | 13958.49 | 56543.94 | 0 | 0 | 0 | 238.708 | 52790.354 | 53029.062 | 0 | n.m. | 4214.9 | n.m. | 784.89 | n.m. | 37346.952 | 15645% | -38831.864 | -73.56% | 3514.878 | 6.628%
948 | 180 | A20705067 | McInness SW Needs Assessment | 11/1/2019 | Charges Continued After Dec 2022 |  | 4015.7 | 2880.42 | 227.89 | 197.59 | 7321.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 4015.7 | n.m. | 2880.42 | n.m. | 227.89 | n.m. | 197.59 | n.m. | 7321.6 | n.m.
949 | 180 | P19104012 | Bellefonte Ext (KY) ROW | 7/1/2019 | Charges Continued After Dec 2022 |  | 3995.08 | 19288.79 | -4339.16 | -22678.33 | -3733.62 | 0 | 0 | 8.174 | 355.587 | -615.796 | -252.035 | 0 | n.m. | 3995.08 | n.m. | 19280.616 | 235877% | -4694.747 | -1320% | -22062.534 | 3583% | -3481.585 | 1381%
950 | 180 | A15702059 | Morganfork-2018Geupgrade | 3/1/2018 | 12/1/2018 | 3951.17 |  | 0 | 0 | 0 | 3951.17 | 0 | 0 | 0 | 0 | 0 | 0 | 3951.17 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3951.17 | n.m.
951 | 180 | P18221010 | Dorton Remote End | 5/1/2019 | Charges Continued After Dec 2022 |  | 3802.9 | 1350.09 | 5335.2 | 9619.56 | 20107.75 | 0 | 0 | 79.008 | 171.707 | 33400.99 | 33651.705 | 0 | n.m. | 3802.9 | n.m. | 1271.082 | 1609% | 5163.493 | 3007% | -23781.43 | -71.2% | -13543.955 | -40.25%
952 | 180 | P16116002 | Stinnett - Pineville Removal | 11/1/2016 | 2021-12-01 | 1011.72 | 556.48 | 134.03 | -3852.4 | 0 | -2150.17 | 20.28 | 411.545 | 190.107 | 166.328 | 0 | 788.26 | 991.44 | 4889% | 144.935 | 35.22% | -56.077 | -29.5% | -4018.728 | -2416% | 0 | n.m. | -2938.43 | -372.8%
953 | 180 | P19092008 | Allen -East Prestonsburg ROW | 11/1/2019 | Charges Continued After Dec 2022 |  | 3708.47 | 5983.13 | 25245.17 | 3252.05 | 38188.82 | 0 | 0 | 0 | 441.787 | 77364.828 | 77806.615 | 0 | n.m. | 3708.47 | n.m. | 5983.13 | n.m. | 24803.383 | 5614% | -74112.778 | -95.8% | -39617.795 | -50.92%
954 | 180 | P19092012 | Betsy Layne - Allen Reconfigur | 5/1/2019 | Charges Continued After Dec 2022 |  | 3298.96 | 6064.84 | 35547.16 | 14941.34 | 59852.3 | 0 | 0 | 18.924 | 196.584 | 51108.364 | 51323.872 | 0 | n.m. | 3298.96 | n.m. | 6045.916 | 31948% | 35350.576 | 17982% | -36167.024 | -70.77% | 8528.428 | 16.62%
955 | 180 | P19091003 | Middle Creek- Prestonsburg | 11/1/2019 | Charges Continued After Dec 2022 |  | 3283.18 | 54282.33 | 3752.49 | 2879.67 | 64197.67 | 0 | 0 | 0 | 2307.389 | 0 | 2307.389 | 0 | n.m. | 3283.18 | n.m. | 54282.33 | n.m. | 1445.101 | 62.63% | 2879.67 | n.m. | 61890.281 | 2682%
956 | 180 | A15710047 | 2BCXLD Jeff - Daisy TelModFib | 4/1/2019 | 2020-06-01 |  | 3254.54 | -3254.54 | 0 | 0 | -3.1832e-12 | 0 | 0 | 682160.178 | 0 | 0 | 682160.178 | 0 | n.m. | 3254.54 | n.m. | -685414.718 | -100.5% | 0 | n.m. | 0 | n.m. | -682160.178 | -100%
957 | 180 | P17084021 | DO NOT USE | 9/1/2017 | 2021-03-01 | 128.28 | 135.53 | -2790.51 | -250.91 | 0 | -2777.61 | 0 | 177.813 | 8387.506 | 137.693 | 0 | 8703.012 | 128.28 | n.m. | -42.283 | -23.78% | -11178.016 | -133.3% | -388.603 | -282.2% | 0 | n.m. | -11480.622 | -131.9%
958 | 180 | P17084038 | Dorton Remote End | 11/1/2017 | 2021-12-01 | -2927.7 | 134.31 | 834.81 | -3848.41 | 1.4211e-14 | -5806.99 | 0 | 117.323 | 150.094 | 63.31 | 0 | 330.727 | -2927.7 | n.m. | 16.987 | 14.48% | 684.716 | 456.2% | -3911.72 | -6179% | 1.4211e-14 | n.m. | -6137.717 | -1856%
959 | 180 | P19092018 | Betsy Layne - Allen ROW | 11/1/2019 | Charges Continued After Dec 2022 |  | 2979.9 | 2431.32 | -785.13 | -4036.09 | 590 | 0 | 0 | 0 | 255.805 | 27839.664 | 28095.469 | 0 | n.m. | 2979.9 | n.m. | 2431.32 | n.m. | -1040.935 | -406.9% | -31875.754 | -114.5% | -27505.469 | -97.9%
960 | 180 | P17084020 | Elwood - Henry Cl. Recon. @ EL | 9/1/2017 | Charges Continued After Dec 2022 | 122.19 | 129.1 | 3063.31 | 219.08 | 171.37 | 3705.05 | 0 | 169.378 | 151.171 | 129.574 | 175489.81 | 175939.933 | 122.19 | n.m. | -40.278 | -23.78% | 2912.139 | 1926% | 89.506 | 69.08% | -175318.44 | -99.9% | -172234.883 | -97.89%
961 | 180 | P17076006 | Kenwood Extension ROW | 10/1/2017 | Charges Continued After Dec 2022 | 46.89 | 1738.4 | 17422.44 | 55429.05 | 87068.26 | 161705.04 | 0 | 65.017 | 104372.527 | 330.898 | 974192.082 | 1078960.524 | 46.89 | n.m. | 1673.383 | 2574% | -86950.087 | -83.31% | 55098.152 | 16651% | -887123.822 | -91.06% | -917255.484 | -85.01%
962 | 180 | P18066001 | Chadwick - England Hill PQ Mit | 4/1/2018 | 2021-01-01 | 2570.05 | 119.88 | -2454.37 | -235.56 | 0 | 8.5265e-13 | 0 | 0 | 137.352 | 0 | 0 | 137.352 | 2570.05 | n.m. | 119.88 | n.m. | -2591.722 | -1887% | -235.56 | n.m. | 0 | n.m. | -137.352 | -100%
963 | 180 | A15710071 | Morehead Station TTMP | 7/1/2019 | Charges Continued After Dec 2022 |  | 2591.81 | 7483.7 | 10318.96 | 4398.83 | 24793.3 | 0 | 0 | 16.355 | 33845.464 | 20552.018 | 54413.837 | 0 | n.m. | 2591.81 | n.m. | 7467.345 | 45658% | -23526.504 | -69.51% | -16153.188 | -78.6% | -29620.537 | -54.44%
964 | 180 | A15710043 | 2BCXLD Topmost 138 - Beckham 1 | 4/1/2019 | 2020-06-01 |  | 2588.17 | -2588.17 | 0 | 0 | 2.7285e-12 | 0 | 0 | 26646.559 | 0 | 0 | 26646.559 | 0 | n.m. | 2588.17 | n.m. | -29234.729 | -109.7% | 0 | n.m. | 0 | n.m. | -26646.559 | -100%
965 | 180 | P17084029 | New Henry Clay Extension | 10/1/2017 | 2021-11-01 | 1217.05 | 112.59 | 91.06 | -2617.79 | 0 | -1197.09 | 0 | 146.231 | 125.846 | 455.802 | 0 | 727.879 | 1217.05 | n.m. | -33.641 | -23.01% | -34.786 | -27.64% | -3073.592 | -674.3% | 0 | n.m. | -1924.969 | -264.5%
966 | 180 | P17084013 | Henry Clay S.S Retirement | 9/1/2017 | 2021-11-01 | -2906.76 | 109.42 | 88.51 | -2544.29 | 0 | -5253.12 | 0 | 115.315 | 128.313 | 41.33 | 0.006 | 284.964 | -2906.76 | n.m. | -5.895 | -5.112% | -39.803 | -31.02% | -2585.62 | -6256% | -0.006 | -100% | -5538.084 | -1943%
967 | 180 | A20705057 | Big Sandy Station Pre Eng | 9/1/2019 | Charges Continued After Dec 2022 |  | 2247.48 | 12258.4 | 1515.55 | 444.33 | 16465.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 2247.48 | n.m. | 12258.4 | n.m. | 1515.55 | n.m. | 444.33 | n.m. | 16465.76 | n.m.
968 | 180 | P18090001 | Inez Proactive Rehab Work | 7/1/2018 | 5/1/2019 | 24526.39 | -22312.19 | 0 | 0 | 0 | 2214.2 | 0 | 0 | 0 | 0 | 0 | 0 | 24526.39 | n.m. | -22312.19 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2214.2 | n.m.
969 | 180 | A20705001 | Inez Station Pre-Eng | 8/1/2019 | Charges Continued After Dec 2022 |  | 2127.29 | -583.09 | 873.85 | -2296.93 | 121.12 | 0 | 0 | 0 | 250.817 | 0 | 250.817 | 0 | n.m. | 2127.29 | n.m. | -583.09 | n.m. | 623.033 | 248.4% | -2296.93 | n.m. | -129.697 | -51.71%
970 | 180 | A15710045 | 2BCXLD Vicco - Jeff TelModFib | 4/1/2019 | 2020-06-01 |  | 2118.37 | -2118.37 | 0 | 0 | 2.7285e-12 | 0 | 0 | 463393.673 | 0 | 0 | 463393.673 | 0 | n.m. | 2118.37 | n.m. | -465512.043 | -100.5% | 0 | n.m. | 0 | n.m. | -463393.673 | -100%
971 | 180 | A15710061 | Johns Creek Station TTMP | 10/1/2019 | 2021-05-01 |  | 1983.77 | 17697.72 | 11383.58 | 0 | 31065.07 | 0 | 0 | 31333.354 | 5365.331 | 0 | 36698.685 | 0 | n.m. | 1983.77 | n.m. | -13635.634 | -43.52% | 6018.249 | 112.2% | 0 | n.m. | -5633.615 | -15.35%
972 | 180 | DP14K02T0 | KP/Raccoon Sta - T ROW | 10/1/2018 | 2021-06-01 | 1175.66 | 706.82 | 395.75 | 75.25 | 0 | 2353.48 | 0 | 0 | 0 | 0 | 0 | 0 | 1175.66 | n.m. | 706.82 | n.m. | 395.75 | n.m. | 75.25 | n.m. | 0 | n.m. | 2353.48 | n.m.
973 | 180 | P17084018 | Beaver Creek - Elwood Retire | 9/1/2017 | Charges Continued After Dec 2022 | 76.6 | 80.91 | -2162.63 | 7520.6 | 900.48 | 6415.96 | 0 | 106.179 | 90.451 | 0 | -168.76 | 27.87 | 76.6 | n.m. | -25.269 | -23.8% | -2253.081 | -2491% | 7520.6 | n.m. | 1069.24 | -633.6% | 6388.09 | 22921%
974 | 180 | P18066003 | Kenova-Eng. Hill KY PQ Mit | 4/1/2018 | 2020-04-01 | 1988.55 | -425.91 | -1562.64 | 0 | 0 | 2.2737e-13 | 0 | 0 | 819078.719 | 0 | 0 | 819078.719 | 1988.55 | n.m. | -425.91 | n.m. | -820641.359 | -100.2% | 0 | n.m. | 0 | n.m. | -819078.719 | -100%
975 | 180 | A15710051 | 2BCXLD Johns Creek - Coleman T | 10/1/2019 | 2020-03-01 |  | 1500 | -1500 | 0 | 0 | 0 | 0 | 0 | 1003819.162 | 0 | 0 | 1003819.162 | 0 | n.m. | 1500 | n.m. | -1005319.162 | -100.1% | 0 | n.m. | 0 | n.m. | -1003819.162 | -100%
976 | 180 | P18066005 | ASFI Tap PQ Mitigations | 4/1/2018 | 2020-02-01 | 1333.13 | 62.18 | -1395.31 | 0 | 0 | 2.2737e-13 | 0 | 0 | 822345.199 | 0 | 0 | 822345.199 | 1333.13 | n.m. | 62.18 | n.m. | -823740.509 | -100.2% | 0 | n.m. | 0 | n.m. | -822345.199 | -100%
977 | 180 | P18025012 | Cedar Creek - Elwood TLINE Wor | 9/1/2018 | Charges Continued After Dec 2022 | 1078.89 | 240.66 | 2466.39 | 7141.76 | 32597.76 | 43525.46 | 0 | 0 | 67.873 | 29008.001 | 188819.34 | 217895.214 | 1078.89 | n.m. | 240.66 | n.m. | 2398.517 | 3534% | -21866.241 | -75.38% | -156221.58 | -82.74% | -174369.754 | -80.02%
978 | 180 | P17083034 | Morgan Fork Remote End | 3/1/2019 | Charges Continued After Dec 2022 |  | 1189.06 | 4759.22 | 3019.2 | 9499.46 | 18466.94 | 0 | 0 | 433.637 | 35808.604 | 112493.974 | 148736.215 | 0 | n.m. | 1189.06 | n.m. | 4325.583 | 997.5% | -32789.404 | -91.57% | -102994.514 | -91.56% | -130269.275 | -87.58%
979 | 180 | DP16K03C0 | Tygart Sta - T line work | 11/1/2019 | Charges Continued After Dec 2022 |  | 1087.28 | 13790.78 | 613.74 | 8368.71 | 23860.51 | 0 | 0 | 0 | 0 | 1.628 | 1.628 | 0 | n.m. | 1087.28 | n.m. | 13790.78 | n.m. | 613.74 | n.m. | 8367.082 | 513949% | 23858.882 | 1465533%
980 | 180 | A15710046 | 2BCXLD Jeff - Hazard TelModFib | 4/1/2019 | 2020-06-01 |  | 948.88 | -948.88 | 0 | 0 | 1.1369e-13 | 0 | 0 | 347607.277 | 0 | 0 | 347607.277 | 0 | n.m. | 948.88 | n.m. | -348556.157 | -100.3% | 0 | n.m. | 0 | n.m. | -347607.277 | -100%
981 | 180 | P17225008 | Princess Station | 12/1/2017 | 2020-11-01 | 35077.43 | -36215.67 | -900.04 | 0 | 0 | -2038.28 | 0 | 646748.465 | -2450.806 | 8.71 | 0 | 644306.369 | 35077.43 | n.m. | -682964.135 | -105.6% | 1550.766 | -63.28% | -8.71 | -100% | 0 | n.m. | -646344.649 | -100.3%
982 | 180 | A15710064 | 2BCXLD Sprigg-Cinderella KY Te | 3/1/2019 | 2020-10-01 |  | 895.36 | -895.36 | 0 | 0 | -3.4106e-13 | 0 | 0 | 365613.498 | 0 | 0 | 365613.498 | 0 | n.m. | 895.36 | n.m. | -366508.858 | -100.2% | 0 | n.m. | 0 | n.m. | -365613.498 | -100%
983 | 180 | P17076010 | Van Lear - Kenwood Str Replace | 6/1/2018 | Charges Continued After Dec 2022 | 42.46 | 830.67 | 31.47 | 29.88 | 25.93 | 960.41 | 0 | 0 | 44.766 | 38.073 | 263118.282 | 263201.121 | 42.46 | n.m. | 830.67 | n.m. | -13.296 | -29.7% | -8.193 | -21.52% | -263092.352 | -99.99% | -262240.711 | -99.64%
984 | 180 | P17083008 | Hays Br. - Morgan Frk. 138 TLN | 3/1/2019 | Charges Continued After Dec 2022 |  | 834.47 | 1279.73 | 15586.49 | 38981.8 | 56682.49 | 0 | 0 | 1374.773 | 390183.817 | 1334487.47 | 1726046.06 | 0 | n.m. | 834.47 | n.m. | -95.043 | -6.913% | -374597.327 | -96.01% | -1295505.67 | -97.08% | -1669363.57 | -96.72%
985 | 180 | P14030101 | Leslie - Clover Fork Line Work | 3/1/2017 | Charges Continued After Dec 2022 | 29.74 | 31.44 | 1313.02 | 2176.04 | 116.34 | 3666.58 | 17.94 | 24328.323 | 985.432 | 36.225 | 1301.888 | 26669.808 | 11.8 | 65.77% | -24296.883 | -99.87% | 327.588 | 33.24% | 2139.815 | 5907% | -1185.548 | -91.06% | -23003.228 | -86.25%
986 | 180 | A15710052 | 2BCXLD Falcon - West Paintsvil | 11/1/2019 | 2020-06-01 |  | 700 | -700 | 0 | 0 | 0 | 0 | 0 | 26564.135 | 0 | 0 | 26564.135 | 0 | n.m. | 700 | n.m. | -27264.135 | -102.6% | 0 | n.m. | 0 | n.m. | -26564.135 | -100%
987 | 180 | P17083006 | Garrett - Eastern 138 TLN | 3/1/2019 | Charges Continued After Dec 2022 |  | 667.8 | 13165.13 | 62984.01 | 67256.54 | 144073.48 | 0 | 0 | 980134.397 | 1150473.498 | 1180724.7 | 3311332.595 | 0 | n.m. | 667.8 | n.m. | -966969.267 | -98.66% | -1087489.488 | -94.53% | -1113468.16 | -94.3% | -3167259.115 | -95.65%
988 | 180 | DP16K03C1 | Tygart Sta - T line work | 12/1/2019 | Charges Continued After Dec 2022 |  | 663.94 | 1246.26 | 63.13 | 6409 | 8382.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 663.94 | n.m. | 1246.26 | n.m. | 63.13 | n.m. | 6409 | n.m. | 8382.33 | n.m.
989 | 180 | A15710042 | 2BCXL Topmost 138 TelModFib | 4/1/2019 | 2020-05-01 |  | 650.61 | -650.61 | 0 | 0 | 6.8212e-13 | 0 | 0 | 405448.976 | 0 | 0 | 405448.976 | 0 | n.m. | 650.61 | n.m. | -406099.586 | -100.2% | 0 | n.m. | 0 | n.m. | -405448.976 | -100%
990 | 180 | P14030016 | Leslie - Stinnett ROW (KPCo) | 11/1/2016 | Charges Continued After Dec 2022 | 119.15 | 7.68 | 3535.24 | 41223.69 | 210289.11 | 255174.87 | 5.99 | 579872.526 | 22304.447 | 152.081 | 7482.17 | 609817.214 | 113.16 | 1889% | -579864.846 | -100% | -18769.207 | -84.15% | 41071.609 | 27006% | 202806.94 | 2711% | -354642.344 | -58.16%
991 | 180 | A15702062 | Morehead Station: Stn Entrnce | 5/1/2019 | 2022-06-01 |  | 482.37 | 307.12 | 2308.53 | -3136.26 | -38.24 | 0 | 0 | 24045.057 | 137.023 | 63967.21 | 88149.29 | 0 | n.m. | 482.37 | n.m. | -23737.937 | -98.72% | 2171.507 | 1585% | -67103.47 | -104.9% | -88187.53 | -100%
992 | 180 | P18221014 | Fleming (Jackhorn) 138KV ADSS | 10/1/2019 | Charges Continued After Dec 2022 |  | 413.9 | 14.93 | 161.39 | 1394.68 | 1984.9 | 0 | 0 | 0 | 19294.325 | 297920.368 | 317214.693 | 0 | n.m. | 413.9 | n.m. | 14.93 | n.m. | -19132.935 | -99.16% | -296525.688 | -99.53% | -315229.793 | -99.37%
993 | 180 | P18001001 | South Neal - Leach KPCo PQ | 2/1/2018 | 2/1/2019 | 802.96 | -407.46 | 0 | -395.5 | 0 | -9.0949e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 802.96 | n.m. | -407.46 | n.m. | 0 | n.m. | -395.5 | n.m. | 0 | n.m. | -9.0949e-13 | n.m.
994 | 180 | P18066002 | Chadwick-Leach PQ Mit | 4/1/2018 | 2020-02-01 | 343.77 | 16.03 | -359.8 | 0 | 0 | 5.6843e-14 | 0 | 0 | 16.659 | 0 | 0 | 16.659 | 343.77 | n.m. | 16.03 | n.m. | -376.459 | -2260% | 0 | n.m. | 0 | n.m. | -16.659 | -100%
995 | 180 | A20705079 | McInnessMet69kV Needs Asm | 11/1/2019 | Charges Continued After Dec 2022 |  | 303.48 | 829.4 | 37.45 | 32.45 | 1202.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 303.48 | n.m. | 829.4 | n.m. | 37.45 | n.m. | 32.45 | n.m. | 1202.78 | n.m.
996 | 180 | P17083026 | Hays Br-Soft Shell Trans Fiber | 3/1/2019 | 2022-03-01 |  | 201.27 | 7.25 | 6.9 | -215.42 | 0 | 0 | 0 | 308.252 | 11083.055 | 410961.168 | 422352.475 | 0 | n.m. | 201.27 | n.m. | -301.002 | -97.65% | -11076.155 | -99.94% | -411176.588 | -100.1% | -422352.475 | -100%
997 | 180 | P14030015 | Lesile - Stinnett Removal | 11/1/2016 | Charges Continued After Dec 2022 | 247.37 | 10.35 | 8.03 | 7.42 | 6.01 | 279.18 | 196.32 | 20697 | 1012.573 | 7.283 | 0 | 21913.176 | 51.05 | 26% | -20686.65 | -99.95% | -1004.543 | -99.21% | 0.137 | 1.881% | 6.01 | n.m. | -21633.996 | -98.73%
998 | 180 | P19091004 | Middle Creek- Prestonsburg ROW | 12/1/2019 | Charges Continued After Dec 2022 |  | 133.9 | 3969.18 | 59.82 | 108.39 | 4271.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 133.9 | n.m. | 3969.18 | n.m. | 59.82 | n.m. | 108.39 | n.m. | 4271.29 | n.m.
999 | 180 | P18025010 | Kewanee Fiber Termination | 5/1/2019 | Charges Continued After Dec 2022 |  | 72.48 | 1067.87 | 837.23 | 483.1 | 2460.68 | 0 | 0 | 91.046 | 10578.86 | 65731.858 | 76401.764 | 0 | n.m. | 72.48 | n.m. | 976.824 | 1073% | -9741.63 | -92.09% | -65248.758 | -99.27% | -73941.084 | -96.78%
1000 | 180 | P18025009 | Cedar Creek Fiber Extension | 5/1/2019 | Charges Continued After Dec 2022 |  | 72.48 | 2.61 | 174.91 | 5935.09 | 6185.09 | 0 | 0 | 277.7 | 36202.04 | 168910.248 | 205389.988 | 0 | n.m. | 72.48 | n.m. | -275.09 | -99.06% | -36027.13 | -99.52% | -162975.158 | -96.49% | -199204.898 | -96.99%
1001 | 180 | P17074009 | CANCEL-Millbrook Frost TL KPCo | 9/1/2017 | 2/1/2019 | -56592.11 | 71.25 | 0 | 0 | 0 | -56520.86 | 0 | 53.385 | 0 | 0 | 0 | 53.385 | -56592.11 | n.m. | 17.865 | 33.46% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -56574.245 | -105974%
1002 | 180 | A15702049 | Cancel | 3/1/2018 | 2020-03-01 | 43902.9 | -43844.3 | -58.6 | 0 | 0 | -5.2388e-11 | 0 | 88.05 | 169.006 | 0 | 0 | 257.056 | 43902.9 | n.m. | -43932.35 | -49895% | -227.606 | -134.7% | 0 | n.m. | 0 | n.m. | -257.056 | -100%
1003 | 180 | A16928015 | Leslie Station Spare Purchase | 1/1/2019 | 2020-05-01 |  | 31.46 | -31.46 | 0 | 0 | 1.2434e-13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 31.46 | n.m. | -31.46 | n.m. | 0 | n.m. | 0 | n.m. | 1.2434e-13 | n.m.
1004 | 180 | A15702042 | Fleming XF/CB Replacements | 5/1/2017 | 11/1/2019 | 236062.7 | -265977.25 | 0 | 0 | 0 | -29914.55 | 952502.199 | 92501.93 | 11789.788 | 0 | 0 | 1056793.917 | -716439.499 | -75.22% | -358479.18 | -387.5% | -11789.788 | -100% | 0 | n.m. | 0 | n.m. | -1086708.467 | -102.8%
1005 | 180 | A15702039 | CANCELLED | 5/1/2017 | 3/1/2018 | -34645.08 |  | 0 | 0 | 0 | -34645.08 | 270011.708 | 0 | 0 | 0 | 0 | 270011.708 | -304656.788 | -112.8% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -304656.788 | -112.8%
1006 | 180 | P17074001 | CANCEL-Frost Station | 9/1/2017 | 12/1/2018 | -27468.64 |  | 0 | 0 | 0 | -27468.64 | 0 | 12.289 | 0 | 0 | 0 | 12.289 | -27468.64 | n.m. | -12.289 | -100% | 0 | n.m. | 0 | n.m. | 0 | n.m. | -27480.929 | -223622%
1007 | 180 | A18730007 | CANCELLED | 8/1/2017 | 3/1/2018 | -13147.1 |  | 0 | 0 | 0 | -13147.1 | 0 | 0 | 0 | 0 | 0 | 0 | -13147.1 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -13147.1 | n.m.
1008 | 180 | P17074010 | CANCELMillbrook Frost ROW KPCo | 9/1/2017 | 12/1/2018 | -568.37 |  | 0 | 0 | 0 | -568.37 | 0 | 0 | 0 | 0 | 0 | 0 | -568.37 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -568.37 | n.m.
1009 | 180 | A15702038 | CANCELLED | 5/1/2017 | 1/1/2019 |  | 4.46 | 0 | 0 | 0 | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 4.46 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4.46 | n.m.
1010 | 180 | A15710048 | 2BCXLD Pikeville SC extension | 4/1/2019 | 11/1/2019 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405394.767 | 0 | 0 | 405394.767 | 0 | n.m. | 0 | n.m. | -405394.767 | -100% | 0 | n.m. | 0 | n.m. | -405394.767 | -100%
1011 | 180 | P17074005 | Millbrook - Siloam Cut in | 9/1/2017 | 12/1/2019 | -788.46 | -132.91 | 0 | 0 | 0 | -921.37 | 0 | 0 | 0 | 0 | 0 | 0 | -788.46 | n.m. | -132.91 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -921.37 | n.m.
1012 | 180 | A15702040 | CANCELLED | 5/1/2017 | 5/1/2019 | -5496.74 | -250.74 | 0 | 0 | 0 | -5747.48 | 137.07 | 0 | 0 | 0 | 0 | 137.07 | -5633.81 | -4110% | -250.74 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -5884.55 | -4293%
1013 | 180 | A18730006 | CANCELLED | 8/1/2017 | 3/1/2018 | -18757.84 |  | 0 | 0 | 0 | -18757.84 | 0 | 0 | 0 | 0 | 0 | 0 | -18757.84 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -18757.84 | n.m.
1014 | 180 | P12088004 | Bellefonte 69 BUS TIE REMOVE | 4/1/2016 | 5/1/2018 | -8018.88 |  | 0 | 0 | 0 | -8018.88 | 0 | 0 | 0 | 0 | 0 | 0 | -8018.88 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -8018.88 | n.m.
1015 | 180 | A15702037 | CANCELLED | 5/1/2017 | 5/1/2018 | -45046.03 |  | 0 | 0 | 0 | -45046.03 | 460435.414 | 0 | 0 | 0 | 0 | 460435.414 | -505481.444 | -109.8% | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -505481.444 | -109.8%
1016 | 180 | A15702043 | Beaver Creek CB AB replace | 5/1/2017 | 11/1/2019 | 51476.16 | -73966.11 | 0 | 0 | 0 | -22489.95 | 601.43 | 0 | 4066.702 | 0 | 0 | 4668.132 | 50874.73 | 8459% | -73966.11 | n.m. | -4066.702 | -100% | 0 | n.m. | 0 | n.m. | -27158.082 | -581.8%
1017 | 180 | P17083009 | Hays Br. Morgan Frk. 138 ROW | 3/1/2019 | 3/1/2019 |  | -393.38 | 3970 | 16961.55 | -17888.17 | 2650 | 0 | 0 | 267.193 | 64314.847 | 121456.57 | 186038.61 | 0 | n.m. | -393.38 | n.m. | 3702.807 | 1386% | -47353.297 | -73.63% | -139344.74 | -114.7% | -183388.61 | -98.58%
1018 | 180 | P10115004 | Canceled | Charges Began Prior to Jan 2015 | 12/1/2019 | 2349.12 | -16199.45 | 0 | 0 | 0 | -13850.33 | 0 | 0 | 0 | 0 | 0 | 0 | 2349.12 | n.m. | -16199.45 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -13850.33 | n.m.
1019 | 180 | P11028004 | CANCELLED | Charges Began Prior to Jan 2015 | 7/1/2018 | -63462.89 |  | 0 | 0 | 0 | -63462.89 | 0 | 0 | 0 | 0 | 0 | 0 | -63462.89 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -63462.89 | n.m.
1020 | 180 | 000017437 | TLKYPHazard-Pineville 161kV | Charges Began Prior to Jan 2015 | 2021-01-01 | 6.87 | 7.91 | 7.46 | 7.76 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 6.87 | n.m. | 7.91 | n.m. | 7.46 | n.m. | 7.76 | n.m. | 0 | n.m. | 30 | n.m.
1021 | 180 | A20020001 | Leon-Morehead69kVRehbLine | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 26601.65 | 505255.44 | 3361001.28 | 3892858.37 | 0 | 0 | 0 | 0 | 7470558.314 | 7470558.314 | 0 | n.m. | 0 | n.m. | 26601.65 | n.m. | 505255.44 | n.m. | -4109557.034 | -55.01% | -3577699.944 | -47.89%
1022 | 180 | KEPCS2002 | KPCo Storm - Transmission | 2020-04-01 | 2022-04-01 |  |  | 3707428.12 | 625725.44 | 5205.77 | 4338359.33 | 0 | 0 | 0 | 0 | 379997.366 | 379997.366 | 0 | n.m. | 0 | n.m. | 3707428.12 | n.m. | 625725.44 | n.m. | -374791.596 | -98.63% | 3958361.964 | 1042%
1023 | 180 | A19750106 | Beaver Creek Failing Transf | 2020-04-01 | 2021-03-01 |  |  | 2311632.4 | 78632.14 |  | 2390264.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 2311632.4 | n.m. | 78632.14 | n.m. | 0 | n.m. | 2390264.54 | n.m.
1024 | 180 | A19750108 | Dewey - Inez Slide Failure | 2020-07-01 | Charges Continued After Dec 2022 |  |  | 98016.84 | 933265.79 | 1090077.15 | 2121359.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 98016.84 | n.m. | 933265.79 | n.m. | 1090077.15 | n.m. | 2121359.78 | n.m.
1025 | 180 | P19036003 | Osborne Extension TLINE | 2020-07-01 | Charges Continued After Dec 2022 |  |  | 538.37 | 229149.83 | 899424.21 | 1129112.41 | 0 | 0 | 0 | 1648104.217 | 2748597.53 | 4396701.747 | 0 | n.m. | 0 | n.m. | 538.37 | n.m. | -1418954.387 | -86.1% | -1849173.32 | -67.28% | -3267589.337 | -74.32%
1026 | 180 | P19215012 | Leach - South Neal KY TLINE | 2020-05-01 | 2022-07-01 |  |  | 80797.18 | 731379.9 | 2438.86 | 814615.94 | 0 | 0 | 0 | 486778.995 | 15945.368 | 502724.363 | 0 | n.m. | 0 | n.m. | 80797.18 | n.m. | 244600.905 | 50.25% | -13506.508 | -84.7% | 311891.577 | 62.04%
1027 | 180 | P19305001 | Orinoco - Stone TLINE | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 86426.62 | 129793.57 | 466356.57 | 682576.76 | 0 | 0 | 0 | 2159655.78 | 4458052.974 | 6617708.754 | 0 | n.m. | 0 | n.m. | 86426.62 | n.m. | -2029862.21 | -93.99% | -3991696.404 | -89.54% | -5935131.994 | -89.69%
1028 | 180 | P17083002 | Garrett - Soft Shell 138kV ROW | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 204560.44 | 138169.35 | 179161.36 | 521891.15 | 0 | 0 | 4236034.691 | 269100.192 | -567.77 | 4504567.113 | 0 | n.m. | 0 | n.m. | -4031474.251 | -95.17% | -130930.842 | -48.66% | 179729.13 | -31655% | -3982675.963 | -88.41%
1029 | 180 | A19750107 | Beaver Creek-Betsy Lane Failur | 2020-06-01 | 2021-10-01 |  |  | 509713.89 | 139727.85 |  | 649441.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 509713.89 | n.m. | 139727.85 | n.m. | 0 | n.m. | 649441.74 | n.m.
1030 | 180 | A20020002 | Leon-Morehead69kVRehab ROW | 2020-10-01 | Charges Continued After Dec 2022 |  |  | 17384.43 | 277997.08 | 224789.35 | 520170.86 | 0 | 0 | 0 | 0 | 717.456 | 717.456 | 0 | n.m. | 0 | n.m. | 17384.43 | n.m. | 277997.08 | n.m. | 224071.894 | 31231% | 519453.404 | 72402%
1031 | 180 | A19750109 | Hazard - Pineville | 2020-07-01 | 2022-03-01 |  |  | 472322.59 | 71767.62 | 1704.85 | 545795.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 472322.59 | n.m. | 71767.62 | n.m. | 1704.85 | n.m. | 545795.06 | n.m.
1032 | 180 | P19294004 | Big Sandy Remote End | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 7256.32 | 36226.62 | 492230.5 | 535713.44 | 0 | 0 | 0 | 405267.039 | 729361.518 | 1134628.557 | 0 | n.m. | 0 | n.m. | 7256.32 | n.m. | -369040.419 | -91.06% | -237131.018 | -32.51% | -598915.117 | -52.79%
1033 | 180 | P19036006 | Beaver Creek - Fleming Cut in | 2020-07-01 | Charges Continued After Dec 2022 |  |  | 80725.3 | 19565.57 | 356309.93 | 456600.8 | 0 | 0 | 0 | 3442.387 | 440553.646 | 443996.033 | 0 | n.m. | 0 | n.m. | 80725.3 | n.m. | 16123.183 | 468.4% | -84243.716 | -19.12% | 12604.767 | 2.839%
1034 | 180 | A20045063 | 0Hatfield Station Work | 2020-07-01 | Charges Continued After Dec 2022 |  |  | 21576.5 | 64070.9 | 155618.12 | 241265.52 | 0 | 0 | 0 | 159.555 | 0 | 159.555 | 0 | n.m. | 0 | n.m. | 21576.5 | n.m. | 63911.345 | 40056% | 155618.12 | n.m. | 241105.965 | 151112%
1035 | 180 | P19305016 | New Camp - Orinoco TLINE | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 21551.1 | 74711.58 | 196786.68 | 293049.36 | 0 | 0 | 0 | 802.602 | 5071249.924 | 5072052.526 | 0 | n.m. | 0 | n.m. | 21551.1 | n.m. | 73908.978 | 9209% | -4874463.244 | -96.12% | -4779003.166 | -94.22%
1036 | 180 | P19305010 | Stone Station Work | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 12528.47 | 24106.93 | 159894.74 | 196530.14 | 0 | 0 | 0 | 296138.123 | 583218.472 | 879356.595 | 0 | n.m. | 0 | n.m. | 12528.47 | n.m. | -272031.193 | -91.86% | -423323.732 | -72.58% | -682826.455 | -77.65%
1037 | 180 | P19305017 | New Camp - Orinoco ROW | 2020-03-01 | Charges Continued After Dec 2022 |  |  | 9276.2 | 22681.05 | 100593.01 | 132550.26 | 0 | 0 | 0 | 257.892 | 649557.726 | 649815.618 | 0 | n.m. | 0 | n.m. | 9276.2 | n.m. | 22423.158 | 8695% | -548964.716 | -84.51% | -517265.358 | -79.6%
1038 | 180 | P19305002 | Orinoco - Stone ROW | 2020-03-01 | Charges Continued After Dec 2022 |  |  | 8216.1 | 21872.39 | 121624.51 | 151713 | 0 | 0 | 0 | 454935.484 | 908776.044 | 1363711.528 | 0 | n.m. | 0 | n.m. | 8216.1 | n.m. | -433063.094 | -95.19% | -787151.534 | -86.62% | -1211998.528 | -88.87%
1039 | 180 | P14030011 | Wooton-Leslie ROW KPCo | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 2773.31 | 110158.49 | 39884.53 | 152816.33 | 0 | 534487.392 | 27947.089 | 112.593 | 9229.18 | 571776.254 | 0 | n.m. | -534487.392 | -100% | -25173.779 | -90.08% | 110045.897 | 97738% | 30655.35 | 332.2% | -418959.924 | -73.27%
1040 | 180 | P19305009 | Hatfield Station Work | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 7927.39 | 9847.25 | 125152.24 | 142926.88 | 0 | 0 | 0 | 137917.268 | 738561.028 | 876478.296 | 0 | n.m. | 0 | n.m. | 7927.39 | n.m. | -128070.018 | -92.86% | -613408.788 | -83.05% | -733551.416 | -83.69%
1041 | 180 | P17083007 | Garrett - Eastern 138 ROW | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 15902.02 | 58646.26 | 49290.35 | 123838.63 | 0 | 0 | 1887199.35 | 577389.914 | 1789642.414 | 4254231.678 | 0 | n.m. | 0 | n.m. | -1871297.33 | -99.16% | -518743.654 | -89.84% | -1740352.064 | -97.25% | -4130393.048 | -97.09%
1042 | 180 | P19215001 | Leach Station Work | 2020-01-01 | 2022-04-01 |  |  | 56464.98 | 108673.55 | -1034.39 | 164104.14 | 0 | 0 | 0 | 142617.524 | 5498.138 | 148115.662 | 0 | n.m. | 0 | n.m. | 56464.98 | n.m. | -33943.974 | -23.8% | -6532.528 | -118.8% | 15988.478 | 10.79%
1043 | 180 | P17083031 | Eastern-Hays Branch SS TLINE | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 4604.1 | 48763.3 | 76281.74 | 129649.14 | 0 | 0 | 2908.524 | 185979.87 | 984407.426 | 1173295.82 | 0 | n.m. | 0 | n.m. | 1695.576 | 58.3% | -137216.57 | -73.78% | -908125.686 | -92.25% | -1043646.68 | -88.95%
1044 | 180 | IT180CCIC | Cloud Computing Imp Cost-KyP T | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 9237.71 | 20777.63 | 42928.81 | 72944.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 9237.71 | n.m. | 20777.63 | n.m. | 42928.81 | n.m. | 72944.15 | n.m.
1045 | 180 | KEPCS2001 | KPCo Storm - Transmission | 2020-04-01 | 2021-10-01 |  |  | 100840.4 | 322.39 |  | 101162.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 100840.4 | n.m. | 322.39 | n.m. | 0 | n.m. | 101162.79 | n.m.
1046 | 180 | P14030010 | Leslie Loop ROW KPCo | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 2985 | 13382.6 | 58224.04 | 74591.64 | 0 | 96170.004 | 4500.82 | 129.729 | 804.006 | 101604.559 | 0 | n.m. | -96170.004 | -100% | -1515.82 | -33.68% | 13252.871 | 10216% | 57420.034 | 7142% | -27012.919 | -26.59%
1047 | 180 | A19511002 | Bellefonte SEL/GE Relay Upgrad | 2020-04-01 | 2021-05-01 |  |  | 83783.6 | 2356.68 |  | 86140.28 | 0 | 0 | 0 | 0 | 11619.948 | 11619.948 | 0 | n.m. | 0 | n.m. | 83783.6 | n.m. | 2356.68 | n.m. | -11619.948 | -100% | 74520.332 | 641.3%
1048 | 180 | P20035004 | Middle Creek-Prestonsburg ROW | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 23718.01 | 4510.4 | 23936.8 | 52165.21 | 0 | 0 | 0 | 563392.035 | 1603540.892 | 2166932.927 | 0 | n.m. | 0 | n.m. | 23718.01 | n.m. | -558881.635 | -99.2% | -1579604.092 | -98.51% | -2114767.717 | -97.59%
1049 | 180 | P17084008 | Myra 138kV Extension ROW | 2020-08-01 | Charges Continued After Dec 2022 |  |  | 8398.5 | -1349.81 | 16066.27 | 23114.96 | 0 | 0 | 203.803 | 50.651 | 960525.168 | 960779.622 | 0 | n.m. | 0 | n.m. | 8194.697 | 4021% | -1400.461 | -2765% | -944458.898 | -98.33% | -937664.662 | -97.59%
1050 | 180 | A19511007 | Wooton SEL/GE Relay Upgrade | 2020-05-01 | 2021-01-01 |  |  | 52155.79 | 0.94 |  | 52156.73 | 0 | 0 | 0 | 0 | 758.6 | 758.6 | 0 | n.m. | 0 | n.m. | 52155.79 | n.m. | 0.94 | n.m. | -758.6 | -100% | 51398.13 | 6775%
1051 | 180 | A19511003 | Big Sandy SEL/GE Relay Upgrade | 2020-02-01 | 2021-01-01 |  |  | 41173.05 | 3815.92 |  | 44988.97 | 0 | 0 | 0 | 0 | 5383.3 | 5383.3 | 0 | n.m. | 0 | n.m. | 41173.05 | n.m. | 3815.92 | n.m. | -5383.3 | -100% | 39605.67 | 735.7%
1052 | 180 | A20085001 | Betsy Layne Pole/Security | 2020-09-01 | 2022-08-01 |  |  | 7271.59 | 26737.86 | 8345.38 | 42354.83 | 0 | 0 | 0 | 0 | 17540.35 | 17540.35 | 0 | n.m. | 0 | n.m. | 7271.59 | n.m. | 26737.86 | n.m. | -9194.97 | -52.42% | 24814.48 | 141.5%
1053 | 180 | A20045015 | Prestonsburg - Thelma 46kV NA | 2020-04-01 | Charges Continued After Dec 2022 |  |  | 9581.97 | 10489.82 | 6630.41 | 26702.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 9581.97 | n.m. | 10489.82 | n.m. | 6630.41 | n.m. | 26702.2 | n.m.
1054 | 180 | A15710058 | Hazard Station TTMP | 2020-01-01 | 2021-11-01 |  |  | 23172.03 | 6876.1 |  | 30048.13 | 0 | 0 | 47000.024 | 3169.893 | 0 | 50169.917 | 0 | n.m. | 0 | n.m. | -23827.994 | -50.7% | 3706.207 | 116.9% | 0 | n.m. | -20121.787 | -40.11%
1055 | 180 | A19511001 | Baker SEL/GE Relay Upgrade | 2020-04-01 | 2021-01-01 |  |  | 23825.47 | 1.38 |  | 23826.85 | 0 | 0 | 0 | 0 | 4733.954 | 4733.954 | 0 | n.m. | 0 | n.m. | 23825.47 | n.m. | 1.38 | n.m. | -4733.954 | -100% | 19092.896 | 403.3%
1056 | 180 | P19215013 | Leach - South Neal KY ROW | 2020-06-01 | 2021-02-01 |  |  | 24768.51 | -2259.57 |  | 22508.94 | 0 | 0 | 0 | 34375.448 | 601.02 | 34976.468 | 0 | n.m. | 0 | n.m. | 24768.51 | n.m. | -36635.018 | -106.6% | -601.02 | -100% | -12467.528 | -35.65%
1057 | 180 | P18221008 | Fleming - Fremont 69kV ROW | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 1859.76 | 4806.78 | 10137.72 | 16804.26 | 0 | 0 | 136.699 | 92226.373 | 0 | 92363.072 | 0 | n.m. | 0 | n.m. | 1723.061 | 1260% | -87419.593 | -94.79% | 10137.72 | n.m. | -75558.812 | -81.81%
1058 | 180 | A19511004 | Bonnyman SEL/GE Relay Upgrade | 2020-02-01 | 2020-12-01 |  |  | 18853.12 |  |  | 18853.12 | 0 | 0 | 0 | 0 | 6966.91 | 6966.91 | 0 | n.m. | 0 | n.m. | 18853.12 | n.m. | 0 | n.m. | -6966.91 | -100% | 11886.21 | 170.6%
1059 | 180 | P19305019 | New Camp Tap ROW | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 3239.72 | 10393.57 | 4709.21 | 18342.5 | 0 | 0 | 0 | 138.154 | 10126.406 | 10264.56 | 0 | n.m. | 0 | n.m. | 3239.72 | n.m. | 10255.416 | 7423% | -5417.196 | -53.5% | 8077.94 | 78.7%
1060 | 180 | P18221007 | Hazard - Fleming 69kV ROW | 2020-05-01 | Charges Continued After Dec 2022 |  |  | 2395.06 | 2192.59 | 12268.67 | 16856.32 | 0 | 0 | 0 | 168272.272 | 0 | 168272.272 | 0 | n.m. | 0 | n.m. | 2395.06 | n.m. | -166079.682 | -98.7% | 12268.67 | n.m. | -151415.952 | -89.98%
1061 | 180 | A20045046 | Allen - Prestonsburg NIP | 2020-08-01 | Charges Continued After Dec 2022 |  |  | 11333.2 | 5375.09 | 515.22 | 17223.51 | 0 | 0 | 0 | 15.027 | 61.908 | 76.935 | 0 | n.m. | 0 | n.m. | 11333.2 | n.m. | 5360.063 | 35670% | 453.312 | 732.2% | 17146.575 | 22287%
1062 | 180 | A20045023 | Betsy Layne - S Pikeville NIP | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 9552.11 | 4915.29 | 533.22 | 15000.62 | 0 | 0 | 0 | 346.884 | 61.91 | 408.794 | 0 | n.m. | 0 | n.m. | 9552.11 | n.m. | 4568.406 | 1317% | 471.31 | 761.3% | 14591.826 | 3569%
1063 | 180 | A19511005 | Dewey SEL/GE Relay Upgrade | 2020-03-01 | 2021-01-01 |  |  | 11739.88 | 473.3 |  | 12213.18 | 0 | 0 | 0 | 0 | 3540.876 | 3540.876 | 0 | n.m. | 0 | n.m. | 11739.88 | n.m. | 473.3 | n.m. | -3540.876 | -100% | 8672.304 | 244.9%
1064 | 180 | P19091011 | Middle Creek BESS | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 326515.79 | 17766.98 | 11399.42 | 355682.19 | 0 | 0 | 0 | 3741979.027 | 1571848.426 | 5313827.453 | 0 | n.m. | 0 | n.m. | 326515.79 | n.m. | -3724212.047 | -99.53% | -1560449.006 | -99.27% | -4958145.263 | -93.31%
1065 | 180 | A21222008 | South Portsmouth Sta Fiber | 2020-04-01 | Charges Continued After Dec 2022 |  |  | 5536.97 | 4436.37 | 1359.39 | 11332.73 | 0 | 0 | 0 | 151.066 | 3423.862 | 3574.928 | 0 | n.m. | 0 | n.m. | 5536.97 | n.m. | 4285.304 | 2837% | -2064.472 | -60.3% | 7757.802 | 217%
1066 | 180 | P19305018 | New Camp Tap TLINE | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 1090.14 | 485.31 | 3375.19 | 4950.64 | 0 | 0 | 0 | 39.738 | 232946.198 | 232985.936 | 0 | n.m. | 0 | n.m. | 1090.14 | n.m. | 445.572 | 1121% | -229571.008 | -98.55% | -228035.296 | -97.88%
1067 | 180 | A20705077 | JohnsC - LeslieN1 69 Needs Asm | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 9263.48 | 306.12 | 265.39 | 9834.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 9263.48 | n.m. | 306.12 | n.m. | 265.39 | n.m. | 9834.99 | n.m.
1068 | 180 | A20705078 | LeslieNo1-Hatfield69 NeedsAsm | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 9166.29 | 302.89 | 262.61 | 9731.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 9166.29 | n.m. | 302.89 | n.m. | 262.61 | n.m. | 9731.79 | n.m.
1069 | 180 | A19511006 | Hazard SEL/GE Relay Upgrade | 2020-03-01 | 2020-12-01 |  |  | 7974.69 |  |  | 7974.69 | 0 | 0 | 0 | 0 | 8831.624 | 8831.624 | 0 | n.m. | 0 | n.m. | 7974.69 | n.m. | 0 | n.m. | -8831.624 | -100% | -856.934 | -9.703%
1070 | 180 | A21222017 | Greenup TS TTMP | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 1430.08 | 4409.15 | 1333.43 | 7172.66 | 0 | 0 | 0 | 0 | 2632.978 | 2632.978 | 0 | n.m. | 0 | n.m. | 1430.08 | n.m. | 4409.15 | n.m. | -1299.548 | -49.36% | 4539.682 | 172.4%
1071 | 180 | P17083024 | Beaver Creek Station Work | 2020-09-01 | Charges Continued After Dec 2022 |  |  | 456.21 | 3258.95 | 1010.18 | 4725.34 | 0 | 0 | 2.074 | 0 | 649.274 | 651.348 | 0 | n.m. | 0 | n.m. | 454.136 | 21897% | 3258.95 | n.m. | 360.906 | 55.59% | 4073.992 | 625.5%
1072 | 180 | P17225025 | Moore Hollow Metering | 2020-07-01 | Charges Continued After Dec 2022 |  |  | 2052.57 | -2052.57 | 136.23 | 136.23 | 0 | 486819.251 | 556357.934 | -8.113 | 0 | 1043169.072 | 0 | n.m. | -486819.251 | -100% | -554305.364 | -99.63% | -2044.457 | 25200% | 136.23 | n.m. | -1043032.842 | -99.99%
1073 | 180 | A20045085 | Leon (KP) NIP | 2020-11-01 | Charges Continued After Dec 2022 |  |  | 94.5 | 1503.17 | 519.97 | 2117.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 94.5 | n.m. | 1503.17 | n.m. | 519.97 | n.m. | 2117.64 | n.m.
1074 | 180 | A20705080 | Sidney 69kV Loop Needs Asm | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 818.46 | 27.03 | 23.46 | 868.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 818.46 | n.m. | 27.03 | n.m. | 23.46 | n.m. | 868.95 | n.m.
1075 | 180 | A20705081 | Bevins 69kV Tap Needs Asm | 2020-01-01 | Charges Continued After Dec 2022 |  |  | 818.46 | 27.03 | 23.46 | 868.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 818.46 | n.m. | 27.03 | n.m. | 23.46 | n.m. | 868.95 | n.m.
1076 | 180 | P20035003 | Do not Use - Use A20705036 | 2020-05-01 | 2020-12-01 |  |  | 783.49 |  |  | 783.49 | 0 | 0 | 0 | -91.395 | 0 | -91.395 | 0 | n.m. | 0 | n.m. | 783.49 | n.m. | 91.395 | -100% | 0 | n.m. | 874.885 | -957.3%
1077 | 180 | P17076009 | Kenwood Station Fiber Ext | 2020-06-01 | Charges Continued After Dec 2022 |  |  | 329.87 | 10.89 | 9.46 | 350.22 | 0 | 0 | 24925.484 | 14.066 | 31779.288 | 56718.838 | 0 | n.m. | 0 | n.m. | -24595.614 | -98.68% | -3.176 | -22.58% | -31769.828 | -99.97% | -56368.618 | -99.38%
1078 | 180 | P19091012 | Middle Creek Station Land | 2020-02-01 | Charges Continued After Dec 2022 |  |  | 101780.93 | 16069.72 | 2440.4 | 120291.05 | 0 | 0 | 0 | 3911.404 | 0 | 3911.404 | 0 | n.m. | 0 | n.m. | 101780.93 | n.m. | 12158.316 | 310.8% | 2440.4 | n.m. | 116379.646 | 2975%
1079 | 180 | A21222013 | 2BCXNLDMorgan County Sta Fiber | 2020-08-01 | 2021-06-01 |  |  | 1916.84 | -1916.84 |  | 0 | 0 | 0 | 0 | 29.639 | 0 | 29.639 | 0 | n.m. | 0 | n.m. | 1916.84 | n.m. | -1946.479 | -6567% | 0 | n.m. | -29.639 | -100%
1080 | 180 | P20035002 | Cancel-MiddleCreek-Falc RemROW | 2020-06-01 | 2021-02-01 |  |  | 589.75 | -589.75 |  | 0 | 0 | 0 | 0 | 210424.449 | 0 | 210424.449 | 0 | n.m. | 0 | n.m. | 589.75 | n.m. | -211014.199 | -100.3% | 0 | n.m. | -210424.449 | -100%
1081 | 180 | A21222014 | 2BCXNLD Lee City Sta Fiber | 2020-08-01 | 2021-06-01 |  |  | 1226.71 | -1226.71 |  | 0 | 0 | 0 | 0 | 35.951 | 0 | 35.951 | 0 | n.m. | 0 | n.m. | 1226.71 | n.m. | -1262.661 | -3512% | 0 | n.m. | -35.951 | -100%
1082 | 180 | A21222012 | 2BCXNLD Morehead Station Fiber | 2020-05-01 | 2021-06-01 |  |  | 2113.29 | -2113.29 |  | 0 | 0 | 0 | 0 | 101.07 | 0 | 101.07 | 0 | n.m. | 0 | n.m. | 2113.29 | n.m. | -2214.36 | -2191% | 0 | n.m. | -101.07 | -100%
1083 | 180 | P19294008 | CANCELED Inez Metering | 2020-06-01 | 2022-12-01 |  |  | 2529.31 | 7275.88 | -9805.19 | 0 | 0 | 0 | 0 | 317421.763 | 423887.794 | 741309.557 | 0 | n.m. | 0 | n.m. | 2529.31 | n.m. | -310145.883 | -97.71% | -433692.984 | -102.3% | -741309.557 | -100%
1084 | 180 | A19750110 | Dewey - Inez Slide Fail ROW | 2020-12-01 | Charges Continued After Dec 2022 |  |  | 207.4 | 70582.59 | -56864.29 | 13925.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 207.4 | n.m. | 70582.59 | n.m. | -56864.29 | n.m. | 13925.7 | n.m.
1085 | 180 | KEPCS2101 | KPCo Storm - Transmission | 2021-02-01 | Charges Continued After Dec 2022 |  |  |  | 10515418.66 | 894122.4 | 11409541.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 10515418.66 | n.m. | 894122.4 | n.m. | 11409541.06 | n.m.
1086 | 180 | TTKY180NN | Forestry KP T non-NERC | 2021-06-01 | Charges Continued After Dec 2022 |  |  |  | 4168085.95 | 1811352.1 | 5979438.05 | 0 | 0 | 0 | 2091519.731 | 3332832.76 | 5424352.491 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2076566.219 | 99.29% | -1521480.66 | -45.65% | 555085.559 | 10.23%
1087 | 180 | P19294011 | Inez Station | 2021-02-01 | Charges Continued After Dec 2022 |  |  |  | 2274057.47 | 3894764.61 | 6168822.08 | 0 | 0 | 0 | 0 | 6727064.044 | 6727064.044 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2274057.47 | n.m. | -2832299.434 | -42.1% | -558241.964 | -8.298%
1088 | 180 | P18221021 | Jackhorn 69kV Ring Bus | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 204976.33 | 2832690.64 | 3037666.97 | 0 | 0 | 0 | 0 | 19149586.468 | 19149586.468 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 204976.33 | n.m. | -16316895.828 | -85.21% | -16111919.498 | -84.14%
1089 | 180 | P18221019 | Jackhorn Station T Work | 2021-02-01 | Charges Continued After Dec 2022 |  |  |  | 1297581.99 | 2168381.52 | 3465963.51 | 0 | 0 | 0 | 0 | 5307391.92 | 5307391.92 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1297581.99 | n.m. | -3139010.4 | -59.14% | -1841428.41 | -34.7%
1090 | 180 | P19294012 | Inez XF Replace Baseline | 2021-02-01 | Charges Continued After Dec 2022 |  |  |  | 676764.94 | 2406481.19 | 3083246.13 | 0 | 0 | 0 | 0 | 3762962.714 | 3762962.714 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 676764.94 | n.m. | -1356481.524 | -36.05% | -679716.584 | -18.06%
1091 | 180 | P18221020 | Jackhorn Station D Work | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 359851.16 | 1357095.08 | 1716946.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 359851.16 | n.m. | 1357095.08 | n.m. | 1716946.24 | n.m.
1092 | 180 | A19750113 | Henry Clay-Elkhorn C. Sl Fail | 2021-03-01 | Charges Continued After Dec 2022 |  |  |  | 1221550.64 | 92314.95 | 1313865.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1221550.64 | n.m. | 92314.95 | n.m. | 1313865.59 | n.m.
1093 | 180 | A21750001 | McKinney - Allen Str51 Failure | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 23765.94 | 1523824.51 | 1547590.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 23765.94 | n.m. | 1523824.51 | n.m. | 1547590.45 | n.m.
1094 | 180 | P17083037 | Eastern Station Land Purchase | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 804301.82 | 26223.5 | 830525.32 | 0 | 0 | 0 | 0 | 18881.242 | 18881.242 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 804301.82 | n.m. | 7342.258 | 38.89% | 811644.078 | 4299%
1095 | 180 | P18025014 | S.Pike - Dorton Fiber Cable | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 17259.18 | 580182.6 | 597441.78 | 0 | 0 | 862.381 | 69910.606 | 370940.402 | 441713.389 | 0 | n.m. | 0 | n.m. | -862.381 | -100% | -52651.426 | -75.31% | 209242.198 | 56.41% | 155728.391 | 35.26%
1096 | 180 | A19750116 | Beaver Creek-McKinney Str Fail | 2021-04-01 | 2022-09-01 |  |  |  | 597711.32 | 17000.93 | 614712.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 597711.32 | n.m. | 17000.93 | n.m. | 614712.25 | n.m.
1097 | 180 | P17083041 | Eastern Station | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 7384.5 | 34072.93 | 41457.43 | 0 | 0 | 0 | 0 | 9818.94 | 9818.94 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7384.5 | n.m. | 24253.99 | 247% | 31638.49 | 322.2%
1098 | 180 | A14068006 | Baker Sta Ballistic/Wall Elect | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 28933.58 | 502259.4 | 531192.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 28933.58 | n.m. | 502259.4 | n.m. | 531192.98 | n.m.
1099 | 180 | A19750111 | Bellefonte-Raceland Slide Fail | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 509967.7 | 17142.95 | 527110.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 509967.7 | n.m. | 17142.95 | n.m. | 527110.65 | n.m.
1100 | 180 | P17083038 | Snag Fork SS | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 197218.53 | 91212.88 | 288431.41 | 0 | 0 | 0 | 0 | 31337.256 | 31337.256 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 197218.53 | n.m. | 59875.624 | 191.1% | 257094.154 | 820.4%
1101 | 180 | P19294010 | Dewey Station Remote End | 2021-02-01 | Charges Continued After Dec 2022 |  |  |  | 126909.61 | 223724.89 | 350634.5 | 0 | 0 | 0 | 0 | 324099.922 | 324099.922 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 126909.61 | n.m. | -100375.032 | -30.97% | 26534.578 | 8.187%
1102 | 180 | P19036004 | Osborne Extension ROW | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 86210.26 | 113197.53 | 199407.79 | 0 | 0 | 0 | 0 | 55928.408 | 55928.408 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 86210.26 | n.m. | 57269.122 | 102.4% | 143479.382 | 256.5%
1103 | 180 | P21043001 | Thelma-Kenwood 46kV Line | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 50354.72 | 42471.43 | 92826.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 50354.72 | n.m. | 42471.43 | n.m. | 92826.15 | n.m.
1104 | 180 | P21043008 | Kenwood-Prestonsburg 46kV Line | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 37691.81 | 27249.78 | 64941.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 37691.81 | n.m. | 27249.78 | n.m. | 64941.59 | n.m.
1105 | 180 | P19215014 | Leach Area Fiber | 2021-12-01 | Charges Continued After Dec 2022 |  |  |  | 1584.59 | 115401.58 | 116986.17 | 0 | 0 | 0 | 178838.215 | 4444.784 | 183282.999 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -177253.625 | -99.11% | 110956.796 | 2496% | -66296.829 | -36.17%
1106 | 180 | A21505004 | Morehead - Index 69kV Line NIP | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 20265.62 | 89903.05 | 110168.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 20265.62 | n.m. | 89903.05 | n.m. | 110168.67 | n.m.
1107 | 180 | P18025016 | Sprigg - Beaver Creek ROW | 2021-01-01 | 2022-06-01 |  |  |  | 95847.83 | 3586.64 | 99434.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 95847.83 | n.m. | 3586.64 | n.m. | 99434.47 | n.m.
1108 | 180 | A21505008 | Index - Helechawa 69kV NIP | 2021-09-01 | Charges Continued After Dec 2022 |  |  |  | 48926.06 | 5635.56 | 54561.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 48926.06 | n.m. | 5635.56 | n.m. | 54561.62 | n.m.
1109 | 180 | P19294009 | Inez-Martiki 138kV Line | 2021-08-01 | 2022-07-01 |  |  |  | 5926.66 | 47597.31 | 53523.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5926.66 | n.m. | 47597.31 | n.m. | 53523.97 | n.m.
1110 | 180 | A20072063 | Thelma 2021 Relay Upgrade | 2021-07-01 | 2022-02-01 |  |  |  | 36803.52 | 2802.3 | 39605.82 | 0 | 0 | 0 | 0 | 12111.252 | 12111.252 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 36803.52 | n.m. | -9308.952 | -76.86% | 27494.568 | 227%
1111 | 180 | P21043002 | Thelma-Kenwood 46kV ROW | 2021-06-01 | Charges Continued After Dec 2022 |  |  |  | 9923.5 | 8976.96 | 18900.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9923.5 | n.m. | 8976.96 | n.m. | 18900.46 | n.m.
1112 | 180 | P19037013 | Dorton Station Work | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 9385.4 | 14781.51 | 24166.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9385.4 | n.m. | 14781.51 | n.m. | 24166.91 | n.m.
1113 | 180 | P19037005 | Henry Clay - Breaks Reconfi | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 14571.68 | 16437.04 | 31008.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 14571.68 | n.m. | 16437.04 | n.m. | 31008.72 | n.m.
1114 | 180 | P21043009 | Kenwood-Prestonsburg 46kV ROW | 2021-06-01 | Charges Continued After Dec 2022 |  |  |  | 9840 | 9110.56 | 18950.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9840 | n.m. | 9110.56 | n.m. | 18950.56 | n.m.
1115 | 180 | P19037004 | Henry Clay - Dorton Reconfig. | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 16755.47 | 13582.75 | 30338.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16755.47 | n.m. | 13582.75 | n.m. | 30338.22 | n.m.
1116 | 180 | P19037014 | Breaks Station Work | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 6410.82 | 15440.38 | 21851.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6410.82 | n.m. | 15440.38 | n.m. | 21851.2 | n.m.
1117 | 180 | P21605002 | Dragon Fly Extension Line Work | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 1445.57 | 23698.78 | 25144.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1445.57 | n.m. | 23698.78 | n.m. | 25144.35 | n.m.
1118 | 180 | P19036007 | Beaver Creek Remote End | 2021-03-01 | Charges Continued After Dec 2022 |  |  |  | 19102.17 | 3855.09 | 22957.26 | 0 | 0 | 0 | 0 | 13536.782 | 13536.782 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19102.17 | n.m. | -9681.692 | -71.52% | 9420.478 | 69.59%
1119 | 180 | A21505003 | Hazard - Jackson 69kV Line NIP | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 19055.35 | 3799.8 | 22855.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 19055.35 | n.m. | 3799.8 | n.m. | 22855.15 | n.m.
1120 | 180 | A21505011 | Leslie Station NIP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 13955.73 | 6435.42 | 20391.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13955.73 | n.m. | 6435.42 | n.m. | 20391.15 | n.m.
1121 | 180 | A21505007 | Jackson - Helechawa 69kV NIP | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 15880.11 | 4016.28 | 19896.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 15880.11 | n.m. | 4016.28 | n.m. | 19896.39 | n.m.
1122 | 180 | P21043004 | Remote End Work at Thelma | 2021-07-01 | Charges Continued After Dec 2022 |  |  |  | 2064.43 | 883.95 | 2948.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2064.43 | n.m. | 883.95 | n.m. | 2948.38 | n.m.
1123 | 180 | A20072029 | Bonnyman 2021 Relay Upgr | 2021-07-01 | 2021-09-01 |  |  |  | 16480.25 |  | 16480.25 | 0 | 0 | 0 | 0 | 7105.786 | 7105.786 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 16480.25 | n.m. | -7105.786 | -100% | 9374.464 | 131.9%
1124 | 180 | P19037011 | Henry Clay-Dorton Reconfig ROW | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 2180 | 13015.54 | 15195.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2180 | n.m. | 13015.54 | n.m. | 15195.54 | n.m.
1125 | 180 | P19037012 | Henry Clay-Breaks Recon ROW | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | 1920 | 10647.36 | 12567.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1920 | n.m. | 10647.36 | n.m. | 12567.36 | n.m.
1126 | 180 | P19037006 | Poor Bottom Extension | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 2873.56 | 4644.72 | 7518.28 | 0 | 0 | 0 | 1227502.118 | 34589.002 | 1262091.12 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -1224628.558 | -99.77% | -29944.282 | -86.57% | -1254572.84 | -99.4%
1127 | 180 | A20072064 | Wooton 2021 Relay Upgrade | 2021-08-01 | 2021-10-01 |  |  |  | 8963.47 |  | 8963.47 | 0 | 0 | 0 | 0 | 6459.806 | 6459.806 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 8963.47 | n.m. | -6459.806 | -100% | 2503.664 | 38.76%
1128 | 180 | A21505005 | Baker 765kV/345kV Yard NIP | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 7566.3 | 233.31 | 7799.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7566.3 | n.m. | 233.31 | n.m. | 7799.61 | n.m.
1129 | 180 | A20077006 | Bonnyman Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 1593.92 | 1502.57 | 3096.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1593.92 | n.m. | 1502.57 | n.m. | 3096.49 | n.m.
1130 | 180 | A20077012 | Hazard Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 2123.72 | 770.36 | 2894.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2123.72 | n.m. | 770.36 | n.m. | 2894.08 | n.m.
1131 | 180 | A20077009 | Hays Branch Sta TTMP | 2021-01-01 | Charges Continued After Dec 2022 |  |  |  | 1902.08 | 899.86 | 2801.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1902.08 | n.m. | 899.86 | n.m. | 2801.94 | n.m.
1132 | 180 | A24112009 | Hatfield Sta TTMP | 2021-06-01 | Charges Continued After Dec 2022 |  |  |  | 2314.74 | 217.64 | 2532.38 | 0 | 0 | 0 | 0 | 10.848 | 10.848 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2314.74 | n.m. | 206.792 | 1906% | 2521.532 | 23244%
1133 | 180 | A24112005 | Dewey Sta TTMP | 2021-08-01 | Charges Continued After Dec 2022 |  |  |  | 2205.67 | 68.02 | 2273.69 | 0 | 0 | 0 | 0 | 10.848 | 10.848 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2205.67 | n.m. | 57.172 | 527% | 2262.842 | 20860%
1134 | 180 | A25101008 | Bellefonte 138kV Sta TTMP | 2021-11-01 | Charges Continued After Dec 2022 |  |  |  | 379.17 | 1453.41 | 1832.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 379.17 | n.m. | 1453.41 | n.m. | 1832.58 | n.m.
1135 | 180 | A19750114 | Breaks Rtg. Wall Fail - Cancel | 2021-04-01 | Charges Continued After Dec 2022 |  |  |  | 101519.1 | -100859.7 | 659.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 101519.1 | n.m. | -100859.7 | n.m. | 659.4 | n.m.
1136 | 180 | P21605001 | Big Sandy Station Work | 2021-10-01 | Charges Continued After Dec 2022 |  |  |  | -102941.8 | 64743.05 | -38198.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -102941.8 | n.m. | 64743.05 | n.m. | -38198.75 | n.m.
1137 | 180 | 180KYLSBO | Trans KY Lease Buyout | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 1250281.68 | 1250281.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1250281.68 | n.m. | 1250281.68 | n.m.
1138 | 180 | A19750118 | Prestonsburg-Middle Ck Slide F | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 80039.05 | 80039.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 80039.05 | n.m. | 80039.05 | n.m.
1139 | 180 | A21750012 | Hazard - Bonnyman 69kV Failure | 2022-08-01 | Charges Continued After Dec 2022 |  |  |  |  | 571297.28 | 571297.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 571297.28 | n.m. | 571297.28 | n.m.
1140 | 180 | A21750013 | Morehead - Index 69kV Failure | 2022-08-01 | Charges Continued After Dec 2022 |  |  |  |  | 275807.37 | 275807.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 275807.37 | n.m. | 275807.37 | n.m.
1141 | 180 | A21750004 | Hazard-Pinevll 161kV Fire Fail | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | 468820.55 | 468820.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 468820.55 | n.m. | 468820.55 | n.m.
1142 | 180 | A21750006 | Big Sandy RE for Failure | 2022-08-01 | Charges Continued After Dec 2022 |  |  |  |  | 121244.92 | 121244.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 121244.92 | n.m. | 121244.92 | n.m.
1143 | 180 | A21750007 | Hays Branch-Morgan Fork Slide | 2022-05-01 | Charges Continued After Dec 2022 |  |  |  |  | 417903.41 | 417903.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 417903.41 | n.m. | 417903.41 | n.m.
1144 | 180 | KEPCS2201 | KPCo Storm - Transmission | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 184873.32 | 184873.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 184873.32 | n.m. | 184873.32 | n.m.
1145 | 180 | A21750002 | Bonnyman-Softshell Failure | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 145551.78 | 145551.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 145551.78 | n.m. | 145551.78 | n.m.
1146 | 180 | B180KYLRR | T/KY/Non-Specific Work - Line | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | -37.57 | -37.57 | 299612.027 | 1402288.731 | 344.539 | 0 | 0 | 1702245.297 | -299612.027 | -100% | -1402288.731 | -100% | -344.539 | -100% | 0 | n.m. | -37.57 | n.m. | -1702282.867 | -100%
1147 | 180 | P21720001 | Bellefonte Station Baseline | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 62479.35 | 62479.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 62479.35 | n.m. | 62479.35 | n.m.
1148 | 180 | A21505001 | Jackson - Helechawa 69kV NIP | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 98917.02 | 98917.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 98917.02 | n.m. | 98917.02 | n.m.
1149 | 180 | A21750008 | Sprigg-Beaver Crk Slide Fail | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 59929.84 | 59929.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 59929.84 | n.m. | 59929.84 | n.m.
1150 | 180 | A21750010 | HysBrnch-Morgan Frk Slide Fail | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 11797.53 | 11797.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11797.53 | n.m. | 11797.53 | n.m.
1151 | 180 | P21027003 | Inez IPP Metering | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | -42266.5 | -42266.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -42266.5 | n.m. | -42266.5 | n.m.
1152 | 180 | P21753001 | Dewey Station | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 29200.04 | 29200.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 29200.04 | n.m. | 29200.04 | n.m.
1153 | 180 | P17083032 | Eastern - Hays Branch SS ROW | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 47294.86 | 47294.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 47294.86 | n.m. | 47294.86 | n.m.
1154 | 180 | P22113001 | Gund Switch KY T - BPID | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 21470.93 | 21470.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 21470.93 | n.m. | 21470.93 | n.m.
1155 | 180 | P22012052 | Peter Creek-Coleman | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 24855.61 | 24855.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 24855.61 | n.m. | 24855.61 | n.m.
1156 | 180 | KEPCS2202 | KPCo Storm - Transmission | 2022-12-01 | Charges Continued After Dec 2022 |  |  |  |  | 337.09 | 337.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 337.09 | n.m. | 337.09 | n.m.
1157 | 180 | P21753002 | Dewey Station Supplemental | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 13825.7 | 13825.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 13825.7 | n.m. | 13825.7 | n.m.
1158 | 180 | A21071002 | BigSandy-Brd KP 765 S&I ROW | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 5767.69 | 5767.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5767.69 | n.m. | 5767.69 | n.m.
1159 | 180 | DP16K03T0 | Tygart Sta - T line ROW | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 5832.5 | 5832.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 5832.5 | n.m. | 5832.5 | n.m.
1160 | 180 | P19036009 | Osborne Fiber Extension | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 3604.73 | 3604.73 | 0 | 0 | 0 | 0 | 79210.382 | 79210.382 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -75605.652 | -95.45% | -75605.652 | -95.45%
1161 | 180 | A21071004 | Baker-DonMarq KP 765 S&I ROW | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 9163.61 | 9163.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9163.61 | n.m. | 9163.61 | n.m.
1162 | 180 | P19104016 | Bellefonte TransFiber | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 11779.33 | 11779.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 11779.33 | n.m. | 11779.33 | n.m.
1163 | 180 | A21071003 | Baker-DonMarq KP 765 S&I | 2022-05-01 | Charges Continued After Dec 2022 |  |  |  |  | 7964.79 | 7964.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7964.79 | n.m. | 7964.79 | n.m.
1164 | 180 | P22745001 | McCoy-Elkhorn Tap Station Work | 2022-11-01 | Charges Continued After Dec 2022 |  |  |  |  | 2650.1 | 2650.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2650.1 | n.m. | 2650.1 | n.m.
1165 | 180 | P22012049 | Peter Creek-Wharncliffe (KY) | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 9766.24 | 9766.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9766.24 | n.m. | 9766.24 | n.m.
1166 | 180 | P21753004 | Thelma Remote End Work | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | 7397.08 | 7397.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 7397.08 | n.m. | 7397.08 | n.m.
1167 | 180 | A21071001 | BigSandy-Broadford KP 765 S&I | 2022-05-01 | Charges Continued After Dec 2022 |  |  |  |  | 6909.77 | 6909.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6909.77 | n.m. | 6909.77 | n.m.
1168 | 180 | P22113004 | Gund Metering Tap ROW | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 4367.77 | 4367.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 4367.77 | n.m. | 4367.77 | n.m.
1169 | 180 | P22012047 | Peter Creek-Wharncliffe KY ROW | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 9175.78 | 9175.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 9175.78 | n.m. | 9175.78 | n.m.
1170 | 180 | P21605004 | Dragon Fly Metering | 2022-08-01 | Charges Continued After Dec 2022 |  |  |  |  | 6631 | 6631 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6631 | n.m. | 6631 | n.m.
1171 | 180 | DR19K05C0 | Hazard DA 2019 Engle Tap | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | 3595.46 | 3595.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3595.46 | n.m. | 3595.46 | n.m.
1172 | 180 | P22012051 | Peter Creek-Coleman ROW | 2022-09-01 | Charges Continued After Dec 2022 |  |  |  |  | 6295.77 | 6295.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 6295.77 | n.m. | 6295.77 | n.m.
1173 | 180 | P22005002 | 47th Street Line Work | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | 2834.91 | 2834.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 2834.91 | n.m. | 2834.91 | n.m.
1174 | 180 | P22012033 | Peter Creek Land Purchase | 2022-08-01 | Charges Continued After Dec 2022 |  |  |  |  | 3482.37 | 3482.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 3482.37 | n.m. | 3482.37 | n.m.
1175 | 180 | P21720008 | Bellefonte - A.K. Steel 69kV | 2022-06-01 | Charges Continued After Dec 2022 |  |  |  |  | 1966.24 | 1966.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 1966.24 | n.m. | 1966.24 | n.m.
1176 | 180 | TTKY180NR | Forestry KY T NERC | 2022-01-01 | Charges Continued After Dec 2022 |  |  |  |  | 3231.57 | 3231.57 | 0 | 0 | 0 | 435655.642 | 700084.942 | 1135740.584 | 0 | n.m. | 0 | n.m. | 0 | n.m. | -435655.642 | -100% | -696853.372 | -99.54% | -1132509.014 | -99.72%
1177 | 180 | A25101007 | John's Creek Sta TTMP | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 954.97 | 954.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 954.97 | n.m. | 954.97 | n.m.
1178 | 180 | A25101004 | S Portsmouth Sta TTMP | 2022-03-01 | Charges Continued After Dec 2022 |  |  |  |  | 954.97 | 954.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 954.97 | n.m. | 954.97 | n.m.
1179 | 180 | P19305021 | Belfry - Stone Trans Fiber | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | 283.92 | 283.92 | 0 | 0 | 0 | 0 | 134381.706 | 134381.706 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -134097.786 | -99.79% | -134097.786 | -99.79%
1180 | 180 | P21205003 | Leslie No.1-Hatfield 69kV | 2022-05-01 | Charges Continued After Dec 2022 |  |  |  |  | 157.4 | 157.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 157.4 | n.m. | 157.4 | n.m.
1181 | 180 | P21043015 | Thelma Station | 2022-07-01 | Charges Continued After Dec 2022 |  |  |  |  | 76.77 | 76.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | 76.77 | n.m. | 76.77 | n.m.
1182 | 180 | P21027001 | Inez 138kV Station Work | 2022-02-01 | Charges Continued After Dec 2022 |  |  |  |  | -36350.35 | -36350.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -36350.35 | n.m. | -36350.35 | n.m.
1183 | 180 | P21027002 | Inez IPP T-Line Work | 2022-04-01 | Charges Continued After Dec 2022 |  |  |  |  | -147682.24 | -147682.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | n.m. | 0 | n.m. | 0 | n.m. | 0 | n.m. | -147682.24 | n.m. | -147682.24 | n.m.
1184 | 180 | Other Budgeted Projects |  | Other | Other | 0 | 0 | 0 | 0 | 0 | 0 | 49044684.249 | 13719159.661 | 14220695.83 | 12584481.757 | -17786955.15 | 71782066.347 | -49044684.249 | -100% | -13719159.661 | -100% | -14220695.83 | -100% | -12584481.757 | -100% | 17786955.15 | -100% | -71782066.347 | -100%
1185 | 180 Total |  |  |  |  | 43145011.25 | 55397644.722 | 49586793.73 | 69439750.6 | 70000351.1 | 287569551.402 | 60080293.892 | 105815700.421 | 95282031.696 | 67826879.352 | 124528959.86 | 335221165.113 | -16935282.642 | -28.19% | -50418055.699 | -47.65% | -45695237.966 | -47.96% | 1612871.248 | 2.378% | -54528608.76 | -43.79% | -47651613.711 | -14.21%
1186 | Total Kentucky Power CWIP Additions |  |  |  |  | 139702471.441 | 173948013.995 | 138263013.916 | 177155376.737 | 201583417.53 | 830652293.619 | 164281854.895 | 225834802.763 | 205491064.664 | 180249307.923 | 307681816.5696 | 965226146.7066 | -24579383.454 | -14.96% | -51886788.768 | -22.98% | -67228050.748 | -32.72% | -3093931.186 | -1.716% | -106098399.0396 | -34.48% | -134573853.0876 | -13.94%
1187
1188 | 110 | X00000317 | For Property Acctg Use Only | Property Acctg | Property Acctg | -52970703.32 | -72563908.817 | -75578922.605 | -91920236.405 | -97057042.35 | -390090813.497 | [6 empty] | -52970703.32 | n.m. | -72563908.817 | n.m. | -75578922.605 | n.m. | -91920236.405 | n.m. | -97057042.35 | n.m. | -390090813.497 | n.m.
1189 | 117 | X00000288 | For Property Acctg Use Only | Property Acctg | Property Acctg | -22703950.39 | -37706926.57 | -21147537.1 | -8817891.32 | -14430067.13 | -104806372.51 | [6 empty] | -22703950.39 | n.m. | -37706926.57 | n.m. | -21147537.1 | n.m. | -8817891.32 | n.m. | -14430067.13 | n.m. | -104806372.51 | n.m.
1190 | 180 | X00000306 | For Property Acctg Use Only | Property Acctg | Property Acctg | -31422001.35 | -49753622.32 | -57126480.06 | -64157772.67 | -46500554.34 | -248960430.74 | [6 empty] | -31422001.35 | n.m. | -49753622.32 | n.m. | -57126480.06 | n.m. | -64157772.67 | n.m. | -46500554.34 | n.m. | -248960430.74 | n.m.
1191 | Total Kentucky Power Transfers to 101/106 |  |  |  |  | -107096655.06 | -160024457.707 | -153852939.765 | -164895900.395 | -157987663.82 | -743857616.747 | 0 | 0 | 0 | 0 | 0 | 0 | -107096655.06 | n.m. | -160024457.707 | n.m. | -153852939.765 | n.m. | -164895900.395 | n.m. | -157987663.82 | n.m. | -743857616.747 | n.m.
1192
1193 | Total Kentucky Power CWIP Activity by Year |  |  |  |  | 32605816.381 | 13923556.288 | -15589925.849 | 12259476.342 | 43595753.71 | 86794676.872 | 164281854.895 | 225834802.763 | 205491064.664 | 180249307.923 | 307681816.5696 | 965226146.7066 | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m. | n.m.
1194
1195 | (1) | Represents the month project expenditures were initially recorded to CWIP (Account 107).
1196 | (2) | Represents the month project expenditures ceased being recorded to CWIP (Account 107).
1197 | Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
1198 | Other | Other amounts reflected in budget; do not directly relate to a project with actual spend during the periods presented.

## Schedule C2
Kentucky Power Company
Case No. 2023-00159
Calculation of Capital Slippage Factor
For the Five Years Ended December 31, 2022
Schedule C2
Year | Actual Annual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Slippage Factor
2018 | 139702471.441 | 164281854.895 | -24579383.454 | -14.96% | 85.04%
2019 | 173948013.995 | 225834802.763 | -51886788.768 | -22.98% | 77.02%
2020 | 138263013.916 | 205491064.664 | -67228050.748 | -32.72% | 67.28%
2021 | 177155376.737 | 180249307.923 | -3093931.186 | -1.716% | 98.28%
2022 | 201583417.53 | 307681816.5696 | -106098399.0396 | -34.48% | 65.52%
Totals | 830652293.619 | 1083538846.8146 | -252886553.1956 | -23.34% | 76.66%
Five Year Average Slippage Factor |  |  |  |  | 78.63%