## BILL SHEET
BLACK MOUNTAIN UTILITY DISTRICT
609 FOUR MILE ROAD |  |  |  | DATE
BAXTER KY 40806 |  |  |  | 2024-06-02
Phone: (606) 573-1277
BROOKS STREET SIRVICE LINE REPLACEMENT
DESCRIPTION | PER | QTY | UNIT PRICE | AMOUNT
LABOR | HR | 13 | 28.18 | 366.34
EQUIPMENT | HR | 13 | 97.75 | 1270.75
1" CTS PIPE | FT | 255 | 0.75 | 191.25
2" PCV SDR 17 | FT | 260 | 2.3 | 598
1" X 1" X 3/4" TEE | PC | 6 | 99.53 | 597.18
1" INCERTS | PC | 8 | 2.42 | 19.36
3/4" INSERTS | PC | 3 | 2.36 | 7.08
GRAVEL | TON | 2 | 25.88 | 51.76
HAND TOOLS | HR | 0.75 | 1.84 | 1.38
PIPE CUTTERS | HR | 0.25 | 0.3 | 0.08
REMOVAL OF DEBRIS | PC | 1 | 28.75 | 28.75
FUEL SURCHARGE | PC | 1 | 57.5 | 57.5
MOBIL FLEET #T6 | MILE | 11 | 1.02 | 11.22
MOBIL FLEET #T3 | MILE | 11 | 1.02 | 11.22
0
0
0
0
0
0
0
0
0
0
0
0
DISCRITION OF WORK DONE |  |  |  | 0
BROOKS STREET HAS A ONE INCH SERVICE LIN RUNNING 124 FEET ONE WAY AND 131 FEET THE OTHER. WE REPLACED LEAK
PRON LINE THAT ONCE THE LINE WAS TOOK OUT IT HAD BEEN REPAIRED 22 TIMES .
WE STARTED AT THE JUNKTION OF 840 AND BROOKS STREET REPLACING LINE WE REPLACED 124 FOOT OF ONE INCH SERVICE LINE
AND PUT THAT LINE IN A TWO INCH CASING SO THAT ROCK CAN NOT BE PUSHED THROUGH THE LINE PUT NEW FITTINGS ON THE
TWO SERVICES THAT IS ONE THE ONE INCH CTS LINE THAT RUNS ON THAT SIDE OF 840.
ON THE OTHER SIDE OF BROOK STREET WE HAVE INSTAILED 131 FEET OF ONE INCH CTS LINE IN A TWO INCH PVC CASING TO
PROTECT THE LINE. WE USED THREE FITTINGS TO HOOK UP THE THREE SERVICES AND COVERED THE LINE AND ADDED GRAVEL
TO THE DRIVE WAYS THAT WE HAD TO CROSS WITH THE NEW PIPE.
|  | SUBTOTAL |  | 3211.87
|  | TOTAL |  | 3211.87

## PARTS LIST
PRODICT # | DISCRIPTION | COST |  |  | UNIT
1 | 3/4" INSERTS | 2.05 | 2.3575 | PC | FT
2 | 3/4" X 1/8" GASKETS |  | 0 | PC | PC
3 | 3/4" PRV | 75 | 86.25 | PC | HR
4 | 3/4" PRV ADAPTER | 39.58 | 45.517 | PC | GAL
5 | 3/4" CORP STOP | 59.24 | 68.126 | PC | TON
6 | 3/4" X 3/4" COUPLINGS | 25.7 | 29.555 | PC | MILE
7 | 3/4" X 3" WRAPS |  | 0 | PC
8 | 3/4" X 5/8" SETTERS STRAIGHT |  | 0 | PC
9 | 3/4" X 5/8" SETTERS TANDOM |  | 0 | PC
10 | 3/4" X 3/4" X 1 TEE | 83.94 | 96.531 | PC
11 | 3/4" X 3/4" X 3/4" TEE | 68 | 78.2 | PC
12 | 3/4" X 90* |  | 0 | PC
13 | 3/4" SETTER CUT OFF VALVES |  | 0 | PC
14 | 3/4" G LOCK NUTS |  | 0 | PC
15 | 3/4" CTS X 3/4" CTS |  | 0 | PC
16 | 3/4" X 1" CTS | 29.21 | 33.5915 | PC
17 | 3/4" PIPE X 3/4" CTS |  | 0 | PC
18 | 3/4" X 1" CTS |  | 0 | PC
19 | 3/4" X 45* |  | 0 | PC
20 | 3/4" CTS X 3/4" PVC |  | 0 | PC
21 | 3/4" CLOSE COUPLINGS |  | 0 | PC
22 | 3/4" CTS PIPE | 0.59 | 0.6785 | PC
23 | 3/4" STREET VALVE | 55.48 | 63.802 | PC
24 | 1" STREET VALVE | 59.21 | 68.0915 | PC
25 | 1" CTS PIPE | 0.65 | 0.7475 | PC
26 | 1" INCERTS | 2.1 | 2.415 | PC
27 | 1" X 1/8" GASKETS |  | 0 | PC
28 | 1" X PRV |  | 0 | PC
29 | 1" PRV APAPTER |  | 0 | PC
30 | 1" CORP STOP |  | 0 | PC
31 | 1" X 1" COUPLINGS | 48.69 | 55.9935 | PC
32 | 1" X 3" WRAPS |  | 0 | PC
33 | 1" SETTERS STRAIGHT |  | 0 | PC
34 | 1" SETTERS TANDOM |  | 0 | PC
35 | 1" X 1" X 3/4" TEE | 86.55 | 99.5325 | PC
36 | 1" X 1" X 1" TEE |  | 0 | PC
37 | 1" X 90* | 54.03 | 62.1345 | PC
38 | 1" SETTER CUT OFF VALVES |  | 0 | PC
39 | 1" G LOCK NUTS |  | 0 | PC
40 | 1" CTS X 1" PEP |  | 0 | PC
41 | 1" PIPE X 3/4" CTS |  | 0 | PC
42 | 1" X 45* |  | 0 | PC
43 | 1" CLOSE COUPLINGS |  | 0 | PC
44 | 1" STREET 90* |  | 0 | PC
45 | 1" X 3/4" BELL REDUCER |  | 0 | PC
46 | 2" X15" WRAP |  | 0 | PC
47 | 3" X 12" WRAP |  | 0 | PC
48 | 3" X 15" WRAP | 167.03 | 192.0845 | PC
49 | 4" X12" WRAP | 217.8 | 250.47 | PC
50 | 4" X 15" WRAP | 183.35 | 210.8525 | PC
51 | 4" X 24" WRAP |  | 0 | PC
52 | 6" X 12" WRAP |  | 0 | PC
53 | 6" X 15" WRAP | 198.44 | 228.206 | PC
54 | 6" X 24" WRAP |  | 0 | PC
55 | 8" X 12" WRAP |  | 0 | PC
56 | 8" X 15" WRAP |  | 0 | PC
57 | 8" X 24" WRAP |  | 0 | PC
58 | 2" MJ 45* |  | 0 | PC
59 | 2" MJ 90* | 84.99 | 97.7385 | PC
60 | 2" MJ COUPLING |  | 0 | PC
61 | EXCAVATOR |  | 0 | PC
62 | 2" 45* HYMAX |  | 0 | PC
63 | 2" 90* HYMAX |  | 0 | PC
64 | 2" COUPLING HYMAX |  | 0 | PC
65 | 2" TEE HYMAX |  | 0 | PC
66 | 3" MJ 45* |  | 0 | PC
67 | 3" MJ 90* |  | 0 | PC
68 | 3" MJ COUPLING |  | 0 | PC
69 | 3" MJ TEE |  | 0 | PC
70 | 3" 45* HYMAX |  | 0 | PC
71 | 3" 90* HYMAX |  | 0 | PC
72 | 3" COUPLING HYMAX | 191.92 | 220.708 | PC
73 | 3" TEE HYMAX |  | 0 | PC
74 | 4" MJ 45* |  | 0 | PC
75 | 4" MJ 90* |  | 0 | PC
76 | 4" MJ COUPLING |  | 0 | PC
77 | 4" MJ TEE |  | 0 | PC
78 | 4" 45* HYMAX |  | 0 | PC
79 | 4" 90* HYMAX |  | 0 | PC
80 | 4" COUPLING HYMAX | 245.93 | 282.8195 | PC
81 | 4" TEE HYMAX |  | 0 | PC
82 | 6" MJ 45* |  | 0 | PC
83 | 6" MJ 90* |  | 0 | PC
84 | 6" MJ COUPLING |  | 0 | PC
85 | 6" MJ TEE |  | 0 | PC
86 | 6" 45* HYMAX |  | 0 | PC
87 | 6" 90* HYMAX |  | 0 | PC
88 | 6" COUPLING HYMAX | 325.69 | 374.5435 | PC
89 | 6" TEE HYMAX |  | 0 | PC
90 | 6" SWIVAL HYMAX | 1546 | 1777.9 | PC
91 | 8" MJ 45* |  | 0 | PC
92 | 8" MJ 90* |  | 0 | PC
93 | 8" MJ COUPLING |  | 0 | PC
94 | 8" MJ TEE |  | 0 | PC
95 | 8" 45* HYMAX |  | 0 | PC
96 | 8" 90* HYMAX |  | 0 | PC
97 | 8" COUPLING HYMAX | 673.15 | 774.1225 | PC
98 | 8" TEE HYMAX |  | 0 | PC
99 | 2" SADDLE DI |  | 0 | PC
100 | 2" SADDLE PVC |  | 0 | PC
101 | 3" SADDLE DI |  | 0 | PC
102 | 3" SADDLE PVC |  | 0 | PC
103 | 4" SADDLE DI |  | 0 | PC
104 | 4" SADDLE PVC |  | 0 | PC
105 | 6" SADDLE DI |  | 0 | PC
106 | 6" SADDLE PVC |  | 0 | PC
107 | 8" SADDLE DI |  | 0 | PC
108 | 8" SADDLE PVC |  | 0 | PC
109 | 2" CAP |  | 0 | PC
110 | 3" CAP |  | 0 | PC
111 | 4" CAP |  | 0 | PC
112 | 6" CAP |  | 0 | PC
113 | 8" CAP |  | 0 | PC
114 | 2" MJ VALVES |  | 0 | PC
115 | 2" FLANGE VALVES |  | 0 | PC
116 | 3" MJ VALVES | 546 | 627.9 | PC
117 | 3" FLANGE VALVES | 546 | 627.9 | PC
118 | 4" ALFA VALVE | 835.25 | 960.5375 | PC
119 | 4" FLANGE VALVE | 798 | 917.7 | PC
120 | 6" ALFA VALVE | 1245 | 1431.75 | PC
121 | 6" FLANGE VALVE | 1124 | 1292.6 | PC
122 | 8" ALFA VALVE | 1687 | 1940.05 | PC
123 | 2" PCV SDR 17 | 2 | 2.3 | FT
124 | 2" D IRON |  | 0 | FT
125 | 3" PVC SDR 17 | 4.18 | 4.807 | FT
126 | 3" D IRON |  | 0 | FT
127 | 4" PVC SDR 17 | 6.54 | 7.521 | FT
128 | 4" D IRON |  | 0 | FT
129 | 6" PVC SDR 17 | 14.7 | 16.905 | FT
130 | 6" D IRON |  | 0 | FT
131 | 8" PVC SDR 17 | 28.45 | 32.7175 | FT
132 | 8" D IRON |  | 0 | FT
133 | 2" TRANS PACK PVC | 61.63 | 70.8745 | PC
134 | 2" TRANS PACK D IRON | 62.24 | 71.576 | PC
135 | 3" TRANS PACK PVC | 71.63 | 82.3745 | PC
136 | 3" TRANS PACK D IRON | 72.24 | 83.076 | PC
137 | 4" TRANS PACK PVC | 81.63 | 93.8745 | PC
138 | 4" TRANS PACK D IRON | 82.24 | 94.576 | PC
139 | 6" TRANS PACK PVC | 91.63 | 105.3745 | PC
140 | 6" TRANS PACK D IRON | 92.24 | 106.076 | PC
141 | 8" TRANS PACK PVC | 101.63 | 116.8745 | PC
142 | 8" TRANS PACK D IRON | 102.24 | 117.576 | PC
143 | BOTTOM VALVE BODY | 62.89 | 72.3235 | PC
144 | TOP VALVE BODY | 62.89 | 72.3235 | PC
145 | VALVE BODY LID | 54.12 | 62.238 | PC
146 | METER PIT | 31.05 | 35.7075 | PC
147 | METER PIT LID | 56.28 | 64.722 | PC
148 | TEFLON TAPE | 0.12 | 0.138 | IN
149 | SMALL POST HYDRANT | 1235 | 1420.25 | PC
150 | LARGE POST HYDRANT | 3200 | 3680 | PC
151 | 14" DIMOND CUT WHEEL | 1.39 | 1.5985 | FT
152 | ROCK BOSS CHAIN | 3.34 | 3.841 | FT
153 | PIPE CUTTERS | 0.03 | 0.0345 | FT
154 | BORING MACHINE | 9.87 | 11.3505 | FT
155 | AIR COMPRESSOR | 8.25 | 9.4875 | HR
156 | HAND TOOLS | 1.6 | 1.84 | HR
157 | BACKHOE | 85 | 97.75 | HR
158 | EXCAVATOR | 85 | 97.75 | HR
159 | IMPACT GUN AND SOCKETS | 2.25 | 2.5875 | HR
160 | SAWS ALL AND BLADES | 2.25 | 2.5875 | HR
161 | MARKING TAPE | 0.13 | 0.1495 | FT
162 | LABOR | 24.5 | 28.175 | HR
163 | WATER LOSS | 0.003 | 0.00345 | GAL
164 | LAB TESTING | 100 | 115 | PC
165 | FLAGING AND SIGHNS | 75 | 86.25 | HR
166 | FUEL SURCHARGE | 50 | 57.5 | PC
167 | GRAVEL | 22.5 | 25.875 | TON
168 | REMOVAL OF DEBRIS | 25 | 28.75 | PC
169 | MOBIL FLEET #T1 | 0.89 | 1.0235 | MILE
170 | MOBIL FLEET #T2 | 0.89 | 1.0235 | MILE
171 | MOBIL FLEET #T3 | 0.89 | 1.0235 | MILE
172 | MOBIL FLEET #T4 | 0.89 | 1.0235 | MILE
173 | MOBIL FLEET #T5 | 0.89 | 1.0235 | MILE
174 | MOBIL FLEET #T6 | 0.89 | 1.0235 | MILE
175 | MOBIL FLEET #T7 | 0.89 | 1.0235 | MILE
176 | MOBIL FLEET #T8 | 0.89 | 1.0235 | MILE
177 | MOBIL FLEET #V1 | 0.89 | 1.0235 | MILE
178 |  |  | 0
179 |  |  | 0
180 |  |  | 0
181 |  |  | 0
182 |  |  | 0
183 |  |  | 0
184 |  |  | 0
185 |  |  | 0
186 |  |  | 0
187 |  |  | 0
188 |  |  | 0
189 |  |  | 0
190 |  |  | 0
191 |  |  | 0
192 |  |  | 0
193 |  |  | 0
194 |  |  | 0
195 |  |  | 0
196 |  |  | 0
197 |  |  | 0
198 |  |  | 0
199 |  |  | 0
200 |  |  | 0
201 |  |  | 0
202 |  |  | 0
203 |  |  | 0
204 |  |  | 0
205 |  |  | 0
206 |  |  | 0
207 |  |  | 0
208 |  |  | 0
209 |  |  | 0
210 |  |  | 0
211 |  |  | 0
212 |  |  | 0
213 |  |  | 0
214 |  |  | 0
215 |  |  | 0
216 |  |  | 0
217 |  |  | 0
218 |  |  | 0
219 |  |  | 0
220 |  |  | 0
221 |  |  | 0
222 |  |  | 0
223 |  |  | 0
224 |  |  | 0
225 |  |  | 0
226 |  |  | 0
227 |  |  | 0
228 |  |  | 0
229 |  |  | 0
230 |  |  | 0
231 |  |  | 0
232 |  |  | 0
233 |  |  | 0
234 |  |  | 0
235 |  |  | 0
236 |  |  | 0
237 |  |  | 0
238 |  |  | 0
239 |  |  | 0
240 |  |  | 0
241 |  |  | 0
242 |  |  | 0
243 |  |  | 0
244 |  |  | 0
245 |  |  | 0
246 |  |  | 0
247 |  |  | 0
248 |  |  | 0

## PARTS USED
PRODICT # | DISCRIPTION | USED
1 | 1" CLOSE COUPLINGS |  | PC
2 | 1" CORP STOP |  | PC
3 | 1" CTS PIPE |  | PC
4 | 1" CTS X 1" PEP |  | PC
5 | 1" G LOCK NUTS |  | PC
6 | 1" INCERTS |  | PC
7 | 1" PIPE X 3/4" CTS |  | PC
8 | 1" PRV APAPTER |  | PC
9 | 1" SETTER CUT OFF VALVES |  | PC
10 | 1" SETTERS STRAIGHT |  | PC
11 | 1" SETTERS TANDOM |  | PC
12 | 1" STREET 90* |  | PC
13 | 1" STREET VALVE |  | PC
14 | 1" X 90* |  | PC
15 | 1" X 1" COUPLINGS |  | PC
16 | 1" X 1" X 1" TEE |  | PC
17 | 1" X 1" X 3/4" TEE |  | PC
18 | 1" X 1/8" GASKETS |  | PC
19 | 1" X 3" WRAPS |  | PC
20 | 1" X 3/4" BELL REDUCER |  | PC
21 | 1" X 45* |  | PC
22 | 1" X PRV |  | PC
23 | 14" DIMOND CUT WHEEL |  | PC
24 | 2" 45* HYMAX |  | PC
25 | 2" 90* HYMAX |  | PC
26 | 2" CAP |  | PC
27 | 2" COUPLING HYMAX |  | PC
28 | 2" D IRON |  | PC
29 | 2" FLANGE VALVES |  | PC
30 | 2" MJ 45* |  | PC
31 | 2" MJ 90* |  | PC
32 | 2" MJ COUPLING |  | PC
33 | 2" MJ VALVES |  | PC
34 | 2" PCV SDR 17 |  | PC
35 | 2" SADDLE DI |  | PC
36 | 2" SADDLE PVC |  | PC
37 | 2" TEE HYMAX |  | PC
38 | 2" TRANS PACK D IRON |  | PC
39 | 2" TRANS PACK PVC |  | PC
40 | 2" X15" WRAP |  | PC
41 | 3" 45* HYMAX |  | PC
42 | 3" 90* HYMAX |  | PC
43 | 3" CAP |  | PC
44 | 3" COUPLING HYMAX |  | PC
45 | 3" D IRON |  | PC
46 | 3" FLANGE VALVES |  | PC
47 | 3" MJ 90* |  | PC
48 | 3" MJ 45* |  | PC
49 | 3" MJ COUPLING |  | PC
50 | 3" MJ TEE |  | PC
51 | 3" MJ VALVES |  | PC
52 | 3" PVC SDR 17 |  | PC
53 | 3" SADDLE DI |  | PC
54 | 3" SADDLE PVC |  | PC
55 | 3" TEE HYMAX |  | PC
56 | 3" TRANS PACK D IRON |  | PC
57 | 3" TRANS PACK PVC |  | PC
58 | 3" X 12" WRAP |  | PC
59 | 3" X 15" WRAP |  | PC
60 | 3/4" CLOSE COUPLINGS |  | PC
61 | 3/4" CORP STOP |  | PC
62 | 3/4" CTS PIPE |  | PC
63 | 3/4" CTS X 3/4" CTS |  | PC
64 | 3/4" CTS X 3/4" PVC |  | PC
65 | 3/4" G LOCK NUTS |  | PC
66 | 3/4" INSERTS |  | PC
67 | 3/4" PIPE X 3/4" CTS |  | PC
68 | 3/4" PRV |  | PC
69 | 3/4" PRV ADAPTER |  | PC
70 | 3/4" SETTER CUT OFF VALVES |  | PC
71 | 3/4" STREET VALVE |  | PC
72 | 3/4" X 1" CTS |  | PC
73 | 3/4" X 1" CTS |  | PC
74 | 3/4" X 1/8" GASKETS |  | PC
75 | 3/4" X 3" WRAPS |  | PC
76 | 3/4" X 3/4" COUPLINGS |  | PC
77 | 3/4" X 3/4" X 1 TEE |  | PC
78 | 3/4" X 3/4" X 3/4" TEE |  | PC
79 | 3/4" X 45* |  | PC
80 | 3/4" X 5/8" SETTERS STRAIGHT |  | PC
81 | 3/4" X 5/8" SETTERS TANDOM |  | PC
82 | 3/4" X 90* |  | PC
83 | 4" 45* HYMAX |  | PC
84 | 4" 90* HYMAX |  | PC
85 | 4" ALFA VALVE |  | PC
86 | 4" CAP |  | PC
87 | 4" COUPLING HYMAX |  | PC
88 | 4" D IRON |  | PC
89 | 4" FLANGE VALVE |  | PC
90 | 4" MJ 45* |  | PC
91 | 4" MJ 90* |  | FT
92 | 4" MJ COUPLING |  | FT
93 | 4" MJ TEE |  | FT
94 | 4" PVC SDR 17 |  | FT
95 | 4" SADDLE DI |  | HR
96 | 4" SADDLE PVC |  | PC
97 | 4" TEE HYMAX |  | HR
98 | 4" TRANS PACK D IRON |  | HR
99 | 4" TRANS PACK PVC |  | PC
100 | 4" X 15" WRAP |  | PC
101 | 4" X 24" WRAP |  | PC
102 | 4" X12" WRAP |  | PC
103 | 6" 45* HYMAX |  | PC
104 | 6" 90* HYMAX |  | PC
105 | 6" ALFA VALVE |  | PC
106 | 6" CAP |  | PC
107 | 6" COUPLING HYMAX |  | PC
108 | 6" D IRON |  | PC
109 | 6" FLANGE VALVE |  | PC
110 | 6" MJ 45* |  | PC
111 | 6" MJ 90* |  | PC
112 | 6" MJ COUPLING |  | PC
113 | 6" MJ TEE |  | PC
114 | 6" PVC SDR 17 |  | PC
115 | 6" SADDLE DI |  | PC
116 | 6" SADDLE PVC |  | PC
117 | 6" SWIVAL HYMAX |  | PC
118 | 6" TEE HYMAX |  | PC
119 | 6" TRANS PACK D IRON |  | PC
120 | 6" TRANS PACK PVC |  | PC
121 | 6" X 12" WRAP |  | PC
122 | 6" X 15" WRAP |  | PC
123 | 6" X 24" WRAP |  | PC
124 | 8" 45* HYMAX |  | PC
125 | 8" 90* HYMAX |  | PC
126 | 8" ALFA VALVE |  | PC
127 | 8" CAP |  | PC
128 | 8" COUPLING HYMAX |  | PC
129 | 8" D IRON |  | PC
130 | 8" MJ 45* |  | PC
131 | 8" MJ 90* |  | PC
132 | 8" MJ COUPLING |  | PC
133 | 8" MJ TEE |  | PC
134 | 8" PVC SDR 17 |  | PC
135 | 8" SADDLE DI |  | PC
136 | 8" SADDLE PVC |  | PC
137 | 8" TEE HYMAX |  | PC
138 | 8" TRANS PACK D IRON |  | PC
139 | 8" TRANS PACK PVC |  | PC
140 | 8" X 12" WRAP |  | PC
141 | 8" X 15" WRAP |  | PC
142 | 8" X 24" WRAP |  | PC
143 | AIR COMPRESSOR |  | PC
144 | BACKHOE |  | PC
145 | BORING MACHINE |  | PC
146 | BOTTOM VALVE BODY |  | PC
147 | EXCAVATOR |  | PC
148 | EXCAVATOR |  | PC
149 | HAND TOOLS |  | PC
150 | IMPACT GUN AND SOCKETS |  | PC
151 | MARKING TAPE |  | PC
152 | METER PIT |  | PC
153 | METER PIT LID |  | PC
154 | PIPE CUTTERS |  | PC
155 | ROCK BOSS CHAIN |  | HR
156 | SAWS ALL AND BLADES |  | HR
157 | TEFLON TAPE |  | FT
158 | TOP VALVE BODY |  | PC
159 | VALVE BODY LID |  | PC
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248