## Exhibit 6 - Schedule C
Fleming-Mason Energy Cooperative, Inc.
Case No. 2023-00223
Request 6 - Construction Projects
|  |  |  | Variance |  |  | Total | Total | Variance | Date | Date
|  | Annual Actual Cost | Annual Original Budget | In | Variance | Percent | Actual | Budget | In | Original | Original | Date | Date
Project | Project |  |  | Dollars | As | Of | Project | Project | Dollars | Budget | Budget | Actual | Actual
No. | Title/Description |  |  | Under/(Over) | Percent | Budget | Cost | Cost | Under/(Over) | Start | End | Start | End
13-00322 | Big Woods 1PH to 3PH | 282930.29 | 79500 | -203430.29 | 255.9% |  | 282930.29 | 79500 | -203430.29 | 2013-01-01 | 2017-12-31 | 2017-03-31 | 2017-12-31
19-313002 | New Sub / Big Woods 3PH | 0 | 56700 | 56700 | -100% |  | 0 | 56700 | 56700 | 2013-01-01 | 2017-12-31 | 2017-03-31 | 2017-12-31
|  | 282930.29 | 136200 | -146730.29 | 107.7% |  | 282930.29 | 136200 | -146730.29
19-311004 | KY 801 to Sharkey 1/0 ACSR to 336 ACSR | 357269.13 | 128800 | -228469.13 | 177.4% |  | 357269.13 | 128800 | -228469.13 | 2018-01-01 | 2022-12-31 | 2019-06-11 | 2021-08-19
19-311006 | KY 801 to Farmers 1/0 ACSR to 336 ACSR | 169228.92 | 151300 | -17928.92 | 11.85% |  | 169228.92 | 151300 | -17928.92 | 2018-01-01 | 2022-12-31 | 2020-01-30 | 2020-12-24
19-313004 | Big Woods Tie/Paris Lane | 193113.92 | 24300 | -168813.92 | 694.7% |  | 193113.92 | 24300 | -168813.92 | 2018-01-01 | 2022-12-31 | 2017-03-31 | 2017-12-31
19-302002 | Wallingford Rd Voltage Conversion | 120549.13 | 69400 | -51149.13 | 73.7% |  | 120549.13 | 69400 | -51149.13 | 2018-01-01 | 2022-12-31 | 2020-12-20 | 2021-05-31
19-309004 | Pea Ridge Rd 1PH to 2 PH | 0 | 99500 | 99500 | -100% |  | 0 | 99500 | 99500 | 2018-01-01 | 2022-12-31 | - | -
|  | 120549.13 | 168900 | 48350.87 | -28.63% |  | 120549.13 | 168900 | 48350.87
19-309003 | Big Run Rd 1PH to 3PH | 112218.33 | 354600 | 242381.67 | -68.35% |  | 112218.33 | 354600 | 242381.67 | 2018-01-01 | 2022-12-31 | 2021-05-17 | 2021-06-30
19-309001 | Wooley Rd Conductor Change | 55412.71 | 73500 | 18087.29 | -24.61% |  | 55412.71 | 73500 | 18087.29 | 2018-01-01 | 2022-12-31 | 2021-05-25 | 2021-09-30
19-301018 | KY 344 to Indian Creek Conductor Change | 545152.94 | 323800 | -221352.94 | 68.36% |  | 545152.94 | 323800 | -221352.94 | 2018-01-01 | 2022-12-31 | 2021-09-01 | 2022-05-13
19-301016 | KY 344 Voltage Conversion | 0 | 60500 | 60500 | -100% |  | 0 | 60500 | 60500 | 2018-01-01 | 2022-12-31 | - | -
|  | 545152.94 | 384300 | -160852.94 | 41.86% |  | 545152.94 | 384300 | -160852.94
|  | 1835875.37 | 1421900 | -413975.37 | 29.11% |  | 1835875.37 | 1421900 | -413975.37