## 7 Schedule C
Schedule C
Kenergy Corp.
Case No. 2023-00276
Psc Information Request No. 1 Item 7
Construction Projects
For Five Years Ended December 31, 2022
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance In Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
2018 | 2018 Distribution Plant Budget | 11717956 | 12816128 | -1098172 | -9.372% | -8.569% | 11717956 | 12816128 | -1098172 | 2018-01-01 | 2018-12-31 | 2018-01-01 | 2018-12-31
2019 | 2019 Distribution Plant Budget | 13651201 | 12758415 | 892786 | 6.54% | 6.998% | 13651201 | 12758415 | 892786 | 2019-01-01 | 2019-12-31 | 2019-01-01 | 2019-12-31
2020 | 2020 Distribution Plant Budget | 13206924 | 13408105 | -201181 | -1.523% | -1.5% | 13206924 | 13408105 | -201181 | 2020-01-01 | 2020-12-31 | 2020-01-01 | 2020-12-31
2021 | 2021 Distribution Plant Budget** | 12438036 | 14612092 | -2174056 | -17.48% | -14.88% | 12438036 | 14612092 | -2174056 | 2021-01-01 | 2021-12-31 | 2021-01-01 | 2021-12-31
2022 | 2022 Distribution Plant Budget* | 15920647 | 13270478 | 2650169 | 16.65% | 19.97% | 15920647 | 13270478 | 2650169 | 2022-01-01 | 2022-12-31 | 2022-01-01 | 2022-12-31
| Total | 66934764 | 66865218 | 69546 | 0.1039% | 0.104% | 66934764 | 66865218 | 69546
**2021 actual includes a $1.8 million credit for FEMA Reimbursement of 2009 ice storm
* 2022 actual includes $2.1 million for Smart Grid Fiber, which was not included in the original budget
Request 7, Page 2 of 2