## Sheet1
Revised 2-23-24 GH
Peaks Mill Water District - Water Loss Reduction Plan 2022-2025
Item # | Description |  | Target Period | Assigned To: | Status
1 | Monitor daily flow from four master meter locations for high water use
| A. | Monitor flow from FPB daily using AMI, develop trend charts. | Started Sept 2022 | Jeff Lee/Greg Heitzman | Ongoing
| B. | Monitor flow from KAWC daily using AMI, develop trend charts | Started Sept 2022 | Jeff Lee/Greg Heitzman | Ongoing
| C. | Use daily trends to Identify potential water main breaks, large leaks or unusual usage. | Started Sept 2022 | Jeff Lee/Greg Heitzman | Ongoing
2 | Divide System into District Metered Areas - read zone meters at monthly metering day
| A. | Zone 1 - Lewis Ferry Road served by FPB master meter # | Started July 2021 | Jeff Lee | Monthly Reports to PMWD Board
| B. | Zone 2 - US Highway 127 at BP Station - control valve and meter, served by FPB and KAWC | Started July 2021 | Jeff Lee | Monthly Reports to PMWD Board
| C. | Zone 3 - Sulphur Lick BPS - served by KAWC and in-line meter | Started July 2021 | Jeff Lee | Monthly Reports to PMWD Board
| D. | Track monthly water loss trends by zone, gallon per customer, etc. | Started July 2021 | Jeff Lee | Monthly Reports to PMWD Board
| E. | Use data to identify areas of highest water loss rates | Started July 2021 | Jeff Lee | Daily monitoring to track trends
| F. | Routinely review operations to identify possible areas of leaks, investigate leaks, and initiate repairs by contractor. | Started July 2021 | Jeff Lee and Contractor Operator. | Ongoing activities to ID leaks, excavate and repairs. Report leak volume estimates to Board. Document on PSC monthly water loss report.
| G. | Review monthly Director's Billing Report to identify potential water theft, billing inconsistencies, meter issues, etc. | Started July 2021 | Nancy Sherrow and Jeff Lee | Follow-up to investigate issue and take action as needed.
3
| A. | Metal Detector | Purchased 8/2022 | Jeff Lee/John McKinney | Routine Operations
| B. | Pressure Data Logger | Purchased 1/23/2023 | Greg Heitzman | Pressure Monitoring
| C. | Digital Leak Detector | Ordered 11/30/23, received Jan, 2024. | Greg Heitzman | Used in routine operations by Jeff Lee to locate leaks.
| D. | Portable ultrasonic meter | On Hold | Greg Heitzman | Available ultrasonic meter from KRWA when needed
| E. | Install pressure monitoring at key locations (tanks, pump stations, control valves) | Installed tanks levels with updated SCADA system 12/2022. | Jeff Lee/Greg Heitzman | Pressure/Level monitored at all tanks, add other locations as funds become available.
4 | Install 10 auto flush devices and ultrasonic meter to measure flushing volumes. Use Cleaner Water Program Grants Funds $113,000.
| A. | Smart Earth Technology ultrasonic meter | Spring 2023 | Blake Gates (resigned 5/31/23) | Installed at Hurt Lane Flush location, hold on other locations, due to bankruptcy filing by Smart Earth Technologies. Investigating other smart meter technologies for applications
| B. | Install 10 Auto Flushers under CWP Project (WX20173035). | 4th Qtr. 2023, 1st Qtr. 2024 | Cartwright Const. | 10 taps and meters installed. Auto Flusher devices delivered, installation planned for March 2024. equipment
| C. | Report metered flush volumes by location, rollup daily flush volumes in monthly report. | 1st Quarter 2024 | Jeff Lee | Flushed meter template completed, monthly tracking initiated in January 2024 (eliminates estimates for monthly flush volumes)
5 | Calculate the water loss monthly and determine the economic value of water (non revenue water)
| A. | Develop trends charts by month for water loss by percent, volume, and volume per customer, report to Board | Started Oct 2022 | Greg Heitzman | Ongoing
| B. | Develop trends charts by month for non revenue water, value of water loss, report to Board quarterly. | Started Jan 2023 | Greg Heitzman | Ongoing
6 | Test 60 meters per year (approximately 5%)
| A. | Test meters for accuracy within AWWA standards, replace meters outside standard accuracy allowance | Started 1st Qtr. 2023 | John McKinney changes out meters, Tim Shera delivers to OCWD for testing | Ongoing
| B. | Requires purchasing 20 meters for rotation of stock and replacements when needed. | October 2024 | Jeff Lee/John McKinney | Ongoing
| C. | Conduct analysis of tested meters to develop plan for replacement with new meter system in 2024-27. Testing by Oldham County Water District | 1st Qtr. 2024 | Greg Heitzman | Complete 2023 meter testing analysis in Jan 2024, report to Board
| D. | Replaced all 1-inch meters with new meters meeting accuracy standards. Deliver to OCWD for testing. Report results to Board. | 1st Qtr. 2024 | Jeff Lee/John McKinney/Tim Shera | 1" meters replaced, testing in March 2024
7 | Identify Capital Projects to reduce water loss and increase system reliability.
| A. | Identify water main replacement projects for areas with high water loss (i.e. Stonewall Subdivision). Update WRIS project profile. | Completed December 2023 | Greg Heitzman | Updated Project Profile for Stonewall Subdivision WX 21073027
| B. | Plan for new AMR meter replacements beginning 2025 (Project WX21073036), use Water Loss Surcharge to find portion of project cost, pending approval of PSC. Update WRIS project profile. | 2024-28 | Greg Heitzman | Updated Project Profile for AMR/AMI Meter Replacement Project WX 21073036 in February 2024. Submitted thru BGADD to KIA.