## (6) Schedule C
Schedule C
Jackson Purchase Energy Corporation
Case No. 2024-00085
Construction Projects
For 5 Years Ended December 31, 2023
Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Variance In Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
506 | Kansas Substation Rebuild | 1614652.99 | 1453000 | 161652.99 | 11.13% | 111.1% | 1614652.99 | 161652.99 | 2016-01-01 | 2019-12-31 | 2019-03-21 | 2020-07-22
509 | Krebs Substation Rebuild | 3282119.9 | 3711000 | -428880.1 | -11.56% | 88.44% | 3282119.9 | -428880.1 | 2021-01-01 | 2022-12-31 | 2022-08-17 | 2023-06-15
508 | New York, Moved Krebs transformer to New York | 191802.67 | 2050000 | -1858197.33 | -90.64% | 9.356% | 191802.67 | -1858197.33 | 2023-01-01 | 2023-12-31 | 2022-09-01 | 2022-10-26
1301 | Construction of New Headquarters | 19123331.51 | 19192000 | -68668.49 | -0.3578% | 99.64% | 19123331.51 | -68668.49 | 2020-01-01 | 2021-12-31 | 2020-02-12 | 2021-08-31
201-21 | Ledbetter Bridge River Crossing | 639564.74 | 650000 | -10435.26 | -1.605% | 98.39% | 639564.74 | -10435.26 | 2022-01-01 | 2022-12-31 | 2020-07-15 | 2020-11-30
201-20 | Draffenville, New Hwy 68 Ckt (In Progress) | 217436.36 | 370000 | -152563.64 | -41.23% | 58.77% | 217436.36 | -152563.64 | 2020-01-01 | 2021-12-31 | 2023-09-08 | TBD
303-12 | Calvert City-Change 1PH/2PH to 3PH | 19504.84 | 16000 | 3504.84 | 21.91% | 121.9% | 19504.84 | 3504.84 | 2021-01-01 | 2021-12-31 | 2021-03-23 | 2021-05-11
304-23 | Old Calvert City Rd- Change 1PH to 3PH | 177058.6 | 86800 | 90258.6 | 104% | 204% | 177058.6 | 90258.6 | 2023-01-01 | 2023-12-31 | 2021-11-03 | 2022-07-27
317-12 | Little Union Roy Lee Rd- Change 1PH to 3PH | 157346.95 | 37000 | 120346.95 | 325.3% | 425.3% | 157346.95 | 120346.95 | 2022-01-01 | 2022-12-31 | 2022-06-20 | 2022-12-14
341-16 | St Rt 1820 Kansas 1PH to 3PH | 347287.22 | 173600 | 173687.22 | 100.1% | 200.1% | 347287.22 | 173687.22 | 2022-01-01 | 2022-12-31 | 2022-06-29 | 2022-11-23
342-16 | Krebs New Hope Church Rd-Change 1PH to 3PH | 260242.78 | 99300 | 160942.78 | 162.1% | 262.1% | 260242.78 | 160942.78 | 2020-01-01 | 2020-12-31 | 2021-11-04 | 2022-06-07
348-21 | New York Slater/Crew Rd-Change 1PH to 3PH | 352208.23 | 168500 | 183708.23 | 109% | 209% | 352208.23 | 183708.23 | 2021-01-01 | 2021-12-31 | 2022-03-14 | 2022-05-04
349-21 | New York Wickliffe/Slater Rd-Change 1PH to 3PH | 160604.65 | 96000 | 64604.65 | 67.3% | 167.3% | 160604.65 | 64604.65 | 2021-01-01 | 2021-12-31 | 2021-11-16 | 2022-02-28
343-16 | Lovelaceville Lov Flo St Rd-Change 1PH to 3PH | 449512.95 | 297000 | 152512.95 | 51.35% | 151.4% | 449512.95 | 152512.95 | 2021-01-01 | 2021-12-31 | 2022-11-08 | 2023-04-26
Project No. | Project Title/Description | Reason for variance
506 | Kansas Substation Rebuild | The cost variance was due to change in scope during the project. Time variance was due to substation transformer delay.
509 | Krebs Substation Rebuild | Only one substation transformer was installed, instead of parallel transformers. This was the cause of the cost variance. Delayed delivery of switches contributed to construction delays.
508 | New York, Moved Krebs transformer to New York | The retired Krebs transformer was moved to New York to increase available capacity. The budgeted cost included a total substation rebuild which wasn't completed. This was the cause of the variance.
1301 | Construction of New Headquarters | N/A
201-21 | Ledbetter Bridge River Crossing | N/A
201-20 | Draffenville, New Hwy 68 Ckt (In Progress) | Construction in progress. Start date of project was rescheduled due to more immediate needs.
303-12 | Calvert City-Change 1PH/2PH to 3PH | Cost variance was due to increase in material costs.
304-23 | Old Calvert City Rd- Change 1PH to 3PH | Cost variance was due to increase in material costs.
317-12 | Little Union Roy Lee Rd- Change 1PH to 3PH | Cost variance was due to increase in material costs.
341-16 | St Rt 1820 Kansas 1PH to 3PH | Cost variance was due to increase in material costs.
342-16 | Krebs New Hope Church Rd-Change 1PH to 3PH | Cost variance was due to increase in material costs. Project completion was delayed due to personnel resources.
348-21 | New York Slater/Crew Rd-Change 1PH to 3PH | Cost variance was due to increase in material costs. Project completion was delayed due to personnel resources.
349-21 | New York Wickliffe/Slater Rd-Change 1PH to 3PH | Cost variance was due to increase in material costs. Project completion was delayed due to personnel resources.
343-16 | Lovelaceville Lov Flo St Rd-Change 1PH to 3PH | Cost variance was due to increase in material costs. Project completion was delayed due to personnel resources.