## (7) Schedule D
Schedule D
Jackson Purchase Energy Corporation
Case No. 2024-00085
Construction Projects
As of 9/1/2021 - 8/31/2022
Line No. (A) | Project No. (B) | Description of Project (C) | Construction Amount (D) | AFUDC Capitalized (E) | Indirect Costs Other (F)* | Total Cost (G=D+E+F) | Estimated Physical Percent Completed (H)
1 | 509 | Krebs Substation Rebuild | 3282119.9 | 0 | 0 | 3282119.9 | 5%
2 | 304-23 | Old Calvert City Rd- Change 1PH to 3PH | 177058.6 | 0 | 0 | 177058.6 | 100%
3 | 317-12 | Little Union Roy Lee Rd- Change 1PH to 3PH | 157346.95 | 0 | 0 | 157346.95 | 20%
4 | 341-16 | St Rt 1820 Kansas 1PH to 3PH | 347287.22 | 0 | 0 | 347287.22 | 40%
5 | 342-16 | Krebs New Hope Church Rd-Change 1PH to 3PH | 260242.78 | 0 | 0 | 260242.78 | 100%
6 | 348-21 | New York Slater/Crew Rd-Change 1PH to 3PH | 352208.23 | 0 | 0 | 352208.23 | 100%
7 | 349-21 | New York Wickliffe/Slater Rd-Change 1PH to 3PH | 160604.65 | 0 | 0 | 160604.65 | 100%
*Explain the nature of all other indirect costs in footnotes.