## Schedule G
KY PSC Case No. 2024-00092
Staff 1-25
Schedule G
Columbia Gas of Kentucky KY PSC Case No. 2024-00092 Construction Projects As of May 22nd, 2024
Line No. (A) | Project No. (B) | Description of Project (C) | Construction Amount (D) | AFUDC Capitalized (E) | Indirect Costs Other (F)* | Total Cost (G = D + E + F) | Esitmated Physical Percent Complete
1 | 22026183001 | INSTALL 4955'-2" PMMP | 103557.34 | 7450.98 | 19566.96 | 130575.28 | 25%
2 | 22026210901 | INSTALL 8OO' OF 2"PMMP MAIN | 39409.04 | 240.9 | 13758.59 | 53408.53 | 100%
3 | 23026255300 | PCE - INSTALL 450'-4" PMMP | 0 | 0 | 0 | 0 | 0%
4 | 23026270600 | INSTALL 205' OF 2" PMMP | 0 | 0 | 0 | 0 | 0%
5 | 23026283100 | INSTALL 1200'-2"&4" PMMP | 8808.51 | 0 | 4033.77 | 12842.28 | 5%
6 | 23026286200 | INSTALL 2000'OF 2"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
7 | 23026288900 | INSTALL 850'-2" PMMP | 0 | 0 | 0 | 0 | 0%
8 | 23026292201 | INSTALL 360'-4" PMMP | 122893.52 | 868.13 | 47796.52 | 171558.17 | 90%
9 | 23026298500 | PCE * INSTALL 4400' OF 4"PMMP | 0 | 0 | 0 | 0 | 0%
10 | 23026298800 | INSTALL 900'-2" PMMP MAIN | 68543.79 | 251.02 | 27893.29 | 96688.1 | 100%
11 | 23026299500 | INSTALL 7000' OF 4"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
12 | 23026300300 | INSTALL 1810'-2" PMMP | 0 | 0 | 0 | 0 | 0%
13 | 23026301800 | INSTALL 1,200'-2" PMMP | 0 | 0 | 0 | 0 | 0%
14 | 23026304300 | INSTALL 700'-2" CSHP | 0 | 0 | 0 | 0 | 0%
15 | 23026304700 | INSTALL 1,300'-2" PMMP | 0 | 0 | 0 | 0 | 0%
16 | 23026304800 | INSTALL 1700'-2" PMMP | 0 | 0 | 0 | 0 | 0%
17 | 23026306300 | INSTALL 13,500' OF 4"/6"PMMP | 0 | 0 | 0 | 0 | 0%
18 | 23026306400 | INSTALL 400'-2" PMMP | 0 | 0 | 0 | 0 | 0%
19 | 24026309500 | INSTALL 215'-2" PMMP | 0 | 0 | 0 | 0 | 100%
20 | 24026310800 | INSTALL 1400' OF 2" PMMP | 4871.73 | 58.33 | 1334.4 | 6264.46 | 5%
21 | 24026311200 | INSTALL 7500' OF 4"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
22 | 24026312200 | INSTALL 230'-2" PMMP | 0 | 0 | 0 | 0 | 0%
23 | 24026314400 | INSTALL 1,200'-4" PMMP | 0 | 0 | 0 | 0 | 0%
24 | 24026317300 | INSTALL 270'-2" PMMP | 19491.55 | 63.85 | 7337.87 | 26893.27 | 100%
25 | 24026324100 | INSTALL 670'-2' PMIP | 0 | 0 | 0 | 0 | 0%
26 | 24026328200 | * PCE * INSTALL 2100'-2"PMMP | 0 | 0 | 0 | 0 | 0%
27 | 24026331500 | INSTALL 300' OF 2"PMMP MAIN | 20908 | 69.39 | 8300.48 | 29277.87 | 100%
28 | 24026332500 | INSTALL 1100'-4" CSHP | 0 | 0 | 0 | 0 | 0%
29 | 24026333600 | INSTALL 75'-2" PMIP | 0 | 0 | 0 | 0 | 0%
30 | 24026335000 | INSTALL 5400'-2"/4" PMMP | 0 | 0 | 0 | 0 | 0%
31 | 24026337000 | INSTALL 675' OF 2"PMMP MAIN | 2118.65 | 7.03 | 841.1 | 2966.78 | 100%
32 | 24026337100 | INSTALL 700'-4" PMMP | 0 | 0 | 0 | 0 | 0%
33 | 24026337900 | INSTALL 2,550'-2" PMMP | 23342.76 | 46.28 | 5536.51 | 28925.55 | 100%
34 | 24026338500 | INSTALL 585' OF 2"PMMP MAIN | 7322.74 | 24.3 | 2907.13 | 10254.17 | 100%
35 | 24026339200 | INSTALL 2725' OF 8"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
36 | 24026340200 | INSTALL 600' OF 8"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
37 | 24026340300 | INSTALL 2280' OF 4"CSHP MAIN | 150.93 | 0.5 | 59.92 | 211.35 | 1%
38 | 24026341300 | INSTALL 330'-2" PMMP | 0 | 0 | 0 | 0 | 0%
39 | 24026341900 | INSTALL 4250' OF 2"/4"PMMP | 0 | 0 | 0 | 0 | 0%
40 | 24026342200 | INSTALL 500'-2" PMIP | 0 | 0 | 0 | 0 | 0%
41 | 24026344200 | INSTALLING 2600'-4"/8" PMMP | 0 | 0 | 0 | 0 | 0%
42 | 18026776700 | REPLACE 4437'-8,12' CSHP | 38418.54 | 1831.44 | 12917.62 | 53167.6 | 15%
43 | 18026794400 | INSTALL 1965'-2" PMMP | 3277.3 | 47.5 | 1225.55 | 4550.35 | 10%
44 | 19026882900 | INSTALL 10400'-2"&4" PMIP | 0 | 0 | 0 | 0 | 0%
45 | 19026913000 | INSTALL 730'-2"PMMP | 129624.36 | 300.03 | 51479.24 | 181403.63 | 100%
46 | 20026972800 | INSTALL 20' - 6"/3" PMMP | 0 | 0 | 0 | 0 | 0%
47 | 20026980200 | INSTALL 7,125'-2"/4" PMMP | 0 | 0 | 0 | 0 | 0%
48 | 21026133400 | INSTALL 3545' OF 2"/4"PMMP | 59.9 | 1.1 | 5.79 | 66.79 | 1%
49 | 21026145601 | INSTALL 1885' - 4" PMMP MAIN | 538322.88 | 16580.73 | 209329.76 | 764233.37 | 100%
50 | 21026152100 | INSTALL 535' OF 8"CSHP MAIN | 17376.1 | 137.83 | 6520.09 | 24034.02 | 20%
51 | 21026153100 | INSTALL 2596'- 4,6" PMLP | 10842.91 | 385.68 | 1130.36 | 12358.95 | 5%
52 | 22026158500 | INSTALL 6027'-2,4" PMMP | 6298.84 | 94.07 | 1241.08 | 7633.99 | 2%
53 | 22026159100 | INSTALL 4100' OF 12"CSHP MAIN | 0 | 0 | 0 | 0 | 0%
54 | 22026161800 | INSTALL 8" PCF | 0 | 0 | 0 | 0 | 0%
55 | 22026163500 | INSTALL 17250' OF 2"/4"PMMP MN | 2138.47 | 110.12 | 166.53 | 2415.12 | 2%
56 | 22026164000 | INSTALL 5,100'-2" PMMP | 832774.83 | 5692.07 | 297306.58 | 1135773.48 | 100%
57 | 22026170800 | INSTALL 15,885'-2"&4"PMMP | 735.65 | 21.12 | 28.3 | 785.07 | 1%
58 | 22026171400 | INSTALL 9000'-2" PMIP | 470.26 | 12.66 | 26.36 | 509.28 | 1%
59 | 22026171600 | INSTALL 4371'-2"&4" PMIP | 137664.14 | 9326.06 | 24695.19 | 171685.39 | 30%
60 | 22026172301 | INSTALL 5000' OF 2"PMMP MAIN | 673834.23 | 3489.31 | 229630.16 | 906953.7 | 100%
61 | 22026178300 | EMER-INSTALL 5'OF 2"PMMP MAIN | 2210.7 | 94.82 | 396.42 | 2701.94 | 75%
62 | 22026208200 | INSTALL 820'-2" PMMP | 212.04 | 5.34 | 5.53 | 222.91 | 2%
63 | 22026217100 | REPLACE MAIN - LEAKAGE | 392.11 | 11.2 | 15.51 | 418.82 | 2%
64 | 22026219200 | INSTALL 2000'-4" PMIP | 0 | 0 | 0 | 0 | 0%
65 | 22026224200 | INSTALL 2300' OF 2"/4"PMMP | 14153.96 | 64 | 5512.95 | 19730.91 | 20%
66 | 22026230600 | EMER-INSTALL 5' OF 3"PMMP MAIN | 0 | 0 | 0 | 0 | 100%
67 | 22026231300 | INSTALL 925' OF 2"PMMP MAIN | 3481.61 | 12.35 | 1377.05 | 4871.01 | 5%
68 | 22026236500 | INSTALL 1225' OF 4"/8"CSHP MN | 13403.87 | 197.74 | 6881.38 | 20482.99 | 5%
69 | 22026237100 | INSTALL 13000'-2" PMMP | 7230.16 | 340.11 | 3925.38 | 11495.65 | 3%
70 | 22026238800 | INSTALL 14475' OF 2"/4"PMMP | 35599.13 | 813.14 | 12917.17 | 49329.44 | 15%
71 | 22026239000 | INSTALL 4110'-4" PMLP/PMMP | 7149.16 | 162.16 | 2602.29 | 9913.61 | 3%
72 | 22026239200 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
73 | 22026239500 | INST 1510'-6" & 2625'-2" PMMP | 234.92 | 7.17 | 39.66 | 281.75 | 1%
74 | 22026239700 | INSTALL 8390'-2" PMMP | 21536.64 | 81.86 | 8519.75 | 30138.25 | 15%
75 | 22026239900 | INSTALL 3845' OF 2,4,6" PMMP | 24513.58 | 311.35 | 8462.81 | 33287.74 | 10%
76 | 22026245100 | EMER-INSTALL 3' OF 2"PHHP MAIN | 2589.41 | 18.18 | 145.17 | 2752.76 | 100%
77 | 23026273700 | INSTALL 6' OF 2"PMMP MAIN | 395.49 | 14.22 | 64.78 | 474.49 | 25%
78 | 23026282800 | EMER - INSTALL 5'-2" PMMP | 8505.03 | 232.43 | 386.97 | 9124.43 | 100%
79 | 23026289700 | INSTALL 70' OF 3"PMLP MAIN | 5204.76 | 226.03 | 1711.27 | 7142.06 | 15%
80 | 23026290300 | INSTALL 4000'- 2"/4"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
81 | 23026290600 | INSTALL 9350' OF 2"/4"PMMP | 121.89 | 0.41 | 48.39 | 170.69 | 2%
82 | 23026294300 | INSTALL 40' OF 4" PMMP | 0 | 0 | 0 | 0 | 0%
83 | 23026297400 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
84 | 23026297700 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
85 | 23026298000 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
86 | 23026298900 | INSTALL LP FITTINGS | 0 | 0 | 0 | 0 | 0%
87 | 23026299100 | INSTALL 13,250'-2"/4"6" PMMP | 0 | 0 | 0 | 0 | 0%
88 | 23026303900 | EMER-INSTALL 3'-2" PMMP MAIN | 1551.09 | 67.02 | 675.31 | 2293.42 | 75%
89 | 23026304400 | EMER-INSTALL 3'-2" PMIP | 0 | 0 | 0 | 0 | 0%
90 | 23026309300 | EMER - INSTALL 5'-4" PMMP | 1673.42 | 34 | 616.74 | 2324.16 | 100%
91 | 24026313000 | INSTALL 1380'-2" PMMP | 0 | 0 | 0 | 0 | 0%
92 | 24026315000 | INSTALL 1000' OF 2"/6"PMMP | 0 | 0 | 0 | 0 | 0%
93 | 24026315400 | INSTALL XXX' OF X-X" PMMP | 0 | 0 | 0 | 0 | 0%
94 | 24026315600 | INSTALL XXXX' OF X" PMMP | 0 | 0 | 0 | 0 | 0%
95 | 24026315800 | INSTALL XXXX' OF 12" CSHP | 0 | 0 | 0 | 0 | 0%
96 | 24026316200 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
97 | 24026316700 | INSTALL 4000' OF 2"PMMP MAIN | 11536.36 | 107 | 4923.71 | 16567.07 | 2%
98 | 24026317400 | INSTALL 4400'-2" PMMP | 0 | 0 | 0 | 0 | 0%
99 | 24026317600 | INSTALL 2500' OF 2"/6"PMMP MN | 0 | 0 | 0 | 0 | 0%
100 | 24026318000 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
101 | 24026318200 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
102 | 24026318400 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
103 | 24026321400 | INSTALL 5000' OF 2"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
104 | 24026321600 | INSTALL ~6900'-10" PMMP | 0 | 0 | 0 | 0 | 0%
105 | 24026321800 | INSTALL 7000'-2" PMMP | 0 | 0 | 0 | 0 | 0%
106 | 24026322000 | INSTALL 7750' OF 2"PMMP MAIN | 480.33 | 1.6 | 190.69 | 672.62 | 1%
107 | 24026322200 | INSTALL 12,500'-2"/4"/6" PMMP | 0 | 0 | 0 | 0 | 0%
108 | 24026330100 | INSTALL 1250'-8" CSHP | 0 | 0 | 0 | 0 | 0%
109 | 24026331100 | EMER - INSTALL ~5'-2" PMMP | 342.37 | 7.7 | 180.21 | 530.28 | 50%
110 | 24026331600 | INSTALL 475' OF 2"PMMP MAIN | 3826.68 | 10.54 | 617.72 | 4454.94 | 7%
111 | 24026332100 | INSERT 50' OF 3" PMLP | 9349.9 | 23.58 | 2821.46 | 12194.94 | 45%
112 | 24026332600 | EMER INSTALL 10'-6" PMMP | 22157.66 | 228.02 | 9838 | 32223.68 | 90%
113 | 24026333000 | EMER-INSTALL 18'-4"PMLP MAIN | 7641.08 | 35.65 | 3102.88 | 10779.61 | 75%
114 | 24026333200 | INSTALL 150' OF 4" PMLP | 3330.34 | 11 | 1315.11 | 4656.45 | 10%
115 | 24026333700 | INSTALL 2640' OF 4"CSHP MAIN | 0 | 0 | 0 | 0 | 0%
116 | 24026334300 | REPLACE MAIN - LEAKAGE | 0 | 0 | 0 | 0 | 0%
117 | 24026336800 | EMER - INSTALL 5' OF 2" PMMP | 3522.24 | 36.25 | 1563.87 | 5122.36 | 75%
118 | 24026338200 | EMER - INSTALL 5'-3" PMMP | 6490.76 | 21.54 | 2576.83 | 9089.13 | 100%
119 | 24026339800 | INSTALL 35' OF 6"PMLP MAIN | 0 | 0 | 0 | 0 | 0%
120 | 24026340600 | INSTALL LP FITTINGS | 0 | 0 | 0 | 0 | 0%
121 | 24026340800 | EMER - INSTALL 15'-2" PMMP | 0 | 0 | 0 | 0 | 0%
122 | 24026341500 | INSTALL 60'-8"/10" CSHP | 0 | 0 | 0 | 0 | 0%
123 | 24026342000 | EMER - INSTALL 2' OF 2"PMMP | 0 | 0 | 0 | 0 | 100%
124 | 24026343700 | EMER - INSTALL 3'-3" PMMP | 0 | 0 | 0 | 0 | 0%
125 | 24026344300 | EMER-INSTALL 6' OF 4" PMIP | 0 | 0 | 0 | 0 | 0%
126 | 18026783600 | INSTALL 405'-8" PMLP | 0 | 0 | 0 | 0 | 0%
127 | 19026867801 | INSTALL 732'-4" PMIP | 13025.28 | 929.51 | 2227.64 | 16182.43 | 25%
128 | 20026939000 | RELOCATE 300'-2" PMMP | 0 | 0 | 0 | 0 | 0%
129 | 20026965000 | INSTALL 6" CRITICAL VALVE | 0 | 0 | 0 | 0 | 0%
130 | 20026971500 | INSTALL 50'-4" CSHP HTR IN/OUT | 0 | 0 | 0 | 0 | 0%
131 | 21026119200 | PM- LAKE CARNICO REPLACEMENT | 2623509.24 | 50389.78 | 367384.81 | 3041283.83 | 100%
132 | 21026119400 | PM- INST FIL/SEP TOYOTA STA | 1759855.51 | 35508.95 | 277841.29 | 2073205.75 | 100%
133 | 21026119600 | PM- TURNER STATION REPLACEMENT | 2813008.23 | 54708.18 | 443728.41 | 3311444.82 | 100%
134 | 21026120400 | PM- TOYOTA ILI REPLACEMENTS | 5887492.5 | 701139.34 | 860825.56 | 7449457.4 | 95%
135 | 21026135500 | INSTALL 75'-4/6/12" CSHP | 0 | 0 | 0 | 0 | 0%
136 | 21026155500 | INSTALL 1400'-4" PMMP | 0 | 0 | 0 | 0 | 0%
137 | 22026160600 | INSTALL 16'-6" PMMP AND C. VLV | 1866.1 | 26.82 | 365.6 | 2258.52 | 40%
138 | 22026166700 | INSTALL 16'-2"PMMP | 1805.34 | 25.36 | 360.19 | 2190.89 | 30%
139 | 22026167800 | INSTALL CRITICAL VALVE | 2075.02 | 26.73 | 410.98 | 2512.73 | 50%
140 | 22026176200 | INSTALL ~10' - 2" PMIP & CSIP | 0 | 0 | 0 | 0 | 0%
141 | 22026182500 | INSTALL 16'-6" PMMP AND C. VLV | 0 | 0 | 0 | 0 | 0%
142 | 22026206500 | INSTALL 2000'-4" PMMP | 0 | 0 | 0 | 0 | 0%
143 | 22026206700 | INSTALL 4000' - 4" PMMP | 0 | 0 | 0 | 0 | 0%
144 | 22026207300 | INSTALL 40'-3" CSMP | 0 | 0 | 0 | 0 | 0%
145 | 22026222000 | INSTALL 16'-6" PMMP/CRI. VLV | 0 | 0 | 0 | 0 | 0%
146 | 23026249600 | PM- DE ILI PH 2 JIM BEAM INST | 851458.83 | 1299.99 | 113183.26 | 965942.08 | 100%
147 | 23026253100 | PM- GREENSITE TRABU INSTALL | 25717.59 | 0 | 5022.08 | 30739.67 | 100%
148 | 23026253700 | PM-GREENSITE HWY 27 INSTALL | 17337.93 | 0 | 3393.01 | 20730.94 | 100%
149 | 23026255500 | INSTALL 2" SS & BYPASS | 0 | 0 | 0 | 0 | 0%
150 | 23026255700 | INSTALL 4,400'-6" PMMP | 0 | 0 | 0 | 0 | 0%
151 | 23026268500 | PM-DE LINE ILI PH 2 BEND 260 | 596954.22 | 826.15 | 119352.78 | 717133.15 | 100%
152 | 23026268600 | PM-DE LINE ILI PH2 DENT 36 | 1120584.65 | 1368.32 | 476890.57 | 1598843.54 | 100%
153 | 23026268700 | PM-DE LINE PH 2 DENT 2/STPL 3 | 601544.17 | 658.69 | 100954.76 | 703157.62 | 100%
154 | 23026292300 | INSTALL 2" SS | 769.69 | 18.06 | 284.58 | 1072.33 | 100%
155 | 23026294900 | FOREST LAKE DR VLV | 0 | 0 | 0 | 0 | 0%
156 | 23026295100 | PARIS PIKE VLV | 0 | 0 | 0 | 0 | 0%
157 | 23026295400 | CORNWALL DR VLV | 0 | 0 | 0 | 0 | 0%
158 | 23026295600 | REDDING RD VLV | 0 | 0 | 0 | 0 | 0%
159 | 23026295800 | LANSDOWNE | 0 | 0 | 0 | 0 | 0%
160 | 23026298300 | INSTALL LP PCF | 0 | 0 | 0 | 0 | 0%
161 | 23026308400 | REPLACE ~800'-12" BSMP | 0 | 0 | 0 | 0 | 0%
162 | 24026310400 | INSTALL VALVE & 5' OF 2" PMMP | 7551.18 | 123.15 | 2816.6 | 10490.93 | 75%
163 | 24026310600 | INSTALL 2, 2" STOPPLE FITTINGS | 4031.87 | 9.72 | 1162.8 | 5204.39 | 50%
164 | 24026334500 | INSTALL HP | 0 | 0 | 0 | 0 | 0%
165 | 24026334600 | INSTALL MP | 0 | 0 | 0 | 0 | 0%
166 | 24026337800 | INSTALL 8" SS | 0 | 0 | 0 | 0 | 100%
167 | 24026338600 | INSTALL HP FITTINGS | 0 | 0 | 0 | 0 | 0%
168 | 24026338800 | INSTALL MP FITTINGS | 0 | 0 | 0 | 0 | 0%
169 | 24026341000 | INSTALL 300'OF 2" PMIP | 0 | 0 | 0 | 0 | 0%
170 | 24026343300 | INSTALL 4" POLY VALVE | 0 | 0 | 0 | 0 | 0%
171 | 22026219900 | INSTALL 530'-2" PMMP | 0 | 0 | 0 | 0 | 0%
172 | 22026241701 | INSTALL 1425' OF 2"PMMP MAIN | 424625.74 | 4832.84 | 169986.33 | 599444.91 | 100%
173 | 23026254900 | INSTALL 620' OF 8"CSHP MAIN | 21940.47 | 11.08 | 8971.87 | 30923.42 | 20%
174 | 23026279500 | INSTALL 339'-8" PMLP | 35472.04 | 115.57 | 13825.28 | 49412.89 | 100%
175 | 23026287300 | INSTALL 121'-4" CSMP | 381.52 | 8.65 | 138.87 | 529.04 | 3%
176 | 23026293700 | INSTALL 74'-2" PMMP | 30707.58 | 65.16 | 12060.56 | 42833.3 | 100%
177 | 23026300401 | INSTALL 1150' 4/2" PMMP | 127739.59 | 1169.42 | 54460.13 | 183369.14 | 100%
178 | 23026301200 | INSTALL 60' OF 6"PMMP MAIN | 0 | 0 | 0 | 0 | 0%
179 | 23026304900 | NEWTOWN PIKE RELOCATIONS | 0 | 0 | 0 | 0 | 0%
180 | 24026313200 | OAKPOINTE 300' ENCROACH RELO | 0 | 0 | 0 | 0 | 0%
181 | 24026328800 | NEWTOWN PIKE MP RELOCATION | 0 | 0 | 0 | 0 | 0%
182 | 24026329000 | INSTALL 580' OF 4" CSHP | 0 | 0 | 0 | 0 | 0%
183 | 24026342400 | INSTALL ~585'-2" PMMP | 0 | 0 | 0 | 0 | 0%
184 | 24026343500 | INSTALL 25'-8" PMLP | 0 | 0 | 0 | 0 | 0%
185 | 20026971400 | INSTALL CWT MODEL 140 HEATER | 11342.84 | 272.21 | 1409.91 | 13024.96 | 80%
186 | 22026163100 | INSTALL CATALYTIC HEATER | 0 | 0 | 0 | 0 | 0%
187 | 22026220300 | INSTALL NEW RELIEF VALVE | 0 | 0 | 0 | 0 | 0%
188 | 23026265300 | INSTALL PILOT REGULATORS | 8925.17 | 66.53 | 407.29 | 9398.99 | 100%
189 | 24026334800 | INSTALL NEW STATION | 0 | 0 | 0 | 0 | 0%
190 | 18026779401 | ACQ 25X25 SITE FOR NEW R-1133 | 15053.61 | 1067.71 | 0 | 16121.32 | 90%
191 | 21026116700 | OBTAIN HP EASEMENT | 10356.23 | 482.54 | 0 | 10838.77 | 50%
192 | 21026123000 | INVESTIGATE/AQUIRE EASEMENT | 9119.84 | 450.01 | 0 | 9569.85 | 60%
193 | 22026207901 | PM- LAND MILLER DR POD | 60000 | 2897.13 | 0 | 62897.13 | 80%
194 | 22026221100 | ACQUIRE EASEMENT | 500 | 9.85 | 0 | 509.85 | 100%
195 | 22026224600 | ACQUIRE LAND RIGHTS | 4000 | 115.53 | 0 | 4115.53 | 100%
196 | 22026235500 | ACQUIRE EASEMENT | 1000 | 26.17 | 0 | 1026.17 | 20%
197 | 23026281000 | OBTAIN NEW EASEMENT | 4092.58 | 62.9 | 0 | 4155.48 | 100%
198 | 23026283900 | ACQUIRE EASEMENTS | 40497 | 1736.68 | 0 | 42233.68 | 90%
199 | 24026312500 | ACQUIRE EASEMENT FOR RELOCATE | 500 | 8.3 | 0 | 508.3 | 5%
200 | 24026334900 | ACQUIRE LAND | 0 | 0 | 0 | 0 | 0%
201 | 24026340500 | ACQUIRE EASEMENT | 3012.5 | 6.72 | 0 | 3019.22 | 25%
202 | 24026341800 | LAND PAYMENT FOR REG SITE EASE | 0 | 0 | 0 | 0 | 0%
203 | 24026344000 | DOCUMENT REG STAT EASEMENT | 0 | 0 | 0 | 0 | 0%
204 | 18026753300 | INSTALL 2 VRG PILOTS | 9118.32 | 512.15 | 1473.66 | 11104.13 | 90%
205 | 21026131700 | INSTALL METER OUTLET VLV | 103.9 | 1.34 | 20.58 | 125.82 | 5%
206 | 22026176400 | INSTALL NEW TOPWORKS | 1893.83 | 4.76 | 120.23 | 2018.82 | 70%
207 | 22026211900 | INSTALL 1" BYPASS VALVE | 1543.67 | 57.9 | 81.01 | 1682.58 | 60%
208 | 22026212800 | REPLACE STATION VALVES | 0 | 0 | 0 | 0 | 0%
209 | 22026225600 | REPLACE GATE VALVES | 0 | 0 | 0 | 0 | 0%
210 | 23026254800 | INSTALL VRG CONTROLLER | 0 | 0 | 0 | 0 | 0%
211 | 23026264000 | INSTALL NEW METER | 14100.25 | 769.24 | 8235.73 | 23105.22 | 100%
212 | 23026276000 | REPLACE ODORIZER R-1439 | 0 | 0 | 0 | 0 | 0%
213 | 23026286900 | HIGHLAND HEIGHTS BREAK METER | 19749.41 | 294.45 | 8115.75 | 28159.61 | 80%
214 | 23026287100 | REPLACE BYPASS VALVE | 0 | 0 | 0 | 0 | 0%
215 | 23026293300 | INSTALL NEW FISHER REGULATORS | 0 | 0 | 0 | 0 | 0%
216 | 23026306500 | INSTALL DRIP TANK | 16274.56 | 57.39 | 6210.13 | 22542.08 | 100%
217 | 23026306800 | INSTALL METER RUN | 7749.24 | 28.36 | 2788.13 | 10565.73 | 90%
218 | 23026307100 | INSTALL NEW METER | 0 | 0 | 0 | 0 | 0%
219 | 23026308100 | INSTALL NEW METER | 0 | 0 | 0 | 0 | 0%
220 | 24026309600 | INSTALL METER | 76.3 | 1.72 | 27.77 | 105.79 | 10%
221 | 24026312800 | INSTALL REGULATOR STATION | 0 | 0 | 0 | 0 | 0%
222 | 24026316400 | EMER-INSTALL CATALYTIC HEATER | 1568.25 | 5.12 | 584.96 | 2158.33 | 100%
223 | 24026335800 | EMER - INSTALL PF REGULATOR | 68945.36 | 388.14 | 28445.32 | 97778.82 | 95%
224 | 24026340000 | EMER-INSTALL NEW PF REGULATOR | 1445.5 | 4.8 | 573.86 | 2024.16 | 100%
225 | 24026337400 | INSTALL NEW FENCE | 0 | 0 | 0 | 0 | 0%
226 | 22026218900 | INSTALL NEW METER | 6057.81 | 600.9 | 2945.96 | 9604.67 | 90%
227 | 24026336600 | INSTALL GMB SETTING | 0 | 0 | 0 | 0 | 0%
228 | 24026340400 | INSTALL GMB SETTING | 0 | 0 | 0 | 0 | 0%
229 | 18026845002 | INSTALL THREE SSD UNITS | 98622.06 | 1307.2 | 28269.37 | 128198.63 | 95%
* The other inderect costs represent Supervision, Engineering, General, and Administrative Costs