## Rate Case Request
KY PSC Case No. 2024-00092
Staff 1-26
Schedule H
Columbia Gas of Kentucky KY PSC Case No. 2024-00092 Construction Projects As of May 22nd, 2024
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I)=(G/H)
1 | 22026183001 | 2023-02-14 | 2024-05-24 | 100% | 134870 | 134870 | 153683 | 113.9%
2 | 22026210901 | 2024-02-12 | 2024-02-20 | 100% | 49945 | 49945 | 53409 | 106.9%
3 | 23026255300 | Not Started | 2025-12-01 | 0% | 281314.259 | 281314.259 | 0 | 0%
4 | 23026270600 | Not Started | 2024-12-31 | 0% | 21365.3441 | 21365.3441 | 0 | 0%
5 | 23026283100 | Not Started | 2024-12-01 | 0% | 101318.8268 | 101318.8268 | 12842 | 12.67%
6 | 23026286200 | Not Started | 2026-12-01 | 0% | 115061.7028 | 115061.7028 | 0 | 0%
7 | 23026288900 | Not Started | 2024-12-25 | 0% | 106250 | 106250 | 0 | 0%
8 | 23026292201 | 2024-01-26 | 2024-04-22 | 100% | 143242.2706 | 171123 | 171558 | 100.3%
9 | 23026298500 | Not Started | 2025-12-01 | 0% | 346601.8505 | 346601.8505 | 0 | 0%
10 | 23026298800 | 2024-03-18 | 2024-04-03 | 100% | 120091.9279 | 120091.9279 | 96688 | 80.51%
11 | 23026299500 | Not Started | 2025-12-01 | 0% | 333435.7792 | 333435.7792 | 0 | 0%
12 | 23026300300 | Not Started | 2024-10-01 | 0% | 170435.8061 | 170435.8061 | 0 | 0%
13 | 23026301800 | Not Started | 2024-10-31 | 0% | 60143.8193 | 60143.8193 | 0 | 0%
14 | 23026304300 | Not Started | 2024-12-31 | 0% | 172537.6881 | 172537.6881 | 0 | 0%
15 | 23026304700 | Not Started | 2024-11-01 | 0% | 74951.6168 | 74951.6168 | 0 | 0%
16 | 23026304800 | Not Started | 2024-10-26 | 0% | 106913.5455 | 106913.5455 | 0 | 0%
17 | 23026306300 | Not Started | 2024-12-31 | 0% | 1057322.7695 | 1057322.7695 | 0 | 0%
18 | 23026306400 | Not Started | 2025-04-30 | 0% | 30096.9335 | 30096.9335 | 0 | 0%
19 | 24026309500 | 2024-05-17 | 2024-05-22 | 100% | 20568.4833 | 20568.4833 | 14692 | 71.43%
20 | 24026310800 | Not Started | 2024-09-10 | 0% | 90793.9332 | 90793.9332 | 6264 | 6.899%
21 | 24026311200 | Not Started | 2024-12-01 | 0% | 390261.5734 | 390261.5734 | 0 | 0%
22 | 24026312200 | 2024-05-28 | 2024-06-14 | 10% | 25802.5654 | 25802.5654 | 3813 | 14.78%
23 | 24026314400 | Not Started | 2024-12-06 | 0% | 220000 | 220000 | 0 | 0%
24 | 24026317300 | 2024-04-01 | 2024-04-08 | 100% | 44548.0974 | 44548.0974 | 26893 | 60.37%
25 | 24026324100 | Not Started | 2024-09-01 | 0% | 68828.4274 | 68828.4274 | 0 | 0%
26 | 24026328200 | Not Started | 2024-12-01 | 0% | 209796.6833 | 209796.6833 | 0 | 0%
27 | 24026331500 | 2024-04-17 | 2024-04-24 | 100% | 28768 | 28768 | 29278 | 101.8%
28 | 24026332500 | Not Started | 2024-12-31 | 0% | 330000 | 330000 | 0 | 0%
29 | 24026333600 | Not Started | 2024-06-24 | 0% | 27562.0605 | 27562.0605 | 0 | 0%
30 | 24026335000 | Not Started | 2025-03-30 | 0% | 578810 | 578810 | 0 | 0%
31 | 24026337000 | 2024-05-07 | 2024-05-21 | 100% | 60312.9634 | 60312.9634 | 40379 | 66.95%
32 | 24026337100 | Not Started | 2024-10-19 | 0% | 132000 | 132000 | 0 | 0%
33 | 24026337900 | 2024-04-22 | 2024-05-09 | 100% | 91900.6833 | 91900.6833 | 82784 | 90.08%
34 | 24026338500 | 2024-04-29 | 2024-05-03 | 100% | 37261.72 | 37261.72 | 27839 | 74.71%
35 | 24026339200 | Not Started | 2025-10-01 | 0% | 153206.9401 | 153206.9401 | 0 | 0%
36 | 24026340200 | Not Started | 2025-10-01 | 0% | 268396.2003 | 268396.2003 | 0 | 0%
37 | 24026340300 | Not Started | 2024-09-06 | 0% | 528055.8668 | 528055.8668 | 0 | 0%
38 | 24026341300 | Not Started | 2024-12-30 | 0% | 65240 | 65240 | 0 | 0%
39 | 24026341900 | Not Started | 2024-07-31 | 0% | 151333 | 151333 | 0 | 0%
40 | 24026342200 | Not Started | 2024-08-06 | 0% | 59969 | 59969 | 0 | 0%
41 | 24026344200 | Not Started | 2026-03-01 | 0% | 306572 | 306572 | 0 | 0%
42 | 18026776700 | Not Started | 2025-12-31 | 0% | 3186017.0036 | 3186017.0036 | 0 | 0%
43 | 18026794400 | Not Started | 2025-12-31 | 0% | 664621.6791 | 664621.6791 | 0 | 0%
44 | 19026882900 | Not Started | 2025-12-31 | 0% | 877632.3957 | 877632.3957 | 0 | 0%
45 | 19026913000 | 2024-01-02 | 2024-03-26 | 100% | 230850.9729 | 230850.9729 | 181404 | 78.58%
46 | 20026972800 | Not Started | 2025-12-31 | 0% | 70459.7552 | 70459.7552 | 0 | 0%
47 | 20026980200 | Not Started | 2025-12-31 | 0% | 71010.6739 | 71010.6739 | 0 | 0%
48 | 21026133400 | Not Started | 2025-12-31 | 0% | 982690.8099 | 982690.8099 | 0 | 0%
49 | 21026145601 | 2023-09-11 | 2024-03-18 | 100% | 707546.3464 | 707546.3464 | 764233 | 108%
50 | 21026152100 | Not Started | 2024-12-31 | 5% | 231546.8917 | 231546.8917 | 24034 | 10.38%
51 | 21026153100 | Not Started | 2025-12-31 | 0% | 473012.3788 | 473012.3788 | 0 | 0%
52 | 22026158500 | Not Started | 2025-12-31 | 0% | 1560656.9673 | 1560656.9673 | 0 | 0%
53 | 22026159100 | Not Started | 2025-12-31 | 0% | 63225.2952 | 63225.2952 | 0 | 0%
54 | 22026161800 | Not Started | 2024-12-31 | 0% | 147.7348 | 147.7348 | 0 | 0%
55 | 22026163500 | Not Started | 2025-12-31 | 0% | 1753296 | 1753296 | 0 | 0%
56 | 22026164000 | 2023-09-11 | 2024-04-10 | 100% | 1122890.0685 | 1122890.0685 | 1135773 | 101.1%
57 | 22026170800 | Not Started | 2025-12-31 | 0% | 4443590.7843 | 4443590.7843 | 0 | 0%
58 | 22026171400 | Not Started | 2025-12-31 | 0% | 712683.5963 | 712683.5963 | 0 | 0%
59 | 22026171600 | Not Started | 2025-12-31 | 0% | 515198.8408 | 515198.8408 | 171685 | 33.32%
60 | 22026172301 | 2024-04-24 | 2024-04-26 | 100% | 1171335.7552 | 1171335.7552 | 906954 | 77.43%
61 | 22026178300 | 2022-03-28 | 2022-03-28 | 100% | 3404 | 3404 | 2702 | 79.38%
62 | 22026208200 | Not Started | 2026-12-31 | 0% | 0 | 0 | 0 | 0%
63 | 22026217100 | Not Started | 2045-03-31 | 0% | 510317.6774 | 510317.6774 | 419 | 0.08211%
64 | 22026219200 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
65 | 22026224200 | 2024-05-27 | 2024-12-31 | 5% | 838012.4975 | 838012.4975 | 19731 | 2.354%
66 | 22026230600 | 2022-10-06 | 2022-10-06 | 100% | 829 | 829 | 0 | 0%
67 | 22026231300 | Not Started | 2024-12-31 | 0% | 210557.5964 | 210557.5964 | 4871 | 2.313%
68 | 22026236500 | Not Started | 2025-12-31 | 0% | 980024.3163 | 980024.3163 | 20483 | 2.09%
69 | 22026237100 | Not Started | 2025-12-31 | 0% | 1449928.0923 | 1449928.0923 | 11496 | 0.7929%
70 | 22026238800 | Not Started | 2025-12-31 | 0% | 1271604.5302 | 1271604.5302 | 49329 | 3.879%
71 | 22026239000 | Not Started | 2025-12-31 | 0% | 1431740.2837 | 1431740.2837 | 9914 | 0.6924%
72 | 22026239200 | Not Started | 2025-12-31 | 0% | 1957912.8951 | 1957912.8951 | 0 | 0%
73 | 22026239500 | Not Started | 2025-12-31 | 0% | 1281677.362 | 1281677.362 | 282 | 0.022%
74 | 22026239700 | Not Started | 2024-12-31 | 0% | 812940.7351 | 812940.7351 | 30138 | 3.707%
75 | 22026239900 | Not Started | 2024-12-31 | 0% | 663757 | 663757 | 33288 | 5.015%
76 | 22026245100 | 2022-12-07 | 2022-12-07 | 100% | 4878 | 4878 | 2753 | 56.44%
77 | 23026273700 | Not Started | 2024-09-30 | 0% | 15144.3052 | 15144.3052 | 474 | 3.13%
78 | 23026282800 | 2023-11-16 | 2023-07-05 | 100% | 5466 | 5466 | 9124 | 166.9%
79 | 23026289700 | Not Started | 2024-12-01 | 0% | 32168.4133 | 32168.4133 | 7142 | 22.2%
80 | 23026290300 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
81 | 23026290600 | Not Started | 2025-12-31 | 0% | 1315887.0567 | 1315887.0567 | 0 | 0%
82 | 23026294300 | Not Started | 2024-12-31 | 0% | 2309.0133 | 2309.0133 | 0 | 0%
83 | 23026297400 | Not Started | 2025-12-31 | 0% | 1318679.6461 | 1318679.6461 | 0 | 0%
84 | 23026297700 | Not Started | 2025-12-31 | 0% | 62695 | 62695 | 0 | 0%
85 | 23026298000 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
86 | 23026298900 | Not Started | 2025-12-31 | 0% | 190.3697 | 190.3697 | 0 | 0%
87 | 23026299100 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
88 | 23026303900 | 2023-10-29 | 2024-10-30 | 100% | 5590.3589 | 5590.3589 | 2293 | 41.02%
89 | 23026304400 | 2023-10-04 | 2023-10-18 | 100% | 1620 | 1620 | 1620 | 100%
90 | 23026309300 | 2024-02-19 | 2024-03-06 | 100% | 8327.2332 | 8327.2332 | 2324 | 27.91%
91 | 24026313000 | Not Started | 2025-09-30 | 0% | 324446.3667 | 324446.3667 | 0 | 0%
92 | 24026315000 | Not Started | 2025-12-31 | 0% | 18135 | 18135 | 0 | 0%
93 | 24026315400 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
94 | 24026315600 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
95 | 24026315800 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
96 | 24026316200 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
97 | 24026316700 | Not Started | 2024-12-31 | 0% | 372718.97 | 372718.97 | 16567 | 4.445%
98 | 24026317400 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
99 | 24026317600 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
100 | 24026318000 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
101 | 24026318200 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
102 | 24026318400 | Not Started | 2024-10-31 | 0% | 0 | 0 | 0 | 0%
103 | 24026321400 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
104 | 24026321600 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
105 | 24026321800 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
106 | 24026322000 | Not Started | 2025-12-31 | 0% | 796002.38 | 796002.38 | 673 | 0.08455%
107 | 24026322200 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
108 | 24026330100 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
109 | 24026331100 | Not Started | 2024-12-29 | 0% | 3498.146 | 3498.146 | 0 | 0%
110 | 24026331600 | Not Started | 2024-12-31 | 0% | 151202.1094 | 151202.1094 | 4455 | 2.946%
111 | 24026332100 | 2024-05-20 | 2024-10-31 | 40% | 34491.8294 | 34491.8294 | 12195 | 35.36%
112 | 24026332600 | 2024-03-01 | 2024-03-28 | 100% | 29701.1651 | 29701.1651 | 32224 | 108.5%
113 | 24026333000 | 2024-03-10 | 2024-03-10 | 100% | 29428.3233 | 29428.3233 | 16843 | 57.23%
114 | 24026333200 | Not Started | 2024-11-30 | 0% | 42362 | 42362 | 4656 | 10.99%
115 | 24026333700 | Not Started | 2025-12-31 | 0% | 8312 | 8312 | 0 | 0%
116 | 24026334300 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
117 | 24026336800 | 2024-03-22 | 2024-03-22 | 100% | 3378.146 | 3378.146 | 5122 | 151.6%
118 | 24026338200 | 2024-03-29 | 2024-03-29 | 100% | 3698.1293 | 3698.1293 | 9089 | 245.8%
119 | 24026339800 | Not Started | 2024-12-31 | 0% | 45030.1866 | 45030.1866 | 0 | 0%
120 | 24026340600 | Not Started | 2024-12-31 | 0% | 5899 | 5899 | 0 | 0%
121 | 24026340800 | Not Started | 2024-12-31 | 0% | 5754.7687 | 5754.7687 | 0 | 0%
122 | 24026341500 | Not Started | 2025-01-31 | 0% | 15305 | 15305 | 0 | 0%
123 | 24026342000 | 2024-05-02 | 2024-05-14 | 100% | 4292.2109 | 4292.2109 | 23.97 | 0.5585%
124 | 24026343700 | 2024-05-16 | 2024-05-22 | 100% | 6477 | 6477 | 3997 | 61.71%
125 | 24026344300 | 2024-05-27 | 2024-05-28 | 100% | 14215 | 14215 | 15446 | 108.7%
126 | 18026783600 | Not Started | 2025-12-31 | 0% | 224727.3482 | 224727.3482 | 0 | 0%
127 | 19026867801 | Not Started | 2024-08-30 | 0% | 133028 | 193114 | 16182 | 8.38%
128 | 20026939000 | Not Started | 2025-12-31 | 0% | 45098.5219 | 45098.5219 | 0 | 0%
129 | 20026965000 | Not Started | 2025-12-31 | 0% | 25782.917 | 25782.917 | 0 | 0%
130 | 20026971500 | Not Started | 2025-12-31 | 0% | 122031.9628 | 122031.9628 | 0 | 0%
131 | 21026119200 | 2021-06-27 | 2022-10-13 | 100% | 3161436 | 3161436 | 3041284 | 96.2%
132 | 21026119400 | 2021-06-27 | 2022-10-06 | 100% | 0 | 0 |  | 0%
133 | 21026119600 | 2021-09-14 | 2022-08-23 | 100% | 1012500 | 1012500 | 3311445 | 327.1%
134 | 21026120400 | 2021-08-30 | 2024-12-31 | 100% | 2721482.95 | 2721482.95 | 7449457 | 273.7%
135 | 21026135500 | Not Started | 2024-12-31 | 0% | 133652.9013 | 133652.9013 | 0 | 0%
136 | 21026155500 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
137 | 22026160600 | Not Started | 2026-12-31 | 0% | 27060.0655 | 27060.0655 | 2259 | 8.348%
138 | 22026166700 | Not Started | 2025-12-31 | 0% | 23816.0655 | 23816.0655 | 2191 | 9.2%
139 | 22026167800 | Not Started | 2025-12-31 | 0% | 25662.0655 | 25662.0655 | 2513 | 9.793%
140 | 22026176200 | Not Started | 2024-08-01 | 0% | 22014.6923 | 22014.6923 | 0 | 0%
141 | 22026182500 | Not Started | 2024-12-31 | 0% | 0 | 0 | 0 | 0%
142 | 22026206500 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
143 | 22026206700 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
144 | 22026207300 | Not Started | 2025-12-31 | 0% | 45743.3997 | 45743.3997 | 0 | 0%
145 | 22026222000 | Not Started | 2026-12-31 | 0% | 0 | 0 | 0 | 0%
146 | 23026249600 | 2023-01-02 | 2023-01-27 | 100% | 593000 | 593000 | 965942 | 162.9%
147 | 23026253100 | 2022-07-31 | 2022-09-26 | 100% | 1236355 | 1236355 | 30740 | 2.486%
148 | 23026253700 | 2022-08-28 | 2022-09-27 | 100% | 1236355 | 1236355 | 20731 | 1.677%
149 | 23026255500 | Not Started | 2024-08-31 | 0% | 17170.3462 | 17170.3462 | 0 | 0%
150 | 23026255700 | Not Started | 2024-12-31 | 0% | 483743.4178 | 483743.4178 | 0 | 0%
151 | 23026268500 | 2023-03-23 | 2023-06-16 | 100% | 1150001 | 1150001 | 717133 | 62.36%
152 | 23026268600 | 2023-03-23 | 2023-06-03 | 100% | 1150001 | 1150001 | 1598844 | 139%
153 | 23026268700 | 2023-03-23 | 2023-05-23 | 100% | 1307000 | 1307000 | 703158 | 53.8%
154 | 23026292300 | 2024-01-03 | 2024-01-16 | 100% | 15645.3381 | 15645.3381 | 1072 | 6.852%
155 | 23026294900 | Not Started | 2027-12-31 | 0% | 0 | 0 | 0 | 0%
156 | 23026295100 | Not Started | 2027-12-31 | 0% | 0 | 0 | 0 | 0%
157 | 23026295400 | Not Started | 2027-12-31 | 0% | 0 | 0 | 0 | 0%
158 | 23026295600 | Not Started | 2027-12-31 | 0% | 0 | 0 | 0 | 0%
159 | 23026295800 | Not Started | 2027-12-31 | 0% | 0 | 0 | 0 | 0%
160 | 23026298300 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
161 | 23026308400 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
162 | 24026310400 | 2024-04-01 | 2024-04-05 | 100% | 11731.9279 | 11731.9279 | 10491 | 89.42%
163 | 24026310600 | Not Started | 2025-12-31 | 0% | 32187.8821 | 32187.8821 | 0 | 0%
164 | 24026334500 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
165 | 24026334600 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
166 | 24026337800 | 2024-04-01 | 2024-04-08 | 100% | 151.4465 | 151.4465 | 2063 | 1362%
167 | 24026338600 | Not Started | 2024-12-31 | 0% | 0 | 0 | 0 | 0%
168 | 24026338800 | Not Started | 2024-12-31 | 0% | 0 | 0 | 0 | 0%
169 | 24026341000 | Not Started | 2024-09-29 | 0% | 37905 | 37905 | 0 | 0%
170 | 24026343300 | Not Started | 2024-10-01 | 0% | 18376 | 18376 | 0 | 0%
171 | 22026219900 | Not Started | 2024-12-31 | 0% | 110032.9281 | 110032.9281 | 0 | 0%
172 | 22026241701 | 2024-01-15 | 2024-05-08 | 100% | 729573.1234 | 729573.1234 | 599445 | 82.16%
173 | 23026254900 | Not Started | 2024-10-01 | 0% | 397622.268 | 397622.268 | 30923 | 7.777%
174 | 23026279500 | 2024-04-22 | 2024-05-10 | 100% | 126473.6122 | 126473.6122 | 67208 | 53.14%
175 | 23026287300 | Not Started | 2024-12-30 | 0% | 118801.3163 | 118801.3163 | 529 | 0.4453%
176 | 23026293700 | 2024-02-19 | 2024-02-21 | 100% | 102228.872 | 102228.872 | 42833 | 41.9%
177 | 23026300401 | 2024-02-26 | 2024-05-16 | 100% | 220213.1673 | 220213.1673 | 183369 | 83.27%
178 | 23026301200 | Not Started | 2024-12-31 | 0% | 35122 | 35122 | 0 | 0%
179 | 23026304900 | Not Started | 2024-06-30 | 0% | 9049 | 9049 | 0 | 0%
180 | 24026313200 | Not Started | 2024-12-31 | 0% | 56718.964 | 56718.964 | 0 | 0%
181 | 24026328800 | Not Started | 2024-10-30 | 0% | 0 | 0 | 0 | 0%
182 | 24026329000 | Not Started | 2024-10-01 | 0% | 360333.9734 | 360333.9734 | 0 | 0%
183 | 24026342400 | Not Started | 2024-06-30 | 0% | 84328.2987 | 84328.2987 | 0 | 0%
184 | 24026343500 | 05--28-24 | 2024-06-30 | 10% | 72915 | 72915 | 14957 | 20.51%
185 | 20026971400 | Not Started | 2024-12-31 | 0% | 157526 | 163857 | 13025 | 7.949%
186 | 22026163100 | Not Started | 2049-12-31 | 0% | 1449966 | 1449966 | 11496 | 0.7928%
187 | 22026220300 | Not Started | 2024-12-31 | 0% | 2415 | 2415 | 0 | 0%
188 | 23026265300 | 2023-10-26 | 2023-10-26 | 100% | 7329 | 9399 |  | 0%
189 | 24026334800 | Not Started | 2025-12-31 | 0% |  |  | 0 | 0%
190 | 18026779401 | 2024-01-08 | 2024-12-31 | 50% | 17250 | 17250 | 16121 | 93.46%
191 | 21026116700 | 2023-04-15 | 2023-12-31 | 100% | 8791 | 8791 | 10839 | 123.3%
192 | 21026123000 | 2021-05-12 | 2021-12-21 | 100% | 17354 | 17354 | 9570 | 55.15%
193 | 22026207901 | 2022-09-22 | 2024-12-31 | 100% | 960001 | 960001 | 62897 | 6.552%
194 | 22026221100 | 2024-01-25 | 2023-12-31 | 100% | 5819 | 5819 | 510 | 8.764%
195 | 22026224600 | 2023-12-31 | 2023-12-31 | 100% | 5705 | 5705 | 4116 | 72.15%
196 | 22026235500 | 2023-12-31 | 2023-12-31 | 100% | 8471 | 8471 | 1026 | 12.11%
197 | 23026281000 | 2024-02-28 | 2023-10-01 | 100% | 11896 | 11896 | 4155 | 34.93%
198 | 23026283900 | 2023-07-12 | 2024-12-31 | 50% | 41635 | 41635 | 42234 | 101.4%
199 | 24026312500 | Not Started | 2024-12-31 | 0% | 892 | 892 | 508 | 56.95%
200 | 24026334900 | Not Started | 2025-01-30 | 0% | 0 | 0 | 0 | 0%
201 | 24026340500 | 2024-04-23 | 2024-12-31 | 0% | 11900 | 11900 | 3019 | 25.37%
202 | 24026341800 | Not Started | 2024-05-31 | 0% | 724 | 724 | 0 | 0%
203 | 24026344000 | 2024-05-21 | 2024-10-01 | 100% | 1428 | 1428 | 0 | 0%
204 | 18026753300 | Not Started | 2023-12-31 | 0% | 10100 | 10100 | 11104 | 109.9%
205 | 21026131700 | Not Started | 2023-12-31 | 0% | 0 | 0 | 0 | 0%
206 | 22026176400 | Not Started | 2024-12-31 | 0% | 46257 | 46257 | 2019 | 4.365%
207 | 22026211900 | Not Started | 2024-09-01 | 0% | 15912 | 15912 | 1683 | 10.58%
208 | 22026212800 | Not Started | 2024-12-31 | 0% | 34925 | 34925 | 0 | 0%
209 | 22026225600 | Not Started | 2024-12-31 | 0% | 964 | 964 | 0 | 0%
210 | 23026254800 | Not Started | 2025-06-01 | 0% | 9944 | 9944 | 0 | 0%
211 | 23026264000 | 2024-05-16 | 2024-12-31 | 100% | 31875 | 31875 | 23105 | 72.49%
212 | 23026276000 | Not Started | 2024-12-31 | 0% | 24767 | 24767 | 0 | 0%
213 | 23026286900 | Not Started | 2024-12-31 | 0% | 103097 | 103097 | 28160 | 27.31%
214 | 23026287100 | Not Started | 2024-09-30 | 0% | 5809 | 5809 | 0 | 0%
215 | 23026293300 | Not Started | 2024-10-01 | 0% | 4301 | 4301 | 0 | 0%
216 | 23026306500 | 2024-02-15 | 2024-07-01 | 50% | 21572 | 21572 | 22542 | 104.5%
217 | 23026306800 | 2024-04-01 | 2024-06-30 | 50% | 89187 | 89187 | 10566 | 11.85%
218 | 23026307100 | Not Started | 2024-12-31 | 0% | 0 | 0 | 0 | 0%
219 | 23026308100 | Not Started | 2024-12-31 | 0% | 41682 | 41682 | 0 | 0%
220 | 24026309600 | Not Started | 2024-12-31 | 0% | 123241 | 123241 | 106 | 0.08601%
221 | 24026312800 | Not Started | 2025-12-31 | 0% | 0 | 0 | 0 | 0%
222 | 24026316400 | 2024-02-07 | 2024-02-09 | 100% | 3661 | 3661 | 2158 | 58.95%
223 | 24026335800 | 2024-03-20 | 2024-10-01 | 36% | 48662 | 48662 | 97779 | 200.9%
224 | 24026340000 | 2024-04-18 | 2024-04-18 | 100% | 5188 | 5188 | 2024 | 39.01%
225 | 24026337400 | Not Started | 2024-12-31 | 0% | 32517 | 32517 | 0 | 0%
226 | 22026218900 | Not Started | 2025-12-31 | 0% | 6442 | 6442 | 9605 | 149.1%
227 | 24026336600 | Not Started | 2024-06-30 | 0% | 49011 | 49011 | 0 | 0%
228 | 24026340400 | Not Started | 2024-09-01 | 0% | 0 | 0 | 0 | 0%
229 | 18026845002 | 2024-04-17 | 2024-04-19 | 100% | 142837 | 142837 | 128199 | 89.75%
Formulas:
Date Construction Work Began (C) = VLOOKUP([Project No. (B)],'Report Detail_1'!$D1:BD175,26,FALSE)
Estimated Project Completion Date (D) = VLOOKUP([Project No. (B)],'Report Detail_1'!$D1:BD175,25,FALSE)

## Report Detail_1
State | Ops Center | Work Loc | Job Order | Cap Flag | PSID | PSID Seq No | Map No | Project Id | Project Engineer | Current RT No | Job Type | Job Status | Job Summary | Resp Suprv | Located At | Address | Cnty Cd | Cty Cd | Stat Dt | Executed By | Entered By | Entered Dt | Priority Dt | Commit Dt | In Out Service Dt | Completed By | Complete Dt | Crew Start Dt | Actual Start Dt | Instl Cd | Bus Unit | Account | Home Dp | Chrg Dp | Affil | Activ | Project | Cst Elem Cd | Cost Obj Cd | Fclty cd | Proj Cd | Chrg Jo No | Chrg Pc | Nifit Work Order | Hours | Units | Total Actual Cost | Actual Labor Cost | Actual Mtl Cost | Actual Oth Cost | Actual Contr Cost | Actual Store Cost | Actual AFUDC Cost | Actual SEGA Cost | Footage
KY | KY - CENTRAL | 2629 | 18026795500 |  |  |  | 6736248A | 1855582 | U128885 |  | 557 | IP | INSTALL 14,600'-2,4,6,8" PMMP | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2024-05-23 |  | U128885 | 2018-09-14 | 2022-11-28 | 2024-11-08 |  |  |  | 2024-01-05 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP7955 | AMRCB |  | 100 | 055732180267955 | 703.6 | 0 | 1079300.65 | 36829.82 | 98812.06 | 29097.35 | 610404.24 | 0 | 10974.31 | 293182.87
KY | KY - EAST | 2633 | 19026867801 |  |  |  | 73641886 | 1962537 | U122858 |  | 559 | PE | INSTALL 732'-4" PMIP | 2600B | SR 40 | SR 40 | 159 | INE | 2023-04-10 |  | U122858 | 2023-04-06 | 2024-08-13 | 2024-08-30 | [5 empty] | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP8678 |  |  | 100 | 055932190268678 |  | 0 | 16182.43 | 0 | 3760.95 | 0 | 9264.33 | 0 | 929.51 | 2227.64
KY | KY - EAST | 2633 | 19026867802 |  |  |  | 73641886 | 1962537 | U122858 |  | 559 | PL | INSTALL 376'-4" PMIP | 2600E | SR 40 | SR 40 | 159 | INE | 2024-05-02 |  | U122858 | 2024-05-02 | 2024-08-13 | 2024-08-30 | [5 empty] | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00559 | 3200559 |  |  | WP8678 |  |  | 100 | 055932190268678 |  | 0
KY | KY - EAST | 2631 | 19026913000 |  |  |  | 7360252I | 1968534 | U132280 |  | 557 | CO | INSTALL 730'-2"PMMP | 2600B | PANOLA | PANOLA | 019 | CAT | 2024-03-29 |  | U132280 | 2019-11-27 | 2024-01-08 | 2024-12-31 | 2024-02-22 | ORA SLONE | 2024-03-26 | 2024-01-02 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9130 | AMRCB |  | 100 | 055732190269130 | 284.6333 | 26754 | 181403.63 | 19595.12 | 5067.14 | 4491.99 | 100470.11 | 0 | 300.03 | 51479.24 | 686
KY | KY - EAST | 2631 | 20026971500 |  |  |  | 7332288M | 2071985 | U132280 |  | 559 | PL | INSTALL 50'-4" CSHP HTR IN/OUT | 2600B | BIGGS LN POD INST PIPE | BIGGS LN POD INST PIPE | 089 | S S | 2021-05-17 |  | BKSLONE | 2020-08-28 | 2024-12-20 | 2024-12-30 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP9715 |  |  | 100 | 055932200269715 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026982400 |  |  |  | 7356256G | 2075256 | U461492 |  | 559 | VO | INSTALL 105' - 2" PMMP | 2600E | 31ST | 229 31ST ST | 019 | ASH | 2024-04-23 |  | U461492 | 2020-10-19 | 2024-12-23 | 2024-12-31 | [5 empty] | A | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 20026983300 |  |  |  | 7356256A | 2075304 | U132280 |  | 557 | IP | INSTALL 6,600'-2"/4" PMMP | 2600B | CHESTNUT | CHESTNUT DR | 019 | ASH | 2024-05-22 |  | U461492 | 2020-10-20 | 2024-03-01 | 2024-12-31 |  |  |  | 2024-04-30 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP9833 | AMRCB |  | 100 | 055732200269833 | 137.15 | 0 | 50449.64 | 492.72 | 25311.45 | -1915.81 | 11783.08 | 0 | 584.47 | 14193.73
KY | KY - EAST | 2631 | 20026983700 |  |  |  | 7352252D | 2075306 | U461383 |  | 557 | VO | INSTALL 700' - 4" PMLP | 2600B | 52ND | 52ND | 019 | ASH | 2023-05-23 |  | U461492 | 2020-10-20 | 2024-12-27 | 2024-12-31 | [5 empty] | B | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 |  |  |  |  | AMRCB |  | 100 | AMRCB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 21026130400 |  |  |  | 7360248A | 2180320 | U938437 |  | 557 | EX | INSTALL 25,111'-2",4" PMMP | 2600B | PADDLE CREEK | PADDLE CREEK RD | 019 | CAT | 2023-12-22 | U128132 | U938437 | 2021-06-29 | 2022-08-04 | 2024-12-08 | 2023-08-15 | CJH C PACK/MBLANKE | 2023-12-05 | 2022-08-01 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP1304 | AMRCB |  | 100 | 055732210261304 | 3538.9667 | 10498840 | 4355642.45 | 266096.51 | 129550.37 | 61361.56 | 3231857.71 | 0 | -9169.45 | 675945.75 | 23540
KY | KY - EAST | 2631 | 21026135500 |  |  |  | 7352252K | 2179598 | U128885 |  | 559 | PE | INSTALL 75'-4/6/12" CSHP | 2600B | SKYLINE | SKYLINE DR | 019 | ASH | 2022-06-01 |  | U938437 | 2021-08-03 | 2024-12-16 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP1355 |  |  | 100 | 055932210261355 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026145601 |  |  |  | 6720212G | 2183195 | U134275 |  | 557 | CO | INSTALL 1885' - 4" PMMP MAIN | 2600B | NEW CIRCLE | 450 E NEW CIRCLE RD | 067 | LEX | 2024-03-22 |  | U134275 | 2023-09-20 | 2023-07-05 | 2024-12-31 | 2024-03-14 | JAMIE LYNN | 2024-03-18 | 2023-09-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1456 | AMRCB |  | 100 | 055732210261456 | 776.5167 | 197902 | 764233.37 | 52493.93 | 14058.6 | 11393.72 | 460376.63 | 0 | 16580.73 | 209329.76 | 1867
KY | KY - EAST | 2631 | 21026148600 |  |  |  | 7348252H | 2183494 | U132280 |  | 561 | VO | INSTALL 450'-4" PMIP | 2600B | US-60 | 7117 US-60 | 019 | SUM | 2023-03-23 |  | U132280 | 2021-10-29 | 2024-12-11 | 2024-12-30 | [5 empty] | B | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 5356.94 | 0 | 0 | 0 | 4412.75 | 0 | 56.96 | 887.23
KY | KY - CENTRAL | 2629 | 21026151900 |  | 501315938 |  | 6740208L | 2183051 | U128885 |  | 555 | VO | INSTALL 420'-2" PMMP | 2600B | CROCKETT | 705 CROCKETT CT | 049 | WIN | 2022-11-02 |  | U128885 | 2021-11-22 | 2024-12-18 | 2024-12-25 | [5 empty] | B | 00032 | 88000000 | 0326290 | 0326290 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 21026152100 |  |  |  | 6716212N | 2075431 | U461383 |  | 557 | PE | INSTALL 535' OF 8"CSHP MAIN | 2600E | ADDISON | 629 ADDISON AV | 067 | LEX | 2022-05-02 |  | U461383 | 2021-11-23 | 2024-12-09 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1521 | AMRCB |  | 100 | 055732210261521 |  | 0 | 24034.02 | 102.33 | 14251.9 | 3021.87 | 0 | 0 | 137.83 | 6520.09
KY | KY - CENTRAL | 2629 | 22026161800 |  |  |  | 6736248A | 1855582 | U128885 |  | 557 | PE | INSTALL 8" PCF | 2600B | MOY FOO | MOY FOO AL | 097 | CYN | 2023-03-28 |  | U128885 | 2022-01-20 | 2024-01-08 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1618 | AMRCB |  | 100 | 055732220261618 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026164000 |  |  |  | 6740232N | 2286363 | U128885 |  | 557 | CO | INSTALL 5,100'-2" PMMP | 2600B | SCOTT | SCOTT AV | 017 | PAR | 2024-04-16 |  | U128885 | 2022-02-08 | 2024-08-08 | 2024-12-31 | 2023-11-01 | EDWARD FOX | 2024-04-10 | 2023-09-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1640 | AMRCB |  | 100 | 055732220261640 | 991.05 | 726831 | 1135773.48 | 68031.93 | 15773.36 | 48242.02 | 700727.52 | 0 | 5692.07 | 297306.58 | 5229
KY | KY - WEST | 2621 | 22026165500 |  |  |  | 6716208G | 2286440 | U134275 |  | 557 | IP | INSTALL 3385' OF 2" PMMP | 2600B | CHEROKEE | CHEROKEE PK | 067 | LEX | 2024-05-17 |  | U134275 | 2022-02-10 | 2024-01-22 | 2024-12-31 |  |  |  | 2024-05-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1655 | AMRCB |  | 100 | 055732220261655 | 8 | 0 | 15846.14 | 0 | 7963.13 | 0 | 3430.24 | 0 | 191.13 | 4261.64 | 0
KY | KY - WEST | 2621 | 22026167400 |  |  |  | 6716216O | 2286548 | U122858 |  | 557 | EX | EMER - INSTALL 5'-3" PMLP | 2600B | ROOSEVELT | 365 ROOSEVELT BV | 067 | LEX | 2022-05-24 | U460266 | U122858 | 2022-02-14 | 2023-06-30 | 2024-02-09 | 2022-02-09 | BJACKSON | 2022-02-09 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1674 |  |  | 100 | 055732220261674 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
KY | KY - WEST | 2623 | 22026169200 |  |  |  | 6684228J | 2286636 | U461383 |  | 557 | CO | EMER-INSTALL 4' OF 2"PMMP MAIN | 2621P | 2ND | W 2ND ST | 073 | FRA | 2024-04-24 |  | U461383 | 2022-02-16 | 2023-09-01 | 2024-12-31 |  | EFGOINS | 2022-02-15 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP1692 |  |  | 100 | 055732220261692 |  | 0 | 4550.53 | 2830.6 | 149.51 | 1062.8 | 0 | 0 | 191.23 | 316.39
KY | KY - WEST | 2621 | 22026171100 |  |  |  | 6720208A | 2286912 | U461383 |  | 557 | CO | INSTALL 2715' OF 2"/4"PMMP | 2600B | ASHLAND | ASHLAND TR | 067 | LEX | 2024-05-23 |  | U461383 | 2022-02-24 | 2024-01-22 | 2024-08-19 | 2024-05-22 | JDUNN | 2024-05-23 | 2024-01-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1711 | AMRCB |  | 100 | 055732220261711 | 699.8 | 217980 | 508709.74 | 34375.42 | 16570.35 | 5874 | 305594.91 | 0 | 4595.53 | 141699.53 | 2595
KY | KY - EAST | 2631 | 22026172301 |  |  |  | 7352260O | 2286985 | U461383 |  | 557 | CO | INSTALL 5000' OF 2"PMMP MAIN | 2600B | VERNA | VERNA | 019 | ASH | 2024-04-26 |  | U461383 | 2024-04-24 | 2023-06-30 | 2024-12-31 | 2023-10-03 | DAVID SKAGGS | 2024-04-26 | 2024-04-24 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP1723 | AMRCB |  | 100 | 055732220261723 | 1256.8667 | 812295 | 906953.7 | 85749.65 | 14365.41 | 15329.66 | 558389.51 | 0 | 3489.31 | 229630.16 | 4923
KY | KY - CENTRAL | 2629 | 22026176200 |  |  |  | 6764172E | 2285854 | U938437 |  | 559 | PE | INSTALL ~10' - 2" PMIP & CSIP | 2600E | RED LICK | RED LICK RD | 065 | IRV | 2024-04-04 |  | U938437 | 2022-03-15 | 2024-07-31 | 2024-08-01 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP1762 |  |  | 100 | 055932220261762 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026177500 |  |  |  | 6764176O | 2286885 | U128885 |  | 557 | EX | EMER - INSTALL 800'-6" CSHP | 2600B | KY RIVER | KY RIVER | 065 | IRV | 2022-10-04 | U128132 | U128885 | 2022-03-21 | 2023-06-05 | 2024-02-23 | 2022-09-20 | WILL FULKS | 2022-09-28 | 2022-08-18 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1775 | AMRCB |  | 100 | 055732220261775 | 510.0833 | 48601 | 1030814.44 | 44749.72 | 132057.98 | 39484.85 | 662212.21 | 0 | 1002.84 | 151306.84 | 917
KY | KY - WEST | 2621 | 22026177900 |  |  |  | 6716204G | 2287639 | U461383 |  | 557 | EX | INSTALL 8' OF 6"PMMP MAIN | 2600B | WILSON DOWNING | 334 WILSON DOWNING RD | 067 | LEX | 2022-08-02 | U128132 | U461383 | 2022-03-22 | 2022-11-23 | 2024-02-07 | 2022-06-30 | DEREK PAYTON | 2022-07-11 | 2022-06-27 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1779 |  |  | 100 | 055732220261779 | 124 | 126 | 36900.11 | 7642.77 | 5001.32 | 1456.13 | 16702.08 | 0 | 26.07 | 6071.74 | 9
KY | KY - WEST | 2621 | 22026178900 |  |  |  | 6728208J | 2287856 | U461383 |  | 557 | EX | INSTALL 620' OF 12"CSHP MAIN | 2600B | BIG POND | 1320 BIG POND CR | 067 | LEX | 2023-08-15 | U136251 | U461383 | 2022-03-30 | 2023-06-09 | 2024-03-31 | 2023-06-29 | BPULLIAM/FISHEL | 2023-06-30 | 2022-04-01 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP1789 | AMRCB |  | 100 | 055732220261789 | 169.8 | 14160 | 268220 | 22444.53 | 29912.65 | 51702.52 | 126168.36 | 0 | 2693.27 | 35298.67 | 590
KY | KY - WEST | 2621 | 22026182500 |  |  |  | 6712212O | 2288351 | U132703 |  | 559 | OP | INSTALL 16'-6" PMMP AND C. VLV | 2600E | LANE ALLEN | 1013 LANE ALLEN RD | 067 | LEX | 2022-11-07 |  | U132703 | 2022-04-20 | 2024-12-30 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP1825 | AMRCB |  | 100 | 055932220261825 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 22026183001 |  | 501327244 |  | 6688228L | 2287144 | U126783 |  | 555 | CO | INSTALL 4955'-2" PMMP | 2600B | LEESTOWN | 1100 LEESTOWN RD | 073 | FRA | 2024-05-24 |  | U126783 | 2024-04-30 | 2024-11-26 | 2024-12-25 | 2023-03-22 | ALEX WILLIAMSON | 2024-05-24 | 2023-02-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP1830 |  |  | 100 | 055532220261830 |  | 1705 | 130575.28 | 17739.46 | 15801.11 | 2375.96 | 67640.81 | 0 | 7450.98 | 19566.96 | 1705
KY | KY - WEST | 2621 | 22026183301 |  |  |  | 6716212B | 1968251 | U134275 |  | 561 | EX | SMRP INSTALL 1120' 8-12" CSHP | 2600B | LEESTOWN | 1498 LEESTOWN RD | 067 | LEX | 2024-04-17 | U136251 | U134275 | 2024-03-11 | 2023-11-29 | 2024-03-15 | 2024-03-04 | JOSH PASLEY/TEAM FISHEL | 2024-03-06 | 2023-09-11 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP1833 | AMRCB |  | 100 | 056132220261833 | 824.8333 | 103494 | 1604004.44 | 66678.58 | 157192.99 | 84034.93 | 935809.91 | 0 | 27981.52 | 332306.51 | 1101
KY | KY - CENTRAL | 2629 | 22026185100 |  |  |  | 7240204B | 2288754 | U128885 |  | 557 | EX | INSTALL 10'-2" PMMP | 2621P | LEVEE | 4760 LEVEE RD | 173 | LEV | 2022-08-23 | U128132 | U128885 | 2022-05-10 | 2023-08-24 | 2024-04-29 | 2022-05-10 | WDENNINGHOFF | 2022-05-10 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP1851 |  |  | 100 | 055732220261851 |  | 2 | 6123.2 | 2711.99 | 502.32 | 249.83 | 1664 | 0 | 4.54 | 990.52 | 2
KY | KY - WEST | 2623 | 22026205401 |  | 501281464 |  | 6696212N | 2289302 | U126783 |  | 555 | EX | INSTALL 1330'-4" PMMP | 2600B | SCHOOL HOUSE | SCHOOL HOUSE RD | 239 | VER | 2024-04-12 | U136251 | U126783 | 2024-03-25 | 2024-03-08 | 2024-04-05 | 2024-03-26 | DEREK PAYTON | 2024-03-26 | 2024-03-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2054 |  |  | 100 | 055532220262054 | 174.9333 | 0 | 278666.05 | 11293.92 | 14380.31 | 5594.86 | 163749.15 | 0 | 1748.41 | 81899.4
KY | KY - EAST | 2631 | 22026205600 |  |  |  | 7352256H | 2289560 | U132280 |  | 557 | EX | INSTALL 1200'-2" PMMP | 2600B | CENTRAL | CENTRAL PY | 019 | ASH | 2022-11-17 | U128132 | U132280 | 2022-06-16 | 2022-09-27 | 2024-12-25 | 2022-10-03 | DAVID SKAGGS | 2022-10-04 | 2022-08-31 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2056 | AMRCB |  | 100 | 055732220262056 | 201.85 | 31700 | 162971.11 | 10645.56 | 6415.71 | 1922.96 | 125499.62 | 0 | 309.91 | 18177.35 | 1268
KY | KY - WEST | 2621 | 22026206000 |  |  |  | 6720212M | 2289588 | U132703 |  | 559 | VO | CB-INSTALL 10'-6" PMMP | 2600E | CLAY | 320 CLAY AV | 067 | LEX | 2022-12-07 |  | U132703 | 2022-06-17 | 2024-12-27 | 2024-12-31 | [5 empty] | B | 00032 | 88000000 | 0326210 | 0326210 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026206900 |  |  |  | 6720212N | 2289650 | U461383 |  | 557 | EX | EMER-INSTALL 16' OF 4"/6"PMLP | 2621P | AURORA | 931 AURORA AV | 067 | LEX | 2022-09-06 | U460266 | U461383 | 2022-06-21 | 2022-06-30 | 2024-05-22 | 2022-07-01 | KKINDER | 2022-07-15 | 2022-07-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2069 | AMRCB |  | 100 | 055732220262069 | 21.9667 | 90 | 11009.07 | 1974.61 | 1383.87 | 159.46 | 6211.57 | 0 | 3.61 | 1275.95 | 18
KY | KY - EAST | 2631 | 22026207100 |  |  |  |  | 2289651 | U938437 |  | 557 | IP | INSTALL 7870'-2", 4" PMMP | 2600B | VIRGINIA | VIRGINIA | 019 | ASH | 2024-05-28 |  | U132280 | 2022-06-21 | 2024-01-02 | 2024-12-31 |  |  |  | 2024-01-02 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2071 | AMRCB |  | 100 | 055732220262071 | 759.15 | 0 | 621506.86 | 41432.3 | 36915.33 | 11393.46 | 350451.2 | 0 | 5002.86 | 176311.71
KY | KY - WEST | 2623 | 22026210901 |  | 501313752 |  | 6716232B | 2289995 | U132703 |  | 555 | EX | INSTALL 8OO' OF 2"PMMP MAIN | 2600B | OAK HILL | OAK HILL LN LT1 | 209 | GEO | 2024-05-28 | U461309 | U132703 | 2023-11-13 | 2024-02-26 | 2024-03-08 | 2024-02-20 | R.HUMPHREYS | 2024-02-20 | 2024-02-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2109 |  |  | 100 | 055532220262109 | 56.25 | 6312 | 53408.53 | 3919.07 | 4251.75 | 3280.74 | 27957.48 | 0 | 240.9 | 13758.59 | 789
KY | KY - WEST | 2621 | 22026217800 |  |  |  | 6716208E | 2290789 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 4"PMLP MAIN | 2621P | ROSEMILL | 591 ROSEMILL DR | 067 | LEX | 2022-11-08 | U130872 | U461383 | 2022-08-12 | 2023-10-31 | 2024-06-29 | 2022-08-17 | R CRAWFORD | 2022-08-18 | 2022-08-16 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2178 | AMRCB |  | 100 | 055732220262178 | 54.3167 | 110 | 12300.82 | 4908.31 | 1034.64 | 300.96 | 4447.36 | 0 | 0.5 | 1609.05 | 10
KY | KY - WEST | 2621 | 22026224200 |  |  |  | 6716212P | 2291708 | U461383 |  | 557 | PE | INSTALL 2300' OF 2"/4"PMMP | 2600E | COLUMBIA | 321 COLUMBIA AV | 067 | LEX | 2023-05-08 |  | U461383 | 2022-09-19 | 2024-10-10 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2242 | AMRCB |  | 100 | 055732220262242 |  | 0 | 19730.91 | 243.43 | 13643.98 | 266.55 | 0 | 0 | 64 | 5512.95
KY | KY - WEST | 2623 | 22026224800 |  |  |  | 6688228A | 2291830 | U126783 |  | 557 | VO | REPLACE MAIN - LEAKAGE | 2621P | SCHENKEL LANE | 565 SCHENKEL LANE | 073 | FRA | 2023-08-08 |  | U126783 | 2022-09-20 | 2023-06-30 | 2024-02-07 | [5 empty] | A | 00032 | 88000000 | 0326230 | 0326230 | 00032 | 05007 |  |  |  |  | AMRCB |  | 100 | AMRCB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 22026227600 |  |  |  | 6744204D | 2292274 | U128885 |  | 557 | EX | EMER - INSTALL 60'-4" PMLP | 2600B | MAPLE | 504 S MAPLE ST | 049 | WIN | 2022-10-10 | U128132 | U128885 | 2022-09-28 | 2022-09-27 | 2024-09-07 | 2022-09-28 | ED FOX | 2022-09-28 | 2022-09-29 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2276 | AMRCB |  | 100 | 055732220262276 | 15.3 | 165 | 21421.89 | 930.81 | 0 | 192.82 | 17356.23 | 0 | 15.54 | 2926.49 | 55
KY | KY - CENTRAL | 2629 | 22026228201 |  |  |  | 6748208I | 2292377 | U128885 |  | 557 | EX | INSTALL 4,225'-2"/6" PMMP | 2600B | MAPLE | MAPLE ST | 049 | WIN | 2023-06-26 | U128132 | U128885 | 2023-04-04 | 2023-06-07 | 2024-09-20 | 2023-05-04 | SHAWN DENNIS | 2023-05-22 | 2023-01-03 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2282 | AMRCB |  | 100 | 055732220262282 | 1232.6333 | 592952 | 1935349.38 | 87394.52 | 194217.88 | 23445.35 | 1330790.74 | 0 | 18527.52 | 280973.37 | 3901
KY | KY - WEST | 2621 | 22026228500 |  |  |  | 6728208M | 2290202 | U122858 |  | 561 | IP | INSTALL 167'-2" PMMP | 2600B | CULZEAN | CULZEAN CT | 067 | LEX | 2024-05-20 |  | U122858 | 2022-09-30 | 2024-06-14 | 2024-06-30 |  |  |  | 2024-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2285 |  |  | 100 | 056132220262285 | 34.95 | 0 | 21908.05 | 0 | 798.44 | 49.2 | 19061.88 | 0 | 612.89 | 1385.64
KY | KY - WEST | 2623 | 22026230600 |  |  |  | 6688228A | 2292673 | U461383 |  | 557 | CO | EMER-INSTALL 5' OF 3"PMMP MAIN | 2621P | COLONIAL | 806 COLONIAL | 073 | FRA | 2024-04-24 |  | U461383 | 2022-10-10 | 2023-09-29 | 2024-05-10 |  | D COLLINS | 2022-10-06 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2306 |  |  | 100 | 055732220262306 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026231300 |  |  |  | 6720212M | 2292814 | U461383 |  | 557 | PE | INSTALL 925' OF 2"PMMP MAIN | 2600B | HIGH | 626 E HIGH ST | 067 | LEX | 2023-03-17 |  | U461383 | 2022-10-13 | 2024-11-11 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2313 | AMRCB |  | 100 | 055732220262313 |  | 0 | 4871.01 | 12.57 | 3457.12 | 11.92 | 0 | 0 | 12.35 | 1377.05
KY | KY - WEST | 2623 | 22026235100 |  | 501338492 |  | 6712228L | 2292762 | U126783 |  | 555 | EX | INSTALL 2160'-2"/4" PMMP | 2600B | BILL PERKINS | BILL PERKINS LN LT62 | 209 | GEO | 2024-03-25 | U128132 | U126783 | 2022-11-09 | 2023-06-09 | 2024-02-29 | 2024-02-09 | R.HUMPHREYS | 2024-02-09 | 2023-10-04 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2351 |  |  | 100 | 055532220262351 | 303.0667 | 89520 | 179234.21 | 18704.02 | 8360.48 | 3310.74 | 100221.81 | 0 | 1807.63 | 46829.53 | 2238
KY | KY - WEST | 2623 | 22026235300 |  |  |  | 6712228F | 2293486 | U132703 |  | 557 | IP | INST 1865'-8" & 390'-2" PMMP | 2600B | OLD LEMONS MILL | 325 OLD LEMONS MILL | 209 | GEO | 2024-03-08 |  | U132703 | 2022-11-09 | 2024-10-17 | 2024-12-31 |  |  |  | 2024-03-08 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2353 | AMRCB |  | 100 | 055732220262353 | 349 | 0 | 411299.7 | 12262.51 | 30464.82 | 33323.66 | 220586.24 | 0 | 1912.26 | 112750.21
KY | KY - WEST | 2621 | 22026236100 |  |  |  | 6720212B | 2293506 | U122858 |  | 561 | VO | INSTALL 1150'-2" PMMP | 2600E | LOCUST | LOCUST AV | 067 | LEX | 2024-02-05 |  | U122858 | 2022-11-11 | 2024-12-30 | 2024-12-31 | [5 empty] | B | 00032 | 88000000 | 0326210 | 0326210 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 22026236700 |  |  |  | 6720212B | 2293506 | U122858 |  | 561 | EX | INSTALL 134'-4" PMLP | 2600E | LOCUST | 328 LOCUST AV | 067 | LEX | 2024-03-13 | U136251 | U122858 | 2022-11-14 | 2024-03-18 | 2024-03-20 | 2024-02-19 | MCRAIG | 2024-02-27 | 2024-02-12 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2367 |  |  | 100 | 056132220262367 | 147.9 | 2880 | 27648.79 | 10788.78 | 1259.06 | 3429.77 | 4478.88 | 0 | 50.47 | 7641.83 | 160
KY | KY - WEST | 2623 | 22026236900 |  |  |  | 6712228C | 2293665 | U132703 |  | 557 | IP | INSTALL 11300'-2" PMMP | 2600B | CLAYTON | CLAYTON | 209 | GEO | 2024-05-23 |  | U132703 | 2022-11-15 | 2024-01-15 | 2024-12-31 |  |  |  | 2024-01-02 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2369 | AMRCB |  | 100 | 055732220262369 | 695.6167 | 0 | 532422.41 | 30051.81 | 28154.01 | 12795.61 | 308843.05 | 0 | 5534.45 | 147043.48
KY | KY - CENTRAL | 2629 | 22026237801 |  |  |  | 6732252O | 2293704 | U128885 |  | 557 | EX | INSTALL 4,100'-2" PMMP | 2600B | BROADWAY | BROADWAY AV | 097 | CYN | 2024-03-07 | U128132 | U128885 | 2023-10-27 | 2024-08-09 | 2024-12-31 | 2024-01-25 | WILL FULKS | 2024-02-27 | 2024-02-22 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP2378 | AMRCB |  | 100 | 055732220262378 | 615.15 | 386910 | 834963.88 | 41931.52 | 17120.46 | 12949.59 | 534594.13 | 0 | 1499.81 | 226868.37 | 4299
KY | KY - WEST | 2623 | 22026238301 |  | 501335909 |  | 6700224H | 2289685 | U126783 |  | 555 | EX | INSTALL 2505'-4" PHHP | 2600B | LEESTOWN | 158 W LEESTOWN RD BOILER | 239 | MID | 2024-03-15 | U128132 | U126783 | 2024-01-10 | 2023-09-11 | 2024-01-31 | 2024-01-01 | J ENSMINGER | 2024-01-08 | 2024-01-12 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2383 |  |  | 100 | 055532220262383 | 585.4667 | 236210 | 289073.85 | 39933.22 | 19240.5 | 20767.49 | 150277.85 | 0 | 6881.16 | 51973.63 | 2990
KY | KY - WEST | 2623 | 22026238401 |  |  |  | 6700224L | 2293724 | U122858 |  | 557 | IP | INSTALL 5765'-2" PMMP | 2600B | WINTER | WINTER | 239 | MID | 2024-05-28 |  | U122858 | 2023-11-28 | 2024-08-09 | 2024-12-31 |  |  |  | 2024-03-19 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2384 | AMRCB |  | 100 | 055732220262384 | 344.9833 | 0 | 268542.23 | 12880.55 | 12028.59 | 4122.04 | 160176.67 | 0 | 1415.53 | 77918.85
KY | KY - WEST | 2621 | 22026239700 |  |  |  | 6720212F | 2293756 | U134275 |  | 557 | PE | INSTALL 8390'-2" PMMP | 2600B | CASTLEWOOD | 209 CASTLEWOOD DR | 067 | LEX | 2023-11-02 |  | U134275 | 2022-11-17 | 2024-06-25 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2397 | AMRCB |  | 100 | 055732220262397 |  | 0 | 30138.25 | 39.03 | 21018.4 | 36.63 | 442.58 | 0 | 81.86 | 8519.75
KY | KY - WEST | 2621 | 22026239701 |  |  |  | 6720212F | 2293756 | U134275 |  | 557 | VO | INSTALL 8390'-2" PMMP | 2600E | CASTLEWOOD | 209 CASTLEWOOD DR | 067 | LEX | 2024-04-15 |  | U134275 | 2024-02-27 | 2024-06-25 | 2024-12-31 | [5 empty] | B | [11 empty] | 22026239700 | 100 |  |  | 0
KY | KY - WEST | 2621 | 22026239900 |  |  |  | 6720208B | 2293757 | U134275 |  | 557 | PE | INSTALL 3845' OF 2,4,6" PMMP | 2600B | RICHMOND | RICHMOND RD | 067 | LEX | 2023-11-03 |  | U134275 | 2022-11-17 | 2024-06-27 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2399 | AMRCB |  | 100 | 055732220262399 |  | 0 | 33287.74 | 0 | 0 | 6517.5 | 17996.08 | 0 | 311.35 | 8462.81
KY | KY - WEST | 2621 | 22026239901 |  |  |  |  | 2293757 |  |  | 557 | OP | INSTALL 3845' OF 2,4,6" PMMP | 2600B | RICHMOND | RICHMOND RD | 067 | LEX | 2024-02-29 |  | U134275 | 2024-02-29 | 2024-06-27 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2399 | AMRCB |  | 100 | 055732220262399 |  | 0
KY | KY - WEST | 2623 | 22026241701 |  |  |  | 6712228B | 2294169 | U461383 |  | 561 | CO | INSTALL 1425' OF 2"PMMP MAIN | 2600B | WASHINGTON | W WASHINGTON ST | 209 | GEO | 2024-05-09 |  | U461383 | 2024-04-08 | 2024-01-15 | 2024-06-01 | 2024-04-12 | LESLIE SHARON | 2024-05-08 | 2024-04-10 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP2417 | AMRCB |  | 100 | 056132220262417 | 540.5667 | 98325 | 599444.91 | 33621.85 | 4332.75 | 34765.58 | 351905.56 | 0 | 4832.84 | 169986.33 | 1425
KY | KY - WEST | 2623 | 22026245100 |  |  |  | 6700228K | 2294541 | U461383 |  | 557 | CO | EMER-INSTALL 3' OF 2"PHHP MAIN | 2600B | ROCKY WATERS | ROCKY WATERS | 209 | GEO | 2024-04-10 |  | U461383 | 2022-12-21 | 2024-12-31 | 2024-12-31 | 2022-12-07 | KEVIN KOUNS | 2022-12-07 |  |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2451 |  |  | 100 | 055732220262451 |  | 3 | 2752.76 | 1940.88 | 0 | 347.03 | 301.5 | 0 | 18.18 | 145.17 | 3
KY | KY - WEST | 2621 | 23026252600 |  |  |  | 6720212B | 2395075 | U461383 |  | 557 | EX | INSTALL 3' OF 4"PMLP MAIN | 2621P | LOCUST | 216 LOCUST AV | 067 | LEX | 2023-02-16 | U128132 | U461383 | 2023-01-20 | 2023-12-28 | 2024-08-26 | 2023-01-25 | LSTANFI | 2023-01-25 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2526 | AMRCB |  | 100 | 055732230262526 | 0.23333 | 5 | 16571.37 | 3932.04 | 307.2 | 278.6 | 9758.8 | 0 | 7.8 | 2286.93 | 5
KY | KY - WEST | 2621 | 23026254900 |  |  |  | 6716208C | 2395330 | U461383 |  | 561 | PE | INSTALL 620' OF 8"CSHP MAIN | 2600B | CONN TERRACE | CONN TERRACE ST | 067 | LEX | 2023-08-23 |  | U461383 | 2023-02-01 | 2024-07-23 | 2024-10-01 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2549 |  |  | 100 | 056132230262549 |  | 0 | 30923.42 | 224.22 | 14684.87 | 212.61 | 6818.77 | 0 | 11.08 | 8971.87
KY | KY - CENTRAL | 2629 | 23026255500 |  |  |  | 6764172E | 2285854 | U938437 |  | 559 | PE | INSTALL 2" SS & BYPASS | 2600B | RED LICK | 66 RED LICK RD | 065 | IRV | 2024-04-04 |  | U136909 | 2023-02-06 | 2024-08-30 | 2024-08-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP2555 |  |  | 100 | 055932230262555 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026255700 |  |  |  | 6740208D | 2395401 | U128885 |  | 559 | OP | INSTALL 4,400'-6" PMMP | 2600E | ROCKWELL | ROCKWELL RD | 049 | WIN | 2023-02-08 |  | U128885 | 2023-02-06 | 2024-12-16 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP2557 |  |  | 100 | 055932230262557 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026262700 |  |  |  | 6712208M | 2395746 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 2621P | PALOMAR COVE | 3905 PALOMAR COVE LN | 067 | LEX | 2023-03-28 | U121331 | U461383 | 2023-02-21 | 2023-03-07 | 2024-05-19 | 2023-02-23 | KKINDER | 2023-03-07 | 2023-02-22 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2627 |  |  | 100 | 055732230262627 | 22.8333 | 25 | 3582.24 | 1399.43 | 125.14 | 79.33 | 1397.45 | 0 | 4.16 | 576.73 | 5
KY | KY - WEST | 2623 | 23026262900 |  | 501344588 |  | 6704212J | 2395698 | U126783 |  | 555 | VO | INSTALL 4600'-6" PMMP | 2600B | PISGAH | 460 PISGAH PK | 239 | VER | 2023-07-25 |  | U126783 | 2023-02-22 | 2024-12-19 | 2024-12-20 | [5 empty] | B | 00032 | 88000000 | 0326230 | 0326230 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026264700 |  |  |  | 6716208D | 2395969 | U461383 |  | 557 | EX | INSTALL 100' OF 3"PMLP MAIN | 2621P | COLUMBIA | 625 COLUMBIA AV | 067 | LEX | 2023-05-25 | U133347 | U461383 | 2023-03-03 | 2023-12-21 | 2024-08-11 | 2023-04-05 | HMCKUNE | 2023-04-19 | 2023-04-03 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2647 | AMRCB |  | 100 | 055732230262647 | 73.7667 | 1200 | 21922.36 | 4253.08 | 2943.07 | 478.99 | 10934.63 | 0 | 29.12 | 3283.47 | 100
KY | KY - WEST | 2621 | 23026266600 |  |  |  | 6720200A | 2395811 |  |  | 559 | VO | INSTALL 50'-4" PMMP | 2600E | ROCKBRIDGE | 1095 ROCKBRIDGE | 067 | LEX | 2023-03-16 |  | U122858 | 2023-03-16 | 2024-08-01 | 2024-08-03 | [5 empty] | B | 00032 | 88000000 | 0326210 | 0326210 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026267200 |  |  |  | 6716208K | 2396254 | U122858 |  | 557 | EX | INSTALL 60'-4" PMLP | 2600B | JESSELIN | 107 JESSELIN DR | 067 | LEX | 2024-04-03 | U128132 | U122858 | 2023-03-16 | 2024-02-12 | 2024-06-30 | 2024-03-28 | JOSHUA COX | 2024-03-28 | 2024-03-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2672 | AMRCB |  | 100 | 055732230262672 | 62.9667 | 801 | 28543.91 | 3968.03 | 2926.07 | 389.48 | 12642.99 | 0 | 98.79 | 8518.55 | 89
KY | KY - WEST | 2621 | 23026268200 |  |  |  | 6716208B | 2396396 | U461383 |  | 557 | EX | INSERT 160' OF 3"PMLP MAIN | 2621P | SAINT JOSEPH | SAINT JOSEPH DR | 067 | LEX | 2023-06-20 | U128132 | U461383 | 2023-03-22 | 2023-12-27 | 2024-08-10 | 2023-04-13 | JOSHUA COX | 2023-04-14 | 2023-04-10 | 2023-04-11 | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2682 | AMRCB |  | 100 | 055732230262682 | 84.2833 | 2310 | 12586.85 | 5594.02 | 3451.23 | 1097.83 | 179.3 | 0 | 26.07 | 2238.4 | 165
KY | KY - WEST | 2621 | 23026270600 |  | 501202041 |  | 6712208M | 2396687 | U134275 |  | 555 | OP | INSTALL 205' OF 2" PMMP | 2600E | MERRIDEW | 3833 MERRIDEW WY | 067 | LEX | 2023-09-29 |  | U134275 | 2023-04-04 | 2024-04-19 | 2024-07-25 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2706 |  |  | 100 | 055532230262706 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026272901 |  | 501347263 |  | 6712204E | 2397231 | U461383 |  | 555 | EX | INSTALL 2500' OF 2"PMMP MAIN | 2600B | POLLY | POLLY CT LT1 | 113 | NIC | 2024-04-03 | U128132 | U461383 | 2024-02-09 | 2024-02-01 | 2024-03-22 | 2024-03-13 | JOSHUA COX | 2024-03-15 | 2024-02-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2729 |  |  | 100 | 055532230262729 | 355.3167 | 123050 | 249918.71 | 23500.97 | 5579.9 | -196.75 | 150200.97 | 0 | 1748.04 | 69085.58 | 2675
KY | KY - WEST | 2621 | 23026278200 |  |  |  | 6720212E | 2398026 | U461383 |  | 557 | EX | EMER-INSTALL 185' OF 4"PMLP | 2600B | 5TH | 201 E 5TH ST | 067 | LEX | 2023-06-23 | U124014 | U461383 | 2023-06-06 | 2024-01-29 | 2024-09-06 | 2023-06-15 | LESLIE SHARON | 2023-06-16 | 2023-06-09 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2782 | AMRCB |  | 100 | 055732230262782 | 68.5 | 1472 | 41523.49 | 4449.03 | 3542.99 | 2962.98 | 24751.4 | 0 | 91.71 | 5725.38 | 184
KY | KY - EAST | 2631 | 23026279200 |  |  |  |  | 2075305 | U132280 |  | 557 | VO | INSTALL 5'-6" PMLP | 2600B | EPPERSON | EPPERSON ST | 019 | ASH | 2023-07-12 |  | U132280 | 2023-06-16 | 2024-12-19 | 2024-12-20 | [5 empty] | B | [11 empty] | 20026983500 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026279500 |  |  |  | 7356256B | 2398273 | U122858 |  | 561 | CO | INSTALL 339'-8" PMLP | 2600E | 18TH | 18TH ST | 019 | ASH | 2024-05-10 |  | U122858 | 2023-06-16 | 2024-12-13 | 2024-12-30 |  | MCOLLET | 2024-05-10 | 2024-04-22 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00561 | 3200561 |  |  | WP2795 | AMRCB |  | 100 | 056132230262795 | 381.7167 | 0 | 49412.89 | 12812.72 | 11180.69 | 11478.63 | 0 | 0 | 115.57 | 13825.28
KY | KY - CENTRAL | 2629 | 23026282200 |  | 501350609 |  | 6732244D | 2398474 | U128885 |  | 555 | VO | INSTALL 13,000'-8" PHHP | 2600E | SEA BISCUIT | 634 SEA BISCUIT WY | 097 | CYN | 2024-02-21 |  | U128885 | 2023-07-05 | 2024-12-31 | 2024-12-31 | [5 empty] | B | 00032 | 88000000 | 0318230 | 0318230 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026282800 |  |  |  | 6688228L | 2398629 | U126783 |  | 557 | CO | EMER - INSTALL 5'-2" PMMP | 2621P | REGENTS PARK | REGENTS PARK | 073 | FRA | 2024-04-24 |  | U126783 | 2023-07-06 | 2024-03-21 | 2024-04-28 |  | EFGOINS | 2023-07-05 | 2023-11-16 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2828 |  |  | 100 | 055732230262828 | 6.1667 | 0 | 9124.43 | 4994.36 | 0 | 1868.67 | 1642 | 0 | 232.43 | 386.97
KY | KY - EAST | 2631 | 23026283100 |  | 501343072 |  | 7356220N | 2398575 | U122858 |  | 555 | PE | INSTALL 1200'-2"&4" PMMP | 2600E | FALLS CREEK | 191 FALLS CREEK DR | 127 | LOU | 2023-10-09 |  | U122858 | 2023-07-07 | 2024-06-13 | 2024-06-30 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2831 |  |  | 100 | 055532230262831 |  | 0 | 12842.28 | 0 | 4130.47 | -2134.19 | 6812.23 | 0 | 0 | 4033.77
KY | KY - EAST | 2631 | 23026283600 |  |  |  | 7352256H | 2289651 | U938437 |  | 557 | IP | INSTALL LP FITTINGS | 2600B | VIRGINIA | VIRGINIA AV | 019 | ASH | 2024-01-02 |  | U938437 | 2023-07-10 | 2024-12-31 | 2024-12-31 |  |  |  | 2024-01-02 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2836 | AMRCB |  | 100 | 055732230262836 | 0.43333 | 0 | 42.87 | 26.07 | 0 | 4.85 | 0 | 0 | 0.7 | 11.25
KY | KY - WEST | 2623 | 23026283801 |  | 501350442 |  | 6700212O | 2398395 | U126783 |  | 555 | EX | INSTALL 5705'-2"/4" PMMP | 2600B | GLENEAGLES | GLENEAGLES WY LT54 | 239 | VER | 2024-05-02 | U136251 | U126783 | 2023-11-01 | 2024-01-22 | 2024-05-31 | 2024-04-08 | DEREK PAYTON | 2024-04-11 | 2024-01-15 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2838 |  |  | 100 | 055532230262838 | 350.45 | 268875 | 370199.15 | 23921.42 | 25539.77 | 536.59 | 212788.33 | 0 | 3789.47 | 103623.57 | 5975
KY | KY - WEST | 2623 | 23026284000 |  |  |  | 6688228B | 2398759 | U461383 |  | 557 | EX | EMER-INSTALL 2' OF 3"PMMP MAIN | 2621P | COMANCHE | 615 COMANCHE TL | 073 | FRA | 2023-08-11 | U128132 | U461383 | 2023-07-13 | 2023-11-30 | 2024-07-25 | 2023-07-12 | CDESPAIN | 2023-07-26 | 2023-07-19 |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2840 |  |  | 100 | 055732230262840 | 8.7667 | 4 | 14848.12 | 7201.21 | 156.69 | 430.34 | 4823.42 | 0 | 30.98 | 2205.48 | 2
KY | KY - EAST | 2631 | 23026284800 |  |  |  | 7352256L | 2398947 | U122858 |  | 557 | EX | EMER - INSTALL 40'-4" PMLP | 2621P | WILLIS | 3412 WILLIS ST | 019 | ASH | 2023-09-12 | U128132 | U122858 | 2023-07-20 | 2024-03-27 | 2024-03-31 | 2023-07-21 | MCOLLET | 2023-07-25 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2848 | AMRCB |  | 100 | 055732230262848 | 2.0833 | 34 | 630.98 | 138.17 | 0 | 347.54 | 45.1 | 0 | 1.36 | 98.81 | 34
KY | KY - CENTRAL | 2629 | 23026286500 |  | 501351304 |  | 6736228K | 2398765 | U128885 |  | 555 | VO | INSTALL 2250'-4" PMMP | 2600E | LINZI | LINZI WY LT45 | 017 | PAR | 2024-02-27 |  | U128885 | 2023-08-03 | 2024-12-09 | 2024-12-31 | [5 empty] | B | 00032 | 88000000 | 0326290 | 0326290 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026286600 |  | 501351304 |  | 6736228K | 2398765 | U128885 |  | 555 | VO | INSTALL 350'-4" PMMP | 2600E | BETHLEHEM | BETHLEHEM RD | 017 | PAR | 2024-02-27 |  | U128885 | 2023-08-03 | 2024-12-18 | 2024-12-25 | [5 empty] | B | 00032 | 88000000 | 0326290 | 0326290 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 23026287300 |  |  |  | 7256276A | 2398923 | U122858 |  | 561 | OP | INSTALL 121'-4" CSMP | 2600E | ALGONQUIN | ALGONQUIN DR E | 161 | MAY | 2024-05-07 |  | U122858 | 2023-08-07 | 2024-03-08 | 2024-12-30 | [5 empty] | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP2873 |  |  | 100 | 056132230262873 |  | 0 | 529.04 | 203.57 | 0 | 177.95 | 0 | 0 | 8.65 | 138.87
KY | KY - WEST | 2621 | 23026287600 |  |  |  | 6712212H | 2399333 | U126783 |  | 559 | IP | INSTALL 30'-4" PMMP | 2621P | OXFORD CIRCLE | 1918 OXFORD CIRCLE | 067 | LEX | 2024-05-01 |  | U126783 | 2023-08-09 | 2023-12-27 | 2024-12-25 |  |  |  | 2024-05-01 |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP2876 |  |  | 100 | 055932230262876 | 87.3167 | 0 | 1449.35 | 0 | 1035.01 | 0 | 0 | 0 | 3.44 | 410.9
KY | KY - WEST | 2621 | 23026288400 |  | 501352417 |  | 6720216A | 2399299 | U461383 |  | 555 | IP | INSTALL 5500' OF 4"PMMP MAIN | 2600B | PROVIDENCE PL | 1021 PROVIDENCE PL PY | 067 | LEX | 2024-04-25 |  | U461383 | 2023-08-10 | 2024-02-12 | 2024-07-31 |  |  |  | 2024-04-01 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2884 |  |  | 100 | 055532230262884 | 144.6667 | 0 | 142683.71 | 8788.75 | 26531.56 | 550.53 | 66657.94 | 0 | 109.1 | 40045.83
KY | KY - WEST | 2623 | 23026288900 |  | 501348814 |  | 6712228D | 2397832 | U126783 |  | 555 | OP | INSTALL 850'-2" PMMP | 2600B | MAIN | 944 E MAIN ST EXT | 209 | GEO | 2024-04-25 |  | U126783 | 2023-08-15 | 2024-12-20 | 2024-12-25 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2889 |  |  | 100 | 055532230262889 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 23026289700 |  |  |  | 6712232N | 2399730 | U461383 |  | 557 | PE | INSTALL 70' OF 3"PMLP MAIN | 2621P | BROADWAY | 359 N BROADWAY ST DN | 209 | GEO | 2023-08-28 |  | U461383 | 2023-08-25 | 2023-11-28 | 2024-07-21 | [5 empty] | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2897 | AMRCB |  | 100 | 055732230262897 |  | 0 | 7142.06 | 1714.89 | 2970.45 | 519.42 | 0 | 0 | 226.03 | 1711.27
KY | KY - WEST | 2621 | 23026292000 |  | 501354002 |  | 6724204F | 2399927 | U461383 |  | 555 | EX | INSTALL 2450' OF 2"PMMP MAIN | 2600B | WESTON | 376 WESTON PK LT1 | 067 | LEX | 2024-02-27 | U124014 | U461383 | 2023-09-05 | 2024-02-12 | 2024-03-01 | 2024-02-20 | DDAVIS | 2024-02-20 | 2024-01-24 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2920 |  |  | 100 | 055532230262920 | 127.1833 | 47787 | 93827.73 | 8973.4 | 4556.47 | 8765.52 | 45780.34 | 0 | 315.05 | 25436.95 | 2811
KY | KY - WEST | 2623 | 23026292201 |  | 501354062 |  | 6684228K | 2180883 | U126783 |  | 555 | CO | INSTALL 360'-4" PMMP | 2600E | BROADWAY | 106 E BROADWAY ST NEW | 073 | FRA | 2024-05-28 |  | U126783 | 2024-03-04 | 2024-01-15 | 2024-02-29 | 2024-03-08 | KEVIN KOUNS | 2024-04-22 | 2024-01-26 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2922 |  |  | 100 | 055532230262922 | 114.25 | 4998 | 171558.17 | 7541.43 | 2418.18 | 3761.92 | 109171.99 | 0 | 868.13 | 47796.52 | 357
KY | KY - EAST | 2631 | 23026292300 |  |  |  | 7352256G | 2399973 | U122858 |  | 559 | CO | INSTALL 2" SS | 2600E | ROBERTS | 3308 ROBERTS DR | 019 | ASH | 2024-01-16 |  | U122858 | 2023-09-06 | 2024-02-27 | 2024-02-28 |  | RECUMP | 2024-01-16 | 2024-01-03 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP2923 |  |  | 100 | 055932230262923 | 9.8333 | 0 | 1072.33 | 634.48 | 0 | 135.21 | 0 | 0 | 18.06 | 284.58
KY | KY - WEST | 2621 | 23026292501 |  |  |  | 6716212B | 1968251 | U134275 |  | 561 | EX | INSTALL 800' OF 2-4" PMMP | 2600B | LEESTOWN | 1500 LEESTOWN RD | 067 | LEX | 2024-04-10 | U136251 | U134275 | 2023-11-01 | 2023-10-18 | 2024-11-30 | 2023-10-06 | JOSH PASLEY | 2023-10-06 | 2023-10-04 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2925 | AMRCB |  | 100 | 056132230262925 | 30.5 | 2382 | 232050.11 | 2864.91 | 7199.81 | 4048.09 | 138102.28 | 0 | 514.38 | 79320.64 | 794
KY | KY - EAST | 2631 | 23026293500 |  |  |  | 7352264E | 2300016 | U461383 |  | 557 | IP | INSTALL 3800' OF 2"PMMP MAIN | 2600B | RIVERSIDE | RIVERSIDE DR | 089 | RUS | 2024-04-19 |  | U461383 | 2023-09-08 | 2024-09-09 | 2024-12-31 |  |  |  | 2024-04-19 |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP2935 | AMRCB |  | 100 | 055732230262935 | 190.4667 | 0 | 61898.74 | 3100.13 | 10440.31 | 25114.85 | 12448.03 | 0 | 235.03 | 10560.39
KY | KY - WEST | 2621 | 23026293700 |  |  |  | 6716216N | 2395080 | U122858 |  | 561 | CO | INSTALL 74'-2" PMMP | 2600E | FORBES | FORBES DR | 067 | LEX | 2024-04-29 |  | U122858 | 2023-09-08 | 2024-06-05 | 2024-06-30 | 2024-02-21 | DBANKS | 2024-02-21 | 2024-02-19 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2937 |  |  | 100 | 056132230262937 | 279.5667 | 1938 | 42833.3 | 19470.27 | 4151.73 | 4750.46 | 2335.12 | 0 | 65.16 | 12060.56 | 51
KY | KY - WEST | 2621 | 23026294300 |  |  |  | 6720208E | 2300125 | U134275 |  | 557 | OP | INSTALL 40' OF 4" PMMP | 2600E | CHINOE | 640 CHINOE RD | 067 | LEX | 2023-09-13 |  | U134275 | 2023-09-13 | 2024-12-27 | 2024-12-31 | [5 empty] | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP2943 | AMRCB |  | 100 | 055732230262943 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 23026294700 |  | 501354264 |  | 7356252L | 2300205 | U122858 |  | 555 | EX | INSTALL 70'-2" PMIP | 2600B | STATE RT 168 | 7914 STATE RT 168 | 019 | CAT | 2024-01-15 | U128132 | U122858 | 2023-09-18 | 2023-12-28 | 2024-01-02 | 2024-01-03 | MCOLLET | 2024-01-05 | 2024-01-02 |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP2947 |  |  | 100 | 055532230262947 | 45.6167 | 740 | 10891.64 | 2958.7 | 0 | 2164.13 | 2843.32 | 0 | 25.81 | 2899.68 | 74
KY | KY - WEST | 2621 | 23026296000 |  | 501354452 |  | 6712212O | 2300248 | U134275 |  | 555 | EX | INSTALL 220' OF 2" PMMP | 2600B | ALEXANDRIA | 1801 ALEXANDRIA DR OUTLOT | 067 | LEX | 2024-01-12 | U124014 | U134275 | 2023-09-20 | 2024-01-26 | 2024-02-01 | 2024-01-11 | DDAVIS | 2024-01-11 | 2024-01-08 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2960 |  |  | 100 | 055532230262960 | 62 | 1680 | 50555.75 | 3929.9 | 2444.33 | 2485.79 | 28097.09 | 0 | 214.71 | 13383.93 | 210
KY | KY - WEST | 2621 | 23026296200 |  |  |  | 6716204F | 1963805 | U122858 |  | 561 | IP | INSTALL 1429'-6" PMMP | 2600B | WILSON DOWNING | WILSON DOWNING RD | 067 | LEX | 2024-01-23 |  | U122858 | 2023-09-22 | 2024-01-15 | 2024-05-31 |  |  |  | 2024-01-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP2962 | AMRCB |  | 100 | 056132230262962 | 508.55 | 0 | 786454.78 | 29714.56 | 35649.09 | 27758.22 | 478483.2 | 0 | 6771.83 | 208077.88
KY | KY - WEST | 2623 | 23026296400 |  |  |  | 6688228A | 2300379 | U461383 |  | 557 | EX | INSTALL 110' OF 2"PMMP MAIN | 2600B | SCHENKEL | 565 SCHENKEL | 073 | FRA | 2024-01-08 | U128132 | U461383 | 2023-09-25 | 2023-12-18 | 2024-01-10 | 2023-12-14 | JOSH PASLEY/STANLEY PIPELINE | 2023-12-21 | 2023-11-14 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP2964 |  |  | 100 | 055732230262964 | 115.8667 | 2460 | 58459.83 | 10068.37 | 2058.17 | 7635.7 | 23102.6 | 0 | 176.82 | 15418.17 | 164
KY | KY - WEST | 2623 | 23026298800 |  | 501171335 |  | 6712236C | 2300590 | U132703 |  | 555 | CO | INSTALL 900'-2" PMMP MAIN | 2600B | YUSEN | 335 E YUSEN DR REAR | 209 | GEO | 2024-04-03 |  | U132703 | 2023-10-04 | 2024-04-04 | 2024-04-17 | 2024-04-08 | DUSTIN DAVIS | 2024-04-03 | 2024-03-18 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP2988 |  |  | 100 | 055532230262988 | 98.0167 | 12166 | 96688.1 | 6278.96 | 1838.57 | 4098.07 | 56328.19 | 0 | 251.02 | 27893.29 | 869
KY | KY - WEST | 2621 | 23026299500 |  | 500630073 |  | 6716220N | 2300672 | U461383 |  | 555 | OP | INSTALL 7000' OF 4"PMMP MAIN | 2600E | GEORGETOWN | 2850 GEORGETOWN RD | 067 | LEX | 2023-10-09 |  | U461383 | 2023-10-06 | 2024-10-31 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2995 |  |  | 100 | 055532230262995 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026299700 |  | 501354375 |  | 6716212N | 2300730 | U461383 |  | 555 | EX | INSTALL 325' OF 2"PMMP MAIN | 2600B | LEGION | 340 LEGION DR | 067 | LEX | 2024-03-25 | U124014 | U461383 | 2023-10-10 | 2024-04-22 | 2024-04-26 | 2024-03-14 | DDAVIS | 2024-03-14 | 2024-03-06 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP2997 |  |  | 100 | 055532230262997 | 50 | 2556 | 51851.3 | 3252.86 | 1470.61 | 1429.99 | 29936.33 | 0 | 113.27 | 15648.24 | 426
KY | KY - EAST | 2631 | 23026300300 |  | 501168502 |  | 7356216C | 2300812 | U122858 |  | 555 | PE | INSTALL 1810'-2" PMMP | 2600E | TOWN HILL | 200 TOWN HILL RD | 127 | LOU | 2024-04-22 |  | U122858 | 2023-10-13 | 2024-09-04 | 2024-10-01 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3003 |  |  | 100 | 055532230263003 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026300401 |  |  |  | 6744208J | 2302060 | U128885 |  | 561 | CO | INSTALL 1150' 4/2" PMMP | 2600B | MARKET | MARKET ST | 049 | WIN | 2024-05-16 |  | U128885 | 2024-05-08 | 2024-02-22 | 2024-04-26 | 2024-04-12 | RANDALL HUMPHREYS | 2024-05-16 | 2024-02-26 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3004 |  |  | 100 | 056132230263004 | 276.75 | 40824 | 183369.14 | 17228.56 | 6439.12 | 20446.64 | 83625.27 | 0 | 1169.42 | 54460.13 | 1134
KY | KY - CENTRAL | 2629 | 23026300600 |  |  |  | 6744208J | 2300593 | U128885 |  | 561 | EX | INSTALL 180'-4" PMLP | 2600B | KITTISON | KITTISON DR | 049 | WIN | 2024-02-01 | U124014 | U128885 | 2023-10-16 | 2023-12-18 | 2024-01-26 | 2024-01-05 | DEREK PAYTON | 2024-01-12 | 2023-12-11 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3006 |  |  | 100 | 056132230263006 | 143.45 | 3933 | 77136.39 | 10321.25 | 4342.53 | -4527.06 | 44634.92 | 0 | 401.76 | 21962.99 | 207
KY | KY - WEST | 2623 | 23026301200 |  |  |  | 6712232L | 2300854 | U461383 |  | 561 | OP | INSTALL 60' OF 6"PMMP MAIN | 2600E | CONNECTOR | CONNECTOR RD | 209 | GEO | 2023-10-26 |  | U461383 | 2023-10-18 | 2024-12-23 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00561 | 3200561 |  |  | WP3012 |  |  | 100 | 056132230263012 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026301800 |  | 501356071 |  | 6748208N | 2300964 | U128885 |  | 555 | PL | INSTALL 1,200'-2" PMMP | 2600E | IRVINE | 1305 IRVINE RD LT1 | 049 | WIN | 2023-10-20 |  | U128885 | 2023-10-20 | 2024-10-21 | 2024-10-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3018 |  |  | 100 | 055532230263018 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026302700 |  | 501340576 |  | 6716216C | 2301170 | U461383 |  | 555 | IP | INSTALL 2720' OF 2"/4"PMMP | 2600B | STOCKTON | 1952 STOCKTON WY | 067 | LEX | 2024-01-02 |  | U461383 | 2023-10-24 | 2024-05-22 | 2024-07-01 |  |  |  | 2024-01-02 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3027 |  |  | 100 | 055532230263027 | 177.1833 | 0 | 83640.85 | 4280.56 | 16006.44 | 297.22 | 39293.56 | 0 | 468.47 | 23294.6
KY | KY - CENTRAL | 2629 | 23026303400 |  |  |  | 6736180D | 2182441 | U128885 |  | 559 | IP | INSTALL 20'-2" CSHP | 2600B | MILLER | MILLER DR | 151 | RIC | 2024-01-29 |  | U128885 | 2023-10-27 | 2024-12-02 | 2024-12-15 |  |  |  | 2023-12-13 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3034 |  |  | 100 | 055932230263034 | 461.5833 | 0 | 176514.11 | 32821.18 | 20431.59 | 5205.5 | 68728.28 | 0 | 3151.16 | 46176.4
KY | KY - WEST | 2621 | 23026303700 |  |  |  | 6720204C | 2301286 | U134275 |  | 557 | EX | EMER - INSTALL 5' OF 2" PMMP | 2621P | LATONIA | 1291 LATONIA PK | 067 | LEX | 2023-11-13 | U128132 | U134275 | 2023-10-30 | 2023-11-03 | 2024-06-30 | 2023-10-27 | JOSHUA COX | 2023-11-03 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3037 |  |  | 100 | 055732230263037 | 2.2667 | 6 | 579.53 | 168.86 | 376.04 | 9.41 | 0 | 0 | 0 | 25.22 | 3
KY | KY - WEST | 2621 | 23026303900 |  |  |  | 6720204J | 2301300 | U122858 |  | 557 | PE | EMER-INSTALL 3'-2" PMMP MAIN | 2621P | OXHILL | OXHILL DR | 067 | LEX | 2023-10-30 |  | U122858 | 2023-10-30 | 2024-06-28 | 2024-06-30 | [5 empty] | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3039 |  |  | 100 | 055732230263039 |  | 0 | 2293.42 | 1197.48 | 278.16 | 75.45 | 0 | 0 | 67.02 | 675.31
KY | KY - CENTRAL | 2629 | 23026304300 |  | 501356514 |  | 6736248E | 2301356 | U128885 |  | 555 | OP | INSTALL 700'-2" CSHP | 2600E | NEW LAIR | NEW LAIR RD | 097 | CYN | 2023-11-06 |  | U128885 | 2023-11-06 | 2024-12-16 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3043 |  |  | 100 | 055532230263043 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026304700 |  | 501357009 |  | 6736248A | 2301476 | U128885 |  | 555 | OP | INSTALL 1,300'-2" PMMP | 2600E | EDUCATION | 1000 EDUCATION DR | 097 | CYN | 2023-11-16 |  | U128885 | 2023-11-07 | 2024-10-16 | 2024-11-01 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3047 |  |  | 100 | 055532230263047 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 23026304800 |  | 501357014 |  | 7240216O | 2301540 | U128885 |  | 555 | PL | INSTALL 1700'-2" PMMP | 2600E | STREET A | STREET A LT1 | 173 | MT | 2023-11-08 |  | U128885 | 2023-11-08 | 2024-10-07 | 2024-10-26 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3048 |  |  | 100 | 055532230263048 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026304900 |  |  |  | 6720216E | 2399054 | U134275 |  | 561 | OP | NEWTOWN PIKE RELOCATIONS | 2600E | NEWTOWN | 1450 NEWTOWN PK | 067 | LEX | 2024-05-14 |  | U134275 | 2023-11-10 | 2024-05-30 | 2024-06-30 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3049 |  |  | 100 | 056132230263049 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 23026306300 |  | 500518173 |  | 6728204I | 2301991 | U461383 |  | 555 | OP | INSTALL 13,500' OF 4"/6"PMMP | 2600E | ATHENS BOONESB | 5380 ATHENS BOONESB RD | 067 | LEX | 2024-02-26 |  | U461383 | 2023-11-29 | 2024-04-29 | 2024-09-01 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3063 |  |  | 100 | 055532230263063 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 23026307300 |  | 501356996 |  | 7364188G | 2301676 | U122858 |  | 555 | EX | INSTALL ~100'-2" PMIP | 2600B | BLACKLOG | 1825 BLACKLOG RD B | 159 | INE | 2024-02-22 | U128132 | U122858 | 2023-12-05 | 2024-01-02 | 2024-01-31 | 2024-01-11 | ORA SLONE | 2024-02-01 | 2024-01-02 |  | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00555 | 3200555 |  |  | WP3073 |  |  | 100 | 055532230263073 | 133.65 | 2831 | 40875.68 | 8372.79 | 932.79 | 1204.1 | 19338.31 | 0 | 76.59 | 10951.1 | 149
KY | KY - WEST | 2623 | 23026307400 |  |  |  | 6700224L | 2302214 | U461383 |  | 557 | EX | EMER-INSTALL 3' OF 2"PMMP | 2621P | OLD TOWNE | 122 OLD TOWNE | 239 | MID | 2024-01-09 | U128132 | U461383 | 2023-12-07 | 2024-03-01 | 2024-03-01 | 2023-12-05 | CDESPAIN | 2023-12-05 |  |  | A | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3074 |  |  | 100 | 055732230263074 |  | 3 | 1356.05 | 758.48 | 194.32 | 41.52 | 0 | 0 | 2.59 | 359.14 | 3
KY | KY - WEST | 2621 | 23026307900 |  |  |  | 6708204G | 2302264 | U461383 |  | 557 | EX | EMER-INSTALL 10'-4"PMMP/VALVE | 2621P | FOREST | 103 FOREST TL | 113 | NIC | 2024-01-16 | U136251 | U461383 | 2023-12-11 | 2024-08-29 | 2024-08-31 | 2023-12-05 | KKINDER | 2023-12-18 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3079 |  |  | 100 | 055732230263079 | 0.95 | 10 | 8046.73 | 5072.51 | 549.68 | 278.33 | 0 | 0 | 19.07 | 2127.14 | 10
KY | KY - WEST | 2623 | 23026308600 |  | 500675130 |  | 6688224K | 2302127 | U126783 |  | 555 | IP | INSTALL 675'-2" PMMP | 2600B | DUNCAN | 690 DUNCAN RD | 073 | FRA | 2024-05-14 |  | U126783 | 2023-12-18 | 2024-04-24 | 2024-05-30 |  |  |  | 2024-04-30 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3086 |  |  | 100 | 055532230263086 | 86.8333 | 0 | 19418.39 | 485.91 | 2765.04 | 30.44 | 9713.02 | 0 | 69.72 | 6354.26
KY | KY - WEST | 2621 | 23026308900 |  |  |  | 6712212G | 2302491 | U134275 |  | 557 | EX | EMER INSTALL 4' OF 3" PMMP | 2621P | KELSEY | 1158 KELSEY DR | 067 | LEX | 2024-01-09 | U136251 | U134275 | 2023-12-20 | 2024-04-29 | 2024-04-30 | 2023-12-22 | MCRAIG | 2023-12-22 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3089 |  |  | 100 | 055732230263089 | 0.2 | 4 | 2961.2 | 1593.52 | 38.81 | 539.08 | 0 | 0 | 6.89 | 782.9 | 4
KY | KY - WEST | 2623 | 24026309500 |  | 501351972 |  | 6716236I | 2302554 | U126783 |  | 555 | EX | INSTALL 215'-2" PMMP | 2600B | MEADOW LARK | 115 MEADOW LARK TR | 209 | GEO | 2024-05-23 | U132645 | U126783 | 2024-01-02 | 2024-05-22 | 2024-05-27 | 2024-05-22 | RANDALL HUMPHREYS | 2024-05-22 | 2024-05-17 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3095 |  |  | 100 | 055532240263095 | 32 | 952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 238
KY | KY - CENTRAL | 2629 | 24026309800 |  | 501358960 |  | 6748208I | 2302466 | U134275 |  | 555 | EX | INSTALL 75' - 2" PMMP | 2600B | SYCAMORE | 17 SYCAMORE ST | 049 | WIN | 2024-02-26 | U128132 | U134275 | 2024-01-03 | 2024-02-13 | 2024-02-15 | 2024-01-26 | JOSH PASLEY/STANLEY PIPELINE | 2024-01-29 | 2024-01-24 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3098 |  |  | 100 | 055532240263098 | 16.1667 | 294 | 19454.59 | 1024.21 | 294.94 | 8377.89 | 6362.18 | 0 | 32.75 | 3362.62 | 98
KY | KY - WEST | 2621 | 24026310400 |  |  |  | 6724208I | 2402788 | U134275 |  | 559 | PE | INSTALL VALVE & 5' OF 2" PMMP | 2621P | RICHMOND | 3101 RICHMOND RD | 067 | LEX | 2024-01-29 |  | U134275 | 2024-01-09 | 2024-12-30 | 2024-12-31 | [5 empty] | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3104 |  |  | 100 | 055932240263104 |  | 0 | 10490.93 | 3087.93 | 519.78 | 161.33 | 3782.14 | 0 | 123.15 | 2816.6
KY | KY - CENTRAL | 2629 | 24026310800 |  | 501356021 |  | 7236212L | 2302559 | U134275 |  | 555 | PE | INSTALL 1400' OF 2" PMMP | 2600B | FOGG | 1929 FOGG PK | 173 | MT | 2024-01-12 |  | U134275 | 2024-01-09 | 2024-08-29 | 2024-09-10 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3108 |  |  | 100 | 055532240263108 |  | 0 | 6264.46 | 0 | 0 | 1294.24 | 3577.49 | 0 | 58.33 | 1334.4
KY | KY - WEST | 2621 | 24026311200 |  | 500518173 |  | 6728204I | 2301991 | U461383 |  | 555 | OP | INSTALL 7500' OF 4"PMMP MAIN | 2600E | ATHENS BOONESB | 5380 ATHENS BOONESB RD | 067 | LEX | 2024-02-26 |  | U461383 | 2024-01-11 | 2024-06-28 | 2024-09-01 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3112 |  |  | 100 | 055532240263112 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026311700 |  | 501314322 |  | 6724208P | 2402885 | U461383 |  | 555 | EX | INSTALL 360' OF 2"PMMP MAIN | 2600B | CHILESBURG | 295 CHILESBURG RD FG 49 | 067 | LEX | 2024-03-05 | CRUCKER | U461383 | 2024-01-15 | 2024-04-09 | 2024-04-12 | 2024-03-04 | DDAVIS | 2024-03-04 | 2024-02-22 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3117 |  |  | 100 | 055532240263117 | 52.5 | 2905 | 38269.21 | 3728.82 | 1607.33 | 1817.4 | 20089.63 | 0 | 190.61 | 10835.42 | 415
KY | KY - WEST | 2621 | 24026311800 |  |  |  | 6716204D | 2402917 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 2"PMMP MAIN | 2621P | KIRKLEVINGTON | 3051 KIRKLEVINGTON | 067 | LEX | 2024-04-30 | U136251 | U461383 | 2024-01-15 | 2024-09-30 | 2024-09-30 | 2024-01-13 | LSTANFI | 2024-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3118 |  |  | 100 | 055732240263118 | 0.46667 | 4 | 2901.06 | 1716.5 | 285.21 | 119.46 | 0 | 0 | 6.38 | 773.51 | 4
KY | KY - WEST | 2623 | 24026312200 |  | 501352315 |  | 6700212N | 2399932 | U126783 |  | 555 | IP | INSTALL 230'-2" PMMP | 2600B | NORMANDY | 200 NORMANDY RD | 239 | VER | 2024-05-28 |  | U126783 | 2024-01-17 | 2024-06-12 | 2024-06-14 |  |  |  | 2024-05-28 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3122 |  |  | 100 | 055532240263122 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2632 | 24026313200 |  |  |  | 7252276K | 2403126 | U134275 |  | 561 | OP | OAKPOINTE 300' ENCROACH RELO | 2600E | OAKPOINTE | 775 OAKPOINTE DR | 161 | MAY | 2024-01-24 |  | U134275 | 2024-01-24 | 2024-12-23 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326320 | 0326320 | 00032 | 00561 | 3200561 |  |  | WP3132 |  |  | 100 | 056132240263132 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026314000 |  |  |  | 6712204H | 2403330 | U461383 |  | 557 | EX | EMER-INSTALL 5' OF 4"PMMP MAIN | 2621P | WINTHROP | 3451 WINTHROP DR | 067 | LEX | 2024-03-14 | U136251 | U461383 | 2024-01-30 | 2024-09-30 | 2024-09-30 | 2024-01-26 | KKINDER | 2024-02-20 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3140 |  |  | 100 | 055732240263140 | 1.6167 | 5 | 519.5 | 127.36 | 244.49 | 6.52 | 0 | 0 | 0 | 141.13 | 5
KY | KY - CENTRAL | 2629 | 24026314400 |  | 501359277 |  | 6736180C | 2402680 |  |  | 555 | OP | INSTALL 1,200'-4" PMMP | 2600E | ROBERT MARTIN | 1414 ROBERT MARTIN | 151 | RIC | 2024-01-31 |  | U128885 | 2024-01-31 | 2024-12-06 | 2024-12-06 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3144 |  |  | 100 | 055532240263144 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026314600 |  |  |  | 6720212M | 2403381 | U461383 |  | 557 | EX | EMER-INSTALL 170' OF 2"/4"PMMP | 2600B | HANOVER | 100 S HANOVER AV | 067 | LEX | 2024-02-13 | U124014 | U461383 | 2024-02-01 | 2024-02-05 | 2024-02-17 | 2024-02-01 | DDAVIS | 2024-02-05 |  |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3146 | AMRCB |  | 100 | 055732240263146 | 55.0667 | 805 | 114843.2 | 18671.74 | 7392.64 | 5095 | 51420.45 | 0 | 211.97 | 32051.4 | 161
KY | KY - CENTRAL | 2629 | 24026316000 |  |  |  | 6764176P | 2403473 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMLP | 2621P | PLUM | 145 PLUM ST | 065 | IRV | 2024-02-28 | U128132 | U128885 | 2024-02-06 | 2024-01-16 | 2024-01-29 | 2024-01-30 | WDENNING | 2024-02-13 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3160 |  |  | 100 | 055732240263160 |  | 2 | 6839.09 | 3653.22 | 571.71 | 756.08 | 0 | 0 | 0 | 1858.08 | 2
KY | KY - WEST | 2621 | 24026316700 |  |  |  | 6720208G | 2403558 | U461383 |  | 557 | PE | INSTALL 4000' OF 2"PMMP MAIN | 2600B | SAINT PHILLIP | SAINT PHILLIP DR | 067 | LEX | 2024-02-27 |  | U461383 | 2024-02-08 | 2024-09-12 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3167 | AMRCB |  | 100 | 055732240263167 |  | 0 | 16567.07 | 1109.58 | 7447.71 | 843.07 | 2136 | 0 | 107 | 4923.71
KY | KY - EAST | 2631 | 24026317100 |  | 100264295 |  | 7356256A | 2403117 | U122858 |  | 555 | VO | INSTALL ~125'-2" PMMP | 2600E | 12TH | 615 12TH ST | 019 | ASH | 2024-02-12 |  | U122858 | 2024-02-09 | 2024-03-27 | 2024-04-01 | [5 empty] | D | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026317300 |  | 501361117 |  | 6696212P | 2403518 | U126783 |  | 555 | CO | INSTALL 270'-2" PMMP | 2600B | SUGARTREE | 224 SUGARTREE LN | 239 | VER | 2024-04-09 |  | U126783 | 2024-02-12 | 2024-04-26 | 2024-04-30 | 2024-04-05 | JOSHUA COX | 2024-04-08 | 2024-04-01 |  | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3173 |  |  | 100 | 055532240263173 | 54.8667 | 1566 | 26893.27 | 3431.77 | 1499.36 | 1268.28 | 13292.14 | 0 | 63.85 | 7337.87 | 174
KY | KY - WEST | 2621 | 24026318600 |  |  |  | 6716208J | 2403677 | U134275 |  | 557 | EX | EMER - INSTALL 11' OF 2" PMMP | 2621P | LOWRY | 150 W LOWRY LN | 067 | LEX | 2024-03-08 | U136251 | U134275 | 2024-02-13 | 2024-03-26 | 2024-03-31 | 2024-02-08 | MCRAIG | 2024-02-21 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3186 |  |  | 100 | 055732240263186 | 0.36667 | 11 | 39209.34 | 5614.64 | 47.94 | 10266.37 | 14477.94 | 0 | 20.58 | 8781.87 | 11
KY | KY - EAST | 2631 | 24026320800 |  |  |  | 7352256C | 2403719 | U122858 |  | 557 | EX | EMER - INSTALL 5'-3" PMIP | 2621P | KENTUCKY | 235 KENTUCKY ST | 019 | ASH | 2024-02-26 | U128132 | U122858 | 2024-02-14 | 2024-03-28 | 2024-03-30 | 2024-02-13 | MCOLLET | 2024-02-22 |  |  | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00557 | 3200557 |  |  | WP3208 |  |  | 100 | 055732240263208 | 0.95 | 4 | 25091.82 | 4573.73 | 0 | 5456.79 | 7968.92 | 0 | 32.72 | 7059.66 | 4
KY | KY - WEST | 2621 | 24026321100 |  | 501361324 |  | 6716216E | 2403608 | U141016 |  | 555 | IP | INSTALL 1400' OF 2" PMMP MAIN | 2600B | DAHLIA | 661 DAHLIA DR LT88 | 067 | LEX | 2024-04-29 |  | U141016 | 2024-02-14 | 2024-05-17 | 2024-06-01 |  |  |  | 2024-04-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3211 |  |  | 100 | 055532240263211 | 87 | 0 | 18552.37 | 886.55 | 3040.49 | 9072.67 | 2652 | 0 | 24.05 | 2876.61
KY | KY - EAST | 2631 | 24026324100 |  | 100253182 |  | 7352256G | 2403829 | U122858 |  | 555 | PE | INSTALL 670'-2' PMIP | 2600E | OLYMPIC | 137 OLYMPIC DR | 019 | ASH | 2024-04-30 |  | U122858 | 2024-02-19 | 2024-05-15 | 2024-06-01 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3241 |  |  | 100 | 055532240263241 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026328300 |  |  |  | 6716208H | 2403957 | U122858 |  | 557 | EX | EMER - INSTALL 26'-6" PMLP | 2621P | MONTCLAIR | MONTCLAIR DR | 067 | LEX | 2024-03-29 | U136251 | U141016 | 2024-02-26 | 2024-03-07 | 2024-03-10 | 2024-02-26 | KKINDER | 2024-02-28 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3283 | AMRCB |  | 100 | 055732240263283 | 3.05 | 26 | 14158.4 | 6673.29 | 2922.53 | 547.97 | 0 | 0 | 23.55 | 3991.06 | 26
KY | KY - WEST | 2621 | 24026328800 |  |  |  | 6720216A | 2399054 | U134275 |  | 561 | OP | NEWTOWN PIKE MP RELOCATION | 2600E | COLEMAN | COLEMAN CT | 067 | LEX | 2024-02-26 |  | U134275 | 2024-02-26 | 2024-05-31 | 2024-06-01 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3288 |  |  | 100 | 056132240263288 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026329000 |  |  |  | 6720216E | 2399054 | U134275 |  | 561 | OP | INSTALL 580' OF 4" CSHP | 2600E | NEWTOWN | 1450 NEWTOWN PK | 067 | LEX | 2024-05-21 |  | U134275 | 2024-02-26 | 2024-04-05 | 2024-06-01 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3290 |  |  | 100 | 056132240263290 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026329400 |  |  |  | 6744208J | 2403993 | U128885 |  | 557 | EX | EMER - INSTALL 2'-3" PMLP | 2621P | ORAGE | ORAGE | 049 | WIN | 2024-03-07 | U128132 | U128885 | 2024-02-27 | 2024-12-18 | 2024-12-31 | 2024-02-21 | NRICHIE | 2024-03-01 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3294 |  |  | 100 | 055732240263294 |  | 2 | 6381.38 | 1473.73 | 833.51 | 1037.83 | 1250.71 | 0 | 12.27 | 1773.33 | 2
KY | KY - CENTRAL | 2629 | 24026329700 |  |  |  | 6740208H | 2404044 | U128885 |  | 557 | EX | EMER - 2'-2" PMMP | 2621P | SHALA-MAR RUE | SHALA-MAR RUE | 049 | WIN | 2024-04-12 | U128132 | U128885 | 2024-02-28 | 2024-12-17 | 2024-12-31 | 2024-02-21 | NRICHIE | 2024-03-14 |  |  | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3297 |  |  | 100 | 055732240263297 |  | 2 | 8567.08 | 2360.78 | 842.37 | 286.18 | 2462.37 | 0 | 0 | 2615.38 | 2
KY | KY - WEST | 2623 | 24026331100 |  |  |  | 6708228G | 2404137 | U126783 |  | 557 | PE | EMER - INSTALL ~5'-2" PMMP | 2600B | WINDING CREEK | WINDING CREEK | 209 | GEO | 2024-03-07 |  | U126783 | 2024-03-04 | 2024-12-27 | 2024-12-29 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3311 |  |  | 100 | 055732240263311 |  | 0 | 530.28 | 312.43 | 0 | 29.94 | 0 | 0 | 7.7 | 180.21
KY | KY - WEST | 2621 | 24026331500 |  | 501362650 |  | 6716208J | 2404261 | U461383 |  | 555 | CO | INSTALL 300' OF 2"PMMP MAIN | 2600B | NORMAN | 2350 NORMAN LN | 067 | LEX | 2024-04-25 |  | U461383 | 2024-03-06 | 2024-10-25 | 2024-10-31 | 2024-04-24 | JOSHUA COX | 2024-04-24 | 2024-04-17 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3315 |  |  | 100 | 055532240263315 | 56.75 | 2646 | 29277.87 | 3549.93 | 1522.37 | 222.3 | 15613.4 | 0 | 69.39 | 8300.48 | 378
KY | KY - WEST | 2621 | 24026331900 |  |  |  | 6716204D | 2404366 | U461383 |  | 557 | EX | EMER - INSTALL 1' OF 2"PMMP | 2621P | KIRKLEVINGTON | 3051 KIRKLEVINGTON DR | 067 | LEX | 2024-04-12 | U136251 | U461383 | 2024-03-08 | 2024-05-01 | 2024-05-01 | 2024-03-08 | RJCRAWF | 2024-04-02 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3319 |  |  | 100 | 055732240263319 | 0.9 | 1 | 3470.33 | 2054.55 | 143.37 | 201.89 | 0 | 0 | 8.02 | 1062.5 | 1
KY | KY - WEST | 2621 | 24026332300 |  | 500518372 |  | 6712204H | 2404114 | U461383 |  | 555 | VO | INSTALL 170' OF 2"PMMP MAIN | 2600E | RETRAC | 479 RETRAC RD | 067 | LEX | 2024-03-28 |  | U461383 | 2024-03-11 | 2024-04-29 | 2024-12-25 | [5 empty] | B | [11 empty] | 24026337000 | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026332500 |  | 501362651 |  | 6712236B | 2404299 |  |  | 555 | OP | INSTALL 1100'-4" CSHP | 2600B | YUSEN | 245 W YUSEN DR CNG | 209 | GEO | 2024-03-12 |  | U126783 | 2024-03-12 | 2024-12-31 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3325 |  |  | 100 | 055532240263325 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2633 | 24026333600 |  | 501028114 |  | 7356152E | 2404396 | U122858 |  | 555 | OP | INSTALL 75'-2" PMIP | 2600B | CHERRY | 111 CHERRY ST | 071 | HAR | 2024-03-18 |  | U122858 | 2024-03-14 | 2024-06-07 | 2024-06-20 | [5 empty] | B | 00032 | 10700001 | 0326330 | 0326330 | 00032 | 00555 | 3200555 |  |  | WP3336 |  |  | 100 | 055532240263336 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026336800 |  |  |  | 6724204D | 2404682 | U134275 |  | 557 | PE | EMER - INSTALL 5' OF 2" PMMP | 2621P | HORSEMINT | 3709 HORSEMINT TR | 067 | LEX | 2024-03-27 |  | U134275 | 2024-03-22 | 2024-04-01 | 2024-05-31 | [5 empty] | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3368 |  |  | 100 | 055732240263368 |  | 0 | 5122.36 | 3018.04 | 0 | 504.2 | 0 | 0 | 36.25 | 1563.87
KY | KY - WEST | 2621 | 24026337000 |  | 500518347 |  | 6712204H | 2404724 | U461383 |  | 555 | CO | INSTALL 675' OF 2"PMMP MAIN | 2600B | RETRAC | 470 RETRAC RD | 067 | LEX | 2024-05-21 |  | U461383 | 2024-03-26 | 2024-04-17 | 2024-06-30 | 2024-05-15 | JOSHUA COX | 2024-05-21 | 2024-05-07 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3370 |  |  | 100 | 055532240263370 | 69.5167 | 5976 | 2966.78 | 0 | 2118.65 | 0 | 0 | 0 | 7.03 | 841.1 | 664
KY | KY - WEST | 2623 | 24026337100 |  | 501363944 |  | 6696212N | 2404754 |  |  | 555 | OP | INSTALL 700'-4" PMMP | 2600B | TYRONE | 1031 TYRONE PK | 239 | VER | 2024-03-27 |  | U126783 | 2024-03-27 | 2024-10-17 | 2024-10-19 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3371 |  |  | 100 | 055532240263371 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026337200 |  | 501359324 |  | 7356252L | 2404538 | U122858 |  | 555 | VO | INSTALL 270'-2" PMIP | 2600E | STATE RT 168 | 8421 STATE RT 168 | 019 | CAT | 2024-05-01 |  | U122858 | 2024-04-01 | 2024-05-14 | 2024-05-20 | [5 empty] | B | 00032 | 88000000 | 0326310 | 0326310 | 00032 | 05007 | [6 empty] | 100 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026337600 |  |  |  | 6744208N | 2404846 | U128885 |  | 561 | CO | INSTALL 30'-2" PMMP | 2600B | BARLOW | 539 BARLOW DR | 049 | WIN | 2024-05-23 |  | U128885 | 2024-04-01 | 2024-05-24 | 2024-05-31 |  | DEREK PAYTON | 2024-05-23 | 2024-05-14 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00561 | 3200561 |  |  | WP3376 |  |  | 100 | 056132240263376 | 64.5 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
KY | KY - EAST | 2631 | 24026337800 |  |  |  | 7360252I | 1968534 | U128885 |  | 559 | CO | INSTALL 8" SS | 2600B | PANOLA | PANOLA ST | 019 | CAT | 2024-04-08 |  | U128885 | 2024-04-01 | 2024-04-30 | 2024-04-30 | 2024-02-22 | ORA SLONE | 2024-04-08 |  |  | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP3378 | AMRCB |  | 100 | 055932240263378 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026337900 |  | 501339588 |  | 6748204C | 2293331 | U128885 |  | 555 | CO | INSTALL 2,550'-2" PMMP | 2600B | DUCLAIR | 105 DUCLAIR DR LT38 | 049 | WIN | 2024-05-09 |  | U128885 | 2024-04-02 | 2024-06-10 | 2024-06-30 | 2024-05-09 | DEREK PAYTON | 2024-05-09 | 2024-04-22 |  | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00555 | 3200555 |  |  | WP3379 |  |  | 100 | 055532240263379 | 115.5333 | 50032 | 28925.55 | 2166.5 | 5244.54 | 9568.54 | 6363.18 | 0 | 46.28 | 5536.51 | 3127
KY | KY - WEST | 2621 | 24026338000 |  |  |  | 6712212K | 2404974 | U122858 |  | 561 | IP | INSTALL 65'-2"&4" PMMP | 2600E | CROSS KEYS | 1295 CROSS KEYS RD | 067 | LEX | 2024-05-28 |  | U122858 | 2024-04-03 | 2024-05-07 | 2024-05-30 |  |  |  | 2024-05-20 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3380 |  |  | 100 | 056132240263380 | 49 | 0 | 19640.96 | 0 | 13750.98 | 385.2 | 0 | 0 | 45.64 | 5459.14
KY | KY - WEST | 2621 | 24026338500 |  | 501364358 |  | 6728208A | 2405110 | U461383 |  | 555 | CO | INSTALL 585' OF 2"PMMP MAIN | 2600B | CAVERSHAM PARK | CAVERSHAM PARK LN LT2 | 067 | LEX | 2024-05-03 |  | U461383 | 2024-04-10 | 2024-06-24 | 2024-06-28 | 2024-05-02 | JOSHUA COX | 2024-05-03 | 2024-04-29 |  | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3385 |  |  | 100 | 055532240263385 | 50.4167 | 3228 | 10254.17 | 625.44 | 2199.59 | 39.16 | 4458.55 | 0 | 24.3 | 2907.13 | 538
KY | KY - CENTRAL | 2629 | 24026338600 |  |  |  | 7240204B | 2288176 |  |  | 559 | OP | INSTALL HP FITTINGS | 2600B | LEVEE | 4672 LEVEE RD | 173 | MT | 2024-04-11 |  | U938437 | 2024-04-11 | 2024-12-30 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3386 |  |  | 100 | 055932240263386 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - CENTRAL | 2629 | 24026338800 |  |  |  | 7240204B | 2288176 |  |  | 559 | OP | INSTALL MP FITTINGS | 2600B | LEVEE | 4672 LEVEE RD | 173 | MT | 2024-04-11 |  | U938437 | 2024-04-11 | 2024-12-31 | 2024-12-31 | [5 empty] | B | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00559 | 3200559 |  |  | WP3388 |  |  | 100 | 055932240263388 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026339800 |  |  |  | 6712212P | 2405285 | U461383 |  | 557 | PE | INSTALL 35' OF 6"PMLP MAIN | 2621P | GETTYSBURG | 1800 GETTYSBURG RD | 067 | LEX | 2024-05-15 |  | U461383 | 2024-04-18 | 2024-09-27 | 2024-10-01 | [5 empty] | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3398 | AMRCB |  | 100 | 055732240263398 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2623 | 24026340300 |  | 501361694 |  | 6708228L | 2403695 | U461383 |  | 555 | OP | INSTALL 2280' OF 4"CSHP MAIN | 2600E | PAYNES DEPOT | 1530 PAYNES DEPOT RD | 209 | GEO | 2024-05-03 |  | U461383 | 2024-04-18 | 2024-07-19 | 2024-09-06 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3403 |  |  | 100 | 055532240263403 |  | 0 | 211.35 | 84.35 | 0 | 66.58 | 0 | 0 | 0.5 | 59.92
KY | KY - WEST | 2623 | 24026340800 |  |  |  | 6712232O | 2405445 | U126783 |  | 557 | PL | EMER - INSTALL 15'-2" PMMP | 2600B | HAMILTON | 523 N HAMILTON ST | 209 | GEO | 2024-04-24 |  | U126783 | 2024-04-24 | 2024-04-30 | 2024-05-04 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00557 | 3200557 |  |  | WP3408 |  |  | 100 | 055732240263408 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026341000 |  |  |  | 7348260P | 2405531 | U141016 |  | 559 | PE | INSTALL 300'OF 2" PMIP | 2600E | CRANCE | CRANCE CT | 019 | ASH | 2024-05-20 |  | U141016 | 2024-04-29 | 2024-09-23 | 2024-09-29 | [5 empty] | A | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00559 | 3200559 |  |  | WP3410 |  |  | 100 | 055932240263410 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026341300 |  | 501315275 |  | 7348244D | 2402689 | U122858 |  | 555 | OP | INSTALL 330'-2" PMMP | 2600E | FIELDS | 15227 FIELDS AV | 019 | CAT | 2024-05-07 |  | U122858 | 2024-05-01 | 2024-12-18 | 2024-12-30 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3413 |  |  | 100 | 055532240263413 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026341900 |  | 501365269 |  | 6728212M | 2405655 | U461383 |  | 555 | PE | INSTALL 4250' OF 2"/4"PMMP | 2600B | BLACKFORD | BLACKFORD PY LT1 | 067 | LEX | 2024-05-23 |  | U461383 | 2024-05-02 | 2024-06-26 | 2024-07-31 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00555 | 3200555 |  |  | WP3419 |  |  | 100 | 055532240263419 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - WEST | 2621 | 24026342000 |  |  |  | 6720208D | 2405691 | U132703 |  | 557 | CO | EMER - INSTALL 2' OF 2"PMMP | 2621P | CREATIVE | CREATIVE | 067 | LEX | 2024-05-14 |  | U132703 | 2024-05-03 | 2024-05-31 | 2024-05-31 |  | MCRAIG | 2024-05-14 |  |  | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00557 | 3200557 |  |  | WP3420 | AMRCB |  | 100 | 055732240263420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KY | KY - EAST | 2631 | 24026342200 |  | 501359309 |  | 7348260H | 2405758 | U122858 |  | 555 | OP | INSTALL 500'-2" PMIP | 2600E | BRYAL | 215 BRYAL DR | 089 | ASH | 2024-05-08 |  | U122858 | 2024-05-08 | 2024-07-26 | 2024-08-06 | [5 empty] | B | 00032 | 10700001 | 0326310 | 0326310 | 00032 | 00555 | 3200555 |  |  | WP3422 |  |  | 100 | 055532240263422 |  | 0
KY | KY - WEST | 2621 | 24026342400 |  |  |  | 6712208N | 2405849 | U122858 |  | 561 | OP | INSTALL ~585'-2" PMMP | 2600E | FOUNTAINBLUE | 3855 FOUNTAINBLUE LN | 067 | LEX | 2024-05-10 |  | U122858 | 2024-05-10 | 2024-06-17 | 2024-06-30 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3424 |  |  | 100 | 056132240263424 |  | 0
KY | KY - WEST | 2621 | 24026343300 |  |  |  | 6724208G | 2406051 | U461383 |  | 559 | PE | INSTALL 4" POLY VALVE | 2621P | PAVILION | 1916 PAVILION WY | 067 | LEX | 2024-05-20 |  | U461383 | 2024-05-20 | 2024-06-28 | 2024-07-01 | [5 empty] | A | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00559 | 3200559 |  |  | WP3433 |  |  | 100 | 055932240263433 |  | 0
KY | KY - WEST | 2621 | 24026343500 |  |  |  | 6720212I | 2406067 | U122858 |  | 561 | PE | INSTALL 25'-8" PMLP | 2600E | ELM TREE | ELM TREE LN | 067 | LEX | 2024-05-22 |  | U122858 | 2024-05-21 | 2024-06-21 | 2024-06-30 | [5 empty] | B | 00032 | 10700001 | 0326210 | 0326210 | 00032 | 00561 | 3200561 |  |  | WP3435 |  |  | 100 | 056132240263435 |  | 0
KY | KY - CENTRAL | 2629 | 24026343700 |  |  |  | 6744208K | 2406069 | U128885 |  | 557 | PE | EMER - INSTALL 3'-3" PMMP | 2621P | MEADOW | MEADOW | 049 | WIN | 2024-05-23 |  | U128885 | 2024-05-21 | 2024-05-10 | 2024-05-17 | [5 empty] | A | 00032 | 10700001 | 0326290 | 0326290 | 00032 | 00557 | 3200557 |  |  | WP3437 |  |  | 100 | 055732240263437 |  | 0
KY | KY - WEST | 2623 | 24026344600 |  | 501365851 |  | 6716236J | 2406147 | U126783 |  | 555 | PL | INSTALLING 145'-2" PMMP | 2600B | MEADOW LARK | 110 MEADOW LARK TR | 209 | GEO | 2024-05-28 |  | U126783 | 2024-05-28 | 2024-08-08 | 2024-08-12 | [5 empty] | B | 00032 | 10700001 | 0326230 | 0326230 | 00032 | 00555 | 3200555 |  |  | WP3446 |  |  | 100 | 055532240263446 |  | 0