## Process (hidden)
Request | Contact | Status | Exhibit | Notes | Legend (Tabs)
Project Detail | VP Finance | Requested |  |  | Links updated
True-up 2023 Actuals | VP Finance | Received |  |  | Questions
Customer Counts and Volumes | Chris Roach/Nathan Jones | Received |  | Exhibit J; Send schedule, should only need volumetric charge | Ready for Review
Leak Expense Savings | VP Finance | Received
Tax | Catherine Huang, Ellie Da Silva |  |  | Will provide monthly schedules; Set-up call and ask about True-up rates (as noted in True-up file)
PSC Assessment Fees | VP Finance | Received |  | Same as "Tax Repairs %" in PY files?
KY Rate Design | Thomas Troup, Sr Rates Analyst | No Changes | Exhibit I
Inputs
Beg FY | 2024 | 2024-10-01
End FY | 2025 | 2025-09-30
Beg True-Up Yr | 2022 | 2022-10-01
End True-up Year | 2023 | 2023-09-30
Questions
Mentions to Joe/Co in E-mail
Exhibit
Prior Year:
B-3 | 32 |  |  | Made corrections to the O&M savings. Previously had double counted cumulative effect due to a change in the support schedules.
I | Notes: Due to the rate design from the latest case we are allcoating 3% less of the increase to G-1 Res and 3% more to G-1 Non-Res.
K-1 | 0 |  |  | Actual Retirements are coming in substantially lower than forecasted for several years now. We may be understating Depreciation in the current filing if this trend continues.

## Exhibit A
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
SURCHARGE SUMMARY
Line Number | Tariff Schedule |  | Customer Charge | Volumetric Charge | Originally Filed
1 | RESIDENTIAL (Rate G-1) |  | 0 | 0.4522 | 0.4362 | 0.016
2 | NON-RESIDENTIAL (Rate G-1) |  | 0
3 |  | Sales: 1-300 |  | 0.3315 | 0.3198 | 0.0117
4 |  | Sales: 301-15000 |  | 0.2304 | 0.2223 | 0.0081
5 |  | Sales: Over 15000 |  | 0.2304 | 0.2223 | 0.0081
6 | INTERRUPTIBLE (Rate G-2) |  | 0
7 |  | Sales: 1-15,000 |  | 0.1336 | 0.1289 | 0.0047
8 |  | Sales: Over 15,000 |  | 0.1095 | 0.1057 | 0.0038
9 | TRANSPORTATION (T-3) |  | 0
10 |  | Interrupt Transport: 1-15,000 |  | 0.0851 | 0.0821 | 0.003
11 |  | Interrupt Transport: Over 15,000 |  | 0.0698 | 0.0673 | 0.0025
12 | TRANSPORTATION (T-4) |  | 0
13 |  | Firm Transport: 1-300 |  | 0.1293 | 0.1248 | 0.0045
14 |  | Firm Transport: 301-15,000 |  | 0.0899 | 0.0867 | 0.0032
15 |  | Firm Transport: Over 15,000 |  | 0.0742 | 0.0716 | 0.0026

## Exhibit B
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
DEFICIENCY
Line |  |  | As Filed | Variance
Number | Description | Total
1 | Project Additions | 73774364.0107 | 71092845.6562 | 2681518.3545
2 | Project Retirements | -11930569.3149 | -8544327.3649 | -3386241.95
3 | Net Change to Gross Plant | 61843794.6957 | 62548518.2912 | -704723.5955
4
5 | Cost of Removal to Accumulated Depr. | 3316849.2288 | 3620023.5633 | -303174.3345
6 | Retirements from Accumulated Depr. | 11930569.3149 | 8544327.3649 | 3386241.95
7 | Depreciation Accrual to Accumulated Depr. | -1350634.4848 | -1416325.4163 | 65690.9315
8 | Net Change to Accumulated Depreciation | 13896784.0589 | 10748025.5119 | 3148758.547
9
10 | Net Change to Net Plant | 75740578.7547 | 73296543.8032 | 2444034.9515
11
12 | Accumulated Deferred Income Taxes | -3471846.9805 | -4031846.256 | 559999.2755
13 | Net Change to Rate Base | 72268731.7742 | 69264697.5472 | 3004034.227
14
15 | Rate of Return | 6.936% | 6.936%
16 | Required Operating Income | 5012559.2359 | 4804199.4219
17
18 | Depreciation & Amortization Expense | 1081958.8615 | 1114804.3273 | -32845.4657
19 | O&M Savings | -12257.4159 | -12257.4159 | 0
20 | Ad Valorem Tax Increase | 602640.0135 | 609507.2286 | -6867.215
21 | Income Taxes on Cost of Service Items | -417249.1941 | -427157.5079 | 9908.3139
22 | Income Taxes on Adjusted Interest Expense | -321989.45 | -308605.1369 | -13384.313
23 | Operating Income at Present Rates | 933102.8151 | 976291.4951 | -43188.68
24
25 | Deficiency | 5945662.051 | 5780490.917 | 165171.134
26 | Tax Factor | 74.56% | 74.56%
27 | Total Rate Adjustment | 7974532.9785 | 7752999.591 | 221533.3875
28
29 | Project Cost True-up | 95117.0927 | 27119.7112 | 67997.3815
30 | Revenue Recovery True-up | 154327.4751 | 154327.4751 | 0
31 | Total True-up | 249444.5678 | 181447.1863 | 67997.3815
32
33 | Total Rate Adjustment | 8223977.5463 | 7934446.7773 | 289530.7691
34
35 | Prior Approved Rate Adjustment* | 4493517 | 4493517
36
37 | Increase in Rate Adjustment from Previous Year (Line 33 - Line 35) | 3730460.5463 | 3440929.7773 | 289530.7691
38
39 | Note: This is the 2024 PRP Rate Adjustment as approved in Case No. 2023-00231

## Exhibit B-1
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
NET RATE BASE FOR FISCAL YEAR 2025
Line |  | Cumulative balance as of
No. | Description | 2024-09-01 | 2024-10-01 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 13-Month Average
|  | (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) | (13) | (14)
Net Investment
1 | Plant in Service | 57377265.6192 | 59685119.7336 | 62385444.0454 | 65522693.8069 | 68441232.6312 | 70810673.0015 | 73428733.6844 | 76333180.2657 | 79256306.0262 | 82238564.6194 | 85198138.0463 | 88036687.9702 | 90352692.6889 | 73774364.0107
2 | Retirements | -10252100.3704 | -10517370.2516 | -10796089.5784 | -11092404.9373 | -11382463.9225 | -11638552.2439 | -11909283.596 | -12196153.5287 | -12486559.291 | -12778164.5221 | -13074327.2981 | -13359662.7416 | -13614268.8127 | -11930569.3149
3 | Investments Activity (Additions net of Retirements) | 47125165.2488 | 49167749.482 | 51589354.4671 | 54430288.8696 | 57058768.7086 | 59172120.7576 | 61519450.0884 | 64137026.737 | 66769746.7352 | 69460400.0973 | 72123810.7482 | 74677025.2286 | 76738423.8762 | 61843794.6957
4
5
6 | Accumulated Depreciation
7
8 | Depreciation Expense | -863200.1092 | -933882.9076 | -1006441.2532 | -1081374.7996 | -1158776.1119 | -1238451.6741 | -1320985.3054 | -1407200.3577 | -1497864.1977 | -1594192.2858 | -1698033.0947 | -1812687.2351 | -1945158.9708 | -1350634.4848
9 | Retirement | 10252100.3704 | 10517370.2516 | 10796089.5784 | 11092404.9373 | 11382463.9225 | 11638552.2439 | 11909283.596 | 12196153.5287 | 12486559.291 | 12778164.5221 | 13074327.2981 | 13359662.7416 | 13614268.8127 | 11930569.3149
10 | Cost of Removal | 2486490.2462 | 2602112.1658 | 2738759.0781 | 2898699.6102 | 3046870.2953 | 3166277.3762 | 3298739.7822 | 3446271.9852 | 3594680.2383 | 3746291.8775 | 3896458.6739 | 4040429.5888 | 4156959.0572 | 3316849.2288
11 | Accumulated Depreciation | 11875390.5074 | 12185599.5098 | 12528407.4032 | 12909729.7479 | 13270558.106 | 13566377.9459 | 13887038.0728 | 14235225.1562 | 14583375.3315 | 14930264.1137 | 15272752.8773 | 15587405.0952 | 15826068.8991 | 13896784.0589
12
13
14 | Accumulated Deferred Income Taxes
15
16 | ADIT | -3161860.005 | -3339647.1771 | -3542355.3066 | -3772850.2234 | -3991902.3139 | -4180546.8146 | -4385796.1023 | -4610497.1847 | -4839333.8308 | -5075840.066 | -5316045.0302 | -5557158.5591 | -5780472.6319 | -4427254.2497
17 | NOLC Variable | 606661.2137 | 657402.5563 | 709490.3054 | 763283.1494 | 818847.5383 | 876044.5521 | 935293.2993 | 997184.843 | 1062270.0556 | 1131421.4847 | 1205966.1005 | 1288273.3259 | 1383371.3394 | 956577.6741
18 | Net ADIT | -2555198.7913 | -2682244.6208 | -2832865.0012 | -3009567.074 | -3173054.7756 | -3304502.2625 | -3450502.803 | -3613312.3417 | -3777063.7752 | -3944418.5813 | -4110078.9297 | -4268885.2332 | -4397101.2925 | -3470676.5755
19
20 | Proration Impact on NOLC | [13 empty] | -1170.405
21
22 | Net Rate Base (Lines 3 + 11 + 18) | 56445356.9649 | 58671104.371 | 61284896.8691 | 64330451.5435 | 67156272.039 | 69433996.4411 | 71955985.3583 | 74758939.5515 | 77576058.2916 | 80446245.6297 | 83286484.6959 | 85995545.0906 | 88167391.4827 | 72268731.7742

## Exhibit B-2
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORCASTED ACTIVITY
AS OF OCTOBER 2022 THROUGH SEPTEMBER 2023
RECOVERY SCHEDULE
Line No. | Surcharge Report | Actual Recovery Year |  | Approved Recovery Amt | Actual Recovery Amt | Over / (Under) Recovered | Carrying Charges | Total Over / (Under) | Weighted Average Cost of Capital
1 | 2023 | 2022-10-01 | 2023-09-30 | 1587695.2151 | 1443377.61 | -144317.6051 | -10009.87 | -154327.4751 | 6.936%
2 |  |  |  | 1587695.2151 | 1443377.61 | -144317.6051 | -10009.87 | -154327.4751

## Exhibit B-3
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORCASTED ACTIVITY
AS OF OCTOBER 2022 THROUGH SEPTEMBER 2023
DEFICIENCY
Line
Number | Description | Actual | As Approved*
1 | Project Additions | 15671184.2754 | 15586559.1225
2 | Project Retirements | -1703102.3208 | -3039582.6785
3 | Net Change to Gross Plant | 13968081.9546 | 12546976.4439
4
5 | Cost of Removal to Accumulated Depr. | 563588.1592 | 790840.5694
6 | Retirements from Accumulated Depr. | 1703102.3208 | 3039582.6785
7 | Depreciation Accrual to Accumulated Depr. | -67843.1499 | -63620.8078
8 | Net Change to Accumulated Depreciation | 2198847.3301 | 3766802.4401
9
10 | Net Change to Net Plant | 16166929.2847 | 16313778.884
11
12 | Accumulated Deferred Income Taxes | -970786.5874 | -1939063
13 | Net Change to Rate Base | 15196142.6973 | 14374715.884
14
15 | Rate of Return | 6.936% | 6.936%
16 | Required Operating Income | 1054004.4575 | 997030.2937
17
18 | Depreciation & Amortization Expense | 224013.2071 | 216444.6703
19 | O&M Savings | -4473.6051 | -4473.6051
20 | Ad Valorem Tax Increase | 136112.6874 | 122264.6523
21 | Income Taxes on Cost of Service Items | -88735.2462 | -83391.8115
22 | Income Taxes on Adjusted Interest Expense | -66171.2022 | -64045.774
23 | Operating Income at Present Rates | 200745.841 | 186798.132
24
25 | Deficiency | 1254750.2985 | 1183828.4257
26 | Tax Factor | 74.56% | 74.56%
27 | Total Proposed Rate Adjustment | 1682812.3078 | 1587695.2151
28
29 | 2023 approved deficiency | 1587695.2151 | 1587695.2151
30
31 | Total 2023 Deficiency | 95117.0927 | 0
32
33 | Note: As Approved in Final Order in Case No. 2022-00222

## Exhibit C
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
ADDITIONS
Line
Number | Description | Mains | Services | Meters | Total
1 | Prior Year: 2023 | 22250566.67 | 8452979.6 | 0 | 30703546.27
2
3 | Prior Year: 2024 | 18083630 | 8259410.3911 | 330678.9581 | 26673719.3492
4
5 | Current Year: 2025 | 26495372.7232 | 6217478.0265 | 262576.3199 | 32975427.0696
6
7 | Total Additions | 66829569.3932 | 22929868.0176 | 593255.278 | 90352692.6889

## Exhibit C-1
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
MONTHLY DEPRECIATION EXPENSE FOR FISCAL YEAR 2025
Line No. |  | Description |  | annual rate | Prior Yr | 2024-10-01 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | Annual Totals | 13-Month Average
FERC 37600: Mains
1 |  | Monthly Investment Additions |  |  |  | 1725954.7885 | 2155133.3447 | 2621685.3828 | 2377211.048 | 1841685.497 | 2087323.2244 | 2373395.9725 | 2381414.6569 | 2449621.5399 | 2401955.4336 | 2298234.9662 | 1781756.8687 | 26495372.7232
2 |  | Cumulative Investment |  |  | 40334196.67 | 42060151.4585 | 44215284.8032 | 46836970.1859 | 49214181.2339 | 51055866.731 | 53143189.9554 | 55516585.9279 | 57898000.5848 | 60347622.1247 | 62749577.5583 | 65047812.5245 | 66829569.3932 |  | 53480693.0116
3 |  | Monthly Retirements |  | 5.61% |  | 96821.5301 | 120897.3198 | 147069.6637 | 133355.2957 | 103313.7189 | 117093.3502 | 133141.28 | 133591.1071 | 137417.3341 | 134743.3907 | 128924.9449 | 99951.8803 | 1486320.8155
4 |  | Cumulative Retirements |  |  | 3883268.671 | 3980090.2011 | 4100987.521 | 4248057.1847 | 4381412.4803 | 4484726.1993 | 4601819.5495 | 4734960.8294 | 4868551.9365 | 5005969.2706 | 5140712.6613 | 5269637.6062 | 5369589.4865 |  | 4620752.5844
5 |  | Depreciable Base |  |  | 36450927.999 | 1629133.2584 | 2034236.0248 | 2474615.7191 | 2243855.7523 | 1738371.7781 | 1970229.8742 | 2240254.6925 | 2247823.5498 | 2312204.2059 | 2267212.0429 | 2169310.0213 | 1681804.9885 | 25009051.9077
6 |  | Monthly Depreciation Expense, book basis |  |  | 0 | 47824.0514 | 49248.0167 | 51153.4708 | 53073.214 | 54746.3969 | 56913.6497 | 59788.6432 | 63250.2915 | 67701.2846 | 73520.4622 | 81872.3058 | 94822.2042 | 753913.9909
7 |  | Cumulative Depreciation |  |  | 608963.0148 | 656787.0662 | 706035.0829 | 757188.5537 | 810261.7677 | 865008.1645 | 921921.8142 | 981710.4575 | 1044960.749 | 1112662.0336 | 1186182.4958 | 1268054.8015 | 1362877.0057 |  | 944816.3852
8 |  |  | Net | Depr.
9 |  | Month | Investment | Rate
10 |  | prior period | 36450927.999 | 1.54% | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 46778.6909 | 561344.2912
11 |  | 2024-10-01 | 1629133.2584 | 1.54% |  | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 1045.3605 | 12544.3261
12 |  | 2024-11-30 | 2034236.0248 | 1.54% |  |  | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 1423.9652 | 15663.6174
13 |  | 2024-12-31 | 2474615.7191 | 1.54% |  |  |  | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 1905.4541 | 19054.541
14 |  | 2025-01-31 | 2243855.7523 | 1.54% |  |  |  |  | 1919.7433 | 1919.7433 | 1919.7433 | 1919.7433 | 1919.7433 | 1919.7433 | 1919.7433 | 1919.7433 | 1919.7433 | 17277.6893
15 |  | 2025-02-28 | 1738371.7781 | 1.54% | [5 empty] | 1673.1828 | 1673.1828 | 1673.1828 | 1673.1828 | 1673.1828 | 1673.1828 | 1673.1828 | 1673.1828 | 13385.4627
16 |  | 2025-03-31 | 1970229.8742 | 1.54% |  | 2025-03-31: 2167.2529; 2025-04-30: 2167.2529; 2025-05-31: 2167.2529; 2025-06-30: 2167.2529; 2025-07-31: 2167.2529; 2025-08-31: 2167.2529; 2025-09-30: 2167.2529 | 15170.77
17 |  | 2025-04-30 | 2240254.6925 | 1.54% |  | 2025-04-30: 2874.9935; 2025-05-31: 2874.9935; 2025-06-30: 2874.9935; 2025-07-31: 2874.9935; 2025-08-31: 2874.9935; 2025-09-30: 2874.9935 | 17249.9611
18 |  | 2025-05-31 | 2247823.5498 | 1.54% |  | 2025-05-31: 3461.6483; 2025-06-30: 3461.6483; 2025-07-31: 3461.6483; 2025-08-31: 3461.6483; 2025-09-30: 3461.6483 | 17308.2413
19 |  | 2025-06-30 | 2312204.2059 | 1.54% |  | 2025-06-30: 4450.9931; 2025-07-31: 4450.9931; 2025-08-31: 4450.9931; 2025-09-30: 4450.9931 | 17803.9724
20 |  | 2025-07-31 | 2267212.0429 | 1.54% |  | 2025-07-31: 5819.1776; 2025-08-31: 5819.1776; 2025-09-30: 5819.1776 | 17457.5327
21 |  | 2025-08-31 | 2169310.0213 | 1.54% |  | 2025-08-31: 8351.8436; 2025-09-30: 8351.8436 | 16703.6872
22 |  | 2025-09-30 | 1681804.9885 | 1.54% |  | 2025-09-30: 12949.8984 | 12949.8984
23 |  | Total: FERC 376 Depr Exp | 61459979.9067 |  | 46778.6909 | 47824.0514 | 49248.0167 | 51153.4708 | 53073.214 | 54746.3969 | 56913.6497 | 59788.6432 | 63250.2915 | 67701.2846 | 73520.4622 | 81872.3058 | 94822.2042 | 753913.9909
24
25
26 | FERC 38000: Services
27 |  | Monthly Investment Additions |  |  |  | 558320.3595 | 523099.4491 | 494673.3506 | 519392.7974 | 506369.8779 | 509231.6066 | 509532.0679 | 519760.592 | 511054.2285 | 535022.9235 | 518421.0189 | 512599.7546 | 6217478.0265
28 |  | Cumulative Investment |  |  | 16712389.9911 | 17270710.3506 | 17793809.7997 | 18288483.1503 | 18807875.9477 | 19314245.8256 | 19823477.4322 | 20333009.5001 | 20852770.0921 | 21363824.3206 | 21898847.2441 | 22417268.263 | 22929868.0176 |  | 19831275.3796
29 |  | Monthly Retirements |  | 28.59% |  | 159643.3903 | 149572.4956 | 141444.4762 | 148512.6338 | 144788.9239 | 145607.1926 | 145693.1051 | 148617.7992 | 146128.3442 | 152981.8355 | 148234.7682 | 146570.2644 | 1777795.229
30 |  | Cumulative Retirements |  |  | 6218828.482 | 6378471.8723 | 6528044.368 | 6669488.8441 | 6818001.4779 | 6962790.4019 | 7108397.5945 | 7254090.6996 | 7402708.4987 | 7548836.843 | 7701818.6785 | 7850053.4467 | 7996623.711 |  | 7110627.3014
31 |  | Depreciable Base |  |  | 10493561.5091 | 398676.9692 | 373526.9535 | 353228.8744 | 370880.1636 | 361580.954 | 363624.414 | 363838.9628 | 371142.7929 | 364925.8843 | 382041.088 | 370186.2507 | 366029.4902 | 4439682.7975
32 |  | Monthly Depreciation Expense, book basis |  |  | 0 | 22098.66 | 22519.7267 | 22957.7305 | 23468.721 | 24029.1715 | 24673.3061 | 25425.24 | 26345.6741 | 27476.9444 | 29056.0475 | 31351.2023 | 35889.968 | 315292.3921
33 |  | Cumulative Depreciation |  |  | 249855.7077 | 271954.3677 | 294474.0944 | 317431.825 | 340900.546 | 364929.7174 | 389603.0236 | 415028.2636 | 441373.9377 | 468850.8821 | 497906.9296 | 529258.1319 | 565148.0998 |  | 395901.1943
34 |  |  | Net | Depr.
35 |  | Month | Investment | Rate
36 |  | prior period | 10493561.5091 | 2.48% | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 21686.6938 | 260240.3254
37 |  | 2024-10-01 | 398676.9692 | 2.48% |  | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 411.9662 | 4943.5944
38 |  | 2024-11-30 | 373526.9535 | 2.48% |  |  | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 421.0667 | 4631.7342
39 |  | 2024-12-31 | 353228.8744 | 2.48% |  |  |  | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 438.0038 | 4380.038
40 |  | 2025-01-31 | 370880.1636 | 2.48% |  |  |  |  | 510.9904 | 510.9904 | 510.9904 | 510.9904 | 510.9904 | 510.9904 | 510.9904 | 510.9904 | 510.9904 | 4598.914
41 |  | 2025-02-28 | 361580.954 | 2.48% | [5 empty] | 560.4505 | 560.4505 | 560.4505 | 560.4505 | 560.4505 | 560.4505 | 560.4505 | 560.4505 | 4483.6038
42 |  | 2025-03-31 | 363624.414 | 2.48% |  | 2025-03-31: 644.1347; 2025-04-30: 644.1347; 2025-05-31: 644.1347; 2025-06-30: 644.1347; 2025-07-31: 644.1347; 2025-08-31: 644.1347; 2025-09-30: 644.1347 | 4508.9427
43 |  | 2025-04-30 | 363838.9628 | 2.48% |  | 2025-04-30: 751.9339; 2025-05-31: 751.9339; 2025-06-30: 751.9339; 2025-07-31: 751.9339; 2025-08-31: 751.9339; 2025-09-30: 751.9339 | 4511.6031
44 |  | 2025-05-31 | 371142.7929 | 2.48% |  | 2025-05-31: 920.4341; 2025-06-30: 920.4341; 2025-07-31: 920.4341; 2025-08-31: 920.4341; 2025-09-30: 920.4341 | 4602.1706
45 |  | 2025-06-30 | 364925.8843 | 2.48% |  | 2025-06-30: 1131.2702; 2025-07-31: 1131.2702; 2025-08-31: 1131.2702; 2025-09-30: 1131.2702 | 4525.081
46 |  | 2025-07-31 | 382041.088 | 2.48% |  | 2025-07-31: 1579.1032; 2025-08-31: 1579.1032; 2025-09-30: 1579.1032 | 4737.3095
47 |  | 2025-08-31 | 370186.2507 | 2.48% |  | 2025-08-31: 2295.1548; 2025-09-30: 2295.1548 | 4590.3095
48 |  | 2025-09-30 | 366029.4902 | 2.48% |  | 2025-09-30: 4538.7657 | 4538.7657
49 |  | Total: FERC 380 Depr Exp | 14933244.3066 |  | 21686.6938 | 22098.66 | 22519.7267 | 22957.7305 | 23468.721 | 24029.1715 | 24673.3061 | 25425.24 | 26345.6741 | 27476.9444 | 29056.0475 | 31351.2023 | 35889.968 | 315292.3921
50
51 | FERC 38100: Meters
52 |  | Monthly Investment Additions |  |  |  | 23578.9664 | 22091.5181 | 20891.0281 | 21934.9789 | 21384.9954 | 21505.8518 | 21518.5409 | 21950.5116 | 21582.8247 | 22595.0699 | 21893.9388 | 21648.0953 | 262576.3199
53 |  | Cumulative Investment |  |  | 330678.9581 | 354257.9245 | 376349.4426 | 397240.4707 | 419175.4496 | 440560.445 | 462066.2968 | 483584.8377 | 505535.3493 | 527118.1741 | 549713.2439 | 571607.1827 | 593255.278 |  | 462395.6195
54 |  | Monthly Retirements |  | 37.34% |  | 8804.9607 | 8249.5113 | 7801.2191 | 8191.0558 | 7985.6785 | 8030.8092 | 8035.5477 | 8196.856 | 8059.5528 | 8437.5498 | 8175.7304 | 8083.9264 | 98052.3978 |  | 0 | Retirment check to source
55 |  | Cumulative Retirements |  |  | 150003.2174 | 158808.1781 | 167057.6894 | 174858.9085 | 183049.9643 | 191035.6428 | 199066.452 | 207101.9997 | 215298.8557 | 223358.4085 | 231795.9583 | 239971.6887 | 248055.6152 |  | 199189.4291
56 |  | Depreciable Base |  |  | 180675.7407 | 14774.0056 | 13842.0068 | 13089.809 | 13743.9231 | 13399.3169 | 13475.0426 | 13482.9932 | 13753.6556 | 13523.2719 | 14157.52 | 13718.2084 | 13564.1689 | 164523.9221
57 |  | Monthly Depreciation Expense, book basis |  |  | 0 | 760.0869 | 790.6023 | 822.345 | 859.3773 | 899.994 | 946.6754 | 1001.1691 | 1067.8743 | 1149.8592 | 1264.2991 | 1430.6324 | 1759.5635 | 12752.4785
58 |  | Cumulative Depreciation |  |  | 4381.3867 | 5141.4736 | 5932.0759 | 6754.4209 | 7613.7982 | 8513.7922 | 9460.4675 | 10461.6366 | 11529.511 | 12679.3702 | 13943.6693 | 15374.3017 | 17133.8653 |  | 9916.9053
59 |  |  | Net | Depr.
60 |  | Month | Investment | Rate
61 |  | prior period | 180675.7407 | 4.85% | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 730.2311 | 8762.7734
62 |  | 2024-10-01 | 14774.0056 | 4.85% |  | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 29.8558 | 358.2696
63 |  | 2024-11-30 | 13842.0068 | 4.85% |  |  | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 30.5153 | 335.6687
64 |  | 2024-12-31 | 13089.809 | 4.85% |  |  |  | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 31.7428 | 317.4279
65 |  | 2025-01-31 | 13743.9231 | 4.85% |  |  |  |  | 37.0322 | 37.0322 | 37.0322 | 37.0322 | 37.0322 | 37.0322 | 37.0322 | 37.0322 | 37.0322 | 333.2901
66 |  | 2025-02-28 | 13399.3169 | 4.85% | [5 empty] | 40.6167 | 40.6167 | 40.6167 | 40.6167 | 40.6167 | 40.6167 | 40.6167 | 40.6167 | 324.9334
67 |  | 2025-03-31 | 13475.0426 | 4.85% |  | 2025-03-31: 46.6814; 2025-04-30: 46.6814; 2025-05-31: 46.6814; 2025-06-30: 46.6814; 2025-07-31: 46.6814; 2025-08-31: 46.6814; 2025-09-30: 46.6814 | 326.7698
68 |  | 2025-04-30 | 13482.9932 | 4.85% |  | 2025-04-30: 54.4938; 2025-05-31: 54.4938; 2025-06-30: 54.4938; 2025-07-31: 54.4938; 2025-08-31: 54.4938; 2025-09-30: 54.4938 | 326.9626
69 |  | 2025-05-31 | 13753.6556 | 4.85% |  | 2025-05-31: 66.7052; 2025-06-30: 66.7052; 2025-07-31: 66.7052; 2025-08-31: 66.7052; 2025-09-30: 66.7052 | 333.5261
70 |  | 2025-06-30 | 13523.2719 | 4.85% |  | 2025-06-30: 81.9848; 2025-07-31: 81.9848; 2025-08-31: 81.9848; 2025-09-30: 81.9848 | 327.9393
71 |  | 2025-07-31 | 14157.52 | 4.85% |  | 2025-07-31: 114.44; 2025-08-31: 114.44; 2025-09-30: 114.44 | 343.3199
72 |  | 2025-08-31 | 13718.2084 | 4.85% |  | 2025-08-31: 166.3333; 2025-09-30: 166.3333 | 332.6666
73 |  | 2025-09-30 | 13564.1689 | 4.85% |  | 2025-09-30: 328.9311 | 328.9311
74 |  | Total: FERC 381 Depr Exp | 345199.6629 |  | 730.2311 | 760.0869 | 790.6023 | 822.345 | 859.3773 | 899.994 | 946.6754 | 1001.1691 | 1067.8743 | 1149.8592 | 1264.2991 | 1430.6324 | 1759.5635 | 12752.4785
75
76 |  | Total Depreciation Expense, Monthly (Lines 22+44+66) |  |  | 69195.6158 | 70682.7983 | 72558.3456 | 74933.5463 | 77401.3123 | 79675.5623 | 82533.6312 | 86215.0524 | 90663.84 | 96328.0881 | 103840.8088 | 114654.1405 | 132471.7356 | 1081958.8615
Note: |  | This Depreciation methodology is consistent with how the Company accounts for Depreciation expense on its books.
[16 empty] | Cum Invest | 90352692.6889
[16 empty] | Cum Retire | 13614268.8127
[16 empty] | Cum Plant | 76738423.8762
[16 empty] | Support Variance | -8.7311e-10

## Exhibit C-2
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
MONTHLY COST OF REMOVAL FOR FISCAL YEAR 2025
Line No. | Description | Prior Yr Balance | 2024-10-01 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | Annual Totals | 13-Month Average
1 | FERC 37600: Mains
2 | Cost of Removal |  | 90839.7257 | 113428.0708 | 137983.4412 | 125116.3709 | 96930.8156 | 109859.1171 | 124915.5775 | 125337.6135 | 128927.4495 | 126418.707 | 120959.7351 | 93776.6773 | 1394493.3012
3 | Accumulated | 1846584.97 | 1937424.6957 | 2050852.7665 | 2188836.2077 | 2313952.5786 | 2410883.3943 | 2520742.5113 | 2645658.0888 | 2770995.7024 | 2899923.1518 | 3026341.8589 | 3147301.5939 | 3241078.2712 |  | 2538505.8301
4
5 | FERC 38000: Services
6 | Cost of Removal |  | 24782.1939 | 23218.8415 | 21957.0909 | 23054.3142 | 22476.2652 | 22603.2889 | 22616.6255 | 23070.6395 | 22684.1897 | 23748.0894 | 23011.1798 | 22752.7911 | 275975.5097
7 | Accumulated | 639905.2762 | 664687.4701 | 687906.3116 | 709863.4025 | 732917.7167 | 755393.9819 | 777997.2709 | 800613.8964 | 823684.5359 | 846368.7256 | 870116.815 | 893127.9949 | 915880.7859 |  | 778343.3987
8
9 | Total Cost of Removal |  | 115621.9196 | 136646.9123 | 159940.5321 | 148170.6852 | 119407.0809 | 132462.406 | 147532.203 | 148408.253 | 151611.6392 | 150166.7964 | 143970.9149 | 116529.4684 | 1670468.811
10 | Accumulated | 2486490.2462 | 2602112.1658 | 2738759.0781 | 2898699.6102 | 3046870.2953 | 3166277.3762 | 3298739.7822 | 3446271.9852 | 3594680.2383 | 3746291.8775 | 3896458.6739 | 4040429.5888 | 4156959.0572 |  | 3316849.2288

## Exhibit D
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
RETIREMENTS
Line
Number | Description | Mains | Services | Meters | Total
1 | Prior Year: 2023 | 932977.76 | 3624933.43 | 0 | 4557911.19
2
1 | Prior Year: 2024 | 2950290.911 | 2593895.052 | 150003.2174 | 5694189.1804
2
3 | Current Year: 2025 | 1486320.8155 | 1777795.229 | 98052.3978 | 3362168.4423
4
5 | Total Retirements | 5369589.4865 | 7996623.711 | 248055.6152 | 13614268.8127

## Exhibit F
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
KENTUCKY PRP ADIT CALCULATION
Line No |  |  | 2022-10-15 | 2022-11-14 | 2022-12-14 | 2023-01-13 | 2023-02-12 | 2023-03-14 | 2023-04-13 | 2023-05-13 | 2023-06-12 | 2023-07-12 | 2023-08-11 | 2023-09-10 | Total |  | 2023-10-01 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | Total |  | 2024-10-01 | 2024-11-30 | 2024-12-31 | 2025-01-31 | 2025-02-28 | 2025-03-31 | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | Total
1 | Book Cost |  | 4009258.76 | 1938511.55 | 1761959.82 | 1756835.46 | 2339838.56 | 2012835.16 | 1919913.12 | 2117019.08 | 2569238.23 | 2531048.9 | 2746811.12 | 442365.32 | 26145635.08 | Book Cost | 1295166.3095 | 1459441.7681 | 1691645.3022 | 1797088.3623 | 1808429.4113 | 1658240.1698 | 2099062.5196 | 2266172.9286 | 1722973.5097 | 1866848.4638 | 1935516.0252 | 1378945.3947 | 20979530.1646 | Book Cost | 2042584.2332 | 2421604.9851 | 2840934.4025 | 2628479.8391 | 2113352.049 | 2347329.3308 | 2617576.6486 | 2632719.9982 | 2690653.3621 | 2663410.6509 | 2553214.4804 | 2061398.6476 | 29613258.6273
2 | Tax Cost |  | 2892445.5823 | 1398522.6459 | 1271150.9041 | 1267453.9782 | 1688056.5988 | 1452142.7812 | 1385104.967 | 1527305.3829 | 1853555.0367 | 1826003.6699 | 1981663.4857 | 319140.6921 | 18862545.7248 | Tax Cost | 1112543.2537 | 1253655.2884 | 1453117.2984 | 1543692.512 | 1553434.4328 | 1424422.4084 | 1803087.2392 | 1946634.4862 | 1480028.1172 | 1603616.1911 | 1662601.3821 | 1184509.1899 | 18021341.7994 | Tax Cost | 1533382.5115 | 1817916.0857 | 2132709.6618 | 1973218.51 | 1586508.4142 | 1762156.8238 | 1965033.4073 | 1976401.6276 | 2019892.6159 | 1999441.3189 | 1916716.2699 | 1547506.6262 | 22230883.8728
3 | FXA01 |  | -1116813.1777 | -539988.9041 | -490808.9159 | -489381.4818 | -651781.9612 | -560692.3788 | -534808.153 | -589713.6971 | -715683.1933 | -705045.2301 | -765147.6343 | -123224.6279 | -7283089.3552 | FXA01 | -182623.0558 | -205786.4797 | -238528.0038 | -253395.8503 | -254994.9785 | -233817.7613 | -295975.2804 | -319538.4424 | -242945.3925 | -263232.2727 | -272914.6431 | -194436.2048 | -2958188.3653 | FXA01 | -509201.7217 | -603688.8994 | -708224.7407 | -655261.3291 | -526843.6348 | -585172.507 | -652543.2413 | -656318.3706 | -670760.7462 | -663969.332 | -636498.2105 | -513892.0214 | -7382374.7546
4
5
6 | [15 empty] | Prior Yr Bal | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | -7283089.3552 | Prior Yr Bal | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205 | -10241277.7205
7 | [15 empty] | Current Yr | -182623.0558 | -205786.4797 | -238528.0038 | -253395.8503 | -254994.9785 | -233817.7613 | -295975.2804 | -319538.4424 | -242945.3925 | -263232.2727 | -272914.6431 | -194436.2048 | -2958188.3653 | Current Yr | -509201.7217 | -603688.8994 | -708224.7407 | -655261.3291 | -526843.6348 | -585172.507 | -652543.2413 | -656318.3706 | -670760.7462 | -663969.332 | -636498.2105 | -513892.0214 | -7382374.7546
8 | FXA01 Cumulative |  | -1116813.1777 | -1656802.0819 | -2147610.9978 | -2636992.4795 | -3288774.4407 | -3849466.8195 | -4384274.9726 | -4973988.6697 | -5689671.8629 | -6394717.093 | -7159864.7273 | -7283089.3552 | -7283089.3552 | FXA01 Cumulative | -7465712.411 | -7671498.8907 | -7910026.8945 | -8163422.7448 | -8418417.7233 | -8652235.4846 | -8948210.7651 | -9267749.2075 | -9510694.5999 | -9773926.8726 | -10046841.5157 | -10241277.7205 | -10241277.7205 | FXA01 Cumulative | -10750479.4421 | -11354168.3415 | -12062393.0822 | -12717654.4113 | -13244498.0461 | -13829670.5531 | -14482213.7944 | -15138532.165 | -15809292.9112 | -16473262.2432 | -17109760.4537 | -17623652.475 | -17623652.475
9 | Deferred Rate |  | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | Deferred Rate | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | Deferred Rate | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95%
10 | FXA01 Tax Effected |  | -278644.8878 | -413372.1194 | -535828.9439 | -657929.6236 | -820549.223 | -960441.9715 | -1093876.6057 | -1241010.1731 | -1419573.1298 | -1595481.9147 | -1786386.2495 | -1817130.7941 | -1817130.7941 | FXA01 Tax Effected | -1862695.2465 | -1914038.9732 | -1973551.7102 | -2036773.9748 | -2100395.222 | -2158732.7534 | -2232578.5859 | -2312303.4273 | -2372918.3027 | -2438594.7547 | -2506686.9582 | -2555198.7913 | -2555198.7913 | FXA01 Tax Effected | -2682244.6208 | -2832865.0012 | -3009567.074 | -3173054.7756 | -3304502.2625 | -3450502.803 | -3613312.3417 | -3777063.7752 | -3944418.5813 | -4110078.9297 | -4268885.2332 | -4397101.2925 | -4397101.2925
11 | [29 empty] | FXA01 Prorated | -2676849.5239 | -2808693.9391 | -2948361.1939 | -3063698.4081 | -3146348.2662 | -3225748.5602 | -3300908.5801 | -3362595.764 | -3411885.1932 | -3446605.7867 | -3466402.1889 | -3471846.9805 | -3471846.9805
12
13
14
15 | Book Depreciation |  | 2719.713 | 4135.4112 | 5831.4974 | 7340.2598 | 9878.6536 | 12359.6655 | 14984.5883 | 18900.7158 | 24643.7327 | 31597.1753 | 44511.3095 | 47110.4849 | 224013.2071 | Book Depreciation | 41140.3179 | 42407.4151 | 43951.5222 | 45775.4414 | 47817.5496 | 49978.5005 | 53070.6009 | 57055.694 | 60967.9348 | 66598.5762 | 75230.1358 | 88293.162 | 639186.9021 | Book Depreciation | 70682.7983 | 72558.3456 | 74933.5463 | 77401.3123 | 79675.5623 | 82533.6312 | 86215.0524 | 90663.84 | 96328.0881 | 103840.8088 | 114654.1405 | 132471.7356 | 1081958.8615
16 | Tax Depreciation |  | 11032.5586 | 16775.3606 | 23655.5608 | 29775.8792 | 40072.9133 | 50137.1773 | 60785.2177 | 76671.0507 | 99967.6886 | 128174.4379 | 180560.8261 | 191104.4221 | 908713.093 | Tax Depreciation | 148035.5157 | 152594.9211 | 158151.0933 | 164714.1156 | 172062.2486 | 179838.0145 | 190964.3428 | 205303.9334 | 219381.3787 | 239642.1581 | 270701.1641 | 317705.9496 | 2556743.8623 | Tax Depreciation | 274054.9127 | 281326.8793 | 290536.1273 | 300104.2739 | 308922.1108 | 320003.5599 | 334277.3517 | 351526.4156 | 373488.1244 | 402616.8242 | 444542.8192 | 513626.0984 | 4195025.4975
17 | FXA02 |  | -8312.8456 | -12639.9494 | -17824.0634 | -22435.6194 | -30194.2598 | -37777.5118 | -45800.6295 | -57770.3348 | -75323.956 | -96577.2626 | -136049.5166 | -143993.9372 | -684699.8859 | FXA02 | -106895.1978 | -110187.5059 | -114199.571 | -118938.6741 | -124244.699 | -129859.5141 | -137893.7419 | -148248.2394 | -158413.4439 | -173043.5819 | -195471.0283 | -229412.7876 | -1746807.9848 | FXA02 | -203372.1143 | -208768.5337 | -215602.581 | -222702.9616 | -229246.5485 | -237469.9287 | -248062.2994 | -260862.5756 | -277160.0363 | -298776.0154 | -329888.6788 | -381154.3628 | -3113066.636
18
19
20
21 | [15 empty] | Prior Yr Bal | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | -684699.8859 | Prior Yr Bal | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707 | -2431507.8707
22 | Current Year | [14 empty] | Current Yr | -106895.1978 | -110187.5059 | -114199.571 | -118938.6741 | -124244.699 | -129859.5141 | -137893.7419 | -148248.2394 | -158413.4439 | -173043.5819 | -195471.0283 | -229412.7876 | -1746807.9848 | Current Yr | -203372.1143 | -208768.5337 | -215602.581 | -222702.9616 | -229246.5485 | -237469.9287 | -248062.2994 | -260862.5756 | -277160.0363 | -298776.0154 | -329888.6788 | -381154.3628 | -3113066.636
23 | FXA02 Cumulative |  | -8312.8456 | -20952.795 | -38776.8583 | -61212.4778 | -91406.7375 | -129184.2493 | -174984.8788 | -232755.2136 | -308079.1696 | -404656.4322 | -540705.9488 | -684699.8859 | -684699.8859 | FXA02 Cumulative | -791595.0837 | -901782.5896 | -1015982.1607 | -1134920.8348 | -1259165.5338 | -1389025.0479 | -1526918.7897 | -1675167.0291 | -1833580.473 | -2006624.0549 | -2202095.0831 | -2431507.8707 | -2431507.8707 | FXA02 Cumulative | -2634879.985 | -2843648.5187 | -3059251.0996 | -3281954.0613 | -3511200.6098 | -3748670.5384 | -3996732.8378 | -4257595.4134 | -4534755.4497 | -4833531.4651 | -5163420.1439 | -5544574.5067 | -5544574.5067
24 | Deferred Rate |  | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | Deferred Rate | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | Deferred Rate | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95% | 24.95%
25 | FXA02 Tax Effected |  | -2074.055 | -5227.7223 | -9674.8262 | -15272.5132 | -22805.981 | -32231.4702 | -43658.7273 | -58072.4258 | -76865.7528 | -100961.7798 | -134906.1342 | -170832.6215 | -170832.6215 | FXA02 Tax Effected | -197502.9734 | -224994.7561 | -253487.5491 | -283162.7483 | -314161.8007 | -346561.7494 | -380966.238 | -417954.1738 | -457478.328 | -500652.7017 | -549422.7232 | -606661.2137 | -606661.2137 | FXA02 Tax Effected | -657402.5563 | -709490.3054 | -763283.1494 | -818847.5383 | -876044.5521 | -935293.2993 | -997184.843 | -1062270.0556 | -1131421.4847 | -1205966.1005 | -1288273.3259 | -1383371.3394 | -1383371.3394
26 | [29 empty] | FXA02 Prorated | -655247.7869 | -700842.4057 | -743360.8591 | -782560.3937 | -818523.9956 | -850745.5745 | -879317.4242 | -903835.8262 | -924202.3429 | -939826.0775 | -950086.2933 | -954124.7021 | -954124.7021
27 |  | Beg Balance | [12 empty] | 13 Month Avg | Beg Balance | [12 empty] | 13 Month Avg | Beg Balance | [12 empty] | 13 Mo Average
28 | Cumulative Deferred Inc. Taxes (excluding NOLC) | 0 | -280718.9428 | -418599.8418 | -545503.7701 | -673202.1368 | -843355.204 | -992673.4417 | -1137535.3329 | -1299082.5989 | -1496438.8826 | -1696443.6945 | -1921292.3837 | -1987963.4157 | -1022523.8189 | -1987963.4157 | -2060198.2199 | -2139033.7293 | -2227039.2593 | -2319936.7231 | -2414557.0227 | -2505294.5029 | -2613544.8239 | -2730257.601 | -2830396.6307 | -2939247.4564 | -3056109.6814 | -3161860.005 | -2537341.467 | -3161860.005 | -3339647.1771 | -3542355.3066 | -3772850.2234 | -3991902.3139 | -4180546.8146 | -4385796.1023 | -4610497.1847 | -4839333.8308 | -5075840.066 | -5316045.0302 | -5557158.5591 | -5780472.6319 | -4427254.2497
29
30 | NOLC | 0 | 2074.055 | 5227.7223 | 9674.8262 | 15272.5132 | 22805.981 | 32231.4702 | 43658.7273 | 58072.4258 | 76865.7528 | 100961.7798 | 134906.1342 | 170832.6215 | 51737.2315 | 170832.6215 | 197502.9734 | 224994.7561 | 253487.5491 | 283162.7483 | 314161.8007 | 346561.7494 | 380966.238 | 417954.1738 | 457478.328 | 500652.7017 | 549422.7232 | 606661.2137 | 361833.8136 | 606661.2137 | 657402.5563 | 709490.3054 | 763283.1494 | 818847.5383 | 876044.5521 | 935293.2993 | 997184.843 | 1062270.0556 | 1131421.4847 | 1205966.1005 | 1288273.3259 | 1383371.3394 | 956577.6741
31
32 | [29 empty] | Proration Impact on NOLC | [12 empty] | -1170.405
33 | Net ADIT | [13 empty] | -970786.5874 | [13 empty] | -2175507.6534 | [13 empty] | -3471846.9805
34
35 | NOLC is calculated in compliance with the 2023 Final Order in Case No. 2022-00222 | [28 empty] | ADIT Proration:
36 | [29 empty] | days in month | 31 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30 | 365
37 | [29 empty] | mid month convention | 15.5 | 30 | 31 | 31 | 28 | 31 | 30 | 31 | 30 | 31 | 31 | 30
38 | [29 empty] | days remaining | 349.5 | 319.5 | 288.5 | 257.5 | 229.5 | 198.5 | 168.5 | 137.5 | 107.5 | 76.5 | 45.5 | 15.5
39 | [29 empty] | pro ration factor | 95.75% | 87.53% | 79.04% | 70.55% | 62.88% | 54.38% | 46.16% | 37.67% | 29.45% | 20.96% | 12.47% | 4.247%

## Exhibit F-1
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
DEFERRED INCOME TAXES
Line
Number | Description | Mains | Services | Meters | Total | Ck Figures
1
2 | Additions to Gross Plant - Book 2023 | 22250566.67 | 8452979.6 | 0 | 30703546.27
3 | Less: Retirements to Book 2023 | -932977.76 | -3624933.43 | 0 | -4557911.19
4 | Book Basis | 21317588.91 | 4828046.17 | 0 | 26145635.08
5 | Repairs Percentage | 27.6% | 67.43% | 0%
6 | Less: Repairs | -6141156.4009 | -5699844.1443 | 0 | -11841000.5452
7 | Add: Deferred Retirements | 932977.76 | 3624933.43 | 0 | 4557911.19
8 | Tax Basis Before Bonus | 16109410.2691 | 2753135.4557 | 0 | 18862545.7248
9 | Bonus Depreciation % | 0% | 0% | 0%
10 | Bonus Depreciation | 0 | 0 | 0 | 0
11 | Tax Basis | 16109410.2691 | 2753135.4557 | 0 | 18862545.7248
12
13 | Additions to Gross Plant - Book 2024 | 18083630 | 8259410.3911 | 330678.9581 | 26673719.3492
14 | Less: Retirements to Book 2024 | -2950290.911 | -2593895.052 | -150003.2174 | -5694189.1804
15 | Book Basis | 15133339.089 | 5665515.3391 | 180675.7407 | 20979530.1688
16 | Repairs Percentage | 32.85% | 32.85% | 0%
17 | Less: Repairs | -5939572.3466 | -2712805.2033 | 0 | -8652377.5499
18 | Add: Deferred Retirements | 2950290.911 | 2593895.052 | 150003.2174 | 5694189.1804
19 | Tax Basis Before Bonus | 12144057.6534 | 5546605.1878 | 330678.9581 | 18021341.7994
20 | Bonus Depreciation % | 0% | 0% | 0%
21 | Bonus Depreciation | 0 | 0 | 0 | 0
22 | Tax Basis | 12144057.6534 | 5546605.1878 | 330678.9581 | 18021341.7994
23
24 | Additions to Gross Plant - Book 2025 | 26495372.7232 | 6217478.0265 | 262576.3199 | 32975427.0696
25 | Less: Retirements to Book 2025 | -1486320.8155 | -1777795.229 | -98052.3978 | -3362168.4423
26 | Book Basis | 25009051.9077 | 4439682.7975 | 164523.9221 | 29613258.6273
27 | Repairs Percentage | 32.85% | 32.85% | 0%
28 | Less: Repairs | -8702411.1387 | -2042132.0582 | 0 | -10744543.1969
29 | Add: Deferred Retirements | 1486320.8155 | 1777795.229 | 98052.3978 | 3362168.4423
30 | Tax Basis Before Bonus | 17792961.5845 | 4175345.9683 | 262576.3199 | 22230883.8728
31 | Bonus Depreciation % | 0% | 0% | 0%
32 | Bonus Depreciation | 0 | 0 | 0 | 0
33 | Tax Basis | 17792961.5845 | 4175345.9683 | 262576.3199 | 22230883.8728
23
24 | FXA01 - Gross | -15413550.3997 | -2458157.6947 | 248055.6152 | -17623652.4793
25 | Deferred Rate | 24.95% | 24.95% | 24.95%
26 | FXA01 - Tax Effected | -3845680.8247 | -613310.3448 | 61889.876 | -4397101.2936
27 | FXA01 - Tax Effected Prorated |  |  |  | -3471846.9805
28
29
30 | Book Depreciation 2023 | 164145.4346 | 59867.7725 | 0 | 224013.2071 | 0
31 | Book Depreciation 2024 | 444817.5802 | 189987.9352 | 4381.3867 | 639186.9021 | 0
32 | Book Depreciation 2025 | 753913.9909 | 315292.3921 | 12752.4785 | 1081958.8615
32 | Book Depreciation | 1362877.0057 | 565148.0998 | 17133.8653 | 1945158.9708
33
34 | Tax Depreciation 2023 | 805470.5135 | 103242.5796 | 0 | 908713.093
35 | Tax Depreciation 2024 | 2137596.8582 | 406746.5431 | 12400.4609 | 2556743.8623
36 | Tax Depreciation 2025 | 3420688.1343 | 740619.0372 | 33718.326 | 4195025.4975
36 | Tax Depreciation | 6363755.506 | 1250608.1599 | 46118.7869 | 7660482.4528
37
38 | FXA02 - Gross | -5000878.5003 | -685460.0601 | -28984.9217 | -5715323.482 | -170748.9754
39 | Deferred Rate | 24.95% | 24.95% | 24.95%
40 | FXA02 - Tax Effected | -1247719.1858 | -171022.285 | -7231.738 | -1425973.2088 | -42601.8694
41 | FXA02 - Tax Effected Prorated |  |  |  | -954124.7021 | 0
42
43 | Calculation of Book Depreciation
44
45 | Book Basis - 2023 | 21317588.91 | 4828046.17 | 0 | 26145635.08 | 0
46 | Book Depreciation Rates - Year 1 | 0.77% | 1.24% | 2.425%
47 | Book Depreciation Rates - Year 2 | 1.54% | 2.48% | 4.85%
48 | Book Depreciation Rates - Year 3 | 1.54% | 2.48% | 4.85%
48 | Book Depreciation 2023 | 820727.173 | 299338.8625 | 0 | 1120066.0356
49
50 | Book Basis - 2024 | 15133339.089 | 5665515.3391 | 180675.7407 | 20979530.1688 | 0.0042111
51 | Book Depreciation Rates - Year 1 | 0.77% | 1.24% | 2.425%
52 | Book Depreciation Rates - Year 2 | 1.54% | 2.48% | 4.85%
52 | Book Depreciation 2024 | 349580.133 | 210757.1706 | 13144.1601 | 573481.4637
53
54 | Book Basis - 2025 | 25009051.9077 | 4439682.7975 | 164523.9221 | 29613258.6273 | 0
55 | Book Depreciation Rates - Year 1 | 0.77% | 1.24% | 2.425%
56 | Book Depreciation 2025 | 192569.6997 | 55052.0667 | 3989.7051 | 251611.4715
53 |  |  |  |  | 2.734%
54 | Calculation of Tax Depreciation
55
56 | Tax Basis - 2023 | 16109410.2691 | 2753135.4557 | 0 | 18862545.7248 | 0
57 | Tax Depreciation Rates - Year 1 | 5% | 3.75% | 3.75%
58 | Tax Depreciation Rates - Year 2 | 9.5% | 7.219% | 7.219%
59 | Tax Depreciation Rates - Year 3 | 8.55% | 6.67% | 6.67%
59 | Tax Depreciation 2023 | 3713219.067 | 485625.563 | 0 | 4198844.6301
60
61 | Tax Basis - 2024 | 12144057.6534 | 5546605.1878 | 330678.9581 | 18021341.7994 | 0
62 | Tax Depreciation Rates - Year 1 | 5% | 3.75% | 3.75%
63 | Tax Depreciation Rates - Year 2 | 9.5% | 7.219% | 7.219%
63 | Tax Depreciation 2024 | 1760888.3597 | 608407.1231 | 36272.1749 | 2405567.6577
64
65 | Tax Basis - 2025 | 17792961.5845 | 4175345.9683 | 262576.3199 | 22230883.8728 | 0
66 | Tax Depreciation Rates - Year 1 | 5% | 3.75% | 3.75%
67 | Tax Depreciation 2024 | 889648.0792 | 156575.4738 | 9846.612 | 1056070.165
65
66 | Tax Rates
67 | Ad Valorem Tax Rate | 0.9745%
68 | Income Tax Rate | 24.95%
69 | State Tax Rate | 5%
70 | Federal Tax Rate | 21%
71 | Uncollectible accounts expense | 0.5%
72 | PSC Assessment | 0.1554%
73 | Gross Up Factor | 1.3412
Note:

## Exhibit G
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
RATE OF RETURN
Line |  |  |  | Weighted
Number | Description | Percent | Cost | Cost
1 | ST Debt | 0.05% | 80.94% | 0.04047%
2 | LT Debt | 45.45% | 3.84% | 1.745%
3 | Equity | 54.5% | 9.45% | 5.15%
4 |  | 100% |  | 6.936%
Notes:

## Exhibit H
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
O&M SAVINGS
Line |  | Annual | Cumulative
Number | Description | Savings | Savings
1 | Prior Year: 2023 | 4473.6051 | 4473.6051
2
3 | Prior Year: 2024 | 4166.4299 | 8640.035
4
5 | Current Year: 2025 | 3617.3809 | 12257.4159

## Exhibit I
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
RATE DESIGN
Case 2021-00214
Line Number | Class of Customers | Rate | Total | Total Dollars | Ratio | Volumetric Charge Ratio | Revenue increase by Class | Budgeted Volumes | Budgeted Customer Counts | Customer Charge | Volumetric Charge
1 | RESIDENTIAL (Rate G-1) |  |  |  | 55.58% |  | 4570913.2508 |  | 1919919.4585
2 | FIRM BILLS | 19.3 | 1930462 | 37257916.6 | [5 empty] | 0 |  | 0
3 | Sales: 1-300 | 1.5483 | 10018608.2345 | 15511811.1295 |  | 100% |  | 10106922.6406 |  |  | 0.4522 | 4570350.4181
4 | Sales: 301-15000 | 1.0762 | 0 | 0 |  | 0% |  | 0
5 | Sales: Over 15000 | 0.8888 | 0 | 0 |  | 0% |  | 0
6 | CLASS TOTAL (Mcf/month) |  | 10018608.2345 | 52769727.7295 |  |  |  | 10106922.6406
7
8 | NON-RESIDENTIAL (Rate G-1) |  |  |  | 26.86% |  | 2208760.572 |  | 241580.4482
9 | FIRM BILLS | 66 | 239727 | 15821982 | [5 empty] | 0 |  | 0
10 | Sales: 1-300 | 1.5483 | 5456430.0249 | 8448190.6075 |  | 87.3% |  | 5817307.6635 |  |  | 0.3315 | 1928437.4905
11 | Sales: 301-15000 | 1.0762 | 1142222.5564 | 1229259.9152 |  | 12.7% |  | 1217766.9283 |  |  | 0.2304 | 280573.5003
12 | Sales: Over 15000 | 0.8888 | 0 | 0 |  | 0% |  | 0 |  |  | 0.2304 | 0
13 | CLASS TOTAL (Mcf/month) |  | 6598652.5813 | 25499432.5227 |  |  |  | 7035074.5918
14
15 | INTERRUPTIBLE (G-2) |  |  |  | 0.3122% |  | 25674.4927 |  | 105
16 | INT BILLS | 520 | 97 | 50440 | [5 empty] | 0 |  | 0
17 | Sales: 1-15000 | 0.9557 | 216799.0505 | 207194.8526 |  | 84.24% |  | 161917.6287 |  |  | 0.1336 | 21632.1952
18 | Sales: Over 15000 | 0.7837 | 49469.0986 | 38768.9326 |  | 15.76% |  | 36946.2833 |  |  | 0.1095 | 4045.618
19 | CLASS TOTAL (Mcf/month) |  | 266268.1491 | 296403.7851 |  |  |  | 198863.9119
20
21 | TRANSPORTATION (T-3) |  |  |  | 8.241% |  | 677725.8667 |  | 840
22 | TRANSPORTATION BILLS | 520 | 838 | 435760 | [5 empty] | 0 |  | 0
23 | Interrupt Transport: 1-15000 | 0.9557 | 4937980.6011 | 4719228.0605 |  | 63.87% |  | 5085746.9406 |  |  | 0.0851 | 432797.0646
24 | Interrupt Transport: Over 15000 | 0.7837 | 3405818.2278 | 2669139.7451 |  | 36.13% |  | 3507735.4554 |  |  | 0.0698 | 244839.9348
25 | CLASS TOTAL (Mcf/month) |  | 8343798.8289 | 7824127.8056 |  |  |  | 8593482.396
26
27 | TRANSPORTATION (T-4) |  |  |  | 9.009% |  | 740903.364 |  | 1500
28 | TRANSPORTATION BILLS | 520 | 1428.6092 | 742876.7816 | [5 empty] | 0 |  | 0
29 | Firm Transport: 1-300 | 1.5483 | 412985.4803 | 639425.4192 |  | 8.187% |  | 469066.6797 |  |  | 0.1293 | 60650.3217
30 | Firm Transport: 301-15000 | 1.0762 | 5249161.7807 | 5649147.9084 |  | 72.33% |  | 5961969.621 |  |  | 0.0899 | 535981.0689
31 | Firm Transport: Over 15000 | 0.8888 | 1712468.096 | 1522041.6437 |  | 19.49% |  | 1945012.0213 |  |  | 0.0742 | 144319.892
32 | CLASS TOTAL (Mcf/month) |  | 7374615.357 | 8553491.7529 |  |  |  | 8376048.322
33
34 | Total Revenue |  |  | 94943183.5959 | 100% |  | 8223977.5463 | 34310391.8623 | 2163944.9067
35
36
37 | [8 empty] | KY Revenue Requirement |  | 8223977.5463 | 8223627.504 | -350.0423
0
Notes: Due to the rate design from the latest case we are allcoating 3% less of the increase to G-1 Res and 3% more to G-1 Non-Res.

## Exhibit J
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORECASTED ACTIVITY
AS OF OCTOBER 2024 THROUGH SEPTEMBER 2025
CUSTOMERS & VOLUMES
Line
Number | Tariff | Description |  | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Total
Customers
1 | G-1 | Residential | Fiscal 2025 Bud | 158138.0379 | 159842.5974 | 160765.194 | 162082.7616 | 161434.4505 | 162231.3745 | 160646.5032 | 161244.9442 | 159740.8625 | 158446.2351 | 158230.7963 | 157115.7012 | 1919919.4585
2 | G-1 | Commercial Firm | Fiscal 2025 Bud | 17919.1742 | 18287.3695 | 18453.2597 | 18973.1838 | 18825.5011 | 18929.6882 | 18776.9479 | 18712.2102 | 18345.0265 | 18015.2692 | 17956.6007 | 17834.2061 | 221028.437
3 | G-1 | Public Authority | Fiscal 2025 Bud | 1484.5115 | 1500.3042 | 1492.4079 | 1512.1487 | 1493.3949 | 1510.1746 | 1490.4338 | 1501.2913 | 1494.382 | 1470.693 | 1473.6541 | 1476.6152 | 17900.0112
4 | G-1 | Industrial Firm | Fiscal 2025 Bud | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 221 | 2652
5
6 | G-2 | Commercial Interruptible | Fiscal 2025 Bud | 2 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 2 | 2 | 2 | 2 | 33
7 | G-2 | Industrial Interruptible | Fiscal 2025 Bud | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 72
8 | G-2 | Public Authority Interruptible | Fiscal 2025 Bud | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9
10 | T-3 | Transportation Interruptible | Fiscal 2025 Bud | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 70 | 840
11 | T-4 | Transportation Firm | Fiscal 2025 Bud | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 1500
12 |  |  |  | 177965.7237 | 180055.2712 | 181135.8616 | 182993.0942 | 182178.3465 | 183097.2373 | 181338.8849 | 181884.4457 | 180004.2709 | 178356.1972 | 178085.0511 | 176850.5225 | 2163944.9067
13
14 |  |  | Volumes
15
16 | G-1 | Residential | Fiscal 2025 Bud | 195076.2253 | 743703.0475 | 1428642.6187 | 2053284.1516 | 2025528.741 | 1579743.5502 | 1004254.8628 | 420673.6262 | 194193.9383 | 160468.3721 | 141886.2205 | 159467.2863 | 10106922.6406
17 | G-1 | Commercial Firm | Fiscal 2025 Bud | 246809.7588 | 395027.8918 | 677860.4112 | 1047528.2328 | 972450.1531 | 761329.3963 | 495580.3469 | 241565.9897 | 170004.3605 | 155241.0104 | 137095.3016 | 200763.6157 | 5501256.4688
18 | G-1 | Public Authority | Fiscal 2025 Bud | 35429.3383 | 69666.9838 | 116721.8691 | 167667.2762 | 160649.1951 | 129687.8992 | 87366.6999 | 48889.5086 | 28513.3739 | 21744.8543 | 20291.4899 | 24900.4243 | 911528.9126
19 | G-1 | Industrial Firm | Fiscal 2025 Bud | 23586.0867 | 44826.5997 | 72965.4115 | 123090.0918 | 117304.5491 | 73144.0536 | 61448.902 | 25849.9044 | 22760.2787 | 15890.3847 | 21628.4976 | 19794.4505 | 622289.2103
20
21 | G-2 | Commercial Interruptible | Fiscal 2025 Bud | 44.3509 | 214.1754 | 1173.2776 | 1673.1304 | 1603.1723 | 1774.5511 | 1005.7432 | 625.054 | 44.7522 | 19.0648 | 28.6976 | 122.4164 | 8328.3859
22 | G-2 | Industrial Interruptible | Fiscal 2025 Bud | 11629.783 | 14848.722 | 22612.802 | 21705.793 | 19061.686 | 15507.082 | 13559.084 | 32460.254 | 7339.06 | 8916.494 | 10097.01 | 12797.756 | 190535.526
23 | G-2 | Public Authority Interruptible | Fiscal 2025 Bud | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24
25 | T-3 | Transportation Interruptible | Fiscal 2025 Bud | 652698.502 | 742351.387 | 761912.736 | 763787.759 | 817082.357 | 738316.267 | 812369.303 | 701600.729 | 733475.751 | 677436.514 | 639155.522 | 553295.569 | 8593482.396
26 | T-4 | Transportation Firm | Fiscal 2025 Bud | 592010.687 | 692613.795 | 749467.461 | 777027.596 | 878313.596 | 758121.323 | 805954.565 | 688123.96 | 646271.893 | 596393.414 | 587574.49 | 604175.542 | 8376048.322
27 |  |  |  | 1757284.732 | 2703252.6022 | 3831356.5872 | 4955764.0308 | 4991993.4496 | 4057624.1225 | 3281539.5069 | 2159789.0258 | 1802603.4076 | 1636110.1083 | 1557757.2293 | 1575317.0602 | 34310391.8623
Notes:

## Exhibit K-1
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORCASTED ACTIVITY
2023 PROJECT DETAILS
|  | No. of | Installation |  |  | Cost of Removal |  |  | Retirements
Projects | Project Description | services | Main | Services | Meters | Main | Services | Meters | Main | Services | Meters
PRP.2636.N Cherry St Greenville | Replace 146' of 2" Mill Wrap Bare Joint, 5212' of 2" Bare Stl, 778' of Fusion Bond Epoxy, 88' of 2" Unknown coating, 736' of 2" Mill Wrap 407' of 3" Bare, 200'of 2" Epoxy, 15' of 2" PE, 498' of 4" Bare Stl, Install 8,080' of 2" HDPE 130 services. | 130 | 722565.25 |  |  | 38029.75
| Contractor |  |  | 419900 |  |  | 22100
| Material |  |  | 52000 | 19892.6
| Overhead |  |  | 103959.57 | 4382.3398 |  | 4868.63
PRP.2636.W Campbell St | Replace 299' of 2" Steel unknown coating, 57' of 1" Bare Steel, 648' of 4" Epoxy, 135' of 4" unknown coating, 50' of 3" Mill Wrap, 2,770' of 4" Bare Steel , 245' of Mill Wrap Bare joint, 554' of 2" painted, 211' of 6" Mill Wrap, 550' of4" Mill Wrap, 14' of 3" Mill Wrap Bare joint, 312' of3" Bare Steel, 271' of 2" Epoxy, 486' of 2" Fusion Bond Epoxy, 3' of 2" PE, 103' of 1.25" Bare Steel, 1,224' of 2" Bare Steel, 102' of 6" Mill Wrap Bare joint, 91' of 6" unkown coating. Install 4,244' of 2" and 2,768' of 4" HDPE. 65 services | 65 | 747260.5 |  |  | 39329.5
| Contractor |  |  | 209950 |  |  | 11050
| Material |  |  | 26000 | 9946.3
| Overhead |  |  | 51979.785 | 2191.1699 |  | 2434.315
PRP.2636.Oak St | Replace 201' of 1.25" Steel unknown coating, 427' of 2" Steel unknown coating, 1,405' of 2" Bare Steel, 123' of 4" Mill Wrap,277' of Mill Wrap, 1,225' of 3" Bare Steel, 197' of 2" Fusion Bond Epoxy, 1,428' of 4" Bare Steel, 31' of 4" PE, Install 3,887' of 2" and 1,428' of 4" HDPE. 62 services | 62 | 570083.6 |  |  | 30004.4
| Contractor |  |  | 200260 |  |  | 10540
| Material |  |  | 24800 | 9487.24
| Overhead |  |  | 49580.718 | 2090.039 |  | 2321.962
PRP.2636.Maple Dr | Replace 201' of 4" Steel unknown coating, 589' of 3" Bare Steel, 235' of 2" Steel unknown coating, 359' of 3" Painted, 71' of 4" Mill Wrap, 451' of 4" Bare Steel, 101' of 2" PE, Install 1,384' of 2" and 672' of 4" HDPE. 23 services | 23 | 218909.45 |  |  | 11521.55
| Contractor |  |  | 74290 |  |  | 3910
| Material |  |  | 9200 | 3519.46
| Overhead |  |  | 18392.847 | 775.337 |  | 861.373
PRP.W Depot St | Replace 125' of 2" Steel unknown coating, 269' of unknown diameter and unknown coating pipe, 276' of 4" Mill Wrap, 204' of 4" Painted, 65' of 2" Epoxy, 604' of 4" Bare, 909' of 2" Bare, Install 1,581' of 2" and 871' of 4" HDPE, 33 services. | 33 | 272399.2 |  |  | 14336.8
| Contractor |  |  | 106590 |  |  | 5610
| Material |  |  | 13200 | 5049.66
| Overhead |  |  | 26389.737 | 1112.4401 |  | 1235.883
PRP.2635.Maple Street | Replace 1268' of 2" Epoxy,527' of 1.25 Bare Stl., 63' of 3" Epoxy, 218' of 2" N/A Plastic, 108' of 1" Bare Stl.,2491' of 2" Bare Stl., 1684' of 3" Bare Stl., 130' of 1.25 PE, Install 5359' of 2" HDPE 110 services | 110 | 929700.4 |  |  | 48931.6
| Contractor |  |  | 355300 |  |  | 18700
| Material |  |  | 44000 | 16832.2
| Overhead |  |  | 87965.79 | 3708.1337 |  | 4119.61
PRP.2635.E Keigan St | Replace 5,570' of 2" Mill Wrap Bare Joint, 1,044' of 4" Mill Wrap Bare Joint, 201' of 2" Steel unknown coating, 76' of 2" Painted, Install 5,847' of 2" and 1044' of 4" HDPE. 95 services | 95 | 686640.05 |  |  | 36138.95
| Contractor |  |  | 306850 |  |  | 16150
| Material |  |  | 38000 | 14536.9
| Overhead |  |  | 75970.455 | 3202.4791 |  | 3557.845
Adyl.2635.St Charles Replacement | Replace 612' of 1.25" Mill Wrap, 305' of 2" PE, 449' of 2" Aldyl-A and 8,718' of 1.25" Adlyl-A, Install 10,085' of 2" HDPE. 90 Services | 90 | 1134333.25 |  |  | 59701.75
| Contractor |  |  | 290700 |  |  | 15300
| Material |  |  | 36000 | 13771.8
| Overhead |  |  | 71972.01 | 3033.9275 |  | 3370.59
PRP.2637.Washington St | Replace 219' of 1.25" Fusion Bond Epoxy, 392' of 2" PE, 111' of 2" Steel unknown coating, 411' of 2" Mill Wrap, 611' of 2" Bare Steel, 1,037' of Mill Wrap Bare joint, 4,430' of 4" bare Steel, Install 2,782' of 2" and 4,430' of 4" HDPE. 68 services | 68 | 668058.05 |  |  | 35160.95
| Contractor |  |  | 219640 |  |  | 11560
| Material |  |  | 27200 | 10405.36
| Overhead |  |  | 54378.852 | 2292.3008 |  | 2546.668
PRP.2637.Hilldale Dr | Replace 66' of 3" Mill Wrap Bare joint, 216' of 2" PE, 703' of 3" Mill Wrap, 245' of 2" Bare Steel, 3,236' of 2" Mill Wrap Bare joint, 1,334' of 2" Mill Wrap, 40' of 2" Fusion Bond Epoxy, Install 6,116' of 2" HDPE. 80 services | 80 | 501115.5 |  |  | 26374.5
| Contractor |  |  | 258400 |  |  | 13600
| Material |  |  | 32000 | 12241.6
| Overhead |  |  | 63975.12 | 2696.8245 |  | 2996.08
PRP.2637.Sunset Ave | Replace 99' of 2" Steel unknown coating, 20' of 6" Mill Wrap, 100' of 2" Bare Steel, 2,515' of 2" Mill Wrap, 1' of 2" Epoxy, 1' of 3" Epoxy, 3,560' of 6" Mill Wrap Bare joint, 931' of 3" Mill Wrap Bare joint, Install 3,668' of 2" and 3,560' of 6" HDPE. 92 services | 92 | 704071.6 |  |  | 37056.4
| Contractor |  |  | 297160 |  |  | 15640
| Material |  |  | 36800 | 14077.84
| Overhead |  |  | 73571.388 | 3101.3482 |  | 3445.492
PRP.2637.Lone Oak 2 | Replace 1,260' of 4" Steel unknown coating, 479' of 2" PE, 238' of 2" Steel unknown coating, 106' of 8" Mill Wrap, 1,928' of 8" Mill Wrap Bare joint, 1,711' of 2" Mill Wrap Bare joint, 171' of 2" Mill Wrap, 73' of Fusion Bond Epoxy, Install 2,672' of 2" , 1,260' of 4" and 2,032' of 8" HDPE 30 services | 30 | 683340.7 |  |  | 35965.3
| Contractor |  |  | 96900 |  |  | 5100
| Material |  |  | 12000 | 4590.6
| Overhead |  |  | 23990.67 | 1011.3092 |  | 1123.53
PRP.2637.North 8th and 11th St | Replace 56' of 2" Steel unknown coating, 1,365' of 2" Mill Wrap Bare joint, 8' of 4" Mill Wrap, 1,465' of 2" Mill Wrap, 314' of 2" Fusion Bond Epoxy, 3,759' of 4" Mill Wrap Bare joint, 513' of 2" PE, 100' of 2" Epoxy, 18' of 4" Epoxy, Install 5,719' of 2" and 1,880' of 4" HDPE. 62 services | 62 | 601737.6 |  |  | 31670.4
| Contractor |  |  | 200260 |  |  | 10540
| Material |  |  | 24800 | 9487.24
| Overhead |  |  | 49580.718 | 2090.039 |  | 2321.962
PRP.2734.US 31W | Replace 978' of 1.25" Fusion Bond Epoxy, 12' of 2" Fusion Bond Epoxy, 462' of 4" Mill Wrap, 19' of 4" PE, 254' of 2" Epoxy, 108' of 1.25" Epoxy, 1,889' of 4" Bare Steel, 490' of 491' of 2" Mill Wrap, 778' of 2" Bare Steel, 30' of 2" PE, with 2,513' of 2" and 1,895' of 4" HDPE. 37 services | 37 | 578739.05 |  |  | 30459.95
| Contractor |  |  | 119510 |  |  | 6290
| Material |  |  | 14800 | 5661.74
| Overhead |  |  | 29588.493 | 1247.2813 |  | 1385.687
PRP.2734.Schweizer Rd | Replace 25,500' of 8" high pressure Bare steel iInstall 25,500' of Fusion Bond Epoxy Steel, project will also includ a new Purchase Station , check meter , YZ odorzer, all electronics and a expanded station lot. | 20 | 8579348.35 |  |  | 451544.65
| Contractor |  |  | 64600 |  |  | 3400
| Material |  |  | 8000 | 3060.4
| Overhead |  |  | 15993.78 | 674.2061 |  | 749.02
Adyl.2736.Lincoln Ave | Replace 2,599' of 2" Adyl A, 3,407' of 2" PE, 1,002' of 1" Adly A, Install 7,008' of 2" HDPE. 53 Services | 53 | 698506.5 |  |  | 36763.5
| Contractor |  |  | 171190 |  |  | 9010
| Material |  |  | 21200 | 8110.06
| Overhead |  |  | 42383.517 | 1786.6462 |  | 1984.903
Adyl. 2736.Cunningham Ave | Replace 3,573' of 2" Adyl A, 5' of 2" PE, 100' of unknown Plastic, 2,399' of 1" Adyl A 5' od 1" PE, Install 6,100' of 2" HDPE. 80 services | 80 | 475578.55 |  |  | 25030.45
| Contractor |  |  | 258400 |  |  | 13600
| Material |  |  | 32000 | 12241.6
| Overhead |  |  | 63975.12 | 2696.8245 |  | 2996.08
PRP.2738.Covington Ave | Replace 105' of 2" Epoxy, 1,210' of 2" Mill Wrap, 8' of 2" Stl., unknown coating, 2,072' of 4" painted, 1,514' of 2" Painted, 210' of 2" Mill Wrap Bare joint, 303' of 1.25" painted, 63' of 1.25" Fusion Bond Epoxy, 345' of 2" Hot Tar, 892' of Fusion Bond Epoxy, Install 6,722' of 2" HDPE 98 services. | 98 | 672708.3 |  |  | 35405.7
| Contractor |  |  | 316540 |  |  | 16660
| Material |  |  | 39200 | 14995.96
| Overhead |  |  | 78369.522 | 3303.61 |  | 3670.198
PRP.2737.Logan Ave | Replace 2,719' of 2" Mill Wrap Bare joint, 2,093' of 4" Mill Wrap Bare joint, 279' of 2" Bare Stl., 33' of 2" PE, Install 3,031' of 2" and 2,093' of 4" HDPE HDPE 92 services. | 92 | 656032 |  |  | 34528
| Contractor |  |  | 297160 |  |  | 15640
| Material |  |  | 36800 | 14077.84
| Overhead |  |  | 73571.388 | 3101.3482 |  | 3445.492
PRP.2737.Portman St | Replace 546' of 2" Bare Stl., 5,215' of Mill Wrap Bare Joint, 489' of 2" Stl unknown coating, 1,132' of 2" Mill Wrap, 567' of 2" Mill Wrap Bare Joint, 100' of 2" PE, Install 2,301' of 2" and 3,817' of HDPE, 103 services. | 103 | 737557.2 |  |  | 38818.8
| Contractor |  |  | 332690 |  |  | 17510
| Material |  |  | 41200 | 15761.06
| Overhead |  |  | 82367.967 | 3472.1615 |  | 3857.453
PRP.2737.Locust St | Replace 1,557'of 2" Bare Stl., 141' of 2" Hot Tar,324' of 2" Mill Wrap, 803' of Fusion Bond Epoxy, 970' of 4" Bare Stl.,Install 2,919' of 2" and 851' of 4" HDPE 88 services | 88 | 436750.15 |  |  | 22986.85
| Contractor |  |  | 284240 |  |  | 14960
| Material |  |  | 35200 | 13465.76
| Overhead |  |  | 70372.632 | 2966.5069 |  | 3295.688
PRP.2737.Orchard St | Replace 809' of 2" Unknown coating, 2,252' of 2" Bare Stl., 1,382' of 2" Mill Wrap , 227' of 2" Hot Tar, Install 4,670' of 2" HDPE 98 services | 98 | 504606.75 |  |  | 26558.25
| Contractor |  |  | 316540 |  |  | 16660
| Material |  |  | 39200 | 14995.96
| Overhead |  |  | 78369.522 | 3303.61 |  | 3670.198
PRP.2738.Mulberry St | Replace 537' of 4" Epoxy, 1,949' of 6" Bare Stl., 151' of 2" Stl. Unknown coating, 67' of 4" Mill Wrap, 1,643' of of 2" Bare Stl., 72' of 2" Fusion Bond Epoxy, 602' of Mill Wrap Bare Joint, 384' of 2" Mill Wrap, 508' of 2" Painted, 361' of 2" PE, 159' of 2" Epoxy, Install 4,678' of 2" and 1,754' of 4" HDPE 90 services. | 90 | 657105.5 |  |  | 34584.5
| Contractor |  |  | 290700 |  |  | 15300
| Material |  |  | 36000 | 13771.8
| Overhead |  |  | 71972.01 | 3033.9275 |  | 3370.59
|  |  | 0 |  |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
| Total specific budgeted projects & bare steel functional |  | 22437147.5 | 7526041.611 | 317254.7899 | 1180902.5 | 352459.249 | 0 | 0 | 0 | 0
| Non specfic bare steel functional |  |  | 55223.2422 | 2327.8955 | 0 | 2586.2124
| Total budgeted 2023 projects |  | 22437147.5 | 7581264.8532 | 319582.6854 | 1180902.5 | 355045.4614 | 0 | 3708967.7164 | 2133914.1728 | 126158.6658
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Actual 2023 Project Costs |  | 22250566.67 | 8452979.6 |  | 894814.97 | 276854.27 |  | 932977.76 | 3624933.43

## Exhibit K-2
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORCASTED ACTIVITY
2024 PROJECT DETAILS
|  | No. of | Installation |  |  | Cost of Removal |  |  | Retirements
Projects | Project Description | services | Main | Services | Meters | Main | Services | Meters | Main | Services | Meters
PRP.2634.Bell Dr | Replace 226' of 4" Steel unknown coating , 428' of 4" Mill Wrap, 1,084' of 2" Mill Wrap, 1,356' of 4" Painted, 918' of 3" Painted with 4,426' of 2" HDPE 59 services | 59 | 450778.8 |  |  | 23725.2
| Contractor |  |  | 200098.5 |  |  | 10531.5
| Material |  |  | 37170 | 9028.18
| Overhead |  |  | 53670.1347 | 2042.1743 |  | 2382.2253
PRP.2634.Hall St | Replace 467' of 1.25" PE, 131' of 2" PE, 183' of 4" Unknown coating, 397' of 1.25" Mill Wrap, 3,034' of 4" Bare Stl., 17' of 4" Epoxy, 728' of 4" Mill Wrap, 238' of 2" Fusion Bond Epoxy, 132' of 4" Painted, 205' of 2" Unknown coating, 1,666' of 6" Bare Stl., 1,253' of 2" Mill Wrap, 79' of4" Fusion Bond Epoxy with 2,823' of 2", 4,041' of 4" and 1,666' of 6" HDPE. 132 Services | 132 | 853465.75 |  |  | 44919.25
| Contractor |  |  | 447678 |  |  | 23562
| Material |  |  | 83160 | 20198.64
| Overhead |  |  | 120075.5556 | 4568.9324 |  | 5329.7244
PRP.2636.Omega St | Replace 251' of 2" Fusion Bond Epoxy, 17' of 2" Mill Wrap, 14' of 8" HDPE, 2,490' of 6" Mill Wrap Bare Joint with 281' of 2" and 2,490' of 8" HDPE. 51 Services | 51 | 514192.25 |  |  | 27062.75
| Contractor |  |  | 172966.5 |  |  | 9103.5
| Material |  |  | 32130 | 7804.02
| Overhead |  |  | 46392.8283 | 1765.2693 |  | 2059.2117
PRP.2636.E 9th St | Replace 243' of 3" Hot tar, 23' of 3" mill Wrap, 79' of 3" Bare Steel, and 64' of 2" Mill Wrap with 408' of 2" HDPE. 2 Services | 2 | 225419.8 |  |  | 11864.2
| Contractor |  |  | 6783 |  |  | 357
| Material |  |  | 1260 | 306.04
| Overhead |  |  | 1819.3266 | 69.2262 |  | 80.7534
PRP.2636.Walnut St (Cloverport) | Replace 466' of 2" Bare Steel,188' of 6" Hot Tar, and 570' of 2" Hot Tar, 442' of 4" Epoxy, 26' of 6" Epoxy with 2324' of 2" HDPE. 16 Services | 16 | 319152.5 |  |  | 16797.5
| Contractor |  |  | 54264 |  |  | 2856
| Material |  |  | 10080 | 2448.32
| Overhead |  |  | 14554.6128 | 553.81 |  | 646.0272
PRP.2636.Davies St (Hawesville) | Replace 401' of 2" Painted Steel with 401' of 2" HDPE. 5 Services | 5 | 62681 |  |  | 3299
| Contractor |  |  | 16957.5 |  |  | 892.5
| Material |  |  | 3150 | 765.1
| Overhead |  |  | 4548.3165 | 173.0656 |  | 201.8835
PRP.2636.KY 171 (Greenville) | Replace 3,266' of 4" Bare Steel with 3,266' of 4" HPD. 1 service | 1 | 437455.05 |  |  | 23023.95
| Contractor |  |  | 3391.5 |  |  | 178.5
| Material |  |  | 630 | 153.02
| Overhead |  |  | 909.6633 | 34.6131 |  | 40.3767
PRP.2636.KY 1473 Phase 2 (Greenville) | Replace 3,926' of 4" Bare Steel with 3,926' of 4" HDPE. 9 Services | 9 | 646114 |  |  | 34006
| Contractor |  |  | 30523.5 |  |  | 1606.5
| Material |  |  | 5670 | 1377.18
| Overhead |  |  | 8186.9697 | 311.5181 |  | 363.3903
PRP.2736.Greenville Rd | Replace 3,019' of 6" Bare Stl. With 3,019' of 2" PE 6 services | 6 | 371536.45 |  |  | 19554.55
| Contractor |  |  | 20349 |  |  | 1071
| Material |  |  | 3780 | 918.12
| Overhead |  |  | 5457.9798 | 207.6787 |  | 242.2602
PRP.2736.Means Ave | Replace97' of 4" MillWrap Bare Joint, 301' of 4" Painted, 139' of 2" Bare Steel, 1,410' of 4" Bare Steel, with 139' of 2" and 1,808' of 4" HDPE. 35 Services | 35 | 443140.8 |  |  | 23323.2
| Contractor |  |  | 118702.5 |  |  | 6247.5
| Material |  |  | 22050 | 5355.7
| Overhead |  |  | 31838.2155 | 1211.4593 |  | 1413.1845
PRP.2736.E 2nd St | Replace 80' of 2 Bare, 176' of 1.25" Adyl A, 1' of 2" Steel unknown coating, 8' of 2" Epoxy, 1,029' of 4" Bare Steel. 11 Services | 11 | 290640.15 |  |  | 15296.85
| Contractor |  |  | 37306.5 |  |  | 1963.5
| Material |  |  | 6930 | 1683.22
| Overhead |  |  | 10006.2963 | 380.7444 |  | 444.1437
PRP.2736.Church St Crofton | Replace 54' of 2" Epoxy, 889' of 1.50" Bare Stl., 330' of 2" Mill Wrap Bare Joint, 1,765' of 2" Painted Stl., 110' of 1.25" Bare Stl., 99' of 2" Fusion Bond Epoxy, 101' of 2" Stl unknown coating, 1,744' of 2" Bare Stl., with 5,093' of 2" HDPE. 66 services | 66 | 542901.25 |  |  | 28573.75
| Contractor |  |  | 223839 |  |  | 11781
| Material |  |  | 41580 | 10099.32
| Overhead |  |  | 60037.7778 | 2284.4662 |  | 2664.8622
PRP.2736.Railroad St Crofton | Replace 38' of 2" Epoxy, 547' of 1.50" Bare Stl.,433' of 2" Mill Wrap Bare Joint, 2,234' of 2" Bare Stl., 185' of 1.25" Bare Stl., 99' of 2" Stl. Unknown coating, 1,531' of 2" Mill Wrap with 5,066' of 2" HDPE. 38 services | 38 | 499684.8 |  |  | 26299.2
| Contractor |  |  | 128877 |  |  | 6783
| Material |  |  | 23940 | 5814.76
| Overhead |  |  | 34567.2054 | 1315.2987 |  | 1534.3146
PRP.2637.Hayes Ave | Replace 963' of 2" Mill Wrap, 1,094' of 1.25" Mill Wrap, 5,412' of 2" Mill Wrap Bare Joint, with 7,469' of 2" HDPE. 103 services | 103 | 689350.4 |  |  | 36281.6
| Contractor |  |  | 349324.5 |  |  | 18385.5
| Material |  |  | 64890 | 15761.06
| Overhead |  |  | 93695.3199 | 3565.1518 |  | 4158.8001
PRP.2637.Bethel St | Replace354' of 2" Fusion Bond Epoxy, 224' of 2" Stl., unknown coating, 2,946' of 2" Mill Wrap, 3,232' of 2" Mill Wrap Bare Joint with 4,159' of 2" and 1,784' of 4" HDPE. 50 services | 50 | 569646.6 |  |  | 29981.4
| Contractor |  |  | 169575 |  |  | 8925
| Material |  |  | 31500 | 7651
| Overhead |  |  | 45483.165 | 1730.6562 |  | 2018.835
PRP.2637.Cardinal Lane | Replace259' of 3" Bare Stl., 5,249' of 6" Mill Wrap Bare Joint, 105' of 2" Stl., unknown coating, 1,076' of 2" Mill Wrap Bare Joint, 1,239' of 2" Mill Wrap with 2,679' of 2" and 5,249' of 6" HDPE. 108 services | 108 | 791176.15 |  |  | 41640.85
| Contractor |  |  | 366282 |  |  | 19278
| Material |  |  | 68040 | 16526.16
| Overhead |  |  | 98243.6364 | 3738.2174 |  | 4360.6836
PRP.2637.North 8th and 11th St | Replace 56' of 2" Steel unknown coating, 1,365' of 2" Mill Wrap Bare joint, 8' of 4" Mill Wrap, 1,465' of 2" Mill Wrap, 314' of 2" Fusion Bond Epoxy, 3,759' of 4" Mill Wrap Bare joint, 513' of 2" PE, 100' of 2" Epoxy, 18' of 4" Epoxy, with 5,719' of 2" and 1,880' of 4" HDPE. 62 services | 62 | 777215.9 |  |  | 40906.1
| Contractor |  |  | 210273 |  |  | 11067
| Material |  |  | 39060 | 9487.24
| Overhead |  |  | 56399.1246 | 2146.0137 |  | 2503.3554
PRP.2734.N Sunrise BG | Replace 2,237' of 2" Bare Stl., 7' of 4" Mill Wrap, 6' of 1.25" PE, 168 of 2' HDPE, 457' of 2" Mill Wrap, 37' of 2" PE, 577' of 3" Bare Stl., with HDPE 48 services. | 48 | 421563.45 |  |  | 22187.55
| Contractor |  |  | 162792 |  |  | 8568
| Material |  |  | 30240 | 7344.96
| Overhead |  |  | 43663.8384 | 1661.43 |  | 1938.0816
PRP.2734.Kenton St BG | Replace 167' of 2" Mill Wrap, 5' of 4" Epoxy, 176' of 1.25" Fusion Bond Epoxy, 1,292' of 4" Bare Stl., with 1,203' of 2" and 437' of 4" HDPE. 45 services | 45 | 305952.25 |  |  | 16102.75
| Contractor |  |  | 152617.5 |  |  | 8032.5
| Material |  |  | 28350 | 6885.9
| Overhead |  |  | 40934.8485 | 1557.5906 |  | 1816.9515
PRP.2734.Johnson Dr BG | Replace 686' of 2" Bare Stl., 144' of 2" painted, 138' of 4" Painted, 661' of 3" bare Stl., 18' of 4" Epoxy 26 services | 26 | 353723 |  |  | 18617
| Contractor |  |  | 88179 |  |  | 4641
| Material |  |  | 16380 | 3978.52
| Overhead |  |  | 23651.2458 | 899.9412 |  | 1049.7942
PRP.2734.Pelham St Franklin | Replace 118' of 2" Bare Stl., 2' of 4" Mill Wrap, 101' of 2" Unknown coating, 280' of 4" Bare Stl., 203' of 2" Mill Wrap, 220' of 2" Painted with 526' of 2" amd 280' of 4" HDPE. 9 services | 9 | 195890.95 |  |  | 10310.05
| Contractor |  |  | 30523.5 |  |  | 1606.5
| Material |  |  | 5670 | 1377.18
| Overhead |  |  | 8186.9697 | 311.5181 |  | 363.3903
PRP.2734.Hopkinsville St | Replace 63' of 2" Mill Wrap Bare Joint, 18' of 2" Mill Wrap, 237' of 2" Bare Steel, 47' of 3" Mill Wrap with 365' of 2" HDPE. 5 Services | 5 | 86166.9 |  |  | 4535.1
| Contractor |  |  | 16957.5 |  |  | 892.5
| Material |  |  | 3150 | 765.1
| Overhead |  |  | 4548.3165 | 173.0656 |  | 201.8835
PRP.2735.E Main St (Glasgow) | Replace 340' of 2" Bare Stl., 38' of 2" HDPE with 378' of 2" HDPE. 5 services | 5 | 136964.35 |  |  | 7208.65
| Contractor |  |  | 16957.5 |  |  | 892.5
| Material |  |  | 3150 | 765.1
| Overhead |  |  | 4548.3165 | 173.0656 |  | 201.8835
PRP.2735. W Union St MUN (Munfordville) | Replace150' of 1.25" Bare Stl., 98' of 1.25" Mill Wrap, 1,453' of 2" Bare Stl., 422' of 2" Mill Wrap with 2,124' of 2" HDPE. 22 services | 22 | 315121.65 |  |  | 16585.35
| Contractor |  |  | 74613 |  |  | 3927
| Material |  |  | 13860 | 3366.44
| Overhead |  |  | 20012.5926 | 761.4887 |  | 888.2874
PRP.2735. Cherry St HC (Horse Cave) | Replace 465' of 1.25" Mill Wrap, 504' of 2" Bare Stl., 141' of 4" painted with 868' of 2" HDPE. 7 services | 7 | 194093.55 |  |  | 10215.45
| Contractor |  |  | 23740.5 |  |  | 1249.5
| Material |  |  | 4410 | 1071.14
| Overhead |  |  | 6367.6431 | 242.2919 |  | 282.6369
PRP.2735.Hogan St PC (Park City) | Replace 30' of 3/4" PE, 372' of 2" Bare Stl., 134' of 2" Mill Wrap, 116' of 2" Epoxy, 1' of 2" Fusion Bond Epoxy, 391' of 2" Stl. unknown coating with 897' of 2" HDPE 14 services | 14 | 152650.75 |  |  | 8034.25
| Contractor |  |  | 47481 |  |  | 2499
| Material |  |  | 8820 | 2142.28
| Overhead |  |  | 12735.2862 | 484.5837 |  | 565.2738
PRP.2738.Shawnee Dr (Campbellsville) | Replace566' of 2" Bare Stl., 117' of 2" painted, 72' of 2" unknown coating, 2,978' of 3" Mill Wrap Bare joint, 973' of 2" Mill Wrap, 100' of 2" Epoxy with 4,807' of 2" HDPE. 74 services | 74 | 472711.45 |  |  | 24879.55
| Contractor |  |  | 250971 |  |  | 13209
| Material |  |  | 46620 | 11323.48
| Overhead |  |  | 67315.0842 | 2561.3712 |  | 2987.8758
PRP.2738.W Court St ( Greensburg) | Replace 53' of 4" Mill Wrap, 105' of 2" painted, 106' of 2" Bare Stl., 116' of 2" Stl., unknown coating, with 379' of 2" HDPE. 5 services | 5 | 203367.45 |  |  | 10703.55
| Contractor |  |  | 16957.5 |  |  | 892.5
| Material |  |  | 3150 | 765.1
| Overhead |  |  | 4548.3165 | 173.0656 |  | 201.8835
PRP.2738.E Grundy St | Replace 100' of 2" unknown coating, 320' of 2" Mill Wrap Bare Joint, 196' of 2" Bare Stl, 105' of 2" Fusion Bond Epoxy, 885' of 2" Mill Wrap, 48' of 2" Hot Tar, 1006' of 2" Painted, 2,335' of 4" Painted, with 5,116' of 2" HDPE, 76 services. | 76 | 592426.65 |  |  | 31180.35
| Contractor |  |  | 257754 |  |  | 13566
| Material |  |  | 47880 | 11629.52
| Overhead |  |  | 69134.4108 | 2630.5974 |  | 3068.6292
PRP.2738.US 528 | Replace 2,175' of2" Painted, 379' of 2" Mill Wrap, 1,168' of 4" Painted, 898' of 2" Epoxy, 1,181' of 4" Mill Wrap, 171' of2" Bare Stl., 10' of 2" Stl. Unknown coating, 224' of 2" Hot Tar, 320' of 2" Mill Wrap Bare joint with 5,304' of 2" and 1,220' of 6" HDPE 162 services. | 162 | 1229406.4 |  |  | 64705.6
| Contractor |  |  | 549423 |  |  | 28917
| Material |  |  | 102060 | 24789.24
| Overhead |  |  | 147365.4546 | 5607.3261 |  | 6541.0254
PRP.2737.Lancaster to Stanford | Project is for FY 2024 Landrights and Suvey only actual construction to begin FY 2025 a revision will be done for the construction. Replacing approximately 60,500' of 4" bare Steel with 8" FBE Steel. | 0 | 2009472.3 |  |  | 105761.7
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
PRP.2737.Portman St | Replace 546' of 2" Bare Stl., 5,215' of Mill Wrap Bare Joint, 489' of 2" Stl unknown coating, 1,132' of 2" Mill Wrap, 567' of 2" Mill Wrap Bare Joint, 100' of 2" PE with 2,301' of 2" and 3,817' of 4" HDPE, 103 services. | 103 | 754341.8 |  |  | 39702.2
| Contractor |  |  | 349324.5 |  |  | 18385.5
| Material |  |  | 64890 | 15761.06
| Overhead |  |  | 93695.3199 | 3565.1518 |  | 4158.8001
PRP.2737.Logan Ave | Replace 2,719' of 2" Mill Wrap Bare joint, 2,093' of 4" Mill Wrap Bare joint, 279' of 2" Bare Stl., 33' of 2" PE with 3,031' of 2" and 2,093' of 4" HDPE. 92 services. | 92 | 657881.65 |  |  | 34625.35
| Contractor |  |  | 312018 |  |  | 16422
| Material |  |  | 57960 | 14077.84
| Overhead |  |  | 83689.0236 | 3184.4074 |  | 3714.6564
PRP.2737.Locust St | Replace 1,557'of 2" Bare Stl., 141' of 2" Hot Tar,324' of 2" Mill Wrap, 803' of Fusion Bond Epoxy, 970' of 4" Bare Stl., with 2,919' of 2" and 851' of 4" HDPE 88 services | 88 | 429637.5 |  |  | 22612.5
| Contractor |  |  | 298452 |  |  | 15708
| Material |  |  | 55440 | 13465.76
| Overhead |  |  | 80050.3704 | 3045.9549 |  | 3553.1496
PRP.2737.W Walnut RR Crossing | Replace 345' of 2" Bare Steel, and 254' of 4" Bare Steel with 599' of 4" HDPE. This will be a Steel Cased Bore. 1 Service | 1 | 298989.7 |  |  | 15736.3
| Contractor |  |  | 3391.5 |  |  | 178.5
| Material |  |  | 630 | 153.02
| Overhead |  |  | 909.6633 | 34.6131 |  | 40.3767
PRP.2737.Alton Rd | Replace 3,981' of 2" Bare Stl., 104' of 2" Stl unknown coating, 1,937' of 4" Bare Stl., 1,599' of 3" Bare Stl., with 5,842' of 2" and 1,779' of 4" HDPE 141 services. | 141 | 788716.6 |  |  | 41511.4
| Contractor |  |  | 478201.5 |  |  | 25168.5
| Material |  |  | 88830 | 21575.82
| Overhead |  |  | 128262.5253 | 4880.4505 |  | 5693.1147
| Total specific budgeted projects & bare steel functional |  | 18083630 | 8269560.8541 | 314660.7489 | 951770 | 367056.2259
| Non specfic bare steel functional |  |  | -10150.463 | 16018.2092 | 0 | -4005.2197
| Total budgeted 2024 projects |  | 18083630 | 8259410.3911 | 330678.9581 | 951770 | 363051.0062 |  | 2950290.911 | 2593895.052 | 150003.2174
|  |  |  | 0 | 0 | 0 | 0
Note: Aldyl-A projects removed per Final Order in Case No. 2023-00231
|  |  | 0 | 0 | 0 | 0 | 0

## Exhibit K-3
ATMOS ENERGY CORPORATION
KENTUCKY PIPE REPLACEMENT PROGRAM
SURCHARGE CALCULATION OF FORCASTED ACTIVITY
2025 PROJECT DETAILS
|  | No. of | Installation |  |  | Cost of Removal |  |  | Retirements
Projects | Project Description | services | Main | Services | Meters | Main | Services | Meters | Main | Services | Meters
PRP.2634.Park Ave | Replace, 117' of 4" Fusion Bond Epoxy, 1,849' of 4" Bare Stl., 78' of 2" Unknown coating, 167' of 2" Mill Wrap, 109' of 4" Epoxy, 490' of 4" Mill Wrap, with 247' of 2" and 2,563' of 4" HDPE. | 32 | 454186.45 |  |  | 23904.55 | [5 empty] | 478091 | 0
| Contractor |  |  | 112328 |  |  | 5912
| Material |  |  | 20864 | 5624.96
| Overhead |  |  | 29941.5616 | 1264.491 |  | 1329.0176
PRP.2636.Buckner St | Replace 1,248' of 2" Painted, 30' of 2" Epoxy, 103' of4" unknown coating, 1,218' of 2" Mill Wrap, 40' of 4" Fusion Bond Epoxy, 395' of 4" Epoxy, 461' of 2" Unknown coating, 371' of 4" Mill Wrap, 904' of4" Bare, 1,182' of 4" Painted, with 2,958' of 2" and 2,994' of 4" HDPE. | 92 | 695000.05 |  |  | 36578.95 | [5 empty] | 731579 | 0
| Contractor |  |  | 322943 |  |  | 16997
| Material |  |  | 59984 | 16171.76
| Overhead |  |  | 86081.9896 | 3635.4116 |  | 3820.9256
PRP.2634.Noel Ave | Replace 492' of 4" Bare Stl., 505' of 2" Painted Stl., 283' of 3" Bare Steel, 55' of 1.25" Epoxy , 6' of 2" PE, 78' of 4" Epoxy, 2,169' of 2" Bare Stl., 419' of Fusion Bond Epoxy,209' of Painted, 244' of 2" Unknown coating, 12' of 3" Epoxy, 15' of 4" PE, 5' of 3/4" PE, 475' of 2" Mill Wrap, 181' of 2" Epoxy, with 3,061' of 2" ,and 2,088' of 4" HDPE. | 53 | 591318.95 |  |  | 31122.05 | [5 empty] | 622441 | 0
| Contractor |  |  | 186043.25 |  |  | 9791.75
| Material |  |  | 34556 | 9316.34
| Overhead |  |  | 49590.7114 | 2094.3132 |  | 2201.1854
PRP.2636.Mill St Utica | Replace 1,915' of bare 2" Steel with 3,463' of 2" HDPE. | 10 | 375138.85 |  |  | 19744.15 | [5 empty] | 394883 | 0
| Contractor |  |  | 35102.5 |  |  | 1847.5
| Material |  |  | 6520 | 1757.8
| Overhead |  |  | 9356.738 | 395.1534 |  | 415.318
PRP.2636.Greene St | Replace 382' of 3" Painted Stl., 8' of 4" Painted, 48' of 2" Bare Steel, 818' of 2" Mill Wrap, 136' of 2" Painted Stl., with 1,1,92' of 2" and 8' of 4" HDPE. | 8 | 263703.85 |  |  | 13879.15 | [5 empty] | 277583 | 0
| Contractor |  |  | 28082 |  |  | 1478
| Material |  |  | 5216 | 1406.24
| Overhead |  |  | 7485.3904 | 316.1228 |  | 332.2544
PRP.Everly Brothers Blvd | Replace 602' of 2" Mill Wrap Bare Joint, with 602' of 2" HDPE | 4 | 109721.2 |  |  | 5774.8 | [5 empty] | 115496 | 0
| Contractor |  |  | 14041 |  |  | 739
| Material |  |  | 2608 | 703.12
| Overhead |  |  | 3742.6952 | 158.0614 |  | 166.1272
PRP.2635.E Keigan St | Replace 5,570' of 2" Mill Wrap Bare Joint, 1,044' of 4" Mill Wrap Bare Joint, 201' of 2" Steel unknown coating, 76' of 2" Painted with 7311' of 2" HDPE. | 95 | 748764.35 |  |  | 39408.65 | [5 empty] | 788173 | 0
| Contractor |  |  | 333473.75 |  |  | 17551.25
| Material |  |  | 61940 | 16699.1
| Overhead |  |  | 88889.011 | 3753.9577 |  | 3945.521
PRP.2635.E Hall St | Replace 2' of 2" PE, 3,849' of 4" Mill Wrap Bare Joint, 212' of 2" Fusion Bond Epoxy, 2,182' of 2" Mill Wrap Bare Joint with 2,394' of 2" and 3,849' of 4" HDPE. | 70 | 610983 |  |  | 32157 | [5 empty] | 643140 | 0
| Contractor |  |  | 245717.5 |  |  | 12932.5
| Material |  |  | 45640 | 12304.6
| Overhead |  |  | 65497.166 | 2766.0741 |  | 2907.226
PRP.2635.W Keigan St | Replace 750' of 4" Mill Wrap Bare Joint, 113' of 4" PE, 1,201' of 2" Mill Wrap, 133' of 2" Mill Wrap, 2" Steel unknown Coating 2,256' of 2" Mill Wrap Bare Joint, 199' of 2" Steel unknown coating with 4,444' of 2" and 208' of 4" HDPE. | 45 | 554371.55 |  |  | 29177.45 | [5 empty] | 583549 | 0
| Contractor |  |  | 157961.25 |  |  | 8313.75
| Material |  |  | 29340 | 7910.1
| Overhead |  |  | 42105.321 | 1778.1905 |  | 1868.931
PRP.2635.W Hall St | Replace 750' of 4" Mill Wrap, 105' of 1.25" steel unknown coating, 5' of .75" Fusion Bond Epoxy, 5' of 4" PE, 4,991' of 2" Mill Wrap Bare joint, 318' of 1" Mill Wrap, 2' of 4" Mill Wrap Bare Joint, 200' of 2" Fusion Bond Epoxy, 111' of 2" PE, 2' of .75" PE with 6,225' of 2" HDPE | 45 | 656286.6 |  |  | 34541.4 | [5 empty] | 690828 | 0
| Contractor |  |  | 157961.25 |  |  | 8313.75
| Material |  |  | 29340 | 7910.1
| Overhead |  |  | 42105.321 | 1778.1905 |  | 1868.931
PRP.2637.Goodman Dr | Replace 2,661' of 2" Mil Wrap Bare Joint, 60' of 2" PE, 6' of 2" Steel unknown coating, 503' of 2" Mill Wrapp, 988' of 1.25" Mill Wrap, 108' of 1.25" Steel unknown coating with 4,337' of 2" HDPE. | 150 | 526098.6 |  |  | 27689.4 | [5 empty] | 553788 | 0
| Contractor |  |  | 526537.5 |  |  | 27712.5
| Material |  |  | 97800 | 26367
| Overhead |  |  | 140351.07 | 5927.3016 |  | 6229.77
PRP.2637.Brown St | Replace 644' of 4" Mill Wrap, 111'of 2" Epoxy, 692' of 4" Bare Steel, 798' of 2" Mill Wrap, 3680' of 4" Mill Wrap Bare Joint with 909' of 2" and 4,016' of 4" HDPE. | 42 | 601442.15 |  |  | 31654.85 | [5 empty] | 633097 | 0
| Contractor |  |  | 147430.5 |  |  | 7759.5
| Material |  |  | 27384 | 7382.76
| Overhead |  |  | 39298.2996 | 1659.6444 |  | 1744.3356
PRP.2637.Minnich Ave | Replace 388' of 2" Fusion Bond Epoxy, 1,984' of 4" Mill Wrap Bare Joint3' of 6" Epoxy, 3036' of 6" Mill Wrap bare Joint, 31' of 4" Epoxy, 13' of 2" PE, 483' of 1" Mill Wrap, 372' of 2" Bare Steel, 410' of 1.25 PE with 2,604' of 2" , 1,116' of 4" and 3,035' of 6" HDPE. | 67 | 969991.8 |  |  | 51052.2 | [5 empty] | 1021044 | 0
| Contractor |  |  | 235186.75 |  |  | 12378.25
| Material |  |  | 43684 | 11777.26
| Overhead |  |  | 62690.1446 | 2647.528 |  | 2782.6306
PRP.2637.Maple Ave | Replace 3,199' of 2" Mill Wrap Bare Joint, 236' of 2" PE, 421' of 2" Fusion Bond Epoxy, 101' of 2" Bare Steel, with 3,957' of 2" HDPE | 44 | 678597.35 |  |  | 35715.65 | [5 empty] | 714313 | 0
| Contractor |  |  | 154451 |  |  | 8129
| Material |  |  | 28688 | 7734.32
| Overhead |  |  | 41169.6472 | 1738.6751 |  | 1827.3992
PRP.2637.Old Mayfield Rd | Replace 3199' of 2" Mill Wrap Bare Joint, 235' 421' 2" Fusion Bond Epoxy, 101' 2" Bare Steel, with 3,957' of 2" HDPE | 44 | 416120.9 |  |  | 21901.1 | [5 empty] | 438022 | 0
| Contractor |  |  | 154451 |  |  | 8129
| Material |  |  | 28688 | 7734.32
| Overhead |  |  | 41169.6472 | 1738.6751 |  | 1827.3992
PRP.2734.Bluegrass Farms | Replace1,173' of 2" Bare Steel with 1,149' of 2" HDPE | 1 | 192181.2 |  |  | 10114.8 | [5 empty] | 202296 | 0
| Contractor |  |  | 3510.25 |  |  | 184.75
| Material |  |  | 652 | 175.78
| Overhead |  |  | 935.6738 | 39.5153 |  | 41.5318
PRP.2734.Bristow Rd | Replace 277' of 1.25" Bare Stl., 58' of 2" Bare Stl., 438' of 4" Bare Stl., with 335' of 2"and 438' of 4" HDPE. | 13 | 197686.45 |  |  | 10404.55 | [5 empty] | 208091 | 0
| Contractor |  |  | 45633.25 |  |  | 2401.75
| Material |  |  | 8476 | 2285.14
| Overhead |  |  | 12163.7594 | 513.6995 |  | 539.9134
PRP.2734.S Spring St | Replace 24' of 3" Bare Stl., 13' of 1.25"Bare Stl.,72' of 2" Bare Stl., with 522' of 2" HDPE | 6 | 208093.7 |  |  | 10952.3 | [5 empty] | 219046 | 0
| Contractor |  |  | 21061.5 |  |  | 1108.5
| Material |  |  | 3912 | 1054.68
| Overhead |  |  | 5614.0428 | 237.0921 |  | 249.1908
PRP.2734.US 68 Main St | Replace 310' of 2" Mill Wrap, 61' of 2" Bare Steel, 175' of 2" PE with 450' of 2" HDPE (Will be a creek crossing rock bore involved) | 3 | 175438.4 |  |  | 9233.6 | [5 empty] | 184672 | 0
| Contractor |  |  | 10530.75 |  |  | 554.25
| Material |  |  | 1956 | 527.34
| Overhead |  |  | 2807.0214 | 118.546 |  | 124.5954
PRP.2738. Sheridan Dr | Replace 86' of 2" Mill Wrap, 255' of 2" Mill Wrap Bare Joint, 193' of 2" Steel unknown coating, 27' of 2" Epoxy, 1,054' of 3" Mill Wrap bare Joint, 25' of 4" Mill Wrap Bare Joint, 259' of 2" Painted, 344' of 2" Fusion Bond Epoxy, 11' of 2" Bare Steel, with 1,254' of 2" and 1,054' of 4" HDPE. | 55 | 393720.85 |  |  | 20722.15 | [5 empty] | 414443 | 0
| Contractor |  |  | 193063.75 |  |  | 10161.25
| Material |  |  | 35860 | 9667.9
| Overhead |  |  | 51462.059 | 2173.3439 |  | 2284.249
PRP.2738.Mayes Ave | Replace 507' of 4" Painted pipe, 419' of 2" Mill Wrap Bare Joint, 224' of 2" Hot Tar, 530' of 2" Epoxy, 1,543' of 2" Painted, 231' of 2" Mill Wrap, 472' of 4" Mill Wrap, 171' of 2" Bare Steel, with 2,218' of 2" and 1,879' of 6" HDPE. | 62 | 702123.15 |  |  | 36953.85 | [5 empty] | 739077 | 0
| Contractor |  |  | 217635.5 |  |  | 11454.5
| Material |  |  | 40424 | 10898.36
| Overhead |  |  | 58011.7756 | 2449.9513 |  | 2574.9716
PRP.2738.Hood Ave | Replace 625' of 2" Mill Wrap, 8' of 2" PE, 872' of 6" Fusion Bond Epoxy, 119' of 6" Bare Stl., 77' of 2" Fusion Bond Epoxy,4' of 2" Painted, 31' of 2" Epoxy, 436' of 2" Bare Stl., with 2,175' of 2" HDPE. | 45 | 337185.4 |  |  | 17746.6 | [5 empty] | 354932 | 0
| Contractor |  |  | 157961.25 |  |  | 8313.75
| Material |  |  | 29340 | 7910.1
| Overhead |  |  | 42105.321 | 1778.1905 |  | 1868.931
PRP.2737.Lancaster - Stanford | Replace 36,050' of 4" Painted Steel Main with 31,400' of 8"Fusion Bond Epoxy, 3900' of 8" and 750' of 2" HDPE. Also replace and relocate the Stanford KY Town Border Station. | 30 | 10143357.1 |  |  | 533860.9 | [5 empty] | 10677218 | 0
| Contractor |  |  | 105307.5 |  |  | 5542.5
| Material |  |  | 19560 | 5273.4
| Overhead |  |  | 28070.214 | 1185.4603 |  | 1245.954
PRP.2737.Rosemont Ave | Replace 723' of 3" Bare Stl., 813' of 2" Bare Stl., 54' of 2" Epoxy, 2036' of 4" Mill Wrap Bare Joint, 423' of 4" Bare Stl., 1,236' of 2" Adyl A with 2,407' of 2" and 2,388' of 4" HDPE. | 95 | 699350.1 |  |  | 36807.9 | [5 empty] | 736158 | 0
| Contractor |  |  | 333473.75 |  |  | 17551.25
| Material |  |  | 61940 | 16699.1
| Overhead |  |  | 88889.011 | 3753.9577 |  | 3945.521
PRP.2737.Dogwood Dr | Replace 26' of 4" Mill Wrap, 679' of 2" Mill Wrap, 465' of 4" Mill Wrap Bare Joint, 926' of2" Fusion Bond Epoxy, 168' of 1.25" Stl. Unknown coating, 1,020' of 3" Mill Wrap Bare Joint, 1,692' of 2" Mill Wrap Bare Joint, 32' of 2" Stl. Unknown coating with 4,547' of 2" and 460' of 4" HDPE. | 70 | 583267.7 |  |  | 30698.3 | [5 empty] | 613966 | 0
| Contractor |  |  | 245717.5 |  |  | 12932.5
| Material |  |  | 45640 | 12304.6
| Overhead |  |  | 65497.166 | 2766.0741 |  | 2907.226
PRP.2736.Elkton Replacement | Elkton 10" Replacement, land, easement, and survey only, construction to begin in FY26 or FY27 | 0 | 4114433.85 |  |  | 216549.15 | [5 empty] | 4330983 | 0
| Contractor |  |  | 0 |  |  | 0
| Material |  |  | 0 | 0
| Overhead |  |  | 0 | 0 |  | 0
PRP.2737.Ohara Dr | Replace 761' of 2" Bare Stl., 688' of 2" Mill Wrap, 11' of 2" HDPE, 105' of 2" unknown coating, 1,583' of 4" Bare Stl., with 1,927' of 2" and 1,223' of 4" HDPE | 43 | 457906.65 |  |  | 24100.35 | [5 empty] | 482007 | 0
| Contractor |  |  | 150940.75 |  |  | 7944.25
| Material |  |  | 28036 | 7558.54
| Overhead |  |  | 40233.9734 | 1699.1598 |  | 1785.8674
| Total specific budgeted projects & bare steel functional |  | 26456470.2 | 6239858.7312 | 263521.5011 | 1392445.8 | 276968.9232
| Non specfic bare steel functional |  | 38902.5232 | -22380.7047 | -945.1812 | 2047.5012 | -993.4135
| Total budgeted 2025 projects |  | 26495372.7232 | 6217478.0265 | 262576.3199 | 1394493.3012 | 275975.5097 |  | 1486320.8155 | 1777795.229 | 98052.3978