## 2020
Atmos Energy Corporation
(Kentucky Division)
Case No. 2024-00276
Construction Projects 2020
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised
Workpaper Reference No(s).:
Project No. | Project Title / Description |  | Annual Actual Cost 2020 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 223979.98 | 0 |  |  | 3.231% | 1835766.73 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 5205.2 | 0 |  |  | 0.2896% | 164546.94 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 43393.58 | 0 |  |  | 0.6098% | 346547.53 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 16402 | 0 |  |  | 0.4177% | 237384.79 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 14113.1 | 0 |  |  | 0.4039% | 229531.41 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 194970.22 | 0 |  |  | 1.528% | 868395.97 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 13056.15 | 0 |  |  | 0.2802% | 159246.39 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 19387.73 | 0 |  |  | 0.2815% | 159985.79 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 126672.75 | 0 |  |  | 2.435% | 1383711.16 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 233955.04 | 0 |  |  | 2.576% | 1463621.34 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2017-09-30 | 09
050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 143929.37 | 0 |  |  | 0.9236% | 524847.98 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 106057.57 | 0 |  |  | 2.243% | 1274756.45 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 9059.91 | 0 |  |  | 0.07259% | 41247.07 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 14595.36 | 0 |  |  | 0.2498% | 141935.63 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 3959.3 | 0 |  |  | 0.4715% | 267955.36 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 14643.75 | 0 |  |  | 0.3109% | 176653.81 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 3822.38 | 0 |  |  | 0.4302% | 244461.01 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 23209.06 | 0 |  |  | 0.2478% | 140824.88 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 10707.81 | 0 |  |  | 0.1866% | 106024.81 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 55780.5 | 0 |  |  | 1.162% | 660277.19 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 39612.85 | 0 |  |  | 0.6676% | 379362.8 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 15689.02 | 0 |  |  | 0.1987% | 112914.32 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 1112258.59 | 0 |  |  | 12.17% | 6916620.06 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 130627.09 | 0 |  |  | 1.407% | 799374.97 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 117516.47 | 0 |  |  | 1.342% | 762775.42 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 116451.92 | 0 |  |  | 1.039% | 590260.65 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 126801.2 | 0 |  |  | 1.332% | 757064.24 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 375262.56 | 0 |  |  | 4.519% | 2567752.25 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 75783.87 | 0 |  |  | 1.691% | 960943.81 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 64457.67 | 0 |  |  | 0.8217% | 466939.84 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 894105.42 | 0 |  |  | 8.942% | 5081497.13 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 383992.07 | 0 |  |  | 4.811% | 2733662.51 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2017-09-30 | 09
050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 75261.42 | 0 |  |  | 1.149% | 652865.34 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 281135.35 | -139.39 |  |  | 3.165% | 1798578.27 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 49741.74 | 755.08 |  |  | 0.5714% | 324706.66 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 46399.21 | 1317.4 |  |  | 0.7778% | 442008.78 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 81950.62 | 1266.99 |  |  | 0.8696% | 494131.64 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 116109.6 | -962.09 |  |  | 0.7475% | 424790.5 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 58507.51 | 139 |  |  | 0.6399% | 363640.46 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 113321.72 | 558.74 |  |  | 0.7667% | 435704.17 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 47523.8 | 500 |  |  | 0.4296% | 244127.05 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 245359.55 | 900 |  |  | 2.662% | 1512491.14 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 119209.91 | -1245.91 |  |  | 1.753% | 996137.43 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 23505.88 | -1567.36 |  |  | 0.3526% | 200359.46 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 517776.09 | -431.33 |  |  | 6.995% | 3974677.3 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 548525.82 | 2170.7 |  |  | 2.262% | 1285274.05 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 1294520.96 | -559.97 |  |  | 5.735% | 3258860.66 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 549046.16 | -3343 |  |  | 4.287% | 2436191.37 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 252360.58 | 500 |  |  | 2.341% | 1330466.14 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 65643.62 | 400 |  |  | 1.603% | 910750.25 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 362945.29 | 4.13 |  |  | 4.18% | 2375133.85 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 257398.07 | 400 |  |  | 2.214% | 1257949.84 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 1693001.4 | -923.05 |  |  | 8.499% | 4829859.01 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 945608.1 | -5569.77 |  |  | 7.151% | 4063774.31 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 112434.05 | -250 |  |  | 2.158% | 1226377.39 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 655038.34 | 1719.39 |  |  | 9.962% | 5660967.94 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 72183.62 | 435.43 |  |  | 2.782% | 1581008.54 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 260750.97 | 500 |  |  | 3.347% | 1902198.82 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 199203.65 | 500 |  |  | 3.359% | 1908588.42 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 68602.01 | 500 |  |  | 3.025% | 1719055.98 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 86331.15 | 500 |  |  | 2.602% | 1478757.52 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 123386.38 | 533.22 |  |  | 3.52% | 2000111.45 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 105752.45 | 500 |  |  | 1.826% | 1037712.74 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 627757.59 | 400 |  |  | 14.12% | 8025021.29 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 702499.24 | 94.93 |  |  | 8.995% | 5111589.27 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 284773.36 | -624.92 |  |  | 3.386% | 1924076.95 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 72883.29 | 42479.01 |  |  | 1.453% | 825570.62 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 23626.12 | 1258.92 |  |  | 0.1834% | 104197.28 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 36629.6 | 30798.99 |  |  | 0.871% | 494968.9 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 78881.77 | 53494.76 |  |  | 1.175% | 667778.1 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 3664.48 | 2233.56 |  |  | 0.2268% | 128896.55 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 3269.4 | 4545.47 |  |  | 0.1577% | 89628.64 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 25551.71 | 11503.51 |  |  | 0.4873% | 276916.13 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 10339.51 | 16134.14 |  |  | 0.4518% | 256761.14 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 87159.78 | 6111.69 |  |  | 0.7525% | 427605.09 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 30934.45 | 19957.36 |  |  | 0.6756% | 383916.85 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 8231.83 | 2681.58 |  |  | 0.1148% | 65251.53 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 122480.51 | -19538.24 |  |  | 3.711% | 2108598.51 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 100833.92 | 502.96 |  |  | 1.44% | 818139.72 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 66510.52 | -666.24 |  |  | 1.27% | 721480.8 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 47795.02 | 500 |  |  | 0.9945% | 565160.32 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 39407.36 | 1911.46 |  |  | 0.5002% | 284269.55 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 2871.6 | -736.55 |  |  | 0.4181% | 237611.58 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 59375.68 | 1330.66 |  |  | 0.9575% | 544104.43 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 50321.72 | 400 |  |  | 0.5835% | 331583.43 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 78079.41 | -6777.6 |  |  | 1.944% | 1104781.64 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 62973.39 | -389.75 |  |  | 1.657% | 941467.49 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 10854.57 | -2299.12 |  |  | 0.2953% | 167801.57 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 207082.87 | -2980.4 |  |  | 3.691% | 2097524.76 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 79193.4 | -295.6 |  |  | 1.232% | 700311.89 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 42836.61 | -1935.72 |  |  | 1.125% | 639059.93 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 51747.08 | 426.09 |  |  | 1.543% | 876612.91 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 20822.41 | -938 |  |  | 0.5294% | 300829.06 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | -1152.83 | 2404 |  |  | 0.4954% | 281532.54 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 62647.89 | 399.65 |  |  | 1.066% | 606042.13 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 46801.36 | -406.8 |  |  | 0.4158% | 236275.64 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 208271.86 | -7134 |  |  | 2.922% | 1660447.75 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2017-12-31 | 12
050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 138145.11 | -13293 |  |  | 3.126% | 1776118.76 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 38617.62 | -143.69 |  |  | 0.5323% | 302468.14 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 218624.24 | 300 |  |  | 3.8% | 2159350.48 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 56382.11 | 334.73 |  |  | 0.9796% | 556648.38 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 147083.13 | 400 |  |  | 0.6741% | 383034.81 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 51465.46 | 433 |  |  | 1.218% | 692407.63 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 20569.95 | 300 |  |  | 0.9759% | 554577.67 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 21343.2 | 400 |  |  | 0.637% | 361957.52 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 68010.91 | -360 |  |  | 0.7756% | 440716.12 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 30681.82 | 300 |  |  | 0.397% | 225607.91 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 258417.65 | 645 |  |  | 4.201% | 2387192.36 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 120664.16 | 1909.01 |  |  | 1.524% | 866004.69 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 17273.75 | 400 |  |  | 0.2425% | 137776.15 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 5336.98 | 13.37 |  |  | 0.1247% | 70884.78 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 910.56 | 7.05 |  |  | 0.02309% | 13123.17 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 1605294.54 | 1466687.75 |  |  | 21.99% | 12497034.13 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 486672.17 | 659087.52 |  |  | 11.84% | 6727791.81 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2020-09-30 | 09
050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 1554069.33 | 1408505.21 |  |  | 22.46% | 12763656.82 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 2451494.92 | 637306.36 |  |  | 16.99% | 9652241 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 864.26 | 597.05 |  |  | 0.02135% | 12134.74 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 965.13 | 50.16 |  |  | 0.01393% | 7917.82 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 590067.64 | 169478.49 |  |  | 3.176% | 1804978.21 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 362960.09 | 708814.17 |  |  | 5.697% | 3237232.91 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 409.97 | 396318.77 |  |  | 1.657% | 941440.72 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26302 | GlasgowPRPMains | Glasgow KY Pipe Replacement Program Functional - Mains | 0 | 0 |  |  | 0.007487% | 4254.39 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2011-08-01 | 08
050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 857893.5 | 454263.24 |  |  | 9.01% | 5119874.85 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 410359.91 | 160913.12 |  |  | 10.74% | 6103905.85 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 2396024.5 | 89664.27 |  |  | 11.18% | 6354885.44 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26312 | ShelbyvillePRPServices | Shelbyville KY PRP Functional - Services | 1949.99 | 64020.09 |  |  | 0.4208% | 239120.71 | Non Budgeted |  | 2019-10-01 | 2020-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
050.44145 | PRP.2738.Springfield Calvary | PRP Replacement of approimately 80,500 feet of vintage gas transmission main with high pressure distribution in Marion and Washington County Kentucky. | 46483.62 | 21767954.19 | -21721470.57 | -99.79% | 38.73% | 22005815.12 | 21767954.19 | 237860.93 | 2019-10-01 | 2020-09-30 | 2016-10-01 | 10 | 2019-08-30 | 08
050.49008 | 2609.ANR Bon Harbor | This project will include the installation of approximately 4 miles of 8 inch 0.322¿ wall, X-52 pipe from ANR/TransCanada Purchase in Stanley, KY to Bon Harbor Storage field to add capacity to the system. Currently Bon Harbor storage field is being fed | 10353.6 | 11815178.03 | -11804824.43 | -99.91% | 16.39% | 9315350.87 | 11815178.03 | -2499827.16 | 2019-10-01 | 2020-09-30 | 2018-07-01 | 07 | 2019-09-30 | 09
050.49856 | 2637.Paducah HCA-06 | Install 15,600' of 8" HP steel. Install 4" regulator station and downrate 5,360' of 8" steel. Project elimates existing HCA. | 292586.28 | 7629971.51 | -7337385.23 | -96.17% | 13.36% | 7591578.26 | 7629971.51 | -38393.25 | 2019-10-01 | 2020-09-30 | 2018-03-08 | 03 | 2019-09-30 | 09
050.49220 | 2609.Farm Taps Replac.FY19 | Replace Farm Taps with Two (2) Man crew and a Welder, for Company owened Transmission Line Farm Taps and One (1) Two man crew and Welder for Texas Gas Farm Taps | 6424.52 | 2784165.14 | -2777740.62 | -99.77% | 3.535% | 2009039.04 | 2784165.14 | -775126.1 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-30 | 09
050.51354 | 2734.WMR Endpoints.FY2020 | Purchase approximately 28,025 endpoints (9,750 - 100 GM-A; 525 - 100 GM-B;17,100 - 300 GM; 650 - 600 GM). Bowling Green area will be 100% WMR at end of project. | 1036324.33 | 2720654.45 | -1684330.12 | -61.91% | 2.536% | 1441103.53 | 2720654.45 | -1279550.92 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-06-30 | 06
050.51868 | PRP.2738.W. Walnut St Lebanon | See project Long Descrption / notes | 1364268.32 | 1817471.68 | -453203.36 | -24.94% | 2.401% | 1364268.32 | 1817471.68 | -453203.36 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.49298 | 2734.Farm Tap Replc.FY19 | Farm Tap Replacements - Contract Labor at 64,000.00 for 11 months, 130,000.00 in materials with stores. Company labor to include service light up. | -915.78 | 1614123.46 | -1615039.24 | -100.1% | 2.84% | 1614033.93 | 1614123.46 | -89.53 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-30 | 09
050.51857 | PRP.2738.McCord St | See Project Long Decsription / notes | 1204394.94 | 1547680.11 | -343285.17 | -22.18% | 2.119% | 1204415.29 | 1547680.11 | -343264.82 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.54687 | PRP.2636.KY 1473 Greenville | Unbudgeted PRP See project Long descirption/notes | 401828.83 | 1544763.95 | -1142935.12 | -73.99% | 0.7071% | 401828.83 | 1544763.95 | -1142935.12 | 2019-10-01 | 2020-09-30 | 2020-08-18 | 08 | 2020-09-30 | 09
050.52910 | 2734.WMR.Endpoints.Ph2.FY20 | Installation of approximately 14,390 WMR endpoints in Bowling Green, KY. | 1402490.18 | 1477519.16 | -75028.98 | -5.078% | 2.468% | 1402490.18 | 1477519.16 | -75028.98 | 2019-10-01 | 2020-09-30 | 2019-12-30 | 12 | 2020-04-30 | 04
050.51876 | PRP.2738.W High St Lebanon | See Project Long Description / notes | 1249218.03 | 1469518.55 | -220300.52 | -14.99% | 2.198% | 1249218.03 | 1469518.55 | -220300.52 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51957 | PRP.2735.Lexington Ave | See Long Description / notes | 1047674.19 | 1367295.7 | -319621.51 | -23.38% | 1.844% | 1047674.19 | 1367295.7 | -319621.51 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.52351 | PRP.2637.S 28th St | See Project Long Description/notes | 1256341.27 | 1319204.69 | -62863.42 | -4.765% | 2.211% | 1256341.27 | 1319204.69 | -62863.42 | 2019-10-01 | 2020-09-30 | 2019-12-25 | 12 | 2020-09-30 | 09
050.51844 | PRP.2734.E 9th Russellville | See Project Long Description / notes | 1287273.5 | 1287273.5 | 0 | 0% | 2.265% | 1287273.5 | 1287273.5 | 0 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.50939 | PRP.2637.N 26th Street | See Long Description/notes | 166133.98 | 1285617.92 | -1119483.94 | -87.08% | 1.444% | 820382.39 | 1285617.92 | -465235.53 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-12-30 | 12
050.51867 | PRP.2734.Jackson - Pearl St | See Project Long Description / notes | 1182248.2 | 1220404.46 | -38156.26 | -3.127% | 2.08% | 1182248.2 | 1220404.46 | -38156.26 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.52016 | 2636. LP.Greenville, FY20 | Replace Approximently 6500" of 6" LP. steel, 4140' of 2" Bare Steel LP. with 4" PE. and 2" PE. IP. with 200 Services | 1149033.54 | 1162811.07 | -13777.53 | -1.185% | 2.022% | 1149033.54 | 1162811.07 | -13777.53 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51920 | 050.2609 Farm Taps 2020 | Update, rebuild Transmissin line Farm Taps on company owened facilities and on Texas Gas facilities | 459275.99 | 1132668.45 | -673392.46 | -59.45% | 0.8082% | 459275.99 | 1132668.45 | -673392.46 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-08-30 | 08
050.49923 | 2739.Replace Farm Taps | Replace 110 Farm Taps in the Shelbyville Area. Contract Labor will be utilized. 5500.00 per tap | 10256.98 | 1109068.57 | -1098811.59 | -99.08% | 0.9914% | 563347.62 | 1109068.57 | -545720.95 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-12-31 | 12
050.51843 | PRP.2737.Hwy 150 | See Long Descirption / notes | 1099292.42 | 1102903.29 | -3610.87 | -0.3274% | 1.934% | 1099292.42 | 1102903.29 | -3610.87 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-07-30 | 07
050.52522 | PRP.2737. Ky 52 - Danville St | See Project Long Description/notes | 933119.55 | 1055853.82 | -122734.27 | -11.62% | 1.642% | 933119.55 | 1055853.82 | -122734.27 | 2019-10-01 | 2020-09-30 | 2020-04-28 | 04 | 2020-09-30 | 09
050.49316 | PRP.2737.W Maple Ave.FY19 | See Notes/ Long Description | 49601.92 | 1051899.47 | -1002297.55 | -95.28% | 1.867% | 1061019.15 | 1051899.47 | 9119.68 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-30 | 09
050.50739 | PRP.2734.N Breathitt St | See Project Long Decription/Notes | 320041.07 | 1045492.78 | -725451.71 | -69.39% | 1.759% | 999775 | 1045492.78 | -45717.78 | 2019-10-01 | 2020-09-30 | 2019-04-12 | 04 | 2019-11-30 | 11
050.49330 | 2735.Farm Tap Replc.FY19 | Farm Tap Replacement s - Glasgow KY. Contract labor - 249,900.00 and Company Labor - 14,000.00 to be spread over 11 months. Materials with stores - 250,000 to be spread for 5 months - Oct. 2018 ther Feb. 2019. | -505.83 | 1010993.99 | -1011499.82 | -100.1% | 1.779% | 1010949.44 | 1010993.99 | -44.55 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-10-31 | 10
050.47910 | PRP.2736.East 13th Street | See Long Description/notes | 71461.25 | 1004432.18 | -932970.93 | -92.89% | 1.666% | 946813 | 1004432.18 | -57619.18 | 2019-10-01 | 2020-09-30 | 2018-04-20 | 04 | 2019-09-30 | 09
050.53707 | PRP.2637.Old Mayfield Rd | See project long Description Notes | 618447.22 | 954741.55 | -336294.33 | -35.22% | 1.088% | 618447.22 | 954741.55 | -336294.33 | 2019-10-01 | 2020-09-30 | 2020-05-10 | 05 | 2020-09-30 | 09
050.49315 | PRP.2738.Robinson Ave.FY19 | See notes/Long Description | 65484.58 | 897032.57 | -831547.99 | -92.7% | 1.376% | 781846.14 | 897032.57 | -115186.43 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-10-30 | 10
050.53187 | 050.2735.Glasgow LP | Replace final 2 LP systems with IP systems in Glasgow KY | 944805.24 | 876604.05 | 68201.19 | 7.78% | 1.663% | 944805.24 | 876604.05 | 68201.19 | 2019-10-01 | 2020-09-30 | 2020-02-03 | 02 | 2020-07-30 | 07
050.51913 | PRP.2636.Allen Street | See Project Long Description / notes | 627301.73 | 802254.44 | -174952.71 | -21.81% | 1.104% | 627612.65 | 802254.44 | -174641.79 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-02-28 | 02
050.47397 | PRP.2637.Mississippi Georgia | See Long Description/notes | 20455.09 | 772358.07 | -751902.98 | -97.35% | 0.9096% | 516905.91 | 772358.07 | -255452.16 | 2019-10-01 | 2020-09-30 | 2018-03-01 | 03 | 2019-09-30 | 09
050.52895 | PRP.2636.Crabtree Ave | See Project Long Description/notes | 822251.55 | 770828.05 | 51423.5 | 6.671% | 1.447% | 822251.55 | 770828.05 | 51423.5 | 2019-10-01 | 2020-09-30 | 2020-02-20 | 02 | 2020-08-30 | 08
050.51390 | 2734.ScottsvilleRdCampb.toI65 | 8 inch HDPE in conjunction with State Hwy Relocation - Scottsville Rd. from Campbell Ln. to I65 | 8508.15 | 739089.02 | -730580.87 | -98.85% | 1.3% | 738636.78 | 739089.02 | -452.24 | 2019-10-01 | 2020-09-30 | 2019-06-03 | 06 | 2019-09-27 | 09
050.49552 | 050.2736.Central Avenue | See Long Description | 770389.62 | 701095.18 | 69294.44 | 9.884% | 1.42% | 806835.19 | 701095.18 | 105740.01 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2020-09-30 | 09
050.49190 | PRP.2637.Clark St Ph 1.FY19 | See Long Description | 976.57 | 699003.21 | -698026.64 | -99.86% | 0.6831% | 388179.82 | 699003.21 | -310823.39 | 2019-10-01 | 2020-09-30 | 2018-10-02 | 10 | 2019-04-28 | 04
050.54130 | PRP.2636.Poplar St Alley | See Project Long Description/notes | 488208.66 | 665716.73 | -177508.07 | -26.66% | 0.8591% | 488208.66 | 665716.73 | -177508.07 | 2019-10-01 | 2020-09-30 | 2020-06-20 | 06 | 2020-09-30 | 09
050.51741 | Replace individual farm taps | We have 64 individual farm tap regulators 9on transmission line) that we plan to rebuild in fiscal '20 in order to meet federal mandate. | 210487.76 | 621990.42 | -411502.66 | -66.16% | 0.3763% | 213844.05 | 621990.42 | -408146.37 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-08-30 | 08
050.51912 | PRP.2734.E Cedar St Franklin | See Project long Description/ notes | 601202.24 | 621420.09 | -20217.85 | -3.253% | 1.058% | 601202.24 | 621420.09 | -20217.85 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-06-10 | 06
050.43361 | 050.2738.Summersville TB | 6" PE and Reg sta to replace HP steel main and retire purchase station | 0 | 619888.66 | -619888.66 | -100% | 0.3591% | 204087.77 | 619888.66 | -415800.89 | 2019-10-01 | 2020-09-30 | 2016-06-01 | 06 | 2016-12-30 | 12
050.50374 | PRP.2737.KY 33 Burgin | See Long Descirption | 25068.31 | 617395.13 | -592326.82 | -95.94% | 0.5749% | 326697.14 | 617395.13 | -290697.99 | 2019-10-01 | 2020-09-30 | 2019-01-26 | 01 | 2019-10-30 | 10
050.51604 | 2636.GrennvilleHwy62Relo. | Relocate 6" on Hwy. 62. State is widening the Hwy | 59088.92 | 614786.58 | -555697.66 | -90.39% | 0.9825% | 558290.33 | 614786.58 | -56496.25 | 2019-10-01 | 2020-09-30 | 2019-07-15 | 07 | 2019-09-27 | 09
050.50079 | PRP.2734.Stuart Ave | See Long Description/ Notes | -1425.29 | 611375.89 | -612801.18 | -100.2% | 1.017% | 578038.45 | 611375.89 | -33337.44 | 2019-10-01 | 2020-09-30 | 2018-12-01 | 12 | 2019-08-30 | 08
050.49147 | PRP.2734.Morgantown Rd.FY19 | See Long Description | 16449.58 | 598673.24 | -582223.66 | -97.25% | 1.049% | 595870.47 | 598673.24 | -2802.77 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-10-30 | 10
050.50707 | 050.2737.Hustonville Adyl A | Replace 13800 Ft of 2 In Adyl-A with HDPE in Hustonville | 1225.12 | 592212.75 | -590987.63 | -99.79% | 0.7537% | 428290.19 | 592212.75 | -163922.56 | 2019-10-01 | 2020-09-30 | 2019-02-25 | 02 | 2019-09-30 | 09
050.50754 | 050.2739.Shelbyville LP | Replace 5200 Ft of remaining LP in Shelbyville | -236.88 | 575092.57 | -575329.45 | -100% | 1.007% | 572074.11 | 575092.57 | -3018.46 | 2019-10-01 | 2020-09-30 | 2019-02-25 | 02 | 2019-09-30 | 09
050.49257 | Contacter Replacement.FY19 | Replacing Contacters at Hickory and Grandview Storage Fields | 3578.41 | 552514.86 | -548936.45 | -99.35% | 0.7393% | 420103.6 | 552514.86 | -132411.26 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-30 | 09
050.49210 | Replace Massac Creek.FY19 | Replace 800 feet of exposed 8 inch HPD in Massac Creek | 885.16 | 543179.69 | -542294.53 | -99.84% | 0.303% | 172171.06 | 543179.69 | -371008.63 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-30 | 09
050.50434 | 050.2637.KY Farm Tap Replace | We propose to install app. 26,000 feet of 2 inch poly main in order to abandon nearly 100 farm tap regulators in western McCracken County. This includes the installation of 2 small 3/4 inch regulator stations. | 24414.14 | 526385.33 | -501971.19 | -95.36% | 0.9383% | 533192.87 | 526385.33 | 6807.54 | 2019-10-01 | 2020-09-30 | 2019-04-01 | 04 | 2019-09-30 | 09
050.50999 | 2734.Glasgow Endpoints | Purchase 5,512 endpoints for installation in Glasgow, KY service area. Installation will be done by contractor (RussMar) and programming done with in-house labor. The Glasgow service area will be 100% WMR at the completion of project. Area currently | 3410.4 | 525144.25 | -521733.85 | -99.35% | 0.9112% | 517820.44 | 525144.25 | -7323.81 | 2019-10-01 | 2020-09-30 | 2019-04-09 | 04 | 2019-09-16 | 09
050.51841 | PRP.2637.Ohio St | See Project Long Description/notes | 370844.82 | 512502.73 | -141657.91 | -27.64% | 0.6526% | 370844.82 | 512502.73 | -141657.91 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.50593 | PRP.2636.Eastwood Dr | See Project Long Description | -802.75 | 498439.43 | -499242.18 | -100.2% | 0.4747% | 269764.78 | 498439.43 | -228674.65 | 2019-10-01 | 2020-09-30 | 2019-04-10 | 04 | 2019-06-30 | 06
050.53086 | PRP.2634.Grapevine Rd. | See project Long Decription/ Notes | 527788.06 | 475716.86 | 52071.2 | 10.95% | 0.9288% | 527788.06 | 475716.86 | 52071.2 | 2019-10-01 | 2020-09-30 | 2020-01-24 | 01 | 2020-08-30 | 08
050.52988 | 2734LP.Newton.Replc | 3685 ft. of 2 inch HDPE will replace existing LP Main on Newton, Herrington, Clyton, Oliver and Scottsville Rd. Contract Labor by Team Construction | 405946.77 | 472787.13 | -66840.36 | -14.14% | 0.7144% | 405946.77 | 472787.13 | -66840.36 | 2019-10-01 | 2020-09-30 | 2019-11-01 | 11 | 2020-07-31 | 07
050.54690 | PRP.2735.Rowletts | Project was in the 7/27/20 KY PRP Filing See project Long Description/Notes | 53.91 | 463474.7 | -463420.79 | -99.99% | 9.487e-05% | 53.91 | 463474.7 | -463420.79 | 2019-10-01 | 2020-09-30 | 2020-10-01 | 10 | 2021-05-30 | 05
050.51093 | 050.2738.Saloma HPD Exposures | Replace 1500 Ft of 6 In Steel to eliminate 2 line exposures in creek crossings | -2461.29 | 456321.85 | -458783.14 | -100.5% | 0.7055% | 400909.53 | 456321.85 | -55412.32 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-07-30 | 07
050.51126 | IND.2638.Gencanna Rev Ext | 1,875 feet of 6 inch steel HPD main (200 PSI MAOP) for Gencanna Hemp Processing Plant | 4705.15 | 445927.87 | -441222.72 | -98.94% | 0.7679% | 436386.49 | 445927.87 | -9541.38 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-09-30 | 09
050.49080 | WMR.2734.Towers.Ph1.FY19 | Central KY WMR infrastructure build-out. Purchasing 7 - 9 Sensus M-400 Towers. Likely locations of towers include Adairville, Auburn, Russellville, Franklin, Elkton, and Woodburn. Build-out will be done in 2 phases within FY2019. | 3270.29 | 428254.83 | -424984.54 | -99.24% | 0.7257% | 412377.59 | 428254.83 | -15877.24 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-04-30 | 04
050.54816 | PRP.2635. S Mcnary St | Unbudgeted 2020 PRP See project long description / notes | 339624.88 | 400363.37 | -60738.49 | -15.17% | 0.5977% | 339624.88 | 400363.37 | -60738.49 | 2019-10-01 | 2020-09-30 | 2020-09-05 | 09 | 2020-09-30 | 09
050.50035 | PRP.2735.Milton Ave | See Long Description / notes | 52732.44 | 385918.62 | -333186.18 | -86.34% | 0.5798% | 329448.5 | 385918.62 | -56470.12 | 2019-10-01 | 2020-09-30 | 2019-03-15 | 03 | 2019-10-30 | 10
050.52045 | 050.2738.Campbellsville LP | Replace 5400 Ft of LP with IP Distribution in Campbellsville | 268905.76 | 377028.38 | -108122.62 | -28.68% | 0.4732% | 268905.76 | 377028.38 | -108122.62 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-30 | 01
050.52475 | 2634.Hwy41APhaseII | Relocate approximentley 2,000' of 4" and 6" Stl. with 4" PE | 380913.95 | 368351.59 | 12562.36 | 3.41% | 0.6703% | 380913.95 | 368351.59 | 12562.36 | 2019-10-01 | 2020-09-30 | 2019-11-01 | 11 | 2020-04-01 | 04
050.54514 | PRP.2635.Nichols St Princeton | See Project Long Description/notes | 349452.62 | 322765.98 | 26686.64 | 8.268% | 0.615% | 349452.62 | 322765.98 | 26686.64 | 2019-10-01 | 2020-09-30 | 2020-07-28 | 07 | 2020-09-30 | 09
050.49286 | 2738.Summersville.Purch.FY19 | Replace Summersville Purchase Station | 2489.72 | 319370.46 | -316880.74 | -99.22% | 0.4636% | 263436.27 | 319370.46 | -55934.19 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-04-30 | 04
050.54248 | PRP.2637.Bridge St Phase 1 | See Project Long Description/notes | 239322.67 | 311167.55 | -71844.88 | -23.09% | 0.4212% | 239322.67 | 311167.55 | -71844.88 | 2019-10-01 | 2020-09-30 | 2020-07-28 | 07 | 2020-09-30 | 09
050.53251 | PRP.2734.Hwy 383 Franklin | Replace 2,891' of 6" Bare Steel with 2,979 ft of 6 Inch and 64 ft of 2 Inch IP HDPE. 29 Services | 295880.62 | 301845.61 | -5964.99 | -1.976% | 0.5207% | 295880.62 | 301845.61 | -5964.99 | 2019-10-01 | 2020-09-30 | 2020-03-07 | 03 | 2020-09-30 | 09
050.51858 | 050.2637.Farm Tap Replacement | Installing app. 11,500 feet of 2 inch poly gas main in an effort to retire 43 farm tap regulators. This is a 2020 FY budgeted item. This is also a mandated compliance issue. There are twelve seperate areas where we are installing this new gas main,. | 291358.02 | 298846.67 | -7488.65 | -2.506% | 0.5127% | 291358.02 | 298846.67 | -7488.65 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-03-30 | 03
050.54858 | 2638.WMR Endpoints.FY2021 | Purchase approximately 1,573 WMR endpoints for Mayfield, KY. The Mayfield work center will be 100% WMR at the conclusion of this project as well as the entire Paducah, KY subregion (Work centers of Paducah, Mayfield, and Union City). | 0 | 293046.64 | -293046.64 | -100% | 0% | 0 | 293046.64 | -293046.64 | 2019-10-01 | 2020-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.51956 | PRP.2735.Woodsonville | See Project Long Description / notes | 227276.49 | 276835.43 | -49558.94 | -17.9% | 0.4% | 227276.49 | 276835.43 | -49558.94 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.44088 | 050.2734.Hwy 31W PI SGlen | Relocate 6 inch HP Steel - State Hwy Widening Hwy 31 - Dillard to Buchanan Park | 101937.51 | 236082.38 | -134144.87 | -56.82% | 0.3283% | 186538.18 | 236082.38 | -49544.2 | 2019-10-01 | 2020-09-30 | 2016-09-12 | 09 | 2019-09-30 | 09
050.52390 | 2612.KY.RTU Upgrades.FY20 | Replacement of Obsolete and Defective RTUs in Kentucky. 6 identified sites. Total $120,000.00 Wireless/Wired upgrades where applicable. | 188371.33 | 220333.24 | -31961.91 | -14.51% | 0.3315% | 188371.33 | 220333.24 | -31961.91 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.50277 | 050.2739.Martinrea TB | Replace town border at Martinrea due to outdated equipment. | 3593.95 | 220151.79 | -216557.84 | -98.37% | 0.2578% | 146516.85 | 220151.79 | -73634.94 | 2019-10-01 | 2020-09-30 | 2019-01-01 | 01 | 2019-09-30 | 09
050.52091 | 2634.SpottsvilleRelocation | Install 250 Feet of 2 inch Stl.,Install 1-2 inch Reg Sta., Install approximently 2500 Feet of 2 inch PE. | 211686.2 | 219116.92 | -7430.72 | -3.391% | 0.3725% | 211686.2 | 219116.92 | -7430.72 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-08 | 11
050.50792 | PRP.2636.Glenn Ct | *** 2019 PRP *** Replace 1,678 ft of 4 Inch Hot Tar, 536 ft of 2 Inch Epoxy, with 1772 ft of 4 Inch and 549 ft of 2 Inch HDPE IP. 43 Services | -4117.85 | 211876.26 | -215994.11 | -101.9% | 0.2655% | 150850.66 | 211876.26 | -61025.6 | 2019-10-01 | 2020-09-30 | 2019-06-02 | 06 | 2019-09-30 | 09
050.50057 | 2609.Wescor 6" Exposure | Repair exposesure's on the Wescor 6" Transmission Line | 12208.48 | 208120.34 | -195911.86 | -94.13% | 0.305% | 173298.76 | 208120.34 | -34821.58 | 2019-10-01 | 2020-09-30 | 2019-06-01 | 06 | 2019-09-30 | 09
050.54374 | 2734.Shive Ln. II P.I. | 1250 ft. of 6" and 1000 ft. of 2" HDPE to replace main in conflict with Shive Lane II P.I. project. This is a City of Bowling Green Improvement Project | 130207.77 | 206136.29 | -75928.52 | -36.83% | 0.2291% | 130207.77 | 206136.29 | -75928.52 | 2019-10-01 | 2020-09-30 | 2020-07-01 | 07 | 2020-09-30 | 09
050.50849 | 050.2637.Untoneable Replace | Replace app. 10,000 feet of 2 inch plastic unlocateable aldyl-A pipe in Western McCracken County | -22599.67 | 199943.16 | -222542.83 | -111.3% | 0% | 0 | 199943.16 | -199943.16 | 2019-10-01 | 2020-09-30 | 2019-04-01 | 04 | 2020-05-30 | 05
050.51029 | 050.009.2736.Nortonville T.B. | Replace T.B. Station in Nortonville. The existing station are out dated. | 4158.96 | 194465.75 | -190306.79 | -97.86% | 0.1879% | 106771.19 | 194465.75 | -87694.56 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-09-30 | 09
050.49530 | Beechbend.Garvin.Tieback.FY19 | 8000 ft.. f 4 inch HDPE to improve Beechbend Rd. in northwest area of Bowling Green. This is an approved FY2019 Capital Budget project. Will Tie in to 4 inch HDPE service line Ft. Webb to Garvin Ln. | -2985.96 | 193159.7 | -196145.66 | -101.5% | 0.3399% | 193159.7 | 193159.7 | 0 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-01 | 09
050.48577 | 2734.EagleRdgApprchCemeteryRd | 6225 ft. of 8 inch HDPE approach main to serve new sub. for Eagle Ridge. located on Cemetery Rd. Developer -Eagle Ridge Development, LLC will provide and close ditch. | -125.57 | 191974.21 | -192099.78 | -100.1% | 0.3378% | 191961.81 | 191974.21 | -12.4 | 2019-10-01 | 2020-09-30 | 2018-05-16 | 05 | 2019-08-01 | 08
050.51033 | 050.009.2635.Poole Purchase | replace Poole Purchase Station with a New and updated station | 10566.42 | 170249.37 | -159682.95 | -93.79% | 0.2292% | 130240.02 | 170249.37 | -40009.35 | 2019-10-01 | 2020-09-30 | 2019-07-01 | 07 | 2019-08-31 | 08
050.49441 | PRP.2734.WKU Normal Dr | See notes/Long Description | -1085.55 | 170184.45 | -171270 | -100.6% | 0.2898% | 164653.46 | 170184.45 | -5530.99 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-07-30 | 07
050.51032 | 050.009.2635.Poole T.B. | Replace Poole T.B. with a new updated Station. | -6140.92 | 165709 | -171849.92 | -103.7% | 0.1895% | 107695.25 | 165709 | -58013.75 | 2019-10-01 | 2020-09-30 | 2019-06-01 | 06 | 2019-09-30 | 09
050.51081 | PRP.2636.E 20th and Allen | Replace approximately 1,328 ft of 4 Inch Bare LP Steel Main with 1,328 ft of 2 Inch IP HDPE and 400 ft of 4 Inch IP HDPE due to the City of Owensboro wanting to Repave E 20th St this fall. 31 Services involved | -2967.32 | 163192.16 | -166159.48 | -101.8% | 0.2887% | 164073.63 | 163192.16 | 881.47 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-07-30 | 07
050.52828 | 050.2637.Carneal Rd Repair | This project is to capture the costs associated with the repair of our 8 inch steel gas main that was damaged on Thursday December 5, 2019 on KY 1420/ Carneal Rd in western McCracken County by Star Construction plowing in a telephone cable. | 113124.85 | 161566.45 | -48441.6 | -29.98% | 0.1991% | 113124.85 | 161566.45 | -48441.6 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.52584 | 050.2637.Paddock At The Oaks | Install 3,225 feet of 4 inch poly pipe and 3,930 feet of 2 inch poly pipe to serve 49 lots in this new subdivision The Paddock at the Oaks | 144630.9 | 147073.13 | -2442.23 | -1.661% | 0.2545% | 144630.9 | 147073.13 | -2442.23 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-08-27 | 08
050.50840 | 2734.Hunt.Grain.6inch.Ext | 9000 ft. of 6 inch HDPE Extension will serve new Grain Facility for Hunts. Farms on Hwy 242 in Richpond. Main will tie in to existing 6inch PE on Nashville Rd. at So. Glen. Customer will purchase materials and provide ditch. . | -11141.94 | 144939.59 | -156081.53 | -107.7% | 0.2631% | 149520.38 | 144939.59 | 4580.79 | 2019-10-01 | 2020-09-30 | 2019-03-14 | 03 | 2019-07-31 | 07
050.51818 | 2635.DawsonSpringsTieBack | Install 1500' of 2" PE, Install 1 - 2" Sta | 5563.16 | 133326.41 | -127763.25 | -95.83% | 0.1935% | 109953.07 | 133326.41 | -23373.34 | 2019-10-01 | 2020-09-30 | 2019-08-12 | 08 | 2019-09-25 | 09
050.51181 | 2609.RidgeRd.FarmTap | Install 1600' of 2" PE. replace 4 Farm Taps with 8 Meters | -2113.27 | 126770.29 | -128883.56 | -101.7% | 0.02132% | 12116.4 | 126770.29 | -114653.89 | 2019-10-01 | 2020-09-30 | 2019-05-08 | 05 | 2019-06-30 | 06
050.50404 | 2734.Mayfield.WMR.Towers | Purchase 2 FLXNT BS M400B2 200 KHZ WMR towers for Mayfield, KY operations area. Locations are: 12975 SR 45 S, Wingo, KY and 1068 State Rt. 45 N, Mayfield, KY | 6945.28 | 124894.79 | -117949.51 | -94.44% | 0.1938% | 110145.31 | 124894.79 | -14749.48 | 2019-10-01 | 2020-09-30 | 2019-01-13 | 01 | 2019-07-30 | 07
050.51369 | 050.2609.linevalves | Rerplace valves on High Pressure Distridution line in Princeton | 1397.05 | 123886.62 | -122489.57 | -98.87% | 0.1515% | 86100.33 | 123886.62 | -37786.29 | 2019-10-01 | 2020-09-30 | 2019-07-01 | 07 | 2019-08-31 | 08
050.52961 | PRP.2737.Somerset St | See Project Long Description/notes | 119272 | 119149.54 | 122.46 | 0.1028% | 0.2099% | 119272 | 119149.54 | 122.46 | 2019-10-01 | 2020-09-30 | 2020-01-20 | 01 | 2020-03-30 | 03
050.52386 | 2612.Gas Supp RTU Install FY20 | Install 4 Identified RTUs for Gas Supply visibility. 22.5K each Total 90K. These will all be wireless upgrades. | 71120.74 | 112205.17 | -41084.43 | -36.62% | 0.1252% | 71120.74 | 112205.17 | -41084.43 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.53893 | Oboro Office Security Gates | Hayden Construction Company to replace security gates at Owensboro, KY service center. Install (2) 30’ x 6’ black aluminum gates. | 111338.07 | 108298.5 | 3039.57 | 2.807% | 0.1959% | 111338.07 | 108298.5 | 3039.57 | 2019-10-01 | 2020-09-30 | 2020-06-01 | 06 | 2020-07-30 | 07
050.51484 | PRP.2636.Hwy 231 | Replace 1,151 ft of Bare 2" IP Stl. with 1,000 ft of 6" PE and 150 ft of 2" IP 7 Services involved. 2" is currently serving Deer Valley Subdivison. This was originally a company crew job that were going to use contract labor to complete. | 1649.79 | 107976.53 | -106326.74 | -98.47% | 0.1709% | 97126.29 | 107976.53 | -10850.24 | 2019-10-01 | 2020-09-30 | 2019-07-03 | 07 | 2019-09-30 | 09
050.52426 | 2734.S.Oak.Sub. Hwy 242 | 2055 of 6" approah, 3763 ft. of 4" and 1407ft. of 2 " HDPE will serve 110 single family lots in S. Oak Sub. located off Hwy 242 in Richpond. Main will be fed off 2 " reg. sta. on Hwy 242 off 6 inch HPD stl. main. Developer to open and close ditch | 123966.28 | 104316.15 | 19650.13 | 18.84% | 0.2182% | 123966.28 | 104316.15 | 19650.13 | 2019-10-01 | 2020-09-30 | 2019-08-21 | 08 | 2020-09-30 | 09
050.50761 | 2734.Garvin.Ln.Ext. | 180 ft. of 4 inch HP steel - Henderson Industrial Park in Franklin. Deposit - Aic Agreement with Franklin-Simpson Industrial Authority. Aic = $67,350.00. Contract Labor will be utilized. | -5189.26 | 104193.9 | -109383.16 | -105% | 0.1834% | 104193.9 | 104193.9 | 0 | 2019-10-01 | 2020-09-30 | 2019-02-26 | 02 | 2019-09-30 | 09
050.51364 | 050.2637.WKCTC Replacement | Upgrade un-tonable existing gas main didtribution system inside college complex. | -1.28 | 102012.68 | -102013.96 | -100% | 0.04351% | 24723.33 | 102012.68 | -77289.35 | 2019-10-01 | 2020-09-30 | 2019-06-01 | 06 | 2019-09-30 | 09
050.52370 | 3302.KY.MDT.FY20.Phase 2 | Purchase replacement MDTs for Kentucky - Phase 2 | 89432.72 | 101831.4 | -12398.68 | -12.18% | 0.1574% | 89432.72 | 101831.4 | -12398.68 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.54818 | 050.2737.Perryville Outage | Project created to capture charges associated with outage in Perryville, KY on September 3, 2020 due to hit main. | 27168.14 | 100234.93 | -73066.79 | -72.9% | 0.04781% | 27168.14 | 100234.93 | -73066.79 | 2019-10-01 | 2020-09-30 | 2020-09-03 | 09 | 2021-02-28 | 02
050.53192 | 2734.Breckenridge,Sub. Ext | 5375 ft. of 6inch. 1315 of 4 ich, and 585 ft. of 2 inch HDPE will serve 44 new residential lots in Breckenridge Subdivision located off Old Scottsviil Rd . Developer to open and close ditch.Atmos will provide bore across Scottsville Rd. | 115104.75 | 96948.92 | 18155.83 | 18.73% | 0.2026% | 115104.75 | 96948.92 | 18155.83 | 2019-10-01 | 2020-09-30 | 2020-01-24 | 01 | 2020-05-29 | 05
050.51804 | KY.Leak.Vehicle.Equip.FY2020 | Purchase 3 SENSIT VMD for Kentucky operations. | 92154.86 | 95589.4 | -3434.54 | -3.593% | 0.1622% | 92154.86 | 95589.4 | -3434.54 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.54326 | KY MDT Replc. Ph3.FY20 | Purchase 25 MDTs for Kentucky operations. | 82316.75 | 95557.5 | -13240.75 | -13.86% | 0.1449% | 82316.75 | 95557.5 | -13240.75 | 2019-10-01 | 2020-09-30 | 2020-06-27 | 06 | 2020-08-15 | 08
050.50521 | 63 FV Replacements | This project is set up to capture the casts of replacing (4) 63 FV Relief Valves around the Mayfield area. | 49912.07 | 94112.67 | -44200.6 | -46.97% | 0.1633% | 92802.13 | 94112.67 | -1310.54 | 2019-10-01 | 2020-09-30 | 2019-06-01 | 06 | 2019-07-31 | 07
050.52935 | 2636.OldhartfordRd. | Replace approximentley 400' of 8" Stl. to repair leak | 63740.07 | 82964.25 | -19224.18 | -23.17% | 0.1122% | 63740.07 | 82964.25 | -19224.18 | 2019-10-01 | 2020-09-30 | 2020-01-02 | 01 | 2020-03-31 | 03
050.51302 | Midwestern Purch RTU Upgrade | Upgrade the RTU at Midwestern purchase. This will consist of RTU, Canopy , Pad, new conduit, grounding grid and contractor labor to install the aforementioned. | -3987.18 | 79856.76 | -83843.94 | -105% | 0.1328% | 75449.59 | 79856.76 | -4407.17 | 2019-10-01 | 2020-09-30 | 2019-05-23 | 05 | 2019-09-30 | 09
050.50763 | 2734.Century.St.4.stl.Ext | 1600 ft. of 4 inch HP steel for new industrial customer on Century St. in the South Industril Park. Main will tie in to existing 4 inch HP steel on Century. Valve will be installed on the end of this extension for future main . Main will serve 8 new cust | 4252.31 | 76468.18 | -72215.87 | -94.44% | 0.06987% | 39702.92 | 76468.18 | -36765.26 | 2019-10-01 | 2020-09-30 | 2018-10-29 | 10 | 2019-09-27 | 09
050.52397 | 2612.Calibration Kits FY20 | Calibration kits for use in division while performing station inspections | 73731.36 | 73796.74 | -65.38 | -0.08859% | 0.1297% | 73731.36 | 73796.74 | -65.38 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-05-31 | 05
050.51491 | 050.2637.Ky 1322 Relocate | We have a section of existing 4 inch poly main exposed in the bar ditch/ small creek that parallels Lovelaceville Rd. We propose to replace app. 1,400 feet of 4 inch poly main. | 33272.17 | 73541.45 | -40269.28 | -54.76% | 0.07473% | 42465.21 | 73541.45 | -31076.24 | 2019-10-01 | 2020-09-30 | 2019-06-10 | 06 | 2019-12-31 | 12
050.52363 | 3302.KY.Desktops.FY20.Phase 2 | Purchase replacement desktops and monitors for KY (Phase 2) | 59848.87 | 70293.54 | -10444.67 | -14.86% | 0.1053% | 59848.87 | 70293.54 | -10444.67 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.51770 | 2636.Equipment.FY2020 | Purchase 9 Sensit Gold CGI, $14,400; 3 Metrotech 810 Locators, $15,000; 2 Junos, $5,200; Laser Methane Detector, $14,500. | 62570.16 | 68621.52 | -6051.36 | -8.818% | 0.1101% | 62570.16 | 68621.52 | -6051.36 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-05-31 | 05
050.54020 | Oboro.Warehouse Garage doors | Frame in at end of building to support (1) 30’ x 14’ and (1) 19’x14’ overhead door and (1) 3’0 x7’0 man door | 65253.01 | 63470.57 | 1782.44 | 2.808% | 0.1148% | 65253.01 | 63470.57 | 1782.44 | 2019-10-01 | 2020-09-30 | 2020-06-01 | 06 | 2020-07-31 | 07
050.51766 | 2637.Equipment.FY2020 | Mueller 1 1/4" and 2" valve changer, $3,500; Ditchwitch locator, $4,700; Destructive tester, $5,000; 2 Sensit G-2, $3,000; Lincoln Welder remote control, $1,300. | 68521.15 | 63361.76 | 5159.39 | 8.143% | 0.1206% | 68521.15 | 63361.76 | 5159.39 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.51674 | 2734.Blevins.Farms.Sub | 2087 ft. of 4 inch and 4646 ft. of 2 inch HDPE will serve 100 new single family building lots in Blevins Farms Sub. located offf Long Rd. at Matlock Rd. Deferrred AGreement. Developer to open and close ditch and install casings for main and services | 43372.02 | 62578.76 | -19206.74 | -30.69% | 0.1102% | 62634.62 | 62578.76 | 55.86 | 2019-10-01 | 2020-09-30 | 2019-07-12 | 07 | 2020-06-01 | 06
050.51756 | 2734.Equipment.FY2020 | 2 No Blow stop changers, $6,400; 2 Metro Tech locators, $8,000; 2 Fisher spilt boxes, $2,000; 10 Junos, $25,000; 4 Sensit G2, $6,000; 2 Trak It 111, $3,000. | 68999.42 | 61649.28 | 7350.14 | 11.92% | 0.1214% | 68999.42 | 61649.28 | 7350.14 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.51127 | COM.2638.Ky 339 Ext - Enon | Install 2,600 feet of 4 inch poly for one existing customer Enon Baptist Church. They are converting from propane. | 656.67 | 61531.12 | -60874.45 | -98.93% | 0.1347% | 76536.6 | 61531.12 | 15005.48 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-09-30 | 09
050.49496 | 2637.WMR Tower.FY2019 | Purchase 1 M-400 WMR Tower for Paducah. Location is 2967 Bandana Road, Paducah, KY. | 0 | 61437.54 | -61437.54 | -100% | 0.1037% | 58907.58 | 61437.54 | -2529.96 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-30 | 09
050.53289 | 2636.SaddlePointPhaseI | Install 2" and 4" Pe for new subdivision | 49197.72 | 61073.13 | -11875.41 | -19.44% | 0.08658% | 49197.72 | 61073.13 | -11875.41 | 2019-10-01 | 2020-09-30 | 2020-02-24 | 02 | 2020-03-23 | 03
050.51506 | 050.2638.Crittendon Relocate | Property owner building new commercial AG business, cutting and excavating very close to our existing 6 inch steel HPD gas main. We propose to replace (lower) app. 600 feet | 8247.52 | 59255.09 | -51007.57 | -86.08% | 0.09982% | 56726.21 | 59255.09 | -2528.88 | 2019-10-01 | 2020-09-30 | 2019-06-24 | 06 | 2019-09-30 | 09
050.51704 | 050.2736.BD Seamless | Replace Reg. station and Meter set at BD Seamless | 19811.32 | 58173.87 | -38362.55 | -65.94% | 0.07491% | 42565.34 | 58173.87 | -15608.53 | 2019-10-01 | 2020-09-30 | 2019-08-01 | 08 | 2019-09-30 | 09
050.49895 | KY.East Diamond.RTU.FY19 | RTU Upgrade for East Diamond Ky. Conduit, ROC, Grounding Grid. | 0 | 54689.44 | -54689.44 | -100% | 0.09862% | 56043.95 | 54689.44 | 1354.51 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-04-30 | 04
050.53763 | PRP.2636.5th-Sycamore | Install new 8" and 6" IP PE crossing that is conflicting with upcoming city paving project. New crossing will be put in service on 2021 PRP project. no services involved | 40118.58 | 53823.25 | -13704.67 | -25.46% | 0.0706% | 40118.58 | 53823.25 | -13704.67 | 2019-10-01 | 2020-09-30 | 2020-04-28 | 04 | 2021-09-30 | 09
050.50974 | 050.2739.CC Greens Drive | Install 2600 Ft of 2 In HDPE in Shelbyville KY | 31939.84 | 53745.38 | -21805.54 | -40.57% | 0.06357% | 36122.89 | 53745.38 | -17622.49 | 2019-10-01 | 2020-09-30 | 2019-05-06 | 05 | 2019-11-30 | 11
050.51471 | 2734.EagleRidgeSub | 4450' of 4" HDPE and 1620' of 2" HDPE for Eagle Rdg Sub Main will tie in to existing 8" HDPE on Cemetery Rd. Developer will open and close ditch and install casings for main and service lines. Deferred agreement with James Cook. | 11506.77 | 52895.85 | -41389.08 | -78.25% | 0.0938% | 53300.96 | 52895.85 | 405.11 | 2019-10-01 | 2020-09-30 | 2019-06-05 | 06 | 2019-09-27 | 09
050.51771 | 2634.Equipment.FY2020 | Replace (9) Sensit Golds,$13,500; Replace (3) Metro-Tech Locaters,$15,000; | 38109.72 | 51986 | -13876.28 | -26.69% | 0.06706% | 38109.72 | 51986 | -13876.28 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.52779 | 050.2637.Birch Bend Rev Ext | Install 2,360' - 2" PE for 49 new residential lots, this residential development is adjoining 10 acres of commercial property being developed currently. | 47084.86 | 49734.06 | -2649.2 | -5.327% | 0.08286% | 47084.86 | 49734.06 | -2649.2 | 2019-10-01 | 2020-09-30 | 2019-11-19 | 11 | 2020-01-31 | 01
050.45546 | 050.2636.Fairview.Spur.Reg | Replace Regulator Station for Fairview Spur and provide inlet and outlet valves. Will utlilize existing valve to existing station and add a downstream valve. Project Engineering by Chase Downing. CP technical review by James Sparks. This is a FY 2017 | -514.07 | 48496.05 | -49010.12 | -101.1% | 0.08444% | 47981.98 | 48496.05 | -514.07 | 2019-10-01 | 2020-09-30 | 2017-03-10 | 03 | 2018-11-30 | 11
050.49484 | 050.2636.Equipment.FY19 | Purchase 1-Fusion Testing Machine, 1-Central Boss III Electofusion Machine, 4-Ritmo Turbo Peeler Kit, 4-Sensit Glods, 5-RYCO Stick Locaters,1-Juno WMR, 1-Pelican 9470M, 1-PJ. Trailer, 1-ERX Mercury | -7137.27 | 48209.74 | -55347.01 | -114.8% | 0.07123% | 40476.7 | 48209.74 | -7733.04 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-05-30 | 05
050.51607 | 2636.YoungDr. | Install 1600' of 2" PE. Main for new customers | 5966.53 | 47252.05 | -41285.52 | -87.37% | 0.08468% | 48118.93 | 47252.05 | 866.88 | 2019-10-01 | 2020-09-30 | 2019-09-02 | 09 | 2019-09-24 | 09
050.52389 | 2612.KY Corrector Repl FY20 | Replacement of Obsolete or Defective Electronic Correctors in Kentucky. | 41502.14 | 46773.5 | -5271.36 | -11.27% | 0.07303% | 41502.14 | 46773.5 | -5271.36 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-02-29 | 02
050.52571 | 050.2735.Carnation Relocation | Relocate 300 Ft of 4 In and Kill 350 Ft of 4 In to Remove Conflicts with City Project | 48639 | 44965.89 | 3673.11 | 8.169% | 0.08559% | 48639 | 44965.89 | 3673.11 | 2019-10-01 | 2020-09-30 | 2019-11-04 | 11 | 2019-12-27 | 12
050.51702 | 050.2638.Houseman Tie-Back | We would like to retire a 4 inch valve that is on a 36 PSI system by runnin app. 520 feet of 4 inch poly pipe that would be a 59 PSI system. | 1590.66 | 44848.42 | -43257.76 | -96.45% | 0.05312% | 30186.36 | 44848.42 | -14662.06 | 2019-10-01 | 2020-09-30 | 2019-07-01 | 07 | 2019-09-28 | 09
050.53912 | 2734.Carter.Crossing.Ext | 1867 ft. of 6 inch and 5617 ft, of 2 inch HDPE will serve New Subdivision for Carter Crossigs lcated off Cumberland Trade in Bowling Geen. Extension will serve 31 Mulit-Family and 121 Siingle Family residentiial lots. Developer provided ditch. | 32313.29 | 42374.79 | -10061.5 | -23.74% | 0.05686% | 32313.29 | 42374.79 | -10061.5 | 2019-10-01 | 2020-09-30 | 2020-05-18 | 05 | 2020-07-31 | 07
050.52647 | 2634.JonesRd.StationUpgrade | Install 300' of 2" PE. Upgrade Farm Tap Station | 39178.12 | 41693.63 | -2515.51 | -6.033% | 0.06894% | 39178.12 | 41693.63 | -2515.51 | 2019-10-01 | 2020-09-30 | 2019-01-02 | 01 | 2020-02-28 | 02
050.51650 | 050.2609.Nortonville Purchase | Rebuild Purchase Station at Nortonville Purchase | -12.37 | 41216.95 | -41229.32 | -100% | 0.05133% | 29170.92 | 41216.95 | -12046.03 | 2019-10-01 | 2020-09-30 | 2019-08-01 | 08 | 2019-09-01 | 09
050.54661 | 2734.Misc.Equipment.FY2021 | Purchase 1 Mueller EH-5 Drilling Machine ($4,200), 5 Sensits G2 Gas Detectors ($8,500), 1 Chart Recorder for Testing Mains ($4,000), 2 All Pro Locators ($7,600), 1 Ingersoll Rand Air Compressor Shop ($2,200), 1 Enhanced Meter Valve Changer Kit ¾” – 1 1/ | 0 | 41034.94 | -41034.94 | -100% | 0% | 0 | 41034.94 | -41034.94 | 2019-10-01 | 2020-09-30 | 2020-10-01 | 10 | 2021-01-31 | 01
050.52624 | 050.2637.Bleich Relocate 2019 | McCracken County Board of Education is building a new Lone Oak Middle School. Part of that project is adding turn lanes to the existing Bleich Rd. Our existing 2 inch steel gas main is affected by the cut for the turn lane. Install 950 feet of 2 " PE | 11733.92 | 37049.56 | -25315.64 | -68.33% | 0.02065% | 11733.92 | 37049.56 | -25315.64 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-03-31 | 03
050.50971 | Estes Ln Easements | This project is to capture the costs associated with securing easements only. Originally the plan was to install some 2,600 of 6 inch poly of "reinforcement", we have moved the pipe installation to the 2020 Fiscal year. This 2019 FY project is for easeme | 3364.98 | 36823.39 | -33458.41 | -90.86% | 0.06096% | 34639.38 | 36823.39 | -2184.01 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2020-09-30 | 09
050.50660 | 2734.RiversLandingEdgeExt | 2960 ft. of 4 inch HDPE and 3940 ft. of 2 inch HDPE will serve 134 lots in new residentail development for Rivers Landing Edge located off Mcfaddin Station St. Developer will open and close ditch ans install casings for main -svc lines | 21364.29 | 34372.72 | -13008.43 | -37.85% | 0.0381% | 21650.65 | 34372.72 | -12722.07 | 2019-10-01 | 2020-09-30 | 2019-02-19 | 02 | 2020-09-30 | 09
050.51161 | 050.2638.Slaughter Imp Growth | Existing gas main running west along E Slaughter Rd is 3/4 inch dupont plastic pipe. A customer is interested in a 800 ft. revenue extension. We want to replace the 700' of 3/4 pls with 2" poly, then 800' more poly for new customer | 23579.85 | 34201.4 | -10621.55 | -31.06% | 0.06195% | 35201.96 | 34201.4 | 1000.56 | 2019-10-01 | 2020-09-30 | 2019-07-01 | 07 | 2019-09-28 | 09
050.50788 | 050.2637.Blandville Relocate | Ky Transportation Cabinet is widening Blandville Rd (US Hwy 62) from Olivet Church Rd to just west of McCracken Blvd. We have 4 inch gas main affected at three locations and one 2 inch gas service affected. | -42459.87 | 33968.71 | -76428.58 | -225% | 0.05647% | 32089.77 | 33968.71 | -1878.94 | 2019-10-01 | 2020-09-30 | 2019-03-04 | 03 | 2019-09-30 | 09
050.52369 | 3302.KY.MDT.FY20.Phase 1 | Purchase replacement MDTs for Kentucky - Phase 1 | 34011.77 | 33943.8 | 67.97 | 0.2002% | 0.05985% | 34011.77 | 33943.8 | 67.97 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.50882 | 2734.Scottsville,Rd.Reloc.II | Relocated 850 ft. of 4 inch PE main in conjunction with new developmentat 5473 Scottsville Rd. Main will tie in to existing 4 inch HDPE on Scottsville Rd. | 25840.22 | 33645.31 | -7805.09 | -23.2% | 0.06131% | 34841.5 | 33645.31 | 1196.19 | 2019-10-01 | 2020-09-30 | 2019-03-21 | 03 | 2019-09-27 | 09
050.50367 | 2734.Upton.Farms.Ext.-B.G. | 305 ft.of 6 inch, 1815 ft. of 4 inch and 1975 ft. of 2 inch HDPE will serve -72 new residential lot in Upton Farm Sub. located off Scottsville Rd. at Upton Rd.Developer will open and close ditch and provide diretional bore of Scottsville Rd. | -3740.93 | 33472.94 | -37213.87 | -111.2% | 0.06292% | 35757.4 | 33472.94 | 2284.46 | 2019-10-01 | 2020-09-30 | 2019-01-07 | 01 | 2019-08-31 | 08
050.50808 | 050.2637.Falconite Oakes Ext | Install 1,475 feet of 2 inch PE gas main for 9 new commercial lots being developed by Falconite, Inc. We are installing an extra 600 feet of 2 inch PE in order to avoid installing a reg sta. it is included in the 1,475 feet | 32919.42 | 33173.63 | -254.21 | -0.7663% | 0.063% | 35799.42 | 33173.63 | 2625.79 | 2019-10-01 | 2020-09-30 | 2019-04-01 | 04 | 2019-11-30 | 11
050.52472 | 050.2635.Trigg Elem Relocate | Trigg County Primary School building a new additipon (gymnasium). Our existing 3 inch steel gas main is in the way. We propose to install 250 feet of new 3 inch steel main and abandon a like amount of 3 inch steel.. This is reimbursable. | 8143.82 | 32711.79 | -24567.97 | -75.1% | 0.01433% | 8143.82 | 32711.79 | -24567.97 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.52846 | Concrete Slabs Glasgow Office | Concrete slabs for the storage containers at Glasgow service center. | 35758.97 | 31852.5 | 3906.47 | 12.26% | 0.06293% | 35758.97 | 31852.5 | 3906.47 | 2019-10-01 | 2020-09-30 | 2019-12-01 | 12 | 2020-01-31 | 01
050.52631 | 2636.5900MillersMillRd. | Install 650' of 2"PE for new customer | 9376.89 | 31220.17 | -21843.28 | -69.97% | 0.0165% | 9376.89 | 31220.17 | -21843.28 | 2019-10-01 | 2020-09-30 | 2019-11-06 | 11 | 2019-11-30 | 11
050.51768 | 2736.Equipment.FY2020 | Replace (2) Sensit Gold, $3,800; Purchase (1) No- Blow Stop Changer, $3,200; Replace Boss II E.F. Machine, $3,700; Purchase (2) Junos, $5,600; Purchase (1) McElroy Mini Tool, $2,300; Purchase (2) SCBA respirators, $6,600. | 30662.85 | 30824.64 | -161.79 | -0.5249% | 0.05396% | 30662.85 | 30824.64 | -161.79 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.51781 | 2737.Equipment.FY2020 | 2 Sensit G-2, $3,928; 1 Odorometer, $4,500; 2 No Blo Stop Changer, $6,400; 1 Ditch Witch locator, $5,000; 1 Heath GMI 700 leak detection unit, $5,300. | 30445.87 | 30736.57 | -290.7 | -0.9458% | 0.05358% | 30445.87 | 30736.57 | -290.7 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.52385 | 2612.KY.Emergency Regulators | Emergency Replacement of regulators in KY | 27362.3 | 30628.01 | -3265.71 | -10.66% | 0.04815% | 27362.3 | 30628.01 | -3265.71 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-03-31 | 03
050.54520 | KY MDT Replc. Ph4.FY20 | Purchase 8 MDTs (Dell Latitude 5420 Rugged) for Kentucky operations | 26384.47 | 30578.4 | -4193.93 | -13.72% | 0.04643% | 26384.47 | 30578.4 | -4193.93 | 2019-10-01 | 2020-09-30 | 2020-07-22 | 07 | 2020-08-31 | 08
050.52348 | 2634.Structures.FY20 | Replace Gutters on Office, $6,794; Concrete drain repairs, $17,821 | 22878.77 | 30109.07 | -7230.3 | -24.01% | 0.04026% | 22878.77 | 30109.07 | -7230.3 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.51539 | 2636.MillersMillRd.Ext. | Install 900' of 2" PE. Main for new customers | 31120.02 | 29964.31 | 1155.71 | 3.857% | 0.05822% | 33083.76 | 29964.31 | 3119.45 | 2019-10-01 | 2020-09-30 | 2019-08-01 | 08 | 2019-09-30 | 09
050.53682 | 050.2739.Ardmore Crossings | 2600 Ft of 2 In HDPE to serve Phase 1 of Ardmore Crossings in Shelbyville KY | 29239.69 | 29263.81 | -24.12 | -0.08242% | 0.05146% | 29239.69 | 29263.81 | -24.12 | 2019-10-01 | 2020-09-30 | 2020-04-13 | 04 | 2020-08-31 | 08
050.54402 | 2734.Oak St. Replc. | Replace 615 ft. of 1.5" Epoxy in conjunction with leak repair on Oak St. attPlumb Springs Rd. Construction by Atmos Crew. | 28450.83 | 28996.93 | -546.1 | -1.883% | 0.05007% | 28450.83 | 28996.93 | -546.1 | 2019-10-01 | 2020-09-30 | 2020-07-10 | 07 | 2020-08-28 | 08
050.50656 | 2736.DanfossMain Ext. | Install 1050' of 4" PE. Main | -18174.96 | 28862.63 | -47037.59 | -163% | 0.01522% | 8649.13 | 28862.63 | -20213.5 | 2019-10-01 | 2020-09-30 | 2019-02-11 | 02 | 2019-06-30 | 06
050.51782 | 2738.Equipment.FY2020 | Purchase 3/4 to 11/4 stop changer, $4,000; 2 four inch TDW shortstop valves, $10,000; Heath odorant detector $4,700; 3 Sensit G2s, $4,500. | 17142.19 | 28378.24 | -11236.05 | -39.59% | 0.03017% | 17142.19 | 28378.24 | -11236.05 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-30 | 01
050.51483 | 050.2739.The Fairways | Install 1400 Ft of 2 In HDPE to serve Cardinal Club | 31612.7 | 28212.69 | 3400.01 | 12.05% | 0.05928% | 33683.65 | 28212.69 | 5470.96 | 2019-10-01 | 2020-09-30 | 2019-06-17 | 06 | 2019-11-30 | 11
050.53081 | COM.2734.A. FranklinBerryJr. | 1045 ft, of 2 inch HDPE wil serve New Commercia Development for A Franklin Berry Sub. Main will tie in to existing 2 inch HDPE on Nashvile Rd. at TAZ Trucking. | 2201.07 | 28076.74 | -25875.67 | -92.16% | 0.003873% | 2201.07 | 28076.74 | -25875.67 | 2019-10-01 | 2020-09-30 | 2019-12-11 | 12 | 2020-08-30 | 08
050.52997 | 2734.Patton.31W.Frk | 500 ft. of 2 inch HDPE will serve new Five Star in Franklin. Main will tie in to existion PE main on Patton Rd. directional bores will be at 31W and Patton Rd.. Construction by Company Crew | 4703.89 | 27638.41 | -22934.52 | -82.98% | 0.008278% | 4703.89 | 27638.41 | -22934.52 | 2019-10-01 | 2020-09-30 | 2019-12-12 | 12 | 2020-03-31 | 03
050.51774 | 2609.Mueller Machine.FY2020 | Purchase C1-36 Mueller machine. | 28829.88 | 26910.4 | 1919.48 | 7.133% | 0.05073% | 28829.88 | 26910.4 | 1919.48 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.53628 | 2734.LoversLn.6.inch Replc | Replace 500 ft. of 6 inch PE in conjunction with main damaged caused by an outside contractor. Damaged was caused by directional bore that parallels gas main on Lovers Ln. at Searcy Ln. | 6379.48 | 26817.38 | -20437.9 | -76.21% | 0.01123% | 6379.48 | 26817.38 | -20437.9 | 2019-10-01 | 2020-09-30 | 2020-04-07 | 04 | 2020-06-16 | 06
050.49894 | KY.Truckline RTU.Upgrade.FY19 | RTU Upgrade for Trunkline KY. | 33.62 | 26137.94 | -26104.32 | -99.87% | 0.02674% | 15196.5 | 26137.94 | -10941.44 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-10-30 | 10
050.52505 | 050.2637.Hwy 62 E Rev Ext | Install 1,100 feet of 2 inch oly main for 2 brand new homes that have started construction. Will also make gas available to one vacant lot and 3 existing homes. | 31144.27 | 25642.23 | 5502.04 | 21.46% | 0.05481% | 31144.27 | 25642.23 | 5502.04 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-05-14 | 05
050.54284 | KY.PGM Calibration Stations.20 | Purchase 12 calibration stations for use with RKI personal gas monitors in KY. | 20303.5 | 25167.81 | -4864.31 | -19.33% | 0.03573% | 20303.5 | 25167.81 | -4864.31 | 2019-10-01 | 2020-09-30 | 2020-06-19 | 06 | 2020-09-30 | 09
050.51778 | 2609.Mueller Equipment.FY2020 | Purchase 4",6", and 8" shell cutters and 4", 6", and 8" piolit bits. | 17624.25 | 24464 | -6839.75 | -27.96% | 0.03101% | 17624.25 | 24464 | -6839.75 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-02-28 | 02
050.52994 | 2734.Shady Ln. Ext | 1000 ft. of 4 inch HDPE will serve new customer on Shady lane located off Old Scottsville Rd. Main wil tie in to existing 4 inch PR on Old Scottsville Rd. Developer wil provide and close ditch. | 7213.35 | 24113.56 | -16900.21 | -70.09% | 0.01269% | 7213.35 | 24113.56 | -16900.21 | 2019-10-01 | 2020-09-30 | 2019-12-17 | 12 | 2020-02-15 | 02
050.53185 | 2734.Highland Way.Sub | 3400 ft. of 2 inch HDPE will serve 36 new residential lots in Highland Way Subdivision located off Highland in Bowling Green Deferred Agreement. Developer will open and close ditch and install casings for main and service lines. | 22386.73 | 23583.16 | -1196.43 | -5.073% | 0.0394% | 22386.73 | 23583.16 | -1196.43 | 2019-10-01 | 2020-09-30 | 2020-02-01 | 02 | 2020-07-30 | 07
050.54670 | 2635.PineSt.Relocate | relocate approximatwly 300' of 2"PE for new culvert installation | 1025.14 | 23485.12 | -22459.98 | -95.63% | 0.001804% | 1025.14 | 23485.12 | -22459.98 | 2019-10-01 | 2020-09-30 | 2020-08-17 | 08 | 2020-09-25 | 09
050.52427 | 050.2637.Hwy 60 W Rev Ext | Install app. 1,250 feet of 2 inch poly main for a new event center being built on US Hwy 60 West across the road from the Golf Driving Range | 21499.91 | 23201.96 | -1702.05 | -7.336% | 0.03783% | 21499.91 | 23201.96 | -1702.05 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.53448 | 2734.Hunters.Crossing.Frk | 1000 ft.of 2 inch HDPE will serve 15 new Single Family lots on Hunters Crossing in Frankln KY. Main will tei in to existinh 2 inch both ways on Hunters Crossing | 18958.25 | 22698.22 | -3739.97 | -16.48% | 0.03336% | 18958.25 | 22698.22 | -3739.97 | 2019-10-01 | 2020-09-30 | 2020-03-18 | 03 | 2020-06-15 | 06
050.52489 | 2636.DillardCt. | Install approximently 1500' 2" PE for subdivision growth | 13568.59 | 22219.07 | -8650.48 | -38.93% | 0.02388% | 13568.59 | 22219.07 | -8650.48 | 2019-10-01 | 2020-09-30 | 2019-11-05 | 11 | 2019-11-08 | 11
050.51146 | 2734.Hardcastle.Sub.Ext. | 855' of 4 inch HDPE approach and 990' of 2 inch HDPE will serve new Hardcastle Sub Phse I located off Hunts Ln. Main will tie in to 8 inch HDPE currently being installed on Cemetery Rd. Jody Allen Dev. to open and close ditch. Deferred agreement | -3755.27 | 21192.9 | -24948.17 | -117.7% | 0.03325% | 18892.66 | 21192.9 | -2300.24 | 2019-10-01 | 2020-09-30 | 2019-04-23 | 04 | 2019-06-28 | 06
050.51608 | 2636.SouthHamptonRd.Main Ext. | Install 650' of 2" PE. Main for Four (4) residental customers | 23359 | 21014.24 | 2344.76 | 11.16% | 0.03805% | 21621.64 | 21014.24 | 607.4 | 2019-10-01 | 2020-09-30 | 2019-08-01 | 08 | 2019-08-23 | 08
050.51518 | 2734.Windsor.Sub.Phase.1 | 1380 ft. of 2 inch HDPE will serve 30 new redidential in Windsoe Sub. located off Elrod Rd. Main will tie in to existing 4 inch PE on Elrod Rd. Developer will open and close ditch and install casings . Deferred Agreement with Barrett Hammer | -1032.21 | 19997.61 | -21029.82 | -105.2% | 0.03441% | 19553.18 | 19997.61 | -444.43 | 2019-10-01 | 2020-09-30 | 2019-06-24 | 06 | 2019-08-30 | 08
050.54559 | 050.2636.NewBoltAnodeBed | Install new Ground Bed on New Bolt Rd. | 20883.83 | 19800 | 1083.83 | 5.474% | 0.03675% | 20883.83 | 19800 | 1083.83 | 2019-10-01 | 2020-09-30 | 2020-08-15 | 08 | 2020-09-15 | 09
050.51780 | 2735.Equipment.FY2020 | 2 Mueller No Blo Valve changers, $6,400; 1 Metro Tech Locator,$4,000; 1 Fisher TW6 Locator, $1,000; 3 Sensit G2, $4,500 | 23003.35 | 19448.88 | 3554.47 | 18.28% | 0.04048% | 23003.35 | 19448.88 | 3554.47 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.54456 | 2635.FranklinSt.DawsonSprings | Replace 200' of 4" stl., with 200' of 4" PE | 20082.21 | 19426.16 | 656.05 | 3.377% | 0.03534% | 20082.21 | 19426.16 | 656.05 | 2019-10-01 | 2020-09-30 | 2020-08-03 | 08 | 2020-08-28 | 08
050.51056 | RES.2637.Magnolia View Ext | Install 700 feet of 2 inch poly for new residential development named Magnolia View Subdivision. Developer is Randy Wiersma. 11 two unit condo's. 22 total meters | -524.68 | 19313.97 | -19838.65 | -102.7% | 0.03118% | 17720.57 | 19313.97 | -1593.4 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-09-30 | 09
050.50426 | 2734.Magnolia.Hills.Phase.I | 1454 ft. of 4 inch HDPE will serve 28 new residential lots in Phase I of Magnolia Hill located off Plano Rd. Main will tie in to existing 4 inch PE main on Plano. 4 inch will be installed for futre developement. | -4544.61 | 18418.61 | -22963.22 | -124.7% | 0.03386% | 19239.04 | 18418.61 | 820.43 | 2019-10-01 | 2020-09-30 | 2019-01-22 | 01 | 2019-07-31 | 07
050.52987 | 050.3338.S Ury St Sys Imp | We currently have 5 commercial customers being served by a 3/4 inch unmapped gas "Service". Sonic Restaurant having pressure problems. We propose to replace the service with 250 feet of new 2 inch main. Retire 250 feet of 3/4 inch svc. | 0 | 18414.48 | -18414.48 | -100% | 0% | 0 | 18414.48 | -18414.48 | 2019-10-01 | 2020-09-30 | 2020-01-08 | 01 | 2021-05-30 | 05
050.52421 | 050.2637.Hinkleville Rd Ext | Install app. 750 feet of 2 inch poly main for one new residential customer requesting gas. | 14980.77 | 18404.8 | -3424.03 | -18.6% | 0.02636% | 14980.77 | 18404.8 | -3424.03 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.53888 | 050.3338.E Palmer St Main Ext | Install 150 feet of 2 inch poly gas main for one residential customer requesting gas service. | 0 | 18397.37 | -18397.37 | -100% | 0% | 0 | 18397.37 | -18397.37 | 2019-10-01 | 2020-09-30 | 2020-05-11 | 05 | 2020-06-30 | 06
050.53552 | 050.2638.Cardinal Rd Improve | Existing gas service feeding 3 risers/ meters is in harms way on KYTC project. Propose to install 825' - 2" PE and new services to "clean up" this situation. | 21114.87 | 18070.79 | 3044.08 | 16.85% | 0.03716% | 21114.87 | 18070.79 | 3044.08 | 2019-10-01 | 2020-09-30 | 2020-03-26 | 03 | 2020-04-30 | 04
050.54307 | RES.2636.BluegrassCommons | Install 860' of 4" PE. for Subdivision Growth | 9643.92 | 17982.14 | -8338.22 | -46.37% | 0.01697% | 9643.92 | 17982.14 | -8338.22 | 2019-10-01 | 2020-09-30 | 2020-06-26 | 06 | 2020-07-20 | 07
050.52860 | 2634.Equipment.Ph 2.FY20 | Replace (2) Boss III E.F. Machines $8,000; Purchase EH5 Muller Tapping Machine $6,000. | 15487.83 | 17837.4 | -2349.57 | -13.17% | 0.02725% | 15487.83 | 17837.4 | -2349.57 | 2019-10-01 | 2020-09-30 | 2019-12-31 | 12 | 2020-02-27 | 02
050.52800 | 050.2737.Stanford Relocation | Relocate 300 Ft of 2 Inch for PVA parking lot | 18216.11 | 17690.13 | 525.98 | 2.973% | 0.03206% | 18216.11 | 17690.13 | 525.98 | 2019-10-01 | 2020-09-30 | 2019-12-02 | 12 | 2019-12-27 | 12
050.53320 | COM.2638.Gideon Crossing | 950 feet of 2 inch poly for one new commercial customer (Mayfield Veterinary Clinic) requesting gas service. | 19309.21 | 17615.46 | 1693.75 | 9.615% | 0.03398% | 19309.21 | 17615.46 | 1693.75 | 2019-10-01 | 2020-09-30 | 2020-03-01 | 03 | 2020-04-30 | 04
050.54440 | COM.2634.CadizCampGround | Install 550' of 4" PE, Install 500' of 2" PE for Camp Ground | 16745.64 | 16745.64 | 0 | 0% | 0.02947% | 16745.64 | 16745.64 | 0 | 2019-10-01 | 2020-09-30 | 2020-08-17 | 08 | 2020-09-25 | 09
050.52933 | 050.2737.Danville ERX FY20 | Install 3 ERX's in Danville Cost Center | 17143.63 | 16662.62 | 481.01 | 2.887% | 0.03017% | 17143.63 | 16662.62 | 481.01 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-04-30 | 04
050.52597 | 050.2737.KY 2141 | Run 280 Ft of 2 In HDPE to serve one customer in Stanford KY | 17999.3 | 16300.62 | 1698.68 | 10.42% | 0.03167% | 17999.3 | 16300.62 | 1698.68 | 2019-10-01 | 2020-09-30 | 2019-11-04 | 11 | 2019-11-29 | 11
050.52362 | 3302.KY.Desktops.FY20.Phase 1 | Purchase replacement desktops and monitors for KY (Phase 1) | 11949.18 | 15779.28 | -3830.1 | -24.27% | 0.02103% | 11949.18 | 15779.28 | -3830.1 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.51783 | 2739.Equipment.FY2020 | 1 Dump trailer, $9,434; 2 Sensit Gold G2, $3,362. | 13954.84 | 15652.08 | -1697.24 | -10.84% | 0.02456% | 13954.84 | 15652.08 | -1697.24 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.52069 | RES.2734.Poplar.Grove.II | 1280 ft. of4 inch HDPE will serve 20 new single family lots in Poplar Grove Sub. Phase II.Developer will open and close ditch and install casings for main and services. | 7336.28 | 15193.71 | -7857.43 | -51.72% | 0.02728% | 15503.17 | 15193.71 | 309.46 | 2019-10-01 | 2020-09-30 | 2019-09-12 | 09 | 2019-09-28 | 09
050.52424 | 050.2637.Menards Rev Ext | Install 550 feet of 2 inch poly main for the new Menards currently under construction. 6,752,000 BTU Load | 11613.24 | 15061.5 | -3448.26 | -22.89% | 0.02044% | 11613.24 | 15061.5 | -3448.26 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.54352 | 2734.Covington.Farms.Ct. | 1000 ft. of 2 inch HDPE will serve 30 new eresidential lots on Covington Farms Ct. off Elrod Rd. Main will tie in to existing 4 inch Steel main on Elrod Rd. Developer will open and cose ditch | 14561.08 | 14857.43 | -296.35 | -1.995% | 0.02562% | 14561.08 | 14857.43 | -296.35 | 2019-10-01 | 2020-09-30 | 2020-06-25 | 06 | 2020-08-31 | 08
050.52422 | 050.2637.Stonepoint Court Ext | Install 625 feet of 2 inch poly main for 4 new lots in this residential subdivision. This is phase one for developer Donny Travis. | 11029.21 | 14758.77 | -3729.56 | -25.27% | 0.01941% | 11029.21 | 14758.77 | -3729.56 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-30 | 12
050.48456 | 050.2737.Caldwell Rectifier | Budgeted replacment rectifier for Danville on Caldwell | 3.8192e-14 | 14030.29 | -14030.29 | -100% | 0.01036% | 5885.7 | 14030.29 | -8144.59 | 2019-10-01 | 2020-09-30 | 2017-10-01 | 10 | 2018-07-27 | 07
050.53131 | 2634.HarrisSt.Upgrade-cancel | Install approximentley 300' of 2" PE FOR Generator | 7970.67 | 13945.55 | -5974.88 | -42.84% | 0.01403% | 7970.67 | 13945.55 | -5974.88 | 2019-10-01 | 2020-09-30 | 2020-02-04 | 02 | 2020-02-28 | 02
050.52863 | 2738.4" TDW Shortstop Valves | Purchase 4 inch TDW shortstop valves. | 14064.47 | 13698.77 | 365.7 | 2.67% | 0.02475% | 14064.47 | 13698.77 | 365.7 | 2019-10-01 | 2020-09-30 | 2019-12-01 | 12 | 2020-02-28 | 02
050.54245 | 2736.Warehouse Electric Gate | Install new electric gate to the warehouse ($10,700) at Hopkinsville service center located at 1833 East 9th Street. | 13578.62 | 13632.87 | -54.25 | -0.3979% | 0.0239% | 13578.62 | 13632.87 | -54.25 | 2019-10-01 | 2020-09-30 | 2020-06-17 | 06 | 2020-08-31 | 08
050.54166 | 2734.Magnolis Hills II-A | Unknown ft. of 2 inch and 1000 ft. 0f 4 inch HDPE will serve Unknown single family lots in Magnoia Hill Phase II-A. Developer will open and Close ditch. | 19039.4 | 13408.41 | 5630.99 | 42% | 0.0335% | 19039.4 | 13408.41 | 5630.99 | 2019-10-01 | 2020-09-30 | 2020-06-08 | 06 | 2020-08-14 | 08
050.53075 | RES.2637.Deer Ridge Tr Ext | Install 800 feet of 2 inch poly gas main along Golf Court Dr ending at the S.E corner of Golf Court and Deer Ridge Trail making gas available to 2 new residential lots in this subdivision. | 20559 | 13392.14 | 7166.86 | 53.52% | 0.03618% | 20559 | 13392.14 | 7166.86 | 2019-10-01 | 2020-09-30 | 2020-03-01 | 03 | 2020-04-30 | 04
050.50525 | 050.2738.KY 55 Extension | 4350 Ft of 4 In HDPE Extended Along KY 55 | -5862.93 | 13333.95 | -19196.88 | -144% | 0.02596% | 14750.18 | 13333.95 | 1416.23 | 2019-10-01 | 2020-09-30 | 2019-02-04 | 02 | 2019-08-30 | 08
050.53021 | 2734.Magnolia.Hills.Phase.II | 360 ft. of 4 inch and 1055 ft. of 2 inch HDPE will serve 42 new single family lots in Phase II of Magnolis Hills Sub. located off Plano Rd. Main will tie in to existing 4 inch in Mag Hills I. Dev. will open and close ditch | 7889.2 | 13186.56 | -5297.36 | -40.17% | 0.01388% | 7889.2 | 13186.56 | -5297.36 | 2019-10-01 | 2020-09-30 | 2020-01-08 | 01 | 2020-04-30 | 04
050.54136 | 3302.HP T2600 MFP Plotter.KY | Purchase HP T2600 MFP, 36" Plotter with 36" color scanner, 6 color. Plotter will be housed in the Owensboro, KY service center. | 13203.98 | 13142.34 | 61.64 | 0.469% | 0.02324% | 13203.98 | 13142.34 | 61.64 | 2019-10-01 | 2020-09-30 | 2020-06-05 | 06 | 2020-07-15 | 07
050.54511 | RES.2734.McClellan Crossings | 1966 ft. of 2 inch HDPE will seve 41 new residential lots in McLellan Crossings Subdivision. Develper will open and close ditch and installing casings for main and services. | 6331.27 | 12862.9 | -6531.63 | -50.78% | 0.01114% | 6331.27 | 12862.9 | -6531.63 | 2019-10-01 | 2020-09-30 | 2020-07-20 | 07 | 2020-09-12 | 09
050.51493 | 2734.Baseboards BG Office | Baseboards for the Bowling Green , KY office This is a FY19 Capital Budget Item | 20.15 | 12843.6 | -12823.45 | -99.84% | 0.02169% | 12323.73 | 12843.6 | -519.87 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-12-31 | 12
050.53901 | 2636.CountFleetLoop | Install 360 of 2" PE. for new customers | 12631.37 | 12631.37 | 0 | 0% | 0.02223% | 12631.37 | 12631.37 | 0 | 2019-10-01 | 2020-09-30 | 2020-09-01 | 09 | 2020-09-11 | 09
050.53601 | RES.2636.CherryBlossomCt. | Install 650' of 2" PE. for growth in subdivision | 9424.44 | 12325.1 | -2900.66 | -23.53% | 0.01658% | 9424.44 | 12325.1 | -2900.66 | 2019-10-01 | 2020-09-30 | 2020-04-06 | 04 | 2020-04-30 | 04
050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 1450 ft.of 6 inch HP Steel Main Ext. locaetd in the BG Transpark. for Banjo, a new industrial customer. Developer to open and close ditch. Chamber will provide AIC of 100% | -61266.72 | 11798.5 | -73065.22 | -619.3% | -0.1078% | -61266.72 | 11798.5 | -73065.22 | 2019-10-01 | 2020-09-30 | 2020-04-13 | 04 | 2020-08-31 | 08
050.51851 | 2636.SturBridge | Replace 400' of 2" Stl. with 2" PE. | 856.78 | 11702.5 | -10845.72 | -92.68% | 0.001508% | 856.78 | 11702.5 | -10845.72 | 2019-10-01 | 2020-09-30 | 2019-08-07 | 08 | 2019-09-30 | 09
050.52365 | 3302.KY.Laptops.FY20.Phase 1 | Purchase replacement laptops for KY - Phase 1 | 11195.45 | 11620.4 | -424.95 | -3.657% | 0.0197% | 11195.45 | 11620.4 | -424.95 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.52366 | 3302.KY.Laptops.FY20.Phase 2 | Purchase replacement laptops for KY - Phase 2 | 12695.23 | 11620.4 | 1074.83 | 9.25% | 0.02234% | 12695.23 | 11620.4 | 1074.83 | 2019-10-01 | 2020-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.52431 | 050.2638.Remington Lower Main | Install 4 inch Mueller Stopper Ftg. Bring in Mueller truck. Stop flow of gas. Weld in 4 inch steel valve. Turn off valve. Lower 4 inch steel in place on Remington Way. | 14763.95 | 11571.18 | 3192.77 | 27.59% | 0.02598% | 14763.95 | 11571.18 | 3192.77 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.54508 | RES.2637.Villa Ridge Dr Ext 2 | Install 350 feet of 2 inch poly main for 7 new residential customers. Developer is Joe Cates Construction Company. | 11530.94 | 11486.43 | 44.51 | 0.3875% | 0.02029% | 11530.94 | 11486.43 | 44.51 | 2019-10-01 | 2020-09-30 | 2020-08-01 | 08 | 2020-09-30 | 09
050.52425 | 050.2637.Foxborough Ct Ext | Install 400 feet of 2 inch poly main for one new home, one existing home, one vacant lot where new home is to be built asap, and one vacant lot. | 9227.27 | 11093.45 | -1866.18 | -16.82% | 0.01624% | 9227.27 | 11093.45 | -1866.18 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.51598 | 2637-Isolation Valves | Install one 4 inch and one 6 inch poly valve to isolate CP areas in south Paducah. | 6603.15 | 11068.44 | -4465.29 | -40.34% | 0.02238% | 12719.35 | 11068.44 | 1650.91 | 2019-10-01 | 2020-09-30 | 2018-10-01 | 10 | 2019-09-28 | 09
050.54175 | RES.2734.McCoy Place V | 1450 ft. of 2 inch HDPE wil serve 25 new lots in McCoy Place Phase V - Developer will open and close ditch | 4609.33 | 10990.2 | -6380.87 | -58.06% | 0.008111% | 4609.33 | 10990.2 | -6380.87 | 2019-10-01 | 2020-09-30 | 2020-06-09 | 06 | 2020-08-14 | 08
050.51243 | 2734.Williamsburg.II | 1745 ft. of 2 inch HDPE will serve 20 new lots in Williamsburg Subdivision located in Franklin. Developer will open and close ditch and install casings for main and service lines. No Agreement per tariff. | 15.87 | 10816.32 | -10800.45 | -99.85% | 0.01903% | 10816.32 | 10816.32 | 0 | 2019-10-01 | 2020-09-30 | 2019-05-16 | 05 | 2019-07-31 | 07
050.51408 | 2636.LondonPikeSpurMain Ext. | Install approximantley 800' of 2" PE. for new customers | 3.81 | 10530.93 | -10527.12 | -99.96% | 0.01138% | 6466.89 | 10530.93 | -4064.04 | 2019-10-01 | 2020-09-30 | 2019-06-17 | 06 | 2019-07-30 | 07
050.50748 | 050.2637.Valley Rd Tie-Back | Install 330 feet of 2 inch pe pipe to connect two systems together | 5.13 | 10381.66 | -10376.53 | -99.95% | 0.02023% | 11494.83 | 10381.66 | 1113.17 | 2019-10-01 | 2020-09-30 | 2019-02-25 | 02 | 2019-09-30 | 09
050.53777 | 050.2634ERXMadisonville | Purchase two (2) ERX | 10065.49 | 10214.68 | -149.19 | -1.461% | 0.01771% | 10065.49 | 10214.68 | -149.19 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-05-31 | 05
050.53616 | BG Office Metal Door Awnings | Purchase 3 metal door awnings (3 x 5) for Bowling Green, KY service center | 10478.87 | 10192.8 | 286.07 | 2.807% | 0.01844% | 10478.87 | 10192.8 | 286.07 | 2019-10-01 | 2020-09-30 | 2020-03-04 | 03 | 2020-04-30 | 04
050.53483 | RES.2636.BobWhiteAve. | Install 325' of 2" PE. for new customers | 11285.31 | 10105.74 | 1179.57 | 11.67% | 0.01986% | 11285.31 | 10105.74 | 1179.57 | 2019-10-01 | 2020-09-30 | 2020-05-04 | 05 | 2020-08-01 | 08
050.53839 | 2734.Skyline.Trl.Pk.Retire | Retire 4052 ft. of 1 1/4 inch MW steel and 2015 ft. of 2 inch MW steel - Skyline Trailer Park that have Idel Risers. Retired main installed in 1968, 1969. 170 and 1972. | 1562.28 | 10099.4 | -8537.12 | -84.53% | 0.002749% | 1562.28 | 10099.4 | -8537.12 | 2019-10-01 | 2020-09-30 | 2020-05-01 | 05 | 2020-06-30 | 06
050.52526 | 2636.Brookfield | Install approximently 850' of 2" PE | 9830.77 | 10071.76 | -240.99 | -2.393% | 0.0173% | 9830.77 | 10071.76 | -240.99 | 2019-10-01 | 2020-09-30 | 2019-10-31 | 10 | 2019-11-01 | 11
050.52646 | 2636.TrifectaPhaseII | Install 635' of 2" PE, for subdivision growth | 8276.25 | 10003.63 | -1727.38 | -17.27% | 0.01456% | 8276.25 | 10003.63 | -1727.38 | 2019-10-01 | 2020-09-30 | 2019-11-06 | 11 | 2019-12-03 | 12
050.53837 | 2734.Keystone.Commons,Ext | 1800 ft. of 2 inch HDPE wil serve new commercial development - Keystone Commons. Develloper will open and close ditch. Main will tie in to existing 2 inch HDPE in the Journey Pure development | 5035.82 | 9649.92 | -4614.1 | -47.81% | 0.008862% | 5035.82 | 9649.92 | -4614.1 | 2019-10-01 | 2020-09-30 | 2020-05-05 | 05 | 2020-06-30 | 06
050.54740 | 2734.Morgantown Rd. Replc | Replace 540 ft. of 2 inch Painted steel in conjunction with leak repair - Morgantown Rd. at Media Dr. | 1786.1 | 9463.54 | -7677.44 | -81.13% | 0.003143% | 1786.1 | 9463.54 | -7677.44 | 2019-10-01 | 2020-09-30 | 2020-08-18 | 08 | 2020-09-30 | 09
050.51772 | 2635.Equipment.FY2020 | Replace Boss III E.F. Machines $4,000; Replace 2 Sensit Golds $3,000 | 8468.9 | 9174 | -705.1 | -7.686% | 0.0149% | 8468.9 | 9174 | -705.1 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.52862 | 2636.Boss III Fusion Processor | Purchase 2 Central Boss III Fusion Processors | 9951.39 | 9143.99 | 807.4 | 8.83% | 0.01751% | 9951.39 | 9143.99 | 807.4 | 2019-10-01 | 2020-09-30 | 2019-12-01 | 12 | 2020-03-31 | 03
050.53683 | COM.2735.Bald Knob Road | 3500 Ft of 2 In HDPE to serve golf course in Park City KY | -512.61 | 8980.13 | -9492.74 | -105.7% | -0.0009021% | -512.61 | 8980.13 | -9492.74 | 2019-10-01 | 2020-09-30 | 2020-04-20 | 04 | 2020-07-30 | 07
050.51767 | 2638.Equipment.FY2020 | Purchase 2 Sensit G-2 leak detectors, $3,000; Rycom marker ball locator, $4,000. | 5291.23 | 8562.4 | -3271.17 | -38.2% | 0.009311% | 5291.23 | 8562.4 | -3271.17 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.54926 | Miller Trailblazer 325 Welder | Purchase Miller Trailblazer 325 Welder with ARC reach (Serial# NA350616R) | 8769.17 | 8305.85 | 463.32 | 5.578% | 0.01543% | 8769.17 | 8305.85 | 463.32 | 2019-10-01 | 2020-09-30 | 2020-09-24 | 09 | 2020-09-30 | 09
050.51410 | 2736.HuntersEstatePhaseIII | Istall 2000' of 2" PE. for developement PhaseIII Hunters Estate | 3.03 | 7531.5 | -7528.47 | -99.96% | 0.009886% | 5617.69 | 7531.5 | -1913.81 | 2019-10-01 | 2020-09-30 | 2019-06-17 | 06 | 2019-07-31 | 07
050.54553 | RES.2734.Hardcastle.Ext | 1570 ft. of 2 inch HDPE will serve 13 new residential lots in Hardcastle Sub. located off Hunts. L.. Dwvwloper to open and close ditch nd install casings for main and servile lines. | 2648.45 | 7510.88 | -4862.43 | -64.74% | 0.004661% | 2648.45 | 7510.88 | -4862.43 | 2019-10-01 | 2020-09-30 | 2020-07-29 | 07 | 2020-08-28 | 08
050.54174 | 2734.Autums.View.Ext.B.G. | 2365 ft. of 2 inch HDPE will serve 48 new residential lots in Autumn Ridge Sub. located off Park Hille St at Iris Hill. Developer will open and close ditch | 8576.38 | 7184.68 | 1391.7 | 19.37% | 0.01509% | 8576.38 | 7184.68 | 1391.7 | 2019-10-01 | 2020-09-30 | 2020-06-09 | 06 | 2020-07-31 | 07
050.54530 | FAM.2737.Davco Drive | 3000 Ft of 2 In HDPE to serve Walker Trail Senior Living Center | 9170.37 | 7178.38 | 1991.99 | 27.75% | 0.01614% | 9170.37 | 7178.38 | 1991.99 | 2019-10-01 | 2020-09-30 | 2020-07-27 | 07 | 2020-08-30 | 08
050.50364 | 2634.MillStHanson | Install approximentley 450' of 2" PE. for new homes | -3741.82 | 7155.39 | -10897.21 | -152.3% | 0.01005% | 5708.81 | 7155.39 | -1446.58 | 2019-10-01 | 2020-09-30 | 2019-01-15 | 01 | 2019-07-31 | 07
050.50996 | 2734.NashvilleRd.2inchExt | 1000 ft. of 2 inch HDPE will serve new commercial development on Nashville Rd. Main will tie in to existing 2 inch PE service line converting to main. Developer will open and close ditch. | -928.28 | 6699.77 | -7628.05 | -113.9% | 0.008626% | 4901.82 | 6699.77 | -1797.95 | 2019-10-01 | 2020-09-30 | 2019-02-07 | 02 | 2019-05-31 | 05
050.54656 | 2739.Misc.Equipment.FY2021 | Purchase 1 No-Blo Valve Changer for .75, 1 and 1.25 IPS ($3,516), 1 Sensit Gold G2 ($1,692) | 0 | 6635.51 | -6635.51 | -100% | 0% | 0 | 6635.51 | -6635.51 | 2019-10-01 | 2020-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54135 | 2637.Parking Lot Sealing.FY20 | Sealing of Paducah, KY service center parking lot. | 6927.64 | 6370.5 | 557.14 | 8.746% | 0.01219% | 6927.64 | 6370.5 | 557.14 | 2019-10-01 | 2020-09-30 | 2020-07-01 | 07 | 2020-08-31 | 08
050.54525 | RES.2636.MeadowGoveCT. | Install 680' of 2" PE. for subdivision | 7184.82 | 6271.52 | 913.3 | 14.56% | 0.01264% | 7184.82 | 6271.52 | 913.3 | 2019-10-01 | 2020-09-30 | 2020-07-23 | 07 | 2020-07-31 | 07
050.54515 | Vivax Metrotech vLoc3 Locator | Purchase Vivax Metrotech vLoc3 Locator | 8157.52 | 6188.78 | 1968.74 | 31.81% | 0.01436% | 8157.52 | 6188.78 | 1968.74 | 2019-10-01 | 2020-09-30 | 2020-07-22 | 07 | 2020-08-31 | 08
050.52620 | 2636.StablefordPhaseII | Install 350' 2" PE. for sbdivision growth | 7333.22 | 6171.35 | 1161.87 | 18.83% | 0.0129% | 7333.22 | 6171.35 | 1161.87 | 2019-10-01 | 2020-09-30 | 2019-11-11 | 11 | 2019-11-29 | 11
050.53355 | 2734.BlueLeve.2 inch Ext | 500 ft. of 2 inch HDPE will serve 3 Churches and Tennis acility and 2 homes o Blue Level Rd.. Main will tie in to existing 2 inch PE service line that will convert to main on Blue evel and McClausland. Atmos will provic de ditcj | 1067.35 | 6137.68 | -5070.33 | -82.61% | 0.001878% | 1067.35 | 6137.68 | -5070.33 | 2019-10-01 | 2020-09-30 | 2020-03-03 | 03 | 2020-06-10 | 06
050.52583 | 050.2738.Roland Street | 1000 Ft of 2 In HDPE installed in Campbellsville KY to serve trailer park | 4386.6 | 6117.06 | -1730.46 | -28.29% | 0.007719% | 4386.6 | 6117.06 | -1730.46 | 2019-10-01 | 2020-09-30 | 2019-11-04 | 11 | 2020-02-28 | 02
050.52499 | 050.2638.Parkway Dr Rev Ext | Install 240 feet of 2 inch poly main for one new residential customer (Sylvia Rodriguez) requesting gas service. | 6024.06 | 6081.47 | -57.41 | -0.944% | 0.0106% | 6024.06 | 6081.47 | -57.41 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-12-31 | 12
050.54384 | RES.2638.US 45 Wingo Main Ext | Install 165 ft of 2 inch poly for one existing residential customer requesting gas service at 9918 St Rt 45 South. Also provides us opportunity to "clean-up" a "shared" yardline across the street | 8817.5 | 5967.46 | 2850.04 | 47.76% | 0.01552% | 8817.5 | 5967.46 | 2850.04 | 2019-10-01 | 2020-09-30 | 2020-07-13 | 07 | 2020-08-30 | 08
050.51136 | 050.2637.Pecan Drive Ext | Install 100 feet of 2 inch poly for one new residential customer (Scott Walker) at 4024 Pecan Drive. | 337.85 | 5958.67 | -5620.82 | -94.33% | 0.00674% | 3829.97 | 5958.67 | -2128.7 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-09-30 | 09
050.54058 | 2734.Forrest.Pk.Retire-Frk | Retire 1079 ft. of 1.25 inch Epoxy and 542 ft. of 2 inch MW - Forrest Park Mobile Home Park - Franklin. Project will eliminate Idel Risers | 5063.47 | 5860.93 | -797.46 | -13.61% | 0.008911% | 5063.47 | 5860.93 | -797.46 | 2019-10-01 | 2020-09-30 | 2020-05-26 | 05 | 2020-07-31 | 07
050.51810 | 2734.Traditions.III.2.inch.HD | 465 ft. of 2 inch HDPE will serve 16 new single family lots in Trditions Sub. located off Lovers Ln. Main will tie in to existing 2 inch PE in alley at Townesend and Washngton Developer will open and close ditch and install casings - main and svs. | 13.24 | 5846.73 | -5833.49 | -99.77% | 0.004815% | 2736.31 | 5846.73 | -3110.42 | 2019-10-01 | 2020-09-30 | 2019-07-22 | 07 | 2019-09-30 | 09
050.51606 | 2636.Hwy604MainExt | Install 500' of 2" PE. for new customer | 1.37 | 5622.68 | -5621.31 | -99.98% | -0.006152% | -3495.91 | 5622.68 | -9118.59 | 2019-10-01 | 2020-09-30 | 2019-07-01 | 07 | 2019-08-31 | 08
050.53749 | 2734.Logan,Estates,Retire | retire 1848 ft. of 2 inch bare steel and 2048 ft. 0f 2 inch steel main - Logan Estates Trailer Park. | 359.35 | 5603.16 | -5243.81 | -93.59% | 0.0006324% | 359.35 | 5603.16 | -5243.81 | 2019-10-01 | 2020-09-30 | 2020-04-24 | 04 | 2020-05-29 | 05
050.54778 | RES.2636.DossDr.Calhoun | Install 875' of 2" PE. for new customers | 4322.28 | 5572.87 | -1250.59 | -22.44% | 0.007606% | 4322.28 | 5572.87 | -1250.59 | 2019-10-01 | 2020-09-30 | 2020-09-01 | 09 | 2020-09-16 | 09
050.54278 | COM.2734.Old Scottsville.6,Ext | 700 ft. of 6 " ahpe will serve a new Convience-Gas Station. Main will tie in to existing newely installed main for Breckinridge Sub. AIC = $20,000.00 - FB Fuels Inc. | -8365.25 | 5293.11 | -13658.36 | -258% | -0.01472% | -8365.25 | 5293.11 | -13658.36 | 2019-10-01 | 2020-09-30 | 2020-06-23 | 06 | 2020-09-30 | 09
050.52761 | 2634.FreeTown Rd.Ret | Retire approximently 1100' of 2" PE. | 1258.13 | 5221.68 | -3963.55 | -75.91% | 0.002214% | 1258.13 | 5221.68 | -3963.55 | 2019-10-01 | 2020-09-30 | 2019-11-18 | 11 | 2019-11-30 | 11
050.53764 | RES.2636.MiddleGround | Install 450' of 2" PE. for 4 customers, thiswill also tie two (2) systems together | 9162.26 | 5112.2 | 4050.06 | 79.22% | 0.01612% | 9162.26 | 5112.2 | 4050.06 | 2019-10-01 | 2020-09-30 | 2020-06-10 | 06 | 2020-08-31 | 08
050.53191 | 2636.GreenbackRd.MainExt. | Install approximantley 500' of 2" PE Main for new customers | 4084.64 | 5007.44 | -922.8 | -18.43% | 0.007188% | 4084.64 | 5007.44 | -922.8 | 2019-10-01 | 2020-09-30 | 2020-02-17 | 02 | 2020-03-15 | 03
050.53755 | RES.2637.Lightfoot Rd Rev Ext | Install 150 feet of 2 inch poly main west along Lightfoot Rd from Harting Ridge for one existing residential customer (Bryce Lawrence) requesting gas service at 7050 Lightfoot Rd | 4116.41 | 4672.64 | -556.23 | -11.9% | 0.007244% | 4116.41 | 4672.64 | -556.23 | 2019-10-01 | 2020-09-30 | 2020-06-01 | 06 | 2020-09-30 | 09
050.54093 | RES.2738.Wilson Subdivision | 1850 Ft of 2 In HDPE to serve a subdivision in Campbellsville KY | 7398.61 | 4645.79 | 2752.82 | 59.25% | 0.01302% | 7398.61 | 4645.79 | 2752.82 | 2019-10-01 | 2020-09-30 | 2020-06-01 | 06 | 2020-08-31 | 08
050.52551 | 050.2637.Central Ave Ext 2 | Install 140 feet of 2 inch poly main for one existing residential cusatomer (James Jackson) requesting gas service. | 5852.6 | 4578.19 | 1274.41 | 27.84% | 0.0103% | 5852.6 | 4578.19 | 1274.41 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-30 | 01
050.53116 | 050.2739.Blackburn Farm Reloc | Relocate 500 Ft of 2 In HDPE to eliminate leak in farm pond | 3560.52 | 4496.11 | -935.59 | -20.81% | 0.006266% | 3560.52 | 4496.11 | -935.59 | 2019-10-01 | 2020-09-30 | 2020-01-27 | 01 | 2020-04-17 | 04
050.52500 | 050.2637.Cleary Dr Main Ext | Install 140 feet of 2 inch poly main for one existing residential customerr (Robert Frejes) requesting gas service. | 4164.88 | 4207.87 | -42.99 | -1.022% | 0.007329% | 4164.88 | 4207.87 | -42.99 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-30 | 01
050.51135 | 050.2637.Jennifer Lynn Dr Ext | Install 80 feet of 2 inch poly main for one existing resdiential customer (Bob Wollfe) at 266 Jennifer Lynn Drive | 368.63 | 4134.62 | -3765.99 | -91.08% | 0.005198% | 2954.03 | 4134.62 | -1180.59 | 2019-10-01 | 2020-09-30 | 2019-05-01 | 05 | 2019-09-30 | 09
050.52740 | 2609.Gauges.FY20 | Purchase two gauges | 4139.14 | 4077.12 | 62.02 | 1.521% | 0.007284% | 4139.14 | 4077.12 | 62.02 | 2019-10-01 | 2020-09-30 | 2019-11-20 | 11 | 2019-12-30 | 12
050.52554 | IND.2735.Cave City Ind Park | 320 Ft of 4 In HDPE to servce industrial park in Cave City | 4326.16 | 4043.53 | 282.63 | 6.99% | 0.007613% | 4326.16 | 4043.53 | 282.63 | 2019-10-01 | 2020-09-30 | 2019-11-04 | 11 | 2020-08-31 | 08
050.53002 | RES.2738.Pickett Road | 1000 Ft of 2 Inch Main to serve multiple customers along Martin Road and Pickett Road in Campbellsville | 3829.53 | 3964.44 | -134.91 | -3.403% | 0.006739% | 3829.53 | 3964.44 | -134.91 | 2019-10-01 | 2020-09-30 | 2020-01-13 | 01 | 2020-02-28 | 02
050.51773 | 2609.Equipment.FY2020 | Purchase 2 Sensit Gold CGI, $3,200. Serial #s: 59061 and 59062 | 3738.56 | 3914.24 | -175.68 | -4.488% | 0.006579% | 3738.56 | 3914.24 | -175.68 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.54039 | 2636.IndustrialLn.Hardinsburg | Move 300' Of PE. | 2938 | 3871.75 | -933.75 | -24.12% | 0.00517% | 2938 | 3871.75 | -933.75 | 2019-10-01 | 2020-09-30 | 2020-05-18 | 05 | 2020-06-30 | 06
050.52432 | 2734.Crystal Gauges | Purchase two crystal gauges for use in Bowling Green surbegion | 4129.21 | 3694.8 | 434.41 | 11.76% | 0.007266% | 4129.21 | 3694.8 | 434.41 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.52433 | 2737.Crystal Gauges | Purchase one crystal cauges for Danville operations | 2124.68 | 3694.8 | -1570.12 | -42.5% | 0.003739% | 2124.68 | 3694.8 | -1570.12 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.54164 | 2836.Chaudoin Dr. Ext. | 585 ft. of 2 inch HDPE will serve new commercial development on Chaundoin Dr. in Hopkinsville. Main will tie in to existin 4 " PE main on Ft. Campbell Blvd. | 3051.48 | 3679.17 | -627.69 | -17.06% | 0.00537% | 3051.48 | 3679.17 | -627.69 | 2019-10-01 | 2020-09-30 | 2020-06-08 | 06 | 2020-08-28 | 08
050.52785 | 050.2638.Hwy 1748 Main Ext | Install 100 feet of 2 inch poly main for one existing residential customer requesting gas service. | 5101.85 | 3466.35 | 1635.5 | 47.18% | 0.008978% | 5101.85 | 3466.35 | 1635.5 | 2019-10-01 | 2020-09-30 | 2019-11-19 | 11 | 2020-02-28 | 02
050.53046 | 2636Hwy60EHardinsburg | Install approximentley 460' of 2"PE for a new Autozone | 5221.32 | 3405.28 | 1816.04 | 53.33% | 0.009188% | 5221.32 | 3405.28 | 1816.04 | 2019-10-01 | 2020-09-30 | 2020-02-04 | 02 | 2020-04-15 | 04
050.52841 | COM.2738.Noe Road | 550 Ft of 2 In HDPE to serve 3 new chicken houses on Noe Road in Campbellsville | 2545.44 | 3313.69 | -768.25 | -23.18% | 0.004479% | 2545.44 | 3313.69 | -768.25 | 2019-10-01 | 2020-09-30 | 2019-12-16 | 12 | 2020-01-24 | 01
050.54506 | 2638.Manitowoc Ice Maker | Purchase ice maker with bin for Mayfield service center. Manitowoc Model No. UDF0190A NEO® Undercounter Ice Maker, cube-style, air-cooled, self contained, 26"W x 28"D x 38-1/2"H, production capacity up to 198 lb/24 hours at 70°/50° (140 lb AHRI certi | 3185.41 | 3198.13 | -12.72 | -0.3977% | 0.005606% | 3185.41 | 3198.13 | -12.72 | 2019-10-01 | 2020-09-30 | 2020-07-21 | 07 | 2020-07-28 | 07
050.52982 | COM.2637.Short S 16th St Ext | Install 75 feet of 2 inch poly main for one mnew commercial customer (Reliable Glass) requesting natural gas service. | 3341.87 | 3177.59 | 164.28 | 5.17% | 0.005881% | 3341.87 | 3177.59 | 164.28 | 2019-10-01 | 2020-09-30 | 2020-01-08 | 01 | 2020-01-31 | 01
050.53706 | 050.2739.Kings Highway | 430 Ft of 2 In HDPE to serve one customer in Waddy KY | 4176.48 | 3074.45 | 1102.03 | 35.84% | 0.00735% | 4176.48 | 3074.45 | 1102.03 | 2019-10-01 | 2020-09-30 | 2020-04-27 | 04 | 2020-05-29 | 05
050.52786 | 050.2637.Eva Drive Rev Ext | Install 150 feet of 2 inch poly main for one new commercial customer. | 4272.42 | 3052.62 | 1219.8 | 39.96% | 0.007518% | 4272.42 | 3052.62 | 1219.8 | 2019-10-01 | 2020-09-30 | 2020-02-01 | 02 | 2020-03-30 | 03
050.51976 | 050.2738.Saloma Road | 1200 Ft of 2 In HDPE to serve 4 customers | 3619.53 | 3019.72 | 599.81 | 19.86% | -0.002269% | -1289.14 | 3019.72 | -4308.86 | 2019-10-01 | 2020-09-30 | 2019-09-02 | 09 | 2019-09-30 | 09
050.54068 | 2636.BoothfieldRd. | Relocate 300 ft. of 2" PE. | 2371.52 | 2963.33 | -591.81 | -19.97% | 0.004173% | 2371.52 | 2963.33 | -591.81 | 2019-10-01 | 2020-09-30 | 2020-07-31 | 07 | 2020-07-31 | 07
050.22147 | 050.2638.King Dr Rev Ext | Install 645' - 2" PE | -1205.51 | 2955.17 | -4160.68 | -140.8% | 0.006366% | 3617.56 | 2955.17 | 662.39 | 2019-10-01 | 2020-09-30 | 2009-07-06 | 07 | 2012-05-23 | 05
050.54564 | RES.2636.PrudenLn | Install 560' of 2" PE. | 4340.28 | 2937.98 | 1402.3 | 47.73% | 0.007638% | 4340.28 | 2937.98 | 1402.3 | 2019-10-01 | 2020-09-30 | 2020-08-17 | 08 | 2020-08-28 | 08
050.53428 | 2636.GoshenRd. | Install 615' of 2" PE. for new customers | 6529.09 | 2902.05 | 3627.04 | 125% | 0.01149% | 6529.09 | 2902.05 | 3627.04 | 2019-10-01 | 2020-09-30 | 2020-05-01 | 05 | 2020-08-31 | 08
050.21983 | 050.2637.Lady Karen Ext | Install 580 feet of 2 inch poly for two existing customers | -680 | 2845.37 | -3525.37 | -123.9% | 0.005191% | 2949.74 | 2845.37 | 104.37 | 2019-10-01 | 2020-09-30 | 2009-04-13 | 04 | 2011-01-21 | 01
050.52403 | Mueller T Drilling Machine | Replace a Mueller "T" Drilling Machine at a cost of $2,273. | 3089.57 | 2780.33 | 309.24 | 11.12% | 0.005437% | 3089.57 | 2780.33 | 309.24 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-04-15 | 04
050.54507 | RES.2637.Highland Ch Rd 2 | Install 35 feet of 2 inch poly main for one new customer (Steve Keiler) requesting natural gas. | 130.42 | 2754.51 | -2624.09 | -95.27% | 0.0002295% | 130.42 | 2754.51 | -2624.09 | 2019-10-01 | 2020-09-30 | 2020-08-01 | 08 | 2021-09-30 | 09
050.53887 | RES.2638.Pryor St Main Ext | Install 75 feet of 2 inch poly main for one new residential customer requesting gas service at 411 Pryor St | 4030.47 | 2668.53 | 1361.94 | 51.04% | 0.007093% | 4030.47 | 2668.53 | 1361.94 | 2019-10-01 | 2020-09-30 | 2020-05-11 | 05 | 2020-05-31 | 05
050.52600 | RES.2737.Secretariat Drive | 150 ft of 2 In HDPE to serve one customer | 6072.29 | 2642.01 | 3430.28 | 129.8% | 0.01069% | 6072.29 | 2642.01 | 3430.28 | 2019-10-01 | 2020-09-30 | 2019-11-04 | 11 | 2019-12-27 | 12
050.54033 | RES.2737.Shawnee Run | 1050 Ft of 2 In HDPE to serve 5 customers in Harrodsburg KY | 1646.31 | 2443.12 | -796.81 | -32.61% | 0.002897% | 1646.31 | 2443.12 | -796.81 | 2019-10-01 | 2020-09-30 | 2020-06-01 | 06 | 2020-08-14 | 08
050.53072 | 2636.PinHighTieIn | Install 300' of 2" PE main | 1582.58 | 2299.6 | -717.02 | -31.18% | 0.002785% | 1582.58 | 2299.6 | -717.02 | 2019-10-01 | 2020-09-30 | 2020-02-04 | 02 | 2020-02-07 | 02
050.54244 | 2736.Security System.FY20 | Purchase security camera system ($1,800) for Hopkinsville service center @1833 East 9th Street. Verkada Outdoor Bullet Camera, 5MP, Varifocal Lens, 30 Days of Storage | 7504.98 | 2293.38 | 5211.6 | 227.2% | 0.01321% | 7504.98 | 2293.38 | 5211.6 | 2019-10-01 | 2020-09-30 | 2020-06-17 | 06 | 2020-08-31 | 08
050.54617 | COM.2734.Cave Mill Station | 270 ft. of 2 inch HDPE will serve and new commercial area. Main will tie in to existing 2 inch HDPE on Cave Mill Station Blvd. | 453.56 | 2147.35 | -1693.79 | -78.88% | 0.0007982% | 453.56 | 2147.35 | -1693.79 | 2019-10-01 | 2020-09-30 | 2020-08-10 | 08 | 2020-09-30 | 09
050.54696 | 2734.Williamsburg III-Frankli | 200 ft. f 2 inch HDPE will serve Williamsburg Subdivision Phase III | 1155 | 2047.08 | -892.08 | -43.58% | 0.002033% | 1155 | 2047.08 | -892.08 | 2019-10-01 | 2020-09-30 | 2020-08-18 | 08 | 2020-09-18 | 09
050.54129 | MC Miller Current Interrupter | Purchase MC Miller Current Interrupter | 1965.63 | 1993.96 | -28.33 | -1.421% | 0.003459% | 1965.63 | 1993.96 | -28.33 | 2019-10-01 | 2020-09-30 | 2020-06-04 | 06 | 2020-06-30 | 06
050.51911 | 2734.BogleTrailer Park Ret. | Retire 499 ft. of 2 inch, 2024 ft. of 1 1/4 inch and 275 ft. od 1 inch steel. - Bogle Trailer Park., off Russellville Rd. in Bowling Green | 1151.92 | 1930.75 | -778.83 | -40.34% | 0.002027% | 1151.92 | 1930.75 | -778.83 | 2019-10-01 | 2020-09-30 | 2019-08-14 | 08 | 2019-09-27 | 09
050.54059 | 2734.Retire.1.25 Stl.Holly. | Retire 993 ft. of 1.25 inch Epoxy . Project wil retire IdleRisers | 1310.6 | 1917.04 | -606.44 | -31.63% | 0.002306% | 1310.6 | 1917.04 | -606.44 | 2019-10-01 | 2020-09-30 | 2020-05-26 | 05 | 2020-07-31 | 07
050.53384 | 2636.Iceland Rd. | Install 200' of 2" PE. Main | 596.65 | 1873.73 | -1277.08 | -68.16% | 0.00105% | 596.65 | 1873.73 | -1277.08 | 2019-10-01 | 2020-09-30 | 2020-03-30 | 03 | 2020-04-10 | 04
050.21748 | 050.2637.New Holt Rd Rev Ext | Install 675' - 2" PE for new Montgomery Gardens greenhouse | -1386 | 1848 | -3234 | -175% | -0.0004011% | -227.92 | 1848 | -2075.92 | 2019-10-01 | 2020-09-30 | 2008-12-05 | 12 | 2009-09-18 | 09
050.51786 | 050.2737.Vincent Drive | 915 Ft of 2 In HDPE to serve three customers in Danville KY | 1336.48 | 1815.33 | -478.85 | -26.38% | -0.001579% | -897.32 | 1815.33 | -2712.65 | 2019-10-01 | 2020-09-30 | 2019-08-05 | 08 | 2019-08-30 | 08
050.51788 | 050.2738.Carlisle Avenue | 350 Ft of 2 In HDPE Extended Along Carlisle Ave in Greensburg KY | 3098.12 | 1793.46 | 1304.66 | 72.75% | 0.005714% | 3247.26 | 1793.46 | 1453.8 | 2019-10-01 | 2020-09-30 | 2019-08-05 | 08 | 2019-08-30 | 08
050.53308 | 2636.BurnsRd.MainExt | Install 270' of 2" PE. Main | 4043.28 | 1661.75 | 2381.53 | 143.3% | 0.007115% | 4043.28 | 1661.75 | 2381.53 | 2019-10-01 | 2020-09-30 | 2020-04-30 | 04 | 2020-04-30 | 04
050.53291 | 26536.RummageRd.MainExt. | Install appoxmately 500' od 2" Pe. for new customers | 2048.65 | 1625.18 | 423.47 | 26.06% | 0.003605% | 2048.65 | 1625.18 | 423.47 | 2019-10-01 | 2020-09-30 | 2020-03-06 | 03 | 2020-04-15 | 04
050.21750 | 050.2637.Brookhaven III | 525' - 2" PE revenue extension for three new lots in Brookhaven subd | -988 | 1481.2 | -2469.2 | -166.7% | 0.001808% | 1027.55 | 1481.2 | -453.65 | 2019-10-01 | 2020-09-30 | 2008-12-08 | 12 | 2009-09-30 | 09
050.54332 | RES.2738.Roberts Road | 250 Feet of 2 Inch Main to serve 2 customers on Roberts Road | 2394.89 | 1369.57 | 1025.32 | 74.86% | 0.004214% | 2394.89 | 1369.57 | 1025.32 | 2019-10-01 | 2020-09-30 | 2020-07-06 | 07 | 2020-08-28 | 08
050.52792 | 2638.HGDS Investments Easement | Purchase easement from HGDS Investments LLC. | 1243.62 | 1276.33 | -32.71 | -2.563% | 0.002188% | 1243.62 | 1276.33 | -32.71 | 2019-10-01 | 2020-09-30 | 2019-12-01 | 12 | 2019-12-31 | 12
050.23055 | 050.2636.Vincent Station Dr. | Install 360 Feet 2 Inch PE | -631 | 1262.01 | -1893.01 | -150% | 0.001612% | 916.29 | 1262.01 | -345.72 | 2019-10-01 | 2020-09-30 | 2009-12-08 | 12 | 2010-01-29 | 01
050.54787 | 050.2638.E South St Retire | Retire 99 feet of 2 inch steel HPD gas main | 564.23 | 1221.89 | -657.66 | -53.82% | 0.0009929% | 564.23 | 1221.89 | -657.66 | 2019-10-01 | 2020-09-30 | 2020-09-01 | 09 | 2020-09-30 | 09
050.53709 | COM.2735.Sanders St | 240 Ft of 2 In HDPE to serve one customer in Cave City | 14.08 | 1219.5 | -1205.42 | -98.85% | 2.478e-05% | 14.08 | 1219.5 | -1205.42 | 2019-10-01 | 2020-09-30 | 2020-04-20 | 04 | 2020-05-30 | 05
050.52498 | 050.2738.Canter Square | 100 Ft of 2 in HDPE to serve one customer | 488.02 | 1219.15 | -731.13 | -59.97% | 0.0008588% | 488.02 | 1219.15 | -731.13 | 2019-10-01 | 2020-09-30 | 2019-10-21 | 10 | 2019-11-22 | 11
050.54806 | FAM.2739.Bluebird Ct | 150 Ft of 2 In HDPE to feed 3 duplexes in Lawrenceburg KY | 1423.3 | 1217.96 | 205.34 | 16.86% | 0.002505% | 1423.3 | 1217.96 | 205.34 | 2019-10-01 | 2020-09-30 | 2020-09-01 | 09 | 2020-09-25 | 09
050.54693 | 050.2739.Enterprise Ct | 600 Ft of 2" HDPE to serve multiple customers | 1276.63 | 1215.39 | 61.24 | 5.039% | 0.002247% | 1276.63 | 1215.39 | 61.24 | 2019-10-01 | 2020-09-30 | 2020-08-17 | 08 | 2020-09-14 | 09
050.53618 | 2634.SlaughtersDollarStore | Install 550' of 2" PE. for Dollar General | 1951.79 | 1127.34 | 824.45 | 73.13% | 0.003435% | 1951.79 | 1127.34 | 824.45 | 2019-10-01 | 2020-09-30 | 2020-04-15 | 04 | 2020-04-29 | 04
050.53290 | 2636.MonarchRd.MainExt. | Install approximateley 750" of 2" main for new customer | 2038.49 | 832.75 | 1205.74 | 144.8% | 0.003587% | 2038.49 | 832.75 | 1205.74 | 2019-10-01 | 2020-09-30 | 2020-05-01 | 05 | 2020-05-30 | 05
050.52829 | 050.2637.Carneal Rd Retire | This project is to capture the costs associated with the retirement of our 8 inch "Transmission" main damaged on December 5, 2019 on KY 1420/Carneal Rd in western McCracken County. | 1401.27 | 500 | 901.27 | 180.3% | 0.002466% | 1401.27 | 500 | 901.27 | 2019-10-01 | 2020-09-30 | 2019-10-01 | 10 | 2020-01-31 | 01
050.52398 | 050.2738.Christerson Lane | 500 Ft of 2 In HDPE to serve one customer in Campbellsville | -223.83 | 297.16 | -520.99 | -175.3% | -0.0003939% | -223.83 | 297.16 | -520.99 | 2019-10-01 | 2020-09-30 | 2019-10-14 | 10 | 2019-11-02 | 11
050.53609 | 050.2637.Denver Av Retirement | Abandon 348 feet of 1 1/4 inch coated steel pipe installed in 1970. This gas main used to feed a mobile home park, park is gone. Property owner wants this main abandoned. | 1517.82 | 175.8 | 1342.02 | 763.4% | 0.002671% | 1517.82 | 175.8 | 1342.02 | 2019-10-01 | 2020-09-30 | 2020-04-01 | 04 | 2020-04-30 | 04
050.54428 | 2734.Lovers.Ln.2".Ext. | Convert 850' of 2 inch HDPE service to main. 1200 Lovers Ln. | 529.29 | 100 | 429.29 | 429.3% | 0.0009314% | 529.29 | 100 | 429.29 | 2019-10-01 | 2020-09-30 | 2020-07-14 | 07 | 2020-08-15 | 08
050.50702 | 2735.Sunnybrook.Retire | Retire 1538 ft. 2 inch epoxy main - Sunnybrook Trailer Park. Cave City | 69.41 | 21.35 | 48.06 | 225.1% | 0.0001221% | 69.41 | 21.35 | 48.06 | 2019-10-01 | 2020-09-30 | 2019-02-21 | 02 | 2019-03-29 | 03
050.52532 | 2636.CedarHurstRelocation | Relocate approximently 1500' of 8" Stl. | -16132.87 | -16132.87 | 0 | 0% | -0.02839% | -16132.87 | -16132.87 | 0 | 2019-10-01 | 2020-09-30 | 2019-11-05 | 11 | 2020-01-20 | 01

## 2021
Atmos Energy Corporation
(Kentucky Division)
Case No. 2024-00276
Construction Projects 2021
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised
Workpaper Reference No(s).:
Project No. | Project Title / Description |  | Annual Actual Cost 2021 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
050.22992 | 050.2735.Redbird Ext - Adair | 450 ft. - 2 inch PE - Redbird- Adairville | -2821 | 3626.46 | -6447.46 |  | -0.002324% | -1359.87 | 3626.46 | -4986.33 | 2020-10-01 | 2021-09-30 | 2009-11-07 | 11 | 2010-09-28 | 09
050.22994 | 050.2734.Ken Bale 2 Inch Ext. | 825 ft. of 2 inch PE - Ken Bale - Bowlingt Green | -1152 | 3175.59 | -4327.59 |  | -0.0007023% | -411 | 3175.59 | -3586.59 | 2020-10-01 | 2021-09-30 | 2009-11-09 | 11 | 2010-09-28 | 09
050.23048 | 2737.COMMERECE DR.PAINT SHOP | INSTALL 2in PE FOR PAINT SHOP | -2234 | 2872.29 | -5106.29 |  | -0.001072% | -627.23 | 2872.29 | -3499.52 | 2020-10-01 | 2021-09-30 | 2009-12-02 | 12 | 2010-11-17 | 11
050.23122 | 2 inch PE Ext. - Northridge V | 2 inch PE Extension - Northrigde V - Bowling Green | -1352.5 | 7861.9 | -9214.4 |  | 0.00719% | 4207.79 | 7861.9 | -3654.11 | 2020-10-01 | 2021-09-30 | 2010-01-20 | 01 | 2010-09-28 | 09
050.23173 | 050.2637.Drawbridge Trace Ext | Install 215' PE for one existing residential customer requesting natural gas | -795.2 | 1532.49 | -2327.69 |  | 0.00201% | 1175.99 | 1532.49 | -356.5 | 2020-10-01 | 2021-09-30 | 2010-02-11 | 02 | 2010-06-01 | 06
050.23520 | 050.2638.Randview Subd | Install 2,600 feet of 2" PE for 14 residential customers requesting natural gas service. | -2869 | 16453.98 | -19322.98 |  | 0.02811% | 16452.24 | 16453.98 | -1.74 | 2020-10-01 | 2021-09-30 | 2010-08-18 | 08 | 2010-09-28 | 09
050.23531 | 050.2636.Hwy 56 | Install 4100 Feet 4 Inch PE | -17933.5 | 65404.06 | -83337.56 |  | 0.05176% | 30291.91 | 65404.06 | -35112.15 | 2020-10-01 | 2021-09-30 | 2010-08-23 | 08 | 2010-09-28 | 09
050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 167369.06 | 0 |  |  | 3.423% | 2003135.79 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 5049.7 | 0 |  |  | 0.2898% | 169596.64 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 25490.29 | 0 |  |  | 0.6358% | 372037.82 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 12483.28 | 0 |  |  | 0.427% | 249868.07 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 20486.34 | 0 |  |  | 0.4272% | 250017.75 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 122505.64 | 0 |  |  | 1.693% | 990901.61 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 8876.7 | 0 |  |  | 0.2873% | 168123.09 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 24090.9 | 0 |  |  | 0.3146% | 184076.69 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 108242.95 | 0 |  |  | 2.549% | 1491954.11 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 142257.5 | 0 |  |  | 2.744% | 1605878.84 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2017-09-30 | 09
050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 38545.86 | 0 |  |  | 0.9627% | 563393.84 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 87607.3 | 0 |  |  | 2.328% | 1362363.75 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 6310.72 | 0 |  |  | 0.08127% | 47557.79 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 621.78 | 0 |  |  | 0.2436% | 142557.41 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 21490.13 | 0 |  |  | 0.4946% | 289445.49 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 30000.22 | 0 |  |  | 0.3531% | 206654.03 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 436.08 | 0 |  |  | 0.4185% | 244897.09 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 8054.31 | 0 |  |  | 0.2544% | 148879.19 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 8159.65 | 0 |  |  | 0.1951% | 114184.46 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 27961.93 | 0 |  |  | 1.176% | 688239.12 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 17933.54 | 0 |  |  | 0.6789% | 397296.34 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 9980.68 | 0 |  |  | 0.21% | 122895 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 1249784.06 | 0 |  |  | 13.96% | 8166404.12 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 101420.64 | 0 |  |  | 1.539% | 900795.61 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 62529.99 | 0 |  |  | 1.41% | 825305.41 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 89435.02 | 0 |  |  | 1.161% | 679695.67 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 133698.15 | 0 |  |  | 1.522% | 890762.39 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 331202.63 | 0 |  |  | 4.954% | 2898954.88 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 91753.23 | 0 |  |  | 1.799% | 1052697.04 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 72477.8 | 0 |  |  | 0.9218% | 539417.64 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 774352.74 | 0 |  |  | 10.01% | 5855849.87 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 302780.34 | 0 |  |  | 5.189% | 3036442.85 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2017-09-30 | 09
050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 62810.77 | 0 |  |  | 1.223% | 715676.11 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 343894.34 | 0 |  |  | 3.661% | 2142472.61 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 50569.41 | 0 |  |  | 0.6413% | 375276.07 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 32736.79 | 0 |  |  | 0.8113% | 474745.57 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 39208.65 | 0 |  |  | 0.9114% | 533340.29 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 20020.81 | 0 |  |  | 0.7601% | 444811.31 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 68728.41 | 0 |  |  | 0.7388% | 432368.87 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 35614.37 | 0 |  |  | 0.8054% | 471318.54 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 33051.01 | 0 |  |  | 0.4737% | 277178.06 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 289098.7 | 0 |  |  | 3.079% | 1801589.84 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 70006.86 | 0 |  |  | 1.822% | 1066144.29 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 33815.52 | 0 |  |  | 0.4002% | 234174.98 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 496692.6 | 0 |  |  | 7.641% | 4471369.9 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 190624.17 | 0 |  |  | 2.522% | 1475898.22 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 174450.63 | 0 |  |  | 5.867% | 3433311.29 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 387065.81 | 0 |  |  | 4.824% | 2823257.18 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 250250.16 | 0 |  |  | 2.701% | 1580716.3 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 62033.66 | 0 |  |  | 1.662% | 972783.91 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 196611.06 | 0 |  |  | 4.395% | 2571744.91 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 165894.52 | 0 |  |  | 2.433% | 1423844.36 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 881561.1 | 0 |  |  | 9.76% | 5711420.11 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 461659.06 | 0 |  |  | 7.733% | 4525433.37 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 183986.21 | 0 |  |  | 2.41% | 1410363.6 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 401465.26 | 0 |  |  | 10.36% | 6062433.2 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 72857.37 | 0 |  |  | 2.826% | 1653865.91 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 184932.44 | 0 |  |  | 3.567% | 2087131.26 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 137290.1 | 0 |  |  | 3.496% | 2045878.52 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 125963.01 | 0 |  |  | 3.153% | 1845018.99 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 91307.28 | 0 |  |  | 2.683% | 1570064.8 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 62091.68 | 0 |  |  | 3.524% | 2062203.13 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 64714.12 | 0 |  |  | 1.884% | 1102426.86 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 438079.85 | 0 |  |  | 14.46% | 8463101.14 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 215927.82 | 0 |  |  | 9.104% | 5327517.09 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 105347.38 | 0 |  |  | 3.468% | 2029424.33 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 64676.53 | 0 |  |  | 1.521% | 890247.15 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 10932.85 | 0 |  |  | 0.1967% | 115130.13 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 22903.35 | 0 |  |  | 0.885% | 517872.25 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 14939.25 | 0 |  |  | 1.167% | 682717.35 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 14416.24 | 0 |  |  | 0.2449% | 143312.79 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 11017.54 | 0 |  |  | 0.172% | 100646.18 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 22685.56 | 0 |  |  | 0.512% | 299601.69 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 5700.22 | 0 |  |  | 0.4485% | 262461.36 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 110924.37 | 0 |  |  | 0.9203% | 538529.46 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 16418.32 | 0 |  |  | 0.6841% | 400335.17 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 3860.97 | 0 |  |  | 0.1181% | 69112.5 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 149362.96 | 0 |  |  | 3.858% | 2257961.47 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 32922.67 | 0 |  |  | 1.454% | 851062.39 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 58053.19 | 0 |  |  | 1.332% | 779533.99 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 20523.02 | 0 |  |  | 1.001% | 585683.34 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 43248.51 | 0 |  |  | 0.5597% | 327518.06 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 4383.05 | 0 |  |  | 0.4135% | 241994.63 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 138729.92 | 0 |  |  | 1.167% | 682834.35 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 47378.85 | 0 |  |  | 0.6476% | 378962.28 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 83252.36 | 0 |  |  | 2.03% | 1188034 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 85071.59 | 0 |  |  | 1.754% | 1026539.08 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 19860.41 | 0 |  |  | 0.3207% | 187661.98 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 165009.03 | 0 |  |  | 3.866% | 2262533.79 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 31611.07 | 0 |  |  | 1.251% | 731922.96 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 20995.78 | 0 |  |  | 1.128% | 660055.71 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 17508.19 | 0 |  |  | 1.528% | 894121.1 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 21235.26 | 0 |  |  | 0.5504% | 322064.32 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | -5767.64 | 0 |  |  | 0.4712% | 275764.9 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 153078.7 | 0 |  |  | 1.297% | 759120.83 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 46527.99 | 0 |  |  | 0.4833% | 282803.63 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 242495.5 | 0 |  |  | 3.252% | 1902943.25 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2017-12-31 | 12
050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 87376.65 | 0 |  |  | 3.184% | 1863495.41 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 27143.68 | 0 |  |  | 0.5633% | 329611.82 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 170724.96 | 0 |  |  | 3.982% | 2330075.44 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 18606.86 | 0 |  |  | 0.983% | 575255.24 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 22292.95 | 0 |  |  | 0.6926% | 405327.76 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 39700.1 | 0 |  |  | 1.251% | 732107.73 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 16111.53 | 0 |  |  | 0.9752% | 570689.2 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 54506.41 | 0 |  |  | 0.7117% | 416463.93 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 54669.24 | 0 |  |  | 0.8465% | 495385.36 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 25485.62 | 0 |  |  | 0.4291% | 251093.53 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 170225.88 | 0 |  |  | 4.37% | 2557418.24 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 57619.81 | 0 |  |  | 1.578% | 923624.5 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 39388.9 | 0 |  |  | 0.3027% | 177165.05 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 3559.71 | 0 |  |  | 0.1272% | 74444.49 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 14.57 | 0 |  |  | 0.02245% | 13137.74 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 2425596.83 | 0 |  |  | 25.5% | 14922630.96 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 1119218.49 | 0 |  |  | 13.41% | 7847010.3 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2020-09-30 | 09
050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 894937.97 | 0 |  |  | 23.34% | 13658594.79 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 1925483.41 | 0 |  |  | 19.78% | 11577724.41 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 1380.27 | 0 |  |  | 0.02309% | 13515.01 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 253.29 | 0 |  |  | 0.01396% | 8171.11 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24183 | 050.2734.Overholt Commercial | 900 ft. of 2" PE Ext. - Overholt Commercial | -4215.8 | 4728.45 | -8944.25 |  | -0.003333% | -1950.39 | 4728.45 | -6678.84 | 2020-10-01 | 2021-09-30 | 2010-09-30 | 09 | 2011-09-28 | 09
050.24212 | 050.2636.Lucas Ln. | Install 240 Ft 2 Inch PE | -1617.12 | 2791.99 | -4409.11 |  | 0.002668% | 1561.41 | 2791.99 | -1230.58 | 2020-10-01 | 2021-09-30 | 2010-10-11 | 10 | 2010-10-24 | 10
050.24215 | 050.2636.Pantle Point | Install 980 Ft 2 Inch PE | -4308.55 | 6873.26 | -11181.81 |  | 0.006033% | 3530.4 | 6873.26 | -3342.86 | 2020-10-01 | 2021-09-30 | 2010-10-13 | 10 | 2011-09-28 | 09
050.24799 | 050.2637.Commerce Dr Ext | Install 1,350 feet of 4 inch PE pipe | -1397.19 | 13086.28 | -14483.47 |  | 0.02591% | 15164.73 | 13086.28 | 2078.45 | 2020-10-01 | 2021-09-30 | 2010-12-02 | 12 | 2011-01-21 | 01
050.24946 | 050.2636.Pleasant Valley Rd. | Install 1244 ft 2 Inch PE | -2427.16 | 8378.05 | -10805.21 |  | 0.01162% | 6799.62 | 8378.05 | -1578.43 | 2020-10-01 | 2021-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
050.24947 | 050.2636.Hwy 54 Whitesville | Install 1000 feet 2 Inch PE | -1381.19 | 6039.02 | -7420.21 |  | 0.003941% | 2306.23 | 6039.02 | -3732.79 | 2020-10-01 | 2021-09-30 | 2011-02-10 | 02 | 2011-09-28 | 09
050.25119 | 050.2634.Grapevine | Install 2,000 Ft 2" PE | -5903.31 | 35380.83 | -41284.14 | -116.7% | 0.03774% | 22083.33 | 35380.83 | -13297.5 | 2020-10-01 | 2021-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 45843.12 | 0 |  |  | 3.163% | 1850821.33 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 1493099.41 | 0 |  |  | 8.083% | 4730332.32 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 1013260.94 | 0 |  |  | 10.48% | 6133135.79 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 6907.11 | 0 |  |  | 10.44% | 6110812.96 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 623687.16 | 0 |  |  | 11.93% | 6978572.6 | Non Budgeted |  | 2020-10-01 | 2021-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.41868 | 050.2739.Shelbyville8Lateral | 4.4 miles of 8 inch HPD steel - Shelbyville Lateral | -1646.93 | 8347969.26 | -8349616.19 | -100% | 14.42% | 8436123.07 | 8347969.26 | 88153.81 | 2020-10-01 | 2021-09-30 | 2015-10-27 | 10 | 2016-12-31 | 12
050.47220 | 050.2637.Hunters Ridge Ext | Install 1,655 feet of 2 inch poly gas main to serve 34 lots in this new residential subdivision. Full deposit required from developer Brad Walker | -0.8 | 39243.2 | -39244 | -100% | 0.04651% | 27217.46 | 39243.2 | -12025.74 | 2020-10-01 | 2021-09-30 | 2018-01-01 | 01 | 2019-09-28 | 09
050.49008 | 2609.ANR Bon Harbor | This project will include the installation of approximately 4 miles of 8 inch 0.322¿ wall, X-52 pipe from ANR/TransCanada Purchase in Stanley, KY to Bon Harbor Storage field to add capacity to the system. Currently Bon Harbor storage field is being fed | -670.31 | 11815178.03 | -11815848.34 | -100% | 15.92% | 9314680.56 | 11815178.03 | -2500497.47 | 2020-10-01 | 2021-09-30 | 2018-07-01 | 07 | 2019-09-30 | 09
050.49552 | 050.2736.Central Avenue | See Long Description | 77128.73 | 701095.18 | -623966.45 | -89% | 1.511% | 883963.92 | 701095.18 | 182868.74 | 2020-10-01 | 2021-09-30 | 2018-10-01 | 10 | 2020-09-30 | 09
050.50660 | 2734.RiversLandingEdgeExt | 2960 ft. of 4 inch HDPE and 3940 ft. of 2 inch HDPE will serve 134 lots in new residentail development for Rivers Landing Edge located off Mcfaddin Station St. Developer will open and close ditch ans install casings for main -svc lines | 367.56 | 34372.72 | -34005.16 | -98.93% | 0.03763% | 22018.21 | 34372.72 | -12354.51 | 2020-10-01 | 2021-09-30 | 2019-02-19 | 02 | 2020-09-30 | 09
050.51741 | Replace individual farm taps | We have 64 individual farm tap regulators 9on transmission line) that we plan to rebuild in fiscal '20 in order to meet federal mandate. | 4399.11 | 621990.42 | -617591.31 | -99.29% | 0.3729% | 218243.16 | 621990.42 | -403747.26 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-08-30 | 08
050.51778 | 2609.Mueller Equipment.FY2020 | Purchase 4",6", and 8" shell cutters and 4", 6", and 8" piolit bits. | 8361.37 | 24464 | -16102.63 | -65.82% | 0.04441% | 25985.62 | 24464 | 1521.62 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-02-28 | 02
050.51843 | PRP.2737.Hwy 150 | See Long Descirption / notes | 146.12 | 1102903.29 | -1102757.17 | -99.99% | 1.879% | 1099438.54 | 1102903.29 | -3464.75 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-07-30 | 07
050.51844 | PRP.2734.E 9th Russellville | See Project Long Description / notes | 4258.45 | 1287273.5 | -1283015.05 | -99.67% | 2.207% | 1291531.95 | 1287273.5 | 4258.45 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51857 | PRP.2738.McCord St | See Project Long Decsription / notes | 1682.8 | 1547680.11 | -1545997.31 | -99.89% | 2.061% | 1206098.09 | 1547680.11 | -341582.02 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51867 | PRP.2734.Jackson - Pearl St | See Project Long Description / notes | 1681.9 | 1220404.46 | -1218722.56 | -99.86% | 2.023% | 1183930.1 | 1220404.46 | -36474.36 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51868 | PRP.2738.W. Walnut St Lebanon | See project Long Descrption / notes | 96.56 | 1817471.68 | -1817375.12 | -99.99% | 2.331% | 1364364.88 | 1817471.68 | -453106.8 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51876 | PRP.2738.W High St Lebanon | See Project Long Description / notes | -261.83 | 1469518.55 | -1469780.38 | -100% | 2.134% | 1248956.2 | 1469518.55 | -220562.35 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.51913 | PRP.2636.Allen Street | See project Long Description / notes | -57.24 | 802254.44 | -802311.68 | -100% | 1.072% | 627555.41 | 802254.44 | -174699.03 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-02-28 | 02
050.51957 | PRP.2735.Lexington Ave | See Long Description / notes | 23414.39 | 1367295.7 | -1343881.31 | -98.29% | 1.83% | 1071088.58 | 1367295.7 | -296207.12 | 2020-10-01 | 2021-09-30 | 2019-10-01 | 10 | 2020-09-30 | 09
050.52351 | PRP.2637.S 28th St | See Project long Description/Notes | 64629.63 | 1319204.69 | -1254575.06 | -95.1% | 2.257% | 1320970.9 | 1319204.69 | 1766.21 | 2020-10-01 | 2021-09-30 | 2019-12-25 | 12 | 2020-09-30 | 09
050.52386 | 2612.Gas Supp RTU Install FY20 | Install 4 Identified RTUs for Gas Supply visibility. 22.5K each Total 90K. These will all be wireless upgrades. | 74.52 | 112205.17 | -112130.65 | -99.93% | 0.1217% | 71195.26 | 112205.17 | -41009.91 | 2020-10-01 | 2021-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.52390 | 2612.KY.RTU Upgrades.FY20 | Replacement of Obsolete and Defective RTUs in Kentucky. 6 identified sites. Total $120,000.00 Wireless/Wired upgrades where applicable. | 117.74 | 220333.24 | -220215.5 | -99.95% | 0.3221% | 188489.07 | 220333.24 | -31844.17 | 2020-10-01 | 2021-09-30 | 2020-01-01 | 01 | 2020-09-30 | 09
050.52426 | 2734.S.Oak.Sub. Hwy 242 | 2055 of 6" approah, 3763 ft. of 4" and 1407ft. of 2 " HDPE will serve 110 single family lots in S. Oak Sub. located off Hwy 242 in Richpond. Main will be fed off 2 " reg. sta. on Hwy 242 off 6 inch HPD stl. main. Developer to open and close ditch | 987.89 | 104316.15 | -103328.26 | -99.05% | 0.2135% | 124954.17 | 104316.15 | 20638.02 | 2020-10-01 | 2021-09-30 | 2019-08-21 | 08 | 2020-09-30 | 09
050.52522 | PRP.2737. Ky 52 - Danville St | See Project Long Description/Notes | 315.16 | 1055853.82 | -1055538.66 | -99.97% | 1.595% | 933434.71 | 1055853.82 | -122419.11 | 2020-10-01 | 2021-09-30 | 2020-04-28 | 04 | 2020-09-30 | 09
050.52532 | 2636.CedarHurstRelocation | Relocate approximently 1500' of 8" Stl. | 16018.98 | 51947.13 | -35928.15 | -69.16% | -0.0001946% | -113.89 | 51947.13 | -52061.02 | 2020-10-01 | 2021-09-30 | 2019-11-05 | 11 | 2020-01-20 | 01
050.52554 | IND.2735.Cave City Ind Park | 320 Ft of 4 In HDPE to servce industrial park in Cave City | 20.78 | 4043.53 | -4022.75 | -99.49% | 0.007428% | 4346.94 | 4043.53 | 303.41 | 2020-10-01 | 2021-09-30 | 2019-11-04 | 11 | 2020-08-31 | 08
050.52883 | RES.2735.Charlie Dowling Road | 600 Ft of 2 In HDPE to serve one house on Charlie Dowling Road in Woodsonville | 1127.45 | 2185.5 | -1058.05 | -48.41% | 0.001927% | 1127.45 | 2185.5 | -1058.05 | 2020-10-01 | 2021-09-30 | 2020-01-06 | 01 | 2020-02-07 | 02
050.52895 | PRP.2636.Crabtree Ave | See Project Long Description/Notes | 8529.19 | 770828.05 | -762298.86 | -98.89% | 1.42% | 830780.74 | 770828.05 | 59952.69 | 2020-10-01 | 2021-09-30 | 2020-02-20 | 02 | 2020-08-30 | 08
050.52988 | 2734LP.Newton.Replc | 3685 ft. of 2 inch HDPE will replace existing LP Main on Newton, Herrington, Clyton, Oliver and Scottsville Rd. Contract Labor by Team Construction | 54.75 | 472787.13 | -472732.38 | -99.99% | 0.6938% | 406001.52 | 472787.13 | -66785.61 | 2020-10-01 | 2021-09-30 | 2019-11-01 | 11 | 2020-07-31 | 07
050.53086 | PRP.2634.Grapevine Rd. | See project Long Decription/ Notes | 4099.88 | 475716.86 | -471616.98 | -99.14% | 0.9089% | 531887.94 | 475716.86 | 56171.08 | 2020-10-01 | 2021-09-30 | 2020-01-24 | 01 | 2020-08-30 | 08
050.53187 | 050.2735.Glasgow LP | Replace final 2 LP systems with IP systems in Glasgow KY | 22.53 | 876604.05 | -876581.52 | -100% | 1.615% | 944827.77 | 876604.05 | 68223.72 | 2020-10-01 | 2021-09-30 | 2020-02-03 | 02 | 2020-07-30 | 07
050.53192 | 2734.Breckenridge,Sub. Ext | 5375 ft. of 6inch. 1315 of 4 ich, and 585 ft. of 2 inch HDPE will serve 44 new residential lots in Breckenridge Subdivision located off Old Scottsviil Rd . Developer to open and close ditch.Atmos will provide bore across Scottsville Rd. | -733.31 | 96948.92 | -97682.23 | -100.8% | 0.1954% | 114371.44 | 96948.92 | 17422.52 | 2020-10-01 | 2021-09-30 | 2020-01-24 | 01 | 2020-05-29 | 05
050.53251 | PRP.2734.Hwy 383 Franklin | Replace 2,891' of 6" Bare Steel with 2,979 ft of 6 Inch and 64 ft of 2 Inch IP HDPE. 29 Services | 8446.94 | 301845.61 | -293398.67 | -97.2% | 0.52% | 304327.56 | 301845.61 | 2481.95 | 2020-10-01 | 2021-09-30 | 2020-03-07 | 03 | 2020-09-30 | 09
050.53428 | 2636.GoshenRd. | Install 615' of 2" PE. for new customers | 450.96 | 11562.61 | -11111.65 | -96.1% | 0.01193% | 6980.05 | 11562.61 | -4582.56 | 2020-10-01 | 2021-09-30 | 2020-05-01 | 05 | 2020-08-31 | 08
050.53483 | RES.2636.BobWhiteAve. | Install 325' of 2" PE. for new customers | -809.41 | 10105.74 | -10915.15 | -108% | 0.0179% | 10475.9 | 10105.74 | 370.16 | 2020-10-01 | 2021-09-30 | 2020-05-04 | 05 | 2020-08-01 | 08
050.53674 | IND.2734.Proj.Banjo.6.inch.HP | 1450 ft.of 6 inch HP Steel Main Ext. locaetd in the BG Transpark. for Banjo, a new industrial customer. Developer to open and close ditch. Chamber will provide AIC of 100% | 62215.38 | 238496.08 | -176280.7 | -73.91% | 0.001621% | 948.66 | 238496.08 | -237547.42 | 2020-10-01 | 2021-09-30 | 2020-04-13 | 04 | 2020-08-31 | 08
050.53707 | PRP.2637.Old Mayfield Rd | See project long Description Notes | 20241.19 | 954741.55 | -934500.36 | -97.88% | 1.091% | 638688.41 | 954741.55 | -316053.14 | 2020-10-01 | 2021-09-30 | 2020-05-10 | 05 | 2020-09-30 | 09
050.53755 | RES.2637.Lightfoot Rd Rev Ext | Install 150 feet of 2 inch poly main west along Lightfoot Rd from Harting Ridge for one existing residential customer (Bryce Lawrence) requesting gas service at 7050 Lightfoot Rd | -5.34 | 4672.64 | -4677.98 | -100.1% | 0.007025% | 4111.07 | 4672.64 | -561.57 | 2020-10-01 | 2021-09-30 | 2020-06-01 | 06 | 2020-09-30 | 09
050.53763 | PRP.2636.5th-Sycamore | Install new 8" and 6" IP PE crossing that is conflicting with upcoming city paving project. New crossing will be put in service on 2021 PRP project. no services involved | 1076.07 | 53823.25 | -52747.18 | -98% | 0.07039% | 41194.65 | 53823.25 | -12628.6 | 2020-10-01 | 2021-09-30 | 2020-04-28 | 04 | 2021-09-30 | 09
050.53764 | RES.2636.MiddleGround | Install 450' of 2" PE. for 4 customers, thiswill also tie two (2) systems together | -592.32 | 5112.2 | -5704.52 | -111.6% | 0.01464% | 8569.94 | 5112.2 | 3457.74 | 2020-10-01 | 2021-09-30 | 2020-06-10 | 06 | 2020-08-31 | 08
050.53901 | 2636.CountFleetLoop | Install 360 of 2" PE. for new customers | -1162.86 | 12631.37 | -13794.23 | -109.2% | 0.0196% | 11468.51 | 12631.37 | -1162.86 | 2020-10-01 | 2021-09-30 | 2020-09-01 | 09 | 2020-09-11 | 09
050.53912 | 2734.Carter.Crossing.Ext | 1867 ft. of 6 inch and 5617 ft, of 2 inch HDPE will serve New Subdivision for Carter Crossigs lcated off Cumberland Trade in Bowling Geen. Extension will serve 31 Mulit-Family and 121 Siingle Family residentiial lots. Developer provided ditch. | 372.04 | 42374.79 | -42002.75 | -99.12% | 0.05585% | 32685.33 | 42374.79 | -9689.46 | 2020-10-01 | 2021-09-30 | 2020-05-18 | 05 | 2020-07-31 | 07
050.54033 | RES.2737.Shawnee Run | 1050 Ft of 2 In HDPE to serve 5 customers in Harrodsburg KY | 69.65 | 5486.37 | -5416.72 | -98.73% | 0.002932% | 1715.96 | 5486.37 | -3770.41 | 2020-10-01 | 2021-09-30 | 2020-06-01 | 06 | 2020-08-14 | 08
050.54093 | RES.2738.Wilson Subdivision | 1850 Ft of 2 In HDPE to serve a subdivision in Campbellsville KY | 117.24 | 4645.79 | -4528.55 | -97.48% | 0.01284% | 7515.85 | 4645.79 | 2870.06 | 2020-10-01 | 2021-09-30 | 2020-06-01 | 06 | 2020-08-31 | 08
050.54129 | MC Miller Current Interrupter | Purchase MC Miller Current Interrupter | 110.84 | 1993.96 | -1883.12 | -94.44% | 0.003548% | 2076.47 | 1993.96 | 82.51 | 2020-10-01 | 2021-09-30 | 2020-06-04 | 06 | 2020-06-30 | 06
050.54130 | PRP.2636.Poplar St Alley | See Project Long Description/notes | 154067.25 | 665716.73 | -511649.48 | -76.86% | 1.098% | 642275.91 | 665716.73 | -23440.82 | 2020-10-01 | 2021-09-30 | 2020-06-20 | 06 | 2020-09-30 | 09
050.54164 | 2836.Chaudoin Dr. Ext. | 585 ft. of 2 inch HDPE will serve new commercial development on Chaundoin Dr. in Hopkinsville. Main will tie in to existin 4 " PE main on Ft. Campbell Blvd. | 82.74 | 3679.17 | -3596.43 | -97.75% | 0.005356% | 3134.22 | 3679.17 | -544.95 | 2020-10-01 | 2021-09-30 | 2020-06-08 | 06 | 2020-08-28 | 08
050.54166 | 2734.Magnolis Hills II-A | Unknown ft. of 2 inch and 1000 ft. 0f 4 inch HDPE will serve Unknown single family lots in Magnoia Hill Phase II-A. Developer will open and Close ditch. | -980.77 | 13408.41 | -14389.18 | -107.3% | 0.03086% | 18058.63 | 13408.41 | 4650.22 | 2020-10-01 | 2021-09-30 | 2020-06-08 | 06 | 2020-08-14 | 08
050.54174 | 2734.Autums.View.Ext.B.G. | 2365 ft. of 2 inch HDPE will serve 48 new residential lots in Autumn Ridge Sub. located off Park Hille St at Iris Hill. Developer will open and close ditch | 63.11 | 7184.68 | -7121.57 | -99.12% | 0.01476% | 8639.49 | 7184.68 | 1454.81 | 2020-10-01 | 2021-09-30 | 2020-06-09 | 06 | 2020-07-31 | 07
050.54175 | RES.2734.McCoy Place V | 1450 ft. of 2 inch HDPE wil serve 25 new lots in McCoy Place Phase V - Developer will open and close ditch | 2106.95 | 10990.2 | -8883.25 | -80.83% | 0.01148% | 6716.28 | 10990.2 | -4273.92 | 2020-10-01 | 2021-09-30 | 2020-06-09 | 06 | 2020-08-14 | 08
050.54248 | PRP.2637.Bridge St Phase 1 | See Project Long Description/notes | 16468.6 | 311167.55 | -294698.95 | -94.71% | 0.4371% | 255791.27 | 311167.55 | -55376.28 | 2020-10-01 | 2021-09-30 | 2020-07-28 | 07 | 2020-09-30 | 09
050.54278 | COM.2734.Old Scottsville.6,Ext | 700 ft. of 6 " ahpe will serve a new Convience-Gas Station. Main will tie in to existing newely installed main for Breckinridge Sub. AIC = $20,000.00 - FB Fuels Inc. | 9130.25 | 25293.11 | -16162.86 | -63.9% | 0.001307% | 765 | 25293.11 | -24528.11 | 2020-10-01 | 2021-09-30 | 2020-06-23 | 06 | 2020-09-30 | 09
050.54279 | RES.2734.Springwater.Cove | 3440ft. of 4" and 2273 ft. of 2" HDPE wi serve 122 new residential subdvision for Springwater Cove located off John D. Jones Rd..Main will tie in to existing 4 inch HDPE in Springwater Sub. Developer will open and close ditch | 9606.32 | 46158.99 | -36552.67 | -79.19% | 0.01642% | 9606.32 | 46158.99 | -36552.67 | 2020-10-01 | 2021-09-30 | 2020-06-22 | 06 | 2020-08-14 | 08
050.54307 | RES.2636.BluegrassCommons | Install 860' of 4" PE. for Subdivision Growth | 405.55 | 17982.14 | -17576.59 | -97.74% | 0.01717% | 10049.47 | 17982.14 | -7932.67 | 2020-10-01 | 2021-09-30 | 2020-06-26 | 06 | 2020-07-20 | 07
050.54332 | RES.2738.Roberts Road | 250 Feet of 2 Inch Main to serve 2 customers on Roberts Road | 59.84 | 1703.57 | -1643.73 | -96.49% | 0.004195% | 2454.73 | 1703.57 | 751.16 | 2020-10-01 | 2021-09-30 | 2020-07-06 | 07 | 2020-08-28 | 08
050.54352 | 2734.Covington.Farms.Ct. | 1000 ft. of 2 inch HDPE will serve 30 new eresidential lots on Covington Farms Ct. off Elrod Rd. Main will tie in to existing 4 inch Steel main on Elrod Rd. Developer will open and cose ditch | 296.35 | 14857.43 | -14561.08 | -98.01% | 0.02539% | 14857.43 | 14857.43 | 0 | 2020-10-01 | 2021-09-30 | 2020-06-25 | 06 | 2020-08-31 | 08
050.54402 | 2734.Oak St. Replc. | Replace 615 ft. of 1.5" Epoxy in conjunction with leak repair on Oak St. attPlumb Springs Rd. Construction by Atmos Crew. | 546.1 | 28996.93 | -28450.83 | -98.12% | 0.04955% | 28996.93 | 28996.93 | 0 | 2020-10-01 | 2021-09-30 | 2020-07-10 | 07 | 2020-08-28 | 08
050.54428 | 2734.Lovers.Ln.2".Ext. | Convert 850' of 2 inch HDPE service to main. 1200 Lovers Ln. | 17.74 | 100 | -82.26 | -82.26% | 0.0009348% | 547.03 | 100 | 447.03 | 2020-10-01 | 2021-09-30 | 2020-07-14 | 07 | 2020-08-15 | 08
050.54440 | COM.2634.CadizCampGround | Install 550' of 4" PE, Install 500' of 2" PE for Camp Ground | -670.08 | 28208.87 | -28878.95 | -102.4% | 0.02747% | 16075.56 | 28208.87 | -12133.31 | 2020-10-01 | 2021-09-30 | 2020-08-17 | 08 | 2020-09-25 | 09
050.54456 | 2635.FranklinSt.DawsonSprings | Replace 200' of 4" stl., with 200' of 4" PE | 337.96 | 19426.16 | -19088.2 | -98.26% | 0.03489% | 20420.17 | 19426.16 | 994.01 | 2020-10-01 | 2021-09-30 | 2020-08-03 | 08 | 2020-08-28 | 08
050.54507 | RES.2637.Highland Ch Rd 2 | Install 35 feet of 2 inch poly main for one new customer (Steve Keiler) requesting natural gas. | 2837.88 | 2754.51 | 83.37 | 3.027% | 0.005072% | 2968.3 | 2754.51 | 213.79 | 2020-10-01 | 2021-09-30 | 2020-08-01 | 08 | 2021-09-30 | 09
050.54511 | RES.2734.McClellan Crossings | 1966 ft. of 2 inch HDPE will seve 41 new residential lots in McLellan Crossings Subdivision. Develper will open and close ditch and installing casings for main and services. | 6632.28 | 12862.9 | -6230.62 | -48.44% | 0.02215% | 12963.55 | 12862.9 | 100.65 | 2020-10-01 | 2021-09-30 | 2020-07-20 | 07 | 2020-09-12 | 09
050.54514 | PRP.2635.Nichols St Princeton | See Project Long Description/notes | -1836.44 | 322765.98 | -324602.42 | -100.6% | 0.594% | 347616.18 | 322765.98 | 24850.2 | 2020-10-01 | 2021-09-30 | 2020-07-28 | 07 | 2020-09-30 | 09
050.54515 | Vivax Metrotech vLoc3 Locator | Purchase Vivax Metrotech vLoc3 Locator | -186.5 | 6188.78 | -6375.28 | -103% | 0.01362% | 7971.02 | 6188.78 | 1782.24 | 2020-10-01 | 2021-09-30 | 2020-07-22 | 07 | 2020-08-31 | 08
050.54525 | RES.2636.MeadowGoveCT. | Install 680' of 2" PE. for subdivision | 249.8 | 6271.52 | -6021.72 | -96.02% | 0.0127% | 7434.62 | 6271.52 | 1163.1 | 2020-10-01 | 2021-09-30 | 2020-07-23 | 07 | 2020-07-31 | 07
050.54530 | FAM.2737.Davco Drive | 3000 Ft of 2 In HDPE to serve Walker Trail Senior Living Center | 76.29 | 7178.38 | -7102.09 | -98.94% | 0.0158% | 9246.66 | 7178.38 | 2068.28 | 2020-10-01 | 2021-09-30 | 2020-07-27 | 07 | 2020-08-30 | 08
050.54553 | RES.2734.Hardcastle.Ext | 1570 ft. of 2 inch HDPE will serve 13 new residential lots in Hardcastle Sub. located off Hunts. L.. Dwvwloper to open and close ditch nd install casings for main and servile lines. | 1229.04 | 7510.88 | -6281.84 | -83.64% | 0.006626% | 3877.49 | 7510.88 | -3633.39 | 2020-10-01 | 2021-09-30 | 2020-07-29 | 07 | 2020-08-28 | 08
050.54559 | 050.2636.NewBoltAnodeBed | Install new Ground Bed on New Bolt Rd. | -707.4 | 19800 | -20507.4 | -103.6% | 0.03448% | 20176.43 | 19800 | 376.43 | 2020-10-01 | 2021-09-30 | 2020-08-15 | 08 | 2020-09-15 | 09
050.54564 | RES.2636.PrudenLn | Install 560' of 2" PE. | -3386.44 | 5515.01 | -8901.45 | -161.4% | 0.00163% | 953.84 | 5515.01 | -4561.17 | 2020-10-01 | 2021-09-30 | 2020-08-17 | 08 | 2020-08-28 | 08
050.54596 | 050.2634.S.MadisonL/P.FY21 | Replace approximately 181' of 1.25" Stl, 1084' of 2" Stl, 5524' of 3" Stl, 9868' of 4" Stl and 490' of 6" Stl, with10570' of 2" HDPE and 2565' of 4" HDPE Retire 3 Reg. Stations | 1385443.3 | 1389570.87 | -4127.57 | -0.297% | 2.367% | 1385443.3 | 1389570.87 | -4127.57 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-04-30 | 04
050.54598 | Virgie St Reg Sta Replace.FY21 | This is an approved FY21 budgeted project. We are setting this up now due to 8 week lead time for securing new regulators. The existing Virgie Street regulator station has obsolete Fisher 630 regulators. Station also has a grade 3 (10/20/2015) leak on th | 24202.01 | 44744.25 | -20542.24 | -45.91% | 0.04136% | 24202.01 | 44744.25 | -20542.24 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54625 | PRP.2737.Danville Ave | Project was in the 7/27/20 KY PRP filing See project Long Description / notes | 795293.31 | 944896.88 | -149603.57 | -15.83% | 1.359% | 795293.31 | 944896.88 | -149603.57 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54626 | PRP.2737.Hill Ct Lancaster | Project was in the 7/27/20 KY PRP Filing See project long Descriptiion/notes | 357289.14 | 397816.3 | -40527.16 | -10.19% | 0.6105% | 357289.14 | 397816.3 | -40527.16 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-01-01 | 01
050.54631 | 2609.Misc.Equipment.FY2021 | Purchase 1 Mueller Air Power Operator ($7,500), 1 Mueller Stopping Machine Unit ($15,500), 1 Metrotech Pipeline Locator VM 810 ($6,400) and 1 Sensit Smart Calibration 360 Station for St. Charles ($5,700) | 48091.33 | 44720.91 | 3370.42 | 7.537% | 0.08218% | 48091.33 | 44720.91 | 3370.42 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54632 | 2634.Misc.Equipment.FY2021 | Purchase 1 Battery Grease Gun BW-20V-4A ($1,260), 2 Timberline Squeeze off 36" ($2,170), and 1 Metrotech 810 Locater ($3,400). | 9193.26 | 8702.1 | 491.16 | 5.644% | 0.01571% | 9193.26 | 8702.1 | 491.16 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54633 | 2635.Misc.Equipment.FY2021 | Purchase 2 Timberline Squeeze Offs 36" ($2,170), 1 Metrotech 810 Locator ($3,400), and 1 Electrofusion Boss III ($3,800) | 12695.8 | 11938.32 | 757.48 | 6.345% | 0.02169% | 12695.8 | 11938.32 | 757.48 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54634 | 2636.Misc.Equipment.FY2021 | Purchase 5 Vivax Vloc-3 Pro ($24,287), Gas Tracker ($23,000), Tapping Trailer ($4,975), 3 Stop Changer 3/4-1 1/4 ($10,800), 2 Archer w/ Command Link ($5,200), 5 Sensit Golds ($7,000), Trailer for Welding Skid ($5,000), and Boring machine Rack and Rods JT | 119369.02 | 116276.91 | 3092.11 | 2.659% | 0.204% | 119369.02 | 116276.91 | 3092.11 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54635 | 2736.Misc.Equipment.FY2021 | Purchase 2 Sensit Gold CGI ($3,200), 1 Vivax Metrotech Locator ($4,900) | 10628.11 | 10320.21 | 307.9 | 2.983% | 0.01816% | 10628.11 | 10320.21 | 307.9 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-10-31 | 10
050.54638 | 2651.Misc.Equipment.FY2021 | Purchase Pipeline Current Mapper ($12,000), Rectifier ($12,000), Heath RMLD ($16,000), Metrotech VM-810 ($3,400), and 2 Sensit Golds ($2,800) | 50928.13 | 58863.42 | -7935.29 | -13.48% | 0.08703% | 50928.13 | 58863.42 | -7935.29 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-01-31 | 01
050.54641 | 2638.Misc.Equipment.FY2021 | Purchase 2 Archer units for WMR ($4,706), Replace 3 Sensit Gold G2 units ($4,500). | 12552.93 | 11729.37 | 823.56 | 7.021% | 0.02145% | 12552.93 | 11729.37 | 823.56 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54642 | 2637.Misc.Equipment.FY2021 | Purchase 6 Archer units for WMR ($14,118), Replace 5 Sensit Gold G-2 units ($7,500), Purchase 20" Husqvarna walk behind concrete saw ($2,000). | 28275.48 | 30091.69 | -1816.21 | -6.036% | 0.04832% | 28275.48 | 30091.69 | -1816.21 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54652 | Line Tamer Sweetwater.FY21 | Purchase 1 Line Tamer Sweetwater 4" - 6" coil Pipe ($34,500); Serial #: 1RCWFJY27L1002174 | 47622.15 | 43956.45 | 3665.7 | 8.339% | 0.08138% | 47622.15 | 43956.45 | 3665.7 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54653 | 2734.RMLD Laser.FY2021 | Purchase 2 RMLD Laser Gas Detection Hand Held ($30,700) | 41535.56 | 39114.87 | 2420.69 | 6.189% | 0.07098% | 41535.56 | 39114.87 | 2420.69 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54654 | 2735.Misc.Equipment.FY2021 | Purchase Heath RMLD (CS) ($15,000), Squeeze tool C165 ($5,578), and Crystal Gauge Digital ($1,500) | 30021.97 | 28129.58 | 1892.39 | 6.727% | 0.0513% | 30021.97 | 28129.58 | 1892.39 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54655 | 2737.Misc.Equipment.FY2021 | Purchase 2 Metrotech 810 locators ($6,400), 2 No Blow Valve changer machines ($7,000), 1 McElroy 4"X6" Pitbull 26 Machine ($10,055), 2 Sensit Gold CGI (G-3) ($5,000), 1 Smartcal Sensit 360 calibrator ($5,700) | 43589.31 | 45326.11 | -1736.8 | -3.832% | 0.07449% | 43589.31 | 45326.11 | -1736.8 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54656 | 2739.Misc.Equipment.FY2021 | Purchase 1 No-Blo Valve Changer for .75, 1 and 1.25 IPS ($3,516), 1 Sensit Gold G2 ($1,692) | 6721.97 | 6635.51 | 86.46 | 1.303% | 0.01149% | 6721.97 | 6635.51 | 86.46 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54657 | 2738.Misc.Equipment.FY2021 | Purchase 4" TD Williamson valve ($12,000), 2 Pelican Remote Area Lights ($1,978) | 2820.27 | 17809.37 | -14989.1 | -84.16% | 0.004819% | 2820.27 | 17809.37 | -14989.1 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-04-30 | 04
050.54661 | 2734.Misc.Equipment.FY2021 | Purchase 1 Mueller EH-5 Drilling Machine ($4,200), 5 Sensits G2 Gas Detectors ($8,500), 1 Chart Recorder for Testing Mains ($4,000), 2 All Pro Locators ($7,600), 1 Ingersoll Rand Air Compressor Shop ($2,200), 1 Enhanced Meter Valve Changer Kit ¾” – 1 1/ | 34017.06 | 41034.94 | -7017.88 | -17.1% | 0.05813% | 34017.06 | 41034.94 | -7017.88 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-01-31 | 01
050.54663 | 2738.Trailer.FY2021 | Purchase Interstate Model 14TST trailer. (VIN# 1JKTST141MM018180) | 15961.03 | 15289.2 | 671.83 | 4.394% | 0.02727% | 15961.03 | 15289.2 | 671.83 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54667 | 2636.MTD Poly Stop.FY2021 | Purchase PE25 Tapping Machine 4", 6", & 8". | 215806.78 | 198518.79 | 17287.99 | 8.708% | 0.3688% | 215806.78 | 198518.79 | 17287.99 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54669 | Replace Mayfield Rd PRS.FY21 | This project is to capture the costs of replacing the Mayfield Road pressure reduction station at the corner of Mayfield Rd & Forsythia Drive. The regulators on this station are obsolete. We also have a grade 3 leak on the station. This original station | 39372.91 | 44906.11 | -5533.2 | -12.32% | 0.06728% | 39372.91 | 44906.11 | -5533.2 | 2020-10-01 | 2021-09-30 | 2020-11-01 | 11 | 2021-04-30 | 04
050.54670 | 2635.PineSt.Relocate | relocate approximatwly 300' of 2"PE for new culvert installation | 22605.86 | 23485.12 | -879.26 | -3.744% | 0.04038% | 23631 | 23485.12 | 145.88 | 2020-10-01 | 2021-09-30 | 2020-08-17 | 08 | 2020-09-25 | 09
050.54687 | PRP.2636.KY 1473 Greenville | Unbudgeted PRP See project Long descirption/notes | -571.32 | 1544763.95 | -1545335.27 | -100% | 0.6857% | 401257.51 | 1544763.95 | -1143506.44 | 2020-10-01 | 2021-09-30 | 2020-08-18 | 08 | 2020-09-30 | 09
050.54689 | PRP.2735.Hiseville | Project was in the 7/27/20 PRP Filing See project long description / notes | 371620.37 | 534336.46 | -162716.09 | -30.45% | 0.635% | 371620.37 | 534336.46 | -162716.09 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-04-30 | 04
050.54690 | PRP.2735.Rowletts | Project was in the 7/27/20 KY PRP Filing See project Long Description/Notes | 414258.67 | 463474.7 | -49216.03 | -10.62% | 0.708% | 414312.58 | 463474.7 | -49162.12 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-05-30 | 05
050.54693 | 050.2739.Enterprise Ct | 600 Ft of 2" HDPE to serve multiple customers | -269.79 | 1215.39 | -1485.18 | -122.2% | 0.001721% | 1006.84 | 1215.39 | -208.55 | 2020-10-01 | 2021-09-30 | 2020-08-17 | 08 | 2020-09-14 | 09
050.54694 | PRP.2735.Grandview Dr | Project was in the 7/27/20 KY PRP filing See project long description/ notes | 810139.8 | 746403.06 | 63736.74 | 8.539% | 1.384% | 810139.8 | 746403.06 | 63736.74 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54696 | 2734.Williamsburg III-Frankli | 200 ft. f 2 inch HDPE will serve Williamsburg Subdivision Phase III | -130.4 | 2047.08 | -2177.48 | -106.4% | 0.001751% | 1024.6 | 2047.08 | -1022.48 | 2020-10-01 | 2021-09-30 | 2020-08-18 | 08 | 2020-09-18 | 09
050.54723 | PRP.2737.W Broadway | Project was in the 7/27/20 KY PRP filing See project Long description / notes | 149290.17 | 438191.66 | -288901.49 | -65.93% | 0.2551% | 149290.17 | 438191.66 | -288901.49 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-02-01 | 02
050.54740 | 2734.Morgantown Rd. Replc | Replace 540 ft. of 2 inch Painted steel in conjunction with leak repair - Morgantown Rd. at Media Dr. | -98.78 | 9463.54 | -9562.32 | -101% | 0.002883% | 1687.32 | 9463.54 | -7776.22 | 2020-10-01 | 2021-09-30 | 2020-08-18 | 08 | 2020-09-30 | 09
050.54742 | PRP.2738.Perryville Rd | Project was in the 7/27/20 KY PRP filing See project Long Description / notes | 1262239.73 | 1195311.07 | 66928.66 | 5.599% | 2.157% | 1262239.73 | 1195311.07 | 66928.66 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54743 | PRP.2635.Princeton North | Project was in the 7/27/20 KY PRP filing See project long description/notes | 1681613.82 | 1570933.98 | 110679.84 | 7.045% | 2.874% | 1681613.82 | 1570933.98 | 110679.84 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-25 | 09
050.54744 | PRP.2636.25th - Clay | Project was in the 7/27/20 KY PRP filing See project long description/notes | 174039.56 | 175091.21 | -1051.65 | -0.6006% | 0.2974% | 174039.56 | 175091.21 | -1051.65 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-10-31 | 10
050.54746 | 2636.East4Th.St.LowPressure | Replace Low Pressure, Install 1025' of 8" PE., 9250' of 4" PE, 2850' of 2" PE. | 1473888.16 | 1479693.21 | -5805.05 | -0.3923% | 2.519% | 1473888.16 | 1479693.21 | -5805.05 | 2020-10-01 | 2021-09-30 | 2020-11-01 | 11 | 2021-04-30 | 04
050.54755 | 050.2634.Low Pressure Services | Service replacement for Low pressure project in Madisonville Phase I | 1079290.12 | 1091445.97 | -12155.85 | -1.114% | 1.844% | 1079290.12 | 1091445.97 | -12155.85 | 2020-10-01 | 2021-09-30 | 2020-11-01 | 11 | 2021-07-30 | 07
050.54757 | 050.2739.KY 53 Widening | Relocate approximately 250 Ft of 4 In HP Steel and 1000 Ft of 2 In IP HDPE to eliminate conflicts with the KY 53 widening in Shelbyville KY | 181329.07 | 183740.89 | -2411.82 | -1.313% | 0.3099% | 181329.07 | 183740.89 | -2411.82 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-02-28 | 02
050.54758 | PRP.2734.Brick St Franklin | Project was in the 7/27/20 KY PRP Filing See project long description /notes | 625379.29 | 655013.88 | -29634.59 | -4.524% | 1.069% | 625379.29 | 655013.88 | -29634.59 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54759 | PRP.2734.LP W Ky. Ave | Project was in the 7/27/20 KY PRP filing See Project Long Description/notes | 1077963.15 | 907464.06 | 170499.09 | 18.79% | 1.842% | 1077963.15 | 907464.06 | 170499.09 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54761 | PRP.2637.Bridge St Phase 2 | Project was in the 7/27/20 KY PRP filing See project long description /notes | 639208.84 | 827345.86 | -188137.02 | -22.74% | 1.092% | 639208.84 | 827345.86 | -188137.02 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-04-07 | 04
050.54762 | PRP.2734.4th St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 925648.9 | 952883.83 | -27234.93 | -2.858% | 1.582% | 925648.9 | 952883.83 | -27234.93 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-08-30 | 08
050.54764 | PRP.2635.Maple Ave | Project was in the KY 7/27/20 PRP Filing See project Long Description /notes | 29415.24 | 585655.93 | -556240.69 | -94.98% | 0.05027% | 29415.24 | 585655.93 | -556240.69 | 2020-10-01 | 2021-09-30 | 2021-10-01 | 10 | 2023-04-30 | 04
050.54778 | RES.2636.DossDr.Calhoun | Install 875' of 2" PE. for new customers | -1099.28 | 9150.34 | -10249.62 | -112% | 0.005508% | 3223 | 9150.34 | -5927.34 | 2020-10-01 | 2021-09-30 | 2020-09-01 | 09 | 2020-09-16 | 09
050.54787 | 050.2638.E South St Retire | Retire 99 feet of 2 inch steel HPD gas main | 6246.01 | 1221.89 | 5024.12 | 411.2% | 0.01164% | 6810.24 | 1221.89 | 5588.35 | 2020-10-01 | 2021-09-30 | 2020-09-01 | 09 | 2020-09-30 | 09
050.54796 | 050.2636.4th.St.Services LP | Replace 125 services associated with the low pressure replacement on 4th. St. | 720880.15 | 723582 | -2701.85 | -0.3734% | 1.232% | 720880.15 | 723582 | -2701.85 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2021-04-30 | 04
050.54806 | FAM.2739.Bluebird Ct | 150 Ft of 2 In HDPE to feed 3 duplexes in Lawrenceburg KY | -260.77 | 1217.96 | -1478.73 | -121.4% | 0.001987% | 1162.53 | 1217.96 | -55.43 | 2020-10-01 | 2021-09-30 | 2020-09-01 | 09 | 2020-09-25 | 09
050.54809 | PRP.2734.E 3rd St Russellvill | Project was in the 7/27/20 KY PRP filing See project long description / notes | 1070444.26 | 1028886.89 | 41557.37 | 4.039% | 1.829% | 1070444.26 | 1028886.89 | 41557.37 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-08-30 | 08
050.54811 | PRP.2734.Pearl-Boat Lndg | Project was in the 7/27/20 KY PRP filing See project decription / notes | 150400.37 | 148104.49 | 2295.88 | 1.55% | 0.257% | 150400.37 | 148104.49 | 2295.88 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-01-31 | 01
050.54812 | 2736.LP East 19th Services | Replacement of 154 services associated with Low Pressure replacement on East 19th St. This is a FY21 Caoital Project | 1040147.82 | 922791.11 | 117356.71 | 12.72% | 1.777% | 1040147.82 | 922791.11 | 117356.71 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2021-04-30 | 04
050.54816 | PRP.2635. S Mcnary St | Unbudgeted 2020 PRP See project long description / notes | 65040.14 | 400363.37 | -335323.23 | -83.75% | 0.6915% | 404665.02 | 400363.37 | 4301.65 | 2020-10-01 | 2021-09-30 | 2020-09-05 | 09 | 2020-09-30 | 09
050.54818 | 050.2737.Perryville Outage | Project created to capture charges associated with outage in Perryville, KY on September 3, 2020 due to hit main. | -26790.41 | 100234.93 | -127025.34 | -126.7% | 0.0006455% | 377.73 | 100234.93 | -99857.2 | 2020-10-01 | 2021-09-30 | 2020-09-03 | 09 | 2021-02-28 | 02
050.54822 | 2736. So. Main LP Repls.Hopk. | Replace approx 69 feet of 1 1/4", 1,712 feet of 2", 430 feet of 3", 6,085 feet of 4" and 3,445 feet of 6". Install 3,218 feet of 4" HDPE and 3,219 feet of 2" HDPE. Retire RS9935 & RS1610. Please see ACE summary Description for more details | 1105067.66 | 960658.85 | 144408.81 | 15.03% | 1.888% | 1105067.66 | 960658.85 | 144408.81 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-05-31 | 05
050.54823 | Apricot Improvements | This is an 8 building (20 meters) Benton Housing Authority property located at the corner of Apricot Ave and Cedar Street in Calvert City, KY. At one time there was a "master meter" situation. At some unknown date Atmos "took over" this property, we remo | 18199.6 | 24956.65 | -6757.05 | -27.08% | 0.0311% | 18199.6 | 24956.65 | -6757.05 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.54825 | 2736.LP S. Main Sevices | Replace 57 services associated low pressure replacement on S. Main St. in Hopkinsville, KY. | 579023.85 | 339615.1 | 239408.75 | 70.49% | 0.9895% | 579023.85 | 339615.1 | 239408.75 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2021-06-30 | 06
050.54826 | Apricot - Services | This project is to capture the costs of installing 22 services associated with the Apricot Improvements project 050.54823, this project is described below in the notes. | 30796.55 | 64001.98 | -33205.43 | -51.88% | 0.05263% | 30796.55 | 64001.98 | -33205.43 | 2020-10-01 | 2021-09-30 | 2020-11-01 | 11 | 2020-12-31 | 12
050.54830 | 2734.LP Cherry St Services | 12 service replacements in conjunction with LP Cherry St. - Franklin. This is FY21 Capital Project | 26117.8 | 71087.58 | -44969.78 | -63.26% | 0.04463% | 26117.8 | 71087.58 | -44969.78 | 2020-10-01 | 2021-09-30 | 2020-11-01 | 11 | 2021-03-31 | 03
050.54847 | 050.2736.E 19th Street | Replace 1,551 feet of of 4" Bare Stl., 966 feet of 6" Bare Stl., 1,633 feet of 2" Epoxy, 952 feet of 2" Bare Stl., 165 feet of 6" Epoxy, 182 feet of 2" Plastic, 4,769 feet of 4" Epoxy, 177 feet of 4" PE., | 1210286.07 | 924654.29 | 285631.78 | 30.89% | 2.068% | 1210286.07 | 924654.29 | 285631.78 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-03-22 | 03
050.54856 | 2734.LP.Cherry.St. - Franklin | Replacing approximately 1,000 feet 4" LP steel with 2" HDPE, tie in to make a 2 way feed in Franklin, KY. | 130781.1 | 132523.6 | -1742.5 | -1.315% | 0.2235% | 130781.1 | 132523.6 | -1742.5 | 2020-10-01 | 2021-09-30 | 2020-11-03 | 11 | 2021-03-31 | 03
050.54858 | 2638.WMR Endpoints.FY2021 | Purchase approximately 1,573 WMR endpoints for Mayfield, KY. The Mayfield work center will be 100% WMR at the conclusion of this project as well as the entire Paducah, KY subregion (Work centers of Paducah, Mayfield, and Union City). | 165725.58 | 293046.64 | -127321.06 | -43.45% | 0.2832% | 165725.58 | 293046.64 | -127321.06 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.55120 | 2736.Office Bathroom Remodel | Remodel office bathrooms at Hopkinsville service center (1833 East 9th Street). Contractor is AKS Flooring & Design Center. | 16674.2 | 16563.3 | 110.9 | 0.6696% | 0.02849% | 16674.2 | 16563.3 | 110.9 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-30 | 12
050.55121 | 2736.Warehouse Concrete.FY21 | Concrete area around new Hopkinsville warehouse ($64,300) located at 1833 East 9th Street. | 83761.82 | 81924.63 | 1837.19 | 2.243% | 0.1431% | 83761.82 | 81924.63 | 1837.19 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.55122 | 2736.Elkton YZ Odorizer FY21 | Install pole mounted YZ Odorizer for Elkton Purchase Station ($25,000). | 35895.18 | 32117.98 | 3777.2 | 11.76% | 0.06134% | 35895.18 | 32117.98 | 3777.2 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.55123 | BG.Front Office Security | Purchase security system for Bowling Green service center front main door and customer entry/exit, includes buzzer and intercom with door camera and monitor. | 5824.9 | 5096.4 | 728.5 | 14.29% | 0.009954% | 5824.9 | 5096.4 | 728.5 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-10-31 | 10
050.55124 | BG Warehouse Security | Purchase security system for main gate Bowling Green warehouse, includes keypad, intercom, and monitor. ($6,000) | 8090.2 | 7644.6 | 445.6 | 5.829% | 0.01382% | 8090.2 | 7644.6 | 445.6 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-10-31 | 10
050.55125 | BG Office Security Fence | Install chain link perimeter fence at Bowling Green service center. ($12,000) | 14588.49 | 15289.2 | -700.71 | -4.583% | 0.02493% | 14588.49 | 15289.2 | -700.71 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.55127 | 2737.Office Security Gate | Installation of security gate at Danville Office ($7,800) located at 449 Whirlaway Drive. | 11520.39 | 11257.09 | 263.3 | 2.339% | 0.01969% | 11520.39 | 11257.09 | 263.3 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.55155 | RES.2737.White Oak Road | 250 Ft of 2 In HDPE to serve two customers in Junction City | 4523.72 | 4026.51 | 497.21 | 12.35% | 0.00773% | 4523.72 | 4026.51 | 497.21 | 2020-10-01 | 2021-09-30 | 2020-10-12 | 10 | 2020-11-27 | 11
050.55156 | 050.2739.Emma Lee Relocate | Relocate 370 Ft of 2 In Main off Emma Lee Drive in Lawrenceburg | 779.92 | 1712.85 | -932.93 | -54.47% | 0.001333% | 779.92 | 1712.85 | -932.93 | 2020-10-01 | 2021-09-30 | 2020-10-12 | 10 | 2020-11-27 | 11
050.55158 | COM.2737.Legion Drive | 600 Ft of 2 In Main Along Legion Drive to Feed Campbellsville University in Harrodsburg | 917.9 | 2091.97 | -1174.07 | -56.12% | 0.001569% | 917.9 | 2091.97 | -1174.07 | 2020-10-01 | 2021-09-30 | 2020-10-12 | 10 | 2020-11-27 | 11
050.55161 | RES.2636.LittleBlueStem | install 1500' of 2" HDPE. for subdivision expansion | 18400.12 | 35270.36 | -16870.24 | -47.83% | 0.03144% | 18400.12 | 35270.36 | -16870.24 | 2020-10-01 | 2021-09-30 | 2020-11-03 | 11 | 2020-11-10 | 11
050.55162 | RES.2636.WatsonCircle | Install 1470' of 2" PE. for subdivision expansion | 22643.92 | 36563.61 | -13919.69 | -38.07% | 0.03869% | 22643.92 | 36563.61 | -13919.69 | 2020-10-01 | 2021-09-30 | 2020-10-20 | 10 | 2020-10-31 | 10
050.55163 | RES.2636.KraussCt. | Install 550' of 2" PE. for subdivision expansion | 9859.26 | 14072.95 | -4213.69 | -29.94% | 0.01685% | 9859.26 | 14072.95 | -4213.69 | 2020-10-01 | 2021-09-30 | 2020-10-08 | 10 | 2020-10-30 | 10
050.55165 | 2612. KY Emergency Reg.FY21 | Emergency Regulator Inventory for KY. | 27306.81 | 31918.87 | -4612.06 | -14.45% | 0.04666% | 27306.81 | 31918.87 | -4612.06 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-06-30 | 06
050.55166 | 2612.KY Corrector Repl.FY21 | Replacement of Obsolete or Defective Electronic Correctors in Kentucky. | 38765.79 | 44686.42 | -5920.63 | -13.25% | 0.06624% | 38765.79 | 44686.42 | -5920.63 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-06-30 | 06
050.55167 | 2612.KY RTU Upgrades.FY21 | Replacement of Obsolete and Defective RTUs in Kentucky. Total $90k Wireless/Wired upgrades where applicable. | 101255.86 | 116699.86 | -15444 | -13.23% | 0.173% | 101255.86 | 116699.86 | -15444 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-06-30 | 06
050.55176 | RES.2637.Triangle Ave Rev Ext | Install 135 feet of 2 inch poly pipe for two existing residential customers requesting natural gas | 5312.72 | 4577.46 | 735.26 | 16.06% | 0.009079% | 5312.72 | 4577.46 | 735.26 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.55180 | RES.2736.Butler Rd. 2 inch HD | Install 500 ft. of 2 inch HDPE on Buter Rd. in Hopkinsville. No Agreement per easement conditions. Directional Bore by Atmos Crew | 6701.38 | 8737.43 | -2036.05 | -23.3% | 0.01145% | 6701.38 | 8737.43 | -2036.05 | 2020-10-01 | 2021-09-30 | 2020-10-14 | 10 | 2020-11-30 | 11
050.55183 | RES.2637.Calvert Drive Ext | Install 250 feet of 2 inch poly main for one existing conversion customer requesting natural gas. House next door is a long svc, Tie it to this main and make short svc out of it. | 9893.12 | 7359.89 | 2533.23 | 34.42% | 0.01691% | 9893.12 | 7359.89 | 2533.23 | 2020-10-01 | 2021-09-30 | 2020-10-15 | 10 | 2020-11-30 | 11
050.55188 | 3302.KY Routers.FY21 | Replace routers in local offices that are at end of life or are no longer supported for Kentucky | 15821.86 | 16945.53 | -1123.67 | -6.631% | 0.02704% | 15821.86 | 16945.53 | -1123.67 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-01-31 | 01
050.55189 | 3302.KY Laptops.FY21 | Purchase replacement laptops and monitors for Kentucky. - | 17833.37 | 20385.6 | -2552.23 | -12.52% | 0.03047% | 17833.37 | 20385.6 | -2552.23 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.55190 | 3302.KY Desktops.FY21 | Purchase replacement desktop and monitors for Kentucky. - | 21543.85 | 26756.1 | -5212.25 | -19.48% | 0.03681% | 21543.85 | 26756.1 | -5212.25 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-01-31 | 01
050.55191 | 3302.KY MDT.FY21 | Purchase 5 replacement MDTs for Kentucky. | 21925.51 | 19111.5 | 2814.01 | 14.72% | 0.03747% | 21925.51 | 19111.5 | 2814.01 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.55205 | COM.2636.BENTREEDR.MN.EXT | Install 375'of 4"HDPE for storage buildings | 26631.18 | 36853.33 | -10222.15 | -27.74% | 0.04551% | 26631.18 | 36853.33 | -10222.15 | 2020-10-01 | 2021-09-30 | 2020-11-02 | 11 | 2020-12-06 | 12
050.55206 | COM.2734.The.Point.Peachtree. | 700 ft. of 2 inch HDPE will serve new commercial development for The Point at Peachtree located off Scottsville Rd. Developer will open and close ditch. | 8824.65 | 6703.3 | 2121.35 | 31.65% | 0.01508% | 8824.65 | 6703.3 | 2121.35 | 2020-10-01 | 2021-09-30 | 2020-10-16 | 10 | 2020-11-30 | 11
050.55304 | RES.2638.Twin Hill Rd Rev Ext | Install 500 feet of 2 inch poly main for one new residential customer (Josh Bowlin) requesting natural gas service. | 4207.16 | 2501.99 | 1705.17 | 68.15% | 0.007189% | 4207.16 | 2501.99 | 1705.17 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.55326 | RES.2638.Race Track Rd Ext | Install 730 feet of 2 inch poly main foe one new residential customer (David Archer) requesting gas service. | 11530.59 | 16125.32 | -4594.73 | -28.49% | 0.0197% | 11530.59 | 16125.32 | -4594.73 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2021-01-30 | 01
050.55331 | PRP.2636.Guenther Alley | **Unbudgeted PRP** Replace 245' of 1.25 Inch Hot Tar and 106' of 1.25 Inch unknown coating with 498' of 2" HDPE. 4 services involved | 6516.51 | 33357.08 | -26840.57 | -80.46% | 0.01114% | 6516.51 | 33357.08 | -26840.57 | 2020-10-01 | 2021-09-30 | 2020-10-23 | 10 | 2020-11-14 | 11
050.55340 | Sorgho KY 4" Steel 3rd Party | 3rd Party Damage - 4" cut steel line in Sorgho, KY. This is off Hwy 56 around the Whispering Meadows subdivision area. | 270142.37 | 279658.15 | -9515.78 | -3.403% | 0.4616% | 270142.37 | 279658.15 | -9515.78 | 2020-10-01 | 2021-09-30 | 2020-10-28 | 10 | 2020-11-30 | 11
050.55353 | 050.2739.Four Roses Retire | Retire approx 700 Ft of 4 In HPD Steel to eliminate conflict with Four Roses Visitor Center | -865.25 | 16277.77 | -17143.02 | -105.3% | -0.001479% | -865.25 | 16277.77 | -17143.02 | 2020-10-01 | 2021-09-30 | 2020-11-02 | 11 | 2020-12-25 | 12
050.55359 | COM.2738.Federal Place Ext | 200 Ft of 2 In HDPE to serve 2 customers off of Federal Place in Campbellsville | 1741.8 | 1572.67 | 169.13 | 10.75% | 0.002976% | 1741.8 | 1572.67 | 169.13 | 2020-10-01 | 2021-09-30 | 2020-11-02 | 11 | 2020-12-25 | 12
050.55371 | RES.2637.Camilla Ln Main Ext | Install 50 feet of 2 inch poly main for one new residential customer (David Simmons) requesting natural gas service at 1530 Camilla Lane. | 2679.48 | 2824.57 | -145.09 | -5.137% | 0.004579% | 2679.48 | 2824.57 | -145.09 | 2020-10-01 | 2021-09-30 | 2020-11-05 | 11 | 2020-11-30 | 11
050.55390 | RES.2636.ADAMSST.HAWESVILLE | Install 260' of 2" PE. for 3 new customers | 1287.47 | 6709.43 | -5421.96 | -80.81% | 0.0022% | 1287.47 | 6709.43 | -5421.96 | 2020-10-01 | 2021-09-30 | 2020-11-06 | 11 | 2020-11-12 | 11
050.55413 | PRP.2635.W Main St | See project Long Description/Notes | 1078083.56 | 853168.53 | 224915.03 | 26.36% | 1.842% | 1078083.56 | 853168.53 | 224915.03 | 2020-10-01 | 2021-09-30 | 2020-11-20 | 11 | 2021-08-30 | 08
050.55436 | IND.2734.Prosperity Phase 2 | Install 2,031 feet of 6 inch steel in Phase 2 | 29168.98 | 308056.34 | -278887.36 | -90.53% | 0.04984% | 29168.98 | 308056.34 | -278887.36 | 2020-10-01 | 2021-09-30 | 2020-11-16 | 11 | 2021-09-30 | 09
050.55440 | RES.2636.PECANAVE.S.MN.EXT | Install 600'of 2" PE. for new customers | 22380.15 | 28514.31 | -6134.16 | -21.51% | 0.03824% | 22380.15 | 28514.31 | -6134.16 | 2020-10-01 | 2021-09-30 | 2020-11-12 | 11 | 2020-11-18 | 11
050.55455 | RES.2739.Twin Lakes Ph 2 | 2300 Ft of 2 In HDPE to serve multiple customers in second phase of Twin Lakes Subdivision | 55293.11 | 55750.74 | -457.63 | -0.8209% | 0.09449% | 55293.11 | 55750.74 | -457.63 | 2020-10-01 | 2021-09-30 | 2020-11-23 | 11 | 2021-01-29 | 01
050.55456 | RES.2634.OATSST.MNEXT. | Iinstall 300' of 2" PE. for Duplex | 25554.7 | 26513.1 | -958.4 | -3.615% | 0.04367% | 25554.7 | 26513.1 | -958.4 | 2020-10-01 | 2021-09-30 | 2020-12-02 | 12 | 2020-12-10 | 12
050.55510 | COM.2736.Davenport Ln. Ext. | 1000 ft.. of 2 inch HDPE will serve commercial development on Davenport Ln. in Hopkinsville. There will be AIC in the amount of $6174.00 | -523.41 | 6806.53 | -7329.94 | -107.7% | -0.0008944% | -523.41 | 6806.53 | -7329.94 | 2020-10-01 | 2021-09-30 | 2020-11-16 | 11 | 2020-12-31 | 12
050.55511 | RES.2735.Short.Cut.HorseCave | 390 ft. of 2 inch HDPE will serve 2 new residential lots on Short Cus Rd. in Horse Cave. There will be $2722.86 in AIC on this project | 344.82 | 5694.71 | -5349.89 | -93.94% | 0.0005892% | 344.82 | 5694.71 | -5349.89 | 2020-10-01 | 2021-09-30 | 2020-11-24 | 11 | 2021-01-15 | 01
050.55525 | RES.2738.Highway 61 | 700 Ft of 2 In HDPE to serve one customer in Summersville | -1962.84 | 4198.7 | -6161.54 | -146.7% | -0.003354% | -1962.84 | 4198.7 | -6161.54 | 2020-10-01 | 2021-09-30 | 2020-11-30 | 11 | 2020-12-31 | 12
050.55528 | COM.2637.Holt Rd Rev Ext_ | Install 400 feet of 2 inch poly for a new commercial development. No deposit is required, gas is available in front of property. We are running this for convenience and for future development along Holt Rd | 11346.34 | 11440.41 | -94.07 | -0.8223% | 0.01939% | 11346.34 | 11440.41 | -94.07 | 2020-10-01 | 2021-09-30 | 2020-11-01 | 11 | 2021-03-28 | 03
050.55530 | RES.2637.Ridge Run 2 | Install525 feet of 2 inch poly main for 13 new residential lots in this second phase of Ridge Run Subdivision. Developer is Phil Higdon Senior | 14118.59 | 14103.02 | 15.57 | 0.1104% | 0.02413% | 14118.59 | 14103.02 | 15.57 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2020-12-30 | 12
050.55531 | RES.2737.Harvest Lane | 310 Ft of 2 In HDPE to serve two new customers in Harrodsburg | 10738.31 | 12309.9 | -1571.59 | -12.77% | 0.01835% | 10738.31 | 12309.9 | -1571.59 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2021-01-29 | 01
050.55536 | RES.2737.Ash Drive | 1000 Ft of 2 In HDPE to serve 3 customers on Ash Dr in Hustonville | -14.87 | 310.24 | -325.11 | -104.8% | -2.541e-05% | -14.87 | 310.24 | -325.11 | 2020-10-01 | 2021-09-30 | 2020-12-01 | 12 | 2020-12-31 | 12
050.55561 | PRP.2637.Broad St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 625580.39 | 740134.15 | -114553.76 | -15.48% | 1.069% | 625580.39 | 740134.15 | -114553.76 | 2020-10-01 | 2021-09-30 | 2020-12-18 | 12 | 2021-09-20 | 09
050.55578 | RES.2636.BIGOAKCIRCLE.MN.EXT | Install 200' of 2" PE. for Residential Growth | 2457.63 | 1922.22 | 535.41 | 27.85% | 0.0042% | 2457.63 | 1922.22 | 535.41 | 2020-10-01 | 2021-09-30 | 2020-12-17 | 12 | 2020-12-22 | 12
050.55587 | 050.2637.Woodville Rd Retire | Abandon 482 feet of 1 1/4 inch poly that used to serve a mobile home park. Mobile homes are now gone. | 3.93 | 660.25 | -656.32 | -99.4% | 6.716e-06% | 3.93 | 660.25 | -656.32 | 2020-10-01 | 2021-09-30 | 2020-12-10 | 12 | 2021-01-30 | 01
050.55639 | 050.2637.Buckner Ln Relocate | City of Paducah is replacing the existing old bridge on Buckner Lane that crosses Crooked Creek. We have 505 feet of 2 inch steel and plastic main that is affected by construction of the new bridge. We propose to install 535 feet of 2 inch poly main. | 24809.54 | 23559.41 | 1250.13 | 5.306% | 0.0424% | 24809.54 | 23559.41 | 1250.13 | 2020-10-01 | 2021-09-30 | 2021-01-01 | 01 | 2021-04-30 | 04
050.55662 | RES.2637.Spann Ln Rev Ext | Install 165 feet of 2 inch poly main for one new residential customer (Travis Watson) requesting natural gas. | 6285.04 | 5321.74 | 963.3 | 18.1% | 0.01074% | 6285.04 | 5321.74 | 963.3 | 2020-10-01 | 2021-09-30 | 2021-01-01 | 01 | 2021-03-30 | 03
050.55667 | PRP.2737.Ledford Lane | Project was in the 7/27/20 KY PRP filing. See project Long description / notes | 392551.21 | 512169.9 | -119618.69 | -23.36% | 0.6708% | 392551.21 | 512169.9 | -119618.69 | 2020-10-01 | 2021-09-30 | 2021-01-25 | 01 | 2021-07-30 | 07
050.55685 | 050.2638.N 16th St Retirement | Abandon 61 feet of 2 inch MW steel main, 41 feet of 1 inch MW steel main | 624.54 | 1344.73 | -720.19 | -53.56% | 0.001067% | 624.54 | 1344.73 | -720.19 | 2020-10-01 | 2021-09-30 | 2021-01-06 | 01 | 2021-02-28 | 02
050.55692 | PRP.2734.High St Alley BG | Project was in the 7/27/20 KY PRP filing See project long description / notes | 712301.33 | 592786.34 | 119514.99 | 20.16% | 1.217% | 712301.33 | 592786.34 | 119514.99 | 2020-10-01 | 2021-09-30 | 2021-01-22 | 01 | 2021-08-30 | 08
050.55693 | PRP.2734.US 31W - Emmett Ave | Replace 411 ft of 4 Inch Bare still main with 417 ft of 4 Inch HDPE . 2 services involved' | 102422.24 | 105431.49 | -3009.25 | -2.854% | 0.175% | 102422.24 | 105431.49 | -3009.25 | 2020-10-01 | 2021-09-30 | 2021-01-05 | 01 | 2021-03-22 | 03
050.55698 | 2734.Ordorator 2 Purchase | Purchase 2 Odorator 2 for Bowling Green operations. | 12519.08 | 12729 | -209.92 | -1.649% | 0.02139% | 12519.08 | 12729 | -209.92 | 2020-10-01 | 2021-09-30 | 2021-01-11 | 01 | 2021-02-28 | 02
050.55705 | RES.2636.BRIDGEWOODDR.MN.EXT | Install approximately 1550' of 2" PE. for subdivision growth | 22607.46 | 23594.48 | -987.02 | -4.183% | 0.03863% | 22607.46 | 23594.48 | -987.02 | 2020-10-01 | 2021-09-30 | 2021-01-14 | 01 | 2021-01-25 | 01
050.55713 | RES.2734.Price Farms IA | 1670 ft. of 4 inch and 780 ft. of 2 inch HDPE will serve 52 new residentill lots in Price Farms Phase IA. Develope wil open and close ditch and install casings for main and service lines. | 22882.75 | 23899.87 | -1017.12 | -4.256% | 0.0391% | 22882.75 | 23899.87 | -1017.12 | 2020-10-01 | 2021-09-30 | 2021-01-11 | 01 | 2021-04-16 | 04
050.55714 | RES.2734.Satgner Farms Phase | 2811 ft. of 4 inch and 3200 ft. of 2 inch HDPE wil serve New Growth Subdivision - Stagner Farms Pahse I located off Elrod.. Rd. Developer will proved open and close ditch and install casings for main and services. Main will tie in to 4" PE - Elrod | 46513.97 | 60045.57 | -13531.6 | -22.54% | 0.07948% | 46513.97 | 60045.57 | -13531.6 | 2020-10-01 | 2021-09-30 | 2021-01-11 | 01 | 2021-03-31 | 03
050.55716 | RES.2734.Carter Crossing IA | 700 ft. of 6 inch and ----- ft. of 2 inch HDPE will serve 76 Residential lot and 20 multi-family lots in Phase IA of Crater Crossings located off Cumberland Trace. Developer will open and close ditch and install casings for main and service lines. | 46711.8 | 32277.52 | 14434.28 | 44.72% | 0.07982% | 46711.8 | 32277.52 | 14434.28 | 2020-10-01 | 2021-09-30 | 2021-06-01 | 06 | 2021-06-01 | 06
050.55738 | PRP.2636.25th St Ann | Unbudgeted PRP See project Long Descriiption notes | 249149.38 | 257410.12 | -8260.74 | -3.209% | 0.4258% | 249149.38 | 257410.12 | -8260.74 | 2020-10-01 | 2021-09-30 | 2021-01-19 | 01 | 2021-05-30 | 05
050.55740 | RES.2636.NORTHWOODDR.MN.EXT | Install 1240' of 2" PE. for subdivision growth | 19972.92 | 19055.93 | 916.99 | 4.812% | 0.03413% | 19972.92 | 19055.93 | 916.99 | 2020-10-01 | 2021-09-30 | 2021-02-16 | 02 | 2021-02-25 | 02
050.55750 | RES.2636.CHELSADR.UTICAMN.EXT | Install 450' of 2" PE. for new customer | 12041.93 | 28820.22 | -16778.29 | -58.22% | 0.02058% | 12041.93 | 28820.22 | -16778.29 | 2020-10-01 | 2021-09-30 | 2021-02-08 | 02 | 2021-02-15 | 02
050.55751 | RES.2636.MILTONRD.MN.EXT | Install 1360' of 2" PE. for new customer | -4802.11 | 13748.8 | -18550.91 | -134.9% | -0.008206% | -4802.11 | 13748.8 | -18550.91 | 2020-10-01 | 2021-09-30 | 2021-02-02 | 02 | 2021-09-30 | 09
050.55786 | RES.2737.KY 2141 | 200 Ft of 2 In HDPE to serve one new customer on KY 2141 in Stanford KY | 615.7 | 1554.12 | -938.42 | -60.38% | 0.001052% | 615.7 | 1554.12 | -938.42 | 2020-10-01 | 2021-09-30 | 2021-01-22 | 01 | 2021-02-26 | 02
050.55787 | INT.2737.Hubble Road Stations | Retire RS 1492 and Hubble Road Farm Tap Station in Stanford | 21232.92 | 23500.29 | -2267.37 | -9.648% | 0.03628% | 21232.92 | 23500.29 | -2267.37 | 2020-10-01 | 2021-09-30 | 2021-01-22 | 01 | 2021-03-30 | 03
050.55810 | PRP.2734.BG Centerline 3 | Replace 30,800 ft of 8" HPD Bare Steel Main with 30,800 ft of 8" Fusion Bond Epoxy HPD Steel main and 3,382 ft of 2" and 4,150 ft of 4" HDPE, also replace 2 Town Border Stations; 8 services | 944174.74 | 12143675.09 | -11199500.35 | -92.22% | 1.613% | 944174.74 | 12143675.09 | -11199500.35 | 2020-10-01 | 2021-09-30 | 2021-01-28 | 01 | 2022-09-30 | 09
050.55814 | PRP.2637.Hill St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 574973.78 | 641453.64 | -66479.86 | -10.36% | 0.9825% | 574973.78 | 641453.64 | -66479.86 | 2020-10-01 | 2021-09-30 | 2021-02-16 | 02 | 2021-09-30 | 09
050.55844 | COM.2637.Barkley Field Ext | Install 7,700 feet of 4 inch poly and 900 of 2 inch poly for Paducah Barkley Field Airport. | 125035.79 | 347918.61 | -222882.82 | -64.06% | 0.2137% | 125035.79 | 347918.61 | -222882.82 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-09-30 | 09
050.55847 | RES.2736.Buttermilk Rd. Ext | 160 ft. of 2 inch HDPE will serve new residential customers on Buttermilk Rd. in Hopkinsville. | 4119.66 | 4684.87 | -565.21 | -12.06% | 0.00704% | 4119.66 | 4684.87 | -565.21 | 2020-10-01 | 2021-09-30 | 2021-02-05 | 02 | 2021-04-30 | 04
050.55848 | RES.2636.BOSTONLAFOONRD.MN.EX | Install 200' of 2"PE. for (2) Two new customers | 5819.6 | 1781.15 | 4038.45 | 226.7% | 0.009945% | 5819.6 | 1781.15 | 4038.45 | 2020-10-01 | 2021-09-30 | 2021-03-03 | 03 | 2021-04-30 | 04
050.55889 | 050.2734. Turner Station | Replace valves and add outlet valve - Turner Regulator Station that feeds Hills Pet Foods. This is an appoved FY2021 project | 10011.55 | 30049 | -20037.45 | -66.68% | 0.01711% | 10011.55 | 30049 | -20037.45 | 2020-10-01 | 2021-09-30 | 2021-02-15 | 02 | 2021-04-15 | 04
050.55902 | 2636.WinklerRd.Replacement | Replace 650' of 2"HDPE | 945.44 | 3224.63 | -2279.19 | -70.68% | 0.001616% | 945.44 | 3224.63 | -2279.19 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-03-31 | 03
050.55906 | RES.2638.Twin Hills Rd Ext 2 | Install 335 feet of 2 inch poly for two customers, one residential and one commercial. | 2733.33 | 2519.25 | 214.08 | 8.498% | 0.004671% | 2733.33 | 2519.25 | 214.08 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-04-30 | 04
050.55908 | Rotary Meters Replacement | This project is to capture the costs of replacing outdated rotary meters in the Mayfield area. This includes the meters, meter loops, regulators, relief valves, etc. | 37559.7 | 63199.22 | -25639.52 | -40.57% | 0.06418% | 37559.7 | 63199.22 | -25639.52 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-05-30 | 05
050.55914 | LP.2734.McGoodwin Svc | Replace 50 sevices in conjunction with McGoodwin LP Main Replacement in Franklin | 15368.82 | 268902.74 | -253533.92 | -94.28% | 0.02626% | 15368.82 | 268902.74 | -253533.92 | 2020-10-01 | 2021-09-30 | 2021-02-18 | 02 | 2021-09-30 | 09
050.55917 | LP.2734.McGoodwin.Replc | Replace approx,. 3000 feet of LP, 30 feet 6" bare, 307 feet 4" bare, 350 feet 3" epoxy, 194 feet 2" epoxy, 215 feet 1.25" bare, 174 feet of 6" epoxy, 1,292 feet 4" epoxy, 407 feet 3" bare, 31 feet 1.5" bare with2165 ft. of 2" PE in Franklin, KY. | 168492.72 | 344894.36 | -176401.64 | -51.15% | 0.2879% | 168492.72 | 344894.36 | -176401.64 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-07-30 | 07
050.55924 | Ground Bed - N 18th St | This project is to capture the costs associated with the installation of a new ground bed at N. 18th Street in Mayfield. The existing ground bed is depleted. | 28157.47 | 36756.7 | -8599.23 | -23.4% | 0.04812% | 28157.47 | 36756.7 | -8599.23 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-07-30 | 07
050.55941 | RES.2637.Bryant Ford Rd Ext | Install 150 ft of 2 inch poly for one conversion customer. | 988.54 | 1848.17 | -859.63 | -46.51% | 0.001689% | 988.54 | 1848.17 | -859.63 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-04-30 | 04
050.55942 | RES.2637.S 29th St Rev Ext | Install 130 feet of 2 inch poly for one residential customer (Carl Mclvain) requesting service. HIS ELECTRIC HEAT PUMP HAS GONE OUT. | 5495.6 | 4206.8 | 1288.8 | 30.64% | 0.009391% | 5495.6 | 4206.8 | 1288.8 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-03-28 | 03
050.55945 | RES.2636.BURLEWBLVDAPARTMENTS | Install 500' of 2"HDPE for apartments | 8239.16 | 2829.4 | 5409.76 | 191.2% | 0.01408% | 8239.16 | 2829.4 | 5409.76 | 2020-10-01 | 2021-09-30 | 2021-03-16 | 03 | 2021-05-30 | 05
050.55951 | IND.2738.American Wood Fiber | Install 2 Inch Regulator Station to feed new load at American Wood Fiber | 130992.83 | 132015.59 | -1022.76 | -0.7747% | 0.2238% | 130992.83 | 132015.59 | -1022.76 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-06-18 | 06
050.55997 | 2636.LP.FREDERICAST. | Install 7,000' of 6" HDPE, 3550 of 2" HDPE,I.P. - retire 12672' of LP. steel | 1369718.91 | 1076988.51 | 292730.4 | 27.18% | 2.341% | 1369718.91 | 1076988.51 | 292730.4 | 2020-10-01 | 2021-09-30 | 2021-03-01 | 03 | 2021-07-30 | 07
050.56027 | RES.2734.Par3 - Olde Stone | ft. of 2 inch HDPE will serve new residential development at Par3 - Ode Stone. Developer will open and close ditch. | 9124.73 | 17638.06 | -8513.33 | -48.27% | 0.01559% | 9124.73 | 17638.06 | -8513.33 | 2020-10-01 | 2021-09-30 | 2021-03-10 | 03 | 2021-04-30 | 04
050.56030 | RES.2734.MagnoliaHillsIII | 3940 ft.of 2 inch HDPE will serve 95 new residential lots in Magnolis Hill Phase III. Developer wil open and close ditch | 8671.77 | 19616.56 | -10944.79 | -55.79% | 0.01482% | 8671.77 | 19616.56 | -10944.79 | 2020-10-01 | 2021-09-30 | 2021-03-10 | 03 | 2021-04-30 | 04
050.56041 | RES.2638.Meadows Subd Phase 8 | Install 1,630 feet of 2 inch poly pipe for 17 new residential lots in the Meadows subdivision.. This will be phase 8 and the last phase in subdivision. Develloper is John Smith. | 35765.92 | 36834.34 | -1068.42 | -2.901% | 0.06112% | 35765.92 | 36834.34 | -1068.42 | 2020-10-01 | 2021-09-30 | 2021-04-01 | 04 | 2021-05-30 | 05
050.56042 | 050.2638.Autumn Ln Retirement | Retire/ Abandon 250' - 2" poly pipe plus 195' - 2" Aldyl A pipe for a total retirement of 445 feet. There are no mre customers on this street. Homes have been razed for a couple of years | 745.02 | 6.67 | 738.35 | 11070% | 0.001273% | 745.02 | 6.67 | 738.35 | 2020-10-01 | 2021-09-30 | 2021-03-15 | 03 | 2021-04-30 | 04
050.56048 | 2735.Oakland Station Rebuild | Rebuild station at Oakland due to valve replacement. Materials are currently in stock.Will be a DIrect Company Labor project | 5423.21 | 16537.16 | -11113.95 | -67.21% | 0.009267% | 5423.21 | 16537.16 | -11113.95 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.56052 | PRP.2636.14th St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 616505.51 | 867695.58 | -251190.07 | -28.95% | 1.054% | 616505.51 | 867695.58 | -251190.07 | 2020-10-01 | 2021-09-30 | 2021-03-20 | 03 | 2021-09-30 | 09
050.56088 | RES.2636.KEENELANDSEBISCUITLP | Install 850' of 2" PE for Subdivision growth | 12192.27 | 16056.73 | -3864.46 | -24.07% | 0.02083% | 12192.27 | 16056.73 | -3864.46 | 2020-10-01 | 2021-09-30 | 2021-04-05 | 04 | 2021-04-09 | 04
050.56097 | PRP.2735.Oakland | Project was in the 7/27/20 KY PRP filing See project long description / notes | 514218.54 | 491409.74 | 22808.8 | 4.642% | 0.8787% | 514218.54 | 491409.74 | 22808.8 | 2020-10-01 | 2021-09-30 | 2021-03-23 | 03 | 2021-09-20 | 09
050.56111 | IND.2734.Proj.Sapphire (AIC) | 100% AIC Main Extension of 6-inch steel to continue gas service across new lots in the Bowling Green Transpark as part of a new phase. Main to be installed along Production Avenue. AIC will be paid by the ITA of Bowling Green. Gas In-Servi | -6045.17 | 254906.88 | -260952.05 | -102.4% | -0.01033% | -6045.17 | 254906.88 | -260952.05 | 2020-10-01 | 2021-09-30 | 2021-03-19 | 03 | 2021-08-31 | 08
050.56112 | IND.2734.Proj.Sapphire (MEC) | Refundable Main Extension of 6-inch steel to provide gas service to a new Industrial Customer currently under construction in a new phase of the Transpark in Bowling Green along Production Avenue. Refund will be paid by the ITA of Bowling G | 202158.68 | 267612.55 | -65453.87 | -24.46% | 0.3455% | 202158.68 | 267612.55 | -65453.87 | 2020-10-01 | 2021-09-30 | 2021-03-19 | 03 | 2021-08-30 | 08
050.56113 | 2735.Mis.Rotary Meters. | Misc. rotary meter replacements - Glasow Area | 30046.01 | 59949.96 | -29903.95 | -49.88% | 0.05134% | 30046.01 | 59949.96 | -29903.95 | 2020-10-01 | 2021-09-30 | 2020-10-01 | 10 | 2021-08-31 | 08
050.56117 | RES.2636.OttawaDr. Main Ext. | Install 640' of 4" HDPE on Ottawa and 375' of 2" HDPE on Skaggs | 18552.64 | 23261.43 | -4708.79 | -20.24% | 0.0317% | 18552.64 | 23261.43 | -4708.79 | 2020-10-01 | 2021-09-30 | 2021-04-01 | 04 | 2021-04-21 | 04
050.56126 | RES.2736.Sain.Ext.Hopk. | 420 ft. of 4 inch HDPE wil serve residential properties on Spain Ln. in Hopkinsville. Company Labor will be utilized - directional bored. AIC = 2500.00 | 2385.66 | 8224.27 | -5838.61 | -70.99% | 0.004077% | 2385.66 | 8224.27 | -5838.61 | 2020-10-01 | 2021-09-30 | 2021-03-22 | 03 | 2021-05-31 | 05
050.56133 | 050.2636.Frederica St Services | Replace 80 LP.Stl. services with 80 intermitate PE. services | 615431.66 | 390971.03 | 224460.63 | 57.41% | 1.052% | 615431.66 | 390971.03 | 224460.63 | 2020-10-01 | 2021-09-30 | 2021-04-01 | 04 | 2021-09-30 | 09
050.56147 | RES.2739.Cherokee Drive | 2000 Ft of 2 In HDPE to serve Cherokee Drive in Shelbyville KY | 2950.46 | 4243.98 | -1293.52 | -30.48% | 0.005042% | 2950.46 | 4243.98 | -1293.52 | 2020-10-01 | 2021-09-30 | 2021-03-29 | 03 | 2021-08-30 | 08
050.56151 | LP.2736.17th.St.Replacement | Replace 101 feet of 1 1/1", 1,750 feet of 2", 4,316 feet of 4" and 3,623 feet of 6" with 3,470 feet of 4" HDPE and 4,038 feet of 2" HDPE. Retire RS9422 . This is a FY21 Capital LP Project. Construction by Martin Contracting. | 573698.16 | 707136.26 | -133438.1 | -18.87% | 0.9804% | 573698.16 | 707136.26 | -133438.1 | 2020-10-01 | 2021-09-30 | 2021-04-01 | 04 | 2021-09-30 | 09
050.56155 | INT.2737.Hill n Dale Station | Install 450 Ft of 2 In HDPE to retire Hill n Dale Reg Sta | 37821.57 | 47386.75 | -9565.18 | -20.19% | 0.06463% | 37821.57 | 47386.75 | -9565.18 | 2020-10-01 | 2021-09-30 | 2021-04-05 | 04 | 2021-04-30 | 04
050.56164 | 050.2638.Hwy 121 SYS IMP | We are connecting a 36 psi system to a 59 psi system. The goal is to bolster the 59 psi system which has a one way feed that serves the local hospital, high school, and elementary school. This system inprovement will require app. 800 feet of 2 inch | 55452.67 | 81806.15 | -26353.48 | -32.21% | 0.09476% | 55452.67 | 81806.15 | -26353.48 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-07-31 | 07
050.56170 | 2734.Redbud Sta. Retire | Redbud Station Retirement - Install 1,700 feet of 2" PE and 300 feet of 4" PE to tie 2 systems together to retire station for property improvements. | 126936.92 | 189843.7 | -62906.78 | -33.14% | 0.2169% | 126936.92 | 189843.7 | -62906.78 | 2020-10-01 | 2021-09-30 | 2021-03-26 | 03 | 2021-07-30 | 07
050.56209 | RES.2636.MAPLELEAFUTICA.MN.EX | Install 2100' of 2" HDPE for subdivision growth | 32560.72 | 33461.14 | -900.42 | -2.691% | 0.05564% | 32560.72 | 33461.14 | -900.42 | 2020-10-01 | 2021-09-30 | 2021-06-03 | 06 | 2021-07-30 | 07
050.56236 | COM.2735.Mammoth Cave Ext | 750 ft. of 2 inch HDPE will serve new extension for Family Dollar in Park City.. | 7409.69 | 10026.92 | -2617.23 | -26.1% | 0.01266% | 7409.69 | 10026.92 | -2617.23 | 2020-10-01 | 2021-09-30 | 2021-04-08 | 04 | 2021-05-31 | 05
050.56239 | RES.2636.VALLEYBROOKTRACE.MN. | Install 400' of 4" HDPE for subdivision | 8603.5 | 11812.8 | -3209.3 | -27.17% | 0.0147% | 8603.5 | 11812.8 | -3209.3 | 2020-10-01 | 2021-09-30 | 2021-05-05 | 05 | 2021-05-18 | 05
050.56252 | Shelbyville KY WMR Towers.FY21 | Purchase 3 FLXNT BS M400 WMR towers for Shelbyville, KY area. Sites 809445 (620 Old Finchville Rd; Shelbyville, KY 40065), 827869 (586 Jeptha Knob Rd; Shelbyville, KY 40065) and 878182 (1306 Buck Creek Rd; Simpsonville, KY 40067) | 159494.81 | 183604.61 | -24109.8 | -13.13% | 0.2725% | 159494.81 | 183604.61 | -24109.8 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-10-31 | 10
050.56254 | RES.2636.NEWBOLTRD.HAYDEN.MN. | Install 3800' of 2" HDPE for new home | 8134.79 | 6708.78 | 1426.01 | 21.26% | 0.0139% | 8134.79 | 6708.78 | 1426.01 | 2020-10-01 | 2021-09-30 | 2021-04-12 | 04 | 2021-05-30 | 05
050.56258 | 050.2637.Said Rd 6 in Replace | Existing 6" steel casing is shorted. We propose to replace 160' of 6" carrier pipe. Casing not required by KYTC due to extra wall thickness of pipe.. | 63914.37 | 67940.35 | -4025.98 | -5.926% | 0.1092% | 63914.37 | 67940.35 | -4025.98 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-09-30 | 09
050.56260 | PRP.2637.S 3rd St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 470773.31 | 706063.62 | -235290.31 | -33.32% | 0.8045% | 470773.31 | 706063.62 | -235290.31 | 2020-10-01 | 2021-09-30 | 2021-06-30 | 06 | 2021-11-16 | 11
050.56264 | 050.2637.Estes Ln SYS IMP | Propose to install 2,600 feet of 6 inch poly main along Estes Lane from Meacham Lane to Husband Rd in order to bolster the system in that area. We also propose to retire RS 1656 Husband Rd Reg Sta. The station sits too close to busy hwy | 181267.36 | 228202.86 | -46935.5 | -20.57% | 0.3098% | 181267.36 | 228202.86 | -46935.5 | 2020-10-01 | 2021-09-30 | 2021-06-01 | 06 | 2021-09-30 | 09
050.56279 | RES.2636.HARMONSFERRYRD.MN.EX | Install 700' of 2" HDPE for new customer | 24203.61 | 7072.48 | 17131.13 | 242.2% | 0.04136% | 24203.61 | 7072.48 | 17131.13 | 2020-10-01 | 2021-09-30 | 2021-05-17 | 05 | 2021-07-30 | 07
050.56292 | 050.009.2636.Swedish Match | Replacement of Swedish Match station due to upgrade faccilities. | 326895.96 | 427146.11 | -100250.15 | -23.47% | 0.5586% | 326895.96 | 427146.11 | -100250.15 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-08-31 | 08
050.56303 | IND.2735.T.Marzetti - | Project to add additional meter station and meter for expansion. T. Marzetti in Hart County, Horse Cave, KY | 66520.34 | 150645.33 | -84124.99 | -55.84% | 0.1137% | 66520.34 | 150645.33 | -84124.99 | 2020-10-01 | 2021-09-30 | 2021-04-21 | 04 | 2021-08-31 | 08
050.56331 | RES.2634.POOLERD.MN.EXT | Install 550' of 2" HDPE main for 2 new customers | 6856.81 | 6303.04 | 553.77 | 8.786% | 0.01172% | 6856.81 | 6303.04 | 553.77 | 2020-10-01 | 2021-09-30 | 2021-05-24 | 05 | 2021-05-28 | 05
050.56348 | RES.2637.Kirby Ln Rev Ext | Install 100 feet of 2 inch poly ain for one existing residential customer (Regan Wainscott) requesting natural gas service. Installing gas heat. | 6398.47 | 3834.14 | 2564.33 | 66.88% | 0.01093% | 6398.47 | 3834.14 | 2564.33 | 2020-10-01 | 2021-09-30 | 2021-05-17 | 05 | 2021-06-30 | 06
050.56349 | COM.2635.ROCKYRIDGERD | Install 125' of 2" HDPE for Athletic Building | 3135.59 | 1494.39 | 1641.2 | 109.8% | 0.005358% | 3135.59 | 1494.39 | 1641.2 | 2020-10-01 | 2021-09-30 | 2021-05-03 | 05 | 2021-05-31 | 05
050.56356 | INT.2739.Clear Creek Exposure | Downrate pressure across exposure in Clear Creek. Replace Old 7 Mile Pike Reg Station and eliminate Goodman Ave Reg Station | 152724.14 | 187325.75 | -34601.61 | -18.47% | 0.261% | 152724.14 | 187325.75 | -34601.61 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-09-22 | 09
050.56372 | PRP.2734.Sycamore St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 737692.9 | 870666.98 | -132974.08 | -15.27% | 1.261% | 737692.9 | 870666.98 | -132974.08 | 2020-10-01 | 2021-09-30 | 2021-05-15 | 05 | 2021-09-30 | 09
050.56401 | 2636.OLDHWY54MN.EXT | Install 850' of 2" HDPE main | 10281.11 | 7290.14 | 2990.97 | 41.03% | 0.01757% | 10281.11 | 7290.14 | 2990.97 | 2020-10-01 | 2021-09-30 | 2021-05-10 | 05 | 2021-05-17 | 05
050.56404 | COM.2636.HWY144HAYDEN.MN.EXT | Install 1006' of 2" HDPE for Hayden Truck Shop | 2484.65 | 9447.38 | -6962.73 | -73.7% | 0.004246% | 2484.65 | 9447.38 | -6962.73 | 2020-10-01 | 2021-09-30 | 2021-06-01 | 06 | 2021-06-08 | 06
050.56411 | RES.2636.SKAGGSCT.MN.EXT | Install 1100' of 2" HDPE for Subdivision growth | 16511.38 | 25338.56 | -8827.18 | -34.84% | 0.02822% | 16511.38 | 25338.56 | -8827.18 | 2020-10-01 | 2021-09-30 | 2021-05-17 | 05 | 2021-05-24 | 05
050.56418 | 2737.Parking Lot Sealing | Budgeted project to seal the parking lot at the Danville office | 7153.78 | 7191.9 | -38.12 | -0.53% | 0.01222% | 7153.78 | 7191.9 | -38.12 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-05-30 | 05
050.56437 | PRP.2734.Gayle Way | Project was in the 7/27/20 KY PRP filing See project long description / notes | 328787.62 | 218739.5 | 110048.12 | 50.31% | 0.5618% | 328787.62 | 218739.5 | 110048.12 | 2020-10-01 | 2021-09-30 | 2021-05-20 | 05 | 2021-09-30 | 09
050.56464 | RES.2635.FAIRVIEWAVE.MN.EXT | Install 125' of 2" HDPE for new customer in Eddyville | 3057.25 | 1515.41 | 1541.84 | 101.7% | 0.005224% | 3057.25 | 1515.41 | 1541.84 | 2020-10-01 | 2021-09-30 | 2021-05-24 | 05 | 2021-05-31 | 05
050.56468 | 050.2637.CountryClub Relocate | City of Paducah is replacing a culvert along Country Club Ln. Our existing 2 inch steel gas main is in the way. We propose to replace 400 feet of 2 inch steel with 2 inch poly. There could be as many as 2 services affected. | 25952.94 | 27710.18 | -1757.24 | -6.341% | 0.04435% | 25952.94 | 27710.18 | -1757.24 | 2020-10-01 | 2021-09-30 | 2021-05-10 | 05 | 2021-06-30 | 06
050.56499 | 2739.Concrete Saw | One concrete saw ($1200). | 1425.98 | 1527.48 | -101.5 | -6.645% | 0.002437% | 1425.98 | 1527.48 | -101.5 | 2020-10-01 | 2021-09-30 | 2021-05-01 | 05 | 2021-09-30 | 09
050.56500 | 2739.Rectifiers | Two JA Rectifiers ($2500, $3100). | 8143.95 | 7190.74 | 953.21 | 13.26% | 0.01392% | 8143.95 | 7190.74 | 953.21 | 2020-10-01 | 2021-09-30 | 2021-06-01 | 06 | 2021-09-15 | 09
050.56509 | RES.2637.May-Met Rd Rev Ext | Install 100 feet of 2 inch P.E main for one new residential customer (Tubby Chapman) requesting natural gas service | 6766.07 | 3746.92 | 3019.15 | 80.58% | 0.01156% | 6766.07 | 3746.92 | 3019.15 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-09-30 | 09
050.56513 | RES.2637.Guyline Dr Rev Ext | Install 425 feet of 2 inch poly main for two new residential customers requesting natural gas. Also makes gas available to one new residential lot. Both | 13450.23 | 11721.73 | 1728.5 | 14.75% | 0.02298% | 13450.23 | 11721.73 | 1728.5 | 2020-10-01 | 2021-09-30 | 2021-06-01 | 06 | 2021-06-30 | 06
050.56524 | PRP.2636.Sycamore St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 347162.98 | 512740.46 | -165577.48 | -32.29% | 0.5932% | 347162.98 | 512740.46 | -165577.48 | 2020-10-01 | 2021-09-30 | 2021-06-10 | 06 | 2021-09-30 | 09
050.56555 | PRP.2635.HWY 62 Relocation | See Project Long Description/notes | 188513.31 | 255068.21 | -66554.9 | -26.09% | 0.3221% | 188513.31 | 255068.21 | -66554.9 | 2020-10-01 | 2021-09-30 | 2021-06-23 | 06 | 2021-09-20 | 09
050.56557 | PRP.2635.KY 109 | Unbudgeted Retire 9 ft of 2" Epoxy, 54 ft of 2" Mill Wrap, 18 ft of 4" Bare Stl with 77 ft of 2" HDPE to eliminate CP Short. | 44348.73 | 40454.39 | 3894.34 | 9.626% | 0.07578% | 44348.73 | 40454.39 | 3894.34 | 2020-10-01 | 2021-09-30 | 2021-06-17 | 06 | 2021-08-30 | 08
050.56562 | Office Parking Lot | 8" Reinforced Concrete Pavement - Remove & Replace | 40498.59 | 41729.48 | -1230.89 | -2.95% | 0.06921% | 40498.59 | 41729.48 | -1230.89 | 2020-10-01 | 2021-09-30 | 2021-06-04 | 06 | 2021-09-30 | 09
050.56567 | RES.2636.MONROEAVE.MN.EXT | Install 600' of 4" HDPE, Install 200' of 2" HDPE for subdivision growth | 24691.91 | 22196.39 | 2495.52 | 11.24% | 0.04219% | 24691.91 | 22196.39 | 2495.52 | 2020-10-01 | 2021-09-30 | 2021-07-05 | 07 | 2021-07-12 | 07
050.56569 | 2637.Office Lighting LED | Provide and install (248) LED lamps in the existing (71) 4’ fluorescent lights. These lamps are 120 volt, and will not need the ballasts that in the existing fixtures. The ballasts in the existing fixtures will be electrically disconnected. | 7548.8 | 7589.03 | -40.23 | -0.5301% | 0.0129% | 7548.8 | 7589.03 | -40.23 | 2020-10-01 | 2021-09-30 | 2021-06-07 | 06 | 2021-07-31 | 07
050.56595 | RES.2637.Eagle Landing Ext | Install app. 2,800 feet of 4 inch poly and 3,300 feet of 2 inch poly to serve 52 lots plus 14 condo units in theis new residential subdivision being developed by Mr. Donny Travis | 134563.55 | 176638.35 | -42074.8 | -23.82% | 0.2299% | 134563.55 | 176638.35 | -42074.8 | 2020-10-01 | 2021-09-30 | 2021-06-14 | 06 | 2021-09-30 | 09
050.56599 | Office Security Gate Opener | Replace Mayfield service center gate opener. Office located at 900 Commonwealth Dr. | 8622.78 | 10855.79 | -2233.01 | -20.57% | 0.01473% | 8622.78 | 10855.79 | -2233.01 | 2020-10-01 | 2021-09-30 | 2021-06-10 | 06 | 2021-09-30 | 09
050.56601 | 2737.Office Lighting | Replace Danville service center lighting with LED | 18967.42 | 19544.1 | -576.68 | -2.951% | 0.03241% | 18967.42 | 19544.1 | -576.68 | 2020-10-01 | 2021-09-30 | 2021-06-10 | 06 | 2021-07-21 | 07
050.56612 | 050.2637.OlivetCh Rd Backfeed | Retire 270 feet of 2 inch poly along with 395 feet of 4 inch poly main. Install 1,150 feet of 2 inch poly main. | 33211.54 | 26257.3 | 6954.24 | 26.48% | 0.05675% | 33211.54 | 26257.3 | 6954.24 | 2020-10-01 | 2021-09-30 | 2021-06-14 | 06 | 2021-07-31 | 07
050.56630 | Pipe Locator - Schmidt | 050.2637.Pipe Locator - Paducah - Schmidt | 1699.97 | 1845.72 | -145.75 | -7.897% | 0.002905% | 1699.97 | 1845.72 | -145.75 | 2020-10-01 | 2021-09-30 | 2021-06-16 | 06 | 2021-09-30 | 09
050.56641 | RES.2634.SIMMENTALDR.MN.EXT | Install 600' of 2" HDPE. for new customers | 12546.33 | 6624.02 | 5922.31 | 89.41% | 0.02144% | 12546.33 | 6624.02 | 5922.31 | 2020-10-01 | 2021-09-30 | 2021-07-12 | 07 | 2021-09-22 | 09
050.56646 | PRP.2737.KY152 | See Project long Description /Notes | 210493.31 | 63695.1 | 146798.21 | 230.5% | 0.3597% | 210493.31 | 63695.1 | 146798.21 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-09-20 | 09
050.56689 | INT.2737.Centre College Reloc | Install 575 ft of 4 In HDPE and 400 ft of 2 In HDPE to retire 650 ft of 4 In Steel, 450 ft of 2 In Steel, and 450 ft of 2 In Poly for Centre College | 7958.7 | 86504 | -78545.3 | -90.8% | 0.0136% | 7958.7 | 86504 | -78545.3 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-08-31 | 08
050.56702 | RES.2638.Mitchell Dr Rev Ext | Install 385 feet of 2 inch poly main for one new home under construction. Will make gas availble to six vacant lots. | -4820.08 | 10651.31 | -15471.39 | -145.3% | -0.008237% | -4820.08 | 10651.31 | -15471.39 | 2020-10-01 | 2021-09-30 | 2021-06-28 | 06 | 2021-09-30 | 09
050.56708 | COM.2638.Grace Park Rev Ext | Install 2,500 feet of 2 inch poly main to serve eight new commercial lots in Grace Park Commercial Subdivision. Some of the new customers will be a Fivestar Convienience Store, C & C Real Estate, A brand new "Spec" building, Workman Bins (Agriculture | 56739.85 | 57701.04 | -961.19 | -1.666% | 0.09696% | 56739.85 | 57701.04 | -961.19 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-09-30 | 09
050.56723 | RES.2734.So.Oaks.Phs.II Ext. | 517 f t. of 4" and 1400 ft. of 2" HDPE will serve 48 new residential lots in South Oaks Sub. Phase II. Developer will open and close ditch and install casings for main and service lines. | 12878.4 | 25132.5 | -12254.1 | -48.76% | 0.02201% | 12878.4 | 25132.5 | -12254.1 | 2020-10-01 | 2021-09-30 | 2021-06-25 | 06 | 2021-08-31 | 08
050.56725 | RES.2737.Valleybrook Dr | 100 Ft of 2 In Poly to serve one new customer on Valleybrook Drive in Danville | -409.19 | 1584.95 | -1994.14 | -125.8% | -0.0006992% | -409.19 | 1584.95 | -1994.14 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-07-31 | 07
050.56726 | RES.2738.Trotter Lane | 250 Ft of 2 in HDPE to serve one new customer on Trotter Lane in Campbellsville | 363.95 | 1754.78 | -1390.83 | -79.26% | 0.0006219% | 363.95 | 1754.78 | -1390.83 | 2020-10-01 | 2021-09-30 | 2021-07-01 | 07 | 2021-07-31 | 07
050.56737 | PRP.2734.Schweizer Road | Replace 25,500' of 8" high pressure Bare steel with 25,500' of Fusion Bond Epoxy Steel, project will also include a new Purchase Station , check meter , YZ odorizer, all electronics and a expanded station lot | 60454.8 | 156794.94 | -96340.14 | -61.44% | 0.1033% | 60454.8 | 156794.94 | -96340.14 | 2020-10-01 | 2021-09-30 | 2021-06-21 | 06 | 2023-09-30 | 09
050.56749 | RES. Peachtree.Ln.Ext | 400 ft. of 4 inch HDPE will serve new residential customers on Peachtree Lane in Bowlng Green. | 7391.76 | 15655.19 | -8263.43 | -52.78% | 0.01263% | 7391.76 | 15655.19 | -8263.43 | 2020-10-01 | 2021-09-30 | 2021-06-28 | 06 | 2021-08-30 | 08
050.56750 | COM.2734.BlueLevelExt. | 380 ft. o 2" HDPE will serve a new commercial development on Blue Level Rd. | 533.28 | 14004.54 | -13471.26 | -96.19% | 0.0009113% | 533.28 | 14004.54 | -13471.26 | 2020-10-01 | 2021-09-30 | 2021-06-28 | 06 | 2021-12-30 | 12
050.56757 | COM.Hwy218.Ext.Horse Cave | 500 ft. of 2 inch HDPE will serve a new grain bin for Bill Jenkins on Hwy 218 in Horse Cave. Main will be installed in private R-O-W. Open and Closed ditch will be provided. Atmos will provide bore. | 3201.34 | 9161.95 | -5960.61 | -65.06% | 0.005471% | 3201.34 | 9161.95 | -5960.61 | 2020-10-01 | 2021-09-30 | 2021-06-24 | 06 | 2021-08-30 | 08
050.56765 | RES.2734.Magnolis III-B | 2478- ft. of 2 inch HDPE will serve 64 new lots in Magnolia III-B located of Plano Rd. Developer will open and close ditch and install casings for main and service lines | 7138.03 | 22670.19 | -15532.16 | -68.51% | 0.0122% | 7138.03 | 22670.19 | -15532.16 | 2020-10-01 | 2021-09-30 | 2021-07-02 | 07 | 2021-07-30 | 07
050.56770 | NG2734.Scottsville Rd. Reloc. | Relocate 140 ft. of 4 inch steel main on Scottsville Rd.- Bryant Way at Crossing to Mall Entrance. Install approx 150 ft. o 4 inch HDPE. This is a State Hwy. Relocation and is 100 % Reimburable. Team Construction wil prefom work. | 16124.75 | 21776.13 | -5651.38 | -25.95% | 0.02755% | 16124.75 | 21776.13 | -5651.38 | 2020-10-01 | 2021-09-30 | 2021-07-06 | 07 | 2021-07-31 | 07
050.56784 | 050.2651.LASER.DETECTORS | PROPOSED TO PURCHASE 3 GAS TRAX LZ-30 HAND HELD LASER REMOTE GAS DETECTORS FOR KY OPERATIONS. | 42562.04 | 42005.7 | 556.34 | 1.324% | 0.07273% | 42562.04 | 42005.7 | 556.34 | 2020-10-01 | 2021-09-30 | 2021-07-08 | 07 | 2021-09-30 | 09
050.56806 | RES.2636.STROUPMN.EXT | Install aproximentley 1500' of 2" HDPE | 5885.78 | 12192.09 | -6306.31 | -51.72% | 0.01006% | 5885.78 | 12192.09 | -6306.31 | 2020-10-01 | 2021-09-30 | 2021-07-12 | 07 | 2021-07-16 | 07
050.56815 | PRP.2636.McCulloch Avenue | Project was in the 7/27/20 KY PRP filing See project long description/notes | 44108.68 | 68022.72 | -23914.04 | -35.16% | 0.07537% | 44108.68 | 68022.72 | -23914.04 | 2020-10-01 | 2021-09-30 | 2021-07-13 | 07 | 2021-09-14 | 09
050.56818 | COM.2638.Mayfield Airport Ex_ | Install 510 feet of 2 inch poly main for three existing and two new hangars. Replace existing non-locateable service. We will be closer to more possible extension(s) | 11835.74 | 13607.94 | -1772.2 | -13.02% | 0.02023% | 11835.74 | 13607.94 | -1772.2 | 2020-10-01 | 2021-09-30 | 2021-08-01 | 08 | 2021-09-30 | 09
050.56826 | 2636.CRISPRD.SYSTEMUPGRADE | Install 3600' of 4" HDPE, relocate, upgrade 2" station, retire 3000' of 2" adaly | 95490.81 | 128767.45 | -33276.64 | -25.84% | 0.1632% | 95490.81 | 128767.45 | -33276.64 | 2020-10-01 | 2021-09-30 | 2021-07-12 | 07 | 2021-08-23 | 08
050.56834 | RES.2636.HWY142.MN.EXT | Install 2000' of 2" HDPE for new growth | 919.44 | 13290.36 | -12370.92 | -93.08% | 0.001571% | 919.44 | 13290.36 | -12370.92 | 2020-10-01 | 2021-09-30 | 2021-08-02 | 08 | 2021-08-18 | 08
050.56888 | RES.2737.Brock Drive | 600 Ft of 2 In HDPE to serve one new customer on Brock Drive in Stanford KY | 685.69 | 3720.28 | -3034.59 | -81.57% | 0.001172% | 685.69 | 3720.28 | -3034.59 | 2020-10-01 | 2021-09-30 | 2021-07-12 | 07 | 2021-09-30 | 09
050.56908 | Com.2735.ParkMammoth Ext. | 800 ft. of 2 imch HDPE will serve Clud House and Maintenance Bldg. Developer toopenand close ditch. | -387.97 | 3296.94 | -3684.91 | -111.8% | -0.000663% | -387.97 | 3296.94 | -3684.91 | 2020-10-01 | 2021-09-30 | 2021-07-19 | 07 | 2021-09-30 | 09
050.56928 | RES.2739.Ardmore Phase 2 | 2 Inch Main Extension for 2nd Phase of Ardmore Crossings in Shelbyville KY | 45385.42 | 47526.32 | -2140.9 | -4.505% | 0.07756% | 45385.42 | 47526.32 | -2140.9 | 2020-10-01 | 2021-09-30 | 2021-08-02 | 08 | 2021-09-30 | 09
050.56937 | RES.2738.Happy Valley | Main extension to feed Happy Valley subdivision in Campbellsville KY | 7096.05 | 9043.05 | -1947 | -21.53% | 0.01213% | 7096.05 | 9043.05 | -1947 | 2020-10-01 | 2021-09-30 | 2021-08-02 | 08 | 2021-08-27 | 08
050.56948 | COM.2736.Marie Dr. Ext | 100 ft of 2 inch HDPE will serve a new assised living facility located on Marie Dr.Developer wi open and close ditch | 1028.67 | 1952.54 | -923.87 | -47.32% | 0.001758% | 1028.67 | 1952.54 | -923.87 | 2020-10-01 | 2021-09-30 | 2021-11-01 | 11 | 2021-12-31 | 12
050.56960 | Paint Paducah Office | We have an agreement with Hernandez Painting to paint interior walls and trim in the Paducah office at 3510 Coleman Rd. | 21001.01 | 21639.3 | -638.29 | -2.95% | 0.03589% | 21001.01 | 21639.3 | -638.29 | 2020-10-01 | 2021-09-30 | 2021-08-01 | 08 | 2021-09-30 | 09
050.56962 | PRP.2635.S Seminary Street | See Project Long Description / Notes | 152251.38 | 505497.28 | -353245.9 | -69.88% | 0.2602% | 152251.38 | 505497.28 | -353245.9 | 2020-10-01 | 2021-09-30 | 2021-08-03 | 08 | 2021-09-30 | 09
050.56967 | 050.2637 Keri Court Retire | Retire 2 sections of 2 inch poly totaling 856 feet at this abandoned mobile home park. | 1702.45 | 614.23 | 1088.22 | 177.2% | 0.002909% | 1702.45 | 614.23 | 1088.22 | 2020-10-01 | 2021-09-30 | 2021-08-01 | 08 | 2021-08-31 | 08
050.56970 | RES.2738.Kountry Korner | 500 Ft of 2 In HDPE to serve one new customer in Summersville KY | 1007.36 | 2574.89 | -1567.53 | -60.88% | 0.001721% | 1007.36 | 2574.89 | -1567.53 | 2020-10-01 | 2021-09-30 | 2021-08-02 | 08 | 2021-09-30 | 09
050.56991 | RES.2734.Drakes.Ridge III | ft. of 4" and ft. of 2" wil sere 29 new building lots in Phase III of Drakes Ridge Sub located off Scottville Rd. Developer will open and close ditch and install casings for main and services. | 7948.77 | 23789.94 | -15841.17 | -66.59% | 0.01358% | 7948.77 | 23789.94 | -15841.17 | 2020-10-01 | 2021-09-30 | 2021-07-27 | 07 | 2021-09-30 | 09
050.57025 | RES.2637.Eagle Landing 2 Ext | Phase 2 of subdivision. Calls for 1,900 feet of 2 inch poly for 72 condo units | 43459.78 | 41517.69 | 1942.09 | 4.678% | 0.07427% | 43459.78 | 41517.69 | 1942.09 | 2020-10-01 | 2021-09-30 | 2021-08-16 | 08 | 2021-09-30 | 09
050.57062 | 2636.OhioCountyHospitalUpgrad | Install 640' of 2" HDPE for Hospital growth, Retire 460' of 2" Stl. | 20377.48 | 15848.65 | 4528.83 | 28.58% | 0.03482% | 20377.48 | 15848.65 | 4528.83 | 2020-10-01 | 2021-09-30 | 2021-08-16 | 08 | 2021-08-24 | 08
050.57134 | 2634.RES.VALLEYBROOKTRACEMN.E | Install 850' of 2" HDPE for subdivision growth | 10984.76 | 15706.37 | -4721.61 | -30.06% | 0.01877% | 10984.76 | 15706.37 | -4721.61 | 2020-10-01 | 2021-09-30 | 2021-08-24 | 08 | 2021-08-31 | 08
050.57160 | PRP.2634.W Noel & Browning St | Replace 162' of 4Inch Bare Steel with new 4Inch HDPE crossing. | 92570.12 | 46229.61 | 46340.51 | 100.2% | 0.1582% | 92570.12 | 46229.61 | 46340.51 | 2020-10-01 | 2021-09-30 | 2021-08-30 | 08 | 2021-09-28 | 09
050.57173 | RES.2734.Lexington II Frk. | 2530 ft. of 2 inch HDPE will serve 39 residentials lots in Lexington Place Phase II in Franklin. Developer will open and close ditch and install casins for main and service lines. | 9567.2 | 17908.58 | -8341.38 | -46.58% | 0.01635% | 9567.2 | 17908.58 | -8341.38 | 2020-10-01 | 2021-09-30 | 2021-08-30 | 08 | 2021-09-30 | 09
050.57191 | NG.2735.Liberty2 inch MW Ret | Retir 179 ft.of 2 inch MW off Liberty at Main St. in Glasgow | 695.58 | 1331.13 | -635.55 | -47.75% | 0.001189% | 695.58 | 1331.13 | -635.55 | 2020-10-01 | 2021-09-30 | 2021-09-01 | 09 | 2021-09-30 | 09

## 2022
Atmos Energy Corporation
(Kentucky Division)
Case No. 2024-00276
Construction Projects 2022
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised
Workpaper Reference No(s).:
Project No. | Project Title / Description |  | Annual Actual Cost 2022 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 188764.93 | 0 |  |  | 3.474% | 2191900.72 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 10463.62 | 0 |  |  | 0.2854% | 180060.26 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 43437.05 | 0 |  |  | 0.6586% | 415474.87 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 14030.61 | 0 |  |  | 0.4183% | 263898.68 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 13151.28 | 0 |  |  | 0.4171% | 263169.03 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 48361.31 | 0 |  |  | 1.647% | 1039262.92 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 16889.1 | 0 |  |  | 0.2933% | 185012.19 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 10746.79 | 0 |  |  | 0.3088% | 194823.48 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 118953.21 | 0 |  |  | 2.553% | 1610907.32 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 134893.58 | 0 |  |  | 2.759% | 1740772.42 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2017-09-30 | 09
050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 23869.15 | 0 |  |  | 0.9309% | 587262.99 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 84676.05 | 0 |  |  | 2.294% | 1447039.8 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 4427.77 | 0 |  |  | 0.0824% | 51985.56 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 10479.39 | 0 |  |  | 0.2426% | 153036.8 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 18017.52 | 0 |  |  | 0.4874% | 307463.01 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 17222.25 | 0 |  |  | 0.3549% | 223876.28 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 35906.37 | 0 |  |  | 0.4451% | 280803.46 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 12233.46 | 0 |  |  | 0.2554% | 161112.65 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5174.21 | 0 |  |  | 0.1892% | 119358.67 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 49968.99 | 0 |  |  | 1.17% | 738208.11 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 41074.74 | 0 |  |  | 0.6948% | 438371.08 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 7100.53 | 0 |  |  | 0.2061% | 129995.53 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 1507918.83 | 0 |  |  | 15.33% | 9674322.95 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 102119.93 | 0 |  |  | 1.59% | 1002915.54 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 80951.91 | 0 |  |  | 1.436% | 906257.32 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 97278.4 | 0 |  |  | 1.232% | 776974.07 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 111437.56 | 0 |  |  | 1.589% | 1002199.95 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 425154.15 | 0 |  |  | 5.269% | 3324109.03 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 69247.1 | 0 |  |  | 1.778% | 1121944.14 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 100678.58 | 0 |  |  | 1.015% | 640096.22 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 864616.4 | 0 |  |  | 10.65% | 6720466.27 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 367255.88 | 0 |  |  | 5.395% | 3403698.73 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2017-09-30 | 09
050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 108244.08 | 0 |  |  | 1.306% | 823920.19 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 321256.23 | 0 |  |  | 3.905% | 2463728.84 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 13574.39 | 0 |  |  | 0.6164% | 388850.46 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 31462.7 | 0 |  |  | 0.8024% | 506208.27 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 48355.27 | 0 |  |  | 0.922% | 581695.56 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 30839.44 | 0 |  |  | 0.7539% | 475650.75 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 29440.71 | 0 |  |  | 0.732% | 461809.58 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 58827.75 | 0 |  |  | 0.8403% | 530146.29 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 36591.5 | 0 |  |  | 0.4973% | 313769.56 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 436094.68 | 0 |  |  | 3.547% | 2237684.52 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 93545.48 | 0 |  |  | 1.838% | 1159689.77 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 47027.71 | 0 |  |  | 0.4457% | 281202.69 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 620434.65 | 0 |  |  | 8.071% | 5091804.55 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 220078.35 | 0 |  |  | 2.688% | 1695976.57 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 244171.86 | 0 |  |  | 5.829% | 3677483.15 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 358638.24 | 0 |  |  | 5.044% | 3181895.42 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 214534.25 | 0 |  |  | 2.846% | 1795250.55 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 81968.46 | 0 |  |  | 1.672% | 1054752.37 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 329964.4 | 0 |  |  | 4.599% | 2901709.31 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 291453.61 | 0 |  |  | 2.719% | 1715297.97 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 902973.49 | 0 |  |  | 10.48% | 6614393.6 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 565591.62 | 0 |  |  | 8.07% | 5091024.99 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 239101.25 | 0 |  |  | 2.615% | 1649464.85 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 539878.9 | 0 |  |  | 10.47% | 6602312.1 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 125458.48 | 0 |  |  | 2.82% | 1779324.39 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 159102.8 | 0 |  |  | 3.56% | 2246234.06 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 195537.01 | 0 |  |  | 3.553% | 2241415.53 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 138551.14 | 0 |  |  | 3.144% | 1983570.13 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 198894.93 | 0 |  |  | 2.804% | 1768959.73 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 166063.36 | 0 |  |  | 3.532% | 2228266.49 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 55101.69 | 0 |  |  | 1.835% | 1157528.55 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 654662.91 | 0 |  |  | 14.45% | 9117764.05 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 229355.58 | 0 |  |  | 8.808% | 5556872.67 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 56835.37 | 0 |  |  | 3.307% | 2086259.7 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 109449.81 | 0 |  |  | 1.585% | 999696.96 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 10985.7 | 0 |  |  | 0.1999% | 126115.83 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 21481.27 | 0 |  |  | 0.8549% | 539353.52 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 32469.86 | 0 |  |  | 1.134% | 715187.21 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 56456.24 | 0 |  |  | 0.3166% | 199769.03 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 18525.22 | 0 |  |  | 0.1889% | 119171.4 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 27693.69 | 0 |  |  | 0.5188% | 327295.38 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 4154.35 | 0 |  |  | 0.4226% | 266615.71 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 91469.07 | 0 |  |  | 0.9986% | 629998.53 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 26265.38 | 0 |  |  | 0.6762% | 426600.55 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 9782.61 | 0 |  |  | 0.1251% | 78895.11 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 87258.19 | 0 |  |  | 3.717% | 2345219.66 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 21812.55 | 0 |  |  | 1.384% | 872874.94 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 5768.11 | 0 |  |  | 1.245% | 785302.1 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 29599.63 | 0 |  |  | 0.9753% | 615282.97 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 33612.36 | 0 |  |  | 0.5724% | 361130.42 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 10625.61 | 0 |  |  | 0.4004% | 252620.24 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 55255.67 | 0 |  |  | 1.17% | 738090.02 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 22457.29 | 0 |  |  | 0.6363% | 401419.57 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 82542.97 | 0 |  |  | 2.014% | 1270576.97 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 39554.37 | 0 |  |  | 1.69% | 1066093.45 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 16803.02 | 0 |  |  | 0.3241% | 204465 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 151428.1 | 0 |  |  | 3.826% | 2413961.89 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 27830.22 | 0 |  |  | 1.204% | 759753.18 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 10273.26 | 0 |  |  | 1.063% | 670328.97 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 49879.23 | 0 |  |  | 1.496% | 944000.33 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 19623.9 | 0 |  |  | 0.5416% | 341688.22 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | -2039.11 | 0 |  |  | 0.4339% | 273725.79 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 35169.83 | 0 |  |  | 1.259% | 794290.66 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 32613.86 | 0 |  |  | 0.5% | 315417.49 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 239582.64 | 0 |  |  | 3.396% | 2142525.89 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2017-12-31 | 12
050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 68863.97 | 0 |  |  | 3.063% | 1932359.38 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 19745.18 | 0 |  |  | 0.5538% | 349357 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 163971.48 | 0 |  |  | 3.953% | 2494046.92 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 24202.85 | 0 |  |  | 0.9502% | 599458.09 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 31767.11 | 0 |  |  | 0.6928% | 437094.87 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 5338.42 | 0 |  |  | 1.169% | 737446.15 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 22026.75 | 0 |  |  | 0.9395% | 592715.95 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 36909.86 | 0 |  |  | 0.7186% | 453373.79 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 50418.26 | 0 |  |  | 0.8651% | 545803.62 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 10296.97 | 0 |  |  | 0.4143% | 261390.5 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 154450.59 | 0 |  |  | 4.299% | 2711868.83 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 86086.35 | 0 |  |  | 1.6% | 1009710.85 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 10178.06 | 0 |  |  | 0.297% | 187343.11 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 6233.04 | 0 |  |  | 0.1279% | 80677.53 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 8.06 | 0 |  |  | 0.02084% | 13145.8 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 695462.07 | 0 |  |  | 24.76% | 15618093.03 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 1381903.02 | 0 |  |  | 14.63% | 9228913.32 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2020-09-30 | 09
050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 1750684.45 | 0 |  |  | 24.42% | 15409279.24 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 1448334.89 | 0 |  |  | 20.65% | 13026059.3 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 1520.4 | 0 |  |  | 0.02383% | 15035.41 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 188.6 | 0 |  |  | 0.01325% | 8359.71 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.25675 | 050..2734.Cave.Mill.Sta.Ext. | 4 inch PE Ext. Cave Mill Sta. | -1697 | 9045.07 | -10742.07 | -118.8% | 0.007381% | 4656.67 | 9045.07 | -4388.4 | 2021-10-01 | 2022-09-30 | 2011-04-15 | 04 | 2011-09-28 | 09
050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 662349.17 | 0 |  |  | 3.984% | 2513170.5 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 1088162.54 | 0 |  |  | 9.223% | 5818494.86 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 1298.35 | 0 |  |  | 9.724% | 6134434.14 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 2400.61 | 0 |  |  | 9.69% | 6113213.57 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 658020.05 | 0 |  |  | 12.1% | 7636592.65 | Non Budgeted |  | 2021-10-01 | 2022-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26745 | 050.2734.Commerce and B White | 1875 ft. of 2 inch PE - Commerce and B. White - Elkton | -5953.75 | 8119.62 | -14073.37 | -173.3% | 0.002826% | 1782.86 | 8119.62 | -6336.76 | 2021-10-01 | 2022-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
050.27061 | 050.2634.Oakwood Dr. | Install 2023 ft 2 Inch PE | -3542.79 | 9698.35 | -13241.14 | -136.5% | 0.007366% | 4647.1 | 9698.35 | -5051.25 | 2021-10-01 | 2022-09-30 | 2011-04-21 | 04 | 2011-09-28 | 09
050.27983 | 050.2636.Menards | Install 1741 ft 2 Inch Pe and 750 ft 4 Inch PE to serve new commercial Developement | -7658.85 | 11988.09 | -19646.94 | -163.9% | 0.002622% | 1654.14 | 11988.09 | -10333.95 | 2021-10-01 | 2022-09-30 | 2011-07-01 | 07 | 2011-09-28 | 09
050.28018 | 050.2635.Hwy 373 | Install 1000 Ft 2 Inch PE | -364.72 | 12924.87 | -13289.59 | -102.8% | 0.01232% | 7773.17 | 12924.87 | -5151.7 | 2021-10-01 | 2022-09-30 | 2011-08-01 | 08 | 2011-09-28 | 09
050.28025 | 050.2634.Hwy 260 | Install 420 Ft 4 Inch PE to serve new addition at the Veterans center in Hanson Ky. | -1890.34 | 4047.41 | -5937.75 | -146.7% | 0.00329% | 2075.46 | 4047.41 | -1971.95 | 2021-10-01 | 2022-09-30 | 2010-12-15 | 12 | 2011-09-28 | 09
050.28262 | 050.2636.King Rd. | Install 600 Ft. 2 Inch PE to serve 1 residential customer | -2269.93 | 4779.25 | -7049.18 | -147.5% | 0.002701% | 1704.29 | 4779.25 | -3074.96 | 2021-10-01 | 2022-09-30 | 2011-10-30 | 10 | 2012-09-28 | 09
050.28267 | 050.2636.Carlton Dr. | Install 1283 Ft 2 Inch PE to serve 1 commercial customer | -5672.71 | 5645.47 | -11318.18 | -200.5% | 0.001732% | 1092.54 | 5645.47 | -4552.93 | 2021-10-01 | 2022-09-30 | 2011-11-01 | 11 | 2012-09-28 | 09
050.28465 | 050.2736.Hwy 41 Nortonville | Install 300 Ft 2 Inch PE to serve 1 residential customers | -1921.48 | 2881.48 | -4802.96 | -166.7% | 0.00367% | 2315.1 | 2881.48 | -566.38 | 2021-10-01 | 2022-09-30 | 2011-11-14 | 11 | 2012-09-28 | 09
050.29015 | 050.2636.Challenger Center 54 | Install 252 ft 2 Inch PE | -1326.59 | 3343 | -4669.59 | -139.7% | 0.003197% | 2016.99 | 3343 | -1326.01 | 2021-10-01 | 2022-09-30 | 2010-08-01 | 08 | 2010-09-28 | 09
050.29150 | 050.2637.Windmere Cv Ext | Install 400 feet of 2 inch PE along Windmere Drive and Windmere Cove. | -3745.54 | 4997.76 | -8743.3 | -174.9% | 0.0007189% | 453.55 | 4997.76 | -4544.21 | 2021-10-01 | 2022-09-30 | 2012-03-01 | 03 | 2013-09-28 | 09
050.29764 | 2739.LAW.BLUEBIRD CT 2012 | INSTALL 300ft OF 2in PE FOR RESTURANT AND FUTURE EXPANSION | -796 | 1193.5 | -1989.5 | -166.7% | 0.001392% | 878.14 | 1193.5 | -315.36 | 2021-10-01 | 2022-09-30 | 2012-03-01 | 03 | 2013-03-01 | 03
050.30242 | 050.2637.Ladera Ln Ext | Install 1,960' of 4" PE and 1,130' of 2" PE | -7470 | 30289.94 | -37759.94 | -124.7% | 0.03151% | 19876.59 | 30289.94 | -10413.35 | 2021-10-01 | 2022-09-30 | 2012-05-07 | 05 | 2012-05-31 | 05
050.30328 | 050.2636.Payton Place | Install approximately 2417 ft 2 Inch PE to serve 28 residential lots | -4572.09 | 11859.42 | -16431.51 | -138.6% | 0.01576% | 9945.72 | 11859.42 | -1913.7 | 2021-10-01 | 2022-09-30 | 2012-05-01 | 05 | 2012-09-28 | 09
050.30730 | 050.2637.Lightfoot Rd Ext | Install 340 feet of 2 inch PE for one new and one existing residential customer. | -1159.95 | 3001.27 | -4161.22 | -138.6% | 0.01117% | 7047.65 | 3001.27 | 4046.38 | 2021-10-01 | 2022-09-30 | 2012-06-15 | 06 | 2012-08-30 | 08
050.35013 | PRP.2609.Fruithill Hoptown 2 | Replace 26000 ft 6 Inch Bare Steel with 12 Inch Steel | -6458.2 | 7419912.38 | -7426370.58 | -100.1% | 10.22% | 6445135.59 | 7419912.38 | -974776.79 | 2021-10-01 | 2022-09-30 | 2013-10-01 | 10 | 2014-12-31 | 12
050.43846 | 050.2637.Royal Park Dr Ext 4 | Install 650 feet of 2 inch PE main for one new residential and 2 existing residential customer requesting gas. | 3300.58 | 3112.16 | 188.42 | 6.054% | 0.009216% | 5814.25 | 3112.16 | 2702.09 | 2021-10-01 | 2022-09-30 | 2016-08-03 | 08 | 2016-11-30 | 11
050.44088 | 050.2734.Hwy 31W PI SGlen | Relocate 6 inch HP Steel - State Hwy Widening Hwy 31 - Dillard to Buchanan Park | -70461.57 | 1174025.58 | -1244487.15 | -106% | 0.184% | 116076.61 | 1174025.58 | -1057948.97 | 2021-10-01 | 2022-09-30 | 2016-09-12 | 09 | 2019-09-30 | 09
050.46190 | 050.2634.Westside Vlv Replace | Replace a 4 inch critical valve that has become nearly impossible to turn. It was installed in 1956. | -12.25 | 6079.01 | -6091.26 | -100.2% | 0% | 0 | 6079.01 | -6079.01 | 2021-10-01 | 2022-09-30 | 2017-06-19 | 06 | 2022-09-30 | 09
050.46537 | 2739.Waddy Line Ph 2 | FY18/19 Budgeted System Improvement project occurring in Shelby County, KY. Replacing 25,000 feet of 6" high pressure steel main with 12" high pressure steel main. Starting R/W preparation and completion of easement acquisition in October FY18. Starting | 48386.59 | 12139301.77 | -12090915.18 | -99.6% | 16.74% | 10562857.35 | 12139301.77 | -1576444.42 | 2021-10-01 | 2022-09-30 | 2017-10-01 | 10 | 2019-03-30 | 03
050.47184 | 2634.Madisonville Equipment | Mueller Tapping Drill @ $9,000, Replace 3" Mole @ $7,000, Concrete Saw @ $2,500, 9 Sensit Golds (Replacement) @ $1,400 each, TD Williamson 3 on 4 Machine Valves and Stopper @ $35,000 | 4837.06 | 82933.06 | -78096 | -94.17% | 0.1422% | 89730.89 | 82933.06 | 6797.83 | 2021-10-01 | 2022-09-30 | 2017-10-01 | 10 | 2018-09-15 | 09
050.48803 | 2634.HWY 41A Phase 1 | Replace Distribution Main for HWY Project | -8849.43 | 565013.23 | -573862.66 | -101.6% | 0.3779% | 238433.14 | 565013.23 | -326580.09 | 2021-10-01 | 2022-09-30 | 2018-06-15 | 06 | 2019-07-31 | 07
050.50630 | 050.2637.Westhaven Dr Ext | Install 100 feet of 2 inch poly main for one existing residential customer requesing natural gas. | -11.33 | 4095.19 | -4106.52 | -100.3% | 0% | 0 | 4095.19 | -4095.19 | 2021-10-01 | 2022-09-30 | 2019-02-07 | 02 | 2022-09-30 | 09
050.50720 | 050.2638.S.11th Street Ext | Install 250 feet of 2 inch poly pipe to tie two systems together and eliminate an A.O.C, a gas service is running under the Graves County Health Department. | -1176.57 | 7578.6 | -8755.17 | -115.5% | 0% | 0 | 7578.6 | -7578.6 | 2021-10-01 | 2022-09-30 | 2019-02-21 | 02 | 2022-09-30 | 09
050.52962 | 050.2739.Commerce Way | 600 Ft of 2 In HDPE to serve multiple customers on Commerce Way | 1018.54 | 1093.77 | -75.23 | -6.878% | 0.001614% | 1018.54 | 1093.77 | -75.23 | 2021-10-01 | 2022-09-30 | 2020-01-06 | 01 | 2020-02-28 | 02
050.54337 | RES.2739.English Garden | 200 Ft of 2 In HDPE to serve two lots in Seascape Subdivison | 1018.54 | 1218 | -199.46 | -16.38% | 0.001614% | 1018.54 | 1218 | -199.46 | 2021-10-01 | 2022-09-30 | 2020-07-06 | 07 | 2020-09-25 | 09
050.54507 | RES.2637.Highland Ch Rd 2 | Install 35 feet of 2 inch poly main for one new customer (Steve Keiler) requesting natural gas. | 822.2 | 2754.51 | -1932.31 | -70.15% | 0.006008% | 3790.5 | 2754.51 | 1035.99 | 2021-10-01 | 2022-09-30 | 2020-08-01 | 08 | 2021-09-30 | 09
050.54596 | 050.2634.S.MadisonL/P.FY21 | Replace approximately 181' of 1.25" Stl, 1084' of 2" Stl, 5524' of 3" Stl, 9868' of 4" Stl and 490' of 6" Stl, with10570' of 2" HDPE and 2565' of 4" HDPE Retire 3 Reg. Stations | -2961.03 | 1389570.87 | -1392531.9 | -100.2% | 2.191% | 1382482.27 | 1389570.87 | -7088.6 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-04-30 | 04
050.54694 | PRP.2735.Grandview Dr | Project was in the 7/27/20 KY PRP filing See project long description/ notes | 1094.61 | 813827.17 | -812732.56 | -99.87% | 1.286% | 811234.41 | 813827.17 | -2592.76 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54723 | PRP.2737.W Broadway | Project was in the 7/27/20 KY PRP filing See project Long description / notes | -510.77 | 438191.66 | -438702.43 | -100.1% | 0.2358% | 148779.4 | 438191.66 | -289412.26 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-02-01 | 02
050.54742 | PRP.2738.Perryville Rd | Project was in the 7/27/20 KY PRP filing See project Long Description / notes | 4425.98 | 1195311.07 | -1190885.09 | -99.63% | 2.008% | 1266665.71 | 1195311.07 | 71354.64 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54743 | PRP.2635.Princeton North | Project was in the 7/27/20 KY PRP filing See project long description/notes | -328.11 | 1681613.82 | -1681941.93 | -100% | 2.665% | 1681285.71 | 1681613.82 | -328.11 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-09-25 | 09
050.54755 | 050.2634.Low Pressure Services | Service replacement for Low pressure project in Madisonville Phase I | -699.49 | 1091445.97 | -1092145.46 | -100.1% | 1.71% | 1078590.63 | 1091445.97 | -12855.34 | 2021-10-01 | 2022-09-30 | 2020-11-01 | 11 | 2021-07-30 | 07
050.54758 | PRP.2734.Brick St Franklin | Project was in the 7/27/20 KY PRP Filing See project long description /notes | 74764.26 | 655013.88 | -580249.62 | -88.59% | 1.11% | 700143.55 | 655013.88 | 45129.67 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54759 | PRP.2734.LP W Ky. Ave | Project was in the 7/27/20 KY PRP filing See Project Long Description/notes | 43939.47 | 1120038.8 | -1076099.33 | -96.08% | 1.778% | 1121902.62 | 1120038.8 | 1863.82 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.54764 | PRP.2635.Maple Ave | Project was in the KY 7/27/20 PRP Filing See project Long Description /notes | 224.63 | 1006727.2 | -1006502.57 | -99.98% | 0.04698% | 29639.87 | 1006727.2 | -977087.33 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2023-04-30 | 04
050.54809 | PRP.2734.E 3rd St Russellvill | Project was in the 7/27/20 KY PRP filing See project long description / notes | -169.62 | 1028886.89 | -1029056.51 | -100% | 1.696% | 1070274.64 | 1028886.89 | 41387.75 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-08-30 | 08
050.54822 | 2736. So. Main LP Repls.Hopk. | Replace approx 69 feet of 1 1/4", 1,712 feet of 2", 430 feet of 3", 6,085 feet of 4" and 3,445 feet of 6". Install 3,218 feet of 4" HDPE and 3,219 feet of 2" HDPE. Retire RS9935 & RS1610. Please see ACE summary Description for more details | -150.4 | 960658.85 | -960809.25 | -100% | 1.751% | 1104917.26 | 960658.85 | 144258.41 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-05-31 | 05
050.54825 | 2736.LP S. Main Sevices | Replace 57 services associated low pressure replacement on S. Main St. in Hopkinsville, KY. | -263.69 | 339615.1 | -339878.79 | -100.1% | 0.9174% | 578760.16 | 339615.1 | 239145.06 | 2021-10-01 | 2022-09-30 | 2020-12-01 | 12 | 2021-06-30 | 06
050.55167 | 2612.KY RTU Upgrades.FY21 | Replacement of Obsolete and Defective RTUs in Kentucky. Total $90k Wireless/Wired upgrades where applicable. | 46.47 | 116699.86 | -116653.39 | -99.96% | 0.1606% | 101302.33 | 116699.86 | -15397.53 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-06-30 | 06
050.55340 | Sorgho KY 4" Steel 3rd Party | 3rd Party Damage - 4" cut steel line in Sorgho, KY. This is off Hwy 56 around the Whispering Meadows subdivision area. | -40539.25 | 279658.15 | -320197.4 | -114.5% | 0.3639% | 229603.12 | 279658.15 | -50055.03 | 2021-10-01 | 2022-09-30 | 2020-10-28 | 10 | 2020-11-30 | 11
050.55413 | PRP.2635.W Main St | See project Long Description/Notes | 707.12 | 1078083.56 | -1077376.44 | -99.93% | 1.71% | 1078790.68 | 1078083.56 | 707.12 | 2021-10-01 | 2022-09-30 | 2020-11-20 | 11 | 2021-08-30 | 08
050.55561 | PRP.2637.Broad St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 24416.5 | 740134.15 | -715717.65 | -96.7% | 1.03% | 649996.89 | 740134.15 | -90137.26 | 2021-10-01 | 2022-09-30 | 2020-12-18 | 12 | 2021-09-20 | 09
050.55667 | PRP.2737.Ledford Lane | Project was in the 7/27/20 KY PRP filing. See project Long description / notes | -86.79 | 512169.9 | -512256.69 | -100% | 0.6221% | 392464.42 | 512169.9 | -119705.48 | 2021-10-01 | 2022-09-30 | 2021-01-25 | 01 | 2021-07-30 | 07
050.55692 | PRP.2734.High St Alley BG | Project was in the 7/27/20 KY PRP filing See project long description / notes | -67.66 | 712301.33 | -712368.99 | -100% | 1.129% | 712233.67 | 712301.33 | -67.66 | 2021-10-01 | 2022-09-30 | 2021-01-22 | 01 | 2021-08-30 | 08
050.55751 | RES.2636.MILTONRD.MN.EXT | Install 1360' of 2" PE. for new customer | 5541.18 | 13748.8 | -8207.62 | -59.7% | 0.001171% | 739.07 | 13748.8 | -13009.73 | 2021-10-01 | 2022-09-30 | 2021-02-02 | 02 | 2021-09-30 | 09
050.55810 | PRP.2734.BG Centerline 3 | Replace 30,800 ft of 8" HPD Bare Steel Main with 30,800 ft of 8" Fusion Bond Epoxy HPD Steel main and 3,382 ft of 2" and 4,150 ft of 4" HDPE, also replace 2 Town Border Stations; 8 services | 12312276.45 | 12143675.09 | 168601.36 | 1.388% | 21.01% | 13256451.19 | 12143675.09 | 1112776.1 | 2021-10-01 | 2022-09-30 | 2021-01-28 | 01 | 2022-09-30 | 09
050.55814 | PRP.2637.Hill St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 521.6 | 641453.64 | -640932.04 | -99.92% | 0.9122% | 575495.38 | 641453.64 | -65958.26 | 2021-10-01 | 2022-09-30 | 2021-02-16 | 02 | 2021-09-30 | 09
050.55844 | COM.2637.Barkley Field Ext | Install 7,700 feet of 4 inch poly and 900 of 2 inch poly for Paducah Barkley Field Airport. | 1390.68 | 347918.61 | -346527.93 | -99.6% | 0.2004% | 126426.47 | 347918.61 | -221492.14 | 2021-10-01 | 2022-09-30 | 2021-07-01 | 07 | 2021-09-30 | 09
050.55914 | LP.2734.McGoodwin Svc | Replace 50 sevices in conjunction with McGoodwin LP Main Replacement in Franklin | 118585.81 | 268902.74 | -150316.93 | -55.9% | 0.2123% | 133954.63 | 268902.74 | -134948.11 | 2021-10-01 | 2022-09-30 | 2021-02-18 | 02 | 2021-09-30 | 09
050.55917 | LP.2734.McGoodwin.Replc | Replace approx,. 3000 feet of LP, 30 feet 6" bare, 307 feet 4" bare, 350 feet 3" epoxy, 194 feet 2" epoxy, 215 feet 1.25" bare, 174 feet of 6" epoxy, 1,292 feet 4" epoxy, 407 feet 3" bare, 31 feet 1.5" bare with2165 ft. of 2" PE in Franklin, KY. | 82465.2 | 344894.36 | -262429.16 | -76.09% | 0.3978% | 250957.92 | 344894.36 | -93936.44 | 2021-10-01 | 2022-09-30 | 2021-03-01 | 03 | 2021-07-30 | 07
050.55997 | 2636.LP.FREDERICAST. | Install 7,000' of 6" HDPE, 3550 of 2" HDPE,I.P. - retire 12672' of LP. steel | 7026.62 | 1376885.51 | -1369858.89 | -99.49% | 2.182% | 1376745.53 | 1376885.51 | -139.98 | 2021-10-01 | 2022-09-30 | 2021-03-01 | 03 | 2021-07-30 | 07
050.56052 | PRP.2636.14th St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 748.02 | 867695.58 | -866947.56 | -99.91% | 0.9784% | 617253.53 | 867695.58 | -250442.05 | 2021-10-01 | 2022-09-30 | 2021-03-20 | 03 | 2021-09-30 | 09
050.56097 | PRP.2735.Oakland | Project was in the 7/27/20 KY PRP filing See project long description / notes | -1939.41 | 514218.54 | -516157.95 | -100.4% | 0.812% | 512279.13 | 514218.54 | -1939.41 | 2021-10-01 | 2022-09-30 | 2021-03-23 | 03 | 2021-09-20 | 09
050.56113 | 2735.Mis.Rotary Meters. | Misc. rotary meter replacements - Glasow Area | 13306.45 | 59949.96 | -46643.51 | -77.8% | 0.06872% | 43352.46 | 59949.96 | -16597.5 | 2021-10-01 | 2022-09-30 | 2020-10-01 | 10 | 2021-08-31 | 08
050.56133 | 050.2636.Frederica St Services | Replace 80 LP.Stl. services with 80 intermitate PE. services | 6003.91 | 577123.27 | -571119.36 | -98.96% | 0.985% | 621435.57 | 577123.27 | 44312.3 | 2021-10-01 | 2022-09-30 | 2021-04-01 | 04 | 2021-09-30 | 09
050.56147 | RES.2739.Cherokee Drive | 2000 Ft of 2 In HDPE to serve Cherokee Drive in Shelbyville KY | -224.62 | 4243.98 | -4468.6 | -105.3% | 0.004321% | 2725.84 | 4243.98 | -1518.14 | 2021-10-01 | 2022-09-30 | 2021-03-29 | 03 | 2021-08-30 | 08
050.56151 | LP.2736.17th.St.Replacement | Replace 101 feet of 1 1/1", 1,750 feet of 2", 4,316 feet of 4" and 3,623 feet of 6" with 3,470 feet of 4" HDPE and 4,038 feet of 2" HDPE. Retire RS9422 . This is a FY21 Capital LP Project. Construction by Martin Contracting. | 1444.17 | 707136.26 | -705692.09 | -99.8% | 0.9116% | 575142.33 | 707136.26 | -131993.93 | 2021-10-01 | 2022-09-30 | 2021-04-01 | 04 | 2021-09-30 | 09
050.56170 | 2734.Redbud Sta. Retire | Redbud Station Retirement - Install 1,700 feet of 2" PE and 300 feet of 4" PE to tie 2 systems together to retire station for property improvements. | -169.26 | 189843.7 | -190012.96 | -100.1% | 0.2009% | 126767.66 | 189843.7 | -63076.04 | 2021-10-01 | 2022-09-30 | 2021-03-26 | 03 | 2021-07-30 | 07
050.56252 | Shelbyville KY WMR Towers.FY21 | Purchase 3 FLXNT BS M400 WMR towers for Shelbyville, KY area. Sites 809445 (620 Old Finchville Rd; Shelbyville, KY 40065), 827869 (586 Jeptha Knob Rd; Shelbyville, KY 40065) and 878182 (1306 Buck Creek Rd; Simpsonville, KY 40067) | 21863.14 | 183604.61 | -161741.47 | -88.09% | 0.2875% | 181357.95 | 183604.61 | -2246.66 | 2021-10-01 | 2022-09-30 | 2021-05-01 | 05 | 2021-10-31 | 10
050.56258 | 050.2637.Said Rd 6 in Replace | Existing 6" steel casing is shorted. We propose to replace 160' of 6" carrier pipe. Casing not required by KYTC due to extra wall thickness of pipe.. | 4872.92 | 67940.35 | -63067.43 | -92.83% | 0.109% | 68787.29 | 67940.35 | 846.94 | 2021-10-01 | 2022-09-30 | 2021-05-01 | 05 | 2021-09-30 | 09
050.56260 | PRP.2637.S 3rd St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 239969.41 | 706063.62 | -466094.21 | -66.01% | 1.127% | 710742.72 | 706063.62 | 4679.1 | 2021-10-01 | 2022-09-30 | 2021-06-30 | 06 | 2021-11-16 | 11
050.56264 | 050.2637.Estes Ln SYS IMP | Propose to install 2,600 feet of 6 inch poly main along Estes Lane from Meacham Lane to Husband Rd in order to bolster the system in that area. We also propose to retire RS 1656 Husband Rd Reg Sta. The station sits too close to busy hwy | 1540.19 | 228202.86 | -226662.67 | -99.33% | 0.2898% | 182807.55 | 228202.86 | -45395.31 | 2021-10-01 | 2022-09-30 | 2021-06-01 | 06 | 2021-09-30 | 09
050.56292 | 050.009.2636.Swedish Match | Replacement of Swedish Match station due to upgrade faccilities. | 11088.86 | 427146.11 | -416057.25 | -97.4% | 0.5357% | 337984.82 | 427146.11 | -89161.29 | 2021-10-01 | 2022-09-30 | 2021-05-01 | 05 | 2021-08-31 | 08
050.56356 | INT.2739.Clear Creek Exposure | Downrate pressure across exposure in Clear Creek. Replace Old 7 Mile Pike Reg Station and eliminate Goodman Ave Reg Station | -2110.89 | 187325.75 | -189436.64 | -101.1% | 0.2387% | 150613.25 | 187325.75 | -36712.5 | 2021-10-01 | 2022-09-30 | 2021-05-01 | 05 | 2021-09-22 | 09
050.56372 | PRP.2734.Sycamore St | Project was in the 7/27/20 KY PRP filing See project long description / notes | 12101.58 | 870666.98 | -858565.4 | -98.61% | 1.188% | 749794.48 | 870666.98 | -120872.5 | 2021-10-01 | 2022-09-30 | 2021-05-15 | 05 | 2021-09-30 | 09
050.56437 | PRP.2734.Gayle Way | Project was in the 7/27/20 KY PRP filing See project long description / notes | 83556.58 | 477517.22 | -393960.64 | -82.5% | 0.6536% | 412344.2 | 477517.22 | -65173.02 | 2021-10-01 | 2022-09-30 | 2021-05-20 | 05 | 2021-09-30 | 09
050.56499 | 2739.Concrete Saw | One concrete saw ($1200). | 40.93 | 1527.48 | -1486.55 | -97.32% | 0.002325% | 1466.91 | 1527.48 | -60.57 | 2021-10-01 | 2022-09-30 | 2021-05-01 | 05 | 2021-09-30 | 09
050.56509 | RES.2637.May-Met Rd Rev Ext | Install 100 feet of 2 inch P.E main for one new residential customer (Tubby Chapman) requesting natural gas service | -24.06 | 3746.92 | -3770.98 | -100.6% | 0.01069% | 6742.01 | 3746.92 | 2995.09 | 2021-10-01 | 2022-09-30 | 2021-07-01 | 07 | 2021-09-30 | 09
050.56524 | PRP.2636.Sycamore St | Project was in the 7/27/20 KY PRP filing See project long description / notes | -1215.23 | 512740.46 | -513955.69 | -100.2% | 0.5484% | 345947.75 | 512740.46 | -166792.71 | 2021-10-01 | 2022-09-30 | 2021-06-10 | 06 | 2021-09-30 | 09
050.56555 | PRP.2635.HWY 62 Relocation | See Project Long Description/notes | -1631.71 | 255068.21 | -256699.92 | -100.6% | 0.2962% | 186881.6 | 255068.21 | -68186.61 | 2021-10-01 | 2022-09-30 | 2021-06-23 | 06 | 2021-09-20 | 09
050.56595 | RES.2637.Eagle Landing Ext | Install app. 2,800 feet of 4 inch poly and 3,300 feet of 2 inch poly to serve 52 lots plus 14 condo units in theis new residential subdivision being developed by Mr. Donny Travis | -2275.6 | 176638.35 | -178913.95 | -101.3% | 0.2097% | 132287.95 | 176638.35 | -44350.4 | 2021-10-01 | 2022-09-30 | 2021-06-14 | 06 | 2021-09-30 | 09
050.56641 | RES.2634.SIMMENTALDR.MN.EXT | Install 600' of 2" HDPE. for new customers | -1554.52 | 6624.02 | -8178.54 | -123.5% | 0.01742% | 10991.81 | 6624.02 | 4367.79 | 2021-10-01 | 2022-09-30 | 2021-07-12 | 07 | 2021-09-22 | 09
050.56646 | PRP.2737.KY152 | See Project long Description /Notes | -366.47 | 210493.31 | -210859.78 | -100.2% | 0.3331% | 210126.84 | 210493.31 | -366.47 | 2021-10-01 | 2022-09-30 | 2021-07-01 | 07 | 2021-09-20 | 09
050.56689 | INT.2737.Centre College Reloc | Install 575 ft of 4 In HDPE and 400 ft of 2 In HDPE to retire 650 ft of 4 In Steel, 450 ft of 2 In Steel, and 450 ft of 2 In Poly for Centre College | -146.12 | 86504 | -86650.12 | -100.2% | 0.01238% | 7812.58 | 86504 | -78691.42 | 2021-10-01 | 2022-09-30 | 2021-07-01 | 07 | 2021-08-31 | 08
050.56702 | RES.2638.Mitchell Dr Rev Ext | Install 385 feet of 2 inch poly main for one new home under construction. Will make gas availble to six vacant lots. | 7841.28 | 10651.31 | -2810.03 | -26.38% | 0.004789% | 3021.2 | 10651.31 | -7630.11 | 2021-10-01 | 2022-09-30 | 2021-06-28 | 06 | 2021-09-30 | 09
050.56708 | COM.2638.Grace Park Rev Ext | Install 2,500 feet of 2 inch poly main to serve eight new commercial lots in Grace Park Commercial Subdivision. Some of the new customers will be a Fivestar Convienience Store, C & C Real Estate, A brand new "Spec" building, Workman Bins (Agriculture | 7361.81 | 62739.85 | -55378.04 | -88.27% | 0.1016% | 64101.66 | 62739.85 | 1361.81 | 2021-10-01 | 2022-09-30 | 2021-07-01 | 07 | 2021-09-30 | 09
050.56737 | PRP.2734.Schweizer Road | Replace 25,500' of 8" high pressure Bare steel with 25,500' of Fusion Bond Epoxy Steel, project will also include a new Purchase Station , check meter , YZ odorizer, all electronics and a expanded station lot | 463447.19 | 10254292.78 | -9790845.59 | -95.48% | 0.8304% | 523901.99 | 10254292.78 | -9730390.79 | 2021-10-01 | 2022-09-30 | 2021-06-21 | 06 | 2023-09-30 | 09
050.56749 | RES. Peachtree.Ln.Ext | 400 ft. of 4 inch HDPE will serve new residential customers on Peachtree Lane in Bowlng Green. | -887.77 | 15655.19 | -16542.96 | -105.7% | 0.01031% | 6503.99 | 15655.19 | -9151.2 | 2021-10-01 | 2022-09-30 | 2021-06-28 | 06 | 2021-08-30 | 08
050.56757 | COM.Hwy218.Ext.Horse Cave | 500 ft. of 2 inch HDPE will serve a new grain bin for Bill Jenkins on Hwy 218 in Horse Cave. Main will be installed in private R-O-W. Open and Closed ditch will be provided. Atmos will provide bore. | -38.39 | 9161.95 | -9200.34 | -100.4% | 0.005014% | 3162.95 | 9161.95 | -5999 | 2021-10-01 | 2022-09-30 | 2021-06-24 | 06 | 2021-08-30 | 08
050.56806 | RES.2636.STROUPMN.EXT | Install aproximentley 1500' of 2" HDPE | -66.07 | 12192.09 | -12258.16 | -100.5% | 0.009225% | 5819.71 | 12192.09 | -6372.38 | 2021-10-01 | 2022-09-30 | 2021-07-12 | 07 | 2021-07-16 | 07
050.56815 | PRP.2636.McCulloch Avenue | Project was in the 7/27/20 KY PRP filing See project long description/notes | -1553.63 | 68022.72 | -69576.35 | -102.3% | 0.06745% | 42555.05 | 68022.72 | -25467.67 | 2021-10-01 | 2022-09-30 | 2021-07-13 | 07 | 2021-09-14 | 09
050.56818 | COM.2638.Mayfield Airport Ex_ | Install 510 feet of 2 inch poly main for three existing and two new hangars. Replace existing non-locateable service. We will be closer to more possible extension(s) | -46.3 | 13607.94 | -13654.24 | -100.3% | 0.01869% | 11789.44 | 13607.94 | -1818.5 | 2021-10-01 | 2022-09-30 | 2021-08-01 | 08 | 2021-09-30 | 09
050.56826 | 2636.CRISPRD.SYSTEMUPGRADE | Install 3600' of 4" HDPE, relocate, upgrade 2" station, retire 3000' of 2" adaly | 22673.86 | 128767.45 | -106093.59 | -82.39% | 0.1873% | 118164.67 | 128767.45 | -10602.78 | 2021-10-01 | 2022-09-30 | 2021-07-12 | 07 | 2021-08-23 | 08
050.56832 | 2739.WMR Endpoints.FY2022 | Purchase approximately 3942 WMR endpoints for Shelbyville, KY | 437566.34 | 408237.78 | 29328.56 | 7.184% | 0.6936% | 437566.34 | 408237.78 | 29328.56 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-08-31 | 08
050.56834 | RES.2636.HWY142.MN.EXT | Install 2000' of 2" HDPE for new growth | -7151.26 | 13290.36 | -20441.62 | -153.8% | -0.009878% | -6231.82 | 13290.36 | -19522.18 | 2021-10-01 | 2022-09-30 | 2021-08-02 | 08 | 2021-08-18 | 08
050.56844 | 2609.Misc.Equipment.FY2022 | Purchase 4 Metrotech VM-810 Pipe Locators ($3,375 each), 2 Stonebor Methanol Injection Pump ($4,900 each) | 29376.92 | 29658.57 | -281.65 | -0.9496% | 0.04656% | 29376.92 | 29658.57 | -281.65 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-11-30 | 11
050.56846 | 2651.Misc.Equipment.FY2022 | Purchase 1 Rycom Line Locator for Princeton ($2,900) and 1 Pipehorm Locator for OWB ($1,500) | 9948.76 | 5600.76 | 4348 | 77.63% | 0.01577% | 9948.76 | 5600.76 | 4348 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56848 | 2634.Misc.Equipment.FY2022 | Purchase 1 Huskie 2" Hydraulic Squeeze Tool ($4,000), 2 Heath Odorant Machines ($5,125 each = $10,250), 1 Sensit Calibration Station ($5,650), 1 Mueller No Blo Valve Changer ($3,950), 1 Utility Trailer ($2,500), and 2 Sensit Gold G3 ($1,825 = $3,650) | 38111.47 | 38187 | -75.53 | -0.1978% | 0.06041% | 38111.47 | 38187 | -75.53 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56850 | 2635.Misc.Equipment.FY2022 | Purchase 2 Sensit Gold G3 ($1,825 each = $3,650), 1 Mueller No Blo Valve Changer ($3,950), 1 Sensit Smart Calibration Station ($5,650), and 2 Jameson Insert Wire ($1,015 each = $2,030) | 19534.58 | 19449.92 | 84.66 | 0.4353% | 0.03096% | 19534.58 | 19449.92 | 84.66 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56852 | 2636.Misc.Equipment.FY2022 | Purchase 1 RKI 4-Gas Monitor Cal Station ($1,600), 2 Footage C850 Hydraulic Squeeze tool 4-8" PE ($8,800 each = $17,600), 2 Hydraulic pump for Footage C850 4-8" PE squeeze tool ($3,400 each = $6,800), 2 Timberline TC2-SR squeeze tool for 1/2-2" PE ($1,20 | 105374.39 | 105396.12 | -21.73 | -0.02062% | 0.167% | 105374.39 | 105396.12 | -21.73 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56854 | 2736.Misc.Equipment.FY2022 | Purchase 1 Tandem Axle Trailer ($2,500), 2 Heath Odorator ($5,125 each = $10,250), 1 Vivax/Metro Tech VM-810 Locator ($3,375), 2 Sensit Gold G3 ($1,825 each = $3,650), and 1 Sensit Smart Calibration Station ($5,650) | 32121.13 | 32363.49 | -242.36 | -0.7489% | 0.05091% | 32121.13 | 32363.49 | -242.36 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56856 | 2609.John Deere 540M.FY2022 | Purchase John Deere 540M Loader/Pallet Forks | 13954.47 | 15274.8 | -1320.33 | -8.644% | 0.02212% | 13954.47 | 15274.8 | -1320.33 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-11-30 | 11
050.56858 | 2637.Misc.Equipment.FY2022 | Purchase 1 Smart Calibration Station ($5,650), 1 Vivax/Metro Tech VM-180 ($3,375), 4 Long Handle/Footage C200 Squeeze Tool ($1,475 each = $5,900), 3 Sensit Gold G-3 ($1,825 each = $5,475), and 1 MC Miller Current Interrupter ($1,565) | 26190.1 | 27959.25 | -1769.15 | -6.328% | 0.04151% | 26190.1 | 27959.25 | -1769.15 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-01-31 | 01
050.56860 | 2638.Misc.Equipment.FY2022 | Purchase 1 Smart Calibration Station ($5,650) and 2 Long Handle/Footage C200 squeeze tool ($1,475 each = $2,950) | 13010.55 | 10946.94 | 2063.61 | 18.85% | 0.02062% | 13010.55 | 10946.94 | 2063.61 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56870 | 2734.Misc.Equipment.FY2022 | Purchase 1 Smart CAL 360 Desktop Calibration Station ($5,650), 1 Air Compressor ($2,500), 1 Bandsaw ($3,500) and 2 3" TDW Valves ($3,913 each = $7,826) | 23741.61 | 24791 | -1049.39 | -4.233% | 0.03763% | 23741.61 | 24791 | -1049.39 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56871 | 2735.Misc.Equipment.FY2022 | Purchase 2 Heath Odorator ($5,125 each = $10,250), 1 Mueller No Blo Valve Changer ($3,950), 1 Crystal 3D Gauge ($1,525) | 19985.19 | 20016.36 | -31.17 | -0.1557% | 0.03168% | 19985.19 | 20016.36 | -31.17 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-02-25 | 02
050.56872 | 2737.Misc.Equipment.FY2022 | Purchase 2 Vivax/Metrotech VM-810 locators ($3,375 each) | 8657.9 | 8592.09 | 65.81 | 0.7659% | 0.01372% | 8657.9 | 8592.09 | 65.81 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-30 | 12
050.56873 | 2737.TD Williamson.FY2022 | Purchase TD Williamson 2" Shortstop plugging machines and 2" valve assemblies ($10,504.04) | 13998.12 | 13370.54 | 627.58 | 4.694% | 0.02219% | 13998.12 | 13370.54 | 627.58 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-01-28 | 01
050.56874 | 2738.Misc.Equipment.FY2022 | Purchase 1 Vermeer EV150 VAC Unit ($37,100) and 1 Sensit Calibration Station ($5,650) | 60724 | 54416.49 | 6307.51 | 11.59% | 0.09625% | 60724 | 54416.49 | 6307.51 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-31 | 12
050.56875 | 2739.Misc.Equipment.FY2022 | Purchase 1 Kit Tracer Mainline 600 FT Rodder Jameson ($2,350), 1 Heath Odorant Nat Gas ($5,125), 1 Cargo Container ($5,300), 1 Footage Piercing U400 tool ($5,750), and 1 CGI Calibration Machine ($5,300) | 27291.31 | 30326.85 | -3035.54 | -10.01% | 0.04326% | 27291.31 | 30326.85 | -3035.54 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-06-30 | 06
050.56888 | RES.2737.Brock Drive | 600 Ft of 2 In HDPE to serve one new customer on Brock Drive in Stanford KY | -93.98 | 3720.28 | -3814.26 | -102.5% | 0.0009379% | 591.71 | 3720.28 | -3128.57 | 2021-10-01 | 2022-09-30 | 2021-07-12 | 07 | 2021-09-30 | 09
050.56908 | Com.2735.ParkMammoth Ext. | 800 ft. of 2 imch HDPE will serve Clud House and Maintenance Bldg. Developer toopenand close ditch. | -13.3 | 3296.94 | -3310.24 | -100.4% | -0.000636% | -401.27 | 3296.94 | -3698.21 | 2021-10-01 | 2022-09-30 | 2021-07-19 | 07 | 2021-09-30 | 09
050.56937 | RES.2738.Happy Valley | Main extension to feed Happy Valley subdivision in Campbellsville KY | -34.05 | 9043.05 | -9077.1 | -100.4% | 0.01119% | 7062 | 9043.05 | -1981.05 | 2021-10-01 | 2022-09-30 | 2021-08-02 | 08 | 2021-08-27 | 08
050.56948 | COM.2736.Marie Dr. Ext | 100 ft of 2 inch HDPE will serve a new assised living facility located on Marie Dr.Developer wi open and close ditch | 1219.36 | 1952.54 | -733.18 | -37.55% | 0.003563% | 2248.03 | 1952.54 | 295.49 | 2021-10-01 | 2022-09-30 | 2021-11-01 | 11 | 2021-12-31 | 12
050.56962 | PRP.2635.S Seminary Street | See Project Long Description / Notes | -997.22 | 505497.28 | -506494.5 | -100.2% | 0.2397% | 151254.16 | 505497.28 | -354243.12 | 2021-10-01 | 2022-09-30 | 2021-08-03 | 08 | 2021-09-30 | 09
050.56967 | 050.2637 Keri Court Retire | Retire 2 sections of 2 inch poly totaling 856 feet at this abandoned mobile home park. | 899.73 | 614.23 | 285.5 | 46.48% | 0.004125% | 2602.18 | 614.23 | 1987.95 | 2021-10-01 | 2022-09-30 | 2021-08-01 | 08 | 2021-08-31 | 08
050.56970 | RES.2738.Kountry Korner | 500 Ft of 2 In HDPE to serve one new customer in Summersville KY | -743.62 | 2574.89 | -3318.51 | -128.9% | 0.000418% | 263.74 | 2574.89 | -2311.15 | 2021-10-01 | 2022-09-30 | 2021-08-02 | 08 | 2021-09-30 | 09
050.56991 | RES.2734.Drakes.Ridge III | ft. of 4" and ft. of 2" wil sere 29 new building lots in Phase III of Drakes Ridge Sub located off Scottville Rd. Developer will open and close ditch and install casings for main and services. | -1232.76 | 23789.94 | -25022.7 | -105.2% | 0.01065% | 6716.01 | 23789.94 | -17073.93 | 2021-10-01 | 2022-09-30 | 2021-07-27 | 07 | 2021-09-30 | 09
050.57003 | 2612.KY Telemetry.FY21 | Purchase and install 5 telemetry devices for KY (Danville, Mayfield, Elkton, Harrdosburg, Shelbyville) | 22767.69 | 25458 | -2690.31 | -10.57% | 0.03609% | 22767.69 | 25458 | -2690.31 | 2021-10-01 | 2022-09-30 | 2021-08-01 | 08 | 2021-11-30 | 11
050.57016 | RES.2636.HWY142FULKERSON | Install 480' of 2"HDPE for new customer | -800 | 2850.25 | -3650.25 | -128.1% | -0.001268% | -800 | 2850.25 | -3650.25 | 2021-10-01 | 2022-09-30 | 2021-08-16 | 08 | 2021-08-19 | 08
050.57025 | RES.2637.Eagle Landing 2 Ext | Phase 2 of subdivision. Calls for 1,900 feet of 2 inch poly for 72 condo units | -569.93 | 41517.69 | -42087.62 | -101.4% | 0.06798% | 42889.85 | 41517.69 | 1372.16 | 2021-10-01 | 2022-09-30 | 2021-08-16 | 08 | 2021-09-30 | 09
050.57032 | PRP.2737.Totten Ave | See Project Long Description/Notes | 989229.13 | 725787.04 | 263442.09 | 36.3% | 1.568% | 989229.13 | 725787.04 | 263442.09 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57034 | PRP.2737.Buford St Lancaster | See Project Long Description/Notes | 505081.72 | 612690.28 | -107608.56 | -17.56% | 0.8006% | 505081.72 | 612690.28 | -107608.56 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-05-01 | 05
050.57062 | 2636.OhioCountyHospitalUpgrad | Install 640' of 2" HDPE for Hospital growth, Retire 460' of 2" Stl. | -3783.33 | 15848.65 | -19631.98 | -123.9% | 0.0263% | 16594.15 | 15848.65 | 745.5 | 2021-10-01 | 2022-09-30 | 2021-08-16 | 08 | 2021-08-24 | 08
050.57068 | PRP.2634.Slaughters | See Project Long Description/Notes | 179266 | 389121.7 | -209855.7 | -53.93% | 0.2841% | 179266 | 389121.7 | -209855.7 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-01-07 | 01
050.57080 | PRP.2737.Pleasantwood Dr | See project long description/notes | 536768.49 | 568867.03 | -32098.54 | -5.643% | 0.8508% | 536768.49 | 568867.03 | -32098.54 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-06-01 | 06
050.57098 | PRP.2637.Schneidman Rd | See Project Long Description/Notes | 505026.95 | 622269.87 | -117242.92 | -18.84% | 0.8005% | 505026.95 | 622269.87 | -117242.92 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-07-15 | 07
050.57117 | PRP.2738.S Harrison | See Project Long Description/Notes | 1092328.56 | 1023598.87 | 68729.69 | 6.715% | 1.731% | 1092328.56 | 1023598.87 | 68729.69 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57127 | PRP.2636.McClarty Ave | See Project Long Description /Notes | 56655.54 | 108530.88 | -51875.34 | -47.8% | 0.0898% | 56655.54 | 108530.88 | -51875.34 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-15 | 12
050.57148 | 2634.SEMINARYST..L.P. | Replace 25' of 11/4' Stl.,2900' of 2" Stl.,604' of 2" Plastic,4696' of 3" Stl.,10982' of 4" Stl.,210' of 4" Plastic, 752' of 6"Stl. Install 12690' of 2" HDPE., 3450' of 4" HDPE. Ret. RS1566, Rs.1558 | 1585299.47 | 1868617.22 | -283317.75 | -15.16% | 2.513% | 1585299.47 | 1868617.22 | -283317.75 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57149 | Adly.2635.Hillview Dr | See project long description/notes | 660924.82 | 644558.68 | 16366.14 | 2.539% | 1.048% | 660924.82 | 644558.68 | 16366.14 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-03-15 | 03
050.57160 | PRP.2634.W Noel & Browning St | Replace 162' of 4Inch Bare Steel with new 4Inch HDPE crossing. | -7943.79 | 90473.66 | -98417.45 | -108.8% | 0.1341% | 84626.33 | 90473.66 | -5847.33 | 2021-10-01 | 2022-09-30 | 2021-08-30 | 08 | 2021-09-28 | 09
050.57173 | RES.2734.Lexington II Frk. | 2530 ft. of 2 inch HDPE will serve 39 residentials lots in Lexington Place Phase II in Franklin. Developer will open and close ditch and install casins for main and service lines. | 2027.56 | 17908.58 | -15881.02 | -88.68% | 0.01838% | 11594.76 | 17908.58 | -6313.82 | 2021-10-01 | 2022-09-30 | 2021-08-30 | 08 | 2021-09-30 | 09
050.57191 | NG.2735.Liberty2 inch MW Ret | Retir 179 ft.of 2 inch MW off Liberty at Main St. in Glasgow | -27.14 | 1331.13 | -1358.27 | -102% | 0.00106% | 668.44 | 1331.13 | -662.69 | 2021-10-01 | 2022-09-30 | 2021-09-01 | 09 | 2021-09-30 | 09
050.57193 | PRP.2636.East 4th St | See project long description/notes | 802401.66 | 779925.6 | 22476.06 | 2.882% | 1.272% | 802401.66 | 779925.6 | 22476.06 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-01-21 | 01
050.57201 | 2634.W. Noel LP. Replacement | Replace 91' of 11/4" Stl., 3337' of 2" Stl.,222' of 2" Plastic, 747' of 3" Stl., 5758' of 4" Stl., and 300' of 4" Plastic, Install 5761' of 2"HDPE. and 4692' of 4" HDPE | 1150900.19 | 1191198.69 | -40298.5 | -3.383% | 1.824% | 1150900.19 | 1191198.69 | -40298.5 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-05-31 | 05
050.57242 | 2634.LP.Seminary St. Services | Replacement of 225 services with the Low Pressure replacement | 1075548.05 | 1250728.98 | -175180.93 | -14.01% | 1.705% | 1075548.05 | 1250728.98 | -175180.93 | 2021-10-01 | 2022-09-30 | 2021-11-01 | 11 | 2022-09-30 | 09
050.57246 | 2634.LP. W. Noel St. services | Replacement of 200 Services with the Low pressure replacement | 717379.5 | 1089010.8 | -371631.3 | -34.13% | 1.137% | 717379.5 | 1089010.8 | -371631.3 | 2021-10-01 | 2022-09-30 | 2021-12-01 | 12 | 2022-06-30 | 06
050.57253 | 050.2609.Trans.Tap Aban. | Abandonment of high pressure taps on Transmission lines | 44413.23 | 64477.92 | -20064.69 | -31.12% | 0.0704% | 44413.23 | 64477.92 | -20064.69 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-08-30 | 08
050.57276 | LP.2736.LP Services Hopk. | Replacement of 80 services associated with Low Pressure replacement on 17th St. This is an approved FY22 project | 648013.7 | 491916.58 | 156097.12 | 31.73% | 1.027% | 648013.7 | 491916.58 | 156097.12 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57291 | 050.2609.KY 554 Exposure | Replace Creek crossing on Farmers property in Owensboro KY. on 8" HPD line | 14660.25 | 122642.02 | -107981.77 | -88.05% | 0.02324% | 14660.25 | 122642.02 | -107981.77 | 2021-10-01 | 2022-09-30 | 2021-08-27 | 08 | 2022-09-30 | 09
050.57546 | IMP.2739.Osprey Cove Reinf | Install 4300 Ft of 4 In HDPE to resolve pressure problems in Osprey Cove | 200578.2 | 312816.91 | -112238.71 | -35.88% | 0.3179% | 200578.2 | 312816.91 | -112238.71 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-03-18 | 03
050.57553 | IND.2734.Century.St.Ext | 100 ft. of 2 inch Steel, 637 Reg. station and 200 ft. of 2 inch PE will serve new Industrial Warehouses ion Centur St in the South Industrial Park | 9743.96 | 21975.3 | -12231.34 | -55.66% | 0.01544% | 9743.96 | 21975.3 | -12231.34 | 2021-10-01 | 2022-09-30 | 2021-10-18 | 10 | 2021-11-30 | 11
050.57555 | RES.2734.Peachtree.Ext. | 500 t. of 2 inch HDPE will serve 4 conversion customers on Peachtree Ln. in Bowling Green. | 7274.79 | 23144.68 | -15869.89 | -68.57% | 0.01153% | 7274.79 | 23144.68 | -15869.89 | 2021-10-01 | 2022-09-30 | 2021-10-18 | 10 | 2021-11-30 | 11
050.57564 | RES.2637.Sandstone Main Ext | Install 90 feet of 2 inch poly main for one existing residential customer (Charity Wilkey) | 6232.13 | 3506.37 | 2725.76 | 77.74% | 0.009878% | 6232.13 | 3506.37 | 2725.76 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-11-30 | 11
050.57565 | 050.2637.Husband Retire Reg | Retire Regulator Station (RS 1656) Husband Rd near Estes Ln. We recently completed a 6 inch system Improvement in order to retire sta | 14064.06 | 24305.62 | -10241.56 | -42.14% | 0.02229% | 14064.06 | 24305.62 | -10241.56 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-11-30 | 11
050.57568 | RES.2738.Belmont Ave | 200 Ft of 2 In HDPE to serve 1 new customer in Greensburg | 2254.18 | 2926.75 | -672.57 | -22.98% | 0.003573% | 2254.18 | 2926.75 | -672.57 | 2021-10-01 | 2022-09-30 | 2021-10-18 | 10 | 2021-11-26 | 11
050.57569 | RES.2737.Asuka | 100 Ft of 2 In HDPE to serve Asuka in Danville | 1645.73 | 1464.78 | 180.95 | 12.35% | 0.002609% | 1645.73 | 1464.78 | 180.95 | 2021-10-01 | 2022-09-30 | 2021-10-18 | 10 | 2021-11-26 | 11
050.57580 | 3302.KY Desktops FY22 | Purchase replacement desktop and monitors for Kentucky | 21799.21 | 23166.78 | -1367.57 | -5.903% | 0.03455% | 21799.21 | 23166.78 | -1367.57 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-01-31 | 01
050.57581 | 3302.KY Laptops FY22 | Purchase replacement laptops and monitors for Kentucky | 83683.89 | 77920.85 | 5763.04 | 7.396% | 0.1326% | 83683.89 | 77920.85 | 5763.04 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-02-28 | 02
050.57582 | 3302.KY MDT FY22 | Purchase replacement MDTs for Kentucky | 105334.14 | 152748 | -47413.86 | -31.04% | 0.167% | 105334.14 | 152748 | -47413.86 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-08-31 | 08
050.57599 | 2612.KY.Emerg. Regulators FY22 | Approval needed to purchase 8 Ky. emergency regulators for cost center 2612 | 25248.83 | 31892.04 | -6643.21 | -20.83% | 0.04002% | 25248.83 | 31892.04 | -6643.21 | 2021-10-01 | 2022-09-30 | 2021-10-31 | 10 | 2022-09-30 | 09
050.57601 | 2612.KY.Corrector Repl. FY22 | Approval needed to replace 12 obsolete correctors in KY | 37462.61 | 44648.86 | -7186.25 | -16.1% | 0.05938% | 37462.61 | 44648.86 | -7186.25 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57602 | 2612.KY.ERX Upgrades FY22 | Approval needed to purchase 28 ERX's for Ky to upgrade | 141127.46 | 145906.07 | -4778.61 | -3.275% | 0.2237% | 141127.46 | 145906.07 | -4778.61 | 2021-10-01 | 2022-09-30 | 2021-10-31 | 10 | 2022-09-30 | 09
050.57603 | 2612.KY.RTU.Upgrades FY22 | Approval needed to purchase 8 RTU for KY cost center 2612 | 207454.84 | 191352.24 | 16102.6 | 8.415% | 0.3288% | 207454.84 | 191352.24 | 16102.6 | 2021-10-01 | 2022-09-30 | 2021-10-31 | 10 | 2022-09-30 | 09
050.57612 | 2612.Equip. Trailers FY22 | Approval is needed to purchase 2 equipment trailers to haul SXS | 7409.81 | 9546.75 | -2136.94 | -22.38% | 0.01175% | 7409.81 | 9546.75 | -2136.94 | 2021-10-01 | 2022-09-30 | 2021-10-31 | 10 | 2022-09-30 | 09
050.57613 | 2612.Misc.Equip. FY22 | Approval needed to upgrade Russelville office with lab and trailer | 26715.63 | 31822.5 | -5106.87 | -16.05% | 0.04235% | 26715.63 | 31822.5 | -5106.87 | 2021-10-01 | 2022-09-30 | 2021-10-31 | 10 | 2022-09-30 | 09
050.57626 | 050.2636.Greenville Surv. | Purchase and Install Surveillance for Greenville Office | 21436.26 | 19093.5 | 2342.76 | 12.27% | 0.03398% | 21436.26 | 19093.5 | 2342.76 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57627 | 050.23636.GRVL Offc Lot Fence | Fence in Lot at Greenville Office | 33027.1 | 57159.58 | -24132.48 | -42.22% | 0.05235% | 33027.1 | 57159.58 | -24132.48 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57628 | 050.2363.Oboro Surv | Upgrade Suveillance at the Owensboro Office | 41566.06 | 31575 | 9991.06 | 31.64% | 0.06589% | 41566.06 | 31575 | 9991.06 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57630 | 050.2609. St. Cha Com/Dehy | Order and recieve Dehy and Contactor for St. Charles Storage | 543225.77 | 613788.97 | -70563.2 | -11.5% | 0.8611% | 543225.77 | 613788.97 | -70563.2 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57631 | 050.2609.Kirk W Valve Replac | Replace 2 Valves in KirkWood Storage Lot 1 - Station Valve 1 - Control Valve | 308.93 | 11410.42 | -11101.49 | -97.29% | 0.0004897% | 308.93 | 11410.42 | -11101.49 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57632 | 050.2363.KY 331 | Replacement of High Pressure facilities along KY 331 in Owensboro KY for State Hwy widening project | 164114.58 | 423220.48 | -259105.9 | -61.22% | 0.2601% | 164114.58 | 423220.48 | -259105.9 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-10-30 | 10
050.57635 | RES.2636.DEERVALLEY.MN.EXT | Install 1890' of 4" HDPE and 880' of 2" HDPE | 43822.5 | 53806.74 | -9984.24 | -18.56% | 0.06946% | 43822.5 | 53806.74 | -9984.24 | 2021-10-01 | 2022-09-30 | 2021-10-22 | 10 | 2021-11-09 | 11
050.57637 | RES.2637.Sherwood Rd Ext | Install 80 feet of 2 inch poly main for one existing customer (Aaron Warmath1195 Sherwood) requesting natural gas | 3523.04 | 3202.39 | 320.65 | 10.01% | 0.005584% | 3523.04 | 3202.39 | 320.65 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-12-30 | 12
050.57638 | RNG.2739.Benson Valley | Build RNG Interconnect at Benson Valley Landfill in Frankfort KY | 20641.31 | 914738.72 | -894097.41 | -97.74% | 0.03272% | 20641.31 | 914738.72 | -894097.41 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2023-06-30 | 06
050.57639 | RES.2638.Story Place Ext | Install 200 feet of 2 inch poly main for one new residential duplex currently under construction for Gary Sanderson in Story Place Subdivision | 11492.94 | 5766.19 | 5726.75 | 99.32% | 0.01822% | 11492.94 | 5766.19 | 5726.75 | 2021-10-01 | 2022-09-30 | 2021-11-01 | 11 | 2021-12-30 | 12
050.57644 | COM.2638.Grace Park Ext 3 | Install 725 feet of 2 Inch poly main for one new commercial customer (Youngblood Excavating Company) requesting natural gas for thier new Office as well as new Shop, and new Warehouse. Almost 40000 square feet of heating,. Water heating as well. | 22197.46 | 25531.8 | -3334.34 | -13.06% | 0.03518% | 22197.46 | 25531.8 | -3334.34 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2021-11-30 | 11
050.57652 | INT.2737.Fire Dept Relocation | Relocate 340 Ft of 2 In Main in Danville on US-150 to eliminate conflicts with new fire department building | 49144.8 | 48862.03 | 282.77 | 0.5787% | 0.0779% | 49144.8 | 48862.03 | 282.77 | 2021-10-01 | 2022-09-30 | 2021-11-01 | 11 | 2022-03-31 | 03
050.57672 | RES.2637.Paris Rd Rev Ext | Install 200 feet of 2 inch poly main for one new residential customer. | 3835.74 | 6054.32 | -2218.58 | -36.64% | 0.00608% | 3835.74 | 6054.32 | -2218.58 | 2021-10-01 | 2022-09-30 | 2021-11-01 | 11 | 2022-05-30 | 05
050.57673 | COM.2637 S Friendship Rd Ext | Install 240 feet of 2 inch poly main for one existing commercial customer (Dairyette Restaurant) requesting natural gas for heat, water heat, cooking equipment. | 7117.93 | 6944.35 | 173.58 | 2.5% | 0.01128% | 7117.93 | 6944.35 | 173.58 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-02-28 | 02
050.57678 | PRP.2634.Hwy 41 Hanson | See project long description / notes | 223251.51 | 244319.34 | -21067.83 | -8.623% | 0.3539% | 223251.51 | 244319.34 | -21067.83 | 2021-10-01 | 2022-09-30 | 2021-01-03 | 01 | 2022-04-30 | 04
050.57709 | RES.2636.OLDCALHOUNRD.MN.EXT | Install 200' of 2" Stl., 800' of 4" HDPE., Install 1- 2" Reg. Station | 33252.37 | 67785.01 | -34532.64 | -50.94% | 0.05271% | 33252.37 | 67785.01 | -34532.64 | 2021-10-01 | 2022-09-30 | 2021-11-01 | 11 | 2021-11-30 | 11
050.57710 | RES.2736.Madisonville.Rd.Ext | 260 t. o 2 inch HDPE will serve one new residential customer at 11195 S. Maidonnville Rd. in Croton.AIC = $4,420.00 | -2871.84 | 7274.85 | -10146.69 | -139.5% | -0.004552% | -2871.84 | 7274.85 | -10146.69 | 2021-10-01 | 2022-09-30 | 2021-11-02 | 11 | 2021-12-31 | 12
050.57724 | PRP.2637.Lieberman St | See project Long Description / Notes | 775351.2 | 747648.65 | 27702.55 | 3.705% | 1.229% | 775351.2 | 747648.65 | 27702.55 | 2021-10-01 | 2022-09-30 | 2022-01-03 | 01 | 2022-09-30 | 09
050.57726 | COM.2635FROTNERDR.MN.EXT | Install 75' of 2" HDPE for expansion | 6052.59 | 927.32 | 5125.27 | 552.7% | 0.009594% | 6052.59 | 927.32 | 5125.27 | 2021-10-01 | 2022-09-30 | 2021-11-05 | 11 | 2021-11-30 | 11
050.57739 | RES.2636VINCENTSTATIONDR.MN.E | Install 370' of 2" HDPE for subdivisin growth | 4168.52 | 7231.27 | -3062.75 | -42.35% | 0.006607% | 4168.52 | 7231.27 | -3062.75 | 2021-10-01 | 2022-09-30 | 2021-11-08 | 11 | 2021-11-22 | 11
050.57745 | RES.2634.HWY136MN.EXT | Install 125' of 2" HDPE for new customer | 949.81 | 1382.46 | -432.65 | -31.3% | 0.001506% | 949.81 | 1382.46 | -432.65 | 2021-10-01 | 2022-09-30 | 2021-11-09 | 11 | 2021-11-12 | 11
050.57762 | INT.2739.US 60 Relocation | Install 300 Ft of 2 In Poly and 80 Ft of 4 In Steel to eliminate conflicts on US 60 as part of KY 53 widening | 40133.09 | 43921.62 | -3788.53 | -8.626% | 0.06361% | 40133.09 | 43921.62 | -3788.53 | 2021-10-01 | 2022-09-30 | 2021-11-15 | 11 | 2022-03-31 | 03
050.57798 | COM.2637.Lov Flo Sta Rd Ext | Install 630 feet of 2 inch poly main for one existing business (M S I Marine Solutions) requesting natural gas for heat. They are coverting from propane. They are located at 250 Lovelaceville Florence Station Rd | 4339.74 | 15280.81 | -10941.07 | -71.6% | 0.006879% | 4339.74 | 15280.81 | -10941.07 | 2021-10-01 | 2022-09-30 | 2021-12-01 | 12 | 2022-01-30 | 01
050.57815 | RES.2734.Magnois.Hills.3-C | 1200 ft. of 4 inch and 2850 ft. od 2 inch HDPE wi serve 104 new residential lots in Magnolia Hills Phase 3-C located off Plano Rd. Developer wi open and close ditch and install casings for mains and services. | 26648.44 | 38479.48 | -11831.04 | -30.75% | 0.04224% | 26648.44 | 38479.48 | -11831.04 | 2021-10-01 | 2022-09-30 | 2021-11-04 | 11 | 2022-01-29 | 01
050.57835 | RES.2636.HWY81 | Install 1850' of 2" HDPE for Home and Body Shop | 49977.37 | 52774.29 | -2796.92 | -5.3% | 0.07922% | 49977.37 | 52774.29 | -2796.92 | 2021-10-01 | 2022-09-30 | 2021-11-22 | 11 | 2021-11-30 | 11
050.57836 | RES.2636.MCFARLANDRD.MN.EXT | Install 1775' of 2" HDPE for new homes | 45091.31 | 47764.44 | -2673.13 | -5.596% | 0.07147% | 45091.31 | 47764.44 | -2673.13 | 2021-10-01 | 2022-09-30 | 2021-12-02 | 12 | 2022-01-31 | 01
050.57841 | COM.2636.FAIRFAXDR.AUTODEALER | Install 400' of 2" HDPE for new car dealership | 5814.36 | 4152.16 | 1662.2 | 40.03% | 0.009216% | 5814.36 | 4152.16 | 1662.2 | 2021-10-01 | 2022-09-30 | 2021-12-06 | 12 | 2021-12-31 | 12
050.57845 | 050.2734.Fence Repl. - B.G. | ence Replacement - Bowling Green Ofice | 14744.26 | 14842.8 | -98.54 | -0.6639% | 0.02337% | 14744.26 | 14842.8 | -98.54 | 2021-10-01 | 2022-09-30 | 2021-12-03 | 12 | 2022-09-30 | 09
050.57855 | RES.2739.Maddie Lane | 500 Ft of 2 In HDPE to serve 14 new customers in Shelbyville KY | 16416.9 | 16029.64 | 387.26 | 2.416% | 0.02602% | 16416.9 | 16029.64 | 387.26 | 2021-10-01 | 2022-09-30 | 2021-12-06 | 12 | 2022-01-28 | 01
050.57867 | RES.2637.Camilla Ln Rev Ext 2 | Install 60 feet of 2 inch poly for one new home under construction at 1520 Camilla Ln. Builder is D.W Simmons Construction | 5323.94 | 5204.34 | 119.6 | 2.298% | 0.008439% | 5323.94 | 5204.34 | 119.6 | 2021-10-01 | 2022-09-30 | 2022-01-01 | 01 | 2022-03-30 | 03
050.57879 | RES.2739.Brooks Ln | 150 Ft of 2 In to serve 1 new customer | 4654.56 | 4481.94 | 172.62 | 3.851% | 0.007378% | 4654.56 | 4481.94 | 172.62 | 2021-10-01 | 2022-09-30 | 2021-12-06 | 12 | 2022-01-28 | 01
050.57882 | RES.2739.Ardmore Phase 3 | 3300 Ft of 2 In Main to serve Phase 3 of Ardmore Crossings in Shelbyville KY | 49931.19 | 78402.76 | -28471.57 | -36.31% | 0.07914% | 49931.19 | 78402.76 | -28471.57 | 2021-10-01 | 2022-09-30 | 2021-12-06 | 12 | 2022-04-01 | 04
050.57888 | PRP.2636.Legion - St Ann | See project Long Description/Notes | 336024.45 | 311013.03 | 25011.42 | 8.042% | 0.5326% | 336024.45 | 311013.03 | 25011.42 | 2021-10-01 | 2022-09-30 | 2021-12-16 | 12 | 2022-03-31 | 03
050.57899 | 050.5734.Matalco Meter Frk. | Replacement of Brown Printing Meterset for new Industrial Customer, Matalco. Gas needed by July 2022 Original project cancelled due to Error in project type | 39871.56 | 39124.57 | 746.99 | 1.909% | 0.0632% | 39871.56 | 39124.57 | 746.99 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57907 | 2638.Mayfield Tornado.21 | Track capital work associated with Mayfield, KY tornado damage. | 79423.72 | 1693619.85 | -1614196.13 | -95.31% | 0.1259% | 79423.72 | 1693619.85 | -1614196.13 | 2021-10-01 | 2022-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57908 | 2734.Bowling Green Tornado.21 | Track capital repair work associated with Bowling Green, KY tornado | 29952.82 | 294016.97 | -264064.15 | -89.81% | 0.04748% | 29952.82 | 294016.97 | -264064.15 | 2021-10-01 | 2022-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57909 | 2635.Dawson Prince.Tornado.21 | Track capital repairs associated with Dawson Springs/Princeton, KY tornado damage | 22692.05 | 610486.23 | -587794.18 | -96.28% | 0.03597% | 22692.05 | 610486.23 | -587794.18 | 2021-10-01 | 2022-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57910 | 2636.OWB-Bremen Tornado.21 | Track capital repairs associated with OWB-Bremen, KY tornado. | 1339.49 | 26891.24 | -25551.75 | -95.02% | 0.002123% | 1339.49 | 26891.24 | -25551.75 | 2021-10-01 | 2022-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57932 | 050.2638.TORNADO-5th-Houseman | This project is to supply gas to app. 140 customers at the Mayfield Housing Authority property at N 5th & Houseman Streets. We propose to install 220 feet of 2 inch poly main, 290 feet of 4 inch poly main. | 1255.56 | 46512.26 | -45256.7 | -97.3% | 0.00199% | 1255.56 | 46512.26 | -45256.7 | 2021-10-01 | 2022-09-30 | 2021-12-15 | 12 | 2021-12-31 | 12
050.57933 | 050.2638.TORNADO-9th-Willow | Install 260 feet of 2 inch poly main in the 400 block of S. 9th Street in order to restore gas service to the local United Way/Food Pantry and Stone's Pharmacy | 416.2 | 9986.38 | -9570.18 | -95.83% | 0.0006597% | 416.2 | 9986.38 | -9570.18 | 2021-10-01 | 2022-09-30 | 2021-12-17 | 12 | 2022-01-31 | 01
050.57959 | COM.2636.FAIRVIEWDR.MN.EXT | Install 2850' of 4" HDPE for new school | 118654.84 | 185852.49 | -67197.65 | -36.16% | 0.1881% | 118654.84 | 185852.49 | -67197.65 | 2021-10-01 | 2022-09-30 | 2021-12-16 | 12 | 2022-01-12 | 01
050.57972 | RES.2635DEPOTST.MN.EXT | Install 1300' of 4" HDPE for feed into Dawson springs | 8670.22 | 361978.45 | -353308.23 | -97.6% | 0.01374% | 8670.22 | 361978.45 | -353308.23 | 2021-10-01 | 2022-09-30 | 2021-12-27 | 12 | 2022-02-28 | 02
050.57993 | 050.2638-TORNADO-12th-Oak St | Install app. 1,500 feet of 2 inch poly main Along Oak St from S 10th to S 12th. This with the installation of a valve will allow us to restore gas to at least 80 homes when they are ready. | 5986.46 | 236947.85 | -230961.39 | -97.47% | 0.009489% | 5986.46 | 236947.85 | -230961.39 | 2021-10-01 | 2022-09-30 | 2022-01-03 | 01 | 2022-02-28 | 02
050.57994 | LP.2736.7th and Clay Replc. | 450 ft. of 2 inch HDPE Replacement 7th. St. at Clay St. Project replaces LP Rgulator Station and main. | 78228.96 | 76157.84 | 2071.12 | 2.72% | 0.124% | 78228.96 | 76157.84 | 2071.12 | 2021-10-01 | 2022-09-30 | 2022-01-04 | 01 | 2022-03-31 | 03
050.58002 | RES.2637.Contest Rd Rev Ext | 1,035 feet of 2 inch poly main to serve 5 customers on Contest Rd just off Krebs Station Rd | 14312.17 | 31300.41 | -16988.24 | -54.27% | 0.02269% | 14312.17 | 31300.41 | -16988.24 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-06-30 | 06
050.58030 | RES.2734 Poplar Grove Phase 2 | 1540 ft. of 4 inch HDPE will drtve 25 New Residentia lots in Phase 2 of Poplar Grove Sub. locayed off Scottsville Rd. Developer will open and close ditch and install casings for main and services. | 13292.34 | 18162.85 | -4870.51 | -26.82% | 0.02107% | 13292.34 | 18162.85 | -4870.51 | 2021-10-01 | 2022-09-30 | 2022-01-11 | 01 | 2022-03-31 | 03
050.58041 | RES.2739.Discovery Phase 1 | 4100 Ft of 2 In Main to serve Phase 1 of Discovery Point | 55519.32 | 55807.96 | -288.64 | -0.5172% | 0.088% | 55519.32 | 55807.96 | -288.64 | 2021-10-01 | 2022-09-30 | 2022-01-03 | 01 | 2022-05-30 | 05
050.58042 | 050.2637.TORNADO-4th-North St | Install app. 3,400 feet of 4 inch poly and 1,120 feet of 2 inch poly main to restore service to app. 75 properties. | 10711.23 | 453904.13 | -443192.9 | -97.64% | 0.01698% | 10711.23 | 453904.13 | -443192.9 | 2021-10-01 | 2022-09-30 | 2022-01-24 | 01 | 2022-03-30 | 03
050.58043 | RES.2738.Forgotten Fields | 400 Ft of 2 In Main to serve 5 houses in Campbellsville KY | 4159.84 | 4349.93 | -190.09 | -4.37% | 0.006594% | 4159.84 | 4349.93 | -190.09 | 2021-10-01 | 2022-09-30 | 2022-01-10 | 01 | 2022-02-25 | 02
050.58045 | RES.2734.Autumn Lake Final | 2755 ft. of 2 inch HDPE will seve 43 new resdemtal lots in the final phase of Autumn Lake Sub. in Franklin. Developer will open and close ditch and install casings for Main and service line crossings. | 12364.97 | 16092.56 | -3727.59 | -23.16% | 0.0196% | 12364.97 | 16092.56 | -3727.59 | 2021-10-01 | 2022-09-30 | 2022-01-13 | 01 | 2022-03-31 | 03
050.58047 | RES.2635.OAKHEIGHTSREPLACEMEN | Replace 1700' of 2" STL. damaged in tornado, install 1700' of 2" HDPE | 6257.17 | 79336.27 | -73079.1 | -92.11% | 0.009918% | 6257.17 | 79336.27 | -73079.1 | 2021-10-01 | 2022-09-30 | 2022-01-24 | 01 | 2022-02-04 | 02
050.58057 | 050.2638.TORNADO-N9th-James | Install 625 feet of 2 inch poly main to restore gas service to 400 block of N. 9th and N. 8th plus the 200 block of W. James Street. We will retire 626 feet of pipe including 136 feet of 1 1/4 inch aldyl-A plastic and 120 feet of "Unknown" pipe. | 3850.91 | 53913.74 | -50062.83 | -92.86% | 0.006104% | 3850.91 | 53913.74 | -50062.83 | 2021-10-01 | 2022-09-30 | 2022-01-17 | 01 | 2022-02-28 | 02
050.58068 | 050.2637.Mayfield Rd Relocate | McCracken County is building the new Lone Oak/ Hendron Fire Department facility at 4300 Mayfield Rd in Paducah. They are cutting down a bank for the installation of new 30 ft wide concrete driveway. Our existing 4 inch steel is in harms way | 8257.04 | 9599.52 | -1342.48 | -13.98% | 0.01309% | 8257.04 | 9599.52 | -1342.48 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-09-30 | 09
050.58101 | 050.2638-TORNADO-Cardinal Rd | This phase (9) includes replacing aldyl-A pipe along Cardinal Rd, Pritchard Rd, and the area where I-69 intersects with U.S Highway 45. We will also "reenergize"the 4 inch on Hwy 45 from Macedonia Rd north to Walnut St. Install 5,000 feet new main. | 7472.44 | 291884.81 | -284412.37 | -97.44% | 0.01184% | 7472.44 | 291884.81 | -284412.37 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-03-30 | 03
050.58126 | 2638.Mayfield Tornado Meters | Meter purchases and retiremenets associated with Mayfield, KY tornado damage. | 463.16 | 162383.08 | -161919.92 | -99.71% | 0.0007341% | 463.16 | 162383.08 | -161919.92 | 2021-10-01 | 2022-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.58145 | RES.2635.FREDRICKRD | Install 1800' of 2" HDPE, to replace tornado damaged stl. | 11080.1 | 149307.34 | -138227.24 | -92.58% | 0.01756% | 11080.1 | 149307.34 | -138227.24 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-03-18 | 03
050.58153 | 050.2638.TORNADO-7th-Broadway | This project is for improvements to our system in Mayfield in order to reinstate gas on the system. We propose to install app. 800 feet of 2 inch poly main, retire 70 feet of 2 inch steel which would have been isolated. | 3918.4 | 56051.07 | -52132.67 | -93.01% | 0.006211% | 3918.4 | 56051.07 | -52132.67 | 2021-10-01 | 2022-09-30 | 2022-01-31 | 01 | 2022-02-28 | 02
050.58156 | RES.LUMBERST.MN.EXT | Replace 485' of 2" Stl., damaged in tornado with 485' of 2" HDPE | 8026.87 | 100809.8 | -92782.93 | -92.04% | 0.01272% | 8026.87 | 100809.8 | -92782.93 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-02-08 | 02
050.58166 | PRP.2636.Bluff Ave | See project long description /notes | 658515.06 | 661975.19 | -3460.13 | -0.5227% | 1.044% | 658515.06 | 661975.19 | -3460.13 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-07-22 | 07
050.58167 | 050.2638.TORNADO-7-Wtr-Walnut | This phase of our Mayfield tornado restoration consists of installing app. 1,400 feet of 2 inch poly main from S 8th & Water down Water to S 7th, then south along S 7th to Walnut St. From there west toS. 8th and east to alley. Retire 760 feet of pipe | 5166.86 | 90086.02 | -84919.16 | -94.26% | 0.00819% | 5166.86 | 90086.02 | -84919.16 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-04-30 | 04
050.58196 | RES.2634.UNIVERSITYCIRCLEMN.E | Install 250' of 2" HDPE | 29.96 | 3810.87 | -3780.91 | -99.21% | 4.749e-05% | 29.96 | 3810.87 | -3780.91 | 2021-10-01 | 2022-09-30 | 2022-02-14 | 02 | 2022-02-18 | 02
050.58204 | RES.2636.OLDHARTFORDRD.MN.EXT | Install 1300' of 2" HDPE for new customers | 47228.08 | 46461.25 | 766.83 | 1.65% | 0.07486% | 47228.08 | 46461.25 | 766.83 | 2021-10-01 | 2022-09-30 | 2022-02-21 | 02 | 2022-02-28 | 02
050.58205 | RES.2637.Blandville Rd Ext | Install 260 feet of 4 inch poly main for five new townhomes being built by D.W Simmons Construction. All will use gas for heat, on demand WH's, and gas logs | 10006.97 | 9302.33 | 704.64 | 7.575% | 0.01586% | 10006.97 | 9302.33 | 704.64 | 2021-10-01 | 2022-09-30 | 2022-02-14 | 02 | 2022-04-30 | 04
050.58214 | RES.2734.Stagner Farms Final | 6500 ft. of 2 inch HDPE will serve 85 Residential lots in the Final Phase of Stagner Farms Subdivision located off Elrod Rd.. Developer will open and close ditch ans install casind for main and services lines. | 24463.78 | 41098.43 | -16634.65 | -40.48% | 0.03878% | 24463.78 | 41098.43 | -16634.65 | 2021-10-01 | 2022-09-30 | 2022-02-10 | 02 | 2022-05-16 | 05
050.58218 | RES.2635.EKEIGANST.TORNADO DA | Replace 1,000' of 2" Stl, tornado damaged, with 1,000' of 2" HDPE | 7413.52 | 93747.23 | -86333.71 | -92.09% | 0.01175% | 7413.52 | 93747.23 | -86333.71 | 2021-10-01 | 2022-09-30 | 2022-03-01 | 03 | 2022-03-07 | 03
050.58222 | LP.2736.Phelps Ave. Replc. | Project replaces remaining LP in Hopkinsville Phelps Ave. There will be two Reg Station and 109 services replaced with this project. See long description. | 976635.69 | 629793.74 | 346841.95 | 55.07% | 1.548% | 976635.69 | 629793.74 | 346841.95 | 2021-10-01 | 2022-09-30 | 2022-02-01 | 02 | 2022-08-31 | 08
050.58224 | RES.2738.Aarons Way | 200 Ft of 2 In HDPE Main to serve 1 customer on Aarons Way | 3071.87 | 2676.2 | 395.67 | 14.78% | 0.004869% | 3071.87 | 2676.2 | 395.67 | 2021-10-01 | 2022-09-30 | 2022-02-14 | 02 | 2022-03-31 | 03
050.58227 | 050.2638.TORNADO-N 5th-Lee | Installing app. 800 feet of 2 inch poly main to serve app 12 customers. Retiring alike amount | 4337.04 | 70372.17 | -66035.13 | -93.84% | 0.006875% | 4337.04 | 70372.17 | -66035.13 | 2021-10-01 | 2022-09-30 | 2022-02-14 | 02 | 2022-04-30 | 04
050.58288 | RES.2635.PINEST.TORNADOREPLAC | Replace 1400' of damaged 2" Stl., with 1400' of 2" HDPE | 4905.5 | 63780.08 | -58874.58 | -92.31% | 0.007776% | 4905.5 | 63780.08 | -58874.58 | 2021-10-01 | 2022-09-30 | 2022-03-14 | 03 | 2022-03-21 | 03
050.58302 | INT.2738.Greensburg 2nd Feed | Replace outdated RS1473 and RS1777. Tie both 35lb systems together to have 2 feeds into main Greensburg system. | 226412.38 | 242445.47 | -16033.09 | -6.613% | 0.3589% | 226412.38 | 242445.47 | -16033.09 | 2021-10-01 | 2022-09-30 | 2022-03-01 | 03 | 2022-08-31 | 08
050.58309 | 2636.RES.FREDERICAST.MN.EXT | Install 350 of 4" HDPE for new customer | 4525.84 | 10536.28 | -6010.44 | -57.05% | 0.007174% | 4525.84 | 10536.28 | -6010.44 | 2021-10-01 | 2022-09-30 | 2022-03-08 | 03 | 2022-03-30 | 03
050.58319 | NG.2735.Park Mammoth Reloc. | Replace 500 ft. of 2" HDPE in conjunction with development plans at Parck City Mammoth Golf Course. Reimbursementby developer will be at 100% | -3542.28 | 7596.48 | -11138.76 | -146.6% | -0.005615% | -3542.28 | 7596.48 | -11138.76 | 2021-10-01 | 2022-09-30 | 2022-02-23 | 02 | 2022-04-29 | 04
050.58326 | PRP.2734.Avery Ct | See Project Long Description Notes | 330199.06 | 240985.87 | 89213.19 | 37.02% | 0.5234% | 330199.06 | 240985.87 | 89213.19 | 2021-10-01 | 2022-09-30 | 2022-04-01 | 04 | 2022-08-15 | 08
050.58328 | INT.2737.Harrodsburg Purchase | Rebuild outdated Harrodsburg Purchase RS1332 | 708221.17 | 796860.65 | -88639.48 | -11.12% | 1.123% | 708221.17 | 796860.65 | -88639.48 | 2021-10-01 | 2022-09-30 | 2022-03-01 | 03 | 2022-10-28 | 10
050.58336 | 050.2638.TORNADO-S9th-WBrdway | This project is to restore natural gas service to the 200 block of W Broadway incl. Carr's Barn & Carr's Steakhouse | 449.49 | 32545.95 | -32096.46 | -98.62% | 0.0007125% | 449.49 | 32545.95 | -32096.46 | 2021-10-01 | 2022-09-30 | 2022-03-01 | 03 | 2022-04-30 | 04
050.58349 | 2635DAWSINSPRINGTORNADORPL | Replace 5900' of tornado damaged Stl. with 5900' of 2" HDPE | 11895.52 | 394549.52 | -382654 | -96.99% | 0.01886% | 11895.52 | 394549.52 | -382654 | 2021-10-01 | 2022-09-30 | 2022-03-21 | 03 | 2022-06-30 | 06
050.58360 | NG Hopk. St. Retire.Russ | Retire 900 ft. of 3 inch bare steel main on Hopkinsville St. between Meadow Ln. and Old Hopksville st. in Russellville | 3804.48 | 5297.57 | -1493.09 | -28.18% | 0.00603% | 3804.48 | 5297.57 | -1493.09 | 2021-10-01 | 2022-09-30 | 2022-02-28 | 02 | 2022-05-31 | 05
050.58361 | PRP.2638. S 15th St | Replace Exposed 3 Inch Bare main ditch crossing with 600' of 4 Inch HDPE. | 34057.45 | 56050.46 | -21993.01 | -39.24% | 0.05398% | 34057.45 | 56050.46 | -21993.01 | 2021-10-01 | 2022-09-30 | 2022-03-01 | 03 | 2022-03-26 | 03
050.58372 | RES.2734.CarterCrossingIIIA | 459 ft. of 6 inch 685 ft. of 4 inch and 1830 ft. of 2 inch HDPE will serve 57 new residential lots in Carters Crossing Phase IIIA. Developer will open and close ditch and install casings for main and service lines | 34954.6 | 41158.2 | -6203.6 | -15.07% | 0.05541% | 34954.6 | 41158.2 | -6203.6 | 2021-10-01 | 2022-09-30 | 2022-03-04 | 03 | 2022-05-31 | 05
050.58395 | RES.2637.E Commerce Ave Ext | Install 290 feet of 2 inch poly main to serve one residential customer at 180 E. Commere Ave. | 12008.24 | 8000.91 | 4007.33 | 50.09% | 0.01903% | 12008.24 | 8000.91 | 4007.33 | 2021-10-01 | 2022-09-30 | 2022-03-09 | 03 | 2022-09-30 | 09
050.58399 | PRP.2635.S Jefferson | **** Revision Comments**** Original Estimate: $1,006,024.51 There were Multiple exposed creek crossings on this project that added an additional 3,492' of main replaced. | 918077.66 | 1017534.57 | -99456.91 | -9.774% | 1.455% | 918077.66 | 1017534.57 | -99456.91 | 2021-10-01 | 2022-09-30 | 2022-04-04 | 04 | 2022-11-15 | 11
050.58418 | COM.2738.Gaines Drive | 1100 Ft of 2 In HDPE to serve 6 new customers on Gaines Dr | 488.39 | 6882.11 | -6393.72 | -92.9% | 0.0007741% | 488.39 | 6882.11 | -6393.72 | 2021-10-01 | 2022-09-30 | 2022-03-21 | 03 | 2022-06-30 | 06
050.58437 | 2634.LP.W.Center St. | Replace 1188' of 2" Stl, 567' of 2" Plastic, 1565' of 3" Stl, 7521' of 4" Stl, 349' of 4" Plastic, 1585' of 6" Stl and 74' of 6" Plastic with 3,268' of 2" HDPE and 6,657' of 4" HDPE Retire RS1567, RS1568 | 1211531.32 | 1110608.36 | 100922.96 | 9.087% | 1.92% | 1211531.32 | 1110608.36 | 100922.96 | 2021-10-01 | 2022-09-30 | 2022-04-01 | 04 | 2022-09-15 | 09
050.58444 | PRP.2737.Lancaster S_ | See project long description/notes | 604232.84 | 647102.65 | -42869.81 | -6.625% | 0.9578% | 604232.84 | 647102.65 | -42869.81 | 2021-10-01 | 2022-09-30 | 2022-04-10 | 04 | 2022-09-30 | 09
050.58473 | PRP.2737.Walnut St | See Project Long Description/Notes | 609491.13 | 675855.82 | -66364.69 | -9.819% | 0.9661% | 609491.13 | 675855.82 | -66364.69 | 2021-10-01 | 2022-09-30 | 2022-05-01 | 05 | 2022-09-30 | 09
050.58475 | COM.2735.Quality Extension | 230 ft. of 2 inch HDPE will serve new commercial customer on Quality St. in Munfordville . Heat utilized for office at Hart County Solid Waste. Atmos Crew will proved ditch and Bacffill. | 613.24 | 5634.4 | -5021.16 | -89.12% | 0.000972% | 613.24 | 5634.4 | -5021.16 | 2021-10-01 | 2022-09-30 | 2022-01-20 | 01 | 2022-05-20 | 05
050.58479 | RES.2737.Logan Creek Dr | 450 Ft of 2 In HDPE to serve one new customer on Logan Creek Dr | 441.96 | 3600.34 | -3158.38 | -87.72% | 0.0007005% | 441.96 | 3600.34 | -3158.38 | 2021-10-01 | 2022-09-30 | 2022-03-28 | 03 | 2022-05-27 | 05
050.58516 | 050.2634.Center St. Services | Retire 225 service, replace with new services on Center St. project | 542630.36 | 794598.82 | -251968.46 | -31.71% | 0.8601% | 542630.36 | 794598.82 | -251968.46 | 2021-10-01 | 2022-09-30 | 2022-05-01 | 05 | 2022-09-30 | 09
050.58521 | PRP.2734.Greenwood Alley | Replace 320 ft of 2 Inch Bare steel main with 320 ft of 2 Inch HDPE. 8 services involved. | 43481.65 | 38291.15 | 5190.5 | 13.56% | 0.06892% | 43481.65 | 38291.15 | 5190.5 | 2021-10-01 | 2022-09-30 | 2022-04-01 | 04 | 2022-04-30 | 04
050.58527 | COM.2637.Old 60 Ext - Kotter | Install 200 feet of 4 inch Poly pipe for two customers requesting natural gas service. Kotter Rady Mix requesting service for existing concrete plant and new office across the street | 31438.41 | 28046.85 | 3391.56 | 12.09% | 0.04983% | 31438.41 | 28046.85 | 3391.56 | 2021-10-01 | 2022-09-30 | 2022-05-01 | 05 | 2022-06-30 | 06
050.58528 | RES.2637.Starr Hill Rd Ext | Install 540 feet of 2 inch poly main for two existing residential customers. Stan Hack will have a double meter loop at this home, son, Nathan Hack to run housepiping to equip shed. | 8725.53 | 12720.07 | -3994.54 | -31.4% | 0.01383% | 8725.53 | 12720.07 | -3994.54 | 2021-10-01 | 2022-09-30 | 2022-05-01 | 05 | 2022-06-30 | 06
050.58529 | 050.2638.TORNADO - 12th-Depot | Install 200 ft of 2 inch poly main to replace existing main damaged during December 10th tornado | 138.7 | 15946.17 | -15807.47 | -99.13% | 0.0002198% | 138.7 | 15946.17 | -15807.47 | 2021-10-01 | 2022-09-30 | 2022-04-01 | 04 | 2022-05-30 | 05
050.58530 | RES.2636.BOSTONSPURMN.EXT | Install 530' of 2" HDPE for new customer | -327.53 | 5299.17 | -5626.7 | -106.2% | -0.0005192% | -327.53 | 5299.17 | -5626.7 | 2021-10-01 | 2022-09-30 | 2022-04-01 | 04 | 2022-05-15 | 05
050.58537 | RES.2636.SADDLEPOINT.MN.EXT | Install 780' of 4" HDPE., Install 800' of 2" HDPE for subdivision growth | 35767.51 | 35573.67 | 193.84 | 0.5449% | 0.05669% | 35767.51 | 35573.67 | 193.84 | 2021-10-01 | 2022-09-30 | 2022-04-06 | 04 | 2022-05-30 | 05
050.58583 | COM.2736.JollyRanch.Cadiz | 850 ft. of 2 inch HDPE will serve 8 new commercial lots in Jolly Ranch Development located off Glenwood Mill Rd. in Cadiz KY. Main will tie in to existing 2" HDPE | 6360.1 | 7193.01 | -832.91 | -11.58% | 0.01008% | 6360.1 | 7193.01 | -832.91 | 2021-10-01 | 2022-09-30 | 2022-04-07 | 04 | 2022-05-31 | 05
050.58598 | 050.2637.Alabama St Retire | Retire 627 feet of 2 inch mill wrapped steel main due to leakage. Main was installed in 1957 | 125.23 | 952.32 | -827.09 | -86.85% | 0.0001985% | 125.23 | 952.32 | -827.09 | 2021-10-01 | 2022-09-30 | 2022-04-11 | 04 | 2022-12-30 | 12
050.58625 | 050.2637.Charter Oak HPD MAIN | Installing new HDPE pipe in order to switch app. 20 farm tap regulator customers to the distribution main | 307532.22 | 313174.78 | -5642.56 | -1.802% | 0.4875% | 307532.22 | 313174.78 | -5642.56 | 2021-10-01 | 2022-09-30 | 2022-06-01 | 06 | 2022-08-31 | 08
050.58637 | PRP.2637.Myers St_ | See project Long Description/Notes | 372731.04 | 309275.88 | 63455.16 | 20.52% | 0.5908% | 372731.04 | 309275.88 | 63455.16 | 2021-10-01 | 2022-09-30 | 2022-05-15 | 05 | 2022-08-30 | 08
050.58640 | RES.2636.TAYLORMINERD.MN.EXT | Install 600' of 2" HDPE for new customers | 4832.78 | 3964.18 | 868.6 | 21.91% | 0.00766% | 4832.78 | 3964.18 | 868.6 | 2021-10-01 | 2022-09-30 | 2022-05-09 | 05 | 2022-09-30 | 09
050.58657 | IND.Owls Head Meterset | Project to move existing meterset at Oles Head due to expansion Meterset 5200.00, Spool Kit 1800.00, @#M Rotary meter, 6800.00, Mooney Regulators, 31,000.00. Compamy Labor for installition of Meter, Reg, | 129109.01 | 68428.76 | 60680.25 | 88.68% | 0.2046% | 129109.01 | 68428.76 | 60680.25 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.58660 | COM.2636.CALUMETTRACEMN.EXT | Install 260' of 4" HDPE for new store | 6921.31 | 5271.96 | 1649.35 | 31.29% | 0.01097% | 6921.31 | 5271.96 | 1649.35 | 2021-10-01 | 2022-09-30 | 2022-05-02 | 05 | 2022-05-16 | 05
050.58665 | Charter Oak HPD-SVCS | This project is set up to capture the costs associated with switching of app. two dozen services from "farm tap" to new "distribution" main and the retirement of said farm tap regulators. | 127617.11 | 151312.79 | -23695.68 | -15.66% | 0.2023% | 127617.11 | 151312.79 | -23695.68 | 2021-10-01 | 2022-09-30 | 2022-05-02 | 05 | 2022-08-31 | 08
050.58666 | RES.2734.DovePointI | 3650 ft. of 4 inch and 565 ft. of 2 inch HDPE will serve107 new single family lots in Dove Point Sub. located off Scottsville Rd. In Alvaton. Main will tie in to existng 6 inch HDPE on Scottsville Rd. Developer will open and close ditch and install | 67482 | 68033.42 | -551.42 | -0.8105% | 0.107% | 67482 | 68033.42 | -551.42 | 2021-10-01 | 2022-09-30 | 2022-03-28 | 03 | 2022-05-31 | 05
050.58668 | PRP.2634.Robards Phase - 1 | See project long Description / notes | 331234.15 | 355760.13 | -24525.98 | -6.894% | 0.525% | 331234.15 | 355760.13 | -24525.98 | 2021-10-01 | 2022-09-30 | 2022-05-05 | 05 | 2022-08-30 | 08
050.58693 | RES.2636.1000HWY136.MN.EXT | Install 800' of 2" HDPE for new customer | 2057.88 | 20339.28 | -18281.4 | -89.88% | 0.003262% | 2057.88 | 20339.28 | -18281.4 | 2021-10-01 | 2022-09-30 | 2022-06-30 | 06 | 2022-09-30 | 09
050.58695 | RES.2634.MILLSTHANSON.MN.EXT. | Install 200' of 2" HDPE for new customer | 1275.94 | 2206.4 | -930.46 | -42.17% | 0.002022% | 1275.94 | 2206.4 | -930.46 | 2021-10-01 | 2022-09-30 | 2022-05-02 | 05 | 2022-05-18 | 05
050.58702 | RES.2637.Olivet Ch Rd Rev Ext | Install 200' - 2" poly main for one new residential customer (Mark Knecht) requesting service at 2245 Olivet Ch Rd. | -2576.82 | 6674.46 | -9251.28 | -138.6% | -0.004084% | -2576.82 | 6674.46 | -9251.28 | 2021-10-01 | 2022-09-30 | 2022-06-01 | 06 | 2022-09-15 | 09
050.58705 | COM.2637.Ky Oaks Mall Ext | Install 200 feet of 2 inch poly main for the new Auto Zone at 3021 New Holt Rd, this is the former Pier 1 site.. Tie-on behind Chuck E Cheese | 7363.91 | 6537.27 | 826.64 | 12.65% | 0.01167% | 7363.91 | 6537.27 | 826.64 | 2021-10-01 | 2022-09-30 | 2022-06-01 | 06 | 2022-07-30 | 07
050.58707 | PI.2734.31W State Hwy.Reloc. | Relocate 2230 ft. of 2 inch PR main along 31W at the transpark in conjunction with State Plan 03-8905.00. Addimg an additional 1000 ft. of 6 inch HDPE and Station to feed existing IP Feed in the Transpark . Project has 30% reimbursement by State Hwy | 222811.1 | 344780.72 | -121969.62 | -35.38% | 0.3532% | 222811.1 | 344780.72 | -121969.62 | 2021-10-01 | 2022-09-30 | 2022-04-27 | 04 | 2022-09-30 | 09
050.58723 | SI.2735.N.Cane.City Tie-IN | Tie In 240 Ft. of 4 inch HDPE will eliminate Purchase Meter at North Cave City TB> Project is an approved FY2022 Buget Item . Installation by Martin Construction | 27350.59 | 75484.54 | -48133.95 | -63.77% | 0.04335% | 27350.59 | 75484.54 | -48133.95 | 2021-10-01 | 2022-09-30 | 2022-04-21 | 04 | 2022-08-31 | 08
050.58735 | RES.2636.SUMMITAVE.MN.EXT | Install 100' of 4" HDPE for new customers | 23408.73 | 28066.83 | -4658.1 | -16.6% | 0.0371% | 23408.73 | 28066.83 | -4658.1 | 2021-10-01 | 2022-09-30 | 2022-05-16 | 05 | 2022-06-30 | 06
050.58736 | Pierce Lackey - DRS Replace | This project is to capture the costs associated with the replacement of the District Regulator Station at Pierce Lackey Court (public housing authority). Work will begin as soon as possible. | 5204.31 | 16617.12 | -11412.81 | -68.68% | 0.008249% | 5204.31 | 16617.12 | -11412.81 | 2021-10-01 | 2022-09-30 | 2022-05-09 | 05 | 2022-06-30 | 06
050.58746 | Ella Munal DRS Replace | This project is set up to capture the costs associated with the replacement of the DRS at Ella Munal Court (Paducah Housing Authority). | 5621.59 | 16528.17 | -10906.58 | -65.99% | 0.008911% | 5621.59 | 16528.17 | -10906.58 | 2021-10-01 | 2022-09-30 | 2022-05-09 | 05 | 2022-06-30 | 06
050.58763 | IND.2734.Reasonover | move main | 18188.46 | 23465.15 | -5276.69 | -22.49% | 0.02883% | 18188.46 | 23465.15 | -5276.69 | 2021-10-01 | 2022-09-30 | 2022-05-10 | 05 | 2022-09-30 | 09
050.58771 | RES.2738.Marshall Ridge Road | 350 Ft of 2 In HDPE Main to serve 1 new customer | 6612.21 | 9276.2 | -2663.99 | -28.72% | 0.01048% | 6612.21 | 9276.2 | -2663.99 | 2021-10-01 | 2022-09-30 | 2022-05-01 | 05 | 2022-06-30 | 06
050.58772 | RES.2738.Meadow Lane Ph 3 | 1400 Ft of 2 In Main to serve 18 tracts in Fieldcrest off of Meadow Lane | 5827.02 | 7223.77 | -1396.75 | -19.34% | 0.009236% | 5827.02 | 7223.77 | -1396.75 | 2021-10-01 | 2022-09-30 | 2022-05-01 | 05 | 2022-06-30 | 06
050.58777 | COM.2636.CALUMETTRACEPH1MN.EX | Iinstall 600' of 4" HDPE for new customers | 7233.48 | 11761.8 | -4528.32 | -38.5% | 0.01147% | 7233.48 | 11761.8 | -4528.32 | 2021-10-01 | 2022-09-30 | 2022-05-16 | 05 | 2022-05-31 | 05
050.58788 | RES.2734.BreckenridgePhase II | 1230 ft. of 4 inch and 1356 ft. of 2 inch HDPE will serve 33 new residential lots in Phase II of Brecenridge l.ocated off Old Scottsville Rd. in Alvaton. Developer will open and close ditch and install casings for main and service lines. | 18396.81 | 20863.67 | -2466.86 | -11.82% | 0.02916% | 18396.81 | 20863.67 | -2466.86 | 2021-10-01 | 2022-09-30 | 2022-02-21 | 02 | 2022-06-30 | 06
050.58795 | COM.2636.GREENVILLEAIRPORT.MN | Install 650' of 2" HDPE for Airport | 3718.81 | 7837.29 | -4118.48 | -52.55% | 0.005895% | 3718.81 | 7837.29 | -4118.48 | 2021-10-01 | 2022-09-30 | 2022-07-01 | 07 | 2022-07-14 | 07
050.58796 | RES.2636.PARKHAVEN.MN.EXT | Install 1500' of 2" HDPE for subdivision growth | 15165.4 | 16713.68 | -1548.28 | -9.264% | 0.02404% | 15165.4 | 16713.68 | -1548.28 | 2021-10-01 | 2022-09-30 | 2022-06-01 | 06 | 2022-06-30 | 06
050.58804 | RES.2635.CARLADR.MN.EXT | Install 750' of 2" HDPE for 6 new customers | 10859.83 | 8772.73 | 2087.1 | 23.79% | 0.01721% | 10859.83 | 8772.73 | 2087.1 | 2021-10-01 | 2022-09-30 | 2022-06-01 | 06 | 2022-06-07 | 06
050.58810 | 2636.Highway 54 Relocatio_ | Replace approximately 6,00' of 2", 3", and 4" Pipe with 6" HDPE for Highway rRelocation project on 54 in Owensboro KY. 25 Services | 737927.34 | 989530.86 | -251603.52 | -25.43% | 1.17% | 737927.34 | 989530.86 | -251603.52 | 2021-10-01 | 2022-09-30 | 2022-05-23 | 05 | 2022-10-30 | 10
050.58833 | LP.050.2736.Phelps LP Services | Project replaces115 services in conjunction with low oressure main replacement on Phelps Ave. in Hopkinsville. | 562203.95 | 468920 | 93283.95 | 19.89% | 0.8911% | 562203.95 | 468920 | 93283.95 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.58835 | Adyl.2635.Sunset Circle | See Project Long Description /Notes | 569512.7 | 376757.49 | 192755.21 | 51.16% | 0.9027% | 569512.7 | 376757.49 | 192755.21 | 2021-10-01 | 2022-09-30 | 2022-06-06 | 06 | 2022-09-30 | 09
050.58836 | PRP.2635.Harmon Dr | See project long description/notes. | 104136.03 | 117820.24 | -13684.21 | -11.61% | 0.1651% | 104136.03 | 117820.24 | -13684.21 | 2021-10-01 | 2022-09-30 | 2022-05-26 | 05 | 2022-06-19 | 06
050.58839 | PRP.2634.Robards Phase-2 | See project long description/notes | 201030.32 | 267255.19 | -66224.87 | -24.78% | 0.3186% | 201030.32 | 267255.19 | -66224.87 | 2021-10-01 | 2022-09-30 | 2022-06-05 | 06 | 2022-09-08 | 09
050.58847 | RES.2636.HWY764N.MN.EXT | Install 380' of 2" HDPE for new customer | 1332.95 | 3806.84 | -2473.89 | -64.99% | 0.002113% | 1332.95 | 3806.84 | -2473.89 | 2021-10-01 | 2022-09-30 | 2022-06-13 | 06 | 2022-09-27 | 09
050.58886 | 2635.HWY60MARIONRELOCATE | Relocate 1,000' of 2" PE for Hwy Widening | 69493.62 | 71860.44 | -2366.82 | -3.294% | 0.1102% | 69493.62 | 71860.44 | -2366.82 | 2021-10-01 | 2022-09-30 | 2022-06-06 | 06 | 2022-07-30 | 07
050.58899 | 2634.41ARELOCATE | Relocate 200' of 4" HDPE on HWY 41A | 17272.9 | 17177.35 | 95.55 | 0.5563% | 0.02738% | 17272.9 | 17177.35 | 95.55 | 2021-10-01 | 2022-09-30 | 2022-06-06 | 06 | 2022-06-21 | 06
050.58908 | RES.2739.Ardmore Phase 4 | XXXX Ft of 2 In HDPE to serve Phase 4 of Ardmore Crossings in Shelbyville KY | 30210.46 | 25818.3 | 4392.16 | 17.01% | 0.04789% | 30210.46 | 25818.3 | 4392.16 | 2021-10-01 | 2022-09-30 | 2022-06-01 | 06 | 2022-08-31 | 08
050.58933 | Mayfield Structures | FY22 structures including cantilever opener for gate (16K), Painting outside of W. James Street (26.5K), parking lot resurface (9.25K), concrete material bins (25K), work stations (5K), fence replacement (32K), and new sewer lateral w/ grinder pump (14.3 | 148274.59 | 158385.03 | -10110.44 | -6.383% | 0.235% | 148274.59 | 158385.03 | -10110.44 | 2021-10-01 | 2022-09-30 | 2022-06-08 | 06 | 2022-09-30 | 09
050.58945 | 2634.NoffsingerLn.Rlocate | Relocate 1000' of 2" Stl. and 500' of 2" PE. for new Dollar Store | 76474.26 | 73524.54 | 2949.72 | 4.012% | 0.1212% | 76474.26 | 73524.54 | 2949.72 | 2021-10-01 | 2022-09-30 | 2022-06-13 | 06 | 2022-06-29 | 06
050.58951 | RES.2734.Lexington Place 3 | Install 1,250 feet of 2 inch poly for app. 20 new residential lots in this (Phase 3) of Lexington Place Subdivision | 3215.51 | 6721.53 | -3506.02 | -52.16% | 0.005097% | 3215.51 | 6721.53 | -3506.02 | 2021-10-01 | 2022-09-30 | 2022-06-15 | 06 | 2022-08-30 | 08
050.58961 | PRP.2636.Oak Ave | See Project Long Description /Notes | 283013.61 | 313547.92 | -30534.31 | -9.738% | 0.4486% | 283013.61 | 313547.92 | -30534.31 | 2021-10-01 | 2022-09-30 | 2022-06-20 | 06 | 2022-09-30 | 09
050.58977 | PRP.2738.Sunny Hill Dr | See project Long Description/Notes | 149936.48 | 113617.49 | 36318.99 | 31.97% | 0.2377% | 149936.48 | 113617.49 | 36318.99 | 2021-10-01 | 2022-09-30 | 2022-07-22 | 07 | 2022-09-25 | 09
050.58996 | 050.2637.Iowa St Replacement | Install app. 550 feet of 2 inch poly main, retire 550 feet of 2 inch steel main (1959). McCracken County Road Department is making improvements. We have conflicts on Iowa St and Starr Hill Rd | 23964.96 | 27365.49 | -3400.53 | -12.43% | 0.03799% | 23964.96 | 27365.49 | -3400.53 | 2021-10-01 | 2022-09-30 | 2022-07-01 | 07 | 2022-08-30 | 08
050.59043 | 2636.HAYDENRD.RELOCATE | Relocate 600' of 6" HDPE for Green Belt | 10664.88 | 60359.13 | -49694.25 | -82.33% | 0.0169% | 10664.88 | 60359.13 | -49694.25 | 2021-10-01 | 2022-09-30 | 2022-06-20 | 06 | 2022-06-30 | 06
050.59046 | COM.2636.SOUTHTOWNBLVD.MN.EXT | Install 820' of 4" HDPE for Aquatic Center | 37850.69 | 45195.07 | -7344.38 | -16.25% | 0.06% | 37850.69 | 45195.07 | -7344.38 | 2021-10-01 | 2022-09-30 | 2022-07-11 | 07 | 2022-07-22 | 07
050.59053 | RES.2739.Robin Place Ph 1 | 750 Ft of 2 In HDPE to serve Phase 1 of Robin Place | 23503.41 | 16324.63 | 7178.78 | 43.98% | 0.03725% | 23503.41 | 16324.63 | 7178.78 | 2021-10-01 | 2022-09-30 | 2022-07-11 | 07 | 2022-08-26 | 08
050.59063 | 050.2638.Park Terrace Retire | Retire 348 feet of (2014) 2 inch poly main. This was formerly a mobile hpme court, now abandoned no customers are left. | 485.43 | 620.71 | -135.28 | -21.79% | 0.0007694% | 485.43 | 620.71 | -135.28 | 2021-10-01 | 2022-09-30 | 2022-07-01 | 07 | 2022-07-30 | 07
050.59069 | 050.2637.Friendship Replace | KYTC making improvements to N Friendship Rd from Lone Oak Rd to Blandville Rd | 43679.36 | 73851.34 | -30171.98 | -40.86% | 0.06923% | 43679.36 | 73851.34 | -30171.98 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-10-30 | 10
050.59081 | RES.2638.Parkway Dr Main Ext | Install 140 feet of 2 inch poly main for one new residential customer and one existing commercial customer (Body shop/ auto repair) | -290.82 | 7112.49 | -7403.31 | -104.1% | -0.000461% | -290.82 | 7112.49 | -7403.31 | 2021-10-01 | 2022-09-30 | 2022-07-18 | 07 | 2022-08-30 | 08
050.59082 | RES.2637.PrincessJennifer Ext | Install 200 feet of 2 inch poly main for two existing residential homes. One customer (Gil Arterburn) requesting new service at 435 Princess Jennifer Dr in Calvert City | 3056.28 | 6474.88 | -3418.6 | -52.8% | 0.004844% | 3056.28 | 6474.88 | -3418.6 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59097 | RES.2637.Kenmar Rd Rev Ext | Install 225 feet of 2 inch poly, coming off 2 inch poly on Babbland Drive. One customer (Brandon Ladd)) requesting gas for new home at 715 Kenmar Rd | 2633.15 | 5040.76 | -2407.61 | -47.76% | 0.004174% | 2633.15 | 5040.76 | -2407.61 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59101 | RES.2637.Paddock 2 Rev Ext | Install 1,215 feet of 2 inch poly main in this (second phase) of Paddock at the Oaks Subdivision. Extension makes gas available to three lots plus three tracts which may be divided. Developer is Chad Willett | 38567.99 | 29756.93 | 8811.06 | 29.61% | 0.06113% | 38567.99 | 29756.93 | 8811.06 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59103 | RES.2636.FUNNYCIDECOVE.MN.EXT | Install 500' of 2" HDPE for Sub Division growth | 9785.21 | 9152.77 | 632.44 | 6.91% | 0.01551% | 9785.21 | 9152.77 | 632.44 | 2021-10-01 | 2022-09-30 | 2022-08-02 | 08 | 2022-08-24 | 08
050.59105 | COM.2636.KNOTTFARS-BERRYRD.MN | Install 800' of 4" HDPE for Chicken Farm | 16531.69 | 17841.24 | -1309.55 | -7.34% | 0.0262% | 16531.69 | 17841.24 | -1309.55 | 2021-10-01 | 2022-09-30 | 2022-07-05 | 07 | 2022-08-30 | 08
050.59106 | 2634.SLOVERCREEKREPLACEMENT | Replace 2" Stl. Creek Crossing | 71186.64 | 76937.23 | -5750.59 | -7.474% | 0.1128% | 71186.64 | 76937.23 | -5750.59 | 2021-10-01 | 2022-09-30 | 2022-07-11 | 07 | 2022-09-29 | 09
050.59121 | 050.2736.Parking Lot Seal Hopk | Project for sealing and striping the parking lot at the Hopkinsville Office | 2690.9 | 3092.25 | -401.35 | -12.98% | 0.004265% | 2690.9 | 3092.25 | -401.35 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.59126 | 050.2637.S 25th St Replace | City making storm sewer omprovements. We need to replace app 400 ft. of 2" PE and 200 ft of 4" PE plus 4 or 5 services | 116947.69 | 74049.09 | 42898.6 | 57.93% | 0.1854% | 116947.69 | 74049.09 | 42898.6 | 2021-10-01 | 2022-09-30 | 2022-07-18 | 07 | 2022-08-30 | 08
050.59158 | COM.2636.ARBYS.MN.EXT | Install 1150' of 2" HDPE for new restaurant | 54875.01 | 48082.71 | 6792.3 | 14.13% | 0.08698% | 54875.01 | 48082.71 | 6792.3 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-08-22 | 08
050.59185 | 050.2638.I-69 at 45 Relocate | A & K Construction building a new Hucks Truck Stop at the intersection of I-69 and US Hwy 45 (Paducah Rd). There are conflicts with our existing 4-inch steel gas main. We will install 560 feet of 4-inch poly main and retire 550 feet of 4" steel. | 3757.92 | 25233.38 | -21475.46 | -85.11% | 0.005957% | 3757.92 | 25233.38 | -21475.46 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59187 | INT.2737.US 27 Widening | Relocate 2000 ft of 2 In Main to elimate conflicts with US 27 Widening | 179681.89 | 79642.34 | 100039.55 | 125.6% | 0.2848% | 179681.89 | 79642.34 | 100039.55 | 2021-10-01 | 2022-09-30 | 2022-07-25 | 07 | 2022-09-30 | 09
050.59192 | Adyl.2635.Westend St | Replace 2621 ft of 2 Inch Adyl A with 2558 Ft of 2 Inch HDPE 13 services involved | 262615.87 | 373594.69 | -110978.82 | -29.71% | 0.4163% | 262615.87 | 373594.69 | -110978.82 | 2021-10-01 | 2022-09-30 | 2022-07-27 | 07 | 2022-09-30 | 09
050.59221 | COM.BAKERAVEUPGRADE | Replace 500' of 1" Stl. with 500' of 2" HDPE for Grain Dyer | 58782.49 | 44591.03 | 14191.46 | 31.83% | 0.09317% | 58782.49 | 44591.03 | 14191.46 | 2021-10-01 | 2022-09-30 | 2022-08-08 | 08 | 2022-08-22 | 08
050.59222 | 050.2638.Lazy Acres Retire | This site is the former mobile home park called Lazy Acres. It was built in 1981. Atmos installed 2 inch plastic gas mains in 1982. There are no more mobile homes today. Property has been purchased as commercial property. Retire 1,016 feet of 2 inch | 1659.42 | 296.66 | 1362.76 | 459.4% | 0.00263% | 1659.42 | 296.66 | 1362.76 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59235 | COM.2734.Bale Commercial.Ext | 2500 ft. of 4 inchHDPE will serve new commercial development for Bale Blvd. located off Lovers Ln. and Middlebridge. Will tie in to existing 6 inch HDPE at Lovers Ln. and fiture round-about at Shive Ln. and Middlebridge. Bale Family Partnership will | -43210.43 | 68239.29 | -111449.72 | -163.3% | -0.06849% | -43210.43 | 68239.29 | -111449.72 | 2021-10-01 | 2022-09-30 | 2022-02-17 | 02 | 2022-09-29 | 09
050.59255 | 050.2637.Oak St Retirement | Retire app. 665 feet of 2 inch mill wrapped steel main from 1961. Main is insactive, we are there retiring services, no active services on this section of main | 1562.48 | 121.59 | 1440.89 | 1185% | 0.002477% | 1562.48 | 121.59 | 1440.89 | 2021-10-01 | 2022-09-30 | 2022-08-01 | 08 | 2022-08-31 | 08
050.59278 | RES.2636.HWY279MN.EXT | Install 2000' of 2" HDPE for new customers | 61134.57 | 21546.66 | 39587.91 | 183.7% | 0.0969% | 61134.57 | 21546.66 | 39587.91 | 2021-10-01 | 2022-09-30 | 2022-09-01 | 09 | 2022-09-23 | 09
050.59377 | PRP.2734.Lost-River Cave | ****** Revision Comments ****** Original Estimate $ 617,953.80 Contractor estimate for contract labor to finish project was under estimated. | 148073.87 | 617923.8 | -469849.93 | -76.04% | 0.2347% | 148073.87 | 617923.8 | -469849.93 | 2021-10-01 | 2022-09-30 | 2022-08-31 | 08 | 2023-02-01 | 02
050.59405 | RES.2636.SCHIEDERTANNERLN.MN. | Install 800' of 2" HDPE for new customers | 6860.91 | 8868.1 | -2007.19 | -22.63% | 0.01088% | 6860.91 | 8868.1 | -2007.19 | 2021-10-01 | 2022-09-30 | 2022-09-01 | 09 | 2022-09-23 | 09
050.59406 | RES.2636.BRIDGEWOOD.MN.EXT | Install 1100' of 2" HDPE for subdivision growth | 19095.79 | 22636.94 | -3541.15 | -15.64% | 0.03027% | 19095.79 | 22636.94 | -3541.15 | 2021-10-01 | 2022-09-30 | 2022-09-01 | 09 | 2022-09-20 | 09
050.59411 | RES.2636.FREESILVERRD.MN.EXT | Install 575' of 2" HDPE for 3 new customers | 1524.05 | 6822.4 | -5298.35 | -77.66% | 0.002416% | 1524.05 | 6822.4 | -5298.35 | 2021-10-01 | 2022-09-30 | 2022-09-02 | 09 | 2022-10-16 | 10
050.59412 | RES.2636.PLEASENTPOINTRD.MN.E | Install 265' of 2" HDPE for new customer | 3771.9 | 2902.6 | 869.3 | 29.95% | 0.005979% | 3771.9 | 2902.6 | 869.3 | 2021-10-01 | 2022-09-30 | 2022-09-05 | 09 | 2022-09-12 | 09
050.59504 | 2636.KY298ROUNDABOUTUPGRADE | Replace 848' of 4" Stl., 189' of 2" Stl., with848' of 4" HDPE and 189' of 2" HDPE | 14165.83 | 160286.57 | -146120.74 | -91.16% | 0.02245% | 14165.83 | 160286.57 | -146120.74 | 2021-10-01 | 2022-09-30 | 2022-09-15 | 09 | 2023-04-28 | 04
050.59524 | PRP.2637.Washington St | ******* Revision Comments ******* Original Estimate: $739,563.14 2,978' of additional main was installed and the 4" PE was changed to 6" PE from the original estimate.Concrete and asphalt exceeded original estimate | 1978.73 | 739563.14 | -737584.41 | -99.73% | 0.003136% | 1978.73 | 739563.14 | -737584.41 | 2021-10-01 | 2022-09-30 | 2022-10-03 | 10 | 2023-03-27 | 03
050.59557 | 3302.KY Laptops Ph2.FY22 | Purchase replacement laptops and monitors for Kentucky - 2nd order for FY22 | 19570.33 | 22264.2 | -2693.87 | -12.1% | 0.03102% | 19570.33 | 22264.2 | -2693.87 | 2021-10-01 | 2022-09-30 | 2022-09-01 | 09 | 2022-09-30 | 09
050.59561 | 2637.Equipment - Processor | EF Processor with case, scanner kit, barcode3, manual, & cp modes by George Fischer Central Plastics, LLC George Fischer Central Plastics, LLC | 5728.15 | 5588.91 | 139.24 | 2.491% | 0.00908% | 5728.15 | 5588.91 | 139.24 | 2021-10-01 | 2022-09-30 | 2022-09-06 | 09 | 2022-09-30 | 09
050.59567 | PRP.2636.N Cherry Street | ******* Revision Comments ****** Original Estimate : $745,938.36 An addtional 2,970' of main was installed concrete and asphalt exceeded estimate. | 824.19 | 745938.36 | -745114.17 | -99.89% | 0.001306% | 824.19 | 745938.36 | -745114.17 | 2021-10-01 | 2022-09-30 | 2022-10-03 | 10 | 2023-02-17 | 02
050.59569 | 050.2734.ERX - Purchase | Purchase ERX | 49424.75 | 47092.58 | 2332.17 | 4.952% | 0.07834% | 49424.75 | 47092.58 | 2332.17 | 2021-10-01 | 2022-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.59651 | RES.2736.Hwwy181.Ext.Elkton | 1300 ft. of 2 inch HDPE will werve 4 new residential customers on Hwy 181 in Elkton. AIC = 3003.00 | 7526.95 | 14925.47 | -7398.52 | -49.57% | 0.01193% | 7526.95 | 14925.47 | -7398.52 | 2021-10-01 | 2022-09-30 | 2022-08-25 | 08 | 2022-09-30 | 09
050.59722 | 050.2609.Kirkwood | Removing compressor station, replacing witrh new reg. stations and dehy, tying into storgae trunkline and High Pressure | 874786.35 | 4044879.71 | -3170093.36 | -78.37% | 1.387% | 874786.35 | 4044879.71 | -3170093.36 | 2021-10-01 | 2022-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
OH.050.10000 |  | UCG Business Unit A&G Overhead Project | 186.36 | 0 | 186.36 |  | 0.04573% | 28851.25 | 0 | 28851.25 | 2021-10-01 | 2022-09-30 | 1999-04-30 | 04 | 2020-12-31 | 12

## 2023
Atmos Energy Corporation
(Kentucky Division)
Case No. 2024-00276
Construction Projects 2023
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised
Workpaper Reference No(s).:
Project No. | Project Title / Description |  | Annual Actual Cost 2023 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 202028.55 | 0 |  |  | 3.805% | 2393929.27 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 7818.08 | 0 |  |  | 0.2986% | 187878.34 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 30757.1 | 0 |  |  | 0.7092% | 446231.97 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 18761.85 | 0 |  |  | 0.4492% | 282660.53 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 38955.16 | 0 |  |  | 0.4802% | 302124.19 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 69146.4 | 0 |  |  | 1.762% | 1108409.32 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 12333.6 | 0 |  |  | 0.3136% | 197345.79 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 16364.29 | 0 |  |  | 0.3356% | 211187.77 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 91429.25 | 0 |  |  | 2.705% | 1702336.57 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 94186.49 | 0 |  |  | 2.916% | 1834958.91 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2017-09-30 | 09
050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 39426.06 | 0 |  |  | 0.996% | 626689.05 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 157202.52 | 0 |  |  | 2.55% | 1604242.32 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 24793.94 | 0 |  |  | 0.122% | 76779.5 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 19391.41 | 0 |  |  | 0.274% | 172428.21 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 36521.75 | 0 |  |  | 0.5467% | 343984.76 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 69736.66 | 0 |  |  | 0.4666% | 293612.94 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 60639.78 | 0 |  |  | 0.5426% | 341443.24 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5410.91 | 0 |  |  | 0.2647% | 166523.56 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 4054.65 | 0 |  |  | 0.1961% | 123413.32 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 19663.25 | 0 |  |  | 1.204% | 757871.36 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 33872.11 | 0 |  |  | 0.7505% | 472243.19 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 15713.95 | 0 |  |  | 0.2316% | 145709.48 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 1098611.36 | 0 |  |  | 17.12% | 10772934.31 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 149265.42 | 0 |  |  | 1.831% | 1152180.96 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 163999.44 | 0 |  |  | 1.701% | 1070256.76 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 108468.17 | 0 |  |  | 1.407% | 885442.24 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 108078.91 | 0 |  |  | 1.765% | 1110278.86 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 473854.44 | 0 |  |  | 6.036% | 3797963.47 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 108783.61 | 0 |  |  | 1.956% | 1230727.75 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 154479.85 | 0 |  |  | 1.263% | 794576.07 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 549602.13 | 0 |  |  | 11.55% | 7270068.4 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 257944.4 | 0 |  |  | 5.819% | 3661643.13 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2017-09-30 | 09
050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 154536.96 | 0 |  |  | 1.555% | 978457.15 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 387272.66 | 0 |  |  | 4.531% | 2851001.5 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 19977.02 | 0 |  |  | 0.6497% | 408827.48 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 34065.38 | 0 |  |  | 0.8586% | 540273.65 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 37627.74 | 0 |  |  | 0.9843% | 619323.3 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 46465.53 | 0 |  |  | 0.8298% | 522116.28 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 54881.43 | 0 |  |  | 0.8212% | 516691.01 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 52017.15 | 0 |  |  | 0.9252% | 582163.44 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 38242.66 | 0 |  |  | 0.5594% | 352012.22 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 460549.83 | 0 |  |  | 4.288% | 2698234.35 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 156176.59 | 0 |  |  | 2.091% | 1315866.36 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 61613.22 | 0 |  |  | 0.5448% | 342815.91 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 702984.98 | 0 |  |  | 9.21% | 5794789.53 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 334123.61 | 0 |  |  | 3.226% | 2030100.18 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 162875.1 | 0 |  |  | 6.103% | 3840358.25 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 411647.25 | 0 |  |  | 5.711% | 3593542.67 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 176645.04 | 0 |  |  | 3.134% | 1971895.59 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 111136.2 | 0 |  |  | 1.853% | 1165888.57 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 247863.28 | 0 |  |  | 5.006% | 3149572.59 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 257649.59 | 0 |  |  | 3.136% | 1972947.56 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 749597.44 | 0 |  |  | 11.7% | 7363991.04 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 826332.24 | 0 |  |  | 9.404% | 5917357.23 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 215443.67 | 0 |  |  | 2.964% | 1864908.52 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 482632.77 | 0 |  |  | 11.26% | 7084944.87 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 95892.08 | 0 |  |  | 2.98% | 1875216.47 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 132847.04 | 0 |  |  | 3.781% | 2379081.1 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 253771.47 | 0 |  |  | 3.966% | 2495187 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 232337.57 | 0 |  |  | 3.522% | 2215907.7 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 210188.83 | 0 |  |  | 3.145% | 1979148.56 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 108440.57 | 0 |  |  | 3.714% | 2336707.06 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 80518.32 | 0 |  |  | 1.968% | 1238046.87 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 712553.54 | 0 |  |  | 15.62% | 9830317.59 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 177784.97 | 0 |  |  | 9.114% | 5734657.64 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 69577.47 | 0 |  |  | 3.426% | 2155837.17 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 118610.04 | 0 |  |  | 1.777% | 1118307 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 13570.26 | 0 |  |  | 0.222% | 139686.09 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 17784.43 | 0 |  |  | 0.8854% | 557137.95 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 27030.17 | 0 |  |  | 1.18% | 742217.38 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 54363.61 | 0 |  |  | 0.4039% | 254132.64 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 20175.07 | 0 |  |  | 0.2215% | 139346.47 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 26396.89 | 0 |  |  | 0.5621% | 353692.27 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 17249.56 | 0 |  |  | 0.4511% | 283865.27 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 81549.91 | 0 |  |  | 1.131% | 711548.44 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 35233.34 | 0 |  |  | 0.734% | 461833.89 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 9335.12 | 0 |  |  | 0.1402% | 88230.23 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 49443.02 | 0 |  |  | 3.806% | 2394662.68 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 24179.43 | 0 |  |  | 1.426% | 897054.37 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 42025.08 | 0 |  |  | 1.315% | 827327.18 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 23540.77 | 0 |  |  | 1.015% | 638823.74 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 7471.29 | 0 |  |  | 0.5858% | 368601.71 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 11487.2 | 0 |  |  | 0.4197% | 264107.44 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 35233.05 | 0 |  |  | 1.229% | 773323.07 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 21644.5 | 0 |  |  | 0.6724% | 423064.07 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 59307.04 | 0 |  |  | 2.114% | 1329884.01 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 21668.74 | 0 |  |  | 1.729% | 1087762.19 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 4519.01 | 0 |  |  | 0.3321% | 208984.01 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 44773.55 | 0 |  |  | 3.908% | 2458735.44 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 47042.97 | 0 |  |  | 1.282% | 806796.15 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 11265.68 | 0 |  |  | 1.083% | 681594.65 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 43429.81 | 0 |  |  | 1.569% | 987430.14 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 20019.23 | 0 |  |  | 0.5749% | 361707.45 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 2461.78 | 0 |  |  | 0.4389% | 276187.57 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 42435.02 | 0 |  |  | 1.33% | 836725.68 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 30832.05 | 0 |  |  | 0.5503% | 346249.54 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 191347.81 | 0 |  |  | 3.709% | 2333873.7 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2017-12-31 | 12
050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 45910.82 | 0 |  |  | 3.144% | 1978270.2 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 19465.8 | 0 |  |  | 0.5862% | 368822.8 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 187622.38 | 0 |  |  | 4.262% | 2681669.3 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 22633.45 | 0 |  |  | 0.9887% | 622091.54 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 53873.51 | 0 |  |  | 0.7803% | 490968.38 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 17690.07 | 0 |  |  | 1.2% | 755136.22 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 128275.55 | 0 |  |  | 1.146% | 720991.5 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 29648.2 | 0 |  |  | 0.7677% | 483021.99 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 33031.11 | 0 |  |  | 0.9199% | 578834.73 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 20476.69 | 0 |  |  | 0.448% | 281867.19 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 146388.66 | 0 |  |  | 4.543% | 2858257.49 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 69471.5 | 0 |  |  | 1.715% | 1079182.35 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 31552.72 | 0 |  |  | 0.3479% | 218895.83 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | 2824.37 | 0 |  |  | 0.1327% | 83501.9 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 57.21 | 0 |  |  | 0.02098% | 13203.01 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 473817.49 | 0 |  |  | 25.57% | 16091910.52 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 1473662.92 | 0 |  |  | 17.01% | 10702576.24 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2020-09-30 | 09
050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 1711583.72 | 0 |  |  | 27.21% | 17120862.96 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 1793319.25 | 0 |  |  | 23.55% | 14819378.55 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 2576.87 | 0 |  |  | 0.02799% | 17612.28 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 131.86 | 0 |  |  | 0.0135% | 8491.57 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 225970.13 | 0 |  |  | 4.353% | 2739140.63 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 778597.6 | 0 |  |  | 10.48% | 6597092.46 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 603.84 | 0 |  |  | 1.497% | 942044.56 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 2756.13 | 0 |  |  | 9.754% | 6137190.27 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 15114.06 | 0 |  |  | 9.74% | 6128327.63 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 1360881.82 | 0 |  |  | 14.3% | 8997474.47 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26312 | ShelbyvillePRPServices | Shelbyville KY PRP Functional - Services | 63.31 | 0 |  |  | 0.3801% | 239184.02 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
050.31536 | 050.2634.Hwy 425 | Install 1100 Ft. 2 Inch PE to serve two Commercial customers | -4291.76 | 5245.76 | -9537.52 | -181.8% | 0.00241% | 1516.17 | 5245.76 | -3729.59 | 2022-10-01 | 2023-09-30 | 2012-07-15 | 07 | 2012-09-28 | 09
050.31561 | 2738.CAM.WOODLAND HEIGHT 2012 | INSTALL 3400ft OF 2in PE FOR SUBDIVISION | -8783 | 8794.12 | -17577.12 | -199.9% | -0.003424% | -2154.45 | 8794.12 | -10948.57 | 2022-10-01 | 2023-09-30 | 2011-12-01 | 12 | 2012-12-01 | 12
050.31690 | 050.2734.S.Glen Ext. | Estimate SouthGlen - 7035 ft -4 inch - 9665 ft -2 inch | -2965.95 | 18685 | -21650.95 | -115.9% | 0.001461% | 919.52 | 18685 | -17765.48 | 2022-10-01 | 2023-09-30 | 2012-06-25 | 06 | 2012-09-28 | 09
050.32136 | 2739.LAW.EAGLE LAKE 2012 | INSTALL 2in PE FOR EAGLE LAKE EXPANSION | -3207 | 4367.92 | -7574.92 | -173.4% | -0.004951% | -3115.4 | 4367.92 | -7483.32 | 2022-10-01 | 2023-09-30 | 2012-07-01 | 07 | 2013-11-01 | 11
050.32147 | 050.2636.W 13th. St. | Install 200 ft 2 Inch PE to serve 1 residential customer | -1156 | 2598.8 | -3754.8 | -144.5% | 0.002149% | 1351.97 | 2598.8 | -1246.83 | 2022-10-01 | 2023-09-30 | 2012-09-28 | 09 | 2013-09-28 | 09
050.33543 | 050.2636.Challenger Ctr. 2 | Install 220 ft 2 Inch PE to serve new Southern Star Central Gas Pipeline Building | -1177.24 | 2145.55 | -3322.79 | -154.9% | 0.001077% | 677.42 | 2145.55 | -1468.13 | 2022-10-01 | 2023-09-30 | 2013-04-01 | 04 | 2013-09-28 | 09
050.33729 | 050.2638.The Meadows 5 Ext | Install 1,300 feet of 2 inch poly for 17 new residential lots in this fifth phase of The Meadows Subdivision. | -509.75 | 6343.44 | -6853.19 | -108% | 0.0153% | 9629.74 | 6343.44 | 3286.3 | 2022-10-01 | 2023-09-30 | 2013-05-02 | 05 | 2013-07-28 | 07
050.33744 | 2738.FEDERAL PLACE 2012 | INSTALL 350ft OF 2in PE FOR NEW CUSTOMER - DOLLAR GENARAL STORE | -2260 | 3163 | -5423 | -171.5% | -0.00128% | -805.46 | 3163 | -3968.46 | 2022-10-01 | 2023-09-30 | 2012-11-01 | 11 | 2013-11-01 | 11
050.34042 | 050.2636.Locust Hill Rd. | Install 661 ft 2 Inch PE to serve 1 residential customer | -4221.54 | 4977.75 | -9199.29 | -184.8% | 1.414e-05% | 8.9 | 4977.75 | -4968.85 | 2022-10-01 | 2023-09-30 | 2013-04-25 | 04 | 2013-09-28 | 09
050.34044 | 050.2636.Button Buck Ct. | Install 503 ft 2 Inch PE to serve 1 residential customer | -3377.69 | 5605.69 | -8983.38 | -160.3% | 0.004579% | 2881.3 | 5605.69 | -2724.39 | 2022-10-01 | 2023-09-30 | 2013-05-01 | 05 | 2013-09-28 | 09
050.34099 | 050.2636.Silver St. | Install 520 ft 2 Inch PE to serve 1 Commercial customer | -4051.43 | 5016.43 | -9067.86 | -180.8% | 0.004699% | 2956.48 | 5016.43 | -2059.95 | 2022-10-01 | 2023-09-30 | 2013-05-15 | 05 | 2013-09-28 | 09
050.46537 | 2739.Waddy Line Ph 2 | FY18/19 Budgeted System Improvement project occurring in Shelby County, KY. Replacing 25,000 feet of 6" high pressure steel main with 12" high pressure steel main. Starting R/W preparation and completion of easement acquisition in October FY18. Starting | -10464.25 | 12139301.77 | -12149766.02 | -100.1% | 16.77% | 10552393.1 | 12139301.77 | -1586908.67 | 2022-10-01 | 2023-09-30 | 2017-10-01 | 10 | 2019-03-30 | 03
050.52962 | 050.2739.Commerce Way | 600 Ft of 2 In HDPE to serve multiple customers on Commerce Way | -200.68 | 1093.77 | -1294.45 | -118.3% | 0.0013% | 817.86 | 1093.77 | -275.91 | 2022-10-01 | 2023-09-30 | 2020-01-06 | 01 | 2020-02-28 | 02
050.54337 | RES.2739.English Garden | 200 Ft of 2 In HDPE to serve two lots in Seascape Subdivison | -200.67 | 1218 | -1418.67 | -116.5% | 0.0013% | 817.87 | 1218 | -400.13 | 2022-10-01 | 2023-09-30 | 2020-07-06 | 07 | 2020-09-25 | 09
050.54764 | PRP.2635.Maple Ave | Project was in the KY 7/27/20 PRP Filing See project Long Description /notes | 722479.15 | 1006727.2 | -284248.05 | -28.23% | 1.195% | 752119.02 | 1006727.2 | -254608.18 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2023-04-30 | 04
050.55179 | 050.2637.Heath St Retirement | Retire 610 feet of 1 1/4 inch plastic gas main, this is a former mobile home park. There are no more mobile homes or customers online. | 369.23 | 333.48 | 35.75 | 10.72% | 0.0005868% | 369.23 | 333.48 | 35.75 | 2022-10-01 | 2023-09-30 | 2020-10-12 | 10 | 2021-07-30 | 07
050.55810 | PRP.2734.BG Centerline 3 | Replace 30,800 ft of 8" HPD Bare Steel Main with 30,800 ft of 8" Fusion Bond Epoxy HPD Steel main and 3,382 ft of 2" and 4,150 ft of 4" HDPE, also replace 2 Town Border Stations; 8 services | 26601.49 | 13256451.19 | -13229849.7 | -99.8% | 21.11% | 13283052.68 | 13256451.19 | 26601.49 | 2022-10-01 | 2023-09-30 | 2021-01-28 | 01 | 2022-09-30 | 09
050.56737 | PRP.2734.Schweizer Road | Replace 25,500' of 8" high pressure Bare steel with 25,500' of Fusion Bond Epoxy Steel, project will also include a new Purchase Station , check meter , YZ odorizer, all electronics and a expanded station lot | 7704630.97 | 10254292.78 | -2549661.81 | -24.86% | 13.08% | 8228532.96 | 10254292.78 | -2025759.82 | 2022-10-01 | 2023-09-30 | 2021-06-21 | 06 | 2023-09-30 | 09
050.56832 | 2739.WMR Endpoints.FY2022 | Purchase approximately 3942 WMR endpoints for Shelbyville, KY | 0.01 | 408237.78 | -408237.77 | -100% | 0.6954% | 437566.35 | 408237.78 | 29328.57 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-08-31 | 08
050.57032 | PRP.2737.Totten Ave | See Project Long Description/Notes | -28.57 | 989229.13 | -989257.7 | -100% | 1.572% | 989200.56 | 989229.13 | -28.57 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57148 | 2634.SEMINARYST..L.P. | Replace 25' of 11/4' Stl.,2900' of 2" Stl.,604' of 2" Plastic,4696' of 3" Stl.,10982' of 4" Stl.,210' of 4" Plastic, 752' of 6"Stl. Install 12690' of 2" HDPE., 3450' of 4" HDPE. Ret. RS1566, Rs.1558 | -67.91 | 1868617.22 | -1868685.13 | -100% | 2.519% | 1585231.56 | 1868617.22 | -283385.66 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57201 | 2634.W. Noel LP. Replacement | Replace 91' of 11/4" Stl., 3337' of 2" Stl.,222' of 2" Plastic, 747' of 3" Stl., 5758' of 4" Stl., and 300' of 4" Plastic, Install 5761' of 2"HDPE. and 4692' of 4" HDPE | 4638.76 | 1191198.69 | -1186559.93 | -99.61% | 1.836% | 1155538.95 | 1191198.69 | -35659.74 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-05-31 | 05
050.57242 | 2634.LP.Seminary St. Services | Replacement of 225 services with the Low Pressure replacement | 2428.17 | 1250728.98 | -1248300.81 | -99.81% | 1.713% | 1077976.22 | 1250728.98 | -172752.76 | 2022-10-01 | 2023-09-30 | 2021-11-01 | 11 | 2022-09-30 | 09
050.57291 | 050.2609.KY 554 Exposure | Replace Creek crossing on Farmers property in Owensboro KY. on 8" HPD line | 3062.94 | 122642.02 | -119579.08 | -97.5% | 0.02817% | 17723.19 | 122642.02 | -104918.83 | 2022-10-01 | 2023-09-30 | 2021-08-27 | 08 | 2022-09-30 | 09
050.57473 | COM.2735.S.Green Ext.Glasgow | 100 ft. of 2 inch HDPE will serve one new business on S, Green St. in Glasgow. Companty Crew will install | 1612.01 | 2979.49 | -1367.48 | -45.9% | 0.002562% | 1612.01 | 2979.49 | -1367.48 | 2022-10-01 | 2023-09-30 | 2021-09-22 | 09 | 2021-10-29 | 10
050.57554 | RES.2734.Massey Springs Ext. | 250 ft. of 2 inch HDPE will serve 5 new multi-family retirement homes in Massey Springs Development off Cave Mille and Smallhoise Rd.. | 2586.6 | 5881.41 | -3294.81 | -56.02% | 0.004111% | 2586.6 | 5881.41 | -3294.81 | 2022-10-01 | 2023-09-30 | 2021-10-14 | 10 | 2021-11-30 | 11
050.57632 | 050.2363.KY 331 | Replacement of High Pressure facilities along KY 331 in Owensboro KY for State Hwy widening project | 101343.63 | 423220.48 | -321876.85 | -76.05% | 0.4219% | 265458.21 | 423220.48 | -157762.27 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-10-30 | 10
050.57638 | RNG.2739.Benson Valley | Build RNG Interconnect at Benson Valley Landfill in Frankfort KY | 3834.14 | 1360373.4 | -1356539.26 | -99.72% | 0.0389% | 24475.45 | 1360373.4 | -1335897.95 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2023-06-30 | 06
050.57724 | PRP.2637.Lieberman St | See project Long Description / Notes | 3219.35 | 747648.65 | -744429.3 | -99.57% | 1.237% | 778570.55 | 747648.65 | 30921.9 | 2022-10-01 | 2023-09-30 | 2022-01-03 | 01 | 2022-09-30 | 09
050.57907 | 2638.Mayfield Tornado.21 | Track capital work associated with Mayfield, KY tornado damage. | 7334.79 | 1693619.85 | -1686285.06 | -99.57% | 0.1379% | 86758.51 | 1693619.85 | -1606861.34 | 2022-10-01 | 2023-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57908 | 2734.Bowling Green Tornado.21 | Track capital repair work associated with Bowling Green, KY tornado | 1285.84 | 294016.97 | -292731.13 | -99.56% | 0.04965% | 31238.66 | 294016.97 | -262778.31 | 2022-10-01 | 2023-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57909 | 2635.Dawson Prince.Tornado.21 | Track capital repairs associated with Dawson Springs/Princeton, KY tornado damage | 2857.24 | 610486.23 | -607628.99 | -99.53% | 0.04061% | 25549.29 | 610486.23 | -584936.94 | 2022-10-01 | 2023-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57910 | 2636.OWB-Bremen Tornado.21 | Track capital repairs associated with OWB-Bremen, KY tornado. | -3132.59 | 26891.24 | -30023.83 | -111.6% | -0.00285% | -1793.1 | 26891.24 | -28684.34 | 2022-10-01 | 2023-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.57932 | 050.2638.TORNADO-5th-Houseman | This project is to supply gas to app. 140 customers at the Mayfield Housing Authority property at N 5th & Houseman Streets. We propose to install 220 feet of 2 inch poly main, 290 feet of 4 inch poly main. | 216.34 | 46512.26 | -46295.92 | -99.53% | 0.002339% | 1471.9 | 46512.26 | -45040.36 | 2022-10-01 | 2023-09-30 | 2021-12-15 | 12 | 2021-12-31 | 12
050.57933 | 050.2638.TORNADO-9th-Willow | Install 260 feet of 2 inch poly main in the 400 block of S. 9th Street in order to restore gas service to the local United Way/Food Pantry and Stone's Pharmacy | 57.4 | 9986.38 | -9928.98 | -99.43% | 0.0007527% | 473.6 | 9986.38 | -9512.78 | 2022-10-01 | 2023-09-30 | 2021-12-17 | 12 | 2022-01-31 | 01
050.57972 | RES.2635DEPOTST.MN.EXT | Install 1300' of 4" HDPE for feed into Dawson springs | 1462.27 | 361978.45 | -360516.18 | -99.6% | 0.0161% | 10132.49 | 361978.45 | -351845.96 | 2022-10-01 | 2023-09-30 | 2021-12-27 | 12 | 2022-02-28 | 02
050.57993 | 050.2638-TORNADO-12th-Oak St | Install app. 1,500 feet of 2 inch poly main Along Oak St from S 10th to S 12th. This with the installation of a valve will allow us to restore gas to at least 80 homes when they are ready. | 821.3 | 236947.85 | -236126.55 | -99.65% | 0.01082% | 6807.76 | 236947.85 | -230140.09 | 2022-10-01 | 2023-09-30 | 2022-01-03 | 01 | 2022-02-28 | 02
050.58042 | 050.2637.TORNADO-4th-North St | Install app. 3,400 feet of 4 inch poly and 1,120 feet of 2 inch poly main to restore service to app. 75 properties. | 786.67 | 453904.13 | -453117.46 | -99.83% | 0.01827% | 11497.9 | 453904.13 | -442406.23 | 2022-10-01 | 2023-09-30 | 2022-01-24 | 01 | 2022-03-30 | 03
050.58047 | RES.2635.OAKHEIGHTSREPLACEMEN | Replace 1700' of 2" STL. damaged in tornado, install 1700' of 2" HDPE | 348.94 | 79336.27 | -78987.33 | -99.56% | 0.0105% | 6606.11 | 79336.27 | -72730.16 | 2022-10-01 | 2023-09-30 | 2022-01-24 | 01 | 2022-02-04 | 02
050.58057 | 050.2638.TORNADO-N9th-James | Install 625 feet of 2 inch poly main to restore gas service to 400 block of N. 9th and N. 8th plus the 200 block of W. James Street. We will retire 626 feet of pipe including 136 feet of 1 1/4 inch aldyl-A plastic and 120 feet of "Unknown" pipe. | 285.83 | 53913.74 | -53627.91 | -99.47% | 0.006574% | 4136.74 | 53913.74 | -49777 | 2022-10-01 | 2023-09-30 | 2022-01-17 | 01 | 2022-02-28 | 02
050.58101 | 050.2638-TORNADO-Cardinal Rd | This phase (9) includes replacing aldyl-A pipe along Cardinal Rd, Pritchard Rd, and the area where I-69 intersects with U.S Highway 45. We will also "reenergize"the 4 inch on Hwy 45 from Macedonia Rd north to Walnut St. Install 5,000 feet new main. | 501.74 | 291884.81 | -291383.07 | -99.83% | 0.01267% | 7974.18 | 291884.81 | -283910.63 | 2022-10-01 | 2023-09-30 | 2022-02-01 | 02 | 2022-03-30 | 03
050.58126 | 2638.Mayfield Tornado Meters | Meter purchases and retiremenets associated with Mayfield, KY tornado damage. | 28.58 | 162383.08 | -162354.5 | -99.98% | 0.0007815% | 491.74 | 162383.08 | -161891.34 | 2022-10-01 | 2023-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.58145 | RES.2635.FREDRICKRD | Install 1800' of 2" HDPE, to replace tornado damaged stl. | 659.27 | 149307.34 | -148648.07 | -99.56% | 0.01866% | 11739.37 | 149307.34 | -137567.97 | 2022-10-01 | 2023-09-30 | 2022-02-01 | 02 | 2022-03-18 | 03
050.58153 | 050.2638.TORNADO-7th-Broadway | This project is for improvements to our system in Mayfield in order to reinstate gas on the system. We propose to install app. 800 feet of 2 inch poly main, retire 70 feet of 2 inch steel which would have been isolated. | 282.51 | 56051.07 | -55768.56 | -99.5% | 0.006676% | 4200.91 | 56051.07 | -51850.16 | 2022-10-01 | 2023-09-30 | 2022-01-31 | 01 | 2022-02-28 | 02
050.58156 | RES.LUMBERST.MN.EXT | Replace 485' of 2" Stl., damaged in tornado with 485' of 2" HDPE | 442.89 | 100809.8 | -100366.91 | -99.56% | 0.01346% | 8469.76 | 100809.8 | -92340.04 | 2022-10-01 | 2023-09-30 | 2022-02-01 | 02 | 2022-02-08 | 02
050.58166 | PRP.2636.Bluff Ave | See project long description /notes | -138.85 | 661975.19 | -662114.04 | -100% | 1.046% | 658376.21 | 661975.19 | -3598.98 | 2022-10-01 | 2023-09-30 | 2022-02-01 | 02 | 2022-07-22 | 07
050.58167 | 050.2638.TORNADO-7-Wtr-Walnut | This phase of our Mayfield tornado restoration consists of installing app. 1,400 feet of 2 inch poly main from S 8th & Water down Water to S 7th, then south along S 7th to Walnut St. From there west toS. 8th and east to alley. Retire 760 feet of pipe | 335.52 | 90086.02 | -89750.5 | -99.63% | 0.008745% | 5502.38 | 90086.02 | -84583.64 | 2022-10-01 | 2023-09-30 | 2022-02-01 | 02 | 2022-04-30 | 04
050.58218 | RES.2635.EKEIGANST.TORNADO DA | Replace 1,000' of 2" Stl, tornado damaged, with 1,000' of 2" HDPE | 419.57 | 93747.23 | -93327.66 | -99.55% | 0.01245% | 7833.09 | 93747.23 | -85914.14 | 2022-10-01 | 2023-09-30 | 2022-03-01 | 03 | 2022-03-07 | 03
050.58222 | LP.2736.Phelps Ave. Replc. | Project replaces remaining LP in Hopkinsville Phelps Ave. There will be two Reg Station and 109 services replaced with this project. See long description. | 77486.3 | 1053715.78 | -976229.48 | -92.65% | 1.675% | 1054121.99 | 1053715.78 | 406.21 | 2022-10-01 | 2023-09-30 | 2022-02-01 | 02 | 2022-08-31 | 08
050.58227 | 050.2638.TORNADO-N 5th-Lee | Installing app. 800 feet of 2 inch poly main to serve app 12 customers. Retiring alike amount | 315.7 | 70372.17 | -70056.47 | -99.55% | 0.007395% | 4652.74 | 70372.17 | -65719.43 | 2022-10-01 | 2023-09-30 | 2022-02-14 | 02 | 2022-04-30 | 04
050.58288 | RES.2635.PINEST.TORNADOREPLAC | Replace 1400' of damaged 2" Stl., with 1400' of 2" HDPE | 285.42 | 63780.08 | -63494.66 | -99.55% | 0.00825% | 5190.92 | 63780.08 | -58589.16 | 2022-10-01 | 2023-09-30 | 2022-03-14 | 03 | 2022-03-21 | 03
050.58302 | INT.2738.Greensburg 2nd Feed | Replace outdated RS1473 and RS1777. Tie both 35lb systems together to have 2 feeds into main Greensburg system. | -83.43 | 242445.47 | -242528.9 | -100% | 0.3597% | 226328.95 | 242445.47 | -16116.52 | 2022-10-01 | 2023-09-30 | 2022-03-01 | 03 | 2022-08-31 | 08
050.58326 | PRP.2734.Avery Ct | See Project Long Description Notes | -191.03 | 330199.06 | -330390.09 | -100.1% | 0.5245% | 330008.03 | 330199.06 | -191.03 | 2022-10-01 | 2023-09-30 | 2022-04-01 | 04 | 2022-08-15 | 08
050.58328 | INT.2737.Harrodsburg Purchase | Rebuild outdated Harrodsburg Purchase RS1332 | 66515.27 | 796860.65 | -730345.38 | -91.65% | 1.231% | 774736.44 | 796860.65 | -22124.21 | 2022-10-01 | 2023-09-30 | 2022-03-01 | 03 | 2022-10-28 | 10
050.58336 | 050.2638.TORNADO-S9th-WBrdway | This project is to restore natural gas service to the 200 block of W Broadway incl. Carr's Barn & Carr's Steakhouse | 22.22 | 32545.95 | -32523.73 | -99.93% | 0.0007497% | 471.71 | 32545.95 | -32074.24 | 2022-10-01 | 2023-09-30 | 2022-03-01 | 03 | 2022-04-30 | 04
050.58349 | 2635DAWSINSPRINGTORNADORPL | Replace 5900' of tornado damaged Stl. with 5900' of 2" HDPE | 1822.83 | 394549.52 | -392726.69 | -99.54% | 0.0218% | 13718.35 | 394549.52 | -380831.17 | 2022-10-01 | 2023-09-30 | 2022-03-21 | 03 | 2022-06-30 | 06
050.58395 | RES.2637.E Commerce Ave Ext | Install 290 feet of 2 inch poly main to serve one residential customer at 180 E. Commere Ave. | -210.32 | 8000.91 | -8211.23 | -102.6% | 0.01875% | 11797.92 | 8000.91 | 3797.01 | 2022-10-01 | 2023-09-30 | 2022-03-09 | 03 | 2022-09-30 | 09
050.58399 | PRP.2635.S Jefferson | **** Revision Comments**** Original Estimate: $1,006,024.51 There were Multiple exposed creek crossings on this project that added an additional 3,492' of main replaced. | 278371.78 | 1143397.02 | -865025.24 | -75.65% | 1.901% | 1196449.44 | 1143397.02 | 53052.42 | 2022-10-01 | 2023-09-30 | 2022-04-04 | 04 | 2022-11-15 | 11
050.58437 | 2634.LP.W.Center St. | Replace 1188' of 2" Stl, 567' of 2" Plastic, 1565' of 3" Stl, 7521' of 4" Stl, 349' of 4" Plastic, 1585' of 6" Stl and 74' of 6" Plastic with 3,268' of 2" HDPE and 6,657' of 4" HDPE Retire RS1567, RS1568 | 409544.53 | 1276407.13 | -866862.6 | -67.91% | 2.576% | 1621075.85 | 1276407.13 | 344668.72 | 2022-10-01 | 2023-09-30 | 2022-04-01 | 04 | 2022-09-15 | 09
050.58444 | PRP.2737.Lancaster S_ | See project long description/notes | 10080.28 | 647102.65 | -637022.37 | -98.44% | 0.9763% | 614313.12 | 647102.65 | -32789.53 | 2022-10-01 | 2023-09-30 | 2022-04-10 | 04 | 2022-09-30 | 09
050.58473 | PRP.2737.Walnut St | See Project Long Description/Notes | 5254.08 | 675855.82 | -670601.74 | -99.22% | 0.977% | 614745.21 | 675855.82 | -61110.61 | 2022-10-01 | 2023-09-30 | 2022-05-01 | 05 | 2022-09-30 | 09
050.58516 | 050.2634.Center St. Services | Retire 225 service, replace with new services on Center St. project | 74656.44 | 794598.82 | -719942.38 | -90.6% | 0.981% | 617286.8 | 794598.82 | -177312.02 | 2022-10-01 | 2023-09-30 | 2022-05-01 | 05 | 2022-09-30 | 09
050.58529 | 050.2638.TORNADO - 12th-Depot | Install 200 ft of 2 inch poly main to replace existing main damaged during December 10th tornado | 26.69 | 15946.17 | -15919.48 | -99.83% | 0.0002629% | 165.39 | 15946.17 | -15780.78 | 2022-10-01 | 2023-09-30 | 2022-04-01 | 04 | 2022-05-30 | 05
050.58545 | NG.2734.Hunter Ct. Retire | Retire 1550 ft. of 4 inch HDPE Between Hunters Ct. and Peach Blossom Ct. Main is currently in a retention area that washes out. Main was originally ibstalled to feed Peach Blossom Ct. which is now being fed off Peachtree Ln. | 1301.02 | 1664.02 | -363 | -21.81% | 0.002068% | 1301.02 | 1664.02 | -363 | 2022-10-01 | 2023-09-30 | 2022-03-30 | 03 | 2022-04-29 | 04
050.58583 | COM.2736.JollyRanch.Cadiz | 850 ft. of 2 inch HDPE will serve 8 new commercial lots in Jolly Ranch Development located off Glenwood Mill Rd. in Cadiz KY. Main will tie in to existing 2" HDPE | -4.45 | 7193.01 | -7197.46 | -100.1% | 0.0101% | 6355.65 | 7193.01 | -837.36 | 2022-10-01 | 2023-09-30 | 2022-04-07 | 04 | 2022-05-31 | 05
050.58598 | 050.2637.Alabama St Retire | Retire 627 feet of 2 inch mill wrapped steel main due to leakage. Main was installed in 1957 | 3726.33 | 3853.15 | -126.82 | -3.291% | 0.006121% | 3851.56 | 3853.15 | -1.59 | 2022-10-01 | 2023-09-30 | 2022-04-11 | 04 | 2022-12-30 | 12
050.58625 | 050.2637.Charter Oak HPD MAIN | Installing new HDPE pipe in order to switch app. 20 farm tap regulator customers to the distribution main | 29184.91 | 313174.78 | -283989.87 | -90.68% | 0.5351% | 336717.13 | 313174.78 | 23542.35 | 2022-10-01 | 2023-09-30 | 2022-06-01 | 06 | 2022-08-31 | 08
050.58637 | PRP.2637.Myers St_ | See project Long Description/Notes | -15.34 | 372731.04 | -372746.38 | -100% | 0.5924% | 372715.7 | 372731.04 | -15.34 | 2022-10-01 | 2023-09-30 | 2022-05-15 | 05 | 2022-08-30 | 08
050.58640 | RES.2636.TAYLORMINERD.MN.EXT | Install 600' of 2" HDPE for new customers | -446.45 | 3964.18 | -4410.63 | -111.3% | 0.006971% | 4386.33 | 3964.18 | 422.15 | 2022-10-01 | 2023-09-30 | 2022-05-09 | 05 | 2022-09-30 | 09
050.58657 | IND.Owls Head Meterset | Project to move existing meterset at Oles Head due to expansion Meterset 5200.00, Spool Kit 1800.00, @#M Rotary meter, 6800.00, Mooney Regulators, 31,000.00. Compamy Labor for installition of Meter, Reg, | -718.4 | 129109.01 | -129827.41 | -100.6% | 0.204% | 128390.61 | 129109.01 | -718.4 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.58668 | PRP.2634.Robards Phase - 1 | See project long Description / notes | 1209.36 | 355760.13 | -354550.77 | -99.66% | 0.5283% | 332443.51 | 355760.13 | -23316.62 | 2022-10-01 | 2023-09-30 | 2022-05-05 | 05 | 2022-08-30 | 08
050.58693 | RES.2636.1000HWY136.MN.EXT | Install 800' of 2" HDPE for new customer | -558.7 | 20339.28 | -20897.98 | -102.7% | 0.002383% | 1499.18 | 20339.28 | -18840.1 | 2022-10-01 | 2023-09-30 | 2022-06-30 | 06 | 2022-09-30 | 09
050.58702 | RES.2637.Olivet Ch Rd Rev Ext | Install 200' - 2" poly main for one new residential customer (Mark Knecht) requesting service at 2245 Olivet Ch Rd. | 8024.69 | 6674.46 | 1350.23 | 20.23% | 0.008658% | 5447.87 | 6674.46 | -1226.59 | 2022-10-01 | 2023-09-30 | 2022-06-01 | 06 | 2022-09-15 | 09
050.58705 | COM.2637.Ky Oaks Mall Ext | Install 200 feet of 2 inch poly main for the new Auto Zone at 3021 New Holt Rd, this is the former Pier 1 site.. Tie-on behind Chuck E Cheese | -2.48 | 6537.27 | -6539.75 | -100% | 0.0117% | 7361.43 | 6537.27 | 824.16 | 2022-10-01 | 2023-09-30 | 2022-06-01 | 06 | 2022-07-30 | 07
050.58707 | PI.2734.31W State Hwy.Reloc. | Relocate 2230 ft. of 2 inch PR main along 31W at the transpark in conjunction with State Plan 03-8905.00. Addimg an additional 1000 ft. of 6 inch HDPE and Station to feed existing IP Feed in the Transpark . Project has 30% reimbursement by State Hwy | -79297.42 | 344780.72 | -424078.14 | -123% | 0.2281% | 143513.68 | 344780.72 | -201267.04 | 2022-10-01 | 2023-09-30 | 2022-04-27 | 04 | 2022-09-30 | 09
050.58810 | 2636.Highway 54 Relocatio_ | Replace approximately 6,00' of 2", 3", and 4" Pipe with 6" HDPE for Highway rRelocation project on 54 in Owensboro KY. 25 Services | -12179.58 | 1093089.94 | -1105269.52 | -101.1% | 1.153% | 725747.76 | 1093089.94 | -367342.18 | 2022-10-01 | 2023-09-30 | 2022-05-23 | 05 | 2022-10-30 | 10
050.58833 | LP.050.2736.Phelps LP Services | Project replaces115 services in conjunction with low oressure main replacement on Phelps Ave. in Hopkinsville. | -113.73 | 562081.47 | -562195.2 | -100% | 0.8933% | 562090.22 | 562081.47 | 8.75 | 2022-10-01 | 2023-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.58835 | Adyl.2635.Sunset Circle | See Project Long Description /Notes | 193.48 | 569512.7 | -569319.22 | -99.97% | 0.9054% | 569706.18 | 569512.7 | 193.48 | 2022-10-01 | 2023-09-30 | 2022-06-06 | 06 | 2022-09-30 | 09
050.58839 | PRP.2634.Robards Phase-2 | See project long description/notes | -66.26 | 267255.19 | -267321.45 | -100% | 0.3194% | 200964.06 | 267255.19 | -66291.13 | 2022-10-01 | 2023-09-30 | 2022-06-05 | 06 | 2022-09-08 | 09
050.58847 | RES.2636.HWY764N.MN.EXT | Install 380' of 2" HDPE for new customer | 2839.35 | 3806.84 | -967.49 | -25.41% | 0.006631% | 4172.3 | 3806.84 | 365.46 | 2022-10-01 | 2023-09-30 | 2022-06-13 | 06 | 2022-09-27 | 09
050.58868 | RES.2734.Lexington Place III | 1375 ft. of 2Inch HDPE will serve 19 new residential lots inLexington Place Subdivision -- Franklin , KY. Developer open and close ditchand install casings for main and services. | 2980.22 | 7279.12 | -4298.9 | -59.06% | 0.004736% | 2980.22 | 7279.12 | -4298.9 | 2022-10-01 | 2023-09-30 | 2022-05-27 | 05 | 2022-07-15 | 07
050.58943 | 050.2734.Office Furniture | Purchase Office furniture for Bowling Green Office | 9025.44 | 9029.37 | -3.93 | -0.04352% | 0.01434% | 9025.44 | 9029.37 | -3.93 | 2022-10-01 | 2023-09-30 | 2022-06-01 | 06 | 2023-01-31 | 01
050.58961 | PRP.2636.Oak Ave | See Project Long Description /Notes | 2358.09 | 313547.92 | -311189.83 | -99.25% | 0.4535% | 285371.7 | 313547.92 | -28176.22 | 2022-10-01 | 2023-09-30 | 2022-06-20 | 06 | 2022-09-30 | 09
050.58977 | PRP.2738.Sunny Hill Dr | See project Long Description/Notes | 75.21 | 149936.48 | -149861.27 | -99.95% | 0.2384% | 150011.69 | 149936.48 | 75.21 | 2022-10-01 | 2023-09-30 | 2022-07-22 | 07 | 2022-09-25 | 09
050.58996 | 050.2637.Iowa St Replacement | Install app. 550 feet of 2 inch poly main, retire 550 feet of 2 inch steel main (1959). McCracken County Road Department is making improvements. We have conflicts on Iowa St and Starr Hill Rd | 5.93 | 27365.49 | -27359.56 | -99.98% | 0.0381% | 23970.89 | 27365.49 | -3394.6 | 2022-10-01 | 2023-09-30 | 2022-07-01 | 07 | 2022-08-30 | 08
050.59069 | 050.2637.Friendship Replace | KYTC making improvements to N Friendship Rd from Lone Oak Rd to Blandville Rd | 9643.12 | 73851.34 | -64208.22 | -86.94% | 0.08474% | 53322.48 | 73851.34 | -20528.86 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-10-30 | 10
050.59082 | RES.2637.PrincessJennifer Ext | Install 200 feet of 2 inch poly main for two existing residential homes. One customer (Gil Arterburn) requesting new service at 435 Princess Jennifer Dr in Calvert City | -28.76 | 6474.88 | -6503.64 | -100.4% | 0.004812% | 3027.52 | 6474.88 | -3447.36 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59097 | RES.2637.Kenmar Rd Rev Ext | Install 225 feet of 2 inch poly, coming off 2 inch poly on Babbland Drive. One customer (Brandon Ladd)) requesting gas for new home at 715 Kenmar Rd | -11.49 | 5040.76 | -5052.25 | -100.2% | 0.004167% | 2621.66 | 5040.76 | -2419.1 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59101 | RES.2637.Paddock 2 Rev Ext | Install 1,215 feet of 2 inch poly main in this (second phase) of Paddock at the Oaks Subdivision. Extension makes gas available to three lots plus three tracts which may be divided. Developer is Chad Willett | -33.36 | 29756.93 | -29790.29 | -100.1% | 0.06124% | 38534.63 | 29756.93 | 8777.7 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59105 | COM.2636.KNOTTFARS-BERRYRD.MN | Install 800' of 4" HDPE for Chicken Farm | -152.22 | 17841.24 | -17993.46 | -100.9% | 0.02603% | 16379.47 | 17841.24 | -1461.77 | 2022-10-01 | 2023-09-30 | 2022-07-05 | 07 | 2022-08-30 | 08
050.59106 | 2634.SLOVERCREEKREPLACEMENT | Replace 2" Stl. Creek Crossing | 1237.81 | 76937.23 | -75699.42 | -98.39% | 0.1151% | 72424.45 | 76937.23 | -4512.78 | 2022-10-01 | 2023-09-30 | 2022-07-11 | 07 | 2022-09-29 | 09
050.59126 | 050.2637.S 25th St Replace | City making storm sewer omprovements. We need to replace app 400 ft. of 2" PE and 200 ft of 4" PE plus 4 or 5 services | 7318.78 | 116947.69 | -109628.91 | -93.74% | 0.1975% | 124266.47 | 116947.69 | 7318.78 | 2022-10-01 | 2023-09-30 | 2022-07-18 | 07 | 2022-08-30 | 08
050.59158 | COM.2636.ARBYS.MN.EXT | Install 1150' of 2" HDPE for new restaurant | -158.66 | 54875.01 | -55033.67 | -100.3% | 0.08696% | 54716.35 | 54875.01 | -158.66 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-08-22 | 08
050.59185 | 050.2638.I-69 at 45 Relocate | A & K Construction building a new Hucks Truck Stop at the intersection of I-69 and US Hwy 45 (Paducah Rd). There are conflicts with our existing 4-inch steel gas main. We will install 560 feet of 4-inch poly main and retire 550 feet of 4" steel. | -144.07 | 25233.38 | -25377.45 | -100.6% | 0.005743% | 3613.85 | 25233.38 | -21619.53 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59187 | INT.2737.US 27 Widening | Relocate 2000 ft of 2 In Main to elimate conflicts with US 27 Widening | -25195.5 | 162067.96 | -187263.46 | -115.5% | 0.2455% | 154486.39 | 162067.96 | -7581.57 | 2022-10-01 | 2023-09-30 | 2022-07-25 | 07 | 2022-09-30 | 09
050.59192 | Adyl.2635.Westend St | Replace 2621 ft of 2 Inch Adyl A with 2558 Ft of 2 Inch HDPE 13 services involved | 17201.1 | 373594.69 | -356393.59 | -95.4% | 0.4447% | 279816.97 | 373594.69 | -93777.72 | 2022-10-01 | 2023-09-30 | 2022-07-27 | 07 | 2022-09-30 | 09
050.59221 | COM.BAKERAVEUPGRADE | Replace 500' of 1" Stl. with 500' of 2" HDPE for Grain Dyer | -245.52 | 58782.49 | -59028.01 | -100.4% | 0.09303% | 58536.97 | 58782.49 | -245.52 | 2022-10-01 | 2023-09-30 | 2022-08-08 | 08 | 2022-08-22 | 08
050.59222 | 050.2638.Lazy Acres Retire | This site is the former mobile home park called Lazy Acres. It was built in 1981. Atmos installed 2 inch plastic gas mains in 1982. There are no more mobile homes today. Property has been purchased as commercial property. Retire 1,016 feet of 2 inch | -54.84 | 296.66 | -351.5 | -118.5% | 0.00255% | 1604.58 | 296.66 | 1307.92 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-09-30 | 09
050.59235 | COM.2734.Bale Commercial.Ext | 2500 ft. of 4 inchHDPE will serve new commercial development for Bale Blvd. located off Lovers Ln. and Middlebridge. Will tie in to existing 6 inch HDPE at Lovers Ln. and fiture round-about at Shive Ln. and Middlebridge. Bale Family Partnership will | 5074.37 | 68239.29 | -63164.92 | -92.56% | -0.06061% | -38136.06 | 68239.29 | -106375.35 | 2022-10-01 | 2023-09-30 | 2022-02-17 | 02 | 2022-09-29 | 09
050.59255 | 050.2637.Oak St Retirement | Retire app. 665 feet of 2 inch mill wrapped steel main from 1961. Main is insactive, we are there retiring services, no active services on this section of main | -59.92 | 121.59 | -181.51 | -149.3% | 0.002388% | 1502.56 | 121.59 | 1380.97 | 2022-10-01 | 2023-09-30 | 2022-08-01 | 08 | 2022-08-31 | 08
050.59278 | RES.2636.HWY279MN.EXT | Install 2000' of 2" HDPE for new customers | -8300 | 61134.57 | -69434.57 | -113.6% | 0.08397% | 52834.57 | 61134.57 | -8300 | 2022-10-01 | 2023-09-30 | 2022-09-01 | 09 | 2022-09-23 | 09
050.59377 | PRP.2734.Lost-River Cave | ****** Revision Comments ****** Original Estimate $ 617,953.80 Contractor estimate for contract labor to finish project was under estimated. | 897650.05 | 1181271.58 | -283621.53 | -24.01% | 1.662% | 1045723.92 | 1181271.58 | -135547.66 | 2022-10-01 | 2023-09-30 | 2022-08-31 | 08 | 2023-02-01 | 02
050.59405 | RES.2636.SCHIEDERTANNERLN.MN. | Install 800' of 2" HDPE for new customers | -462.14 | 8868.1 | -9330.24 | -105.2% | 0.01017% | 6398.77 | 8868.1 | -2469.33 | 2022-10-01 | 2023-09-30 | 2022-09-01 | 09 | 2022-09-23 | 09
050.59411 | RES.2636.FREESILVERRD.MN.EXT | Install 575' of 2" HDPE for 3 new customers | 2016.18 | 6822.4 | -4806.22 | -70.45% | 0.005626% | 3540.23 | 6822.4 | -3282.17 | 2022-10-01 | 2023-09-30 | 2022-09-02 | 09 | 2022-10-16 | 10
050.59412 | RES.2636.PLEASENTPOINTRD.MN.E | Install 265' of 2" HDPE for new customer | -216.05 | 2902.6 | -3118.65 | -107.4% | 0.005651% | 3555.85 | 2902.6 | 653.25 | 2022-10-01 | 2023-09-30 | 2022-09-05 | 09 | 2022-09-12 | 09
050.59449 | PRP.2737.Orchard St | *** Revision Comments **** Original estimate: $533,293.66 Hard surface repair exceeded original estimate. | 623972.01 | 625360.13 | -1388.12 | -0.222% | 0.9917% | 623972.01 | 625360.13 | -1388.12 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-04-08 | 04
050.59450 | PRP.2738.Covington Ave | Revision Comments: Original Estimate $740,326.82 An additional 2,154' of main was installed for tie backs and additional bare main found with restoration causing project to exceed original estimate. | 959307.76 | 740326.82 | 218980.94 | 29.58% | 1.525% | 959307.76 | 740326.82 | 218980.94 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-09-30 | 09
050.59492 | 050.2609. Equipment | Purchase bush hog 10'/storage ($17,000), 2 tandem utility trailers 14' ($6,000 each), and 3 digital crystal gauges 20000PSI ($1,600 each) | 42467.33 | 54231.89 | -11764.56 | -21.69% | 0.06749% | 42467.33 | 54231.89 | -11764.56 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-06-30 | 06
050.59495 | 050.2612 KMD Measurement | KY Prover replacement program and misc calibration equipment | 144991.9 | 233647.94 | -88656.04 | -37.94% | 0.2304% | 144991.9 | 233647.94 | -88656.04 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59498 | 050.2634. Equipment | Purchase 2-4" Williamson valves ($11,500 each), 3 Sensit golds ($1,500 each), 810 locator ($3,500), 2 Jamison insert tools ($1,100 each), Heath odorator 2 ($5,100), Mole/Hose kit ($4,500), and Scaper Kit Ritmo .5"-2" ($2,025) | 55355.19 | 69821.76 | -14466.57 | -20.72% | 0.08798% | 55355.19 | 69821.76 | -14466.57 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-07-30 | 07
050.59504 | 2636.KY298ROUNDABOUTUPGRADE | Replace 848' of 4" Stl., 189' of 2" Stl., with848' of 4" HDPE and 189' of 2" HDPE | 261073.4 | 275470.4 | -14397 | -5.226% | 0.4374% | 275239.23 | 275470.4 | -231.17 | 2022-10-01 | 2023-09-30 | 2022-09-15 | 09 | 2023-04-28 | 04
050.59511 | PRP.2737.East Main St | Revision Comments:Original estimate $805,191.16 This project was not the project we budgeted for due to State paving plans. The State made us go under the side walk and they were 5" wide and 8" to 12" thick. Restoration costs were well above our original | 1612461.36 | 805191.16 | 807270.2 | 100.3% | 2.563% | 1612461.36 | 805191.16 | 807270.2 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-09-30 | 09
050.59513 | PRP.2738.Mulberry St | Revision Comments:Original Estimate $715,180.55 An additional 2,320' of main was installes from original estimate due to additinal bare main found. There was 3740' of 6" Stl that was unable to be retired on the asbuilts no 6" to retire in this Tax Cod | 804010.79 | 715180.55 | 88830.24 | 12.42% | 1.278% | 804010.79 | 715180.55 | 88830.24 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-09-30 | 09
050.59524 | PRP.2637.Washington St | ******* Revision Comments ******* Original Estimate: $739,563.14 2,978' of additional main was installed and the 4" PE was changed to 6" PE from the original estimate.Concrete and asphalt exceeded original estimate | 1365593.2 | 1367930.03 | -2336.83 | -0.1708% | 2.173% | 1367571.93 | 1367930.03 | -358.1 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-03-27 | 03
050.59543 | 050.2635.Princeton Equipment | 2 Sensit golds ($1,500 each), 2 Ritmo Ef Peeler kit ($2,000 each), 2-810 Metrotech ($3,500 each), Milwaukee M18 cordless tool kit ($1,000), 2 Jamison tools ($1,000 each), Heath odorator 2 ($5,100), stop changer ($4,200), and Laser Leak Detector Gas Track | 45255.68 | 58980.33 | -13724.65 | -23.27% | 0.07192% | 45255.68 | 58980.33 | -13724.65 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-04-30 | 04
050.59546 | 050.2636.Equipment 2023 | Purchase of TDW Equipment ($97,000), MSA340 Fusion Box ($4,600), 8" PE Cutter ($1,500), 2 Ritmo Scraper Peeler Kit ($1,900 each), 6 VM810 Locators ($3,200 each), 5 Sensit Gold ($2,086 each), Smart Cal Station Greenville ($6,500), 2 Footage C400 2"-6" ($4 | 223942.47 | 248959.52 | -25017.05 | -10.05% | 0.3559% | 223942.47 | 248959.52 | -25017.05 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59565 | 050.2638.Misc Equipment | This project is set up to capture the costs of the FY '23 misc equipment budgeted for the Mayfield marea. Includes 2- Sensit Gold units ($4,400), a line locator ($3,800), and EF battery processor ($4,500) for a total of $12,700 | 12092.92 | 15708.63 | -3615.71 | -23.02% | 0.01922% | 12092.92 | 15708.63 | -3615.71 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2022-12-31 | 12
050.59566 | 050.2637.Misc Equipment | This project is to capture the costs of misc equpment budgeted to the Paducah area, includes one crystal guage, two EF processors, three Sensit Gold leak detectors, two line and marker ball locators, two UT gauges, and one 5' x 7' dump trailer | 47622.4 | 47991.72 | -369.32 | -0.7695% | 0.07569% | 47622.4 | 47991.72 | -369.32 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2022-12-31 | 12
050.59567 | PRP.2636.N Cherry Street | ******* Revision Comments ****** Original Estimate : $745,938.36 An addtional 2,970' of main was installed concrete and asphalt exceeded estimate. | 864865.61 | 866161 | -1295.39 | -0.1496% | 1.376% | 865689.8 | 866161 | -471.2 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-02-17 | 02
050.59651 | RES.2736.Hwwy181.Ext.Elkton | 1300 ft. of 2 inch HDPE will werve 4 new residential customers on Hwy 181 in Elkton. AIC = 3003.00 | 4511.17 | 14925.47 | -10414.3 | -69.78% | 0.01913% | 12038.12 | 14925.47 | -2887.35 | 2022-10-01 | 2023-09-30 | 2022-08-25 | 08 | 2022-09-30 | 09
050.59657 | 050.2609 St. Char. Dehy PH. 2 | Project to install 670 hp Dearing compressor, compressor building, dehy, filter/seperators, meter skids, regulation/control skids, MCC building, and all supporting equipment at the St. Charles Station in Dawson Springs, KY. | 1344346.13 | 2762868.98 | -1418522.85 | -51.34% | 2.137% | 1344346.13 | 2762868.98 | -1418522.85 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2025-02-28 | 02
050.59667 | Equipmt.2734.BG FY23 | Purchase 3 Vloc 3 Locators ($4,800 each). 2 Sensit G-2 Gold ($1,786 each), and 2 Track It 3 ($1,367 each) | 21463.31 | 25611.25 | -4147.94 | -16.2% | 0.03411% | 21463.31 | 25611.25 | -4147.94 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-05-31 | 05
050.59668 | Eqpmt.2735.FY23 | Routing for approval. Increase in cost of items since estimate was completed. Purchase Sensit Smartcal 360 desktop cal station ($5,650), 2 Vivax/Metrotech VM-810 line locators ($3,375 each), TDW 3x4 Shortstop plugging assembly ($21,000), Sensit Gas-Tr | 59495.45 | 57392.16 | 2103.29 | 3.665% | 0.09456% | 59495.45 | 57392.16 | 2103.29 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59669 | Eqpmt.2736.FY23 | Purchase LED Worklights , 15' stands for worksite ($1,600), Plasma Cutter for C&M shop ($4,500), Metrotech V-Loc Pro 3 w/ Omni locator ($5,700), Black Widow battery operated grease gun ($2,500), 2 Sensit Gold ($2,000 each), and Jameson Svc. Line locator | 21688.09 | 23872.17 | -2184.08 | -9.149% | 0.03447% | 21688.09 | 23872.17 | -2184.08 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-04-30 | 04
050.59699 | 2737.Misc.Equip.FY23 | Purchase Current Mapper for corrosion and shorts ($11,458), Laser Leak Detector ($11,565), Battery Operated Electrofusion Machine ($4,100), 2 Sensit Leak Detector ($1,786 each), and VM 810 Locactor ($3,140) | 43113 | 41850.51 | 1262.49 | 3.017% | 0.06852% | 43113 | 41850.51 | 1262.49 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-06-30 | 06
050.59700 | 2738.Misc.Equip.FY23 | Purchase Mainline Tracer 600' Jameson Tool ($2,321), No-Blo Valve Changer ($4,193), 3 VLOC3-Pro Locator W/MLA attachment ($5,995 each), LZ30 Gas Trac Leak Detector ($10,880), Squeeze Tool Remote 1/2"-2" ($1,552), and Crystal Gauge 0-300 lb ($2,101) | 48833.55 | 48278.69 | 554.86 | 1.149% | 0.07761% | 48833.55 | 48278.69 | 554.86 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59701 | 2739.Misc.Equip.FY23 | Purchase Ditch Witch hydrovac trailer fx20B ($30,000) and 2 FLASHLIGHT PELICAN 940 REMOTE AREA LIGHTING 3000 LUMS ($1,018 each) | 47803.56 | 48427.91 | -624.35 | -1.289% | 0.07597% | 47803.56 | 48427.91 | -624.35 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2024-01-30 | 01
050.59714 | NG.2734.Lovers Ln Relocation | Relocate approx. 500' due to new City street being built and new intersection at Lovers Lane | 11502.89 | 32297.84 | -20794.95 | -64.38% | 0.01828% | 11502.89 | 32297.84 | -20794.95 | 2022-10-01 | 2023-09-30 | 2022-09-28 | 09 | 2022-10-30 | 10
050.59722 | 050.2609.Kirkwood | Removing compressor station, replacing witrh new reg. stations and dehy, tying into storgae trunkline and High Pressure | 4580438.56 | 4044879.71 | 535558.85 | 13.24% | 8.67% | 5455224.91 | 4044879.71 | 1410345.2 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59727 | 050.2635 Building Upgrade | Replace floor in the office, upgrade bathrooms | 37911.73 | 35870.1 | 2041.63 | 5.692% | 0.06025% | 37911.73 | 35870.1 | 2041.63 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59744 | 050.2636.Water Meter | Resurface parking lot, upgrade water meter at the office | 1927.99 | 23748.48 | -21820.49 | -91.88% | 0.003064% | 1927.99 | 23748.48 | -21820.49 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59745 | 050.2736 Shop Addition | Add onto the shop at Hopkinsville whse | 87337.82 | 87337.82 | 0 | 0% | 0.1388% | 87337.82 | 87337.82 | 0 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59966 | RES.2738.Hwy 1157 | 370 Ft of 2 In HDPE Main to serve 1 new customer on KY-1157 | 10729.13 | 13996.68 | -3267.55 | -23.35% | 0.01705% | 10729.13 | 13996.68 | -3267.55 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2022-12-30 | 12
050.60011 | RES.2636.PEBBLEWOODDR.MN.EXT | Install 2500' of 2" HDPE for subdivision growth | 43284.83 | 40403.31 | 2881.52 | 7.132% | 0.06879% | 43284.83 | 40403.31 | 2881.52 | 2022-10-01 | 2023-09-30 | 2022-10-24 | 10 | 2022-11-04 | 11
050.60034 | PRP.2734.31W BG | Revision Comments: Original estimate $615, 595.31 Project exceeded estimate due to required depths that were made in rock for the State for pending HWY project on 31W. | 839192.69 | 615595.31 | 223597.38 | 36.32% | 1.334% | 839192.69 | 615595.31 | 223597.38 | 2022-10-01 | 2023-09-30 | 2022-10-21 | 10 | 2023-09-28 | 09
050.60040 | COM.2638.Commerce Ext-HP-IP | Convert existing 2 inch steel HPD (200# maop) to I.P (60# maop). Install new reg station, run 200' - 2" poly for one new commercial building (Auto repair). Remove existing farm tap regs. | 18818.84 | 17344.88 | 1473.96 | 8.498% | 0.02991% | 18818.84 | 17344.88 | 1473.96 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2022-12-30 | 12
050.60043 | RES.2734.CartersCrossing 4 | 4335 ftt. of 2 inch HDPE will serve 124 new residential lots in Phase 4 of Carters Crossing located off Cumberland tTrace Rd. Developer will open and close ditch and Install Casings for main and service lines | 18216.5 | 18825.32 | -608.82 | -3.234% | 0.02895% | 18216.5 | 18825.32 | -608.82 | 2022-10-01 | 2023-09-30 | 2022-10-19 | 10 | 2023-07-30 | 07
050.60046 | 050.2637.US Hwy 45 S Relocate | This property has been purchased by Hutson, Inc. They plan to build a new John Deere dealership at this location. There is a bank mthey will be cutting down. Our existing 4 inch steel gas main is on private property on this bank and is affected. | 437.37 | 61393.71 | -60956.34 | -99.29% | 0.0006951% | 437.37 | 61393.71 | -60956.34 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2023-02-28 | 02
050.60054 | INT.2737.Boyle Co High School | Relocate 450 Ft of 4 In HDPE to eliminate conflicts with baseball field | 2836.9 | 32495.95 | -29659.05 | -91.27% | 0.004509% | 2836.9 | 32495.95 | -29659.05 | 2022-10-01 | 2023-09-30 | 2022-10-03 | 10 | 2022-12-30 | 12
050.60076 | RES.2734.Lexington Pl P4 | Phase 4 - install approx 1900' of 2" PE - serve approx 24 new lots - developer to open and close ditch | 4699.75 | 12145.54 | -7445.79 | -61.3% | 0.007469% | 4699.75 | 12145.54 | -7445.79 | 2022-10-01 | 2023-09-30 | 2022-10-24 | 10 | 2022-11-30 | 11
050.60077 | RES.2637.Stonepoint 2 Rev Ext | Install 200 feet of 2 inch poly gas main for 2 new residential customers requesting natural gas. Donny Travis and David Freeman are the 2 customers. | 9316.87 | 9656.89 | -340.02 | -3.521% | 0.01481% | 9316.87 | 9656.89 | -340.02 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-01-30 | 01
050.60083 | 2736.19TH.ST.RELOCATE | Replace 225' of 4" HDPE for Bridge Replacement | 30708.38 | 29471.81 | 1236.57 | 4.196% | 0.0488% | 30708.38 | 29471.81 | 1236.57 | 2022-10-01 | 2023-09-30 | 2022-11-01 | 11 | 2022-11-15 | 11
050.60091 | IND.2734.Technology Way Exten | Extend 6" PE to serve new building in Transpark | 8915.91 | 33623.1 | -24707.19 | -73.48% | 0.01417% | 8915.91 | 33623.1 | -24707.19 | 2022-10-01 | 2023-09-30 | 2022-10-26 | 10 | 2022-12-31 | 12
050.60094 | RES.2638.Moonlight Dr Ext | Install 200 feet of 2 inch poly main to serve one existing residential customer and three vacant lots. | 8430.39 | 6351.86 | 2078.53 | 32.72% | 0.0134% | 8430.39 | 6351.86 | 2078.53 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2022-11-30 | 11
050.60095 | 2739.WMR_Endpoints.FY23 | Project to purchase, install, and program 3360 WMR Endpoints in Shelbyville, KY | 330031.79 | 319074.78 | 10957.01 | 3.434% | 0.5245% | 330031.79 | 319074.78 | 10957.01 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60099 | RES.2637.Richland Place Ext | Install 725 feet of 2 inch poly main to serve two duplex town homes. Builder is Nathan Hack. Subdivision is called Richland Place. | 11915.21 | 17229.17 | -5313.96 | -30.84% | 0.01894% | 11915.21 | 17229.17 | -5313.96 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-04-30 | 04
050.60100 | 050.3302.KY.LAPTOPS.FY23 | Purchase replacement laptops and monitors for Kentucky | 9321.1 | 19914.1 | -10593 | -53.19% | 0.01481% | 9321.1 | 19914.1 | -10593 | 2022-10-01 | 2023-09-30 | 2022-10-28 | 10 | 2023-07-30 | 07
050.60101 | 050.3302.KY.MDT.FY23 | Purchase replacement MDTs for Kentucky | 78720.27 | 83320.96 | -4600.69 | -5.522% | 0.1251% | 78720.27 | 83320.96 | -4600.69 | 2022-10-01 | 2023-09-30 | 2022-10-28 | 10 | 2023-07-30 | 07
050.60102 | 050.3302.KY.Routers.FY23 | Replace routers in local offices that are at end of life or are no longer supported for Kentucky | 20792 | 31196.29 | -10404.29 | -33.35% | 0.03304% | 20792 | 31196.29 | -10404.29 | 2022-10-01 | 2023-09-30 | 2022-10-28 | 10 | 2023-09-30 | 09
050.60119 | 2612.KY.Emerg. Regulators FY23 | Approval is needed to purchase 8 emergency regulators for KY. Cost center 2612 | 5566.84 | 30983 | -25416.16 | -82.03% | 0.008847% | 5566.84 | 30983 | -25416.16 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-10-30 | 10
050.60121 | 2612.KY.Corrector Repl. FY23 | Approval needed to replace 12 obsolete correctors in KY | 40465.89 | 43376.2 | -2910.31 | -6.709% | 0.06431% | 40465.89 | 43376.2 | -2910.31 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-05-30 | 05
050.60152 | RES.2734.South Glen Gables | Approx 4850' of 4" PE to serve 76 new lots | 59551.26 | 56961.87 | 2589.39 | 4.546% | 0.09464% | 59551.26 | 56961.87 | 2589.39 | 2022-10-01 | 2023-09-30 | 2022-11-15 | 11 | 2023-09-30 | 09
050.60154 | COM.2734.Charlie Ct | 500' of 2" PE to serve 4 new commercial lots | 2820.66 | 6107.12 | -3286.46 | -53.81% | 0.004483% | 2820.66 | 6107.12 | -3286.46 | 2022-10-01 | 2023-09-30 | 2022-11-08 | 11 | 2023-01-31 | 01
050.60158 | 050.2637.S 5th Replacement | Install 350 feet of 2 inch poly, retire app.90 feet of 3/4 inch steel main | 39925.08 | 34561.43 | 5363.65 | 15.52% | 0.06345% | 39925.08 | 34561.43 | 5363.65 | 2022-10-01 | 2023-09-30 | 2022-11-07 | 11 | 2022-12-30 | 12
050.60160 | RES.2734.WinstonLn.Frk | 500 ft.of 2 inch HDPE will serve one new customer on Winston Ln. in Franklin | -3672.77 | 8959.84 | -12632.61 | -141% | -0.005837% | -3672.77 | 8959.84 | -12632.61 | 2022-10-01 | 2023-09-30 | 2022-10-28 | 10 | 2023-02-28 | 02
050.60171 | RES.2738.Ashwood Dr | 60 Ft of 2 In HDPE to serve 1 new customer | 1040.19 | 1060.82 | -20.63 | -1.945% | 0.001653% | 1040.19 | 1060.82 | -20.63 | 2022-10-01 | 2023-09-30 | 2022-11-01 | 11 | 2022-12-31 | 12
050.60179 | 050.2637.Temple St Retire | Retire app. 600 feet of 2 inch M.W steel gas main (1962) on Temple and Bethel Streets. Houses were razed years ago. Property now owned by Southland Baptist Church. They plan on this becoming parking lot in the future | 1666.45 | 1666.45 | 0 | 0% | 0.002648% | 1666.45 | 1666.45 | 0 | 2022-10-01 | 2023-09-30 | 2022-09-01 | 09 | 2023-01-30 | 01
050.60180 | RES.2637.Olivet Place Rev Ext | Install 750 feet of 2 inch poly main to serve seven (duplex) townhomes for a total of 14 gas meters. Each unit will be over 4,000 sq. ft utilizing gas for on demand WH & heat | 21907.06 | 18868.42 | 3038.64 | 16.1% | 0.03482% | 21907.06 | 18868.42 | 3038.64 | 2022-10-01 | 2023-09-30 | 2022-10-15 | 10 | 2023-02-28 | 02
050.60183 | SINT.2734.BG Purchase 2 Repl | Previous Estimate of 2,003,630.63 Additional rock and fence revision due to customers request for privacy. Schedule lengthened and increase time for 3rd party inspection and Xray. Revised one station run to accomodate existing MAOP vs the original plan | 2074837.73 | 1808479.45 | 266358.28 | 14.73% | 3.298% | 2074837.73 | 1808479.45 | 266358.28 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60185 | COM.2638.B way S10th to S9th | Install app. 585 feet of 2 inch poly main Greer Neon Company as well as new businesses on West Broadway between S. 10th and S. 9th Streets | 24383.12 | 24571.54 | -188.42 | -0.7668% | 0.03875% | 24383.12 | 24571.54 | -188.42 | 2022-10-01 | 2023-09-30 | 2022-11-10 | 11 | 2022-12-30 | 12
050.60193 | INT.2738.Springfield Reinf | System reinforcement project to feed Altech | 109957.22 | 359070.92 | -249113.7 | -69.38% | 0.1748% | 109957.22 | 359070.92 | -249113.7 | 2022-10-01 | 2023-09-30 | 2022-12-01 | 12 | 2023-09-30 | 09
050.60208 | IND.2737.Southern Soul Spirit | System replacement and main extension to serve Southern Soul Distillery | 238106.44 | 252050.43 | -13943.99 | -5.532% | 0.3784% | 238106.44 | 252050.43 | -13943.99 | 2022-10-01 | 2023-09-30 | 2022-11-01 | 11 | 2023-03-31 | 03
050.60211 | COM.2638.N 12th St Main Ext | Install 330 feet of 2 inch poly main for Dexter Youngblood at 320 North 12th Street in Mayfield. This is a commercial business. | 5579.52 | 9434.6 | -3855.08 | -40.86% | 0.008867% | 5579.52 | 9434.6 | -3855.08 | 2022-10-01 | 2023-09-30 | 2022-11-01 | 11 | 2022-12-30 | 12
050.60232 | COM.2735.Southside Baptist Ch | 4" PE extension where customer is opening and closing ditch. Approximately 500' , Company crew will install pipe | 5542.86 | 4164.57 | 1378.29 | 33.1% | 0.008809% | 5542.86 | 4164.57 | 1378.29 | 2022-10-01 | 2023-09-30 | 2022-11-21 | 11 | 2023-01-31 | 01
050.60260 | COM.2637.Hansen Rd Rev Ext | Install 300 feet of 2 inch poly main for one new commercial customer. Creative Stiitches (Barry Wallace) requesting natural gas | 4840.54 | 8885.08 | -4044.54 | -45.52% | 0.007693% | 4840.54 | 8885.08 | -4044.54 | 2022-10-01 | 2023-09-30 | 2022-12-01 | 12 | 2023-01-30 | 01
050.60267 | 2737.Warehouse Upgrades | Budgeted project to replace 3 man doors and 3 overhead doors at the Danville Warehouse | 26210.37 | 26989.6 | -779.23 | -2.887% | 0.04166% | 26210.37 | 26989.6 | -779.23 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-12-30 | 12
050.60268 | COM.2738.New Columbia Rd | 800 Ft of 2 In HDPE to serve a new storage unit facility | -1031.74 | 3198.05 | -4229.79 | -132.3% | -0.00164% | -1031.74 | 3198.05 | -4229.79 | 2022-10-01 | 2023-09-30 | 2022-11-28 | 11 | 2022-12-30 | 12
050.60276 | IND.2734 Henderson Ind | Rerouting for Revision Approval. Project was set up under Company labor to install the pipe, instead Contract labor was needed to finish the project. 1744' of 4" Steel and 517 of 2" steel. Developer open/close ditch. Will serve 2 spec buildings in Hende | 244652.81 | 244615.14 | 37.67 | 0.0154% | 0.3888% | 244652.81 | 244615.14 | 37.67 | 2022-10-01 | 2023-09-30 | 2022-12-01 | 12 | 2023-07-30 | 07
050.60296 | 050.2736.Hopkinsville | Purchase land in Christian County, Hopkinsville | 9554.05 | 62566.8 | -53012.75 | -84.73% | 0.01518% | 9554.05 | 62566.8 | -53012.75 | 2022-10-01 | 2023-09-30 | 2022-11-18 | 11 | 2024-09-30 | 09
050.60309 | 050.2609.KirkWood Leak Det. | KirkWood Storage Station Leak Det. | 19172.6 | 124143.76 | -104971.16 | -84.56% | 0.03047% | 19172.6 | 124143.76 | -104971.16 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2024-04-30 | 04
050.60312 | 050.2634.Heater, Parking Lot | Purchase heater for shop, reseal parking lot at the Madisonville Office | 9544.77 | 63809.55 | -54264.78 | -85.04% | 0.01517% | 9544.77 | 63809.55 | -54264.78 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60313 | RES.2634.MILLSTONEWAYHANSON.M | Install 750' of 2" HDPE for Subdivision 42413 | 4983.26 | 7909.33 | -2926.07 | -37% | 0.00792% | 4983.26 | 7909.33 | -2926.07 | 2022-10-01 | 2023-09-30 | 2022-12-05 | 12 | 2023-01-31 | 01
050.60328 | PRP.2636.W Campbell St | ***** Revision Comments ***** Original Estimate $777,735.82 Asphalt and concrete exceeded original estimate. | 860058.55 | 862241.51 | -2182.96 | -0.2532% | 1.367% | 860058.55 | 862241.51 | -2182.96 | 2022-10-01 | 2023-09-30 | 2022-12-28 | 12 | 2023-04-28 | 04
050.60352 | RES.050.Clapp Rd Rev Ext | Install 5550 feet of 2 inch poly for one new home being built to replace home that was damaged by 2021 tornado. Due to the tonado we also had to retire app. 500 ft of 2 inch poly main. Because of these factors there is no charge for main extension | 17630.05 | 13296.04 | 4334.01 | 32.6% | 0.02802% | 17630.05 | 13296.04 | 4334.01 | 2022-10-01 | 2023-09-30 | 2022-12-01 | 12 | 2023-01-30 | 01
050.60353 | 050.2638.Copeland Ln Replace | Retire 579 feet of 1 inch steel main. Install 230 feet of 2 inch poly main along Copeland Lane. | 27440.66 | 26847.73 | 592.93 | 2.208% | 0.04361% | 27440.66 | 26847.73 | 592.93 | 2022-10-01 | 2023-09-30 | 2022-12-01 | 12 | 2023-02-28 | 02
050.60354 | 050.2638.Sedalia Rd Rev Ext | Install 200 feet of 2 inch poly main for two new residential customers (Steve Lamb) requesting gas service. | 2117.23 | 1586.19 | 531.04 | 33.48% | 0.003365% | 2117.23 | 1586.19 | 531.04 | 2022-10-01 | 2023-09-30 | 2022-12-01 | 12 | 2023-02-28 | 02
050.60365 | IND.2734.Tyson Foods | 3400' of 8" steel in the Transpark for Tyson Foods and will make service available to Envision. Chamber to open the ditch. Martin Contracting will install pipe, pad, and backfill. Company Inspection. The incorrect CB was chosen and corrected. | 874811.89 | 1300115.79 | -425303.9 | -32.71% | 1.39% | 874811.89 | 1300115.79 | -425303.9 | 2022-10-01 | 2023-09-30 | 2022-12-12 | 12 | 2023-05-31 | 05
050.60371 | 2637 - Parking Lot | Improvements to the parking lot at the Paducah office, 3510 Coleman Rd | 13596.52 | 13494.8 | 101.72 | 0.7538% | 0.02161% | 13596.52 | 13494.8 | 101.72 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60386 | COM.2736.GLENWOOD MILL.MN.EXT | Install 400' of 2" HDPE for new commercial businesses | 1211.21 | 4319.09 | -3107.88 | -71.96% | 0.001925% | 1211.21 | 4319.09 | -3107.88 | 2022-10-01 | 2023-09-30 | 2023-01-03 | 01 | 2023-01-12 | 01
050.60387 | RES.2736.FAIRWAYCTELKTONMN.EX | Install 1000' of 2" HDPE for new subdivision | 19782.18 | 20167.79 | -385.61 | -1.912% | 0.03144% | 19782.18 | 20167.79 | -385.61 | 2022-10-01 | 2023-09-30 | 2022-12-12 | 12 | 2023-02-28 | 02
050.60388 | COMM.2636.GATEWAYMALL.MN.EXT | Install 300' of 2" HDPE for Strip Mall | 1658.01 | 3242.65 | -1584.64 | -48.87% | 0.002635% | 1658.01 | 3242.65 | -1584.64 | 2022-10-01 | 2023-09-30 | 2022-12-14 | 12 | 2022-12-30 | 12
050.60389 | RES.2636.TULECREEKRD.MN.EXT | Install 2300' of 2" HDPE for new customers | -1429.89 | 23697.98 | -25127.87 | -106% | -0.002272% | -1429.89 | 23697.98 | -25127.87 | 2022-10-01 | 2023-09-30 | 2023-01-04 | 01 | 2023-02-28 | 02
050.60390 | RES.2636.KNOTTRD.MN.EXT | Install 1800' of 2" HDPE for new customers | 678.67 | 18539.89 | -17861.22 | -96.34% | 0.001079% | 678.67 | 18539.89 | -17861.22 | 2022-10-01 | 2023-09-30 | 2022-12-13 | 12 | 2023-02-28 | 02
050.60391 | RES.2636.ST.LAWRENCESPUR.MN.E | Install 500' of 2" HDPE for new customer | 3286.26 | 2192.36 | 1093.9 | 49.9% | 0.005223% | 3286.26 | 2192.36 | 1093.9 | 2022-10-01 | 2023-09-30 | 2023-01-04 | 01 | 2023-01-27 | 01
050.60408 | RES.2737.Ash Rd | 190 Ft of 2 In HDPE to serve 1 new customer | 80.93 | 2814.48 | -2733.55 | -97.12% | 0.0001286% | 80.93 | 2814.48 | -2733.55 | 2022-10-01 | 2023-09-30 | 2023-01-03 | 01 | 2023-02-25 | 02
050.60417 | Paris Rd Ground Bed | This project is to capture the costs associated with the replacement of our Paris Rd ground bed in Mayfield. Ground bed is nearly depleted. Replacement cannot wait until next fiscal year. | 61006.08 | 57580.21 | 3425.87 | 5.95% | 0.09696% | 61006.08 | 57580.21 | 3425.87 | 2022-10-01 | 2023-09-30 | 2022-12-15 | 12 | 2023-06-30 | 06
050.60491 | COM.2735.Rogers Rd Ext | Install approx. 315' of 2" PE to serve one new customer-Customer AIC | 690.06 | 2918.92 | -2228.86 | -76.36% | 0.001097% | 690.06 | 2918.92 | -2228.86 | 2022-10-01 | 2023-09-30 | 2023-01-07 | 01 | 2023-02-28 | 02
050.60525 | PRP.2635.Summit Dr | See Project Long Descrption/Notes | 243623.61 | 267820.28 | -24196.67 | -9.035% | 0.3872% | 243623.61 | 267820.28 | -24196.67 | 2022-10-01 | 2023-09-30 | 2023-01-20 | 01 | 2023-04-08 | 04
050.60529 | RES.2739.Winter Garden | 200 Ft of 2 In HDPE to serve 3 homes on Winter Garden in Lawrenceburg | 9990.14 | 9833.07 | 157.07 | 1.597% | 0.01588% | 9990.14 | 9833.07 | 157.07 | 2022-10-01 | 2023-09-30 | 2023-01-02 | 01 | 2023-01-27 | 01
050.60530 | RES.2739.Twin Lakes Section 3 | 2100 Ft of 2 In HDPE to serve Sections 3 and 4 of Twin Lakes Subdivision | 27850.7 | 52916.37 | -25065.67 | -47.37% | 0.04426% | 27850.7 | 52916.37 | -25065.67 | 2022-10-01 | 2023-09-30 | 2023-01-02 | 01 | 2023-03-31 | 03
050.60544 | FY23 KMD MEC Forfeitures | FY23 - Moving old MEC forfeiture for 040.12909 - $5,401.18 Needed this project due to assets being C040. Asset ID 17507824 - 1,050 4" Main | -5401.18 | 0 | -5401.18 |  | -0.008584% | -5401.18 | 0 | -5401.18 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-12-31 | 12
050.60576 | PRP.2637.Hilldale Rd | See Project Long Description/Notes | 409486.74 | 516181 | -106694.26 | -20.67% | 0.6508% | 409486.74 | 516181 | -106694.26 | 2022-10-01 | 2023-09-30 | 2023-01-20 | 01 | 2023-06-30 | 06
050.60580 | 2734.31WBristow Relocate | Relocate approximately 750' of 2" PE to resolve conflicts with US31W entrance improvements to Bristow Elementary. Includes to directional drills under US31W for 2 main crossings. Project is a non-reimbursable KYTC public improvement | 80181.66 | 69357.32 | 10824.34 | 15.61% | 0.1274% | 80181.66 | 69357.32 | 10824.34 | 2022-10-01 | 2023-09-30 | 2023-01-31 | 01 | 2023-04-30 | 04
050.60591 | 2734.Ashley Cir Relocate | Relocate approx. 360' of 4" PE and 20' of 2" PE to resolve conflicts with city widening project. Construction of a turning lane onto Scottsville Rd. Company labor will install | 4728.18 | 13532.8 | -8804.62 | -65.06% | 0.007514% | 4728.18 | 13532.8 | -8804.62 | 2022-10-01 | 2023-09-30 | 2023-01-23 | 01 | 2023-03-31 | 03
050.60596 | 2734.Cypress Way Replacement | Replace approximately 700' of 2" steel with 2" PE in conjunction with renovations of Greenwood High School. Unbudgeted replacement. The School Contractor will open ditch and Company labor will install pipe. | 3627 | 8460.67 | -4833.67 | -57.13% | 0.005764% | 3627 | 8460.67 | -4833.67 | 2022-10-01 | 2023-09-30 | 2023-01-30 | 01 | 2023-04-30 | 04
050.60616 | 050.2636.DeerValleyRein. | Install 1900' of 6" HDPE, 1300' of 4" HDPE, and a 2" regulator Station to provide 2nd feed into Deer Valley | 530763.17 | 562630.59 | -31867.42 | -5.664% | 0.8435% | 530763.17 | 562630.59 | -31867.42 | 2022-10-01 | 2023-09-30 | 2023-02-03 | 02 | 2023-06-30 | 06
050.60629 | RES.2637.Westhaven Dr Rev Ext | Install 350 feet of 2 inch poly main to serve three new residential customers requesting gas service. This also lets us put a two-way fee on this main. | 13920.9 | 11500.58 | 2420.32 | 21.05% | 0.02212% | 13920.9 | 11500.58 | 2420.32 | 2022-10-01 | 2023-09-30 | 2023-01-23 | 01 | 2023-02-28 | 02
050.60637 | 050.2636.Deer Valley Services | install 32 replacement services | 200059.43 | 196963.29 | 3096.14 | 1.572% | 0.318% | 200059.43 | 196963.29 | 3096.14 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-06-30 | 06
050.60641 | COM.2738.West Broadway | 150 Ft of 2 In HDPE to serve 1 new customer | 3148.46 | 1235.53 | 1912.93 | 154.8% | 0.005004% | 3148.46 | 1235.53 | 1912.93 | 2022-10-01 | 2023-09-30 | 2023-02-06 | 02 | 2023-03-28 | 03
050.60648 | 2651.WMR Transceiver Upgr.FY23 | Replace/upgrade 9 WMR transceivers for Kentucky ((2 in Owensboro, Calhoun, Hardinsburgh, Fordsville, Hartford, Hawesville, Madisonville and Calvert City) | 96120.13 | 99370.8 | -3250.67 | -3.271% | 0.1528% | 96120.13 | 99370.8 | -3250.67 | 2022-10-01 | 2023-09-30 | 2023-01-25 | 01 | 2023-09-30 | 09
050.60707 | RES.2739.Robin Place Ph 2 | 900 Ft of 2 In HDPE to serve 11 lots on Phase 2 of Robin Place | 21662.08 | 19666.55 | 1995.53 | 10.15% | 0.03443% | 21662.08 | 19666.55 | 1995.53 | 2022-10-01 | 2023-09-30 | 2023-02-06 | 02 | 2023-03-31 | 03
050.60785 | RES.2734.Dove Point Phase 2 | 1000' 4" PE to serve 22 additional lots in Dove Point. Developer to open and close ditch, Company labor to install pipe. | 9323.8 | 11843.17 | -2519.37 | -21.27% | 0.01482% | 9323.8 | 11843.17 | -2519.37 | 2022-10-01 | 2023-09-30 | 2023-02-21 | 02 | 2023-04-30 | 04
050.60816 | PRP.2634.Boggess Blvd | See Project Long Description /Notes | 569688.96 | 528855.76 | 40833.2 | 7.721% | 0.9054% | 569688.96 | 528855.76 | 40833.2 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-07-15 | 07
050.60817 | IND.2737.Luca Mariano | 3000 Ft of 6 In HDPE to serve Luca Mariano Distillery in Danville | -16758.45 | 237535.41 | -254293.86 | -107.1% | -0.02663% | -16758.45 | 237535.41 | -254293.86 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-05-31 | 05
050.60825 | 050.2636.Bevier Field | Repair leaks, remove above ground facilities, Install 500' of 6" Stl. | 277284.43 | 162300.83 | 114983.6 | 70.85% | 0.4407% | 277284.43 | 162300.83 | 114983.6 | 2022-10-01 | 2023-09-30 | 2023-04-01 | 04 | 2023-09-30 | 09
050.60831 | RES. 2634.GREYSTONE | Install 1100' of 2" HDPE for new subdivision | 17085.48 | 11588.19 | 5497.29 | 47.44% | 0.02715% | 17085.48 | 11588.19 | 5497.29 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-03-31 | 03
050.60834 | 050.2636.Downs Food Group | Install 4" Meter/Reg. Station, Install 120' of 2" Stl. | 222005.13 | 243758.24 | -21753.11 | -8.924% | 0.3528% | 222005.13 | 243758.24 | -21753.11 | 2022-10-01 | 2023-09-30 | 2023-04-15 | 04 | 2023-08-31 | 08
050.60836 | RES.2637.Paddock Phase 3 | Install 1,020 feet of 2 inch poly main to serve 15 new residential lots in this third phase of the Paddock at the Oaks subdivision by Chad Willett. | 7698.93 | 24241.83 | -16542.9 | -68.24% | 0.01224% | 7698.93 | 24241.83 | -16542.9 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-05-28 | 05
050.60858 | RES.2638.Terryaire Dr Ext | Install 300 feet of 2 inch poly main for one new residential customer (Laura Cook) requesting gas at 192 Teryaire Drive | 6638.13 | 8589.06 | -1950.93 | -22.71% | 0.01055% | 6638.13 | 8589.06 | -1950.93 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-03-31 | 03
050.60867 | RES.2737.W Kentucky Ave | 315 Ft of 2 In HDPE to serve 1 new customer | 493.22 | 3043.99 | -2550.77 | -83.8% | 0.0007839% | 493.22 | 3043.99 | -2550.77 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-04-28 | 04
050.60872 | RES.2635.ELAINEDR.MN.EXT | Install 275' of 2" HDPE for new customer | -78.38 | 1648.61 | -1726.99 | -104.8% | -0.0001246% | -78.38 | 1648.61 | -1726.99 | 2022-10-01 | 2023-09-30 | 2023-04-01 | 04 | 2023-04-30 | 04
050.60877 | RES.ST.LAWRENCERD.MN.EXT | Install 800' of 2" HDPE for new customer | 4640.31 | 8476.98 | -3836.67 | -45.26% | 0.007375% | 4640.31 | 8476.98 | -3836.67 | 2022-10-01 | 2023-09-30 | 2023-03-06 | 03 | 2023-03-31 | 03
050.60878 | RES.2634.LAKEWOODDR.MN.EXT | Instal 820' of 2" HDPE for new subdivision | 10177.79 | 19603.27 | -9425.48 | -48.08% | 0.01618% | 10177.79 | 19603.27 | -9425.48 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-04-28 | 04
050.60923 | 2636.Wendall Ford Station | Replace Station and reroute 2" stl. | 9467.9 | 24291.34 | -14823.44 | -61.02% | 0.01505% | 9467.9 | 24291.34 | -14823.44 | 2022-10-01 | 2023-09-30 | 2023-03-09 | 03 | 2023-04-30 | 04
050.60924 | RES.2736.EASTRUTH | Install 525' of 2" HDPE for 6 new customers | 6049.2 | 5672.87 | 376.33 | 6.634% | 0.009614% | 6049.2 | 5672.87 | 376.33 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-04-27 | 04
050.60959 | RES.2636.THE PRESERVE | Install 4250' of 4" HDPE, Install 2000' of 2" HDPE for new subdivision | 211120.61 | 69023.07 | 142097.54 | 205.9% | 0.3355% | 211120.61 | 69023.07 | 142097.54 | 2022-10-01 | 2023-09-30 | 2023-03-01 | 03 | 2023-06-15 | 06
050.60972 | COM.2734.KPCustoms.Ext | Install approx 350' of 2" PE for 4 new commercial customers. Main will be installed in private easement. | 1131.96 | 5117.98 | -3986.02 | -77.88% | 0.001799% | 1131.96 | 5117.98 | -3986.02 | 2022-10-01 | 2023-09-30 | 2023-03-20 | 03 | 2023-05-31 | 05
050.61007 | RES.2738.Blackberry Lane | 700 Ft of 2 In HDPE to serve 2 customers on Blackberry Lane | 15440.25 | 15361.92 | 78.33 | 0.5099% | 0.02454% | 15440.25 | 15361.92 | 78.33 | 2022-10-01 | 2023-09-30 | 2023-03-20 | 03 | 2023-08-31 | 08
050.61020 | 050.2636.Greenville Rectifier | Replace damaged rectifier in Greenville | 6402.32 | 7446.15 | -1043.83 | -14.02% | 0.01018% | 6402.32 | 7446.15 | -1043.83 | 2022-10-01 | 2023-09-30 | 2023-04-01 | 04 | 2023-06-30 | 06
050.61029 | RES.2636.KINGRD.MN.EXT | Install 1350' for new subdivision | 6408.03 | 13984.63 | -7576.6 | -54.18% | 0.01018% | 6408.03 | 13984.63 | -7576.6 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-05-31 | 05
050.61030 | RES.2636.BOSTONRD.MN.EXT | Install 275' of 2: HDPE for new customer | 1549.86 | 2900.89 | -1351.03 | -46.57% | 0.002463% | 1549.86 | 2900.89 | -1351.03 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-04-28 | 04
050.61034 | IND.2737.Southern Soul Meter | 4 Inch Transport Meterset to serve Southern Soul Distillery in Lancaster KY | 64877.21 | 102286.29 | -37409.08 | -36.57% | 0.1031% | 64877.21 | 102286.29 | -37409.08 | 2022-10-01 | 2023-09-30 | 2023-04-01 | 04 | 2023-08-31 | 08
050.61043 | IND.2739.Weiland Meter | 4 Inch Transport Meterset to serve Weiland in Shelbyville KY | 89265.18 | 125042.23 | -35777.05 | -28.61% | 0.1419% | 89265.18 | 125042.23 | -35777.05 | 2022-10-01 | 2023-09-30 | 2023-04-01 | 04 | 2023-08-16 | 08
050.61044 | 050.2637.Minnich Ave Sys Imp | Install 300 feet of 2 inch poly main along Minnich Ave to coonect Minnich to Friedman Lane gas main creating a two-way feef. Retire leaking 4 inch valve at Friedman & Pines Rd. Install new 4 inch poly valve | 18960.57 | 17313.38 | 1647.19 | 9.514% | 0.03013% | 18960.57 | 17313.38 | 1647.19 | 2022-10-01 | 2023-09-30 | 2023-04-01 | 04 | 2023-05-28 | 05
050.61060 | PRP.2637.Sunset Ave | See Project Long Description/Notes | 472638.35 | 747260.79 | -274622.44 | -36.75% | 0.7512% | 472638.35 | 747260.79 | -274622.44 | 2022-10-01 | 2023-09-30 | 2023-04-04 | 04 | 2023-07-31 | 07
050.61063 | RES.2637.Oakview Estates Ext | Install 2,600 feet of 2 inch poly main to serve 29 new residential lots in Oakview Estates Subd. being developed by Chris "Potsy" Potter.. This is phase 1 of 2 | 30424.7 | 26850.1 | 3574.6 | 13.31% | 0.04835% | 30424.7 | 26850.1 | 3574.6 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-06-30 | 06
050.61088 | 2609.Kimbel 3 Casing Replace. | Replace casing top joint on Kimbel #3 Well at St. Charles Storage Field - | 457912.52 | 464772.12 | -6859.6 | -1.476% | 0.7278% | 457912.52 | 464772.12 | -6859.6 | 2022-10-01 | 2023-09-30 | 2023-04-15 | 04 | 2023-09-29 | 09
050.61096 | PRP.2636.Oak St | See Project Long Description /Notes | 477045.75 | 607223.73 | -130177.98 | -21.44% | 0.7582% | 477045.75 | 607223.73 | -130177.98 | 2022-10-01 | 2023-09-30 | 2023-04-11 | 04 | 2023-07-31 | 07
050.61097 | PRP.2737.Helm St | Revision Comments: Original estimate: $ 683,579.72 This was not the project we budgeted for due to State paving plans. Concrete and Asphalt costs exceeded what was bugted for the original project. The State made us run under the sidewalk. | 856832.12 | 683579.72 | 173252.4 | 25.34% | 1.362% | 856832.12 | 683579.72 | 173252.4 | 2022-10-01 | 2023-09-30 | 2023-04-11 | 04 | 2023-09-30 | 09
050.61115 | RES.2637.Guess Court Ext | Install 960 feet of 2 inch poly main to serve twelve duplex town homes or a total of 24 meters. Develper is Donny Travis of D & D Development. | 8922.8 | 15161.48 | -6238.68 | -41.15% | 0.01418% | 8922.8 | 15161.48 | -6238.68 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-06-30 | 06
050.61141 | RES.2734.Adairv.227BurrAlley | Extend approx. 115' of 1.25 PE to serve one residential customer | 2720.27 | 1185.16 | 1535.11 | 129.5% | 0.004323% | 2720.27 | 1185.16 | 1535.11 | 2022-10-01 | 2023-09-30 | 2023-04-17 | 04 | 2023-05-31 | 05
050.61142 | 2735.HorseCaveBypass | Relocate 650 feet of 4 inch HDPE for new bypass | 46902.7 | 41911.24 | 4991.46 | 11.91% | 0.07454% | 46902.7 | 41911.24 | 4991.46 | 2022-10-01 | 2023-09-30 | 2023-05-01 | 05 | 2023-08-31 | 08
050.61154 | RES.2734.SouthParkCommonsPH1 | 103 lots in South Park Commons Phase 1. Install 800' 6" PE, 5,484' 4" PE, and 2,784' 2" PE. Devloper to open and close ditch. Company labor to install pipe. | 100221.55 | 91626.05 | 8595.5 | 9.381% | 0.1593% | 100221.55 | 91626.05 | 8595.5 | 2022-10-01 | 2023-09-30 | 2023-04-17 | 04 | 2023-09-30 | 09
050.61164 | IND.2734.LoganAlum.Meter Repl | Replacement of Logan Al Meter/Reg set. Includes Reg-Meterset, Heater, Filter/Sep, and all electronics needed. First Cut will be the contractor, Contract Insp utilized. DUE TO UNKNOWNS ON HOW LOGAN WILL REIMBURSE, SUBJECT TO REVISION | -242876.88 | 2406761.29 | -2649638.17 | -110.1% | -0.386% | -242876.88 | 2406761.29 | -2649638.17 | 2022-10-01 | 2023-09-30 | 2023-03-02 | 03 | 2024-01-17 | 01
050.61165 | COM.2739.Williamsburg Drive | 400 Ft of 2 In HDPE | -290.11 | 1356.29 | -1646.4 | -121.4% | -0.0004611% | -290.11 | 1356.29 | -1646.4 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-05-27 | 05
050.61251 | COM.2637.John Puryear Dr Ext | Install 885 feet of 2 inch poly gas main to serve a new commercial development being built by Dean Owen, CPA. Two buildings under construction currently including a new office bldg and a new storage bldg. | 7200.26 | 20357.81 | -13157.55 | -64.63% | 0.01144% | 7200.26 | 20357.81 | -13157.55 | 2022-10-01 | 2023-09-30 | 2023-05-01 | 05 | 2023-07-30 | 07
050.61264 | RES.2739.Ardmore Ph 5 | 2800 Ft of 2 In HDPE to serve Phase 5 of Ardmore Crossings | 73628.56 | 73665.25 | -36.69 | -0.04981% | 0.117% | 73628.56 | 73665.25 | -36.69 | 2022-10-01 | 2023-09-30 | 2023-04-03 | 04 | 2023-05-26 | 05
050.61295 | IND.2739.Meggitt Meter | 4 Inch Transport Meterset to serve Meggitt in Danville KY | 92654.4 | 100211.42 | -7557.02 | -7.541% | 0.1473% | 92654.4 | 100211.42 | -7557.02 | 2022-10-01 | 2023-09-30 | 2023-05-01 | 05 | 2023-08-31 | 08
050.61301 | COM.2734.BG.560 Waterbury Ct. | Install app. 700' of 2" HDPE to serve one commercial customer. AIC provided from customer per tariff | -2885.29 | 5672.78 | -8558.07 | -150.9% | -0.004586% | -2885.29 | 5672.78 | -8558.07 | 2022-10-01 | 2023-09-30 | 2023-04-24 | 04 | 2023-08-31 | 08
050.61335 | RES.2636.DARWINGEORGEST.MN.EX | Install 400' of 2" HDPE for 2 new customers | 1090.25 | 4242.29 | -3152.04 | -74.3% | 0.001733% | 1090.25 | 4242.29 | -3152.04 | 2022-10-01 | 2023-09-30 | 2023-06-01 | 06 | 2023-06-30 | 06
050.61367 | 2734.KYTC.KY 1008 Relocation | Replace approx. 650' of 4" PE and 120' of 2" PE to resolve conflicts in KYTC project 3-80106 in Franklin KY. Contract labor will be used to complete the work. | 18847.94 | 175807.51 | -156959.57 | -89.28% | 0.02995% | 18847.94 | 175807.51 | -156959.57 | 2022-10-01 | 2023-09-30 | 2023-05-22 | 05 | 2024-05-30 | 05
050.61375 | IND.2734.EnvisionP1.Transpark | Install approx 3500' of 8" steel for new EV Battery plant, Envision Phase 1, in Transpark. Pipe will be installed in public utility easement with drive access provided by Envision outside of any secured fencing to meterset. | 566859.3 | 1111263.76 | -544404.46 | -48.99% | 0.9009% | 566859.3 | 1111263.76 | -544404.46 | 2022-10-01 | 2023-09-30 | 2023-03-27 | 03 | 2023-09-30 | 09
050.61391 | RES.2634.CONTINENTALDR.MN.EXT | Install 200' of 2" HDPE for new customer | 978.46 | 2109.53 | -1131.07 | -53.62% | 0.001555% | 978.46 | 2109.53 | -1131.07 | 2022-10-01 | 2023-09-30 | 2023-05-24 | 05 | 2023-05-31 | 05
050.61402 | 2734.Ashley Cir Roundabout | Routing for revision due to needing to bore more than anticipated for the relcoation and needing to replace more 2" than anticipated to eliminate a section of isloated steel. Relocate approximately 500' of 2" Steel and 2" PE to resolve conflicts with th | 88321.59 | 90351.77 | -2030.18 | -2.247% | 0.1404% | 88321.59 | 90351.77 | -2030.18 | 2022-10-01 | 2023-09-30 | 2023-05-26 | 05 | 2023-08-31 | 08
050.61404 | COMM.2736LACYLN.MN.EXT | Install 250 of 2" HDPE for Main ext. for exis | 1264.66 | 2610.72 | -1346.06 | -51.56% | 0.00201% | 1264.66 | 2610.72 | -1346.06 | 2022-10-01 | 2023-09-30 | 2023-05-25 | 05 | 2023-06-15 | 06
050.61415 | PRP.2636.W. Depot St | See Project Long Description/Notes | 122008.45 | 173404.25 | -51395.8 | -29.64% | 0.1939% | 122008.45 | 173404.25 | -51395.8 | 2022-10-01 | 2023-09-30 | 2023-06-15 | 06 | 2023-07-30 | 07
050.61417 | COMM.2736.1600N.MN.ST.MN.EXT | Install 350' of 2" HDPE for customer growth | -1170.29 | 2526.66 | -3696.95 | -146.3% | -0.00186% | -1170.29 | 2526.66 | -3696.95 | 2022-10-01 | 2023-09-30 | 2023-06-01 | 06 | 2023-06-30 | 06
050.61429 | Comm.2634.Madisonville Sports | Install 2500' of 4" HDPE for Sports Complex | 20789.67 | 31390.02 | -10600.35 | -33.77% | 0.03304% | 20789.67 | 31390.02 | -10600.35 | 2022-10-01 | 2023-09-30 | 2023-06-01 | 06 | 2023-06-30 | 06
050.61435 | 2734.BG Repave/Reseed Lot | Repave existing parking lot next to BG office. Reseed and straw rest of exisiting parking lot to repair and dispose of old asphalt. | 125869.16 | 97000 | 28869.16 | 29.76% | 0.2% | 125869.16 | 97000 | 28869.16 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.61470 | PRP.2636.Maple Dr | See Project Long Description / Notes | 205367.03 | 236218.87 | -30851.84 | -13.06% | 0.3264% | 205367.03 | 236218.87 | -30851.84 | 2022-10-01 | 2023-09-30 | 2023-06-29 | 06 | 2023-09-30 | 09
050.61471 | RES.2736.11830S.MADISONVILLER | Install 250' of 2" HDPE for new customer | -437.2 | 2625.91 | -3063.11 | -116.6% | -0.0006948% | -437.2 | 2625.91 | -3063.11 | 2022-10-01 | 2023-09-30 | 2023-06-12 | 06 | 2023-08-31 | 08
050.61501 | Adyl.2635.St Charles | See Project Long Description/Notes | 704082.16 | 1189088.55 | -485006.39 | -40.79% | 1.119% | 704082.16 | 1189088.55 | -485006.39 | 2022-10-01 | 2023-09-30 | 2023-06-12 | 06 | 2023-09-30 | 09
050.61502 | PRP.2637.Lone Oak Rd | See Project LOng Description /Notes | 722858.48 | 736283.08 | -13424.6 | -1.823% | 1.149% | 722858.48 | 736283.08 | -13424.6 | 2022-10-01 | 2023-09-30 | 2023-06-30 | 06 | 2023-09-30 | 09
050.61509 | 050.2634.Poole Purchase | Replace Poole Purchase, 60' of 2" Stl., 1 - 2" Reg. Station, 1 - 2" Meter Station, 1 - Odorizor | 115498.29 | 156850.7 | -41352.41 | -26.36% | 0.1836% | 115498.29 | 156850.7 | -41352.41 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.61529 | 050.2637.US 45 at Goad Retire | Property owner creating a small pond. We have a small amount of 1 1/4 inch steel main affected plus one gas service. We propose to abandon 210 feet of 1 1/4 inch. We will relocate two gas services and retire one gas service. Pond owner tearing down t | 946.33 | 754.36 | 191.97 | 25.45% | 0.001504% | 946.33 | 754.36 | 191.97 | 2022-10-01 | 2023-09-30 | 2023-06-26 | 06 | 2023-07-30 | 07
050.61531 | PRP-Aldyl-A.2635.Princeton Svc | PRP-Aldyl-A.2635.Princeton Services | 274289.04 | 0 |  |  | 0.4359% | 274289.04 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2023-06-21 | 06 | 2025-09-30 | 09
050.61532 | PRP-Aldyl-A.2736.Hopkins Svc | PRP-Aldyl-A.2736.Hopkinsville Services | 619174.56 | 0 |  |  | 0.984% | 619174.56 | Non Budgeted |  | 2022-10-01 | 2023-09-30 | 2023-06-21 | 06 | 2025-09-30 | 09
050.61556 | Adyl.2736.Cunningham Ave | See Project Long Description / Notes | 315853.72 | 505134.17 | -189280.45 | -37.47% | 0.502% | 315853.72 | 505134.17 | -189280.45 | 2022-10-01 | 2023-09-30 | 2023-06-30 | 06 | 2023-09-30 | 09
050.61557 | Adyl.2736.Lincoln Ave | ***** 2023 Adyl ***** Replace 617'1.25" Adyl A, 6' of 3" Steel, 99' of 2" PE, 1,002' of 1" Adyl A, 1,531' of 2" PE, 3,386' of 2" Adyl A with 7,008' of 2" HDPE. | 464944.54 | 729347.34 | -264402.8 | -36.25% | 0.7389% | 464944.54 | 729347.34 | -264402.8 | 2022-10-01 | 2023-09-30 | 2023-06-24 | 06 | 2023-09-30 | 09
050.61567 | 2738.KY Cooperage Tunnel Relo | Sending revision for approval due to footage being slightly more than anticipated. Lowering 120' of 4" to accomodate tunnel crossing under HWY 68. Martin contracting will be completing the work under existing MSA rates. | 3790.84 | 27521.87 | -23731.03 | -86.23% | 0.006025% | 3790.84 | 27521.87 | -23731.03 | 2022-10-01 | 2023-09-30 | 2023-06-28 | 06 | 2023-08-31 | 08
050.61593 | 050.2637.Forest Ave Sys Imp | One service feeding three homes. We propose to install 100 feet of 2 inch poly main. We will then install three separate services. | 8668.51 | 4289.53 | 4378.98 | 102.1% | 0.01378% | 8668.51 | 4289.53 | 4378.98 | 2022-10-01 | 2023-09-30 | 2023-07-03 | 07 | 2023-07-31 | 07
050.61594 | RES.2634EASTMORTON.MN.EXT | Install 270' of 2" HDPE, ret. 612' of 2" Stl | 6916.47 | 3243.66 | 3672.81 | 113.2% | 0.01099% | 6916.47 | 3243.66 | 3672.81 | 2022-10-01 | 2023-09-30 | 2023-08-01 | 08 | 2023-08-30 | 08
050.61599 | RES.2634.UNIVERSITYCIRCLE.MN. | Install 300' of 2" HDPE for new customers | 2491.12 | 4808.82 | -2317.7 | -48.2% | 0.003959% | 2491.12 | 4808.82 | -2317.7 | 2022-10-01 | 2023-09-30 | 2023-07-03 | 07 | 2023-09-30 | 09
050.61629 | RES.2637.Nace Ln Rev Ext | Install 300 feet of 2 inch poly gas main for three new residential duplexes being built by Mark Hicks. 6 meters in total. | 11952.96 | 8447.86 | 3505.1 | 41.49% | 0.019% | 11952.96 | 8447.86 | 3505.1 | 2022-10-01 | 2023-09-30 | 2023-07-10 | 07 | 2023-09-30 | 09
050.61639 | RES.2636.HEATHERSTONEAPPROCH. | Install 2300' of 4" HDPE approch main for new subdivision | 62166.58 | 41916.65 | 20249.93 | 48.31% | 0.0988% | 62166.58 | 41916.65 | 20249.93 | 2022-10-01 | 2023-09-30 | 2023-07-10 | 07 | 2023-09-30 | 09
050.61645 | 2739.Blacktop Reseal | Reseal parking lot at Shelbyville office | 15287.81 | 14721.6 | 566.21 | 3.846% | 0.0243% | 15287.81 | 14721.6 | 566.21 | 2022-10-01 | 2023-09-30 | 2023-07-01 | 07 | 2023-09-30 | 09
050.61646 | RES.2736.POGUERD.MN.EXT | Install 1900' of 2" HDPE, Ret. 12 Hi pressure Taps | 36381.37 | 16498.49 | 19882.88 | 120.5% | 0.05782% | 36381.37 | 16498.49 | 19882.88 | 2022-10-01 | 2023-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61689 | RES.2638.Placid Ct Rev Ext | INstall160 feet of 2 inch poly main along Placid court off Lakeshore Drive for one conversion customer at 33 Placid Court | 6095.12 | 2390.65 | 3704.47 | 155% | 0.009687% | 6095.12 | 2390.65 | 3704.47 | 2022-10-01 | 2023-09-30 | 2023-07-24 | 07 | 2023-09-30 | 09
050.61708 | IND.2734.Trader Joes.Frk | Install approx. 2200' of 4" Steel to serve the new Trader Joes Distribution Facility. 100% AIC and they will provide an open and close ditch. Team Construction will be the Contractor installing pipe. Project will be 100% Xray | 62983.25 | 350693.61 | -287710.36 | -82.04% | 0.1001% | 62983.25 | 350693.61 | -287710.36 | 2022-10-01 | 2023-09-30 | 2023-07-25 | 07 | 2024-02-28 | 02
050.61766 | RES.2636.GOLDFINCH.MN.EXT | Install 200' of 2" HDPE for one new customer | 1045.08 | 1852.01 | -806.93 | -43.57% | 0.001661% | 1045.08 | 1852.01 | -806.93 | 2022-10-01 | 2023-09-30 | 2023-08-07 | 08 | 2023-08-30 | 08
050.61779 | 050.009.Heath Ordorators | Purchase 3-Heath Odorators @ 4800.00 each for Owensboro | 21195.62 | 17665.92 | 3529.7 | 19.98% | 0.03369% | 21195.62 | 17665.92 | 3529.7 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.61783 | RES.2638.Crouch Dr Rev Ext | Install 100 feet of 2 inch poly main for one new residential customer (Fred Nesler) requesting service. | 7495.2 | 4808.79 | 2686.41 | 55.86% | 0.01191% | 7495.2 | 4808.79 | 2686.41 | 2022-10-01 | 2023-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61796 | RES.2636.COLLEGEDR.MN.EXT | Install 250' of 2" HDPE for new customer | 2655.36 | 3034.58 | -379.22 | -12.5% | 0.00422% | 2655.36 | 3034.58 | -379.22 | 2022-10-01 | 2023-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61825 | COM.2736.FARMCREDIT.MN.EXT | Install 1650 of 4" HDPE for Farm Credit | 17850.53 | 18912.91 | -1062.38 | -5.617% | 0.02837% | 17850.53 | 18912.91 | -1062.38 | 2022-10-01 | 2023-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61827 | 2738.RMLD | Project to purchase replacment RMLD for Campbellsville office | 20705.72 | 16561.8 | 4143.92 | 25.02% | 0.03291% | 20705.72 | 16561.8 | 4143.92 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.61829 | COMM.2634.HASONSCHOOLRELOCA | Replace 1000' of 4" STL. with 1000" of 4" HDPE for turning lane at Hanson School | 76752.37 | 225266.55 | -148514.18 | -65.93% | 0.122% | 76752.37 | 225266.55 | -148514.18 | 2022-10-01 | 2023-09-30 | 2023-08-01 | 08 | 2023-08-25 | 08
050.61848 | RES.2636.HEATHERSTONE.MN.EXT | Install 1600' of 4" HDPE and 2500' of 2" HDPE for new subdivision | 78625.04 | 88766.52 | -10141.48 | -11.42% | 0.125% | 78625.04 | 88766.52 | -10141.48 | 2022-10-01 | 2023-09-30 | 2023-08-07 | 08 | 2023-09-30 | 09
050.61875 | RES.050.Stonehaven Ln Rev Ext | Install 700 feet of 2 inch poly main for one customer requsting natrural gas, this gets us closer to future phase if subdivision. | 5411.2 | 6894.24 | -1483.04 | -21.51% | 0.0086% | 5411.2 | 6894.24 | -1483.04 | 2022-10-01 | 2023-09-30 | 2023-08-14 | 08 | 2023-09-30 | 09
050.61950 | IND.2735.Bluegrass Dairy EXT | Extending 4" steel main to supply increased load and new meterset. First cut fabrication to supply the station and meterset and company labor to install. Customer to provide AIC. | -42355.74 | 182561.78 | -224917.52 | -123.2% | -0.06732% | -42355.74 | 182561.78 | -224917.52 | 2022-10-01 | 2023-09-30 | 2023-08-11 | 08 | 2023-09-30 | 09
050.62002 | COM.2636.WENDALLFORDFIREMN.EX | Install 3,000' of 4" HDPE for Fire Dept. training facility | 49399.94 | 65131.16 | -15731.22 | -24.15% | 0.07851% | 49399.94 | 65131.16 | -15731.22 | 2022-10-01 | 2023-09-30 | 2023-09-01 | 09 | 2023-09-28 | 09
050.62042 | COM.2734.Sterling Business | Install approx. 3400' of 4" PE and 1500' of 2" PE to serve new business park off Russellville Rd. Delveoper to open and close ditch. Company labor to install pipe. Customer to pay AIC | -18181.28 | 83624.08 | -101805.36 | -121.7% | -0.0289% | -18181.28 | 83624.08 | -101805.36 | 2022-10-01 | 2023-09-30 | 2023-08-28 | 08 | 2024-01-31 | 01
050.62083 | RES.2636.COUNTRYCLUBLN.MN.EXT | Install 600' of 2" HDPE for new home, Ret.300' of 2" plastic | 5565.93 | 6140.78 | -574.85 | -9.361% | 0.008846% | 5565.93 | 6140.78 | -574.85 | 2022-10-01 | 2023-09-30 | 2023-09-01 | 09 | 2023-09-25 | 09
050.62101 | COM.2737.CHICK-FIL-A.MN.EXT | Installing 1275' of 2" HDPE for new customer | 4486.43 | 38271.57 | -33785.14 | -88.28% | 0.00713% | 4486.43 | 38271.57 | -33785.14 | 2022-10-01 | 2023-09-30 | 2023-09-11 | 09 | 2023-09-28 | 09
050.62117 | COMM.SPORTSCOMPLEXPH2.MN.EXT | Install 480' of 4" HDPE for Sports complex | 1563.09 | 7768.93 | -6205.84 | -79.88% | 0.002484% | 1563.09 | 7768.93 | -6205.84 | 2022-10-01 | 2023-09-30 | 2023-09-08 | 09 | 2023-09-22 | 09
050.62146 | 050.3302.KY.LAPTOP.FY23 | PURCHASE TWO RUGGED LATITUDE 5430 LAPTOPS WITH MODEM INSTALLED FOR KENTUCKY. | 5614.9 | 5765.96 | -151.06 | -2.62% | 0.008924% | 5614.9 | 5765.96 | -151.06 | 2022-10-01 | 2023-09-30 | 2023-09-12 | 09 | 2023-09-30 | 09
050.62182 | 050.009.2636.Owensboro Out. | owensboro outage | 54779.18 | 182321.46 | -127542.28 | -69.95% | 0.08706% | 54779.18 | 182321.46 | -127542.28 | 2022-10-01 | 2023-09-30 | 2023-09-14 | 09 | 2023-09-30 | 09
050.62234 | Wmson Equip FY23 | This project is to capture the costs of purchasing Williamson tapping equipment for use in the Paducah area. We propose to purchase and pay for this equipment by the end og the fiscal year. | 18450.08 | 23309.2 | -4859.12 | -20.85% | 0.02932% | 18450.08 | 23309.2 | -4859.12 | 2022-10-01 | 2023-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
OH.050.10000 |  | UCG Business Unit A&G Overhead Project | 3378.25 | 0 | 3378.25 |  | 0.05122% | 32229.5 | 0 | 32229.5 | 2022-10-01 | 2023-09-30 | 1999-04-30 | 04 | 2020-12-31 | 12

## 2024
Atmos Energy Corporation
(Kentucky Division)
Case No. 2024-00276
Construction Projects 2024
Data:______ Base Period _____ Forecasted Period
Type of Filing:___X__ Original _____ Updated _____ Revised
Workpaper Reference No(s).:
Project No. | Project Title / Description |  | Annual Actual Cost 2024 | Total Cost Estimate | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Total Cost Estimate | Variance in Dollars | Original Budget Start | Date Original Budget End | Actual Start Year | Actual Start Month | Estimated Completion Year | Estimated Completion Month
050.23602 | BowlingGreen Growth RESI MEAS | Bowling Green KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 247280.9 | 0 |  |  | 4.126% | 2641210.17 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23603 | KY.Glasgow Growth RESI MEAS | Glasgow KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 17921.53 | 0 |  |  | 0.3215% | 205799.87 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23604 | Hopkinsville Growth RESI MEAS | Hopkinsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 30815.26 | 0 |  |  | 0.7453% | 477047.23 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23605 | KY.Danville Growth RESI MEAS | Danville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 21488.29 | 0 |  |  | 0.4751% | 304148.82 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23606 | CampbellsvilleGrowth RESI MEAS | Campbellsville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 37031.17 | 0 |  |  | 0.5298% | 339155.36 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23607 | KY.ShelbyvilleGrowth RESI MEAS | Shelbyville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 68774.31 | 0 |  |  | 1.839% | 1177183.63 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23608 | Madisonville Growth RESI MEAS | Madisonville KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 18018.45 | 0 |  |  | 0.3364% | 215364.24 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23609 | KY.Princeton Growth RESI MEAS | Princeton KY Growth RESI MEAS Functional; Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 12477.71 | 0 |  |  | 0.3494% | 223665.48 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23610 | KY.OwensboroGrowth RESI MEAS | Owensboro KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 139137.99 | 0 |  |  | 2.877% | 1841474.56 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23611 | KY.Paducah Growth RESI MEAS | Paducah Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 111944.4 | 0 |  |  | 3.041% | 1946903.31 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2017-09-30 | 09
050.23612 | KY.Mayfield Growth RESI MEAS | Mayfield KY Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications (ie diaphragm meters). | 31880.09 | 0 |  |  | 1.029% | 658569.14 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-10 | 09 | 2015-09-30 | 09
050.23638 | BowlingGreen Growth COMM MEAS | Bowling Green Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 241402 | 0 |  |  | 2.883% | 1845644.32 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23639 | KY.Glasgow Growth COMM MEAS | Glasgow Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 20171.24 | 0 |  |  | 0.1515% | 96950.74 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23640 | Hopkinsville Growth COMM MEAS | Hopkinsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 1373.82 | 0 |  |  | 0.2715% | 173802.03 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23641 | KY.Danville Growth COMM MEAS | Danville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (i.e rotary meters) | 119792.91 | 0 |  |  | 0.7245% | 463777.67 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23642 | CampbellsvilleGrowth COMM MEAS | Campbellsville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 35525.29 | 0 |  |  | 0.5142% | 329138.23 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23643 | KY.ShelbyvilleGrowth COMM MEAS | Shelbyville KY Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 46313.15 | 0 |  |  | 0.6058% | 387756.39 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23644 | Madisonville Growth COMM MEAS | Madisonville Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 5433.06 | 0 |  |  | 0.2686% | 171956.62 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23645 | KY.Princeton Growth COMM MEAS | Princeton Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 6339.73 | 0 |  |  | 0.2027% | 129753.05 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23646 | KYOwensboro Growth COMM MEAS | Owensboro Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 137604.07 | 0 |  |  | 1.399% | 895475.43 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23647 | KY.Paducah Growth COMM MEAS | Paducah Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 38365.98 | 0 |  |  | 0.7977% | 510609.17 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23648 | KY.Mayfield Growth COMM MEAS | Mayfield Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications (ie rotary meters). | 119498.47 | 0 |  |  | 0.4143% | 265207.95 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-11 | 09 | 2015-09-30 | 09
050.23674 | 050.KY.BowlingGrowthServices | Bowling Green KY Growth Services Functional | 706173.4 | 0 |  |  | 17.93% | 11479107.71 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23675 | 050.KY.GlasgowGrowthServices | Glasgow Growth Services Functional | 102261.6 | 0 |  |  | 1.96% | 1254442.56 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23676 | 050.KY.HopkinsGrowthServices | Hopkinsville KY Growth Services Functional | 80329.34 | 0 |  |  | 1.797% | 1150586.1 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23677 | 050.KY.DanvilleGrowthServices | Danville Growth Services Functional | 54904.07 | 0 |  |  | 1.469% | 940346.31 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23678 | 050.KY.CampbellGrowthServices | Campbellsville KY Growth Services Functional | 145794.63 | 0 |  |  | 1.962% | 1256073.49 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23679 | KY.ShelbyvilleGrowthServices | Shelbyville KY Growth Services Functional | 356510.21 | 0 |  |  | 6.49% | 4154473.68 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23680 | 050.KY.MadisonGrowthServices | Madisonville KY Growth Services Functional | 54961.15 | 0 |  |  | 2.009% | 1285688.9 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23681 | 050.KY.PrincetonGrowthServices | Princeton Growth Services Functional | 93802.74 | 0 |  |  | 1.388% | 888378.81 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23682 | 050.KY.OboroGrowthServices | Owensboro Growth Services Functional | 548972.73 | 0 |  |  | 12.22% | 7819041.13 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23683 | 050.KY.PaducahGrowthServices | Paducah Growth Services Functional | 274986.65 | 0 |  |  | 6.15% | 3936629.78 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2017-09-30 | 09
050.23684 | 050.KY.MayfieldGrowthServices | Mayfield Growth Services Functional | 151736.23 | 0 |  |  | 1.766% | 1130193.38 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-12 | 09 | 2015-09-30 | 09
050.23716 | 050.KY.BowlingIntegMains | Bowling Green Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 457317.22 | 0 |  |  | 5.168% | 3308318.72 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23717 | 050.KY.GlasgowIntegMains | Glasgow Non Growth Mains Functional | 41624.08 | 0 |  |  | 0.7037% | 450451.56 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23718 | 050.KY.HopkinsIntegMains | Hopkinsville Non Growth Mains Functional | 72359.15 | 0 |  |  | 0.9571% | 612632.8 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23719 | 050.KY.DanvilleIntegMains | Danville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 50354.24 | 0 |  |  | 1.046% | 669677.54 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23720 | 050.KY.CampbellIntegMains | Campbellsville Non Growth Mains Functional | 52912.52 | 0 |  |  | 0.8983% | 575028.8 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23721 | 050.KY.ShelbyvilleIntegMains | Shelbyville KY Non Growth Mains Functional | 11019.81 | 0 |  |  | 0.8244% | 527710.82 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23722 | 050.KY.MadisonIntegMains | Madisonville Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 58613.23 | 0 |  |  | 1.001% | 640776.67 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23723 | 050.KY.PrincetonIntegMains | Princeton Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 53090.17 | 0 |  |  | 0.6329% | 405102.39 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23724 | 050.KY.OboroIntegMains | Owensboro Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 364025.18 | 0 |  |  | 4.784% | 3062259.53 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23725 | 050.KY.PaducahIntegMains | Paducah Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 93986.53 | 0 |  |  | 2.203% | 1409852.89 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23726 | 050.KY.MayfieldIntegMains | Mayfield Non Growth Mains Functional. Pipe, fittings, etc. 2" and larger in pipe diameter. These items shall be directed to the mains functional. | 45473.47 | 0 |  |  | 0.6066% | 388289.38 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23754 | BowlingGreenIntegServices | Bowling Green Non Growth Services Functional | 977057.59 | 0 |  |  | 10.58% | 6771847.12 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23755 | GlasgowIntegServices | Glasgow Non Growth Services Functional | 382897.93 | 0 |  |  | 3.77% | 2412998.11 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23756 | HopkinsIntegServices | Hopkinsville Non Growth Services Functional | 271864.38 | 0 |  |  | 6.424% | 4112222.63 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23757 | DanvilleIntegServices | Danville Non Growth Services Functional | 222757.51 | 0 |  |  | 5.962% | 3816300.18 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23758 | CampbellIntegServices | Campbellsville Non Growth Services Functional | 133240.29 | 0 |  |  | 3.289% | 2105135.88 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23759 | KY.ShelbyvilleIntegServices | Shelbyville KY Non Growth Services Functional | 112737.77 | 0 |  |  | 1.997% | 1278626.34 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23760 | MadisonIntegServices | Madisonville Non Growth Services Functional | 357312.3 | 0 |  |  | 5.479% | 3506884.89 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23761 | PrincetonIntegServices | Princeton Non Growth Services Functional | 292577.75 | 0 |  |  | 3.539% | 2265525.31 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23762 | OboroIntegServices | Owensboro Non Growth Services Functional | 799833.03 | 0 |  |  | 12.75% | 8163824.07 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23763 | PaducahIntegServices | Paducah Non Growth Services Functional | 945025.03 | 0 |  |  | 10.72% | 6862382.26 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23764 | MayfieldIntegServices | Mayfield Non Growth Services Functional | 287732.75 | 0 |  |  | 3.363% | 2152641.27 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-13 | 09 | 2015-09-30 | 09
050.23793 | Bowling Green Integ RESI MEAS | Bowling Green Non Growth RESI MEAS Functional . Meters, regulators, and meterset items typically used for residential applications. | 727136.71 | 0 |  |  | 12.2% | 7812081.58 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23794 | KY.Glasgow Integ RESI MEAS | Glasgow Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 164290.58 | 0 |  |  | 3.186% | 2039507.05 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23795 | KY.HopkinsvilleInteg RESI MEAS | Hopkinsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 168951.1 | 0 |  |  | 3.981% | 2548032.2 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23796 | KY.Danville Integ RESI MEAS | Danville Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 312898.04 | 0 |  |  | 4.387% | 2808085.04 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23797 | Campbellsville Integ RESI MEAS | Campbellsville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 308671.43 | 0 |  |  | 3.944% | 2524579.13 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23798 | KY.Shelbyville Integ RESI MEAS | Shelbyville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 267832.68 | 0 |  |  | 3.51% | 2246981.24 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23799 | KYMadisonville Integ RESI MEAS | Madisonville KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 34680.56 | 0 |  |  | 3.705% | 2371387.62 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23800 | KY.Princeton Integ RESI MEAS | Princeton KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 64754.43 | 0 |  |  | 2.035% | 1302801.3 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23801 | KY.Owensboro Integ RESI MEAS | Owensboro Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 646676.48 | 0 |  |  | 16.37% | 10476994.07 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23802 | KY.Paducah Integ RESI MEAS | Paducah KY Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 236695.99 | 0 |  |  | 9.329% | 5971353.63 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2016-09-30 | 09
050.23803 | KY.Mayfield Integ RESI MEAS | Mayfield Non Growth RESI MEAS Functional. Meters, regulators, and meterset items typically used for residential applications. | 52662.05 | 0 |  |  | 3.45% | 2208499.22 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23871 | BowlingGreenInteg CP/ ANODE | Bowling Green Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 75236.21 | 0 |  |  | 1.865% | 1193543.21 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23872 | Glasgow Integ CP / ANODES | Glasgow Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 42985.19 | 0 |  |  | 0.2854% | 182671.28 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23873 | Hopkinsville Integ CP/ ANODE | Hopkinsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 21746.01 | 0 |  |  | 0.9043% | 578883.96 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23874 | Danville Integ CP / ANODES | Danville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 38569.74 | 0 |  |  | 1.22% | 780787.12 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23875 | Campbell Integ CP/ ANODE | Campbellsville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 64680.81 | 0 |  |  | 0.4981% | 318813.45 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23876 | KY.Shelbyville Integ CP/ ANODE | Shelbyville KY Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 15221.91 | 0 |  |  | 0.2415% | 154568.38 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23877 | Madisonville Integ CP/ ANODE | Madisonville Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 26512.29 | 0 |  |  | 0.594% | 380204.56 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23878 | Princeton Integ CP/ ANODE | Princeton Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 8636.38 | 0 |  |  | 0.457% | 292501.65 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23879 | Owensboro Integ CP / ANODE | Owensboro Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 91805.59 | 0 |  |  | 1.255% | 803354.03 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23880 | Paducah Integ CP / ANODE | Paducah Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 35048.69 | 0 |  |  | 0.7762% | 496882.58 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23881 | KY.Mayfield Integ CP / ANODE | Mayfield Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 4290.28 | 0 |  |  | 0.1445% | 92520.51 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-14 | 09 | 2015-09-30 | 09
050.23910 | BowlingGreenLeakMains | Bowling Green Leak Functional Mains | 35228.85 | 0 |  |  | 3.796% | 2429891.53 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23911 | GlasgowLeakMains | Glasgow Leak Functional Mains | 19443.48 | 0 |  |  | 1.432% | 916497.85 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23912 | HopkinsvilleLeakMains | Hopkinsville Leak Functional Mains | 53684.28 | 0 |  |  | 1.376% | 881011.46 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23913 | DanvilleLeakMains | Danville Leak Functional Mains | 16671.49 | 0 |  |  | 1.024% | 655495.23 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23914 | CampbellsvilleLeakMains | Campbellsville Leak Functional Mains | 38182.65 | 0 |  |  | 0.6355% | 406784.36 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23915 | KY.ShelbyvilleLeakMains | Shelbyville KY Leak Functional Mains | 2266.3 | 0 |  |  | 0.4161% | 266373.74 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23916 | MadisonvilleLeakMains | Madisonville Leak Functional Mains | 62580.97 | 0 |  |  | 1.306% | 835904.04 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23917 | PrincetonLeakMains | Princeton Leak Functional Mains | 30186.4 | 0 |  |  | 0.7081% | 453250.47 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23918 | OwensboroLeakMains | Owensboro Leak Functional Mains | 60321.96 | 0 |  |  | 2.172% | 1390205.97 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23919 | PaducahLeakMains | Paducah Leak Functional Mains | 13320.81 | 0 |  |  | 1.72% | 1101083 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23920 | MayfieldLeakMains | Mayfield Leak Functional Mains | 9939.19 | 0 |  |  | 0.342% | 218923.2 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23949 | BowlingGreenLeakServices | Bowling Green Leak Functional Services | 86881.57 | 0 |  |  | 3.977% | 2545617.01 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23950 | GlasgowLeakServices | Glasgow Leak Functional Services | 16490.4 | 0 |  |  | 1.286% | 823286.55 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23951 | HopkinsvilleLeakServices | Hopkinsville Leak Functional Services | 6547.6 | 0 |  |  | 1.075% | 688142.25 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23952 | DanvilleLeakServices | Danville Leak Functional Services | 30655.18 | 0 |  |  | 1.59% | 1018085.32 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23953 | CampbellsvilleLeakServices | Campbellsville Leak Services Functional | 27276.66 | 0 |  |  | 0.6077% | 388984.11 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23954 | KY.ShelbyvilleLeakServices | Shelbyville KY Leak Services Functional | 8167.14 | 0 |  |  | 0.4442% | 284354.71 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23955 | MadisonvilleLeakServices | Madisonville Leak Services Functional | 27500.57 | 0 |  |  | 1.35% | 864226.25 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23956 | PrincetonLeaksServices | Princeton Leak Functional Services | 22272.6 | 0 |  |  | 0.5757% | 368522.14 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23957 | OwensboroLeakServices | Owensboro Leak Services Functional | 282479.66 | 0 |  |  | 4.087% | 2616353.36 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2017-12-31 | 12
050.23958 | PaducahLeakServices | Paducah Leak Functional Services | 114696.16 | 0 |  |  | 3.27% | 2092966.36 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23959 | MayfieldLeakServices | Mayfield Leak Functional Services | 23922.46 | 0 |  |  | 0.6136% | 392745.26 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23989 | Bowling Green Integ COMM MEAS | Bowling Green Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 353651.89 | 0 |  |  | 4.742% | 3035321.19 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23990 | KY.Glasgow Integ COMM MEAS | Glasgow Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 28904.54 | 0 |  |  | 1.017% | 650996.08 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23991 | KYHopkinsville Integ COMM MEAS | Hopkinsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 37578.06 | 0 |  |  | 0.8257% | 528546.44 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23992 | KY.Danville Integ COMM MEAS | Danville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 24219 | 0 |  |  | 1.218% | 779355.22 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23993 | Campbellsville Integ COMM MEAS | Campbellsville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 52362.83 | 0 |  |  | 1.208% | 773354.33 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23994 | KY.Shelbyville Integ COMM MEAS | Shelbyville KY Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 29463.09 | 0 |  |  | 0.8006% | 512485.08 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23995 | KYMadisonville Integ COMM MEAS | Madisonville Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 34118.13 | 0 |  |  | 0.9576% | 612952.86 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23996 | KY.Princeton Integ COMM MEAS | Princeton Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 34432 | 0 |  |  | 0.4941% | 316299.19 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23997 | KY.Owensboro Integ COMM MEAS | Owensboro Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 271295.9 | 0 |  |  | 4.889% | 3129553.39 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23998 | KY.Paducah Integ COMM MEAS | Paducah Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 375769.22 | 0 |  |  | 2.273% | 1454951.57 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.23999 | KY.Mayfield Integ COMM MEAS | Mayfield Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 24346.83 | 0 |  |  | 0.38% | 243242.66 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-15 | 09 | 2015-09-30 | 09
050.24078 | KYStorageLeakMains | Storage & Transmission Leak Functional - Mains | -1.19 | 0 |  |  | 0.1304% | 83500.71 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24079 | KY.StorageLeakServices | Storage & Transmission Leak Functional - Services | 29.96 | 0 |  |  | 0.02067% | 13232.97 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24084 | BowlingGreenPRPServices | Bowling Green KY PRP Functional - Services | 705532.82 | 0 |  |  | 26.24% | 16797443.34 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24085 | DanvillePRPServices | Danville KY PRP Functional - Services | 2620273.27 | 0 |  |  | 20.81% | 13322849.51 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2020-09-30 | 09
050.24086 | OwensboroPRPServices | Owensboro KY PRP Functional - Services | 461356.68 | 0 |  |  | 27.47% | 17582219.64 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24087 | PaducahPRPServices | Paducah KY PRP Functional - Services | 1935049.95 | 0 |  |  | 26.17% | 16754428.5 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.24109 | KY.Storage Integ RESI MEAS | KY Storage & Transmission Non Growth Functional - RESI MEAS. Meters, regulators, and meterset items typically used for residential applications. | 60.23 | 0 |  |  | 0.01786% | 11434.08 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24110 | KY.Storage Integ COMM MEAS | KY Storage and Transmission Non-Growth COMM MEAS Functional. Meters, regulators, and meterset items typically used for commercial/light industrial applications. | 2611.16 | 0 |  |  | 0.03159% | 20223.44 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.24111 | KY.Storage Integ CP/ ANODE | KY Storage and Transmission Non-Growth Anode/Cathodic Protection Functional. Anodes and other items related to cathodic protection of the system. | 1538.51 | 0 |  |  | 0.01567% | 10030.08 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-20 | 09 | 2015-09-30 | 09
050.26288 | MadisonvillePRPServices | Madisonville KY PRP Functional - Services | 1046330.98 | 0 |  |  | 5.914% | 3785471.61 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26295 | PrincetonPRPServices | Princeton KY PRP Functional - Services | 198697.92 | 0 |  |  | 10.62% | 6795790.38 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26300 | MayfieldPRPServices | Mayfield KY PRP Functional - Services | 418.83 | 0 |  |  | 1.472% | 942463.39 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26303 | GlasgowPRPServices | Glasgow KY PRP Functional - Services | 263788.71 | 0 |  |  | 10% | 6400978.98 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26306 | HopkinsvillePRPServices | Hopkinsville KY PRP Functional - Services | 725763.97 | 0 |  |  | 10.71% | 6854091.6 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26309 | CampbellsvillePRPServices | Campbellsville KY PRP Functional - Services | 1895423.77 | 0 |  |  | 17.02% | 10892898.24 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2015-09-30 | 09
050.26312 | ShelbyvillePRPServices | Shelbyville KY PRP Functional - Services | 448.63 | 0 |  |  | 0.3744% | 239632.65 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2010-09-16 | 09 | 2016-09-30 | 09
050.35882 | 050.2637.Royal Park Estates | Install 2,040 ft for new residential subdivision. Extension makes gas available to 8 existing homes, 3 vacant lots, two homes under construction, & one existing church | -1739.74 | 10321.68 | -12061.42 |  | 0.04008% | 25656.46 | 10321.68 | 15334.78 | 2023-10-01 | 2024-09-30 | 2013-11-11 | 11 | 2014-09-28 | 09
050.36058 | 050.2636.Millers Mill Rd. | Install 300 Ft 3/4 Inch Steell 1 MT Deason Farm Tap and 2080 ft 2 Inch PE to serve 10 residential customers | -1860 | 22834.5 | -24694.5 |  | 0.03401% | 21770.41 | 22834.5 | -1064.09 | 2023-10-01 | 2024-09-30 | 2013-11-20 | 11 | 2014-09-28 | 09
050.36380 | 2739.CLOVERBROOK 9a 2014 | INSTALL XXX OF 2" PE TO SERVE 21 LOTS IN CLOVERBROOK | -10026 | 9738.87 | -19764.87 |  | 0.001787% | 1143.68 | 9738.87 | -8595.19 | 2023-10-01 | 2024-09-30 | 2013-10-01 | 10 | 2014-10-01 | 10
050.36765 | 2738.NOE_RD_CHICKEN_HOUSES | INSTALL 8000' OF 4 in PE TO SERVE 5 EXISTING CHICKEN HOUSES | -14758 | 69507.65 | -84265.65 |  | 0.04514% | 28896.45 | 69507.65 | -40611.2 | 2023-10-01 | 2024-09-30 | 2014-02-01 | 02 | 2015-02-01 | 02
050.36790 | 050.2636.Hwy 951 Phase 2 | Install 829 ft 2Inch PE to serve 1 residential customer | -5651.27 | 10923.28 | -16574.55 |  | 0.002002% | 1281.81 | 10923.28 | -9641.47 | 2023-10-01 | 2024-09-30 | 2014-04-25 | 04 | 2014-09-28 | 09
050.37118 | 050.2636.Sir Wren | Install 295 ft 2 Inch PE to serve 1 residential customer | -3485.69 | 5242.61 | -8728.3 |  | 0.0004376% | 280.1 | 5242.61 | -4962.51 | 2023-10-01 | 2024-09-30 | 2014-06-10 | 06 | 2014-09-28 | 09
050.37233 | 2738.SALOMA RD 2014 | INSTALL 1040' OF 2" PE ON SALOMA ROAD | -1512 | 8584.68 | -10096.68 |  | -2.315e-05% | -14.82 | 8584.68 | -8599.5 | 2023-10-01 | 2024-09-30 | 2014-04-15 | 04 | 2015-04-15 | 04
050.37808 | 2738.SPR.HWY 150.CORNERSTONE | INSTALL 3500' OF 4" PE TO SERVE A NEW CUSTOMER ON 150 BYPASS ON WEST SIDE OF SPRINGFIELD - CORNERSTONE CHRISTIAN CHURCH | -4190 | 24903.49 | -29093.49 |  | 0.02152% | 13774.24 | 24903.49 | -11129.25 | 2023-10-01 | 2024-09-30 | 2014-01-01 | 01 | 2014-09-30 | 09
050.51704 | 050.2736.BD Seamless | Replace Reg. station and Meter set at BD Seamless | -66.83 | 58173.87 | -58240.7 |  | 0.06639% | 42498.51 | 58173.87 | -15675.36 | 2023-10-01 | 2024-09-30 | 2019-08-01 | 08 | 2019-09-30 | 09
050.52421 | 050.2637.Hinkleville Rd Ext | Install app. 750 feet of 2 inch poly main for one new residential customer requesting gas. | 3563.75 | 18404.8 | -14841.05 |  | 0.02897% | 18544.52 | 18404.8 | 139.72 | 2023-10-01 | 2024-09-30 | 2019-10-01 | 10 | 2019-11-30 | 11
050.54428 | 2734.Lovers.Ln.2".Ext. | Convert 850' of 2 inch HDPE service to main. 1200 Lovers Ln. | -3.62 | 100 | -103.62 |  | 0.0008489% | 543.41 | 100 | 443.41 | 2023-10-01 | 2024-09-30 | 2020-07-14 | 07 | 2020-08-15 | 08
050.54598 | Virgie St Reg Sta Replace.FY21 | This is an approved FY21 budgeted project. We are setting this up now due to 8 week lead time for securing new regulators. The existing Virgie Street regulator station has obsolete Fisher 630 regulators. Station also has a grade 3 (10/20/2015) leak on th | -83.78 | 44744.25 | -44828.03 |  | 0.03768% | 24118.23 | 44744.25 | -20626.02 | 2023-10-01 | 2024-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54642 | 2637.Misc.Equipment.FY2021 | Purchase 6 Archer units for WMR ($14,118), Replace 5 Sensit Gold G-2 units ($7,500), Purchase 20" Husqvarna walk behind concrete saw ($2,000). | 1632.18 | 30091.69 | -28459.51 |  | 0.04672% | 29907.66 | 30091.69 | -184.03 | 2023-10-01 | 2024-09-30 | 2020-10-01 | 10 | 2020-11-30 | 11
050.54812 | 2736.LP East 19th Services | Replacement of 154 services associated with Low Pressure replacement on East 19th St. This is a FY21 Caoital Project | -413.88 | 1040147.82 | -1040561.7 |  | 1.624% | 1039733.94 | 1040147.82 | -413.88 | 2023-10-01 | 2024-09-30 | 2020-12-01 | 12 | 2021-04-30 | 04
050.55122 | 2736.Elkton YZ Odorizer FY21 | Install pole mounted YZ Odorizer for Elkton Purchase Station ($25,000). | 3379.72 | 32117.98 | -28738.26 |  | 0.06136% | 39274.9 | 32117.98 | 7156.92 | 2023-10-01 | 2024-09-30 | 2020-10-01 | 10 | 2020-12-31 | 12
050.55847 | RES.2736.Buttermilk Rd. Ext | 160 ft. of 2 inch HDPE will serve new residential customers on Buttermilk Rd. in Hopkinsville. | -31.27 | 4684.87 | -4716.14 |  | 0.006387% | 4088.39 | 4684.87 | -596.48 | 2023-10-01 | 2024-09-30 | 2021-02-05 | 02 | 2021-04-30 | 04
050.56048 | 2735.Oakland Station Rebuild | Rebuild station at Oakland due to valve replacement. Materials are currently in stock.Will be a DIrect Company Labor project | -32.51 | 16537.16 | -16569.67 |  | 0.008421% | 5390.7 | 16537.16 | -11146.46 | 2023-10-01 | 2024-09-30 | 2020-10-01 | 10 | 2021-09-30 | 09
050.56151 | LP.2736.17th.St.Replacement | Replace 101 feet of 1 1/1", 1,750 feet of 2", 4,316 feet of 4" and 3,623 feet of 6" with 3,470 feet of 4" HDPE and 4,038 feet of 2" HDPE. Retire RS9422 . This is a FY21 Capital LP Project. Construction by Martin Contracting. | -135.56 | 707136.26 | -707271.82 |  | 0.8983% | 575006.77 | 707136.26 | -132129.49 | 2023-10-01 | 2024-09-30 | 2021-04-01 | 04 | 2021-09-30 | 09
050.56170 | 2734.Redbud Sta. Retire | Redbud Station Retirement - Install 1,700 feet of 2" PE and 300 feet of 4" PE to tie 2 systems together to retire station for property improvements. | -55.53 | 189843.7 | -189899.23 |  | 0.198% | 126712.13 | 189843.7 | -63131.57 | 2023-10-01 | 2024-09-30 | 2021-03-26 | 03 | 2021-07-30 | 07
050.56737 | PRP.2734.Schweizer Road | Replace 25,500' of 8" high pressure Bare steel with 25,500' of Fusion Bond Epoxy Steel, project will also include a new Purchase Station , check meter , YZ odorizer, all electronics and a expanded station lot | 94323.33 | 10254292.78 | -10159969.45 |  | 13% | 8322856.29 | 10254292.78 | -1931436.49 | 2023-10-01 | 2024-09-30 | 2021-06-21 | 06 | 2023-09-30 | 09
050.56948 | COM.2736.Marie Dr. Ext | 100 ft of 2 inch HDPE will serve a new assised living facility located on Marie Dr.Developer wi open and close ditch | -7.46 | 1952.54 | -1960 |  | 0.0035% | 2240.57 | 1952.54 | 288.03 | 2023-10-01 | 2024-09-30 | 2021-11-01 | 11 | 2021-12-31 | 12
050.57276 | LP.2736.LP Services Hopk. | Replacement of 80 services associated with Low Pressure replacement on 17th St. This is an approved FY22 project | -398.28 | 648013.7 | -648411.98 |  | 1.012% | 647615.42 | 648013.7 | -398.28 | 2023-10-01 | 2024-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.57553 | IND.2734.Century.St.Ext | 100 ft. of 2 inch Steel, 637 Reg. station and 200 ft. of 2 inch PE will serve new Industrial Warehouses ion Centur St in the South Industrial Park | -58.32 | 21975.3 | -22033.62 |  | 0.01513% | 9685.64 | 21975.3 | -12289.66 | 2023-10-01 | 2024-09-30 | 2021-10-18 | 10 | 2021-11-30 | 11
050.57555 | RES.2734.Peachtree.Ext. | 500 t. of 2 inch HDPE will serve 4 conversion customers on Peachtree Ln. in Bowling Green. | -46.05 | 23144.68 | -23190.73 |  | 0.01129% | 7228.74 | 23144.68 | -15915.94 | 2023-10-01 | 2024-09-30 | 2021-10-18 | 10 | 2021-11-30 | 11
050.57638 | RNG.2739.Benson Valley | Build RNG Interconnect at Benson Valley Landfill in Frankfort KY | 6560.86 | 1360373.4 | -1353812.54 |  | 0.04849% | 31036.31 | 1360373.4 | -1329337.09 | 2023-10-01 | 2024-09-30 | 2021-10-01 | 10 | 2023-06-30 | 06
050.57710 | RES.2736.Madisonville.Rd.Ext | 260 t. o 2 inch HDPE will serve one new residential customer at 11195 S. Maidonnville Rd. in Croton.AIC = $4,420.00 | -8.4 | 7274.85 | -7283.25 |  | -0.0045% | -2880.24 | 7274.85 | -10155.09 | 2023-10-01 | 2024-09-30 | 2021-11-02 | 11 | 2021-12-31 | 12
050.57815 | RES.2734.Magnois.Hills.3-C | 1200 ft. of 4 inch and 2850 ft. od 2 inch HDPE wi serve 104 new residential lots in Magnolia Hills Phase 3-C located off Plano Rd. Developer wi open and close ditch and install casings for mains and services. | -84.61 | 38479.48 | -38564.09 |  | 0.0415% | 26563.83 | 38479.48 | -11915.65 | 2023-10-01 | 2024-09-30 | 2021-11-04 | 11 | 2022-01-29 | 01
050.57907 | 2638.Mayfield Tornado.21 | Track capital work associated with Mayfield, KY tornado damage. | -2499.47 | 1693619.85 | -1696119.32 |  | 0.1316% | 84259.04 | 1693619.85 | -1609360.81 | 2023-10-01 | 2024-09-30 | 2021-12-10 | 12 | 2022-09-30 | 09
050.58030 | RES.2734 Poplar Grove Phase 2 | 1540 ft. of 4 inch HDPE will drtve 25 New Residentia lots in Phase 2 of Poplar Grove Sub. locayed off Scottsville Rd. Developer will open and close ditch and install casings for main and services. | -33.96 | 18162.85 | -18196.81 |  | 0.02071% | 13258.38 | 18162.85 | -4904.47 | 2023-10-01 | 2024-09-30 | 2022-01-11 | 01 | 2022-03-31 | 03
050.58045 | RES.2734.Autumn Lake Final | 2755 ft. of 2 inch HDPE will seve 43 new resdemtal lots in the final phase of Autumn Lake Sub. in Franklin. Developer will open and close ditch and install casings for Main and service line crossings. | -52.59 | 16092.56 | -16145.15 |  | 0.01923% | 12312.38 | 16092.56 | -3780.18 | 2023-10-01 | 2024-09-30 | 2022-01-13 | 01 | 2022-03-31 | 03
050.58196 | RES.2634.UNIVERSITYCIRCLEMN.E | Install 250' of 2" HDPE | -29.96 | 3810.87 | -3840.83 |  | 0% | 0 | 3810.87 | -3810.87 | 2023-10-01 | 2024-09-30 | 2022-02-14 | 02 | 2022-02-18 | 02
050.58319 | NG.2735.Park Mammoth Reloc. | Replace 500 ft. of 2" HDPE in conjunction with development plans at Parck City Mammoth Golf Course. Reimbursementby developer will be at 100% | -41.92 | 7596.48 | -7638.4 |  | -0.005599% | -3584.2 | 7596.48 | -11180.68 | 2023-10-01 | 2024-09-30 | 2022-02-23 | 02 | 2022-04-29 | 04
050.58372 | RES.2734.CarterCrossingIIIA | 459 ft. of 6 inch 685 ft. of 4 inch and 1830 ft. of 2 inch HDPE will serve 57 new residential lots in Carters Crossing Phase IIIA. Developer will open and close ditch and install casings for main and service lines | -98.98 | 41158.2 | -41257.18 |  | 0.05445% | 34855.62 | 41158.2 | -6302.58 | 2023-10-01 | 2024-09-30 | 2022-03-04 | 03 | 2022-05-31 | 05
050.58583 | COM.2736.JollyRanch.Cadiz | 850 ft. of 2 inch HDPE will serve 8 new commercial lots in Jolly Ranch Development located off Glenwood Mill Rd. in Cadiz KY. Main will tie in to existing 2" HDPE | -40.79 | 7193.01 | -7233.8 |  | 0.009865% | 6314.86 | 7193.01 | -878.15 | 2023-10-01 | 2024-09-30 | 2022-04-07 | 04 | 2022-05-31 | 05
050.58736 | Pierce Lackey - DRS Replace | This project is to capture the costs associated with the replacement of the District Regulator Station at Pierce Lackey Court (public housing authority). Work will begin as soon as possible. | -47.98 | 16617.12 | -16665.1 |  | 0.008055% | 5156.33 | 16617.12 | -11460.79 | 2023-10-01 | 2024-09-30 | 2022-05-09 | 05 | 2022-06-30 | 06
050.58746 | Ella Munal DRS Replace | This project is set up to capture the costs associated with the replacement of the DRS at Ella Munal Court (Paducah Housing Authority). | -48.71 | 16528.17 | -16576.88 |  | 0.008706% | 5572.88 | 16528.17 | -10955.29 | 2023-10-01 | 2024-09-30 | 2022-05-09 | 05 | 2022-06-30 | 06
050.58763 | IND.2734.Reasonover | move main | -16.18 | 23465.15 | -23481.33 |  | 0.02839% | 18172.28 | 23465.15 | -5292.87 | 2023-10-01 | 2024-09-30 | 2022-05-10 | 05 | 2022-09-30 | 09
050.58788 | RES.2734.BreckenridgePhase II | 1230 ft. of 4 inch and 1356 ft. of 2 inch HDPE will serve 33 new residential lots in Phase II of Brecenridge l.ocated off Old Scottsville Rd. in Alvaton. Developer will open and close ditch and install casings for main and service lines. | -28.93 | 20863.67 | -20892.6 |  | 0.02869% | 18367.88 | 20863.67 | -2495.79 | 2023-10-01 | 2024-09-30 | 2022-02-21 | 02 | 2022-06-30 | 06
050.58833 | LP.050.2736.Phelps LP Services | Project replaces115 services in conjunction with low oressure main replacement on Phelps Ave. in Hopkinsville. | -5.35 | 562081.47 | -562086.82 |  | 0.8781% | 562084.87 | 562081.47 | 3.4 | 2023-10-01 | 2024-09-30 | 2021-10-01 | 10 | 2022-09-30 | 09
050.59450 | PRP.2738.Covington Ave | Revision Comments: Original Estimate $740,326.82 An additional 2,154' of main was installed for tie backs and additional bare main found with restoration causing project to exceed original estimate. | 4.95 | 959307.76 | -959302.81 |  | 1.499% | 959312.71 | 959307.76 | 4.95 | 2023-10-01 | 2024-09-30 | 2022-10-03 | 10 | 2023-09-30 | 09
050.59495 | 050.2612 KMD Measurement | KY Prover replacement program and misc calibration equipment | 4395.62 | 233647.94 | -229252.32 |  | 0.2334% | 149387.52 | 233647.94 | -84260.42 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59511 | PRP.2737.East Main St | Revision Comments:Original estimate $805,191.16 This project was not the project we budgeted for due to State paving plans. The State made us go under the side walk and they were 5" wide and 8" to 12" thick. Restoration costs were well above our original | -428.35 | 1612461.36 | -1612889.71 |  | 2.518% | 1612033.01 | 1612461.36 | -428.35 | 2023-10-01 | 2024-09-30 | 2022-10-03 | 10 | 2023-09-30 | 09
050.59524 | PRP.2637.Washington St | ******* Revision Comments ******* Original Estimate: $739,563.14 2,978' of additional main was installed and the 4" PE was changed to 6" PE from the original estimate.Concrete and asphalt exceeded original estimate | 7006.75 | 1367930.03 | -1360923.28 |  | 2.147% | 1374578.68 | 1367930.03 | 6648.65 | 2023-10-01 | 2024-09-30 | 2022-10-03 | 10 | 2023-03-27 | 03
050.59657 | 050.2609 St. Char. Dehy PH. 2 | Project to install 670 hp Dearing compressor, compressor building, dehy, filter/seperators, meter skids, regulation/control skids, MCC building, and all supporting equipment at the St. Charles Station in Dawson Springs, KY. | 10852486.43 | 13005158.17 | -2152671.74 |  | 19.05% | 12196832.56 | 13005158.17 | -808325.61 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2025-02-28 | 02
050.59668 | Eqpmt.2735.FY23 | Routing for approval. Increase in cost of items since estimate was completed. Purchase Sensit Smartcal 360 desktop cal station ($5,650), 2 Vivax/Metrotech VM-810 line locators ($3,375 each), TDW 3x4 Shortstop plugging assembly ($21,000), Sensit Gas-Tr | 18825.88 | 78321.33 | -59495.45 |  | 0.1224% | 78321.33 | 78321.33 | 0 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.59722 | 050.2609.Kirkwood | Removing compressor station, replacing witrh new reg. stations and dehy, tying into storgae trunkline and High Pressure | 53804.74 | 5407661.37 | -5353856.63 |  | 8.606% | 5509029.65 | 5407661.37 | 101368.28 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60034 | PRP.2734.31W BG | Revision Comments: Original estimate $615, 595.31 Project exceeded estimate due to required depths that were made in rock for the State for pending HWY project on 31W. | 1827.1 | 839192.69 | -837365.59 |  | 1.314% | 841019.79 | 839192.69 | 1827.1 | 2023-10-01 | 2024-09-30 | 2022-10-21 | 10 | 2023-09-28 | 09
050.60040 | COM.2638.Commerce Ext-HP-IP | Convert existing 2 inch steel HPD (200# maop) to I.P (60# maop). Install new reg station, run 200' - 2" poly for one new commercial building (Auto repair). Remove existing farm tap regs. | -98.26 | 17344.88 | -17443.14 |  | 0.02925% | 18720.58 | 17344.88 | 1375.7 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2022-12-30 | 12
050.60095 | 2739.WMR_Endpoints.FY23 | Project to purchase, install, and program 3360 WMR Endpoints in Shelbyville, KY | 565.62 | 319074.78 | -318509.16 |  | 0.5165% | 330597.41 | 319074.78 | 11522.63 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60152 | RES.2734.South Glen Gables | Approx 4850' of 4" PE to serve 76 new lots | -134.3 | 56961.87 | -57096.17 |  | 0.09282% | 59416.96 | 56961.87 | 2455.09 | 2023-10-01 | 2024-09-30 | 2022-11-15 | 11 | 2023-09-30 | 09
050.60183 | SINT.2734.BG Purchase 2 Repl | Previous Estimate of 2,003,630.63 Additional rock and fence revision due to customers request for privacy. Schedule lengthened and increase time for 3rd party inspection and Xray. Revised one station run to accomodate existing MAOP vs the original plan | 54592.24 | 2108625.37 | -2054033.13 |  | 3.327% | 2129429.97 | 2108625.37 | 20804.6 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.60193 | INT.2738.Springfield Reinf | System reinforcement project to feed Altech | 1313.52 | 359070.92 | -357757.4 |  | 0.1738% | 111270.74 | 359070.92 | -247800.18 | 2023-10-01 | 2024-09-30 | 2022-12-01 | 12 | 2023-09-30 | 09
050.60309 | 050.2609.KirkWood Leak Det. | KirkWood Storage Station Leak Det. | 51074.22 | 124143.76 | -73069.54 |  | 0.1097% | 70246.82 | 124143.76 | -53896.94 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2024-04-30 | 04
050.60310 | 050.2609.St. Charles Lead Det. | 2609 St. Charles Leak Detection | 112258.4 | 164523.02 | -52264.62 |  | 0.1754% | 112258.4 | 164523.02 | -52264.62 | 2023-10-01 | 2024-09-30 | 2022-12-01 | 12 | 2025-02-28 | 02
050.60596 | 2734.Cypress Way Replacement | Replace approximately 700' of 2" steel with 2" PE in conjunction with renovations of Greenwood High School. Unbudgeted replacement. The School Contractor will open ditch and Company labor will install pipe. | -9.38 | 8460.67 | -8470.05 |  | 0.005652% | 3617.62 | 8460.67 | -4843.05 | 2023-10-01 | 2024-09-30 | 2023-01-30 | 01 | 2023-04-30 | 04
050.60816 | PRP.2634.Boggess Blvd | See Project Long Description /Notes | 1542.72 | 528855.76 | -527313.04 |  | 0.8924% | 571231.68 | 528855.76 | 42375.92 | 2023-10-01 | 2024-09-30 | 2023-03-01 | 03 | 2023-07-15 | 07
050.60825 | 050.2636.Bevier Field | Repair leaks, remove above ground facilities, Install 500' of 6" Stl. | 4230 | 277284.43 | -273054.43 |  | 0.4398% | 281514.43 | 277284.43 | 4230 | 2023-10-01 | 2024-09-30 | 2023-04-01 | 04 | 2023-09-30 | 09
050.60834 | 050.2636.Downs Food Group | Install 4" Meter/Reg. Station, Install 120' of 2" Stl. | -632.13 | 243758.24 | -244390.37 |  | 0.3458% | 221373 | 243758.24 | -22385.24 | 2023-10-01 | 2024-09-30 | 2023-04-15 | 04 | 2023-08-31 | 08
050.61007 | RES.2738.Blackberry Lane | 700 Ft of 2 In HDPE to serve 2 customers on Blackberry Lane | -105.09 | 15361.92 | -15467.01 |  | 0.02396% | 15335.16 | 15361.92 | -26.76 | 2023-10-01 | 2024-09-30 | 2023-03-20 | 03 | 2023-08-31 | 08
050.61034 | IND.2737.Southern Soul Meter | 4 Inch Transport Meterset to serve Southern Soul Distillery in Lancaster KY | -220.72 | 102286.29 | -102507.01 |  | 0.101% | 64656.49 | 102286.29 | -37629.8 | 2023-10-01 | 2024-09-30 | 2023-04-01 | 04 | 2023-08-31 | 08
050.61043 | IND.2739.Weiland Meter | 4 Inch Transport Meterset to serve Weiland in Shelbyville KY | -253.61 | 125042.23 | -125295.84 |  | 0.1391% | 89011.57 | 125042.23 | -36030.66 | 2023-10-01 | 2024-09-30 | 2023-04-01 | 04 | 2023-08-16 | 08
050.61060 | PRP.2637.Sunset Ave | See Project Long Description/Notes | -37.18 | 747260.79 | -747297.97 |  | 0.7383% | 472601.17 | 747260.79 | -274659.62 | 2023-10-01 | 2024-09-30 | 2023-04-04 | 04 | 2023-07-31 | 07
050.61088 | 2609.Kimbel 3 Casing Replace. | Replace casing top joint on Kimbel #3 Well at St. Charles Storage Field - | 772.35 | 464772.12 | -463999.77 |  | 0.7166% | 458684.87 | 464772.12 | -6087.25 | 2023-10-01 | 2024-09-30 | 2023-04-15 | 04 | 2023-09-29 | 09
050.61097 | PRP.2737.Helm St | Revision Comments: Original estimate: $ 683,579.72 This was not the project we budgeted for due to State paving plans. Concrete and Asphalt costs exceeded what was bugted for the original project. The State made us run under the sidewalk. | -1306.27 | 856832.12 | -858138.39 |  | 1.337% | 855525.85 | 856832.12 | -1306.27 | 2023-10-01 | 2024-09-30 | 2023-04-11 | 04 | 2023-09-30 | 09
050.61154 | RES.2734.SouthParkCommonsPH1 | 103 lots in South Park Commons Phase 1. Install 800' 6" PE, 5,484' 4" PE, and 2,784' 2" PE. Devloper to open and close ditch. Company labor to install pipe. | -695.84 | 91626.05 | -92321.89 |  | 0.1555% | 99525.71 | 91626.05 | 7899.66 | 2023-10-01 | 2024-09-30 | 2023-04-17 | 04 | 2023-09-30 | 09
050.61164 | IND.2734.LoganAlum.Meter Repl | Replacement of Logan Al Meter/Reg set. Includes Reg-Meterset, Heater, Filter/Sep, and all electronics needed. First Cut will be the contractor, Contract Insp utilized. DUE TO UNKNOWNS ON HOW LOGAN WILL REIMBURSE, SUBJECT TO REVISION | 88508.1 | 2406761.29 | -2318253.19 |  | -0.2412% | -154368.78 | 2406761.29 | -2561130.07 | 2023-10-01 | 2024-09-30 | 2023-03-02 | 03 | 2024-01-17 | 01
050.61295 | IND.2739.Meggitt Meter | 4 Inch Transport Meterset to serve Meggitt in Danville KY | -275.94 | 100211.42 | -100487.36 |  | 0.1443% | 92378.46 | 100211.42 | -7832.96 | 2023-10-01 | 2024-09-30 | 2023-05-01 | 05 | 2023-08-31 | 08
050.61367 | 2734.KYTC.KY 1008 Relocation | Replace approx. 650' of 4" PE and 120' of 2" PE to resolve conflicts in KYTC project 3-80106 in Franklin KY. Contract labor will be used to complete the work. | 152922.03 | 175807.51 | -22885.48 |  | 0.2683% | 171769.97 | 175807.51 | -4037.54 | 2023-10-01 | 2024-09-30 | 2023-05-22 | 05 | 2024-05-30 | 05
050.61375 | IND.2734.EnvisionP1.Transpark | Install approx 3500' of 8" steel for new EV Battery plant, Envision Phase 1, in Transpark. Pipe will be installed in public utility easement with drive access provided by Envision outside of any secured fencing to meterset. | 6738.58 | 1111263.76 | -1104525.18 |  | 0.8961% | 573597.88 | 1111263.76 | -537665.88 | 2023-10-01 | 2024-09-30 | 2023-03-27 | 03 | 2023-09-30 | 09
050.61402 | 2734.Ashley Cir Roundabout | Routing for revision due to needing to bore more than anticipated for the relcoation and needing to replace more 2" than anticipated to eliminate a section of isloated steel. Relocate approximately 500' of 2" Steel and 2" PE to resolve conflicts with th | -99.64 | 90351.77 | -90451.41 |  | 0.1378% | 88221.95 | 90351.77 | -2129.82 | 2023-10-01 | 2024-09-30 | 2023-05-26 | 05 | 2023-08-31 | 08
050.61403 | 2734.Highland Way Roundabout | Relocate approximately 500' of 2" PE, 4" steel, and 2" steel with 2" PE to resolve conflicts with drainage and storm sewer for the City. Team Construction will complete the work and Company Inspection will be used. | 75832.29 | 74002.2 | 1830.09 |  | 0.1185% | 75832.29 | 74002.2 | 1830.09 | 2023-10-01 | 2024-09-30 | 2023-05-29 | 05 | 2024-04-12 | 04
050.61470 | PRP.2636.Maple Dr | See Project Long Description / Notes | -96.21 | 236218.87 | -236315.08 |  | 0.3207% | 205270.82 | 236218.87 | -30948.05 | 2023-10-01 | 2024-09-30 | 2023-06-29 | 06 | 2023-09-30 | 09
050.61501 | Adyl.2635.St Charles | See Project Long Description/Notes | -510.73 | 1189088.55 | -1189599.28 |  | 1.099% | 703571.43 | 1189088.55 | -485517.12 | 2023-10-01 | 2024-09-30 | 2023-06-12 | 06 | 2023-09-30 | 09
050.61502 | PRP.2637.Lone Oak Rd | See Project LOng Description /Notes | 10105.85 | 736283.08 | -726177.23 |  | 1.145% | 732964.33 | 736283.08 | -3318.75 | 2023-10-01 | 2024-09-30 | 2023-06-30 | 06 | 2023-09-30 | 09
050.61509 | 050.2634.Poole Purchase | Replace Poole Purchase, 60' of 2" Stl., 1 - 2" Reg. Station, 1 - 2" Meter Station, 1 - Odorizor | 31819.33 | 156850.7 | -125031.37 |  | 0.2301% | 147317.62 | 156850.7 | -9533.08 | 2023-10-01 | 2024-09-30 | 2022-10-01 | 10 | 2023-09-30 | 09
050.61531 | PRP-Aldyl-A.2635.Princeton Svc | PRP-Aldyl-A.2635.Princeton Services | -1264.37 | 0 |  |  | 0.4265% | 273024.67 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2023-06-21 | 06 | 2025-09-30 | 09
050.61532 | PRP-Aldyl-A.2736.Hopkins Svc | PRP-Aldyl-A.2736.Hopkinsville Services | 1869.06 | 0 |  |  | 0.9702% | 621043.62 | Non Budgeted |  | 2023-10-01 | 2024-09-30 | 2023-06-21 | 06 | 2025-09-30 | 09
050.61556 | Adyl.2736.Cunningham Ave | See Project Long Description / Notes | 56492.52 | 505134.17 | -448641.65 |  | 0.5817% | 372346.24 | 505134.17 | -132787.93 | 2023-10-01 | 2024-09-30 | 2023-06-30 | 06 | 2023-09-30 | 09
050.61557 | Adyl.2736.Lincoln Ave | ***** 2023 Adyl ***** Replace 617'1.25" Adyl A, 6' of 3" Steel, 99' of 2" PE, 1,002' of 1" Adyl A, 1,531' of 2" PE, 3,386' of 2" Adyl A with 7,008' of 2" HDPE. | 11470.39 | 729347.34 | -717876.95 |  | 0.7443% | 476414.93 | 729347.34 | -252932.41 | 2023-10-01 | 2024-09-30 | 2023-06-24 | 06 | 2023-09-30 | 09
050.61567 | 2738.KY Cooperage Tunnel Relo | Sending revision for approval due to footage being slightly more than anticipated. Lowering 120' of 4" to accomodate tunnel crossing under HWY 68. Martin contracting will be completing the work under existing MSA rates. | -89.95 | 27521.87 | -27611.82 |  | 0.005782% | 3700.89 | 27521.87 | -23820.98 | 2023-10-01 | 2024-09-30 | 2023-06-28 | 06 | 2023-08-31 | 08
050.61593 | 050.2637.Forest Ave Sys Imp | One service feeding three homes. We propose to install 100 feet of 2 inch poly main. We will then install three separate services. | -210.38 | 4289.53 | -4499.91 |  | 0.01321% | 8458.13 | 4289.53 | 4168.6 | 2023-10-01 | 2024-09-30 | 2023-07-03 | 07 | 2023-07-31 | 07
050.61594 | RES.2634EASTMORTON.MN.EXT | Install 270' of 2" HDPE, ret. 612' of 2" Stl | -40.76 | 3243.66 | -3284.42 |  | 0.01074% | 6875.71 | 3243.66 | 3632.05 | 2023-10-01 | 2024-09-30 | 2023-08-01 | 08 | 2023-08-30 | 08
050.61599 | RES.2634.UNIVERSITYCIRCLE.MN. | Install 300' of 2" HDPE for new customers | 52613.06 | 53864.81 | -1251.75 |  | 0.08608% | 55104.18 | 53864.81 | 1239.37 | 2023-10-01 | 2024-09-30 | 2023-07-03 | 07 | 2023-09-30 | 09
050.61629 | RES.2637.Nace Ln Rev Ext | Install 300 feet of 2 inch poly gas main for three new residential duplexes being built by Mark Hicks. 6 meters in total. | -610.74 | 8447.86 | -9058.6 |  | 0.01772% | 11342.22 | 8447.86 | 2894.36 | 2023-10-01 | 2024-09-30 | 2023-07-10 | 07 | 2023-09-30 | 09
050.61639 | RES.2636.HEATHERSTONEAPPROCH. | Install 2300' of 4" HDPE approch main for new subdivision | -1868.71 | 62166.58 | -64035.29 |  | 0.0942% | 60297.87 | 62166.58 | -1868.71 | 2023-10-01 | 2024-09-30 | 2023-07-10 | 07 | 2023-09-30 | 09
050.61646 | RES.2736.POGUERD.MN.EXT | Install 1900' of 2" HDPE, Ret. 12 Hi pressure Taps | -2246.42 | 36381.37 | -38627.79 |  | 0.05333% | 34134.95 | 36381.37 | -2246.42 | 2023-10-01 | 2024-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61689 | RES.2638.Placid Ct Rev Ext | INstall160 feet of 2 inch poly main along Placid court off Lakeshore Drive for one conversion customer at 33 Placid Court | 17.31 | 2390.65 | -2373.34 |  | 0.009549% | 6112.43 | 2390.65 | 3721.78 | 2023-10-01 | 2024-09-30 | 2023-07-24 | 07 | 2023-09-30 | 09
050.61708 | IND.2734.Trader Joes.Frk | Install approx. 2200' of 4" Steel to serve the new Trader Joes Distribution Facility. 100% AIC and they will provide an open and close ditch. Team Construction will be the Contractor installing pipe. Project will be 100% Xray | 229350.03 | 350693.61 | -121343.58 |  | 0.4567% | 292333.28 | 350693.61 | -58360.33 | 2023-10-01 | 2024-09-30 | 2023-07-25 | 07 | 2024-02-28 | 02
050.61783 | RES.2638.Crouch Dr Rev Ext | Install 100 feet of 2 inch poly main for one new residential customer (Fred Nesler) requesting service. | 1441.68 | 4808.79 | -3367.11 |  | 0.01396% | 8936.88 | 4808.79 | 4128.09 | 2023-10-01 | 2024-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61796 | RES.2636.COLLEGEDR.MN.EXT | Install 250' of 2" HDPE for new customer | 1500.15 | 3034.58 | -1534.43 |  | 0.006492% | 4155.51 | 3034.58 | 1120.93 | 2023-10-01 | 2024-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61825 | COM.2736.FARMCREDIT.MN.EXT | Install 1650 of 4" HDPE for Farm Credit | 6292.45 | 18912.91 | -12620.46 |  | 0.03772% | 24142.98 | 18912.91 | 5230.07 | 2023-10-01 | 2024-09-30 | 2023-08-01 | 08 | 2023-09-30 | 09
050.61829 | COMM.2634.HASONSCHOOLRELOCA | Replace 1000' of 4" STL. with 1000" of 4" HDPE for turning lane at Hanson School | -683.93 | 225266.55 | -225950.48 |  | 0.1188% | 76068.44 | 225266.55 | -149198.11 | 2023-10-01 | 2024-09-30 | 2023-08-01 | 08 | 2023-08-25 | 08
050.61848 | RES.2636.HEATHERSTONE.MN.EXT | Install 1600' of 4" HDPE and 2500' of 2" HDPE for new subdivision | -1299.62 | 88766.52 | -90066.14 |  | 0.1208% | 77325.42 | 88766.52 | -11441.1 | 2023-10-01 | 2024-09-30 | 2023-08-07 | 08 | 2023-09-30 | 09
050.61875 | RES.050.Stonehaven Ln Rev Ext | Install 700 feet of 2 inch poly main for one customer requsting natrural gas, this gets us closer to future phase if subdivision. | -509.56 | 6894.24 | -7403.8 |  | 0.007657% | 4901.64 | 6894.24 | -1992.6 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-09-30 | 09
050.61913 | 050.009 Madisonville Equipment | Misc. equipment for Madisonville. Purchase Mueller Valve Changer (1 @ $4,341), Jameson 1/8"x300ft complete kit (1 @ $1,100), Radiodetection Locator R10/81PDLM (1 @ $2,840), Radiodetection PCM 25W Transmitter (1 @ $5,880), LZ30 (1 @ $10,215), and Ritmo | 36500.38 | 32137.25 | 4363.13 |  | 0.05702% | 36500.38 | 32137.25 | 4363.13 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.61950 | IND.2735.Bluegrass Dairy EXT | Extending 4" steel main to supply increased load and new meterset. First cut fabrication to supply the station and meterset and company labor to install. Customer to provide AIC. | 17433.54 | 182561.78 | -165128.24 |  | -0.03893% | -24922.2 | 182561.78 | -207483.98 | 2023-10-01 | 2024-09-30 | 2023-08-11 | 08 | 2023-09-30 | 09
050.61969 | Misc Equip | This project is to capture the costs of misc equipment for Mayfield, KY. Cost center is 2638. This is for fiscal year 2024. Includes (2) Muleller no-blo kits at $4,400 ea, 1 Metrotech model 810 at $3,140, and 1 Sensit Gold at $1,400 for a total of $13,34 | 18836.48 | 16365.51 | 2470.97 |  | 0.02943% | 18836.48 | 16365.51 | 2470.97 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.61970 | 2637 - Misc Equip | This project is to capture costs of a misc equipment project for Paducah, KY. This is for cost center 2637. This is for fiscal year 2024. Equip incl. (4) Mueller no-blo kits at $4,400 ea, a Jamison bi-directional insertion tool at $11,100, (4) Sensit Gol | 107084.44 | 104940.47 | 2143.97 |  | 0.1673% | 107084.44 | 104940.47 | 2143.97 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-05-30 | 05
050.61977 | 050.009.2735.Misc.Equip | Purchase 4 VLOC3 Line Locators, 2 Sensit Gold | 29040.24 | 25434.02 | 3606.22 |  | 0.04537% | 29040.24 | 25434.02 | 3606.22 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.61978 | 050.009.2737.Misc.Equip | Purchasing 1 tapping machine, 2 VLOC3 pipe locators, 1 Drive by WMR unit, and 1 powermax plasma cutter. | 43322.44 | 34350.4 | 8972.04 |  | 0.06768% | 43322.44 | 34350.4 | 8972.04 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.61981 | 050.009.2734.BG.Equipment | Purchase MetroTech Locators (3 @ $4,600 ea), Poly Tapping Machine (1 @ $23,148), TDW Tapping Gun (1 @ $3,400), Torch Beveling Machine (1 @ $2,500), Water Pump (1 @ $2,000), and Sensit Gold (4 @ $1,400) | 68946.26 | 61889.61 | 7056.65 |  | 0.1077% | 68946.26 | 61889.61 | 7056.65 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-09-30 | 09
050.61984 | 050.009.2635Equipment | Purchase Mazco Safety Stopper (1 @ $23,023) Ritmo Aligner 63 Clamp 1/2"-2" 45&90 (1 @ $1,820) Metrotech 810 Locator (1 @ $3,140) 2" Footage piercing tool (aka Mole) and control box w/ hose (1 @ $4,192) Crystal Guage w/case (1 @ $3,208) | 46200.99 | 43407.87 | 2793.12 |  | 0.07218% | 46200.99 | 43407.87 | 2793.12 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.61993 | 050.009.2636 Equipment | Purchase Stihl TS 800 Concrete Saw (2 @ $2,015 ea) GFCP Boss III Fusion Processor (2 @ $4,700 ea) Mueller Service Tooling (3 @ $4,000 ea) 2" Piercing Mole with hose and controller (1 @ $4,192) PLCS Stop Changer (1 @ $4,500) Jameson Direction Mainline ins | 149126.53 | 170473.67 | -21347.14 |  | 0.233% | 149126.53 | 170473.67 | -21347.14 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-05-31 | 05
050.61994 | 050.009.2651 Equipment | Purchase VMD Tablet w/software dock and car charger (2 @ $6,417 ea) Current Mapper (1 @ $12,089) 8100 Receiver for Current Mapper (1 @ $2,840) Power Inverter for Current Mapper (1 @ $1,400) | 36369.78 | 34175.06 | 2194.72 |  | 0.05682% | 36369.78 | 34175.06 | 2194.72 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-01-31 | 01
050.61995 | 050.009.2736 Equipment | Purchase Mueller Valve Changer (1 @ $4,341) Metrotech 810 Locator (1 @ $3,140) Ritmo Aligner 63 Clamp 1/2"-2" 45&90 (1 @ $1,820) Jameson 1/8"x300ft complete kit (1 @ $1,100) | 14480.29 | 12759.94 | 1720.35 |  | 0.02262% | 14480.29 | 12759.94 | 1720.35 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.62002 | COM.2636.WENDALLFORDFIREMN.EX | Install 3,000' of 4" HDPE for Fire Dept. training facility | -14988.66 | 65131.16 | -80119.82 |  | 0.05376% | 34411.28 | 65131.16 | -30719.88 | 2023-10-01 | 2024-09-30 | 2023-09-01 | 09 | 2023-09-28 | 09
050.62003 | 050.009.2738.Misc.Equip | 2 Sensit Gold leak detectors, 2 clamp kits, 1 Easylink device, 1 Motor angle drive tap machine, 1 Squeeze tool | 30032.99 | 29087.43 | 945.56 |  | 0.04692% | 30032.99 | 29087.43 | 945.56 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2023-12-31 | 12
050.62004 | 050.009.2739.Misc.Equip | 2 Sensit Gold leak detectors, 1 LZ30 gas trac leak detector, 1 Squeeze tool, 1 Sure-loc Locator | 29929.3 | 27188.33 | 2740.97 |  | 0.04676% | 29929.3 | 27188.33 | 2740.97 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-08-31 | 08
050.62042 | COM.2734.Sterling Business | Install approx. 3400' of 4" PE and 1500' of 2" PE to serve new business park off Russellville Rd. Delveoper to open and close ditch. Company labor to install pipe. Customer to pay AIC | 10463.59 | 83624.08 | -73160.49 |  | -0.01206% | -7717.69 | 83624.08 | -91341.77 | 2023-10-01 | 2024-09-30 | 2023-08-28 | 08 | 2024-01-31 | 01
050.62044 | PRP.2737.Locust St | **** 2024 PRP **** Project created to order materials on Oct 1st Fiscal 2024 no charges will occur until after Oct 1st. Replace 1,557'of 2" Bare Steel, 141' of 2" Hot Tar,324' of 2" Mill Wrap, 803' of Fusion Bond Epoxy, 970' of 4" Bare Steel, with 2 | 465544.7 | 444910.93 | 20633.77 |  | 0.7273% | 465544.7 | 444910.93 | 20633.77 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-03-30 | 03
050.62066 | PRP.2634.Bell Dr | **** 2024 PRP **** Project created to order materials on Oct 1st Fiscal 2024 no charges will occur until after Oct 1st. Replace 226' of 4" Steel unknown coating , 428' of 4" Mill Wrap, 1,084' of 2" Mill Wrap, 1,356' of 4" Painted, 918' of 3" Painted | 289331.39 | 451489.31 | -162157.92 |  | 0.452% | 289331.39 | 451489.31 | -162157.92 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-01-02 | 01
050.62067 | PRP.2736.Church St Crofton | **** 2024 PRP **** Project created to order materials on Oct 1st Fiscal 2024 no charges will occur until after Oct 1st. Replace 54' of 2" Epoxy, 889' of 1.50" Bare Steel, 330' of 2" Mill Wrap Bare Joint, 1,765' of 2" Painted Steel, 110' of 1.25" Bare | 388848.28 | 551806.44 | -162958.16 |  | 0.6075% | 388848.28 | 551806.44 | -162958.16 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2023-12-08 | 12
050.62075 | PRP.2737.Lancaster to Stanford | Project is for Land rights and Survey only for the 60,500' of 4" Bare Steel to be replaced with 8" FBE Steel in FY2025. A seperate project will be created for the actual construction in FY2025 | 1845987.02 | 2204869.48 | -358882.46 |  | 2.884% | 1845987.02 | 2204869.48 | -358882.46 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-09-30 | 09
050.62081 | PRP.2637.Cardinal Ln | **** 2024 PRP **** Project created to order materials on Oct 1st Fiscal 2024 no charges will occur until after Oct 1st. Replace 259' of 3" Bare Steel, 5,249' of 6" Mill Wrap Bare Joint, 105' of 2" Steel, unknown coating, 1,076' of 2" Mill Wrap Bare J | 1076631.65 | 1059505.5 | 17126.15 |  | 1.682% | 1076631.65 | 1059505.5 | 17126.15 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-02-28 | 02
050.62083 | RES.2636.COUNTRYCLUBLN.MN.EXT | Install 600' of 2" HDPE for new home, Ret.300' of 2" plastic | 3070.24 | 6140.78 | -3070.54 |  | 0.01349% | 8636.17 | 6140.78 | 2495.39 | 2023-10-01 | 2024-09-30 | 2023-09-01 | 09 | 2023-09-25 | 09
050.62084 | PRP.2734.N Sunrise Dr | **** 2024 PRP **** Project created to order materials on Oct 1st Fiscal 2024 no charges will occur until after Oct 1st. Replace 2,237' of 2" Bare Steel, 7' of 4" Mill Wrap, 6' of 1.25" PE, 168 of 2' HDPE, 457' of 2" Mill Wrap, 37' of 2" PE, 577' of 3 | 458214.11 | 437266.78 | 20947.33 |  | 0.7158% | 458214.11 | 437266.78 | 20947.33 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-04-30 | 04
050.62092 | PRP.2735.W Union St | See Project Long Description / Notes | 383011.02 | 322584.13 | 60426.89 |  | 0.5983% | 383011.02 | 322584.13 | 60426.89 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-04-30 | 04
050.62093 | PRP.2734.Johnson Dr | See Project Long Description / Notes | 362896.52 | 357275.37 | 5621.15 |  | 0.5669% | 362896.52 | 357275.37 | 5621.15 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-04-30 | 04
050.62094 | PRP.2737.Logan Ave | See Project Long Description / Notes | 629817.63 | 683691.57 | -53873.94 |  | 0.9839% | 629817.63 | 683691.57 | -53873.94 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-05-02 | 05
050.62098 | PRP.2738.E Grundy Ave | See project Long Description/Notes | 405666.79 | 620611.14 | -214944.35 |  | 0.6337% | 405666.79 | 620611.14 | -214944.35 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-05-31 | 05
050.62102 | PRP.2738.Shawnee Dr | See Project Long Description / Notes *** Revision Comment*** Project is not overbudget but is over the final approvers limit with overheads. | 565850.03 | 544831.72 | 21018.31 |  | 0.884% | 565850.03 | 544831.72 | 21018.31 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-05-31 | 05
050.62103 | PRP.2738.US 528 | **** 2024 PRP **** Project created to order materials on Oct 1st Fiscal 2024 no charges will occur until after Oct 1st. Replace 2,175' of2" Painted, 379' of 2" Mill Wrap, 1,168' of 4" Painted, 898' of 2" Epoxy, 1,181' of 4" Mill Wrap, 171' of2" Bare | 1162591.27 | 1301903.25 | -139311.98 |  | 1.816% | 1162591.27 | 1301903.25 | -139311.98 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-09-30 | 09
050.62117 | COMM.SPORTSCOMPLEXPH2.MN.EXT | Install 480' of 4" HDPE for Sports complex | -194.54 | 7768.93 | -7963.47 |  | 0.002138% | 1368.55 | 7768.93 | -6400.38 | 2023-10-01 | 2024-09-30 | 2023-09-08 | 09 | 2023-09-22 | 09
050.62118 | RES.2635.FORDSFERRYRD.MN.EXT | Install 150' of 2" HDPE for new customer | 1478.07 | 1171.45 | 306.62 |  | 0.002309% | 1478.07 | 1171.45 | 306.62 | 2023-10-01 | 2024-09-30 | 2023-09-11 | 09 | 2023-09-25 | 09
050.62182 | 050.009.2636.Owensboro Out. | owensboro outage | -2020.53 | 182321.46 | -184341.99 |  | 0.08242% | 52758.65 | 182321.46 | -129562.81 | 2023-10-01 | 2024-09-30 | 2023-09-14 | 09 | 2023-09-30 | 09
050.62434 | 2734.Russellville Med Ctr 4in | Install approximately 3200' of 4" PE to replace 2" steel section along HWY 431. Team Construction wiill install the pipe and Company Inspection will be utilized. | 1023291.95 | 1022284.57 | 1007.38 |  | 1.599% | 1023291.95 | 1022284.57 | 1007.38 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-02-29 | 02
050.62480 | 050.009.WMR Shelbyville | Purchase 3218 WMR devices for Shelbyville KY at 57.24 ea. | 258061.06 | 259068.25 | -1007.19 |  | 0.4031% | 258061.06 | 259068.25 | -1007.19 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-06-30 | 06
050.62582 | 050.3302.KY.Desktops.FY24 | Purchase replacement desktop and monitors for Kentucky | 7919.04 | 12881.42 | -4962.38 |  | 0.01237% | 7919.04 | 12881.42 | -4962.38 | 2023-10-01 | 2024-09-30 | 2023-10-26 | 10 | 2024-09-30 | 09
050.62583 | 050.3302.KY.Laptops.FY24 | Purchase replacement laptops and monitors for Kentucky | 21111.04 | 50789.52 | -29678.48 |  | 0.03298% | 21111.04 | 50789.52 | -29678.48 | 2023-10-01 | 2024-09-30 | 2023-10-26 | 10 | 2024-09-30 | 09
050.62584 | 050.3302.KY.MDT.FY24 | Purchase replacement MDTs for Kentucky | 110814.03 | 153350 | -42535.97 |  | 0.1731% | 110814.03 | 153350 | -42535.97 | 2023-10-01 | 2024-09-30 | 2023-10-26 | 10 | 2024-09-30 | 09
050.62592 | 621 Willow way main ext. | 425 feet of 2" main added to serve residential customer | -1568.36 | 3614.11 | -5182.47 |  | -0.00245% | -1568.36 | 3614.11 | -5182.47 | 2023-10-01 | 2024-09-30 | 2023-10-26 | 10 | 2023-10-31 | 10
050.62614 | 335 Hannover Dr main ext. | Extending 530' of 2" HDPE main to serve a new residential customer | -8.47 | 8735.47 | -8743.94 |  | -1.323e-05% | -8.47 | 8735.47 | -8743.94 | 2023-10-01 | 2024-09-30 | 2023-11-14 | 11 | 2024-01-12 | 01
050.62615 | RES.2637.Ogden Lndg Rd Ext | Install 250 feet of 2 inch poly main. Retire farm tap regulator. Install new 3/4 inch DRS at new location. One customer requesting natural gas. | 25568.36 | 25698.9 | -130.54 |  | 0.03994% | 25568.36 | 25698.9 | -130.54 | 2023-10-01 | 2024-09-30 | 2023-10-23 | 10 | 2023-11-30 | 11
050.62617 | 050.2638.Hardeman Fm Tap Repl | In our ongoing effort to get rid of farm tap regulators we propose to install 2,250 feet of 2 inch poly main. We will retire two small (3/4 inch) stations as well as 13 farm tap regulators.. Services will be charged to non-growth functionals. | 83798 | 77844.02 | 5953.98 |  | 0.1309% | 83798 | 77844.02 | 5953.98 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-05-30 | 05
050.62618 | COM.2734.Keystone Commons | Install approx. 575' of 2" PE to serve 5 Star and other Commercials lots. 100% AIC. Customer to open and close ditch. Company labor to install pipe | 2356.78 | 7830.5 | -5473.72 |  | 0.003682% | 2356.78 | 7830.5 | -5473.72 | 2023-10-01 | 2024-09-30 | 2023-10-30 | 10 | 2024-01-31 | 01
050.62619 | Crossroads Industrial Main ex | Adding 380' of 2" HDPE main to serve future commercial growth | -13302.19 | 26619.18 | -39921.37 |  | -0.02078% | -13302.19 | 26619.18 | -39921.37 | 2023-10-01 | 2024-09-30 | 2023-10-30 | 10 | 2024-01-31 | 01
050.62622 | PRP.2736.Railroad Street | See Project Long Description/Notes | 471447.56 | 501496.61 | -30049.05 |  | 0.7365% | 471447.56 | 501496.61 | -30049.05 | 2023-10-01 | 2024-09-30 | 2023-11-06 | 11 | 2024-01-05 | 01
050.62628 | RES.2637.Gull Harbor Cove Ext | Install 300 feet of 2 inch poly gas main for three new residential customers in Marina Village Subdivision. | 9182.93 | 4945.25 | 4237.68 |  | 0.01435% | 9182.93 | 4945.25 | 4237.68 | 2023-10-01 | 2024-09-30 | 2023-10-23 | 10 | 2023-12-30 | 12
050.62629 | 050.009.2635.Jenkins Rd. | Install 2,000' of 2" HDPE. for new customers | 6215.74 | 19321.96 | -13106.22 |  | 0.00971% | 6215.74 | 19321.96 | -13106.22 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-09-30 | 09
050.62636 | Saddlebred Pointe Phase 1 | Adding 2200' of 2" main to serve a new residential development. | 23741.89 | 54688.11 | -30946.22 |  | 0.03709% | 23741.89 | 54688.11 | -30946.22 | 2023-10-01 | 2024-09-30 | 2023-09-22 | 09 | 2024-01-12 | 01
050.62637 | RES.2636.HEATHERSTONEPHII | Install 2800' of 4" HDPE and 500' of 2" HDPE for subdivision growth | 82985.32 | 76667.79 | 6317.53 |  | 0.1296% | 82985.32 | 76667.79 | 6317.53 | 2023-10-01 | 2024-09-30 | 2023-10-02 | 10 | 2024-01-15 | 01
050.62639 | FY24 Wellhead Repl | Replacing Wellheads for AEC Storage Fields in Hopkins County | 1055109.74 | 2263748.61 | -1208638.87 |  | 1.648% | 1055109.74 | 2263748.61 | -1208638.87 | 2023-10-01 | 2024-09-30 | 2023-11-01 | 11 | 2024-09-30 | 09
050.62643 | Ascend Elements Ext | Install Approx. 2000' of 6" Steel main to Ascend Elements in Hopkinsville KY to provide them with initial (Phase I) Heat & Processing Load (150 MCFH Firm) | 968190.45 | 1643472.44 | -675281.99 |  | 1.513% | 968190.45 | 1643472.44 | -675281.99 | 2023-10-01 | 2024-09-30 | 2023-08-16 | 08 | 2024-05-31 | 05
050.62645 | RES.2636.LIVIA.MN.EXT | Install 200' of 2" HDPE for a new customer | 2467.38 | 5043.95 | -2576.57 |  | 0.003855% | 2467.38 | 5043.95 | -2576.57 | 2023-10-01 | 2024-09-30 | 2023-10-16 | 10 | 2023-10-31 | 10
050.62651 | 050.009.2736 Struct. Improv. | Paint office, table and chairs for meeting room, office for two offices | 35932.39 | 34350.4 | 1581.99 |  | 0.05613% | 35932.39 | 34350.4 | 1581.99 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-04-15 | 04
050.62653 | 050.009.2737.Danville.Shed | A new storage shed is being built due to the old one being destroyed by severe weather. | 51198.89 | 58303.68 | -7104.79 |  | 0.07998% | 51198.89 | 58303.68 | -7104.79 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-09-30 | 09
050.62666 | 114 Sherman Ave | 100' main extension for residential property | 2381.63 | 1722.11 | 659.52 |  | 0.003721% | 2381.63 | 1722.11 | 659.52 | 2023-10-01 | 2024-09-30 | 2023-11-13 | 11 | 2024-01-12 | 01
050.62667 | 050.2634 Struct.Improvment | Madisonville Structural Improvements - Warehouse concrete and outdoor lighting | 57636.15 | 57636.15 | 0 |  | 0.09004% | 57636.15 | 57636.15 | 0 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-04-30 | 04
050.62668 | 2739.Wild Turkey Reinf | Project to replace HPD to serve expansion of Wild Turkey Distillery. | -1129926.21 | 2433574.13 | -3563500.34 |  | -1.765% | -1129926.21 | 2433574.13 | -3563500.34 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-09-30 | 09
050.62671 | RES.2636.3281HAYDENRD.MN.EXT | Install 350' of 2" HDPE for new custmer | 10174.71 | 11504.98 | -1330.27 |  | 0.0159% | 10174.71 | 11504.98 | -1330.27 | 2023-10-01 | 2024-09-30 | 2023-11-02 | 11 | 2023-11-16 | 11
050.62691 | RES.2636.FOXRUN.MN.EXT | Install 450' of 2" HDPE for new customer | 3003.41 | 4796.08 | -1792.67 |  | 0.004692% | 3003.41 | 4796.08 | -1792.67 | 2023-10-01 | 2024-09-30 | 2023-11-06 | 11 | 2023-11-27 | 11
050.62694 | 050.2635 Office Furn. | Princeton Structural Improvements - Cubicles for office space | 16628.72 | 14671.2 | 1957.52 |  | 0.02598% | 16628.72 | 14671.2 | 1957.52 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-03-15 | 03
050.62716 | PRP.2634.Hall Street | Revision Comments: Orginal Estimate $893,061.00 Concrete, Asphalt repair and Camera inspection exceeded original estimate. | 1193400 | 1173626.13 | 19773.87 |  | 1.864% | 1193400 | 1173626.13 | 19773.87 | 2023-10-01 | 2024-09-30 | 2023-12-18 | 12 | 2024-05-31 | 05
050.62720 | 050.2638.N 5th St Retirement | Retire 80 feet of 2 inch poly mmain. Main used to serve three customers. The December 2021 tornado damaged all three buildings. Now all three have been razed. No need for this main that is in an alley. | 279.84 | 490.46 | -210.62 |  | 0.0004372% | 279.84 | 490.46 | -210.62 | 2023-10-01 | 2024-09-30 | 2023-11-13 | 11 | 2023-11-30 | 11
050.62733 | 2637.Struct Imp FY 24 | This project is to capture the costs associated with improvements to the warehouse and grounds at our 3034 Parker Street Paducah office. Includes sealing of the parking lot, landscaping, a Verkada camera system, and a 22 wat back up generator. | 35640.36 | 59907.4 | -24267.04 |  | 0.05568% | 35640.36 | 59907.4 | -24267.04 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-09-30 | 09
050.62741 | 2638.Struct Imp FY 24 | This project is to capture the costs associated with improvements to the warehouse and grounds at our James Street Mayfield office.Includes structural improvements, a Verkada camera system, and a 13 watt backup generator. | 202139.42 | 161067.39 | 41072.03 |  | 0.3158% | 202139.42 | 161067.39 | 41072.03 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-09-30 | 09
050.62761 | 2612.KY.Corrector FY24 | Approval needed to replace 6 obsolete correctors in KY | 30561.78 | 36750.27 | -6188.49 |  | 0.04774% | 30561.78 | 36750.27 | -6188.49 | 2023-10-01 | 2024-09-30 | 2024-01-30 | 01 | 2024-09-30 | 09
050.62762 | 2612.KY.Emerg. Regs | Approval needed purchase 5 emergency regulators for 2612 | 46090.3 | 49000.36 | -2910.06 |  | 0.072% | 46090.3 | 49000.36 | -2910.06 | 2023-10-01 | 2024-09-30 | 2024-03-31 | 03 | 2024-09-30 | 09
050.62763 | 2612.KY.ERX Upgrade | Approval needed to pruchase 25 ERX for 2612 | 140581.12 | 153126.12 | -12545 |  | 0.2196% | 140581.12 | 153126.12 | -12545 | 2023-10-01 | 2024-09-30 | 2024-03-31 | 03 | 2024-09-30 | 09
050.62765 | 2612.KY.Pneum Controllers | approval is needed to purchase 6 Pneumatic Controllers for 2612 cost center | 11697.29 | 36750.27 | -25052.98 |  | 0.01827% | 11697.29 | 36750.27 | -25052.98 | 2023-10-01 | 2024-09-30 | 2024-03-31 | 03 | 2024-09-30 | 09
050.62767 | 2634.HWY.1078RELOCTE | Replace 80' of 2" Stl. for state project | 78.95 | 48736.43 | -48657.48 |  | 0.0001233% | 78.95 | 48736.43 | -48657.48 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-01-31 | 01
050.62783 | PRP.2737.W Walnut RR xing | See project long description/notes | 19441.11 | 316775.4 | -297334.29 |  | 0.03037% | 19441.11 | 316775.4 | -297334.29 | 2023-10-01 | 2024-09-30 | 2023-11-30 | 11 | 2024-12-28 | 12
050.62788 | COM.2734.Menards BG | Install approx. 2300' of 4" PE and 500' of 2" PE to serve the Menards Development. Developer to open and close ditch, Company labor to install pipe. AIC of $15,200 | 11815.08 | 43380.59 | -31565.51 |  | 0.01846% | 11815.08 | 43380.59 | -31565.51 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-03-31 | 03
050.62798 | COMM.DUNAWAYTIMBER.MN.EXT | Install 1700' of 2" HDPE for Commercial customer | -5805.22 | 18288.22 | -24093.44 |  | -0.009069% | -5805.22 | 18288.22 | -24093.44 | 2023-10-01 | 2024-09-30 | 2023-11-27 | 11 | 2023-12-15 | 12
050.62808 | PRP.2636.Omega Street | See Project Long Description /Notes | 577816.87 | 529880.99 | 47935.88 |  | 0.9027% | 577816.87 | 529880.99 | 47935.88 | 2023-10-01 | 2024-09-30 | 2023-12-11 | 12 | 2024-04-30 | 04
050.62809 | 2734.KYTC Nashville Rd.BG | Approx. 3505' of 2" PE and 2100' of 6" PE to resolve conflicts with KYTC project 3-8857 along Nashville Rd. in Bowling Green. Team Construction will complete the work under MSA pricing and Company FCC will inspect. Project is not reimbursable | 1265015.96 | 923123.67 | 341892.29 |  | 1.976% | 1265015.96 | 923123.67 | 341892.29 | 2023-10-01 | 2024-09-30 | 2024-01-02 | 01 | 2024-12-31 | 12
050.62882 | 2738.1048.Roberts rd.Main.Ext | 550' Main extension to serve residential customer on Roberts rd | -488.67 | 2074.88 | -2563.55 |  | -0.0007634% | -488.67 | 2074.88 | -2563.55 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2023-12-31 | 12
050.62883 | RES.2637NUNNBLVD.MN.EXT | Install 500' of 2" HDPE for new customers | 6715.97 | 3854.39 | 2861.58 |  | 0.01049% | 6715.97 | 3854.39 | 2861.58 | 2023-10-01 | 2024-09-30 | 2023-12-04 | 12 | 2024-01-31 | 01
050.62884 | 050.2637.N Friendship Phase 4 | Install almost 2,600 feet of 2 and 4 inch poly pipe. 2,230 feet of poly pipe is to be retired. 2,180 feet is on private property. This is 97.7% which is reimbursable. Thism is the second phase of KYTC road project. Current let date is July 15, 2024 *I | 62716.07 | 264385.56 | -201669.49 |  | 0.09798% | 62716.07 | 264385.56 | -201669.49 | 2023-10-01 | 2024-09-30 | 2024-05-01 | 05 | 2024-09-30 | 09
050.62912 | 2739.Robin Rd main ext | 840' of 2" HDPE being added to serve residential development | 19198.47 | 21006.75 | -1808.28 |  | 0.02999% | 19198.47 | 21006.75 | -1808.28 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-01-31 | 01
050.62916 | 2739.Fairfield Inn | 400' of 2" HDPE main extended to serve Fairfield Inn | 38966.05 | 36678 | 2288.05 |  | 0.06087% | 38966.05 | 36678 | 2288.05 | 2023-10-01 | 2024-09-30 | 2023-12-01 | 12 | 2024-01-31 | 01
050.62922 | RES.2636.CHARLIEBROWNRD.MN.EX | Install 800' of 2" HDPE for new customers | -234.85 | 8473.99 | -8708.84 |  | -0.0003669% | -234.85 | 8473.99 | -8708.84 | 2023-10-01 | 2024-09-30 | 2023-12-18 | 12 | 2024-02-28 | 02
050.62934 | 050.2634.Misc.Equipment | Purchase (1) Perco Axial Cutter 2"-8" PAC28 | 10160.71 | 9530.17 | 630.54 |  | 0.01587% | 10160.71 | 9530.17 | 630.54 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-03-31 | 03
050.62941 | PRP.2637.Hayes Avenue | See Project Long Description/Notes | 654998.52 | 729644.08 | -74645.56 |  | 1.023% | 654998.52 | 729644.08 | -74645.56 | 2023-10-01 | 2024-09-30 | 2024-01-08 | 01 | 2024-05-24 | 05
050.62985 | RES.2638.E Ann St Main Ext | Install 100 ft of 2 inch poly main for one new residential customer in Mayfield, KY at 321 East Ann Street | 6140.23 | 4496.35 | 1643.88 |  | 0.009592% | 6140.23 | 4496.35 | 1643.88 | 2023-10-01 | 2024-09-30 | 2024-01-02 | 01 | 2024-09-30 | 09
050.62992 | PRP.2734.Kenton Street | See Project Long Description/Notes | 279376.31 | 319445.25 | -40068.94 |  | 0.4364% | 279376.31 | 319445.25 | -40068.94 | 2023-10-01 | 2024-09-30 | 2024-01-14 | 01 | 2024-05-30 | 05
050.63017 | RES.2636.TIMBERTRAIL.MN.EXT | Install 150' of 2" HDPE for new customer | 3733.75 | 1105.62 | 2628.13 |  | 0.005833% | 3733.75 | 1105.62 | 2628.13 | 2023-10-01 | 2024-09-30 | 2024-02-28 | 02 | 2024-02-28 | 02
050.63029 | 050.2637.MLK Blvd Retirement | Retire 140 feet of 1 1/4 inch steel main | 362 | 612.54 | -250.54 |  | 0.0005655% | 362 | 612.54 | -250.54 | 2023-10-01 | 2024-09-30 | 2024-01-08 | 01 | 2024-09-30 | 09
050.63044 | RES.2734.SouthParkCommonsPH2 | Install approx. 5500' of 2" PE and 1100' of 4" PE to serve phase 2 of the developement. Developer to open/close ditch and Company labor to install pipe. | 33602.52 | 46828.02 | -13225.5 |  | 0.05249% | 33602.52 | 46828.02 | -13225.5 | 2023-10-01 | 2024-09-30 | 2024-01-22 | 01 | 2024-04-30 | 04
050.63050 | RES.2734.South Haven PH1 | First phase of South Haven Development. 625' of 2" PE and 1825' of 4" PE. Developer to open and close ditch and Company labor to install the pipe. | 25134.88 | 25610.98 | -476.1 |  | 0.03927% | 25134.88 | 25610.98 | -476.1 | 2023-10-01 | 2024-09-30 | 2024-01-22 | 01 | 2024-06-30 | 06
050.63090 | 2612.KY.Testing Equipment | KY Prover replacement program and misc. calibration equipmnet | 170876.29 | 183390 | -12513.71 |  | 0.2669% | 170876.29 | 183390 | -12513.71 | 2023-10-01 | 2024-09-30 | 2023-08-15 | 08 | 2024-08-01 | 08
050.63100 | 2735.R&S.Salvage | 3800' of 4" HDPE | 21296.46 | 29332.76 | -8036.3 |  | 0.03327% | 21296.46 | 29332.76 | -8036.3 | 2023-10-01 | 2024-09-30 | 2024-01-22 | 01 | 2024-08-31 | 08
050.63106 | PRP.2636.KY 1473 Phase Two | See Project Long Description /Notes | 533061.51 | 675787.49 | -142725.98 |  | 0.8328% | 533061.51 | 675787.49 | -142725.98 | 2023-10-01 | 2024-09-30 | 2024-01-30 | 01 | 2024-06-30 | 06
050.63126 | PRP.2636.E 9th Street | See Project Long Description/Notes | 79353.35 | 235749.13 | -156395.78 |  | 0.124% | 79353.35 | 235749.13 | -156395.78 | 2023-10-01 | 2024-09-30 | 2024-01-08 | 01 | 2024-03-01 | 03
050.63165 | 2636.OWB TB#1 Reg/Reliefs | Project to replace Fisher regulator and Rockwell relief valves with Mooney regulator and relief valves | 49643.6 | 54673.78 | -5030.18 |  | 0.07755% | 49643.6 | 54673.78 | -5030.18 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-07-30 | 07
050.63166 | 050.2609 Hickory Methane Det | Ordering material for Methane Leak Detection at Hickory Storage Field | 60385.8 | 130606.38 | -70220.58 |  | 0.09434% | 60385.8 | 130606.38 | -70220.58 | 2023-10-01 | 2024-09-30 | 2024-02-01 | 02 | 2024-09-30 | 09
050.63168 | 050.2609 Grandview Methane Det | Methane Detection monitoring equipment for Grandview Storage field | 71250.98 | 131610.2 | -60359.22 |  | 0.1113% | 71250.98 | 131610.2 | -60359.22 | 2023-10-01 | 2024-09-30 | 2024-02-01 | 02 | 2024-09-30 | 09
050.63170 | 050.2637.N 21 st Retirement | Retire 53 feet of 2 inch steel main | 290.8 | 1093.64 | -802.84 |  | 0.0004543% | 290.8 | 1093.64 | -802.84 | 2023-10-01 | 2024-09-30 | 2024-01-29 | 01 | 2024-03-30 | 03
050.63179 | 2734.Franklynn Hills Ext.Adv | Extend approx. 70' of 2" PE to serve one new residential customer in Adairville. Company labor to install main. | 3761.17 | 2420.49 | 1340.68 |  | 0.005876% | 3761.17 | 2420.49 | 1340.68 | 2023-10-01 | 2024-09-30 | 2024-02-01 | 02 | 2024-09-30 | 09
050.63187 | COM.2734.Hennessy Way | Install approx. 450' 4" PE to serve commercial development off Hennessy Way. Developer to open and close ditch, Atmos Energy to install pipe and provide padding material | 5854.78 | 5785.11 | 69.67 |  | 0.009146% | 5854.78 | 5785.11 | 69.67 | 2023-10-01 | 2024-09-30 | 2024-02-05 | 02 | 2024-04-30 | 04
050.63204 | 2734.BG Structure Improvements | Bowling Green Structural Improvements approved FY24 CB- Interior painting, Security Gate and fencing, parking lot seal and resurface, overhead door opener | 43386.96 | 77023.8 | -33636.84 |  | 0.06778% | 43386.96 | 77023.8 | -33636.84 | 2023-10-01 | 2024-09-30 | 2024-02-01 | 02 | 2024-09-30 | 09
050.63208 | 050.2636.Greenville W/H | Install water heater at the Greenville Office | 7065.43 | 3667.8 | 3397.63 |  | 0.01104% | 7065.43 | 3667.8 | 3397.63 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-09-30 | 09
050.63210 | RES.2636.OPPERTUNITYWAY.MN.EX | Install 300' of 2" HDPE for new customer | 3516.36 | 3724.72 | -208.36 |  | 0.005493% | 3516.36 | 3724.72 | -208.36 | 2023-10-01 | 2024-09-30 | 2024-02-12 | 02 | 2024-02-28 | 02
050.63219 | RES.2637.Oakview Estates 2 | Install 1,625 feet of 2 inch PE main for 36 new residential lots in this phase 2 | 11064.7 | 57564.98 | -46500.28 |  | 0.01729% | 11064.7 | 57564.98 | -46500.28 | 2023-10-01 | 2024-09-30 | 2024-05-01 | 05 | 2024-08-30 | 08
050.63222 | RES.2734.Breckenridge PH3 | Install approx. 450' of 4" PE and 1100' of 2" PE to serve phase 3 of the development. Developer to open/close ditch and Company Labor to install pipe and purchase padding material | 11921.84 | 12845.06 | -923.22 |  | 0.01862% | 11921.84 | 12845.06 | -923.22 | 2023-10-01 | 2024-09-30 | 2024-02-13 | 02 | 2024-05-31 | 05
050.63226 | 2734.Creekside Bend PH1 | Install approx. 5348' of 6" PE and 1368' of 2" PE to serve phase 1 of the new development. Delveloper to open/close ditch, Company to install pipe and purchase padding material. | 122851.52 | 106788.12 | 16063.4 |  | 0.1919% | 122851.52 | 106788.12 | 16063.4 | 2023-10-01 | 2024-09-30 | 2024-02-19 | 02 | 2024-09-30 | 09
050.63251 | PRP.2636.Davies Street | Replace 401' of 2" Painted Steel with 401' of 2" HDPE | 39841.77 | 66939.98 | -27098.21 |  | 0.06224% | 39841.77 | 66939.98 | -27098.21 | 2023-10-01 | 2024-09-30 | 2024-02-15 | 02 | 2024-04-30 | 04
050.63252 | PRP.2636.Walnut Street | See Project Long Description/Notes | 105993.93 | 277266.89 | -171272.96 |  | 0.1656% | 105993.93 | 277266.89 | -171272.96 | 2023-10-01 | 2024-09-30 | 2024-02-17 | 02 | 2024-04-30 | 04
050.63266 | 2738.31 Keltner Rd | 375' of 2" Main extension to serve residential customer | 330.81 | 2225.18 | -1894.37 |  | 0.0005168% | 330.81 | 2225.18 | -1894.37 | 2023-10-01 | 2024-09-30 | 2024-02-12 | 02 | 2024-03-30 | 03
050.63297 | RES.2734.123 Modern Maid Ext | Extend approximately 165' of 2" PE to serve one residential customer. Customer to open and close ditch, Company labor to install pipe and padding material | 1102.21 | 1858.75 | -756.54 |  | 0.001722% | 1102.21 | 1858.75 | -756.54 | 2023-10-01 | 2024-09-30 | 2024-02-26 | 02 | 2024-09-30 | 09
050.63332 | PRP.2737.Portman Street | Revision Comments: Original Estimate $786,781.00 An additional 3,000' of main was replaced on this project and sidewalk replacement exceeded original estimate. | 1014383.63 | 786781.11 | 227602.52 |  | 1.585% | 1014383.63 | 786781.11 | 227602.52 | 2023-10-01 | 2024-09-30 | 2024-04-02 | 04 | 2024-09-30 | 09
050.63338 | PRP.2737.Alton Road | See Project Long Description /Notes | 640667.21 | 827231.56 | -186564.35 |  | 1.001% | 640667.21 | 827231.56 | -186564.35 | 2023-10-01 | 2024-09-30 | 2024-03-02 | 03 | 2024-09-30 | 09
050.63387 | 2738.Columbia ave | retiring 2" main on Columbia Ave bridge | 2501.86 | 59411.51 | -56909.65 |  | 0.003908% | 2501.86 | 59411.51 | -56909.65 | 2023-10-01 | 2024-09-30 | 2024-02-19 | 02 | 2024-08-30 | 08
050.63389 | PRP.2735.E Main Street | Revision Comments: original estimate $147,994.66 Additional footage replaced, traffic control and hard surface repair exceeded original estimate. | 323121.14 | 314409.04 | 8712.1 |  | 0.5048% | 323121.14 | 314409.04 | 8712.1 | 2023-10-01 | 2024-09-30 | 2024-04-02 | 04 | 2024-07-10 | 07
050.63415 | RES.050.Slaughter Rd Ext 2 | 230ft 2" PE Gas Main for 1 existing residential customer- Mike Jones @ 599 E Slaughter Rd | 1127.55 | 2032.24 | -904.69 |  | 0.001761% | 1127.55 | 2032.24 | -904.69 | 2023-10-01 | 2024-09-30 | 2024-04-17 | 04 | 2024-05-30 | 05
050.63416 | COMM.2736.RACETRAC.MN.EXT | Install 450' of 4" HDPE for Com. growth | 2157.76 | 8486.29 | -6328.53 |  | 0.003371% | 2157.76 | 8486.29 | -6328.53 | 2023-10-01 | 2024-09-30 | 2024-03-14 | 03 | 2024-07-31 | 07
050.63432 | 050.3302.KY.Routers.FY24 | Replace routers in local Kentucky Offices | 6129.01 | 14671.2 | -8542.19 |  | 0.009575% | 6129.01 | 14671.2 | -8542.19 | 2023-10-01 | 2024-09-30 | 2024-03-18 | 03 | 2024-09-30 | 09
050.63433 | US-60 Bridge Relocation | Relocating existing 4" line for a bridge replacement. | 9573.17 | 498459.17 | -488886 |  | 0.01496% | 9573.17 | 498459.17 | -488886 | 2023-10-01 | 2024-09-30 | 2024-03-11 | 03 | 2024-09-30 | 09
050.63448 | PRP.2637.Bethel Street | See project long description/notes. | 543138.35 | 590140.78 | -47002.43 |  | 0.8485% | 543138.35 | 590140.78 | -47002.43 | 2023-10-01 | 2024-09-30 | 2024-03-29 | 03 | 2024-08-09 | 08
050.63451 | INT.2636.North Main Street RS | Replace fam tap station on North Main Street in Beaver Dam | 28021.03 | 31974.89 | -3953.86 |  | 0.04378% | 28021.03 | 31974.89 | -3953.86 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-09-30 | 09
050.63452 | INT.2636.Wayne Bridge Road RS | Replace farm tap station on Wayne Bridge Road in Owensboro | 29136.84 | 29170.46 | -33.62 |  | 0.04552% | 29136.84 | 29170.46 | -33.62 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-09-30 | 09
050.63455 | RES.2736.CROUCHFARMSESTATES | Install 2200' of 2" HDPE for new subdivision in Elkton | 10107.84 | 19170.66 | -9062.82 |  | 0.01579% | 10107.84 | 19170.66 | -9062.82 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-04-30 | 04
050.63457 | 2735.South Cooper Industrial | 3300' of High Pressure 4" steel to serve new industrial park in Glasgow | -320151.89 | 561328.04 | -881479.93 |  | -0.5001% | -320151.89 | 561328.04 | -881479.93 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-09-30 | 09
050.63476 | COMM.2634.AHLSTROM.UPGRADE | Upgrade 725' of 2" HDPE with 4" HDPE for additional load | 68753.14 | 65539.68 | 3213.46 |  | 0.1074% | 68753.14 | 65539.68 | 3213.46 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-04-22 | 04
050.63499 | 2636.HWY.60 RELOCATE | Replace 450' of 4" HDPE | 34264.2 | 29985.4 | 4278.8 |  | 0.05353% | 34264.2 | 29985.4 | 4278.8 | 2023-10-01 | 2024-09-30 | 2024-04-04 | 04 | 2024-05-31 | 05
050.63500 | 2636.Hwy.142 2inPE. Relocatio | Replace 800' of 2" PE | 39592.72 | 25763.12 | 13829.6 |  | 0.06185% | 39592.72 | 25763.12 | 13829.6 | 2023-10-01 | 2024-09-30 | 2024-04-15 | 04 | 2024-05-31 | 05
050.63510 | 2738. SWEDA Upgrade | Replacing Existing 4" with 6" and 8" Poly | -31408.66 | 293013.92 | -324422.58 |  | -0.04907% | -31408.66 | 293013.92 | -324422.58 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-07-31 | 07
050.63526 | COMM.2636.CHICKFILA.MN.EXT | Install 225' of 2" HDPE for one new customer | 3897.72 | 1490.3 | 2407.42 |  | 0.006089% | 3897.72 | 1490.3 | 2407.42 | 2023-10-01 | 2024-09-30 | 2024-04-08 | 04 | 2024-04-17 | 04
050.63527 | 050.009.2734.Locators | Seven locators to be purchased for each office in KY not including the main hubs. | 64918.03 | 62841.64 | 2076.39 |  | 0.1014% | 64918.03 | 62841.64 | 2076.39 | 2023-10-01 | 2024-09-30 | 2024-04-01 | 04 | 2024-09-30 | 09
050.63534 | PRP.2636.KY - 171 | Replace 3,266' of 4" bare steel and 15' of 4" HDPE with 3,248' of 4" HDPE. | 213943.76 | 465298.82 | -251355.06 |  | 0.3342% | 213943.76 | 465298.82 | -251355.06 | 2023-10-01 | 2024-09-30 | 2024-04-20 | 04 | 2024-06-30 | 06
050.63535 | 2634.BIGLOTSRELOCATE | Relocate 250' of 4" Stl. with 4" HDPE due to washout | 4813.55 | 10140.5 | -5326.95 |  | 0.00752% | 4813.55 | 10140.5 | -5326.95 | 2023-10-01 | 2024-09-30 | 2024-04-08 | 04 | 2024-04-29 | 04
050.63555 | 2737.GilbertFarm HPD Exposure | Replace 160' of 6" steel to eliminate exposure on Harrodsburg HPD | 76106.14 | 53609.56 | 22496.58 |  | 0.1189% | 76106.14 | 53609.56 | 22496.58 | 2023-10-01 | 2024-09-30 | 2024-04-15 | 04 | 2024-09-30 | 09
050.63557 | RES.2637.NEW.HOPE.RD.EXT.II | 100' 2" PE MAIN EXT | 5203.37 | 4688.72 | 514.65 |  | 0.008129% | 5203.37 | 4688.72 | 514.65 | 2023-10-01 | 2024-09-30 | 2024-04-16 | 04 | 2024-06-30 | 06
050.63558 | 2739.Tile.Village.Relocate | Run 1500' of 2" HDPE to reroute main from under Francis Recycling | 37066.88 | 85131.38 | -48064.5 |  | 0.05791% | 37066.88 | 85131.38 | -48064.5 | 2023-10-01 | 2024-09-30 | 2024-05-01 | 05 | 2024-09-30 | 09
050.63560 | 2739.Hammond Creek Exposure | Lower 160' of 4" HP across creek in Lawrenceburg | 79044.16 | 45904.21 | 33139.95 |  | 0.1235% | 79044.16 | 45904.21 | 33139.95 | 2023-10-01 | 2024-09-30 | 2024-04-29 | 04 | 2024-09-30 | 09
050.63589 | RES.2635.4FORDSFERRYRD.MN.EXT | Install 150' of 2" HDPE for one new customer | 1115.95 | 1054.18 | 61.77 |  | 0.001743% | 1115.95 | 1054.18 | 61.77 | 2023-10-01 | 2024-09-30 | 2024-05-01 | 05 | 2024-05-30 | 05
050.63615 | COMM.2636.BIGRIVERS MN.EXT. | Install 800' of 2" HDPE for new Commercial customer | 11517.04 | 29617.36 | -18100.32 |  | 0.01799% | 11517.04 | 29617.36 | -18100.32 | 2023-10-01 | 2024-09-30 | 2024-06-03 | 06 | 2024-07-31 | 07
050.63629 | INT.2736.10 Inch Leak Repairs | Install 1500 Ft of 4 Inch HDPE to eliminate leaks | 319666.28 | 338618.52 | -18952.24 |  | 0.4994% | 319666.28 | 338618.52 | -18952.24 | 2023-10-01 | 2024-09-30 | 2024-05-01 | 05 | 2024-07-27 | 07
050.63665 | RES.2739.Twin Lakes Phase 4 | 1400' of 2" main to serve residential development. | 18245.38 | 19142.1 | -896.72 |  | 0.0285% | 18245.38 | 19142.1 | -896.72 | 2023-10-01 | 2024-09-30 | 2024-05-13 | 05 | 2024-08-31 | 08
050.63676 | COMM.2634.SOUTHHOPKINSSCHOOLR | Relocate 450' of 2" Adyl A with 450' of 2" HDPE | 6149.39 | 8944.92 | -2795.53 |  | 0.009607% | 6149.39 | 8944.92 | -2795.53 | 2023-10-01 | 2024-09-30 | 2024-06-01 | 06 | 2024-06-30 | 06
050.63684 | 2739.Midland Industrial | 500' of 2" main extension to serve commercial development | 2315.33 | 2627.56 | -312.23 |  | 0.003617% | 2315.33 | 2627.56 | -312.23 | 2023-10-01 | 2024-09-30 | 2024-05-13 | 05 | 2024-06-28 | 06
050.63685 | 2739.Carlton Crossing Develop | 200' of 2" HP steel and 1900' of 2" HDPE to serve commercial development | 26955.66 | 66679.66 | -39724 |  | 0.04211% | 26955.66 | 66679.66 | -39724 | 2023-10-01 | 2024-09-30 | 2024-05-13 | 05 | 2024-09-30 | 09
050.63697 | J&D Main Extension | 750' of 4" poly to serve J&D Distillery | 37734.61 | 42520.29 | -4785.68 |  | 0.05895% | 37734.61 | 42520.29 | -4785.68 | 2023-10-01 | 2024-09-30 | 2024-05-20 | 05 | 2024-08-30 | 08
050.63706 | PRP.2734.Pelham St. Franklin | Revision Comments: Original Estimate $ 224.564.71 An additional 1,102' of main was replaced on this project. | 254298.06 | 224564.71 | 29733.35 |  | 0.3973% | 254298.06 | 224564.71 | 29733.35 | 2023-10-01 | 2024-09-30 | 2024-05-22 | 05 | 2024-09-30 | 09
050.63720 | PRP.2734.Hopkinsville St. | See Project Long Description /Notes | 94968.34 | 102086.12 | -7117.78 |  | 0.1484% | 94968.34 | 102086.12 | -7117.78 | 2023-10-01 | 2024-09-30 | 2024-05-24 | 05 | 2024-07-27 | 07
050.63742 | 2734.BG Town Border 4 Replace | Replacement of TB4 in Bowling Green at the intersection of Smallhouse Rd. and Campbell Ln. Replace inlet piping and outlet piping. New station will be in new easement located in a fenced area. First Cut Fab to complete the work with Company Insp. | 438443.98 | 644228.19 | -205784.21 |  | 0.6849% | 438443.98 | 644228.19 | -205784.21 | 2023-10-01 | 2024-09-30 | 2024-05-20 | 05 | 2024-11-30 | 11
050.63747 | 2737.Morgan Soaper Dr | 300' main extension to serve commercial development | 2129.91 | 22901.94 | -20772.03 |  | 0.003327% | 2129.91 | 22901.94 | -20772.03 | 2023-10-01 | 2024-09-30 | 2024-06-04 | 06 | 2024-08-02 | 08
050.63763 | PRP.2738.W Court St. | See project Long Description /Notes | 95581.14 | 142924.07 | -47342.93 |  | 0.1493% | 95581.14 | 142924.07 | -47342.93 | 2023-10-01 | 2024-09-30 | 2024-05-30 | 05 | 2024-08-16 | 08
050.63766 | S.2636.SADDLEBENDPH3.MN.EXT | Install 700' of 2" HDPE for customer growth | 5250.12 | 5320.05 | -69.93 |  | 0.008202% | 5250.12 | 5320.05 | -69.93 | 2023-10-01 | 2024-09-30 | 2024-06-03 | 06 | 2024-06-28 | 06
050.63783 | PRP.2736.Greenville Road | Replace 3,019 Ft of 6Inch Bare Stl. With 2,236 Ft of 2 Inch HDPE 6 services | 154129.11 | 381041.7 | -226912.59 |  | 0.2408% | 154129.11 | 381041.7 | -226912.59 | 2023-10-01 | 2024-09-30 | 2024-06-15 | 06 | 2024-07-30 | 07
050.63795 | 2738.US-68 Roundabout relocat | Relocate 4000' of 4" HDPE and 600' of 2" HDPE for future roundabout on US-68 | 305518.72 | 356565.4 | -51046.68 |  | 0.4773% | 305518.72 | 356565.4 | -51046.68 | 2023-10-01 | 2024-09-30 | 2024-07-01 | 07 | 2024-09-30 | 09
050.63796 | PRP.2637.N 8th and 11th St. | See project long description /notes | 800667.05 | 818801.9 | -18134.85 |  | 1.251% | 800667.05 | 818801.9 | -18134.85 | 2023-10-01 | 2024-09-30 | 2024-06-15 | 06 | 2024-09-30 | 09
050.63843 | IND.2736.TODDCOUNTY MN.EXT | Install 1200' of 4" HDPE for Industrial Park | -20269.3 | 24377.35 | -44646.65 |  | -0.03167% | -20269.3 | 24377.35 | -44646.65 | 2023-10-01 | 2024-09-30 | 2024-07-01 | 07 | 2024-07-31 | 07
050.63848 | 2734.COM.Veterans Home | Install approximatly 700' of 4" PE and 100' of 2" Steel with a station to extend main to serve the new Veterans Home in Transpark | 54461.74 | 63004.37 | -8542.63 |  | 0.08508% | 54461.74 | 63004.37 | -8542.63 | 2023-10-01 | 2024-09-30 | 2024-06-17 | 06 | 2024-09-30 | 09
050.63890 | 2734.AMR.Tower Replacement | Retirement of the old/damaged wmr tower and installing a new one. | 15919.09 | 14147.31 | 1771.78 |  | 0.02487% | 15919.09 | 14147.31 | 1771.78 | 2023-10-01 | 2024-09-30 | 2024-06-24 | 06 | 2024-09-30 | 09
050.63928 | PRP.2736.Means Avenue | See Project Long Description/Notes | 327801.35 | 466497.07 | -138695.72 |  | 0.5121% | 327801.35 | 466497.07 | -138695.72 | 2023-10-01 | 2024-09-30 | 2024-07-20 | 07 | 2024-09-30 | 09
050.63942 | COMM.2636.MUHLENBERGAIRPORT.M | Install 600' of 2" HDPE at Muhlenberg Airport for new growth | 8458.85 | 6467 | 1991.85 |  | 0.01321% | 8458.85 | 6467 | 1991.85 | 2023-10-01 | 2024-09-30 | 2024-07-05 | 07 | 2024-07-31 | 07
050.63971 | PRP.2735.Cherry St. | See Project Long Description /Notes | 104440.08 | 209001.2 | -104561.12 |  | 0.1632% | 104440.08 | 209001.2 | -104561.12 | 2023-10-01 | 2024-09-30 | 2024-07-18 | 07 | 2024-09-30 | 09
050.63973 | PRP.2736.E 2nd Street | See Project Long Description/Notes | 158971.54 | 308772.04 | -149800.5 |  | 0.2483% | 158971.54 | 308772.04 | -149800.5 | 2023-10-01 | 2024-09-30 | 2024-07-31 | 07 | 2024-09-30 | 09
050.63981 | 050.2636.Calhoun Sta. | Land right purchase for Calhoun Station | 13810.1 | 14444.78 | -634.68 |  | 0.02157% | 13810.1 | 14444.78 | -634.68 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-09-30 | 09
050.64011 | PRP.2735.Hogan St. | See Project Long Description/notes | 92727.47 | 160748.89 | -68021.42 |  | 0.1449% | 92727.47 | 160748.89 | -68021.42 | 2023-10-01 | 2024-09-30 | 2024-07-31 | 07 | 2024-09-20 | 09
050.64013 | RES.2638.MALLARD.CV.MN.EXT | INSTALL 65FT OF 2" HDPE FOR SINGLE RESIDENCE | 954.56 | 1711.79 | -757.23 |  | 0.001491% | 954.56 | 1711.79 | -757.23 | 2023-10-01 | 2024-09-30 | 2024-08-13 | 08 | 2024-08-31 | 08
050.64049 | 2734.RES.Moorman Ln Ext | Extend 2" PE on Moorman Lane to serve 5 residential customers. | 1171.58 | 6406.8 | -5235.22 |  | 0.00183% | 1171.58 | 6406.8 | -5235.22 | 2023-10-01 | 2024-09-30 | 2024-06-24 | 06 | 2024-12-30 | 12
050.64065 | RES.2736.SIVLEYRDREPLACEMENT | Replace 300' of 4" HDPE | 4331.79 | 4347.75 | -15.96 |  | 0.006767% | 4331.79 | 4347.75 | -15.96 | 2023-10-01 | 2024-09-30 | 2024-08-01 | 08 | 2024-08-30 | 08
050.64072 | PRP.2634.N Franklin St. | See project Long Description /Notes | 444379.61 | 447885 | -3505.39 |  | 0.6942% | 444379.61 | 447885 | -3505.39 | 2023-10-01 | 2024-09-30 | 2024-08-02 | 08 | 2024-09-30 | 09
050.64075 | RES.2636.PRUDENLN.REPLACEMENT | Replace 220' of 2" HDPE for lake | 1423.52 | 1967.3 | -543.78 |  | 0.002224% | 1423.52 | 1967.3 | -543.78 | 2023-10-01 | 2024-09-30 | 2024-08-01 | 08 | 2024-08-31 | 08
050.64084 | New HVAC unit | New HVAC unit | 39579.25 | 41797.7 | -2218.45 |  | 0.06183% | 39579.25 | 41797.7 | -2218.45 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-09-30 | 09
050.64086 | IND.2635.MARIONTIEBACK | Install 1200' of 2" HDPE for second feed to the Industrial Park in Marion | 6398.97 | 22659.48 | -16260.51 |  | 0.009997% | 6398.97 | 22659.48 | -16260.51 | 2023-10-01 | 2024-09-30 | 2024-08-01 | 08 | 2024-08-31 | 08
050.64098 | RES.2637.BLANDVILLE.RD.MN.EXT | INSTALL 240FT OF 4" HDPE | 3095.53 | 4549.82 | -1454.29 |  | 0.004836% | 3095.53 | 4549.82 | -1454.29 | 2023-10-01 | 2024-09-30 | 2024-08-19 | 08 | 2024-08-23 | 08
050.64230 | 2734.COM.Performance Feeds Ex | Install approximately 900' of 4" PE to serve Performance Feeds Grain dryer. Customer to pay 100% AIC. Customer of open ditch and Company crew to install pipe and inspect | -25883.93 | 31584.66 | -57468.59 |  | -0.04044% | -25883.93 | 31584.66 | -57468.59 | 2023-10-01 | 2024-09-30 | 2024-08-12 | 08 | 2024-12-30 | 12
050.64231 | COMM.2636.HARTFORD.MN.EXT | Install 1,000' of 2" HDPE to remove services from High Pressure | 11298.96 | 14002.23 | -2703.27 |  | 0.01765% | 11298.96 | 14002.23 | -2703.27 | 2023-10-01 | 2024-09-30 | 2024-08-08 | 08 | 2024-09-30 | 09
050.64233 | 2734.Purple Toad Relocate | Replace approximately 450' of 4" PE to accodmodate Purple Toad entrances to new winery. Customer to pay 100% | 5709.79 | 10018.98 | -4309.19 |  | 0.00892% | 5709.79 | 10018.98 | -4309.19 | 2023-10-01 | 2024-09-30 | 2024-08-12 | 08 | 2024-09-30 | 09
050.64235 | COM.2734.Evergreen Commons Ex | Install approx. 700' of 4" PE and 268' of 2" PE to serve the commercial development off Nashville Rd. in Bowling Green. Company labor to install pipe and customer to open/close ditch | 10994.62 | 9039.84 | 1954.78 |  | 0.01718% | 10994.62 | 9039.84 | 1954.78 | 2023-10-01 | 2024-09-30 | 2024-07-31 | 07 | 2024-09-30 | 09
050.64263 | RES.2636.BRIARRIDGE.MN.EXT | Install 1500' for new subdivision growth | 26692.78 | 25679.91 | 1012.87 |  | 0.0417% | 26692.78 | 25679.91 | 1012.87 | 2023-10-01 | 2024-09-30 | 2024-08-05 | 08 | 2024-09-30 | 09
050.64296 | 2734.BG Misc Equipment FY25 | Mustang Steel Squeeze Off, Scraper Peeler Pipe/SaddelOutlet 2-6, 6" McElroy BF Cradel, 4" McElroy Iron/Trimmer Set, 2"-8" Poly Tap/Stopple Equp., SENSIT Gold G3, Valetrix 3k PSI Data Logging Guage | 1935.08 | 205975 | -204039.92 |  | 0.003023% | 1935.08 | 205975 | -204039.92 | 2023-10-01 | 2024-09-30 | 2024-08-01 | 08 | 2025-09-30 | 09
050.64312 | PRP.2635.Park Ave | See Project long Description/Notes | 215602.02 | 247295.42 | -31693.4 |  | 0.3368% | 215602.02 | 247295.42 | -31693.4 | 2023-10-01 | 2024-09-30 | 2024-08-29 | 08 | 2024-09-30 | 09
050.64336 | 2637.WOODLAND.DR.REPLACE | REPLACE 530FT OF 2" STEEL WITH 2" HDPE | 3151.93 | 18615.15 | -15463.22 |  | 0.004924% | 3151.93 | 18615.15 | -15463.22 | 2023-10-01 | 2024-09-30 | 2024-09-03 | 09 | 2024-09-06 | 09
050.64343 | COMM.2634.OLDBLACKTOPPLANT.MN | Install 500' of 2" HDPE for Old Black Top Plant | 3807.12 | 10831.36 | -7024.24 |  | 0.005948% | 3807.12 | 10831.36 | -7024.24 | 2023-10-01 | 2024-09-30 | 2024-09-03 | 09 | 2024-09-12 | 09
050.64347 | RES.2636.FIDDLESTICKS.MN.EXT | Install 500' of 2" HDPE for subdivision growth | 6329.83 | 10186.22 | -3856.39 |  | 0.009889% | 6329.83 | 10186.22 | -3856.39 | 2023-10-01 | 2024-09-30 | 2024-09-03 | 09 | 2024-09-24 | 09
050.64351 | 2637.CINDY.DR.REPLACE | REPLACE EXPOSED MAIN WITH 2" HDPE (300FT) | 14275.95 | 11855.07 | 2420.88 |  | 0.0223% | 14275.95 | 11855.07 | 2420.88 | 2023-10-01 | 2024-09-30 | 2024-09-03 | 09 | 2024-09-10 | 09
050.64353 | RES.2736.7TH.ST.MN.EXT | INSTALL 150' OF 2" HDPE | 1922.87 | 1434.63 | 488.24 |  | 0.003004% | 1922.87 | 1434.63 | 488.24 | 2023-10-01 | 2024-09-30 | 2024-09-03 | 09 | 2024-09-21 | 09
050.64361 | 2738.Taylor.Co.HS.Pool | 300' of 2" HDPE to serve Taylor County High Scheel | 863.62 | 7541.1 | -6677.48 |  | 0.001349% | 863.62 | 7541.1 | -6677.48 | 2023-10-01 | 2024-09-30 | 2024-09-02 | 09 | 2024-09-21 | 09
050.64362 | 2739.Nautical Chase Sub | 1300' of 2" HDPE to serve residential development | 2581.7 | 7217.76 | -4636.06 |  | 0.004033% | 2581.7 | 7217.76 | -4636.06 | 2023-10-01 | 2024-09-30 | 2024-09-02 | 09 | 2024-09-21 | 09
050.64383 | 2637.HWY282.FARMTAPS | INSTALL 2,650FT OF 2" HDPE FOR ODORIZED SERVICE LINES & REMOVAL OF FARM TAPS WITH STINK POTS | 61456.44 | 83095.46 | -21639.02 |  | 0.09601% | 61456.44 | 83095.46 | -21639.02 | 2023-10-01 | 2024-09-30 | 2024-09-05 | 09 | 2024-09-28 | 09
050.64438 | 050.009.2651 Leak Equipment | Purchase:1-RMLD Leak Detector, 1-VMD Leak Detector | 59069.62 | 55653.73 | 3415.89 |  | 0.09228% | 59069.62 | 55653.73 | 3415.89 | 2023-10-01 | 2024-09-30 | 2023-08-14 | 08 | 2024-12-31 | 12
050.64468 | RES.2734.ParkWLn Olde Stone | Install approx. 135' of 2" PE to serve townhomes in Olde Stone. Developer to open and close ditch, Company Labor to install pipe. | 1068.74 | 1349.8 | -281.06 |  | 0.00167% | 1068.74 | 1349.8 | -281.06 | 2023-10-01 | 2024-09-30 | 2024-09-13 | 09 | 2024-09-30 | 09
050.64480 | COM.2734.BG Airport | Install approx. 500' of 2" PE to serve new hanger. Chandler is the developer and Company labor to install in an open/close ditch. | 1070.87 | 1620.2 | -549.33 |  | 0.001673% | 1070.87 | 1620.2 | -549.33 | 2023-10-01 | 2024-09-30 | 2024-09-13 | 09 | 2024-10-31 | 10
050.64481 | 2737.Danville.Towers | Installing six new AMR towers. | 9389.13 | 898900.62 | -889511.49 |  | 0.01467% | 9389.13 | 898900.62 | -889511.49 | 2023-10-01 | 2024-09-30 | 2024-10-01 | 10 | 2025-09-30 | 09
050.64483 | 2738.Campbellsville Towers | Four Tower Site Builds for Campbellsville WMR | 3110.15 | 696011.75 | -692901.6 |  | 0.004859% | 3110.15 | 696011.75 | -692901.6 | 2023-10-01 | 2024-09-30 | 2024-10-01 | 10 | 2025-09-30 | 09
050.64631 | 2734.Equipment.Trailer | Purchase trailer for survey and leak detection. | 5168.53 | 5021.83 | 146.7 |  | 0.008074% | 5168.53 | 5021.83 | 146.7 | 2023-10-01 | 2024-09-30 | 2024-09-19 | 09 | 2024-09-30 | 09
050.64657 | 050.009.GreenvilleSta. | Purchase land rights for GreenvilleStation Replacement | 17569.63 | 18776.1 | -1206.47 |  | 0.02745% | 17569.63 | 18776.1 | -1206.47 | 2023-10-01 | 2024-09-30 | 2023-10-01 | 10 | 2024-12-31 | 12

## Criteria (hidden)
*Not blank Project
Run this query for each FY
For FY 24 it is only up to August 2024