## Project Est Cost
| Estimated | Estimated
| Start | Completion
Name | Date | Date | Estimated Costs | FY25 | FY26 | FY27 | FY28 | Total | Project Description
2739.Wild Turkey Reinforcement - Construction | 2024-10-01 | 2025-09-30 | Est. Costs w AFUDC | 2227141.6795 |  |  |  | 2227141.6795 | Replacing 17,500' of 8" Steel, 2600' of 6" HDPE, 1100' of 2" HDPE to serve Wild Turkey Expansion. Phase 2 will handle Construction
|  |  | Est. Costs w/o AFUDC | 2122137 |  |  |  | 2122137
2739.Zaring Mill to Pierce Industrial Replacement | 2024-10-01 | 2025-09-30 | Est. Costs w AFUDC | 2586764.7518 |  |  |  | 2586764.7518 | Install 5100' of 8" Steel HPD from Zaring Mill Road to Pierce Industrial Road.
|  |  | Est. Costs w/o AFUDC | 2487703 |  |  |  | 2487703
2609.Hawesville 192.624 Replacement | 2024-10-01 | 2025-09-30 | Est. Costs w AFUDC | 2677220.3395 |  |  |  | 2677220.3395 | Installing meter/regulator stations, valves and pipeline for 192.624
|  |  | Est. Costs w/o AFUDC | 2631198 |  |  |  | 2631198
2739.Ohio Valley Reinforcement Phase 2 | 2025-10-01 | 2026-03-31 | Est. Costs w AFUDC |  | 3093099 |  |  | 3093099 | Install 6800' of 8" Steel HPD from Pierce Industrial Road to Ohio Valley.
|  |  | Est. Costs w/o AFUDC |  | 2907018 |  |  | 2907018
2609.Hickory Wellhead Replacement | 2025-10-01 | 2026-09-30 | Est. Costs w AFUDC |  | 1970570 |  |  | 1970570 | Replace 10 wellheads to eliminate valve stem leaks
|  |  | Est. Costs w/o AFUDC |  | 1890300 |  |  | 1890300
2609.Liberty Purchase Inlet Piping | 2025-10-01 | 2026-09-30 | Est. Costs w AFUDC |  | 2392977 |  |  | 2392977 | Replace approximately 7000' of 6". Acquire ROW. Falls under 192.624
|  |  | Est. Costs w/o AFUDC |  | 2273328.15 |  |  | 2273328.15
2609.Hawesville 192.624 Replacement Ph2 | 2025-10-01 | 2026-09-30 | Est. Costs w AFUDC |  | 2108782 |  |  | 2108782 | Installing meter/regulator stations, valves and pipeline for 192.624
|  |  | Est. Costs w/o AFUDC |  | 2003342.9 |  |  | 2003342.9
2609.St.Charles Well Replacement | 2026-10-01 | 2027-09-30 | Est. Costs w AFUDC |  |  | 2120300 |  | 2120300 | St. Charles Kimbel #1 Well Replacement
|  |  | Est. Costs w/o AFUDC |  |  | 2021498 |  | 2021498
2609.Hawesville Domtar Line 192.624 | 2026-10-01 | 2027-09-30 | Est. Costs w AFUDC |  |  | 2405000 |  | 2405000 | Install Regulator Station / Pressure Test Per 192.624
|  |  | Est. Costs w/o AFUDC |  |  | 2287011 |  | 2287011
2609.Nortonville Purchase | 2026-10-01 | 2027-09-30 | Est. Costs w AFUDC |  |  | 2340000 |  | 2340000 | Upgrading Nortonville Purchase Site with new Meter and regulator sets
|  |  | Est. Costs w/o AFUDC |  |  | 2221380 |  | 2221380
2734.Hwy 100 Purchase Replacement | 2027-03-01 | 2027-06-30 | Est. Costs w AFUDC |  |  | 2122250 |  | 2122250 | Replace Hwy 100 purchase at TN Gas Pipeline. Estimate from First cut Fab
|  |  | Est. Costs w/o AFUDC |  |  | 2014699 |  | 2014699
2638.Symsonia HP System Replacement | 2026-10-01 | 2027-09-30 | Est. Costs w AFUDC |  |  | 3580549.7 |  | 3580549.7 | Upgrade TXGT purchase to Symsonia to eliminate 2" HPD exposed in creek and 62 f.taps. New TBS will eliminate TBS along highway. 2" HPD will be replaced w/ 20,600' of 6" PE. including the replacement of 40 short and 40 long services. Planned to be in State R/W. First Cut completing station work.
|  |  | Est. Costs w/o AFUDC |  |  | 3420944 |  | 3420944
2734. Bowling Green 192.624 | 2027-10-01 | 2028-09-30 | Est. Costs w AFUDC |  |  |  | 5312800.5 | 5312800.5 | Replace approx 11000' of 6" and 8" Pipeline per 192.624
|  |  | Est. Costs w/o AFUDC |  |  |  | 5059810 | 5059810
2637.Palma Purchase Replacement | 2027-10-01 | 2028-09-30 | Est. Costs w AFUDC |  |  |  | 2863729.05 | 2863729.05 | Replace Palma Purchase Station with new site and station. Estimate based off First Cut Fabrication pricing and scope of similar projects. Station, heater, yz odorizer, filter, check meter, canopies, fencing, design/fabrication/installation. Contract Inspection
|  |  | Est. Costs w/o AFUDC |  |  |  | 2727361 | 2727361
2636.5th St Regulator Station | 2027-10-01 | 2028-09-30 | Est. Costs w AFUDC |  |  |  | 2095785.3 | 2095785.3 | Install new larger station at 5th St Lot to replace RS 1520, RS 1312, RS 1317. Install 6000' of 8" HDPE from new station to OWB TB#2.
|  |  | Est. Costs w/o AFUDC |  |  |  | 1995986 | 1995986