## Exhibit 6 - Schedule C
Big Sandy Rural Electric Cooperative Coorporation
Case No. 2024-00287
Construction Projects
|  |  |  | Variance |  |  | Total | Total | Variance | Date | Date
|  | Annual Actual Cost | Annual Original Budget | In | Variance | Percent | Actual | Budget | In | Original | Original | Date | Date
Project | Project |  |  | Dollars | As | Of | Project | Project | Dollars | Budget | Budget | Actual | Actual
No. | Title/Description |  |  | Under/(Over) | Percent | Budget | Cost | Cost | Under/(Over) | Start | End | Start | End
21- 301 | Kizer Road Reconductor (22449) | 312006.8 | 84002 | -228004.8 | 271.4% |  | 312006.8 | 84002 | -228004.8 | 2021-01-01 | 2024-12-31 | 2022-07-19 | 2023-05-10
24- 302 | Wooten Road Mulit-Phase (23218) | 88589.2 | 81599 | -228004.8 | 8.567% |  | 88589.2 | 81599 | -6990.2 | 2021-01-01 | 2024-12-31 | 2023-10-24 | 2023-12-06
22- 303 | Stonecoal Road Multi-Phase (22410) | 106389.75 | 69489 | -36900.75 | 53.1% |  | 106389.75 | 69489 | -36900.75 | 2021-01-01 | 2024-12-31 | 2022-04-07 | 2023-01-04
23- 304 | Big Branch Abbott Reliability (23561) | 94836.75 | 137684 | 42847.25 | -31.12% |  | 94836.75 | 137684 | 42847.25 | 2021-01-01 | 2024-12-31 | 2024-08-01 | *in progress
|  | 601822.5 | 372774 | -450063.1 | 61.44% |  | 601822.5 | 372774 | -229048.5