## Schedule E
Schedule E
Shelby Energy Cooperative, Inc.
Case No. 2024-00351
Construction Work in Progress - Percent Complete*
As of 1/1/2023 - 12/31/2023
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (G/H)
1 | 315 | 2023-05-25 | 2024-04-30 | 64% | 1026707 | 1026707 | 423822.14 | 41.28%
2 | Lightning | 2023-09-01 | 2025-07-01 | 18% | 4300000 | 4300000 | 1424708.49 | 33.13%
*Should be based on expenditures including AFUDC