## (6) Schedule C
Schedule C
Shelby Energy Cooperative, Inc.
Case No. 2024-00351
Construction Projects
For 5 Years Ended December 31, 2023
Project No. | Project Title/Description | Actual Cost | Original Budget | Variance In Dollars | Variance As Percent | Percent Of Budget | Total Actual Project Cost | Variance In Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
308 | Bardstown Trail - Change 1PH to 3PH - 2.4 miles | 573461.76 | 290400 | 283061.76 | 97.47% | 197.5% | 573461.76 | 283061.76 | 2018-01-01 | 2021-12-31 | 2021-12-03 | 2023-01-23
313 | New Castle Sub Feeder 2 Change 1PH to 3PH - 3.5 miles | 456772.45 | 362670 | 94102.45 | 25.95% | 125.9% | 456772.45 | 94102.45 | 2018-01-01 | 2021-12-31 | 2021-11-23 | 2023-06-02
331 | Pea Ridge Rd. Change 2PH to 3PH | 36268.79 | 18900 | 17368.79 | 91.9% | 191.9% | 36268.79 | 17368.79 | 2018-01-01 | 2021-12-31 | 2021-08-01 | 2022-09-01
356 | Eminence Pike Change 1PH to 3PH - 2.4 miles | 275453.72 | 396000 | -120546.28 | -30.44% | 69.56% | 275453.72 | -120546.28 | 2014-01-01 | 2017-12-31 | 2017-07-20 | 2019-04-01
357 | Eminence Pike Change 2PH to 3PH - 2.8 miles | 196185.99 | 126000 | 70185.99 | 55.7% | 155.7% | 196185.99 | 70185.99 | 2014-01-01 | 2017-12-31 | 2017-06-07 | 2019-05-15
369 | Pea Ridge Rd. to Back Creek Change 2PH to 3PH - 1.3 miles | 220377.02 | 122850 | 97527.02 | 79.39% | 179.4% | 220377.02 | 97527.02 | 2018-01-01 | 2021-12-31 | 2018-10-11 | 2019-11-08
368 | Leland Dr. Change 1PH to 2PH - 0.2 miles | 58616.04 | 12600 | 46016.04 | 365.2% | 465.2% | 58616.04 | 46016.04 | 2018-01-01 | 2021-12-31 | 2021-04-05 | 2021-06-14
370 | Back Creek Rd. to Cat Ridge Rd. Change 1PH to 3PH - 1.7 miles | 439084.94 | 160650 | 278434.94 | 173.3% | 273.3% | 439084.94 | 278434.94 | 2018-01-01 | 2021-12-31 | 2020-12-21 | 2021-04-16
367 | Mason Way Change 1PH to 3PH - 0.5 miles | 191395.15 | 47250 | 144145.15 | 305.1% | 405.1% | 191395.15 | 144145.15 | 2018-01-01 | 2021-12-31 | 2021-02-01 | 2021-05-24
372 | Cooper's Bottom Change 1PH to 3PH - 1.8 miles | 100525.41 | 178605 | -78079.59 | -43.72% | 56.28% | 100525.41 | -78079.59 | 2018-01-01 | 2021-12-31 | 2021-03-31 | 2021-05-04
Project No. | Project Title/Description | Reason for variance
308 | Bardstown Trail - Change 1PH to 3PH - 2.4 miles | Inflationary pressures on material and labor. Membership difficulties resulting in change of scope. Poor production from subpar contractor crew no longer on site.
313 | New Castle Sub Feeder 2 Change 1PH to 3PH - 3.5 miles | Inflationary pressures
331 | Pea Ridge Rd. Change 2PH to 3PH | Inaccurate model map resulted in total reconductor vs adding 1 more phase
356 | Eminence Pike Change 1PH to 3PH - 2.4 miles | Combined with 357 for total project of $522,00 original budget. Finished at $471,640.
357 | Eminence Pike Change 2PH to 3PH - 2.8 miles | Combined with 356 for total project of $522,00 original budget. Finished at $471,640.
369 | Pea Ridge Rd. to Back Creek Change 2PH to 3PH - 1.3 miles | Terrain issues. Had to use bulldozer and track machine for most all project, thus increasing cost from traditional construction
368 | Leland Dr. Change 1PH to 2PH - 0.2 miles | Inflationary pressures on material and labor along with poor weather conditions for construction
370 | Back Creek Rd. to Cat Ridge Rd. Change 1PH to 3PH - 1.7 miles | Change of scope of work to re-route of line, had to add underground conductor to satisfy member
367 | Mason Way Change 1PH to 3PH - 0.5 miles | Same reason as 368. Not accessable by truck
372 | Cooper's Bottom Change 1PH to 3PH - 1.8 miles | Change of scope of work to shorten route and thus reduce costs