## Sheet1
Line No. (A) | Project No. (B) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (H/G) | Explanation
14 | SG601SW | 42090 | 42090 | 880809.36 | 2093% | This project is apart of a larger scale body of work and the estimate is managed at the funding account level
53 | DUKTKYE23 | 50000 | 2920 | 181018.1 | 6199% | This is a transportation blanket project that do not set up to have an actual estimate. The existing estimate is a generic estimate to allow capital charges to be applied
65 | MX0006935 | 268.6 | 268.6 | 58837.13 | 21905% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval
75 | MX0006936 | 268.6 | 268.6 | 50185.29 | 18684% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
159 | MX6277290 | 268.6 | 268.6 | 41770.02 | 15551% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
170 | MX0000704 | 268.6 | 268.6 | 14026.65 | 5222% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
179 | MX0000780 | 268.6 | 268.6 | 6360.14 | 2368% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
183 | MX0000782 | 268.6 | 268.6 | 5576.35 | 2076% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
193 | MX0006937 | 268.6 | 268.6 | 5281.36 | 1966% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
205 | MX0000778 | 268.6 | 268.6 | 5258.14 | 1958% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
215 | SKY2301DC | 100 | 100 | 147702.52 | 147703% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
216 | KSTMOH | 100 | 100 | 123520.64 | 123521% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
220 | SKY2210DC | 100 | 100 | 54594.2 | 54594% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
222 | KPPL | 100 | 100 | 52989.21 | 52989% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
230 | SKY2201DC | 100 | 100 | 48072.01 | 48072% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
234 | SKY2206DC | 100 | 100 | 43492.98 | 43493% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
245 | KSLNOLE | 100 | 100 | 42401.1 | 42401% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
265 | SKY2203DC | 100 | 100 | 39678.29 | 39678% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
320 | SKY2302DC | 100 | 100 | 37626.09 | 37626% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
333 | SKY2307DC | 100 | 100 | 26211.31 | 26211% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
338 | SKY2207DC | 100 | 100 | 15722.89 | 15723% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
351 | SKY2309DC | 100 | 100 | 10893.93 | 10894% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
352 | SKY2305DC | 100 | 100 | 10823.53 | 10824% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
360 | SKY2304DC | 100 | 100 | 9237.44 | 9237% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
367 | KCTRLSL | 100 | 100 | 8761.95 | 8762% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
385 | SKY2205DC | 100 | 100 | 7513.1 | 7513% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
405 | SKY2308DC | 100 | 100 | 6112.98 | 6113% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
407 | SKY2209DC | 100 | 100 | 4247.48 | 4247% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
415 | SKY2204DC | 100 | 100 | 3724.04 | 3724% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
418 | SKY2007DC | 100 | 100 | 2935.3 | 2935% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
419 | CAPAUTOKY | 100 | 100 | 2610.33 | 2610% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
421 | K2241SURK | 91.4 | 91.4 | 56668.5 | 62001% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
432 | K2152SURK | 91.4 | 91.4 | 43733.6 | 47849% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
440 | K2055SURK | 91.4 | 91.4 | 31604.97 | 34579% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
456 | KK0078S22 | 91.4 | 91.4 | 14831.08 | 16227% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
465 | KK0299S22 | 91.4 | 91.4 | 5109.43 | 5590% | This is a generic estimate, entered by a Template. This generic estimate is sent over via interface to allow the project preliminary capital spend (engineer labor, purchase orders, etc.) prior to the actual estimate design being completed. Once the estimate is approved in the interface system, it is interfaced to the asset management system where all project details, including the estimate, are reviewed before final approval.
Total: |  |  |  | 2099941.44