## SCHEDULE H
| DUKE ENERGY KENTUCKY | [6 empty] | SCHEDULE H
CASE NO. 2024-00354
CONSTRUCTION WORK IN PROGRESS - PERCENT COMPLETE
AS OF FEBRUARY 29, 2024
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (H/G)
1 | M18037501 | 2021-11-01 | 2025-04-04 | 9.52% | 8582743 | 8698488.61 | 6218997.07 | 71.5%
2 | MX3999738 | 2022-02-01 | 2025-03-13 | 2.377% | 268.6 | 951439.67 | 3462859.29 | 364%
3 | KSBDUG | 2020-01-01 | 2028-04-01 | 26.19% | 3 | 3478437.72 | 2860008.87 | 82.22%
4 | SG336SW | 2016-09-01 | 2026-06-01 | 56.35% | 1049863.37 | 1049863.37 | 2060302.371 | 196.2%
5 | M18037503 | 2022-01-01 | 2024-06-30 | 6.367% | 2658385.48 | 1952021.1 | 1694170.66 | 86.79%
6 | M18038302 | 2022-04-01 | 2024-09-30 | N/A | 5718572 | 4327941 | 1569705.46 | 36.27%
7 | DKY213502 | 2021-06-01 | 2025-08-01 | 17.87% | 6087134 | 6087134 | 1522376.06 | 25.01%
8 | EB021215X | 2022-07-01 | 2024-12-31 | N/A | 691419.87 | 1776134.31 | 1380015.02 | 77.7%
9 | EBS01303X | 2023-01-01 | 2024-06-30 | N/A | 1417296.84 | 1897680.22 | 1304467.21 | 68.74%
10 | M19030001 | 2021-07-01 | 2025-07-11 | 16.45% | 814497.49 | 17026164.77 | 1147894.73 | 6.742%
11 | M19029901 | 2021-07-01 | 2025-07-22 | 16.33% | 984733.98 | 22055241.59 | 1109656.05 | 5.031%
12 | MX1089713 | 2021-11-01 | 2025-05-29 | 9.119% | 732676.29 | 916641.46 | 1054738.54 | 115.1%
13 | MX9851050 | 2023-04-01 | 2024-12-26 | N/A | 875581.45 | 1051911.61 | 1031239.32 | 98.03%
14 | SG601SW | 2017-06-01 | 2025-03-31 | 60.59% | 42090 | 42090 | 880809.36 | 2093%
15 | KYGLT2102 | 2022-02-01 | 2024-09-28 | 2.784% | 658237.71 | 1886882.78 | 809952.63 | 42.93%
16 | DKY213501 | 2021-06-01 | 2025-07-29 | 17.91% | 1245722 | 2065388.84 | 725354.86 | 35.12%
17 | MX5977873 | 2021-01-01 | 2025-05-01 | 26.76% | 268.6 | 940544.82 | 712080.01 | 75.71%
18 | MX1089758 | 2021-11-01 | 2025-05-29 | 9.119% | 494404.97 | 575413.44 | 676858.9 | 117.6%
19 | M18037502 | 2021-12-01 | 2024-07-01 | 9.438% | 1070377.38 | 1379877.65 | 596303.54 | 43.21%
20 | SG764MAT1 | 2019-10-01 | 2030-03-31 | 22.98% | 217462.26 | 217462.26 | 493208.14 | 226.8%
21 | MX8555714 | 2023-10-01 | 2024-09-26 | N/A | 871956.57 | 483489.68 | 474142.54 | 98.07%
22 | MX5313258 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 464473.56 | 430984.87 | 92.79%
23 | M21049101 | 2022-07-01 | 2024-05-14 | N/A | 1113048.63 | 1368507.85 | 430128.31 | 31.43%
24 | SG960ORCH | 2021-09-01 | 2026-09-30 | 9.704% | 939747 | 939747 | 423272.36 | 45.04%
25 | EB020684X | 2022-08-01 | 2025-08-31 | N/A | 385542.32 | 1205675.32 | 385063.19 | 31.94%
26 | M19030901 | 2022-03-01 | 2027-09-07 | N/A | 2794337.82 | 2774043.22 | 364757.24 | 13.15%
27 | MX1089667 | 2021-11-01 | 2025-05-29 | 9.119% | 268.6 | 890339.9 | 362471.88 | 40.71%
28 | M18038301 | 2022-04-01 | 2024-09-30 | N/A | 660919.23 | 1446927.45 | 360599.29 | 24.92%
29 | CEBIC23 | 2023-03-01 | 2024-03-31 | N/A | 104330.32 | 104330.32 | 348280.56 | 333.8%
30 | 04000156 | 2023-01-01 | 2026-12-31 | N/A | 1732563 | 1732563 | 315284.86 | 18.2%
31 | MX0002134 | 2022-05-01 | 2025-03-13 | N/A | 268.6 | 218883.85 | 309390.42 | 141.3%
32 | M21037402 | 2021-08-01 | 2026-03-03 | 12.6% | 2253809 | 4748160.48 | 309119.62 | 6.51%
33 | 400113005 | 2023-10-01 | 2025-03-15 | N/A | 46812 | 46812 | 298071.03 | 636.7%
34 | M18038303 | 2022-10-01 | 2024-10-13 | N/A | 300289.97 | 267270 | 284453.81 | 106.4%
35 | MX0002133 | 2022-02-01 | 2025-03-13 | 2.377% | 268.6 | 225622.03 | 284279.56 | 126%
36 | HROPTEB | 2023-06-01 | 2024-10-31 | N/A | 295000 | 295000 | 273927.62 | 92.86%
37 | M21049901 | 2023-01-01 | 2026-01-16 | N/A | 7714215.63 | 7714215.63 | 271106.76 | 3.514%
38 | MX9101587 | 2023-08-01 | 2024-08-01 | N/A | 113318.88 | 301579.99 | 267449.15 | 88.68%
39 | M19030902 | 2023-02-01 | 2027-07-23 | N/A | 13258853.48 | 12875233.82 | 260993.94 | 2.027%
40 | MX6282574 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 185646.68 | 257716.79 | 138.8%
41 | EDUKEKY23 | 2023-03-01 | 2024-03-31 | N/A | 50000 | 50000 | 249102.27 | 498.2%
42 | MX6246270 | 2023-04-01 | 2024-09-27 | N/A | 199911.72 | 265191.41 | 240389.47 | 90.65%
43 | MX9160207 | 2023-05-01 | 2024-10-29 | N/A | 197256.75 | 222385.61 | 239541.7 | 107.7%
44 | WD010068X | 2023-07-01 | 2024-12-31 | N/A | 5236259.82 | 6751449.86 | 232143.38 | 3.438%
45 | EOPLTFM | 2023-04-01 | 2027-03-31 | N/A | 210000 | 210000 | 226485.53 | 107.9%
46 | SG1093SW | 2021-11-01 | 2025-01-26 | 10.07% | 56870 | 221078.2 | 221078.2 | 100%
47 | EB022017X | 2022-12-01 | 2024-12-31 | N/A | 194836.53 | 457785.22 | 207180.54 | 45.26%
48 | EB020345X | 2023-03-01 | 2024-12-31 | N/A | 1115807.65 | 2351601.35 | 206991.69 | 8.802%
49 | MXA352205 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 138081.42 | 197784.69 | 143.2%
50 | MX5999394 | 2023-02-01 | 2025-03-13 | N/A | 118594.16 | 123212.71 | 191160.7 | 155.1%
51 | MX5999267 | 2023-02-01 | 2025-03-13 | N/A | 135863.7 | 140064.2 | 189131.36 | 135%
52 | ASDEKCD | 2022-08-01 | 2050-12-31 | N/A | 1 | 184837.5 | 184837.5 | 100%
53 | DUKTKYE23 | 2023-09-01 | 2023-03-01 | N/A | 50000 | 2920 | 181018.1 | 6199%
54 | M22008401 | 2023-01-01 | 2024-04-30 | N/A | 172431.73 | 217908.88 | 179822.06 | 82.52%
55 | SG732TR04 | 2021-02-01 | 2026-03-20 | 20.93% | 1545935 | 1545935 | 176276.64 | 11.4%
56 | M19030903 | 2023-03-01 | 2028-01-08 | N/A | 8486456.4 | 7100156.48 | 170708.4 | 2.404%
57 | MX9365045 | 2021-03-01 | 2025-03-31 | 24.41% | 268.6 | 790939.84 | 170207.06 | 21.52%
58 | SG776OP1 | 2022-06-01 | 2030-03-31 | N/A | 542269.02 | 542269.02 | 167264.39 | 30.85%
59 | M21046401 | 2022-12-01 | 2028-08-06 | N/A | 6049242.28 | 6049242.28 | 165545.07 | 2.737%
60 | MX5977890 | 2021-01-01 | 2025-03-27 | 27.36% | 268.6 | 923755.12 | 161181.05 | 17.45%
61 | EB022168X | 2023-11-01 | 2025-03-15 | N/A | 4842533.45 | 5300413.09 | 153023.56 | 2.887%
62 | MX3045963 | 2019-11-01 | 2031-02-27 | 20.55% | 710378.55 | 577620.88 | 149923.74 | 25.96%
63 | MX7369915 | 2024-01-01 | 2024-06-18 | N/A | 66770.06 | 154397.95 | 149596.95 | 96.89%
64 | MX7372051 | 2021-10-01 | 2025-07-29 | 10.74% | 268.6 | 178856.07 | 149048.66 | 83.33%
65 | SKY2301DC | 2023-01-01 | 2023-09-30 | N/A | 100 | 100 | 147702.52 | 147703%
66 | CONTROLS | 2022-08-01 | 2027-03-31 | N/A | 61125 | 61125 | 146406.55 | 239.5%
67 | SG960DASH | 2021-09-01 | 2026-09-30 | 9.704% | 179000 | 179000 | 143448.4 | 80.14%
68 | EB021948X | 2022-08-01 | 2024-05-15 | N/A | 78916.88 | 78916.88 | 143151.17 | 181.4%
69 | UIRATEDES | 2021-02-01 | 2022-03-31 | 92.67% | 213693 | 213693 | 137854.68 | 64.51%
70 | MX6490130 | 2023-07-01 | 2024-06-27 | N/A | 268.6 | 512600.17 | 137203.23 | 26.77%
71 | MX5764593 | 2020-06-01 | 2025-05-01 | 35.49% | 268.6 | 99891.89 | 137147.26 | 137.3%
72 | 348527125 | 2023-08-01 | 2025-06-29 | N/A | 366827 | 366827 | 133149.46 | 36.3%
73 | CEB022007 | 2022-11-01 | 2028-12-31 | N/A | 22801029 | 22801029 | 130699.15 | 0.5732%
74 | M20044401 | 2022-08-01 | 2026-02-03 | N/A | 4884421.11 | 4884421.11 | 130356.57 | 2.669%
75 | KSTMOH | 2017-12-01 | 2067-12-31 | 8.474% | 100 | 100 | 123520.64 | 123521%
76 | EB022421X | 2023-12-01 | 2025-03-15 | N/A | 4842533.45 | 5301159.96 | 121214.97 | 2.287%
77 | V2147HAZK | 2023-11-01 | 2026-03-31 | N/A | 1 | 116290.62 | 116290.62 | 100%
78 | WD010070X | 2023-05-01 | 2024-08-31 | N/A | 118083.98 | 118083.98 | 115493.48 | 97.81%
79 | EB022437X | 2023-11-01 | 2024-02-28 | N/A | 207697.08 | 207697.08 | 111108.65 | 53.5%
80 | TKY190401 | 2019-01-01 | 2025-08-05 | 47.92% | 296051.84 | 301667.34 | 110039.32 | 36.48%
81 | MX5254728 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 78316.55 | 108103.19 | 138%
82 | 400055029 | 2023-10-01 | 2025-06-29 | N/A | 233568 | 233568 | 105065.79 | 44.98%
83 | MX9197324 | 2023-12-01 | 2024-07-25 | N/A | 78503.73 | 117809.97 | 104972.45 | 89.1%
84 | SG1165SW | 2023-01-01 | 2025-03-31 | N/A | 221611 | 191389 | 104313.03 | 54.5%
85 | M22034701 | 2023-06-01 | 2027-01-18 | N/A | 6048572 | 6069238.69 | 102194.72 | 1.684%
86 | MX9171230 | 2023-12-01 | 2024-08-22 | N/A | 50328.64 | 61119.27 | 97738.81 | 159.9%
87 | EB022070X | 2023-09-01 | 2024-12-31 | N/A | 92045.14 | 92045.14 | 93178.39 | 101.2%
88 | MX5254718 | 2022-11-01 | 2025-07-29 | N/A | 61262.73 | 60902.25 | 92700.72 | 152.2%
89 | MX5254741 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 57361.03 | 88362.04 | 154%
90 | MX5254734 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 95712.53 | 86565.89 | 90.44%
91 | MX1701475 | 2022-03-01 | 2025-07-29 | N/A | 268.6 | 83826.31 | 84335.56 | 100.6%
92 | MX7372046 | 2022-05-01 | 2025-07-29 | N/A | 43618.42 | 74413.37 | 84002.46 | 112.9%
93 | MX5254727 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 51529.71 | 83200.31 | 161.5%
94 | MX5254707 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 47575.04 | 82866.45 | 174.2%
95 | MX9624624 | 2024-01-01 | 2024-07-11 | N/A | 65865.89 | 122523.73 | 82776.37 | 67.56%
96 | MX5254717 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 48423.89 | 82298.91 | 170%
97 | MX5254732 | 2022-11-01 | 2025-02-28 | N/A | 268.6 | 61561.69 | 81489.32 | 132.4%
98 | MX6180924 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 62661.33 | 80479.79 | 128.4%
99 | SG1105SW | 2022-12-01 | 2025-11-30 | N/A | 52971 | 52971 | 80265.32 | 151.5%
100 | MX5254704 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 49154.68 | 80196.2 | 163.2%
101 | 400055030 | 2023-11-01 | 2025-06-29 | N/A | 588820 | 79340.88 | 79340.88 | 100%
102 | MX5254705 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 53831.38 | 79317.84 | 147.3%
103 | MX7372054 | 2021-10-01 | 2025-03-13 | 11.91% | 268.6 | 48829.95 | 78980.26 | 161.7%
104 | MX8393170 | 2024-02-01 | 2024-08-21 | N/A | 87062.68 | 133710.21 | 78066.67 | 58.38%
105 | MX5254742 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 70089.61 | 77684.77 | 110.8%
106 | MX5254726 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 66501.06 | 77454.04 | 116.5%
107 | MX5254730 | 2023-02-01 | 2025-05-01 | N/A | 268.6 | 69290.16 | 77335.88 | 111.6%
108 | DKY213503 | 2021-07-01 | 2025-01-31 | 18.47% | 1580691 | 1038020.94 | 76764.78 | 7.395%
109 | MX6180918 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 54748.01 | 76238.64 | 139.3%
110 | MX5254737 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 63526.75 | 75606.37 | 119%
111 | WD050029X | 2023-02-01 | 2023-10-01 | N/A | 50144.75 | 50144.75 | 75458.03 | 150.5%
112 | EB021551X | 2023-03-01 | 2024-12-31 | N/A | 279091.06 | 279091.06 | 75171.63 | 26.93%
113 | MX5254708 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 51293.26 | 74384.01 | 145%
114 | MX5254729 | 2023-02-01 | 2025-05-01 | N/A | 268.6 | 61809.61 | 73627.6 | 119.1%
115 | MX1975019 | 2019-10-01 | 2026-06-29 | 35.77% | 268.6 | 258105.13 | 73073.19 | 28.31%
116 | KRXRCM | 2020-01-01 | 2068-03-31 | 4.477% | 100 | 1832149.71 | 72323.97 | 3.947%
117 | MX5353113 | 2022-11-01 | 2025-02-28 | N/A | 268.6 | 55003.83 | 72126.91 | 131.1%
118 | MX5254711 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 53308.51 | 71842.8 | 134.8%
119 | MX5254722 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 54246.19 | 71478.02 | 131.8%
120 | MX5254714 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 49601.08 | 71370.56 | 143.9%
121 | MX9353335 | 2023-08-01 | 2024-06-27 | N/A | 47143.65 | 47443.09 | 71189.64 | 150.1%
122 | MX5254720 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 55099.62 | 71093.99 | 129%
123 | MX5254739 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 54390.47 | 71002.4 | 130.5%
124 | M19030908 | 2023-02-01 | 2028-01-08 | N/A | 170520.48 | 176623.17 | 70877.48 | 40.13%
125 | PH2ASPASW | 2023-09-01 | 2026-03-31 | N/A | 1184758 | 1184758 | 70635.4 | 5.962%
126 | MX5254719 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 50150.77 | 70397.7 | 140.4%
127 | MX9804712 | 2023-10-01 | 2024-11-28 | N/A | 70232.74 | 97961.86 | 70371.85 | 71.84%
128 | MX6180900 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 70111.72 | 70215.54 | 100.1%
129 | MX7372045 | 2021-10-01 | 2025-07-29 | 10.74% | 268.6 | 48513.28 | 70197.47 | 144.7%
130 | MX6180914 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 59087.89 | 70127.32 | 118.7%
131 | MX6465013 | 2023-10-01 | 2025-12-29 | N/A | 268.6 | 87109.6 | 70017.67 | 80.38%
132 | MX7372047 | 2021-10-01 | 2025-07-29 | 10.74% | 268.6 | 47980.35 | 69413.9 | 144.7%
133 | V2128HAZK | 2023-08-01 | 2026-03-31 | N/A | 1 | 69364.5 | 69364.5 | 100%
134 | SG764BLK1 | 2019-04-01 | 2030-03-31 | 26.49% | 217462.26 | 68694.53 | 68694.53 | 100%
135 | MX5254738 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 48912.6 | 68592.42 | 140.2%
136 | MX1473566 | 2021-12-01 | 2025-07-29 | 6.662% | 268.6 | 50342.45 | 68124.18 | 135.3%
137 | MX9353342 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 65338.92 | 67839.01 | 103.8%
138 | MX5254725 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 50843.16 | 66422.7 | 130.6%
139 | MX5254721 | 2022-12-01 | 2025-05-29 | N/A | 268.6 | 52135.28 | 66406.72 | 127.4%
140 | EB022267X | 2023-11-01 | 2024-03-15 | N/A | 76519.86 | 76519.86 | 64900.25 | 84.81%
141 | MX1473561 | 2021-12-01 | 2025-03-13 | 7.429% | 268.6 | 56445.34 | 64768.19 | 114.7%
142 | MX6180915 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 61424.39 | 64568.43 | 105.1%
143 | MX6180912 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 56668.96 | 64481.07 | 113.8%
144 | MX0535898 | 2023-10-01 | 2024-07-29 | N/A | 129715.6 | 89501.31 | 64467.75 | 72.03%
145 | MX6180925 | 2022-12-01 | 2025-08-28 | N/A | 268.6 | 52936.73 | 63712.93 | 120.4%
146 | MX6180927 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 57075.06 | 62559.13 | 109.6%
147 | V2189HAZK | 2023-01-01 | 2025-03-31 | N/A | 1 | 62246.51 | 62246.51 | 100%
148 | MX5254733 | 2023-02-01 | 2025-02-28 | N/A | 268.6 | 50304.24 | 62017.67 | 123.3%
149 | MX6180916 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 51537.94 | 61865.63 | 120%
150 | MX1701481 | 2021-12-01 | 2025-07-29 | 6.662% | 44547.54 | 52105.68 | 61713.83 | 118.4%
151 | MX5352287 | 2023-02-01 | 2025-02-28 | N/A | 268.6 | 28992.77 | 61432.37 | 211.9%
152 | MX9353338 | 2023-08-01 | 2024-06-27 | N/A | 47886.64 | 48591.48 | 60641.23 | 124.8%
153 | MX6180911 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 48541.26 | 60513.25 | 124.7%
154 | MX9353339 | 2023-08-01 | 2024-06-27 | N/A | 55014.3 | 54659.97 | 59686.31 | 109.2%
155 | MX5254701 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 54660.58 | 59653.79 | 109.1%
156 | EB022230X | 2023-05-01 | 2023-09-30 | N/A | 97787.19 | 97787.19 | 59596.7 | 60.95%
157 | MX5254699 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 55464.83 | 58966.78 | 106.3%
158 | MX1701474 | 2022-03-01 | 2025-07-29 | N/A | 268.6 | 49019.11 | 58942.18 | 120.2%
159 | MX0006935 | 2023-11-01 | 2026-09-28 | N/A | 268.6 | 268.6 | 58837.13 | 21905%
160 | MX6180921 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 51005.17 | 58726.9 | 115.1%
161 | MX6180926 | 2022-12-01 | 2025-08-28 | N/A | 268.6 | 49795.44 | 58684.1 | 117.9%
162 | MX6518423 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 49118.7 | 58658.79 | 119.4%
163 | MX7372048 | 2021-10-01 | 2025-07-29 | 10.74% | 268.6 | 54025.21 | 57672.38 | 106.8%
164 | MX9353336 | 2023-08-01 | 2024-06-27 | N/A | 268.6 | 57294.18 | 57413.84 | 100.2%
165 | MX6180901 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 58581.68 | 57408.05 | 98%
166 | MX5254713 | 2022-11-01 | 2025-07-29 | N/A | 268.6 | 53758.98 | 57143.78 | 106.3%
167 | MX6180906 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 53807.86 | 57134.25 | 106.2%
168 | MX5254698 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 47206.67 | 56735.24 | 120.2%
169 | MX7372056 | 2021-10-01 | 2025-03-13 | 11.91% | 268.6 | 49397.18 | 56695.98 | 114.8%
170 | K2241SURK | 2021-11-01 | 2024-12-31 | 10.29% | 91.4 | 91.4 | 56668.5 | 62001%
171 | MX7372057 | 2022-04-01 | 2025-03-13 | N/A | 48072.68 | 51031.8 | 56563.63 | 110.8%
172 | SG732TR05 | 2021-05-01 | 2027-03-31 | 14.03% | 1545935 | 1545935 | 56340.02 | 3.644%
173 | MX5441962 | 2022-07-01 | 2025-07-29 | N/A | 53623.08 | 55590.56 | 56191.95 | 101.1%
174 | M21050001 | 2023-05-01 | 2026-07-28 | N/A | 6158150.97 | 6158150.97 | 55811.68 | 0.9063%
175 | E1214 | 2008-09-01 | 2050-12-31 | 31.87% | 0 | 0 | 55000
176 | GPACCRUAL | 2005-03-01 | 2049-07-31 | 38.27% | 1 | 54949.37 | 54949.37 | 100%
177 | CPADEK | 2018-03-01 | 2050-12-31 | 12.17% | 1 | 54750.33 | 54750.33 | 100%
178 | MX5254743 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 48409.48 | 54733.78 | 113.1%
179 | SKY2210DC | 2022-12-01 | 2022-09-30 | N/A | 100 | 100 | 54594.2 | 54594%
180 | MX7372055 | 2021-12-01 | 2025-03-13 | 7.429% | 268.6 | 50933.23 | 54077.97 | 106.2%
181 | MX9353337 | 2023-08-01 | 2024-06-27 | N/A | 51523.17 | 51523.17 | 53595.85 | 104%
182 | CEBVLV24 | 2024-01-01 | 2025-03-31 | N/A | 534100.5 | 534100.5 | 53508.7 | 10.02%
183 | KPPL | 2017-12-01 | 2067-12-31 | 8.474% | 100 | 100 | 52989.21 | 52989%
184 | MX5254702 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 42460.94 | 52765.79 | 124.3%
185 | MX5821049 | 2022-09-01 | 2025-03-13 | N/A | 268.6 | 49902.97 | 52530.22 | 105.3%
186 | MX9778065 | 2024-02-01 | 2024-09-28 | N/A | 80466.09 | 80189.75 | 51895.95 | 64.72%
187 | M21033001 | 2023-05-01 | 2025-01-13 | N/A | 267542.13 | 267542.13 | 51823.02 | 19.37%
188 | EB021969X | 2022-06-01 | 2024-12-31 | N/A | 60858.98 | 60858.98 | 51622.19 | 84.82%
189 | MX2725027 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 38811.41 | 51485.25 | 132.7%
190 | KYGLT2003 | 2022-08-01 | 2024-09-08 | N/A | 209900.63 | 209900.63 | 51173.91 | 24.38%
191 | LTHTRTVMT | 2022-05-01 | 2023-08-03 | N/A | 9360 | 48665 | 50848.3 | 104.5%
192 | ALTMETVEN | 2023-03-01 | 2050-12-31 | N/A | 0 | 0 | 50789.03
193 | MX0006936 | 2023-11-01 | 2026-09-28 | N/A | 268.6 | 268.6 | 50185.29 | 18684%
194 | MX2725052 | 2022-12-01 | 2024-06-27 | N/A | 268.6 | 45795.26 | 50069.22 | 109.3%
195 | M20032601 | 2021-02-01 | 2027-09-30 | 16.12% | 172663 | 173649.36 | 50044.12 | 28.82%
196 | EB020687X | 2022-06-01 | 2024-12-31 | N/A | 722349.24 | 722349.24 | 50037.56 | 6.927%
197 | MX7372041 | 2021-10-01 | 2025-03-13 | 11.91% | 268.6 | 45712.85 | 49961.82 | 109.3%
198 | M18038401 | 2022-04-01 | 2025-02-01 | N/A | 948016.3 | 1674509.17 | 49849.46 | 2.977%
199 | MX9353345 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 48579.28 | 49605.91 | 102.1%
200 | MX9353348 | 2023-09-01 | 2025-05-29 | N/A | 51001.77 | 48625.86 | 49146.46 | 101.1%
201 | MX9353349 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 55058.98 | 49006.9 | 89.01%
202 | MX9353351 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 50189.18 | 48436.45 | 96.51%
203 | EB021749X | 2023-11-01 | 2025-12-31 | N/A | 2801808.39 | 2801808.39 | 48398.13 | 1.727%
204 | MX6180910 | 2022-12-01 | 2025-08-28 | N/A | 268.6 | 45060.21 | 48216.61 | 107%
205 | SKY2201DC | 2022-02-01 | 2022-09-30 | 11.2% | 100 | 100 | 48072.01 | 48072%
206 | MX1601026 | 2022-02-01 | 2025-07-29 | 2.119% | 268.6 | 64553 | 47137.41 | 73.02%
207 | MX1466916 | 2024-01-01 | 2024-07-18 | N/A | 50093.86 | 48958.31 | 46886.61 | 95.77%
208 | 349472020 | 2022-03-01 | 2024-06-30 | N/A | 58359 | 46872.76 | 46872.76 | 100%
209 | MX9918857 | 2021-03-01 | 2024-05-30 | 30.69% | 43495.54 | 60851.73 | 46848.07 | 76.99%
210 | EB022083X | 2023-03-01 | 2025-12-31 | N/A | 82211.94 | 82211.94 | 46347.88 | 56.38%
211 | EB022048X | 2022-12-01 | 2025-02-28 | N/A | 81161.76 | 81161.76 | 46316.45 | 57.07%
212 | LTHCDDSLT | 2022-06-01 | 2025-09-30 | N/A | 115970 | 115970 | 44732.28 | 38.57%
213 | MX5821220 | 2022-09-01 | 2025-02-28 | N/A | 268.6 | 32527.25 | 44620.72 | 137.2%
214 | LTHTRLIVS | 2021-07-01 | 2024-06-30 | 22.1% | 29192 | 29192 | 44610.08 | 152.8%
215 | K2152SURK | 2022-02-01 | 2025-03-31 | 2.34% | 91.4 | 91.4 | 43733.6 | 47849%
216 | SKY2206DC | 2022-06-01 | 2022-09-30 | N/A | 100 | 100 | 43492.98 | 43493%
217 | M22016101 | 2023-12-01 | 2030-07-16 | N/A | 4465725.4 | 4465725.4 | 43464.84 | 0.9733%
218 | MX5261357 | 2022-08-01 | 2025-03-31 | N/A | 268.6 | 153516.26 | 42949.07 | 27.98%
219 | MX6465474 | 2023-06-01 | 2025-12-29 | N/A | 268.6 | 51769.61 | 42449.81 | 82%
220 | KSLNOLE | 2018-02-01 | 2067-04-01 | 8.287% | 100 | 100 | 42401.1 | 42401%
221 | SG1181SW | 2023-04-01 | 2025-03-31 | N/A | 1029544.56 | 85244 | 42002.26 | 49.27%
222 | MX6277290 | 2020-04-01 | 2025-05-01 | 37.61% | 268.6 | 268.6 | 41770.02 | 15551%
223 | EB022435X | 2023-12-01 | 2024-02-28 | N/A | 34283.87 | 34283.87 | 41656.07 | 121.5%
224 | CWDIC23 | 2023-03-01 | 2024-03-01 | N/A | 57018.04 | 57018.04 | 41312.02 | 72.45%
225 | MX0653634 | 2024-01-01 | 2024-08-19 | N/A | 51305.9 | 50228.83 | 41180.69 | 81.99%
226 | CGRREPLA | 2023-03-01 | 2050-12-31 | N/A | 50000 | 50000 | 40801.087 | 81.6%
227 | SG1059HW | 2022-09-01 | 2025-03-31 | N/A | 74157.59 | 74157.59 | 39927.06 | 53.84%
228 | 400055023 | 2023-01-01 | 2024-06-29 | N/A | 26600 | 39887.93 | 39887.93 | 100%
229 | V2070HAZK | 2023-01-01 | 2025-03-31 | N/A | 1 | 39856.89 | 39856.89 | 100%
230 | SKY2203DC | 2022-05-01 | 2022-09-30 | N/A | 100 | 100 | 39678.29 | 39678%
231 | 400055024 | 2023-01-01 | 2024-06-30 | N/A | 37866 | 67274 | 39188.3 | 58.25%
232 | MX8540456 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 281277.49 | 39015.05 | 13.87%
233 | MX2158210 | 2021-12-01 | 2025-07-29 | 6.662% | 24555.94 | 47117.65 | 38668.44 | 82.07%
234 | SKY2302DC | 2023-02-01 | 2023-09-30 | N/A | 100 | 100 | 37626.09 | 37626%
235 | TPO000215 | 2023-12-01 | 2026-03-31 | N/A | 49131.36 | 49131.36 | 37424.06 | 76.17%
236 | MX2725028 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 36626.63 | 37061.07 | 101.2%
237 | LTHTRMTLS | 2021-03-01 | 2024-08-30 | 28.48% | 25480 | 34698 | 36065.14 | 103.9%
238 | MX8239349 | 2023-02-01 | 2024-03-31 | N/A | 23881.35 | 34940.59 | 35945.27 | 102.9%
239 | MX0319572 | 2021-08-01 | 2025-05-29 | 15.1% | 13981.08 | 38025.13 | 34873.16 | 91.71%
240 | 400055032 | 2023-11-01 | 2025-06-29 | N/A | 128160 | 42720 | 34561.27 | 80.9%
241 | KMW23256 | 2023-11-01 | 2024-03-30 | N/A | 32320 | 34133.32 | 34133.32 | 100%
242 | EB022450X | 2024-01-01 | 2027-12-31 | N/A | 892784.48 | 11809083.34 | 34102.1 | 0.2888%
243 | MX5820993 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 38470.33 | 33143.13 | 86.15%
244 | MX5820950 | 2022-09-01 | 2025-03-13 | N/A | 268.6 | 26270.83 | 32406.2 | 123.4%
245 | K2055SURK | 2021-11-01 | 2024-12-31 | 10.29% | 91.4 | 91.4 | 31604.97 | 34579%
246 | MX2725025 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 37755.32 | 31549.7 | 83.56%
247 | MX5322977 | 2022-07-01 | 2025-05-29 | N/A | 268.6 | 393168.92 | 31544.86 | 8.023%
248 | MX2725026 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 37660.18 | 31483.4 | 83.6%
249 | MX2158197 | 2022-08-01 | 2025-07-29 | N/A | 19399.18 | 38194.27 | 30948.09 | 81.03%
250 | MX1601027 | 2022-02-01 | 2025-07-29 | 2.119% | 21884.56 | 25476.99 | 30511.82 | 119.8%
251 | EB022062X | 2023-02-01 | 2025-02-15 | N/A | 161085.57 | 161085.57 | 29779.16 | 18.49%
252 | WDC00101X | 2024-02-01 | 2024-12-15 | N/A | 771358.81 | 1019661.03 | 29740.04 | 2.917%
253 | MX1601029 | 2022-02-01 | 2025-07-29 | 2.119% | 268.6 | 22400.6 | 29035.24 | 129.6%
254 | MX0002132 | 2022-05-01 | 2025-03-13 | N/A | 268.6 | 49415.73 | 28835.02 | 58.35%
255 | MX5821168 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 24344.33 | 28749.24 | 118.1%
256 | MX7057150 | 2023-10-01 | 2024-07-18 | N/A | 47505.76 | 38463.97 | 28487.76 | 74.06%
257 | MX1601031 | 2022-02-01 | 2025-07-29 | 2.119% | 268.6 | 21338.11 | 28394.78 | 133.1%
258 | MX2158190 | 2021-12-01 | 2025-07-29 | 6.662% | 16250.33 | 25929.94 | 28263.43 | 109%
259 | IT2300007 | 2023-03-01 | 2026-03-31 | N/A | 23510 | 75845 | 28003.55 | 36.92%
260 | MX7058120 | 2023-10-01 | 2024-07-18 | N/A | 50765.25 | 36816.03 | 27939.46 | 75.89%
261 | MX2725024 | 2022-04-01 | 2025-05-01 | N/A | 268.6 | 35959.14 | 27428.46 | 76.28%
262 | TVMYLLVKY | 2024-02-01 | 2050-12-31 | N/A | 2 | 27055.81 | 27055.81 | 100%
263 | MX6453958 | 2023-10-01 | 2025-12-29 | N/A | 268.6 | 233253.57 | 26839.67 | 11.51%
264 | MX5820998 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 22128.27 | 26215.55 | 118.5%
265 | SKY2307DC | 2023-07-01 | 2023-09-30 | N/A | 100 | 100 | 26211.31 | 26211%
266 | MX5821188 | 2022-10-01 | 2025-07-29 | N/A | 268.6 | 23203.45 | 25970.14 | 111.9%
267 | MX5821163 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 24763.82 | 25686.04 | 103.7%
268 | MX2158204 | 2021-12-01 | 2025-07-29 | 6.662% | 21678.2 | 31042.81 | 25627.49 | 82.56%
269 | M22031301 | 2023-08-01 | 2025-02-07 | N/A | 593942.2 | 49058.59 | 24971.4 | 50.9%
270 | M23006702 | 2023-12-01 | 2025-02-15 | N/A | 1130021.67 | 1130021.67 | 24926.5 | 2.206%
271 | KRFSCM | 2021-05-01 | 2068-03-31 | 1.768% | 100 | 1961890.39 | 24626.42 | 1.255%
272 | MX8564271 | 2021-08-01 | 2025-07-29 | 14.47% | 268.6 | 25875.2 | 24440.8 | 94.46%
273 | EB021392X | 2022-03-01 | 2025-12-31 | N/A | 668294.44 | 668294.44 | 24405.08 | 3.652%
274 | 349472029 | 2023-04-01 | 2025-05-28 | N/A | 21714 | 48888 | 24215.06 | 49.53%
275 | SG459FB01 | 2018-02-01 | 2025-06-30 | 54.99% | 37132 | 37132 | 23641.45 | 63.67%
276 | MX5821228 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 20326.95 | 23489.29 | 115.6%
277 | MX1601030 | 2022-02-01 | 2025-07-29 | 2.119% | 18532.9 | 19609.38 | 23017.56 | 117.4%
278 | M19030907 | 2023-02-01 | 2028-01-08 | N/A | 76949.48 | 87099.54 | 22754.9 | 26.13%
279 | IT2100108 | 2021-11-01 | 2025-03-31 | 9.551% | 22221 | 29845 | 22487.78 | 75.35%
280 | MX0319573 | 2021-08-01 | 2025-05-29 | 15.1% | 25435.13 | 26901.86 | 22395.4 | 83.25%
281 | MX9563302 | 2023-09-01 | 2025-09-25 | N/A | 268.6 | 356221.94 | 22312.26 | 6.264%
282 | MX9660088 | 2023-06-01 | 2025-09-10 | N/A | 268.6 | 173789.18 | 22294.7 | 12.83%
283 | M21037401 | 2021-08-01 | 2026-07-06 | 11.72% | 160173 | 185590.81 | 22275.4 | 12%
284 | MX2565156 | 2024-02-01 | 2024-08-26 | N/A | 268.6 | 130328.13 | 21982.43 | 16.87%
285 | MX6327144 | 2024-01-01 | 2025-02-27 | N/A | 268.6 | 22062.71 | 21430.17 | 97.13%
286 | MX2158216 | 2022-04-01 | 2025-07-29 | N/A | 15795.11 | 15795.11 | 21411.53 | 135.6%
287 | IT2300106 | 2023-12-01 | 2024-11-01 | N/A | 187860 | 17801 | 21363.99 | 120%
288 | MX9369394 | 2023-06-01 | 2025-07-29 | N/A | 268.6 | 173706.8 | 21350.25 | 12.29%
289 | MX9919685 | 2021-08-01 | 2025-03-13 | 15.98% | 268.6 | 19330.54 | 20860.33 | 107.9%
290 | MX0394883 | 2024-01-01 | 2024-06-27 | N/A | 50477.68 | 67418.41 | 20845.79 | 30.92%
291 | KLEDAL | 2020-04-01 | 2067-04-01 | 4.066% | 100 | 20395.54 | 20770.42 | 101.8%
292 | MX4194121 | 2022-04-01 | 2024-07-29 | N/A | 268.6 | 57543.44 | 20409.07 | 35.47%
293 | MX9563423 | 2023-09-01 | 2025-05-15 | N/A | 268.6 | 306556.77 | 19697.57 | 6.425%
294 | MX9114464 | 2023-07-01 | 2025-06-29 | N/A | 268.6 | 335515.68 | 19583.96 | 5.837%
295 | MX0698823 | 2023-09-01 | 2024-06-29 | N/A | 19677.14 | 42046.08 | 19264.31 | 45.82%
296 | MX1975744 | 2021-06-01 | 2026-08-27 | 14.22% | 268.6 | 311710.14 | 18868.95 | 6.053%
297 | MX6453758 | 2023-12-01 | 2025-12-29 | N/A | 268.6 | 103017.68 | 18862.13 | 18.31%
298 | 349472028 | 2023-04-01 | 2025-05-28 | N/A | 9324 | 29010 | 18808.25 | 64.83%
299 | MX9382916 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 53553.93 | 18408.59 | 34.37%
300 | MX9353368 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 66606.52 | 18309.09 | 27.49%
301 | TC2300036 | 2023-08-01 | 2024-08-29 | N/A | 57748 | 57748 | 18256.92 | 31.61%
302 | MX9563131 | 2023-10-01 | 2025-03-31 | N/A | 268.6 | 271895.52 | 18036.79 | 6.634%
303 | MX9353352 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 47691.84 | 17819.04 | 37.36%
304 | MX0319571 | 2021-08-01 | 2025-05-29 | 15.1% | 268.6 | 17016.21 | 17591.09 | 103.4%
305 | V2132REMK | 2023-09-01 | 2026-03-31 | N/A | 1 | 17559.14 | 17559.14 | 100%
306 | MX9919684 | 2021-08-01 | 2025-03-13 | 15.98% | 268.6 | 16750.94 | 17474.46 | 104.3%
307 | M19029902 | 2023-09-01 | 2025-05-02 | N/A | 57738 | 57738 | 17149.29 | 29.7%
308 | MX2725066 | 2022-12-01 | 2025-05-01 | N/A | 268.6 | 35203.54 | 17108.06 | 48.6%
309 | MX0319570 | 2021-08-01 | 2025-05-29 | 15.1% | 268.6 | 19148.54 | 16963.92 | 88.59%
310 | MX9353364 | 2023-08-01 | 2025-02-27 | N/A | 268.6 | 48709.73 | 16938.43 | 34.77%
311 | TKY190402 | 2018-12-01 | 2025-08-08 | 48.53% | 120817.29 | 120817.29 | 16938.09 | 14.02%
312 | MX9353357 | 2023-08-01 | 2025-02-27 | N/A | 268.6 | 51491.84 | 16690.31 | 32.41%
313 | MX0319574 | 2021-08-01 | 2025-05-29 | 15.1% | 26949.67 | 17337.1 | 16449.25 | 94.88%
314 | MX6472764 | 2024-02-01 | 2024-06-14 | N/A | 48871.94 | 44181.24 | 15956.52 | 36.12%
315 | MX9353367 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 64309.45 | 15942.36 | 24.79%
316 | MX6451512 | 2023-12-01 | 2025-12-29 | N/A | 268.6 | 131535.56 | 15939.82 | 12.12%
317 | MX5352573 | 2022-11-01 | 2025-02-28 | N/A | 268.6 | 51323.43 | 15906.85 | 30.99%
318 | MX8549113 | 2024-02-01 | 2025-05-29 | N/A | 58585.31 | 54028.22 | 15894.11 | 29.42%
319 | MX0850305 | 2023-11-01 | 2025-05-29 | N/A | 268.6 | 59529.86 | 15821.82 | 26.58%
320 | SKY2207DC | 2022-06-01 | 2022-09-30 | N/A | 100 | 100 | 15722.89 | 15723%
321 | MX0319569 | 2021-08-01 | 2025-05-29 | 15.1% | 268.6 | 17155.25 | 15685.56 | 91.43%
322 | 400055027 | 2023-08-01 | 2024-06-30 | N/A | 13069 | 15636.53 | 15636.53 | 100%
323 | M19019401 | 2020-12-01 | 2028-06-19 | 16.47% | 4551557.9 | 4551557.9 | 15580.63 | 0.3423%
324 | MX9353358 | 2023-08-01 | 2025-02-27 | N/A | 268.6 | 53281.85 | 15511.53 | 29.11%
325 | SG1134HW | 2023-02-01 | 2026-03-11 | N/A | 498485 | 498485 | 15507.66 | 3.111%
326 | MX9353366 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 63993.83 | 15493.73 | 24.21%
327 | MX9919686 | 2022-10-01 | 2025-03-13 | N/A | 268.6 | 21123.16 | 15321.97 | 72.54%
328 | MX8548941 | 2024-02-01 | 2025-05-29 | N/A | 36940.33 | 36940.33 | 15123.43 | 40.94%
329 | MX5971474 | 2022-11-01 | 2025-02-28 | N/A | 268.6 | 54192.85 | 15085.73 | 27.84%
330 | WDC00087X | 2023-02-01 | 2025-08-31 | N/A | 218769.33 | 218769.33 | 15082.25 | 6.894%
331 | WDC00056X | 2024-01-01 | 2025-12-25 | N/A | 2476761.27 | 2476761.27 | 15067.34 | 0.6083%
332 | MX9442677 | 2023-06-01 | 2025-10-29 | N/A | 268.6 | 363862.78 | 14901.99 | 4.095%
333 | KK0078S22 | 2023-03-01 | 2025-12-31 | N/A | 91.4 | 91.4 | 14831.08 | 16227%
334 | MX7891201 | 2022-01-01 | 2025-05-29 | 4.662% | 21970.73 | 17231.05 | 14779.51 | 85.77%
335 | MX6465684 | 2023-06-01 | 2025-12-29 | N/A | 268.6 | 349293.68 | 14683.15 | 4.204%
336 | KSMCELL | 2019-03-01 | 2067-04-01 | 6.235% | 0 | 0 | 14565.1
337 | MX6327150 | 2023-11-01 | 2025-02-27 | N/A | 268.6 | 21931.3 | 14430.07 | 65.8%
338 | MX0000704 | 2019-09-01 | 2030-10-07 | 22.47% | 268.6 | 268.6 | 14026.65 | 5222%
339 | V2199REMK | 2023-04-01 | 2025-03-31 | N/A | 1 | 13812.4 | 13812.4 | 100%
340 | KMW23089 | 2023-07-01 | 2023-12-31 | N/A | 12650 | 12857 | 13700.55 | 106.6%
341 | M23006703 | 2023-12-01 | 2025-02-11 | N/A | 781242.89 | 781242.89 | 13636.35 | 1.745%
342 | M23022401 | 2023-08-01 | 2025-01-10 | N/A | 182892.33 | 170902.27 | 12968.32 | 7.588%
343 | MX9064744 | 2021-06-01 | 2026-07-29 | 14.44% | 268.6 | 38393.48 | 12581.4 | 32.77%
344 | CMU060004 | 2016-07-01 | 2025-03-31 | 64.73% | 5500499.03 | 5500499.03 | 12459.69 | 0.2265%
345 | M20028901 | 2023-08-01 | 2027-01-01 | N/A | 3253228.76 | 5208198.58 | 12437.55 | 0.2388%
346 | MX5291241 | 2022-08-01 | 2025-01-29 | N/A | 268.6 | 10114.16 | 12358.33 | 122.2%
347 | M23006701 | 2023-12-01 | 2025-02-25 | N/A | 808187.73 | 808187.73 | 12344.94 | 1.527%
348 | MX8534364 | 2023-03-01 | 2024-01-31 | N/A | 18159.18 | 16634.47 | 12210.42 | 73.4%
349 | MX9567011 | 2024-02-01 | 2024-07-04 | N/A | 55219.43 | 54284.4 | 12000.27 | 22.11%
350 | MX1701480 | 2021-12-01 | 2025-07-29 | 6.662% | 0 | 0 | 11535.27
351 | SKY2309DC | 2023-07-01 | 2023-09-30 | N/A | 100 | 100 | 10893.93 | 10894%
352 | SKY2305DC | 2023-04-01 | 2023-09-30 | N/A | 100 | 100 | 10823.53 | 10824%
353 | MX9660090 | 2023-06-01 | 2025-11-10 | N/A | 268.6 | 148978.7 | 10715.69 | 7.193%
354 | SG359SW | 2018-09-01 | 2024-06-30 | 59.93% | 229797.94 | 10638.02 | 10638.02 | 100%
355 | LTHTRFELD | 2022-03-01 | 2024-08-30 | N/A | 33157 | 21383.67 | 10566.32 | 49.41%
356 | KFPLOMX | 2017-09-01 | 2067-12-31 | 8.927% | 0 | 0 | 9922.49
357 | M19030906 | 2023-02-01 | 2028-01-08 | N/A | 133907.75 | 130420.09 | 9916.36 | 7.603%
358 | LTHTTVMSG | 2022-05-01 | 2024-09-01 | N/A | 9360 | 9360 | 9904.63 | 105.8%
359 | MX2725029 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 3198.82 | 9630.97 | 301.1%
360 | SKY2304DC | 2023-03-01 | 2023-09-30 | N/A | 100 | 100 | 9237.44 | 9237%
361 | IT2300069 | 2023-08-01 | 2024-09-29 | N/A | 9623 | 9623 | 9111.41 | 94.68%
362 | MX7372059 | 2022-07-01 | 2025-03-13 | N/A | 0 | 0 | 9103.82
363 | CEBIC24 | 2024-02-01 | 2025-03-31 | N/A | 102509.42 | 102509.42 | 8946.02 | 8.727%
364 | MX6327145 | 2024-02-01 | 2025-02-27 | N/A | 268.6 | 36975.73 | 8900.49 | 24.07%
365 | SG459FB02 | 2018-02-01 | 2024-09-28 | 61.21% | 37132 | 37132 | 8897.93 | 23.96%
366 | LTHRUNITY | 2022-05-01 | 2024-11-30 | N/A | 114271 | 55537.31 | 8836.49 | 15.91%
367 | KCTRLSL | 2024-02-01 | 2030-12-31 | N/A | 100 | 100 | 8761.95 | 8762%
368 | MX6465372 | 2023-11-01 | 2025-12-29 | N/A | 268.6 | 49121.86 | 8742.79 | 17.8%
369 | MX8052768 | 2023-03-01 | 2024-03-30 | N/A | 8750.78 | 8681.03 | 8736.38 | 100.6%
370 | M22016102 | 2023-12-01 | 2029-12-24 | N/A | 10464 | 10464 | 8689.89 | 83.05%
371 | M22031401 | 2023-06-01 | 2025-08-31 | N/A | 1628922 | 1628922 | 8656.25 | 0.5314%
372 | M22034705 | 2023-08-01 | 2025-12-29 | N/A | 137249.13 | 137249.13 | 8531.93 | 6.216%
373 | V2287REMK | 2023-10-01 | 2026-03-31 | N/A | 1 | 8350.61 | 8350.61 | 100%
374 | M23010001 | 2023-08-01 | 2025-02-03 | N/A | 416563.72 | 568531.58 | 8318.6 | 1.463%
375 | IT2300078 | 2023-12-01 | 2024-11-30 | N/A | 11742 | 8199.98 | 8199.98 | 100%
376 | MX7891217 | 2021-11-01 | 2025-05-29 | 9.119% | 5560.38 | 5560.38 | 8180.75 | 147.1%
377 | KPOLIR | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 5540975.95 | 8157.82 | 0.1472%
378 | V2299REMK | 2023-03-01 | 2025-03-31 | N/A | 1 | 8132.34 | 8132.34 | 100%
379 | MX0451750 | 2024-02-01 | 2024-10-29 | N/A | 268.6 | 130777.63 | 8046.21 | 6.153%
380 | 349472021 | 2022-06-01 | 2025-03-31 | N/A | 9788 | 14139 | 8008.69 | 56.64%
381 | MX6450653 | 2024-02-01 | 2025-12-29 | N/A | 268.6 | 73203.9 | 7720.83 | 10.55%
382 | M21030701 | 2023-05-01 | 2025-11-24 | N/A | 269807.66 | 269807.66 | 7700.97 | 2.854%
383 | KROWMAJ | 2022-04-01 | 2036-10-17 | N/A | 3600000 | 7641.46 | 7641.46 | 100%
384 | V2205REMK | 2023-02-01 | 2025-03-31 | N/A | 1 | 7548.11 | 7548.11 | 100%
385 | SKY2205DC | 2022-06-01 | 2022-09-30 | N/A | 100 | 100 | 7513.1 | 7513%
386 | KOUTUG | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 4440180.13 | 7467.92 | 0.1682%
387 | MX9726813 | 2023-06-01 | 2025-12-29 | N/A | 268.6 | 374073.71 | 7399.6 | 1.978%
388 | 400055031 | 2023-11-01 | 2025-06-29 | N/A | 67963 | 67963 | 7389.55 | 10.87%
389 | MX1193729 | 2022-08-01 | 2025-05-29 | N/A | 268.6 | 170676.15 | 7385.36 | 4.327%
390 | ASDEKRO | 2022-09-01 | 2050-12-31 | N/A | 1 | 7324.14 | 7324.14 | 100%
391 | RCTSOFTWR | 2022-04-01 | 2025-03-31 | N/A | 3017 | 3017 | 7265.3 | 240.8%
392 | IT2200149 | 2022-12-01 | 2023-10-31 | N/A | 13718 | 7217.04 | 7217.04 | 100%
393 | IT2200122 | 2022-12-01 | 2024-05-29 | N/A | 10558 | 7156.26 | 7156.26 | 100%
394 | MX8137248 | 2022-09-01 | 2025-05-29 | N/A | 7848.19 | 9960.85 | 7003.55 | 70.31%
395 | MX6464431 | 2023-02-01 | 2024-03-30 | N/A | 3625.26 | 3625.26 | 6880.61 | 189.8%
396 | SKY2401DC | 2024-01-01 | 2024-09-30 | N/A | 0 | 0 | 6670.24
397 | M22000301 | 2024-02-01 | 2026-01-05 | N/A | 919903.55 | 919903.55 | 6636.79 | 0.7215%
398 | KHYDRCM | 2023-05-01 | 2068-03-31 | N/A | 100 | 104497.68 | 6570.56 | 6.288%
399 | SG1187SW | 2024-01-01 | 2025-07-31 | N/A | 254255.37 | 254255.37 | 6494.7 | 2.554%
400 | MX7891191 | 2021-11-01 | 2025-05-29 | 9.119% | 268.6 | 5701.25 | 6479.19 | 113.6%
401 | FERC88123 | 2023-12-01 | 2025-12-31 | N/A | 6788 | 6788 | 6468.92 | 95.3%
402 | M22034702 | 2023-08-01 | 2026-07-27 | N/A | 4075493.78 | 4075493.78 | 6449.55 | 0.1583%
403 | MX6465585 | 2023-11-01 | 2025-12-29 | N/A | 268.6 | 44430 | 6414.93 | 14.44%
404 | CS2300002 | 2023-05-01 | 2024-05-29 | N/A | 17727 | 6374.986 | 6374.986 | 100%
405 | MX0000780 | 2019-09-01 | 2030-10-18 | 22.41% | 268.6 | 268.6 | 6360.14 | 2368%
406 | IT2300008 | 2023-05-01 | 2025-03-31 | N/A | 2981 | 10270 | 6280.07 | 61.15%
407 | SKY2308DC | 2023-07-01 | 2023-09-30 | N/A | 100 | 100 | 6112.98 | 6113%
408 | MX8137236 | 2022-09-01 | 2025-05-29 | N/A | 6747.09 | 7953.66 | 6022.93 | 75.73%
409 | MX7891216 | 2021-11-01 | 2025-05-29 | 9.119% | 5796.84 | 5796.84 | 5999.19 | 103.5%
410 | MX9383139 | 2023-05-01 | 2024-03-21 | N/A | 9846.3 | 23024.57 | 5953.18 | 25.86%
411 | SGKAMIMGT | 2016-01-01 | 2023-02-01 | 86.94% | 603878 | 603878 | 5945.01 | 0.9845%
412 | IT2300085 | 2023-10-01 | 2024-09-30 | N/A | 7650 | 7650 | 5801.43 | 75.84%
413 | MX7891218 | 2021-11-01 | 2025-05-29 | 9.119% | 268.6 | 5235.42 | 5778.72 | 110.4%
414 | MX1601020 | 2022-04-01 | 2025-07-29 | N/A | 24251.72 | 3915.05 | 5760.85 | 147.1%
415 | MX0000782 | 2019-09-01 | 2030-11-15 | 22.26% | 268.6 | 268.6 | 5576.35 | 2076%
416 | MX5821234 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 48098.96 | 5433.92 | 11.3%
417 | V2078REMK | 2023-09-01 | 2025-03-31 | N/A | 1 | 5422.02 | 5422.02 | 100%
418 | MX0006937 | 2023-11-01 | 2027-01-28 | N/A | 268.6 | 268.6 | 5281.36 | 1966%
419 | MX0000778 | 2019-09-01 | 2030-10-18 | 22.41% | 268.6 | 268.6 | 5258.14 | 1958%
420 | MX9441824 | 2023-09-01 | 2030-07-29 | N/A | 268.6 | 137180.2 | 5133.61 | 3.742%
421 | KK0299S22 | 2023-03-01 | 2024-12-31 | N/A | 91.4 | 91.4 | 5109.43 | 5590%
422 | MX6090364 | 2023-07-01 | 2025-05-01 | N/A | 268.6 | 100706.38 | 5067.45 | 5.032%
423 | 400089001 | 2022-06-01 | 2027-03-31 | N/A | 1 | 5057.05 | 5057.05 | 100%
424 | CEB020297 | 2016-07-01 | 2019-12-31 | 100% | 8670871 | 8670871 | 4951.04 | 0.0571%
425 | MX5821193 | 2022-11-01 | 2025-02-28 | N/A | 268.6 | 49816.21 | 4941.03 | 9.919%
426 | OLEKY | 2015-01-01 | 2020-12-31 | 100% | 11 | 878166.59 | 4925.86 | 0.5609%
427 | M21034401 | 2023-05-01 | 2026-09-27 | N/A | 271956.83 | 271956.83 | 4755.21 | 1.749%
428 | M21053101 | 2023-10-01 | 2025-12-29 | N/A | 1123902.03 | 1123902.03 | 4671.96 | 0.4157%
429 | MX1532892 | 2024-01-01 | 2025-03-31 | N/A | 4639.47 | 4639.47 | 4651.82 | 100.3%
430 | MX8137256 | 2022-09-01 | 2025-05-29 | N/A | 2195.75 | 2502.35 | 4579.99 | 183%
431 | MX0442133 | 2023-09-01 | 2023-11-20 | N/A | 7545.16 | 13923.72 | 4504.06 | 32.35%
432 | SKY2209DC | 2022-07-01 | 2022-09-30 | N/A | 100 | 100 | 4247.48 | 4247%
433 | MX6497693 | 2023-12-01 | 2025-12-29 | N/A | 268.6 | 840284.92 | 4219.14 | 0.5021%
434 | MX8137265 | 2022-09-01 | 2025-05-29 | N/A | 5969.74 | 7111.72 | 4142.25 | 58.25%
435 | MX9067337 | 2023-04-01 | 2023-12-31 | N/A | 14504.88 | 14504.88 | 4043.46 | 27.88%
436 | V2128REMK | 2023-10-01 | 2026-03-31 | N/A | 1 | 4022.54 | 4022.54 | 100%
437 | M23029501 | 2023-09-01 | 2025-08-25 | N/A | 123330.27 | 206909.08 | 3944.36 | 1.906%
438 | MX7372044 | 2022-06-01 | 2023-10-26 | N/A | 268.6 | 268.6 | 3914.27 | 1457%
439 | IT2200029 | 2022-03-01 | 2022-07-30 | N/A | 2187 | 3749.62 | 3749.62 | 100%
440 | SKY2204DC | 2022-06-01 | 2022-09-30 | N/A | 100 | 100 | 3724.04 | 3724%
441 | IT2300027 | 2023-06-01 | 2024-06-29 | N/A | 5887 | 3719.56 | 3719.56 | 100%
442 | MX1701478 | 2022-04-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 3599.05 | 1340%
443 | MX6498024 | 2024-02-01 | 2025-12-29 | N/A | 268.6 | 544917.03 | 3398.31 | 0.6236%
444 | V2199HAZK | 2023-02-01 | 2025-03-31 | N/A | 1 | 3353.3 | 3353.3 | 100%
445 | SG1037SW | 2022-01-01 | 2024-01-31 | 7.632% | 77982 | 77982 | 3326.31 | 4.265%
446 | MX0619837 | 2023-12-01 | 2024-05-29 | N/A | 16382.68 | 16382.68 | 3320.19 | 20.27%
447 | 400160001 | 2024-01-01 | 2025-03-31 | N/A | 405203 | 405203 | 3312.38 | 0.8175%
448 | MX9353370 | 2023-08-01 | 2025-05-29 | N/A | 268.6 | 61653.06 | 3306.69 | 5.363%
449 | 400055001 | 2023-05-01 | 2024-07-30 | N/A | 10056 | 10056 | 3295.87 | 32.78%
450 | MX8137212 | 2022-08-01 | 2025-05-29 | N/A | 2300.97 | 2499.35 | 3275.42 | 131.1%
451 | SG732TR02 | 2019-02-01 | 2022-03-31 | 97.31% | 986106.22 | 986106.22 | 3177.13 | 0.3222%
452 | 349472031 | 2023-10-01 | 2024-06-30 | N/A | 13549 | 3074.75 | 3074.75 | 100%
453 | 400149HW2 | 2023-08-01 | 2026-03-31 | N/A | 8367 | 8367 | 3049.43 | 36.45%
454 | MX5821167 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 28539.09 | 2946.48 | 10.32%
455 | CO2300002 | 2023-06-01 | 2024-10-30 | N/A | 5468 | 5468 | 2937.48 | 53.72%
456 | SKY2007DC | 2020-08-01 | 2021-03-31 | 100% | 100 | 100 | 2935.3 | 2935%
457 | MX9353369 | 2023-08-01 | 2025-03-01 | N/A | 268.6 | 57505.61 | 2927.6 | 5.091%
458 | IT2200107 | 2023-02-01 | 2025-05-28 | N/A | 20243 | 42957 | 2900.81 | 6.753%
459 | MX9353383 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 67464.54 | 2842.12 | 4.213%
460 | MX9353376 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 47795.54 | 2773.32 | 5.802%
461 | MX5821185 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 30751.77 | 2652.52 | 8.626%
462 | MX9353380 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 57104.94 | 2633.71 | 4.612%
463 | MX5821190 | 2022-10-01 | 2025-05-01 | N/A | 268.6 | 36110.01 | 2627.81 | 7.277%
464 | MX6293612 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 12510.52 | 2611.05 | 20.87%
465 | CAPAUTOKY | 2014-03-01 | 2020-12-31 | 100% | 100 | 100 | 2610.33 | 2610%
466 | MXA353386 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 48405.61 | 2518.08 | 5.202%
467 | LTHCDEPJB | 2023-12-01 | 2024-08-30 | N/A | 3247 | 3247 | 2494.68 | 76.83%
468 | MX2725056 | 2022-12-01 | 2024-06-27 | N/A | 268.6 | 40165.42 | 2490.93 | 6.202%
469 | MX9353377 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 51221.69 | 2471.92 | 4.826%
470 | MX5821155 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 23128.42 | 2388.61 | 10.33%
471 | IT2300116 | 2024-01-01 | 2025-06-30 | N/A | 26083 | 26083 | 2355.92 | 9.032%
472 | RW2241A | 2022-04-01 | 2024-10-31 | N/A | 1 | 2333.66 | 2333.66 | 100%
473 | M23034501 | 2024-01-01 | 2027-05-31 | N/A | 3760149 | 3760149 | 2274.25 | 0.06048%
474 | IT2300086 | 2023-11-01 | 2025-03-31 | N/A | 13994 | 13994 | 2238.95 | 16%
475 | MX9353398 | 2023-11-01 | 2025-02-27 | N/A | 268.6 | 55980.74 | 2225.49 | 3.975%
476 | MX6200358 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 43724.73 | 2211.76 | 5.058%
477 | MX2725055 | 2022-12-01 | 2024-06-27 | N/A | 268.6 | 24296.08 | 2174.1 | 8.948%
478 | MX9353403 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 46914.88 | 2135.13 | 4.551%
479 | MX2725030 | 2022-12-01 | 2025-02-28 | N/A | 268.6 | 4280.95 | 2099.04 | 49.03%
480 | MX6200359 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 38283.92 | 2069.61 | 5.406%
481 | KBANNER | 2019-09-01 | 2067-04-01 | 5.242% | 0 | 0 | 2006.59
482 | MX6200360 | 2022-12-01 | 2025-12-29 | N/A | 268.6 | 39337.39 | 2003.81 | 5.094%
483 | MX9353392 | 2023-11-01 | 2025-03-06 | N/A | 268.6 | 51878.07 | 1999.65 | 3.855%
484 | IT2300068 | 2023-08-01 | 2024-05-29 | N/A | 8753 | 1984.98 | 1984.98 | 100%
485 | MX9353399 | 2023-11-01 | 2025-02-27 | N/A | 268.6 | 62995.31 | 1978.64 | 3.141%
486 | MX5821171 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 18858.26 | 1938.19 | 10.28%
487 | MX9353372 | 2023-08-01 | 2025-02-27 | N/A | 268.6 | 49766.34 | 1882.76 | 3.783%
488 | MX9353384 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 54421 | 1864.47 | 3.426%
489 | MX9353397 | 2023-11-01 | 2025-03-06 | N/A | 268.6 | 53916.5 | 1859.72 | 3.449%
490 | 400109M | 2023-06-01 | 2025-03-31 | N/A | 329532 | 8752.66 | 1852.78 | 21.17%
491 | MX9353413 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 52188.18 | 1842.3 | 3.53%
492 | RWT055A | 2021-07-01 | 2024-09-30 | 20.39% | 5000 | 5000 | 1833.14 | 36.66%
493 | MX1701469 | 2021-10-01 | 2023-02-28 | 29.13% | 268.6 | 268.6 | 1817.56 | 676.7%
494 | MX9353391 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 51179.76 | 1806.16 | 3.529%
495 | MX9353387 | 2023-08-01 | 2025-12-29 | N/A | 268.6 | 44889.26 | 1792.83 | 3.994%
496 | ETSPDCAPK | 2008-07-01 | 2050-12-31 | 32.15% | 0 | 0 | 1788.244
497 | MX9353408 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 50107.63 | 1783.44 | 3.559%
498 | KSCDL | 2021-07-01 | 2067-12-31 | 1.425% | 100 | 100 | 1767.06 | 1767%
499 | MX1490271 | 2023-12-01 | 2025-05-29 | N/A | 268.6 | 37299.76 | 1757.55 | 4.712%
500 | MX9353395 | 2023-11-01 | 2025-03-06 | N/A | 268.6 | 55593.96 | 1716.31 | 3.087%
501 | KRIOTCU | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 54332.49 | 1690.41 | 3.111%
502 | MX9353371 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 50741.79 | 1682.31 | 3.315%
503 | MX9353389 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 45280.19 | 1621.1 | 3.58%
504 | MX9353388 | 2023-08-01 | 2025-03-06 | N/A | 268.6 | 50572.01 | 1607.66 | 3.179%
505 | MXA821161 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 29957.41 | 1558.32 | 5.202%
506 | 348527062 | 2022-10-01 | 2025-03-31 | N/A | 36639 | 36639 | 1541.69 | 4.208%
507 | MX2725051 | 2023-11-01 | 2025-03-06 | N/A | 268.6 | 38657.65 | 1522.9 | 3.939%
508 | MX9353374 | 2023-08-01 | 2025-02-27 | N/A | 268.6 | 48070.53 | 1496.58 | 3.113%
509 | 400149SW2 | 2023-12-01 | 2026-03-31 | N/A | 14912 | 14912 | 1492.28 | 10.01%
510 | MX6327155 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 34617.07 | 1465.08 | 4.232%
511 | 344598001 | 2018-04-01 | 2019-12-24 | 100% | 479779 | 368742.35 | 1456.65 | 0.395%
512 | MX5821165 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 22531.58 | 1414.19 | 6.276%
513 | MX5821208 | 2022-11-01 | 2025-01-29 | N/A | 20068.82 | 20068.82 | 1363.7 | 6.795%
514 | MX6327139 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 39752.22 | 1360.94 | 3.424%
515 | M22034703 | 2023-10-01 | 2026-07-27 | N/A | 613997.37 | 613997.37 | 1360.51 | 0.2216%
516 | MX5821223 | 2022-11-01 | 2025-01-29 | N/A | 268.6 | 20787.22 | 1336.88 | 6.431%
517 | KCMCOH | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 409447.79 | 1312.38 | 0.3205%
518 | MX9353405 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 60565.58 | 1264.21 | 2.087%
519 | MX9353404 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 54888.95 | 1244.77 | 2.268%
520 | MX5821149 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 28034.02 | 1214.89 | 4.334%
521 | MX9353407 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 43208.19 | 1210.51 | 2.802%
522 | MX9353412 | 2023-11-01 | 2025-08-29 | N/A | 268.6 | 45012.51 | 1187.33 | 2.638%
523 | MX6287686 | 2023-10-01 | 2025-05-29 | N/A | 21106.31 | 22501.65 | 1180.13 | 5.245%
524 | MX5821182 | 2022-10-01 | 2025-07-29 | N/A | 268.6 | 19692.62 | 1179.24 | 5.988%
525 | MX6287660 | 2023-10-01 | 2025-05-29 | N/A | 21204.5 | 22713.13 | 1177.32 | 5.183%
526 | K2210SURK | 2022-02-01 | 2024-03-01 | 3.557% | 91.4 | 91.4 | 1174.21 | 1285%
527 | PH2ASPAHW | 2023-10-01 | 2026-03-31 | N/A | 11718 | 11718 | 1173.96 | 10.02%
528 | MX5821004 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 1166.19 | 434.2%
529 | M22034704 | 2023-07-01 | 2026-01-06 | N/A | 568351.42 | 568351.42 | 1162.77 | 0.2046%
530 | M24001501 | 2024-02-01 | 2025-06-13 | N/A | 25353.61 | 25353.61 | 1161.46 | 4.581%
531 | MX6287643 | 2023-10-01 | 2025-05-29 | N/A | 21719.29 | 22684.92 | 1156.55 | 5.098%
532 | MX6207287 | 2023-10-01 | 2025-05-29 | N/A | 17061.73 | 22704.84 | 1156.35 | 5.093%
533 | MX6287635 | 2023-10-01 | 2025-05-29 | N/A | 20879.86 | 22270.83 | 1149.1 | 5.16%
534 | MX6287625 | 2023-10-01 | 2025-05-29 | N/A | 20371.86 | 22213.42 | 1147.94 | 5.168%
535 | MX6287677 | 2023-10-01 | 2025-05-29 | N/A | 20518.67 | 25047.49 | 1140.32 | 4.553%
536 | MX2725053 | 2022-12-01 | 2024-06-27 | N/A | 268.6 | 41203.81 | 1120.24 | 2.719%
537 | V2078HAZK | 2023-02-01 | 2025-03-31 | N/A | 1 | 1087.87 | 1087.87 | 100%
538 | URDSTSP | 2015-07-01 | 2050-12-31 | 18.77% | 100 | 100 | 1082.56 | 1083%
539 | MX6287652 | 2023-10-01 | 2025-05-29 | N/A | 19703.95 | 34882.79 | 1051.78 | 3.015%
540 | SKY2310DC | 2023-08-01 | 2023-09-30 | N/A | 100 | 100 | 1033.79 | 1034%
541 | SPOLCMKY | 2022-07-01 | 2050-12-31 | N/A | 2 | 1022.73 | 1022.73 | 100%
542 | IT2300094 | 2023-11-01 | 2026-03-31 | N/A | 10409 | 10409 | 1002.25 | 9.629%
543 | V2070REMK | 2023-08-01 | 2025-03-31 | N/A | 1 | 1001.34 | 1001.34 | 100%
544 | MX5821196 | 2022-10-01 | 2025-01-29 | N/A | 268.6 | 20314.69 | 989.13 | 4.869%
545 | MX9353402 | 2023-11-01 | 2025-02-27 | N/A | 268.6 | 52916.41 | 968.55 | 1.83%
546 | KPDMCAP | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 1848672.78 | 964.39 | 0.05217%
547 | SG744MTR | 2018-07-01 | 2021-12-31 | 100% | 248821.93 | 248821.93 | 960.43 | 0.386%
548 | MX5821349 | 2022-10-01 | 2025-07-29 | N/A | 268.6 | 21321.08 | 954.07 | 4.475%
549 | MX9353393 | 2023-11-01 | 2025-03-06 | N/A | 268.6 | 58017.89 | 952.4 | 1.642%
550 | MX7372058 | 2022-06-01 | 2025-03-13 | N/A | 268.6 | 268.6 | 890.34 | 331.5%
551 | 349472033 | 2024-01-01 | 2025-03-31 | N/A | 18113 | 7763 | 844.99 | 10.88%
552 | M18043901 | 2021-05-01 | 2027-12-18 | 12.51% | 3044649.6 | 7209264.71 | 838.44 | 0.01163%
553 | MX5222181 | 2022-08-01 | 2025-07-29 | N/A | 0 | 0 | 829.79
554 | MX4279989 | 2022-04-01 | 2025-09-11 | N/A | 283945.63 | 283945.63 | 813.45 | 0.2865%
555 | MX9635259 | 2023-06-01 | 2024-03-30 | N/A | 15520.12 | 7637.15 | 812.65 | 10.64%
556 | M21049902 | 2023-07-01 | 2025-12-09 | N/A | 40965.28 | 40965.28 | 806.61 | 1.969%
557 | MX9353394 | 2023-11-01 | 2025-03-06 | N/A | 268.6 | 51750.06 | 805.36 | 1.556%
558 | M22021901 | 2024-01-01 | 2027-08-14 | N/A | 5089437.15 | 6361000.17 | 772.5 | 0.01214%
559 | MX8548579 | 2024-02-01 | 2025-05-29 | N/A | 57258.53 | 57258.53 | 766.71 | 1.339%
560 | MX1701448 | 2021-11-01 | 2025-07-29 | 8.712% | 268.6 | 268.6 | 744.06 | 277%
561 | MX7372052 | 2022-08-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 738.35 | 274.9%
562 | MX7372050 | 2022-06-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 727.93 | 271%
563 | M23009501 | 2023-10-01 | 2024-11-03 | N/A | 988571.76 | 121638.6 | 716.2 | 0.5888%
564 | MX8547401 | 2024-02-01 | 2025-02-28 | N/A | 268.6 | 3078.87 | 700.45 | 22.75%
565 | V2076HAZK | 2024-01-01 | 2026-03-31 | N/A | 1 | 695.47 | 695.47 | 100%
566 | MX7372049 | 2022-06-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 629.81 | 234.5%
567 | M19030002 | 2024-02-01 | 2025-02-25 | N/A | 71420 | 68547.61 | 608.04 | 0.887%
568 | KYGLT2103 | 2022-02-01 | 2024-11-19 | 2.642% | 31157 | 590.79 | 590.79 | 100%
569 | M20032701 | 2020-12-01 | 2021-05-28 | 100% | 77656 | 52574.39 | 491.43 | 0.9347%
570 | SGDER02 | 2023-11-01 | 2026-12-31 | N/A | 4100 | 4100 | 444.84 | 10.85%
571 | KRSOH | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 8958094.86 | 432.13 | 0.004824%
572 | MX5821189 | 2022-10-01 | 2025-05-01 | N/A | 268.6 | 2226.62 | 396.58 | 17.81%
573 | KCMCUG | 2017-12-01 | 2067-12-31 | 8.474% | 100 | 87944.18 | 379.81 | 0.4319%
574 | 349472034 | 2024-02-01 | 2026-03-31 | N/A | 61569 | 61569 | 359.64 | 0.5841%
575 | 315986HW8 | 2021-10-01 | 2022-06-30 | 55.15% | 163350 | 90589.27 | 340.49 | 0.3759%
576 | MX5821351 | 2022-10-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 339.63 | 126.4%
577 | KCRFR | 2017-11-01 | 2067-12-31 | 8.624% | 100 | 1815488.73 | 338.16 | 0.01863%
578 | MX5821352 | 2022-10-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 262.58 | 97.76%
579 | ETSFHCAPK | 2008-07-01 | 2050-12-31 | 32.15% | 0 | 0 | 257.929
580 | SGRFSKY | 2017-01-01 | 2025-12-31 | 57.33% | 102 | 77914.05 | 244.79 | 0.3142%
581 | EB022198X | 2024-02-01 | 2024-12-24 | N/A | 501081.85 | 898328.6 | 242.58 | 0.027%
582 | SGDLSKY | 2017-05-01 | 2025-12-31 | 55.72% | 102 | 86048.1 | 240.45 | 0.2794%
583 | MX5821151 | 2022-09-01 | 2025-07-29 | N/A | 268.6 | 1464.27 | 217.27 | 14.84%
584 | SGCAPATKY | 2017-01-01 | 2025-12-31 | 57.33% | 102 | 102 | 211.73 | 207.6%
585 | SG781SW | 2018-07-01 | 2021-03-31 | 100% | 187143.5 | 99113.7 | 200.96 | 0.2028%
586 | KLPF | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 2005758.35 | 191.23 | 0.009534%
587 | MX1701471 | 2022-06-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 177.13 | 65.95%
588 | KUC348450 | 2017-10-01 | 2022-06-30 | 92.96% | 100 | 100 | 167.24 | 167.2%
589 | V2287HAZK | 2024-01-01 | 2026-03-31 | N/A | 1 | 160.49 | 160.49 | 100%
590 | KROWCONS | 2022-04-01 | 2036-10-17 | N/A | 3600000 | 159.53 | 159.53 | 100%
591 | SGRXRKY | 2019-02-01 | 2050-12-31 | 9.635% | 2 | 28625.4 | 159 | 0.5555%
592 | SGHYDRKY | 2016-10-01 | 2025-12-31 | 58.5% | 102 | 412716.28 | 130.38 | 0.03159%
593 | PDOHRPLKY | 2016-02-01 | 2025-12-31 | 61.28% | 1 | 435458.82 | 106.85 | 0.02454%
594 | MX5821358 | 2022-10-01 | 2025-07-29 | N/A | 268.6 | 268.6 | 102.7 | 38.24%
595 | KRIOTCO | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 872763.29 | 98.74 | 0.01131%
596 | MX5254697 | 2022-09-01 | 2024-09-28 | N/A | 268.6 | 268.6 | 93.54 | 34.83%
597 | M23010901 | 2023-11-01 | 2025-08-16 | N/A | 696803.78 | 696803.78 | 83.02 | 0.01191%
598 | SPOLOTHKY | 2019-04-01 | 2050-12-31 | 9.175% | 2 | 79.5 | 79.5 | 100%
599 | 400113006 | 2024-02-01 | 2025-03-31 | N/A | 46906 | 46906 | 78.28 | 0.1669%
600 | SG489SW | 2016-11-01 | 2018-12-31 | 100% | 39053.22 | 39053.22 | 66.58 | 0.1705%
601 | MX9310771 | 2024-01-01 | 2025-08-29 | N/A | 268.6 | 419036.62 | 57.06 | 0.01362%
602 | KRUCSMCM | 2019-06-01 | 2068-03-31 | 5.623% | 100 | 1900877.46 | 50.45 | 0.002654%
603 | M18037504 | 2022-07-01 | 2023-07-01 | N/A | 63208 | 63208 | 50.09 | 0.07925%
604 | MX9780049 | 2023-06-01 | 2024-11-14 | N/A | 268.6 | 176273.25 | 45.71 | 0.02593%
605 | KRTXO | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 300719.27 | 45.05 | 0.01498%
606 | D1912DS1 | 2016-09-01 | 2017-09-01 | 100% | 2776527.3 | 3040390.6 | 41.6 | 0.001368%
607 | KMTROWS | 2018-12-01 | 2026-03-31 | 44.27% | 112016.29 | 4001405 | 39.4 | 0.0009847%
608 | KRUCSEC | 2018-04-01 | 2067-12-31 | 7.864% | 100 | 756923.68 | 27.55 | 0.00364%
609 | ICCONSTRD | 2017-10-01 | 2030-09-30 | 33.94% | 1 | 26.04 | 26.04 | 100%
610 | SG1010Z1R | 2023-07-01 | 2024-01-23 | N/A | 464002 | 18.1 | 18.1 | 100%
611 | KPOLCM | 2017-09-01 | 2067-12-31 | 8.927% | 100 | 3202799.15 | 17.05 | 0.0005323%
612 | SKY1911DC | 2020-01-01 | 2020-03-31 | 100% | 100 | 100 | 15.47 | 15.47%
613 | KCMCEUG | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 899555.09 | 14.67 | 0.001631%
614 | M19016703 | 2019-08-01 | 2021-03-12 | 100% | 0 | 0 | 14.05
615 | KRCR | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 1004527.99 | 11.84 | 0.001179%
616 | KRRRCM | 2019-06-01 | 2068-03-31 | 5.623% | 100 | 624361.58 | 10.12 | 0.001621%
617 | MX5821211 | 2022-10-01 | 2024-12-29 | N/A | 268.6 | 268.6 | 9.03 | 3.362%
618 | MX5821218 | 2022-10-01 | 2024-12-29 | N/A | 268.6 | 268.6 | 9.03 | 3.362%
619 | 315986HW7 | 2021-04-01 | 2021-12-31 | 100% | 152040 | 43701.55 | 6.85 | 0.01567%
620 | MX9353381 | 2023-08-01 | 2025-08-28 | N/A | 268.6 | 6587.96 | 5.87 | 0.0891%
621 | 349472032 | 2024-02-01 | 2026-03-31 | N/A | 24871 | 24871 | 2.76 | 0.0111%
622 | 315986HW6 | 2020-03-01 | 2020-11-30 | 100% | 51975 | 170886.9 | 2.58 | 0.00151%
623 | MX9353353 | 2023-08-01 | 2025-03-01 | N/A | 268.6 | 268.6 | 2.51 | 0.9345%
624 | KCIPLW085 | 2017-03-01 | 2019-03-31 | 100% | 197245 | 197245 | 2.48 | 0.001257%
625 | M19016704 | 2019-08-01 | 2021-03-12 | 100% | 0 | 0 | 1.32
626 | KMTROWT | 2019-01-01 | 2026-03-31 | 43.61% | 12543.49 | 898017 | 1.01 | 0.0001125%
627 | INCENTIVE | 2009-12-01 | 2009-12-10 | 100% | 0 | 0 | -0.716
628 | KRUPOH | 2017-09-01 | 2067-12-31 | 8.927% | 100 | 2103512.29 | -0.96 | -4.564e-05%
629 | KCIUPOH | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 1188146.01 | -8.31 | -0.0006994%
630 | SG344SW | 2016-01-01 | 2020-03-31 | 100% | 73774 | 84114.46 | -12.04 | -0.01431%
631 | SG685TUGK | 2020-01-01 | 2026-03-31 | 34.59% | 400000 | 400000 | -16.64 | -0.00416%
632 | SGOVH | 2016-01-01 | 2025-12-15 | 61.88% | 100 | 100 | -53.68 | -53.68%
633 | SG336OUA | 2018-08-01 | 2021-05-28 | 100% | 155000 | 156182.6 | -65.45 | -0.04191%
634 | TKYTOOL | 2017-11-01 | 2050-12-31 | 13.04% | 100 | 11 | -114.11 | -1037%
635 | KCOU | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 2146214.04 | -171.98 | -0.008013%
636 | M19016706 | 2020-01-01 | 2027-02-08 | 30.4% | 87142 | 87142 | -244.96 | -0.2811%
637 | SG983TMT2 | 2019-08-01 | 2021-11-02 | 100% | 44390.63 | 29832.07 | -312.51 | -1.048%
638 | KCIPOH | 2017-08-01 | 2067-12-31 | 9.08% | 100 | 9290219.83 | -457.58 | -0.004925%
639 | 78906 | 1999-12-01 | 2000-04-13 | 100% | 1 | -472.79 | -472.79
640 | KSVDTUG | 2018-08-01 | 2068-03-31 | 7.205% | 0 | 0 | -568.7
641 | 359140001 | 2019-01-01 | 2024-02-15 | 61.68% | 169292 | 140607.54 | -606.6 | -0.4314%
642 | 35035 | 2000-06-01 | 2000-04-13 | 100% | 1 | -856 | -856
643 | MX9998915 | 2018-05-01 | 2024-07-26 | 61.41% | 268.6 | 268.6 | -969.27 | -360.9%
644 | 400109 | 2022-07-01 | 2024-01-19 | N/A | 1166239 | 781409.79 | -1768.55 | -0.2263%
645 | OLE09RPKY | 2009-02-01 | 2050-12-31 | 31.19% | 12244 | 3428.36 | -2675.6 | -78.04%
646 | MX8659310 | 2023-09-01 | 2024-05-09 | N/A | 75956.57 | 72987.49 | -19858.08 | -27.21%
647 | KCMCEOH | 2017-10-01 | 2067-12-31 | 8.778% | 100 | 2524984.67 | -22709 | -0.8994%
648 | DISOHDK | 2018-01-01 | 2026-03-31 | 50.45% | 0 | 0 | -39873.965
649 | KMTROWR2 | 2022-05-01 | 2026-03-31 | N/A | 1 | -49243.73 | -49243.73
650 | M21050401 | 2022-01-01 | 2025-12-23 | 3.994% | 755724 | 740611.96 | -51652.59 | -6.974%
651 | MX0935094 | 2023-12-01 | 2025-02-23 | N/A | 45361.66 | 54910.42 | -56920.99 | -103.7%
652 | MX0394663 | 2024-02-01 | 2024-08-22 | N/A | 57011.66 | 62201.44 | -57011.74 | -91.66%
653 | MX0867359 | 2022-10-01 | 2026-02-26 | N/A | 94725.55 | 94725.55 | -115903.26 | -122.4%
654 | MX9907616 | 2023-08-01 | 2024-11-14 | N/A | 268.6 | 233577.06 | -138437.03 | -59.27%
655 | MX0467189 | 2024-02-01 | 2025-02-27 | N/A | 138941.36 | 138941.36 | -168785.2 | -121.5%
656 | Blank
57567952.057