## 2015-2024
Duke Energy Kentucky
Case No. 2024-00354
AG-DR-01-076 subpart c
DEK Planned Outage from 2015 - 2024
Unit | Primary Fuel Type | Event Start | Event End | Event Type | Event Description
East Bend Steam-2 | Coal | 2015-03-21 00:15 | 2015-03-30 04:00 | PO | Planned Spring Outage
Woodsdale CT-5 | Natural Gas | 2015-09-28 10:30 | 2015-10-02 17:59 | PO | Exciter modification
Woodsdale CT-6 | Natural Gas | 2015-09-28 10:30 | 2015-10-02 17:47 | PO | Exciter modification
Woodsdale CT-2 | Natural Gas | 2015-10-12 10:00 | 2015-10-15 17:56 | PO | Exciter modification
Woodsdale CT-1 | Natural Gas | 2015-10-12 10:00 | 2015-10-15 17:20 | PO | Install Smart Gen modifications
East Bend Steam-2 | Coal | 2016-03-24 01:15 | 2016-05-01 03:59 | PO | Planned spring outage-Reheat tube replacement installation critical path
Woodsdale CT-1 | Natural Gas | 2016-04-30 10:00 | 2016-05-13 21:04 | PO | Boroscope and Fire Protection Upgrade
Woodsdale CT-2 | Natural Gas | 2016-05-01 10:00 | 2016-05-16 18:04 | PO | Boroscope and Fire Protection Upgrade
Woodsdale CT-3 | Natural Gas | 2016-05-07 11:00 | 2016-05-19 17:22 | PO | Boroscope and Fire Protection Upgrade
Woodsdale CT-5 | Natural Gas | 2016-05-14 10:00 | 2016-05-20 14:40 | PO | Boroscope and Fire Protection Upgrade
Woodsdale CT-6 | Natural Gas | 2016-05-14 10:00 | 2016-05-20 18:07 | PO | Boroscope and Fire Protection Upgrade
Woodsdale CT-4 | Natural Gas | 2016-05-22 11:00 | 2016-05-27 18:30 | PO | Boroscope and Fire Protection Upgrade
Woodsdale CT-1 | Natural Gas | 2017-03-04 11:30 | 2017-05-08 14:17 | PO | hot gas path outage
East Bend Steam-2 | Coal | 2017-04-29 04:32 | 2017-05-08 03:59 | PO | Spring Outage-Precip Wash
Woodsdale CT-1 | Natural Gas | 2017-05-08 17:34 | 2017-05-09 17:52 | PO | Planned C Inspection Outage
Woodsdale CT-1 | Natural Gas | 2017-05-09 20:31 | 2017-05-11 15:59 | PO | Planned C Inspection Outage
Woodsdale CT-5 | Natural Gas | 2017-09-09 16:00 | 2017-09-18 17:28 | PO | Doble testing and relay upgrades
Woodsdale CT-6 | Natural Gas | 2017-09-09 16:00 | 2017-09-18 17:28 | PO | Tagged for doble testing and relay upgrades
Woodsdale CT-3 | Natural Gas | 2017-09-18 10:00 | 2017-09-22 20:15 | PO | Doble Testing
Woodsdale CT-4 | Natural Gas | 2017-09-18 10:00 | 2017-09-22 20:15 | PO | Doble Testing
Woodsdale CT-2 | Natural Gas | 2017-09-23 10:00 | 2017-09-29 20:21 | PO | Outage: Doble testing
Woodsdale CT-1 | Natural Gas | 2017-09-23 10:00 | 2017-09-29 20:21 | PO | Outage: Doble testing
East Bend Steam-2 | Coal | 2018-03-03 00:19 | 2018-06-01 04:00 | PO | Spring Planned Outage-ESP rebuild and Dry Bottom Ash Conversion
Woodsdale CT-2 | Natural Gas | 2018-09-17 10:00 | 2018-09-20 15:59 | PO | Replace Main Natural Gas Valve NG001
Woodsdale CT-5 | Natural Gas | 2018-09-17 10:00 | 2018-09-20 15:59 | PO | Replace Main Natural Gas Valve NG001
Woodsdale CT-1 | Natural Gas | 2018-09-17 10:00 | 2018-09-20 15:36 | PO | Replace Main Natural Gas Valve NG001
Woodsdale CT-3 | Natural Gas | 2018-09-17 10:00 | 2018-09-20 16:01 | PO | Replace Main Natural Gas Valve NG001
Woodsdale CT-4 | Natural Gas | 2018-09-17 10:00 | 2018-09-20 16:03 | PO | Replace Main Natural Gas Valve NG001
Woodsdale CT-6 | Natural Gas | 2018-09-17 10:00 | 2018-09-20 16:04 | PO | Replace Main Natural Gas Valve NG001
Woodsdale CT-5 | Natural Gas | 2018-10-19 10:00 | 2018-10-19 22:00 | PO | Out for fire protection testing
Woodsdale CT-6 | Natural Gas | 2018-10-19 10:00 | 2018-10-19 22:00 | PO | Out for fire protection testing
Woodsdale CT-2 | Natural Gas | 2018-10-19 11:30 | 2018-10-19 16:35 | PO | Testing for fuel oil project
Woodsdale CT-3 | Natural Gas | 2018-10-22 10:00 | 2018-10-23 13:30 | PO | Out for fire protection testing
Woodsdale CT-4 | Natural Gas | 2018-10-22 10:00 | 2018-10-22 20:40 | PO | Out for fire protection testing
Woodsdale CT-2 | Natural Gas | 2018-11-02 10:00 | 2018-12-09 13:00 | PO | Outage to install fuel oil capability
Woodsdale CT-1 | Natural Gas | 2018-11-02 10:00 | 2018-12-26 15:59 | PO | Outage to install fuel oil capability
Woodsdale CT-2 | Natural Gas | 2019-01-01 05:00 | 2019-05-08 15:29 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-1 | Natural Gas | 2019-02-09 11:00 | 2019-04-04 23:14 | PO | Tie in to new Fuel Oil System
Woodsdale CT-5 | Natural Gas | 2019-03-10 10:00 | 2019-04-26 22:25 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-03-10 10:00 | 2019-04-28 22:14 | PO | Fuel Oil Outage
East Bend Steam-2 | Coal | 2019-04-03 04:00 | 2019-05-04 12:08 | PO | Repair to LPB L-1 Blades
Woodsdale CT-1 | Natural Gas | 2019-04-05 00:07 | 2019-04-05 14:58 | PO | Fuel Oil Outage
Woodsdale CT-1 | Natural Gas | 2019-04-05 20:12 | 2019-04-07 12:42 | PO | Fuel Oil Outage
Woodsdale CT-1 | Natural Gas | 2019-04-07 16:03 | 2019-04-09 18:15 | PO | Fuel Oil Outage
Woodsdale CT-4 | Natural Gas | 2019-04-09 10:00 | 2019-05-20 15:58 | PO | Fuel Oil Outage
Woodsdale CT-1 | Natural Gas | 2019-04-09 19:17 | 2019-04-10 17:32 | PO | Fuel Oil Outage
Woodsdale CT-1 | Natural Gas | 2019-04-10 20:48 | 2019-04-11 12:42 | PO | Fuel Oil Outage
Woodsdale CT-3 | Natural Gas | 2019-04-11 10:00 | 2019-05-26 17:01 | PO | Fuel Oil Outage
Woodsdale CT-1 | Natural Gas | 2019-04-12 03:22 | 2019-04-12 11:22 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-04-26 22:47 | 2019-04-27 16:01 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-04-27 16:48 | 2019-04-28 13:01 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-04-28 17:41 | 2019-04-29 15:56 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-04-28 22:39 | 2019-04-29 12:57 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-04-29 17:08 | 2019-04-30 11:36 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-04-29 21:48 | 2019-04-30 16:02 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-04-30 12:25 | 2019-05-01 11:38 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-04-30 16:07 | 2019-05-01 19:27 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-05-01 16:18 | 2019-05-03 11:16 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-01 19:38 | 2019-05-03 21:58 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-05-03 21:08 | 2019-05-04 16:43 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-03 22:06 | 2019-05-04 18:49 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-04 18:53 | 2019-05-14 19:04 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-05-04 19:25 | 2019-05-14 20:30 | PO | Fuel Oil Outage
Woodsdale CT-2 | Natural Gas | 2019-05-08 19:33 | 2019-05-09 12:41 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-2 | Natural Gas | 2019-05-09 16:03 | 2019-05-14 11:21 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-5 | Natural Gas | 2019-05-14 20:00 | 2019-05-15 11:25 | PO | Fuel Oil Outage
Woodsdale CT-2 | Natural Gas | 2019-05-14 20:21 | 2019-05-18 13:53 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-6 | Natural Gas | 2019-05-14 21:17 | 2019-05-15 15:25 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-15 17:23 | 2019-05-16 12:13 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-05-15 20:16 | 2019-05-17 11:54 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-16 20:52 | 2019-05-17 18:20 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-05-17 20:39 | 2019-05-20 13:30 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-17 22:26 | 2019-05-19 00:40 | PO | Fuel Oil Outage
Woodsdale CT-2 | Natural Gas | 2019-05-18 15:09 | 2019-05-21 17:31 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-5 | Natural Gas | 2019-05-19 02:08 | 2019-05-21 12:15 | PO | Fuel Oil Outage
Woodsdale CT-6 | Natural Gas | 2019-05-20 17:31 | 2019-05-22 11:46 | PO | Fuel Oil Outage
Woodsdale CT-4 | Natural Gas | 2019-05-20 20:32 | 2019-05-27 15:32 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-21 16:10 | 2019-05-22 12:11 | PO | Fuel Oil Outage
Woodsdale CT-2 | Natural Gas | 2019-05-21 18:06 | 2019-05-23 14:18 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-5 | Natural Gas | 2019-05-22 12:13 | 2019-05-22 21:16 | PO | Fuel Oil Outage
Woodsdale CT-5 | Natural Gas | 2019-05-22 21:55 | 2019-05-23 11:17 | PO | Fuel Oil Outage
Woodsdale CT-2 | Natural Gas | 2019-05-23 18:14 | 2019-05-24 12:15 | PO | During burner inspection found damaged turbine blades
Woodsdale CT-3 | Natural Gas | 2019-05-26 18:54 | 2019-05-27 09:03 | PO | Fuel Oil Outage
Woodsdale CT-3 | Natural Gas | 2019-05-27 12:57 | 2019-05-27 18:22 | PO | Fuel Oil Outage
Woodsdale CT-4 | Natural Gas | 2019-05-27 15:46 | 2019-05-30 21:51 | PO | Fuel Oil Outage
Woodsdale CT-3 | Natural Gas | 2019-05-27 21:49 | 2019-05-28 14:42 | PO | Fuel Oil Outage
Woodsdale CT-3 | Natural Gas | 2019-05-28 23:06 | 2019-05-30 11:41 | PO | Fuel Oil Outage
Woodsdale CT-3 | Natural Gas | 2019-05-30 19:57 | 2019-05-30 22:12 | PO | Fuel Oil Outage
Woodsdale CT-4 | Natural Gas | 2019-05-30 23:55 | 2019-05-31 09:11 | PO | Fuel Oil Outage
Woodsdale CT-1 | Natural Gas | 2019-09-18 10:00 | 2019-11-19 15:57 | PO | Generator upgrade
Woodsdale CT-5 | Natural Gas | 2019-09-21 10:00 | 2019-10-19 12:00 | PO | SFC outage
Woodsdale CT-4 | Natural Gas | 2019-09-21 10:00 | 2019-11-18 16:53 | PO | Begin U4 Compressor Outage
Woodsdale CT-6 | Natural Gas | 2019-09-21 10:00 | 2019-10-19 11:56 | PO | SFC outage
Woodsdale CT-3 | Natural Gas | 2019-10-12 10:00 | 2019-10-30 12:09 | PO | SFC outage
Woodsdale CT-2 | Natural Gas | 2019-11-02 10:00 | 2019-11-19 17:37 | PO | SFC and synchronizer outage
Woodsdale CT-2 | Natural Gas | 2020-03-07 05:01 | 2020-03-21 01:00 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-1 | Natural Gas | 2020-03-07 05:01 | 2020-03-21 01:00 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-3 | Natural Gas | 2020-03-14 04:59 | 2020-03-21 01:00 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-4 | Natural Gas | 2020-03-14 04:59 | 2020-03-21 00:47 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-5 | Natural Gas | 2020-03-21 10:00 | 2020-03-27 22:20 | PO | Spring Prep Outage
Woodsdale CT-6 | Natural Gas | 2020-03-21 10:00 | 2020-03-27 22:01 | PO | Spring Prep Outage
Woodsdale CT-2 | Natural Gas | 2020-04-25 10:00 | 2020-04-25 19:25 | PO | Plant Blackstart; disconnected from grid
Woodsdale CT-5 | Natural Gas | 2020-04-25 10:00 | 2020-04-25 19:25 | PO | Plant Blackstart; disconnected from grid
Woodsdale CT-1 | Natural Gas | 2020-04-25 10:00 | 2020-04-25 19:25 | PO | Plant Blackstart; disconnected from grid
Woodsdale CT-3 | Natural Gas | 2020-04-25 10:00 | 2020-04-25 19:25 | PO | Plant Blackstart; disconnected from grid
Woodsdale CT-4 | Natural Gas | 2020-04-25 10:00 | 2020-04-25 19:25 | PO | Plant Blackstart; disconnected from grid
Woodsdale CT-6 | Natural Gas | 2020-04-25 10:00 | 2020-04-25 19:25 | PO | Plant Blackstart; disconnected from grid
East Bend Steam-2 | Coal | 2020-05-14 05:00 | 2020-05-24 12:00 | PO | Planned outage for FGD cleaning
Woodsdale CT-2 | Natural Gas | 2020-09-12 10:00 | 2020-09-18 22:55 | PO | Main NG to plant isolated for modifications
Woodsdale CT-5 | Natural Gas | 2020-09-12 10:00 | 2020-09-20 15:55 | PO | Main NG to plant isolated for modifications
Woodsdale CT-1 | Natural Gas | 2020-09-12 10:00 | 2020-09-19 17:15 | PO | Main NG to plant isolated for modifications
Woodsdale CT-3 | Natural Gas | 2020-09-12 10:00 | 2020-09-18 22:55 | PO | Main NG to plant isolated for modifications
Woodsdale CT-4 | Natural Gas | 2020-09-12 10:00 | 2020-09-18 22:55 | PO | Main NG to plant isolated for modifications
Woodsdale CT-6 | Natural Gas | 2020-09-12 10:00 | 2020-09-20 15:28 | PO | Main NG to plant isolated for modifications
East Bend Steam-2 | Coal | 2020-09-18 21:12 | 2020-11-21 00:58 | PO | 2020 Fall Planned Outage
Woodsdale CT-3 | Natural Gas | 2020-09-18 22:55 | 2020-10-09 21:13 | PO | Stack repairs
Woodsdale CT-4 | Natural Gas | 2020-09-18 22:55 | 2020-10-06 16:09 | PO | Stack repairs
Woodsdale CT-2 | Natural Gas | 2020-11-02 11:00 | 2020-11-13 20:34 | PO | Generator Breaker Outage
Woodsdale CT-1 | Natural Gas | 2020-11-02 11:00 | 2020-11-13 20:22 | PO | Generator Breaker Outage
Woodsdale CT-5 | Natural Gas | 2020-11-14 11:00 | 2020-11-19 22:41 | PO | Bus Duct Heater Repairs
Woodsdale CT-6 | Natural Gas | 2020-11-14 11:00 | 2020-11-19 22:41 | PO | Bus Duct Heater Repairs
Woodsdale CT-5 | Natural Gas | 2021-03-13 11:00 | 2021-05-27 13:09 | PO | Generator Rewind Outage
Woodsdale CT-6 | Natural Gas | 2021-03-13 11:00 | 2021-06-07 15:26 | PO | Generator Rewind Outage
East Bend Steam-2 | Coal | 2021-04-24 03:14 | 2021-05-03 10:00 | PO | 2021 Spring Planned Outage
Woodsdale CT-3 | Natural Gas | 2021-05-15 10:00 | 2021-05-22 13:51 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-4 | Natural Gas | 2021-05-15 10:00 | 2021-05-22 13:09 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-3 | Natural Gas | 2021-05-22 13:57 | 2021-05-22 15:30 | PO | Spring Prep and Boroscope Inspection
Woodsdale CT-5 | Natural Gas | 2021-05-27 13:15 | 2021-05-27 14:53 | PO | Generator Rewind Outage
East Bend Steam-2 | Coal | 2021-09-11 03:02 | 2021-11-21 05:00 | PO | Planned Fall Outage
Woodsdale CT-2 | Natural Gas | 2021-09-13 10:00 | 2021-09-17 17:00 | PO | Transformer Bank 39 Annunciator Outage
Woodsdale CT-1 | Natural Gas | 2021-09-13 10:00 | 2021-09-17 19:30 | PO | Replace Annunciator on Transformer Bank 39.
Woodsdale CT-3 | Natural Gas | 2021-09-18 10:00 | 2021-09-25 19:03 | PO | TB40 annunciator outage, replace fuel valve
Woodsdale CT-4 | Natural Gas | 2021-09-18 10:00 | 2021-09-25 18:25 | PO | TB40 annunciator outage, stack repairs
Woodsdale CT-1 | Natural Gas | 2021-12-11 11:00 | 2021-12-14 22:14 | PO | Perform Eddy Current Testing on row 4 turbine blades.
East Bend Steam-2 | Coal | 2021-12-26 02:44 | 2021-12-26 04:28 | PO | 5 MW Trip to Test Relays
Woodsdale CT-2 | Natural Gas | 2022-03-18 10:00 | 2022-03-25 20:49 | PO | Boroscope inspection
Woodsdale CT-1 | Natural Gas | 2022-03-18 10:00 | 2022-03-25 20:51 | PO | Boroscope inspection
Woodsdale CT-3 | Natural Gas | 2022-03-18 10:00 | 2022-06-01 04:00 | PO | Generator field rewind
Woodsdale CT-4 | Natural Gas | 2022-03-18 10:00 | 2022-03-25 20:48 | PO | Boroscope inspection
Woodsdale CT-4 | Natural Gas | 2022-03-30 13:00 | 2022-04-01 23:00 | PO | Opened Bank 1602 to move crane for GT3 Gen lift.
Woodsdale CT-5 | Natural Gas | 2022-04-23 10:00 | 2022-04-28 16:38 | PO | Boroscope inspection
Woodsdale CT-6 | Natural Gas | 2022-04-23 10:00 | 2022-04-28 19:12 | PO | Boroscope inspection
Woodsdale CT-4 | Natural Gas | 2022-05-13 11:00 | 2022-05-13 21:20 | PO | Crane outage, for GT3 Gen Rotor.
Woodsdale CT-1 | Natural Gas | 2022-05-20 10:00 | 2022-05-25 13:20 | PO | Inspect Turbine Blades
Woodsdale CT-4 | Natural Gas | 2022-06-06 14:05 | 2022-06-06 21:50 | PO | Crane outage, for GT3 Gen Rotor
Woodsdale CT-2 | Natural Gas | 2022-09-17 10:00 | 2022-09-23 20:20 | PO | Replace Natural Gas Valves.
Woodsdale CT-1 | Natural Gas | 2022-09-17 10:00 | 2022-09-23 18:50 | PO | Replace Natural Gas Valves.
East Bend Steam-2 | Coal | 2022-09-24 04:00 | 2022-11-03 04:17 | PO | Planned Fall 2022 Outage - Critical path SAH Basket replacement
Woodsdale CT-4 | Natural Gas | 2022-10-01 10:00 | 2022-10-06 19:37 | PO | Replace Natural Gas Valves.
Woodsdale CT-5 | Natural Gas | 2022-10-08 10:00 | 2022-10-13 19:14 | PO | Replace Natural Gas Valves.
Woodsdale CT-6 | Natural Gas | 2022-10-08 10:00 | 2022-10-13 19:17 | PO | Replace Natural Gas Valves.
Woodsdale CT-6 | Natural Gas | 2022-10-31 09:00 | 2022-10-31 16:49 | PO | Natural Gas Flowmeter Calibration
Woodsdale CT-2 | Natural Gas | 2023-03-04 11:00 | 2023-03-18 17:49 | PO | Borescope inspection / Spring Prep
Woodsdale CT-1 | Natural Gas | 2023-03-04 11:00 | 2023-03-18 17:34 | PO | Borescope inspection / Spring Prep
Woodsdale CT-4 | Natural Gas | 2023-03-11 11:00 | 2023-03-24 12:53 | PO | Borescope inspection / Spring Prep
Woodsdale CT-5 | Natural Gas | 2023-03-18 10:00 | 2023-04-01 18:23 | PO | Borescope inspection / Spring Prep.
Woodsdale CT-6 | Natural Gas | 2023-03-18 10:00 | 2023-04-01 18:20 | PO | Borescope inspection / Spring Prep
Woodsdale CT-2 | Natural Gas | 2023-03-18 17:55 | 2023-03-18 19:35 | PO | Borescope inspection / Spring Prep
East Bend Steam-2 | Coal | 2023-04-20 03:40 | 2023-05-07 07:26 | PO | Summer Prep Spring Outage
Woodsdale CT-1 | Natural Gas | 2023-05-01 10:00 | 2023-05-04 20:00 | PO | Outage for Fuel Oil Tubing Repairs
Woodsdale CT-2 | Natural Gas | 2023-05-04 10:00 | 2023-05-05 21:00 | PO | Outage for Fuel Oil Tubing Repairs
Woodsdale CT-4 | Natural Gas | 2023-05-11 10:00 | 2023-05-12 19:27 | PO | Outage for Fuel Oil Tubing Repairs
Woodsdale CT-4 | Natural Gas | 2023-06-30 10:00 | 2023-07-02 18:31 | PO | Opened Bank 1602 to move crane for GT3 Gen lift.
Woodsdale CT-2 | Natural Gas | 2023-08-08 10:00 | 2023-08-10 11:35 | PO | Plant outage to inspect receiver air tanks
Woodsdale CT-5 | Natural Gas | 2023-08-08 10:00 | 2023-08-10 11:35 | PO | Plant outage to inspect receiver air tanks
Woodsdale CT-1 | Natural Gas | 2023-08-08 10:00 | 2023-08-10 11:35 | PO | Plant outage to inspect receiver air tanks
Woodsdale CT-3 | Natural Gas | 2023-08-08 10:00 | 2023-08-10 11:35 | PO | Plant outage to inspect receiver air tanks
Woodsdale CT-4 | Natural Gas | 2023-08-08 10:00 | 2023-08-10 11:35 | PO | Plant outage to inspect receiver air tanks
Woodsdale CT-6 | Natural Gas | 2023-08-08 10:00 | 2023-08-10 11:35 | PO | Plant outage to inspect receiver air tanks
East Bend Steam-2 | Coal | 2023-09-18 04:00 | 2023-11-07 03:00 | PO | Fall Planned Outage
Woodsdale CT-2 | Natural Gas | 2023-09-23 04:00 | 2023-10-06 20:13 | PO | Fall outage / Borescope
Woodsdale CT-1 | Natural Gas | 2023-09-23 04:00 | 2023-10-06 19:12 | PO | Fall outage / Borescope
Woodsdale CT-3 | Natural Gas | 2023-09-30 04:00 | 2023-10-13 15:24 | PO | Fall outage / Borescope
Woodsdale CT-4 | Natural Gas | 2023-09-30 04:00 | 2023-10-13 15:18 | PO | Fall outage / Borescope
Woodsdale CT-5 | Natural Gas | 2023-10-09 04:00 | 2023-10-20 21:16 | PO | Fall outage / Borescope
Woodsdale CT-6 | Natural Gas | 2023-10-09 04:00 | 2023-10-20 21:32 | PO | Fall outage / Borescope
East Bend Steam-2 | Coal | 2023-11-07 10:54 | 2023-11-08 06:36 | PO | Boiler Feed Pump and Turbine Overspeed Protection Control Upgrade Testing
East Bend Steam-2 | Coal | 2023-11-12 03:56 | 2023-11-12 13:14 | PO | Boiler Feed Pump and Turbine Overspeed Protection Control Upgrade Testing
East Bend Steam-2 | Coal | 2023-11-12 13:28 | 2023-11-13 05:46 | PO | Boiler Feed Pump and Turbine Overspeed Protection Control Upgrade Testing
Woodsdale CT-2 | Natural Gas | 2023-11-16 11:00 | 2023-11-16 23:00 | PO | Repairs made on main plant UPS system, both primary and backups.
Woodsdale CT-5 | Natural Gas | 2023-11-16 11:00 | 2023-11-16 23:00 | PO | Repairs made on main plant UPS system, both primary and backups.
Woodsdale CT-1 | Natural Gas | 2023-11-16 11:00 | 2023-11-16 23:00 | PO | Repairs made on main plant UPS system, both primary and backups.
Woodsdale CT-3 | Natural Gas | 2023-11-16 11:00 | 2023-11-16 23:00 | PO | Repairs made on main plant UPS system, both primary and backups.
Woodsdale CT-4 | Natural Gas | 2023-11-16 11:00 | 2023-11-16 23:00 | PO | Repairs made on main plant UPS system, both primary and backups.
Woodsdale CT-6 | Natural Gas | 2023-11-16 11:00 | 2023-11-16 23:00 | PO | Repairs made on main plant UPS system, both primary and backups.
Woodsdale CT-1 | Natural Gas | 2024-03-01 05:01 | 2024-05-23 19:41 | PO | Turbine blade replacement, rows 1-4
Woodsdale CT-6 | Natural Gas | 2024-03-27 04:01 | 2024-03-27 13:27 | PO | Unit unavailable to change out gas fuel flow meter.
Woodsdale CT-2 | Natural Gas | 2024-04-20 04:01 | 2024-05-03 20:51 | PO | Spring outage/Borescope
Woodsdale CT-3 | Natural Gas | 2024-04-27 04:01 | 2024-05-10 15:18 | PO | Spring outage/Borescope
Woodsdale CT-4 | Natural Gas | 2024-04-27 04:01 | 2024-05-09 21:10 | PO | Spring outage/Borescope
Woodsdale CT-6 | Natural Gas | 2024-05-11 10:00 | 2024-06-03 16:06 | PO | Spring outage/Borescope
Woodsdale CT-2 | Natural Gas | 2024-08-19 04:01 | 2024-08-24 03:59 | PO | Control room consolidation
Woodsdale CT-5 | Natural Gas | 2024-08-19 04:01 | 2024-08-24 03:59 | PO | Control room consolidation
Woodsdale CT-1 | Natural Gas | 2024-08-19 04:01 | 2024-08-24 03:59 | PO | Control room consolidation
Woodsdale CT-3 | Natural Gas | 2024-08-19 04:01 | 2024-08-24 03:59 | PO | Control room consolidation
Woodsdale CT-4 | Natural Gas | 2024-08-19 04:01 | 2024-08-24 03:59 | PO | Control room consolidation
Woodsdale CT-6 | Natural Gas | 2024-08-19 04:01 | 2024-08-24 03:59 | PO | Control room consolidation
East Bend Steam-2 | Coal | 2024-09-06 16:30 | 2024-11-05 16:17 | PO | 2024 Fall Outage - FGD Ductwork replacement - CBU Buckets - SBAC Overhaul
Woodsdale CT-4 | Natural Gas | 2024-09-07 04:01 | 2024-11-20 17:56 | PO | Unit Major (overhaul)
Woodsdale CT-2 | Natural Gas | 2024-09-12 04:01 | 2024-09-12 20:00 | PO | Enbridge working on their regulating station.
Woodsdale CT-1 | Natural Gas | 2024-09-12 04:01 | 2024-09-12 20:00 | PO | Enbridge working on their regulating station.
Woodsdale CT-3 | Natural Gas | 2024-09-12 04:01 | 2024-09-12 20:00 | PO | Enbridge working on their regulating station.
Woodsdale CT-2 | Natural Gas | 2024-09-14 04:01 | 2024-09-28 17:51 | PO | Fall Outage
Woodsdale CT-1 | Natural Gas | 2024-09-14 04:01 | 2024-09-28 17:50 | PO | Fall Outage
Woodsdale CT-3 | Natural Gas | 2024-09-21 04:01 | 2024-10-05 10:40 | PO | Fall Outage
Woodsdale CT-5 | Natural Gas | 2024-09-26 04:01 | 2024-09-26 20:00 | PO | Enbridge working on their regulating station.
Woodsdale CT-6 | Natural Gas | 2024-09-26 04:01 | 2024-09-26 20:00 | PO | Enbridge working on their regulating station.
Woodsdale CT-5 | Natural Gas | 2024-09-28 04:01 | 2024-10-12 09:24 | PO | Fall Outage
Woodsdale CT-6 | Natural Gas | 2024-09-28 04:01 | 2024-10-18 21:31 | PO | Fall Outage
Woodsdale CT-4 | Natural Gas | 2024-11-20 22:12 | 2024-11-21 19:41 | PO | Unit Major (overhaul)