## 2019
Duke Energy Kentucky Electric
Year 2019
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75084 | FPIT | 338802004 | Mobile Durable Team | 73514.33 |  | 73514.33 |  |  | 99026.05 | 52783 | 46243.05 | 2018-09-17 12:12 | 2020-05-28 | 2018-10-01 | 2020-05-28
75084 | FPIT | 323850001 | Fleet Asset Lifecycle & Mobile Solu | 13278.31 |  | 13278.31 |  |  | 29626.58 | 31846 | -2219.42 | 2018-02-19 16:06 | 2020-02-15 | 2018-03-01 | 2020-02-11
75084 | FPIT | IT1900019 | System Operations Checkout Automati | 18647.74 |  | 18647.74 |  |  | 18647.74 | 19356 | -708.26 | 2019-09-11 07:36 | 2020-07-31 | 2019-09-01 | 2020-07-23
75084 | FPIT | 338802003 | EAM Platform Optimization | 55494.88 |  | 55494.88 |  |  | 72154.78 | 147321.02 | -75166.24 | 2018-04-25 12:44 | 2020-05-30 | 2018-06-01 | 2020-03-31
75084 | FPIT | 346954001 | ISOP Granular Forecasting | 62055.44 |  | 62055.44 |  |  | 96202.99 | 139345 | -43142.01 | 2018-05-14 11:31 | 2024-09-30 | 2018-05-01
75084 | FPIT | 323326007 | Workstation Refresh 2017-2019 | 388.72 |  | 388.72 |  |  | 7848.31 | 8934 | -1085.69 | 2018-11-06 12:04 | 2019-03-31 | 2018-12-01 | 2019-03-31
75084 | FPIT | 338802005 | Maximo Durable Team | 141372.42 |  | 141372.42 |  |  | 153832.35 | 33459 | 120373.35 | 2018-09-13 14:56 | 2020-05-28 | 2018-10-01 | 2020-05-28
75084 | FPIT | 338802008 | EcoSys Durable Team Acciunting | 157.56 |  | 157.56 |  |  | 1564.8 | 52026 | -50461.2 | 2018-09-14 13:41 | 2019-05-29 | 2018-09-01 | 2019-05-31
75084 | FPIT | IT1900009 | Transmission Estimating Tool | 6659.46 |  | 6659.46 |  |  | 6659.46 | 75989 | -69329.54 | 2019-04-01 08:13 | 2020-01-30 | 2019-04-01 | 2020-01-04
75084 | FPIT | 338802006 | Smallworld/myWorld Durable Team | 343.59 |  | 343.59 |  |  | 343.59 | 48911 | -48567.41 | 2018-09-06 13:18 | 2020-05-28 | 2019-04-01 | 2020-11-10
75084 | SG000358F | SG358HW19 | SG DEE MDM Scale HWre Phase 4 - 358 | 6198.64 |  | 6198.64 |  |  | 57589.79 | 30270.21 | 27319.58 | 2018-05-09 10:54 | 2019-08-18 | 2018-05-01 | 2019-09-24
75084 | SG000358F | SG358SW2 | SG DEE MDM Scale Sftwre Phs 4 - 358 | 15678.13 |  | 15678.13 |  |  | 34149.17 | 10496.03 | 23653.14 | 2018-05-07 16:55 | 2019-08-18 | 2018-05-01 | 2019-09-24
75084 | SG000358F | SG358SVR | DEE MDM Scale | 1132.97 |  | 1132.97 |  |  | 1132.97 | 1504 | -371.03 | 2019-09-24 07:55 | 2020-01-31 | 2019-11-01 | 2020-03-31
75084 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 987.28 |  | 987.28 |  |  | 42263.06 | 44829.46 | -2566.4 | 2017-04-24 18:07 | 2018-12-31 | 2017-05-01 | 2019-03-31
75084 | SG000489F | SG489SW | SG DEE Openway AMI Scale - 489 | -52.71 |  | -52.71 |  |  | 29476.16 | 22987.85 | 6488.31 | 2016-11-23 11:18 | 2018-12-31 | 2016-11-01 | 2019-03-31
75084 | SG000489F | SG489SVR2 | DEE Openway Scale | 15365.7 |  | 15365.7 |  |  | 15365.7 | 22338 | -6972.3 | 2019-01-22 21:39 | 2020-03-31 | 2019-01-01 | 2019-09-30
75084 | SG000489F | SG489SVR3 | DEE Openway Scale | 10.33 |  | 10.33 |  |  | 10.33 | 1707 | -1696.67 | 2019-09-25 08:02 | 2020-10-31 | 2019-10-01 | 2020-10-26
75084 | SG000540F | SG540SW | DEE Vehicle Area Network | 0.03 |  | 0.03 |  |  | 0.03 | 109210 | -109209.97 | 2017-04-13 09:21 | 2020-12-17 | 2017-04-01 | 2018-07-16
75084 | SG000540F | SG540HW | DEE Vehicle Area Network | 89270.48 |  | 89270.48 |  |  | 105093.31 | 273196 | -168102.69 | 2018-04-12 17:01 | 2020-12-17 | 2018-09-01 | 2021-05-15
75084 | SG000540F | SG540SW3 | DEE Vehicle Area Network | 283466.72 |  | 283466.72 |  |  | 283466.72 | 23338 | 260128.72 | 2018-04-19 09:53 | 2020-12-17 | 2019-04-01 | 2021-05-15
75084 | SGKAMIF | SG169MTRS | SG KY AMI Electric Meters - 169 | -239812.29 |  | -239812.29 |  |  | 21321634.4 | 23298670 | -1977035.6 | 2017-06-07 11:18 | 2019-02-28 | 2017-06-01
75084 | SGKAMIF | SGKAMIMGT | TBC DEK AMI Mgmt Project | 214023.48 |  | 214023.48 |  |  | 1507876.72 | 603878 | 903998.72 | 2016-01-20 16:12 | 2023-02-01 | 2016-01-01
75084 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | 69772.29 |  | 69772.29 |  |  | 112302.23 | 110269.74 | 2032.49 | 2018-07-12 09:08 | 2021-03-31 | 2018-07-01 | 2021-03-31
75084 | FMDT2017 | MDTKE17 | Panasonic CF53 Units- Kentucky | 229245.01 |  | 229245.01 |  |  | 267576.44 | 87508.08 | 180068.36 | 2017-12-14 11:20 | 2020-06-01 | 2018-01-01 | 2020-05-01
75084 | SGITOMSGI | SGSWDOMC | SG AMI DOMS S/W Module Capital | 0.05 |  | 0.05 |  |  | 28994.34 | 37300 | -8305.66 | 2012-12-20 | 2015-08-29 | 2013-01-01 | 2017-01-15
75084 | DKY2133 | MX2167589 | Mt Zion Rbld Sam Neace - DKY2133 | -23716.35 |  | -23716.35 |  |  | 116570.08 | 80732.48 | 35837.6 | 2017-09-14 18:02 | 2019-06-01 | 2017-09-01 | 2019-04-29
75084 | DKY2133 | DKY213319 | Mt Zion 22.4MVA Bk 2 DS1 | 1485930.52 |  | 1485930.52 |  |  | 1634740.2 | 3017877 | -1383136.8 | 2018-01-29 18:02 | 2020-03-24 | 2018-04-01 | 2020-04-23
75084 | DKY2133 | MX2167975 | Mt Zion Rbld Weaver Rd - DKY2133 | 1825726.5 |  | 1825726.5 |  |  | 1959812.03 | 242159.7 | 1717652.33 | 2017-10-05 10:01 | 2021-07-29 | 2017-10-01 | 2021-01-28
75084 | DKY2133 | DKY213318 | TBC - Mt Zion 138kV Loop TS1 | -122233.8 |  | -122233.8 |  |  | 10093.87 | 0 | 10093.87 | 2018-01-29 18:02 | 2020-12-31 | 2018-04-01
75084 | DKY2133 | DKY213321 | Bank 1 low-side breaker | 192764.15 |  | 192764.15 |  |  | 205978.85 | 357627 | -151648.15 | 2018-10-24 18:03 | 2020-05-19 | 2018-11-01 | 2020-06-04
75084 | DKY2133 | DKY213320 | TBC - TL Pole Replacements | 6633.06 |  | 6633.06 |  |  | 6633.06 | 154917 | -148283.94 | 2019-03-05 14:01 | 2020-12-31 | 2019-03-01
75084 | DKY1959 | D1959DS1 | Cov Sub expansion DKY1959 | 27924.94 |  | 27924.94 |  |  | 317429.53 | 290451 | 26978.53 | 2017-05-16 17:18 | 2019-04-18 | 2017-07-01 | 2019-02-01
75084 | KYGLPRT | MX7343749 | 2166 P2 X-fer distribution underbui | 30218.55 |  | 30218.55 |  |  | 34995.33 | 18473.43 | 16521.9 | 2018-02-16 10:13 | 2019-06-01 | 2018-06-01 | 2019-04-04
75084 | KYGLPRT | KYGLPR15 | GLT P2 Cir 5983 HLP 2 Poles Dist UB | -9582.55 |  | -9582.55 |  |  | -5.1159e-13 | 20079 | -20079 | 2017-02-16 14:01 | 2020-12-31 | 2017-06-01
75084 | KYGLPRT | MX7360458 | Transfer distribution underbuild fo | 10145.55 |  | 10145.55 |  |  | 11247.91 | 10915.73 | 332.18 | 2018-02-26 14:50 | 2021-03-31 | 2018-12-01 | 2021-03-18
75084 | KYGLPRT | MX8766989 | Transfer distribution underbuild fo | 2970.81 |  | 2970.81 |  |  | 63526.62 | 63063.25 | 463.37 | 2018-07-17 14:02 | 2019-06-01 | 2018-08-01 | 2019-02-13
75084 | KYGLPRT | MX8520300 | Transfer distribution underbuild fo | 54036.11 |  | 54036.11 |  |  | 93035.05 | 42589.04 | 50446.01 | 2018-07-12 14:02 | 2019-06-01 | 2018-07-01 | 2019-04-08
75084 | KYGLPRT | MX0092935 | Transfer distribution underbuild fo | 15752.73 |  | 15752.73 |  |  | 15752.73 | 22024.98 | -6272.25 | 2018-10-09 14:02 | 2019-09-30 | 2019-01-01 | 2019-06-08
75084 | KYGLPRT | KYGLPRT06 | TBC - GLT P1 Cir6763 22 Pole Replac | 89.61 |  | 89.61 |  |  | 89.61 | 396000 | -395910.39 | 2018-04-30 14:05 | 2021-03-31 | 2019-11-01
75084 | KYGLPRT | KYGLPRT03 | GLT P1 Cir 966 Repl 5 poles | 4156.24 |  | 4156.24 |  |  | 4156.24 | 86199.78 | -82043.54 | 2018-04-16 10:01 | 2021-03-31 | 2019-07-01 | 2020-07-21
75084 | KYGLPRT | MX0763098 | TRANSMISSION UNDERBUILD | 8484.97 |  | 8484.97 |  |  | 8484.97 | 13207.09 | -4722.12 | 2018-12-05 10:14 | 2019-09-30 | 2019-01-01 | 2019-04-21
75084 | KYGLPRT | KYGLPRT07 | GLT P2 Cir 6763 6 pole Replacements | 186.82 |  | 186.82 |  |  | 186.82 | 108000 | -107813.18 | 2018-06-12 10:01 | 2021-03-31 | 2019-05-01
75084 | KYGLPRT | MX1325365 | F5983 X-fer UB for 6 - P2 wood to s | 9685.21 |  | 9685.21 |  |  | 9685.21 | 76917.35 | -67232.14 | 2019-04-23 18:01 | 2023-03-30 | 2019-07-01
75084 | DKY2208 | D2208RS1 | Turfway Sub Site Purch | 222634.9 |  | 222634.9 |  |  | 2573341.32 | 382562 | 2190779.32 | 2017-05-23 15:54 | 2019-03-02 | 2017-06-01 | 2019-02-20
75084 | DMAJRIFA | EMR248 | Dixie Repl RTU Processor | -135.91 |  | -135.91 |  |  | 5395.17 | 5283.72 | 111.45 | 2016-11-09 15:17 | 2018-03-31 | 2016-11-01 | 2017-03-31
75084 | RELDFA | MKRDYKY | Make Ready Kentucky | 556.86 |  | 556.86 |  |  | 402612.7 | 10 | 402602.7 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084 | ORDFA | OUTOHRLKY | Outage Replace OH - Kentucky | 4706.77 |  | 4706.77 |  |  | 378659.98 | 10 | 378649.98 | 2015-06-13 14:20 | 2025-12-31 | 2016-02-01
75084 | ORDFA | SKY1905DC | TO CAPTURE 2019 CAPITAL STORM #5 | 4809.63 |  | 4809.63 |  |  | 4809.63 | 0 | 4809.63 | 2019-05-07 20:57 | 2020-03-31 | 2019-06-01
75084 | ORDFA | SKY1910DC | TO CAPTURE 2019 CAPITAL STORM #10 | 788.69 |  | 788.69 |  |  | 788.69 | 0 | 788.69 | 2019-05-07 21:10 | 2020-03-31 | 2019-12-01
75084 | ORDFA | SKY1904DC | TO CAPTURE 2019 CAPITAL STORM # 4 | 7864.52 |  | 7864.52 |  |  | 7864.52 | 0 | 7864.52 | 2019-05-06 13:41 | 2020-03-31 | 2019-07-01
75084 | ORDFA | SKY1908DC | TO CAPTURE 2019 CAPITAL STORM #8 | 4355.54 |  | 4355.54 |  |  | 4355.54 | 0 | 4355.54 | 2019-05-07 21:05 | 2020-03-31 | 2019-08-01
75084 | ORDFA | SKY1909DC | TO CAPTURE 2019 CAPITAL STORM #9 | 10141.48 |  | 10141.48 |  |  | 10141.48 | 0 | 10141.48 | 2019-05-07 21:08 | 2020-03-31 | 2019-12-01
75084 | ORDFA | SKY1906DC | TO CAPTURE 2019 CAPITAL STORM #6 | 17771.06 |  | 17771.06 |  |  | 17771.06 | 0 | 17771.06 | 2019-05-07 21:01 | 2020-03-31 | 2019-07-01
75084 | ORDFA | SKY1907DC | TO CAPTURE 2019 CAPITAL STORM #7 | 18643.2 |  | 18643.2 |  |  | 18643.2 | 0 | 18643.2 | 2019-05-07 21:03 | 2020-03-31 | 2019-08-01
75084 | RELTFA | KYRELT1 | F6763 DOT Mt Zion Rd-Dixie Hwy | 1305995.73 |  | 1305995.73 |  |  | 1810938.88 | 35000 | 1775938.88 | 2015-07-25 18:59 | 2020-04-13 | 2015-09-01 | 2020-03-18
75084 | DECCIRFA | P7274 | TBC DEC 6892567 Donaldson 41 | 2512.63 |  | 2512.63 |  |  | 121946.46 | 205737.82 | -83791.36 | 2015-01-14 | 2020-12-31 | 2015-01-01
75084 | DECCIRFA | P7273 | DEC 6892574 Donaldson 41 | -31580.87 |  | -31580.87 |  |  | 133028.15 | 88334.91 | 44693.24 | 2015-01-14 | 2017-11-15 | 2015-01-01 | 2017-10-27
75084 | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | 17005.56 |  | 17005.56 |  |  | 763732.58 | 10 | 763722.58 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084 | NBFA | NBKYCI | Commerc & Indust Cust Adds-MW-D | 108895.26 |  | 108895.26 |  |  | 1445592.29 | 0 | 1445592.29 | 2016-01-21 13:58 | 2025-12-31 | 2016-02-01
75084 | NBFA | NBKYRES | Residential Customer Adds-MW-D | 27235.07 |  | 27235.07 |  |  | 2280954.58 | 0 | 2280954.58 | 2016-01-21 13:51 | 2025-12-31 | 2016-02-01
75084 | AMIKYCS | C9052 | AMI Buffington Advance Metering | -40866.61 |  | -40866.61 |  |  | 0 | 75000 | -75000 | 2016-06-29 16:36 | 2020-12-31 | 2016-06-01
75084 | AMIKYCS | C9051 | AMI Dixie Advanced Metering | -9707.01 |  | -9707.01 |  |  | -4.5475e-13 | 17000 | -17000 | 2016-06-29 16:33 | 2020-12-31 | 2016-06-01
75084 | AMIKYCS | C9049 | AMI Florence Advance Metering | -41159.31 |  | -41159.31 |  |  | 5.2864e-12 | 80000 | -80000 | 2016-06-29 16:25 | 2020-12-31 | 2016-06-01
75084 | AMIKYCS | C9050 | AMI Villa Advanced Metering | -40690.35 |  | -40690.35 |  |  | 1.1369e-12 | 50000 | -50000 | 2016-06-29 16:29 | 2020-12-31 | 2016-06-01
75084 | NCIPLOWK | KCIPLW999 | Electronic Keys | 79415.43 |  | 79415.43 |  |  | 398239.25 | 29929 | 368310.25 | 2017-11-17 14:50 | 2020-03-31 | 2017-11-01 | 2018-07-12
75084 | NCIPLOWK | KCIPLW076 | Covington - Ky NERC CIP Low | -2.76 |  | -2.76 |  |  | -3.638e-12 | 195323 | -195323 | 2017-02-09 13:59 | 2019-03-31 | 2017-02-01
75084 | TKY1687 | T1687DS4 | Richwood Comm Upgrade - TKY1687 | 4465.64 |  | 4465.64 |  |  | 196004.86 | 68854 | 127150.86 | 2017-02-10 18:06 | 2018-09-30 | 2017-05-01 | 2018-09-27
75084 | TKY1687 | T1687DS3 | Crittenden Comm Upgrade - TKY1687 | 46353.11 |  | 46353.11 |  |  | 194886.86 | 68854 | 126032.86 | 2017-02-10 18:06 | 2018-11-14 | 2017-05-01 | 2018-10-25
75084 | TKY1687 | T1687DS6 | White Tower Comm Upgrade - TKY1687 | 55762.2 |  | 55762.2 |  |  | 193709.73 | 68854 | 124855.73 | 2017-02-10 18:06 | 2018-11-14 | 2017-05-01 | 2018-10-11
75084 | DKY2149 | D2149DL2 | AM 20709176 Walton 2 Intercon | -2614.56 |  | -2614.56 |  |  | 45275.2 | 31950.28 | 13324.92 | 2017-02-14 09:34 | 2018-07-31 | 2017-10-01 | 2018-03-11
75084 | SG000430F | SG430B | Aero Pkwy Instl UG Cable | -131314.99 |  | -131314.99 |  |  | 1364547.46 | 1003250.66 | 361296.8 | 2016-04-04 13:41 | 2018-03-31 | 2016-04-01 | 2018-03-31
75084 | SG000430F | SG430A | Aero Pkwy Instl UG Conduit | 10651.13 |  | 10651.13 |  |  | 1984459.55 | 1185872.83 | 798586.72 | 2016-04-04 13:28 | 2018-03-31 | 2016-04-01 | 2017-06-21
75084 | DKY1930 | D1930DL2 | AM Erlanger Rd | 3614.03 |  | 3614.03 |  |  | 176238.01 | 75463.43 | 100774.58 | 2017-04-13 11:13 | 2018-06-15 | 2017-06-01 | 2018-04-05
75084 | DKY1930 | D1930DL1 | AM 11851684 Recd Donaldson 42 Riggs | 5358.79 |  | 5358.79 |  |  | 958314.67 | 261996.83 | 696317.84 | 2016-12-19 09:23 | 2018-08-30 | 2017-01-01 | 2018-08-30
75084 | KFSF45122 | KFS845122 | RFS 11845122 Beaver 42. I | 531.59 |  | 531.59 |  |  | 72526.7 | 62681.66 | 9845.04 | 2017-06-08 10:03 | 2018-07-30 | 2018-05-01 | 2018-11-06
75084 | RLFA | KGENSWG | Kentucky Switchgear Repl Program | 12223.49 |  | 12223.49 |  |  | 18103.12 | 100 | 18003.12 | 2016-03-28 10:49 | 2030-12-31 | 2018-05-01
75084 | SGPMYUF | SGYFA2SW | DEE YFA Ver 2 DER - Software | 0.06 |  | 0.06 |  |  | 24961.71 | 36217 | -11255.29 | 2016-01-08 10:09 | 2017-05-24 | 2016-01-01 | 2017-03-07
75084 | SG000829F | SG829PT01 | Wireless & Optical Test Equipment | -297.39 |  | -297.39 |  |  | 23010.76 | 25644.65 | -2633.89 | 2018-05-23 15:02 | 2019-03-30 | 2018-06-01 | 2018-11-21
75084 | GLPRTFA | KYGLPR7 | GLT P2 Cir 5967 4 Poles | 470.78 |  | 470.78 |  |  | 104442.25 | 108000 | -3557.75 | 2016-09-01 09:04 | 2017-01-30 | 2016-09-01 | 2017-01-17
75084 | CP17BATK | MX6589455 | Donaldson Repl 125VDC Station Batt | -84.74 |  | -84.74 |  |  | 12959.26 | 7271.16 | 5688.1 | 2017-12-07 18:02 | 2019-03-31 | 2018-01-01 | 2019-02-15
75084 | DKY2205 | D2205DL1 | AM 20888790 Oakbrook 41-42 Rconf | 1009.27 |  | 1009.27 |  |  | 49823.95 | 36809.95 | 13014 | 2017-03-09 14:25 | 2018-07-31 | 2017-09-01 | 2018-06-02
75084 | CAPFA | CAPAUTOKY | Capacitor Automation - Kentucky | 26.24 |  | 26.24 |  |  | 2610.33 | 49 | 2561.33 | 2014-01-15 | 2020-12-31 | 2014-03-01
75084 | SGAMF | SG344SW | SG DEE Distrib System Health - SW | 22818.93 |  | 22818.93 |  |  | 85185.01 | 73774 | 11411.01 | 2015-12-18 14:25 | 2020-03-31 | 2016-01-01 | 2019-12-31
75084 | FTDITKE | TDITKE | PD KENTUCKY IT HARDWARE | 512.76 |  | 512.76 |  |  | 2830.63 | 1 | 2829.63 | 2010-07-01 | 2025-12-25 | 2016-05-01
75084 | SGDMSCF | SG361SW | SG DEE DMS Project 10 SW | 156221.14 |  | 156221.14 |  |  | 158404.05 | 266133.19 | -107729.14 | 2015-12-18 15:11 | 2022-05-28 | 2016-01-01 | 2022-03-31
75084 | SG000336F | SG336SW | SG DEE DMS ADMS - Software | 266554.07 |  | 266554.07 |  |  | 647480.23 | 1049863.37 | -402383.14 | 2016-09-06 17:51 | 2024-05-28 | 2016-09-01
75084 | SG000336F | SG336OUA | SG Oracle Utilities Analytics Softw | 99694.71 |  | 99694.71 |  |  | 117366.1 | 155000 | -37633.9 | 2018-07-30 10:48 | 2021-05-28 | 2018-08-01 | 2021-07-01
75084 | SG000336F | SG336SVR2 | SG Oracle Utilities Analytics Hardw | 25392.8 |  | 25392.8 |  |  | 25392.8 | 20696 | 4696.8 | 2018-08-14 17:44 | 2020-06-30 | 2019-06-01 | 2020-06-30
75084 | SG000436F | SGOTVKY | DEK Cap Cutout Repl-Oil-to-Vac | 6309.84 |  | 6309.84 |  |  | 6341.79 | 83 | 6258.79 | 2016-05-16 10:18 | 2025-12-31 | 2017-01-01
75084 | SG000601F | SG601SW | DEE ADP Software - 601 | 62000.18 |  | 62000.18 |  |  | 81002.24 | 42090 | 38912.24 | 2017-06-21 17:55 | 2025-03-31 | 2017-06-01
75084 | SGEAMIOCF | SG305SVRS | SG DEE OpenWay Ops Center Servers | -24831.01 |  | -24831.01 |  |  | 0.09 | 5323.07 | -5322.98 | 2016-09-06 11:56 | 2020-12-31 | 2016-09-01
75084 | SGEAMIOCF | SG305SW | SG DEE OpenWay Ops Center Software | -141142.99 |  | -141142.99 |  |  | -0.14 | 189544.12 | -189544.26 | 2016-08-01 10:09 | 2020-12-31 | 2016-08-01
75084 | DKY2199 | D2199DL3 | AM 21607381 Hebron | 432404.7 |  | 432404.7 |  |  | 442383.91 | 250919.99 | 191463.92 | 2017-06-27 13:39 | 2020-07-30 | 2017-11-01 | 2020-07-21
75084 | DKY2199 | D2199DL2 | AM 21607299 Hebron - DKY2199 | 1762271.12 |  | 1762271.12 |  |  | 1965958.78 | 238000.64 | 1727958.14 | 2017-06-27 13:32 | 2020-07-30 | 2017-07-01 | 2020-07-29
75084 | DKY2199 | D2199DL4 | AM 21607440 Hebron | 63922.01 |  | 63922.01 |  |  | 64686.64 | 41400.28 | 23286.36 | 2017-06-27 13:44 | 2020-07-30 | 2018-03-01 | 2020-07-31
75084 | DKY2199 | D2199DL1 | AM 21606995 Hebron | 168153.17 |  | 168153.17 |  |  | 206059.67 | 65607.29 | 140452.38 | 2017-06-27 13:20 | 2019-11-01 | 2017-12-01 | 2019-09-28
75084 | DKY2016 | D2016DS1 | Donaldson TB 3 - DKY2016 | 4877816.1 |  | 4877816.1 |  |  | 5562476.83 | 4019811 | 1542665.83 | 2017-07-18 07:20 | 2020-02-28 | 2017-08-01 | 2020-03-12
75084 | DKY2016 | D2016DS2 | Donaldson TB 4 - DKY2016 | 3012372.05 |  | 3012372.05 |  |  | 3505399.92 | 3960624 | -455224.08 | 2017-07-18 07:32 | 2020-02-16 | 2017-08-01 | 2020-03-12
75084 | DKY2016 | MX2175246 | Donaldson 48 Ln Ext - DKY2016 | 175476.77 |  | 175476.77 |  |  | 740288.64 | 162040.89 | 578247.75 | 2017-10-12 12:00 | 2020-06-25 | 2017-10-01 | 2020-04-23
75084 | DKY2016 | MX9917129 | Donaldson 48 UG Exits Conduit - DKY | 44560.62 |  | 44560.62 |  |  | 199621.74 | 39264.85 | 160356.89 | 2018-09-25 14:02 | 2019-12-26 | 2018-11-01 | 2019-02-28
75084 | DKY2016 | MX0265492 | TBC De-energize Segment Circuit 41 | 28.23 |  | 28.23 |  |  | 1240.5 | 0 | 1240.5 | 2018-11-09 14:02 | 2020-12-31 | 2018-12-01
75084 | DKY2016 | MX2175719 | Donaldson 46 Ln Ext - DKY2016 | 23259.88 |  | 23259.88 |  |  | 106743.13 | 147197.24 | -40454.11 | 2017-10-12 14:01 | 2019-06-01 | 2018-07-01 | 2018-12-24
75084 | DKY2016 | MX9916539 | Donaldson 46 UG Exits Conduit - DKY | 23168.08 |  | 23168.08 |  |  | 23528.51 | 5502.55 | 18025.96 | 2018-09-25 14:02 | 2019-09-01 | 2018-10-01 | 2019-05-29
75084 | DKY2016 | MX9916982 | Donaldson 46 UG Exits Conductor - D | 80754.28 |  | 80754.28 |  |  | 80754.28 | 38743.91 | 42010.37 | 2018-09-25 14:02 | 2019-11-28 | 2019-06-01 | 2019-11-25
75084 | DKY2016 | MX2800033 | Donaldson 42 Exit - DKY2016 | 7529.91 |  | 7529.91 |  |  | 7529.91 | 9341.62 | -1811.71 | 2019-05-29 14:02 | 2020-10-29 | 2019-10-01 | 2020-09-01
75084 | DKY2016 | MX2969660 | TBC Donaldson Bus Tie - DKY2016 | 13619.39 |  | 13619.39 |  |  | 13619.39 | 26506.01 | -12886.62 | 2019-06-13 10:01 | 2021-03-01 | 2019-08-01
75084 | DKY2016 | MX9917170 | Donaldson 48 UG Exits Conductor - D | 77648.85 |  | 77648.85 |  |  | 77648.85 | 33869.48 | 43779.37 | 2018-09-25 14:02 | 2019-11-28 | 2019-06-01 | 2019-11-25
75084 | 75084IK | KOUTUG | Outage Related UG Cap Replacements | 513368.45 |  | 513368.45 |  |  | 1874099.6 | 93 | 1874006.6 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCOH | Non-Emergency OH Corrective Replace | 29842.08 |  | 29842.08 |  |  | -145678.82 | 93 | -145771.82 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEOH | Emergency OH Corrective Replacement | 263177.7 |  | 263177.7 |  |  | 454387.69 | 93 | 454294.69 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KPOLIR | Non Emerg Pole Replace Insp Based | 28822.13 |  | 28822.13 |  |  | 384330.86 | 93 | 384237.86 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPDMCPU | Public Damage UG Capital Replacemnt | 107220.03 |  | 107220.03 |  |  | 53983.35 | 93 | 53890.35 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRIOTCO | OH Imprvmnt From PQRI Outage Invest | 201068.07 |  | 201068.07 |  |  | 352052.09 | 93 | 351959.09 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLCM | Reactive Pole Replacements | 459529.59 |  | 459529.59 |  |  | 867362.82 | 93 | 867269.82 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KPPL | Stub Pole Removal Only | 6781.79 |  | 6781.79 |  |  | 19752.75 | 2 | 19750.75 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KLPF | Line Patrol Follow Up | 324555.35 |  | 324555.35 |  |  | 1204787.3 | 93 | 1204694.3 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTR1PH | Single PH Transformer Replace Dry | 26505.64 |  | 26505.64 |  |  | 46469.85 | 93 | 46376.85 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRUCSM | UG Primary Small Cable Replacement | 190770.79 |  | 190770.79 |  |  | 315925.13 | 93 | 315832.13 | 2017-03-27 14:22 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCUG | Non-Emergency UG Corrective Repl | 38494.85 |  | 38494.85 |  |  | 74281.46 | 93 | 74188.46 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KSMF | Capital Replacements from SMEI Insp | 2926.62 |  | 2926.62 |  |  | 8460.96 | 93 | 8367.96 | 2017-03-27 14:35 | 2067-12-31 | 2018-03-01
75084 | 75084IK | KCBLDT | UG Cable Replacement Dwntn Network | 66740.56 |  | 66740.56 |  |  | 80878.69 | 93 | 80785.69 | 2017-03-24 15:38 | 2067-12-31 | 2018-10-01
75084 | 75084IK | KRRR | Recloser Replacements | 664417.24 |  | 664417.24 |  |  | 1129246.29 | 96 | 1129150.29 | 2017-03-27 13:10 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRIOTCU | UG Imprvmnt From PQRI Outage Invest | 27415.02 |  | 27415.02 |  |  | 51390.68 | 93 | 51297.68 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCIPOH | C&I Customer Additions OH | 1197905.17 |  | 1197905.17 |  |  | 3287226.63 | 93 | 3287133.63 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRXR | Transformer Retrofit | 135948.86 |  | 135948.86 |  |  | 361085.37 | 84 | 361001.37 | 2017-03-27 14:28 | 2067-12-31 | 2018-01-01
75084 | 75084IK | KCMCEUG | Emergency UG Corrective Replacement | 93308.17 |  | 93308.17 |  |  | 222586.66 | 93 | 222493.66 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRFS | Circuit Sectionalization | 63822.6 |  | 63822.6 |  |  | 197848.18 | 95 | 197753.18 | 2017-03-27 12:39 | 2067-12-31 | 2018-02-01
75084 | 75084IK | MX8683892 | Declared Circuit - Donaldson (55) 5 | 16072.55 |  | 16072.55 |  |  | 19950.21 | 49876.34 | -29926.13 | 2018-09-27 14:02 | 2022-02-28 | 2018-12-01 | 2021-10-26
75084 | 75084IK | KDLS | Dline Switch Replacements | 74559.53 |  | 74559.53 |  |  | 137871.69 | 70 | 137801.69 | 2017-03-27 11:53 | 2067-12-31 | 2018-02-01
75084 | 75084IK | MX0920154 | MXCONV-Declared Circuits Kenton 46 | 309410.46 |  | 309410.46 |  |  | 613454.57 | 118477.7 | 494976.87 | 2018-03-14 18:02 | 2020-07-09 | 2018-06-01 | 2019-12-30
75084 | 75084IK | KRSOH | Residential Cust Adds Single Fam OH | 885953.12 |  | 885953.12 |  |  | 2553830 | 93 | 2553737 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KSTMOH | OH Capital Replacement Due to Storm | 40220.77 |  | 40220.77 |  |  | 123520.64 | 93 | 123427.64 | 2017-03-27 14:40 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KRTP1PH | Single PH Transformer Replac Leaker | 5809.18 |  | 5809.18 |  |  | 8141.58 | 93 | 8048.58 | 2017-03-27 13:17 | 2067-12-31 | 2018-07-01
75084 | 75084IK | KPDMCAP | Public Damage OH Capital Replacemen | 268159.45 |  | 268159.45 |  |  | 427298.16 | 80 | 427218.16 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KOTV | Cap Oil to Vac Changeout | 16504.25 |  | 16504.25 |  |  | 43136.03 | 93 | 43043.03 | 2017-03-27 12:10 | 2067-12-31 | 2018-02-01
75084 | 75084IK | KOUTOH | Outage Related OH Cap Replacements | 476860.61 |  | 476860.61 |  |  | 1205147.44 | 93 | 1205054.44 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01
75084 | 75084IK | MX0675382 | Westpack Customer Station | 404.6 |  | 404.6 |  |  | 1423.69 | 10800.23 | -9376.54 | 2017-12-15 14:01 | 2023-06-29 | 2018-03-01
75084 | 75084IK | KRUCSEC | UG Sec/Service Cable Replacement | 95556.78 |  | 95556.78 |  |  | 102215.21 | 93 | 102122.21 | 2017-03-27 13:33 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRUPOH | Residential Customer Upgrade OH | 266289.01 |  | 266289.01 |  |  | 608281.99 | 93 | 608188.99 | 2017-03-27 14:26 | 2067-12-31 | 2017-11-01
75084 | 75084IK | KCIUPOH | C&I Customer Upgrade OH | 55270.62 |  | 55270.62 |  |  | 51931.24 | 93 | 51838.24 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01
75084 | 75084IK | MX1848383 | TBC MXCONV-Capacitor Automation MT. | 7332.16 |  | 7332.16 |  |  | 49514.55 | 57824.65 | -8310.1 | 2018-03-12 14:01 | 2022-09-01 | 2018-08-01
75084 | 75084IK | MX9127121 | JT-E- TRAEMORE PH A | 61269.9 |  | 61269.9 |  |  | 54980.15 | 88590.34 | -33610.19 | 2018-07-17 14:02 | 2019-10-11 | 2018-09-01 | 2019-07-31
75084 | 75084IK | KRTXO | Overhead Transformer Replacement | 24372.58 |  | 24372.58 |  |  | 41869.31 | 93 | 41776.31 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEDT | Emerg DTUG Corrective Replacements | 43669.37 |  | 43669.37 |  |  | 70709.7 | 93 | 70616.7 | 2017-03-24 15:47 | 2067-12-31 | 2018-06-01
75084 | 75084IK | KCMCDT | Non-Emerg DTUG Corrective Replace | 793.46 |  | 793.46 |  |  | 1164.82 | 93 | 1071.82 | 2017-03-24 15:45 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRTP3PH | Three PH Transformer Replace Leaker | 66402.32 |  | 66402.32 |  |  | 109215.53 | 95 | 109120.53 | 2017-03-27 13:19 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRTXLF | Transformer Livefront Replace | 78094.93 |  | 78094.93 |  |  | 147315.12 | 72691.76 | 74623.36 | 2017-07-27 15:37 | 2067-12-31 | 2018-10-01
75084 | 75084IK | KRTR3PH | Three PH Transformer Replace Dry | 13658.34 |  | 13658.34 |  |  | 29606.94 | 95 | 29511.94 | 2017-03-27 13:26 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRCR | Capacitor Replacements & Assoc UOP | 286897.81 |  | 286897.81 |  |  | 308581.17 | 90 | 308491.17 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOWS | Secondary OH Wire Corr Replacement | 3600.14 |  | 3600.14 |  |  | 5741.2 | 93 | 5648.2 | 2017-03-27 11:47 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KCMCOWP | Primary OH Wire Corr Replacement | 8135.75 |  | 8135.75 |  |  | 8596.36 | 93 | 8503.36 | 2017-03-27 11:33 | 2067-12-31 | 2018-11-01
75084 | 75084IK | MX9998915 | URD Wilder 41 | 456.91 |  | 456.91 |  |  | 16397.44 | 0 | 16397.44 | 2018-04-27 10:01 | 2023-07-29 | 2018-05-01
75084 | 75084IK | MX9998916 | Transformer Replacement Kenton 41 | 5.39 |  | 5.39 |  |  | 236.08 | 0 | 236.08 | 2018-03-26 10:02 | 2023-10-29 | 2018-05-01
75084 | 75084IK | KRGR | Regulator replacements | 22221.59 |  | 22221.59 |  |  | 42146.83 | 0 | 42146.83 | 2017-07-27 13:27 | 2067-12-31 | 2017-11-01
75084 | 75084IK | MX9214707 | SOG Circuit Segmentation Batavia 4 | -84.02 |  | -84.02 |  |  | -2.8422e-14 | 0 | -2.8422e-14 | 2018-12-13 14:01 | 2020-03-31 | 2018-12-01
75084 | 75084IK | KSVDTUG | Instl/Repl Pump W Stop Valve in Vau | -30839.04 |  | -30839.04 |  |  | 0 | 0 | 0 | 2017-12-07 11:41 | 2068-03-31 | 2018-08-01
75084 | 75084IK | KROC | OH Deteriorated Conductor Replace | 21661.95 |  | 21661.95 |  |  | 22430.02 | 0 | 22430.02 | 2018-07-11 10:07 | 2067-12-31 | 2018-11-01
75084 | 75084IK | KET135853 | DET 10135853 Hands 44 310 | 734839.29 |  | 734839.29 |  |  | 1459936.75 | 656630.49 | 803306.26 | 2016-11-07 10:03 | 2020-09-28 | 2016-12-01 | 2019-11-03
75084 | 75084IK | MX2140942 | UG LINE EXT - 1730 LAKELAND PARK DR | 60575.37 |  | 60575.37 |  |  | 76167.38 | 56759.24 | 19408.14 | 2017-12-13 10:01 | 2018-01-05 | 2018-01-01 | 2018-05-08
75084 | 75084IK | MX8285098 | INFRASTRUCTIURE FOR SUBDIVISION D | 2178.48 |  | 2178.48 |  |  | 15489.93 | 14166.09 | 1323.84 | 2018-05-09 18:05 | 2019-06-01 | 2018-05-01 | 2019-01-20
75084 | 75084IK | MX1281917 | INFRASTRUCTIURE FOR SUBDIVISION D | 911.24 |  | 911.24 |  |  | 9209.92 | 8191.98 | 1017.94 | 2017-11-03 14:01 | 2019-01-31 | 2018-04-01 | 2018-12-19
75084 | 75084IK | MX0090259 | MXCONV-Transformer Retrofit YORK 42 | 1652.24 |  | 1652.24 |  |  | 32610.26 | 42782.63 | -10172.37 | 2018-04-18 14:01 | 2018-12-28 | 2018-06-01 | 2018-11-09
75084 | 75084IK | MX7691568 | Circuit Segementation Self Healing | 55601.21 |  | 55601.21 |  |  | 63486.56 | 48280.72 | 15205.84 | 2018-05-25 14:02 | 2019-07-01 | 2018-06-01 | 2019-08-13
75084 | 75084IK | MX9579446 | JT- E - Arcadia Highlands Phase 4 | 11784.57 |  | 11784.57 |  |  | 10850.57 | 12695.07 | -1844.5 | 2018-08-24 18:04 | 2019-08-30 | 2018-09-01 | 2019-07-14
75084 | 75084IK | MX7740641 | JT, E-AOSTA VALLEY PH. 6 | 883.83 |  | 883.83 |  |  | 14035.52 | 19174.35 | -5138.83 | 2018-04-11 18:02 | 2019-06-01 | 2018-04-01 | 2018-12-27
75084 | 75084IK | MX7691570 | Circuit Segmentation Self Healing B | 5283.85 |  | 5283.85 |  |  | 38966.87 | 44183.81 | -5216.94 | 2018-06-26 18:03 | 2019-07-30 | 2018-07-01 | 2019-05-29
75084 | 75084IK | MX0090254 | MXCONV-Transformer Retrofit LIMABUR | 1525.22 |  | 1525.22 |  |  | 26343.81 | 52534.55 | -26190.74 | 2018-04-17 14:01 | 2019-06-01 | 2018-06-01 | 2018-11-22
75084 | 75084IK | MX7691569 | Circuit Segementation Self Healing | 56212.3 |  | 56212.3 |  |  | 85715.61 | 39899.12 | 45816.49 | 2018-06-25 10:02 | 2019-12-29 | 2018-07-01 | 2019-10-31
75084 | 75084IK | MX7691571 | Circuit Segmentation Self Healing B | 19593.59 |  | 19593.59 |  |  | 50791.67 | 58415 | -7623.33 | 2018-06-27 10:02 | 2019-07-30 | 2018-07-01 | 2019-06-11
75084 | 75084IK | MX7743111 | INFRASTRUCTIURE FOR SUBDIVISION D | 1884.34 |  | 1884.34 |  |  | 17843.74 | 26179.83 | -8336.09 | 2018-03-26 14:02 | 2018-11-24 | 2018-05-01 | 2018-11-26
75084 | 75084IK | MX7691573 | Circuit Segmentation Self Healing W | 20518.51 |  | 20518.51 |  |  | 50840.2 | 48785.98 | 2054.22 | 2018-06-19 10:01 | 2019-07-30 | 2018-07-01 | 2019-08-18
75084 | 75084IK | MX7691572 | Circuit Segmentation Self Healing B | 2067.62 |  | 2067.62 |  |  | 37391.19 | 43667.13 | -6275.94 | 2018-06-29 14:03 | 2019-08-14 | 2018-07-01 | 2019-05-12
75084 | 75084IK | MX8683121 | Declared Circuit - Limaburg (189) 1 | 19739.67 |  | 19739.67 |  |  | 23448.67 | 8916.15 | 14532.52 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-05-27
75084 | 75084IK | MX7880714 | JT, E-WALTON POINTE PHASE 3 | 31036.61 |  | 31036.61 |  |  | 28843.61 | 24220.88 | 4622.73 | 2018-04-11 14:01 | 2019-07-31 | 2018-06-01 | 2019-07-21
75084 | 75084IK | MX7972270 | MAJOR IMPROVE DIST RELIABLITY LINE | 43239.1 |  | 43239.1 |  |  | 139355.48 | 87518.4 | 51837.08 | 2018-07-24 14:02 | 2019-09-02 | 2018-08-01 | 2019-05-10
75084 | 75084IK | MX7997177 | JT, E-TUSCANY PHASE B SECTION 1 | 51432.66 |  | 51432.66 |  |  | 33906.66 | 78395.14 | -44488.48 | 2018-04-12 10:01 | 2019-07-30 | 2018-06-01 | 2019-06-02
75084 | 75084IK | MX8684198 | Declared Circuit - Hebron (152) 152 | 35013.48 |  | 35013.48 |  |  | 38073.35 | 14209.12 | 23864.23 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-09-17
75084 | 75084IK | MX6843545 | INFRASTRUCTIURE FOR SUBDIVISION D | 15825.53 |  | 15825.53 |  |  | 32306.13 | 17816 | 14490.13 | 2018-01-04 14:01 | 2019-06-22 | 2018-03-01 | 2019-03-19
75084 | 75084IK | MX7838790 | JT, E-ASHLEY OAKS SUBDIVISION | 13427.87 |  | 13427.87 |  |  | 12362.62 | 9052.39 | 3310.23 | 2018-04-11 14:01 | 2019-11-29 | 2018-06-01 | 2019-06-30
75084 | 75084IK | MX1948881 | SAWGRASS SUBDIVISION PHASE A | 34.39 |  | 34.39 |  |  | 36960.85 | 36830.14 | 130.71 | 2017-11-03 14:01 | 2019-03-31 | 2018-01-01 | 2018-09-24
75084 | 75084IK | MX8735624 | JT-E- HARMONY PH.D PT.1 | 20894.26 |  | 20894.26 |  |  | 18798.01 | 22271.65 | -3473.64 | 2018-08-03 10:02 | 2019-04-18 | 2018-08-01 | 2019-06-10
75084 | 75084IK | MX8684114 | TBC - Declared Circuit - Hebron (15 | 19707.7 |  | 19707.7 |  |  | 22343.36 | 3958.41 | 18384.95 | 2018-09-27 14:02 | 2020-12-31 | 2018-12-01
75084 | 75084IK | MX2163149 | TED BUSHELMAN BLVD | 164873.29 |  | 164873.29 |  |  | 258945.24 | 96365.48 | 162579.76 | 2017-12-13 10:01 | 2018-01-19 | 2018-02-01 | 2018-05-21
75084 | 75084IK | MX0090256 | MXCONV-Transformer Retrofit SILVER | 259.89 |  | 259.89 |  |  | 49283.37 | 120339.21 | -71055.84 | 2018-09-17 10:02 | 2019-06-01 | 2018-09-01 | 2019-01-25
75084 | 75084IK | MX7708497 | JT, E-RESERVE AT MEADOWOOD | 13511.23 |  | 13511.23 |  |  | 33988.95 | 50046.7 | -16057.75 | 2018-03-20 18:02 | 2019-06-28 | 2018-05-01 | 2019-05-28
75084 | 75084IK | MX6839574 | COMMERCIAL PRIMARY/SECONDARY/SVC | -1286.64 |  | -1286.64 |  |  | 199297.45 | 168944.61 | 30352.84 | 2018-10-24 18:03 | 2019-07-01 | 2018-11-01 | 2019-02-28
75084 | 75084IK | MX0004925 | INFRASTRUCTIURE FOR SUBDIVISION D | 29004.54 |  | 29004.54 |  |  | 24790.54 | 32901.06 | -8110.52 | 2018-10-24 18:03 | 2019-11-29 | 2018-11-01 | 2019-07-29
75084 | 75084IK | MX8215200 | JT, E-AUDUBON FOREST SUBDIVISION | 33150.26 |  | 33150.26 |  |  | 29393.26 | 24640.12 | 4753.14 | 2018-05-01 14:01 | 2019-12-01 | 2018-12-01 | 2019-07-30
75084 | 75084IK | MX9481816 | INFRASTRUCTIURE FOR SUBDIVISION D | 20639.57 |  | 20639.57 |  |  | 19177.57 | 12428.57 | 6749 | 2018-09-26 10:02 | 2019-08-31 | 2018-09-01 | 2019-06-24
75084 | 75084IK | MX8684039 | Declared Circuit - Oakbrook (210) 2 | 21280.95 |  | 21280.95 |  |  | 25417.96 | 11313.35 | 14104.61 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-07-23
75084 | 75084IK | MX8452464 | TBC - D-LINE PORTION:SOGOakbrookDon | 1032.58 |  | 1032.58 |  |  | 1032.58 | 32098.48 | -31065.9 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452468 | TBC D-LINE PORTION:SOGOakbrookDona | 1021.47 |  | 1021.47 |  |  | 1021.47 | 33590.87 | -32569.4 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX1845281 | TBC - DLINE PORTION: SEGMENT OF CIR | 8263.47 |  | 8263.47 |  |  | 8263.47 | 32769.79 | -24506.32 | 2019-03-08 18:01 | 2020-12-31 | 2019-05-01
75084 | 75084IK | MX8452467 | TBC - D-LINE PORTION:SOGOakbrookDon | 1997.65 |  | 1997.65 |  |  | 1997.65 | 33965.74 | -31968.09 | 2019-01-16 14:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452447 | D-LINE PORTION:SOG Dixie Mt Zion 31 | 567.12 |  | 567.12 |  |  | 567.12 | 34181.52 | -33614.4 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8755128 | Det. Conductor - Constance (41) 424 | 1841896.16 |  | 1841896.16 |  |  | 1841896.16 | 712968.4 | 1128927.76 | 2018-12-17 10:02 | 2020-09-28 | 2019-01-01 | 2020-08-10
75084 | 75084IK | MX1249090 | JT-E-ALEXANDER CIRCLE | 25990.28 |  | 25990.28 |  |  | 25990.28 | 31214.31 | -5224.03 | 2019-01-21 18:02 | 2020-02-24 | 2019-04-01 | 2020-02-09
75084 | 75084IK | MX1816336 | INFRASTRUCTIURE FOR SUBDIVISION D | 184534.62 |  | 184534.62 |  |  | 184534.62 | 226516.58 | -41981.96 | 2019-04-08 18:01 | 2020-01-21 | 2019-05-01 | 2019-12-11
75084 | 75084IK | MX6746469 | ELEC - C/I; - 501 MAIN, COVINGTON - | 144825.04 |  | 144825.04 |  |  | 144825.04 | 118838.8 | 25986.24 | 2018-10-15 18:03 | 2019-09-30 | 2019-01-01 | 2019-07-17
75084 | 75084IK | MX2906469 | JT-E-ALDERBROOK PH 3 PART A | -1409.28 |  | -1409.28 |  |  | -1409.28 | 59798.22 | -61207.5 | 2019-07-31 18:03 | 2020-06-30 | 2019-08-01 | 2020-05-27
75084 | 75084IK | MX1234300 | JT-E-ARCADIA POD A - PHASE 1 | 20071.96 |  | 20071.96 |  |  | 20071.96 | 17217.55 | 2854.41 | 2019-01-16 18:01 | 2019-10-23 | 2019-06-01 | 2019-09-19
75084 | 75084IK | MX4306278 | JT-E-Aosta Valley - Ph 7 - Part 1 | -3653 |  | -3653 |  |  | -3653 | 31136.62 | -34789.62 | 2019-10-21 14:01 | 2020-09-15 | 2019-12-01 | 2020-08-05
75084 | 75084IK | MX0494866 | MXCONV-Transformer Retrofit KENTON | 591.53 |  | 591.53 |  |  | 591.53 | 96102.31 | -95510.78 | 2019-11-18 18:01 | 2021-03-25 | 2019-11-01 | 2021-02-23
75084 | 75084IK | MX2263766 | DEN,RESIDENTIAL PRIMARY/SECONDARY/S | 26805.01 |  | 26805.01 |  |  | 26805.01 | 42978.64 | -16173.63 | 2019-04-30 14:01 | 2020-06-18 | 2019-10-01 | 2020-06-09
75084 | 75084IK | MX8452449 | TBC - D-LINE PORTION: SEGMENTATION | 3044.68 |  | 3044.68 |  |  | 3044.68 | 35683.15 | -32638.47 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452457 | TBC - D-LINE PORTION:SOGHandsWhiteT | 1322.84 |  | 1322.84 |  |  | 1322.84 | 37813.26 | -36490.42 | 2019-01-21 14:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2906128 | JT-E-WESTBROOK ESTATES PH 3 | -1865 |  | -1865 |  |  | -1865 | 9038.61 | -10903.61 | 2019-08-08 14:01 | 2021-07-04 | 2019-08-01 | 2021-06-16
75084 | 75084IK | MX9317640 | JT-E- TUSCANY - PHASE C SECTION 12 | 99632.32 |  | 99632.32 |  |  | 99632.32 | 130235.55 | -30603.23 | 2018-08-01 14:04 | 2019-12-17 | 2019-01-01 | 2019-09-15
75084 | 75084IK | MX6405659 | JT, E-EVERGREEN APARTMENTS | 33091.43 |  | 33091.43 |  |  | 33091.43 | 16371.21 | 16720.22 | 2018-01-09 10:01 | 2019-11-28 | 2019-05-01 | 2019-09-09
75084 | 75084IK | MX8452469 | TBC - D-LINE PORTION:SOGOakbrookDon | 1379.03 |  | 1379.03 |  |  | 1379.03 | 35375.69 | -33996.66 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452443 | TBC D-LINE PORTION: SEGMENTATION OF | 108.85 |  | 108.85 |  |  | 108.85 | 0 | 108.85 | 2018-12-10 18:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2210676 | JT-E-TUSCANY PH C - SEC 15/16 | 41297.68 |  | 41297.68 |  |  | 41297.68 | 40594.49 | 703.19 | 2019-04-23 14:01 | 2020-01-13 | 2019-08-01 | 2019-12-10
75084 | 75084IK | KRTXLFCM | CD - Upgd Live Front Trsfr Reactive | 47872.99 |  | 47872.99 |  |  | 47872.99 | 97 | 47775.99 | 2019-03-21 16:21 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX0044401 | KEG - 494 JONES ROAD - COMMERCIAL P | -2698.43 |  | -2698.43 |  |  | -2698.43 | 109599.01 | -112297.44 | 2019-06-28 14:08 | 2020-02-20 | 2019-07-01 | 2020-02-23
75084 | 75084IK | MX0266351 | ST ELIZABETH HOSPITAL, MEDICAL VILL | 53399.23 |  | 53399.23 |  |  | 53399.23 | 120458.98 | -67059.75 | 2019-05-24 10:02 | 2019-12-01 | 2019-06-01 | 2019-12-16
75084 | 75084IK | MX8452462 | TBC D-LINE PORTION:SOGOakbrookDona | 1190.7 |  | 1190.7 |  |  | 1190.7 | 33531.78 | -32341.08 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | KDLSCM | CD - OH DLine Switch Repl Reactive | 4758.23 |  | 4758.23 |  |  | 4758.23 | 70 | 4688.23 | 2019-03-21 16:06 | 2068-03-31 | 2019-07-01
75084 | 75084IK | MX3699429 | TMG- COMM PRIMARY - 4805 AERO PARKW | 19340 |  | 19340 |  |  | 19340 | 66211.76 | -46871.76 | 2019-09-27 14:28 | 2020-02-20 | 2019-10-01 | 2020-02-20
75084 | 75084IK | MX8452460 | TBC - D-LINE PORTION:SOGHandsWhiteT | 1188.58 |  | 1188.58 |  |  | 1188.58 | 35892.4 | -34703.82 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2800852 | TMG, COM. INSTALL PRIM/SEC/SVC - 23 | 36720.96 |  | 36720.96 |  |  | 36720.96 | 52468.31 | -15747.35 | 2019-09-06 08:01 | 2020-03-19 | 2019-10-01 | 2020-04-02
75084 | 75084IK | MX7481259 | Newport Levee xfmr Tie CAK-4378 to | 1031.03 |  | 1031.03 |  |  | 1031.03 | 3356.67 | -2325.64 | 2019-10-22 10:01 | 2020-04-16 | 2019-12-01 | 2020-03-30
75084 | 75084IK | MX2178128 | INFRASTRUCTIURE FOR JT-E-TUSCANY P | 33131.87 |  | 33131.87 |  |  | 33131.87 | 31359.33 | 1772.54 | 2019-04-08 18:01 | 2019-12-30 | 2019-05-01 | 2019-12-16
75084 | 75084IK | MX2168625 | CABLE UG OTHER TESTED REPLACE SMALL | 931.28 |  | 931.28 |  |  | 931.28 | 53872.4 | -52941.12 | 2019-03-11 10:01 | 2021-06-29 | 2019-05-01 | 2021-06-28
75084 | 75084IK | MX3602527 | JT-E-WHITESTONE LINKS SECTION 5 | 8647.52 |  | 8647.52 |  |  | 8647.52 | 13063.75 | -4416.23 | 2019-08-07 14:01 | 2020-05-21 | 2019-08-01 | 2020-03-29
75084 | 75084IK | KRRRCM | CD - Recl Elec Repl - Reactive | 104176.49 |  | 104176.49 |  |  | 104176.49 | 95 | 104081.49 | 2019-03-21 15:37 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX1576657 | Verona 41 Inst 4- 1ph Automated Cap | 94196.56 |  | 94196.56 |  |  | 94196.56 | 76863.06 | 17333.5 | 2019-04-18 18:01 | 2021-09-28 | 2019-04-01 | 2021-08-17
75084 | 75084IK | KRUCLGCM | CD - UG Cable Repl LG Reactive | 5778.56 |  | 5778.56 |  |  | 5778.56 | 97 | 5681.56 | 2019-03-21 16:28 | 2068-03-31 | 2019-09-01
75084 | 75084IK | MX3072339 | JT-E-Tuscany PH C Sec 10, 13,14 | 68577.66 |  | 68577.66 |  |  | 68577.66 | 139577.83 | -71000.17 | 2019-07-11 10:02 | 2020-05-31 | 2019-08-01 | 2020-04-21
75084 | 75084IK | KRUCSMCM | CD - UG Cable Repl Reactive | 270841.37 |  | 270841.37 |  |  | 270841.37 | 97 | 270744.37 | 2019-03-21 16:34 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX3169670 | POLE REPLACE - KY LANDSLIDE | 51402.43 |  | 51402.43 |  |  | 51402.43 | 41789.69 | 9612.74 | 2019-06-28 14:01 | 2020-01-29 | 2019-06-01 | 2020-01-13
75084 | 75084IK | MX1568931 | JT-E-TIMBER CREEK SUB - PH 1 | 17843.08 |  | 17843.08 |  |  | 17843.08 | 60373.53 | -42530.45 | 2019-04-08 10:01 | 2020-07-29 | 2019-07-01 | 2020-06-04
75084 | 75084IK | MX8452466 | TBC D-LINE PORTION:SOGOakbrookDo | 2099.64 |  | 2099.64 |  |  | 2099.64 | 28505.75 | -26406.11 | 2019-01-21 18:02 | 2021-03-01 | 2019-01-01
75084 | 75084IK | MX8452459 | TBC - D-LINE PORTION:SOGHandsWhiteT | 887.98 |  | 887.98 |  |  | 887.98 | 32996.5 | -32108.52 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX4982531 | EMERGENT UG EXIT WORK DKY2133 CIRCU | 31150.2 |  | 31150.2 |  |  | 31150.2 | 66711.02 | -35560.82 | 2019-12-05 18:01 | 2020-03-17 | 2019-12-01 | 2020-04-05
75084 | 75084IK | MX4267853 | COMMERCIAL PRIMARY/SECONDARY/SVC | 45120.4 |  | 45120.4 |  |  | 45120.4 | 108693.37 | -63572.97 | 2019-11-25 10:12 | 2020-04-23 | 2019-11-01 | 2020-04-08
75084 | 75084IK | MX2873686 | JT-E-TRAEMORE PH B | -11523 |  | -11523 |  |  | -11523 | 81367.57 | -92890.57 | 2019-06-06 15:12 | 2020-08-11 | 2019-07-01 | 2020-07-12
75084 | 75084IK | MX8452456 | TBC - D-LINE PORTION:SOGHandsWhiteT | 2130.82 |  | 2130.82 |  |  | 2130.82 | 38023.53 | -35892.71 | 2019-01-17 17:22 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX1072643 | Wildcat Run Phase 4 - Part 3 | 16772.62 |  | 16772.62 |  |  | 16772.62 | 25695.51 | -8922.89 | 2019-01-07 14:01 | 2020-02-03 | 2019-01-01 | 2019-12-25
75084 | 75084IK | MX8452471 | TBC D-LINE PORTION:SOGOakbrookDona | 1129.64 |  | 1129.64 |  |  | 1129.64 | 31085.43 | -29955.79 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2864348 | JT-E-ARCADIA PH I | -5582 |  | -5582 |  |  | -5582 | 39368.3 | -44950.3 | 2019-06-07 10:02 | 2020-09-07 | 2019-07-01 | 2020-08-05
75084 | 75084IK | MX2320502 | INFRASTRUCTIURE FOR SUBDIVISION D | 32408.41 |  | 32408.41 |  |  | 32408.41 | 44965.71 | -12557.3 | 2019-04-26 10:01 | 2020-01-15 | 2019-05-01 | 2019-12-25
75084 | 75084IK | MX9977953 | CABLE UG REPLACE SMALL | 84344.07 |  | 84344.07 |  |  | 84344.07 | 289037.3 | -204693.23 | 2019-04-01 10:01 | 2020-03-26 | 2019-05-01 | 2020-04-26
75084 | 75084IK | MX8452470 | D-LINE PORTION:SOGOakbrookDonaldson | 732.81 |  | 732.81 |  |  | 732.81 | 31552.49 | -30819.68 | 2019-01-16 14:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX4559811 | TMG - TEMP SERVICE FOR COMM - AMAZO | -47750.71 |  | -47750.71 |  |  | -47750.71 | 67513.7 | -115264.41 | 2019-11-27 10:01 | 2020-05-14 | 2019-12-01 | 2020-04-27
75084 | 75084IK | MX1429119 | 107 chambers | 184193.02 |  | 184193.02 |  |  | 184193.02 | 103354.18 | 80838.84 | 2019-03-07 10:01 | 2019-11-01 | 2019-03-01 | 2019-07-30
75084 | 75084IK | MX0494865 | MXCONV-Transformer Retrofit HANDS | 737.68 |  | 737.68 |  |  | 737.68 | 209984.34 | -209246.66 | 2019-11-18 18:01 | 2022-12-29 | 2019-11-01
75084 | 75084IK | MX8452461 | TBC - D-LINE PORTION:SOGHandsWhiteT | 1839.23 |  | 1839.23 |  |  | 1839.23 | 37951.33 | -36112.1 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX0532482 | DEN,RESIDENTIAL ELECTRIC,TAPESTRY A | 187651.62 |  | 187651.62 |  |  | 187651.62 | 158085.63 | 29565.99 | 2019-03-28 10:01 | 2019-10-30 | 2019-04-01 | 2019-09-15
75084 | 75084IK | MX1469801 | TBC D-LINE PORTION: SEGMENTATION O | 6148.6 |  | 6148.6 |  |  | 6148.6 | 35524.8 | -29376.2 | 2019-04-15 10:02 | 2021-03-01 | 2019-05-01
75084 | 75084IK | MX2168034 | Mt Zion UG Exits - DKY2133 | 2254.72 |  | 2254.72 |  |  | 2254.72 | 63516.3 | -61261.58 | 2019-12-17 18:01 | 2020-08-29 | 2019-12-01 | 2020-08-20
75084 | 75084IK | KMHR | Manhole Lid Retrofit Replacement | 802.63 |  | 802.63 |  |  | 802.63 | 0 | 802.63 | 2017-07-27 14:56 | 2067-12-31 | 2019-12-01
75084 | 75084IK | MX1816539 | INFRASTRUCTIURE FOR ARCADIA PHASE M | 9952.3 |  | 9952.3 |  |  | 9952.3 | 38855.28 | -28902.98 | 2019-05-14 18:01 | 2020-06-02 | 2019-07-01 | 2020-04-29
75084 | 75084IK | MX1349088 | INFRASTRUCTIURE FOR SUBDIVISION D | 44354.03 |  | 44354.03 |  |  | 44354.03 | 37826.78 | 6527.25 | 2019-02-22 14:02 | 2020-02-27 | 2019-02-01 | 2020-02-02
75084 | 75084IK | MX1172586 | INFRASTRUCTIURE FOR ARBOR SPRINGS | 1239.98 |  | 1239.98 |  |  | 1239.98 | 8730.5 | -7490.52 | 2019-01-16 18:01 | 2020-05-31 | 2019-02-01 | 2020-04-27
75084 | 75084IK | MX3045963 | Declared Circuit - Donaldson 41 - 2 | 4168.76 |  | 4168.76 |  |  | 4168.76 | 628843.53 | -624674.77 | 2019-09-09 14:01 | 2031-02-27 | 2019-11-01
75084 | 75084IK | MX2449322 | JT-E-NORTH WALTON POINTE PH 4 | 14195.04 |  | 14195.04 |  |  | 14195.04 | 15882.2 | -1687.16 | 2019-05-06 18:01 | 2020-04-26 | 2019-05-01 | 2020-03-08
75084 | 75084IK | MX8452448 | TBC - D-LINE PORTION: SEGMENTATION | 2744.5 |  | 2744.5 |  |  | 2744.5 | 31737.33 | -28992.83 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX9955971 | TMG-COMMERCIAL PRIMARY - 2505 TED B | 165266.02 |  | 165266.02 |  |  | 165266.02 | 142956.41 | 22309.61 | 2018-12-19 10:01 | 2019-05-24 | 2019-01-01 | 2019-06-02
75084 | 75084IK | MX0322031 | LOAD GROWTH, LOAD TRANSFER AND TIE | -6518.71 |  | -6518.71 |  |  | -6518.71 | 118358.51 | -124877.22 | 2019-06-04 10:02 | 2019-11-28 | 2019-06-01 | 2019-11-14
75084 | 75084IK | MX3835592 | MPO - 91 BANKLICK RD - COMM PERM EL | -17089.15 |  | -17089.15 |  |  | -17089.15 | 50873.74 | -67962.89 | 2019-10-21 14:01 | 2020-09-03 | 2019-10-01 | 2020-08-27
75084 | 75084IK | MX0706061 | INFRASTRUCTIURE FOR SUBDIVISION D | 19811.53 |  | 19811.53 |  |  | 19811.53 | 24386.62 | -4575.09 | 2018-12-19 10:01 | 2020-03-15 | 2019-10-01 | 2020-03-11
75084 | 75084IK | MX8176166 | JFS - PERM ELEC - LOGISTICS PARK 75 | 144080.68 |  | 144080.68 |  |  | 144080.68 | 110224.02 | 33856.66 | 2019-06-04 10:02 | 2019-12-19 | 2019-07-01 | 2019-12-19
75084 | 75084IK | MX2180887 | INFRASTRUCTIURE FOR Cantering Hills | 12401.35 |  | 12401.35 |  |  | 12401.35 | 18427.86 | -6026.51 | 2019-05-20 10:01 | 2020-04-08 | 2019-06-01 | 2020-04-08
75084 | 75084IK | MX2467744 | TMG - COM PRIM/SEC/SVC - CVG CARGO | 59441.72 |  | 59441.72 |  |  | 59441.72 | 59589.57 | -147.85 | 2019-05-08 18:01 | 2019-11-21 | 2019-07-01 | 2019-11-17
75084 | 75084IK | MX1281268 | JT-E-ARCADIA POD A - PHASE 2 | 33370.59 |  | 33370.59 |  |  | 33370.59 | 23673.14 | 9697.45 | 2019-01-25 18:01 | 2019-12-25 | 2019-08-01 | 2019-12-03
75084 | 75084IK | KRNUUG | Removal of non-utilized infrastruct | 3.36 |  | 3.36 |  |  | 3.36 | 0 | 3.36 | 2018-07-24 10:51 | 2068-03-31 | 2019-08-01
75084 | 75084IK | MX2210518 | INFRASTRUCTIURE FOR WHITESTONE LIN | 11059.3 |  | 11059.3 |  |  | 11059.3 | 16781.72 | -5722.42 | 2019-05-08 14:01 | 2020-05-21 | 2019-05-01 | 2020-03-29
75084 | 75084IK | MX3267506 | TJB RESIDENTIAL PRIMARY/SECONDARY/S | 4633.81 |  | 4633.81 |  |  | 4633.81 | 33975.33 | -29341.52 | 2019-11-08 14:01 | 2020-03-26 | 2019-12-01 | 2020-04-29
75084 | 75084IK | MX4307495 | JT-E-Steeplechase Sec 18 | -7642 |  | -7642 |  |  | -7642 | 75393.15 | -83035.15 | 2019-10-21 14:01 | 2021-01-03 | 2019-11-01
75084 | SG000440F | SGRFSKY | DEK Sectionalization | 11135.65 |  | 11135.65 |  |  | 71632.51 | 83 | 71549.51 | 2016-05-16 10:23 | 2025-12-31 | 2017-01-01
75084 | DKY2017 | D2017DL5 | RUSD Donaldson Hwy Retire - DKY2017 | -10308.85 |  | -10308.85 |  |  | 2783.18 | 12270.87 | -9487.69 | 2017-04-25 11:29 | 2023-04-30 | 2017-12-01
75084 | DKY2017 | D2017DL3 | AM 21113304 Davidson Hwy - DKY2017 | 139885.35 |  | 139885.35 |  |  | 142887.95 | 204529.81 | -61641.86 | 2017-04-17 15:00 | 2020-12-18 | 2017-07-01 | 2020-10-26
75084 | DKY2017 | D2017DL1 | TBC AM 21113152 Donaldson Hwy | 2128151.21 |  | 2128151.21 |  |  | 2201654.81 | 0 | 2201654.81 | 2017-04-17 14:46 | 2021-03-31 | 2017-04-01
75084 | DKY2017 | D2017DL4 | RUSD Donaldson Retire Erlanger Road | 82.92 |  | 82.92 |  |  | 82.92 | 94106.3 | -94023.38 | 2017-04-25 11:01 | 2021-04-30 | 2019-03-01 | 2021-05-10
75084 | DKY2017 | MX1113152 | MXCONV-Donaldson 43 Instl UG Condui | 2125084.15 |  | 2125084.15 |  |  | 2125084.15 | 2636453.11 | -511368.96 | 2018-11-09 14:02 | 2020-09-28 | 2019-04-01 | 2020-09-22
75084 | DKY2017 | MXA113380 | MXCONV-Donaldson Instl UG Cable DKY | 310146.17 |  | 310146.17 |  |  | 310146.17 | 1304605.52 | -994459.35 | 2019-04-09 14:01 | 2020-11-26 | 2019-04-01 | 2020-10-19
75084 | DKY2017 | D2017DL2 | TBC RUSD Donaldson Install UG | 664739.55 |  | 664739.55 |  |  | 664739.55 | 0 | 664739.55 | 2017-04-25 10:46 | 2021-03-31 | 2019-11-01
75084 | DKY2019 | MX2240021 | Buffington 43 Ln Ext - DKY2019 | 29679.78 |  | 29679.78 |  |  | 47908.52 | 108589.89 | -60681.37 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-16
75084 | DKY2019 | MX2239929 | Buffington 43 UB Pt 2 - DKY2019 | 137038.63 |  | 137038.63 |  |  | 147785.1 | 84712.23 | 63072.87 | 2017-10-18 18:02 | 2020-03-30 | 2018-01-01 | 2020-04-06
75084 | DKY2019 | MX2239881 | TBC-Dixie 46 Ln Ext - DKY2019 | -12271.62 |  | -12271.62 |  |  | 781.08 | 183148.71 | -182367.63 | 2017-10-18 18:02 | 2020-06-30 | 2018-01-01
75084 | DKY2019 | MX2239971 | Dixie 45 Ln Ext - DKY2019 | 16680.25 |  | 16680.25 |  |  | 42884.15 | 145406.88 | -102522.73 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-14
75084 | DKY2019 | MX1269760 | Buffington 43 UG - DKY2019 | 12141.07 |  | 12141.07 |  |  | 19270.46 | 20243.51 | -973.05 | 2018-03-19 14:01 | 2021-05-01 | 2018-04-01 | 2021-03-29
75084 | DKY2019 | D2019DL2 | TBC AM 21269675 Rbld Industrial Rd | 424.25 |  | 424.25 |  |  | 30355.15 | 0 | 30355.15 | 2017-05-09 09:46 | 2020-12-31 | 2017-05-01
75084 | DKY2019 | D2019DL3 | TBC AM 21269760 Rbld Industrial Rd | 184.83 |  | 184.83 |  |  | 13223.56 | 0 | 13223.56 | 2017-05-09 09:51 | 2020-12-31 | 2017-07-01
75084 | DKY2019 | MX2240623 | Buffington 42 UB Trnsfr - DKY2019 | 14895.97 |  | 14895.97 |  |  | 25729.62 | 11669.98 | 14059.64 | 2017-10-18 18:02 | 2020-10-29 | 2018-01-01 | 2020-10-19
75084 | DKY2019 | D2019DL1 | Dixie 45 46 Exits - DKY2019 | 376692.28 |  | 376692.28 |  |  | 397876.07 | 263109.52 | 134766.55 | 2017-05-09 09:41 | 2019-11-29 | 2017-07-01 | 2019-10-03
75084 | DKY2019 | MX0840788 | Dixie 45-46 Station Exits Overhead | 76966.36 |  | 76966.36 |  |  | 76966.36 | 38462.25 | 38504.11 | 2019-03-22 10:01 | 2019-12-29 | 2019-06-01 | 2019-12-22
75084 | DKY2019 | MX1269037 | Dixie 45-46 Conduit - DKY2019 | 472642.44 |  | 472642.44 |  |  | 472642.44 | 299781.46 | 172860.98 | 2019-03-21 14:01 | 2020-03-30 | 2019-07-01 | 2020-02-12
75084 | TKY1935 | T1935DS1 | Hebron XTR Rel Rpl - TKY1935 | 377985.81 |  | 377985.81 |  |  | 640645.94 | 807940.13 | -167294.19 | 2017-07-13 14:02 | 2020-06-30 | 2017-11-01 | 2020-07-02
75084 | TKY1695 | T1695TS2 | Kenton F966 Rel Repl - TKY1695 | 45733.01 |  | 45733.01 |  |  | 156932.65 | 352819 | -195886.35 | 2016-10-07 18:03 | 2021-02-15 | 2016-12-01 | 2021-03-17
75084 | TKY1695 | T1695TS1 | Buffington F966 CB Rel Repl - TKY16 | 1664855.5 |  | 1664855.5 |  |  | 2159606.09 | 1153424 | 1006182.09 | 2016-10-07 18:03 | 2020-04-05 | 2016-10-01 | 2020-03-27
75084 | SG000459F | SG459FB01 | 2018 Midwest Fiber Activation | 9079.74 |  | 9079.74 |  |  | 22434.06 | 37132 | -14697.94 | 2018-02-08 16:47 | 2023-03-01 | 2018-02-01
75084 | SG000459F | SG459FB02 | 2018 Midwest Fiber Activation | 4388.92 |  | 4388.92 |  |  | 7002.62 | 37132 | -30129.38 | 2018-02-08 16:57 | 2023-03-01 | 2018-02-01
75084 | SG000459F | SG459BUFF | DEK Fiber Buffington to Verona | 2934676.57 |  | 2934676.57 |  |  | 2934676.57 | 2073294.06 | 861382.51 | 2019-02-28 14:16 | 2020-07-30 | 2019-04-01 | 2020-06-27
75084 | SG000223F | SG223SW | DEE Transmission Health & Risk Mgt | 130104.09 |  | 130104.09 |  |  | 424894.85 | 1016639 | -591744.15 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01
75084 | SG000732F | SG732BTR | SG DEK Battery Replacement | 902.23 |  | 902.23 |  |  | 76602.78 | 33850 | 42752.78 | 2017-10-11 15:39 | 2026-03-31 | 2018-02-01
75084 | SG000732F | SG732TR01 | DEK Towers & Shelters - Verona | 32688.1 |  | 32688.1 |  |  | 36323.52 | 968336.2 | -932012.68 | 2018-09-11 15:00 | 2021-09-30 | 2018-09-01 | 2021-04-15
75084 | SG000732F | SG732TR02 | DEK Tower & Shelter - Verona 2 | 4707.03 |  | 4707.03 |  |  | 4707.03 | 968336 | -963628.97 | 2019-01-23 11:05 | 2022-03-31 | 2019-02-01
75084 | SG000776F | SG776OPS | Transport Terminal Optical EOL | 24700.37 |  | 24700.37 |  |  | 44038.15 | 371480 | -327441.85 | 2018-02-14 12:38 | 2023-03-31 | 2018-03-01
75084 | SG000776F | SG776MTR | Transport Terminal Optical EOL | 16238.43 |  | 16238.43 |  |  | 345779.43 | 1 | 345778.43 | 2018-02-15 09:50 | 2028-03-31 | 2018-03-01
75084 | SG000438F | SGSELFKY | DEK Segmentation & Automation | 271078.55 |  | 271078.55 |  |  | 345056.68 | 1 | 345055.68 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01
75084 | SG000438F | SG438LIC | SG DEK YFA Device Licenses | 58596.2 |  | 58596.2 |  |  | 103661.3 | 8250 | 95411.3 | 2018-06-11 10:54 | 2020-03-31 | 2018-07-01 | 2020-06-30
75084 | SG000438F | SG438DOTS | Distribution Operator Training Sim | 6132.01 |  | 6132.01 |  |  | 6132.01 | 1 | 6131.01 | 2019-10-31 16:15 | 2021-09-30 | 2019-10-01 | 2022-03-31
75084 | 75084HW | KHWYR | Highway Relocations Reimb | -15411.39 |  | -15411.39 |  |  | 90133.52 | 80 | 90053.52 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01
75084 | 75084HW | MX9624173 | Ri-I-71/I-75 & KY 536 Inneerchange | 24.4 |  | 24.4 |  |  | 2640.42 | 142487.26 | -139846.84 | 2018-09-06 14:02 | 2021-01-14 | 2018-09-01 | 2021-01-19
75084 | 75084HW | KCOU | Make Ready Other Util Attachments | 93301.61 |  | 93301.61 |  |  | 587605.84 | 91 | 587514.84 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01
75084 | 75084HW | KCRFN | Customer Requested Mods Nonreimb | 36961.17 |  | 36961.17 |  |  | 77593.45 | 80 | 77513.45 | 2017-03-24 15:19 | 2067-12-31 | 2018-06-01
75084 | 75084HW | KCRFR | Customer Requested Mods Reimb | -29967.75 |  | -29967.75 |  |  | -41876.08 | 98 | -41974.08 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01
75084 | 75084HW | KHWYN | Highway Relocations Nonreimb | 287297.52 |  | 287297.52 |  |  | 428492.6 | 80 | 428412.6 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01
75084 | 75084HW | MX9612876 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 953.28 |  | 953.28 |  |  | 5831.79 | 132976.53 | -127144.74 | 2018-08-28 10:02 | 2021-01-30 | 2018-09-01 | 2021-01-27
75084 | 75084HW | MX1661647 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 715240.24 |  | 715240.24 |  |  | 751456.56 | 228.31 | 751228.25 | 2017-11-28 14:01 | 2021-03-18 | 2017-12-01 | 2021-02-21
75084 | 75084HW | MX7090228 | RI-6th St Beautification, undergrou | 1571.8 |  | 1571.8 |  |  | 11126.33 | 150507.84 | -139381.51 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-05-22
75084 | 75084HW | MX7090285 | RI-6th St Beautification, overhead | 44542.54 |  | 44542.54 |  |  | 56642.53 | 155930.4 | -99287.87 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-03-09
75084 | 75084HW | MX9060418 | I-71 /I-75 & KY 536 Interchange (D | 1412.89 |  | 1412.89 |  |  | 34556.86 | 68431.55 | -33874.69 | 2018-07-12 14:02 | 2020-09-30 | 2018-07-01 | 2020-07-26
75084 | 75084HW | KMODC | Other Capital Modifications | 42713.52 |  | 42713.52 |  |  | 50897.79 | 80 | 50817.79 | 2017-03-24 15:33 | 2067-12-31 | 2018-07-01
75084 | 75084HW | MX8360139 | MXCONV-RI-North Bend Road at World | -69813.02 |  | -69813.02 |  |  | -9688.89 | 59842.81 | -69531.7 | 2018-05-07 18:02 | 2019-06-01 | 2018-05-01 | 2019-01-16
75084 | 75084HW | MX6295870 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 66150.52 |  | 66150.52 |  |  | 172216.46 | 83155.24 | 89061.22 | 2017-11-30 18:02 | 2019-06-01 | 2017-12-01 | 2019-05-21
75084 | 75084HW | MX7752157 | RI-Amsterdam Rd Road Improvement | 399081.57 |  | 399081.57 |  |  | 399876.47 | 163902.06 | 235974.41 | 2018-11-06 14:02 | 2019-09-02 | 2018-11-01 | 2019-07-28
75084 | 75084HW | MX1298730 | RELO; 123 W 4TH; OVATION SITE A - P | 18708.25 |  | 18708.25 |  |  | 18708.25 | 44193.76 | -25485.51 | 2019-03-27 14:01 | 2019-11-28 | 2019-04-01 | 2019-12-30
75084 | 75084HW | MX2513722 | RI - PARK POINTE RELOCATION; AMSTER | 214646.66 |  | 214646.66 |  |  | 214646.66 | 429103.61 | -214456.95 | 2019-07-29 14:02 | 2021-03-31 | 2019-08-01 | 2021-03-03
75084 | 75084HW | MX2483019 | RI-Reconstruction of the I-75/71 Ri | 102827.86 |  | 102827.86 |  |  | 102827.86 | 383026.87 | -280199.01 | 2019-05-06 10:16 | 2021-06-17 | 2019-05-01 | 2021-06-14
75084 | 75084HW | MX1072194 | Wendell H. Ford Blvd. Utility Reloc | -110022.72 |  | -110022.72 |  |  | -110022.72 | 144128.97 | -254151.69 | 2019-02-06 18:01 | 2019-11-15 | 2019-05-01 | 2019-10-09
75084 | 75084HW | MX2388911 | RSC - Design - 602 Altamont Ave | 210767.7 |  | 210767.7 |  |  | 210767.7 | 81750.88 | 129016.82 | 2019-07-23 14:01 | 2020-02-13 | 2019-08-01 | 2020-03-26
75084 | 75084HW | MX2481408 | RI-Reconstruction of the (-75/71 Ri | 229401.27 |  | 229401.27 |  |  | 229401.27 | 343628.23 | -114226.96 | 2019-05-06 14:01 | 2021-02-25 | 2019-05-01 | 2021-02-02
75084 | 75084HW | MX2481659 | RI -Reconstruction of the I-75/71 | 15803.74 |  | 15803.74 |  |  | 15803.74 | 522132.65 | -506328.91 | 2019-05-06 14:01 | 2021-02-25 | 2019-06-01 | 2021-01-27
75084 | 75084HW | MX0791880 | JFS - JOHN R GREEN - PHASE 1 | 51464.86 |  | 51464.86 |  |  | 51464.86 | 174890.1 | -123425.24 | 2019-02-11 18:01 | 2020-02-27 | 2019-02-01 | 2020-02-23
75084 | 75084HW | MX3659710 | RELO; 123 W 4TH; OVATION SITE A - P | -172547.75 |  | -172547.75 |  |  | -172547.75 | 83683.41 | -256231.16 | 2019-09-18 10:01 | 2020-03-30 | 2019-12-01 | 2020-08-20
75084 | 75084HW | MX2906263 | OH CABLE CLEARS ISSUES REPLACE | 3024.56 |  | 3024.56 |  |  | 3024.56 | 57085.1 | -54060.54 | 2019-06-24 18:01 | 2020-05-31 | 2019-11-01 | 2020-04-21
75084 | 75084HW | MX3300657 | MT.ZION @ HEMPSTEADE - CONDUIT & CA | 21695.31 |  | 21695.31 |  |  | 21695.31 | 62826.31 | -41131 | 2019-07-11 10:02 | 2019-11-05 | 2019-07-01 | 2019-11-17
75084 | 75084HW | MX1096567 | Exhibit A DEK 1812MCI0545DEK, MAKE- | -21720.43 |  | -21720.43 |  |  | -21720.43 | 49290.4 | -71010.83 | 2019-08-23 14:01 | 2020-02-23 | 2019-08-01 | 2020-01-26
75084 | 75084HW | MX2288324 | HANDS PK @ CRYSTAL LAKE DR, RELOCAT | 4.46 |  | 4.46 |  |  | 4.46 | 159886.58 | -159882.12 | 2019-10-03 14:01 | 2020-10-12 | 2019-10-01 | 2020-08-12
75084 | 75084HW | MX1276918 | KY 536 - Mt.ZION RD. (CABLE WORK) | 4194.28 |  | 4194.28 |  |  | 4194.28 | 225364.83 | -221170.55 | 2019-02-04 10:02 | 2020-12-24 | 2019-02-01 | 2020-10-28
75084 | 75084HW | MX3147077 | HW Crossing Removal - DKYHW2672 | 68.65 |  | 68.65 |  |  | 68.65 | 436.56 | -367.91 | 2019-06-26 14:01 | 2020-08-01 | 2019-08-01 | 2020-10-06
75084 | 75084HW | MX1277017 | KY 536 - Mt. ZION RD. (CONDUIT WORK | 3841.38 |  | 3841.38 |  |  | 3841.38 | 132813.99 | -128972.61 | 2019-02-04 10:02 | 2020-11-12 | 2019-02-01 | 2020-11-01
75084 | 75084HW | MX2423627 | KY 17 S/O GLEASON RD,RELOCATION HIG | 106725.91 |  | 106725.91 |  |  | 106725.91 | 90074.95 | 16650.96 | 2019-10-02 18:01 | 2020-03-16 | 2019-10-01 | 2020-04-01
75084 | 75084HW | MX1276812 | KY 536 (OH WORK) | 175685.07 |  | 175685.07 |  |  | 175685.07 | 137747.11 | 37937.96 | 2019-02-04 10:02 | 2021-01-30 | 2019-02-01 | 2021-01-27
75084 | SGEDMS3F | SGDMS3SW | DEE DMS 3.5 Upgrade - Software | 16316.91 |  | 16316.91 |  |  | 242695.68 | 210242 | 32453.68 | 2015-11-19 10:10 | 2021-01-31 | 2016-09-01 | 2019-12-31
75084 | KECF20154 | KEC920154 | DEC 8920154 Kenton 46 | -30813.58 |  | -30813.58 |  |  | 507.46 | 150467.62 | -149960.16 | 2015-10-23 10:05 | 2020-12-31 | 2016-09-01
75084 | CP18SUBK | MX8667739 | Marshall TB1 replace X0,1,2,3 Bushi | 6744.98 |  | 6744.98 |  |  | 12606.49 | 9204.03 | 3402.46 | 2018-06-05 14:02 | 2020-03-30 | 2018-08-01 | 2020-01-14
75084 | CP18SUBK | MX8693329 | CAPITAL Richwood TB2 replace H2, X2 | 104.56 |  | 104.56 |  |  | 7481.32 | 9907.33 | -2426.01 | 2018-06-08 10:02 | 2021-03-31 | 2018-10-01 | 2020-08-16
75084 | CP18SUBK | MX8693627 | CAPITAL Richwood TB3 replace X3 Bus | 3952.17 |  | 3952.17 |  |  | 6387.89 | 3280.81 | 3107.08 | 2018-06-08 10:02 | 2022-03-31 | 2018-10-01 | 2022-08-31
75084 | CP18SUBK | MX0093848 | CAPITAL Kenton TB3 replace one bad | -500.22 |  | -500.22 |  |  | -2.8422e-14 | 466.04 | -466.04 | 2018-10-09 14:02 | 2019-12-31 | 2018-11-01
75084 | CP18SUBK | MX0106047 | CAPITAL White Tower TB1 replace two | 861.77 |  | 861.77 |  |  | 1958.27 | 882.31 | 1075.96 | 2018-10-10 14:02 | 2020-03-31 | 2018-11-01 | 2019-10-24
75084 | CP18SUBK | MX8593684 | CAPITAL Bellevue TB1 repl 13kV Arre | -3.2 |  | -3.2 |  |  | 997 | 856.83 | 140.17 | 2018-06-01 10:01 | 2019-03-31 | 2018-06-01 | 2019-03-04
75084 | CP18SUBK | MX0076115 | CAPITAL Dixie TB2 replace one bad f | 847.21 |  | 847.21 |  |  | 1371.05 | 466.04 | 905.01 | 2018-10-08 18:02 | 2020-03-31 | 2018-10-01 | 2019-10-24
75084 | CP18SUBK | MX0077066 | CAPITAL Crescent TB2 replace one ba | 731.45 |  | 731.45 |  |  | 1331.76 | 447.05 | 884.71 | 2018-10-09 10:02 | 2020-03-31 | 2018-11-01 | 2019-10-24
75084 | CP18SUBK | MX0090746 | CAPITAL Bellevue TB1 replace one ba | 176.09 |  | 176.09 |  |  | 776.4 | 447.05 | 329.35 | 2018-10-09 14:02 | 2020-03-31 | 2018-11-01 | 2019-11-26
75084 | CP18SUBK | MX0088995 | CAPITAL Buffington TB7 replace one | 544.78 |  | 544.78 |  |  | 1254.02 | 540.75 | 713.27 | 2018-10-09 14:02 | 2019-03-31 | 2018-11-01 | 2019-06-05
75084 | CP18SUBK | MX0089985 | CAPITAL Claryville TB1 replace one | -1.76 |  | -1.76 |  |  | 771.64 | 466.04 | 305.6 | 2018-10-09 14:02 | 2019-03-31 | 2018-11-01 | 2019-03-12
75084 | CP18SUBK | MX1432670 | CAPITAL Alexandria South TB1 replac | 6884.29 |  | 6884.29 |  |  | 6884.29 | 73242.45 | -66358.16 | 2019-02-12 14:01 | 2020-03-31 | 2019-06-01 | 2020-01-07
75084 | CP18SUBK | MX1450766 | CAPITAL Constance TB2 replace HS Ar | 3536.46 |  | 3536.46 |  |  | 3536.46 | 3795.57 | -259.11 | 2019-02-12 14:01 | 2022-03-31 | 2019-04-01
75084 | CP18SUBK | MX1464046 | CAPITAL Richwood TB2 replace HS & L | 1985.16 |  | 1985.16 |  |  | 1985.16 | 3468.26 | -1483.1 | 2019-02-12 14:01 | 2021-03-31 | 2019-03-01 | 2020-08-16
75084 | CP18SUBK | MX1488550 | CAPITAL Wilder TB4 replace X0, X1, | 17815.43 |  | 17815.43 |  |  | 17815.43 | 17460.92 | 354.51 | 2019-02-12 14:01 | 2022-03-31 | 2019-03-01
75084 | CP18SUBK | MX1434007 | CAPITAL Altas TB1 replace HS LA's | 2406.99 |  | 2406.99 |  |  | 2406.99 | 2618.11 | -211.12 | 2019-02-12 14:01 | 2021-03-31 | 2019-04-01 | 2020-07-15
75084 | CP18SUBK | MX1464324 | CAPITAL Richwood TB3 replace HS Arr | 1534.61 |  | 1534.61 |  |  | 1534.61 | 2837.22 | -1302.61 | 2019-02-12 14:01 | 2022-03-31 | 2019-06-01 | 2022-08-31
75084 | CP18SUBK | MX1543301 | CAPITAL Wilder TB1 replace X1, X2, | 21316.56 |  | 21316.56 |  |  | 21316.56 | 20594.56 | 722 | 2019-02-14 18:01 | 2021-03-31 | 2019-09-01 | 2021-03-14
75084 | CP18SUBK | MX1488496 | CAPITAL Wilder TB1 replace H & X & | 6053.48 |  | 6053.48 |  |  | 6053.48 | 5761.61 | 291.87 | 2019-02-12 14:01 | 2021-03-31 | 2019-03-01 | 2021-03-14
75084 | TKY2204 | T2204DS1 | Buffington Rcfgr 4_5 - TKY2204 | 864368.8 |  | 864368.8 |  |  | 950427.89 | 2109259 | -1158831.11 | 2018-05-02 10:01 | 2021-02-20 | 2018-06-01 | 2021-03-30
75084 | KARF51805 | KAR851805 | LAR 10851805 Wilder 44 | 817142.44 |  | 817142.44 |  |  | 917627.57 | 313344.88 | 604282.69 | 2016-07-26 14:03 | 2020-03-31 | 2016-09-01 | 2019-12-17
75084 | TLRKY | TLRKY24 | FIF 2 P1 poles CA9-18 and CA9-922 | 130410.48 |  | 130410.48 |  |  | 130410.48 | 143159 | -12748.52 | 2019-06-12 14:01 | 2019-10-16 | 2019-06-01 | 2019-10-02
75084 | TKY1791 | T1791DS1 | Villa TB2 and Bus 2 Swgr Rpl - TKY1 | 354212.77 |  | 354212.77 |  |  | 954908.28 | 2193964.25 | -1239055.97 | 2017-05-17 14:03 | 2020-07-14 | 2017-07-01 | 2020-08-24
75084 | TKY1791 | T1791TS1 | Villa 69kV Bus 1 CCVT Rpl - TKY1791 | 1109361.68 |  | 1109361.68 |  |  | 1410158.18 | 814297.47 | 595860.71 | 2017-05-17 14:03 | 2020-07-25 | 2017-08-01 | 2020-08-24
75084 | TKY1791 | MX4426283 | Villa Distribution Layout - TKY1791 | 16922.62 |  | 16922.62 |  |  | 16922.62 | 4514.62 | 12408 | 2019-10-16 10:01 | 2020-02-13 | 2019-11-01 | 2020-02-24
75084 | TKY2128 | T2128TL1 | F966 Rcnfgr Villa Loop TL - TKY2128 | 120817.44 |  | 120817.44 |  |  | 133698.05 | 167889.26 | -34191.21 | 2017-05-30 14:04 | 2020-07-17 | 2018-02-01 | 2020-08-10
75084 | TKY2128 | T2128TS1 | Villa-Inst 69 kV Ring Bus - TKY2128 | 2353770.95 |  | 2353770.95 |  |  | 3119645.55 | 4352926.57 | -1233281.02 | 2017-05-30 14:04 | 2020-07-17 | 2017-08-01 | 2020-08-10
75084 | 75084IL | KSLNOLE | Non Ole Street Light Replacements | 15329.71 |  | 15329.71 |  |  | 39300.8 | 58 | 39242.8 | 2017-03-28 09:41 | 2067-04-01 | 2018-02-01
75084 | 75084IL | KCAL | Area Light New Installs | 244625.37 |  | 244625.37 |  |  | 275599.01 | 98 | 275501.01 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KLEDSL | LED Street Light Retrofit | -158065.56 |  | -158065.56 |  |  | 233326.66 | 58 | 233268.66 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01
75084 | 75084IL | KSLRPL | Street Light Replacements | 145622.41 |  | 145622.41 |  |  | 196748.25 | 58 | 196690.25 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KALRPL | Area Light Replacements | 34658.34 |  | 34658.34 |  |  | 40196.1 | 58 | 40138.1 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01
75084 | 75084IL | MX6293181 | Florence Lighting Upgrade Phase 1 | -35801.7 |  | -35801.7 |  |  | -221342.75 | 240125.13 | -461467.88 | 2018-03-12 14:01 | 2019-01-30 | 2018-04-01 | 2019-03-04
75084 | 75084IL | MX6293467 | Florence Lighting Upgrade Phase 2 | 169120.44 |  | 169120.44 |  |  | -87968.1 | 343744.48 | -431712.58 | 2018-03-12 14:01 | 2019-01-25 | 2018-04-01 | 2019-03-04
75084 | 75084IL | MX1977699 | BBB, Notre Dame Academy Lighti | 4789.88 |  | 4789.88 |  |  | 87140.72 | 61644.58 | 25496.14 | 2017-11-15 14:01 | 2018-04-03 | 2017-12-01 | 2018-06-03
75084 | 75084IL | MX6486641 | Florence Lighting Upgrade Phase 3 | -26156.11 |  | -26156.11 |  |  | -63442.31 | 66900.04 | -130342.35 | 2018-03-12 14:01 | 2018-09-28 | 2018-05-01 | 2019-01-29
75084 | 75084IL | MX7423928 | STREET LIGHT REMOVE/INSTALL | 118677.3 |  | 118677.3 |  |  | 208873.37 | 132816.68 | 76056.69 | 2018-08-20 10:03 | 2019-05-01 | 2018-10-01 | 2019-06-10
75084 | 75084IL | KSMCELL | Outdoor Lighting Small Cell Regultd | 11005.31 |  | 11005.31 |  |  | 11005.31 | 0 | 11005.31 | 2017-09-20 15:00 | 2067-04-01 | 2019-03-01
75084 | 75084IL | KBANNER | DEK Streetlight Electric Banners | 1376.74 |  | 1376.74 |  |  | 1376.74 | 0 | 1376.74 | 2017-09-20 14:53 | 2067-04-01 | 2019-09-01
75084 | 75084IL | MX0211957 | TRANSPORT DR UPS BUILDING INSTALL | 8841.44 |  | 8841.44 |  |  | 8841.44 | 36637.07 | -27795.63 | 2019-04-12 10:01 | 2020-03-30 | 2019-04-01 | 2020-04-05
75084 | 75084IL | MX2019094 | JFS - STREET LIGHT PROJECT -CITY OF | -86393.56 |  | -86393.56 |  |  | -86393.56 | 49935.78 | -136329.34 | 2019-06-06 15:12 | 2021-03-31 | 2019-06-01
75084 | 75084IL | MX0047542 | AREA LIGHT PRIVATE REMOVE/INSTALL | 224581.65 |  | 224581.65 |  |  | 224581.65 | 141991.5 | 82590.15 | 2018-11-06 10:02 | 2019-12-29 | 2019-01-01 | 2019-12-11
75084 | 75084IL | MX9473912 | SMILE BLDG LIGHTING ERLANGER | 38642.21 |  | 38642.21 |  |  | 38642.21 | 142289.25 | -103647.04 | 2019-03-25 14:01 | 2019-09-30 | 2019-04-01 | 2019-09-29
75084 | 75084IL | MX2752398 | MANHATTAN HARBOUR 17 STREETLIGHTS | 128311.93 |  | 128311.93 |  |  | 128311.93 | 109328.27 | 18983.66 | 2019-06-21 10:01 | 2020-02-13 | 2019-07-01 | 2020-01-14
75084 | SG000468F | SG468MDM | SG DEK Next Gen Cellular | 332811.45 |  | 332811.45 |  |  | 429570.9 | 1684462.49 | -1254891.59 | 2017-10-10 12:47 | 2026-03-31 | 2018-01-01 | 2022-08-24
75084 | KIAF05495 | KIA705495 | DA 10705495 Alexandria So | -35.66 |  | -35.66 |  |  | 5898.08 | 53637.18 | -47739.1 | 2017-01-04 10:04 | 2019-03-01 | 2017-04-01 | 2019-01-08
75084 | KECF20153 | KEC920153 | DC 8920153 Bellevue 42 | 354035.08 |  | 354035.08 |  |  | 369924.62 | 298274.18 | 71650.44 | 2015-10-23 10:05 | 2020-03-31 | 2016-09-01 | 2020-01-07
75084 | 75084VM | VDHAZPGKY | VDHAZPGKY | 325847.23 |  | 325847.23 |  |  | 678779.45 | 1 | 678778.45 | 2017-05-25 15:32 | 2050-12-31 | 2018-01-01
75084 | 75084VM | VDREMVCKY | VDREMVCKY | 679759.88 |  | 679759.88 |  |  | 919732.58 | 1 | 919731.58 | 2017-05-25 11:52 | 2050-12-30 | 2018-01-01
75084 | SG000586F | SGDLSKY | RUSD DEK D-Line Switch Replacement | -25399.23 |  | -25399.23 |  |  | 272301.65 | 94 | 272207.65 | 2016-12-19 11:23 | 2025-12-31 | 2017-05-01
75084 | DKY2134 | D2134DL2 | AM 21801679 Oakbrook 42 | 1784825.09 |  | 1784825.09 |  |  | 1806779.96 | 529469.63 | 1277310.33 | 2017-07-25 14:20 | 2019-12-31 | 2018-03-01 | 2020-03-19
75084 | SG000794F | SG794DES | DEK Land Mobile Radio Design | -56438.41 |  | -56438.41 |  |  | 1232.61 | 154508.56 | -153275.95 | 2018-06-15 13:19 | 2025-03-01 | 2018-06-01 | 2021-02-28
75084 | SG000435F | SGCAPATKY | DEK Cap Automation | 61136.68 |  | 61136.68 |  |  | 81539.09 | 83 | 81456.09 | 2016-05-16 10:15 | 2025-12-31 | 2017-01-01
75084 | SG000435F | MX1848370 | TBC MXCONV-Capacitor Automation HAN | 2243.59 |  | 2243.59 |  |  | 2243.59 | 116060.84 | -113817.25 | 2019-05-01 10:02 | 2022-09-01 | 2019-06-01
75084 | SG000439F | SGGENSWKY | DEK Switchgear Upgrades-Automation | 8824.87 |  | 8824.87 |  |  | 12613.32 | 83 | 12530.32 | 2016-05-16 10:22 | 2025-12-31 | 2017-01-01
75084 | SG000744F | SG744MTR | DEK GridWAN | 8997.9 |  | 8997.9 |  |  | 11160.62 | 248821.93 | -237661.31 | 2018-05-25 13:28 | 2021-12-31 | 2018-07-01
75084 | SG000744F | SG744BLK | DEK GridWAN | 113243.04 |  | 113243.04 |  |  | 114890.5 | 248821.93 | -133931.43 | 2018-05-25 13:54 | 2031-03-31 | 2018-11-01
75084 | FARCOSSW | ARCOSSW | ARCOS System Outage Project | 16492.9 |  | 16492.9 |  |  | 130895.26 | 129249 | 1646.26 | 2018-06-10 21:10 | 2022-03-31 | 2018-07-01 | 2022-03-31
75084 | TOUTKY | OUT69KY | KY T-line Emergency Repl on 69kV | 20214.39 |  | 20214.39 |  |  | 81602.95 | 6 | 81596.95 | 2017-01-17 10:23 | 2050-12-31 | 2017-01-01
75084 | TOUTKY | TOUTKY01 | Servc rest P1 Due to high winds on | 63719.92 |  | 63719.92 |  |  | 216726.66 | 18000 | 198726.66 | 2018-02-09 10:02 | 2021-02-19 | 2018-11-01 | 2021-03-21
75084 | TOUTKY | TOUTKY03 | Auto Damage 6761 Pole 5G-328 Stub P | -5999.57 |  | -5999.57 |  |  | 7130.23 | 18000 | -10869.77 | 2018-04-09 18:02 | 2019-09-01 | 2018-05-01 | 2019-02-27
75084 | TOUTKY | MX1476595 | F966 X-fer UB for 2 - P1 wood to st | 734.2 |  | 734.2 |  |  | 734.2 | 2794.53 | -2060.33 | 2019-02-07 10:06 | 2021-07-30 | 2019-12-01 | 2021-06-03
75084 | TOUTKY | MX1040009 | F6785 P1 Pole replace 36BN-350 | 6232.23 |  | 6232.23 |  |  | 6232.23 | 9054.07 | -2821.84 | 2019-01-02 10:01 | 2019-09-01 | 2019-01-01 | 2019-05-20
75084 | TOUTKY | TOUTKY06 | 2019 Storm #5 restorations for 5966 | -22.51 |  | -22.51 |  |  | -22.51 | 0 | -22.51 | 2019-03-21 14:05 | 2020-12-31 | 2019-06-01
75084 | TOUTKY | TOUTKY05 | F5967 Autodamage 1 P1 pole replace | 38503.5 |  | 38503.5 |  |  | 38503.5 | 55812 | -17308.5 | 2019-03-07 14:01 | 2020-01-18 | 2019-03-01 | 2019-06-29
75084 | PRTFA | KYPRTF2 | PRTOH P1 Cir 6763 HLP626 | 215.36 |  | 215.36 |  |  | 11653.16 | 27000 | -15346.84 | 2016-12-22 14:57 | 2021-03-31 | 2018-04-01
75084 | DKY2198 | MX7724805 | Constance 41 LN Ext PME at sub - DK | 253435.7 |  | 253435.7 |  |  | 259297.64 | 92830.61 | 166467.03 | 2018-03-20 18:02 | 2020-02-24 | 2018-06-01 | 2020-02-23
75084 | DKY2198 | MX7724731 | Constance 41 Ln Ext Cable - DKY2198 | 1528514.84 |  | 1528514.84 |  |  | 1634730.11 | 762323.62 | 872406.49 | 2018-03-20 18:02 | 2020-03-30 | 2018-08-01 | 2020-01-28
75084 | DKY2198 | MX7724526 | Constance 41 Ln Ext Pt1 - DKY2198 | 1033417.99 |  | 1033417.99 |  |  | 1645440.47 | 951049.63 | 694390.84 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2018-07-27
75084 | DKY2198 | MX7724611 | Constance 41-43 LN Ext Pt II - DKY2 | 3427774.8 |  | 3427774.8 |  |  | 3495416.11 | 186281.75 | 3309134.36 | 2018-03-20 18:02 | 2019-12-29 | 2018-03-01 | 2019-12-05
75084 | DKY2198 | MX7724670 | Constance 41-43 LN Ext Pt III - DKY | 1048489.76 |  | 1048489.76 |  |  | 1391992.53 | 778204.8 | 613787.73 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2019-08-04
75084 | DKY2198 | DKY219802 | Constance 41-43 Feeder Exit Reloc | 74559.34 |  | 74559.34 |  |  | 74559.34 | 176913 | -102353.66 | 2019-02-04 18:01 | 2020-01-25 | 2019-02-01 | 2020-01-09
75084 | DKY2198 | MX9545158 | Constance Remove Existing OH - DKY2 | 98420.02 |  | 98420.02 |  |  | 98420.02 | 177911.29 | -79491.27 | 2018-08-22 10:02 | 2022-06-29 | 2019-11-01 | 2022-06-16
75084 | SG000432F | SGRUCKY | DEK Cable Replacement | 2515.45 |  | 2515.45 |  |  | 2613.95 | 83 | 2530.95 | 2016-05-16 10:08 | 2025-12-31 | 2017-01-01
75084 | TKY1901 | T1901TS1 | Buffington TB1 Rpl - TKY1901 | 2057552.71 |  | 2057552.71 |  |  | 2325806.63 | 2785992 | -460185.37 | 2017-12-14 15:58 | 2020-03-03 | 2018-02-01 | 2020-02-15
75084 | TKY1901 | TKY190101 | Rpl TPU Relays for TB7 | 95940.98 |  | 95940.98 |  |  | 142175.02 | 451134 | -308958.98 | 2018-07-30 10:02 | 2021-06-07 | 2018-07-01 | 2021-07-07
75084 | TKY1901 | T1901DS1 | Buffington Swgr Rpl - TKY1901 | 2317577.41 |  | 2317577.41 |  |  | 2775964.04 | 3344657 | -568692.96 | 2017-12-04 15:07 | 2020-01-14 | 2018-04-01 | 2020-02-15
75084 | TKY1901 | MX3850173 | TBC Buffington 43 UGFE Rpl - T | 7022.69 |  | 7022.69 |  |  | 7022.69 | 0 | 7022.69 | 2019-08-29 14:01 | 2021-03-01 | 2019-10-01
75084 | TKY1901 | MX3850088 | Buffington 41 UGFE Rpl - TKY1901 | 95945.28 |  | 95945.28 |  |  | 95945.28 | 12112.08 | 83833.2 | 2019-08-29 14:01 | 2020-03-30 | 2019-10-01 | 2020-02-11
75084 | TKY1901 | MX3850163 | Buffington 42 UGFE Rpl - TKY1901 | 51623.42 |  | 51623.42 |  |  | 51623.42 | 0 | 51623.42 | 2019-08-29 14:01 | 2022-03-31 | 2019-09-01
75084 | TKY2227 | T2227TL2 | F5967 Decoursey Pole Repl TL | 6007.27 |  | 6007.27 |  |  | 18264.49 | 6725687 | -6707422.51 | 2018-04-30 14:01 | 2025-10-13 | 2018-09-01
75084 | TKY2227 | T2227TL1 | F5967 Claryville Pole Repl TL | 222852.35 |  | 222852.35 |  |  | 227888.81 | 7186714 | -6958825.19 | 2018-04-30 14:01 | 2025-11-08 | 2018-09-01
75084 | TKY2227 | TKY222702 | F5967 Hwy 177 Decoursey Sub | 3133.75 |  | 3133.75 |  |  | 3133.75 | 0 | 3133.75 | 2019-04-29 14:22 | 2025-10-03 | 2019-07-01
75084 | TKY2227 | TKY222701 | F5967 Licking River Crossing Marsh | 6953.57 |  | 6953.57 |  |  | 6953.57 | 0 | 6953.57 | 2019-04-29 14:22 | 2025-10-03 | 2019-10-01
75084 | SG000792F | SG792SW | SG DEE Gen Liab Claim Anlytic - 792 | 31646.15 |  | 31646.15 |  |  | 35388.81 | 22428.18 | 12960.63 | 2018-07-25 14:52 | 2020-03-31 | 2018-07-01 | 2020-02-29
75084 | KECF20155 | KEC920155 | DEC 8920155 Oakbrook 41 | 57226.55 |  | 57226.55 |  |  | 69950.2 | 18342.29 | 51607.91 | 2015-10-26 18:05 | 2020-10-20 | 2016-09-01 | 2020-10-07
75084 | ICPRJDSTR | ICCONSTRT | Interconnection Capital Project | 509.23 |  | 509.23 |  |  | 509.23 | 1 | 508.23 | 2017-09-28 12:05 | 2030-09-30 | 2017-10-01
75084 | ICPRJDSTR | ICCONSTRD | Interconnection Capital Project | 6554.86 |  | 6554.86 |  |  | 6554.86 | 1 | 6553.86 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01
75084 | SG000795F | SG795SW | SG DEE Auto Mter Provisioning - 795 | 9513.39 |  | 9513.39 |  |  | 10811.34 | 13121 | -2309.66 | 2018-07-03 13:02 | 2020-02-15 | 2018-10-01 | 2020-03-31
75084 | KYTOOLF | TKYTOOL | Transmission Capital Tool Purchases | 14240.63 |  | 14240.63 |  |  | 168022.87 | 100 | 167922.87 | 2017-11-16 13:07 | 2050-12-31 | 2017-11-01
75084 | SG990113F | SCMCOWSKY | SG-Sec OH Wire Cor Replcmnt DMWKY | 23434.76 |  | 23434.76 |  |  | 72932 | 1 | 72931 | 2017-04-03 14:03 | 2050-12-31 | 2018-03-01
75084 | CP17TBRK | 17TB17 | Kentucky Univ Repl Bk4 Bush | -276.84 |  | -276.84 |  |  | 17112.84 | 15322.35 | 1790.49 | 2017-03-23 14:37 | 2019-03-31 | 2017-10-01 | 2018-07-31
75084 | CP17TBRK | MX6575892 | Empire Repl H1, H2, H3 bushings on | 7409.05 |  | 7409.05 |  |  | 7409.05 | 10697.21 | -3288.16 | 2017-12-07 18:02 | 2021-03-31 | 2019-11-01 | 2020-08-04
75084 | SG000770F | SG770MAS | 2018 MAS Radio | 94847.73 |  | 94847.73 |  |  | 152505.32 | 112986 | 39519.32 | 2018-02-13 17:18 | 2019-03-31 | 2018-02-01
75084 | SG000797F | SG797SVRS | SG DEE FND Upgrade - 797 | 2445.23 |  | 2445.23 |  |  | 6433.18 | 2476 | 3957.18 | 2018-08-14 17:33 | 2020-07-06 | 2018-09-01 | 2020-06-11
75084 | SG000797F | SG797SW | SG DEE FND Upgrade - 797 | 20653.69 |  | 20653.69 |  |  | 23280.21 | 18436 | 4844.21 | 2018-08-14 17:01 | 2020-07-06 | 2018-09-01 | 2020-06-11
75084 | SG000437F | SGHYDRKY | DEK Recloser Replacements | 1023.86 |  | 1023.86 |  |  | 2948.66 | 83 | 2865.66 | 2016-05-16 10:20 | 2025-12-31 | 2016-10-01
75084 | ETERRASRC | E-TERRASR | Modeling Tool e-terrasource | 51961.28 |  | 51961.28 |  |  | 72632.56 | 264721.28 | -192088.72 | 2018-08-09 12:41 | 2019-11-30 | 2018-08-01 | 2020-01-15
75084 | DEMERKY | MX7048752 | Covington Repl Cooling Fans TB1 | 749.91 |  | 749.91 |  |  | 13116.32 | 7451.28 | 5665.04 | 2018-01-23 20:20 | 2020-03-31 | 2018-01-01 | 2019-10-26
75084 | DEMERKY | MX1490615 | CAPITAL Villa TB1 replace X0, X1, X | 6843.6 |  | 6843.6 |  |  | 6843.6 | 9790.92 | -2947.32 | 2019-02-12 14:01 | 2021-03-31 | 2019-06-01 | 2020-12-30
75084 | DEMERKY | BUFF45 | Buffinton Repl Bk45 CT's | 65193.62 |  | 65193.62 |  |  | 65193.62 | 61273.46 | 3920.16 | 2019-09-06 12:00 | 2020-06-30 | 2019-09-01 | 2019-12-31
75084 | DEMERKY | MX1687352 | CAPITAL Augustine CB 324 Circuit 42 | 3422.1 |  | 3422.1 |  |  | 3422.1 | 4782.03 | -1359.93 | 2019-02-26 14:01 | 2020-03-31 | 2019-02-01 | 2020-05-27
75084 | DEMERKY | MX0655166 | CAPITAL Covington TB1 replace windi | -18.51 |  | -18.51 |  |  | -1.0658e-14 | 0 | -1.0658e-14 | 2018-11-28 10:01 | 2019-09-30 | 2018-11-01
75084 | DEMERKY | MX1565883 | CAPITAL Cold Spring Circuit 49 repl | 29060.16 |  | 29060.16 |  |  | 29060.16 | 29561.4 | -501.24 | 2019-02-14 10:01 | 2020-12-31 | 2019-02-01
75084 | DEMERKY | MX3310258 | CAPITAL White Tower replace 3 Singl | 35424.4 |  | 35424.4 |  |  | 35424.4 | 31090.41 | 4333.99 | 2019-07-11 10:02 | 2020-03-30 | 2019-07-01 | 2019-10-19
75084 | SG000444F | SGRTRKY | DEK Upgrade Livefront Transformers | 84.32 |  | 84.32 |  |  | 1737.59 | 83 | 1654.59 | 2016-05-16 10:12 | 2025-12-31 | 2016-07-01
75084 | SG000443F | SGCBINJKY | DEK Cable Injection | 219.85 |  | 219.85 |  |  | 242.25 | 83 | 159.25 | 2016-05-16 09:52 | 2025-12-31 | 2017-01-01
75084 | KCTFOOL | KCTOOL | TOOLS BLANKET | 188689.3 |  | 188689.3 |  |  | 225415.49 | 1 | 225414.49 | 2018-07-27 15:23 | 2069-04-01 | 2018-11-01
75084 | KUCF48397 | KUC348397 | RUC 10348397. Cable repla | 3912.33 |  | 3912.33 |  |  | 211705.75 | 99264.17 | 112441.58 | 2017-06-07 18:04 | 2019-03-01 | 2017-10-01 | 2019-01-27
75084 | M170111 | M17011101 | Litton Sub Prop Purch | 39279.86 |  | 39279.86 |  |  | 48839.09 | 1873674 | -1824834.91 | 2018-08-20 18:03 | 2022-02-05 | 2018-08-01 | 2021-10-09
75084 | M180077 | M18007706 | T LIne RLE - Oakbrook-Aero-Woodspoi | 165763.28 |  | 165763.28 |  |  | 165804.73 | 241552 | -75747.27 | 2018-11-08 18:02 | 2020-09-26 | 2018-12-01 | 2020-09-30
75084 | M180077 | M18007702 | Aero Substation - New Sub | 863449.03 |  | 863449.03 |  |  | 884940.19 | 9181543 | -8296602.81 | 2018-11-08 18:02 | 2021-02-27 | 2018-11-01 | 2021-03-16
75084 | M180077 | M18007704 | Oakbrook Substation | 839724.55 |  | 839724.55 |  |  | 841545 | 6995209 | -6153664 | 2018-11-08 18:02 | 2021-02-06 | 2018-12-01 | 2021-02-09
75084 | M180077 | M18007705 | 138kV Oakbrook to Aero Line | 71394.6 |  | 71394.6 |  |  | 71809.41 | 1813508 | -1741698.59 | 2018-11-08 18:02 | 2021-02-05 | 2018-12-01 | 2021-02-11
75084 | M180077 | M18007703 | 138KV F23983 Woodspoint to Aero | 359.9 |  | 359.9 |  |  | 774.71 | 0 | 774.71 | 2018-11-08 18:02 | 2020-12-27 | 2018-12-01
75084 | M180077 | M18007701 | Woodspoint Substation | 33228.91 |  | 33228.91 |  |  | 33390.94 | 0 | 33390.94 | 2018-11-08 18:02 | 2021-02-19 | 2018-12-01
75084 | M180077 | M18007708 | 138kV F6782 Florence to Woodspoint | 2.21 |  | 2.21 |  |  | 2.21 | 0 | 2.21 | 2019-02-06 14:05 | 2021-02-06 | 2019-08-01
75084 | M180077 | MX4580155 | Oakbrook D-Line Relo - M180077 | 26697.31 |  | 26697.31 |  |  | 26697.31 | 80415.64 | -53718.33 | 2019-10-30 14:01 | 2020-10-04 | 2019-11-01 | 2020-08-30
75084 | M180077 | M18007707 | Buffington Relay Upgrade for 6763 | 91679.25 |  | 91679.25 |  |  | 91679.25 | 284384.67 | -192705.42 | 2019-01-28 10:02 | 2020-10-18 | 2019-03-01 | 2020-08-20
75084 | KHRF44679 | KHR744679 | RI 9744679 6th St e/o Cra | 1030.98 |  | 1030.98 |  |  | -4.1211e-13 | 0 | -4.1211e-13 | 2016-02-05 14:05 | 2020-03-31 | 2016-02-01
75084 | DKY2131 | D2131DL3 | AM 21798304 Hands 45 | 444.56 |  | 444.56 |  |  | 19535.11 | 217039.47 | -197504.36 | 2017-07-25 13:52 | 2020-07-16 | 2017-11-01 | 2020-07-16
75084 | DKY2131 | D2131DL1 | AM 21797163 Hands 45 - DKY2131 | 486575.48 |  | 486575.48 |  |  | 606303.54 | 378745.87 | 227557.67 | 2017-07-25 13:41 | 2019-12-14 | 2017-10-01 | 2019-11-24
75084 | DKY2131 | D2131DL2 | AM 21798154 Kenton 42 | 866.82 |  | 866.82 |  |  | 866.82 | 179482.88 | -178616.06 | 2017-07-25 13:46 | 2020-11-26 | 2019-04-01 | 2020-10-07
75084 | TKY2188 | MX9749639 | TBC Augustine F5985 12kV Rbld UB | 1392.36 |  | 1392.36 |  |  | 7741.92 | 0 | 7741.92 | 2018-09-07 10:02 | 2020-12-31 | 2018-11-01
75084 | TKY2188 | T2188DS1 | Augustine_Instl 22_4MVA XTR - TKY2 | 284672.13 |  | 284672.13 |  |  | 3214001.92 | 2593925.42 | 620076.5 | 2017-07-06 13:26 | 2019-02-15 | 2017-07-01 | 2019-01-27
75084 | SG00359F | SG359SW | SG SADM Software - 359 | 21453.66 |  | 21453.66 |  |  | 29200.81 | 227863.84 | -198663.03 | 2018-09-27 06:52 | 2022-12-01 | 2018-09-01
75084 | SG00359F | SG359HW | SG SADM Hardware - 359 | 79.68 |  | 79.68 |  |  | 79.68 | 11355.38 | -11275.7 | 2018-09-28 16:48 | 2022-12-01 | 2019-01-01
75084 | SG00359F | SG359SW2 | SG SADM Software - 359 | 59665.21 |  | 59665.21 |  |  | 59665.21 | 227863.84 | -168198.63 | 2019-08-15 08:00 | 2022-12-01 | 2019-09-01
75084 | SG00359F | SG359NDD | SG SADM SW New Device Driver - 359 | 0.07 |  | 0.07 |  |  | 0.07 | 0 | 0.07 | 2018-09-28 16:17 | 2020-05-01 | 2019-07-01
75084 | DKY2132 | DKY213201 | Longbranch EKPC 138kV Loop TS | 153041.93 |  | 153041.93 |  |  | 162402.38 | 1583233.98 | -1420831.6 | 2018-06-21 10:05 | 2021-07-05 | 2018-09-01 | 2021-08-04
75084 | DKY2132 | DKY213202 | Longbranch Inst XFMR 2 DS | 275215.99 |  | 275215.99 |  |  | 275215.99 | 3128772.08 | -2853556.09 | 2018-06-21 10:05 | 2021-08-09 | 2019-02-01 | 2021-09-08
75084 | DKY2132 | DKY213203 | Longbranch EKPC CIR 6785 TL | 3906.57 |  | 3906.57 |  |  | 3906.57 | 127025.26 | -123118.69 | 2018-06-21 10:05 | 2021-09-07 | 2019-05-01 | 2021-08-04
75084 | TKY1904 | TKY190402 | Blackwell F6761 Rel Rpl | 10233.09 |  | 10233.09 |  |  | 10598.14 | 0 | 10598.14 | 2018-08-30 14:02 | 2025-12-08 | 2018-12-01
75084 | TKY1904 | TKY190401 | Buffington F6761 Rel Rpl | 15329.96 |  | 15329.96 |  |  | 15329.96 | 0 | 15329.96 | 2018-08-30 14:02 | 2025-06-20 | 2019-01-01
75084 | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | 0.06 |  | 0.06 |  |  | 51858.36 | 250000 | -198141.64 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084 | SGETOASF | SGETOAS | SG TOA Replacement Software | 112108.68 |  | 112108.68 |  |  | 559889.38 | 208124 | 351765.38 | 2015-04-06 13:58 | 2020-03-31 | 2015-05-01 | 2019-10-20
75084 | TKY1453 | T1453DL1 | Dixie 41-42 UG Exits TKY1453 | -12045.52 |  | -12045.52 |  |  | 214199.38 | 66147.36 | 148052.02 | 2017-07-06 15:45 | 2019-05-04 | 2017-07-01 | 2018-08-03
75084 | KILF64406 | KIL564406 | UG 10564406 West End 41 | 75677.45 |  | 75677.45 |  |  | 404905.77 | 462121.21 | -57215.44 | 2016-07-01 18:06 | 2017-05-28 | 2016-08-01 | 2017-04-12
75084 | TKY1611 | T1611DS1 | Augustine Swgr Repl - TKY1611 | 499818.74 |  | 499818.74 |  |  | 917956.31 | 1219379 | -301422.69 | 2017-03-23 18:02 | 2019-04-30 | 2017-03-01 | 2019-06-04
75084 | TKY1611 | MX1490565 | Augustine Bus 5 Rep - TKY1611 | 12198.23 |  | 12198.23 |  |  | 12198.23 | 2.67 | 12195.56 | 2019-02-12 14:01 | 2019-12-30 | 2019-03-01 | 2019-05-26
75084 | DKY1929 | D1929RS1 | RUSD Taylor Mill Purch Sub Property | 33102.21 |  | 33102.21 |  |  | 256048.65 | 282613 | -26564.35 | 2016-08-17 13:44 | 2019-04-04 | 2016-11-01 | 2019-03-18
75084 | DKY2018 | D2018DS1 | Dixie BK 4 - DKY2018 - DKY2018 | 291936.5 |  | 291936.5 |  |  | 2514646.84 | 3407443 | -892796.16 | 2017-06-07 07:50 | 2019-04-23 | 2017-08-01 | 2019-05-01
75084 | DKY2018 | D2018TL1 | Dixie 6764 Line Relo TL - DKY2018 | 94.87 |  | 94.87 |  |  | 19080.79 | 135025 | -115944.21 | 2017-06-07 08:15 | 2019-03-01 | 2017-11-01 | 2019-02-21
75084 | DKY2018 | D2018TS1 | Dixie 69kV Loop - DKY2018 | 36960.6 |  | 36960.6 |  |  | 491682.04 | 1145705 | -654022.96 | 2017-06-07 07:42 | 2019-04-23 | 2017-07-01 | 2019-05-01
75084 | DKY2018 | MX9533906 | Dixie Bank 4 Bus Duct Tie - DKY2018 | 2240.33 |  | 2240.33 |  |  | 17999.26 | 5192.15 | 12807.11 | 2018-08-24 10:02 | 2019-09-01 | 2018-11-01 | 2019-05-01
75084 | DKY2151 | D2151DL1 | AM 20710413 Crittenden Gen Intrc | -364.06 |  | -364.06 |  |  | 123651.86 | 75335.28 | 48316.58 | 2017-02-14 10:22 | 2018-07-31 | 2017-03-01 | 2018-03-15
75084 | DKY1912 | D1912DS1 | Covington Xtr 2_RUSD - DKY1912 | 3411.9 |  | 3411.9 |  |  | 3035951.1 | 2776527.3 | 259423.8 | 2016-08-19 09:12 | 2017-09-01 | 2016-09-01 | 2018-08-19
75084 | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 316800 |  | 316800 |  |  | 1463350.98 | 823726 | 639624.98 | 2014-02-18 | 2019-02-16 | 2014-03-01 | 2019-04-09
75084 | AMKY0960 | MX0792827 | TBC Kenton Station Exits - AMKY | 28251 |  | 28251 |  |  | 28251 | 0 | 28251 | 2018-12-07 10:01 | 2020-12-31 | 2019-01-01
75084 | TKY2009 | T2009DS1 | Kenton TB3 Rpl - TKY2009 | 566620.78 |  | 566620.78 |  |  | 2016603.88 | 1962535 | 54068.88 | 2017-04-27 14:03 | 2019-04-20 | 2017-06-01 | 2019-04-09
75084 | SG000726F | SG726SVRS | SG DEE AMI BlueCat Scale - 726 | 0.01 |  | 0.01 |  |  | 821.15 | 2783 | -1961.85 | 2017-06-29 15:36 | 2018-03-28 | 2017-07-01 | 2018-05-23
75084 | KHRF51720 | KHR851720 | RI 11851720 Rice Pike | 86.27 |  | 86.27 |  |  | 319526.75 | 75014.92 | 244511.83 | 2017-04-13 14:02 | 2018-05-01 | 2017-04-01 | 2018-07-04
75084 | SG000790F | SG790TMGR | SG DEE TUG Systems Target Manager | 14739.62 |  | 14739.62 |  |  | 36879.11 | 33758.02 | 3121.09 | 2018-04-17 15:07 | 2019-09-30 | 2018-04-01 | 2019-09-11
75084 | SG000790F | SG790VISU | SG DEE TUG Target Visualization | 5387.98 |  | 5387.98 |  |  | 16728.18 | 26181.24 | -9453.06 | 2018-04-17 17:00 | 2019-07-30 | 2018-04-01 | 2019-09-11
75084 | DKY2127 | DKY212701 | Verona New 69kV V structure - DKY21 | 943566.04 |  | 943566.04 |  |  | 1336108.08 | 726368 | 609740.08 | 2018-01-25 14:02 | 2019-10-15 | 2018-04-01 | 2019-11-15
75084 | DKY2127 | DKY212703 | Verona F6761 Loop TL - DKY2127 | 207806.66 |  | 207806.66 |  |  | 337648.07 | 860984 | -523335.93 | 2018-01-25 14:02 | 2019-10-15 | 2018-08-01 | 2019-11-15
75084 | DKY2127 | DKY212702 | Verona BK 2 - DKY2127 | 1470866.4 |  | 1470866.4 |  |  | 1671731.49 | 2299493 | -627761.51 | 2018-01-25 14:02 | 2019-10-15 | 2018-04-01 | 2019-11-15
75084 | DKY2127 | MX1674974 | Verona Bk2 - DKY2127 | 33422.36 |  | 33422.36 |  |  | 33422.36 | 24632.09 | 8790.27 | 2019-05-16 10:03 | 2019-09-12 | 2019-05-01 | 2019-11-15
75084 | TEMERKY | MX8442100 | CAPITAL Wilder CB 832 replace (6) B | -414.99 |  | -414.99 |  |  | 43783.57 | 35418.31 | 8365.26 | 2018-05-17 14:02 | 2019-03-31 | 2018-09-01 | 2019-01-17
75084 | TEMERKY | MX8897771 | CAPITAL Buffington repl 125VDC Batt | 3576.08 |  | 3576.08 |  |  | 37491 | 43032.5 | -5541.5 | 2018-06-28 10:02 | 2019-03-31 | 2018-09-01 | 2019-05-06
75084 | TEMERKY | MX8430902 | CAPITAL Wilder CB 830 replace 6 Bus | -492.66 |  | -492.66 |  |  | 56716.84 | 35418.31 | 21298.53 | 2018-05-17 10:02 | 2019-03-31 | 2018-09-01 | 2019-01-29
75084 | TEMERKY | MX8898156 | CAPITAL Buffington repl 125VDC Batt | 3560.76 |  | 3560.76 |  |  | 37475.68 | 40659.11 | -3183.43 | 2018-06-28 10:02 | 2019-03-31 | 2018-09-01 | 2019-05-06
75084 | TEMERKY | MX7600673 | CAPITAL Wilder Repl Main Battery Ba | -374.98 |  | -374.98 |  |  | 33648.97 | 41644.35 | -7995.38 | 2018-03-12 14:01 | 2019-03-31 | 2018-08-01 | 2018-12-26
75084 | DKY2217 | D2217RS1 | Petersburg Sub Site - DKY2217 | 261638.73 |  | 261638.73 |  |  | 347050.29 | 382562 | -35511.71 | 2017-05-18 18:02 | 2019-10-27 | 2017-07-01 | 2019-10-08
75084 | KHRF55669 | KHR355669 | RI 10355669 Washington St | -13232.26 |  | -13232.26 |  |  | 131284.56 | 101560.5 | 29724.06 | 2016-07-22 18:06 | 2017-07-28 | 2016-08-01 | 2017-06-20
75084 | KHRF97697 | KHR297697 | DOT 7297697 Covington 43 | -15776.3 |  | -15776.3 |  |  | 37914.68 | 39491.86 | -1577.18 | 2016-07-07 18:05 | 2018-01-01 | 2016-07-01 | 2017-10-10
75084 | KUCF61112 | KUC261112 | UG 10261112 Constance 42 | 873.02 |  | 873.02 |  |  | 804394.48 | 360637.32 | 443757.16 | 2017-01-10 14:04 | 2019-03-19 | 2017-03-01 | 2018-08-10
75084 | KETF35854 | KET135854 | DET 10135854 Villa 43 348 | 110425.32 |  | 110425.32 |  |  | 1427985.32 | 350417.94 | 1077567.38 | 2016-11-04 18:06 | 2019-06-30 | 2016-12-01 | 2019-03-12
75084 | KETF35851 | KET135851 | DET 10135851 West End 41 | 47152.6 |  | 47152.6 |  |  | 1542226.62 | 414893.11 | 1127333.51 | 2016-05-02 14:04 | 2019-06-14 | 2016-05-01 | 2019-05-25
75084 | KUCF48463 | KUC348463 | UG 10348463 Decoursey 41 | 32573.71 |  | 32573.71 |  |  | 301910.19 | 199651.38 | 102258.81 | 2017-02-15 14:04 | 2019-03-01 | 2017-07-01 | 2019-03-31
75084 | SG000598F | SG598CDEQ | SG DEE Secure Network Infrastructur | 5576.2 |  | 5576.2 |  |  | 148317.46 | 85620 | 62697.46 | 2017-09-12 16:44 | 2019-04-30 | 2017-09-01 | 2019-04-30
75084 | TKY1914 | T1914DS1 | Longbranch Rel Rpl XTR 1 - TKY1914 | 10304.79 |  | 10304.79 |  |  | 317907.12 | 247959 | 69948.12 | 2017-04-26 15:56 | 2019-06-29 | 2017-11-01 | 2019-01-22
75084 | KYRELT | KYRELT02 | F6761 Richwood eo 71/75 | -554606.93 |  | -554606.93 |  |  | -546606.12 | 1152231 | -1698837.12 | 2018-09-04 10:02 | 2019-09-04 | 2018-09-01 | 2019-08-10
75084 | CP17LTCRK | 17LTCR03 | KY Univ Repl TB4 Load Tap Changer | -889.25 |  | -889.25 |  |  | 48157.84 | 52076.25 | -3918.41 | 2017-07-20 06:50 | 2019-03-31 | 2017-10-01 | 2018-07-31
75084 | M180463 | M18046301 | EMERGENT - Cold Spring Circuit 49 - | -682.26 |  | -682.26 |  |  | 22601.62 | 48795.63 | -26194.01 | 2018-07-23 18:03 | 2019-05-08 | 2018-08-01 | 2019-02-28
75084 | M180164 | M18016401 | SPCC Upg Kenton | 212469.31 |  | 212469.31 |  |  | 249514.08 | 310204 | -60689.92 | 2018-05-02 18:02 | 2019-08-27 | 2018-06-01 | 2019-09-21
75084 | M180164 | M18016402 | Crescent Upg SPCC | 46416.27 |  | 46416.27 |  |  | 46416.27 | 71049 | -24632.73 | 2018-12-28 14:01 | 2019-11-02 | 2019-01-01 | 2019-10-31
75084 | M180346 | M18034601 | Emergent - Circuit #5962 10 Pole re | 1066639.3 |  | 1066639.3 |  |  | 1083120.97 | 2274991 | -1191870.03 | 2018-07-16 14:02 | 2019-08-10 | 2018-08-01 | 2019-07-05
75084 | M180346 | MX1419097 | F5962 X-fer UB for 1 wood to steel | 7142.11 |  | 7142.11 |  |  | 7142.11 | 3939.76 | 3202.35 | 2019-04-24 10:01 | 2020-01-23 | 2019-07-01 | 2020-01-05
75084 | M180581 | M18058101 | EMERGENCY - Replace Buffington TB 4 | 181069.81 |  | 181069.81 |  |  | 597528.91 | 736486.42 | -138957.51 | 2018-11-19 14:01 | 2019-04-30 | 2018-11-01 | 2019-04-25
75084 | 75084 | KMTROWS | KY - Meters-AMI-Self Contained | 368226.65 |  | 368226.65 |  |  | 369090.78 | 99863.96 | 269226.82 | 2018-11-02 18:04 | 2026-03-31 | 2018-12-01
75084 | 75084 | EMETERKY | Electric Meter Blanket | 631816.58 |  | 631816.58 |  |  | 2843239.66 | 295697.19 | 2547542.47 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01 | 2019-05-14
75084 | 75084 | MX2586486 | OLD TWENHOFEL MIDDLE SCHOOL | -193.71 |  | -193.71 |  |  | 14233.01 | 37465.22 | -23232.21 | 2018-01-09 14:01 | 2018-02-16 | 2018-01-01 | 2018-08-23
75084 | 75084 | KMTROWT | KY - Meters-AMI-T Rated | 110447.44 |  | 110447.44 |  |  | 110447.44 | 11182.68 | 99264.76 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | 75084 | KMTRNOT | KY - Meters-Not AMI- T Rated | 55003.59 |  | 55003.59 |  |  | 55003.59 | 520.12 | 54483.47 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | 75084 | KMTRNOS | KY Meters-Not AMI-SelfContained | 4730.03 |  | 4730.03 |  |  | 4730.03 | 5461.31 | -731.28 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | M190085 | M19008501 | EMERGENCY - Kenton Replace TB 1 | 1443089.28 |  | 1443089.28 |  |  | 1443089.28 | 1830863 | -387773.72 | 2019-04-10 18:01 | 2019-10-28 | 2019-04-01 | 2019-10-25
75084 | KFSF45125 | KFS845125 | RFS 11845125 Claryville 42 | 113283.65 |  | 113283.65 |  |  | 113283.65 | 87341.66 | 25941.99 | 2017-06-28 14:02 | 2020-02-27 | 2019-02-01 | 2020-02-12
75084 | M180095 | M18009501 | Kenton XTR 1 Rpl | 186306.14 |  | 186306.14 |  |  | 186306.14 | 2336966 | -2150659.86 | 2019-03-07 10:01 | 2023-12-29 | 2019-03-01
75084 | SG000764F | SG764BLK1 | DEK 2019-2020 Microwave Upgrades | 478392.87 |  | 478392.87 |  |  | 478392.87 | 217462.26 | 260930.61 | 2019-02-25 09:15 | 2028-03-31 | 2019-04-01
75084 | SG000764F | SG764MAT1 | DEK 2019-2020 Microwave Upgrades | 43692.41 |  | 43692.41 |  |  | 43692.41 | 217462.26 | -173769.85 | 2019-02-25 08:41 | 2028-03-31 | 2019-10-01
75084 | TKY1999 | TKY199903 | Constance Bus 1 Swgr CB Rpl | 92959.58 |  | 92959.58 |  |  | 92959.58 | 2390612 | -2297652.42 | 2018-07-06 10:02 | 2024-06-21 | 2019-02-01
75084 | TKY1999 | TKY199902 | Constance 69kV TLS | 16695.75 |  | 16695.75 |  |  | 16695.75 | 0 | 16695.75 | 2018-07-06 10:02 | 2024-06-10 | 2019-02-01
75084 | TKY1999 | TKY199904 | Constance 138kV switches | 2.03 |  | 2.03 |  |  | 2.03 | 0 | 2.03 | 2019-03-07 10:05 | 2021-05-25 | 2019-03-01
75084 | M190055 | M19005501 | Beaver Cambium Radio Upgrades | 143416.78 |  | 143416.78 |  |  | 143416.78 | 245834 | -102417.22 | 2019-06-06 11:17 | 2020-03-10 | 2019-06-01 | 2020-03-05
75084 | M190055 | M19005503 | Cold Spring Cambium Upgrade | 69780.43 |  | 69780.43 |  |  | 69780.43 | 114679 | -44898.57 | 2019-06-06 11:02 | 2020-04-14 | 2019-06-01 | 2020-04-30
75084 | M190055 | M19005502 | Blackwell Cambium Radio Upgrade | 80190.14 |  | 80190.14 |  |  | 80190.14 | 117617 | -37426.86 | 2019-06-06 11:17 | 2020-04-13 | 2019-06-01 | 2020-04-15
75084 | DKY2125 | DKY212501 | New 69kV V structure | 32979.24 |  | 32979.24 |  |  | 32979.24 | 904914.56 | -871935.32 | 2019-02-22 10:01 | 2022-02-15 | 2019-03-01 | 2022-03-16
75084 | DKY2125 | DKY212502 | Grant Metering | 10888.59 |  | 10888.59 |  |  | 10888.59 | 918433 | -907544.41 | 2019-02-22 10:01 | 2021-10-08 | 2019-08-01 | 2021-07-07
75084 | DKY2125 | DKY212503 | Dry Ridge BK 2 | 40890.45 |  | 40890.45 |  |  | 40890.45 | 1629020 | -1588129.55 | 2019-02-22 10:01 | 2022-02-15 | 2019-04-01 | 2022-03-16
75084 | DKY2125 | DKY212504 | Dry Ridge F3568 Loop TL | 8844.95 |  | 8844.95 |  |  | 8844.95 | 166179.8 | -157334.85 | 2019-02-22 10:01 | 2022-02-15 | 2019-06-01 | 2022-03-16
75084 | SG000909F | SMODEMKY | DEK Modem Replacement | 3899.57 |  | 3899.57 |  |  | 3899.57 | 1 | 3898.57 | 2018-12-14 11:31 | 2068-12-31 | 2019-03-01
75084 | SG990124F | SGRXRKY | SG - Transformer Retrofit DMWKY | 3290.58 |  | 3290.58 |  |  | 3290.58 | 1 | 3289.58 | 2017-04-06 08:06 | 2050-12-31 | 2019-02-01
75084 | DKYHW2672 | MX3147286 | TBC Hebron 43 45 UG Cable - DKYHW26 | 308.93 |  | 308.93 |  |  | 308.93 | 1796.56 | -1487.63 | 2019-06-26 14:01 | 2021-07-01 | 2019-08-01
75084 | DKYHW2672 | MX3147011 | Hebron OH Work - DKYHW2672 | 308.93 |  | 308.93 |  |  | 308.93 | 227039.51 | -226730.58 | 2019-06-26 14:01 | 2021-12-29 | 2019-08-01 | 2021-11-21
75084 | DKYHW2672 | MX3146693 | Hebron Pole Inst - DKYHW2672 | 155147.94 |  | 155147.94 |  |  | 155147.94 | 63734.56 | 91413.38 | 2019-06-26 14:01 | 2020-09-28 | 2019-07-01 | 2020-07-22
75084 | DKYHW2672 | MX3147246 | Hebron 41 42 UG Cable - DKYHW2672 | 651.17 |  | 651.17 |  |  | 651.17 | 464106.03 | -463454.86 | 2019-06-26 14:01 | 2020-09-29 | 2019-08-01 | 2020-10-07
75084 | DKYHW2672 | MX3147307 | Hebron 41 42 OH Relo - DKYHW2672 | 1716.28 |  | 1716.28 |  |  | 1716.28 | 40647.45 | -38931.17 | 2019-06-26 14:01 | 2020-10-13 | 2019-08-01 | 2020-10-19
75084 | M190226 | M19022601 | 138 kV F23983 Woodspoint to Aero | 244990.84 |  | 244990.84 |  |  | 244990.84 | 5133016 | -4888025.16 | 2019-10-08 14:01 | 2023-03-04 | 2019-11-01
75084 | M190270 | M19027001 | Emergency - Replace Limaburg TB 1 A | 913816.94 |  | 913816.94 |  |  | 913816.94 | 1081592 | -167775.06 | 2019-10-24 10:13 | 2020-03-15 | 2019-10-01 | 2020-03-20
75084 | DKY2447 | MX1424546 | Constance 43 LN Ext DKY2447 | 10560.52 |  | 10560.52 |  |  | 10560.52 | 1616077.2 | -1605516.68 | 2019-06-17 18:02 | 2021-10-18 | 2019-09-01 | 2021-10-17
75084 | SG000723F | SG723SVR | DEE AMI Operations Project | 6943.75 |  | 6943.75 |  |  | 6943.75 | 1 | 6942.75 | 2019-12-20 15:16 | 2025-12-31 | 2019-12-01 | 2020-08-26
75084 | SG000842F | SG842RCR | DEK Reclosure Control Replacement | 560071.29 |  | 560071.29 |  |  | 560071.29 | 1062774 | -502702.71 | 2018-10-16 17:02 | 2024-03-31 | 2019-03-01
75084 | SGGIPMGTF | SGGIPMGT | SG GIP Management Allocation | 605.58 |  | 605.58 |  |  | 605.58 | 0 | 605.58 | 2019-03-20 16:03 | 2030-12-31 | 2019-04-01
75084 | M180378 | M18037801 | Richwood BK 4- Install | 8216.63 |  | 8216.63 |  |  | 8216.63 | 2360214.13 | -2351997.5 | 2019-09-12 14:01 | 2023-07-21 | 2019-10-01
75084 | M180378 | M18037802 | Richwood BK 4- Mod Xmission Structu | 1907.1 |  | 1907.1 |  |  | 1907.1 | 523888.35 | -521981.25 | 2019-09-16 18:01 | 2023-08-04 | 2019-10-01
75084 | TOT00003 | WEBFG | WebFG Replacement | 486.08 |  | 486.08 |  |  | 486.08 | 79688 | -79201.92 | 2019-10-18 07:58 | 2022-03-31 | 2019-10-01 | 2022-04-14
75084 | M190087 | M19008701 | Emergent - Circuit 6763 Replace ABS | 8064.67 |  | 8064.67 |  |  | 8064.67 | 340853.09 | -332788.42 | 2019-07-10 14:09 | 2020-09-30 | 2019-08-01 | 2020-09-26
75084 | SG000983F | SG983TMT2 | SG DEE TMT Phase II | 4525.56 |  | 4525.56 |  |  | 4525.56 | 44390.63 | -39865.07 | 2019-08-14 14:04 | 2021-11-02 | 2019-09-01 | 2022-01-01
75084 | SG000719F | SG719SW | SG DEE Auto Net Metering Solu - 719 | 7610.3 |  | 7610.3 |  |  | 7610.3 | 8535.73 | -925.43 | 2018-08-27 09:35 | 2020-03-31 | 2019-05-01 | 2020-03-07
75084 | M190153 | M19015301 | GLT F6763 Rpl - Limaburg to Oakbroo | 10893.87 |  | 10893.87 |  |  | 10893.87 | 647545.95 | -636652.08 | 2019-10-03 14:14 | 2021-01-05 | 2019-10-01 | 2020-10-08
75084 | M190153 | M19015302 | GLT F6763 Rpl Oakbrook to Swi#406 | 6477.94 |  | 6477.94 |  |  | 6477.94 | 2661488.14 | -2655010.2 | 2019-10-04 10:01 | 2021-02-06 | 2019-11-01 | 2020-10-08
75084 | M190153 | M19015304 | GLT F6763 Rpl - Empire to Dixie | 2644.57 |  | 2644.57 |  |  | 2644.57 | 307070 | -304425.43 | 2019-10-04 10:01 | 2021-05-14 | 2019-11-01 | 2021-06-06
75084 | M190153 | M19015303 | GLT F6763 Rpl - Swi #406 to Empire | 4333.06 |  | 4333.06 |  |  | 4333.06 | 714261 | -709927.94 | 2019-10-04 10:01 | 2021-05-21 | 2019-10-01 | 2021-05-25
75084 | M190153 | M19015305 | GLT F6761 Rpl - Swi #387 to Buffing | 3433.67 |  | 3433.67 |  |  | 3433.67 | 687406 | -683972.33 | 2019-10-04 10:01 | 2021-01-15 | 2019-10-01 | 2021-02-06
75084 | M190153 | M19015306 | GLT F6763 Rpl - Swi#387 to Buffingt | 2068 |  | 2068 |  |  | 2068 | 501611.81 | -499543.81 | 2019-10-04 10:01 | 2021-02-07 | 2019-11-01 | 2021-02-04
75084 | M180553 | M18055301 | Woodspoint Sub Purc Site | 9510.81 |  | 9510.81 |  |  | 9510.81 | 1597931 | -1588420.19 | 2018-10-29 10:05 | 2020-12-31 | 2019-01-01
75084 | DKY2637 | MX1425791 | TBC Limaburg 41 & 43 Reco CVG DKY26 | 3855.49 |  | 3855.49 |  |  | 3855.49 | 0 | 3855.49 | 2019-10-02 14:01 | 2023-12-27 | 2019-11-01
75084 | DKY2618 | MX3629351 | Areo Sub Exits - DKY2618 | 379.71 |  | 379.71 |  |  | 379.71 | 164617.64 | -164237.93 | 2019-09-23 18:01 | 2021-03-31 | 2019-10-01 | 2020-12-29
75084 | SG000838F | SG838BTR | DEK EOL Power Supplies | 44102.49 |  | 44102.49 |  |  | 44102.49 | 81484 | -37381.51 | 2019-01-22 08:29 | 2022-03-31 | 2019-04-01
75084 | SG990022F | SRRRKY | SG - Reclosure Replacements DMWKY | 11054.97 |  | 11054.97 |  |  | 11054.97 | 1 | 11053.97 | 2017-04-04 13:14 | 2050-12-31 | 2019-03-01
75084 | SG000685F | MX0000778 | 2020 DEK TUG 25998217 JACKSON RD PH | 5212.43 |  | 5212.43 |  |  | 5212.43 | 0 | 5212.43 | 2019-09-16 14:01 | 2030-10-18 | 2019-09-01
75084 | SG000685F | MX0000476 | 2021 TUG 2606514 N TALBOT AVE PHASE | 7760.17 |  | 7760.17 |  |  | 7760.17 | 0 | 7760.17 | 2019-05-31 14:01 | 2022-10-20 | 2019-07-01
75084 | SG000685F | MX0000477 | 2020 TUG 26062514 N TALBOT AVE PHAS | 2711.41 |  | 2711.41 |  |  | 2711.41 | 0 | 2711.41 | 2019-05-31 14:01 | 2022-11-10 | 2019-08-01
75084 | SG000685F | MX0000782 | 2020 DEK TUG 25998217 JACKSON RD PH | 5527.89 |  | 5527.89 |  |  | 5527.89 | 0 | 5527.89 | 2019-09-16 14:01 | 2030-11-15 | 2019-09-01
75084 | SG000685F | MX0000780 | 2020 DEK TUG 25998217 JACKSON RD PH | 6304.85 |  | 6304.85 |  |  | 6304.85 | 0 | 6304.85 | 2019-09-16 14:01 | 2030-10-18 | 2019-09-01
75084 | SG000685F | MX0000632 | TBC 2020 TUG 25990991 Tonya Dr Ins | 833.53 |  | 833.53 |  |  | 833.53 | 0 | 833.53 | 2019-06-19 14:01 | 2022-09-01 | 2019-08-01
75084 | SG000685F | MX0000704 | 2020 TUG 25998562 GREENBRIAR AVE PH | 13904.71 |  | 13904.71 |  |  | 13904.71 | 0 | 13904.71 | 2019-09-16 14:01 | 2030-10-07 | 2019-09-01
75084 | M180388 | M18038801 | Aero Dist Substation | 505782.08 |  | 505782.08 |  |  | 505782.08 | 6981494 | -6475711.92 | 2019-03-27 14:01 | 2021-03-01 | 2019-04-01 | 2021-03-16
75084 | M190271 | M19027101 | Emergency- Replace Augustine TB 3 | 808287.65 |  | 808287.65 |  |  | 808287.65 | 764123 | 44164.65 | 2019-10-30 14:11 | 2020-03-29 | 2019-11-01 | 2020-04-22
75084 | TOT00002 | MWEMSKY | Midwest EMS Replacement Project | 126951.1 |  | 126951.1 |  |  | 126951.1 | 679701.48 | -552750.38 | 2019-07-22 08:59 | 2023-03-30 | 2019-09-01
75084 | SG001006F | SG1006SW | DEK FISR Pre-Scale - Software | 1782.57 |  | 1782.57 |  |  | 1782.57 | 384800 | -383017.43 | 2019-10-22 10:44 | 2022-03-31 | 2019-10-01 | 2022-02-09
75084 | SG990033F | SPOLIRKY | SG-Emergy Pole Replace Insp DMWKY | 155850.24 |  | 155850.24 |  |  | 155850.24 | 1 | 155849.24 | 2017-04-03 15:44 | 2050-12-31 | 2019-10-01
75084 | M190167 | M19016702 | Claryville 2019 DMVPN Upgrade | 41.76 |  | 41.76 |  |  | 41.76 | 85223 | -85181.24 | 2019-08-13 18:01 | 2021-03-31 | 2019-08-01 | 2020-04-29
75084 | M190167 | M19016703 | Thomas More 2019 DMVPN Upgrade | 14.05 |  | 14.05 |  |  | 14.05 | 0 | 14.05 | 2019-08-13 18:01 | 2021-03-12 | 2019-08-01
75084 | M190167 | M19016701 | Limaburg 2019 DMVPN Upgrade | 24.76 |  | 24.76 |  |  | 24.76 | 9857.93 | -9833.17 | 2019-08-13 18:01 | 2020-08-01 | 2019-08-01 | 2020-04-09
75084 | M190167 | M19016704 | Villa 2019 DMVPN Upgrade | 1.32 |  | 1.32 |  |  | 1.32 | 0 | 1.32 | 2019-08-13 18:01 | 2021-03-12 | 2019-08-01
75084 | DKY2210 | D2210DL1 | AM 21520192 Donaldson 45 | 209185.11 |  | 209185.11 |  |  | 209185.11 | 503139.5 | -293954.39 | 2017-06-15 14:35 | 2020-08-15 | 2019-05-01 | 2020-08-12
75084 | DKY2210 | MX4120786 | TBC Donaldson 47 UG Conduit SOG - D | 722.83 |  | 722.83 |  |  | 722.83 | 0 | 722.83 | 2019-09-23 14:01 | 2020-12-31 | 2019-12-01
75084 | DKY2210 | MX4121529 | Donaldson 43 Reco SOG - DKY2210 | 2059.68 |  | 2059.68 |  |  | 2059.68 | 101138.5 | -99078.82 | 2019-09-23 14:01 | 2021-03-31 | 2019-12-01 | 2021-03-15
75084 | DKY2210 | MX4127002 | Donaldson 47 UG Cable SOG - DKY2210 | 1330.42 |  | 1330.42 |  |  | 1330.42 | 24685.12 | -23354.7 | 2019-09-23 14:01 | 2020-09-13 | 2019-12-01 | 2020-08-25
75084 | DKY2645 | MX1975019 | Wilder 43 Ln Ext- DKY2645 | 1800.57 |  | 1800.57 |  |  | 1800.57 | 369283.68 | -367483.11 | 2019-07-25 14:01 | 2023-03-31 | 2019-10-01
75084 | MDTMTR20 | MDTDEKMTR | Install Win 7 Panasonic Toughbooks | 16649.75 |  | 16649.75 |  |  | 16649.75 | 27874 | -11224.25 | 2019-10-11 08:47 | 2020-06-30 | 2019-10-01 | 2020-03-31
75084 | DKY2451 | MX1425894 | Hebron 45 LN Ext DKY2451 | 4238.22 |  | 4238.22 |  |  | 4238.22 | 325392.17 | -321153.95 | 2019-10-02 14:01 | 2022-03-22 | 2019-12-01 | 2022-03-15
75084 | SG000791F | SG791SVR | SG DEE Oracle Upgrade Servers | 2.48 |  | 2.48 |  |  | 2.48 | 37212.15 | -37209.67 | 2018-08-07 13:32 | 2020-05-31 | 2019-05-01 | 2020-02-10
75084 | M190086 | M19008601 | Emergent - Circuit 6763 Replace ABS | 4866.44 |  | 4866.44 |  |  | 4866.44 | 228764.57 | -223898.13 | 2019-08-30 14:01 | 2020-09-26 | 2019-09-01 | 2020-09-26
75084 | M190220 | M19022001 | Emergent Repl ABS 817 F15268 T-Line | 18442.96 |  | 18442.96 |  |  | 18442.96 | 311345.37 | -292902.41 | 2019-09-25 14:01 | 2020-05-01 | 2019-10-01 | 2020-06-30
75084 | M190220 | M19022002 | Emergent-Constance Sub Rpl ABS 817 | 1207.25 |  | 1207.25 |  |  | 1207.25 | 31370.28 | -30163.03 | 2019-11-07 14:01 | 2020-05-01 | 2019-11-01 | 2020-06-03
75084 | DKY2214 | MX1424737 | Constance 43 SG DKY2214 | 1623.64 |  | 1623.64 |  |  | 1623.64 | 122686.92 | -121063.28 | 2019-07-25 14:01 | 2021-10-06 | 2019-09-01 | 2021-09-28
75084 | SG000502F | SG502SW | SG DEE Device Entry Alert Sys - 502 | 156.26 |  | 156.26 |  |  | 156.26 | 69968.07 | -69811.81 | 2018-08-31 13:48 | 2020-12-31 | 2019-01-01 | 2020-09-30
75084 | M190190 | M19019001 | Taylor Mill Sub PT II | 8453.97 |  | 8453.97 |  |  | 8453.97 | 2350000 | -2341546.03 | 2019-08-20 14:01 | 2021-02-13 | 2019-08-01 | 2021-03-11
75084 | 75084RR | KNANC | Neighborhood Area Ntwk Replacements | 42196.27 |  | 42196.27 |  |  | 42196.27 | 0 | 42196.27 | 2017-03-27 14:46 | 2067-04-01 | 2019-05-01
75084 | SG990086F | SPOLOTHKY | SG-Oth UOP Repl Thru Pol Insp DMWKY | 662.86 |  | 662.86 |  |  | 662.86 | 1 | 661.86 | 2017-04-04 08:01 | 2050-12-31 | 2019-04-01
75085 | CUSTCONN | 315986A | Customer Connect - Core | 1655866.18 |  | 1655866.18 |  |  | 2245133.6 | 3313201.21 | -1068067.61 | 2017-08-10 10:40 | 2022-12-05 | 2017-08-01 | 2022-07-06
75085 | CUSTCONN | 315986B | Customer Connect- Analytics | -40.82 |  | -40.82 |  |  | 155611.92 | 99396.72 | 56215.2 | 2017-08-10 13:07 | 2018-09-30 | 2017-08-01 | 2018-09-30
75085 | CUSTCONN | 315986C | Customer Connect- Release 2 | 123826.45 |  | 123826.45 |  |  | 430981.16 | 267635.67 | 163345.49 | 2017-08-10 14:25 | 2019-05-28 | 2017-08-01 | 2019-06-18
75085 | CUSTCONN | 315986D | Customer Connect- Release 3 | 124020.57 |  | 124020.57 |  |  | 276026.84 | 399313.16 | -123286.32 | 2017-08-10 15:24 | 2019-12-30 | 2017-08-01 | 2019-12-31
75085 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 135305.12 |  | 135305.12 |  |  | 228054.43 | 166907.14 | 61147.29 | 2017-08-11 10:38 | 2020-09-01 | 2017-08-01 | 2020-09-01
75085 | CUSTCONN | 315986HW1 | Customer Connect- Hardware Proj 1 | 182.65 |  | 182.65 |  |  | 239080.45 | 62909 | 176171.45 | 2017-09-05 18:39 | 2018-10-01 | 2017-09-01 | 2018-10-01
75085 | CUSTCONN | 315986HW4 | Customer Connect- Hardware Proj 2 | 92633.49 |  | 92633.49 |  |  | 191224.68 | 76896 | 114328.68 | 2018-08-31 12:26 | 2019-06-01 | 2018-08-01 | 2019-08-01
75085 | CUSTCONN | 315986HW5 | Customer Connect- Hardware Proj 3 | 90537.95 |  | 90537.95 |  |  | 90537.95 | 61250 | 29287.95 | 2019-09-03 14:42 | 2020-06-01 | 2019-09-01 | 2020-06-15
75085 | FPIT | PCTA481AU | PCTA481AU CDP Authenticated Site | 220.74 |  | 220.74 |  |  | 2715461.94 | 1159204 | 1556257.94 | 2016-02-11 12:16 | 2018-10-31 | 2016-03-01 | 2018-10-31
75085 | FPIT | 342284C | Outage Detection Platform | 45172.8 |  | 45172.8 |  |  | 72924.01 | 9664.27 | 63259.74 | 2017-09-06 16:54 | 2020-04-30 | 2017-09-01 | 2020-04-30
75085 | FPIT | 344368 | Customer Transformer Mapping Engine | 102832.11 |  | 102832.11 |  |  | 128041.28 | 22936.91 | 105104.37 | 2017-10-23 13:29 | 2020-03-31 | 2017-11-01 | 2020-03-31
75085 | FPIT | 307482 | Customer Mobile App | 3220.26 |  | 3220.26 |  |  | 47151.33 | 28598 | 18553.33 | 2017-05-08 15:19 | 2019-06-25 | 2017-06-01 | 2019-06-25
75085 | FPIT | 344598001 | Duke Customer IVR Replacement | 164666.61 |  | 164666.61 |  |  | 203776.55 | 282698 | -78921.45 | 2018-04-10 15:20 | 2020-02-12 | 2018-04-01 | 2020-01-30
75085 | FPIT | 336593019 | New Call Ctr SIP Trunks | 7517.78 |  | 7517.78 |  |  | 21043.99 | 14982 | 6061.99 | 2018-03-14 16:41 | 2020-03-31 | 2018-03-01 | 2020-03-31
75085 | FPIT | 307482001 | Customer Mobile App - Phase 2 | 34356.56 |  | 34356.56 |  |  | 34356.56 | 40467 | -6110.44 | 2018-12-28 09:07 | 2020-03-31 | 2019-01-01 | 2020-03-20
75085 | FPIT | 344637001 | MW Test Data Enhancement | -1.99 |  | -1.99 |  |  | 0.07 | 2622 | -2621.93 | 2018-03-14 10:39 | 2018-12-28 | 2018-03-01 | 2018-12-28
75080 | FPIT | 307600DEK | BASS Program- Phase 1 Release 3 KY | 1187.53 |  | 1187.53 |  |  | 50763.33 | 156838 | -106074.67 | 2017-12-11 12:35 | 2019-02-15 | 2018-04-01 | 2019-01-15
75080 | FPIT | 336593EOC | Install CISCO Switches & Rtrs | -389.97 |  | -389.97 |  |  | 49081.46 | 88500 | -39418.54 | 2017-07-07 14:43 | 2018-06-30 | 2017-07-01 | 2018-05-31
75080 | FPIT | 354154SG1 | DXT Spend Governance | 112384.59 |  | 112384.59 |  |  | 158642.73 | 62115 | 96527.73 | 2018-11-26 13:36 | 2020-03-31 | 2018-11-01 | 2020-03-17
75080 | FPIT | 323326002 | 2018 Workstation Refresh-Phase 2-Q1 | 1047.22 |  | 1047.22 |  |  | 330939.56 | 86615 | 244324.56 | 2018-01-17 13:39 | 2018-12-29 | 2018-02-01 | 2018-12-31
75080 | FPIT | 323326005 | Workstation Refresh 2017-2019 | 4875.56 |  | 4875.56 |  |  | 14116.87 | 212265 | -198148.13 | 2018-06-19 16:01 | 2019-06-30 | 2018-07-01 | 2019-03-31
75080 | FPIT | 359140001 | ISOP Data Management | 24369.97 |  | 24369.97 |  |  | 24369.97 | 169292 | -144922.03 | 2018-12-19 15:02 | 2023-03-29 | 2019-01-01
75080 | FPIT | 354154001 | DXT Agile Product Team | 101783.79 |  | 101783.79 |  |  | 102229.84 | 100336 | 1893.84 | 2018-11-13 13:30 | 2020-03-31 | 2018-12-01 | 2020-03-31
75080 | FPIT | 348527007 | My Duke Replacement | 128197.02 |  | 128197.02 |  |  | 128197.02 | 103515 | 24682.02 | 2019-10-02 08:27 | 2020-03-31 | 2019-10-01 | 2020-02-15
75080 | FPIT | 354299001 | Outage Map Refresh | 37919.84 |  | 37919.84 |  |  | 37919.84 | 41964.72 | -4044.88 | 2019-10-02 10:46 | 2020-04-30 | 2019-10-01 | 2020-04-30
75080 | FPIT | CY190HW13 | IT-OT ANA Workstream HW | 58407.81 |  | 58407.81 |  |  | 58407.81 | 2784426 | -2726018.19 | 2019-12-05 14:44 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | 307600007 | BASS - Ground Water Sample | 50258.91 |  | 50258.91 |  |  | 51044.59 | 59475 | -8430.41 | 2018-08-14 10:14 | 2020-02-08 | 2018-11-01 | 2020-02-15
75080 | FPIT | CY190SW13 | IT-OT ANA Workstream SW | 12235 |  | 12235 |  |  | 12235 | 885364 | -873129 | 2019-12-05 14:32 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | 323326008 | Workstation Refresh 2017-2019 | 65394.47 |  | 65394.47 |  |  | 65394.47 | 70972 | -5577.53 | 2018-12-19 09:22 | 2020-03-03 | 2019-01-01 | 2020-03-03
75080 | FPIT | 359688001 | ISOP Spend Governance Non-Project W | 236.79 |  | 236.79 |  |  | 12917.59 | 18130 | -5212.41 | 2018-12-13 11:24 | 2019-07-30 | 2018-12-01 | 2019-07-31
75080 | RESBLDKY | KMW170248 | Ice Machine Replacement | -492.41 |  | -492.41 |  |  | 25126.74 | 30588 | -5461.26 | 2017-10-19 11:23 | 2018-03-31 | 2017-11-01 | 2018-03-28
75080 | RESBLDKY | KMW100007 | Water Heater Replacement | 11.74 |  | 11.74 |  |  | 19291.74 | 21250 | -1958.26 | 2018-11-14 15:55 | 2019-07-14 | 2018-12-01 | 2019-03-14
75080 | RESBLDKY | KMW190104 | Augustine Complete Roofing Replace | 1257992.84 |  | 1257992.84 |  |  | 1257992.84 | 1284525 | -26532.16 | 2019-04-23 14:51 | 2020-04-30 | 2019-05-01 | 2020-02-26
75080 | RESBLDKY | KMW190160 | Erlanger Operations Center Complete | 1371640.04 |  | 1371640.04 |  |  | 1371640.04 | 1386095 | -14454.96 | 2019-07-03 16:01 | 2020-04-29 | 2019-07-01 | 2020-03-31
75080 | RESBLDKY | KMW190103 | Erlanger Ops Center Paving P-3 | 288101.83 |  | 288101.83 |  |  | 288101.83 | 73343 | 214758.83 | 2019-05-01 12:20 | 2020-01-29 | 2019-05-01 | 2020-01-31
75080 | RESBLDKY | KMW190074 | Erlanger HVAC System Replacement | 7477.35 |  | 7477.35 |  |  | 7477.35 | 7694 | -216.65 | 2019-03-07 16:11 | 2019-12-03 | 2019-03-01 | 2019-07-17
75080 | RESBLDKY | KMW190359 | Erlanger Transformer Replacement | 7343.69 |  | 7343.69 |  |  | 7343.69 | 7528 | -184.31 | 2019-08-02 09:02 | 2020-03-29 | 2019-12-01 | 2020-01-30
75080 | RESBLDKY | KMW000182 | Complete Furniture Assemby | 10308.87 |  | 10308.87 |  |  | 10308.87 | 9791 | 517.87 | 2019-04-09 10:58 | 2019-10-12 | 2019-06-01 | 2019-08-20
75080 | RESBLDKY | KMW190198 | 1 Furniture Assembly for Erlanger O | 5350.01 |  | 5350.01 |  |  | 5350.01 | 5432 | -81.99 | 2019-05-07 12:10 | 2019-11-07 | 2019-06-01 | 2019-09-06
75080 | RESBLDKY | KMW000106 | Electronic furniture assembly | 3040.84 |  | 3040.84 |  |  | 3040.84 | 2604 | 436.84 | 2019-01-11 14:27 | 2019-07-17 | 2019-03-01 | 2019-05-08
75080 | RESBLDKY | KMW190234 | HVAC Replacement | 10395.94 |  | 10395.94 |  |  | 10395.94 | 16961 | -6565.06 | 2019-05-29 10:05 | 2019-10-30 | 2019-10-01 | 10/19/2019
75080 | FMWAVEKY | NINT732B | Butler Microwave pre-fab building | 10624.48 |  | 10624.48 |  |  | 123818 | 113900 | 9918 | 2017-02-03 15:17 | 2018-11-30 | 2017-03-01 | 2018-11-11
75080 | RESMDKY | KMW18289B | Acquisition of 1 building at 1262 C | 5025.07 |  | 5025.07 |  |  | 2738278.31 | 2802750 | -64471.69 | 2018-10-24 09:35 | 2019-03-31 | 2018-10-01 | 2019-03-19
75080 | RESMDKY | KMW18289A | Acquisition of 6.68 acres at 1262 C | 5796 |  | 5796 |  |  | 887430.27 | 934250 | -46819.73 | 2018-10-24 09:52 | 2019-03-31 | 2018-10-01 | 2019-03-19
75080 | MWAVE | 348643007 | CIOPS RFID Asset Tracking DEK | -2918.72 |  | -2918.72 |  |  | 52.87 | 59330 | -59277.13 | 2018-04-20 16:08 | 2020-03-01 | 2018-06-01 | 2020-04-01
75080 | MWAVE | 336593050 | Open Gear Jurisdictional | -164.62 |  | -164.62 |  |  | 6.3505e-14 | 31991 | -31991 | 2018-07-26 09:31 | 2019-08-15 | 2018-08-01
75080 | CAPBUDK | DISOHDK | DEK Distribution Overhead Pool | 122.55 |  | 122.55 |  |  | 8417.06 | 0 | 8417.06 | 2017-07-31 11:00 | 2026-03-31 | 2018-01-01
75080 | FLKY0249G | DUKTKYE19 | Fleet Off-Road Vehicles - KY | 350857.41 |  | 350857.41 |  |  | 350857.41 | 20000 | 330857.41 | 2019-01-11 10:56 | 2050-12-31 | 2019-03-01
75080 | ASSETCPAK | CPADEK | DEK Capital CPA ALLOCATION | -470.71 |  | -470.71 |  |  | 7.75 | 1 | 6.75 | 2018-01-31 08:58 | 2050-12-31 | 2018-03-01
75080 | DIGSIGN | DIGSI | Digital Signs | 3242.71 |  | 3242.71 |  |  | 3242.71 | 150000 | -146757.29 | 2019-01-25 10:08 | 2020-01-01 | 2019-03-01 | 2020-01-15
75080 | SG001010F | SG1010Z1L | DEK LMR - Ohio/Kentucky - Erlanger | 337702.87 |  | 337702.87 |  |  | 337702.87 | 5597208.53 | -5259505.66 | 2019-11-01 12:38 | 2024-03-31 | 2019-11-01
75080 | SG001010F | SG1010Z1O | DEK LMR - Ohio/Kentucky - Erlanger | 64916.22 |  | 64916.22 |  |  | 64916.22 | 1399302.13 | -1334385.91 | 2019-11-01 12:28 | 2024-03-31 | 2019-11-01
75080 | MRTP2019 | 355813001 | 2019 Kentucky Optical EOL Replaceme | 96587.28 |  | 96587.28 |  |  | 96587.28 | 81990 | 14597.28 | 2018-12-19 15:26 | 2020-03-30 | 2019-04-01 | 2020-03-31
75080 | GENERIC | INCENTIVE | Incentive True-up | -270.66 |  | -270.66 |  |  | -270.66 | 0 | -270.66 | 2019-11-22 10:36 | 2050-12-31 | 2019-11-01
75080 | TOOLFA2 | TOOLKTY | TOOLS & EQUIPMENT | 1212.81 |  | 1212.81 |  |  | 1212.81 | 100 | 1112.81 | 2017-01-20 10:02 | 2050-12-31 | 2019-09-01
75080 | SG001011F | SG1009Z1O | DEK LMR - Ohio/Kentucky - Erlanger | 2.2 |  | 2.2 |  |  | 2.2 | 1399302.13 | -1399299.93 | 2019-09-24 11:58 | 2021-03-10 | 2019-10-01
75080 | SG001011F | SG1009Z1L | DEK LMR - Ohio/Kentucky - Erlanger | 3.06 |  | 3.06 |  |  | 3.06 | 5597208.53 | -5597205.47 | 2019-09-24 12:15 | 2021-03-10 | 2019-10-01
75081 | PCTAIT31 | PCTAI31J | PGO Long Range Planning Tool | -27.35 |  | -27.35 |  |  | 969.28 | 60069 | -59099.72 | 2014-06-19 | 2015-10-30 | 2014-06-01 | 2015-06-16
75081 | FPITF | 323123DEK | GenVision- FHO Data Analytics | 12697.35 |  | 12697.35 |  |  | 27745.46 | 11446 | 16299.46 | 2017-12-20 07:17 | 2020-03-28 | 2018-01-01 | 2020-10-31
75081 | FPITF | 307600001 | BASS-DMR Deployments Fossil/Hydro | 21964.45 |  | 21964.45 |  |  | 49720.94 | 12302 | 37418.94 | 2017-12-21 15:57 | 2020-01-31 | 2018-01-01 | 2020-01-31
75081 | FPITF | NP1900002 | FHO/Renewables TCA Solution Project | 28234.92 |  | 28234.92 |  |  | 28234.92 | 18581 | 9653.92 | 2019-06-05 14:01 | 2020-04-02 | 2019-06-01 | 2020-04-01
75081 | FPITF | 337767001 | KMS Upgrade | -246.66 |  | -246.66 |  |  | 2554.23 | 2357 | 197.23 | 2018-09-25 12:52 | 2020-02-29 | 2018-10-01 | 2020-02-21
75081 | EB021409 | EB021409X | U2 Lime Injection System | 10152323.26 |  | 10152323.26 |  |  | 17214351.5 | 20857179.62 | -3642828.12 | 2016-05-16 11:48 | 2020-04-30 | 2016-05-01 | 2020-06-24
75081 | EB020768 | CEB020768 | PSM Remote Safe Havens | 219336.35 |  | 219336.35 |  |  | 1081851.21 | 1090039.97 | -8188.76 | 2017-09-14 23:28 | 2020-03-31 | 2017-09-01 | 2020-03-01
75081 | EB021281 | CEB021281 | EB W. Landfill Cell 2 Construction | 15759589.5 |  | 15759589.5 |  |  | 16032899.92 | 21601631.47 | -5568731.55 | 2017-11-30 08:30 | 2020-04-30 | 2018-01-01 | 2020-05-05
75081 | EB020745 | CEB020745 | CCP EB Lined Retention Basin - East | 9652856.81 |  | 9652856.81 |  |  | 9655901.61 | 12974782.23 | -3318880.62 | 2018-11-16 14:14 | 2020-06-30 | 2018-12-01 | 2020-03-30
75081 | EB020557 | CEB020557 | PSM Ammonia Tank Vapor Barrier | 1023997.24 |  | 1023997.24 |  |  | 1137768.02 | 1394964.77 | -257196.75 | 2018-11-20 09:13 | 2020-08-31 | 2018-12-01 | 2020-03-30
75081 | EB020056 | EB020056X | Sec Superheat Outlet Header Rep | -75.69 |  | -75.69 |  |  | 6753439.8 | 8908328.79 | -2154888.99 | 2016-10-20 15:10 | 2018-12-01 | 2016-10-01 | 2018-09-29
75081 | EB020290 | CEB020290 | Lined Retention Basin | 413277 |  | 413277 |  |  | 10604186.61 | 3085662 | 7518524.61 | 2016-07-11 18:39 | 2018-11-15 | 2016-08-01 | 2019-02-28
75081 | EB021410 | CEB021410 | Dry Bottom Ash Conversion | 493603.8 |  | 493603.8 |  |  | 31307840.32 | 24439593 | 6868247.32 | 2015-10-15 14:37 | 2018-08-30 | 2015-12-01 | 2018-09-10
75081 | EB021422 | EB021422X | Precipitator Hot Side Rebuild | 311004.52 |  | 311004.52 |  |  | 37169107.25 | 34338949.86 | 2830157.39 | 2015-12-04 13:47 | 2019-05-31 | 2016-01-01 | 2018-09-29
75081 | EB020691 | CEB020691 | PSM Ammonia Storage Tank Level | 24703.3 |  | 24703.3 |  |  | 280899.46 | 181450.31 | 99449.15 | 2017-10-16 14:20 | 2019-03-31 | 2017-12-01 | 2018-09-01
75081 | EB020336 | EB020336X | Scanner/Igniter Replacement | 1705.26 |  | 1705.26 |  |  | 712617.79 | 488807.31 | 223810.48 | 2017-09-28 12:27 | 2018-08-15 | 2017-10-01 | 2018-09-29
75081 | EB020298 | CEB020298 | East Bend SW / PW REROUTE | 2284861.22 |  | 2284861.22 |  |  | 31171002.56 | 29960739 | 1210263.56 | 2016-07-01 15:23 | 2019-05-01 | 2016-08-01 | 2019-06-30
75081 | EB020941 | EB020941X | Replace F Conveyor Tower Siding | 67486.21 |  | 67486.21 |  |  | 79944.61 | 101553.09 | -21608.48 | 2018-11-30 13:59 | 2019-08-15 | 2018-12-01 | 2019-09-01
75081 | EB020800 | EB020800X | 2-2 Condenser Vac Pump HE | 1400.34 |  | 1400.34 |  |  | 26084.02 | 40301.21 | -14217.19 | 2018-02-12 19:13 | 2018-08-31 | 2018-06-01 | 2018-09-11
75081 | EB020902 | EB020902X | Rep B Conv Mag Sep Rectifier (SM18) | -23.25 |  | -23.25 |  |  | 10847.77 | 11241.03 | -393.26 | 2018-11-30 10:23 | 2018-12-31 | 2018-12-01 | 2019-02-28
75081 | EB020146 | EB020146X | Replace 2nd Layer SCR Catalyst | 2158882.33 |  | 2158882.33 |  |  | 2563477.12 | 2971507.27 | -408030.15 | 2018-09-19 12:49 | 2019-09-08 | 2018-10-01 | 2019-08-03
75081 | EB020919 | EB020919X | Replace LBU Fire Protection Piping | 24771.61 |  | 24771.61 |  |  | 57860.07 | 61088.19 | -3228.12 | 2018-11-30 15:18 | 2018-12-31 | 2018-12-01 | 2019-02-28
75081 | EB020690 | CEB020690 | PSM Barrier for pipeline | 16948.56 |  | 16948.56 |  |  | 172152.14 | 223972.13 | -51819.99 | 2018-09-14 15:07 | 2018-12-31 | 2018-10-01 | 2019-03-21
75081 | EB020937 | EB020937X | Replace Trailer City Network Cable | 1545.18 |  | 1545.18 |  |  | 13214.96 | 28964.93 | -15749.97 | 2018-11-30 14:24 | 2018-12-31 | 2018-12-01 | 2019-02-28
75081 | EB020939 | EB020939X | Replace G Conveyor Belt | 59360.31 |  | 59360.31 |  |  | 109599.42 | 103455.8 | 6143.62 | 2018-12-27 11:33 | 2019-06-30 | 2018-12-01 | 2019-08-03
75081 | EB020906 | EB020906X | Replace LBU HVACs | 7434.64 |  | 7434.64 |  |  | 59396.64 | 76830.69 | -17434.05 | 2018-09-26 12:17 | 2019-07-30 | 2018-12-01 | 2019-08-14
75081 | EB020945 | EB020945X | 2-10 CT Motor and Gearbox Repl | 199574.27 |  | 199574.27 |  |  | 217341.67 | 229420.39 | -12078.72 | 2018-11-30 15:37 | 2019-07-01 | 2018-12-01 | 2019-06-13
75081 | EB020957 | EB020957X | 2-1 Pulv Roll Wheel Repl | 956386.94 |  | 956386.94 |  |  | 956386.94 | 673327.74 | 283059.2 | 2019-02-08 15:27 | 2019-08-30 | 2019-02-01 | 2019-08-09
75081 | EB020804 | CEB020804 | PSM Thermal - East ; | 304813.02 |  | 304813.02 |  |  | 304813.02 | 323743.94 | -18930.92 | 2019-03-11 08:45 | 2019-12-31 | 2019-03-01 | 2019-08-03
75081 | EB021151 | EB021151X | CBU Headboat Phone Cable Repl | 59594.47 |  | 59594.47 |  |  | 59594.47 | 67480.86 | -7886.39 | 2019-11-12 12:35 | 2020-02-29 | 2019-11-01 | 2020-03-02
75081 | EB020740 | EB020740X | Replace Vertimill Heat Exchanger | 387406.64 |  | 387406.64 |  |  | 387406.64 | 3785702.06 | -3398295.42 | 2019-06-26 13:32 | 2021-06-30 | 2019-08-01 | 2021-06-30
75081 | EB020960 | EB020960X | Trailer City Fence Install (SM19) | 23918.2 |  | 23918.2 |  |  | 23918.2 | 16681.45 | 7236.75 | 2019-01-24 10:07 | 2019-08-31 | 2019-03-01 | 2019-08-10
75081 | EB020676 | EB020676X | Replace 480V Head Boat Power Feed | 123180.94 |  | 123180.94 |  |  | 123180.94 | 201016.65 | -77835.71 | 2019-08-16 10:31 | 2020-01-15 | 2019-09-01 | 2020-03-06
75081 | EB020952 | EB020952X | 2-3 IDF Outlet Exp Joint Repl | 35167.78 |  | 35167.78 |  |  | 35167.78 | 33385.43 | 1782.35 | 2018-12-13 15:35 | 2019-08-31 | 2019-03-01 | 2019-08-03
75081 | EB020827 | EB020827X | Repl WSP Instrument Air Dryer(SM19) | 40162.28 |  | 40162.28 |  |  | 40162.28 | 44198.89 | -4036.61 | 2019-01-24 08:55 | 2020-01-01 | 2019-02-01 | 2019-12-01
75081 | EB1912 | CEBVLV019 | 2019 Misc Valve Blanket | 494421.81 |  | 494421.81 |  |  | 494421.81 | 426371.54 | 68050.27 | 2019-01-16 14:55 | 2020-03-31 | 2019-02-01 | 2020-03-31
75081 | EB1912 | CEBVLV20 | 2020 Misc Valve Blanket | 221902.1 |  | 221902.1 |  |  | 221902.1 | 584721.92 | -362819.82 | 2019-11-12 11:51 | 2021-03-31 | 2019-12-01
75081 | EB021125 | EB021125X | Replace 2-2 Boiler Room Sump Pump | 77732.8 |  | 77732.8 |  |  | 77732.8 | 77035.98 | 696.82 | 2019-07-16 12:54 | 2019-10-31 | 2019-08-01 | 2019-12-05
75081 | EB020948 | EB020948X | Purchase JLG Lift | 71361.6 |  | 71361.6 |  |  | 71361.6 | 71664.26 | -302.66 | 2019-01-11 12:16 | 2019-02-28 | 2019-02-01 | 2019-04-11
75081 | EB020813 | CEB020813 | SmartGen EBS XFMR IR Monitoring | 59501.35 |  | 59501.35 |  |  | 59501.35 | 114305.77 | -54804.42 | 2019-03-18 15:37 | 2022-12-31 | 2019-07-01
75081 | EB021153 | EB021153X | 2-1 Pug Mill Gearbox Replacement | 7022.06 |  | 7022.06 |  |  | 7022.06 | 54374.41 | -47352.35 | 2019-11-21 17:31 | 2020-02-29 | 2019-11-01 | 2020-02-21
75081 | EB020635 | EB020635X | Repl FGD Building West Wall Siding | 900738.47 |  | 900738.47 |  |  | 900738.47 | 900477.45 | 261.02 | 2019-06-10 14:55 | 2020-03-31 | 2019-07-01 | 2020-02-29
75081 | EB020953 | EB020953X | Rep 2-1 CW Pmp Inlet-Outlet Exp Jnt | 54968.83 |  | 54968.83 |  |  | 54968.83 | 41623.05 | 13345.78 | 2019-01-11 13:30 | 2019-06-30 | 2019-02-01 | 2019-08-03
75081 | EB020350 | EB020350X | Underground Fuel Oil Day Tank (EF) | 22050.29 |  | 22050.29 |  |  | 22050.29 | 4265539.18 | -4243488.89 | 2019-11-25 10:02 | 2022-02-21 | 2019-12-01 | 2022-03-25
75081 | EB021120 | CEB021120 | FHO Cybersecurity ASA - Replacement | 23795.74 |  | 23795.74 |  |  | 23795.74 | 71687.19 | -47891.45 | 2019-04-22 15:24 | 2020-03-31 | 2019-05-01 | 2019-09-24
75081 | EBS01265 | EBS01265X | FGD to WSP Ug Prcs Pipe Repl (EF | 265148.2 |  | 265148.2 |  |  | 265148.2 | 4122675.36 | -3857527.16 | 2019-10-15 15:54 | 2020-12-30 | 2019-10-01 | 2021-01-22
75081 | EB020566 | CEB020566 | PSM Safe Havens - East Bend U2 | 421424.78 |  | 421424.78 |  |  | 421424.78 | 542839.75 | -121414.97 | 2019-09-05 08:01 | 2021-08-30 | 2019-09-01 | 2021-09-24
75081 | EB020950 | EB020950X | Install H2S Monitoring System | 712624.08 |  | 712624.08 |  |  | 712624.08 | 712624.08 | 0 | 2019-02-06 13:22 | 2019-12-31 | 2019-02-01 | 2019-12-13
75081 | EB021118 | EB021118I | L-1 LPB Rotor Blade Row (Ins Reimb) | -885198.85 |  | -885198.85 |  |  | -885198.85 | -902895.08 | 17696.23 | 2019-07-23 14:07 | 2019-12-15 | 2019-07-01 | 2019-08-03
75081 | EB021118 | EB021118X | Replace L-1 LPB Rotor Blade Row | 1745488.56 |  | 1745488.56 |  |  | 1745488.56 | 1738276.49 | 7212.07 | 2019-05-06 12:45 | 2020-02-28 | 2019-05-01 | 2019-08-03
75081 | EB020701 | EB020701X | LBU Dust Mitigation | 5733.92 |  | 5733.92 |  |  | 5733.92 | 1656005.53 | -1650271.61 | 2019-09-13 09:37 | 2022-02-28 | 2019-11-01 | 2022-03-18
75081 | EB020671 | EB020671X | SmartGen EBS Visual Camera Monit | 203180.99 |  | 203180.99 |  |  | 203180.99 | 217916.29 | -14735.3 | 2019-10-15 15:36 | 2020-03-31 | 2019-10-01 | 2020-03-31
75081 | EB020951 | CEB020951 | NERC-CIP 003 V7 | 32240.94 |  | 32240.94 |  |  | 32240.94 | 31477.62 | 763.32 | 2018-12-12 15:36 | 2020-03-31 | 2019-07-01 | 2020-03-31
75081 | EB020820 | EB020820X | Replace E Conveyor Hoods | 77776.47 |  | 77776.47 |  |  | 77776.47 | 129734.98 | -51958.51 | 2019-07-09 11:36 | 2019-12-31 | 2019-07-01 | 2020-03-11
75081 | EB020392 | EB020392X | HCAD Repl Crusher to F Conv Chute | 58135.03 |  | 58135.03 |  |  | 58135.03 | 1154709.74 | -1096574.71 | 2019-12-18 11:20 | 2021-03-07 | 2019-12-01 | 2021-02-20
75081 | EB021450 | EB021450X | Replace CRW Tank | 463603.45 |  | 463603.45 |  |  | 463603.45 | 986809.52 | -523206.07 | 2019-10-15 16:30 | 2021-06-22 | 2019-10-01 | 2021-02-19
75081 | EB020685 | EB020685X | FGD Breaker Replacement Phase 3 | 102077.87 |  | 102077.87 |  |  | 102077.87 | 656853.33 | -554775.46 | 2019-12-05 10:03 | 2021-06-22 | 2019-12-01 | 2021-02-19
75081 | EB021309 | EB021309X | 2-3 Pulv Roll Wheel Repl 2020 | 204801.05 |  | 204801.05 |  |  | 204801.05 | 901595.47 | -696794.42 | 2019-12-18 13:57 | 2021-05-11 | 2019-12-01 | 2021-02-21
75081 | EB021130 | EB021130X | Replace Fly Ash Common Exhauster | 42176.35 |  | 42176.35 |  |  | 42176.35 | 42656.41 | -480.06 | 2019-08-15 12:43 | 2020-01-31 | 2019-08-01 | 2019-11-20
75081 | EB020787 | EB020787X | Replace 9 Fire Hydrants | 84822.75 |  | 84822.75 |  |  | 84822.75 | 80996.43 | 3826.32 | 2019-05-28 10:57 | 2019-11-15 | 2019-06-01 | 2019-11-14
75081 | EB020901 | EB020901X | WSP 2ST1 6.9KV Transformer Repl | 166740.39 |  | 166740.39 |  |  | 166740.39 | 139429.55 | 27310.84 | 2018-12-27 11:50 | 2021-07-30 | 2019-05-01 | 2021-08-18
75081 | EB021143 | EB021143X | L-1 LPB Rotor Blade Row(Gen Side) | 3027852.18 |  | 3027852.18 |  |  | 3027852.18 | 1738276.49 | 1289575.69 | 2019-10-15 13:01 | 2020-02-11 | 2019-10-01 | 2020-02-26
75081 | EB021143 | EB021143I | Insurance reimbursement EB021143X | -1960970.74 |  | -1960970.74 |  |  | -1960970.74 | -1900000 | -60970.74 | 2019-12-06 16:13 | 2020-02-11 | 2019-12-01 | 2020-02-26
75081 | EB021123 | EB021123X | 2-1 WSP Cake Transfer Belt | 13458.46 |  | 13458.46 |  |  | 13458.46 | 23521.36 | -10062.9 | 2019-05-01 09:44 | 2019-08-30 | 2019-05-01 | 2019-08-04
75081 | EB021149 | EB021149X | Repl LPB L-0 Blade Row (Turb End) | 933571.62 |  | 933571.62 |  |  | 933571.62 | 986531.28 | -52959.66 | 2019-10-31 16:13 | 2020-02-12 | 2019-10-01 | 2020-02-26
75081 | EB020297 | CEB020297 | CCP East Bend East FGD Pond Rtrmnt | 4950.94 |  | 4950.94 |  |  | 4950.94 | 0 | 4950.94 | 2016-04-26 14:56 | 2019-12-31 | 2019-01-01 | 2020-01-15
75081 | EB021155 | EB021155X | Repl Lower Absorber Building Roof | 97108.37 |  | 97108.37 |  |  | 97108.37 | 281446.53 | -184338.16 | 2019-12-20 13:26 | 2020-02-28 | 2019-12-01 | 2020-05-24
75081 | EB021127 | EB021127X | Repl WSP Mixer Feed Scale (SM19) | 14075.87 |  | 14075.87 |  |  | 14075.87 | 31103.83 | -17027.96 | 2019-08-16 09:03 | 2020-01-31 | 2019-09-01 | 2020-03-31
75081 | EB021116 | EB021116X | Repl WSP Mixer Disch Belt (19) | 23075.42 |  | 23075.42 |  |  | 23075.42 | 23832.31 | -756.89 | 2019-05-01 09:00 | 2019-08-30 | 2019-05-01 | 2019-08-04
75081 | EB020954 | EB020954X | Rep 2-2 CW Pmp Inlet Exp Jnt | 21072.37 |  | 21072.37 |  |  | 21072.37 | 23565.92 | -2493.55 | 2019-01-11 13:46 | 2019-06-30 | 2019-02-01 | 2019-08-03
75081 | EB020973 | EB020973X | 2-9 CT Motor and Gearbox Repl | 253854.17 |  | 253854.17 |  |  | 253854.17 | 220901.81 | 32952.36 | 2019-02-20 13:27 | 2019-09-30 | 2019-03-01 | 2019-09-17
75081 | EB021114 | EB021114X | WSP Live Bottom Silo Exp Joint (19) | 9062.1 |  | 9062.1 |  |  | 9062.1 | 17908.35 | -8846.25 | 2019-06-17 12:24 | 2019-11-30 | 2019-06-01 | 2020-02-06
75081 | EB020903 | EB020903X | 2-3 WSP Vacuum Pmp Repl (SM18) | 41722.23 |  | 41722.23 |  |  | 41722.23 | 41235.38 | 486.85 | 2018-11-30 10:47 | 2018-12-31 | 2019-05-01 | 2019-03-28
75081 | EB021068 | EB021068X | U2-4 IDF Lube Oil CLR Cable Replc. | 29607.39 |  | 29607.39 |  |  | 29607.39 | 32134.65 | -2527.26 | 2019-03-25 06:42 | 2019-08-31 | 2019-05-01 | 2019-08-23
75081 | EB020084 | EB020084X | Retire FGD Reheat Fan | 0.52 |  | 0.52 |  |  | 0.52 | 0 | 0.52 | 2017-10-13 12:05 | 2019-05-31 | 2019-01-01 | 2019-06-29
75081 | EB021126 | EB021126X | Repl WSP Mixer Disch Scale (SM19) | 11028.8 |  | 11028.8 |  |  | 11028.8 | 31096.77 | -20067.97 | 2019-08-16 09:53 | 2020-01-31 | 2019-09-01 | 2020-03-31
75081 | MU060004 | CMU060004 | Miami Fort 6 Decommissioning | 12459.69 |  | 12459.69 |  |  | 12459.69 | 0 | 12459.69 | 2016-07-13 17:08 | 2025-03-31 | 2019-01-01
75081 | EB020947 | EB020947X | 2-1 WSP Vac Pump Replacement | 48336.72 |  | 48336.72 |  |  | 48336.72 | 66351.87 | -18015.15 | 2018-11-30 10:07 | 2018-12-15 | 2019-05-01 | 2019-03-28
75081 | EB021134 | EB021134X | Replace G Conveyor Gearbox | 30086.13 |  | 30086.13 |  |  | 30086.13 | 26904.65 | 3181.48 | 2019-10-28 10:45 | 2020-02-29 | 2019-10-01 | 2020-01-28
75081 | EB021154 | EB021154X | Core Monitor Cable Replacement | 2188.28 |  | 2188.28 |  |  | 2188.28 | 4081.84 | -1893.56 | 2019-12-06 08:50 | 2020-02-29 | 2019-12-01 | 02/23/2020
75082 | FPITF | 323123DKT | GenVision- FHO Data Analytics | 131666.36 |  | 131666.36 |  |  | 143137.44 | 68016 | 75121.44 | 2017-12-21 13:54 | 2020-03-28 | 2018-01-01 | 2020-10-30
75082 | FPITF | 307600001 | BASS-DMR Deployments Fossil/Hydro | 13002.79 |  | 13002.79 |  |  | 36292.21 | 73111 | -36818.79 | 2017-12-21 17:56 | 2020-01-31 | 2018-01-01 | 2020-01-31
75082 | FPITF | NP1900002 | FHO/Renewables TCA Solution Project | 20861.38 |  | 20861.38 |  |  | 20861.38 | 13734 | 7127.38 | 2019-06-05 14:12 | 2020-04-02 | 2019-06-01 | 2020-04-01
75082 | FPITF | 337767001 | KMS Upgrade | -196.6 |  | -196.6 |  |  | 2035.99 | 1878 | 157.99 | 2018-09-25 14:30 | 2020-03-02 | 2018-10-01 | 2020-02-21
75082 | FPITF | 355814013 | 2019 end of life server replacement | 8379.84 |  | 8379.84 |  |  | 8379.84 | 13210 | -4830.16 | 2019-06-12 14:42 | 2019-12-06 | 2019-07-01 | 2019-12-07
75082 | KYSC0001 | KYSCOCC | Emerson Ovation Compact Controller | 281232.89 |  | 281232.89 |  |  | 338452.15 | 0 | 338452.15 | 2018-10-30 11:20 | 2019-01-01 | 2018-11-01
75082 | KYSC0001 | KYSCPM | KY solar common cost | -25055.8 |  | -25055.8 |  |  | -1.1653e-11 | 1 | -1 | 2017-08-17 12:39 | 2017-12-31 | 2017-08-01 | 2018-03-15
75082 | KYSC0001 | WAL1PM | Walton 1 solar owners cost | 7516.76 |  | 7516.76 |  |  | 517163.19 | 575893.12 | -58729.93 | 2017-08-17 12:40 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2PM | Walton 2 solar owners cost | 7516.76 |  | 7516.76 |  |  | 486797.36 | 575723.1 | -88925.74 | 2017-08-17 12:40 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | KYSCPIT | KY PIT costs | -34041.22 |  | -34041.22 |  |  | -4.5475e-13 | 0 | -4.5475e-13 | 2017-08-17 12:42 | 2017-12-31 | 2018-01-01 | 2018-03-15
75082 | KYSC0001 | CRITPM | Crittenden solar owners cost | 10022.27 |  | 10022.27 |  |  | 805636.58 | 767424.88 | 38211.7 | 2017-08-17 12:41 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL2PIT | Walton 2 PIT costs | 10212.37 |  | 10212.37 |  |  | 12374.48 | 23210.84 | -10836.36 | 2017-08-17 12:44 | 2017-12-31 | 2018-05-01 | 2018-03-15
75082 | KYSC0001 | WAL1PIT | Walton 1 PIT costs | 10212.37 |  | 10212.37 |  |  | 12374.48 | 23217.7 | -10843.22 | 2017-08-17 12:43 | 2017-12-31 | 2018-05-01 | 2018-03-15
75082 | KYSC0001 | CRITPIT | Crittenden PIT costs | 13616.49 |  | 13616.49 |  |  | 16499.31 | 30939.49 | -14440.18 | 2017-08-17 12:45 | 2017-12-31 | 2018-05-01 | 2018-03-15
75082 | WDC00004 | WDC00004X | Install Fuel Oil System - BOP | -11372110.86 |  | -11372110.86 |  |  | 27804161.68 | 25801931.95 | 2002229.73 | 2016-08-22 15:04 | 2019-07-01 | 2016-08-01 | 2019-07-05
75082 | WDC00004 | WDC000044 | Install Fuel Oil System U4 | 4263438.12 |  | 4263438.12 |  |  | 4263438.12 | 4645924.95 | -382486.83 | 2019-03-29 15:27 | 2019-08-27 | 2019-04-01 | 2019-08-31
75082 | WDC00004 | WDC000045 | Install Fuel Oil System U5 | 4247858.92 |  | 4247858.92 |  |  | 4247858.92 | 4645892.78 | -398033.86 | 2019-03-29 15:37 | 2019-07-27 | 2019-04-01 | 2019-07-31
75082 | WDC00004 | WDC000046 | Install Fuel Oil System U6 | 4247858.83 |  | 4247858.83 |  |  | 4247858.83 | 4645924.95 | -398066.12 | 2019-03-29 15:42 | 2019-08-27 | 2019-04-01 | 2019-07-31
75082 | WDC00004 | WDC000043 | Install Fuel Oil System U3 | 4261397.63 |  | 4261397.63 |  |  | 4261397.63 | 4645924.95 | -384527.32 | 2019-03-29 15:22 | 2019-08-27 | 2019-04-01 | 2019-08-27
75082 | WDC00004 | WDC000041 | Install Fuel Oil System U1 | 4245697.41 |  | 4245697.41 |  |  | 4245697.41 | 4645423.16 | -399725.75 | 2019-03-29 14:38 | 2019-06-30 | 2019-04-01 | 2019-07-05
75082 | WDC00004 | WDC000042 | Install Fuel Oil System U2 | 4264097.85 |  | 4264097.85 |  |  | 4264097.85 | 4645423.16 | -381325.31 | 2019-03-29 15:15 | 2019-07-22 | 2019-04-01 | 2019-08-23
75082 | WDCM0042 | CWDCM0042 | McAfee & Equip Install | 150816.32 |  | 150816.32 |  |  | 188389.63 | 175341.82 | 13047.81 | 2018-10-13 11:25 | 2019-04-30 | 2018-12-01 | 2019-06-25
75082 | WDC01240 | WDC01240X | U3 & U4 SFC | 1273370.53 |  | 1273370.53 |  |  | 1273370.53 | 1423897.08 | -150526.55 | 2019-02-08 13:28 | 2019-12-31 | 2019-02-01 | 2020-02-15
75082 | WD010037 | WD010037X | U1 Generator Rotor Rewind | 1160397.05 |  | 1160397.05 |  |  | 1160397.05 | 1574479.63 | -414082.58 | 2019-08-08 08:17 | 2020-02-08 | 2019-08-01 | 2020-02-20
75082 | WDC01239 | WDC01239X | U5 & U6 SFC | 1165717.93 |  | 1165717.93 |  |  | 1165717.93 | 1432798.68 | -267080.75 | 2019-02-08 13:58 | 2020-02-19 | 2019-02-01 | 2020-01-15
75082 | WD020019 | WD020019X | WD02 Turbine Section Replacement | 2079231.63 |  | 2079231.63 |  |  | 2079231.63 | 3635292.47 | -1556060.84 | 2019-01-22 12:22 | 2019-08-31 | 2019-02-01 | 2019-08-08
75082 | WD020019 | WD020019I | WD02 Turbine outage Insurance reimb | -595543.55 |  | -595543.55 |  |  | -595543.55 | -489000 | -106543.55 | 2019-04-26 08:34 | 2019-08-31 | 2019-04-01 | 2019-08-08
75082 | WD050001 | WD050001X | U5 Dual Channel Synchronizer | 46960.36 |  | 46960.36 |  |  | 46960.36 | 44997.46 | 1962.9 | 2019-02-19 09:38 | 2020-02-28 | 2019-08-01 | 2020-01-15
75082 | WDC01238 | WDC01238X | U1 & U2 SFC | 1117993.66 |  | 1117993.66 |  |  | 1117993.66 | 1423897.08 | -305903.42 | 2019-02-08 14:27 | 2020-01-01 | 2019-02-01 | 2020-02-19
75082 | WD020001 | WD020001X | U2 Dual Channel Synchronizer | 43103.34 |  | 43103.34 |  |  | 43103.34 | 45681.51 | -2578.17 | 2019-02-19 10:34 | 2020-02-27 | 2019-08-01 | 2020-02-19
75082 | WD060001 | WD060001X | U6 Dual Channel Synchronizer | 52774.65 |  | 52774.65 |  |  | 52774.65 | 44620.42 | 8154.23 | 2019-02-19 09:08 | 2020-02-01 | 2019-08-01 | 2020-01-15
75082 | WD040013 | WD040013X | U4 125V DC Battery Replacement | 27664.52 |  | 27664.52 |  |  | 27664.52 | 28471.98 | -807.46 | 2019-02-19 11:08 | 2019-07-30 | 2019-05-01 | 2019-08-09
75082 | WD020017 | WD020017X | U2 125V DC Battery Replacement | 15853.41 |  | 15853.41 |  |  | 15853.41 | 28660.13 | -12806.72 | 2019-01-31 15:09 | 2020-09-30 | 2019-05-01 | 2019-07-06
75082 | WDCM0051 | WDCM0051X | Station Discharge Lift Station Cont | 14161.85 |  | 14161.85 |  |  | 14161.85 | 35857.39 | -21695.54 | 2019-11-25 13:22 | 2020-12-31 | 2019-12-01 | 2021-03-03
75082 | WD040008 | WD040008X | WDC U4 Comp Caulking & R17 Blades | 374980.31 |  | 374980.31 |  |  | 374980.31 | 377155.29 | -2174.98 | 2019-07-22 09:40 | 2020-01-18 | 2019-09-01 | 2020-02-18
75082 | WD020015 | WD020015X | U2 Generator Rotor Rewind | 1714495.8 |  | 1714495.8 |  |  | 1714495.8 | 1612021.66 | 102474.14 | 2019-01-14 12:19 | 2019-07-30 | 2019-01-01 | 2019-07-05
75082 | WDC00048 | CWDC00048 | NERC-CIP 003 V7 Tough Notebook | 25307.53 |  | 25307.53 |  |  | 25307.53 | 30670.19 | -5362.66 | 2018-12-07 07:45 | 2020-03-31 | 2019-10-01 | 2020-03-31
75082 | WD010005 | WD010005X | U1 Dual Channel Synchronizer | 51215.51 |  | 51215.51 |  |  | 51215.51 | 45777.4 | 5438.11 | 2019-02-19 11:46 | 2020-02-19 | 2019-08-01 | 2020-02-19
75082 | WDC00059 | WDC00059X | FIRE PROT, WDC, CO2 Compliance | 202501.61 |  | 202501.61 |  |  | 202501.61 | 229689.39 | -27187.78 | 2019-09-25 09:16 | 2020-03-25 | 2019-10-01 | 2020-03-13
75082 | WD030001 | WD030001X | U3 Dual Channel Synchronizer | 47199.91 |  | 47199.91 |  |  | 47199.91 | 45333.19 | 1866.72 | 2019-02-19 10:20 | 2020-02-01 | 2019-08-01 | 2020-01-30
75082 | WD050010 | WD050010X | CT5 "A" Phase Iso-phase Replacement | 173924.95 |  | 173924.95 |  |  | 173924.95 | 217632.82 | -43707.87 | 2018-12-18 09:19 | 2019-08-10 | 2019-03-01 | 2019-06-28
75082 | WD040002 | WD040002X | U4 Dual Channel Synchronizer | 19392.32 |  | 19392.32 |  |  | 19392.32 | 45353.81 | -25961.49 | 2019-02-19 10:09 | 2020-02-08 | 2019-10-01 | 2020-02-15
75082 | WDC00058 | CWDC00058 | FHO Cybersecurity ASA - Replacement | 9152.91 |  | 9152.91 |  |  | 9152.91 | 19947.31 | -10794.4 | 2019-08-30 10:13 | 2020-03-31 | 2019-09-01 | 2020-01-31
75082 | WD030009 | WD030009X | U3 125V DC Battery Replacement | 15854.74 |  | 15854.74 |  |  | 15854.74 | 28625.74 | -12771 | 2019-02-19 10:49 | 2019-10-30 | 2019-05-01 | 2019-08-09
75082 | WD010039 | WD010039X | U1 125V DC Battery Replacement | 25215.28 |  | 25215.28 |  |  | 25215.28 | 28632.25 | -3416.97 | 2019-01-31 14:30 | 2019-07-19 | 2019-03-01 | 2019-07-06
|  |  |  | 170084618.89 | 145520280.951 | -24564337.939 | -16.88%

## 2020
Duke Energy Kentucky Electric
Year 2020
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75084 | FENABLES | ENABLETDG | ENABLETDG Clearing Project | 1.31 |  | 1.31 |  |  | 3.2742e-11 | 801485.44 | -801485.44 | 2015-05-12 14:57 | 2018-10-01 | 2015-05-01 | 2019-02-28
75084 | FENABLES | MOBS | Enable Mobility Software | -5.79 |  | -5.79 |  |  | 883408.68 | 932343 | -48934.32 | 2015-03-30 14:54 | 2017-10-31 | 2015-05-01 | 2017-11-07
75084 | FPIT | 338802004 | Mobile Durable Team | 13361.13 |  | 13361.13 |  |  | 112387.18 | 52783 | 59604.18 | 2018-09-17 12:12 | 2020-05-28 | 2018-10-01 | 2020-05-28
75084 | FPIT | IT1900019 | System Operations Checkout Automati | 1905.49 |  | 1905.49 |  |  | 20553.23 | 19356 | 1197.23 | 2019-09-11 07:36 | 2020-07-31 | 2019-09-01 | 2020-07-23
75084 | FPIT | 338802003 | EAM Platform Optimization | 887.89 |  | 887.89 |  |  | 73042.67 | 147321.02 | -74278.35 | 2018-04-25 12:44 | 2020-05-30 | 2018-06-01 | 2020-03-31
75084 | FPIT | 346954001 | ISOP Granular Forecasting | 84689.45 |  | 84689.45 |  |  | 180892.44 | 139345 | 41547.44 | 2018-05-14 11:31 | 2024-09-30 | 2018-05-01
75084 | FPIT | LTHITTAMO | LTH - IT Telecom Asset Managemt | 7813.84 |  | 7813.84 |  |  | 7813.84 | 96831 | -89017.16 | 2020-07-28 14:30 | 2022-12-30 | 2020-10-01 | 2022-09-30
75084 | FPIT | IT1900073 | EAM 2020 Mobile Durable Team | 69686.17 |  | 69686.17 |  |  | 69686.17 | 36572 | 33114.17 | 2020-01-20 08:34 | 2021-05-30 | 2020-01-01 | 2021-06-08
75084 | FPIT | 349472SW1 | Multi-instance of Service Suite | 17546.87 |  | 17546.87 |  |  | 17546.87 | 36419 | -18872.13 | 2020-03-06 09:43 | 2020-11-29 | 2020-03-01 | 2020-11-29
75084 | FPIT | 338802005 | Maximo Durable Team | 2376.04 |  | 2376.04 |  |  | 156208.39 | 33459 | 122749.39 | 2018-09-13 14:56 | 2020-05-28 | 2018-10-01 | 2020-05-28
75084 | FPIT | IT20SW08D | ITOA 2020 Product Enhancements | 29261.45 |  | 29261.45 |  |  | 29261.45 | 34187 | -4925.55 | 2020-03-26 08:44 | 2022-03-01 | 2020-03-01 | 2022-01-08
75084 | FPIT | IT1900074 | EAM 2020 Maximo Durable Team | 41152.43 |  | 41152.43 |  |  | 41152.43 | 229288 | -188135.57 | 2020-01-20 10:48 | 2021-05-30 | 2020-01-01 | 2021-06-08
75084 | FPIT | 338802HW3 | EAM Platform Optimization | 7.36 |  | 7.36 |  |  | 7.36 | 59872 | -59864.64 | 2018-04-25 14:24 | 2019-10-31 | 2020-07-01 | 2020-03-31
75084 | FPIT | NE2000001 | FSO Back-up Site CIP Implementation | 13859.63 |  | 13859.63 |  |  | 13859.63 | 26829 | -12969.37 | 2020-04-17 10:36 | 2020-10-29 | 2020-04-01 | 2020-10-31
75084 | FPIT | IT1900009 | Transmission Estimating Tool | 189.31 |  | 189.31 |  |  | 6848.77 | 75989 | -69140.23 | 2019-04-01 08:13 | 2020-01-30 | 2019-04-01 | 2020-01-04
75084 | FPIT | 338802006 | Smallworld/myWorld Durable Team | -332.62 |  | -332.62 |  |  | 10.97 | 48911 | -48900.03 | 2018-09-06 13:18 | 2020-05-28 | 2019-04-01 | 2020-11-10
75084 | FPIT | 349472HW1 | Multi-instance of Service Suite | 5095.72 |  | 5095.72 |  |  | 5095.72 | 13125 | -8029.28 | 2020-03-06 10:42 | 2020-11-29 | 2020-03-01 | 2020-11-29
75084 | FPIT | 349472002 | Bentley Subscription License | 1158823.56 |  | 1158823.56 |  |  | 1158823.56 | 1182335 | -23511.44 | 2020-03-09 08:18 | 2020-08-28 | 2020-03-01 | 2020-04-01
75084 | SG000358F | SG358HW19 | SG DEE MDM Scale HWre Phase 4 - 358 | -12.67 |  | -12.67 |  |  | 57577.12 | 30270.21 | 27306.91 | 2018-05-09 10:54 | 2019-08-18 | 2018-05-01 | 2019-09-24
75084 | SG000358F | SG358SVR2 | DEE MDM Sclae | 1868.27 |  | 1868.27 |  |  | 1868.27 | 1378 | 490.27 | 2020-04-16 07:15 | 2020-08-31 | 2020-04-01 | 2020-07-31
75084 | SG000358F | SG358SVR | DEE MDM Scale | 1424.37 |  | 1424.37 |  |  | 2557.34 | 1504 | 1053.34 | 2019-09-24 07:55 | 2020-01-31 | 2019-11-01 | 2020-03-31
75084 | SG000489F | SG489SVRS | SG DEE Openway Scale Servers | 0.09 |  | 0.09 |  |  | 42263.15 | 44829.46 | -2566.31 | 2017-04-24 18:07 | 2018-12-31 | 2017-05-01 | 2019-03-31
75084 | SG000489F | SG489SVR2 | DEE Openway Scale | 282.69 |  | 282.69 |  |  | 15648.39 | 22338 | -6689.61 | 2019-01-22 21:39 | 2020-03-31 | 2019-01-01 | 2019-09-30
75084 | SG000489F | SG489SW2 | DEE Openway Scale | 6453.16 |  | 6453.16 |  |  | 6453.16 | 2881 | 3572.16 | 2020-02-03 09:09 | 2020-10-31 | 2020-01-01 | 2020-10-26
75084 | SG000489F | SG489SVR3 | DEE Openway Scale | 5003.81 |  | 5003.81 |  |  | 5014.14 | 1707 | 3307.14 | 2019-09-25 08:02 | 2020-10-31 | 2019-10-01 | 2020-10-26
75084 | SG000489F | SG489SVR4 | DEE Openway Scale | 5.45 |  | 5.45 |  |  | 5.45 | 634 | -628.55 | 2020-01-29 21:38 | 2020-10-31 | 2020-03-01
75084 | SG000540F | SG540SW | DEE Vehicle Area Network | 0.03 |  | 0.03 |  |  | 0.06 | 109210 | -109209.94 | 2017-04-13 09:21 | 2020-12-17 | 2017-04-01 | 2018-07-16
75084 | SG000540F | SG540HW | DEE Vehicle Area Network | 16365.08 |  | 16365.08 |  |  | 121458.39 | 273196 | -151737.61 | 2018-04-12 17:01 | 2020-12-17 | 2018-09-01 | 2021-05-15
75084 | SGKAMIF | SG169MTRS | SG KY AMI Electric Meters - 169 | 1534259.57 |  | 1534259.57 |  |  | 22855893.97 | 23298670 | -442776.03 | 2017-06-07 11:18 | 2019-02-28 | 2017-06-01
75084 | SGKAMIF | SGKAMIMGT | TBC DEK AMI Mgmt Project | -1507876.72 |  | -1507876.72 |  |  | 2.0486e-10 | 603878 | -603878 | 2016-01-20 16:12 | 2023-02-01 | 2016-01-01
75084 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | -742.15 |  | -742.15 |  |  | 111560.08 | 110269.74 | 1290.34 | 2018-07-12 09:08 | 2021-03-31 | 2018-07-01 | 2021-03-31
75084 | FMDT2017 | MDTKE17 | Panasonic CF53 Units- Kentucky | -20287.16 |  | -20287.16 |  |  | 247289.28 | 87508.08 | 159781.2 | 2017-12-14 11:20 | 2020-06-01 | 2018-01-01 | 2020-05-01
75084 | SGITOMSGI | SGSWDOMC | SG AMI DOMS S/W Module Capital | 0.05 |  | 0.05 |  |  | 28994.39 | 37300 | -8305.61 | 2012-12-20 | 2015-08-29 | 2013-01-01 | 2017-01-15
75084 | DKY2133 | DKY213319 | Mt Zion 22.4MVA Bk 2 DS1 | 1249122.43 |  | 1249122.43 |  |  | 2883862.63 | 3017877 | -134014.37 | 2018-01-29 18:02 | 2020-03-24 | 2018-04-01 | 2020-04-23
75084 | DKY2133 | MX2167975 | Mt Zion Rbld Weaver Rd - DKY2133 | -171540.49 |  | -171540.49 |  |  | 1788271.54 | 242159.7 | 1546111.84 | 2017-10-05 10:01 | 2021-07-29 | 2017-10-01 | 2021-01-28
75084 | DKY2133 | DKY213318 | TBC - Mt Zion 138kV Loop TS1 | -10093.87 |  | -10093.87 |  |  | 2.0486e-10 | 0 | 2.0486e-10 | 2018-01-29 18:02 | 2020-12-31 | 2018-04-01
75084 | DKY2133 | DKY213321 | Bank 1 low-side breaker | 154301.45 |  | 154301.45 |  |  | 360280.3 | 357627 | 2653.3 | 2018-10-24 18:03 | 2020-05-19 | 2018-11-01 | 2020-06-04
75084 | DKY2133 | DKY213320 | TBC - TL Pole Replacements | -6633.06 |  | -6633.06 |  |  | 4.5111e-12 | 154917 | -154917 | 2019-03-05 14:01 | 2020-12-31 | 2019-03-01
75084 | KYGLPRT | MX7343749 | 2166 P2 X-fer distribution underbui | 1796.46 |  | 1796.46 |  |  | 36791.79 | 18473.43 | 18318.36 | 2018-02-16 10:13 | 2019-06-01 | 2018-06-01 | 2019-04-04
75084 | KYGLPRT | MX7360458 | Transfer distribution underbuild fo | 254.99 |  | 254.99 |  |  | 11502.9 | 10915.73 | 587.17 | 2018-02-26 14:50 | 2021-03-31 | 2018-12-01 | 2021-03-18
75084 | KYGLPRT | MX8766989 | Transfer distribution underbuild fo | -2605.04 |  | -2605.04 |  |  | 60921.58 | 63063.25 | -2141.67 | 2018-07-17 14:02 | 2019-06-01 | 2018-08-01 | 2019-02-13
75084 | KYGLPRT | MX8520300 | Transfer distribution underbuild fo | 12315.33 |  | 12315.33 |  |  | 105350.38 | 42589.04 | 62761.34 | 2018-07-12 14:02 | 2019-06-01 | 2018-07-01 | 2019-04-08
75084 | KYGLPRT | MX1200896 | F966 X-fer UB for 5 - P1 wood to st | 18224.94 |  | 18224.94 |  |  | 18224.94 | 10353.15 | 7871.79 | 2019-05-10 14:01 | 2020-09-28 | 2020-01-01 | 2020-08-26
75084 | KYGLPRT | KYGLPRT06 | TBC - GLT P1 Cir6763 22 Pole Replac | -89.61 |  | -89.61 |  |  | -1.138e-14 | 396000 | -396000 | 2018-04-30 14:05 | 2021-03-31 | 2019-11-01
75084 | KYGLPRT | MX7360495 | Transfer distribution underbuild fo | 15492.28 |  | 15492.28 |  |  | 15492.28 | 48380.24 | -32887.96 | 2018-02-26 13:38 | 2021-07-29 | 2020-01-01 | 2021-07-20
75084 | KYGLPRT | KYGLPRT03 | GLT P1 Cir 966 Repl 5 poles | 83095.67 |  | 83095.67 |  |  | 87251.91 | 86199.78 | 1052.13 | 2018-04-16 10:01 | 2021-03-31 | 2019-07-01 | 2020-07-21
75084 | KYGLPRT | MX7109799 | T-EMERGENT GLT TR_UB F5985 Transfer | 15718.61 |  | 15718.61 |  |  | 15718.61 | 10286.94 | 5431.67 | 2020-06-10 18:01 | 2022-02-28 | 2020-07-01 | 2021-12-07
75084 | KYGLPRT | MX5944931 | TBC GLT F6763 (M19015301) Tran_UB | 21107.76 |  | 21107.76 |  |  | 21107.76 | 21608 | -500.24 | 2020-02-27 18:01 | 2022-07-01 | 2020-03-01
75084 | KYGLPRT | KYGLPRT07 | GLT P2 Cir 6763 6 pole Replacements | -186.82 |  | -186.82 |  |  | 1.4655e-14 | 108000 | -108000 | 2018-06-12 10:01 | 2021-03-31 | 2019-05-01
75084 | KYGLPRT | KYGLPRT05 | GLT P2 Cir 966 Repl 1 Pole | 83612.35 |  | 83612.35 |  |  | 83612.35 | 96243.4 | -12631.05 | 2018-04-30 14:05 | 2020-07-29 | 2020-03-01 | 2020-07-07
75084 | KYGLPRT | MX1325365 | F5983 X-fer UB for 6 - P2 wood to s | 58.48 |  | 58.48 |  |  | 9743.69 | 76917.35 | -67173.66 | 2019-04-23 18:01 | 2023-03-30 | 2019-07-01
75084 | RELDFA | MKRDYKY | Make Ready Kentucky | 4023.48 |  | 4023.48 |  |  | 406636.18 | 10 | 406626.18 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084 | ORDFA | SKY2009DC | TO CAPTURE 2020 CAPITAL STORM #9 | 16329.83 |  | 16329.83 |  |  | 16329.83 | 13973.46 | 2356.37 | 2020-07-14 16:54 | 2021-03-31 | 2020-11-01
75084 | ORDFA | SKY2001DC | TO CAPTURE 2020 CAPITAL STORM #1 | 11692.22 |  | 11692.22 |  |  | 11692.22 | 0 | 11692.22 | 2019-05-07 21:27 | 2020-12-31 | 2020-01-01
75084 | ORDFA | SKY2008DC | TO CAPTURE 2020 CAPITAL STORM #8 | 5175.35 |  | 5175.35 |  |  | 5175.35 | 4180.51 | 994.84 | 2020-07-14 16:52 | 2021-03-31 | 2020-08-01
75084 | ORDFA | SKY1910DC | TO CAPTURE 2019 CAPITAL STORM #10 | 8185.73 |  | 8185.73 |  |  | 8974.42 | 0 | 8974.42 | 2019-05-07 21:10 | 2020-03-31 | 2019-12-01
75084 | ORDFA | SKY2002DC | TO CAPTURE 2020 CAPITAL STORM #2 | 112401.31 |  | 112401.31 |  |  | 112401.31 | 0 | 112401.31 | 2019-05-07 21:29 | 2020-12-31 | 2020-04-01
75084 | ORDFA | SKY1911DC | TO CAPTURE 2019 CAPITAL STORM #11 | 15.47 |  | 15.47 |  |  | 15.47 | 0 | 15.47 | 2019-05-07 21:12 | 2020-03-31 | 2020-01-01
75084 | ORDFA | SKY2004DC | TO CAPTURE 2020 CAPITAL STORM #4 | 14807.31 |  | 14807.31 |  |  | 14807.31 | 12207.31 | 2600 | 2019-12-11 16:53 | 2020-12-31 | 2020-07-01
75084 | ORDFA | SKY1909DC | TO CAPTURE 2019 CAPITAL STORM #9 | 10807.69 |  | 10807.69 |  |  | 20949.17 | 0 | 20949.17 | 2019-05-07 21:08 | 2020-03-31 | 2019-12-01
75084 | ORDFA | SKY2006DC | TO CAPTURE 2020 CAPITAL STORM #6 | 27194.15 |  | 27194.15 |  |  | 27194.15 | 25222.56 | 1971.59 | 2019-12-13 09:08 | 2020-12-31 | 2020-07-01
75084 | ORDFA | SKY2007DC | TO CAPTURE 2020 CAPITAL STORM #7 | 2935.3 |  | 2935.3 |  |  | 2935.3 | 0 | 2935.3 | 2020-07-14 16:49 | 2021-03-31 | 2020-08-01
75084 | ORDFA | SKY2003DC | TO CAPTURE 2020 CAPITAL STORM #3 | 9267.71 |  | 9267.71 |  |  | 9267.71 | 0 | 9267.71 | 2019-05-07 21:31 | 2020-12-31 | 2020-06-01
75084 | RELTFA | KYRELT1 | F6763 DOT Mt Zion Rd-Dixie Hwy | 939070.99 |  | 939070.99 |  |  | 2750009.87 | 35000 | 2715009.87 | 2015-07-25 18:59 | 2020-04-13 | 2015-09-01 | 2020-03-18
75084 | DECCIRFA | P7274 | TBC DEC 6892567 Donaldson 41 | -121946.46 |  | -121946.46 |  |  | 1.3642e-12 | 205737.82 | -205737.82 | 2015-01-14 | 2020-12-31 | 2015-01-01
75084 | DECCIRFA | P7273 | DEC 6892574 Donaldson 41 | 6.58 |  | 6.58 |  |  | 133034.73 | 88334.91 | 44699.82 | 2015-01-14 | 2017-11-15 | 2015-01-01 | 2017-10-27
75084 | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | 6559.24 |  | 6559.24 |  |  | 770291.82 | 10 | 770281.82 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084 | NBFA | NBKYCI | Commerc & Indust Cust Adds-MW-D | 3918.14 |  | 3918.14 |  |  | 1449510.43 | 0 | 1449510.43 | 2016-01-21 13:58 | 2025-12-31 | 2016-02-01
75084 | NBFA | NBKYRES | Residential Customer Adds-MW-D | -8517.28 |  | -8517.28 |  |  | 2272437.3 | 0 | 2272437.3 | 2016-01-21 13:51 | 2025-12-31 | 2016-02-01
75084 | NCIPLOWK | KCIPLW999 | Electronic Keys | 22672.88 |  | 22672.88 |  |  | 420912.13 | 29929 | 390983.13 | 2017-11-17 14:50 | 2020-03-31 | 2017-11-01 | 2018-07-12
75084 | DKY1930 | D1930DL1 | AM 11851684 Recd Donaldson 42 Riggs | -2801.41 |  | -2801.41 |  |  | 955513.26 | 261996.83 | 693516.43 | 2016-12-19 09:23 | 2018-08-30 | 2017-01-01 | 2018-08-30
75084 | RLFA | LPFUKY | Line Patrol Insp followup KY | -8254.16 |  | -8254.16 |  |  | 1122162.19 | 400000 | 722162.19 | 2010-12-22 | 2015-12-31 | 2011-03-01
75084 | RLFA | DLSKY | DLine Switches 34.5kv Replace KY | -681.78 |  | -681.78 |  |  | 28856.98 | 9 | 28847.98 | 2014-08-04 | 2020-12-31 | 2016-03-01
75084 | RLFA | KGENSWG | Kentucky Switchgear Repl Program | -20.6 |  | -20.6 |  |  | 18082.52 | 100 | 17982.52 | 2016-03-28 10:49 | 2030-12-31 | 2018-05-01
75084 | SGPMYUF | SGYFA2SW | DEE YFA Ver 2 DER - Software | 0.06 |  | 0.06 |  |  | 24961.77 | 36217 | -11255.23 | 2016-01-08 10:09 | 2017-05-24 | 2016-01-01 | 2017-03-07
75084 | GLPRTFA | KYGLPR11 | F5967 Repl HL867 to HL872 and HL876 | -39980.43 |  | -39980.43 |  |  | 752.44 | 220579 | -219826.56 | 2016-11-14 13:36 | 2021-06-30 | 2017-05-01
75084 | CAPFA | OTVSRKY | Cap Oil to Vac Switch Repl KY | 3318.68 |  | 3318.68 |  |  | 26890.12 | 100000 | -73109.88 | 2010-12-22 | 2050-12-31 | 2011-08-01
75084 | VMTDFA | GGARKY | TVM Reactive Cap - DEK | 27251.44 |  | 27251.44 |  |  | 27251.44 | 2 | 27249.44 | 2019-10-16 15:20 | 2050-12-31 | 2020-03-01
75084 | VMTDFA | TVMBLLVKY | TVM NonNERC Cap - DEK | 209179.16 |  | 209179.16 |  |  | 209179.16 | 2 | 209177.16 | 2019-10-16 14:36 | 2050-12-31 | 2020-03-01
75084 | VMDDTFA | VMCMCKY | R/W CKT MAINT CAP KENTUCKY | -843 |  | -843 |  |  | 2231479.15 | 1 | 2231478.15 | 2012-01-25 | 2050-12-31 | 2012-02-01
75084 | SGAMF | SG344SW | SG DEE Distrib System Health - SW | -1094.63 |  | -1094.63 |  |  | 84090.38 | 73774 | 10316.38 | 2015-12-18 14:25 | 2020-03-31 | 2016-01-01 | 2019-12-31
75084 | SGDMSCF | SG361SW | SG DEE DMS Project 10 SW | 177955.02 |  | 177955.02 |  |  | 336359.07 | 266133.19 | 70225.88 | 2015-12-18 15:11 | 2022-05-28 | 2016-01-01 | 2022-03-31
75084 | SG000336F | SG336SW | SG DEE DMS ADMS - Software | 321437.59 |  | 321437.59 |  |  | 968917.82 | 1049863.37 | -80945.55 | 2016-09-06 17:51 | 2024-05-28 | 2016-09-01
75084 | SG000336F | SG336OUA | SG Oracle Utilities Analytics Softw | 31129.69 |  | 31129.69 |  |  | 148495.79 | 155000 | -6504.21 | 2018-07-30 10:48 | 2021-05-28 | 2018-08-01 | 2021-07-01
75084 | SG000336F | SG336SVR2 | SG Oracle Utilities Analytics Hardw | 26524.98 |  | 26524.98 |  |  | 51917.78 | 20696 | 31221.78 | 2018-08-14 17:44 | 2020-06-30 | 2019-06-01 | 2020-06-30
75084 | SG000601F | SG601SW | DEE ADP Software - 601 | 111659.88 |  | 111659.88 |  |  | 192662.12 | 42090 | 150572.12 | 2017-06-21 17:55 | 2025-03-31 | 2017-06-01
75084 | SGEAMIOCF | SG305SVRS | SG DEE OpenWay Ops Center Servers | -0.21 |  | -0.21 |  |  | -0.12 | 5323.07 | -5323.19 | 2016-09-06 11:56 | 2020-12-31 | 2016-09-01
75084 | SGEAMIOCF | SG305SW | SG DEE OpenWay Ops Center Software | 0.33 |  | 0.33 |  |  | 0.19 | 189544.12 | -189543.93 | 2016-08-01 10:09 | 2020-12-31 | 2016-08-01
75084 | DKY2199 | D2199DL3 | AM 21607381 Hebron | 138481.73 |  | 138481.73 |  |  | 580865.64 | 250919.99 | 329945.65 | 2017-06-27 13:39 | 2020-07-30 | 2017-11-01 | 2020-07-21
75084 | DKY2199 | D2199DL2 | AM 21607299 Hebron - DKY2199 | 119801.08 |  | 119801.08 |  |  | 2085759.86 | 238000.64 | 1847759.22 | 2017-06-27 13:32 | 2020-07-30 | 2017-07-01 | 2020-07-29
75084 | DKY2199 | D2199DL4 | AM 21607440 Hebron | 7599.1 |  | 7599.1 |  |  | 72285.74 | 41400.28 | 30885.46 | 2017-06-27 13:44 | 2020-07-30 | 2018-03-01 | 2020-07-31
75084 | DKY2199 | D2199DL1 | AM 21606995 Hebron | -17772.44 |  | -17772.44 |  |  | 188287.23 | 65607.29 | 122679.94 | 2017-06-27 13:20 | 2019-11-01 | 2017-12-01 | 2019-09-28
75084 | DKY2016 | D2016DS1 | Donaldson TB 3 - DKY2016 | 61964.21 |  | 61964.21 |  |  | 5624441.04 | 4019811 | 1604630.04 | 2017-07-18 07:20 | 2020-02-28 | 2017-08-01 | 2020-03-12
75084 | DKY2016 | D2016DS2 | Donaldson TB 4 - DKY2016 | 110941.57 |  | 110941.57 |  |  | 3616341.49 | 3960624 | -344282.51 | 2017-07-18 07:32 | 2020-02-16 | 2017-08-01 | 2020-03-12
75084 | DKY2016 | MX2175246 | Donaldson 48 Ln Ext - DKY2016 | -9964.6 |  | -9964.6 |  |  | 730324.04 | 162040.89 | 568283.15 | 2017-10-12 12:00 | 2020-06-25 | 2017-10-01 | 2020-04-23
75084 | DKY2016 | MX9917129 | Donaldson 48 UG Exits Conduit - DKY | 2635.11 |  | 2635.11 |  |  | 202256.85 | 39264.85 | 162992 | 2018-09-25 14:02 | 2019-12-26 | 2018-11-01 | 2019-02-28
75084 | DKY2016 | MX0265492 | TBC De-energize Segment Circuit 41 | -1240.5 |  | -1240.5 |  |  | 2.2737e-13 | 0 | 2.2737e-13 | 2018-11-09 14:02 | 2020-12-31 | 2018-12-01
75084 | DKY2016 | MX2175719 | Donaldson 46 Ln Ext - DKY2016 | -7170.09 |  | -7170.09 |  |  | 99573.04 | 147197.24 | -47624.2 | 2017-10-12 14:01 | 2019-06-01 | 2018-07-01 | 2018-12-24
75084 | DKY2016 | MX9916982 | Donaldson 46 UG Exits Conductor - D | -6573.42 |  | -6573.42 |  |  | 74180.86 | 38743.91 | 35436.95 | 2018-09-25 14:02 | 2019-11-28 | 2019-06-01 | 2019-11-25
75084 | DKY2016 | MX2800033 | Donaldson 42 Exit - DKY2016 | 25815.44 |  | 25815.44 |  |  | 33345.35 | 9341.62 | 24003.73 | 2019-05-29 14:02 | 2020-10-29 | 2019-10-01 | 2020-09-01
75084 | DKY2016 | MX2969660 | TBC Donaldson Bus Tie - DKY2016 | -13619.39 |  | -13619.39 |  |  | -6.537e-13 | 26506.01 | -26506.01 | 2019-06-13 10:01 | 2021-03-01 | 2019-08-01
75084 | DKY2016 | MX9917170 | Donaldson 48 UG Exits Conductor - D | -8975.06 |  | -8975.06 |  |  | 68673.79 | 33869.48 | 34804.31 | 2018-09-25 14:02 | 2019-11-28 | 2019-06-01 | 2019-11-25
75084 | DKY2016 | MX4849834 | Donaldson 46 - Circuit Tie to Donal | 48358.1 |  | 48358.1 |  |  | 48358.1 | 52620.61 | -4262.51 | 2019-11-26 18:01 | 2020-06-29 | 2020-01-01 | 2020-04-27
75084 | 75084IK | KOUTUG | Outage Related UG Cap Replacements | 525523.19 |  | 525523.19 |  |  | 2399622.79 | 93 | 2399529.79 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOTT | Pothead Termination | 355.28 |  | 355.28 |  |  | 137594.8 | 93 | 137501.8 | 2017-03-27 12:34 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOH | Non-Emergency OH Corrective Replace | 249252.41 |  | 249252.41 |  |  | 103573.59 | 93 | 103480.59 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEOH | Emergency OH Corrective Replacement | 324347.62 |  | 324347.62 |  |  | 778735.31 | 93 | 778642.31 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KPOLIR | Non Emerg Pole Replace Insp Based | 87253.8 |  | 87253.8 |  |  | 471584.66 | 93 | 471491.66 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPDMCPU | Public Damage UG Capital Replacemnt | 155791.49 |  | 155791.49 |  |  | 209774.84 | 93 | 209681.84 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRIOTCO | OH Imprvmnt From PQRI Outage Invest | 72696.77 |  | 72696.77 |  |  | 424748.86 | 93 | 424655.86 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLCM | Reactive Pole Replacements | 402249.53 |  | 402249.53 |  |  | 1269612.35 | 93 | 1269519.35 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KPPL | Stub Pole Removal Only | 9175.49 |  | 9175.49 |  |  | 28928.24 | 2 | 28926.24 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KCAPAUTO | Capacitor Automation Upgrade | 197688.53 |  | 197688.53 |  |  | 626259.49 | 93 | 626166.49 | 2017-03-24 15:35 | 2067-12-31 | 2018-01-01
75084 | 75084IK | KLPF | Line Patrol Follow Up | 157842.93 |  | 157842.93 |  |  | 1362630.23 | 93 | 1362537.23 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTR1PH | Single PH Transformer Replace Dry | 4083.8 |  | 4083.8 |  |  | 50553.65 | 93 | 50460.65 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRUCSM | UG Primary Small Cable Replacement | 5340.69 |  | 5340.69 |  |  | 321265.82 | 93 | 321172.82 | 2017-03-27 14:22 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCUG | Non-Emergency UG Corrective Repl | 27639.53 |  | 27639.53 |  |  | 101920.99 | 93 | 101827.99 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KSMF | Capital Replacements from SMEI Insp | -543.53 |  | -543.53 |  |  | 7917.43 | 93 | 7824.43 | 2017-03-27 14:35 | 2067-12-31 | 2018-03-01
75084 | 75084IK | KCBLDT | UG Cable Replacement Dwntn Network | -116.02 |  | -116.02 |  |  | 80762.67 | 93 | 80669.67 | 2017-03-24 15:38 | 2067-12-31 | 2018-10-01
75084 | 75084IK | KRRR | Recloser Replacements | 46941.74 |  | 46941.74 |  |  | 1176188.03 | 96 | 1176092.03 | 2017-03-27 13:10 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRIOTCU | UG Imprvmnt From PQRI Outage Invest | 3202.34 |  | 3202.34 |  |  | 54593.02 | 93 | 54500.02 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCIPOH | C&I Customer Additions OH | 789258.83 |  | 789258.83 |  |  | 4076485.46 | 93 | 4076392.46 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLEIR | Emergency Pole Replace Insp Based | -604.39 |  | -604.39 |  |  | 29729.3 | 93 | 29636.3 | 2017-03-27 12:25 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRXR | Transformer Retrofit | 14178.75 |  | 14178.75 |  |  | 375264.12 | 84 | 375180.12 | 2017-03-27 14:28 | 2067-12-31 | 2018-01-01
75084 | 75084IK | KCMCEUG | Emergency UG Corrective Replacement | 160904.63 |  | 160904.63 |  |  | 383491.29 | 93 | 383398.29 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRFS | Circuit Sectionalization | -14799.73 |  | -14799.73 |  |  | 183048.45 | 95 | 182953.45 | 2017-03-27 12:39 | 2067-12-31 | 2018-02-01
75084 | 75084IK | MX8683892 | Declared Circuit - Donaldson (55) 5 | 2027.01 |  | 2027.01 |  |  | 21977.22 | 49876.34 | -27899.12 | 2018-09-27 14:02 | 2022-02-28 | 2018-12-01 | 2021-10-26
75084 | 75084IK | KDLS | Dline Switch Replacements | 23436 |  | 23436 |  |  | 161307.69 | 70 | 161237.69 | 2017-03-27 11:53 | 2067-12-31 | 2018-02-01
75084 | 75084IK | MX0920154 | MXCONV-Declared Circuits Kenton 46 | -242076.36 |  | -242076.36 |  |  | 371378.21 | 118477.7 | 252900.51 | 2018-03-14 18:02 | 2020-07-09 | 2018-06-01 | 2019-12-30
75084 | 75084IK | KRSOH | Residential Cust Adds Single Fam OH | 1382765.56 |  | 1382765.56 |  |  | 3936595.56 | 93 | 3936502.56 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTP1PH | Single PH Transformer Replac Leaker | 48401.21 |  | 48401.21 |  |  | 56542.79 | 93 | 56449.79 | 2017-03-27 13:17 | 2067-12-31 | 2018-07-01
75084 | 75084IK | KPDMCAP | Public Damage OH Capital Replacemen | 167491.56 |  | 167491.56 |  |  | 594789.72 | 80 | 594709.72 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KOTV | Cap Oil to Vac Changeout | 31334.08 |  | 31334.08 |  |  | 74470.11 | 93 | 74377.11 | 2017-03-27 12:10 | 2067-12-31 | 2018-02-01
75084 | 75084IK | KOUTOH | Outage Related OH Cap Replacements | 649203.19 |  | 649203.19 |  |  | 1854350.63 | 93 | 1854257.63 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01
75084 | 75084IK | MX0675382 | Westpack Customer Station | -0.54 |  | -0.54 |  |  | 1423.15 | 10800.23 | -9377.08 | 2017-12-15 14:01 | 2023-06-29 | 2018-03-01
75084 | 75084IK | KRUCSEC | UG Sec/Service Cable Replacement | 82698.02 |  | 82698.02 |  |  | 184913.23 | 93 | 184820.23 | 2017-03-27 13:33 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRUPOH | Residential Customer Upgrade OH | 273467.81 |  | 273467.81 |  |  | 881749.8 | 93 | 881656.8 | 2017-03-27 14:26 | 2067-12-31 | 2017-11-01
75084 | 75084IK | KCIUPOH | C&I Customer Upgrade OH | 252329.09 |  | 252329.09 |  |  | 304260.33 | 93 | 304167.33 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01
75084 | 75084IK | MX1848383 | TBC MXCONV-Capacitor Automation MT. | -16323.71 |  | -16323.71 |  |  | 33190.84 | 57824.65 | -24633.81 | 2018-03-12 14:01 | 2022-09-01 | 2018-08-01
75084 | 75084IK | KRMOH | Residential Cust Adds Multi Fam OH | -39.35 |  | -39.35 |  |  | 26230.76 | 93 | 26137.76 | 2017-03-27 13:07 | 2067-12-31 | 2017-08-01
75084 | 75084IK | MX9127121 | JT-E- TRAEMORE PH A | 17.45 |  | 17.45 |  |  | 54997.6 | 88590.34 | -33592.74 | 2018-07-17 14:02 | 2019-10-11 | 2018-09-01 | 2019-07-31
75084 | 75084IK | MX7639718 | MXCONV-Upgrade Distri Transformer S | -943.02 |  | -943.02 |  |  | -5.4623e-14 | 13028.17 | -13028.17 | 2018-03-19 10:02 | 2020-12-31 | 2018-03-01
75084 | 75084IK | KRTXO | Overhead Transformer Replacement | 34729.42 |  | 34729.42 |  |  | 76598.73 | 93 | 76505.73 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEDT | Emerg DTUG Corrective Replacements | 149674.21 |  | 149674.21 |  |  | 220383.91 | 93 | 220290.91 | 2017-03-24 15:47 | 2067-12-31 | 2018-06-01
75084 | 75084IK | KCMCDT | Non-Emerg DTUG Corrective Replace | -3.16 |  | -3.16 |  |  | 1161.66 | 93 | 1068.66 | 2017-03-24 15:45 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KUGCBINJ | UG Cable Injection | 334.52 |  | 334.52 |  |  | 244584.52 | 95 | 244489.52 | 2017-03-27 14:37 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRTP3PH | Three PH Transformer Replace Leaker | 45976.3 |  | 45976.3 |  |  | 155191.83 | 95 | 155096.83 | 2017-03-27 13:19 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRTXLF | Transformer Livefront Replace | -23865.24 |  | -23865.24 |  |  | 123449.88 | 72691.76 | 50758.12 | 2017-07-27 15:37 | 2067-12-31 | 2018-10-01
75084 | 75084IK | KRTR3PH | Three PH Transformer Replace Dry | 1106.02 |  | 1106.02 |  |  | 30712.96 | 95 | 30617.96 | 2017-03-27 13:26 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRCR | Capacitor Replacements & Assoc UOP | 114312.8 |  | 114312.8 |  |  | 422893.97 | 90 | 422803.97 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOWS | Secondary OH Wire Corr Replacement | 6578.61 |  | 6578.61 |  |  | 12319.81 | 93 | 12226.81 | 2017-03-27 11:47 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KCMCOWP | Primary OH Wire Corr Replacement | 2776.56 |  | 2776.56 |  |  | 11372.92 | 93 | 11279.92 | 2017-03-27 11:33 | 2067-12-31 | 2018-11-01
75084 | 75084IK | MX9998915 | URD Wilder 41 | 38.27 |  | 38.27 |  |  | 16435.71 | 0 | 16435.71 | 2018-04-27 10:01 | 2023-07-29 | 2018-05-01
75084 | 75084IK | KRGR | Regulator replacements | 1097.23 |  | 1097.23 |  |  | 43244.06 | 0 | 43244.06 | 2017-07-27 13:27 | 2067-12-31 | 2017-11-01
75084 | 75084IK | KSVDTUG | Instl/Repl Pump W Stop Valve in Vau | -568.7 |  | -568.7 |  |  | -568.7 | 0 | -568.7 | 2017-12-07 11:41 | 2068-03-31 | 2018-08-01
75084 | 75084IK | KROC | OH Deteriorated Conductor Replace | -6359.95 |  | -6359.95 |  |  | 16070.07 | 0 | 16070.07 | 2018-07-11 10:07 | 2067-12-31 | 2018-11-01
75084 | 75084IK | KET135853 | DET 10135853 Hands 44 310 | 111940.17 |  | 111940.17 |  |  | 1571876.92 | 656630.49 | 915246.43 | 2016-11-07 10:03 | 2020-09-28 | 2016-12-01 | 2019-11-03
75084 | 75084IK | MX8285098 | INFRASTRUCTIURE FOR SUBDIVISION D | -24.75 |  | -24.75 |  |  | 15465.18 | 14166.09 | 1299.09 | 2018-05-09 18:05 | 2019-06-01 | 2018-05-01 | 2019-01-20
75084 | 75084IK | MX0705683 | TDSIC UPGRADE OF CAPACITORS BY ADDI | -911.48 |  | -911.48 |  |  | 23010.4 | 63278.29 | -40267.89 | 2018-03-20 18:02 | 2018-07-31 | 2018-06-01 | 2018-11-24
75084 | 75084IK | MX1281917 | INFRASTRUCTIURE FOR SUBDIVISION D | -8.76 |  | -8.76 |  |  | 9201.16 | 8191.98 | 1009.18 | 2017-11-03 14:01 | 2019-01-31 | 2018-04-01 | 2018-12-19
75084 | 75084IK | MX0090259 | MXCONV-Transformer Retrofit YORK 42 | -235 |  | -235 |  |  | 32375.26 | 42782.63 | -10407.37 | 2018-04-18 14:01 | 2018-12-28 | 2018-06-01 | 2018-11-09
75084 | 75084IK | MX7691568 | Circuit Segementation Self Healing | -43.22 |  | -43.22 |  |  | 63443.34 | 48280.72 | 15162.62 | 2018-05-25 14:02 | 2019-07-01 | 2018-06-01 | 2019-08-13
75084 | 75084IK | MX9579446 | JT- E - Arcadia Highlands Phase 4 | 2.35 |  | 2.35 |  |  | 10852.92 | 12695.07 | -1842.15 | 2018-08-24 18:04 | 2019-08-30 | 2018-09-01 | 2019-07-14
75084 | 75084IK | MX0924912 | MXCONV-JT- E TRIPLE CROWN SUBD SEC | -90.14 |  | -90.14 |  |  | 46540.62 | 213849.76 | -167309.14 | 2017-11-03 14:01 | 2018-03-01 | 2017-11-01 | 2018-05-07
75084 | 75084IK | MX7740641 | JT, E-AOSTA VALLEY PH. 6 | -27.62 |  | -27.62 |  |  | 14007.9 | 19174.35 | -5166.45 | 2018-04-11 18:02 | 2019-06-01 | 2018-04-01 | 2018-12-27
75084 | 75084IK | MX7691570 | Circuit Segmentation Self Healing B | 216.4 |  | 216.4 |  |  | 39183.27 | 44183.81 | -5000.54 | 2018-06-26 18:03 | 2019-07-30 | 2018-07-01 | 2019-05-29
75084 | 75084IK | MX0090254 | MXCONV-Transformer Retrofit LIMABUR | -179.32 |  | -179.32 |  |  | 26164.49 | 52534.55 | -26370.06 | 2018-04-17 14:01 | 2019-06-01 | 2018-06-01 | 2018-11-22
75084 | 75084IK | MX7691569 | Circuit Segementation Self Healing | -890.79 |  | -890.79 |  |  | 84824.82 | 39899.12 | 44925.7 | 2018-06-25 10:02 | 2019-12-29 | 2018-07-01 | 2019-10-31
75084 | 75084IK | MX1236245 | INFRASTRUCTIURE FOR SUBDIVISION D | -102.59 |  | -102.59 |  |  | 46814.04 | 30202.98 | 16611.06 | 2017-11-03 14:01 | 2018-06-01 | 2017-11-01 | 2018-07-12
75084 | 75084IK | MX1655106 | INFRASTRUCTIURE FOR SUBDIVISION D | -45.77 |  | -45.77 |  |  | 22570.37 | 12941.13 | 9629.24 | 2017-11-03 14:01 | 2018-05-18 | 2018-01-01 | 2018-06-15
75084 | 75084IK | MX7691571 | Circuit Segmentation Self Healing B | 49.71 |  | 49.71 |  |  | 50841.38 | 58415 | -7573.62 | 2018-06-27 10:02 | 2019-07-30 | 2018-07-01 | 2019-06-11
75084 | 75084IK | MX7691573 | Circuit Segmentation Self Healing W | 1881.77 |  | 1881.77 |  |  | 52721.97 | 48785.98 | 3935.99 | 2018-06-19 10:01 | 2019-07-30 | 2018-07-01 | 2019-08-18
75084 | 75084IK | MX7691572 | Circuit Segmentation Self Healing B | 19.01 |  | 19.01 |  |  | 37410.2 | 43667.13 | -6256.93 | 2018-06-29 14:03 | 2019-08-14 | 2018-07-01 | 2019-05-12
75084 | 75084IK | MX8683121 | Declared Circuit - Limaburg (189) 1 | 30.55 |  | 30.55 |  |  | 23479.22 | 8916.15 | 14563.07 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-05-27
75084 | 75084IK | MX0169713 | MXCONV-Circuit Sectionalization Bea | -1298.54 |  | -1298.54 |  |  | 26257.51 | 100852.4 | -74594.89 | 2017-11-03 14:01 | 2018-06-30 | 2018-03-01 | 2018-08-21
75084 | 75084IK | MX0090253 | MXCONV-Transformer Retrofit KENTON | -378.62 |  | -378.62 |  |  | 47099.62 | 66741.76 | -19642.14 | 2018-04-18 10:02 | 2019-06-01 | 2018-06-01 | 2019-01-21
75084 | 75084IK | MX2345743 | JT, E-EAGLE RIDGE PH. 2 PT. 2 | -22.43 |  | -22.43 |  |  | 8521.79 | 13650.65 | -5128.86 | 2017-12-18 14:01 | 2018-08-31 | 2017-12-01 | 2018-08-02
75084 | 75084IK | MX7880714 | JT, E-WALTON POINTE PHASE 3 | 5.46 |  | 5.46 |  |  | 28849.07 | 24220.88 | 4628.19 | 2018-04-11 14:01 | 2019-07-31 | 2018-06-01 | 2019-07-21
75084 | 75084IK | MX7972270 | MAJOR IMPROVE DIST RELIABLITY LINE | -7521.96 |  | -7521.96 |  |  | 131833.52 | 87518.4 | 44315.12 | 2018-07-24 14:02 | 2019-09-02 | 2018-08-01 | 2019-05-10
75084 | 75084IK | MX1675871 | INFRASTRUCTIURE FOR SUBDIVISION D | -61.56 |  | -61.56 |  |  | 25172.19 | 28275 | -3102.81 | 2017-11-03 14:01 | 2018-03-01 | 2017-12-01 | 2018-06-12
75084 | 75084IK | MX8684198 | Declared Circuit - Hebron (152) 152 | -797.67 |  | -797.67 |  |  | 37275.68 | 14209.12 | 23066.56 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-09-17
75084 | 75084IK | MX6843545 | INFRASTRUCTIURE FOR SUBDIVISION D | 2.65 |  | 2.65 |  |  | 32308.78 | 17816 | 14492.78 | 2018-01-04 14:01 | 2019-06-22 | 2018-03-01 | 2019-03-19
75084 | 75084IK | MX7838790 | JT, E-ASHLEY OAKS SUBDIVISION | 0.16 |  | 0.16 |  |  | 12362.78 | 9052.39 | 3310.39 | 2018-04-11 14:01 | 2019-11-29 | 2018-06-01 | 2019-06-30
75084 | 75084IK | MX8735624 | JT-E- HARMONY PH.D PT.1 | 5.42 |  | 5.42 |  |  | 18803.43 | 22271.65 | -3468.22 | 2018-08-03 10:02 | 2019-04-18 | 2018-08-01 | 2019-06-10
75084 | 75084IK | MX8684114 | TBC - Declared Circuit - Hebron (15 | -22343.36 |  | -22343.36 |  |  | 1.819e-12 | 3958.41 | -3958.41 | 2018-09-27 14:02 | 2020-12-31 | 2018-12-01
75084 | 75084IK | MX2163149 | TED BUSHELMAN BLVD | -451.64 |  | -451.64 |  |  | 258493.6 | 96365.48 | 162128.12 | 2017-12-13 10:01 | 2018-01-19 | 2018-02-01 | 2018-05-21
75084 | 75084IK | MX1691827 | INFRASTRUCTIURE FOR SUBDIVISION D | -26.42 |  | -26.42 |  |  | 11151.38 | 12916.08 | -1764.7 | 2017-11-03 14:01 | 2018-07-02 | 2017-11-01 | 2018-09-04
75084 | 75084IK | MX0090256 | MXCONV-Transformer Retrofit SILVER | -328.28 |  | -328.28 |  |  | 48955.09 | 120339.21 | -71384.12 | 2018-09-17 10:02 | 2019-06-01 | 2018-09-01 | 2019-01-25
75084 | 75084IK | MX6839574 | COMMERCIAL PRIMARY/SECONDARY/SVC | -1429.81 |  | -1429.81 |  |  | 197867.64 | 168944.61 | 28923.03 | 2018-10-24 18:03 | 2019-07-01 | 2018-11-01 | 2019-02-28
75084 | 75084IK | MX9481816 | INFRASTRUCTIURE FOR SUBDIVISION D | 3.71 |  | 3.71 |  |  | 19181.28 | 12428.57 | 6752.71 | 2018-09-26 10:02 | 2019-08-31 | 2018-09-01 | 2019-06-24
75084 | 75084IK | MX8684039 | Declared Circuit - Oakbrook (210) 2 | 1260.05 |  | 1260.05 |  |  | 26678.01 | 11313.35 | 15364.66 | 2018-09-27 14:02 | 2019-09-13 | 2018-12-01 | 2019-07-23
75084 | 75084IK | MX8452464 | TBC - D-LINE PORTION:SOGOakbrookDon | -1032.58 |  | -1032.58 |  |  | 2.5491e-13 | 32098.48 | -32098.48 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452468 | TBC D-LINE PORTION:SOGOakbrookDona | -1021.47 |  | -1021.47 |  |  | 1.7764e-14 | 33590.87 | -33590.87 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX1845281 | TBC - DLINE PORTION: SEGMENT OF CIR | -8263.47 |  | -8263.47 |  |  | -1.4211e-13 | 32769.79 | -32769.79 | 2019-03-08 18:01 | 2020-12-31 | 2019-05-01
75084 | 75084IK | MX8452467 | TBC - D-LINE PORTION:SOGOakbrookDon | -1997.65 |  | -1997.65 |  |  | -2.5757e-14 | 33965.74 | -33965.74 | 2019-01-16 14:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452447 | D-LINE PORTION:SOG Dixie Mt Zion 31 | -567.12 |  | -567.12 |  |  | -3.6415e-14 | 34181.52 | -34181.52 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8755128 | Det. Conductor - Constance (41) 424 | 291369.5 |  | 291369.5 |  |  | 2133265.66 | 712968.4 | 1420297.26 | 2018-12-17 10:02 | 2020-09-28 | 2019-01-01 | 2020-08-10
75084 | 75084IK | MX1249090 | JT-E-ALEXANDER CIRCLE | -2375.55 |  | -2375.55 |  |  | 23614.73 | 31214.31 | -7599.58 | 2019-01-21 18:02 | 2020-02-24 | 2019-04-01 | 2020-02-09
75084 | 75084IK | MX1816336 | INFRASTRUCTIURE FOR SUBDIVISION D | -5162.12 |  | -5162.12 |  |  | 179372.5 | 226516.58 | -47144.08 | 2019-04-08 18:01 | 2020-01-21 | 2019-05-01 | 2019-12-11
75084 | 75084IK | MX2866326 | KENTUCKY 2019 LINE PATROL OH REPLAC | 383.97 |  | 383.97 |  |  | 383.97 | 8023.11 | -7639.14 | 2020-09-09 10:01 | 2022-11-29 | 2020-10-01
75084 | 75084IK | MX6746469 | ELEC - C/I; - 501 MAIN, COVINGTON - | 1044.05 |  | 1044.05 |  |  | 145869.09 | 118838.8 | 27030.29 | 2018-10-15 18:03 | 2019-09-30 | 2019-01-01 | 2019-07-17
75084 | 75084IK | MX2906469 | JT-E-ALDERBROOK PH 3 PART A | 50649.34 |  | 50649.34 |  |  | 49240.06 | 59798.22 | -10558.16 | 2019-07-31 18:03 | 2020-06-30 | 2019-08-01 | 2020-05-27
75084 | 75084IK | KSBDUG | New Customer Work - Res Subdiv Infr | 282402.4 |  | 282402.4 |  |  | 282402.4 | 0 | 282402.4 | 2019-09-26 10:05 | 2028-04-01 | 2020-01-01
75084 | 75084IK | MX4306278 | JT-E-Aosta Valley - Ph 7 - Part 1 | 42136.83 |  | 42136.83 |  |  | 38483.83 | 31136.62 | 7347.21 | 2019-10-21 14:01 | 2020-09-15 | 2019-12-01 | 2020-08-05
75084 | 75084IK | MX3500363 | JT-E-SANCTUARY VILLAGE PH 1 | 123611.71 |  | 123611.71 |  |  | 123611.71 | 392484.74 | -268873.03 | 2019-08-08 10:01 | 2020-11-23 | 2020-02-01 | 2020-11-16
75084 | 75084IK | MX0494866 | MXCONV-Transformer Retrofit KENTON | 81699.66 |  | 81699.66 |  |  | 82291.19 | 96102.31 | -13811.12 | 2019-11-18 18:01 | 2021-03-25 | 2019-11-01 | 2021-02-23
75084 | 75084IK | MX2263766 | DEN,RESIDENTIAL PRIMARY/SECONDARY/S | 27971.08 |  | 27971.08 |  |  | 54776.09 | 42978.64 | 11797.45 | 2019-04-30 14:01 | 2020-06-18 | 2019-10-01 | 2020-06-09
75084 | 75084IK | MX8452449 | TBC - D-LINE PORTION: SEGMENTATION | -3044.68 |  | -3044.68 |  |  | -1.819e-12 | 35683.15 | -35683.15 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452457 | TBC - D-LINE PORTION:SOGHandsWhiteT | -1322.84 |  | -1322.84 |  |  | -4.5297e-14 | 37813.26 | -37813.26 | 2019-01-21 14:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | KELT3PH | End of Life Pad Transf 3PH Non Leak | 585898.31 |  | 585898.31 |  |  | 585898.31 | 0 | 585898.31 | 2020-01-09 15:04 | 2067-12-31 | 2020-02-01
75084 | 75084IK | MX6405659 | JT, E-EVERGREEN APARTMENTS | 9.02 |  | 9.02 |  |  | 33100.45 | 16371.21 | 16729.24 | 2018-01-09 10:01 | 2019-11-28 | 2019-05-01 | 2019-09-09
75084 | 75084IK | MX8452469 | TBC - D-LINE PORTION:SOGOakbrookDon | -1379.03 |  | -1379.03 |  |  | -1.6431e-13 | 35375.69 | -35375.69 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8452443 | TBC D-LINE PORTION: SEGMENTATION OF | -108.85 |  | -108.85 |  |  | 2.276e-15 | 0 | 2.276e-15 | 2018-12-10 18:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2210676 | JT-E-TUSCANY PH C - SEC 15/16 | -4130.85 |  | -4130.85 |  |  | 37166.83 | 40594.49 | -3427.66 | 2019-04-23 14:01 | 2020-01-13 | 2019-08-01 | 2019-12-10
75084 | 75084IK | KRTXLFCM | CD - Upgd Live Front Trsfr Reactive | 22567.43 |  | 22567.43 |  |  | 70440.42 | 97 | 70343.42 | 2019-03-21 16:21 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX6321718 | Longbranch 44 Part 3 - DKY2747 | 444.6 |  | 444.6 |  |  | 444.6 | 356874.67 | -356430.07 | 2020-12-10 18:02 | 2023-01-29 | 2020-12-01 | 2023-02-13
75084 | 75084IK | MX0044401 | KEG - 494 JONES ROAD - COMMERCIAL P | -1127.47 |  | -1127.47 |  |  | -3825.9 | 109599.01 | -113424.91 | 2019-06-28 14:08 | 2020-02-20 | 2019-07-01 | 2020-02-23
75084 | 75084IK | MX5265973 | MPO - 101 4TH W - PERM ELEC | 250189.97 |  | 250189.97 |  |  | 250189.97 | 170265.46 | 79924.51 | 2020-03-02 18:01 | 2021-03-22 | 2020-07-01 | 2021-03-19
75084 | 75084IK | MX7473884 | Oakbrook 42 Ln Ext DKY2769 | 36510.01 |  | 36510.01 |  |  | 36510.01 | 81317.73 | -44807.72 | 2020-09-16 18:01 | 2022-12-29 | 2020-10-01 | 2022-10-17
75084 | 75084IK | MX5068175 | PJG- 300 Richard Knock Blvd; Beaver | 81814.1 |  | 81814.1 |  |  | 81814.1 | 65923.97 | 15890.13 | 2020-10-05 10:01 | 2021-03-07 | 2020-10-01 | 2021-02-09
75084 | 75084IK | MX0266351 | ST ELIZABETH HOSPITAL, MEDICAL VILL | -33281.29 |  | -33281.29 |  |  | 20117.94 | 120458.98 | -100341.04 | 2019-05-24 10:02 | 2019-12-01 | 2019-06-01 | 2019-12-16
75084 | 75084IK | MX8452462 | TBC D-LINE PORTION:SOGOakbrookDona | -1190.7 |  | -1190.7 |  |  | -7.4607e-14 | 33531.78 | -33531.78 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX7890923 | UPGRADE TO EXISTING SERVICE COMMERC | 354.32 |  | 354.32 |  |  | 354.32 | 243913.75 | -243559.43 | 2020-11-17 10:01 | 2022-11-24 | 2020-11-01 | 2022-10-30
75084 | 75084IK | KDLSCM | CD - OH DLine Switch Repl Reactive | 386.47 |  | 386.47 |  |  | 5144.7 | 70 | 5074.7 | 2019-03-21 16:06 | 2068-03-31 | 2019-07-01
75084 | 75084IK | MX3699429 | TMG- COMM PRIMARY - 4805 AERO PARKW | -5283.82 |  | -5283.82 |  |  | 14056.18 | 66211.76 | -52155.58 | 2019-09-27 14:28 | 2020-02-20 | 2019-10-01 | 2020-02-20
75084 | 75084IK | MX8452460 | TBC - D-LINE PORTION:SOGHandsWhiteT | -1188.58 |  | -1188.58 |  |  | 4.4409e-15 | 35892.4 | -35892.4 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2800852 | TMG, COM. INSTALL PRIM/SEC/SVC - 23 | 10001.63 |  | 10001.63 |  |  | 46722.59 | 52468.31 | -5745.72 | 2019-09-06 08:01 | 2020-03-19 | 2019-10-01 | 2020-04-02
75084 | 75084IK | MX7481259 | Newport Levee xfmr Tie CAK-4378 to | 7847.14 |  | 7847.14 |  |  | 8878.17 | 3356.67 | 5521.5 | 2019-10-22 10:01 | 2020-04-16 | 2019-12-01 | 2020-03-30
75084 | 75084IK | MX2178128 | INFRASTRUCTIURE FOR JT-E-TUSCANY P | -225.91 |  | -225.91 |  |  | 32905.96 | 31359.33 | 1546.63 | 2019-04-08 18:01 | 2019-12-30 | 2019-05-01 | 2019-12-16
75084 | 75084IK | MX2168625 | CABLE UG OTHER TESTED REPLACE SMALL | 151.81 |  | 151.81 |  |  | 1083.09 | 53872.4 | -52789.31 | 2019-03-11 10:01 | 2021-06-29 | 2019-05-01 | 2021-06-28
75084 | 75084IK | MX3602527 | JT-E-WHITESTONE LINKS SECTION 5 | 10929.85 |  | 10929.85 |  |  | 19577.37 | 13063.75 | 6513.62 | 2019-08-07 14:01 | 2020-05-21 | 2019-08-01 | 2020-03-29
75084 | 75084IK | KRRRCM | CD - Recl Elec Repl - Reactive | 46428.53 |  | 46428.53 |  |  | 150605.02 | 95 | 150510.02 | 2019-03-21 15:37 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX1576657 | Verona 41 Inst 4- 1ph Automated Cap | 2736.95 |  | 2736.95 |  |  | 96933.51 | 76863.06 | 20070.45 | 2019-04-18 18:01 | 2021-09-28 | 2019-04-01 | 2021-08-17
75084 | 75084IK | KRNUIF | Removal of non-utilized infrastruct | 888.01 |  | 888.01 |  |  | 888.01 | 0 | 888.01 | 2017-12-13 12:01 | 2068-03-31 | 2020-07-01
75084 | 75084IK | KRUCLGCM | CD - UG Cable Repl LG Reactive | 3270.37 |  | 3270.37 |  |  | 9048.93 | 97 | 8951.93 | 2019-03-21 16:28 | 2068-03-31 | 2019-09-01
75084 | 75084IK | MX1378817 | TMG- COMMERCIAL PRIM/SEC - CVG- CON | 363589.55 |  | 363589.55 |  |  | 363589.55 | 386380.64 | -22791.09 | 2019-10-31 18:01 | 2020-07-09 | 2020-01-01 | 2020-06-30
75084 | 75084IK | MX7103196 | 35 W PIKE EMERGENCY TRANFORMER REPL | 20219.83 |  | 20219.83 |  |  | 20219.83 | 7421.26 | 12798.57 | 2020-06-11 10:01 | 2020-10-20 | 2020-06-01 | 2020-10-11
75084 | 75084IK | MX3072339 | JT-E-Tuscany PH C Sec 10, 13,14 | 16704.58 |  | 16704.58 |  |  | 85282.24 | 139577.83 | -54295.59 | 2019-07-11 10:02 | 2020-05-31 | 2019-08-01 | 2020-04-21
75084 | 75084IK | KRUCSMCM | CD - UG Cable Repl Reactive | 170903.96 |  | 170903.96 |  |  | 441745.33 | 97 | 441648.33 | 2019-03-21 16:34 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX3169670 | POLE REPLACE - KY LANDSLIDE | -29682.45 |  | -29682.45 |  |  | 21719.98 | 41789.69 | -20069.71 | 2019-06-28 14:01 | 2020-01-29 | 2019-06-01 | 2020-01-13
75084 | 75084IK | MX1568931 | JT-E-TIMBER CREEK SUB - PH 1 | 37396.12 |  | 37396.12 |  |  | 55239.2 | 60373.53 | -5134.33 | 2019-04-08 10:01 | 2020-07-29 | 2019-07-01 | 2020-06-04
75084 | 75084IK | MX6785518 | RLM; 411 W 6TH; COVINGTON42; COMMER | 20853.98 |  | 20853.98 |  |  | 20853.98 | 75386.32 | -54532.34 | 2020-09-15 14:01 | 2021-03-31 | 2020-12-01 | 2021-04-05
75084 | 75084IK | MX3255123 | TMG - COM. PRIM/SEC/SVC - 4706 AERO | 112658.25 |  | 112658.25 |  |  | 112658.25 | 65098.74 | 47559.51 | 2019-09-06 08:01 | 2021-01-21 | 2020-09-01 | 2021-01-12
75084 | 75084IK | MX8452466 | TBC D-LINE PORTION:SOGOakbrookDo | -2099.64 |  | -2099.64 |  |  | 4.5475e-13 | 28505.75 | -28505.75 | 2019-01-21 18:02 | 2021-03-01 | 2019-01-01
75084 | 75084IK | MX8452459 | TBC - D-LINE PORTION:SOGHandsWhiteT | -887.98 |  | -887.98 |  |  | 3.6415e-14 | 32996.5 | -32996.5 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2168562 | PROACTIVE REPLACEMENT SECTIONS OF C | 17614.45 |  | 17614.45 |  |  | 17614.45 | 109689.05 | -92074.6 | 2020-09-25 14:01 | 2021-09-28 | 2020-09-01 | 2021-08-01
75084 | 75084IK | MX4982531 | EMERGENT UG EXIT WORK DKY2133 CIRCU | 96131.59 |  | 96131.59 |  |  | 127281.79 | 66711.02 | 60570.77 | 2019-12-05 18:01 | 2020-03-17 | 2019-12-01 | 2020-04-05
75084 | 75084IK | MX4267853 | COMMERCIAL PRIMARY/SECONDARY/SVC | 21637.38 |  | 21637.38 |  |  | 66757.78 | 108693.37 | -41935.59 | 2019-11-25 10:12 | 2020-04-23 | 2019-11-01 | 2020-04-08
75084 | 75084IK | MX2873686 | JT-E-TRAEMORE PH B | 85896.76 |  | 85896.76 |  |  | 74373.76 | 81367.57 | -6993.81 | 2019-06-06 15:12 | 2020-08-11 | 2019-07-01 | 2020-07-12
75084 | 75084IK | MX8452456 | TBC - D-LINE PORTION:SOGHandsWhiteT | -2130.82 |  | -2130.82 |  |  | -8.8818e-14 | 38023.53 | -38023.53 | 2019-01-17 17:22 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX1072643 | Wildcat Run Phase 4 - Part 3 | -1828.93 |  | -1828.93 |  |  | 14943.69 | 25695.51 | -10751.82 | 2019-01-07 14:01 | 2020-02-03 | 2019-01-01 | 2019-12-25
75084 | 75084IK | MX8452471 | TBC D-LINE PORTION:SOGOakbrookDona | -1129.64 |  | -1129.64 |  |  | 2.8422e-14 | 31085.43 | -31085.43 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX2864348 | JT-E-ARCADIA PH I | 34970.08 |  | 34970.08 |  |  | 29388.08 | 39368.3 | -9980.22 | 2019-06-07 10:02 | 2020-09-07 | 2019-07-01 | 2020-08-05
75084 | 75084IK | MX2320502 | INFRASTRUCTIURE FOR SUBDIVISION D | -7678.19 |  | -7678.19 |  |  | 24730.22 | 44965.71 | -20235.49 | 2019-04-26 10:01 | 2020-01-15 | 2019-05-01 | 2019-12-25
75084 | 75084IK | MX6660111 | JT-E-SANCTUARY VILLAGE PHASE 1, PAR | -5598.5 |  | -5598.5 |  |  | -5598.5 | 91842.81 | -97441.31 | 2020-12-18 14:01 | 2021-06-27 | 2020-12-01 | 2021-05-31
75084 | 75084IK | MX9977953 | CABLE UG REPLACE SMALL | 14250.22 |  | 14250.22 |  |  | 98594.29 | 289037.3 | -190443.01 | 2019-04-01 10:01 | 2020-03-26 | 2019-05-01 | 2020-04-26
75084 | 75084IK | MX8452470 | D-LINE PORTION:SOGOakbrookDonaldson | -732.81 |  | -732.81 |  |  | 0 | 31552.49 | -31552.49 | 2019-01-16 14:01 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX1187308 | Deteriorated Conductor - White Towe | 27179.58 |  | 27179.58 |  |  | 27179.58 | 130833.25 | -103653.67 | 2020-08-05 10:01 | 2021-11-11 | 2020-08-01 | 2021-11-02
75084 | 75084IK | MX4559811 | TMG - TEMP SERVICE FOR COMM - AMAZO | 74937.72 |  | 74937.72 |  |  | 27187.01 | 67513.7 | -40326.69 | 2019-11-27 10:01 | 2020-05-14 | 2019-12-01 | 2020-04-27
75084 | 75084IK | MX0705679 | TBC MXCONV-Capacitor Automation CRE | 9283.29 |  | 9283.29 |  |  | 9283.29 | 76143.9 | -66860.61 | 2018-04-09 18:02 | 2022-09-01 | 2020-04-01
75084 | 75084IK | MX8234316 | CAK-32 SWITCHGEAR MANUAL OTHER REPL | 51817.93 |  | 51817.93 |  |  | 51817.93 | 50357.01 | 1460.92 | 2019-08-28 14:01 | 2021-03-25 | 2020-09-01 | 2020-12-30
75084 | 75084IK | MX7196196 | JT-E-STEEPLECHASE SEC 18, PH 2/3 | 55527.87 |  | 55527.87 |  |  | 55527.87 | 55017.77 | 510.1 | 2020-08-05 14:01 | 2021-01-20 | 2020-09-01 | 2020-12-23
75084 | 75084IK | MX1429119 | 107 chambers | 14717.88 |  | 14717.88 |  |  | 198910.9 | 103354.18 | 95556.72 | 2019-03-07 10:01 | 2019-11-01 | 2019-03-01 | 2019-07-30
75084 | 75084IK | MX0494865 | MXCONV-Transformer Retrofit HANDS | 8.29 |  | 8.29 |  |  | 745.97 | 209984.34 | -209238.37 | 2019-11-18 18:01 | 2022-12-29 | 2019-11-01
75084 | 75084IK | MX8452461 | TBC - D-LINE PORTION:SOGHandsWhiteT | -1839.23 |  | -1839.23 |  |  | 1.1824e-13 | 37951.33 | -37951.33 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX4318557 | TBC CONDUCTOR OH NEUTRAL REPLACE | 1944.5 |  | 1944.5 |  |  | 1944.5 | 10533.78 | -8589.28 | 2020-12-09 10:02 | 2022-04-01 | 2020-12-01
75084 | 75084IK | MX0532482 | DEN,RESIDENTIAL ELECTRIC,TAPESTRY A | 9350.16 |  | 9350.16 |  |  | 197001.78 | 158085.63 | 38916.15 | 2019-03-28 10:01 | 2019-10-30 | 2019-04-01 | 2019-09-15
75084 | 75084IK | MX1469801 | TBC D-LINE PORTION: SEGMENTATION O | -6148.6 |  | -6148.6 |  |  | -1.8119e-13 | 35524.8 | -35524.8 | 2019-04-15 10:02 | 2021-03-01 | 2019-05-01
75084 | 75084IK | KGENSWCM | CD - UG SWGR Repl Reactive | 131.74 |  | 131.74 |  |  | 131.74 | 93 | 38.74 | 2019-03-21 16:13 | 2068-03-31 | 2020-05-01
75084 | 75084IK | MX2168034 | Mt Zion UG Exits - DKY2133 | 122027.45 |  | 122027.45 |  |  | 124282.17 | 63516.3 | 60765.87 | 2019-12-17 18:01 | 2020-08-29 | 2019-12-01 | 2020-08-20
75084 | 75084IK | KMHR | Manhole Lid Retrofit Replacement | 542.77 |  | 542.77 |  |  | 1345.4 | 0 | 1345.4 | 2017-07-27 14:56 | 2067-12-31 | 2019-12-01
75084 | 75084IK | MX1816539 | INFRASTRUCTIURE FOR ARCADIA PHASE M | 29526.48 |  | 29526.48 |  |  | 39478.78 | 38855.28 | 623.5 | 2019-05-14 18:01 | 2020-06-02 | 2019-07-01 | 2020-04-29
75084 | 75084IK | MX4746421 | JT-E-NORTH WALTON POINTE PH 5 | 45578.39 |  | 45578.39 |  |  | 45578.39 | 56430.23 | -10851.84 | 2020-02-06 14:01 | 2020-11-29 | 2020-02-01 | 2020-11-18
75084 | 75084IK | MX1349088 | INFRASTRUCTIURE FOR SUBDIVISION D | 742.54 |  | 742.54 |  |  | 45096.57 | 37826.78 | 7269.79 | 2019-02-22 14:02 | 2020-02-27 | 2019-02-01 | 2020-02-02
75084 | 75084IK | MX5851830 | TRANSFORMER UG THREE PHASE END OF L | 30784.1 |  | 30784.1 |  |  | 30784.1 | 50887.03 | -20102.93 | 2020-03-20 10:02 | 2021-03-30 | 2020-11-01 | 2021-04-04
75084 | 75084IK | MX5723882 | MPO - 10 BEACON DR - COMM UPGRADE | 18333.61 |  | 18333.61 |  |  | 18333.61 | 21317.63 | -2984.02 | 2020-03-10 14:01 | 2020-08-09 | 2020-03-01 | 2020-07-02
75084 | 75084IK | KRXRCM | CD - Transf Retrofit - Reactive | 1467.02 |  | 1467.02 |  |  | 1467.02 | 84 | 1383.02 | 2019-03-21 15:58 | 2068-03-31 | 2020-01-01
75084 | 75084IK | MX5977198 | Limaburg 43 Ln Ext to CVG Conrac Bl | 381897.88 |  | 381897.88 |  |  | 381897.88 | 391628.46 | -9730.58 | 2020-08-18 14:01 | 2021-09-28 | 2020-11-01 | 2021-09-19
75084 | 75084IK | MX1172586 | INFRASTRUCTIURE FOR ARBOR SPRINGS | 4902.15 |  | 4902.15 |  |  | 6142.13 | 8730.5 | -2588.37 | 2019-01-16 18:01 | 2020-05-31 | 2019-02-01 | 2020-04-27
75084 | 75084IK | MX3953015 | JT-E-Enclave at South Ridge - Ph 2 | 27020.51 |  | 27020.51 |  |  | 27020.51 | 23971.81 | 3048.7 | 2019-09-17 18:01 | 2020-10-25 | 2020-01-01 | 2020-08-24
75084 | 75084IK | MX8452455 | TBC D-LINE PORTION:SOGHandsWhiteTow | 833.68 |  | 833.68 |  |  | 833.68 | 76145.04 | -75311.36 | 2019-12-23 18:01 | 2022-10-01 | 2020-01-01
75084 | 75084IK | MX3045963 | Declared Circuit - Donaldson 41 - 2 | 136471.44 |  | 136471.44 |  |  | 140640.2 | 628843.53 | -488203.33 | 2019-09-09 14:01 | 2031-02-27 | 2019-11-01
75084 | 75084IK | MX2449322 | JT-E-NORTH WALTON POINTE PH 4 | 3495.04 |  | 3495.04 |  |  | 17690.08 | 15882.2 | 1807.88 | 2019-05-06 18:01 | 2020-04-26 | 2019-05-01 | 2020-03-08
75084 | 75084IK | MX4519392 | JT- E - Park Pointe | -8520.28 |  | -8520.28 |  |  | -8520.28 | 164587.57 | -173107.85 | 2020-03-25 14:01 | 2021-07-08 | 2020-03-01 | 2021-06-27
75084 | 75084IK | MX8452448 | TBC - D-LINE PORTION: SEGMENTATION | -2744.5 |  | -2744.5 |  |  | 2.9488e-13 | 31737.33 | -31737.33 | 2019-01-21 18:02 | 2020-12-31 | 2019-01-01
75084 | 75084IK | MX8234278 | CAK-35 SWITCHGEAR MANUAL OTHER REPL | 47507.81 |  | 47507.81 |  |  | 47507.81 | 53939.54 | -6431.73 | 2019-08-28 10:01 | 2020-09-03 | 2020-05-01 | 2020-09-03
75084 | 75084IK | MX4412975 | Deteriorated Conductor (Wilder 42) | 31561.41 |  | 31561.41 |  |  | 31561.41 | 55117.03 | -23555.62 | 2020-07-02 10:01 | 2022-12-15 | 2020-07-01 | 2022-11-23
75084 | 75084IK | MX5607965 | DEN,VOLTAGE COMPLAINT,632 NELSON PL | 6885.43 |  | 6885.43 |  |  | 6885.43 | 100046.32 | -93160.89 | 2020-03-06 14:01 | 2020-10-29 | 2020-06-01 | 2020-10-25
75084 | 75084IK | MX7682127 | Mt Zion WORK NEEDED TO FINISH FP- D | 14526.24 |  | 14526.24 |  |  | 14526.24 | 13030.02 | 1496.22 | 2020-09-04 18:01 | 2021-06-29 | 2020-09-01 | 2021-06-16
75084 | 75084IK | MX0322031 | LOAD GROWTH, LOAD TRANSFER AND TIE | 14.08 |  | 14.08 |  |  | -6504.63 | 118358.51 | -124863.14 | 2019-06-04 10:02 | 2019-11-28 | 2019-06-01 | 2019-11-14
75084 | 75084IK | MX3835592 | MPO - 91 BANKLICK RD - COMM PERM EL | 46644.35 |  | 46644.35 |  |  | 29555.2 | 50873.74 | -21318.54 | 2019-10-21 14:01 | 2020-09-03 | 2019-10-01 | 2020-08-27
75084 | 75084IK | MX0706061 | INFRASTRUCTIURE FOR SUBDIVISION D | 20488.47 |  | 20488.47 |  |  | 40300 | 24386.62 | 15913.38 | 2018-12-19 10:01 | 2020-03-15 | 2019-10-01 | 2020-03-11
75084 | 75084IK | MX5812475 | KEG - 975 EADS - RESIDENTIAL PRIMAR | 16185.77 |  | 16185.77 |  |  | 16185.77 | 98761.93 | -82576.16 | 2020-03-06 14:01 | 2020-09-28 | 2020-04-01 | 2020-09-06
75084 | 75084IK | MX7154409 | NEW-Circuit Sectionalization Bellev | 39240.94 |  | 39240.94 |  |  | 39240.94 | 91889.28 | -52648.34 | 2020-06-16 10:01 | 2021-02-28 | 2020-08-01 | 2021-01-12
75084 | 75084IK | MX0705681 | TBC MXCONV-Capacitor Automation CRE | 3492.66 |  | 3492.66 |  |  | 3492.66 | 59525.72 | -56033.06 | 2018-05-10 10:01 | 2022-09-01 | 2020-04-01
75084 | 75084IK | MX1572579 | INFRASTRUCTIURE FOR ARCADIA VINEYAR | 33662.81 |  | 33662.81 |  |  | 33662.81 | 24189.95 | 9472.86 | 2019-04-29 14:22 | 2020-11-18 | 2020-06-01 | 2020-11-16
75084 | 75084IK | MX6404515 | JT-E-Tuscany Ph C, Sec 17,19,20 | 62056.29 |  | 62056.29 |  |  | 62056.29 | 63761.47 | -1705.18 | 2020-06-24 10:01 | 2021-02-16 | 2020-06-01 | 2021-02-08
75084 | 75084IK | MX8176166 | JFS - PERM ELEC - LOGISTICS PARK 75 | -10468.05 |  | -10468.05 |  |  | 133612.63 | 110224.02 | 23388.61 | 2019-06-04 10:02 | 2019-12-19 | 2019-07-01 | 2019-12-19
75084 | 75084IK | MX5872280 | TRANSFORMER UG THREE PHASE END OF L | 35314.11 |  | 35314.11 |  |  | 35314.11 | 50562.79 | -15248.68 | 2020-03-31 10:02 | 2021-03-30 | 2020-12-01 | 2021-04-04
75084 | 75084IK | MX4307999 | JT-E-NORTHERN LIGHTS SUBDIVISION | -913.75 |  | -913.75 |  |  | -913.75 | 19320.82 | -20234.57 | 2019-10-15 10:01 | 2021-08-03 | 2020-05-01 | 2021-07-11
75084 | 75084IK | MX2180887 | INFRASTRUCTIURE FOR Cantering Hills | 4994.98 |  | 4994.98 |  |  | 17396.33 | 18427.86 | -1031.53 | 2019-05-20 10:01 | 2020-04-08 | 2019-06-01 | 2020-04-08
75084 | 75084IK | MX2467744 | TMG - COM PRIM/SEC/SVC - CVG CARGO | 16347.21 |  | 16347.21 |  |  | 75788.93 | 59589.57 | 16199.36 | 2019-05-08 18:01 | 2019-11-21 | 2019-07-01 | 2019-11-17
75084 | 75084IK | MX1281268 | JT-E-ARCADIA POD A - PHASE 2 | -2198.8 |  | -2198.8 |  |  | 31171.79 | 23673.14 | 7498.65 | 2019-01-25 18:01 | 2019-12-25 | 2019-08-01 | 2019-12-03
75084 | 75084IK | MX2210518 | INFRASTRUCTIURE FOR WHITESTONE LIN | 5273.6 |  | 5273.6 |  |  | 16332.9 | 16781.72 | -448.82 | 2019-05-08 14:01 | 2020-05-21 | 2019-05-01 | 2020-03-29
75084 | 75084IK | MX3267506 | TJB RESIDENTIAL PRIMARY/SECONDARY/S | 928.33 |  | 928.33 |  |  | 5562.14 | 33975.33 | -28413.19 | 2019-11-08 14:01 | 2020-03-26 | 2019-12-01 | 2020-04-29
75084 | 75084IK | MX4307495 | JT-E-Steeplechase Sec 18 | 7642 |  | 7642 |  |  | 0 | 75393.15 | -75393.15 | 2019-10-21 14:01 | 2021-01-03 | 2019-11-01
75084 | 75084IK | MX8234251 | CAK-30 SWITCHGEAR MANUAL OTHER REPL | 54853.57 |  | 54853.57 |  |  | 54853.57 | 46975.83 | 7877.74 | 2019-08-28 14:01 | 2020-11-28 | 2020-04-01 | 2020-10-13
75084 | 75084IK | KPOLRNF | Pole Reinforcements | 10746.03 |  | 10746.03 |  |  | 10746.03 | 93 | 10653.03 | 2017-03-27 12:32 | 2067-12-31 | 2020-10-01
75084 | SG000440F | SGRFSKY | DEK Sectionalization | 414.04 |  | 414.04 |  |  | 72046.55 | 83 | 71963.55 | 2016-05-16 10:23 | 2025-12-31 | 2017-01-01
75084 | DKY2017 | D2017DL5 | RUSD Donaldson Hwy Retire - DKY2017 | 96351.06 |  | 96351.06 |  |  | 99134.24 | 12270.87 | 86863.37 | 2017-04-25 11:29 | 2023-04-30 | 2017-12-01
75084 | DKY2017 | D2017DL3 | AM 21113304 Davidson Hwy - DKY2017 | 36854.74 |  | 36854.74 |  |  | 179742.69 | 204529.81 | -24787.12 | 2017-04-17 15:00 | 2020-12-18 | 2017-07-01 | 2020-10-26
75084 | DKY2017 | D2017DL1 | TBC AM 21113152 Donaldson Hwy | -2201654.81 |  | -2201654.81 |  |  | 2.2123e-10 | 0 | 2.2123e-10 | 2017-04-17 14:46 | 2021-03-31 | 2017-04-01
75084 | DKY2017 | D2017DL4 | RUSD Donaldson Retire Erlanger Road | 59050.3 |  | 59050.3 |  |  | 59133.22 | 94106.3 | -34973.08 | 2017-04-25 11:01 | 2021-04-30 | 2019-03-01 | 2021-05-10
75084 | DKY2017 | MX1113152 | MXCONV-Donaldson 43 Instl UG Condui | 5823454.74 |  | 5823454.74 |  |  | 7948538.89 | 2636453.11 | 5312085.78 | 2018-11-09 14:02 | 2020-09-28 | 2019-04-01 | 2020-09-22
75084 | DKY2017 | MXA113380 | MXCONV-Donaldson Instl UG Cable DKY | 1905124.79 |  | 1905124.79 |  |  | 2215270.96 | 1304605.52 | 910665.44 | 2019-04-09 14:01 | 2020-11-26 | 2019-04-01 | 2020-10-19
75084 | DKY2017 | D2017DL2 | TBC RUSD Donaldson Install UG | -664739.55 |  | -664739.55 |  |  | 1.7462e-10 | 0 | 1.7462e-10 | 2017-04-25 10:46 | 2021-03-31 | 2019-11-01
75084 | DKY2019 | MX2240021 | Buffington 43 Ln Ext - DKY2019 | 355975.8 |  | 355975.8 |  |  | 403884.32 | 108589.89 | 295294.43 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-16
75084 | DKY2019 | MX2239929 | Buffington 43 UB Pt 2 - DKY2019 | -3828.97 |  | -3828.97 |  |  | 143956.13 | 84712.23 | 59243.9 | 2017-10-18 18:02 | 2020-03-30 | 2018-01-01 | 2020-04-06
75084 | DKY2019 | MX2239881 | TBC-Dixie 46 Ln Ext - DKY2019 | -781.08 |  | -781.08 |  |  | 2.0357e-12 | 183148.71 | -183148.71 | 2017-10-18 18:02 | 2020-06-30 | 2018-01-01
75084 | DKY2019 | MX2239971 | Dixie 45 Ln Ext - DKY2019 | 10118.02 |  | 10118.02 |  |  | 53002.17 | 145406.88 | -92404.71 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-14
75084 | DKY2019 | MX1269760 | Buffington 43 UG - DKY2019 | 58551.52 |  | 58551.52 |  |  | 77821.98 | 20243.51 | 57578.47 | 2018-03-19 14:01 | 2021-05-01 | 2018-04-01 | 2021-03-29
75084 | DKY2019 | D2019DL2 | TBC AM 21269675 Rbld Industrial Rd | -30355.15 |  | -30355.15 |  |  | -1.0232e-12 | 0 | -1.0232e-12 | 2017-05-09 09:46 | 2020-12-31 | 2017-05-01
75084 | DKY2019 | D2019DL3 | TBC AM 21269760 Rbld Industrial Rd | -13223.56 |  | -13223.56 |  |  | -1.1369e-13 | 0 | -1.1369e-13 | 2017-05-09 09:51 | 2020-12-31 | 2017-07-01
75084 | DKY2019 | MX2240623 | Buffington 42 UB Trnsfr - DKY2019 | 217694.71 |  | 217694.71 |  |  | 243424.33 | 11669.98 | 231754.35 | 2017-10-18 18:02 | 2020-10-29 | 2018-01-01 | 2020-10-19
75084 | DKY2019 | D2019DL1 | Dixie 45 46 Exits - DKY2019 | -45203.7 |  | -45203.7 |  |  | 352672.37 | 263109.52 | 89562.85 | 2017-05-09 09:41 | 2019-11-29 | 2017-07-01 | 2019-10-03
75084 | DKY2019 | MX0840788 | Dixie 45-46 Station Exits Overhead | -2216.04 |  | -2216.04 |  |  | 74750.32 | 38462.25 | 36288.07 | 2019-03-22 10:01 | 2019-12-29 | 2019-06-01 | 2019-12-22
75084 | DKY2019 | MX1269037 | Dixie 45-46 Conduit - DKY2019 | 1918.27 |  | 1918.27 |  |  | 474560.71 | 299781.46 | 174779.25 | 2019-03-21 14:01 | 2020-03-30 | 2019-07-01 | 2020-02-12
75084 | TKY1935 | T1935DS1 | Hebron XTR Rel Rpl - TKY1935 | 124487.46 |  | 124487.46 |  |  | 765133.4 | 807940.13 | -42806.73 | 2017-07-13 14:02 | 2020-06-30 | 2017-11-01 | 2020-07-02
75084 | TKY1695 | T1695TS2 | Kenton F966 Rel Repl - TKY1695 | 230794.36 |  | 230794.36 |  |  | 387727.01 | 352819 | 34908.01 | 2016-10-07 18:03 | 2021-02-15 | 2016-12-01 | 2021-03-17
75084 | TKY1695 | T1695TS1 | Buffington F966 CB Rel Repl - TKY16 | 598227.11 |  | 598227.11 |  |  | 2757833.2 | 1153424 | 1604409.2 | 2016-10-07 18:03 | 2020-04-05 | 2016-10-01 | 2020-03-27
75084 | TKY1695 | T1695TS3 | Villa F966 Rel Repl - TKY1695 | 3509.82 |  | 3509.82 |  |  | 2.9104e-11 | 356799 | -356799 | 2016-10-07 18:03 | 2020-12-31 | 2016-12-01
75084 | KUCF61121 | KUC261121 | TBC UG 10261121 Villa 44 | 31.77 |  | 31.77 |  |  | 1783.02 | 131529.73 | -129746.71 | 2017-04-11 14:03 | 2021-07-01 | 2017-06-01
75084 | SG000459F | SG459FB01 | 2018 Midwest Fiber Activation | 1207.39 |  | 1207.39 |  |  | 23641.45 | 37132 | -13490.55 | 2018-02-08 16:47 | 2023-03-01 | 2018-02-01
75084 | SG000459F | SG459FB02 | 2018 Midwest Fiber Activation | 1066.45 |  | 1066.45 |  |  | 8069.07 | 37132 | -29062.93 | 2018-02-08 16:57 | 2023-03-01 | 2018-02-01
75084 | SG000459F | SG459BUFF | DEK Fiber Buffington to Verona | 127859.49 |  | 127859.49 |  |  | 3062536.06 | 2073294.06 | 989242 | 2019-02-28 14:16 | 2020-07-30 | 2019-04-01 | 2020-06-27
75084 | SG000223F | SG223SW | DEE Transmission Health & Risk Mgt | 96880.6 |  | 96880.6 |  |  | 521775.45 | 1016639 | -494863.55 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01
75084 | SG000732F | SG732BTR | SG DEK Battery Replacement | -1176.29 |  | -1176.29 |  |  | 75426.49 | 33850 | 41576.49 | 2017-10-11 15:39 | 2026-03-31 | 2018-02-01
75084 | SG000732F | SG732TR01 | DEK Towers & Shelters - Verona | 1289424.41 |  | 1289424.41 |  |  | 1325747.93 | 968336.2 | 357411.73 | 2018-09-11 15:00 | 2021-09-30 | 2018-09-01 | 2021-04-15
75084 | SG000732F | SG732TR02 | DEK Tower & Shelter - Verona 2 | 10951.36 |  | 10951.36 |  |  | 15658.39 | 968336 | -952677.61 | 2019-01-23 11:05 | 2022-03-31 | 2019-02-01
75084 | SG000732F | SG732TR03 | Communication Tower , Shelter and S | 500.71 |  | 500.71 |  |  | 500.71 | 1519055 | -1518554.29 | 2020-10-30 10:38 | 2023-03-31 | 2020-12-01
75084 | SG000776F | SG776OPS | Transport Terminal Optical EOL | -2003.81 |  | -2003.81 |  |  | 42034.34 | 371480 | -329445.66 | 2018-02-14 12:38 | 2023-03-31 | 2018-03-01
75084 | SG000776F | SG776MTR | Transport Terminal Optical EOL | -19682.84 |  | -19682.84 |  |  | 326096.59 | 1 | 326095.59 | 2018-02-15 09:50 | 2028-03-31 | 2018-03-01
75084 | SG000438F | SGSELFKY | DEK Segmentation & Automation | 707898.1 |  | 707898.1 |  |  | 1052954.78 | 1 | 1052953.78 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01
75084 | SG000438F | SG438LIC | SG DEK YFA Device Licenses | 7316.6 |  | 7316.6 |  |  | 110977.9 | 8250 | 102727.9 | 2018-06-11 10:54 | 2020-03-31 | 2018-07-01 | 2020-06-30
75084 | SG000438F | SG438DOTS | Distribution Operator Training Sim | 10043.08 |  | 10043.08 |  |  | 16175.09 | 1 | 16174.09 | 2019-10-31 16:15 | 2021-09-30 | 2019-10-01 | 2022-03-31
75084 | 75084HW | KHWYR | Highway Relocations Reimb | -1027.02 |  | -1027.02 |  |  | 89106.5 | 80 | 89026.5 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01
75084 | 75084HW | MX9624173 | Ri-I-71/I-75 & KY 536 Inneerchange | 107193.93 |  | 107193.93 |  |  | 109834.35 | 142487.26 | -32652.91 | 2018-09-06 14:02 | 2021-01-14 | 2018-09-01 | 2021-01-19
75084 | 75084HW | KCOU | Make Ready Other Util Attachments | -366682.01 |  | -366682.01 |  |  | 220923.83 | 91 | 220832.83 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01
75084 | 75084HW | KCRFN | Customer Requested Mods Nonreimb | 55797.88 |  | 55797.88 |  |  | 133391.33 | 80 | 133311.33 | 2017-03-24 15:19 | 2067-12-31 | 2018-06-01
75084 | 75084HW | KCRFR | Customer Requested Mods Reimb | 13530.67 |  | 13530.67 |  |  | -28345.41 | 98 | -28443.41 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01
75084 | 75084HW | KHWYN | Highway Relocations Nonreimb | 155546.04 |  | 155546.04 |  |  | 584038.64 | 80 | 583958.64 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01
75084 | 75084HW | MX9612876 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 113755.66 |  | 113755.66 |  |  | 119587.45 | 132976.53 | -13389.08 | 2018-08-28 10:02 | 2021-01-30 | 2018-09-01 | 2021-01-27
75084 | 75084HW | MX1661647 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 418688.45 |  | 418688.45 |  |  | 1170145.01 | 228.31 | 1169916.7 | 2017-11-28 14:01 | 2021-03-18 | 2017-12-01 | 2021-02-21
75084 | 75084HW | MX7090228 | RI-6th St Beautification, undergrou | 213438.26 |  | 213438.26 |  |  | 224564.59 | 150507.84 | 74056.75 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-05-22
75084 | 75084HW | MX7090285 | RI-6th St Beautification, overhead | 145602.92 |  | 145602.92 |  |  | 202245.45 | 155930.4 | 46315.05 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-03-09
75084 | 75084HW | MX9060418 | I-71 /I-75 & KY 536 Interchange (D | 26062.8 |  | 26062.8 |  |  | 60619.66 | 68431.55 | -7811.89 | 2018-07-12 14:02 | 2020-09-30 | 2018-07-01 | 2020-07-26
75084 | 75084HW | KMODC | Other Capital Modifications | 68593.75 |  | 68593.75 |  |  | 119491.54 | 80 | 119411.54 | 2017-03-24 15:33 | 2067-12-31 | 2018-07-01
75084 | 75084HW | MX6295185 | RI-Ky 338 Reconstruction & Sidewalk | -314.4 |  | -314.4 |  |  | 87457.37 | 62118.25 | 25339.12 | 2018-02-09 14:01 | 2018-03-23 | 2018-02-01 | 2018-06-24
75084 | 75084HW | MX8360139 | MXCONV-RI-North Bend Road at World | -1377.11 |  | -1377.11 |  |  | -11066 | 59842.81 | -70908.81 | 2018-05-07 18:02 | 2019-06-01 | 2018-05-01 | 2019-01-16
75084 | 75084HW | MX6295870 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 4744 |  | 4744 |  |  | 176960.46 | 83155.24 | 93805.22 | 2017-11-30 18:02 | 2019-06-01 | 2017-12-01 | 2019-05-21
75084 | 75084HW | MX6342340 | RELOCATION HIGHWAY DOT SPECIFIC PRO | -519.71 |  | -519.71 |  |  | 143198.41 | 109582.18 | 33616.23 | 2017-11-28 14:01 | 2018-07-01 | 2017-12-01 | 2018-07-25
75084 | 75084HW | MX7752157 | RI-Amsterdam Rd Road Improvement | 423.47 |  | 423.47 |  |  | 400299.94 | 163902.06 | 236397.88 | 2018-11-06 14:02 | 2019-09-02 | 2018-11-01 | 2019-07-28
75084 | 75084HW | MX1298730 | RELO; 123 W 4TH; OVATION SITE A - P | -6963.24 |  | -6963.24 |  |  | 11745.01 | 44193.76 | -32448.75 | 2019-03-27 14:01 | 2019-11-28 | 2019-04-01 | 2019-12-30
75084 | 75084HW | MX6277290 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 5102.39 |  | 5102.39 |  |  | 5102.39 | 0 | 5102.39 | 2020-04-02 18:01 | 2023-09-03 | 2020-04-01
75084 | 75084HW | MX2513722 | RI - PARK POINTE RELOCATION; AMSTER | 262609.62 |  | 262609.62 |  |  | 477256.28 | 429103.61 | 48152.67 | 2019-07-29 14:02 | 2021-03-31 | 2019-08-01 | 2021-03-03
75084 | 75084HW | MX2483019 | RI-Reconstruction of the I-75/71 Ri | 592870.06 |  | 592870.06 |  |  | 695697.92 | 383026.87 | 312671.05 | 2019-05-06 10:16 | 2021-06-17 | 2019-05-01 | 2021-06-14
75084 | 75084HW | MX5740957 | S WARD, BELLEVUE, LANDSLIDE RELO | 47578.64 |  | 47578.64 |  |  | 47578.64 | 42074.83 | 5503.81 | 2020-10-01 14:01 | 2021-05-13 | 2020-10-01 | 2021-04-28
75084 | 75084HW | MX5301338 | KENTABOO AVE RECONSTRUCTION - PHASE | 148301.69 |  | 148301.69 |  |  | 148301.69 | 174958.54 | -26656.85 | 2020-07-08 18:01 | 2021-05-04 | 2020-07-01 | 2021-04-28
75084 | 75084HW | MX1072194 | Wendell H. Ford Blvd. Utility Reloc | 284064.31 |  | 284064.31 |  |  | 174041.59 | 144128.97 | 29912.62 | 2019-02-06 18:01 | 2019-11-15 | 2019-05-01 | 2019-10-09
75084 | 75084HW | MX2388911 | RSC - Design - 602 Altamont Ave | 22105.34 |  | 22105.34 |  |  | 232873.04 | 81750.88 | 151122.16 | 2019-07-23 14:01 | 2020-02-13 | 2019-08-01 | 2020-03-26
75084 | 75084HW | MX5888698 | KYTC KY RT 3060 FROGTOWN RD | 23679.7 |  | 23679.7 |  |  | 23679.7 | 104635.29 | -80955.59 | 2020-04-02 18:01 | 2021-09-30 | 2020-04-01 | 2021-08-18
75084 | 75084HW | MX5931078 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 180.74 |  | 180.74 |  |  | 180.74 | 77608.13 | -77427.39 | 2020-04-02 18:01 | 2022-12-29 | 2020-09-01
75084 | 75084HW | MX2481408 | RI-Reconstruction of the (-75/71 Ri | 417845.2 |  | 417845.2 |  |  | 647246.47 | 343628.23 | 303618.24 | 2019-05-06 14:01 | 2021-02-25 | 2019-05-01 | 2021-02-02
75084 | 75084HW | MX2972789 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 400883.06 |  | 400883.06 |  |  | 400883.06 | 295758.93 | 105124.13 | 2019-10-21 18:01 | 2021-08-05 | 2020-04-01 | 2021-08-05
75084 | 75084HW | MX2481659 | RI -Reconstruction of the I-75/71 | 577054.82 |  | 577054.82 |  |  | 592858.56 | 522132.65 | 70725.91 | 2019-05-06 14:01 | 2021-02-25 | 2019-06-01 | 2021-01-27
75084 | 75084HW | MX5847868 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 276003.96 |  | 276003.96 |  |  | 276003.96 | 199520.97 | 76482.99 | 2020-04-02 18:01 | 2021-06-24 | 2020-04-01 | 2021-05-09
75084 | 75084HW | MX2593985 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 14.01 |  | 14.01 |  |  | 14.01 | 0 | 14.01 | 2019-08-09 10:01 | 2021-01-30 | 2020-09-01 | 2021-01-27
75084 | 75084HW | MX0791880 | JFS - JOHN R GREEN - PHASE 1 | -7087.23 |  | -7087.23 |  |  | 44377.63 | 174890.1 | -130512.47 | 2019-02-11 18:01 | 2020-02-27 | 2019-02-01 | 2020-02-23
75084 | 75084HW | MX5776890 | TJB, CLEARANCE ISSUES, CONST REQUIR | 16581.51 |  | 16581.51 |  |  | 16581.51 | 67088.95 | -50507.44 | 2020-03-06 14:01 | 2020-09-24 | 2020-05-01 | 2020-09-03
75084 | 75084HW | MX3659710 | RELO; 123 W 4TH; OVATION SITE A - P | 203567.16 |  | 203567.16 |  |  | 31019.41 | 83683.41 | -52664 | 2019-09-18 10:01 | 2020-03-30 | 2019-12-01 | 2020-08-20
75084 | 75084HW | MX2906263 | OH CABLE CLEARS ISSUES REPLACE | 35681.11 |  | 35681.11 |  |  | 38705.67 | 57085.1 | -18379.43 | 2019-06-24 18:01 | 2020-05-31 | 2019-11-01 | 2020-04-21
75084 | 75084HW | MX7501803 | MAKE-READY,2003MCI0269DEK JOINT USE | -82822.56 |  | -82822.56 |  |  | -82822.56 | 67158.37 | -149980.93 | 2020-07-27 10:01 | 2021-08-29 | 2020-08-01 | 2021-07-21
75084 | 75084HW | MX7793948 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 175429.94 |  | 175429.94 |  |  | 175429.94 | 361208.66 | -185778.72 | 2020-08-17 14:01 | 2021-08-05 | 2020-09-01 | 2021-06-29
75084 | 75084HW | MX2156340 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 418.39 |  | 418.39 |  |  | 418.39 | 1044.91 | -626.52 | 2019-04-24 14:01 | 2022-03-31 | 2020-10-01 | 2022-03-09
75084 | 75084HW | MX3300657 | MT.ZION @ HEMPSTEADE - CONDUIT & CA | -3165.31 |  | -3165.31 |  |  | 18530 | 62826.31 | -44296.31 | 2019-07-11 10:02 | 2019-11-05 | 2019-07-01 | 2019-11-17
75084 | 75084HW | MX1096567 | Exhibit A DEK 1812MCI0545DEK, MAKE- | -68.5 |  | -68.5 |  |  | -21788.93 | 49290.4 | -71079.33 | 2019-08-23 14:01 | 2020-02-23 | 2019-08-01 | 2020-01-26
75084 | 75084HW | MX4550664 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 48644.06 |  | 48644.06 |  |  | 48644.06 | 244472.16 | -195828.1 | 2020-01-16 10:01 | 2021-11-26 | 2020-02-01 | 2021-09-20
75084 | 75084HW | MX6153497 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 19421.3 |  | 19421.3 |  |  | 19421.3 | 18714.91 | 706.39 | 2020-03-19 14:01 | 2020-08-13 | 2020-03-01 | 2020-08-04
75084 | 75084HW | MX2288324 | HANDS PK @ CRYSTAL LAKE DR, RELOCAT | 175322.59 |  | 175322.59 |  |  | 175327.05 | 159886.58 | 15440.47 | 2019-10-03 14:01 | 2020-10-12 | 2019-10-01 | 2020-08-12
75084 | 75084HW | MX4705742 | TMG - CVG / VAULT 12 - PRIMARY METE | -3075.03 |  | -3075.03 |  |  | -3075.03 | 53974.14 | -57049.17 | 2020-05-04 10:01 | 2021-01-28 | 2020-06-01 | 2021-01-11
75084 | 75084HW | MX1276918 | KY 536 - Mt.ZION RD. (CABLE WORK) | 102234.67 |  | 102234.67 |  |  | 106428.95 | 225364.83 | -118935.88 | 2019-02-04 10:02 | 2020-12-24 | 2019-02-01 | 2020-10-28
75084 | 75084HW | MX6240781 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 728.11 |  | 728.11 |  |  | 728.11 | 160184.27 | -159456.16 | 2020-04-02 18:01 | 2022-06-30 | 2020-04-01 | 2022-07-18
75084 | 75084HW | MX6058319 | RI-Reconstruction of the I-75/71 Ri | 80808.12 |  | 80808.12 |  |  | 80808.12 | 66415.04 | 14393.08 | 2020-03-11 10:02 | 2020-09-28 | 2020-04-01 | 2020-09-01
75084 | 75084HW | MX3147077 | HW Crossing Removal - DKYHW2672 | -68.66 |  | -68.66 |  |  | -0.01 | 436.56 | -436.57 | 2019-06-26 14:01 | 2020-08-01 | 2019-08-01 | 2020-10-06
75084 | 75084HW | MX1277017 | KY 536 - Mt. ZION RD. (CONDUIT WORK | 13824.11 |  | 13824.11 |  |  | 17665.49 | 132813.99 | -115148.5 | 2019-02-04 10:02 | 2020-11-12 | 2019-02-01 | 2020-11-01
75084 | 75084HW | MX2423627 | KY 17 S/O GLEASON RD,RELOCATION HIG | -3747.56 |  | -3747.56 |  |  | 102978.35 | 90074.95 | 12903.4 | 2019-10-02 18:01 | 2020-03-16 | 2019-10-01 | 2020-04-01
75084 | 75084HW | MX5357416 | 305 Main St. Bromley KY KDOT Pole r | 7834.14 |  | 7834.14 |  |  | 7834.14 | 21429.18 | -13595.04 | 2020-01-24 14:01 | 2020-06-04 | 2020-02-01 | 2020-05-19
75084 | 75084HW | MX1276812 | KY 536 (OH WORK) | -23796.28 |  | -23796.28 |  |  | 151888.79 | 137747.11 | 14141.68 | 2019-02-04 10:02 | 2021-01-30 | 2019-02-01 | 2021-01-27
75084 | 75084HW | MX3504426 | ST JOSEPH LN, SIDEWALK PROJECT | 16894.68 |  | 16894.68 |  |  | 16894.68 | 44173.09 | -27278.41 | 2019-11-05 10:01 | 2020-05-31 | 2019-11-01 | 2020-05-20
75084 | 75084HW | MX6706663 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 40898.08 |  | 40898.08 |  |  | 40898.08 | 24806.4 | 16091.68 | 2020-05-07 14:01 | 2021-03-01 | 2020-06-01 | 2021-01-19
75084 | 75084HW | MX7240607 | KYTC AA HIGHWAY AT GLENRIDGE INTERS | 22560.37 |  | 22560.37 |  |  | 22560.37 | 30819.59 | -8259.22 | 2020-06-29 10:01 | 2020-12-03 | 2020-07-01 | 2020-11-26
75084 | 75084HW | MX4815423 | HILLVIEW DRIVE PAVEMENT/STORM,RELOC | 7855.19 |  | 7855.19 |  |  | 7855.19 | 16753.81 | -8898.62 | 2020-01-09 14:01 | 2020-07-02 | 2020-03-01 | 2020-06-15
75084 | 75084HW | MX7541330 | MAKE-READY, 2007MCI0336DEK JOINT US | -50251.14 |  | -50251.14 |  |  | -50251.14 | 39389.7 | -89640.84 | 2020-12-01 18:02 | 2021-07-14 | 2020-12-01 | 2021-07-14
75084 | 75084HW | MX6385455 | KY 536 - Mt. Zion (Temp work) | 11976.6 |  | 11976.6 |  |  | 11976.6 | 22151.38 | -10174.78 | 2020-04-14 14:01 | 2020-09-13 | 2020-04-01 | 2020-07-22
75084 | 75084HW | MX5788435 | TMG - COMMERCIAL RELOCATION - 7370 | 30161.49 |  | 30161.49 |  |  | 30161.49 | 109410.3 | -79248.81 | 2020-03-06 14:01 | 2020-12-20 | 2020-07-01 | 2020-11-30
75084 | KECF20154 | KEC920154 | DEC 8920154 Kenton 46 | -507.46 |  | -507.46 |  |  | 3.2969e-12 | 150467.62 | -150467.62 | 2015-10-23 10:05 | 2020-12-31 | 2016-09-01
75084 | CP18SUBK | MX8693329 | CAPITAL Richwood TB2 replace H2, X2 | 4990.39 |  | 4990.39 |  |  | 12471.71 | 9907.33 | 2564.38 | 2018-06-08 10:02 | 2021-03-31 | 2018-10-01 | 2020-08-16
75084 | CP18SUBK | MX8693627 | CAPITAL Richwood TB3 replace X3 Bus | 2392.81 |  | 2392.81 |  |  | 8780.7 | 3280.81 | 5499.89 | 2018-06-08 10:02 | 2022-03-31 | 2018-10-01 | 2022-08-31
75084 | CP18SUBK | MX1464046 | CAPITAL Richwood TB2 replace HS & L | 7045.97 |  | 7045.97 |  |  | 9031.13 | 3468.26 | 5562.87 | 2019-02-12 14:01 | 2021-03-31 | 2019-03-01 | 2020-08-16
75084 | CP18SUBK | MX1488550 | CAPITAL Wilder TB4 replace X0, X1, | 3904.44 |  | 3904.44 |  |  | 21719.87 | 17460.92 | 4258.95 | 2019-02-12 14:01 | 2022-03-31 | 2019-03-01
75084 | CP18SUBK | MX1434007 | CAPITAL Altas TB1 replace HS LA's | 4250.88 |  | 4250.88 |  |  | 6657.87 | 2618.11 | 4039.76 | 2019-02-12 14:01 | 2021-03-31 | 2019-04-01 | 2020-07-15
75084 | CP18SUBK | MX1543301 | CAPITAL Wilder TB1 replace X1, X2, | 28981.76 |  | 28981.76 |  |  | 50298.32 | 20594.56 | 29703.76 | 2019-02-14 18:01 | 2021-03-31 | 2019-09-01 | 2021-03-14
75084 | CP18SUBK | MX1488496 | CAPITAL Wilder TB1 replace H & X & | 3144.37 |  | 3144.37 |  |  | 9197.85 | 5761.61 | 3436.24 | 2019-02-12 14:01 | 2021-03-31 | 2019-03-01 | 2021-03-14
75084 | TKY2204 | T2204DS1 | Buffington Rcfgr 4_5 - TKY2204 | 1348213.95 |  | 1348213.95 |  |  | 2298641.84 | 2109259 | 189382.84 | 2018-05-02 10:01 | 2021-02-20 | 2018-06-01 | 2021-03-30
75084 | TKY2204 | MX8413578 | Buffington TX Feed to Buss Circuits | 17942.37 |  | 17942.37 |  |  | 17942.37 | 904.8 | 17037.57 | 2020-10-13 10:01 | 2021-05-01 | 2020-10-01 | 2021-03-01
75084 | TKY2204 | MX8400391 | Buffington Cable & Term Pole Re-Bui | 128266.48 |  | 128266.48 |  |  | 128266.48 | 47097.51 | 81168.97 | 2020-10-13 10:01 | 2021-03-04 | 2020-11-01 | 2021-03-01
75084 | KARF51805 | KAR851805 | LAR 10851805 Wilder 44 | 123157.29 |  | 123157.29 |  |  | 1040784.86 | 313344.88 | 727439.98 | 2016-07-26 14:03 | 2020-03-31 | 2016-09-01 | 2019-12-17
75084 | TKY1791 | T1791DS1 | Villa TB2 and Bus 2 Swgr Rpl - TKY1 | 1256046.03 |  | 1256046.03 |  |  | 2210954.31 | 2193964.25 | 16990.06 | 2017-05-17 14:03 | 2020-07-14 | 2017-07-01 | 2020-08-24
75084 | TKY1791 | T1791TS1 | Villa 69kV Bus 1 CCVT Rpl - TKY1791 | -584506.99 |  | -584506.99 |  |  | 825651.19 | 814297.47 | 11353.72 | 2017-05-17 14:03 | 2020-07-25 | 2017-08-01 | 2020-08-24
75084 | TKY1791 | T1791DL1 | AM 22674175 Villa 41. | 157451.25 |  | 157451.25 |  |  | 157451.25 | 112128.9 | 45322.35 | 2017-11-02 14:26 | 2020-08-31 | 2020-03-01 | 2020-08-20
75084 | TKY1791 | MX4426283 | Villa Distribution Layout - TKY1791 | 316.19 |  | 316.19 |  |  | 17238.81 | 4514.62 | 12724.19 | 2019-10-16 10:01 | 2020-02-13 | 2019-11-01 | 2020-02-24
75084 | TKY1791 | T1791DL2 | AM 22674438 Villa 42. | -59.26 |  | -59.26 |  |  | -59.26 | 0 | -59.26 | 2017-11-02 14:30 | 2020-08-31 | 2020-01-01 | 2020-06-09
75084 | TKY2128 | T2128TL1 | F966 Rcnfgr Villa Loop TL - TKY2128 | 47154.88 |  | 47154.88 |  |  | 180852.93 | 167889.26 | 12963.67 | 2017-05-30 14:04 | 2020-07-17 | 2018-02-01 | 2020-08-10
75084 | TKY2128 | T2128TS1 | Villa-Inst 69 kV Ring Bus - TKY2128 | 1242918.09 |  | 1242918.09 |  |  | 4362563.64 | 4352926.57 | 9637.07 | 2017-05-30 14:04 | 2020-07-17 | 2017-08-01 | 2020-08-10
75084 | 75084IL | KSLNOLE | Non Ole Street Light Replacements | 5416.78 |  | 5416.78 |  |  | 44717.58 | 58 | 44659.58 | 2017-03-28 09:41 | 2067-04-01 | 2018-02-01
75084 | 75084IL | KCAL | Area Light New Installs | 291553.5 |  | 291553.5 |  |  | 567152.51 | 98 | 567054.51 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KLEDSL | LED Street Light Retrofit | 3655.34 |  | 3655.34 |  |  | 236982 | 58 | 236924 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01
75084 | 75084IL | KSLRPL | Street Light Replacements | 167073.91 |  | 167073.91 |  |  | 363822.16 | 58 | 363764.16 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KALRPL | Area Light Replacements | 58599.71 |  | 58599.71 |  |  | 98795.81 | 58 | 98737.81 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01
75084 | 75084IL | KRUL | UG Cable Lighting Replacements | 3394.99 |  | 3394.99 |  |  | 5676.72 | 91 | 5585.72 | 2017-03-28 09:39 | 2067-04-01 | 2018-05-01
75084 | 75084IL | MX1977699 | BBB, Notre Dame Academy Lighti | 76113.05 |  | 76113.05 |  |  | 163253.77 | 61644.58 | 101609.19 | 2017-11-15 14:01 | 2018-04-03 | 2017-12-01 | 2018-06-03
75084 | 75084IL | KSMCELL | Outdoor Lighting Small Cell Regultd | 1711.63 |  | 1711.63 |  |  | 12716.94 | 0 | 12716.94 | 2017-09-20 15:00 | 2067-04-01 | 2019-03-01
75084 | 75084IL | KBANNER | DEK Streetlight Electric Banners | 629.85 |  | 629.85 |  |  | 2006.59 | 0 | 2006.59 | 2017-09-20 14:53 | 2067-04-01 | 2019-09-01
75084 | 75084IL | MX4010060 | WILDER FIRE STATION & PARK AREA | 19163.83 |  | 19163.83 |  |  | 19163.83 | 98655.86 | -79492.03 | 2020-02-04 18:01 | 2020-11-12 | 2020-05-01 | 2020-10-27
75084 | 75084IL | MX0211957 | TRANSPORT DR UPS BUILDING INSTALL | 42288.93 |  | 42288.93 |  |  | 51130.37 | 36637.07 | 14493.3 | 2019-04-12 10:01 | 2020-03-30 | 2019-04-01 | 2020-04-05
75084 | 75084IL | MX4108382 | 6TH & SCOTT ST UG CONVERSION ST LIG | 155416.06 |  | 155416.06 |  |  | 155416.06 | 106128.95 | 49287.11 | 2020-06-16 18:01 | 2021-03-30 | 2020-10-01 | 2021-03-16
75084 | 75084IL | MX9863276 | CRESCENT SPRINGS INSTALL PART 2 | 55554.86 |  | 55554.86 |  |  | 55554.86 | 51273.61 | 4281.25 | 2020-05-12 10:01 | 2021-02-25 | 2020-05-01 | 2021-02-22
75084 | 75084IL | MX3586213 | CITY OF WILDER STREET LIGHT UPGRADE | -23667.65 |  | -23667.65 |  |  | -23667.65 | 58074.51 | -81742.16 | 2020-02-20 10:01 | 2020-08-06 | 2020-02-01 | 2020-06-28
75084 | 75084IL | MX2019094 | JFS - STREET LIGHT PROJECT -CITY OF | 86393.56 |  | 86393.56 |  |  | 0 | 49935.78 | -49935.78 | 2019-06-06 15:12 | 2021-03-31 | 2019-06-01
75084 | 75084IL | MX0047542 | AREA LIGHT PRIVATE REMOVE/INSTALL | 42.78 |  | 42.78 |  |  | 224624.43 | 141991.5 | 82632.93 | 2018-11-06 10:02 | 2019-12-29 | 2019-01-01 | 2019-12-11
75084 | 75084IL | MX9473912 | SMILE BLDG LIGHTING ERLANGER | 176804.99 |  | 176804.99 |  |  | 215447.2 | 142289.25 | 73157.95 | 2019-03-25 14:01 | 2019-09-30 | 2019-04-01 | 2019-09-29
75084 | 75084IL | KLEDAL | LED Area Light Retrofit | 22.28 |  | 22.28 |  |  | 22.28 | 58 | -35.72 | 2017-03-28 09:35 | 2067-04-01 | 2020-04-01
75084 | 75084IL | MX7650909 | OVATION MUSIC VENUE LIGHTING 4TH & | -4011.9 |  | -4011.9 |  |  | -4011.9 | 40107.76 | -44119.66 | 2020-08-27 14:01 | 2021-03-18 | 2020-10-01 | 2021-03-01
75084 | 75084IL | MX2752398 | MANHATTAN HARBOUR 17 STREETLIGHTS | -341.27 |  | -341.27 |  |  | 127970.66 | 109328.27 | 18642.39 | 2019-06-21 10:01 | 2020-02-13 | 2019-07-01 | 2020-01-14
75084 | SG000468F | SG468MDM | SG DEK Next Gen Cellular | 316417.14 |  | 316417.14 |  |  | 745988.04 | 1684462.49 | -938474.45 | 2017-10-10 12:47 | 2026-03-31 | 2018-01-01 | 2022-08-24
75084 | KIAF05495 | KIA705495 | DA 10705495 Alexandria So | -46.53 |  | -46.53 |  |  | 5851.55 | 53637.18 | -47785.63 | 2017-01-04 10:04 | 2019-03-01 | 2017-04-01 | 2019-01-08
75084 | KECF20153 | KEC920153 | DC 8920153 Bellevue 42 | 343795.16 |  | 343795.16 |  |  | 713719.78 | 298274.18 | 415445.6 | 2015-10-23 10:05 | 2020-03-31 | 2016-09-01 | 2020-01-07
75084 | 75084VM | VDHAZPGKY | VDHAZPGKY | 245435.63 |  | 245435.63 |  |  | 924215.08 | 1 | 924214.08 | 2017-05-25 15:32 | 2050-12-31 | 2018-01-01
75084 | 75084VM | VDREMVCKY | VDREMVCKY | 251171.76 |  | 251171.76 |  |  | 1170904.34 | 1 | 1170903.34 | 2017-05-25 11:52 | 2050-12-30 | 2018-01-01
75084 | SG000586F | SGDLSKY | RUSD DEK D-Line Switch Replacement | -7889.46 |  | -7889.46 |  |  | 264412.19 | 94 | 264318.19 | 2016-12-19 11:23 | 2025-12-31 | 2017-05-01
75084 | DKY2134 | D2134DL2 | AM 21801679 Oakbrook 42 | 300701.66 |  | 300701.66 |  |  | 2107481.62 | 529469.63 | 1578011.99 | 2017-07-25 14:20 | 2019-12-31 | 2018-03-01 | 2020-03-19
75084 | SG000794F | SG794DES | DEK Land Mobile Radio Design | 29489.71 |  | 29489.71 |  |  | 30722.32 | 154508.56 | -123786.24 | 2018-06-15 13:19 | 2025-03-01 | 2018-06-01 | 2021-02-28
75084 | SG000435F | SGCAPATKY | DEK Cap Automation | 1395.51 |  | 1395.51 |  |  | 82934.6 | 83 | 82851.6 | 2016-05-16 10:15 | 2025-12-31 | 2017-01-01
75084 | SG000439F | SGGENSWKY | DEK Switchgear Upgrades-Automation | 888.41 |  | 888.41 |  |  | 13501.73 | 83 | 13418.73 | 2016-05-16 10:22 | 2025-12-31 | 2017-01-01
75084 | SG000439F | MX9412214 | 20BN-1300 - SWITCHGEAR MANUAL OTHER | 2546.91 |  | 2546.91 |  |  | 2546.91 | 103867.86 | -101320.95 | 2019-12-13 10:01 | 2022-01-28 | 2020-07-01 | 2022-01-11
75084 | SG000439F | MX4279797 | SWITCHGEAR AUTO - 20BN-BK-1063 | 43510.67 |  | 43510.67 |  |  | 43510.67 | 123669.03 | -80158.36 | 2019-12-13 10:01 | 2021-01-29 | 2020-09-01 | 2021-01-10
75084 | SG000744F | SG744MTR | DEK GridWAN | 648.37 |  | 648.37 |  |  | 11808.99 | 248821.93 | -237012.94 | 2018-05-25 13:28 | 2021-12-31 | 2018-07-01
75084 | SG000744F | SG744BLK | DEK GridWAN | 50457.19 |  | 50457.19 |  |  | 165347.69 | 248821.93 | -83474.24 | 2018-05-25 13:54 | 2031-03-31 | 2018-11-01
75084 | FARCOSSW | ARCOSSW | ARCOS System Outage Project | 9031.09 |  | 9031.09 |  |  | 139926.35 | 129249 | 10677.35 | 2018-06-10 21:10 | 2022-03-31 | 2018-07-01 | 2022-03-31
75084 | FARCOSSW | ARCOS21 | ARCOS Renewal | 118653.62 |  | 118653.62 |  |  | 118653.62 | 118654 | -0.38 | 2020-12-16 21:41 | 2021-09-30 | 2020-12-01 | 2021-04-25
75084 | TOUTKY | OUT69KY | KY T-line Emergency Repl on 69kV | 82539.43 |  | 82539.43 |  |  | 164142.38 | 6 | 164136.38 | 2017-01-17 10:23 | 2050-12-31 | 2017-01-01
75084 | TOUTKY | TOUTKY01 | Servc rest P1 Due to high winds on | 970036.04 |  | 970036.04 |  |  | 1186762.7 | 18000 | 1168762.7 | 2018-02-09 10:02 | 2021-02-19 | 2018-11-01 | 2021-03-21
75084 | TOUTKY | MX1476595 | F966 X-fer UB for 2 - P1 wood to st | 731.84 |  | 731.84 |  |  | 1466.04 | 2794.53 | -1328.49 | 2019-02-07 10:06 | 2021-07-30 | 2019-12-01 | 2021-06-03
75084 | TOUTKY | MX1040009 | F6785 P1 Pole replace 36BN-350 | 254.61 |  | 254.61 |  |  | 6486.84 | 9054.07 | -2567.23 | 2019-01-02 10:01 | 2019-09-01 | 2019-01-01 | 2019-05-20
75084 | TOUTKY | MX8024108 | F5967 I-275 crossing failure and re | 2506.14 |  | 2506.14 |  |  | 2506.14 | 0 | 2506.14 | 2020-09-08 18:01 | 2021-03-31 | 2020-09-01 | 2020-12-28
75084 | TOUTKY | TOUTKY06 | 2019 Storm #5 restorations for 5966 | 22.51 |  | 22.51 |  |  | -9.0949e-13 | 0 | -9.0949e-13 | 2019-03-21 14:05 | 2020-12-31 | 2019-06-01
75084 | PRTFA | KYPRTF2 | PRTOH P1 Cir 6763 HLP626 | -11653.16 |  | -11653.16 |  |  | -1.5916e-12 | 27000 | -27000 | 2016-12-22 14:57 | 2021-03-31 | 2018-04-01
75084 | DKY2198 | MX7724805 | Constance 41 LN Ext PME at sub - DK | -1060.6 |  | -1060.6 |  |  | 258237.04 | 92830.61 | 165406.43 | 2018-03-20 18:02 | 2020-02-24 | 2018-06-01 | 2020-02-23
75084 | DKY2198 | MX7724731 | Constance 41 Ln Ext Cable - DKY2198 | -293490.63 |  | -293490.63 |  |  | 1341239.48 | 762323.62 | 578915.86 | 2018-03-20 18:02 | 2020-03-30 | 2018-08-01 | 2020-01-28
75084 | DKY2198 | MX7724526 | Constance 41 Ln Ext Pt1 - DKY2198 | 23914.47 |  | 23914.47 |  |  | 1669354.94 | 951049.63 | 718305.31 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2018-07-27
75084 | DKY2198 | MX7724611 | Constance 41-43 LN Ext Pt II - DKY2 | -13871.27 |  | -13871.27 |  |  | 3481544.84 | 186281.75 | 3295263.09 | 2018-03-20 18:02 | 2019-12-29 | 2018-03-01 | 2019-12-05
75084 | DKY2198 | MX7724670 | Constance 41-43 LN Ext Pt III - DKY | -1263.84 |  | -1263.84 |  |  | 1390728.69 | 778204.8 | 612523.89 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2019-08-04
75084 | DKY2198 | MX9545158 | Constance Remove Existing OH - DKY2 | 91235.72 |  | 91235.72 |  |  | 189655.74 | 177911.29 | 11744.45 | 2018-08-22 10:02 | 2022-06-29 | 2019-11-01 | 2022-06-16
75084 | SG000432F | SGRUCKY | DEK Cable Replacement | 31917.35 |  | 31917.35 |  |  | 34531.3 | 83 | 34448.3 | 2016-05-16 10:08 | 2025-12-31 | 2017-01-01
75084 | TKY1901 | T1901TS1 | Buffington TB1 Rpl - TKY1901 | -2461.18 |  | -2461.18 |  |  | 2323345.45 | 2785992 | -462646.55 | 2017-12-14 15:58 | 2020-03-03 | 2018-02-01 | 2020-02-15
75084 | TKY1901 | TKY190101 | Rpl TPU Relays for TB7 | 175000.82 |  | 175000.82 |  |  | 317175.84 | 451134 | -133958.16 | 2018-07-30 10:02 | 2021-06-07 | 2018-07-01 | 2021-07-07
75084 | TKY1901 | T1901DS1 | Buffington Swgr Rpl - TKY1901 | 165687.48 |  | 165687.48 |  |  | 2941651.52 | 3344657 | -403005.48 | 2017-12-04 15:07 | 2020-01-14 | 2018-04-01 | 2020-02-15
75084 | TKY1901 | MX3850173 | TBC Buffington 43 UGFE Rpl - T | -7022.69 |  | -7022.69 |  |  | 4.7251e-13 | 0 | 4.7251e-13 | 2019-08-29 14:01 | 2021-03-01 | 2019-10-01
75084 | TKY1901 | MX3850088 | Buffington 41 UGFE Rpl - TKY1901 | 1616.99 |  | 1616.99 |  |  | 97562.27 | 12112.08 | 85450.19 | 2019-08-29 14:01 | 2020-03-30 | 2019-10-01 | 2020-02-11
75084 | TKY1901 | MX3850163 | Buffington 42 UGFE Rpl - TKY1901 | 580.81 |  | 580.81 |  |  | 52204.23 | 0 | 52204.23 | 2019-08-29 14:01 | 2022-03-31 | 2019-09-01
75084 | TKY2227 | T2227TL2 | F5967 Decoursey Pole Repl TL | -7785.75 |  | -7785.75 |  |  | 10478.74 | 6725687 | -6715208.26 | 2018-04-30 14:01 | 2025-10-13 | 2018-09-01
75084 | TKY2227 | T2227TL1 | F5967 Claryville Pole Repl TL | -217574.67 |  | -217574.67 |  |  | 10314.14 | 7186714 | -7176399.86 | 2018-04-30 14:01 | 2025-11-08 | 2018-09-01
75084 | TKY2227 | TKY222702 | F5967 Hwy 177 Decoursey Sub | -3014.42 |  | -3014.42 |  |  | 119.33 | 0 | 119.33 | 2019-04-29 14:22 | 2025-10-03 | 2019-07-01
75084 | TKY2227 | TKY222701 | F5967 Licking River Crossing Marsh | -6744.34 |  | -6744.34 |  |  | 209.23 | 0 | 209.23 | 2019-04-29 14:22 | 2025-10-03 | 2019-10-01
75084 | SG000792F | SG792SW | SG DEE Gen Liab Claim Anlytic - 792 | 900.23 |  | 900.23 |  |  | 36289.04 | 22428.18 | 13860.86 | 2018-07-25 14:52 | 2020-03-31 | 2018-07-01 | 2020-02-29
75084 | KECF20155 | KEC920155 | DEC 8920155 Oakbrook 41 | 23005.97 |  | 23005.97 |  |  | 92956.17 | 18342.29 | 74613.88 | 2015-10-26 18:05 | 2020-10-20 | 2016-09-01 | 2020-10-07
75084 | ICPRJDSTR | ICCONSTRD | Interconnection Capital Project | 9170.4 |  | 9170.4 |  |  | 15725.26 | 1 | 15724.26 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01
75084 | SG000795F | SG795SW | SG DEE Auto Mter Provisioning - 795 | 189.99 |  | 189.99 |  |  | 11001.33 | 13121 | -2119.67 | 2018-07-03 13:02 | 2020-02-15 | 2018-10-01 | 2020-03-31
75084 | SG000442F | SGPILCKY | DEK PILC Reactive | 429.91 |  | 429.91 |  |  | 114555.35 | 83 | 114472.35 | 2016-05-16 10:05 | 2025-12-31 | 2017-01-01
75084 | KYTOOLF | TKYTOOL | Transmission Capital Tool Purchases | -4377.97 |  | -4377.97 |  |  | 163644.9 | 100 | 163544.9 | 2017-11-16 13:07 | 2050-12-31 | 2017-11-01
75084 | SG990113F | SCMCOWSKY | SG-Sec OH Wire Cor Replcmnt DMWKY | -567.99 |  | -567.99 |  |  | 72364.01 | 1 | 72363.01 | 2017-04-03 14:03 | 2050-12-31 | 2018-03-01
75084 | CP17TBRK | 17TB15 | Constance Repl Bk1 Bush | 42971.42 |  | 42971.42 |  |  | 50127.4 | 49552.5 | 574.9 | 2017-03-23 14:29 | 2019-03-31 | 2017-10-01 | 2020-06-02
75084 | CP17TBRK | MX6575892 | Empire Repl H1, H2, H3 bushings on | 9326.99 |  | 9326.99 |  |  | 16736.04 | 10697.21 | 6038.83 | 2017-12-07 18:02 | 2021-03-31 | 2019-11-01 | 2020-08-04
75084 | SG000770F | SG770MAS | 2018 MAS Radio | 72281.08 |  | 72281.08 |  |  | 224786.4 | 112986 | 111800.4 | 2018-02-13 17:18 | 2019-03-31 | 2018-02-01
75084 | SG000797F | SG797SVRS | SG DEE FND Upgrade - 797 | 378.49 |  | 378.49 |  |  | 6811.67 | 2476 | 4335.67 | 2018-08-14 17:33 | 2020-07-06 | 2018-09-01 | 2020-06-11
75084 | SG000797F | SG797SW | SG DEE FND Upgrade - 797 | 3556.31 |  | 3556.31 |  |  | 26836.52 | 18436 | 8400.52 | 2018-08-14 17:01 | 2020-07-06 | 2018-09-01 | 2020-06-11
75084 | SG000437F | SGHYDRKY | DEK Recloser Replacements | 57191.35 |  | 57191.35 |  |  | 60140.01 | 83 | 60057.01 | 2016-05-16 10:20 | 2025-12-31 | 2016-10-01
75084 | DEMERKY | MX7048752 | Covington Repl Cooling Fans TB1 | -252.31 |  | -252.31 |  |  | 12864.01 | 7451.28 | 5412.73 | 2018-01-23 20:20 | 2020-03-31 | 2018-01-01 | 2019-10-26
75084 | DEMERKY | MX1490615 | CAPITAL Villa TB1 replace X0, X1, X | 25301.03 |  | 25301.03 |  |  | 32144.63 | 9790.92 | 22353.71 | 2019-02-12 14:01 | 2021-03-31 | 2019-06-01 | 2020-12-30
75084 | DEMERKY | MXA085468 | CAPITAL Donaldson replace Phase B T | 26619.58 |  | 26619.58 |  |  | 26619.58 | 21685.42 | 4934.16 | 2020-01-16 18:07 | 2021-03-31 | 2020-08-01 | 2021-02-01
75084 | DEMERKY | BUFF45 | Buffinton Repl Bk45 CT's | -826.83 |  | -826.83 |  |  | 64366.79 | 61273.46 | 3093.33 | 2019-09-06 12:00 | 2020-06-30 | 2019-09-01 | 2019-12-31
75084 | DEMERKY | MX1565883 | CAPITAL Cold Spring Circuit 49 repl | -29060.16 |  | -29060.16 |  |  | -7.3896e-13 | 29561.4 | -29561.4 | 2019-02-14 10:01 | 2020-12-31 | 2019-02-01
75084 | DEMERKY | MX4792376 | CAPITAL Claryville Cir 43 Phase C V | 23503.29 |  | 23503.29 |  |  | 23503.29 | 19798.1 | 3705.19 | 2019-12-04 14:01 | 2021-03-31 | 2020-01-01 | 2020-05-10
75084 | DEMERKY | MX3926129 | CAPITAL Florence TB4 replace 1 pump | 1224.18 |  | 1224.18 |  |  | 1224.18 | 12973.9 | -11749.72 | 2019-09-05 16:16 | 2021-03-31 | 2020-01-01
75084 | DEMERKY | MX7213742 | CAPITAL Dixie TB2 replace 3 Fans | 3597.73 |  | 3597.73 |  |  | 3597.73 | 11462.04 | -7864.31 | 2020-06-24 10:01 | 2021-03-31 | 2020-09-01 | 2021-01-24
75084 | DEMERKY | MX3310258 | CAPITAL White Tower replace 3 Singl | -679.4 |  | -679.4 |  |  | 34745 | 31090.41 | 3654.59 | 2019-07-11 10:02 | 2020-03-30 | 2019-07-01 | 2019-10-19
75084 | DEMERKY | MX4946544 | CAPITAL Alexandria South TB1 replac | 2714.24 |  | 2714.24 |  |  | 2714.24 | 7569.04 | -4854.8 | 2019-12-04 14:01 | 2022-03-31 | 2020-08-01
75084 | DEMERKY | MX6022220 | CAPITAL Marshall Cir 41 replace Lig | 1194.74 |  | 1194.74 |  |  | 1194.74 | 9579.6 | -8384.86 | 2020-03-06 14:01 | 2021-03-31 | 2020-03-01 | 2020-06-19
75084 | DEMERKY | MX7213708 | CAPITAL Crescent TB1 replace Fan | 2995.52 |  | 2995.52 |  |  | 2995.52 | 10299.59 | -7304.07 | 2020-06-22 18:01 | 2021-09-30 | 2020-10-01 | 2021-04-07
75084 | DEMERKY | MX5091197 | CAPITAL Alexandria South replace st | 1846.59 |  | 1846.59 |  |  | 1846.59 | 10303.01 | -8456.42 | 2019-12-17 18:01 | 2021-03-31 | 2020-06-01 | 2020-08-24
75084 | DEMERKY | MX7213764 | CAPITAL White Tower TB1 replace 2 F | 2454.94 |  | 2454.94 |  |  | 2454.94 | 10630.25 | -8175.31 | 2020-06-22 18:01 | 2021-03-31 | 2020-09-01 | 2021-01-20
75084 | DEMERKY | MX5713838 | CAPITAL Beaver Tb1 & Cir 41 replace | 13578.31 |  | 13578.31 |  |  | 13578.31 | 23036.02 | -9457.71 | 2020-02-05 18:01 | 2021-03-31 | 2020-02-01 | 2020-05-13
75084 | SG000444F | SGRTRKY | DEK Upgrade Livefront Transformers | 60290.26 |  | 60290.26 |  |  | 62027.85 | 83 | 61944.85 | 2016-05-16 10:12 | 2025-12-31 | 2016-07-01
75084 | KCTFOOL | KCTOOL | TOOLS BLANKET | 71609.67 |  | 71609.67 |  |  | 297025.16 | 1 | 297024.16 | 2018-07-27 15:23 | 2069-04-01 | 2018-11-01
75084 | KUCF48388 | KUC348388 | TBC UG 10348388 Richwood 43 | -309.67 |  | -309.67 |  |  | 5928.3 | 0 | 5928.3 | 2017-04-11 14:03 | 2021-09-30 | 2017-06-01
75084 | KUCF48450 | KUC348450 | UG 10348450 Crescent 44 | 38.67 |  | 38.67 |  |  | 2566.64 | 0 | 2566.64 | 2017-04-11 14:03 | 2022-06-30 | 2017-10-01
75084 | KUCF48397 | KUC348397 | RUC 10348397. Cable repla | -9805.46 |  | -9805.46 |  |  | 201900.29 | 99264.17 | 102636.12 | 2017-06-07 18:04 | 2019-03-01 | 2017-10-01 | 2019-01-27
75084 | DKY1931 | D1931DL2 | TBC AM 10895849 General Dr Part 2 | 212.48 |  | 212.48 |  |  | 18443.24 | 0 | 18443.24 | 2016-07-29 14:18 | 2021-08-01 | 2017-05-01
75084 | DKY1931 | D1931DL1 | AM 10894240 General Drive Part 1 | 2.81 |  | 2.81 |  |  | 195269.13 | 87223.94 | 108045.19 | 2016-07-29 14:11 | 2018-03-15 | 2016-08-01 | 2017-08-18
75084 | M170111 | M17011101 | Litton Sub Prop Purch | 7168.58 |  | 7168.58 |  |  | 56007.67 | 1873674 | -1817666.33 | 2018-08-20 18:03 | 2022-02-05 | 2018-08-01 | 2021-10-09
75084 | M180077 | M18007706 | T LIne RLE - Oakbrook-Aero-Woodspoi | 64131.75 |  | 64131.75 |  |  | 229936.48 | 241552 | -11615.52 | 2018-11-08 18:02 | 2020-09-26 | 2018-12-01 | 2020-09-30
75084 | M180077 | M18007702 | Aero Substation - New Sub | 7150063.92 |  | 7150063.92 |  |  | 8035004.11 | 9181543 | -1146538.89 | 2018-11-08 18:02 | 2021-02-27 | 2018-11-01 | 2021-03-16
75084 | M180077 | M18007704 | Oakbrook Substation | 4787965.47 |  | 4787965.47 |  |  | 5629510.47 | 6995209 | -1365698.53 | 2018-11-08 18:02 | 2021-02-06 | 2018-12-01 | 2021-02-09
75084 | M180077 | M18007705 | 138kV Oakbrook to Aero Line | 1555048.17 |  | 1555048.17 |  |  | 1626857.58 | 1813508 | -186650.42 | 2018-11-08 18:02 | 2021-02-05 | 2018-12-01 | 2021-02-11
75084 | M180077 | M18007703 | 138KV F23983 Woodspoint to Aero | -774.71 |  | -774.71 |  |  | -2.9104e-11 | 0 | -2.9104e-11 | 2018-11-08 18:02 | 2020-12-27 | 2018-12-01
75084 | M180077 | M18007701 | Woodspoint Substation | -33390.94 |  | -33390.94 |  |  | 7.4238e-11 | 0 | 7.4238e-11 | 2018-11-08 18:02 | 2021-02-19 | 2018-12-01
75084 | M180077 | M18007708 | 138kV F6782 Florence to Woodspoint | -2.21 |  | -2.21 |  |  | 5.0515e-15 | 0 | 5.0515e-15 | 2019-02-06 14:05 | 2021-02-06 | 2019-08-01
75084 | M180077 | MX4580155 | Oakbrook D-Line Relo - M180077 | 51489.79 |  | 51489.79 |  |  | 78187.1 | 80415.64 | -2228.54 | 2019-10-30 14:01 | 2020-10-04 | 2019-11-01 | 2020-08-30
75084 | M180077 | M18007707 | Buffington Relay Upgrade for 6763 | 193247.96 |  | 193247.96 |  |  | 284927.21 | 284384.67 | 542.54 | 2019-01-28 10:02 | 2020-10-18 | 2019-03-01 | 2020-08-20
75084 | DKY2131 | D2131DL3 | AM 21798304 Hands 45 | 495859.94 |  | 495859.94 |  |  | 515395.05 | 217039.47 | 298355.58 | 2017-07-25 13:52 | 2020-07-16 | 2017-11-01 | 2020-07-16
75084 | DKY2131 | D2131DL1 | AM 21797163 Hands 45 - DKY2131 | -7955.4 |  | -7955.4 |  |  | 598348.14 | 378745.87 | 219602.27 | 2017-07-25 13:41 | 2019-12-14 | 2017-10-01 | 2019-11-24
75084 | DKY2131 | MX5764593 | Kenton 42 - Highway Crossing | 4136.02 |  | 4136.02 |  |  | 4136.02 | 93286.16 | -89150.14 | 2020-05-06 14:01 | 2023-03-31 | 2020-10-01
75084 | DKY2131 | MX2583979 | Hands 45 UG Cable Install - DKY2131 | 120893.1 |  | 120893.1 |  |  | 120893.1 | 192217.89 | -71324.79 | 2019-06-11 14:01 | 2020-11-26 | 2020-02-01 | 2020-10-28
75084 | DKY2131 | D2131DL2 | AM 21798154 Kenton 42 | 217024.92 |  | 217024.92 |  |  | 217891.74 | 179482.88 | 38408.86 | 2017-07-25 13:46 | 2020-11-26 | 2019-04-01 | 2020-10-07
75084 | TKY2188 | MX9749639 | TBC Augustine F5985 12kV Rbld UB | -7741.92 |  | -7741.92 |  |  | -1.6698e-12 | 0 | -1.6698e-12 | 2018-09-07 10:02 | 2020-12-31 | 2018-11-01
75084 | TKY2188 | T2188DS1 | Augustine_Instl 22_4MVA XTR - TKY2 | 8742.97 |  | 8742.97 |  |  | 3222744.89 | 2593925.42 | 628819.47 | 2017-07-06 13:26 | 2019-02-15 | 2017-07-01 | 2019-01-27
75084 | SG00359F | SG359SW | SG SADM Software - 359 | 3250.28 |  | 3250.28 |  |  | 32451.09 | 227863.84 | -195412.75 | 2018-09-27 06:52 | 2022-12-01 | 2018-09-01
75084 | SG00359F | SG359HW | SG SADM Hardware - 359 | 0.26 |  | 0.26 |  |  | 79.94 | 11355.38 | -11275.44 | 2018-09-28 16:48 | 2022-12-01 | 2019-01-01
75084 | SG00359F | SG359SW2 | SG SADM Software - 359 | 4210.61 |  | 4210.61 |  |  | 63875.82 | 227863.84 | -163988.02 | 2019-08-15 08:00 | 2022-12-01 | 2019-09-01
75084 | SG00359F | SG359NDD | SG SADM SW New Device Driver - 359 | -0.07 |  | -0.07 |  |  | 0 | 0 | 0 | 2018-09-28 16:17 | 2020-05-01 | 2019-07-01
75084 | DKY2132 | DKY213201 | Longbranch EKPC 138kV Loop TS | 502935.37 |  | 502935.37 |  |  | 665337.75 | 1583233.98 | -917896.23 | 2018-06-21 10:05 | 2021-07-05 | 2018-09-01 | 2021-08-04
75084 | DKY2132 | DKY213202 | Longbranch Inst XFMR 2 DS | 1581309.31 |  | 1581309.31 |  |  | 1856525.3 | 3128772.08 | -1272246.78 | 2018-06-21 10:05 | 2021-08-09 | 2019-02-01 | 2021-09-08
75084 | DKY2132 | DKY213203 | Longbranch EKPC CIR 6785 TL | 6551.74 |  | 6551.74 |  |  | 10458.31 | 127025.26 | -116566.95 | 2018-06-21 10:05 | 2021-09-07 | 2019-05-01 | 2021-08-04
75084 | DKY2132 | MX8763054 | Longbranch 43-44 UG - DKY2132 | 67603.91 |  | 67603.91 |  |  | 67603.91 | 71912.58 | -4308.67 | 2018-07-05 10:02 | 2023-03-31 | 2020-06-01
75084 | DKY2132 | MX8762998 | Longbranch 44 Part 1 - DKY2132 | 36321.94 |  | 36321.94 |  |  | 36321.94 | 93589.52 | -57267.58 | 2018-12-07 10:01 | 2022-06-29 | 2020-06-01 | 2022-05-30
75084 | DKY2132 | MX9015414 | Longbranch 44 Part 2 - DKY2132 | 143048.64 |  | 143048.64 |  |  | 143048.64 | 527718.36 | -384669.72 | 2018-12-07 10:01 | 2022-11-29 | 2020-06-01 | 2022-12-18
75084 | DKY2132 | MX8762834 | Longbranch 43 - DKY2132 | 26749.31 |  | 26749.31 |  |  | 26749.31 | 8841.68 | 17907.63 | 2018-07-05 10:02 | 2021-01-29 | 2020-06-01 | 2020-12-30
75084 | TKY1904 | TKY190401 | Buffington F6761 Rel Rpl | 570.26 |  | 570.26 |  |  | 15900.22 | 0 | 15900.22 | 2018-08-30 14:02 | 2025-06-20 | 2019-01-01
75084 | SGAMIDMS | SGADMS33 | SG Upgrade Alstom DMS to ver 3.3 | 0.24 |  | 0.24 |  |  | 136474.33 | 68579 | 67895.33 | 2014-12-18 | 2016-07-20 | 2014-12-01 | 2016-07-15
75084 | SGAMIDMS | SGADMS32 | SG Upgrade to DMS ver 3.2 | 0.06 |  | 0.06 |  |  | 51858.42 | 250000 | -198141.58 | 2014-06-17 | 2016-02-20 | 2014-06-01 | 2015-03-31
75084 | SGETOASF | SGETOAS | SG TOA Replacement Software | 1661.62 |  | 1661.62 |  |  | 561551 | 208124 | 353427 | 2015-04-06 13:58 | 2020-03-31 | 2015-05-01 | 2019-10-20
75084 | KHRF51813 | KHR451813 | RI 10451813 5310 Madison | 5.66 |  | 5.66 |  |  | 61686.34 | 45244.52 | 16441.82 | 2016-12-05 14:04 | 2017-08-15 | 2016-12-01 | 2018-01-29
75084 | KHRF53148 | KHR653148 | DOT 20653148 Ky 236 Mt Zion | 479.76 |  | 479.76 |  |  | 682561.09 | 265402.16 | 417158.93 | 2017-02-13 14:04 | 2018-03-31 | 2017-03-01 | 2018-05-03
75084 | TKY1611 | MX1490565 | Augustine Bus 5 Rep - TKY1611 | -269.75 |  | -269.75 |  |  | 11928.48 | 2.67 | 11925.81 | 2019-02-12 14:01 | 2019-12-30 | 2019-03-01 | 2019-05-26
75084 | DKY2018 | D2018DS1 | Dixie BK 4 - DKY2018 - DKY2018 | 14259.7 |  | 14259.7 |  |  | 2528906.54 | 3407443 | -878536.46 | 2017-06-07 07:50 | 2019-04-23 | 2017-08-01 | 2019-05-01
75084 | DKY2018 | D2018TL1 | Dixie 6764 Line Relo TL - DKY2018 | 5.83 |  | 5.83 |  |  | 19086.62 | 135025 | -115938.38 | 2017-06-07 08:15 | 2019-03-01 | 2017-11-01 | 2019-02-21
75084 | DKY2018 | D2018TS1 | Dixie 69kV Loop - DKY2018 | 23201.17 |  | 23201.17 |  |  | 514883.21 | 1145705 | -630821.79 | 2017-06-07 07:42 | 2019-04-23 | 2017-07-01 | 2019-05-01
75084 | DKY2018 | MX9533906 | Dixie Bank 4 Bus Duct Tie - DKY2018 | 0.02 |  | 0.02 |  |  | 17999.28 | 5192.15 | 12807.13 | 2018-08-24 10:02 | 2019-09-01 | 2018-11-01 | 2019-05-01
75084 | DKY2151 | D2151DL1 | AM 20710413 Crittenden Gen Intrc | -3.09 |  | -3.09 |  |  | 123648.77 | 75335.28 | 48313.49 | 2017-02-14 10:22 | 2018-07-31 | 2017-03-01 | 2018-03-15
75084 | DKY1912 | D1912DS1 | Covington Xtr 2_RUSD - DKY1912 | 4439.5 |  | 4439.5 |  |  | 3040390.6 | 2776527.3 | 263863.3 | 2016-08-19 09:12 | 2017-09-01 | 2016-09-01 | 2018-08-19
75084 | AMKY0960 | H2111 | Kenton Sub 13kV Bus 3l - AMKY0960 | 28979.83 |  | 28979.83 |  |  | 1492330.81 | 823726 | 668604.81 | 2014-02-18 | 2019-02-16 | 2014-03-01 | 2019-04-09
75084 | AMKY0960 | MX0792827 | TBC Kenton Station Exits - AMKY | -28251 |  | -28251 |  |  | 0 | 0 | 0 | 2018-12-07 10:01 | 2020-12-31 | 2019-01-01
75084 | DKY2150 | D2150DL1 | AM 20709498 Verona 42 Rbld | 8.93 |  | 8.93 |  |  | 302463.88 | 129954.31 | 172509.57 | 2017-02-14 10:11 | 2018-03-31 | 2017-02-01 | 2018-02-16
75084 | SG000726F | SG726SVRS | SG DEE AMI BlueCat Scale - 726 | 0.01 |  | 0.01 |  |  | 821.16 | 2783 | -1961.84 | 2017-06-29 15:36 | 2018-03-28 | 2017-07-01 | 2018-05-23
75084 | KHRF51720 | KHR851720 | RI 11851720 Rice Pike | -330.01 |  | -330.01 |  |  | 319196.74 | 75014.92 | 244181.82 | 2017-04-13 14:02 | 2018-05-01 | 2017-04-01 | 2018-07-04
75084 | DKY2127 | DKY212701 | Verona New 69kV V structure - DKY21 | 3068.16 |  | 3068.16 |  |  | 1339176.24 | 726368 | 612808.24 | 2018-01-25 14:02 | 2019-10-15 | 2018-04-01 | 2019-11-15
75084 | DKY2127 | DKY212702 | Verona BK 2 - DKY2127 | 371.88 |  | 371.88 |  |  | 1672103.37 | 2299493 | -627389.63 | 2018-01-25 14:02 | 2019-10-15 | 2018-04-01 | 2019-11-15
75084 | DKY2127 | MX1674974 | Verona Bk2 - DKY2127 | 324.7 |  | 324.7 |  |  | 33747.06 | 24632.09 | 9114.97 | 2019-05-16 10:03 | 2019-09-12 | 2019-05-01 | 2019-11-15
75084 | TEMERKY | MX7515375 | CAPITAL Wilder Cir 2166 replace Pha | 9422.95 |  | 9422.95 |  |  | 9422.95 | 16087.25 | -6664.3 | 2020-07-21 10:02 | 2021-03-31 | 2020-07-01 | 2020-11-10
75084 | TEMERKY | MX8656881 | CAPITAL Silver Grove Cir 5983 Phase | 9066.64 |  | 9066.64 |  |  | 9066.64 | 17032.91 | -7966.27 | 2020-11-06 10:01 | 2021-03-31 | 2020-11-01 | 2021-02-15
75084 | DKY2217 | D2217RS1 | Petersburg Sub Site - DKY2217 | 378.87 |  | 378.87 |  |  | 347429.16 | 382562 | -35132.84 | 2017-05-18 18:02 | 2019-10-27 | 2017-07-01 | 2019-10-08
75084 | KHRF55669 | KHR355669 | RI 10355669 Washington St | 159.33 |  | 159.33 |  |  | 131443.89 | 101560.5 | 29883.39 | 2016-07-22 18:06 | 2017-07-28 | 2016-08-01 | 2017-06-20
75084 | KHRF82804 | KHR082804 | RI 10082804 15 Spiral Dr | -35.24 |  | -35.24 |  |  | -6813.67 | 59622.55 | -66436.22 | 2016-08-23 14:03 | 2017-08-28 | 2016-10-01 | 2018-01-04
75084 | KUCF61112 | KUC261112 | UG 10261112 Constance 42 | -1739.68 |  | -1739.68 |  |  | 802654.8 | 360637.32 | 442017.48 | 2017-01-10 14:04 | 2019-03-19 | 2017-03-01 | 2018-08-10
75084 | KIPF08146 | KIP708146 | NB 20708146 Beaver 41 Reb | -184.88 |  | -184.88 |  |  | 328646.61 | 200686.44 | 127960.17 | 2017-02-16 10:04 | 2018-01-31 | 2017-03-01 | 2017-12-06
75084 | KETF35854 | KET135854 | DET 10135854 Villa 43 348 | -7350.95 |  | -7350.95 |  |  | 1420634.37 | 350417.94 | 1070216.43 | 2016-11-04 18:06 | 2019-06-30 | 2016-12-01 | 2019-03-12
75084 | KETF35851 | KET135851 | DET 10135851 West End 41 | 247084.77 |  | 247084.77 |  |  | 1789311.39 | 414893.11 | 1374418.28 | 2016-05-02 14:04 | 2019-06-14 | 2016-05-01 | 2019-05-25
75084 | KUCF48463 | KUC348463 | UG 10348463 Decoursey 41 | 5003.97 |  | 5003.97 |  |  | 306914.16 | 199651.38 | 107262.78 | 2017-02-15 14:04 | 2019-03-01 | 2017-07-01 | 2019-03-31
75084 | KUCF47633 | KUC447633 | UG 20447633 Constance 42 | -322.82 |  | -322.82 |  |  | 1158626.73 | 328397.17 | 830229.56 | 2017-02-22 14:02 | 2018-04-30 | 2017-03-01 | 2018-07-17
75084 | DKY1973 | D1973DL1 | AM 11028173 York 43 Ln Ext | 160.39 |  | 160.39 |  |  | 204081.21 | 83908.12 | 120173.09 | 2016-08-17 08:12 | 2017-10-31 | 2016-08-01 | 2017-09-14
75084 | KOCF56175 | KOC556175 | DET 11556175 Kenton 44 Re | -497.15 |  | -497.15 |  |  | 731931.45 | 283200.78 | 448730.67 | 2017-01-10 18:05 | 2018-03-31 | 2017-03-01 | 2018-05-05
75084 | KUCF48481 | KUC348481 | UG 10348481 Crescent 41 | 3.16 |  | 3.16 |  |  | 12368.68 | 16692.2 | -4323.52 | 2017-02-20 18:06 | 2019-04-01 | 2017-07-01 | 2017-09-21
75084 | SG000598F | SG598CDEQ | SG DEE Secure Network Infrastructur | 0.06 |  | 0.06 |  |  | 148317.52 | 85620 | 62697.52 | 2017-09-12 16:44 | 2019-04-30 | 2017-09-01 | 2019-04-30
75084 | KIPF03154 | KIP703154 | NB 10703154 9001 US 42 Un | -24.71 |  | -24.71 |  |  | 61050.24 | 57736.31 | 3313.93 | 2016-08-09 18:04 | 2018-02-22 | 2017-03-01 | 2017-10-12
75084 | KYRELT | KYRELT02 | F6761 Richwood eo 71/75 | 550564.48 |  | 550564.48 |  |  | 3958.36 | 1152231 | -1148272.64 | 2018-09-04 10:02 | 2019-09-04 | 2018-09-01 | 2019-08-10
75084 | KHRF81342 | KHR181342 | DOT 7181342 Empire 41 Rel | 0.57 |  | 0.57 |  |  | 742047.21 | 246600.03 | 495447.18 | 2017-01-18 14:05 | 2017-12-01 | 2017-02-01 | 2018-03-19
75084 | M180463 | M18046301 | EMERGENT - Cold Spring Circuit 49 - | 28339.25 |  | 28339.25 |  |  | 50940.87 | 48795.63 | 2145.24 | 2018-07-23 18:03 | 2019-05-08 | 2018-08-01 | 2019-02-28
75084 | M180346 | M18034601 | Emergent - Circuit #5962 10 Pole re | 1128.39 |  | 1128.39 |  |  | 1084249.36 | 2274991 | -1190741.64 | 2018-07-16 14:02 | 2019-08-10 | 2018-08-01 | 2019-07-05
75084 | M180346 | MX1419097 | F5962 X-fer UB for 1 wood to steel | 625.79 |  | 625.79 |  |  | 7767.9 | 3939.76 | 3828.14 | 2019-04-24 10:01 | 2020-01-23 | 2019-07-01 | 2020-01-05
75084 | KIPF44149 | KIP344149 | NB 21344149 RIVIERA DR - | 6.23 |  | 6.23 |  |  | 8246.67 | 14117.06 | -5870.39 | 2017-07-26 14:04 | 2017-12-01 | 2017-10-01 | 2017-12-27
75084 | KIPF89003 | KIP189003 | NB 11189003 Duveneck Squa | -17.13 |  | -17.13 |  |  | 60577.67 | 65005.6 | -4427.93 | 2017-02-23 18:03 | 2018-05-31 | 2017-10-01 | 2018-01-11
75084 | SG000485F | SG485SW | SG Ext Cust Facing Wbpge SW - 485 | -0.55 |  | -0.55 |  |  | 0 | 37848 | -37848 | 2018-06-12 09:57 | 2020-02-28 | 2018-06-01 | 2019-01-01
75084 | SG000485F | SG485SVRS | SG Ext Cust Facing Wbpge HW - 485 | -0.05 |  | -0.05 |  |  | -8.8818e-16 | 3200 | -3200 | 2018-06-12 10:52 | 2020-02-28 | 2018-06-01 | 2019-01-01
75084 | 75084 | KMTROWS | KY - Meters-AMI-Self Contained | 285437.42 |  | 285437.42 |  |  | 654528.2 | 99863.96 | 554664.24 | 2018-11-02 18:04 | 2026-03-31 | 2018-12-01
75084 | 75084 | EMETERKY | Electric Meter Blanket | 157492.66 |  | 157492.66 |  |  | 3000732.32 | 295697.19 | 2705035.13 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01 | 2019-05-14
75084 | 75084 | MX2586486 | OLD TWENHOFEL MIDDLE SCHOOL | 2103.21 |  | 2103.21 |  |  | 16336.22 | 37465.22 | -21129 | 2018-01-09 14:01 | 2018-02-16 | 2018-01-01 | 2018-08-23
75084 | 75084 | KMTROWT | KY - Meters-AMI-T Rated | 375175.73 |  | 375175.73 |  |  | 485623.17 | 11182.68 | 474440.49 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | 75084 | KMTRNOT | KY - Meters-Not AMI- T Rated | 77347.34 |  | 77347.34 |  |  | 132350.93 | 520.12 | 131830.81 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | 75084 | KMTRNOS | KY Meters-Not AMI-SelfContained | 30759.58 |  | 30759.58 |  |  | 35489.61 | 5461.31 | 30028.3 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | M190085 | M19008501 | EMERGENCY - Kenton Replace TB 1 | 1054.38 |  | 1054.38 |  |  | 1444143.66 | 1830863 | -386719.34 | 2019-04-10 18:01 | 2019-10-28 | 2019-04-01 | 2019-10-25
75084 | KFSF45125 | KFS845125 | RFS 11845125 Claryville 42 | 38410.05 |  | 38410.05 |  |  | 151693.7 | 87341.66 | 64352.04 | 2017-06-28 14:02 | 2020-02-27 | 2019-02-01 | 2020-02-12
75084 | M180095 | M18009501 | Kenton XTR 1 Rpl | -31533.32 |  | -31533.32 |  |  | 154772.82 | 2336966 | -2182193.18 | 2019-03-07 10:01 | 2023-12-29 | 2019-03-01
75084 | M200255 | M20025501 | Emgt - Decoursey Retire MTU | 25.07 |  | 25.07 |  |  | 25.07 | 0 | 25.07 | 2020-10-01 14:01 | 2021-02-20 | 2020-10-01 | 2021-03-30
75084 | SG000764F | SG764BLK1 | DEK 2019-2020 Microwave Upgrades | 545619.32 |  | 545619.32 |  |  | 1024012.19 | 217462.26 | 806549.93 | 2019-02-25 09:15 | 2028-03-31 | 2019-04-01
75084 | SG000764F | SG764MAT1 | DEK 2019-2020 Microwave Upgrades | 208742.47 |  | 208742.47 |  |  | 252434.88 | 217462.26 | 34972.62 | 2019-02-25 08:41 | 2028-03-31 | 2019-10-01
75084 | TKY1999 | TKY199903 | Constance Bus 1 Swgr CB Rpl | 1045.84 |  | 1045.84 |  |  | 94005.42 | 2390612 | -2296606.58 | 2018-07-06 10:02 | 2024-06-21 | 2019-02-01
75084 | TKY1999 | TKY199902 | Constance 69kV TLS | 187.85 |  | 187.85 |  |  | 16883.6 | 0 | 16883.6 | 2018-07-06 10:02 | 2024-06-10 | 2019-02-01
75084 | TKY1999 | TKY199904 | Constance 138kV switches | -2.03 |  | -2.03 |  |  | -2.276e-15 | 0 | -2.276e-15 | 2019-03-07 10:05 | 2021-05-25 | 2019-03-01
75084 | M190055 | M19005501 | Beaver Cambium Radio Upgrades | 51813.73 |  | 51813.73 |  |  | 195230.51 | 245834 | -50603.49 | 2019-06-06 11:17 | 2020-03-10 | 2019-06-01 | 2020-03-05
75084 | M190055 | M19005503 | Cold Spring Cambium Upgrade | 21851.06 |  | 21851.06 |  |  | 91631.49 | 114679 | -23047.51 | 2019-06-06 11:02 | 2020-04-14 | 2019-06-01 | 2020-04-30
75084 | M190055 | M19005502 | Blackwell Cambium Radio Upgrade | 26358.78 |  | 26358.78 |  |  | 106548.92 | 117617 | -11068.08 | 2019-06-06 11:17 | 2020-04-13 | 2019-06-01 | 2020-04-15
75084 | DKY2125 | DKY212501 | New 69kV V structure | 105498.81 |  | 105498.81 |  |  | 138478.05 | 904914.56 | -766436.51 | 2019-02-22 10:01 | 2022-02-15 | 2019-03-01 | 2022-03-16
75084 | DKY2125 | DKY212502 | Grant Metering | 98620.79 |  | 98620.79 |  |  | 109509.38 | 918433 | -808923.62 | 2019-02-22 10:01 | 2021-10-08 | 2019-08-01 | 2021-07-07
75084 | DKY2125 | MX8804068 | Remove cable for Grant CAP Bank - D | 13.43 |  | 13.43 |  |  | 13.43 | 0 | 13.43 | 2020-11-30 10:02 | 2021-03-18 | 2020-12-01 | 2021-03-14
75084 | DKY2125 | MX6297880 | Dry Ridge Pole Repl UB - DKY2125 | 40.26 |  | 40.26 |  |  | 40.26 | 64542.37 | -64502.11 | 2020-04-03 14:01 | 2021-10-19 | 2020-12-01 | 2021-10-13
75084 | DKY2125 | DKY212503 | Dry Ridge BK 2 | 330994.62 |  | 330994.62 |  |  | 371885.07 | 1629020 | -1257134.93 | 2019-02-22 10:01 | 2022-02-15 | 2019-04-01 | 2022-03-16
75084 | DKY2125 | DKY212504 | Dry Ridge F3568 Loop TL | 31506.04 |  | 31506.04 |  |  | 40350.99 | 166179.8 | -125828.81 | 2019-02-22 10:01 | 2022-02-15 | 2019-06-01 | 2022-03-16
75084 | SG000909F | SMODEMKY | DEK Modem Replacement | 117254.49 |  | 117254.49 |  |  | 121154.06 | 1 | 121153.06 | 2018-12-14 11:31 | 2068-12-31 | 2019-03-01
75084 | DKYHW2672 | MX3147286 | TBC Hebron 43 45 UG Cable - DKYHW26 | -130.21 |  | -130.21 |  |  | 178.72 | 1796.56 | -1617.84 | 2019-06-26 14:01 | 2021-07-01 | 2019-08-01
75084 | DKYHW2672 | MX3147011 | Hebron OH Work - DKYHW2672 | 7658.46 |  | 7658.46 |  |  | 7967.39 | 227039.51 | -219072.12 | 2019-06-26 14:01 | 2021-12-29 | 2019-08-01 | 2021-11-21
75084 | DKYHW2672 | MX3146693 | Hebron Pole Inst - DKYHW2672 | -171413.28 |  | -171413.28 |  |  | -16265.34 | 63734.56 | -79999.9 | 2019-06-26 14:01 | 2020-09-28 | 2019-07-01 | 2020-07-22
75084 | DKYHW2672 | MX3147246 | Hebron 41 42 UG Cable - DKYHW2672 | -654.9 |  | -654.9 |  |  | -3.73 | 464106.03 | -464109.76 | 2019-06-26 14:01 | 2020-09-29 | 2019-08-01 | 2020-10-07
75084 | DKYHW2672 | MX3147307 | Hebron 41 42 OH Relo - DKYHW2672 | -1881.92 |  | -1881.92 |  |  | -165.64 | 40647.45 | -40813.09 | 2019-06-26 14:01 | 2020-10-13 | 2019-08-01 | 2020-10-19
75084 | M190226 | MX7488872 | D-Const Reco Woodspoint-Aero - M190 | 5127.67 |  | 5127.67 |  |  | 5127.67 | 184107.64 | -178979.97 | 2020-07-20 10:01 | 2023-06-29 | 2020-09-01
75084 | M190226 | M19022601 | 138 kV F23983 Woodspoint to Aero | 3365429.61 |  | 3365429.61 |  |  | 3610420.45 | 5133016 | -1522595.55 | 2019-10-08 14:01 | 2023-03-04 | 2019-11-01
75084 | M190226 | M19022602 | F23983 T Line RLE | 4666248.88 |  | 4666248.88 |  |  | 4666248.88 | 7486323 | -2820074.12 | 2019-10-08 14:01 | 2023-01-06 | 2020-01-01
75084 | M190226 | MX7488796 | Woodspoint UB Rebuild - M190226 | 30838.75 |  | 30838.75 |  |  | 30838.75 | 35997.9 | -5159.15 | 2020-07-20 10:01 | 2021-09-28 | 2020-09-01 | 2021-08-08
75084 | M190226 | MX7488839 | D-Const UG Transfers - M190226 | 66.36 |  | 66.36 |  |  | 66.36 | 5697.77 | -5631.41 | 2020-07-20 10:01 | 2023-06-29 | 2020-09-01
75084 | M200191 | M20019101 | EMR - Hands Remov MTU & Inst SPCC | 35756.56 |  | 35756.56 |  |  | 35756.56 | 40455 | -4698.44 | 2020-05-29 10:01 | 2021-12-04 | 2020-07-01 | 2021-04-04
75084 | M190297 | M19029701 | 5967 Rbld Claryville to HL 864 | 362898.2 |  | 362898.2 |  |  | 362898.2 | 6743234 | -6380335.8 | 2020-11-11 14:01 | 2023-07-18 | 2020-11-01
75084 | SG000564F | SG564LC&I | DEK Large CI Follow On Project | 3168.05 |  | 3168.05 |  |  | 3168.05 | 121743 | -118574.95 | 2020-10-09 17:10 | 2021-10-31 | 2020-11-01 | 2021-12-01
75084 | M190270 | M19027001 | Emergency - Replace Limaburg TB 1 A | -421033.35 |  | -421033.35 |  |  | 492783.59 | 1081592 | -588808.41 | 2019-10-24 10:13 | 2020-03-15 | 2019-10-01 | 2020-03-20
75084 | DKY2447 | MX1424546 | Constance 43 LN Ext DKY2447 | 1209615.85 |  | 1209615.85 |  |  | 1220176.37 | 1616077.2 | -395900.83 | 2019-06-17 18:02 | 2021-10-18 | 2019-09-01 | 2021-10-17
75084 | SG000723F | SG723SW | DEE AMI Operations Tool | 18118.02 |  | 18118.02 |  |  | 18118.02 | 38014 | -19895.98 | 2020-01-15 11:35 | 2022-07-30 | 2020-04-01 | 2022-07-31
75084 | SG000723F | SG723SVR | DEE AMI Operations Project | 86.63 |  | 86.63 |  |  | 7030.38 | 1 | 7029.38 | 2019-12-20 15:16 | 2025-12-31 | 2019-12-01 | 2020-08-26
75084 | SG000493F | SG943MAIF | Advanced Reliability Metrics | 4399.64 |  | 4399.64 |  |  | 4399.64 | 50359 | -45959.36 | 2020-06-29 17:04 | 2022-03-31 | 2020-07-01 | 2022-01-15
75084 | SG000842F | SG842RCR | DEK Reclosure Control Replacement | 149652.67 |  | 149652.67 |  |  | 709723.96 | 1062774 | -353050.04 | 2018-10-16 17:02 | 2024-03-31 | 2019-03-01
75084 | SGGIPMGTF | SGGIPMGT | SG GIP Management Allocation | -605.58 |  | -605.58 |  |  | 1.3642e-12 | 0 | 1.3642e-12 | 2019-03-20 16:03 | 2030-12-31 | 2019-04-01
75084 | M180378 | M18037801 | Richwood BK 4- Install | 300562.11 |  | 300562.11 |  |  | 308778.74 | 2360214.13 | -2051435.39 | 2019-09-12 14:01 | 2023-07-21 | 2019-10-01
75084 | M180378 | M18037802 | Richwood BK 4- Mod Xmission Structu | 113985.84 |  | 113985.84 |  |  | 115892.94 | 523888.35 | -407995.41 | 2019-09-16 18:01 | 2023-08-04 | 2019-10-01
75084 | M180378 | M18037803 | F6761 Loop | 2985.13 |  | 2985.13 |  |  | 2985.13 | 0 | 2985.13 | 2019-09-12 14:01 | 2023-07-10 | 2020-06-01
75084 | TOT00003 | WEBFG | WebFG Replacement | 14665.8 |  | 14665.8 |  |  | 15151.88 | 79688 | -64536.12 | 2019-10-18 07:58 | 2022-03-31 | 2019-10-01 | 2022-04-14
75084 | M190087 | MX6297484 | T-Emergent F6763 (T-DPN M19008701) | 29066.28 |  | 29066.28 |  |  | 29066.28 | 31313.21 | -2246.93 | 2020-04-07 14:01 | 2021-09-28 | 2020-05-01 | 2021-08-30
75084 | M190087 | M19008701 | Emergent - Circuit 6763 Replace ABS | 300087.94 |  | 300087.94 |  |  | 308152.61 | 340853.09 | -32700.48 | 2019-07-10 14:09 | 2020-09-30 | 2019-08-01 | 2020-09-26
75084 | SG000983F | SG983TMT2 | SG DEE TMT Phase II | 16646.67 |  | 16646.67 |  |  | 21172.23 | 44390.63 | -23218.4 | 2019-08-14 14:04 | 2021-11-02 | 2019-09-01 | 2022-01-01
75084 | SG000719F | SG719SW | SG DEE Auto Net Metering Solu - 719 | 153.11 |  | 153.11 |  |  | 7763.41 | 8535.73 | -772.32 | 2018-08-27 09:35 | 2020-03-31 | 2019-05-01 | 2020-03-07
75084 | M180604 | M18060412 | Kentucky University Install SPCC pe | 83884.35 |  | 83884.35 |  |  | 83884.35 | 101095 | -17210.65 | 2020-03-04 14:01 | 2021-02-12 | 2020-03-01 | 2021-02-18
75084 | M180604 | M18060406 | Constance Install SPCC per oil cont | 127790.81 |  | 127790.81 |  |  | 127790.81 | 143249 | -15458.19 | 2020-03-04 14:01 | 2021-01-09 | 2020-03-01 | 2021-02-10
75084 | M180604 | M18060410 | Florence Install SPCC per oil conta | 68996.12 |  | 68996.12 |  |  | 68996.12 | 80275 | -11278.88 | 2020-03-04 14:01 | 2021-02-07 | 2020-03-01 | 2021-01-25
75084 | M180604 | M18060414 | Richwood Install SPCC per oil conta | 129277.01 |  | 129277.01 |  |  | 129277.01 | 114181 | 15096.01 | 2020-03-04 14:01 | 2020-10-16 | 2020-03-01 | 2020-11-10
75084 | M180604 | M18060409 | Empire Install SPCC per oil contain | 38255.69 |  | 38255.69 |  |  | 38255.69 | 42308 | -4052.31 | 2020-03-04 14:01 | 2021-02-07 | 2020-03-01 | 2020-12-24
75084 | M180604 | M18060403 | Bellevue Install SPCC per oil conta | 78540.51 |  | 78540.51 |  |  | 78540.51 | 77953 | 587.51 | 2020-03-04 14:01 | 2021-02-09 | 2020-03-01 | 2021-03-30
75084 | M180604 | M18060405 | Cold Spring Install SPCC per oil co | 106417.42 |  | 106417.42 |  |  | 106417.42 | 112751 | -6333.58 | 2020-03-04 14:01 | 2021-01-16 | 2020-03-01 | 2021-01-28
75084 | M180604 | M18060416 | York Install SPCC per oil containme | 72471.42 |  | 72471.42 |  |  | 72471.42 | 64758 | 7713.42 | 2020-03-04 14:01 | 2020-10-30 | 2020-03-01 | 2020-11-30
75084 | M180604 | M18060404 | Blackwell Install SPCC per oil cont | 19870.76 |  | 19870.76 |  |  | 19870.76 | 23068 | -3197.24 | 2020-03-04 14:01 | 2021-02-16 | 2020-05-01 | 2021-03-30
75084 | M180604 | M18060401 | Alexandria South Install SPCC per o | 54747.04 |  | 54747.04 |  |  | 54747.04 | 54013 | 734.04 | 2020-03-04 14:01 | 2020-10-06 | 2020-03-01 | 2020-11-18
75084 | M180604 | M18060411 | Hebron Install SPCC per oil contain | 113556.37 |  | 113556.37 |  |  | 113556.37 | 114896 | -1339.63 | 2020-03-04 14:01 | 2021-01-31 | 2020-03-01 | 2021-01-13
75084 | M180604 | M18060417 | Erlanger Gas Install SPCC per oil c | 32250.05 |  | 32250.05 |  |  | 32250.05 | 57836 | -25585.95 | 2020-03-04 14:01 | 2021-02-07 | 2020-03-01 | 2021-02-22
75084 | M180604 | M18060402 | Atlas Install SPCC per oil containm | 54826.29 |  | 54826.29 |  |  | 54826.29 | 64467 | -9640.71 | 2020-03-04 14:01 | 2020-11-13 | 2020-03-01 | 2020-12-21
75084 | M180604 | M18060407 | Crittenden Install SPCC per oil con | 58519.89 |  | 58519.89 |  |  | 58519.89 | 65942 | -7422.11 | 2020-03-04 14:01 | 2021-01-22 | 2020-03-01 | 2021-02-09
75084 | M180604 | M18060408 | Dry Ridge Install SPCC per oil cont | 36389.24 |  | 36389.24 |  |  | 36389.24 | 50943 | -14553.76 | 2020-03-04 14:01 | 2021-02-02 | 2020-03-01 | 2021-03-30
75084 | M190153 | M19015301 | GLT F6763 Rpl - Limaburg to Oakbroo | 635428.59 |  | 635428.59 |  |  | 646322.46 | 647545.95 | -1223.49 | 2019-10-03 14:14 | 2021-01-05 | 2019-10-01 | 2020-10-08
75084 | M190153 | MX5967380 | GLT TRANS UB F6763 (M19015301) | 44226.26 |  | 44226.26 |  |  | 44226.26 | 43758.15 | 468.11 | 2020-06-02 14:01 | 2020-12-29 | 2020-06-01 | 2020-12-28
75084 | M190153 | M19015302 | GLT F6763 Rpl Oakbrook to Swi#406 | 2491874.37 |  | 2491874.37 |  |  | 2498352.31 | 2661488.14 | -163135.83 | 2019-10-04 10:01 | 2021-02-06 | 2019-11-01 | 2020-10-08
75084 | M190153 | M19015304 | GLT F6763 Rpl - Empire to Dixie | 55764.4 |  | 55764.4 |  |  | 58408.97 | 307070 | -248661.03 | 2019-10-04 10:01 | 2021-05-14 | 2019-11-01 | 2021-06-06
75084 | M190153 | M19015303 | GLT F6763 Rpl - Swi #406 to Empire | 35156.55 |  | 35156.55 |  |  | 39489.61 | 714261 | -674771.39 | 2019-10-04 10:01 | 2021-05-21 | 2019-10-01 | 2021-05-25
75084 | M190153 | MX6488060 | Transfer D-Line UB on F6763 GLT F67 | 1664.34 |  | 1664.34 |  |  | 1664.34 | 12313.06 | -10648.72 | 2020-04-22 14:01 | 2021-11-29 | 2020-08-01 | 2021-12-14
75084 | M190153 | MX6012113 | T-GLT F6763 (T-DPN M19015302) Trans | 83427 |  | 83427 |  |  | 83427 | 95593.85 | -12166.85 | 2020-03-04 14:01 | 2022-02-13 | 2020-05-01 | 2022-03-14
75084 | M190153 | M19015305 | GLT F6761 Rpl - Swi #387 to Buffing | 408946.88 |  | 408946.88 |  |  | 412380.55 | 687406 | -275025.45 | 2019-10-04 10:01 | 2021-01-15 | 2019-10-01 | 2021-02-06
75084 | M190153 | MX6489239 | Transfer D-Line UB on F6763 GLT F67 | 1752.97 |  | 1752.97 |  |  | 1752.97 | 21388.36 | -19635.39 | 2020-04-22 14:01 | 2021-08-05 | 2020-08-01 | 2021-07-19
75084 | M190153 | M19015306 | GLT F6763 Rpl - Swi#387 to Buffingt | 757728.07 |  | 757728.07 |  |  | 759796.07 | 501611.81 | 258184.26 | 2019-10-04 10:01 | 2021-02-07 | 2019-11-01 | 2021-02-04
75084 | M190153 | MX6489978 | Transfer D-Line UB on F6763 GLT F67 | 17028.11 |  | 17028.11 |  |  | 17028.11 | 48959.54 | -31931.43 | 2020-04-22 14:01 | 2021-05-01 | 2020-08-01 | 2021-03-14
75084 | M190153 | MX6014189 | Transfer D-Line UB on F6763 GLT F67 | 20615.9 |  | 20615.9 |  |  | 20615.9 | 18427.27 | 2188.63 | 2020-03-04 18:01 | 2021-03-31 | 2020-04-01 | 2021-03-14
75084 | M180553 | M18055301 | Woodspoint Sub Purc Site | -9510.81 |  | -9510.81 |  |  | -1.9792e-11 | 1597931 | -1597931 | 2018-10-29 10:05 | 2020-12-31 | 2019-01-01
75084 | DKY2637 | MX1425791 | TBC Limaburg 41 & 43 Reco CVG DKY26 | 2078.87 |  | 2078.87 |  |  | 5934.36 | 0 | 5934.36 | 2019-10-02 14:01 | 2023-12-27 | 2019-11-01
75084 | DKY2618 | MX5358828 | Permanent Primary Service - DKY2618 | 244187.73 |  | 244187.73 |  |  | 244187.73 | 326336.3 | -82148.57 | 2020-01-16 10:01 | 2023-03-31 | 2020-10-01
75084 | DKY2618 | MX3629351 | Areo Sub Exits - DKY2618 | 321220.97 |  | 321220.97 |  |  | 321600.68 | 164617.64 | 156983.04 | 2019-09-23 18:01 | 2021-03-31 | 2019-10-01 | 2020-12-29
75084 | DKY2618 | MX5358777 | Amazon Dist Conduits - DKY2618 | 427297.18 |  | 427297.18 |  |  | 427297.18 | 574515.35 | -147218.17 | 2020-01-16 10:01 | 2020-11-29 | 2020-04-01 | 2020-11-17
75084 | M190194 | M19019401 | Turfway Sub | 1028.21 |  | 1028.21 |  |  | 1028.21 | 0 | 1028.21 | 2020-12-08 14:19 | 2028-06-19 | 2020-12-01
75084 | SG000838F | SG838BTR | DEK EOL Power Supplies | 32674.47 |  | 32674.47 |  |  | 76776.96 | 81484 | -4707.04 | 2019-01-22 08:29 | 2022-03-31 | 2019-04-01
75084 | SG001017F | SG1017SW | DEE FND Hardening | 406.42 |  | 406.42 |  |  | 406.42 | 3132 | -2725.58 | 2020-07-29 11:51 | 2020-12-30 | 2020-08-01 | 2021-02-28
75084 | SG001041F | SG1041SW | DEE ADP SOG Automation Tool | 7252.48 |  | 7252.48 |  |  | 7252.48 | 32007.13 | -24754.65 | 2020-06-08 08:52 | 2021-12-31 | 2020-06-01 | 2022-03-31
75084 | M200039 | M20003903 | NKU Cambium Radio Upgrade | 112324.34 |  | 112324.34 |  |  | 112324.34 | 117150 | -4825.66 | 2020-03-23 18:01 | 2020-12-08 | 2020-03-01 | 2021-01-01
75084 | M200039 | M20003904 | Hebron Cambium Radio Upgrade | 35342.96 |  | 35342.96 |  |  | 35342.96 | 120284 | -84941.04 | 2020-03-23 18:01 | 2021-08-30 | 2020-03-01 | 2021-07-08
75084 | M200039 | M20003901 | Atlas Cambium Radio Upgrade | 4957.61 |  | 4957.61 |  |  | 4957.61 | 232638 | -227680.39 | 2020-03-23 18:01 | 2022-01-29 | 2020-03-01 | 2022-03-03
75084 | M200039 | M20003905 | Dry Ridge Cambium Radio Upgrade | 10507.77 |  | 10507.77 |  |  | 10507.77 | 193637 | -183129.23 | 2020-03-23 18:01 | 2022-06-27 | 2020-03-01 | 2022-03-03
75084 | M200039 | M20003902 | Florence Cambium Radio Upgrade | 36820.6 |  | 36820.6 |  |  | 36820.6 | 109147 | -72326.4 | 2020-03-23 18:01 | 2021-07-10 | 2020-03-01 | 2021-07-26
75084 | SG990022F | SRRRKY | SG - Reclosure Replacements DMWKY | 32009.68 |  | 32009.68 |  |  | 43064.65 | 1 | 43063.65 | 2017-04-04 13:14 | 2050-12-31 | 2019-03-01
75084 | SG990022F | MX1525938 | SG-RECLOSERREPLACEMENT AS A PROGRAM | 2472.69 |  | 2472.69 |  |  | 2472.69 | 40804.39 | -38331.7 | 2020-02-24 14:01 | 2021-07-29 | 2020-04-01 | 2021-06-29
75084 | SG000685F | MX0000778 | 2020 DEK TUG 25998217 JACKSON RD PH | 45.71 |  | 45.71 |  |  | 5258.14 | 0 | 5258.14 | 2019-09-16 14:01 | 2030-10-18 | 2019-09-01
75084 | SG000685F | MX0000476 | 2021 TUG 2606514 N TALBOT AVE PHASE | 101.01 |  | 101.01 |  |  | 7861.18 | 0 | 7861.18 | 2019-05-31 14:01 | 2022-10-20 | 2019-07-01
75084 | SG000685F | MX0000477 | 2020 TUG 26062514 N TALBOT AVE PHAS | 37.65 |  | 37.65 |  |  | 2749.06 | 0 | 2749.06 | 2019-05-31 14:01 | 2022-11-10 | 2019-08-01
75084 | SG000685F | SG685TUGK | DEK TUG Easement/ROW Blanket | 134461.53 |  | 134461.53 |  |  | 134461.53 | 400000 | -265538.47 | 2019-10-22 11:24 | 2026-03-31 | 2020-01-01
75084 | SG000685F | MX0000782 | 2020 DEK TUG 25998217 JACKSON RD PH | 48.46 |  | 48.46 |  |  | 5576.35 | 0 | 5576.35 | 2019-09-16 14:01 | 2030-11-15 | 2019-09-01
75084 | SG000685F | MX0000780 | 2020 DEK TUG 25998217 JACKSON RD PH | 55.29 |  | 55.29 |  |  | 6360.14 | 0 | 6360.14 | 2019-09-16 14:01 | 2030-10-18 | 2019-09-01
75084 | SG000685F | MX0000632 | TBC 2020 TUG 25990991 Tonya Dr Ins | 14.22 |  | 14.22 |  |  | 847.75 | 0 | 847.75 | 2019-06-19 14:01 | 2022-09-01 | 2019-08-01
75084 | SG000685F | MX0000704 | 2020 TUG 25998562 GREENBRIAR AVE PH | 121.94 |  | 121.94 |  |  | 14026.65 | 0 | 14026.65 | 2019-09-16 14:01 | 2030-10-07 | 2019-09-01
75084 | M180388 | M18038801 | Aero Dist Substation | 9643212.24 |  | 9643212.24 |  |  | 10148994.32 | 6981494 | 3167500.32 | 2019-03-27 14:01 | 2021-03-01 | 2019-04-01 | 2021-03-16
75084 | M200327 | M20032701 | Emgt - Grant Retire MTUs | 25223.73 |  | 25223.73 |  |  | 25223.73 | 0 | 25223.73 | 2020-12-08 18:02 | 2021-05-28 | 2020-12-01 | 2021-06-12
75084 | SG000949F | SG949MTLD | DEE Maintain Load & Generation | 8711.88 |  | 8711.88 |  |  | 8711.88 | 13378 | -4666.12 | 2020-08-17 12:31 | 2022-04-30 | 2020-08-01 | 2022-03-15
75084 | M190271 | M19027101 | Emergency- Replace Augustine TB 3 | -699886.25 |  | -699886.25 |  |  | 108401.4 | 764123 | -655721.6 | 2019-10-30 14:11 | 2020-03-29 | 2019-11-01 | 2020-04-22
75084 | M190233 | MX4865782 | F5983 Lafarge to Silver Grove X-fer | 416.17 |  | 416.17 |  |  | 416.17 | 25682.58 | -25266.41 | 2019-11-26 14:01 | 2022-03-31 | 2020-09-01 | 2022-03-01
75084 | M190233 | MX4864988 | F5983 Dayton to Lafarge X-fer UB fo | 428.4 |  | 428.4 |  |  | 428.4 | 222076.86 | -221648.46 | 2019-11-26 18:01 | 2023-01-29 | 2020-12-01 | 2022-11-09
75084 | TOT00002 | MWEMSKY2 | DEK EMS Replacement Project | 4098.88 |  | 4098.88 |  |  | 4098.88 | 1646591 | -1642492.12 | 2020-12-17 11:46 | 2024-12-31 | 2020-12-01
75084 | TOT00002 | MWEMSKY | Midwest EMS Replacement Project | 299282.68 |  | 299282.68 |  |  | 426233.78 | 679701.48 | -253467.7 | 2019-07-22 08:59 | 2023-03-30 | 2019-09-01
75084 | SG000724F | SG724SW | DEE MDM Technical Health | 12133.68 |  | 12133.68 |  |  | 12133.68 | 22747 | -10613.32 | 2020-08-19 16:40 | 2021-06-24 | 2020-08-01 | 2021-09-30
75084 | SG001006F | SG1006SW | DEK FISR Pre-Scale - Software | 287595.4 |  | 287595.4 |  |  | 289377.97 | 384800 | -95422.03 | 2019-10-22 10:44 | 2022-03-31 | 2019-10-01 | 2022-02-09
75084 | M200330 | M20033001 | GLT F5966 Rpl Poles, Insp Year 2019 | 325091.49 |  | 325091.49 |  |  | 325091.49 | 192628.03 | 132463.46 | 2020-10-01 14:01 | 2021-02-12 | 2020-10-01 | 2021-03-15
75084 | M200290 | M20029001 | F5983 KY SD1 Relocation | 10321.18 |  | 10321.18 |  |  | 10321.18 | 90543 | -80221.82 | 2020-09-15 14:01 | 2021-11-08 | 2020-09-01 | 2021-12-06
75084 | SG990033F | SPOLIRKY | SG-Emergy Pole Replace Insp DMWKY | 62509.23 |  | 62509.23 |  |  | 218359.47 | 1 | 218358.47 | 2017-04-03 15:44 | 2050-12-31 | 2019-10-01
75084 | M200038 | M20003801 | F6763 KYTC Relocation Mt Zion Road. | 40803.36 |  | 40803.36 |  |  | 40803.36 | 517592.97 | -476789.61 | 2020-04-15 18:01 | 2021-08-21 | 2020-04-01 | 2021-09-02
75084 | M200028 | M20002801 | Emergent - Thomas More Replace Regu | 37990.22 |  | 37990.22 |  |  | 37990.22 | 80504 | -42513.78 | 2020-03-19 14:01 | 2020-12-18 | 2020-04-01 | 2020-11-21
75084 | M200056 | M20005602 | GLT 5967 Rpl Poles ABS 436 White T | 12000 |  | 12000 |  |  | 12000 | 0 | 12000 | 2020-12-21 18:01 | 2024-02-25 | 2020-12-01
75084 | M200056 | M20005601 | GLT 5967 Rpl Poles Wilder Sub ABS | 37150.6 |  | 37150.6 |  |  | 37150.6 | 480208 | -443057.4 | 2020-12-21 18:01 | 2024-01-26 | 2020-12-01
75084 | M200056 | M20005603 | GLT 5967 Rpl Poles White Tower Sub | 12000 |  | 12000 |  |  | 12000 | 0 | 12000 | 2020-12-21 18:01 | 2024-02-18 | 2020-12-01
75084 | M190167 | M19016702 | Claryville 2019 DMVPN Upgrade | 20500.41 |  | 20500.41 |  |  | 20542.17 | 85223 | -64680.83 | 2019-08-13 18:01 | 2021-03-31 | 2019-08-01 | 2020-04-29
75084 | M190167 | M19016705 | Thomas More 2019 DMVPN Upgrade 2 | 10701.22 |  | 10701.22 |  |  | 10701.22 | 11371.09 | -669.87 | 2020-01-28 10:01 | 2022-08-27 | 2020-01-01 | 2020-04-30
75084 | M190167 | M19016701 | Limaburg 2019 DMVPN Upgrade | 9851.62 |  | 9851.62 |  |  | 9876.38 | 9857.93 | 18.45 | 2019-08-13 18:01 | 2020-08-01 | 2019-08-01 | 2020-04-09
75084 | M190167 | M19016706 | Villa 2019 DMVPN Upgrade 2 | 302.92 |  | 302.92 |  |  | 302.92 | 85275 | -84972.08 | 2020-01-28 10:01 | 2027-02-08 | 2020-01-01
75084 | DKY2210 | D2210DL1 | AM 21520192 Donaldson 45 | 991216.42 |  | 991216.42 |  |  | 1200401.53 | 503139.5 | 697262.03 | 2017-06-15 14:35 | 2020-08-15 | 2019-05-01 | 2020-08-12
75084 | DKY2210 | MX4120786 | TBC Donaldson 47 UG Conduit SOG - D | -722.83 |  | -722.83 |  |  | 0 | 0 | 0 | 2019-09-23 14:01 | 2020-12-31 | 2019-12-01
75084 | DKY2210 | MX4121529 | Donaldson 43 Reco SOG - DKY2210 | 193346.58 |  | 193346.58 |  |  | 195406.26 | 101138.5 | 94267.76 | 2019-09-23 14:01 | 2021-03-31 | 2019-12-01 | 2021-03-15
75084 | DKY2210 | MX4127002 | Donaldson 47 UG Cable SOG - DKY2210 | 55174.6 |  | 55174.6 |  |  | 56505.02 | 24685.12 | 31819.9 | 2019-09-23 14:01 | 2020-09-13 | 2019-12-01 | 2020-08-25
75084 | DKY2210 | MXA120786 | Donaldson 45/47 Ext | 32579.73 |  | 32579.73 |  |  | 32579.73 | 13831.5 | 18748.23 | 2020-01-16 10:01 | 2020-06-04 | 2020-02-01 | 2020-06-09
75084 | M190259 | MX4517175 | F6782 X-fer UB for 8 wood to steel | 1753.18 |  | 1753.18 |  |  | 1753.18 | 88243.07 | -86489.89 | 2019-11-26 18:01 | 2022-10-13 | 2020-07-01 | 2022-10-16
75084 | M190259 | MX4420788 | GLT F6782 Florence to Donaldson (M1 | 44378.12 |  | 44378.12 |  |  | 44378.12 | 50005.65 | -5627.53 | 2020-02-28 14:01 | 2021-09-28 | 2020-08-01 | 2021-08-25
75084 | M200148 | M20014801 | F6761 Mt Zion Road Relocation | 38256.44 |  | 38256.44 |  |  | 38256.44 | 844710.61 | -806454.17 | 2020-05-19 10:24 | 2021-08-13 | 2020-05-01 | 2021-09-02
75084 | KYGLT20 | KYGLT2001 | GLT F965 Rpl Poles | 2924.61 |  | 2924.61 |  |  | 2924.61 | 694336 | -691411.39 | 2020-09-09 14:01 | 2023-08-29 | 2020-09-01
75084 | DKY2645 | MX1975019 | Wilder 43 Ln Ext- DKY2645 | 9544.33 |  | 9544.33 |  |  | 11344.9 | 369283.68 | -357938.78 | 2019-07-25 14:01 | 2023-03-31 | 2019-10-01
75084 | SG001069F | SG1069GDQ | DEE Grid Data Quality GDQ | 195.46 |  | 195.46 |  |  | 195.46 | 195874 | -195678.54 | 2020-10-26 14:01 | 2024-03-31 | 2020-11-01 | 2023-01-31
75084 | SG001042F | SG1042SW | DEE Openway License Extension | 17025.36 |  | 17025.36 |  |  | 17025.36 | 16841 | 184.36 | 2020-07-28 21:29 | 2020-10-30 | 2020-09-01 | 2020-12-31
75084 | MDTMTR20 | TBKDEK | CF54 TOUGHBOOK | 8189.2 |  | 8189.2 |  |  | 8189.2 | 8631 | -441.8 | 2020-03-10 12:35 | 2020-11-30 | 2020-07-01 | 2020-08-25
75084 | MDTMTR20 | MDTDEKMTR | Install Win 7 Panasonic Toughbooks | -2.3 |  | -2.3 |  |  | 16647.45 | 27874 | -11226.55 | 2019-10-11 08:47 | 2020-06-30 | 2019-10-01 | 2020-03-31
75084 | MDTMTR20 | TBKGETDEK | Toughbook and Getacs | 26747.25 |  | 26747.25 |  |  | 26747.25 | 68173 | -41425.75 | 2020-03-16 10:17 | 2021-03-31 | 2020-06-01 | 2022-03-31
75084 | DKY2451 | MX1425894 | Hebron 45 LN Ext DKY2451 | 25838.39 |  | 25838.39 |  |  | 30076.61 | 325392.17 | -295315.56 | 2019-10-02 14:01 | 2022-03-22 | 2019-12-01 | 2022-03-15
75084 | DKY2451 | MX7616715 | Hebron 45 Recloser Install - SOG - | 1211.86 |  | 1211.86 |  |  | 1211.86 | 42104.37 | -40892.51 | 2020-10-14 10:01 | 2022-03-22 | 2020-10-01 | 2022-03-15
75084 | SG000791F | SG791SVR | SG DEE Oracle Upgrade Servers | -2.48 |  | -2.48 |  |  | 1.3656e-14 | 37212.15 | -37212.15 | 2018-08-07 13:32 | 2020-05-31 | 2019-05-01 | 2020-02-10
75084 | SG001057F | SG1057SW | DEE Customer Mapping Engine | 5355.59 |  | 5355.59 |  |  | 5355.59 | 150716 | -145360.41 | 2020-08-27 15:29 | 2023-10-31 | 2020-09-01 | 2022-12-15
75084 | SG001057F | SG1057SVR | DEE Customer Mapping Engine | 11613.39 |  | 11613.39 |  |  | 11613.39 | 7291 | 4322.39 | 2020-08-26 21:08 | 2023-10-31 | 2020-12-01 | 2022-12-15
75084 | M190086 | M19008601 | Emergent - Circuit 6763 Replace ABS | 232797.68 |  | 232797.68 |  |  | 237664.12 | 228764.57 | 8899.55 | 2019-08-30 14:01 | 2020-09-26 | 2019-09-01 | 2020-09-26
75084 | M190086 | MX6298727 | T-Emergent F6763 (T-DPN M19008601) | 4492.52 |  | 4492.52 |  |  | 4492.52 | 1862.48 | 2630.04 | 2020-05-12 10:01 | 2021-03-31 | 2020-06-01 | 2021-03-16
75084 | M190157 | M19015701 | GLT - F5966 Rpl Poles, Insp Year 20 | 14788.89 |  | 14788.89 |  |  | 14788.89 | 25034 | -10245.11 | 2019-10-10 14:01 | 2021-06-30 | 2020-01-01
75084 | M190220 | M19022001 | Emergent Repl ABS 817 F15268 T-Line | 293898.91 |  | 293898.91 |  |  | 312341.87 | 311345.37 | 996.5 | 2019-09-25 14:01 | 2020-05-01 | 2019-10-01 | 2020-06-30
75084 | M190220 | M19022002 | Emergent-Constance Sub Rpl ABS 817 | 30214.87 |  | 30214.87 |  |  | 31422.12 | 31370.28 | 51.84 | 2019-11-07 14:01 | 2020-05-01 | 2019-11-01 | 2020-06-03
75084 | SG001040F | SG1040SW | DEE SGG License Extension | 7716.4 |  | 7716.4 |  |  | 7716.4 | 0 | 7716.4 | 2020-04-16 17:16 | 2020-05-31 | 2020-04-01 | 2020-07-21
75084 | DKY2214 | MX1424737 | Constance 43 SG DKY2214 | 312.74 |  | 312.74 |  |  | 1936.38 | 122686.92 | -120750.54 | 2019-07-25 14:01 | 2021-10-06 | 2019-09-01 | 2021-09-28
75084 | DKY2633 | MX1423978 | Verona 41 Eads Rd Reco - SOG - DKY2 | 31985.9 |  | 31985.9 |  |  | 31985.9 | 204868.11 | -172882.21 | 2020-10-05 18:05 | 2022-05-26 | 2020-11-01 | 2022-05-25
75084 | SG000551F | SG551NOK | Nokia Network Services Platform | 10193.51 |  | 10193.51 |  |  | 10193.51 | 17998 | -7804.49 | 2020-12-07 17:22 | 2023-03-30 | 2020-12-01
75084 | SG000502F | SG502HW | SG DEE Device Entry Alert Sys - 502 | 457.54 |  | 457.54 |  |  | 457.54 | 798.99 | -341.45 | 2018-09-28 15:25 | 2020-12-31 | 2020-02-01 | 2020-09-30
75084 | SG000502F | SG502SW | SG DEE Device Entry Alert Sys - 502 | 12149.78 |  | 12149.78 |  |  | 12306.04 | 69968.07 | -57662.03 | 2018-08-31 13:48 | 2020-12-31 | 2019-01-01 | 2020-09-30
75084 | SG000946F | SG946CONN | Establish T&D Connectivity SW | 6329.57 |  | 6329.57 |  |  | 6329.57 | 33939 | -27609.43 | 2020-07-27 11:21 | 2022-01-03 | 2020-08-01 | 2022-03-31
75084 | SG001043F | SG1043SW | DEE FND License Extension | 28018.27 |  | 28018.27 |  |  | 28018.27 | 27900 | 118.27 | 2020-07-29 09:01 | 2020-10-30 | 2020-09-01 | 2020-12-31
75084 | SG000940F | SG940SVR | DEE EDMS Platform Upgrade | 16801.11 |  | 16801.11 |  |  | 16801.11 | 13545 | 3256.11 | 2020-04-24 15:48 | 2020-12-18 | 2020-05-01 | 2021-02-07
75084 | M190244 | MX4877019 | F2166 Covington to Newport Steel X- | 3151.03 |  | 3151.03 |  |  | 3151.03 | 33025.21 | -29874.18 | 2019-11-27 14:01 | 2022-07-29 | 2020-10-01 | 2022-06-09
75084 | M190244 | MX4876167 | F2166 West End to Covington X-fer U | 1496.29 |  | 1496.29 |  |  | 1496.29 | 25239.31 | -23743.02 | 2019-11-27 14:01 | 2021-11-29 | 2020-12-01 | 2021-08-09
75084 | FTDITKEPD | TCPRLFKY | Copperleaf Software module | 10093.02 |  | 10093.02 |  |  | 10093.02 | 10299 | -205.98 | 2020-05-28 16:10 | 2021-06-30 | 2020-06-01 | 2021-06-30
75084 | M190190 | M19019001 | Taylor Mill Sub PT II | 2342504.31 |  | 2342504.31 |  |  | 2350958.28 | 2350000 | 958.28 | 2019-08-20 14:01 | 2021-02-13 | 2019-08-01 | 2021-03-11
75084 | SG001076F | SG1076OCT | DEE Capital Investment Planning | 85038.97 |  | 85038.97 |  |  | 85038.97 | 231176 | -146137.03 | 2020-11-11 10:19 | 2023-03-31 | 2020-12-01
75084 | 75084RR | KMODEM | Proactive Replace Smart Dev Modem | 49422.68 |  | 49422.68 |  |  | 49422.68 | 50000 | -577.32 | 2017-12-07 13:26 | 2068-03-31 | 2020-04-01
75084 | 75084RR | KNANC | Neighborhood Area Ntwk Replacements | 12664.91 |  | 12664.91 |  |  | 54861.18 | 0 | 54861.18 | 2017-03-27 14:46 | 2067-04-01 | 2019-05-01
75084 | SG001001F | SG1001SW | DEE IoT Platform Assessment POC | 1593.29 |  | 1593.29 |  |  | 1593.29 | 27663.6 | -26070.31 | 2020-09-11 18:40 | 2022-12-31 | 2020-09-01
75084 | TLRKY20 | TLRKY2001 | FIF 1 P2 Stub Pole replace Cir 596 | 16994.7 |  | 16994.7 |  |  | 16994.7 | 26014.08 | -9019.38 | 2020-03-17 14:01 | 2020-09-07 | 2020-05-01 | 2020-09-17
75084 | SG000520F | MX0494881 | MXCONV-Transformer Retrofit DAYTON | 153918.59 |  | 153918.59 |  |  | 153918.59 | 148626.35 | 5292.24 | 2020-03-12 10:02 | 2021-03-25 | 2020-07-01 | 2021-02-23
75084 | RES75084 | KMW200501 | Augustine Overhead Door Replacement | -7053.99 |  | -7053.99 |  |  | -7053.99 | 6676 | -13729.99 | 2020-11-10 08:55 | 2021-08-30 | 2020-12-01
75084 | RES75084 | KMW200390 | Augustine Heater Replacement | 35055.6 |  | 35055.6 |  |  | 35055.6 | 29118 | 5937.6 | 2020-09-09 17:16 | 2021-08-01 | 2020-11-01 | 2021-01-29
75085 | CUSTCONN | 315986A | Customer Connect - Core | 1936858.56 |  | 1936858.56 |  |  | 4181992.16 | 3313201.21 | 868790.95 | 2017-08-10 10:40 | 2022-12-05 | 2017-08-01 | 2022-07-06
75085 | CUSTCONN | 315986C | Customer Connect- Release 2 | 7122.36 |  | 7122.36 |  |  | 438103.52 | 267635.67 | 170467.85 | 2017-08-10 14:25 | 2019-05-28 | 2017-08-01 | 2019-06-18
75085 | CUSTCONN | 315986D | Customer Connect- Release 3 | 570.01 |  | 570.01 |  |  | 276596.85 | 399313.16 | -122716.31 | 2017-08-10 15:24 | 2019-12-30 | 2017-08-01 | 2019-12-31
75085 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 120055.26 |  | 120055.26 |  |  | 348109.69 | 166907.14 | 181202.55 | 2017-08-11 10:38 | 2020-09-01 | 2017-08-01 | 2020-09-01
75085 | CUSTCONN | 315986HW5 | Customer Connect- Hardware Proj 3 | 18320.55 |  | 18320.55 |  |  | 108858.5 | 61250 | 47608.5 | 2019-09-03 14:42 | 2020-06-01 | 2019-09-01 | 2020-06-15
75085 | CUSTCONN | 315986HW6 | Customer Connect- Hardware Proj 4 | 83307.24 |  | 83307.24 |  |  | 83307.24 | 30625 | 52682.24 | 2020-03-12 11:24 | 2021-03-15 | 2020-03-01 | 2021-06-01
75085 | FPIT | 342284C | Outage Detection Platform | 5277.7 |  | 5277.7 |  |  | 78201.71 | 9664.27 | 68537.44 | 2017-09-06 16:54 | 2020-04-30 | 2017-09-01 | 2020-04-30
75085 | FPIT | 344368 | Customer Transformer Mapping Engine | -66871.07 |  | -66871.07 |  |  | 61170.21 | 22936.91 | 38233.3 | 2017-10-23 13:29 | 2020-03-31 | 2017-11-01 | 2020-03-31
75085 | FPIT | 344598001 | Duke Customer IVR Replacement | 13591.61 |  | 13591.61 |  |  | 217368.16 | 282698 | -65329.84 | 2018-04-10 15:20 | 2020-02-12 | 2018-04-01 | 2020-01-30
75085 | FPIT | 336593019 | New Call Ctr SIP Trunks | 72.82 |  | 72.82 |  |  | 21116.81 | 14982 | 6134.81 | 2018-03-14 16:41 | 2020-03-31 | 2018-03-01 | 2020-03-31
75085 | FPIT | 307482001 | Customer Mobile App - Phase 2 | 180.46 |  | 180.46 |  |  | 34537.02 | 40467 | -5929.98 | 2018-12-28 09:07 | 2020-03-31 | 2019-01-01 | 2020-03-20
75085 | FPIT | 307482002 | Customer Mobile App - Phase 3 | 4357.38 |  | 4357.38 |  |  | 4357.38 | 37822 | -33464.62 | 2019-12-19 13:47 | 2022-03-15 | 2020-01-01 | 2022-03-31
75085 | FPIT | 344368001 | Customer to Transformer Mapping HW | 72192.91 |  | 72192.91 |  |  | 72192.91 | 79114 | -6921.09 | 2020-11-06 11:23 | 2020-03-31 | 2020-11-01 | 2020-03-31
75085 | FPIT | CC1900003 | Street Light Repair Request SW | 42433.34 |  | 42433.34 |  |  | 42433.34 | 53252.24 | -10818.9 | 2020-02-28 08:21 | 2021-03-31 | 2020-07-01 | 2021-03-31
75080 | FPIT | 354154SG1 | DXT Spend Governance | 13150.18 |  | 13150.18 |  |  | 171792.91 | 62115 | 109677.91 | 2018-11-26 13:36 | 2020-03-31 | 2018-11-01 | 2020-03-17
75080 | FPIT | 359140001 | ISOP Data Management | 46956.41 |  | 46956.41 |  |  | 71326.38 | 169292 | -97965.62 | 2018-12-19 15:02 | 2023-03-29 | 2019-01-01
75080 | FPIT | 354154001 | DXT Agile Product Team | 41926.26 |  | 41926.26 |  |  | 144156.1 | 100336 | 43820.1 | 2018-11-13 13:30 | 2020-03-31 | 2018-12-01 | 2020-03-31
75080 | FPIT | CC1900002 | Vegetation Management Communication | 20276.16 |  | 20276.16 |  |  | 20276.16 | 34275 | -13998.84 | 2020-01-24 17:04 | 2021-10-31 | 2020-03-01 | 2021-10-31
75080 | FPIT | 348527007 | My Duke Replacement | 9415.86 |  | 9415.86 |  |  | 137612.88 | 103515 | 34097.88 | 2019-10-02 08:27 | 2020-03-31 | 2019-10-01 | 2020-02-15
75080 | FPIT | CC1900004 | Federal Government Affairs Map | 9334.09 |  | 9334.09 |  |  | 9334.09 | 5865 | 3469.09 | 2020-02-10 14:12 | 2020-07-15 | 2020-02-01 | 2020-07-31
75080 | FPIT | CC2000005 | Planned Outages Portal SW | 3198.2 |  | 3198.2 |  |  | 3198.2 | 48524 | -45325.8 | 2020-10-20 13:20 | 2022-02-28 | 2020-10-01 | 2022-03-10
75080 | FPIT | 307482SW2 | Customer Mobile App - Phase 3 | 20590.41 |  | 20590.41 |  |  | 20590.41 | 60515 | -39924.59 | 2020-04-13 09:04 | 2022-03-15 | 2020-04-01 | 2022-03-31
75080 | FPIT | 349395006 | ITOT OT SIEM Phase 2 HW Workstream | 17733.21 |  | 17733.21 |  |  | 17733.21 | 64242 | -46508.79 | 2020-04-03 15:02 | 2022-10-28 | 2020-05-01 | 2022-10-18
75080 | FPIT | CC1900001 | Customer Analytics Engine | 27924.32 |  | 27924.32 |  |  | 27924.32 | 55612 | -27687.68 | 2020-01-27 07:55 | 2022-03-31 | 2020-02-01 | 2022-03-31
75080 | FPIT | 354299001 | Outage Map Refresh | 3107.26 |  | 3107.26 |  |  | 41027.1 | 41964.72 | -937.62 | 2019-10-02 10:46 | 2020-04-30 | 2019-10-01 | 2020-04-30
75080 | FPIT | CS2000002 | Web Outage Reporting Platform | 23125.11 |  | 23125.11 |  |  | 23125.11 | 12300 | 10825.11 | 2020-04-16 18:33 | 2021-01-31 | 2020-04-01 | 2021-01-01
75080 | FPIT | CY190HW13 | IT-OT ANA Workstream HW | 295640.19 |  | 295640.19 |  |  | 354048 | 2784426 | -2430378 | 2019-12-05 14:44 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | 307600007 | BASS - Ground Water Sample | 454.42 |  | 454.42 |  |  | 51499.01 | 59475 | -7975.99 | 2018-08-14 10:14 | 2020-02-08 | 2018-11-01 | 2020-02-15
75080 | FPIT | CY190SW13 | IT-OT ANA Workstream SW | 2726.73 |  | 2726.73 |  |  | 14961.73 | 885364 | -870402.27 | 2019-12-05 14:32 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | CS1900001 | Voice of the Customer Engagement Pl | 8491.12 |  | 8491.12 |  |  | 8491.12 | 27483 | -18991.88 | 2020-01-29 15:52 | 2022-03-31 | 2020-02-01 | 2022-03-31
75080 | FPIT | CC2000003 | SiteCore JSS Front End Modernizatio | 13051.8 |  | 13051.8 |  |  | 13051.8 | 57443 | -44391.2 | 2020-06-25 21:05 | 2022-05-30 | 2020-08-01 | 2022-05-31
75080 | FPIT | CY190SW16 | ITOT ANA Workstream Tufin SW | 41967.92 |  | 41967.92 |  |  | 41967.92 | 50484 | -8516.08 | 2020-11-30 19:55 | 2022-10-28 | 2020-12-01 | 2022-10-18
75080 | FPIT | SE2000001 | End of life replacement for Firewal | 8519.17 |  | 8519.17 |  |  | 8519.17 | 25952 | -17432.83 | 2020-04-17 13:25 | 2021-03-31 | 2020-05-01 | 2021-03-31
75080 | FPIT | IT2000004 | Adapt 2 SW | 159537.26 |  | 159537.26 |  |  | 159537.26 | 153514 | 6023.26 | 2020-03-03 08:10 | 2021-10-30 | 2020-03-01 | 2021-10-31
75080 | FPIT | 323326008 | Workstation Refresh 2017-2019 | 58.42 |  | 58.42 |  |  | 65452.89 | 70972 | -5519.11 | 2018-12-19 09:22 | 2020-03-03 | 2019-01-01 | 2020-03-03
75080 | FPIT | 354154002 | Durable Team - DXT | 6502.27 |  | 6502.27 |  |  | 6502.27 | 41369 | -34866.73 | 2020-03-05 14:49 | 2020-09-28 | 2020-03-01 | 2020-09-30
75080 | RESBLDKY | KMW190104 | Augustine Complete Roofing Replace | 648.5 |  | 648.5 |  |  | 1258641.34 | 1284525 | -25883.66 | 2019-04-23 14:51 | 2020-04-30 | 2019-05-01 | 2020-02-26
75080 | RESBLDKY | IMW200055 | Erlanger Ops Ctr-EV Charging Statio | 44305.77 |  | 44305.77 |  |  | 44305.77 | 50657 | -6351.23 | 2020-05-20 22:22 | 2021-02-28 | 2020-08-01 | 2021-01-08
75080 | RESBLDKY | KMW200162 | Erlanger Ops Center LED Lighting | 104282.04 |  | 104282.04 |  |  | 104282.04 | 117892 | -13609.96 | 2020-10-08 11:05 | 2021-03-31 | 2020-11-01 | 2021-03-31
75080 | RESBLDKY | KMW190160 | Erlanger Operations Center Complete | 289.4 |  | 289.4 |  |  | 1371929.44 | 1386095 | -14165.56 | 2019-07-03 16:01 | 2020-04-29 | 2019-07-01 | 2020-03-31
75080 | RESBLDKY | KMW200218 | Erlanger Crew Room HVAC Replacement | 7464.72 |  | 7464.72 |  |  | 7464.72 | 8708 | -1243.28 | 2020-06-03 11:58 | 2021-03-15 | 2020-07-01 | 2020-07-01
75080 | RESBLDKY | KMW200113 | Erlanger Ops Sit to stand assemblie | 15088.13 |  | 15088.13 |  |  | 15088.13 | 13225 | 1863.13 | 2020-03-06 13:46 | 2020-09-13 | 2020-07-01 | 2020-09-24
75080 | RESBLDKY | KMW200089 | Augustine Ops Outdoor Lighting | 49188.65 |  | 49188.65 |  |  | 49188.65 | 78603 | -29414.35 | 2020-08-03 12:50 | 2021-03-31 | 2020-10-01 | 2021-03-17
75080 | RESBLDKY | KMW200027 | Erlanger Exhaust Replacement | 1401.84 |  | 1401.84 |  |  | 1401.84 | 7269 | -5867.16 | 2020-02-05 08:21 | 2020-10-30 | 2020-02-01 | 2020-05-19
75080 | RESBLDKY | KMW190251 | Erlanger Transformer Screenwall Rep | 27215.17 |  | 27215.17 |  |  | 27215.17 | 33851 | -6635.83 | 2020-01-15 13:57 | 2020-10-03 | 2020-01-01 | 2020-09-19
75080 | RESBLDKY | KMW200161 | Erlanger Ops Center Façade | 207690.52 |  | 207690.52 |  |  | 207690.52 | 251411 | -43720.48 | 2020-09-15 10:50 | 2021-06-29 | 2020-10-01 | 2021-04-30
75080 | RESBLDKY | KMW200266 | Erlanger Ice Machine Replacement | 10899.54 |  | 10899.54 |  |  | 10899.54 | 11664 | -764.46 | 2020-07-07 15:31 | 2021-03-15 | 2020-09-01 | 2020-12-01
75080 | MWAVE | 348643007 | CIOPS RFID Asset Tracking DEK | -52.87 |  | -52.87 |  |  | -7.3774e-14 | 59330 | -59330 | 2018-04-20 16:08 | 2020-03-01 | 2018-06-01 | 2020-04-01
75080 | CAPBUDK | DISOHDK | DEK Distribution Overhead Pool | 2 |  | 2 |  |  | 8419.06 | 0 | 8419.06 | 2017-07-31 11:00 | 2026-03-31 | 2018-01-01
75080 | FLKY0249G | DUKTKYE20 | Fleet Off-Road Vehicles - KY | 102672.55 |  | 102672.55 |  |  | 102672.55 | 100000 | 2672.55 | 2019-11-07 12:58 | 2020-12-31 | 2020-12-01 | 2021-03-31
75080 | FLKY0249G | DKETKYE20 | DKETKYE19 | 185963.98 |  | 185963.98 |  |  | 185963.98 | 1 | 185962.98 | 2020-03-02 15:34 | 2020-12-31 | 2020-12-01 | 2021-03-31
75080 | ASSETCPAK | CPADEK | DEK Capital CPA ALLOCATION | 804.21 |  | 804.21 |  |  | 811.96 | 1 | 810.96 | 2018-01-31 08:58 | 2050-12-31 | 2018-03-01
75080 | DIGSIGN | DIGSI | Digital Signs | -6.15 |  | -6.15 |  |  | 3236.56 | 150000 | -146763.44 | 2019-01-25 10:08 | 2020-01-01 | 2019-03-01 | 2020-01-15
75080 | SG001010F | SG1010Z1L | DEK LMR - Ohio/Kentucky - Erlanger | 751754.24 |  | 751754.24 |  |  | 1089457.11 | 5597208.53 | -4507751.42 | 2019-11-01 12:38 | 2024-03-31 | 2019-11-01
75080 | SG001010F | SG1010Z1O | DEK LMR - Ohio/Kentucky - Erlanger | 154395.09 |  | 154395.09 |  |  | 219311.31 | 1399302.13 | -1179990.82 | 2019-11-01 12:28 | 2024-03-31 | 2019-11-01
75080 | SG001010F | SG1010B2T | DEM LMR Towers and Shelters | 12095.03 |  | 12095.03 |  |  | 12095.03 | 1777260 | -1765164.97 | 2020-04-24 09:32 | 2021-09-01 | 2020-06-01 | 2021-09-03
75080 | MRTP2019 | 355813001 | 2019 Kentucky Optical EOL Replaceme | 36017.54 |  | 36017.54 |  |  | 132604.82 | 81990 | 50614.82 | 2018-12-19 15:26 | 2020-03-30 | 2019-04-01 | 2020-03-31
75080 | CAMERA20 | CAMERADEK | Security Cameras | 385154.03 |  | 385154.03 |  |  | 385154.03 | 300000 | 85154.03 | 2020-01-21 13:41 | 2025-12-31 | 2020-04-01
75080 | MRTP2020 | 400019004 | Cambium Work for Kentucky | 14699.95 |  | 14699.95 |  |  | 14699.95 | 15407 | -707.05 | 2020-11-10 09:33 | 2021-10-30 | 2020-11-01 | 2021-10-31
75080 | MRTP2020 | 400019003 | Install optical node at Verona towe | 8763.01 |  | 8763.01 |  |  | 8763.01 | 10125 | -1361.99 | 2020-08-17 20:51 | 2021-03-31 | 2020-08-01 | 2021-03-01
75080 | DVV2020 | 400019001 | SD-WAN Pilot at multiple Midwest Lo | 13133.93 |  | 13133.93 |  |  | 13133.93 | 19737 | -6603.07 | 2020-06-23 15:08 | 2021-03-15 | 2020-07-01 | 2021-03-17
75080 | GENERIC | INCENTIVE | Incentive True-up | 693771.86 |  | 693771.86 |  |  | 693501.2 | 0 | 693501.2 | 2019-11-22 10:36 | 2050-12-31 | 2019-11-01
75080 | TOOLFA2 | BKYTOOL | Tool & Equipment Purchases - DEK | 7231.72 |  | 7231.72 |  |  | 7231.72 | 50000 | -42768.28 | 2020-02-20 11:35 | 2050-12-31 | 2020-04-01
75080 | TOOLFA2 | TOOLKTY | TOOLS & EQUIPMENT | 7185.75 |  | 7185.75 |  |  | 8398.56 | 100 | 8298.56 | 2017-01-20 10:02 | 2050-12-31 | 2019-09-01
75080 | SG001011F | SG1009Z1L | DEK LMR - Ohio/Kentucky - Erlanger | 0.01 |  | 0.01 |  |  | 3.07 | 5597208.53 | -5597205.46 | 2019-09-24 12:15 | 2021-03-10 | 2019-10-01
75081 | FPITF | 323123DEK | GenVision- FHO Data Analytics | 10596.95 |  | 10596.95 |  |  | 38342.41 | 11446 | 26896.41 | 2017-12-20 07:17 | 2020-03-28 | 2018-01-01 | 2020-10-31
75081 | FPITF | 307600001 | BASS-DMR Deployments Fossil/Hydro | 179.38 |  | 179.38 |  |  | 49900.32 | 12302 | 37598.32 | 2017-12-21 15:57 | 2020-01-31 | 2018-01-01 | 2020-01-31
75081 | FPITF | IT2000019 | Mobile Component Assessment Applica | 9042.45 |  | 9042.45 |  |  | 9042.45 | 12415 | -3372.55 | 2020-06-09 15:59 | 2022-07-30 | 2020-06-01 | 2022-07-31
75081 | FPITF | NP1900002 | FHO/Renewables TCA Solution Project | 9904.57 |  | 9904.57 |  |  | 38139.49 | 18581 | 19558.49 | 2019-06-05 14:01 | 2020-04-02 | 2019-06-01 | 2020-04-01
75081 | FPITF | IT2000050 | NERC GADS Reporting Platform | 2426.89 |  | 2426.89 |  |  | 2426.89 | 6625 | -4198.11 | 2020-07-22 11:43 | 2021-12-30 | 2020-08-01 | 2021-12-20
75081 | FPITF | IT1900022 | TWI Welding Qualifier Appl | 1696.09 |  | 1696.09 |  |  | 1696.09 | 3096 | -1399.91 | 2019-08-15 13:50 | 2020-08-29 | 2020-01-01 | 2020-07-27
75081 | FPITF | IT190HW22 | TWI Welding Qualifier Application | 14.08 |  | 14.08 |  |  | 14.08 | 660 | -645.92 | 2019-08-20 11:36 | 2020-08-29 | 2020-03-01 | 2020-07-27
75081 | EB021409 | EB021409X | U2 Lime Injection System | 4081567.59 |  | 4081567.59 |  |  | 21295919.09 | 20857179.62 | 438739.47 | 2016-05-16 11:48 | 2020-04-30 | 2016-05-01 | 2020-06-24
75081 | EB020768 | CEB020768 | PSM Remote Safe Havens | 9379.96 |  | 9379.96 |  |  | 1091231.17 | 1090039.97 | 1191.2 | 2017-09-14 23:28 | 2020-03-31 | 2017-09-01 | 2020-03-01
75081 | EB021281 | CEB021281 | EB W. Landfill Cell 2 Construction | 911682.04 |  | 911682.04 |  |  | 16944581.96 | 21601631.47 | -4657049.51 | 2017-11-30 08:30 | 2020-04-30 | 2018-01-01 | 2020-05-05
75081 | EB020745 | CEB020745 | CCP EB Lined Retention Basin - East | 624824.7 |  | 624824.7 |  |  | 10280726.31 | 12974782.23 | -2694055.92 | 2018-11-16 14:14 | 2020-06-30 | 2018-12-01 | 2020-03-30
75081 | EB020557 | CEB020557 | PSM Ammonia Tank Vapor Barrier | 233106.92 |  | 233106.92 |  |  | 1370874.94 | 1394964.77 | -24089.83 | 2018-11-20 09:13 | 2020-08-31 | 2018-12-01 | 2020-03-30
75081 | EB020290 | CEB020290 | Lined Retention Basin | -279598.93 |  | -279598.93 |  |  | 10324587.68 | 3085662 | 7238925.68 | 2016-07-11 18:39 | 2018-11-15 | 2016-08-01 | 2019-02-28
75081 | EB020298 | CEB020298 | East Bend SW / PW REROUTE | -1288623.32 |  | -1288623.32 |  |  | 29882379.24 | 29960739 | -78359.76 | 2016-07-01 15:23 | 2019-05-01 | 2016-08-01 | 2019-06-30
75081 | EB020804 | CEB020804 | PSM Thermal - East ; | 1799.4 |  | 1799.4 |  |  | 306612.42 | 323743.94 | -17131.52 | 2019-03-11 08:45 | 2019-12-31 | 2019-03-01 | 2019-08-03
75081 | EB020740 | EB020740X | Replace Vertimill Heat Exchanger | 3378702.45 |  | 3378702.45 |  |  | 3766109.09 | 3785702.06 | -19592.97 | 2019-06-26 13:32 | 2021-06-30 | 2019-08-01 | 2021-06-30
75081 | EB020676 | EB020676X | Replace 480V Head Boat Power Feed | 9036.34 |  | 9036.34 |  |  | 132217.28 | 201016.65 | -68799.37 | 2019-08-16 10:31 | 2020-01-15 | 2019-09-01 | 2020-03-06
75081 | EB020827 | EB020827X | Repl WSP Instrument Air Dryer(SM19) | 115.88 |  | 115.88 |  |  | 40278.16 | 44198.89 | -3920.73 | 2019-01-24 08:55 | 2020-01-01 | 2019-02-01 | 2019-12-01
75081 | EB1912 | CEBVLV019 | 2019 Misc Valve Blanket | 398.86 |  | 398.86 |  |  | 494820.67 | 426371.54 | 68449.13 | 2019-01-16 14:55 | 2020-03-31 | 2019-02-01 | 2020-03-31
75081 | EB1912 | CEBVLV21 | 2021 Misc Valve Blanket | 222356.51 |  | 222356.51 |  |  | 222356.51 | 586829.72 | -364473.21 | 2020-12-14 10:40 | 2022-03-31 | 2020-12-01
75081 | EB1912 | CEBVLV20 | 2020 Misc Valve Blanket | 355636.63 |  | 355636.63 |  |  | 577538.73 | 584721.92 | -7183.19 | 2019-11-12 11:51 | 2021-03-31 | 2019-12-01
75081 | EB020766 | EB020766X | Replace 2-2 Flame Scanners | 125001.57 |  | 125001.57 |  |  | 125001.57 | 136706.39 | -11704.82 | 2020-02-26 13:31 | 2021-02-15 | 2020-03-01 | 2021-02-20
75081 | EB020680 | EB020680X | Evergreen Upgrade | 1168039.05 |  | 1168039.05 |  |  | 1168039.05 | 4926682.82 | -3758643.77 | 2020-09-28 13:02 | 2021-12-31 | 2020-10-01 | 2022-03-25
75081 | EB020813 | CEB020813 | SmartGen EBS XFMR IR Monitoring | 26170.4 |  | 26170.4 |  |  | 85671.75 | 114305.77 | -28634.02 | 2019-03-18 15:37 | 2022-12-31 | 2019-07-01
75081 | EB021379 | EB021379X | Replace GEN/GSU/UAT Prot Relays | 185592.6 |  | 185592.6 |  |  | 185592.6 | 1263954.92 | -1078362.32 | 2020-05-05 07:34 | 2022-02-28 | 2020-05-01 | 2022-03-25
75081 | EB020635 | EB020635X | Repl FGD Building West Wall Siding | -261.02 |  | -261.02 |  |  | 900477.45 | 900477.45 | 0 | 2019-06-10 14:55 | 2020-03-31 | 2019-07-01 | 2020-02-29
75081 | EB020350 | EB020350X | Underground Fuel Oil Day Tank (EF) | 1879061.93 |  | 1879061.93 |  |  | 1901112.22 | 4265539.18 | -2364426.96 | 2019-11-25 10:02 | 2022-02-21 | 2019-12-01 | 2022-03-25
75081 | EBS01265 | EBS01265X | FGD to WSP Ug Prcs Pipe Repl (EF | 3348652.71 |  | 3348652.71 |  |  | 3613800.91 | 4122675.36 | -508874.45 | 2019-10-15 15:54 | 2020-12-30 | 2019-10-01 | 2021-01-22
75081 | EB021600 | EB021600X | 2-2 CT Motor and Gearbox Repl | 60646.97 |  | 60646.97 |  |  | 60646.97 | 317922.86 | -257275.89 | 2020-12-29 15:02 | 2021-07-09 | 2020-12-01 | 2021-07-13
75081 | EB021162 | EB021162X | Economizer Expansion Joint | 12252.72 |  | 12252.72 |  |  | 12252.72 | 164533.23 | -152280.51 | 2019-12-18 13:13 | 2022-02-28 | 2020-01-01 | 2022-02-01
75081 | EB020566 | CEB020566 | PSM Safe Havens - East Bend U2 | 216438.3 |  | 216438.3 |  |  | 637863.08 | 542839.75 | 95023.33 | 2019-09-05 08:01 | 2021-08-30 | 2019-09-01 | 2021-09-24
75081 | EB021161 | EB021161X | SCR Expansion Joints | 29601.16 |  | 29601.16 |  |  | 29601.16 | 390055.54 | -360454.38 | 2019-12-18 12:53 | 2022-02-28 | 2020-01-01 | 2022-02-01
75081 | EB021160 | EB021160X | Stack Expansion Joint | 303746.31 |  | 303746.31 |  |  | 303746.31 | 275706.1 | 28040.21 | 2019-12-18 12:16 | 2021-03-31 | 2020-01-01 | 2021-02-20
75081 | EB021079 | EB021079X | Replace Cooling Tower Bypass Valves | 335048.06 |  | 335048.06 |  |  | 335048.06 | 314430.84 | 20617.22 | 2019-12-20 12:53 | 2020-12-30 | 2020-02-01 | 2021-02-20
75081 | EB020890 | EB020890X | Generator Stator Rewind | 2671181.64 |  | 2671181.64 |  |  | 2671181.64 | 13504143.66 | -10832962.02 | 2020-08-06 11:19 | 2022-02-28 | 2020-08-01 | 2022-03-25
75081 | EB020701 | EB020701X | LBU Dust Mitigation | 375872.27 |  | 375872.27 |  |  | 381606.19 | 1656005.53 | -1274399.34 | 2019-09-13 09:37 | 2022-02-28 | 2019-11-01 | 2022-03-18
75081 | EB021307 | EB021307X | 2-6 Pulv Roll Wheel Repl | 444024.25 |  | 444024.25 |  |  | 444024.25 | 1197370.95 | -753346.7 | 2020-12-29 14:38 | 2021-12-31 | 2020-12-01 | 2022-03-25
75081 | EB020671 | EB020671X | SmartGen EBS Visual Camera Monit | 32401.91 |  | 32401.91 |  |  | 235582.9 | 217916.29 | 17666.61 | 2019-10-15 15:36 | 2020-03-31 | 2019-10-01 | 2020-03-31
75081 | EB021156 | EB021156X | Install 2-3 ID Fan #2 LO Pump Cable | 17063.15 |  | 17063.15 |  |  | 17063.15 | 25684.31 | -8621.16 | 2019-12-06 09:27 | 2020-05-15 | 2020-01-01 | 2020-04-30
75081 | EB020951 | CEB020951 | NERC-CIP 003 V7 | -17500 |  | -17500 |  |  | 14740.94 | 31477.62 | -16736.68 | 2018-12-12 15:36 | 2020-03-31 | 2019-07-01 | 2020-03-31
75081 | EB021386 | EB021386X | LPA Turbine L-0 & L-1 Blades | 4224080.82 |  | 4224080.82 |  |  | 4224080.82 | 4773416.17 | -549335.35 | 2020-03-11 12:08 | 2021-02-16 | 2020-03-01 | 2021-02-20
75081 | EB020820 | EB020820X | Replace E Conveyor Hoods | 36252.22 |  | 36252.22 |  |  | 114028.69 | 129734.98 | -15706.29 | 2019-07-09 11:36 | 2019-12-31 | 2019-07-01 | 2020-03-11
75081 | EB020879 | EB020879X | Repl 2-4 CT Fan Brkr Arc Flash Mitg | 34971.73 |  | 34971.73 |  |  | 34971.73 | 155881.11 | -120909.38 | 2020-12-18 12:48 | 2021-12-31 | 2020-12-01 | 2022-03-25
75081 | EB020392 | EB020392X | HCAD Repl Crusher to F Conv Chute | 523210.34 |  | 523210.34 |  |  | 581345.37 | 1154709.74 | -573364.37 | 2019-12-18 11:20 | 2021-03-07 | 2019-12-01 | 2021-02-20
75081 | EB021450 | EB021450X | Replace CRW Tank | 619861.54 |  | 619861.54 |  |  | 1083464.99 | 986809.52 | 96655.47 | 2019-10-15 16:30 | 2021-06-22 | 2019-10-01 | 2021-02-19
75081 | EB020818 | EB020818X | FGD Biocide System H2S Mitigation | 152479.02 |  | 152479.02 |  |  | 152479.02 | 203174.91 | -50695.89 | 2020-07-01 14:25 | 2022-09-30 | 2020-07-01 | 2022-09-15
75081 | EB020685 | EB020685X | FGD Breaker Replacement Phase 3 | 456657.68 |  | 456657.68 |  |  | 558735.55 | 656853.33 | -98117.78 | 2019-12-05 10:03 | 2021-06-22 | 2019-12-01 | 2021-02-19
75081 | EB020698 | EB020698X | 3A Lime Conveyor Belt Replacement | 172756.05 |  | 172756.05 |  |  | 172756.05 | 195732.7 | -22976.65 | 2020-06-30 10:51 | 2021-02-15 | 2020-07-01 | 2021-02-19
75081 | EB021309 | EB021309X | 2-3 Pulv Roll Wheel Repl 2020 | 583437.04 |  | 583437.04 |  |  | 788238.09 | 901595.47 | -113357.38 | 2019-12-18 13:57 | 2021-05-11 | 2019-12-01 | 2021-02-21
75081 | EB021133 | EB021133X | Replace East Turbine Bay Door | 10508.11 |  | 10508.11 |  |  | 10508.11 | 10796.96 | -288.85 | 2019-09-06 11:23 | 2020-12-30 | 2020-01-01 | 2021-01-02
75081 | EB021598 | EB021598X | LPA and LPB L-2 Blade Replacement | 490909.5 |  | 490909.5 |  |  | 490909.5 | 4499980.22 | -4009070.72 | 2020-12-18 15:58 | 2022-02-28 | 2020-12-01 | 2022-03-25
75081 | EB021589 | 8SFYTOOLS | Entp High Risk Tool - FHO DEK Coal | 973.64 |  | 973.64 |  |  | 973.64 | 1155.68 | -182.04 | 2020-10-20 16:21 | 2022-06-30 | 2020-11-01 | 2022-08-05
75081 | EB020930 | EB020930M | EBS 2020 Vertimill Rebuild | 161297.58 |  | 161297.58 |  |  | 161297.58 | 161410.1 | -112.52 | 2019-07-25 15:04 | 2021-02-15 | 2020-07-01 | 2020-06-23
75081 | EB020901 | EB020901X | WSP 2ST1 6.9KV Transformer Repl | 42677.36 |  | 42677.36 |  |  | 209417.75 | 139429.55 | 69988.2 | 2018-12-27 11:50 | 2021-07-30 | 2019-05-01 | 2021-08-18
75081 | EB021583 | EB021583X | 2-1 SBAC 1st Stage Cooler Rep | 69014.62 |  | 69014.62 |  |  | 69014.62 | 88244.21 | -19229.59 | 2020-12-08 09:03 | 2021-02-28 | 2020-12-01 | 2021-02-21
75081 | EB021143 | EB021143X | L-1 LPB Rotor Blade Row(Gen Side) | 57327.32 |  | 57327.32 |  |  | 3085179.5 | 1738276.49 | 1346903.01 | 2019-10-15 13:01 | 2020-02-11 | 2019-10-01 | 2020-02-26
75081 | EB021143 | EB021143I | Insurance reimbursement EB021143X | -33197.95 |  | -33197.95 |  |  | -1994168.69 | -1900000 | -94168.69 | 2019-12-06 16:13 | 2020-02-11 | 2019-12-01 | 2020-02-26
75081 | EB021163 | EB021163X | 2-5 CT Motor and Gearbox Repl | 307596.86 |  | 307596.86 |  |  | 307596.86 | 306892.41 | 704.45 | 2020-01-20 09:00 | 2020-09-18 | 2020-01-01 | 2020-09-30
75081 | EB020297 | CEB020297 | CCP East Bend East FGD Pond Rtrmnt | 0.1 |  | 0.1 |  |  | 4951.04 | 0 | 4951.04 | 2016-04-26 14:56 | 2019-12-31 | 2019-01-01 | 2020-01-15
75081 | EB021226 | EB021226X | Radial Stacker Belt Replacement | 41784.86 |  | 41784.86 |  |  | 41784.86 | 29549 | 12235.86 | 2020-08-11 11:31 | 2021-01-31 | 2020-08-01 | 2020-12-08
75081 | EB021155 | EB021155X | Repl Lower Absorber Building Roof | 184989.28 |  | 184989.28 |  |  | 282097.65 | 281446.53 | 651.12 | 2019-12-20 13:26 | 2020-02-28 | 2019-12-01 | 2020-05-24
75081 | EB021127 | EB021127X | Repl WSP Mixer Feed Scale (SM19) | 12733.04 |  | 12733.04 |  |  | 26808.91 | 31103.83 | -4294.92 | 2019-08-16 09:03 | 2020-01-31 | 2019-09-01 | 2020-03-31
75081 | EB021157 | EB021157X | 2-4 ID Fan Lube Oil Htr Cable | 11433.39 |  | 11433.39 |  |  | 11433.39 | 25684.31 | -14250.92 | 2019-12-06 09:45 | 2020-05-15 | 2020-01-01 | 2020-04-30
75081 | CEB02DITC | CCEB2DITC | East Bend Ditch Liner | 165314.11 |  | 165314.11 |  |  | 165314.11 | 175000 | -9685.89 | 2020-11-25 11:33 | 2021-03-31 | 2020-12-01 | 2021-02-28
75081 | EB021126 | EB021126X | Repl WSP Mixer Disch Scale (SM19) | 1795.77 |  | 1795.77 |  |  | 12824.57 | 31096.77 | -18272.2 | 2019-08-16 09:53 | 2020-01-31 | 2019-09-01 | 2020-03-31
75081 | EB021165 | EB021165X | 2-1 Closed Cooling Water Heat Exch | 202816.16 |  | 202816.16 |  |  | 202816.16 | 207792.06 | -4975.9 | 2020-02-26 12:56 | 2020-09-30 | 2020-03-01 | 2020-08-15
75081 | EB021563 | EB021563X | Repl WSP Mixer Disch Belt | 28966.89 |  | 28966.89 |  |  | 28966.89 | 21055.87 | 7911.02 | 2020-07-28 13:29 | 2020-10-15 | 2020-08-01 | 2020-10-08
75081 | EB021592 | EB021592X | Extraction Steam Bellows Repl | 29940.04 |  | 29940.04 |  |  | 29940.04 | 48109.6 | -18169.56 | 2020-12-08 09:24 | 2021-02-15 | 2020-12-01 | 02/15/2021
75082 | FPITF | 323123DKT | GenVision- FHO Data Analytics | -49560.43 |  | -49560.43 |  |  | 93577.01 | 68016 | 25561.01 | 2017-12-21 13:54 | 2020-03-28 | 2018-01-01 | 2020-10-30
75082 | FPITF | 307600001 | BASS-DMR Deployments Fossil/Hydro | 136.16 |  | 136.16 |  |  | 36428.37 | 73111 | -36682.63 | 2017-12-21 17:56 | 2020-01-31 | 2018-01-01 | 2020-01-31
75082 | FPITF | IT2000019 | Mobile Component Assessment Applica | 6807.05 |  | 6807.05 |  |  | 6807.05 | 9292 | -2484.95 | 2020-06-09 16:08 | 2022-07-30 | 2020-06-01 | 2022-07-31
75082 | FPITF | NP1900002 | FHO/Renewables TCA Solution Project | 7320.26 |  | 7320.26 |  |  | 28181.64 | 13734 | 14447.64 | 2019-06-05 14:12 | 2020-04-02 | 2019-06-01 | 2020-04-01
75082 | FPITF | 337767001 | KMS Upgrade | 128.7 |  | 128.7 |  |  | 2164.69 | 1878 | 286.69 | 2018-09-25 14:30 | 2020-03-02 | 2018-10-01 | 2020-02-21
75082 | FPITF | 2000001 | 2020 End of Life Replacement | 8295.12 |  | 8295.12 |  |  | 8295.12 | 11843 | -3547.88 | 2020-05-08 12:10 | 2021-03-31 | 2020-07-01 | 2021-03-09
75082 | FPITF | IT2000050 | NERC GADS Reporting Platform | 1816.28 |  | 1816.28 |  |  | 1816.28 | 4958 | -3141.72 | 2020-07-22 11:49 | 2021-12-30 | 2020-08-01 | 2021-12-20
75082 | KYSC0001 | KYSCOCC | Emerson Ovation Compact Controller | -338452.15 |  | -338452.15 |  |  | 1.5007e-11 | 0 | 1.5007e-11 | 2018-10-30 11:20 | 2019-01-01 | 2018-11-01
75082 | KYSC0001 | WAL2CON | Walton 2 solar construction | 4618.46 |  | 4618.46 |  |  | 1665606.45 | 2018869.74 | -353263.29 | 2017-08-17 12:30 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | WAL1CON | Walton 1 solar construction | 4618.46 |  | 4618.46 |  |  | 1973447.71 | 1994194.98 | -20747.27 | 2017-08-17 12:28 | 2017-12-31 | 2017-09-01 | 2018-03-15
75082 | KYSC0001 | CRITCON | Crittenden solar construction | 6157.94 |  | 6157.94 |  |  | 2723337.82 | 3190661.23 | -467323.41 | 2017-08-17 12:31 | 2017-12-31 | 2017-08-01 | 2018-03-15
75082 | KYSC0001 | CRITGPM | Crittenden GPM | 134260.23 |  | 134260.23 |  |  | 191890.09 | 23846.56 | 168043.53 | 2017-08-17 12:38 | 2017-12-31 | 2017-11-01 | 2018-03-15
75082 | KYSC0001 | WAL1GPM | Walton 1 GPM | 100695.2 |  | 100695.2 |  |  | 121440.42 | 17895 | 103545.42 | 2017-08-17 12:36 | 2017-12-31 | 2017-11-01 | 2018-03-15
75082 | KYSC0001 | WAL2GPM | Walton 2 GPM | 100695.2 |  | 100695.2 |  |  | 121440.42 | 17889.72 | 103550.7 | 2017-08-17 12:37 | 2017-12-31 | 2017-11-01 | 2018-03-15
75082 | WDC00004 | WDC00004X | Install Fuel Oil System - BOP | 132767.74 |  | 132767.74 |  |  | 27936929.42 | 25801931.95 | 2134997.47 | 2016-08-22 15:04 | 2019-07-01 | 2016-08-01 | 2019-07-05
75082 | WDC00004 | WDC000044 | Install Fuel Oil System U4 | -1022.29 |  | -1022.29 |  |  | 4262415.83 | 4645924.95 | -383509.12 | 2019-03-29 15:27 | 2019-08-27 | 2019-04-01 | 2019-08-31
75082 | WDC00004 | WDC000045 | Install Fuel Oil System U5 | -8936.41 |  | -8936.41 |  |  | 4238922.51 | 4645892.78 | -406970.27 | 2019-03-29 15:37 | 2019-07-27 | 2019-04-01 | 2019-07-31
75082 | WDC00004 | WDC000046 | Install Fuel Oil System U6 | -8936.44 |  | -8936.44 |  |  | 4238922.39 | 4645924.95 | -407002.56 | 2019-03-29 15:42 | 2019-08-27 | 2019-04-01 | 2019-07-31
75082 | WDC00004 | WDC000043 | Install Fuel Oil System U3 | -8936.41 |  | -8936.41 |  |  | 4252461.22 | 4645924.95 | -393463.73 | 2019-03-29 15:22 | 2019-08-27 | 2019-04-01 | 2019-08-27
75082 | WDC00004 | WDC000041 | Install Fuel Oil System U1 | -8936.41 |  | -8936.41 |  |  | 4236761 | 4645423.16 | -408662.16 | 2019-03-29 14:38 | 2019-06-30 | 2019-04-01 | 2019-07-05
75082 | WDC00004 | WDC000042 | Install Fuel Oil System U2 | -8936.41 |  | -8936.41 |  |  | 4255161.44 | 4645423.16 | -390261.72 | 2019-03-29 15:15 | 2019-07-22 | 2019-04-01 | 2019-08-23
75082 | WDC01240 | WDC01240X | U3 & U4 SFC | 3203.78 |  | 3203.78 |  |  | 1276574.31 | 1423897.08 | -147322.77 | 2019-02-08 13:28 | 2019-12-31 | 2019-02-01 | 2020-02-15
75082 | WD010037 | WD010037X | U1 Generator Rotor Rewind | 85030.44 |  | 85030.44 |  |  | 1245427.49 | 1574479.63 | -329052.14 | 2019-08-08 08:17 | 2020-02-08 | 2019-08-01 | 2020-02-20
75082 | WD020019 | WD020019I | WD02 Turbine outage Insurance reimb | -327029.64 |  | -327029.64 |  |  | -922573.19 | -489000 | -433573.19 | 2019-04-26 08:34 | 2019-08-31 | 2019-04-01 | 2019-08-08
75082 | WDCM0054 | WDCM0054X | Nat Gas System Purge Modifications | 235285.99 |  | 235285.99 |  |  | 235285.99 | 201046.5 | 34239.49 | 2020-07-28 10:40 | 2020-12-31 | 2020-07-01 | 2020-12-18
75082 | WD050008 | WD050008X | OPTIM U5 Gen Field Rewind | 330579 |  | 330579 |  |  | 330579 | 1200566.34 | -869987.34 | 2020-11-30 11:18 | 2021-12-30 | 2020-12-01 | 2021-08-27
75082 | WD060010 | WD060010X | OPTIM U6 Gen Field Rewind | 330579 |  | 330579 |  |  | 330579 | 1195758.31 | -865179.31 | 2020-11-30 11:44 | 2022-12-30 | 2020-12-01 | 2021-09-07
75082 | WDC01238 | WDC01238X | U1 & U2 SFC | 11290.14 |  | 11290.14 |  |  | 1129283.8 | 1423897.08 | -294613.28 | 2019-02-08 14:27 | 2020-01-01 | 2019-02-01 | 2020-02-19
75082 | WG048C | CWDVLV19 | 2019 Miscellaneous Valves | 586.29 |  | 586.29 |  |  | 586.29 | 43076.57 | -42490.28 | 2019-01-25 13:57 | 2030-12-30 | 2020-03-01 | 2020-06-30
75082 | WDCM0051 | WDCM0051X | Station Discharge Lift Station Cont | 17080.27 |  | 17080.27 |  |  | 31242.12 | 35857.39 | -4615.27 | 2019-11-25 13:22 | 2020-12-31 | 2019-12-01 | 2021-03-03
75082 | WD040008 | WD040008X | WDC U4 Comp Caulking & R17 Blades | 2174.26 |  | 2174.26 |  |  | 377154.57 | 377155.29 | -0.72 | 2019-07-22 09:40 | 2020-01-18 | 2019-09-01 | 2020-02-18
75082 | WDC00048 | CWDC00048 | NERC-CIP 003 V7 Tough Notebook | -15000 |  | -15000 |  |  | 10307.53 | 30670.19 | -20362.66 | 2018-12-07 07:45 | 2020-03-31 | 2019-10-01 | 2020-03-31
75082 | WDCM0055 | WDCM0055X | Repl Demin Acid Tank Outlet Pipelin | 19352.24 |  | 19352.24 |  |  | 19352.24 | 27972 | -8619.76 | 2020-12-15 07:57 | 2021-02-28 | 2020-12-01 | 2021-03-03
75082 | WD060017 | WD060017X | IPB Phases B & C Replacement | 306138.73 |  | 306138.73 |  |  | 306138.73 | 573108.58 | -266969.85 | 2020-12-21 14:31 | 2021-08-07 | 2020-12-01 | 2021-08-10
75082 | WDC00059 | WDC00059X | FIRE PROT, WDC, CO2 Compliance | 16540.23 |  | 16540.23 |  |  | 219041.84 | 229689.39 | -10647.55 | 2019-09-25 09:16 | 2020-03-25 | 2019-10-01 | 2020-03-13
75082 | WDC00067 | WDC00067X | UPS HVAC Unit Replacement | 38144.49 |  | 38144.49 |  |  | 38144.49 | 27670.1 | 10474.39 | 2020-09-01 08:35 | 2021-01-10 | 2020-10-01 | 2021-02-10
|  |  |  | 125063180.33 | 150042328.9516 | 24979148.6216 | 16.65%

## 2021
Duke Energy Kentucky Electric
Year 2021
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75084 | FPIT | 346954001 | ISOP Granular Forecasting | 80195.79 |  | 80195.79 |  |  | 261088.23 | 139345 | 121743.23 | 2018-05-14 11:31 | 2024-09-30 | 2018-05-01
75084 | FPIT | LTHITTAMO | LTH - IT Telecom Asset Managemt | 52419.2 |  | 52419.2 |  |  | 60233.04 | 96831 | -36597.96 | 2020-07-28 14:30 | 2022-12-30 | 2020-10-01 | 2022-09-30
75084 | FPIT | IT1900073 | EAM 2020 Mobile Durable Team | 11134.16 |  | 11134.16 |  |  | 80820.33 | 36572 | 44248.33 | 2020-01-20 08:34 | 2021-05-30 | 2020-01-01 | 2021-06-08
75084 | FPIT | IT20SW08D | ITOA 2020 Product Enhancements | 24182.32 |  | 24182.32 |  |  | 53443.77 | 34187 | 19256.77 | 2020-03-26 08:44 | 2022-03-01 | 2020-03-01 | 2022-01-08
75084 | FPIT | IT1900074 | EAM 2020 Maximo Durable Team | 931.63 |  | 931.63 |  |  | 42084.06 | 229288 | -187203.94 | 2020-01-20 10:48 | 2021-05-30 | 2020-01-01 | 2021-06-08
75084 | FPIT | 338802HW3 | EAM Platform Optimization | -7.36 |  | -7.36 |  |  | 0 | 59872 | -59872 | 2018-04-25 14:24 | 2019-10-31 | 2020-07-01 | 2020-03-31
75084 | FPIT | 349472S13 | JuMP Application | 4863.33 |  | 4863.33 |  |  | 4863.33 | 4400.08 | 463.25 | 2021-02-08 08:10 | 2022-07-30 | 2021-06-01 | 2022-10-01
75084 | FPIT | 349472005 | ESRI Subscription License Agreement | 182663.78 |  | 182663.78 |  |  | 182663.78 | 1153589 | -970925.22 | 2020-12-15 18:56 | 2021-05-30 | 2021-01-01 | 2021-04-01
75084 | FPIT | 349472SW6 | EAM-SC next gen mobile platform SW | 16535.14 |  | 16535.14 |  |  | 16535.14 | 24420 | -7884.86 | 2020-12-15 20:51 | 2022-07-29 | 2021-01-01 | 2022-09-27
75084 | FPIT | 338802006 | Smallworld/myWorld Durable Team | -10.97 |  | -10.97 |  |  | 7.5034e-14 | 48911 | -48911 | 2018-09-06 13:18 | 2020-05-28 | 2019-04-01 | 2020-11-10
75084 | FPIT | 349472010 | New Smallworld storage servers | 2675.8 |  | 2675.8 |  |  | 2675.8 | 17389 | -14713.2 | 2020-12-29 09:01 | 2022-03-31 | 2021-02-01 | 2022-03-31
75084 | FPIT | 349472016 | Autodesk Subscription Agreement | 23570.51 |  | 23570.51 |  |  | 23570.51 | 23607 | -36.49 | 2021-10-29 14:46 | 2022-03-20 | 2021-11-01 | 2022-03-20
75084 | FPIT | IT2100088 | OAM - Oracle Access HW | 666.32 |  | 666.32 |  |  | 666.32 | 107 | 559.32 | 2021-08-26 12:20 | 2022-03-01 | 2021-11-01 | 03/31/2022
75084 | FPIT | IT2100120 | OSI PI Software License Renewal | 30024.9 |  | 30024.9 |  |  | 30024.9 | 30225 | -200.1 | 2021-12-17 11:42 | 2022-06-29 | 2021-12-01 | 03/31/2022
75084 | SG000489F | SG489SVR3 | DEE Openway Scale | 5.37 |  | 5.37 |  |  | 5019.51 | 1707 | 3312.51 | 2019-09-25 08:02 | 2020-10-31 | 2019-10-01 | 2020-10-26
75084 | SG000489F | SG489SVR4 | DEE Openway Scale | -5.45 |  | -5.45 |  |  | -1.563e-15 | 634 | -634 | 2020-01-29 21:38 | 2020-10-31 | 2020-03-01
75084 | SG000540F | SG540SW | DEE Vehicle Area Network | -0.06 |  | -0.06 |  |  | -7.9581e-13 | 109210 | -109210 | 2017-04-13 09:21 | 2020-12-17 | 2017-04-01 | 2018-07-16
75084 | SG000540F | SG540HW | DEE Vehicle Area Network | 21276.73 |  | 21276.73 |  |  | 142735.12 | 273196 | -130460.88 | 2018-04-12 17:01 | 2020-12-17 | 2018-09-01 | 2021-05-15
75084 | SGKAMIF | SG169MTRS | SG KY AMI Electric Meters - 169 | 443.43 |  | 443.43 |  |  | 22856337.4 | 23298670 | -442332.6 | 2017-06-07 11:18 | 2019-02-28 | 2017-06-01
75084 | SG000781F | SG781SW | SG DEE PPM PIMS Phase 2 Build Out | -0.07 |  | -0.07 |  |  | 111560.01 | 110269.74 | 1290.27 | 2018-07-12 09:08 | 2021-03-31 | 2018-07-01 | 2021-03-31
75084 | DKY2133 | MX2167975 | Mt Zion Rbld Weaver Rd - DKY2133 | -109534.3 |  | -109534.3 |  |  | 1678737.24 | 242159.7 | 1436577.54 | 2017-10-05 10:01 | 2021-07-29 | 2017-10-01 | 2021-01-28
75084 | KYGLPRT | MX7360458 | Transfer distribution underbuild fo | -154.72 |  | -154.72 |  |  | 11348.18 | 10915.73 | 432.45 | 2018-02-26 14:50 | 2021-03-31 | 2018-12-01 | 2021-03-18
75084 | KYGLPRT | MX7360495 | Transfer distribution underbuild fo | 45370.38 |  | 45370.38 |  |  | 60862.66 | 48380.24 | 12482.42 | 2018-02-26 13:38 | 2021-07-29 | 2020-01-01 | 2021-07-20
75084 | KYGLPRT | MX7109799 | T-EMERGENT GLT TR_UB F5985 Transfer | 2738.61 |  | 2738.61 |  |  | 18457.22 | 10286.94 | 8170.28 | 2020-06-10 18:01 | 2022-02-28 | 2020-07-01 | 2021-12-07
75084 | KYGLPRT | MX1079885 | GLT F5985 TLine OHGLPR138 3 poles | 19490.91 |  | 19490.91 |  |  | 19490.91 | 8501.81 | 10989.1 | 2021-06-02 10:02 | 2022-01-27 | 2021-07-01 | 2022-01-03
75084 | KYGLPRT | MX1325365 | F5983 X-fer UB for 6 - P2 wood to s | -205.55 |  | -205.55 |  |  | 9538.14 | 76917.35 | -67379.21 | 2019-04-23 18:01 | 2023-03-30 | 2019-07-01
75084 | RELDFA | MKRDYKY | Make Ready Kentucky | 1405.52 |  | 1405.52 |  |  | 408041.7 | 10 | 408031.7 | 2015-01-07 | 2025-12-31 | 2015-04-01
75084 | ORDFA | SKY2109DC | TO CAPTURE 2021 CAPITAL STORM #9 | 20706.03 |  | 20706.03 |  |  | 20706.03 | 18008.29 | 2697.74 | 2021-05-04 14:34 | 2022-03-31 | 2021-12-01 | 2022-03-30
75084 | ORDFA | SKY2104DC | TO CAPTURE 2021 CAPITAL STORM #4 | 6333.74 |  | 6333.74 |  |  | 6333.74 | 0 | 6333.74 | 2020-12-07 16:53 | 2022-03-31 | 2021-06-01
75084 | ORDFA | SKY2106DC | TBC TO CAPTURE 2021 CAPITAL STOR | 2035.35 |  | 2035.35 |  |  | 2035.35 | 0 | 2035.35 | 2020-12-07 16:59 | 2022-10-01 | 2021-07-01
75084 | ORDFA | SKY2004DC | TO CAPTURE 2020 CAPITAL STORM #4 | -293.49 |  | -293.49 |  |  | 14513.82 | 12207.31 | 2306.51 | 2019-12-11 16:53 | 2020-12-31 | 2020-07-01
75084 | ORDFA | SKY2103DC | TO CAPTURE 2021 CAPITAL STORM #3 | 3667.28 |  | 3667.28 |  |  | 3667.28 | 0 | 3667.28 | 2020-12-07 16:50 | 2022-03-31 | 2021-03-01
75084 | ORDFA | SKY2108DC | TBC TO CAPTURE 2021 CAPITAL STOR | 2143.6 |  | 2143.6 |  |  | 2143.6 | 0 | 2143.6 | 2021-05-04 14:31 | 2022-10-01 | 2021-10-01
75084 | ORDFA | SKY2105DC | TO CAPTURE 2021 CAPITAL STORM #5 | 6794.48 |  | 6794.48 |  |  | 6794.48 | 5176.57 | 1617.91 | 2020-12-07 16:57 | 2022-03-31 | 2021-06-01 | 2021-09-30
75084 | OLE08FA | OLEKY | Kentucky New Lighting Install - OLE | 6512.77 |  | 6512.77 |  |  | 776804.59 | 10 | 776794.59 | 2014-08-04 | 2020-12-31 | 2015-01-01
75084 | SGCSFA | STKYT37 | SG DEK Self Healing Team 37 Capital | -12134.9 |  | -12134.9 |  |  | 44708.8 | 71071.44 | -26362.64 | 2014-04-21 | 2015-04-30 | 2014-05-01 | 2015-01-31
75084 | SG000430F | SG430C | Aero Pkwy Instl OH | -14149.35 |  | -14149.35 |  |  | 50746.65 | 29984.55 | 20762.1 | 2016-04-04 13:42 | 2017-09-01 | 2016-04-01 | 2016-12-02
75084 | SGPMYUF | SGYFA2SW | DEE YFA Ver 2 DER - Software | 0.06 |  | 0.06 |  |  | 24961.83 | 36217 | -11255.17 | 2016-01-08 10:09 | 2017-05-24 | 2016-01-01 | 2017-03-07
75084 | GLPRTFA | KYGLPR11 | F5967 Repl HL867 to HL872 and HL876 | -752.44 |  | -752.44 |  |  | -3.5314e-12 | 220579 | -220579 | 2016-11-14 13:36 | 2021-06-30 | 2017-05-01
75084 | VMTDFA | GGARKY | TVM Reactive Cap - DEK | 85.8 |  | 85.8 |  |  | 27337.24 | 2 | 27335.24 | 2019-10-16 15:20 | 2050-12-31 | 2020-03-01
75084 | VMTDFA | TVMBLLVKY | TVM NonNERC Cap - DEK | 135.73 |  | 135.73 |  |  | 209314.89 | 2 | 209312.89 | 2019-10-16 14:36 | 2050-12-31 | 2020-03-01
75084 | SGDMSCF | SG361SW | SG DEE DMS Project 10 SW | -336359.07 |  | -336359.07 |  |  | 1.1642e-10 | 266133.19 | -266133.19 | 2015-12-18 15:11 | 2022-05-28 | 2016-01-01 | 2022-03-31
75084 | SG000336F | SG336SW | SG DEE DMS ADMS - Software | -969274.34 |  | -969274.34 |  |  | -356.52 | 1049863.37 | -1050219.89 | 2016-09-06 17:51 | 2024-05-28 | 2016-09-01
75084 | SG000336F | SG336OUA | SG Oracle Utilities Analytics Softw | 7252.95 |  | 7252.95 |  |  | 155748.74 | 155000 | 748.74 | 2018-07-30 10:48 | 2021-05-28 | 2018-08-01 | 2021-07-01
75084 | SG000601F | SG601SW | DEE ADP Software - 601 | -192510.73 |  | -192510.73 |  |  | 151.39 | 42090 | -41938.61 | 2017-06-21 17:55 | 2025-03-31 | 2017-06-01
75084 | DKY2199 | D2199DL3 | AM 21607381 Hebron | -39592.24 |  | -39592.24 |  |  | 541273.4 | 250919.99 | 290353.41 | 2017-06-27 13:39 | 2020-07-30 | 2017-11-01 | 2020-07-21
75084 | DKY2199 | D2199DL2 | AM 21607299 Hebron - DKY2199 | -162.15 |  | -162.15 |  |  | 2085597.71 | 238000.64 | 1847597.07 | 2017-06-27 13:32 | 2020-07-30 | 2017-07-01 | 2020-07-29
75084 | 75084IK | KOUTUG | Outage Related UG Cap Replacements | 311080.68 |  | 311080.68 |  |  | 2710703.47 | 93 | 2710610.47 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KCMCOH | Non-Emergency OH Corrective Replace | 69539.49 |  | 69539.49 |  |  | 173113.08 | 93 | 173020.08 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEOH | Emergency OH Corrective Replacement | 348444.1 |  | 348444.1 |  |  | 1127179.41 | 93 | 1127086.41 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KPOLIR | Non Emerg Pole Replace Insp Based | 802399.87 |  | 802399.87 |  |  | 1273984.53 | 93 | 1273891.53 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPDMCPU | Public Damage UG Capital Replacemnt | 159173.37 |  | 159173.37 |  |  | 368948.21 | 93 | 368855.21 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KRIOTCO | OH Imprvmnt From PQRI Outage Invest | 9490.18 |  | 9490.18 |  |  | 434239.04 | 93 | 434146.04 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPOLCM | Reactive Pole Replacements | 322337.55 |  | 322337.55 |  |  | 1591949.9 | 93 | 1591856.9 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KPPL | Stub Pole Removal Only | 7594.57 |  | 7594.57 |  |  | 36522.81 | 2 | 36520.81 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KCAPAUTO | Capacitor Automation Upgrade | 1284240.2 |  | 1284240.2 |  |  | 1910499.69 | 93 | 1910406.69 | 2017-03-24 15:35 | 2067-12-31 | 2018-01-01
75084 | 75084IK | KLPF | Line Patrol Follow Up | 121244.06 |  | 121244.06 |  |  | 1483874.29 | 93 | 1483781.29 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTR1PH | Single PH Transformer Replace Dry | 9042.48 |  | 9042.48 |  |  | 59596.13 | 93 | 59503.13 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01
75084 | 75084IK | KCMCUG | Non-Emergency UG Corrective Repl | 51050.76 |  | 51050.76 |  |  | 152971.75 | 93 | 152878.75 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01
75084 | 75084IK | KSMF | Capital Replacements from SMEI Insp | 7587.89 |  | 7587.89 |  |  | 15505.32 | 93 | 15412.32 | 2017-03-27 14:35 | 2067-12-31 | 2018-03-01
75084 | 75084IK | KRRR | Recloser Replacements | 18817.61 |  | 18817.61 |  |  | 1195005.64 | 96 | 1194909.64 | 2017-03-27 13:10 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRIOTCU | UG Imprvmnt From PQRI Outage Invest | 10386.79 |  | 10386.79 |  |  | 64979.81 | 93 | 64886.81 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCIPOH | C&I Customer Additions OH | 716226.43 |  | 716226.43 |  |  | 4792711.89 | 93 | 4792618.89 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRXR | Transformer Retrofit | 61184.41 |  | 61184.41 |  |  | 436448.53 | 84 | 436364.53 | 2017-03-27 14:28 | 2067-12-31 | 2018-01-01
75084 | 75084IK | KCMCEUG | Emergency UG Corrective Replacement | 99540.98 |  | 99540.98 |  |  | 483032.27 | 93 | 482939.27 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01
75084 | 75084IK | MX8683892 | Declared Circuit - Donaldson (55) 5 | 66147.76 |  | 66147.76 |  |  | 88124.98 | 49876.34 | 38248.64 | 2018-09-27 14:02 | 2022-02-28 | 2018-12-01 | 2021-10-26
75084 | 75084IK | KDLS | Dline Switch Replacements | 186.57 |  | 186.57 |  |  | 161494.26 | 70 | 161424.26 | 2017-03-27 11:53 | 2067-12-31 | 2018-02-01
75084 | 75084IK | KRSOH | Residential Cust Adds Single Fam OH | 1162882.92 |  | 1162882.92 |  |  | 5099478.48 | 93 | 5099385.48 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KPDMCAP | Public Damage OH Capital Replacemen | 227162.5 |  | 227162.5 |  |  | 821952.22 | 80 | 821872.22 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KOUTOH | Outage Related OH Cap Replacements | 302523.14 |  | 302523.14 |  |  | 2156873.77 | 93 | 2156780.77 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01
75084 | 75084IK | MX0675382 | Westpack Customer Station | -0.1 |  | -0.1 |  |  | 1423.05 | 10800.23 | -9377.18 | 2017-12-15 14:01 | 2023-06-29 | 2018-03-01
75084 | 75084IK | KRUCSEC | UG Sec/Service Cable Replacement | 152259.66 |  | 152259.66 |  |  | 337172.89 | 93 | 337079.89 | 2017-03-27 13:33 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRUPOH | Residential Customer Upgrade OH | 361319.33 |  | 361319.33 |  |  | 1243069.13 | 93 | 1242976.13 | 2017-03-27 14:26 | 2067-12-31 | 2017-11-01
75084 | 75084IK | KCIUPOH | C&I Customer Upgrade OH | 250680.46 |  | 250680.46 |  |  | 554940.79 | 93 | 554847.79 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRMOH | Residential Cust Adds Multi Fam OH | 152325.15 |  | 152325.15 |  |  | 178555.91 | 93 | 178462.91 | 2017-03-27 13:07 | 2067-12-31 | 2017-08-01
75084 | 75084IK | KRTXO | Overhead Transformer Replacement | 115123.99 |  | 115123.99 |  |  | 191722.72 | 93 | 191629.72 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCEDT | Emerg DTUG Corrective Replacements | -388.13 |  | -388.13 |  |  | 219995.78 | 93 | 219902.78 | 2017-03-24 15:47 | 2067-12-31 | 2018-06-01
75084 | 75084IK | KRTP3PH | Three PH Transformer Replace Leaker | 21987.66 |  | 21987.66 |  |  | 177179.49 | 95 | 177084.49 | 2017-03-27 13:19 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KRTR3PH | Three PH Transformer Replace Dry | 26051.15 |  | 26051.15 |  |  | 56764.11 | 95 | 56669.11 | 2017-03-27 13:26 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KRCR | Capacitor Replacements & Assoc UOP | 115910.04 |  | 115910.04 |  |  | 538804.01 | 90 | 538714.01 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01
75084 | 75084IK | KCMCOWS | Secondary OH Wire Corr Replacement | 9210.76 |  | 9210.76 |  |  | 21530.57 | 93 | 21437.57 | 2017-03-27 11:47 | 2067-12-31 | 2018-04-01
75084 | 75084IK | KCMCOWP | Primary OH Wire Corr Replacement | 11518.75 |  | 11518.75 |  |  | 22891.67 | 93 | 22798.67 | 2017-03-27 11:33 | 2067-12-31 | 2018-11-01
75084 | 75084IK | MX9998915 | URD Wilder 41 | 17.11 |  | 17.11 |  |  | 16452.82 | 0 | 16452.82 | 2018-04-27 10:01 | 2023-07-29 | 2018-05-01
75084 | 75084IK | KROC | OH Deteriorated Conductor Replace | 129844.07 |  | 129844.07 |  |  | 145914.14 | 0 | 145914.14 | 2018-07-11 10:07 | 2067-12-31 | 2018-11-01
75084 | 75084IK | MX0924912 | MXCONV-JT- E TRIPLE CROWN SUBD SEC | -1599.72 |  | -1599.72 |  |  | 44940.9 | 213849.76 | -168908.86 | 2017-11-03 14:01 | 2018-03-01 | 2017-11-01 | 2018-05-07
75084 | 75084IK | MX0705495 | INSTALLATION OF SELF HEALING NEWWOR | -3016.65 |  | -3016.65 |  |  | 55099.6 | 55214.64 | -115.04 | 2018-02-14 10:01 | 2019-06-01 | 2018-03-01 | 2019-01-08
75084 | 75084IK | MX6839574 | COMMERCIAL PRIMARY/SECONDARY/SVC | -17722.99 |  | -17722.99 |  |  | 180144.65 | 168944.61 | 11200.04 | 2018-10-24 18:03 | 2019-07-01 | 2018-11-01 | 2019-02-28
75084 | 75084IK | MX8215200 | JT, E-AUDUBON FOREST SUBDIVISION | -1.81 |  | -1.81 |  |  | 29391.45 | 24640.12 | 4751.33 | 2018-05-01 14:01 | 2019-12-01 | 2018-12-01 | 2019-07-30
75084 | 75084IK | MX8755128 | Det. Conductor - Constance (41) 424 | 2973.67 |  | 2973.67 |  |  | 2136239.33 | 712968.4 | 1423270.93 | 2018-12-17 10:02 | 2020-09-28 | 2019-01-01 | 2020-08-10
75084 | 75084IK | MX2866326 | KENTUCKY 2019 LINE PATROL OH REPLAC | 0.54 |  | 0.54 |  |  | 384.51 | 8023.11 | -7638.6 | 2020-09-09 10:01 | 2022-11-29 | 2020-10-01
75084 | 75084IK | MX5977890 | Florence 46 Ln Ext to Aero | 22421.54 |  | 22421.54 |  |  | 22421.54 | 12338.21 | 10083.33 | 2021-01-27 10:02 | 2023-03-31 | 2021-01-01
75084 | 75084IK | KSBDUG | New Customer Work - Res Subdiv Infr | 602592.43 |  | 602592.43 |  |  | 884994.83 | 0 | 884994.83 | 2019-09-26 10:05 | 2028-04-01 | 2020-01-01
75084 | 75084IK | MX3500363 | JT-E-SANCTUARY VILLAGE PH 1 | -12609.62 |  | -12609.62 |  |  | 111002.09 | 392484.74 | -281482.65 | 2019-08-08 10:01 | 2020-11-23 | 2020-02-01 | 2020-11-16
75084 | 75084IK | MX0494866 | MXCONV-Transformer Retrofit KENTON | 6366.04 |  | 6366.04 |  |  | 88657.23 | 96102.31 | -7445.08 | 2019-11-18 18:01 | 2021-03-25 | 2019-11-01 | 2021-02-23
75084 | 75084IK | KELT3PH | End of Life Pad Transf 3PH Non Leak | 1078298.02 |  | 1078298.02 |  |  | 1664196.33 | 0 | 1664196.33 | 2020-01-09 15:04 | 2067-12-31 | 2020-02-01
75084 | 75084IK | MX2906128 | JT-E-WESTBROOK ESTATES PH 3 | 8219.71 |  | 8219.71 |  |  | 6354.71 | 9038.61 | -2683.9 | 2019-08-08 14:01 | 2021-07-04 | 2019-08-01 | 2021-06-16
75084 | 75084IK | KRTXLFCM | CD - Upgd Live Front Trsfr Reactive | 122112.32 |  | 122112.32 |  |  | 192552.74 | 97 | 192455.74 | 2019-03-21 16:21 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX6321718 | Longbranch 44 Part 3 - DKY2747 | 475741.97 |  | 475741.97 |  |  | 476186.57 | 356874.67 | 119311.9 | 2020-12-10 18:02 | 2023-01-29 | 2020-12-01 | 2023-02-13
75084 | 75084IK | KPOLOTH | Oth UOP Repl Found Thru Pole Insp | 9503.14 |  | 9503.14 |  |  | 9503.14 | 93 | 9410.14 | 2017-03-27 12:30 | 2067-12-31 | 2021-07-01
75084 | 75084IK | MX5265973 | MPO - 101 4TH W - PERM ELEC | -14093.94 |  | -14093.94 |  |  | 236096.03 | 170265.46 | 65830.57 | 2020-03-02 18:01 | 2021-03-22 | 2020-07-01 | 2021-03-19
75084 | 75084IK | MX7473884 | Oakbrook 42 Ln Ext DKY2769 | 109305.14 |  | 109305.14 |  |  | 145815.15 | 81317.73 | 64497.42 | 2020-09-16 18:01 | 2022-12-29 | 2020-10-01 | 2022-10-17
75084 | 75084IK | MX5068175 | PJG- 300 Richard Knock Blvd; Beaver | -1046.33 |  | -1046.33 |  |  | 80767.77 | 65923.97 | 14843.8 | 2020-10-05 10:01 | 2021-03-07 | 2020-10-01 | 2021-02-09
75084 | 75084IK | MX0604532 | Transformer Retrofit HANDS 43 | 144167.72 |  | 144167.72 |  |  | 144167.72 | 119596.25 | 24571.47 | 2021-04-22 10:02 | 2022-01-27 | 2021-07-01 | 2022-01-18
75084 | 75084IK | MX7890923 | UPGRADE TO EXISTING SERVICE COMMERC | 359353.06 |  | 359353.06 |  |  | 359707.38 | 243913.75 | 115793.63 | 2020-11-17 10:01 | 2022-11-24 | 2020-11-01 | 2022-10-30
75084 | 75084IK | KRFSCM | CD - Circ Sect - Reactive | 4646.92 |  | 4646.92 |  |  | 4646.92 | 89 | 4557.92 | 2019-03-21 15:28 | 2068-03-31 | 2021-05-01
75084 | 75084IK | MX7134076 | 2005CBT0779DEK DUKE TO REPLACE DUKE | 84512.19 |  | 84512.19 |  |  | 84512.19 | 61014.73 | 23497.46 | 2021-01-13 10:02 | 2021-07-29 | 2021-01-01 | 2021-07-14
75084 | 75084IK | MX8021723 | JT-E-WESTBROOK ESTATES PH 2 | 59874.56 |  | 59874.56 |  |  | 59874.56 | 55186.91 | 4687.65 | 2021-02-02 18:02 | 2021-08-10 | 2021-03-01 | 2021-07-27
75084 | 75084IK | MX2168625 | CABLE UG OTHER TESTED REPLACE SMALL | 78611.44 |  | 78611.44 |  |  | 79694.53 | 53872.4 | 25822.13 | 2019-03-11 10:01 | 2021-06-29 | 2019-05-01 | 2021-06-28
75084 | 75084IK | MX8107799 | Deteriorated Conductor - HEBRON (15 | 48590.97 |  | 48590.97 |  |  | 48590.97 | 43703.13 | 4887.84 | 2021-03-03 10:02 | 2022-03-16 | 2021-03-01 | 2022-03-16
75084 | 75084IK | MX2084151 | Deteriorated Conductor - Claryville | 371629.99 |  | 371629.99 |  |  | 371629.99 | 244553.23 | 127076.76 | 2021-03-24 10:02 | 2022-03-30 | 2021-04-01 | 2022-03-08
75084 | 75084IK | MX4866781 | Deteriorated Conductor - Claryville | 400675.11 |  | 400675.11 |  |  | 400675.11 | 254760.91 | 145914.2 | 2021-03-24 10:02 | 2022-02-28 | 2021-04-01 | 2022-02-13
75084 | 75084IK | MX0291269 | COMMERCIAL SERVICE FOR SOLAR/WIND/M | 224660.18 |  | 224660.18 |  |  | 224660.18 | 288352.06 | -63691.88 | 2021-05-26 14:02 | 2023-02-16 | 2021-06-01
75084 | 75084IK | KRRRCM | CD - Recl Elec Repl - Reactive | 105561.86 |  | 105561.86 |  |  | 256166.88 | 95 | 256071.88 | 2019-03-21 15:37 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX1576657 | Verona 41 Inst 4- 1ph Automated Cap | 26487.38 |  | 26487.38 |  |  | 123420.89 | 76863.06 | 46557.83 | 2019-04-18 18:01 | 2021-09-28 | 2019-04-01 | 2021-08-17
75084 | 75084IK | MX1006763 | Mt Zion - correct circuits config- | 17447.65 |  | 17447.65 |  |  | 17447.65 | 11641.06 | 5806.59 | 2021-05-20 10:02 | 2023-02-28 | 2021-06-01
75084 | 75084IK | KRNUIF | Removal of non-utilized infrastruct | 5752.67 |  | 5752.67 |  |  | 6640.68 | 0 | 6640.68 | 2017-12-13 12:01 | 2068-03-31 | 2020-07-01
75084 | 75084IK | KRUCLGCM | CD - UG Cable Repl LG Reactive | 28917.36 |  | 28917.36 |  |  | 37966.29 | 97 | 37869.29 | 2019-03-21 16:28 | 2068-03-31 | 2019-09-01
75084 | 75084IK | MX9852485 | 12000 Old Lexington Pike Line Exten | 223010.51 |  | 223010.51 |  |  | 223010.51 | 151333.27 | 71677.24 | 2021-03-15 10:02 | 2022-03-31 | 2021-07-01 | 2022-02-20
75084 | 75084IK | MX8566565 | ZKH - 101 ANDREWS WAY - SD1 - WILDE | -99102.8 |  | -99102.8 |  |  | -99102.8 | 56317.69 | -155420.49 | 2021-07-23 18:03 | 2022-10-27 | 2021-08-01 | 2022-10-11
75084 | 75084IK | MX7103196 | 35 W PIKE EMERGENCY TRANFORMER REPL | -224.43 |  | -224.43 |  |  | 19995.4 | 7421.26 | 12574.14 | 2020-06-11 10:01 | 2020-10-20 | 2020-06-01 | 2020-10-11
75084 | 75084IK | KRUCSMCM | CD - UG Cable Repl Reactive | 426805.21 |  | 426805.21 |  |  | 868550.54 | 97 | 868453.54 | 2019-03-21 16:34 | 2068-03-31 | 2019-06-01
75084 | 75084IK | MX6785518 | RLM; 411 W 6TH; COVINGTON42; COMMER | 62526.19 |  | 62526.19 |  |  | 83380.17 | 75386.32 | 7993.85 | 2020-09-15 14:01 | 2021-03-31 | 2020-12-01 | 2021-04-05
75084 | 75084IK | MX0883845 | RETROFITTING OVERHEAD TRANSFORMERS | 2219.28 |  | 2219.28 |  |  | 2219.28 | 2493.7 | -274.42 | 2021-05-12 10:02 | 2021-10-31 | 2021-06-01 | 2021-10-12
75084 | 75084IK | MX8250982 | Deteriorated Conductor - Crittenden | 501267.53 |  | 501267.53 |  |  | 501267.53 | 496269.57 | 4997.96 | 2021-03-24 10:02 | 2022-12-01 | 2021-04-01 | 2022-11-30
75084 | 75084IK | MX3255123 | TMG - COM. PRIM/SEC/SVC - 4706 AERO | -9775.23 |  | -9775.23 |  |  | 102883.02 | 65098.74 | 37784.28 | 2019-09-06 08:01 | 2021-01-21 | 2020-09-01 | 2021-01-12
75084 | 75084IK | MX2168562 | PROACTIVE REPLACEMENT SECTIONS OF C | 106151.6 |  | 106151.6 |  |  | 123766.05 | 109689.05 | 14077 | 2020-09-25 14:01 | 2021-09-28 | 2020-09-01 | 2021-08-01
75084 | 75084IK | MX8940536 | UG CABLE REPLACE SMALL - PROACTIVE | 18576.14 |  | 18576.14 |  |  | 18576.14 | 71645.53 | -53069.39 | 2021-02-10 18:02 | 2021-08-26 | 2021-02-01 | 2021-08-01
75084 | 75084IK | MX8022852 | PERM ELEC SERV;COMM/INDUST;OTHER;CI | -2317.85 |  | -2317.85 |  |  | -2317.85 | 23793.81 | -26111.66 | 2021-06-04 10:02 | 2022-08-08 | 2021-06-01 | 2022-09-18
75084 | 75084IK | MX8373261 | JT-E-Sawgrass Ph C, Part 1 | 76643 |  | 76643 |  |  | 76643 | 64179.94 | 12463.06 | 2021-07-20 14:02 | 2022-02-02 | 2021-08-01 | 2021-12-19
75084 | 75084IK | MX0305398 | KSL; BOONE COUNTY HIGHSCHOOL; 8330 | 17409.06 |  | 17409.06 |  |  | 17409.06 | 51653.96 | -34244.9 | 2021-07-30 10:02 | 2022-02-03 | 2021-08-01 | 2022-01-30
75084 | 75084IK | MX6660111 | JT-E-SANCTUARY VILLAGE PHASE 1, PAR | 92513.94 |  | 92513.94 |  |  | 86915.44 | 91842.81 | -4927.37 | 2020-12-18 14:01 | 2021-06-27 | 2020-12-01 | 2021-05-31
75084 | 75084IK | MX4866850 | Deteriorated Conductor - Claryville | 20760.86 |  | 20760.86 |  |  | 20760.86 | 27702.32 | -6941.46 | 2021-05-07 18:02 | 2022-02-24 | 2021-05-01 | 2021-11-03
75084 | 75084IK | MX1187308 | Deteriorated Conductor - White Towe | 185907.28 |  | 185907.28 |  |  | 213086.86 | 130833.25 | 82253.61 | 2020-08-05 10:01 | 2021-11-11 | 2020-08-01 | 2021-11-02
75084 | 75084IK | MX4559811 | TMG - TEMP SERVICE FOR COMM - AMAZO | -67.37 |  | -67.37 |  |  | 27119.64 | 67513.7 | -40394.06 | 2019-11-27 10:01 | 2020-05-14 | 2019-12-01 | 2020-04-27
75084 | 75084IK | MX8234316 | CAK-32 SWITCHGEAR MANUAL OTHER REPL | 808.06 |  | 808.06 |  |  | 52625.99 | 50357.01 | 2268.98 | 2019-08-28 14:01 | 2021-03-25 | 2020-09-01 | 2020-12-30
75084 | 75084IK | MX7196196 | JT-E-STEEPLECHASE SEC 18, PH 2/3 | -1100.44 |  | -1100.44 |  |  | 54427.43 | 55017.77 | -590.34 | 2020-08-05 14:01 | 2021-01-20 | 2020-09-01 | 2020-12-23
75084 | 75084IK | MX4318557 | TBC CONDUCTOR OH NEUTRAL REPLACE | -1944.5 |  | -1944.5 |  |  | -9.0816e-14 | 10533.78 | -10533.78 | 2020-12-09 10:02 | 2022-04-01 | 2020-12-01
75084 | 75084IK | KGENSWCM | CD - UG SWGR Repl Reactive | 38576.28 |  | 38576.28 |  |  | 38708.02 | 93 | 38615.02 | 2019-03-21 16:13 | 2068-03-31 | 2020-05-01
75084 | 75084IK | KMHR | Manhole Lid Retrofit Replacement | -0.96 |  | -0.96 |  |  | 1344.44 | 0 | 1344.44 | 2017-07-27 14:56 | 2067-12-31 | 2019-12-01
75084 | 75084IK | MX4746421 | JT-E-NORTH WALTON POINTE PH 5 | -6773.35 |  | -6773.35 |  |  | 38805.04 | 56430.23 | -17625.19 | 2020-02-06 14:01 | 2020-11-29 | 2020-02-01 | 2020-11-18
75084 | 75084IK | MX5977873 | Aero Sub Ln Ext to Bosch | 174945.64 |  | 174945.64 |  |  | 174945.64 | 184612.66 | -9667.02 | 2021-01-08 18:02 | 2023-05-01 | 2021-01-01
75084 | 75084IK | MX9048687 | McCULLUM PK-COMMERCIAL PRIMARY/SECO | 191242.12 |  | 191242.12 |  |  | 191242.12 | 138788.98 | 52453.14 | 2021-01-14 12:13 | 2022-11-30 | 2021-01-01
75084 | 75084IK | MX5851830 | TRANSFORMER UG THREE PHASE END OF L | 14727.38 |  | 14727.38 |  |  | 45511.48 | 50887.03 | -5375.55 | 2020-03-20 10:02 | 2021-03-30 | 2020-11-01 | 2021-04-04
75084 | 75084IK | KRXRCM | CD - Transf Retrofit - Reactive | 70793.91 |  | 70793.91 |  |  | 72260.93 | 84 | 72176.93 | 2019-03-21 15:58 | 2068-03-31 | 2020-01-01
75084 | 75084IK | MX5977198 | Limaburg 43 Ln Ext to CVG Conrac Bl | 13461.92 |  | 13461.92 |  |  | 395359.8 | 391628.46 | 3731.34 | 2020-08-18 14:01 | 2021-09-28 | 2020-11-01 | 2021-09-19
75084 | 75084IK | MX9918857 | STEFFEN RD-POLE REPLACEMENTS - NON- | 19622.36 |  | 19622.36 |  |  | 19622.36 | 26594.21 | -6971.85 | 2021-03-18 14:02 | 2023-05-01 | 2021-03-01
75084 | 75084IK | MX5916365 | JT-E-Hills at Crescent Springs Ph 1 | 46480.91 |  | 46480.91 |  |  | 46480.91 | 43804.03 | 2676.88 | 2021-02-01 18:01 | 2021-09-05 | 2021-02-01 | 2021-08-25
75084 | 75084IK | MX4497255 | OPEN LOOP - CABLE UG REPLACE SMALL- | 5856.34 |  | 5856.34 |  |  | 5856.34 | 57496.83 | -51640.49 | 2021-10-06 10:02 | 2022-06-29 | 2021-12-01 | 2022-06-13
75084 | 75084IK | MX3045963 | Declared Circuit - Donaldson 41 - 2 | 8315.04 |  | 8315.04 |  |  | 148955.24 | 628843.53 | -479888.29 | 2019-09-09 14:01 | 2031-02-27 | 2019-11-01
75084 | 75084IK | MX8073135 | UDF - 5093 PRIDE PKWY - ZKH -COMMER | 77370.76 |  | 77370.76 |  |  | 77370.76 | 45185.54 | 32185.22 | 2021-04-01 18:03 | 2021-10-07 | 2021-04-01 | 2021-09-14
75084 | 75084IK | MX4519392 | JT- E - Park Pointe | 202580.28 |  | 202580.28 |  |  | 194060 | 164587.57 | 29472.43 | 2020-03-25 14:01 | 2021-07-08 | 2020-03-01 | 2021-06-27
75084 | 75084IK | MX1977350 | Oakbrook 42 DKY2769 - Part 2 Recond | 3823.82 |  | 3823.82 |  |  | 3823.82 | 58673.78 | -54849.96 | 2021-08-13 10:12 | 2023-03-23 | 2021-10-01
75084 | 75084IK | MX0817561 | Limaburg 43 - PILC Replacement | 414328.08 |  | 414328.08 |  |  | 414328.08 | 353340.8 | 60987.28 | 2021-08-26 14:01 | 2022-01-01 | 2021-09-01 | 2021-12-20
75084 | 75084IK | MX7275238 | JT-E-SANCTUARY VILLAGE PH 1, PART 3 | 109271.92 |  | 109271.92 |  |  | 109271.92 | 98255.74 | 11016.18 | 2021-02-10 18:02 | 2021-11-18 | 2021-03-01 | 2021-09-08
75084 | 75084IK | MX4412975 | Deteriorated Conductor (Wilder 42) | 68117.03 |  | 68117.03 |  |  | 99678.44 | 55117.03 | 44561.41 | 2020-07-02 10:01 | 2022-12-15 | 2020-07-01 | 2022-11-23
75084 | 75084IK | MX7682127 | Mt Zion WORK NEEDED TO FINISH FP- D | 7016.95 |  | 7016.95 |  |  | 21543.19 | 13030.02 | 8513.17 | 2020-09-04 18:01 | 2021-06-29 | 2020-09-01 | 2021-06-16
75084 | 75084IK | KSCDL | Sys Capacity Distrib Load Transfers | 1767.06 |  | 1767.06 |  |  | 1767.06 | 93 | 1674.06 | 2017-03-27 14:31 | 2067-12-31 | 2021-07-01
75084 | 75084IK | MX8105481 | JT-E-ARCADIA PH K & L | 92466.34 |  | 92466.34 |  |  | 92466.34 | 83663.7 | 8802.64 | 2021-01-19 10:02 | 2021-07-29 | 2021-02-01 | 2021-07-14
75084 | 75084IK | MX6321063 | Longbranch 44 PT 2 | 301287.47 |  | 301287.47 |  |  | 301287.47 | 218837.74 | 82449.73 | 2021-04-06 18:02 | 2023-02-16 | 2021-04-01 | 2023-01-16
75084 | 75084IK | MX9815429 | KSL; 7900 FOUNDATION DR; BUFFINGTON | -170568.35 |  | -170568.35 |  |  | -170568.35 | 164557.11 | -335125.46 | 2021-11-15 14:01 | 2022-04-28 | 2021-11-01 | 2022-04-11
75084 | 75084IK | MX4154470 | OPEN LOOP - CABLE UG REPLACE SMALL- | 8855.48 |  | 8855.48 |  |  | 8855.48 | 63412.35 | -54556.87 | 2021-10-06 10:02 | 2023-02-07 | 2021-12-01
75084 | 75084IK | MX7154409 | NEW-Circuit Sectionalization Bellev | 48280.91 |  | 48280.91 |  |  | 87521.85 | 91889.28 | -4367.43 | 2020-06-16 10:01 | 2021-02-28 | 2020-08-01 | 2021-01-12
75084 | 75084IK | MX1793644 | Transformer Retrofit - Crescent 43 | 2286.88 |  | 2286.88 |  |  | 2286.88 | 53485.55 | -51198.67 | 2021-09-13 10:02 | 2023-03-30 | 2021-11-01
75084 | 75084IK | MX1572579 | INFRASTRUCTIURE FOR ARCADIA VINEYAR | -4453.1 |  | -4453.1 |  |  | 29209.71 | 24189.95 | 5019.76 | 2019-04-29 14:22 | 2020-11-18 | 2020-06-01 | 2020-11-16
75084 | 75084IK | MX8701723 | JT-E-ALEXANDRIA FLATS, SEC 1 | -5080.19 |  | -5080.19 |  |  | -5080.19 | 75038.83 | -80119.02 | 2021-08-24 10:01 | 2022-11-01 | 2021-08-01 | 2022-09-21
75084 | 75084IK | MX2493908 | KEG - 472 CHAMBERS - STEEPLECHASE S | 74478.11 |  | 74478.11 |  |  | 74478.11 | 72361.34 | 2116.77 | 2019-12-09 10:01 | 2021-06-24 | 2021-02-01 | 2021-06-02
75084 | 75084IK | MX6404515 | JT-E-Tuscany Ph C, Sec 17,19,20 | -6987.59 |  | -6987.59 |  |  | 55068.7 | 63761.47 | -8692.77 | 2020-06-24 10:01 | 2021-02-16 | 2020-06-01 | 2021-02-08
75084 | 75084IK | MX5872280 | TRANSFORMER UG THREE PHASE END OF L | 20053.15 |  | 20053.15 |  |  | 55367.26 | 50562.79 | 4804.47 | 2020-03-31 10:02 | 2021-03-30 | 2020-12-01 | 2021-04-04
75084 | 75084IK | MX4307999 | JT-E-NORTHERN LIGHTS SUBDIVISION | 24634.56 |  | 24634.56 |  |  | 23720.81 | 19320.82 | 4399.99 | 2019-10-15 10:01 | 2021-08-03 | 2020-05-01 | 2021-07-11
75084 | 75084IK | MX1261517 | RLM: 1431 DIXIE: MULTIFAMILY PRIMAR | 43925.42 |  | 43925.42 |  |  | 43925.42 | 48426.64 | -4501.22 | 2021-09-22 10:01 | 2022-07-27 | 2021-10-01 | 2022-06-13
75084 | 75084IK | MX7465108 | JT-E-Sanctuary Village Ph 1, Part 5 | 62945.76 |  | 62945.76 |  |  | 62945.76 | 60324.99 | 2620.77 | 2021-02-08 10:02 | 2021-11-18 | 2021-03-01 | 2021-09-08
75084 | 75084IK | MX8234251 | CAK-30 SWITCHGEAR MANUAL OTHER REPL | -2115.56 |  | -2115.56 |  |  | 52738.01 | 46975.83 | 5762.18 | 2019-08-28 14:01 | 2020-11-28 | 2020-04-01 | 2020-10-13
75084 | SG000440F | SGRFSKY | DEK Sectionalization | 2473.25 |  | 2473.25 |  |  | 74519.8 | 83 | 74436.8 | 2016-05-16 10:23 | 2025-12-31 | 2017-01-01
75084 | DKY2017 | D2017DL5 | RUSD Donaldson Hwy Retire - DKY2017 | -80416.11 |  | -80416.11 |  |  | 18718.13 | 12270.87 | 6447.26 | 2017-04-25 11:29 | 2023-04-30 | 2017-12-01
75084 | DKY2017 | D2017DL3 | AM 21113304 Davidson Hwy - DKY2017 | -19246.8 |  | -19246.8 |  |  | 160495.89 | 204529.81 | -44033.92 | 2017-04-17 15:00 | 2020-12-18 | 2017-07-01 | 2020-10-26
75084 | DKY2017 | D2017DL4 | RUSD Donaldson Retire Erlanger Road | -53938.98 |  | -53938.98 |  |  | 5194.24 | 94106.3 | -88912.06 | 2017-04-25 11:01 | 2021-04-30 | 2019-03-01 | 2021-05-10
75084 | DKY2017 | MX1113152 | MXCONV-Donaldson 43 Instl UG Condui | 159204.73 |  | 159204.73 |  |  | 8107743.62 | 2636453.11 | 5471290.51 | 2018-11-09 14:02 | 2020-09-28 | 2019-04-01 | 2020-09-22
75084 | DKY2017 | MXA113380 | MXCONV-Donaldson Instl UG Cable DKY | 255503.49 |  | 255503.49 |  |  | 2470774.45 | 1304605.52 | 1166168.93 | 2019-04-09 14:01 | 2020-11-26 | 2019-04-01 | 2020-10-19
75084 | DKY2019 | MX2240021 | Buffington 43 Ln Ext - DKY2019 | 9639.82 |  | 9639.82 |  |  | 413524.14 | 108589.89 | 304934.25 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-16
75084 | DKY2019 | MX2239971 | Dixie 45 Ln Ext - DKY2019 | -50366.37 |  | -50366.37 |  |  | 2635.8 | 145406.88 | -142771.08 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-14
75084 | DKY2019 | MX1269760 | Buffington 43 UG - DKY2019 | 376306.72 |  | 376306.72 |  |  | 454128.7 | 20243.51 | 433885.19 | 2018-03-19 14:01 | 2021-05-01 | 2018-04-01 | 2021-03-29
75084 | TKY1695 | T1695TS2 | Kenton F966 Rel Repl - TKY1695 | 122320.75 |  | 122320.75 |  |  | 510047.76 | 352819 | 157228.76 | 2016-10-07 18:03 | 2021-02-15 | 2016-12-01 | 2021-03-17
75084 | KUCF61121 | KUC261121 | TBC UG 10261121 Villa 44 | -1783.02 |  | -1783.02 |  |  | -1.8296e-13 | 131529.73 | -131529.73 | 2017-04-11 14:03 | 2021-07-01 | 2017-06-01
75084 | SG000223F | SG223SW | DEE Transmission Health & Risk Mgt | 95572.95 |  | 95572.95 |  |  | 617348.4 | 1016639 | -399290.6 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01
75084 | SG000732F | SG732TR01 | DEK Towers & Shelters - Verona | 232246.51 |  | 232246.51 |  |  | 1557994.44 | 968336.2 | 589658.24 | 2018-09-11 15:00 | 2021-09-30 | 2018-09-01 | 2021-04-15
75084 | SG000732F | SG732TR04 | DEK Twr,Sheltr,PwrSup_Sparta MW | 4532.34 |  | 4532.34 |  |  | 4532.34 | 1519055 | -1514522.66 | 2021-02-05 14:19 | 2024-03-31 | 2021-02-01
75084 | SG000732F | SG732TR02 | DEK Tower & Shelter - Verona 2 | 4398.77 |  | 4398.77 |  |  | 20057.16 | 968336 | -948278.84 | 2019-01-23 11:05 | 2022-03-31 | 2019-02-01
75084 | SG000732F | SG732TR03 | Communication Tower , Shelter and S | 51162.11 |  | 51162.11 |  |  | 51662.82 | 1519055 | -1467392.18 | 2020-10-30 10:38 | 2023-03-31 | 2020-12-01
75084 | SG000732F | SG732TR05 | Comm Towers,Shelters-Ryland Heights | 3050.43 |  | 3050.43 |  |  | 3050.43 | 1519055 | -1516004.57 | 2021-03-11 16:09 | 2025-03-31 | 2021-05-01
75084 | SG000732F | SG732TR06 | Communication Tower, Shelter and Sy | 1130237.03 |  | 1130237.03 |  |  | 1130237.03 | 1777260 | -647022.97 | 2021-06-10 07:49 | 2022-11-15 | 2021-06-01 | 2022-11-30
75084 | SG000438F | SGSELFKY | DEK Segmentation & Automation | 426264.83 |  | 426264.83 |  |  | 1479219.61 | 1 | 1479218.61 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01
75084 | SG000438F | MX7372069 | Villa 43 K95-22 INSTALL SEG SHT 112 | 65498.63 |  | 65498.63 |  |  | 65498.63 | 54576.55 | 10922.08 | 2021-04-12 10:02 | 2022-02-13 | 2021-06-01 | 2022-02-15
75084 | SG000438F | MX1277606 | Longbranch 44 PT 2 - Recl 1 Mount Z | 60759.59 |  | 60759.59 |  |  | 60759.59 | 47359.32 | 13400.27 | 2021-10-28 14:01 | 2023-01-29 | 2021-11-01
75084 | SG000438F | SG438DOTS | Distribution Operator Training Sim | 50.92 |  | 50.92 |  |  | 16226.01 | 1 | 16225.01 | 2019-10-31 16:15 | 2021-09-30 | 2019-10-01 | 2022-03-31
75084 | SG000438F | MX1278018 | Longbranch 44 PT 2 - Recl 2 Mount Z | 63122.06 |  | 63122.06 |  |  | 63122.06 | 46482.63 | 16639.43 | 2021-10-28 14:01 | 2023-01-29 | 2021-11-01 | 2023-01-26
75084 | SG000438F | MX1278081 | Longbranch 44 PT 2 - Recl 3 Mount Z | 15554.72 |  | 15554.72 |  |  | 15554.72 | 46603.9 | -31049.18 | 2021-10-28 14:01 | 2023-01-29 | 2021-11-01
75084 | 75084HW | KHWYR | Highway Relocations Reimb | -32703.72 |  | -32703.72 |  |  | 56402.78 | 80 | 56322.78 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01
75084 | 75084HW | MX9624173 | Ri-I-71/I-75 & KY 536 Inneerchange | -16434.33 |  | -16434.33 |  |  | 93400.02 | 142487.26 | -49087.24 | 2018-09-06 14:02 | 2021-01-14 | 2018-09-01 | 2021-01-19
75084 | 75084HW | KCOU | Make Ready Other Util Attachments | 477101.92 |  | 477101.92 |  |  | 698025.75 | 91 | 697934.75 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01
75084 | 75084HW | KCRFN | Customer Requested Mods Nonreimb | 54604.53 |  | 54604.53 |  |  | 187995.86 | 80 | 187915.86 | 2017-03-24 15:19 | 2067-12-31 | 2018-06-01
75084 | 75084HW | KCRFR | Customer Requested Mods Reimb | 38378.61 |  | 38378.61 |  |  | 10033.2 | 98 | 9935.2 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01
75084 | 75084HW | KHWYN | Highway Relocations Nonreimb | 376039.31 |  | 376039.31 |  |  | 960077.95 | 80 | 959997.95 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01
75084 | 75084HW | MX9612876 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 9786.3 |  | 9786.3 |  |  | 129373.75 | 132976.53 | -3602.78 | 2018-08-28 10:02 | 2021-01-30 | 2018-09-01 | 2021-01-27
75084 | 75084HW | MX1661647 | RELOCATION HIGHWAY DOT SPECIFIC PRO | -73126.92 |  | -73126.92 |  |  | 1097018.09 | 228.31 | 1096789.78 | 2017-11-28 14:01 | 2021-03-18 | 2017-12-01 | 2021-02-21
75084 | 75084HW | MX7090228 | RI-6th St Beautification, undergrou | -126071.29 |  | -126071.29 |  |  | 98493.3 | 150507.84 | -52014.54 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-05-22
75084 | 75084HW | MX7090285 | RI-6th St Beautification, overhead | -136821.47 |  | -136821.47 |  |  | 65423.98 | 155930.4 | -90506.42 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-03-09
75084 | 75084HW | KMODC | Other Capital Modifications | 25959.93 |  | 25959.93 |  |  | 145451.47 | 80 | 145371.47 | 2017-03-24 15:33 | 2067-12-31 | 2018-07-01
75084 | 75084HW | MX6295870 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 4356.78 |  | 4356.78 |  |  | 181317.24 | 83155.24 | 98162 | 2017-11-30 18:02 | 2019-06-01 | 2017-12-01 | 2019-05-21
75084 | 75084HW | MX6277290 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 15058.64 |  | 15058.64 |  |  | 20161.03 | 0 | 20161.03 | 2020-04-02 18:01 | 2023-09-03 | 2020-04-01
75084 | 75084HW | MX2513722 | RI - PARK POINTE RELOCATION; AMSTER | 85087.07 |  | 85087.07 |  |  | 562343.35 | 429103.61 | 133239.74 | 2019-07-29 14:02 | 2021-03-31 | 2019-08-01 | 2021-03-03
75084 | 75084HW | MX2483019 | RI-Reconstruction of the I-75/71 Ri | 134500.9 |  | 134500.9 |  |  | 830198.82 | 383026.87 | 447171.95 | 2019-05-06 10:16 | 2021-06-17 | 2019-05-01 | 2021-06-14
75084 | 75084HW | MX5740957 | S WARD, BELLEVUE, LANDSLIDE RELO | -6296.07 |  | -6296.07 |  |  | 41282.57 | 42074.83 | -792.26 | 2020-10-01 14:01 | 2021-05-13 | 2020-10-01 | 2021-04-28
75084 | 75084HW | MX5301338 | KENTABOO AVE RECONSTRUCTION - PHASE | -6420.92 |  | -6420.92 |  |  | 141880.77 | 174958.54 | -33077.77 | 2020-07-08 18:01 | 2021-05-04 | 2020-07-01 | 2021-04-28
75084 | 75084HW | MX5888698 | KYTC KY RT 3060 FROGTOWN RD | 73918.36 |  | 73918.36 |  |  | 97598.06 | 104635.29 | -7037.23 | 2020-04-02 18:01 | 2021-09-30 | 2020-04-01 | 2021-08-18
75084 | 75084HW | MX5931078 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 12962.86 |  | 12962.86 |  |  | 13143.6 | 77608.13 | -64464.53 | 2020-04-02 18:01 | 2022-12-29 | 2020-09-01
75084 | 75084HW | MX2481408 | RI-Reconstruction of the (-75/71 Ri | -108111.61 |  | -108111.61 |  |  | 539134.86 | 343628.23 | 195506.63 | 2019-05-06 14:01 | 2021-02-25 | 2019-05-01 | 2021-02-02
75084 | 75084HW | MX2972789 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 384300.38 |  | 384300.38 |  |  | 785183.44 | 295758.93 | 489424.51 | 2019-10-21 18:01 | 2021-08-05 | 2020-04-01 | 2021-08-05
75084 | 75084HW | MX2481659 | RI -Reconstruction of the I-75/71 | -213.27 |  | -213.27 |  |  | 592645.29 | 522132.65 | 70512.64 | 2019-05-06 14:01 | 2021-02-25 | 2019-06-01 | 2021-01-27
75084 | 75084HW | MX5847868 | RELOCATION HIGHWAY DOT SPECIFIC PRO | -59688.67 |  | -59688.67 |  |  | 216315.29 | 199520.97 | 16794.32 | 2020-04-02 18:01 | 2021-06-24 | 2020-04-01 | 2021-05-09
75084 | 75084HW | MX1642381 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 112682.16 |  | 112682.16 |  |  | 112682.16 | 97249.08 | 15433.08 | 2021-07-15 14:02 | 2021-11-29 | 2021-07-01 | 2021-10-31
75084 | 75084HW | MX7501803 | MAKE-READY,2003MCI0269DEK JOINT USE | 67562.23 |  | 67562.23 |  |  | -15260.33 | 67158.37 | -82418.7 | 2020-07-27 10:01 | 2021-08-29 | 2020-08-01 | 2021-07-21
75084 | 75084HW | MX9326744 | JOYCE AVE DRAINAGE IMPROVEMENTS - 4 | 15467.25 |  | 15467.25 |  |  | 15467.25 | 43565.51 | -28098.26 | 2021-04-01 10:02 | 2021-10-31 | 2021-04-01 | 2021-08-04
75084 | 75084HW | MX7793948 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 127862.29 |  | 127862.29 |  |  | 303292.23 | 361208.66 | -57916.43 | 2020-08-17 14:01 | 2021-08-05 | 2020-09-01 | 2021-06-29
75084 | 75084HW | MX1386064 | RLM: 535 MADISON: OH CABLE CLEARS I | 44501.81 |  | 44501.81 |  |  | 44501.81 | 60952.97 | -16451.16 | 2021-09-22 10:01 | 2022-03-17 | 2021-09-01 | 2022-03-16
75084 | 75084HW | MX2156340 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 11.46 |  | 11.46 |  |  | 429.85 | 1044.91 | -615.06 | 2019-04-24 14:01 | 2022-03-31 | 2020-10-01 | 2022-03-09
75084 | 75084HW | MX1096567 | Exhibit A DEK 1812MCI0545DEK, MAKE- | 5277.68 |  | 5277.68 |  |  | -16511.25 | 49290.4 | -65801.65 | 2019-08-23 14:01 | 2020-02-23 | 2019-08-01 | 2020-01-26
75084 | 75084HW | MX4550664 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 29544.65 |  | 29544.65 |  |  | 78188.71 | 244472.16 | -166283.45 | 2020-01-16 10:01 | 2021-11-26 | 2020-02-01 | 2021-09-20
75084 | 75084HW | MX2288324 | HANDS PK @ CRYSTAL LAKE DR, RELOCAT | 2390.3 |  | 2390.3 |  |  | 177717.35 | 159886.58 | 17830.77 | 2019-10-03 14:01 | 2020-10-12 | 2019-10-01 | 2020-08-12
75084 | 75084HW | MX4705742 | TMG - CVG / VAULT 12 - PRIMARY METE | -10984.13 |  | -10984.13 |  |  | -14059.16 | 53974.14 | -68033.3 | 2020-05-04 10:01 | 2021-01-28 | 2020-06-01 | 2021-01-11
75084 | 75084HW | MX0630129 | WILBERS LN RECONSTRUCTION | 73454.88 |  | 73454.88 |  |  | 73454.88 | 78840.75 | -5385.87 | 2021-06-09 10:02 | 2022-03-23 | 2021-07-01 | 2022-03-06
75084 | 75084HW | MX2506723 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 4315.16 |  | 4315.16 |  |  | 4315.16 | 173052.3 | -168737.14 | 2021-10-07 10:02 | 2022-07-28 | 2021-10-01 | 2022-06-13
75084 | 75084HW | MX1276918 | KY 536 - Mt.ZION RD. (CABLE WORK) | -12230.47 |  | -12230.47 |  |  | 94198.48 | 225364.83 | -131166.35 | 2019-02-04 10:02 | 2020-12-24 | 2019-02-01 | 2020-10-28
75084 | 75084HW | MX6240781 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 283878.02 |  | 283878.02 |  |  | 284606.13 | 160184.27 | 124421.86 | 2020-04-02 18:01 | 2022-06-30 | 2020-04-01 | 2022-07-18
75084 | 75084HW | MX3147077 | HW Crossing Removal - DKYHW2672 | 182.3 |  | 182.3 |  |  | 182.29 | 436.56 | -254.27 | 2019-06-26 14:01 | 2020-08-01 | 2019-08-01 | 2020-10-06
75084 | 75084HW | MX1277017 | KY 536 - Mt. ZION RD. (CONDUIT WORK | -360.12 |  | -360.12 |  |  | 17305.37 | 132813.99 | -115508.62 | 2019-02-04 10:02 | 2020-11-12 | 2019-02-01 | 2020-11-01
75084 | 75084HW | MX0523594 | RELOCATION HIGHWAY DOT SPECIFIC PRO | -0.01 |  | -0.01 |  |  | -0.01 | 17873.77 | -17873.78 | 2021-04-09 18:02 | 2021-10-28 | 2021-04-01 | 2021-09-19
75084 | 75084HW | MX1276812 | KY 536 (OH WORK) | -6095.56 |  | -6095.56 |  |  | 145793.23 | 137747.11 | 8046.12 | 2019-02-04 10:02 | 2021-01-30 | 2019-02-01 | 2021-01-27
75084 | 75084HW | MX6706663 | RELOCATION HIGHWAY DOT SPECIFIC PRO | -7759.18 |  | -7759.18 |  |  | 33138.9 | 24806.4 | 8332.5 | 2020-05-07 14:01 | 2021-03-01 | 2020-06-01 | 2021-01-19
75084 | 75084HW | MX7240607 | KYTC AA HIGHWAY AT GLENRIDGE INTERS | -2673.22 |  | -2673.22 |  |  | 19887.15 | 30819.59 | -10932.44 | 2020-06-29 10:01 | 2020-12-03 | 2020-07-01 | 2020-11-26
75084 | 75084HW | MX1072480 | CHAPMAN LN STREET RECONSTRUCTION | 65493.66 |  | 65493.66 |  |  | 65493.66 | 60940.85 | 4552.81 | 2021-08-18 14:03 | 2022-02-20 | 2021-09-01 | 2022-02-20
75084 | 75084HW | MX0880544 | Aero Parkway Turn lane Relocation | -38856.35 |  | -38856.35 |  |  | -38856.35 | 82588.18 | -121444.53 | 2021-05-13 14:02 | 2021-12-30 | 2021-06-01 | 2021-11-01
75084 | 75084HW | MX7541330 | MAKE-READY, 2007MCI0336DEK JOINT US | 36034.05 |  | 36034.05 |  |  | -14217.09 | 39389.7 | -53606.79 | 2020-12-01 18:02 | 2021-07-14 | 2020-12-01 | 2021-07-14
75084 | 75084HW | MX0692287 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 498.67 |  | 498.67 |  |  | 498.67 | 31915.46 | -31416.79 | 2021-04-26 18:02 | 2021-09-23 | 2021-05-01 | 2021-09-19
75084 | 75084HW | MX2120706 | TMG- 614 MADISON AVE.-INSTALL - CO | -69056.84 |  | -69056.84 |  |  | -69056.84 | 70608.08 | -139664.92 | 2021-10-08 18:02 | 2022-05-05 | 2021-10-01 | 2022-05-04
75084 | 75084HW | MX9147524 | Mt. Zion Road Transmission Underbui | 86114.61 |  | 86114.61 |  |  | 86114.61 | 79912.7 | 6201.91 | 2021-01-19 10:02 | 2022-05-16 | 2021-04-01 | 2022-03-16
75084 | 75084HW | MX1478604 | RELOCATION HIGHWAY DOT SPECIFIC PRO | 2209.24 |  | 2209.24 |  |  | 2209.24 | 14375.21 | -12165.97 | 2021-06-29 18:02 | 2022-06-23 | 2021-07-01 | 2022-06-21
75084 | 75084HW | MX1330863 | DKY2927 WESTERN AVE STABILIZATION P | 13986.74 |  | 13986.74 |  |  | 13986.74 | 118278.11 | -104291.37 | 2021-12-09 18:02 | 2022-06-09 | 2021-12-01 | 05/22/2022
75084 | CP18SUBK | MX1488550 | CAPITAL Wilder TB4 replace X0, X1, | 68.39 |  | 68.39 |  |  | 21788.26 | 17460.92 | 4327.34 | 2019-02-12 14:01 | 2022-03-31 | 2019-03-01
75084 | CP18SUBK | MX1543301 | CAPITAL Wilder TB1 replace X1, X2, | 3020.24 |  | 3020.24 |  |  | 53318.56 | 20594.56 | 32724 | 2019-02-14 18:01 | 2021-03-31 | 2019-09-01 | 2021-03-14
75084 | TKY2204 | T2204DS1 | Buffington Rcfgr 4_5 - TKY2204 | 190887.56 |  | 190887.56 |  |  | 2489529.4 | 2109259 | 380270.4 | 2018-05-02 10:01 | 2021-02-20 | 2018-06-01 | 2021-03-30
75084 | TKY2204 | MX8413578 | Buffington TX Feed to Buss Circuits | -77.83 |  | -77.83 |  |  | 17864.54 | 904.8 | 16959.74 | 2020-10-13 10:01 | 2021-05-01 | 2020-10-01 | 2021-03-01
75084 | TKY2204 | MX8400391 | Buffington Cable & Term Pole Re-Bui | -49627.63 |  | -49627.63 |  |  | 78638.85 | 47097.51 | 31541.34 | 2020-10-13 10:01 | 2021-03-04 | 2020-11-01 | 2021-03-01
75084 | KARF51805 | KAR851805 | LAR 10851805 Wilder 44 | -27587.74 |  | -27587.74 |  |  | 1013197.12 | 313344.88 | 699852.24 | 2016-07-26 14:03 | 2020-03-31 | 2016-09-01 | 2019-12-17
75084 | TKY1791 | T1791TS1 | Villa 69kV Bus 1 CCVT Rpl - TKY1791 | 1705.95 |  | 1705.95 |  |  | 827357.14 | 814297.47 | 13059.67 | 2017-05-17 14:03 | 2020-07-25 | 2017-08-01 | 2020-08-24
75084 | 75084IL | KSLNOLE | Non Ole Street Light Replacements | -2316.48 |  | -2316.48 |  |  | 42401.1 | 58 | 42343.1 | 2017-03-28 09:41 | 2067-04-01 | 2018-02-01
75084 | 75084IL | KCAL | Area Light New Installs | 446818.75 |  | 446818.75 |  |  | 1013971.26 | 98 | 1013873.26 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KLEDSL | LED Street Light Retrofit | -166346.35 |  | -166346.35 |  |  | 70635.65 | 58 | 70577.65 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01
75084 | 75084IL | KSLRPL | Street Light Replacements | 273410.01 |  | 273410.01 |  |  | 637232.17 | 58 | 637174.17 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01
75084 | 75084IL | KALRPL | Area Light Replacements | 43094.05 |  | 43094.05 |  |  | 141889.86 | 58 | 141831.86 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01
75084 | 75084IL | KRUL | UG Cable Lighting Replacements | 13937.92 |  | 13937.92 |  |  | 19614.64 | 91 | 19523.64 | 2017-03-28 09:39 | 2067-04-01 | 2018-05-01
75084 | 75084IL | MX6293181 | Florence Lighting Upgrade Phase 1 | 176234.22 |  | 176234.22 |  |  | -45108.53 | 240125.13 | -285233.66 | 2018-03-12 14:01 | 2019-01-30 | 2018-04-01 | 2019-03-04
75084 | 75084IL | MX6486641 | Florence Lighting Upgrade Phase 3 | 48835.71 |  | 48835.71 |  |  | -14606.6 | 66900.04 | -81506.64 | 2018-03-12 14:01 | 2018-09-28 | 2018-05-01 | 2019-01-29
75084 | 75084IL | MX6643892 | MAIN ST BROMLEY STREET LIGHTING | 82298.35 |  | 82298.35 |  |  | 82298.35 | 51229.6 | 31068.75 | 2020-05-21 10:01 | 2022-01-27 | 2021-06-01 | 2022-01-09
75084 | 75084IL | MX4108382 | 6TH & SCOTT ST UG CONVERSION ST LIG | 77315.96 |  | 77315.96 |  |  | 232732.02 | 106128.95 | 126603.07 | 2020-06-16 18:01 | 2021-03-30 | 2020-10-01 | 2021-03-16
75084 | 75084IL | MX9863276 | CRESCENT SPRINGS INSTALL PART 2 | 18477.41 |  | 18477.41 |  |  | 74032.27 | 51273.61 | 22758.66 | 2020-05-12 10:01 | 2021-02-25 | 2020-05-01 | 2021-02-22
75084 | 75084IL | MX2173036 | LED Conversion - Villa Hills, KY P | 128821.22 |  | 128821.22 |  |  | 128821.22 | 237221.08 | -108399.86 | 2021-07-15 14:02 | 2022-05-26 | 2021-10-01 | 2022-05-16
75084 | 75084IL | MX7650909 | OVATION MUSIC VENUE LIGHTING 4TH & | 3860.96 |  | 3860.96 |  |  | -150.94 | 40107.76 | -40258.7 | 2020-08-27 14:01 | 2021-03-18 | 2020-10-01 | 2021-03-01
75084 | 75084IL | MX2174696 | LED Conversion - Villa Hills, KY Pa | 202201.92 |  | 202201.92 |  |  | 202201.92 | 150836.84 | 51365.08 | 2021-07-15 10:02 | 2022-02-24 | 2021-10-01 | 2022-02-21
75084 | 75084IL | MX9409958 | C5 75/71 NORTHERN KENTUCKY LOGISTIC | 255678.41 |  | 255678.41 |  |  | 255678.41 | 187589.23 | 68089.18 | 2021-03-16 10:03 | 2022-01-02 | 2021-05-01 | 2021-10-26
75084 | 75084IL | KPPLLGT | Purple Light Replace | 24366.43 |  | 24366.43 |  |  | 24366.43 | 0 | 24366.43 | 2021-04-16 11:58 | 2069-12-31 | 2021-07-01
75084 | 75084IL | KCSL | Street Light New Installs | 105.31 |  | 105.31 |  |  | 105.31 | 97 | 8.31 | 2017-03-28 09:32 | 2067-04-01 | 2021-11-01
75084 | SG000468F | SG468MDM | SG DEK Next Gen Cellular | 87840.54 |  | 87840.54 |  |  | 833828.58 | 1684462.49 | -850633.91 | 2017-10-10 12:47 | 2026-03-31 | 2018-01-01 | 2022-08-24
75084 | 75084VM | VDHAZPGKY | VDHAZPGKY | 28759.26 |  | 28759.26 |  |  | 952974.34 | 1 | 952973.34 | 2017-05-25 15:32 | 2050-12-31 | 2018-01-01
75084 | 75084VM | VDREMVCKY | VDREMVCKY | 507127.71 |  | 507127.71 |  |  | 1678032.05 | 1 | 1678031.05 | 2017-05-25 11:52 | 2050-12-30 | 2018-01-01
75084 | 75084VM | VDHAZL2KY | VDHAZL2KY | 219703.7 |  | 219703.7 |  |  | 219703.7 | 1 | 219702.7 | 2020-12-22 15:04 | 2050-12-31 | 2021-02-01
75084 | 75084VM | VDEXTCUKY | VDEXTCUKY | 6930.81 |  | 6930.81 |  |  | 6930.81 | 0 | 6930.81 | 2017-07-13 12:51 | 2050-12-31 | 2021-01-01
75084 | SG000586F | SGDLSKY | RUSD DEK D-Line Switch Replacement | 60798.52 |  | 60798.52 |  |  | 325210.71 | 94 | 325116.71 | 2016-12-19 11:23 | 2025-12-31 | 2017-05-01
75084 | DKY2134 | D2134DL2 | AM 21801679 Oakbrook 42 | 172829.64 |  | 172829.64 |  |  | 2280311.26 | 529469.63 | 1750841.63 | 2017-07-25 14:20 | 2019-12-31 | 2018-03-01 | 2020-03-19
75084 | SG000794F | SG794DES | DEK Land Mobile Radio Design | 1604.27 |  | 1604.27 |  |  | 32326.59 | 154508.56 | -122181.97 | 2018-06-15 13:19 | 2025-03-01 | 2018-06-01 | 2021-02-28
75084 | SG000794F | SG794ETOS | DEE LMR Project 1 Cores | 8015.84 |  | 8015.84 |  |  | 8015.84 | 11229.12 | -3213.28 | 2020-12-17 12:45 | 2024-03-31 | 2021-01-01
75084 | SG000439F | MX9412214 | 20BN-1300 - SWITCHGEAR MANUAL OTHER | 194478.14 |  | 194478.14 |  |  | 197025.05 | 103867.86 | 93157.19 | 2019-12-13 10:01 | 2022-01-28 | 2020-07-01 | 2022-01-11
75084 | SG000439F | MX9412328 | 20BN-1298 - SWITCHGEAR MANUAL OTHER | 104272.02 |  | 104272.02 |  |  | 104272.02 | 75779.98 | 28492.04 | 2019-12-13 10:01 | 2022-01-28 | 2021-08-01 | 2022-01-09
75084 | SG000439F | MX4279797 | SWITCHGEAR AUTO - 20BN-BK-1063 | -1833.23 |  | -1833.23 |  |  | 41677.44 | 123669.03 | -81991.59 | 2019-12-13 10:01 | 2021-01-29 | 2020-09-01 | 2021-01-10
75084 | SG000744F | SG744MTR | DEK GridWAN | 2949.38 |  | 2949.38 |  |  | 14758.37 | 248821.93 | -234063.56 | 2018-05-25 13:28 | 2021-12-31 | 2018-07-01
75084 | SG000744F | SG744BLK | DEK GridWAN | 87807.72 |  | 87807.72 |  |  | 253155.41 | 248821.93 | 4333.48 | 2018-05-25 13:54 | 2031-03-31 | 2018-11-01
75084 | FARCOSSW | ARCOSSW | ARCOS System Outage Project | 7972.95 |  | 7972.95 |  |  | 147899.3 | 129249 | 18650.3 | 2018-06-10 21:10 | 2022-03-31 | 2018-07-01 | 2022-03-31
75084 | FARCOSSW | ARCOS21 | ARCOS Renewal | 29.8 |  | 29.8 |  |  | 118683.42 | 118654 | 29.42 | 2020-12-16 21:41 | 2021-09-30 | 2020-12-01 | 2021-04-25
75084 | TOUTKY | OUT69KY | KY T-line Emergency Repl on 69kV | 82192.37 |  | 82192.37 |  |  | 246334.75 | 6 | 246328.75 | 2017-01-17 10:23 | 2050-12-31 | 2017-01-01
75084 | TOUTKY | TOUTKY01 | Servc rest P1 Due to high winds on | -20835.05 |  | -20835.05 |  |  | 1165927.65 | 18000 | 1147927.65 | 2018-02-09 10:02 | 2021-02-19 | 2018-11-01 | 2021-03-21
75084 | TOUTKY | MX1476595 | F966 X-fer UB for 2 - P1 wood to st | 8073.96 |  | 8073.96 |  |  | 9540 | 2794.53 | 6745.47 | 2019-02-07 10:06 | 2021-07-30 | 2019-12-01 | 2021-06-03
75084 | TOUTKY | MX8024108 | F5967 I-275 crossing failure and re | -2506.14 |  | -2506.14 |  |  | 4.5031e-13 | 0 | 4.5031e-13 | 2020-09-08 18:01 | 2021-03-31 | 2020-09-01 | 2020-12-28
75084 | DKY2198 | MX7724526 | Constance 41 Ln Ext Pt1 - DKY2198 | 2457.66 |  | 2457.66 |  |  | 1671812.6 | 951049.63 | 720762.97 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2018-07-27
75084 | DKY2198 | MX9545158 | Constance Remove Existing OH - DKY2 | 36461.38 |  | 36461.38 |  |  | 226117.12 | 177911.29 | 48205.83 | 2018-08-22 10:02 | 2022-06-29 | 2019-11-01 | 2022-06-16
75084 | SG000432F | SGRUCKY | DEK Cable Replacement | 129080.29 |  | 129080.29 |  |  | 163611.59 | 83 | 163528.59 | 2016-05-16 10:08 | 2025-12-31 | 2017-01-01
75084 | TKY1901 | TKY190101 | Rpl TPU Relays for TB7 | 131990.09 |  | 131990.09 |  |  | 449165.93 | 451134 | -1968.07 | 2018-07-30 10:02 | 2021-06-07 | 2018-07-01 | 2021-07-07
75084 | TKY1901 | MX3850088 | Buffington 41 UGFE Rpl - TKY1901 | 58029.12 |  | 58029.12 |  |  | 155591.39 | 12112.08 | 143479.31 | 2019-08-29 14:01 | 2020-03-30 | 2019-10-01 | 2020-02-11
75084 | TKY1901 | MX3850163 | Buffington 42 UGFE Rpl - TKY1901 | -52204.23 |  | -52204.23 |  |  | 5.7696e-12 | 0 | 5.7696e-12 | 2019-08-29 14:01 | 2022-03-31 | 2019-09-01
75084 | TKY2227 | T2227TL2 | F5967 Decoursey Pole Repl TL | -10478.74 |  | -10478.74 |  |  | 1.5916e-12 | 6725687 | -6725687 | 2018-04-30 14:01 | 2025-10-13 | 2018-09-01
75084 | TKY2227 | T2227TL1 | F5967 Claryville Pole Repl TL | -10314.14 |  | -10314.14 |  |  | -2.5864e-12 | 7186714 | -7186714 | 2018-04-30 14:01 | 2025-11-08 | 2018-09-01
75084 | TKY2227 | TKY222702 | F5967 Hwy 177 Decoursey Sub | -119.33 |  | -119.33 |  |  | -2.7293e-13 | 0 | -2.7293e-13 | 2019-04-29 14:22 | 2025-10-03 | 2019-07-01
75084 | TKY2227 | TKY222701 | F5967 Licking River Crossing Marsh | -209.23 |  | -209.23 |  |  | -3.979e-12 | 0 | -3.979e-12 | 2019-04-29 14:22 | 2025-10-03 | 2019-10-01
75084 | SG000792F | SG792SW | SG DEE Gen Liab Claim Anlytic - 792 | 0.05 |  | 0.05 |  |  | 36289.09 | 22428.18 | 13860.91 | 2018-07-25 14:52 | 2020-03-31 | 2018-07-01 | 2020-02-29
75084 | ICPRJDSTR | ICCONSTRT | Interconnection Capital Project | -517.47 |  | -517.47 |  |  | -8.24 | 1 | -9.24 | 2017-09-28 12:05 | 2030-09-30 | 2017-10-01
75084 | ICPRJDSTR | ICCONSTRD | Interconnection Capital Project | -15745.55 |  | -15745.55 |  |  | -20.29 | 1 | -21.29 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01
75084 | SG000770F | SG770MAS | 2018 MAS Radio | 39305.55 |  | 39305.55 |  |  | 264091.95 | 112986 | 151105.95 | 2018-02-13 17:18 | 2019-03-31 | 2018-02-01
75084 | SG000437F | SGHYDRKY | DEK Recloser Replacements | 229102.06 |  | 229102.06 |  |  | 289242.07 | 83 | 289159.07 | 2016-05-16 10:20 | 2025-12-31 | 2016-10-01
75084 | DEMERKY | MXA085468 | CAPITAL Donaldson replace Phase B T | 1816.19 |  | 1816.19 |  |  | 28435.77 | 21685.42 | 6750.35 | 2020-01-16 18:07 | 2021-03-31 | 2020-08-01 | 2021-02-01
75084 | DEMERKY | MX1264996 | CAPITAL Florence TB2 replace Fan | 965.18 |  | 965.18 |  |  | 965.18 | 5509.56 | -4544.38 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01
75084 | DEMERKY | MX1264572 | CAPITAL Limaburg TB3 replace High S | 4470.81 |  | 4470.81 |  |  | 4470.81 | 6241.33 | -1770.52 | 2021-06-11 18:02 | 2021-09-15 | 2021-07-01 | 2022-02-06
75084 | DEMERKY | MX1265720 | CAPITAL Bellevue TB2 replace Fan | 2159.64 |  | 2159.64 |  |  | 2159.64 | 5537.71 | -3378.07 | 2021-06-11 18:02 | 2022-03-31 | 2021-10-01 | 2022-03-06
75084 | DEMERKY | MX9649956 | CAPITAL Claryville Cir 42 replace L | 4264.63 |  | 4264.63 |  |  | 4264.63 | 10152.45 | -5887.82 | 2021-02-02 14:02 | 2022-03-31 | 2021-02-01 | 2021-08-01
75084 | DEMERKY | MX3926129 | CAPITAL Florence TB4 replace 1 pump | -1224.18 |  | -1224.18 |  |  | 7.2764e-13 | 12973.9 | -12973.9 | 2019-09-05 16:16 | 2021-03-31 | 2020-01-01
75084 | DEMERKY | MX1296858 | CAPITAL Beaver TB1 replace Fuses & | 13514.46 |  | 13514.46 |  |  | 13514.46 | 11201.12 | 2313.34 | 2021-06-14 18:02 | 2022-03-31 | 2021-06-01 | 2022-09-12
75084 | DEMERKY | MX9649988 | CAPITAL Beaver TB1 replace Fan | 1161.61 |  | 1161.61 |  |  | 1161.61 | 10246.29 | -9084.68 | 2021-02-02 14:02 | 2022-03-31 | 2021-03-01 | 2021-08-01
75084 | DEMERKY | MX1593217 | CAPITAL Villa TB 1 replace Radiator | 1914.63 |  | 1914.63 |  |  | 1914.63 | 69980.49 | -68065.86 | 2021-07-14 10:02 | 2022-03-31 | 2021-10-01
75084 | DEMERKY | MX9649979 | CAPITAL Buffington TB7 replace Fan | 1135.5 |  | 1135.5 |  |  | 1135.5 | 10246.29 | -9110.79 | 2021-02-02 14:02 | 2022-03-31 | 2021-03-01 | 2021-08-01
75084 | DEMERKY | MX4946544 | CAPITAL Alexandria South TB1 replac | 1.76 |  | 1.76 |  |  | 2716 | 7569.04 | -4853.04 | 2019-12-04 14:01 | 2022-03-31 | 2020-08-01
75084 | DEMERKY | MX2831125 | CAPITAL White Tower CB 223 replace | 12181.4 |  | 12181.4 |  |  | 12181.4 | 6546.64 | 5634.76 | 2021-11-02 14:02 | 2023-03-31 | 2021-11-01
75084 | DEMERKY | MX1106016 | CAPITAL Florence TB1 replace Fan | 971.11 |  | 971.11 |  |  | 971.11 | 10273 | -9301.89 | 2021-05-28 18:02 | 2022-03-31 | 2021-07-01 | 2021-11-03
75084 | DEMERKY | MX8409811 | CAPITAL Augustine TB1 replace Fan | 4216.14 |  | 4216.14 |  |  | 4216.14 | 10252.58 | -6036.44 | 2020-10-28 18:02 | 2021-09-28 | 2021-03-01 | 2021-08-01
75084 | DEMERKY | MX7213708 | CAPITAL Crescent TB1 replace Fan | 0.37 |  | 0.37 |  |  | 2995.89 | 10299.59 | -7303.7 | 2020-06-22 18:01 | 2021-09-30 | 2020-10-01 | 2021-04-07
75084 | DEMERKY | MX3062206 | CAPITAL Crittenden TB 2 replace 3 H | 479.74 |  | 479.74 |  |  | 479.74 | 10342.05 | -9862.31 | 2021-11-22 10:01 | 2023-02-28 | 2021-11-01
75084 | DEMERKY | MX1266781 | CAPITAL Crescent TB3 replace Fan | 1193.51 |  | 1193.51 |  |  | 1193.51 | 5507.91 | -4314.4 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01 | 2021-11-01
75084 | DEMERKY | MX1267112 | CAPITAL Crescent TB2 replace Fan | 947.3 |  | 947.3 |  |  | 947.3 | 5503.46 | -4556.16 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01 | 2021-11-01
75084 | DEMERKY | MX9642139 | CAPITAL Thomas More TB1 replace Fan | 1238.94 |  | 1238.94 |  |  | 1238.94 | 10260.54 | -9021.6 | 2021-02-02 14:02 | 2022-03-31 | 2021-04-01 | 2021-08-01
75084 | DEMERKY | MX3192862 | CAPITAL White Tower Cir 42 replace | 108.35 |  | 108.35 |  |  | 108.35 | 4853.76 | -4745.41 | 2021-12-13 14:02 | 2023-03-31 | 2021-12-01
75084 | DEMERKY | MX9641894 | CAPITAL Augustine TB5 replace Fan | 1117.03 |  | 1117.03 |  |  | 1117.03 | 1302.47 | -185.44 | 2021-02-02 14:02 | 2022-03-31 | 2021-02-01 | 06/13/2021
75084 | KCTFOOL | KCTOOL | TOOLS BLANKET | 281299.1 |  | 281299.1 |  |  | 578324.26 | 1 | 578323.26 | 2018-07-27 15:23 | 2069-04-01 | 2018-11-01
75084 | DKY2020 | D2020DL1 | TBC AM 20868748 Bellevue 43 Rlbd RU | -856.61 |  | -856.61 |  |  | -6.839e-14 | 0 | -6.839e-14 | 2017-03-07 10:12 | 2021-08-28 | 2017-04-01
75084 | DKY2020 | MX9210067 | Bellevue 43 Reco - Kyles Ln - SOG - | 302498.67 |  | 302498.67 |  |  | 302498.67 | 171956.2 | 130542.47 | 2021-01-04 10:02 | 2022-02-17 | 2021-01-01 | 2022-02-15
75084 | DKY2020 | MX9210584 | Wilder 42 ROW Rem - SOG DKY2020 | 8237.78 |  | 8237.78 |  |  | 8237.78 | 13934.41 | -5696.63 | 2021-01-04 10:02 | 2022-08-04 | 2021-08-01 | 2022-07-27
75084 | KUCF48388 | KUC348388 | TBC UG 10348388 Richwood 43 | -5928.3 |  | -5928.3 |  |  | -5.1159e-13 | 0 | -5.1159e-13 | 2017-04-11 14:03 | 2021-09-30 | 2017-06-01
75084 | KUCF48397 | KUC348397 | RUC 10348397. Cable repla | -36476.23 |  | -36476.23 |  |  | 165424.06 | 99264.17 | 66159.89 | 2017-06-07 18:04 | 2019-03-01 | 2017-10-01 | 2019-01-27
75084 | DKY1931 | D1931DL2 | TBC AM 10895849 General Dr Part 2 | -18443.24 |  | -18443.24 |  |  | -4.3165e-13 | 0 | -4.3165e-13 | 2016-07-29 14:18 | 2021-08-01 | 2017-05-01
75084 | DKY1931 | MX0240701 | Augustine 46 - General Drive OH to | 22717.36 |  | 22717.36 |  |  | 22717.36 | 283263.19 | -260545.83 | 2021-03-16 14:02 | 2023-01-29 | 2021-03-01
75084 | M170111 | M17011101 | Litton Sub Prop Purch | 1690781.68 |  | 1690781.68 |  |  | 1746789.35 | 1873674 | -126884.65 | 2018-08-20 18:03 | 2022-02-05 | 2018-08-01 | 2021-10-09
75084 | M180077 | M18007702 | Aero Substation - New Sub | 41295.7 |  | 41295.7 |  |  | 8076299.81 | 9181543 | -1105243.19 | 2018-11-08 18:02 | 2021-02-27 | 2018-11-01 | 2021-03-16
75084 | M180077 | M18007704 | Oakbrook Substation | 42017.59 |  | 42017.59 |  |  | 5671528.06 | 6995209 | -1323680.94 | 2018-11-08 18:02 | 2021-02-06 | 2018-12-01 | 2021-02-09
75084 | M180077 | M18007705 | 138kV Oakbrook to Aero Line | -19897.2 |  | -19897.2 |  |  | 1606960.38 | 1813508 | -206547.62 | 2018-11-08 18:02 | 2021-02-05 | 2018-12-01 | 2021-02-11
75084 | M180077 | MX8402985 | Oakbrook D-Line Re-Relo - M180077 | 93188.13 |  | 93188.13 |  |  | 93188.13 | 55571.97 | 37616.16 | 2020-10-12 14:01 | 2021-10-29 | 2021-03-01 | 2021-10-10
75084 | DKY2131 | MX5764593 | Kenton 42 - Highway Crossing | 9873.88 |  | 9873.88 |  |  | 14009.9 | 93286.16 | -79276.26 | 2020-05-06 14:01 | 2023-03-31 | 2020-10-01
75084 | DKY2131 | MX0767161 | Decoursey 41 - Sawmill Dr - Relocat | 63991.12 |  | 63991.12 |  |  | 63991.12 | 42490.4 | 21500.72 | 2021-04-30 10:02 | 2021-09-28 | 2021-05-01 | 2021-09-27
75084 | DKY2131 | MX2583979 | Hands 45 UG Cable Install - DKY2131 | 11223.28 |  | 11223.28 |  |  | 132116.38 | 192217.89 | -60101.51 | 2019-06-11 14:01 | 2020-11-26 | 2020-02-01 | 2020-10-28
75084 | DKY2131 | D2131DL2 | AM 21798154 Kenton 42 | -25850.29 |  | -25850.29 |  |  | 192041.45 | 179482.88 | 12558.57 | 2017-07-25 13:46 | 2020-11-26 | 2019-04-01 | 2020-10-07
75084 | DKY2131 | MX0761831 | EMGT - Relocate UG Conduit Sawmill | 111234.61 |  | 111234.61 |  |  | 111234.61 | 14250.84 | 96983.77 | 2021-05-05 10:02 | 2021-08-26 | 2021-05-01 | 2021-08-22
75084 | TKY2188 | T2188DS1 | Augustine_Instl 22_4MVA XTR - TKY2 | 44.27 |  | 44.27 |  |  | 3222789.16 | 2593925.42 | 628863.74 | 2017-07-06 13:26 | 2019-02-15 | 2017-07-01 | 2019-01-27
75084 | SG00359F | SG359SW | SG SADM Software - 359 | -32451.09 |  | -32451.09 |  |  | -1.6769e-12 | 227863.84 | -227863.84 | 2018-09-27 06:52 | 2022-12-01 | 2018-09-01
75084 | SG00359F | SG359SW2 | SG SADM Software - 359 | -63870.9 |  | -63870.9 |  |  | 4.92 | 227863.84 | -227858.92 | 2019-08-15 08:00 | 2022-12-01 | 2019-09-01
75084 | DKY2132 | DKY213201 | Longbranch EKPC 138kV Loop TS | 554835.57 |  | 554835.57 |  |  | 1220173.32 | 1583233.98 | -363060.66 | 2018-06-21 10:05 | 2021-07-05 | 2018-09-01 | 2021-08-04
75084 | DKY2132 | DKY213202 | Longbranch Inst XFMR 2 DS | 1805418.21 |  | 1805418.21 |  |  | 3661943.51 | 3128772.08 | 533171.43 | 2018-06-21 10:05 | 2021-08-09 | 2019-02-01 | 2021-09-08
75084 | DKY2132 | DKY213203 | Longbranch EKPC CIR 6785 TL | 109452.5 |  | 109452.5 |  |  | 119910.81 | 127025.26 | -7114.45 | 2018-06-21 10:05 | 2021-09-07 | 2019-05-01 | 2021-08-04
75084 | DKY2132 | MX8763054 | Longbranch 43-44 UG - DKY2132 | 506513.71 |  | 506513.71 |  |  | 574117.62 | 71912.58 | 502205.04 | 2018-07-05 10:02 | 2023-03-31 | 2020-06-01
75084 | DKY2132 | MX8762998 | Longbranch 44 Part 1 - DKY2132 | 95621.47 |  | 95621.47 |  |  | 131943.41 | 93589.52 | 38353.89 | 2018-12-07 10:01 | 2022-06-29 | 2020-06-01 | 2022-05-30
75084 | DKY2132 | MX9015414 | Longbranch 44 Part 2 - DKY2132 | 62005.57 |  | 62005.57 |  |  | 205054.21 | 527718.36 | -322664.15 | 2018-12-07 10:01 | 2022-11-29 | 2020-06-01 | 2022-12-18
75084 | DKY2132 | MX8762834 | Longbranch 43 - DKY2132 | 6345.26 |  | 6345.26 |  |  | 33094.57 | 8841.68 | 24252.89 | 2018-07-05 10:02 | 2021-01-29 | 2020-06-01 | 2020-12-30
75084 | MWAVEKYEL | NINT2156B | Cisco Data Network | -1865.39 |  | -1865.39 |  |  | 7598.09 | 10183 | -2584.91 | 2017-02-20 07:17 | 2018-03-31 | 2017-07-01 | 2018-03-06
75084 | TEMERKY | MX9650032 | CAPITAL Villa CB 635 replace 2 Bush | 511.68 |  | 511.68 |  |  | 511.68 | 16215.11 | -15703.43 | 2021-02-02 14:02 | 2022-03-31 | 2021-06-01 | 2021-09-15
75084 | TEMERKY | MX1264145 | CAPITAL Cir 965 replace Phase C LA | 618.59 |  | 618.59 |  |  | 618.59 | 5235.15 | -4616.56 | 2021-06-11 18:02 | 2022-03-31 | 2021-06-01
75084 | TEMERKY | MX1266171 | CAPITAL Silver Grove TB23 replace F | 880.12 |  | 880.12 |  |  | 880.12 | 0 | 880.12 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01
75084 | TEMERKY | MX9649928 | CAPITAL Buffington TB3 replace ETM | 5666.7 |  | 5666.7 |  |  | 5666.7 | 9873.3 | -4206.6 | 2021-02-02 14:02 | 2022-03-31 | 2021-02-01
75084 | KETF35851 | KET135851 | DET 10135851 West End 41 | -48232.36 |  | -48232.36 |  |  | 1741079.03 | 414893.11 | 1326185.92 | 2016-05-02 14:04 | 2019-06-14 | 2016-05-01 | 2019-05-25
75084 | 75084 | KMTROWS | KY - Meters-AMI-Self Contained | 903046.66 |  | 903046.66 |  |  | 1557574.86 | 99863.96 | 1457710.9 | 2018-11-02 18:04 | 2026-03-31 | 2018-12-01
75084 | 75084 | EMETERKY | Electric Meter Blanket | -276196.22 |  | -276196.22 |  |  | 2724536.1 | 295697.19 | 2428838.91 | 2015-03-09 09:46 | 2025-12-31 | 2015-04-01 | 2019-05-14
75084 | 75084 | KMTROWT | KY - Meters-AMI-T Rated | 317269.81 |  | 317269.81 |  |  | 802892.98 | 11182.68 | 791710.3 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | 75084 | KMTRNOT | KY - Meters-Not AMI- T Rated | 86908.27 |  | 86908.27 |  |  | 219259.2 | 520.12 | 218739.08 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | 75084 | KMTRNOS | KY Meters-Not AMI-SelfContained | 45497.85 |  | 45497.85 |  |  | 80987.46 | 5461.31 | 75526.15 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01
75084 | M180095 | M18009501 | Kenton XTR 1 Rpl | 100.43 |  | 100.43 |  |  | 154873.25 | 2336966 | -2182092.75 | 2019-03-07 10:01 | 2023-12-29 | 2019-03-01
75084 | M200255 | M20025501 | Emgt - Decoursey Retire MTU | -25.07 |  | -25.07 |  |  | -8.3673e-13 | 0 | -8.3673e-13 | 2020-10-01 14:01 | 2021-02-20 | 2020-10-01 | 2021-03-30
75084 | SG000764F | SG764BLK1 | DEK 2019-2020 Microwave Upgrades | 434572.79 |  | 434572.79 |  |  | 1458584.98 | 217462.26 | 1241122.72 | 2019-02-25 09:15 | 2028-03-31 | 2019-04-01
75084 | SG000764F | SG764MAT1 | DEK 2019-2020 Microwave Upgrades | 192484.88 |  | 192484.88 |  |  | 444919.76 | 217462.26 | 227457.5 | 2019-02-25 08:41 | 2028-03-31 | 2019-10-01
75084 | TKY1999 | TKY199903 | Constance Bus 1 Swgr CB Rpl | -8992.89 |  | -8992.89 |  |  | 85012.53 | 2390612 | -2305599.47 | 2018-07-06 10:02 | 2024-06-21 | 2019-02-01
75084 | DKY2125 | DKY212501 | New 69kV V structure | 651943.31 |  | 651943.31 |  |  | 790421.36 | 904914.56 | -114493.2 | 2019-02-22 10:01 | 2022-02-15 | 2019-03-01 | 2022-03-16
75084 | DKY2125 | DKY212502 | Grant Metering | 808818.55 |  | 808818.55 |  |  | 918327.93 | 918433 | -105.07 | 2019-02-22 10:01 | 2021-10-08 | 2019-08-01 | 2021-07-07
75084 | DKY2125 | MX6297880 | Dry Ridge Pole Repl UB - DKY2125 | 85147.1 |  | 85147.1 |  |  | 85187.36 | 64542.37 | 20644.99 | 2020-04-03 14:01 | 2021-10-19 | 2020-12-01 | 2021-10-13
75084 | DKY2125 | DKY212503 | Dry Ridge BK 2 | 832131.69 |  | 832131.69 |  |  | 1204016.76 | 1629020 | -425003.24 | 2019-02-22 10:01 | 2022-02-15 | 2019-04-01 | 2022-03-16
75084 | DKY2125 | DKY212504 | Dry Ridge F3568 Loop TL | 273975.96 |  | 273975.96 |  |  | 314326.95 | 166179.8 | 148147.15 | 2019-02-22 10:01 | 2022-02-15 | 2019-06-01 | 2022-03-16
75084 | DKY2125 | MX9769240 | Dry Ridge Sub Expansion - Fall 2021 | 6986.66 |  | 6986.66 |  |  | 6986.66 | 2060.15 | 4926.51 | 2021-03-08 10:03 | 2022-02-07 | 2021-04-01 | 2022-02-02
75084 | SG990124F | SGRXRKY | SG - Transformer Retrofit DMWKY | 29141.34 |  | 29141.34 |  |  | 32431.92 | 1 | 32430.92 | 2017-04-06 08:06 | 2050-12-31 | 2019-02-01
75084 | DKYHW2672 | MX3147286 | TBC Hebron 43 45 UG Cable - DKYHW26 | -178.72 |  | -178.72 |  |  | -2.5091e-14 | 1796.56 | -1796.56 | 2019-06-26 14:01 | 2021-07-01 | 2019-08-01
75084 | DKYHW2672 | MX3147011 | Hebron OH Work - DKYHW2672 | -35257.8 |  | -35257.8 |  |  | -27290.41 | 227039.51 | -254329.92 | 2019-06-26 14:01 | 2021-12-29 | 2019-08-01 | 2021-11-21
75084 | DKYHW2672 | MX3147246 | Hebron 41 42 UG Cable - DKYHW2672 | 5730.47 |  | 5730.47 |  |  | 5726.74 | 464106.03 | -458379.29 | 2019-06-26 14:01 | 2020-09-29 | 2019-08-01 | 2020-10-07
75084 | M190226 | MX7488872 | D-Const Reco Woodspoint-Aero - M190 | 6774.13 |  | 6774.13 |  |  | 11901.8 | 184107.64 | -172205.84 | 2020-07-20 10:01 | 2023-06-29 | 2020-09-01
75084 | M190226 | M19022601 | 138 kV F23983 Woodspoint to Aero | 5553039.37 |  | 5553039.37 |  |  | 9163459.82 | 5133016 | 4030443.82 | 2019-10-08 14:01 | 2023-03-04 | 2019-11-01
75084 | M190226 | M19022602 | F23983 T Line RLE | 1920071.52 |  | 1920071.52 |  |  | 6586320.4 | 7486323 | -900002.6 | 2019-10-08 14:01 | 2023-01-06 | 2020-01-01
75084 | M190226 | MX7488796 | Woodspoint UB Rebuild - M190226 | 95882.45 |  | 95882.45 |  |  | 126721.2 | 35997.9 | 90723.3 | 2020-07-20 10:01 | 2021-09-28 | 2020-09-01 | 2021-08-08
75084 | M190226 | MX7488839 | D-Const UG Transfers - M190226 | 3041.75 |  | 3041.75 |  |  | 3108.11 | 5697.77 | -2589.66 | 2020-07-20 10:01 | 2023-06-29 | 2020-09-01
75084 | M200191 | M20019101 | EMR - Hands Remov MTU & Inst SPCC | 2019.72 |  | 2019.72 |  |  | 37776.28 | 40455 | -2678.72 | 2020-05-29 10:01 | 2021-12-04 | 2020-07-01 | 2021-04-04
75084 | M190297 | M19029701 | 5967 Rbld Claryville to HL 864 | -34518.18 |  | -34518.18 |  |  | 328380.02 | 6743234 | -6414853.98 | 2020-11-11 14:01 | 2023-07-18 | 2020-11-01
75084 | M190297 | M19029702 | F5967 Line RLE | 251.03 |  | 251.03 |  |  | 251.03 | 307328 | -307076.97 | 2020-11-11 14:01 | 2022-12-31 | 2021-03-01
75084 | SG000564F | SG564LC&I | DEK Large CI Follow On Project | 71284.39 |  | 71284.39 |  |  | 74452.44 | 121743 | -47290.56 | 2020-10-09 17:10 | 2021-10-31 | 2020-11-01 | 2021-12-01
75084 | DKY2447 | MX1424546 | Constance 43 LN Ext DKY2447 | 352550.65 |  | 352550.65 |  |  | 1572727.02 | 1616077.2 | -43350.18 | 2019-06-17 18:02 | 2021-10-18 | 2019-09-01 | 2021-10-17
75084 | SG000723F | SG723SW | DEE AMI Operations Tool | 23248.03 |  | 23248.03 |  |  | 41366.05 | 38014 | 3352.05 | 2020-01-15 11:35 | 2022-07-30 | 2020-04-01 | 2022-07-31
75084 | SG000493F | SG943MAIF | Advanced Reliability Metrics | 23054.39 |  | 23054.39 |  |  | 27454.03 | 50359 | -22904.97 | 2020-06-29 17:04 | 2022-03-31 | 2020-07-01 | 2022-01-15
75084 | SG000842F | SG842RCR | DEK Reclosure Control Replacement | 49124.45 |  | 49124.45 |  |  | 758848.41 | 1062774 | -303925.59 | 2018-10-16 17:02 | 2024-03-31 | 2019-03-01
75084 | M180378 | M18037801 | Richwood BK 4- Install | 38985.81 |  | 38985.81 |  |  | 347764.55 | 2360214.13 | -2012449.58 | 2019-09-12 14:01 | 2023-07-21 | 2019-10-01
75084 | M180378 | M18037802 | Richwood BK 4- Mod Xmission Structu | 7052.34 |  | 7052.34 |  |  | 122945.28 | 523888.35 | -400943.07 | 2019-09-16 18:01 | 2023-08-04 | 2019-10-01
75084 | M180378 | M18037803 | F6761 Loop | 3.1 |  | 3.1 |  |  | 2988.23 | 0 | 2988.23 | 2019-09-12 14:01 | 2023-07-10 | 2020-06-01
75084 | TOT00003 | WEBFG | WebFG Replacement | 6625.29 |  | 6625.29 |  |  | 21777.17 | 79688 | -57910.83 | 2019-10-18 07:58 | 2022-03-31 | 2019-10-01 | 2022-04-14
75084 | M190087 | MX6297484 | T-Emergent F6763 (T-DPN M19008701) | 29143.68 |  | 29143.68 |  |  | 58209.96 | 31313.21 | 26896.75 | 2020-04-07 14:01 | 2021-09-28 | 2020-05-01 | 2021-08-30
75084 | SG000983F | SG983TMT2 | SG DEE TMT Phase II | 8338.72 |  | 8338.72 |  |  | 29510.95 | 44390.63 | -14879.68 | 2019-08-14 14:04 | 2021-11-02 | 2019-09-01 | 2022-01-01
75084 | M180604 | M18060412 | Kentucky University Install SPCC pe | 5889.8 |  | 5889.8 |  |  | 89774.15 | 101095 | -11320.85 | 2020-03-04 14:01 | 2021-02-12 | 2020-03-01 | 2021-02-18
75084 | M180604 | M18060410 | Florence Install SPCC per oil conta | 1546.08 |  | 1546.08 |  |  | 70542.2 | 80275 | -9732.8 | 2020-03-04 14:01 | 2021-02-07 | 2020-03-01 | 2021-01-25
75084 | M180604 | M18060403 | Bellevue Install SPCC per oil conta | 22862.79 |  | 22862.79 |  |  | 101403.3 | 77953 | 23450.3 | 2020-03-04 14:01 | 2021-02-09 | 2020-03-01 | 2021-03-30
75084 | M180604 | M18060405 | Cold Spring Install SPCC per oil co | 1304.31 |  | 1304.31 |  |  | 107721.73 | 112751 | -5029.27 | 2020-03-04 14:01 | 2021-01-16 | 2020-03-01 | 2021-01-28
75084 | M180604 | M18060404 | Blackwell Install SPCC per oil cont | 5441.75 |  | 5441.75 |  |  | 25312.51 | 23068 | 2244.51 | 2020-03-04 14:01 | 2021-02-16 | 2020-05-01 | 2021-03-30
75084 | M180604 | M18060411 | Hebron Install SPCC per oil contain | 3498.94 |  | 3498.94 |  |  | 117055.31 | 114896 | 2159.31 | 2020-03-04 14:01 | 2021-01-31 | 2020-03-01 | 2021-01-13
75084 | M180604 | M18060408 | Dry Ridge Install SPCC per oil cont | -566.16 |  | -566.16 |  |  | 35823.08 | 50943 | -15119.92 | 2020-03-04 14:01 | 2021-02-02 | 2020-03-01 | 2021-03-30
75084 | M190153 | M19015301 | GLT F6763 Rpl - Limaburg to Oakbroo | 10899.6 |  | 10899.6 |  |  | 657222.06 | 647545.95 | 9676.11 | 2019-10-03 14:14 | 2021-01-05 | 2019-10-01 | 2020-10-08
75084 | M190153 | MX5967380 | GLT TRANS UB F6763 (M19015301) | 4563.54 |  | 4563.54 |  |  | 48789.8 | 43758.15 | 5031.65 | 2020-06-02 14:01 | 2020-12-29 | 2020-06-01 | 2020-12-28
75084 | M190153 | M19015302 | GLT F6763 Rpl Oakbrook to Swi#406 | 19006.96 |  | 19006.96 |  |  | 2517359.27 | 2661488.14 | -144128.87 | 2019-10-04 10:01 | 2021-02-06 | 2019-11-01 | 2020-10-08
75084 | M190153 | M19015304 | GLT F6763 Rpl - Empire to Dixie | 328754.96 |  | 328754.96 |  |  | 387163.93 | 307070 | 80093.93 | 2019-10-04 10:01 | 2021-05-14 | 2019-11-01 | 2021-06-06
75084 | M190153 | M19015303 | GLT F6763 Rpl - Swi #406 to Empire | 704971.35 |  | 704971.35 |  |  | 744460.96 | 714261 | 30199.96 | 2019-10-04 10:01 | 2021-05-21 | 2019-10-01 | 2021-05-25
75084 | M190153 | MX6488060 | Transfer D-Line UB on F6763 GLT F67 | 105810.59 |  | 105810.59 |  |  | 107474.93 | 12313.06 | 95161.87 | 2020-04-22 14:01 | 2021-11-29 | 2020-08-01 | 2021-12-14
75084 | M190153 | MX6012113 | T-GLT F6763 (T-DPN M19015302) Trans | 148334.35 |  | 148334.35 |  |  | 231761.35 | 95593.85 | 136167.5 | 2020-03-04 14:01 | 2022-02-13 | 2020-05-01 | 2022-03-14
75084 | M190153 | M19015305 | GLT F6761 Rpl - Swi #387 to Buffing | 92567.16 |  | 92567.16 |  |  | 504947.71 | 687406 | -182458.29 | 2019-10-04 10:01 | 2021-01-15 | 2019-10-01 | 2021-02-06
75084 | M190153 | MX6489239 | Transfer D-Line UB on F6763 GLT F67 | 23398.85 |  | 23398.85 |  |  | 25151.82 | 21388.36 | 3763.46 | 2020-04-22 14:01 | 2021-08-05 | 2020-08-01 | 2021-07-19
75084 | M190153 | M19015306 | GLT F6763 Rpl - Swi#387 to Buffingt | -38361.48 |  | -38361.48 |  |  | 721434.59 | 501611.81 | 219822.78 | 2019-10-04 10:01 | 2021-02-07 | 2019-11-01 | 2021-02-04
75084 | M190153 | MX6489978 | Transfer D-Line UB on F6763 GLT F67 | 32175.59 |  | 32175.59 |  |  | 49203.7 | 48959.54 | 244.16 | 2020-04-22 14:01 | 2021-05-01 | 2020-08-01 | 2021-03-14
75084 | M190153 | MX6014189 | Transfer D-Line UB on F6763 GLT F67 | 8536.29 |  | 8536.29 |  |  | 29152.19 | 18427.27 | 10724.92 | 2020-03-04 18:01 | 2021-03-31 | 2020-04-01 | 2021-03-14
75084 | DKY2637 | MX1425791 | TBC Limaburg 41 & 43 Reco CVG DKY26 | -5934.36 |  | -5934.36 |  |  | -8.8818e-13 | 0 | -8.8818e-13 | 2019-10-02 14:01 | 2023-12-27 | 2019-11-01
75084 | M210374 | M21037401 | Limaburg-Oakbrook RLE | 2104.87 |  | 2104.87 |  |  | 2104.87 | 160173 | -158068.13 | 2021-08-04 14:03 | 2024-03-10 | 2021-08-01
75084 | M210374 | M21037402 | Hebron-Route 237 RLE | 21530.49 |  | 21530.49 |  |  | 21530.49 | 2253809 | -2232278.51 | 2021-08-04 14:03 | 2024-03-10 | 2021-08-01
75084 | DKY2618 | MX5358828 | Permanent Primary Service - DKY2618 | 1270959.79 |  | 1270959.79 |  |  | 1515147.52 | 326336.3 | 1188811.22 | 2020-01-16 10:01 | 2023-03-31 | 2020-10-01
75084 | DKY2618 | MX3629351 | Areo Sub Exits - DKY2618 | 24597.49 |  | 24597.49 |  |  | 346198.17 | 164617.64 | 181580.53 | 2019-09-23 18:01 | 2021-03-31 | 2019-10-01 | 2020-12-29
75084 | DKY2618 | MX0541691 | Primary Service 2 - Amazon - DKY261 | -57133.8 |  | -57133.8 |  |  | -57133.8 | 42750.1 | -99883.9 | 2021-05-18 14:02 | 2021-12-29 | 2021-05-01 | 2021-12-14
75084 | DKY2618 | MX5358777 | Amazon Dist Conduits - DKY2618 | -533.71 |  | -533.71 |  |  | 426763.47 | 574515.35 | -147751.88 | 2020-01-16 10:01 | 2020-11-29 | 2020-04-01 | 2020-11-17
75084 | DKY2618 | MX9992812 | Primary Service 2 - Amazon - DKY261 | 265599.1 |  | 265599.1 |  |  | 265599.1 | 156473.13 | 109125.97 | 2021-02-25 14:02 | 2022-11-29 | 2021-03-01
75084 | M190194 | M19019401 | Turfway Sub | 2395.81 |  | 2395.81 |  |  | 3424.02 | 0 | 3424.02 | 2020-12-08 14:19 | 2028-06-19 | 2020-12-01
75084 | SG000838F | SG838BTR | DEK EOL Power Supplies | 81797.69 |  | 81797.69 |  |  | 158574.65 | 81484 | 77090.65 | 2019-01-22 08:29 | 2022-03-31 | 2019-04-01
75084 | SG001017F | SG1017SW | DEE FND Hardening | -406.42 |  | -406.42 |  |  | -1.1147e-13 | 3132 | -3132 | 2020-07-29 11:51 | 2020-12-30 | 2020-08-01 | 2021-02-28
75084 | SG001041F | SG1041SW | DEE ADP SOG Automation Tool | 27368.55 |  | 27368.55 |  |  | 34621.03 | 32007.13 | 2613.9 | 2020-06-08 08:52 | 2021-12-31 | 2020-06-01 | 2022-03-31
75084 | M200039 | M20003903 | NKU Cambium Radio Upgrade | 367.42 |  | 367.42 |  |  | 112691.76 | 117150 | -4458.24 | 2020-03-23 18:01 | 2020-12-08 | 2020-03-01 | 2021-01-01
75084 | M200039 | M20003904 | Hebron Cambium Radio Upgrade | 88056.51 |  | 88056.51 |  |  | 123399.47 | 120284 | 3115.47 | 2020-03-23 18:01 | 2021-08-30 | 2020-03-01 | 2021-07-08
75084 | M200039 | M20003901 | Atlas Cambium Radio Upgrade | 114365.96 |  | 114365.96 |  |  | 119323.57 | 232638 | -113314.43 | 2020-03-23 18:01 | 2022-01-29 | 2020-03-01 | 2022-03-03
75084 | M200039 | M20003905 | Dry Ridge Cambium Radio Upgrade | 117528.11 |  | 117528.11 |  |  | 128035.88 | 193637 | -65601.12 | 2020-03-23 18:01 | 2022-06-27 | 2020-03-01 | 2022-03-03
75084 | M200039 | M20003902 | Florence Cambium Radio Upgrade | 86754.34 |  | 86754.34 |  |  | 123574.94 | 109147 | 14427.94 | 2020-03-23 18:01 | 2021-07-10 | 2020-03-01 | 2021-07-26
75084 | DKY2135 | DKY213502 | Taylor Mill Sub Install | 20768.24 |  | 20768.24 |  |  | 20768.24 | 6087134 | -6066365.76 | 2021-06-04 14:02 | 2025-01-18 | 2021-06-01
75084 | DKY2135 | DKY213501 | Taylor Mill Sub 69kV Take Off | 2572.96 |  | 2572.96 |  |  | 2572.96 | 1245722 | -1243149.04 | 2021-06-04 14:02 | 2025-01-18 | 2021-06-01
75084 | DKY2135 | DKY213504 | Bldg Demo | 1.36 |  | 1.36 |  |  | 1.36 | 0 | 1.36 | 2021-06-08 10:18 | 2022-03-01 | 2021-10-01 | 2022-03-27
75084 | DKY2135 | DKY213503 | F5967 Loop Thru Taylor Mill | 1292.52 |  | 1292.52 |  |  | 1292.52 | 1507486 | -1506193.48 | 2021-06-04 14:02 | 2025-01-26 | 2021-07-01
75084 | SG990022F | MX4546275 | 2021 PROACTIVE RECL RPL, KNK-5759, | 63283.95 |  | 63283.95 |  |  | 63283.95 | 40247.01 | 23036.94 | 2021-03-25 10:02 | 2022-12-29 | 2021-04-01 | 2022-11-28
75084 | SG990022F | SRRRKY | SG - Reclosure Replacements DMWKY | 496844.63 |  | 496844.63 |  |  | 539909.28 | 1 | 539908.28 | 2017-04-04 13:14 | 2050-12-31 | 2019-03-01
75084 | SG990022F | MX4546269 | 2021 PROACTIVE RECL RPL, KNK-3706, | 48587.98 |  | 48587.98 |  |  | 48587.98 | 42599.42 | 5988.56 | 2021-01-21 10:26 | 2021-09-28 | 2021-02-01 | 2021-09-06
75084 | SG990022F | MX1525938 | SG-RECLOSERREPLACEMENT AS A PROGRAM | 40871.85 |  | 40871.85 |  |  | 43344.54 | 40804.39 | 2540.15 | 2020-02-24 14:01 | 2021-07-29 | 2020-04-01 | 2021-06-29
75084 | SG000685F | SG685TUGK | DEK TUG Easement/ROW Blanket | 1481.09 |  | 1481.09 |  |  | 135942.62 | 400000 | -264057.38 | 2019-10-22 11:24 | 2026-03-31 | 2020-01-01
75084 | M180388 | M18038801 | Aero Dist Substation | -1035259.21 |  | -1035259.21 |  |  | 9113735.11 | 6981494 | 2132241.11 | 2019-03-27 14:01 | 2021-03-01 | 2019-04-01 | 2021-03-16
75084 | M200327 | M20032701 | Emgt - Grant Retire MTUs | -24732.3 |  | -24732.3 |  |  | 491.43 | 0 | 491.43 | 2020-12-08 18:02 | 2021-05-28 | 2020-12-01 | 2021-06-12
75084 | SG000949F | SG949MTLD | DEE Maintain Load & Generation | 14560.46 |  | 14560.46 |  |  | 23272.34 | 13378 | 9894.34 | 2020-08-17 12:31 | 2022-04-30 | 2020-08-01 | 2022-03-15
75084 | M190233 | MX4865782 | F5983 Lafarge to Silver Grove X-fer | 40308.07 |  | 40308.07 |  |  | 40724.24 | 25682.58 | 15041.66 | 2019-11-26 14:01 | 2022-03-31 | 2020-09-01 | 2022-03-01
75084 | M190233 | MX4864988 | F5983 Dayton to Lafarge X-fer UB fo | 129416.04 |  | 129416.04 |  |  | 129844.44 | 222076.86 | -92232.42 | 2019-11-26 18:01 | 2023-01-29 | 2020-12-01 | 2022-11-09
75084 | TOT00002 | MWEMSKY2 | DEK EMS Replacement Project | 304438.21 |  | 304438.21 |  |  | 308537.09 | 1646591 | -1338053.91 | 2020-12-17 11:46 | 2024-12-31 | 2020-12-01
75084 | TOT00002 | MWEMSKY | Midwest EMS Replacement Project | -426233.78 |  | -426233.78 |  |  | 0 | 679701.48 | -679701.48 | 2019-07-22 08:59 | 2023-03-30 | 2019-09-01
75084 | SG000724F | SG724SW | DEE MDM Technical Health | 4939.4 |  | 4939.4 |  |  | 17073.08 | 22747 | -5673.92 | 2020-08-19 16:40 | 2021-06-24 | 2020-08-01 | 2021-09-30
75084 | SG001006F | SG1006SW | DEK FISR Pre-Scale - Software | 29051.9 |  | 29051.9 |  |  | 318429.87 | 384800 | -66370.13 | 2019-10-22 10:44 | 2022-03-31 | 2019-10-01 | 2022-02-09
75084 | M200330 | M20033001 | GLT F5966 Rpl Poles, Insp Year 2019 | -130096.89 |  | -130096.89 |  |  | 194994.6 | 192628.03 | 2366.57 | 2020-10-01 14:01 | 2021-02-12 | 2020-10-01 | 2021-03-15
75084 | M200290 | M20029001 | F5983 KY SD1 Relocation | 17715.01 |  | 17715.01 |  |  | 28036.19 | 90543 | -62506.81 | 2020-09-15 14:01 | 2021-11-08 | 2020-09-01 | 2021-12-06
75084 | SG990033F | SPOLIRKY | SG-Emergy Pole Replace Insp DMWKY | 10597.73 |  | 10597.73 |  |  | 228957.2 | 1 | 228956.2 | 2017-04-03 15:44 | 2050-12-31 | 2019-10-01
75084 | M200038 | M20003801 | F6763 KYTC Relocation Mt Zion Road. | 624984.62 |  | 624984.62 |  |  | 665787.98 | 517592.97 | 148195.01 | 2020-04-15 18:01 | 2021-08-21 | 2020-04-01 | 2021-09-02
75084 | M200056 | M20005602 | GLT 5967 Rpl Poles ABS 436 White T | -11134.36 |  | -11134.36 |  |  | 865.64 | 0 | 865.64 | 2020-12-21 18:01 | 2024-02-25 | 2020-12-01
75084 | M200056 | M20005601 | GLT 5967 Rpl Poles Wilder Sub ABS | 40916.64 |  | 40916.64 |  |  | 78067.24 | 480208 | -402140.76 | 2020-12-21 18:01 | 2024-01-26 | 2020-12-01
75084 | M200056 | M20005603 | GLT 5967 Rpl Poles White Tower Sub | -7300.87 |  | -7300.87 |  |  | 4699.13 | 0 | 4699.13 | 2020-12-21 18:01 | 2024-02-18 | 2020-12-01
75084 | M200056 | M20005604 | GLT 5967 Rpl Poles, Insp Year 2016 | 889.91 |  | 889.91 |  |  | 889.91 | 114396 | -113506.09 | 2020-12-21 18:01 | 2023-12-10 | 2021-02-01
75084 | SG001081F | SG1081SW | DEK SCADA DMS Upgrade | 1144219.17 |  | 1144219.17 |  |  | 1144219.17 | 1215071 | -70851.83 | 2021-05-14 14:27 | 2022-04-30 | 2021-05-01 | 2022-05-20
75084 | M190167 | M19016706 | Villa 2019 DMVPN Upgrade 2 | 0.69 |  | 0.69 |  |  | 303.61 | 85275 | -84971.39 | 2020-01-28 10:01 | 2027-02-08 | 2020-01-01
75084 | DKY2210 | D2210DL1 | AM 21520192 Donaldson 45 | -12375.62 |  | -12375.62 |  |  | 1188025.91 | 503139.5 | 684886.41 | 2017-06-15 14:35 | 2020-08-15 | 2019-05-01 | 2020-08-12
75084 | DKY2210 | MX0043268 | Donaldson 45 - Follow up work for f | 23112.53 |  | 23112.53 |  |  | 23112.53 | 7418.92 | 15693.61 | 2021-03-03 10:02 | 2021-08-19 | 2021-03-01 | 2021-07-21
75084 | DKY2210 | MX4121529 | Donaldson 43 Reco SOG - DKY2210 | 1385.27 |  | 1385.27 |  |  | 196791.53 | 101138.5 | 95653.03 | 2019-09-23 14:01 | 2021-03-31 | 2019-12-01 | 2021-03-15
75084 | M190259 | MX4517175 | F6782 X-fer UB for 8 wood to steel | 59150.28 |  | 59150.28 |  |  | 60903.46 | 88243.07 | -27339.61 | 2019-11-26 18:01 | 2022-10-13 | 2020-07-01 | 2022-10-16
75084 | M190259 | MX4420788 | GLT F6782 Florence to Donaldson (M1 | 55571.98 |  | 55571.98 |  |  | 99950.1 | 50005.65 | 49944.45 | 2020-02-28 14:01 | 2021-09-28 | 2020-08-01 | 2021-08-25
75084 | M210251 | M21025101 | Grant Cambium Radio | 18505.19 |  | 18505.19 |  |  | 18505.19 | 128087 | -109581.81 | 2021-07-20 18:02 | 2023-02-07 | 2021-07-01 | 2023-01-19
75084 | M200381 | M20038101 | EMR - Buffington TB 45 ETM | 36468.31 |  | 36468.31 |  |  | 36468.31 | 71511 | -35042.69 | 2021-01-19 18:02 | 2021-11-09 | 2021-03-01 | 2021-12-15
75084 | M200335 | M20033501 | Hands Rpl ABS 837 and ABS 839 | 510866.51 |  | 510866.51 |  |  | 510866.51 | 455488.1 | 55378.41 | 2021-02-03 14:01 | 2022-03-22 | 2021-02-01 | 2022-03-17
75084 | M200148 | M20014801 | F6761 Mt Zion Road Relocation | 848883.15 |  | 848883.15 |  |  | 887139.59 | 844710.61 | 42428.98 | 2020-05-19 10:24 | 2021-08-13 | 2020-05-01 | 2021-09-02
75084 | 23040042A | MX0319573 | SUB OPT -UPGRADE OF CAPACITORS BY A | 1462.57 |  | 1462.57 |  |  | 1462.57 | 23077.95 | -21615.38 | 2021-08-06 14:02 | 2024-03-30 | 2021-08-01
75084 | M210280 | M21028001 | EMERGENT - HANDS SUBSTATION REPLACE | 13778.45 |  | 13778.45 |  |  | 13778.45 | 105658 | -91879.55 | 2021-05-12 18:02 | 2022-06-17 | 2021-06-01 | 2022-07-15
75084 | 20670045A | MX9919641 | SUB OPT -UPGRADE OF CAPACITORS BY A | 709.27 |  | 709.27 |  |  | 709.27 | 16146.47 | -15437.2 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20670045A | MX1701464 | 0670045A: Buffington 45 K117-660 RE | 33.31 |  | 33.31 |  |  | 33.31 | 0 | 33.31 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01
75084 | 20670045A | MX1701461 | 0670045A: Buffington 45 K116-472 IN | 1122.2 |  | 1122.2 |  |  | 1122.2 | 44901.57 | -43779.37 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX9919640 | SUB OPT -UPGRADE OF CAPACITORS BY A | 866.73 |  | 866.73 |  |  | 866.73 | 16598.73 | -15732 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20670045A | MX9919639 | SUB OPT -UPGRADE OF CAPACITORS BY A | 1438.82 |  | 1438.82 |  |  | 1438.82 | 21366.89 | -19928.07 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20670045A | MX1701463 | 0670045A: Buffington 45 K117-114 IN | 1541.59 |  | 1541.59 |  |  | 1541.59 | 44985.64 | -43444.05 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1393380 | 0670045A: Buffington 45 K106-490 IN | 1425.76 |  | 1425.76 |  |  | 1425.76 | 45129.26 | -43703.5 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701462 | 0670045A: Buffington 45 K117-112 IN | 2006.57 |  | 2006.57 |  |  | 2006.57 | 44552.1 | -42545.53 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1393381 | 0670045A: Buffington 45 K117-177 IN | 1678.69 |  | 1678.69 |  |  | 1678.69 | 43388.09 | -41709.4 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701457 | 0670045A: Buffington 45 BNK-5624 RE | 22.72 |  | 22.72 |  |  | 22.72 | 0 | 22.72 | 2021-10-21 10:02 | 2023-02-02 | 2021-12-01
75084 | 20670045A | MX1701456 | 0670045A: Buffington 45 BNK-5621 RE | 22.72 |  | 22.72 |  |  | 22.72 | 0 | 22.72 | 2021-10-21 10:02 | 2023-02-02 | 2021-12-01
75084 | KYGLT20 | KYGLT2001 | GLT F965 Rpl Poles | 40269.03 |  | 40269.03 |  |  | 43193.64 | 694336 | -651142.36 | 2020-09-09 14:01 | 2023-08-29 | 2020-09-01
75084 | KYGLT20 | MX7817789 | GLT TR_UB F1881 (OHGLT2002) Transfe | 20648.93 |  | 20648.93 |  |  | 20648.93 | 10615.16 | 10033.77 | 2020-09-24 10:01 | 2021-09-28 | 2021-02-01 | 2021-07-28
75084 | KYGLT20 | MX8204271 | GLT TR_UB F965 T-Line KYGLT2001 Tra | 1947.33 |  | 1947.33 |  |  | 1947.33 | 25351.75 | -23404.42 | 2020-09-24 10:01 | 2023-09-28 | 2021-03-01
75084 | KYGLT20 | MX8203329 | GLT TR_UB F6785 T-Line OHGLT2010 | 6699.09 |  | 6699.09 |  |  | 6699.09 | 36544.94 | -29845.85 | 2020-10-21 14:01 | 2022-12-29 | 2021-01-01 | 2022-12-18
75084 | KYGLT20 | KYGLT2002 | GLT F5962 Rpl Poles | 7329.62 |  | 7329.62 |  |  | 7329.62 | 28842 | -21512.38 | 2020-12-01 18:02 | 2021-08-27 | 2021-03-01 | 2021-07-20
75084 | 23040041A | MX0319572 | SUB OPT -UPGRADE OF CAPACITORS BY A | 1346.58 |  | 1346.58 |  |  | 1346.58 | 12341.72 | -10995.14 | 2021-08-06 14:02 | 2024-03-30 | 2021-08-01
75084 | 23040041A | MX0319569 | SUB OPT -UPGRADE OF CAPACITORS BY A | 664.25 |  | 664.25 |  |  | 664.25 | 24404.92 | -23740.67 | 2021-08-10 10:02 | 2024-03-30 | 2021-08-01
75084 | 23040041A | MX0319571 | SUB OPT -UPGRADE OF CAPACITORS BY A | 621.35 |  | 621.35 |  |  | 621.35 | 16389.15 | -15767.8 | 2021-08-10 10:02 | 2024-03-30 | 2021-08-01
75084 | 23040041A | MX0319570 | SUB OPT -UPGRADE OF CAPACITORS BY A | 684.86 |  | 684.86 |  |  | 684.86 | 16201.61 | -15516.75 | 2021-08-10 10:02 | 2024-03-30 | 2021-08-01
75084 | 20670041A | MX1393377 | 0670041A: Buffington 41 K106-57 INS | 1164.01 |  | 1164.01 |  |  | 1164.01 | 45214.57 | -44050.56 | 2021-11-16 10:01 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | 20670041A | MX1701488 | 0670041A: Buffington 41 K106-544 IN | 1661.72 |  | 1661.72 |  |  | 1661.72 | 45212.76 | -43551.04 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1393379 | 0670041A: Buffington 41 K106-470 IN | 1226.9 |  | 1226.9 |  |  | 1226.9 | 51507.07 | -50280.17 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701450 | 0670041A: Buffington 41 K107-316 IN | 672.47 |  | 672.47 |  |  | 672.47 | 82843.09 | -82170.62 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701469 | 0670041A: Buffington 41 K116-9 REPR | 33.31 |  | 33.31 |  |  | 33.31 | 0 | 33.31 | 2021-10-21 10:02 | 2023-02-28 | 2021-10-01
75084 | 20670041A | MX1701449 | 0670041A: Buffington 41 K106-488 IN | 2045.88 |  | 2045.88 |  |  | 2045.88 | 40620.48 | -38574.6 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701487 | 0670041A: Buffington 41 26BN-218 IN | 1867.08 |  | 1867.08 |  |  | 1867.08 | 43932.67 | -42065.59 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | M200382 | M20038201 | EMR - Bellevue TB 2 ETM | 17076.88 |  | 17076.88 |  |  | 17076.88 | 54602 | -37525.12 | 2021-01-19 18:02 | 2022-10-21 | 2021-03-01 | 2022-08-05
75084 | DKY2645 | MX1975019 | Wilder 43 Ln Ext- DKY2645 | 52630.44 |  | 52630.44 |  |  | 63975.34 | 369283.68 | -305308.34 | 2019-07-25 14:01 | 2023-03-31 | 2019-10-01
75084 | DKY2645 | MX9064744 | Wilder 43 Rt9 Overhead Work - SOG D | 12564.56 |  | 12564.56 |  |  | 12564.56 | 32129.26 | -19564.7 | 2021-06-28 10:02 | 2023-03-16 | 2021-06-01
75084 | DKY2645 | MX1975744 | Wilder 43 Ln Ext Rt 9 to Central - | 18843.7 |  | 18843.7 |  |  | 18843.7 | 292340.2 | -273496.5 | 2020-10-09 10:01 | 2023-03-30 | 2021-06-01
75084 | SG001069F | SG1069GDQ | DEE Grid Data Quality GDQ | -131.27 |  | -131.27 |  |  | 64.19 | 195874 | -195809.81 | 2020-10-26 14:01 | 2024-03-31 | 2020-11-01 | 2023-01-31
75084 | M180387 | M18038701 | Cold Spring TB 9 LS Upgd | 160144.68 |  | 160144.68 |  |  | 160144.68 | 814576.06 | -654431.38 | 2021-02-16 18:02 | 2023-01-16 | 2021-03-01
75084 | SG001042F | SG1042SW | DEE Openway License Extension | -147.18 |  | -147.18 |  |  | 16878.18 | 16841 | 37.18 | 2020-07-28 21:29 | 2020-10-30 | 2020-09-01 | 2020-12-31
75084 | M190299 | M19029901 | F5967 Rbld Pole HL736 to HL 661 | 34245.48 |  | 34245.48 |  |  | 34245.48 | 25354607.12 | -25320361.64 | 2021-06-07 18:02 | 2026-02-13 | 2021-07-01
75084 | EAMHPBU | 349472009 | New EAM 2021 Mobile Durable Team | 3468.48 |  | 3468.48 |  |  | 3468.48 | 39130 | -35661.52 | 2021-01-13 12:53 | 2022-05-30 | 2021-02-01 | 2022-08-15
75084 | EAMHPBU | 349472008 | EAM 2021 Maximo Durable Team | 16418.75 |  | 16418.75 |  |  | 16418.75 | 84630 | -68211.25 | 2021-01-22 15:03 | 2022-05-30 | 2021-02-01
75084 | MDTMTR20 | TBKGETDEK | Toughbook and Getacs | 37.65 |  | 37.65 |  |  | 26784.9 | 68173 | -41388.1 | 2020-03-16 10:17 | 2021-03-31 | 2020-06-01 | 2022-03-31
75084 | 20550043A | MX9919684 | SUB OPT -UPGRADE OF CAPACITORS BY A | 722.81 |  | 722.81 |  |  | 722.81 | 16961.6 | -16238.79 | 2021-08-10 10:02 | 2023-06-15 | 2021-08-01
75084 | 20550043A | MX9919685 | SUB OPT -UPGRADE OF CAPACITORS BY A | 1870.13 |  | 1870.13 |  |  | 1870.13 | 18764.78 | -16894.65 | 2021-08-10 10:02 | 2023-06-15 | 2021-08-01
75084 | 20550043A | MX7372041 | 0550043A: Donaldson 43 21BN-302 REM | 3128.97 |  | 3128.97 |  |  | 3128.97 | 38388.05 | -35259.08 | 2021-10-22 09:12 | 2023-06-15 | 2021-10-01
75084 | 20550043A | MX1518718 | SUB OPT - Automated Switchgear (Eas | 66.67 |  | 66.67 |  |  | 66.67 | 0 | 66.67 | 2021-11-01 14:01 | 2023-03-31 | 2021-11-01
75084 | 20550043A | MX1064765 | SUB OPT - Donaldson 43 CVG South Re | 8506.19 |  | 8506.19 |  |  | 8506.19 | 0 | 8506.19 | 2021-11-01 10:01 | 2023-06-15 | 2021-11-01
75084 | 20550043A | K2055SURK | SUB OPT - SUR - DONALDSON - 2055 | 22761.9 |  | 22761.9 |  |  | 22761.9 | 77.69 | 22684.21 | 2021-05-20 09:31 | 2023-03-31 | 2021-11-01
75084 | 20550043A | MX1518649 | SUB OPT - Automated Switchgear CVG | 7339.27 |  | 7339.27 |  |  | 7339.27 | 0 | 7339.27 | 2021-11-01 10:01 | 2023-05-23 | 2021-11-01
75084 | SG001117F | SG001117 | DEE LMR Consoles | 744979.97 |  | 744979.97 |  |  | 744979.97 | 874447 | -129467.03 | 2021-08-25 19:52 | 2023-03-31 | 2021-09-01
75084 | 21520041A | MX7891218 | SUB OPT -REPLACEMENT OF EXISTING RE | 1043.28 |  | 1043.28 |  |  | 1043.28 | 4505.46 | -3462.18 | 2021-10-20 14:02 | 2024-08-29 | 2021-11-01
75084 | 20670044A | MX1701453 | 0670044A: Buffington 44 K106-284 IN | 1874.76 |  | 1874.76 |  |  | 1874.76 | 46702.95 | -44828.19 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670044A | MX1701452 | 0670044A: Buffington 44 K106-115 RE | 99.88 |  | 99.88 |  |  | 99.88 | 0 | 99.88 | 2021-10-21 10:02 | 2023-02-02 | 2021-11-01
75084 | 20670044A | MX1701455 | 0670044A: Buffington 44 K107-430 IN | 1508.95 |  | 1508.95 |  |  | 1508.95 | 44820.96 | -43312.01 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670044A | MX1701451 | 0670044A: Buffington 44 K105-368 IN | 2209.99 |  | 2209.99 |  |  | 2209.99 | 44442.98 | -42232.99 | 2021-10-01 14:01 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | DKY2754 | MX6322062 | Thomas More 41 Ln Ext DKY2754 | 32925.51 |  | 32925.51 |  |  | 32925.51 | 619257.84 | -586332.33 | 2021-01-07 18:02 | 2023-03-31 | 2021-03-01
75084 | DKY2451 | MX1425894 | Hebron 45 LN Ext DKY2451 | 459722.06 |  | 459722.06 |  |  | 489798.67 | 325392.17 | 164406.5 | 2019-10-02 14:01 | 2022-03-22 | 2019-12-01 | 2022-03-15
75084 | DKY2451 | MX7616715 | Hebron 45 Recloser Install - SOG - | 55896.38 |  | 55896.38 |  |  | 57108.24 | 42104.37 | 15003.87 | 2020-10-14 10:01 | 2022-03-22 | 2020-10-01 | 2022-03-15
75084 | 22410044A | MX7372047 | 2410044A: Florence 44 31BN-1326 INS | 2542.19 |  | 2542.19 |  |  | 2542.19 | 43984.74 | -41442.55 | 2021-10-22 09:12 | 2022-11-29 | 2021-10-01
75084 | 22410044A | MX7372048 | 2410044A: Florence 44 BNK-2793 INST | 1328.64 |  | 1328.64 |  |  | 1328.64 | 48817.22 | -47488.58 | 2021-10-22 09:12 | 2022-11-29 | 2021-10-01
75084 | 22410044A | MX7372045 | 2410044A: Florence 44 25BN-725 INST | 2222.06 |  | 2222.06 |  |  | 2222.06 | 44697.77 | -42475.71 | 2021-10-21 14:01 | 2024-03-30 | 2021-10-01
75084 | 22410044A | MX1701448 | 2410044A: Florence 44 BNK-6116 REPR | 38.59 |  | 38.59 |  |  | 38.59 | 0 | 38.59 | 2021-10-22 13:47 | 2024-03-30 | 2021-11-01
75084 | 22410044A | MX2158204 | SUB OPT - TRANSFORMER UG 3-PHASE EN | 14944.89 |  | 14944.89 |  |  | 14944.89 | 20181.62 | -5236.73 | 2021-09-01 14:02 | 2024-03-30 | 2021-12-01
75084 | SG001057F | SG1057SW | DEE Customer Mapping Engine | 38042.34 |  | 38042.34 |  |  | 43397.93 | 150716 | -107318.07 | 2020-08-27 15:29 | 2023-10-31 | 2020-09-01 | 2022-12-15
75084 | SG001057F | SG1057SVR | DEE Customer Mapping Engine | 1508.86 |  | 1508.86 |  |  | 13122.25 | 7291 | 5831.25 | 2020-08-26 21:08 | 2023-10-31 | 2020-12-01 | 2022-12-15
75084 | 20670047A | MX1701467 | 0670047A: Buffington 47 K116-195 IN | 1751.99 |  | 1751.99 |  |  | 1751.99 | 44567.74 | -42815.75 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393384 | 0670047A: Buffington 47 K116-611 IN | 903.44 |  | 903.44 |  |  | 903.44 | 47387.16 | -46483.72 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393385 | 0670047A: Buffington 47 K116-25 INS | 1964.85 |  | 1964.85 |  |  | 1964.85 | 44274.37 | -42309.52 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1701466 | 0670047A: Buffington 47 K107-318 RE | 33.31 |  | 33.31 |  |  | 33.31 | 0 | 33.31 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01
75084 | 20670047A | MX1393383 | 0670047A: Buffington 47 K116-210 IN | 1830.13 |  | 1830.13 |  |  | 1830.13 | 45647.76 | -43817.63 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1701468 | 0670047A: Buffington 47 K116-409 IN | 2105.29 |  | 2105.29 |  |  | 2105.29 | 43947.82 | -41842.53 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393382 | 0670047A: Buffington 47 26BN-58 INS | 1527.8 |  | 1527.8 |  |  | 1527.8 | 43289.81 | -41762.01 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20420044A | MX7372056 | 0420044A: Constance 44 21BN-396 INS | 1786.96 |  | 1786.96 |  |  | 1786.96 | 44441.08 | -42654.12 | 2021-10-22 09:12 | 2023-06-15 | 2021-10-01
75084 | 20420044A | MX7372055 | 0420044A: Constance 44 21BN-625 INS | 1751.53 |  | 1751.53 |  |  | 1751.53 | 41260.05 | -39508.52 | 2021-10-22 09:12 | 2023-06-15 | 2021-12-01
75084 | 20420044A | MX7372054 | 20420044A: Constance 44 21BN-635 I | 3583.98 |  | 3583.98 |  |  | 3583.98 | 43253.22 | -39669.24 | 2021-10-22 09:12 | 2023-06-15 | 2021-10-01
75084 | M190086 | M19008601 | Emergent - Circuit 6763 Replace ABS | -5071.04 |  | -5071.04 |  |  | 232593.08 | 228764.57 | 3828.51 | 2019-08-30 14:01 | 2020-09-26 | 2019-09-01 | 2020-09-26
75084 | M190086 | MX6298727 | T-Emergent F6763 (T-DPN M19008601) | 12835.39 |  | 12835.39 |  |  | 17327.91 | 1862.48 | 15465.43 | 2020-05-12 10:01 | 2021-03-31 | 2020-06-01 | 2021-03-16
75084 | M190157 | M19015701 | GLT - F5966 Rpl Poles, Insp Year 20 | -14788.89 |  | -14788.89 |  |  | -1.8474e-13 | 25034 | -25034 | 2019-10-10 14:01 | 2021-06-30 | 2020-01-01
75084 | M210391 | M21039101 | Emergent - Bellevue Substation Repl | 1056698.58 |  | 1056698.58 |  |  | 1056698.58 | 1501567 | -444868.42 | 2021-08-19 18:04 | 2022-03-22 | 2021-08-01 | 2022-04-20
75084 | M190220 | M19022001 | Emergent Repl ABS 817 F15268 T-Line | 720.27 |  | 720.27 |  |  | 313062.14 | 311345.37 | 1716.77 | 2019-09-25 14:01 | 2020-05-01 | 2019-10-01 | 2020-06-30
75084 | DKY2214 | MX1424737 | Constance 43 SG DKY2214 | 309280.46 |  | 309280.46 |  |  | 311216.84 | 122686.92 | 188529.92 | 2019-07-25 14:01 | 2021-10-06 | 2019-09-01 | 2021-09-28
75084 | DKY2633 | MX1423978 | Verona 41 Eads Rd Reco - SOG - DKY2 | 256131.48 |  | 256131.48 |  |  | 288117.38 | 204868.11 | 83249.27 | 2020-10-05 18:05 | 2022-05-26 | 2020-11-01 | 2022-05-25
75084 | M200412 | M20041201 | EMR - Mt Zion Rpl Reg | 70698.98 |  | 70698.98 |  |  | 70698.98 | 95107.25 | -24408.27 | 2021-01-28 14:02 | 2021-06-21 | 2021-02-01 | 2021-06-05
75084 | M190298 | M19029801 | F5967 Rbld HL 864 to HL 801 | 43943.62 |  | 43943.62 |  |  | 43943.62 | 23140666.42 | -23096722.8 | 2021-06-07 18:02 | 2023-07-04 | 2021-06-01
75084 | M190298 | M19029803 | F5967 Rbld HL801 - HL746 - HL736 | 5917.95 |  | 5917.95 |  |  | 5917.95 | 998899.36 | -992981.41 | 2021-06-07 18:02 | 2023-03-13 | 2021-08-01
75084 | SG000551F | SG551NOK | Nokia Network Services Platform | 2035.01 |  | 2035.01 |  |  | 12228.52 | 17998 | -5769.48 | 2020-12-07 17:22 | 2023-03-30 | 2020-12-01
75084 | SG000502F | SG502SW | SG DEE Device Entry Alert Sys - 502 | -9.99 |  | -9.99 |  |  | 12296.05 | 69968.07 | -57672.02 | 2018-08-31 13:48 | 2020-12-31 | 2019-01-01 | 2020-09-30
75084 | DKY2722 | MX9365045 | Villa 43 Ln Ext to Thom More 41 - D | 12012.52 |  | 12012.52 |  |  | 12012.52 | 837596.92 | -825584.4 | 2021-01-07 14:02 | 2023-05-01 | 2021-03-01
75084 | SG001145F | SG001145 | DEE Power Monitoring & Mgmnt System | 4436.25 |  | 4436.25 |  |  | 4436.25 | 5173 | -736.75 | 2021-07-08 15:45 | 2022-11-30 | 2021-07-01 | 2022-06-18
75084 | M200326 | M20032601 | Emgt - Hands Flood Mitigation | 43172.3 |  | 43172.3 |  |  | 43172.3 | 168205.24 | -125032.94 | 2021-02-16 18:02 | 2023-11-20 | 2021-02-01
75084 | DKY2753 | MX6321825 | Covington 44 Ln Ext to Augustine 42 | 16434.59 |  | 16434.59 |  |  | 16434.59 | 9307.46 | 7127.13 | 2021-01-07 18:02 | 2021-08-30 | 2021-02-01 | 2021-08-09
75084 | 20550041A | MX7372065 | SUB OPT - INSTALLATION OF SELF HEAL | 628.36 |  | 628.36 |  |  | 628.36 | 41759.97 | -41131.61 | 2021-08-23 10:01 | 2023-02-02 | 2021-09-01 | 2023-02-05
75084 | 20550041A | MX7372067 | 0550041A: Donaldson 41 26BN-246 INS | 1220.46 |  | 1220.46 |  |  | 1220.46 | 45568.45 | -44347.99 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX7372063 | 0550041A: Donaldson 41 K116-982 IN | 1209.53 |  | 1209.53 |  |  | 1209.53 | 47524.19 | -46314.66 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX1701486 | 0550041A: Donaldson 41 26BN-1086 IN | 1747.99 |  | 1747.99 |  |  | 1747.99 | 44820.84 | -43072.85 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX7372064 | 0550041A: Donaldson 41 BNK-1184 INS | 1109.05 |  | 1109.05 |  |  | 1109.05 | 44050.59 | -42941.54 | 2021-10-21 10:02 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | 20550041A | MX7372068 | 0550041A: Donaldson 41 26BN-616 INS | 1732.8 |  | 1732.8 |  |  | 1732.8 | 41285.61 | -39552.81 | 2021-10-22 09:12 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | SG000946F | SG946CONN | Establish T&D Connectivity SW | 6797.39 |  | 6797.39 |  |  | 13126.96 | 33939 | -20812.04 | 2020-07-27 11:21 | 2022-01-03 | 2020-08-01 | 2022-03-31
75084 | 22410047A | MX7372051 | 2410047A: Florence 47 BNK-2806 INST | 2233.85 |  | 2233.85 |  |  | 2233.85 | 55988.65 | -53754.8 | 2021-10-22 09:12 | 2024-03-30 | 2021-10-01
75084 | 22410047A | MX1473566 | 2410047A: Florence 47 BNK-8073 INST | 1595.55 |  | 1595.55 |  |  | 1595.55 | 304316.79 | -302721.24 | 2021-10-21 14:01 | 2024-03-30 | 2021-12-01
75084 | DVV2021 | 400051013 | CIP-012 Ohio/KY | 16643.86 |  | 16643.86 |  |  | 16643.86 | 91312 | -74668.14 | 2021-06-18 17:14 | 2024-03-31 | 2021-06-01
75084 | 22100042A | MX1701485 | TBC 2100042A: Oakbrook 42 Btw 25BN | 1253.43 |  | 1253.43 |  |  | 1253.43 | 43167.24 | -41913.81 | 2021-10-21 10:02 | 2023-03-31 | 2021-12-01
75084 | 22100042A | MX1701482 | 2100042A: Oakbrook 42 20BN-22 INSTA | 1011.34 |  | 1011.34 |  |  | 1011.34 | 44819.16 | -43807.82 | 2021-10-21 10:02 | 2023-06-15 | 2021-12-01
75084 | 22100042A | MX1701483 | TBC 2100042A: Oakbrook 42 25BN-264 | 826.17 |  | 826.17 |  |  | 826.17 | 41130.11 | -40303.94 | 2021-10-21 10:02 | 2023-03-31 | 2021-12-01
75084 | SG001043F | SG1043SW | DEE FND License Extension | -242.19 |  | -242.19 |  |  | 27776.08 | 27900 | -123.92 | 2020-07-29 09:01 | 2020-10-30 | 2020-09-01 | 2020-12-31
75084 | SG000940F | SG940SVR | DEE EDMS Platform Upgrade | -85.54 |  | -85.54 |  |  | 16715.57 | 13545 | 3170.57 | 2020-04-24 15:48 | 2020-12-18 | 2020-05-01 | 2021-02-07
75084 | M190244 | MX4877019 | F2166 Covington to Newport Steel X- | 20095.33 |  | 20095.33 |  |  | 23246.36 | 33025.21 | -9778.85 | 2019-11-27 14:01 | 2022-07-29 | 2020-10-01 | 2022-06-09
75084 | M190244 | MX4876167 | F2166 West End to Covington X-fer U | 58198.93 |  | 58198.93 |  |  | 59695.22 | 25239.31 | 34455.91 | 2019-11-27 14:01 | 2021-11-29 | 2020-12-01 | 2021-08-09
75084 | M200376 | M20037601 | Emr - Cir 5967 Rpl Hwy Crossing | 2272080.96 |  | 2272080.96 |  |  | 2272080.96 | 2354434 | -82353.04 | 2020-12-03 14:02 | 2022-02-21 | 2021-02-01 | 2022-03-03
75084 | M210257 | M21025701 | EMR COLD SPRINGS TO WILDER - 69KV H | 33196.65 |  | 33196.65 |  |  | 33196.65 | 2407350 | -2374153.35 | 2021-05-05 10:02 | 2022-07-30 | 2021-05-01 | 2022-08-25
75084 | M190190 | M19019001 | Taylor Mill Sub PT II | -493.89 |  | -493.89 |  |  | 2350464.39 | 2350000 | 464.39 | 2019-08-20 14:01 | 2021-02-13 | 2019-08-01 | 2021-03-11
75084 | SG001076F | SG1076OCT | DEE Capital Investment Planning | 46034.87 |  | 46034.87 |  |  | 131073.84 | 231176 | -100102.16 | 2020-11-11 10:19 | 2023-03-31 | 2020-12-01
75084 | 75084RR | KMODEM | Proactive Replace Smart Dev Modem | 20232.98 |  | 20232.98 |  |  | 69655.66 | 50000 | 19655.66 | 2017-12-07 13:26 | 2068-03-31 | 2020-04-01
75084 | 75084RR | KNANC | Neighborhood Area Ntwk Replacements | 16834.55 |  | 16834.55 |  |  | 71695.73 | 0 | 71695.73 | 2017-03-27 14:46 | 2067-04-01 | 2019-05-01
75084 | SG001001F | SG1001SW | DEE IoT Platform Assessment POC | -1593.29 |  | -1593.29 |  |  | -2.8422e-13 | 27663.6 | -27663.6 | 2020-09-11 18:40 | 2022-12-31 | 2020-09-01
75084 | M210025 | M21002501 | EMR - Rpl Grant CB 221 | 186630.13 |  | 186630.13 |  |  | 186630.13 | 215528.52 | -28898.39 | 2021-01-21 18:02 | 2021-07-03 | 2021-01-01 | 2021-07-14
75084 | SG001092F | SG1092SLR | DEK Aero Solar | 3456752.19 |  | 3456752.19 |  |  | 3456752.19 | 4976446 | -1519693.81 | 2021-03-12 10:30 | 2022-10-15 | 2021-03-01
75084 | SG000954F | SG954KYFR | DEK Fuse Replacement AFWS | 293325.54 |  | 293325.54 |  |  | 293325.54 | 3940594 | -3647268.46 | 2019-10-22 15:06 | 2026-03-31 | 2021-01-01
75084 | TLRKY20 | TLRKY2001 | FIF 1 P2 Stub Pole replace Cir 596 | -471.85 |  | -471.85 |  |  | 16522.85 | 26014.08 | -9491.23 | 2020-03-17 14:01 | 2020-09-07 | 2020-05-01 | 2020-09-17
75084 | 20670046A | MX9919642 | SUB OPT -UPGRADE OF CAPACITORS BY A | 626.57 |  | 626.57 |  |  | 626.57 | 16005.94 | -15379.37 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 22410042A | K2241SURK | SUB OPT - SUR - FLORENCE - 2241 | 34498.29 |  | 34498.29 |  |  | 34498.29 | 77.69 | 34420.6 | 2021-05-04 12:07 | 2024-03-31 | 2021-11-01
75084 | 22410042A | MX2158190 | SUB OPT - TRANSFORMER UG 3-PHASE EN | 2271.34 |  | 2271.34 |  |  | 2271.34 | 15692.92 | -13421.58 | 2021-09-01 14:02 | 2024-03-30 | 2021-12-01
75084 | SG000520F | MX0494881 | MXCONV-Transformer Retrofit DAYTON | 11675.63 |  | 11675.63 |  |  | 165594.22 | 148626.35 | 16967.87 | 2020-03-12 10:02 | 2021-03-25 | 2020-07-01 | 2021-02-23
75084 | 22410046A | MX8564271 | SUB OPT -TRANSFORMER UG THREE PHASE | 2219.26 |  | 2219.26 |  |  | 2219.26 | 20331.37 | -18112.11 | 2021-07-06 10:03 | 2024-03-30 | 2021-08-01
75084 | 22410046A | MX2158210 | SUB OPT - TRANSFORMER UG 3-PHASE EN | 19075.64 |  | 19075.64 |  |  | 19075.64 | 23199.72 | -4124.08 | 2021-09-01 14:02 | 2024-03-30 | 2021-12-01
75084 | 22410046A | MX1701480 | 2410046A: Florence 46 30BN-672 REPR | 135.8 |  | 135.8 |  |  | 135.8 | 0 | 135.8 | 2021-12-07 10:01 | 2024-03-30 | 2021-12-01
75084 | 22410046A | MX1701481 | 2410046A: Florence 46 31BN-1347 INS | 13329.48 |  | 13329.48 |  |  | 13329.48 | 43414.29 | -30084.81 | 2021-10-21 10:02 | 2024-03-30 | 2021-12-01
75084 | 21520042A | MX1089713 | SUB OPT Hebron 42 Reco Pt 2 - 21520 | 31991.6 |  | 31991.6 |  |  | 31991.6 | 589991.61 | -558000.01 | 2021-11-02 10:02 | 2024-08-29 | 2021-11-01
75084 | 21520042A | MX1089758 | SUB OPT Hebron 42 Reco Part 1 - 215 | 41631.54 |  | 41631.54 |  |  | 41631.54 | 403119.11 | -361487.57 | 2021-11-02 10:02 | 2024-08-29 | 2021-11-01
75084 | 21520042A | MX1089667 | SUB OPT Hebron 42 Reco Part 1 - 215 | 37553.1 |  | 37553.1 |  |  | 37553.1 | 591554.32 | -554001.22 | 2021-11-02 10:02 | 2025-03-31 | 2021-11-01
75084 | 21520042A | MX7891216 | SUB OPT -REPLACEMENT OF EXISTING RE | 1192 |  | 1192 |  |  | 1192 | 5005.02 | -3813.02 | 2021-11-04 14:01 | 2024-08-29 | 2021-11-01
75084 | 21520042A | MX7891191 | SUB OPT -REPLACEMENT OF EXISTING RE | 1409.12 |  | 1409.12 |  |  | 1409.12 | 4968.19 | -3559.07 | 2021-10-20 14:02 | 2024-08-29 | 2021-11-01
75084 | 21520042A | MX7891217 | SUB OPT -REPLACEMENT OF EXISTING RE | 1356.35 |  | 1356.35 |  |  | 1356.35 | 0 | 1356.35 | 2021-11-22 18:02 | 2024-08-29 | 2021-11-01
75084 | M210413 | M21041301 | EMERGENT - REPLACE CLARYVILLE TB 3 | 733984.47 |  | 733984.47 |  |  | 733984.47 | 1960120 | -1226135.53 | 2021-09-03 10:01 | 2022-04-03 | 2021-09-01 | 2022-03-17
75084 | M210095 | M21009501 | Villa TB 1 ETM Rpl | 17575.43 |  | 17575.43 |  |  | 17575.43 | 61096 | -43520.57 | 2021-03-09 10:02 | 2021-12-07 | 2021-03-01 | 2021-12-28
75084 | M210258 | M21025801 | EMR Cir 15268 Rpl I-275 Hwy Crossi | 596.74 |  | 596.74 |  |  | 596.74 | 0 | 596.74 | 2021-05-13 14:02 | 2023-06-10 | 2021-06-01
75084 | M180439 | M18043901 | 5967 Rbld Pt 1 Swi 602_Decoursey | 838.44 |  | 838.44 |  |  | 838.44 | 0 | 838.44 | 2019-04-26 14:07 | 2027-07-20 | 2021-05-01
75084 | DKY2748 | MX6322098 | Aero to CVG South Ln Ext | 48417.78 |  | 48417.78 |  |  | 48417.78 | 30547.85 | 17869.93 | 2021-07-08 08:01 | 2021-12-02 | 2021-07-01 | 2021-11-28
75084 | DKY2748 | MX1561891 | Aero to CVG South Ln Ext - New Gear | 27529.06 |  | 27529.06 |  |  | 27529.06 | 727870.64 | -700341.58 | 2021-07-08 08:01 | 2022-11-29 | 2021-08-01
75084 | M210146 | M21014601 | Emergent - Wilder TB 3 Install Powe | 328768.72 |  | 328768.72 |  |  | 328768.72 | 377777 | -49008.28 | 2021-03-18 18:03 | 2022-06-28 | 2021-03-01 | 2022-05-22
75084 | 20550044A | RWT055A | ROW - Donaldson - H9320550044 | 1086.82 |  | 1086.82 |  |  | 1086.82 | 5000 | -3913.18 | 2021-06-16 08:35 | 2023-03-31 | 2021-07-01
75084 | 20550044A | MX1473561 | 0550044A: Donaldson 44 26BN-1308 RE | 580.6 |  | 580.6 |  |  | 580.6 | 45686.85 | -45106.25 | 2021-10-21 14:01 | 2023-06-15 | 2021-12-01
75084 | 23040043A | MX0319574 | SUB OPT -UPGRADE OF CAPACITORS BY A | 1413.95 |  | 1413.95 |  |  | 1413.95 | 24462.8 | -23048.85 | 2021-08-06 14:02 | 2024-03-30 | 2021-08-01
75084 | 23040043A | MX7891230 | SUB OP 2022 RECL RPL, KNK-5686, WHI | 683.42 |  | 683.42 |  |  | 683.42 | 14973.99 | -14290.57 | 2021-11-15 14:01 | 2024-03-30 | 2021-12-01
75084 | M190300 | M19030001 | F5967 Rbld HL 661 to Decoursey | 30431.95 |  | 30431.95 |  |  | 30431.95 | 17596346.92 | -17565914.97 | 2021-06-07 18:02 | 2025-07-07 | 2021-07-01
75084 | 22410045A | MXA701477 | TBC 2410045A: Florence 45 25BN-507 | 1974.22 |  | 1974.22 |  |  | 1974.22 | 72821.71 | -70847.49 | 2021-10-22 13:47 | 2024-03-30 | 2021-10-01
75084 | 22410045A | MX0002522 | 2023 Sub Opt TUG - Pheasant Dr - Ea | 571.33 |  | 571.33 |  |  | 571.33 | 0 | 571.33 | 2021-12-13 14:11 | 2024-03-30 | 2021-12-01
75084 | 22410045A | MX1701479 | TBC 2410045A: Florence 45 Btw 25BN | 1010.27 |  | 1010.27 |  |  | 1010.27 | 43634.32 | -42624.05 | 2021-10-21 10:02 | 2024-03-30 | 2021-12-01
75084 | 22410045A | MX0002524 | 2023 Sub Opt TUG - Pheasant Dr - We | 4399.59 |  | 4399.59 |  |  | 4399.59 | 0 | 4399.59 | 2021-12-13 14:11 | 2024-03-30 | 2021-12-01
75084 | RES75084 | KMW200501 | Augustine Overhead Door Replacement | 7053.99 |  | 7053.99 |  |  | -4.3698e-13 | 6676 | -6676 | 2020-11-10 08:55 | 2021-08-30 | 2020-12-01
75084 | RES75084 | KMW200390 | Augustine Heater Replacement | -13000 |  | -13000 |  |  | 22055.6 | 29118 | -7062.4 | 2020-09-09 17:16 | 2021-08-01 | 2020-11-01 | 2021-01-29
75084 | SG001140F | SG1140M21 | DEK EOL Modem Replacements | 24720.64 |  | 24720.64 |  |  | 24720.64 | 64493 | -39772.36 | 2021-12-17 11:34 | 2022-07-31 | 2021-12-01
75084 | 20670043A | MX2158161 | SUB OPT - TRANSFORMER UG 3-PHASE EN | 16814.13 |  | 16814.13 |  |  | 16814.13 | 19560.85 | -2746.72 | 2021-09-01 14:02 | 2023-02-02 | 2021-12-01 | 2023-02-05
75084 | 20670043A | MX2158154 | SUB OPT - TRANSFORMER UG 3-PHASE EN | 16699.69 |  | 16699.69 |  |  | 16699.69 | 21526.42 | -4826.73 | 2021-09-01 10:01 | 2023-02-02 | 2021-12-01 | 02/05/2023
75084 | M210323 | M21032301 | EMR - Circuit 965 Replace ABS 346 | 8087.4 |  | 8087.4 |  |  | 8087.4 | 139856 | -131768.6 | 2021-11-12 14:01 | 2022-08-29 | 2021-12-01 | 2022-08-29
75084 | M210102 | M21010201 | Wilder SPCC Install | 4898.46 |  | 4898.46 |  |  | 4898.46 | 70505 | -65606.54 | 2021-08-24 10:01 | 2022-02-28 | 2021-08-01 | 2021-12-15
75084 | M210428 | M21042801 | Buffington Substation - Disconnect | 6876.26 |  | 6876.26 |  |  | 6876.26 | 104596 | -97719.74 | 2021-10-12 10:02 | 2022-08-05 | 2021-11-01 | 07/29/2022
75084 | M180375 | M18037502 | Litton Sub- Ext Xmission | 662.29 |  | 662.29 |  |  | 662.29 | 0 | 662.29 | 2021-10-29 14:02 | 2024-06-28 | 2021-12-01
75084 | M180375 | M18037501 | Litton Sub- construct Sub | 441.04 |  | 441.04 |  |  | 441.04 | 8574167 | -8573725.96 | 2021-10-29 14:02 | 2024-06-28 | 2021-11-01
75085 | CUSTCONN | 315986A | Customer Connect - Core | 937668.64 |  | 937668.64 |  |  | 5119660.8 | 3313201.21 | 1806459.59 | 2017-08-10 10:40 | 2022-12-05 | 2017-08-01 | 2022-07-06
75085 | CUSTCONN | 315986E | Customer Connect- Universal Bill | 69.98 |  | 69.98 |  |  | 348179.67 | 166907.14 | 181272.53 | 2017-08-11 10:38 | 2020-09-01 | 2017-08-01 | 2020-09-01
75085 | CUSTCONN | 315986F | Customer Connect- R6-8 Scope | 393249.39 |  | 393249.39 |  |  | 393249.39 | 76898 | 316351.39 | 2021-03-30 10:43 | 2022-06-30 | 2021-04-01 | 2022-07-06
75085 | CUSTCONN | 315986HW7 | Customer Connect - Hardware Proj 5 | 41079.11 |  | 41079.11 |  |  | 41079.11 | 89586 | -48506.89 | 2021-04-21 14:04 | 2021-12-31 | 2021-04-01 | 2021-12-31
75085 | CUSTCONN | 315986HW6 | Customer Connect- Hardware Proj 4 | 17234.06 |  | 17234.06 |  |  | 100541.3 | 30625 | 69916.3 | 2020-03-12 11:24 | 2021-03-15 | 2020-03-01 | 2021-06-01
75085 | CUSTCONN | 315986HW8 | Customer Connect- Hardware Proj 6 | 28821.85 |  | 28821.85 |  |  | 28821.85 | 96250 | -67428.15 | 2021-09-27 15:14 | 2022-06-30 | 2021-10-01 | 2022-09-15
75085 | FPIT | 307482002 | Customer Mobile App - Phase 3 | 99.89 |  | 99.89 |  |  | 4457.27 | 37822 | -33364.73 | 2019-12-19 13:47 | 2022-03-15 | 2020-01-01 | 2022-03-31
75085 | FPIT | CS2100007 | Verint License Purchase | 14495.76 |  | 14495.76 |  |  | 14495.76 | 25285 | -10789.24 | 2021-07-20 09:31 | 2021-12-29 | 2021-09-01 | 2021-12-31
75085 | FPIT | 344637001 | MW Test Data Enhancement | -0.07 |  | -0.07 |  |  | 1.1102e-15 | 2622 | -2622 | 2018-03-14 10:39 | 2018-12-28 | 2018-03-01 | 2018-12-28
75085 | FPIT | CS2100008 | Nuance IVR Enhancements | 4085.34 |  | 4085.34 |  |  | 4085.34 | 5958 | -1872.66 | 2021-07-16 11:35 | 2022-08-31 | 2021-08-01 | 2022-08-31
75085 | FPIT | CC1900003 | Street Light Repair Request SW | 20393.49 |  | 20393.49 |  |  | 62826.83 | 53252.24 | 9574.59 | 2020-02-28 08:21 | 2021-03-31 | 2020-07-01 | 2021-03-31
75085 | FPIT | CS2100009 | Avaya License Purchase #2 | 15471.55 |  | 15471.55 |  |  | 15471.55 | 26941 | -11469.45 | 2021-07-27 16:26 | 2021-11-29 | 2021-09-01 | 2021-12-31
75085 | FPIT | CS2100005 | Infrastructure for 24/7 Intouch | 2809.33 |  | 2809.33 |  |  | 2809.33 | 2789 | 20.33 | 2021-05-27 11:46 | 2022-01-31 | 2021-06-01 | 2022-02-28
75085 | FPIT | CS2100006 | Upland Right Answer License Purchas | 5582.46 |  | 5582.46 |  |  | 5582.46 | 8574 | -2991.54 | 2021-06-16 10:57 | 2022-01-31 | 2021-07-01 | 2022-01-31
75085 | FPIT | CS2100003 | Aspect License purchase | 8347.36 |  | 8347.36 |  |  | 8347.36 | 8343 | 4.36 | 2021-04-26 16:38 | 2021-08-29 | 2021-06-01 | 2021-09-30
75085 | FPIT | CS2100004 | Avaya License Purchase | 31772.05 |  | 31772.05 |  |  | 31772.05 | 32036 | -263.95 | 2021-05-12 09:03 | 2021-09-28 | 2021-05-01 | 2021-09-30
75080 | FPIT | NINT1105K | Implement Rates and Regulatory Stra | -230817.41 |  | -230817.41 |  |  | -6.9349e-12 | 234263 | -234263 | 2017-08-15 14:48 | 2022-01-31 | 2017-08-01 | 2022-03-31
75080 | FPIT | 323174Q4I | Q4 2017 End of Life Server | -200.11 |  | -200.11 |  |  | 8689.56 | 8685 | 4.56 | 2017-10-16 14:30 | 2018-03-31 | 2017-12-01 | 2018-03-31
75080 | FPIT | 359140001 | ISOP Data Management | 47546.1 |  | 47546.1 |  |  | 118872.48 | 169292 | -50419.52 | 2018-12-19 15:02 | 2023-03-29 | 2019-01-01
75080 | FPIT | CC1900002 | Vegetation Management Communication | 31200.44 |  | 31200.44 |  |  | 51476.6 | 34275 | 17201.6 | 2020-01-24 17:04 | 2021-10-31 | 2020-03-01 | 2021-10-31
75080 | FPIT | CC2000005 | Planned Outages Portal SW | 46820.72 |  | 46820.72 |  |  | 50018.92 | 48524 | 1494.92 | 2020-10-20 13:20 | 2022-02-28 | 2020-10-01 | 2022-03-10
75080 | FPIT | 307482SW2 | Customer Mobile App - Phase 3 | 32950.23 |  | 32950.23 |  |  | 53540.64 | 60515 | -6974.36 | 2020-04-13 09:04 | 2022-03-15 | 2020-04-01 | 2022-03-31
75080 | FPIT | 349395006 | ITOT OT SIEM Phase 2 HW Workstream | 10593.38 |  | 10593.38 |  |  | 28326.59 | 64242 | -35915.41 | 2020-04-03 15:02 | 2022-10-28 | 2020-05-01 | 2022-10-18
75080 | FPIT | CC1900001 | Customer Analytics Engine | 29219.02 |  | 29219.02 |  |  | 57143.34 | 55612 | 1531.34 | 2020-01-27 07:55 | 2022-03-31 | 2020-02-01 | 2022-03-31
75080 | FPIT | CS2000002 | Web Outage Reporting Platform | -109.85 |  | -109.85 |  |  | 23015.26 | 12300 | 10715.26 | 2020-04-16 18:33 | 2021-01-31 | 2020-04-01 | 2021-01-01
75080 | FPIT | CY190HW13 | IT-OT ANA Workstream HW | 2039604.73 |  | 2039604.73 |  |  | 2393652.73 | 2784426 | -390773.27 | 2019-12-05 14:44 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | IT2000010 | EnCompass Client/Server Version 4.1 | 3140 |  | 3140 |  |  | 3140 | 3839 | -699 | 2020-03-17 09:05 | 2020-07-30 | 2021-04-01 | 2020-08-01
75080 | FPIT | 400055002 | Chatbot Channels | 12797.35 |  | 12797.35 |  |  | 12797.35 | 12437 | 360.35 | 2020-12-08 09:28 | 2022-03-31 | 2021-01-01 | 2022-03-31
75080 | FPIT | CY190SW13 | IT-OT ANA Workstream SW | 3835.44 |  | 3835.44 |  |  | 18797.17 | 885364 | -866566.83 | 2019-12-05 14:32 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | CS1900001 | Voice of the Customer Engagement Pl | 11350.76 |  | 11350.76 |  |  | 19841.88 | 27483 | -7641.12 | 2020-01-29 15:52 | 2022-03-31 | 2020-02-01 | 2022-03-31
75080 | FPIT | CC2000003 | SiteCore JSS Front End Modernizatio | 33585.53 |  | 33585.53 |  |  | 46637.33 | 57443 | -10805.67 | 2020-06-25 21:05 | 2022-05-30 | 2020-08-01 | 2022-05-31
75080 | FPIT | CY190SW16 | ITOT ANA Workstream Tufin SW | 868.77 |  | 868.77 |  |  | 42836.69 | 50484 | -7647.31 | 2020-11-30 19:55 | 2022-10-28 | 2020-12-01 | 2022-10-18
75080 | FPIT | SE2000001 | End of life replacement for Firewal | 355.33 |  | 355.33 |  |  | 8874.5 | 25952 | -17077.5 | 2020-04-17 13:25 | 2021-03-31 | 2020-05-01 | 2021-03-31
75080 | FPIT | IT2000004 | Adapt 2 SW | 15878.65 |  | 15878.65 |  |  | 175415.91 | 153514 | 21901.91 | 2020-03-03 08:10 | 2021-10-30 | 2020-03-01 | 2021-10-31
75080 | FPIT | 400055010 | Digital Assistant Platform Ph 1 | 2845.78 |  | 2845.78 |  |  | 2845.78 | 6670 | -3824.22 | 2021-07-26 14:34 | 2022-03-15 | 2021-10-01 | 2022-03-31
75080 | FPIT | SE2100003 | End of life Repl for Firewalls | 14227.52 |  | 14227.52 |  |  | 14227.52 | 6180 | 8047.52 | 2021-04-14 21:48 | 2022-03-31 | 2021-04-01 | 2022-03-31
75080 | FPIT | 349395SW6 | ITOT OT SIEM SW Workstream | 17299.45 |  | 17299.45 |  |  | 17299.45 | 71164 | -53864.55 | 2021-12-01 18:03 | 2022-10-28 | 2021-12-01 | 2022-10-18
75080 | FPIT | 400055009 | Call Center Analytics SW | 4716.48 |  | 4716.48 |  |  | 4716.48 | 11775 | -7058.52 | 2021-05-26 08:31 | 2022-09-30 | 2021-06-01 | 2022-09-30
75080 | FPIT | LTHCESCS | WO Optimization Work Input/Call-SW | 9578.2 |  | 9578.2 |  |  | 9578.2 | 27500 | -17921.8 | 2021-02-25 18:39 | 2022-03-31 | 2021-02-01 | 2021-03-31
75080 | FPIT | 400055011 | Engage Maps | 2175.06 |  | 2175.06 |  |  | 2175.06 | 3153 | -977.94 | 2021-10-15 15:54 | 2022-03-31 | 2021-11-01 | 2022-03-31
75080 | RESBLDKY | KMW100007 | Water Heater Replacement | -1765.04 |  | -1765.04 |  |  | 17526.7 | 21250 | -3723.3 | 2018-11-14 15:55 | 2019-07-14 | 2018-12-01 | 2019-03-14
75080 | RESBLDKY | KMW477910 | Electronic furniture assembly | -481.44 |  | -481.44 |  |  | 2517.92 | 2615 | -97.08 | 2018-06-14 14:47 | 2018-12-14 | 2018-09-01 | 2018-12-17
75080 | RESBLDKY | KMW498659 | Envision Center Compressor Replacem | -1154.91 |  | -1154.91 |  |  | 8663.11 | 10419 | -1755.89 | 2018-08-16 15:54 | 2019-03-15 | 2018-11-01 | 2018-11-30
75080 | RESBLDKY | KMW190104 | Augustine Complete Roofing Replace | -105284.66 |  | -105284.66 |  |  | 1153356.68 | 1284525 | -131168.32 | 2019-04-23 14:51 | 2020-04-30 | 2019-05-01 | 2020-02-26
75080 | RESBLDKY | KMW200162 | Erlanger Ops Center LED Lighting | 9155.77 |  | 9155.77 |  |  | 113437.81 | 117892 | -4454.19 | 2020-10-08 11:05 | 2021-03-31 | 2020-11-01 | 2021-03-31
75080 | RESBLDKY | KMW190103 | Erlanger Ops Center Paving P-3 | -24984.7 |  | -24984.7 |  |  | 263117.13 | 73343 | 189774.13 | 2019-05-01 12:20 | 2020-01-29 | 2019-05-01 | 2020-01-31
75080 | RESBLDKY | KMW3CEB80 | Erlanger Ops Center Renovation | 23897.48 |  | 23897.48 |  |  | 23897.48 | 9223169 | -9199271.52 | 2021-02-03 10:15 | 2023-11-08 | 2021-02-01
75080 | RESBLDKY | KMW200218 | Erlanger Crew Room HVAC Replacement | -1087.52 |  | -1087.52 |  |  | 6377.2 | 8708 | -2330.8 | 2020-06-03 11:58 | 2021-03-15 | 2020-07-01 | 2020-07-01
75080 | RESBLDKY | KMW200113 | Erlanger Ops Sit to stand assemblie | -2067.54 |  | -2067.54 |  |  | 13020.59 | 13225 | -204.41 | 2020-03-06 13:46 | 2020-09-13 | 2020-07-01 | 2020-09-24
75080 | RESBLDKY | KMW200089 | Augustine Ops Outdoor Lighting | 9744.23 |  | 9744.23 |  |  | 58932.88 | 78603 | -19670.12 | 2020-08-03 12:50 | 2021-03-31 | 2020-10-01 | 2021-03-17
75080 | RESBLDKY | KMW200027 | Erlanger Exhaust Replacement | -250.3 |  | -250.3 |  |  | 1151.54 | 7269 | -6117.46 | 2020-02-05 08:21 | 2020-10-30 | 2020-02-01 | 2020-05-19
75080 | RESBLDKY | KMW190074 | Erlanger HVAC System Replacement | -1079.36 |  | -1079.36 |  |  | 6397.99 | 7694 | -1296.01 | 2019-03-07 16:11 | 2019-12-03 | 2019-03-01 | 2019-07-17
75080 | RESBLDKY | KMW190251 | Erlanger Transformer Screenwall Rep | -1006.51 |  | -1006.51 |  |  | 26208.66 | 33851 | -7642.34 | 2020-01-15 13:57 | 2020-10-03 | 2020-01-01 | 2020-09-19
75080 | RESBLDKY | KMW200161 | Erlanger Ops Center Façade | -391.65 |  | -391.65 |  |  | 207298.87 | 251411 | -44112.13 | 2020-09-15 10:50 | 2021-06-29 | 2020-10-01 | 2021-04-30
75080 | RESBLDKY | KMW190359 | Erlanger Transformer Replacement | -1381.3 |  | -1381.3 |  |  | 5962.39 | 7528 | -1565.61 | 2019-08-02 09:02 | 2020-03-29 | 2019-12-01 | 2020-01-30
75080 | RESBLDKY | KMW3F3417 | Fire Main Replacement | 99319.68 |  | 99319.68 |  |  | 99319.68 | 130480 | -31160.32 | 2021-09-20 08:53 | 2022-03-31 | 2021-09-01 | 2022-03-21
75080 | RESBLDKY | KMW000182 | Complete Furniture Assemby | -443.35 |  | -443.35 |  |  | 9865.52 | 9791 | 74.52 | 2019-04-09 10:58 | 2019-10-12 | 2019-06-01 | 2019-08-20
75080 | RESBLDKY | KMW000106 | Electronic furniture assembly | -489.83 |  | -489.83 |  |  | 2551.01 | 2604 | -52.99 | 2019-01-11 14:27 | 2019-07-17 | 2019-03-01 | 2019-05-08
75080 | RESBLDKY | KMW200266 | Erlanger Ice Machine Replacement | -1408.52 |  | -1408.52 |  |  | 9491.02 | 11664 | -2172.98 | 2020-07-07 15:31 | 2021-03-15 | 2020-09-01 | 2020-12-01
75080 | RESBLDKY | KMW211076 | HVAC Replacement | 485.61 |  | 485.61 |  |  | 485.61 | 12463 | -11977.39 | 2021-12-02 10:05 | 2022-04-07 | 2021-12-01 | 05/24/2022
75080 | CAPBUDK | GPACCRUAL | Midwest Vacation Accrual | 44618.99 |  | 44618.99 |  |  | 44618.99 | 1 | 44617.99 | 2021-03-18 08:47 | 2051-03-31 | 2021-03-01
75080 | FLKY0249G | DKETKYE21 | Fleet On-Road Vehicles-Elec-KY | 9106.53 |  | 9106.53 |  |  | 9106.53 | 1 | 9105.53 | 2021-01-25 11:10 | 2021-12-31 | 2021-11-01 | 2022-03-31
75080 | FLKY0249G | DUKTKYE20 | Fleet Off-Road Vehicles - KY | -81623 |  | -81623 |  |  | 21049.55 | 100000 | -78950.45 | 2019-11-07 12:58 | 2020-12-31 | 2020-12-01 | 2021-03-31
75080 | FLKY0249G | DKETKYE20 | DKETKYE19 | 87540.67 |  | 87540.67 |  |  | 273504.65 | 1 | 273503.65 | 2020-03-02 15:34 | 2020-12-31 | 2020-12-01 | 2021-03-31
75080 | ASSETCPAK | CPADEK | DEK Capital CPA ALLOCATION | 5926.93 |  | 5926.93 |  |  | 6738.89 | 1 | 6737.89 | 2018-01-31 08:58 | 2050-12-31 | 2018-03-01
75080 | SG001010F | SG1010Z1L | DEK LMR - Ohio/Kentucky - Erlanger | 452523.5 |  | 452523.5 |  |  | 1541980.61 | 5597208.53 | -4055227.92 | 2019-11-01 12:38 | 2024-03-31 | 2019-11-01
75080 | SG001010F | SG1010Z1O | DEK LMR - Ohio/Kentucky - Erlanger | 138078.09 |  | 138078.09 |  |  | 357389.4 | 1399302.13 | -1041912.73 | 2019-11-01 12:28 | 2024-03-31 | 2019-11-01
75080 | SG001010F | SG1010B2T | DEM LMR Towers and Shelters | 73051.42 |  | 73051.42 |  |  | 85146.45 | 1777260 | -1692113.55 | 2020-04-24 09:32 | 2021-09-01 | 2020-06-01 | 2021-09-03
75080 | CAMERA20 | CAMERADEK | Security Cameras | -40464.91 |  | -40464.91 |  |  | 344689.12 | 300000 | 44689.12 | 2020-01-21 13:41 | 2025-12-31 | 2020-04-01
75080 | MRTP2020 | 400019004 | Cambium Work for Kentucky | 16699.96 |  | 16699.96 |  |  | 31399.91 | 15407 | 15992.91 | 2020-11-10 09:33 | 2021-10-30 | 2020-11-01 | 2021-10-31
75080 | DVV2020 | 400019001 | SD-WAN Pilot at multiple Midwest Lo | 13721.19 |  | 13721.19 |  |  | 26855.12 | 19737 | 7118.12 | 2020-06-23 15:08 | 2021-03-15 | 2020-07-01 | 2021-03-17
75080 | GENERIC | INCENTIVE | Incentive True-up | -194417.63 |  | -194417.63 |  |  | 499083.57 | 0 | 499083.57 | 2019-11-22 10:36 | 2050-12-31 | 2019-11-01
75080 | DVV2021 | 400052001 | 2021 Cisco EOL Device Replacement | 84738.99 |  | 84738.99 |  |  | 84738.99 | 1367991 | -1283252.01 | 2021-01-06 10:53 | 2022-03-31 | 2021-02-01 | 2022-06-30
75080 | TOOLFA2 | BKYTOOL | Tool & Equipment Purchases - DEK | 55589.31 |  | 55589.31 |  |  | 62821.03 | 50000 | 12821.03 | 2020-02-20 11:35 | 2050-12-31 | 2020-04-01
75080 | MRTP2021 | 400052002 | Space Link satelite technology - KY | 6504.99 |  | 6504.99 |  |  | 6504.99 | 29783 | -23278.01 | 2021-07-06 13:42 | 2022-06-30 | 2021-09-01 | 2022-06-30
75081 | PCTAIT218 | AIT21808S | FSO Forecasting Consolidation | 562.13 |  | 562.13 |  |  | -1.4552e-13 | 37846.81 | -37846.81 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081 | PCTAIT218 | AIT21808H | FSO Forecasting Consolidation | 13.43 |  | 13.43 |  |  | 1.1213e-14 | 1518.46 | -1518.46 | 2014-04-17 | 2015-12-31 | 2014-06-01 | 2016-03-31
75081 | FPITF | IT2000019 | Mobile Component Assessment Applica | 17850.7 |  | 17850.7 |  |  | 26893.15 | 12415 | 14478.15 | 2020-06-09 15:59 | 2022-07-30 | 2020-06-01 | 2022-07-31
75081 | FPITF | IT2000050 | NERC GADS Reporting Platform | 6459.84 |  | 6459.84 |  |  | 8886.73 | 6625 | 2261.73 | 2020-07-22 11:43 | 2021-12-30 | 2020-08-01 | 2021-12-20
75081 | FPITF | IT1900022 | TWI Welding Qualifier Appl | 14.03 |  | 14.03 |  |  | 1710.12 | 3096 | -1385.88 | 2019-08-15 13:50 | 2020-08-29 | 2020-01-01 | 2020-07-27
75081 | FPITF | IT190HW22 | TWI Welding Qualifier Application | -14.08 |  | -14.08 |  |  | 2.1164e-16 | 660 | -660 | 2019-08-20 11:36 | 2020-08-29 | 2020-03-01 | 2020-07-27
75081 | EB021409 | EB021409X | U2 Lime Injection System | 3807.04 |  | 3807.04 |  |  | 21299726.13 | 20857179.62 | 442546.51 | 2016-05-16 11:48 | 2020-04-30 | 2016-05-01 | 2020-06-24
75081 | EB020740 | EB020740X | Replace Vertimill Heat Exchanger | 452082.5 |  | 452082.5 |  |  | 4218191.59 | 3785702.06 | 432489.53 | 2019-06-26 13:32 | 2021-06-30 | 2019-08-01 | 2021-06-30
75081 | EB020676 | EB020676X | Replace 480V Head Boat Power Feed | -9193.46 |  | -9193.46 |  |  | 123023.82 | 201016.65 | -77992.83 | 2019-08-16 10:31 | 2020-01-15 | 2019-09-01 | 2020-03-06
75081 | EB1912 | CEBVLV21 | 2021 Misc Valve Blanket | 486768.52 |  | 486768.52 |  |  | 709125.03 | 586829.72 | 122295.31 | 2020-12-14 10:40 | 2022-03-31 | 2020-12-01
75081 | EB1912 | CEBVLV20 | 2020 Misc Valve Blanket | 13173.58 |  | 13173.58 |  |  | 590712.31 | 584721.92 | 5990.39 | 2019-11-12 11:51 | 2021-03-31 | 2019-12-01
75081 | EB020680 | EB020680X | Evergreen Upgrade | 3606817.83 |  | 3606817.83 |  |  | 4774856.88 | 4926682.82 | -151825.94 | 2020-09-28 13:02 | 2021-12-31 | 2020-10-01 | 2022-03-25
75081 | EB020813 | CEB020813 | SmartGen EBS XFMR IR Monitoring | 356.78 |  | 356.78 |  |  | 86028.53 | 114305.77 | -28277.24 | 2019-03-18 15:37 | 2022-12-31 | 2019-07-01
75081 | EB021379 | EB021379X | Replace GEN/GSU/UAT Prot Relays | 1043853.94 |  | 1043853.94 |  |  | 1229446.54 | 1263954.92 | -34508.38 | 2020-05-05 07:34 | 2022-02-28 | 2020-05-01 | 2022-03-25
75081 | EB020350 | EB020350X | Underground Fuel Oil Day Tank (EF) | 2405635 |  | 2405635 |  |  | 4306747.22 | 4265539.18 | 41208.04 | 2019-11-25 10:02 | 2022-02-21 | 2019-12-01 | 2022-03-25
75081 | EBS01265 | EBS01265X | FGD to WSP Ug Prcs Pipe Repl (EF | 12082.11 |  | 12082.11 |  |  | 3625883.02 | 4122675.36 | -496792.34 | 2019-10-15 15:54 | 2020-12-30 | 2019-10-01 | 2021-01-22
75081 | EB021600 | EB021600X | 2-2 CT Motor and Gearbox Repl | 285619.45 |  | 285619.45 |  |  | 346266.42 | 317922.86 | 28343.56 | 2020-12-29 15:02 | 2021-07-09 | 2020-12-01 | 2021-07-13
75081 | EB021162 | EB021162X | Economizer Expansion Joint | 185311.4 |  | 185311.4 |  |  | 197564.12 | 164533.23 | 33030.89 | 2019-12-18 13:13 | 2022-02-28 | 2020-01-01 | 2022-02-01
75081 | EB020566 | CEB020566 | PSM Safe Havens - East Bend U2 | 32700.23 |  | 32700.23 |  |  | 670563.31 | 542839.75 | 127723.56 | 2019-09-05 08:01 | 2021-08-30 | 2019-09-01 | 2021-09-24
75081 | EB021161 | EB021161X | SCR Expansion Joints | 311238.73 |  | 311238.73 |  |  | 340839.89 | 390055.54 | -49215.65 | 2019-12-18 12:53 | 2022-02-28 | 2020-01-01 | 2022-02-01
75081 | EB021754 | EB021754X | Transformer 2A Cooling Fans Rep | 3975.53 |  | 3975.53 |  |  | 3975.53 | 4703.06 | -727.53 | 2021-05-07 08:26 | 2021-12-31 | 2021-06-01 | 2022-02-15
75081 | EB021160 | EB021160X | Stack Expansion Joint | 1102.9 |  | 1102.9 |  |  | 304849.21 | 275706.1 | 29143.11 | 2019-12-18 12:16 | 2021-03-31 | 2020-01-01 | 2021-02-20
75081 | EB020890 | EB020890X | Generator Stator Rewind | 10944518 |  | 10944518 |  |  | 13615699.64 | 13504143.66 | 111555.98 | 2020-08-06 11:19 | 2022-02-28 | 2020-08-01 | 2022-03-25
75081 | EB020701 | EB020701X | LBU Dust Mitigation | 1285224.61 |  | 1285224.61 |  |  | 1666830.8 | 1656005.53 | 10825.27 | 2019-09-13 09:37 | 2022-02-28 | 2019-11-01 | 2022-03-18
75081 | EB021307 | EB021307X | 2-6 Pulv Roll Wheel Repl | 670456.92 |  | 670456.92 |  |  | 1114481.17 | 1197370.95 | -82889.78 | 2020-12-29 14:38 | 2021-12-31 | 2020-12-01 | 2022-03-25
75081 | EB021371 | EB021371X | SMARTGEN-EBS U2 T/G VIB MONITOR EOL | 428.86 |  | 428.86 |  |  | 428.86 | 34661.94 | -34233.08 | 2021-05-20 13:35 | 2023-12-31 | 2021-06-01
75081 | EB021752 | EB021752X | Turbine Ventilating Valve SV-2 | 93714.44 |  | 93714.44 |  |  | 93714.44 | 68851.4 | 24863.04 | 2021-05-18 10:36 | 2021-12-30 | 2021-05-01 | 2022-03-26
75081 | EB021386 | EB021386X | LPA Turbine L-0 & L-1 Blades | 1398.31 |  | 1398.31 |  |  | 4225479.13 | 4773416.17 | -547937.04 | 2020-03-11 12:08 | 2021-02-16 | 2020-03-01 | 2021-02-20
75081 | EB021787 | EB021787X | WSP Cake Transfer Conveyor Belt Rep | 33260.64 |  | 33260.64 |  |  | 33260.64 | 24421.3 | 8839.34 | 2021-08-30 08:26 | 2022-02-21 | 2021-10-01 | 2022-03-25
75081 | EB020826 | EB020826X | Replace Flame Scanners & Igniters | 700601.69 |  | 700601.69 |  |  | 700601.69 | 707956.32 | -7354.63 | 2020-12-07 08:55 | 2022-02-28 | 2021-01-01 | 2022-03-25
75081 | EB020879 | EB020879X | Repl 2-4 CT Fan Brkr Arc Flash Mitg | 54376.93 |  | 54376.93 |  |  | 89348.66 | 155881.11 | -66532.45 | 2020-12-18 12:48 | 2021-12-31 | 2020-12-01 | 2022-03-25
75081 | EB020392 | EB020392X | HCAD Repl Crusher to F Conv Chute | 3574.32 |  | 3574.32 |  |  | 584919.69 | 1154709.74 | -569790.05 | 2019-12-18 11:20 | 2021-03-07 | 2019-12-01 | 2021-02-20
75081 | EB021450 | EB021450X | Replace CRW Tank | -63099.94 |  | -63099.94 |  |  | 1020365.05 | 986809.52 | 33555.53 | 2019-10-15 16:30 | 2021-06-22 | 2019-10-01 | 2021-02-19
75081 | EB020818 | EB020818X | FGD Biocide System H2S Mitigation | 84668.18 |  | 84668.18 |  |  | 237147.2 | 203174.91 | 33972.29 | 2020-07-01 14:25 | 2022-09-30 | 2020-07-01 | 2022-09-15
75081 | EB021309 | EB021309X | 2-3 Pulv Roll Wheel Repl 2020 | 1902.2 |  | 1902.2 |  |  | 790140.29 | 901595.47 | -111455.18 | 2019-12-18 13:57 | 2021-05-11 | 2019-12-01 | 2021-02-21
75081 | EB021598 | EB021598X | LPA and LPB L-2 Blade Replacement | 3520575.74 |  | 3520575.74 |  |  | 4011485.24 | 4499980.22 | -488494.98 | 2020-12-18 15:58 | 2022-02-28 | 2020-12-01 | 2022-03-25
75081 | EB021772 | EB021772X | 2-2 PA Outlet Damper Cable Replace | 12960.96 |  | 12960.96 |  |  | 12960.96 | 18879.68 | -5918.72 | 2021-06-30 07:28 | 2022-02-19 | 2021-08-01 | 2022-03-25
75081 | EB021589 | 8SFYTOOLS | Entp High Risk Tool - FHO DEK Coal | 2923.65 |  | 2923.65 |  |  | 3897.29 | 1155.68 | 2741.61 | 2020-10-20 16:21 | 2022-06-30 | 2020-11-01 | 2022-08-05
75081 | EB020901 | EB020901X | WSP 2ST1 6.9KV Transformer Repl | -83283.99 |  | -83283.99 |  |  | 126133.76 | 139429.55 | -13295.79 | 2018-12-27 11:50 | 2021-07-30 | 2019-05-01 | 2021-08-18
75081 | EB021785 | EB021785X | Replace IK Sootblower | 34208.09 |  | 34208.09 |  |  | 34208.09 | 45209.18 | -11001.09 | 2021-07-12 09:35 | 2022-11-30 | 2021-12-01 | 2022-12-06
75081 | EB021743 | EB021743X | 2-1 SBAC 2nd Stage Cooler Replace | 54611.15 |  | 54611.15 |  |  | 54611.15 | 51450.35 | 3160.8 | 2021-03-29 12:23 | 2021-04-23 | 2021-03-01 | 2021-06-29
75081 | EB021789 | EB021789X | 2021 CBU Inshore Ladder Head Shaft | 237880.68 |  | 237880.68 |  |  | 237880.68 | 301706.69 | -63826.01 | 2021-08-30 09:05 | 2022-02-10 | 2021-09-01 | 2022-03-01
75081 | EB021813 | EB021813X | Main Oil Tank Earthen Berm Liner | 256509.11 |  | 256509.11 |  |  | 256509.11 | 383562 | -127052.89 | 2021-12-10 10:31 | 2022-03-31 | 2021-12-01 | 2022-02-25
75081 | EB021761 | EB021761X | 2A-3 Absorber Motor Stator Rewind | 62629.62 |  | 62629.62 |  |  | 62629.62 | 67462.04 | -4832.42 | 2021-06-15 11:16 | 2021-07-30 | 2021-06-01 | 2021-09-15
75081 | EB021751 | EB021751X | Physical Lock Pilot | 153489.47 |  | 153489.47 |  |  | 153489.47 | 216857.16 | -63367.69 | 2021-05-07 07:34 | 2022-11-30 | 2021-06-01 | 2022-11-08
75081 | EB021763 | EB021763X | Repl SCR Sonic Horn Air Compressor | 18050.38 |  | 18050.38 |  |  | 18050.38 | 14352.65 | 3697.73 | 2021-05-18 11:26 | 2021-12-31 | 2021-06-01 | 2022-03-25
75081 | EB020084 | EB020084X | Retire FGD Reheat Fan | -0.52 |  | -0.52 |  |  | 1.0214e-14 | 0 | 1.0214e-14 | 2017-10-13 12:05 | 2019-05-31 | 2019-01-01 | 2019-06-29
75081 | EB021794 | EB021794X | 2-1 & 2-2 PA Fan Shafts | 204435.29 |  | 204435.29 |  |  | 204435.29 | 186816.31 | 17618.98 | 2021-09-29 09:48 | 2022-01-31 | 2021-10-01 | 2022-03-26
75081 | EB021199 | EB021199X | WSP 2ST2 6.9KV Transformer Repl | 84500.9 |  | 84500.9 |  |  | 84500.9 | 185057.23 | -100556.33 | 2021-10-26 15:05 | 2022-06-30 | 2021-10-01 | 2022-07-25
75081 | EB021722 | EB021722X | North Thickener Tank Replacement | 37159.5 |  | 37159.5 |  |  | 37159.5 | 2672404.4 | -2635244.9 | 2021-10-08 15:33 | 2022-12-31 | 2021-10-01
75081 | CEB02DITC | CCEB2DITC | East Bend Ditch Liner | 6099.01 |  | 6099.01 |  |  | 171413.12 | 175000 | -3586.88 | 2020-11-25 11:33 | 2021-03-31 | 2020-12-01 | 2021-02-28
75081 | EB021720 | EB021720X | Repl 2-2 Fly Ash Exhauster Blower | 39560.12 |  | 39560.12 |  |  | 39560.12 | 46365.49 | -6805.37 | 2021-03-29 11:36 | 2021-06-12 | 2021-03-01 | 2021-06-29
75081 | CEBASPHLT | CCEBASPHL | CCP East Bend Asphalt Installation | 805924.99 |  | 805924.99 |  |  | 805924.99 | 783044.71 | 22880.28 | 2021-06-21 17:24 | 2021-12-31 | 2021-09-01 | 2022-01-01
75081 | EB021771 | EB021771X | MSP FP Fire Reel and Enclosure Repl | 30992.38 |  | 30992.38 |  |  | 30992.38 | 28549.66 | 2442.72 | 2021-06-15 10:23 | 2021-12-31 | 2021-12-01 | 2022-03-21
75081 | EB021799 | EB021799X | 2A & 2C Module Outlet Exp Jnt | 18351.66 |  | 18351.66 |  |  | 18351.66 | 59085.12 | -40733.46 | 2021-10-26 15:18 | 2022-12-31 | 2021-12-01 | 2023-02-03
75081 | EB021748 | EB021748X | 2-2 WSP Vacuum Pmp Repl (SM) | 57231.4 |  | 57231.4 |  |  | 57231.4 | 55288.34 | 1943.06 | 2021-04-21 10:33 | 2021-07-30 | 2021-04-01 | 07/14/2021
75081 | EB021815 | EB021815X | Main & Neutral Flex Link Repl | 215709.69 |  | 215709.69 |  |  | 215709.69 | 187389.6 | 28320.09 | 2021-12-21 10:46 | 2022-03-31 | 2021-12-01 | 03/25/2022
75081 | EB021823 | EB021823X | Governor Valve Repl 2021 | 327101.1 |  | 327101.1 |  |  | 327101.1 | 292616.54 | 34484.56 | 2021-12-27 09:00 | 2022-03-31 | 2021-12-01 | 03/25/2022
75082 | FPITF | 323123DKT | GenVision- FHO Data Analytics | -60824 |  | -60824 |  |  | 32753.01 | 68016 | -35262.99 | 2017-12-21 13:54 | 2020-03-28 | 2018-01-01 | 2020-10-30
75082 | FPITF | IT2000019 | Mobile Component Assessment Applica | 13376.24 |  | 13376.24 |  |  | 20183.29 | 9292 | 10891.29 | 2020-06-09 16:08 | 2022-07-30 | 2020-06-01 | 2022-07-31
75082 | FPITF | 2000001 | 2020 End of Life Replacement | -17.31 |  | -17.31 |  |  | 8277.81 | 11843 | -3565.19 | 2020-05-08 12:10 | 2021-03-31 | 2020-07-01 | 2021-03-09
75082 | FPITF | IT2000050 | NERC GADS Reporting Platform | 4833.62 |  | 4833.62 |  |  | 6649.9 | 4958 | 1691.9 | 2020-07-22 11:49 | 2021-12-30 | 2020-08-01 | 2021-12-20
75082 | FPITF | IT2100019 | 2021 Server EOL | 8370.54 |  | 8370.54 |  |  | 8370.54 | 12191 | -3820.46 | 2021-03-11 09:43 | 2022-03-31 | 2021-03-01 | 2021-08-11
75082 | WDC00004 | WDC00004X | Install Fuel Oil System - BOP | 124228.15 |  | 124228.15 |  |  | 28061157.57 | 25801931.95 | 2259225.62 | 2016-08-22 15:04 | 2019-07-01 | 2016-08-01 | 2019-07-05
75082 | WD040012 | WD040012X | WGS U4 Generator Rotor Rewind | -49906.66 |  | -49906.66 |  |  | 1498210.7 | 1555038.42 | -56827.72 | 2017-11-13 10:54 | 2018-05-15 | 2017-11-01 | 2018-05-27
75082 | WD050008 | WD050008X | OPTIM U5 Gen Field Rewind | 865229.96 |  | 865229.96 |  |  | 1195808.96 | 1200566.34 | -4757.38 | 2020-11-30 11:18 | 2021-12-30 | 2020-12-01 | 2021-08-27
75082 | WD060010 | WD060010X | OPTIM U6 Gen Field Rewind | 966818.48 |  | 966818.48 |  |  | 1297397.48 | 1195758.31 | 101639.17 | 2020-11-30 11:44 | 2022-12-30 | 2020-12-01 | 2021-09-07
75082 | WD010053 | WD010053X | SMARTGEN-WDC U1 T/G VIB MONITOR EOL | 219.44 |  | 219.44 |  |  | 219.44 | 6824.07 | -6604.63 | 2021-05-18 08:46 | 2023-12-31 | 2021-06-01
75082 | WG048C | CWDVLV21 | 2021 Miscellaneous Valves (GMA) | 36587.69 |  | 36587.69 |  |  | 36587.69 | 44961 | -8373.31 | 2021-02-04 13:34 | 2022-03-30 | 2021-06-01
75082 | WD060018 | WD060018X | SMARTGEN-WDC U6 T/G VIB MONITOR EOL | 204.04 |  | 204.04 |  |  | 204.04 | 6824.07 | -6620.03 | 2021-05-18 09:57 | 2023-12-31 | 2021-06-01
75082 | WD040020 | WD040020X | SMARTGEN-WDC U4 T/G VIB MONITOR EOL | 139.34 |  | 139.34 |  |  | 139.34 | 6824.07 | -6684.73 | 2021-05-18 09:43 | 2023-12-31 | 2021-06-01
75082 | WD010059 | WD010059I | WD01 Emergent Outage-(Ins Claim) | -3309702.14 |  | -3309702.14 |  |  | -3309702.14 | -3316763.51 | 7061.37 | 2021-09-21 07:19 | 2021-11-15 | 2021-09-01 | 2021-11-19
75082 | WD010059 | WD010059X | WD01 Emergent Outage-June/July 2021 | 4621533.8 |  | 4621533.8 |  |  | 4621533.8 | 5144120.41 | -522586.61 | 2021-08-11 09:09 | 2021-11-15 | 2021-08-01 | 2021-11-19
75082 | WD020008 | WD020008X | U2 AA Module HVAC Replacement | 1229.65 |  | 1229.65 |  |  | 1229.65 | 30620.34 | -29390.69 | 2021-09-23 12:50 | 2022-06-04 | 2021-09-01 | 2022-05-25
75082 | WD030013 | WD030013X | SMARTGEN-WDC U3 T/G VIB MONITOR EOL | 149.74 |  | 149.74 |  |  | 149.74 | 6824.07 | -6674.33 | 2021-05-18 09:33 | 2023-12-31 | 2021-06-01
75082 | WDC00053 | WDC00053X | Replace Transformer Annunciators | 52211.09 |  | 52211.09 |  |  | 52211.09 | 44029.61 | 8181.48 | 2021-06-22 07:12 | 2022-02-15 | 2021-06-01 | 2022-01-25
75082 | WD050019 | WD050019X | SMARTGEN-WDC U5 T/G VIB MONITOR EOL | 149.74 |  | 149.74 |  |  | 149.74 | 6824.07 | -6674.33 | 2021-05-18 09:51 | 2023-12-31 | 2021-06-01
75082 | WDCM0055 | WDCM0055X | Repl Demin Acid Tank Outlet Pipelin | 3142.88 |  | 3142.88 |  |  | 22495.12 | 27972 | -5476.88 | 2020-12-15 07:57 | 2021-02-28 | 2020-12-01 | 2021-03-03
75082 | WD060017 | WD060017X | IPB Phases B & C Replacement | 246264.34 |  | 246264.34 |  |  | 552403.07 | 573108.58 | -20705.51 | 2020-12-21 14:31 | 2021-08-07 | 2020-12-01 | 2021-08-10
75082 | WD020021 | WD020021X | SMARTGEN-WDC U2 T/G VIB MONITOR EOL | 225.73 |  | 225.73 |  |  | 225.73 | 6824.07 | -6598.34 | 2021-05-18 09:21 | 2023-12-31 | 2021-06-01
75082 | WDCM0069 | WDCM0069X | Chemical Curtain | 10357.63 |  | 10357.63 |  |  | 10357.63 | 16818.35 | -6460.72 | 2021-09-23 13:57 | 2022-03-10 | 2021-09-01 | 2022-03-06
|  |  |  | 95806859.09 | 107957721.2346 | 12150862.1446 | 11.26%

## 2022
Duke Energy Kentucky Electric
Year 2022
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75085 | CUSTCONN | 400109 | 400109 - CUST ENHANCEMENT AND OPTIMIZATION | 182768.54 |  | 182768.54 |  |  | 182768.54 | 685559 | -502790.46 | 2022-06-20 14:22 | 2024-01-19 | 2022-07-01 | 2024-01-26
75085 | FPIT | 307482002 | 307482002 - CUSTOMER MOBILE APP - PHASE 3 | -0.25 |  | -0.25 |  |  | 4457.02 | 37822 | -33364.98 | 2019-12-19 13:47 | 2022-03-15 | 2020-01-01 | 2022-03-31
75080 | FPIT | 307482003 | 307482003 - CUSTOMER MOBILE APP - PHASE 4 | 47361.96 |  | 47361.96 |  |  | 47361.96 | 49782 | -2420.04 | 2021-12-30 09:25 | 2023-03-31 | 2022-01-01 | 2023-03-31
75084 | FPIT | 346954001 | 346954001 - ISOP GRANULAR FORECASTING | 86157.43 |  | 86157.43 |  |  | 347245.66 | 572625 | -225379.34 | 2018-05-14 11:31 | 2025-03-31 | 2018-05-01 | open
75080 | FPIT | 349395006 | 349395006 - ITOT OT SIEM PHASE 2 HW WORKSTREAM | 13708.97 |  | 13708.97 |  |  | 42499.72 | 5497 | 37002.72 | 2020-04-03 15:02 | 2022-10-28 | 2020-05-01 | 2022-10-18
75084 | EAMHPBU | 349472008 | 349472008 - EAM 2021 MAXIMO DURABLE TEAM | 799.7 |  | 799.7 |  |  | 12357.54 | 13541 | -1183.46 | 2021-01-22 15:03 | 2022-05-30 | 2021-02-01 | 2022-08-15
75084 | EAMHPBU | 349472009 | 349472009 - NEW EAM 2021 MOBILE DURABLE TEAM | 213.59 |  | 213.59 |  |  | 3682.07 | 39130 | -35447.93 | 2021-01-13 12:53 | 2022-05-30 | 2021-02-01 | 2022-08-15
75084 | FPIT | 349472010 | 349472010 - NEW SMALLWORLD STORAGE SERVERS | -0.07 |  | -0.07 |  |  | 2675.73 | 2782 | -106.27 | 2020-12-29 09:01 | 2022-03-31 | 2021-02-01 | 2022-03-31
75084 | FPIT | 349472016 | 349472016 - AUTODESK SUBSCRIPTION AGREEMENT | -7.57 |  | -7.57 |  |  | 23562.94 | 23607 | -44.06 | 2021-10-29 14:46 | 2022-03-20 | 2021-11-01 | 2022-03-20
75084 | EAMHPBU | 349472018 | 349472018 - EAM 2022 MAXIMO DURABLE TEAM | 16069.81 |  | 16069.81 |  |  | 16069.81 | 13250 | 2819.81 | 2022-01-04 15:40 | 2023-05-30 | 2022-01-01 | 2023-07-17
75084 | FPIT | 349472020 | 349472020 - SLATE - EAM WORK MGMT SCHEDULING TO | 16804.69 |  | 16804.69 |  |  | 16804.69 | 44680 | -27875.31 | 2022-03-18 16:07 | 2024-06-30 | 2022-03-01 | 2024-06-30
75084 | FPIT | 349472021 | 349472021 - FMA ENHANCEMENTS | 4326.53 |  | 4326.53 |  |  | 4326.53 | 9426 | -5099.47 | 2022-05-18 12:21 | 2025-03-31 | 2022-06-01 | open
75084 | FPIT | 349472023 | 349472023 - SMALLWORLD ENHANCEMENTS | 1810.17 |  | 1810.17 |  |  | 1810.17 | 8782 | -6971.83 | 2022-09-29 18:15 | 2025-03-30 | 2022-11-01 | 2024-03-31
75084 | FPIT | 349472024 | 349472024 - NEW PRIMAVERA OAM SERVERS | 74.86 |  | 74.86 |  |  | 74.86 | 345 | -270.14 | 2022-09-29 16:22 | 2023-08-08 | 2022-10-01 | 2023-08-08
75080 | FPIT | 359140001 | 359140001 - ISOP DATA MANAGEMENT | 11068.9 |  | 11068.9 |  |  | 129941.38 | 289733 | -159791.62 | 2018-12-19 15:02 | 2024-02-15 | 2019-01-01 | 2024-02-17
75080 | MRTP2020 | 400019004 | 400019004 - CAMBIUM WORK FOR KENTUCKY | 8.57 |  | 8.57 |  |  | 31408.48 | 15407 | 16001.48 | 2020-11-10 09:33 | 2021-10-30 | 2020-11-01 | 2021-10-31
75084 | DVV2021 | 400051013 | 400051013 - CIP-012 OHIO/KY | 17044.86 |  | 17044.86 |  |  | 33688.72 | 91312 | -57623.28 | 2021-06-18 17:14 | 2024-03-31 | 2021-06-01 | 2024-01-31
75080 | DVV2021 | 400052001 | 400052001 - 2021 CISCO EOL DEVICE REPLACEMENT | -3812.05 |  | -3812.05 |  |  | 80926.94 | 1367991 | -1287064.06 | 2021-01-06 10:53 | 2022-03-31 | 2021-02-01 | 2022-06-30
75080 | MRTP2021 | 400052002 | 400052002 - SPACE LINK SATELITE TECHNOLOGY - KY | 80.72 |  | 80.72 |  |  | 6585.71 | 29783 | -23197.29 | 2021-07-06 13:42 | 2022-06-30 | 2021-09-01 | 2022-06-30
75080 | FPIT | 400055002 | 400055002 - CHATBOT CHANNELS | 11.87 |  | 11.87 |  |  | 12809.22 | 12437 | 372.22 | 2020-12-08 09:28 | 2022-03-31 | 2021-01-01 | 2022-03-31
75080 | FPIT | 400055004 | 400055004 - INSPECTION PORTAL 2021 | 18633.05 |  | 18633.05 |  |  | 18633.05 | 21453 | -2819.95 | 2020-12-16 11:28 | 2023-07-03 | 2022-01-01 | 2023-07-31
75080 | FPIT | 400055005 | 400055005 - BUILDER PORTAL 2021 | 11062.95 |  | 11062.95 |  |  | 24401.23 | 35647 | -11245.77 | 2020-12-10 17:46 | 2023-09-30 | 2021-01-01 | 2023-09-30
75080 | FPIT | 400055007 | 400055007 - USAGE ALERTS | 27865.87 |  | 27865.87 |  |  | 50028.94 | 47004 | 3024.94 | 2021-03-04 16:42 | 2024-03-31 | 2021-03-01 | 2023-03-31
75080 | FPIT | 400055009 | 400055009 - CALL CENTER ANALYTICS SW | 7910.8 |  | 7910.8 |  |  | 12627.28 | 11775 | 852.28 | 2021-05-26 08:31 | 2022-09-30 | 2021-06-01 | 2022-09-30
75080 | FPIT | 400055010 | 400055010 - DIGITAL ASSISTANT PLATFORM PH 1 | 480.25 |  | 480.25 |  |  | 3326.03 | 6670 | -3343.97 | 2021-07-26 14:34 | 2022-03-15 | 2021-10-01 | 2022-03-31
75080 | FPIT | 400055011 | 400055011 - ENGAGE MAPS | 2486.14 |  | 2486.14 |  |  | 4661.2 | 3153 | 1508.2 | 2021-10-15 15:54 | 2022-03-31 | 2021-11-01 | 2022-03-31
75080 | FPIT | 400055012 | 400055012 - OUTAGE ALERTS IMPROVEMENTS | 5479.58 |  | 5479.58 |  |  | 6963.53 | 8909 | -1945.47 | 2021-09-30 09:51 | 2022-03-31 | 2021-10-01 | 2022-03-31
75080 | FPIT | 400055015 | 400055015 - ATLANTIS (CUSTOMER ANALYTICS ENGINE | 25766.78 |  | 25766.78 |  |  | 25766.78 | 45663 | -19896.22 | 2021-12-29 10:29 | 2023-12-30 | 2022-01-01 | 2024-01-01
75080 | FPIT | 400055016 | 400055016 - TITAN (VOICE OF THE CUSTOMER ENGAGE | 15054.06 |  | 15054.06 |  |  | 15054.06 | 22207 | -7152.94 | 2021-12-20 13:20 | 2023-10-31 | 2022-01-01 | 2023-10-31
75080 | FPIT | 400055017 | 400055017 - DIGITAL ASSISTANT PLATFORM 2022 ENH | 29930.17 |  | 29930.17 |  |  | 29930.17 | 30300 | -369.83 | 2021-12-20 10:18 | 2023-06-30 | 2022-01-01 | 2023-07-04
75080 | FPIT | 400055018 | 400055018 - PING IT AUTOMATION 2022 | 23471.23 |  | 23471.23 |  |  | 23471.23 | 33084 | -9612.77 | 2022-02-10 18:02 | 2023-06-30 | 2022-03-01 | 2023-06-30
75080 | FPIT | 400055019 | 400055019 - PING IT 2022 ENHANCEMENTS | 5289.43 |  | 5289.43 |  |  | 5289.43 | 8094 | -2804.57 | 2022-05-24 14:49 | 2023-03-31 | 2022-09-01 | 2023-03-31
75080 | FPIT | 400055020 | 400055020 - SHORT URL MANAGEMENT APP | 16683.71 |  | 16683.71 |  |  | 16683.71 | 14866 | 1817.71 | 2022-03-08 08:35 | 2023-01-15 | 2022-03-01 | 2022-11-15
75080 | FPIT | 400055022 | 400055022 - BUSINESS OUTBOUND NOTIFICATION PLAT | 38.5 |  | 38.5 |  |  | 38.5 | 11897 | -11858.5 | 2022-05-19 11:25 | 2023-03-31 | 2022-10-01 | 2023-03-31
75080 | DVV2022 | 400098001 | 400098001 - 2022 CISCO VIPTELA SDWAN SOLUTION | 112456.73 |  | 112456.73 |  |  | 112456.73 | 30621 | 81835.73 | 2021-11-17 12:35 | 2023-09-30 | 2022-02-01 | 2023-07-25
75080 | DVV2022 | 400098002 | 400098002 - TELECOM NETWORK TRANSFORMATION PROG | 323385.39 |  | 323385.39 |  |  | 323385.39 | 380661 | -57275.61 | 2021-11-17 10:14 | 2023-03-31 | 2022-01-01 | 2023-03-31
75080 | MRTP2022 | 400098003 | 400098003 - TBC- 2022 MRTP PAGING REPLACEMENT | 4918.84 |  | 4918.84 |  |  | 4918.84 | 138775 | -133856.16 | 2021-11-22 14:02 | 2023-03-31 | 2022-01-01 | cancelled
75080 | MRTP2022 | 400098004 | 400098004 - 2022 TELECOM LMR HARRIS RADIO TEST | 45698.48 |  | 45698.48 |  |  | 45698.48 | 54910 | -9211.52 | 2022-05-27 11:22 | 2022-10-28 | 2022-07-01 | 2022-11-08
75080 | FPIT | 400113002 | 400113002 - WORKSTATION REFRESH 2023-2024 | 14945.962 |  | 14945.962 |  |  | 14945.96 | 46939 | -31993.04 | 2022-07-29 09:26 | 2023-03-30 | 2022-08-01 | 2023-04-17
75080 | FPIT | 400113003 | 400113003 - WORKSTATION REFRESH 2023/24 | 41599.84 |  | 41599.84 |  |  | 41599.84 | 46831 | -5231.16 | 2022-12-13 13:19 | 2024-03-28 | 2022-12-01 | 2024-03-31
75080 | FPIT | 307482SW2 | 307482SW2 - CUSTOMER MOBILE APP - PHASE 3 | 396.97 |  | 396.97 |  |  | 53937.61 | 60515 | -6577.39 | 2020-04-13 09:04 | 2022-03-15 | 2020-04-01 | 2022-03-31
75085 | CUSTCONN | 315986A | 315986A - CUSTOMER CONNECT - CORE | 1345676.549 |  | 1345676.549 |  |  | 6465337.35 | 3313201.21 | 3152136.14 | 2017-08-10 10:40 | 2022-12-05 | 2017-08-01 | 2022-07-06
75085 | CUSTCONN | 315986F | 315986F - CUSTOMER CONNECT- R6-8 SCOPE | 265561.61 |  | 265561.61 |  |  | 658811 | 76898 | 581913 | 2021-03-30 10:43 | 2022-06-30 | 2021-04-01 | 2022-07-06
75085 | CUSTCONN | 315986HW7 | 315986HW7 - CUSTOMER CONNECT - HARDWARE PROJ 5 | 11.26 |  | 11.26 |  |  | 41090.37 | 89586 | -48495.63 | 2021-04-21 14:04 | 2021-12-31 | 2021-04-01 | 2021-12-31
75085 | CUSTCONN | 315986HW8 | 315986HW8 - CUSTOMER CONNECT- HARDWARE PROJ 6 | 24426.01 |  | 24426.01 |  |  | 53247.86 | 96250 | -43002.14 | 2021-09-27 15:14 | 2022-06-30 | 2021-10-01 | 2022-09-15
75080 | FPIT | 349395SW6 | 349395SW6 - ITOT OT SIEM SW WORKSTREAM | 265.76 |  | 265.76 |  |  | 17565.21 | 71164 | -53598.79 | 2021-12-01 18:03 | 2022-10-28 | 2021-12-01 | 2022-10-18
75084 | FPIT | 349472S13 | 349472S13 - JUMP APPLICATION | 2028.64 |  | 2028.64 |  |  | 6891.97 | 4607.94 | 2284.03 | 2021-02-08 08:10 | 2022-07-30 | 2021-06-01 | 2022-10-01
75084 | FPIT | 349472S14 | 349472S14 - NEW ESRI INTEGRATIONS AND INFRA | 51387.47 |  | 51387.47 |  |  | 59657.3 | 532359 | -472701.7 | 2021-02-09 12:29 | 2023-11-30 | 2021-03-01 | 2024-03-06
75084 | FPIT | 349472SW6 | 349472SW6 - EAM-SC NEXT GEN MOBILE PLATFORM SW | 7197.36 |  | 7197.36 |  |  | 23732.5 | 24420 | -687.5 | 2020-12-15 20:51 | 2022-07-29 | 2021-01-01 | 2022-09-27
75084 | FARCOSSW | ARCOSSW | ARCOSSW - ARCOS SYSTEM OUTAGE PROJECT | 312.43 |  | 312.43 |  |  | 148211.73 | 129249 | 18962.73 | 2018-06-10 21:10 | 2022-03-31 | 2018-07-01 | 2022-03-31
75084 | RES75084 | ASDEKCD | ASDEKCD - ADMN SVCS BLANKET FOR CUST DEL DEK | 42920.6 |  | 42920.6 |  |  | 42920.6 | 0 | 42920.6 | 2022-07-11 16:31 | 2050-12-31 | 2022-08-01 | open
75080 | RESBLDKY | ASDEKRO | ASDEKRO - ADMN SVCS BLANKET FOR REG OTHER DEK | 528.09 |  | 528.09 |  |  | 528.09 | 0 | 528.09 | 2022-07-11 16:51 | 2050-12-31 | 2022-09-01 | open
75080 | TOOLFA2 | BKYTOOL | BKYTOOL - TOOL & EQUIPMENT PURCHASES - DEK | 7461.45 |  | 7461.45 |  |  | 70282.48 | 50000 | 20282.48 | 2020-02-20 11:35 | 2050-12-31 | 2020-04-01 | open
75080 | FPIT | CC1900001 | CC1900001 - CUSTOMER ANALYTICS ENGINE | 1355.71 |  | 1355.71 |  |  | 58499.05 | 52612 | 5887.05 | 2020-01-27 07:55 | 2022-03-31 | 2020-02-01 | 2022-03-31
75080 | FPIT | CC1900002 | CC1900002 - VEGETATION MANAGEMENT COMMUNICATION | 2972.27 |  | 2972.27 |  |  | 54448.87 | 50641 | 3807.87 | 2020-01-24 17:04 | 2021-10-31 | 2020-03-01 | 2021-10-31
75080 | FPIT | CC2000003 | CC2000003 - SITECORE JSS FRONT END MODERNIZATIO | 7809.28 |  | 7809.28 |  |  | 54446.61 | 57443 | -2996.39 | 2020-06-25 21:05 | 2022-05-30 | 2020-08-01 | 2022-05-31
75080 | FPIT | CC2000005 | CC2000005 - PLANNED OUTAGES PORTAL SW | 4666.37 |  | 4666.37 |  |  | 54685.29 | 48524 | 6161.29 | 2020-10-20 13:20 | 2022-02-28 | 2020-10-01 | 2022-03-10
75082 | KYSC0016 | CCRIC22 | CCRIC22 - INSTRUMENTATION & CONTROLS (GMA) | 3442 |  | 3442 |  |  | 3442 | 7459.2 | -4017.2 | 2022-10-31 13:09 | 2023-03-01 | 2022-10-01 | 2023-03-31
75081 | EB020813 | CEB020813 | CEB020813 - SMARTGEN EBS XFMR IR MONITORING | 3637.25 |  | 3637.25 |  |  | 89665.78 | 114305.77 | -24639.99 | 2019-03-18 15:37 | 2022-12-31 | 2019-07-01 | 2023-01-31
75081 | EB022007 | CEB022007 | CEB022007 - EASTBEND WEST LANDFILL CELL 3 | 11850.25 |  | 11850.25 |  |  | 11850.25 | 22801029 | -22789178.75 | 2022-09-28 09:23 | 2028-12-31 | 2022-11-01 | open
75081 | EB1922 | CEB1922 | CEB1922 - EBS-2 GENERAL EQUIPMENT | 76176.29 |  | 76176.29 |  |  | 2389957.5 | 2211650.74 | 178306.76 | 2005-08-10 | 2028-12-31 | 2008-07-01 | 2001-05-01
75081 | EB022045 | CEBIC22 | CEBIC22 - INSTRUMENTATION & CONTROLS (GMA) | 271188.09 |  | 271188.09 |  |  | 271188.09 | 93970.32 | 177217.77 | 2022-10-31 15:40 | 2023-03-01 | 2022-10-01 | 2023-03-31
75081 | EB1912 | CEBVLV21 | CEBVLV21 - 2021 MISC VALVE BLANKET | 26608.34 |  | 26608.34 |  |  | 735733.37 | 586829.72 | 148903.65 | 2020-12-14 10:40 | 2022-03-31 | 2020-12-01 | open
75081 | EB1912 | CEBVLV22 | CEBVLV22 - 2022 MISC VALVE BLANKET | 541133.62 |  | 541133.62 |  |  | 541133.62 | 451928.08 | 89205.54 | 2022-01-24 12:30 | 2023-03-31 | 2022-03-01 | 2023-03-31
75080 | FPIT | CO2200002 | CO2200002 - UTILITY ASSISTANCE MODERN ARCHITECT | 1670.17 |  | 1670.17 |  |  | 1670.17 | 6593 | -4922.83 | 2022-06-30 10:29 | 2022-12-29 | 2022-07-01 | 2023-03-15
75085 | FPCNTRL | CONTROLS | CONTROLS - SMART CONTROLS SYSTEM MGMT. TOOL | 70547.91 |  | 70547.91 |  |  | 70547.91 | 61125 | 9422.91 | 2022-08-24 14:58 | 2027-03-31 | 2022-08-01 | open
75080 | ASSETCPAK | CPADEK | CPADEK - DEK CAPITAL CPA ALLOCATION | 6830.81 |  | 6830.81 |  |  | 13569.7 | 0 | 13569.7 | 2018-01-31 08:58 | 2050-12-31 | 2018-03-01 | open
75080 | FPIT | CS1900001 | CS1900001 - VOICE OF THE CUSTOMER ENGAGEMENT PL | 72.43 |  | 72.43 |  |  | 19914.31 | 27483 | -7568.69 | 2020-01-29 15:52 | 2022-03-31 | 2020-02-01 | 2022-03-31
75085 | FPIT | CS2100008 | CS2100008 - NUANCE IVR ENHANCEMENTS | 1043.6 |  | 1043.6 |  |  | 5128.94 | 5958 | -829.06 | 2021-07-16 11:35 | 2022-08-31 | 2021-08-01 | 2022-08-31
75085 | FPIT | CS2100010 | CS2100010 - CONTACT CENTER WORK FROM HOME | 1654.92 |  | 1654.92 |  |  | 1654.92 | 6922 | -5267.08 | 2022-01-26 14:18 | 2022-11-28 | 2022-02-01 | 2023-01-06
75085 | FPIT | CS2200001 | CS2200001 - REVENUE ASSURANCE ART TOOL | 19892.54 |  | 19892.54 |  |  | 19892.54 | 16175 | 3717.54 | 2022-04-07 10:19 | 2023-08-31 | 2022-04-01 | 2023-08-31
75085 | FPIT | CS2200002 | CS2200002 - IVR ENHANCEMENTS 2022 | 5693.61 |  | 5693.61 |  |  | 5693.61 | 6837 | -1143.39 | 2022-05-05 12:49 | 2023-05-01 | 2022-05-01 | 2023-04-30
75085 | FPIT | CS2200005 | CS2200005 - UPLAND RIGHT ANSWER LICENSE PURCHAS | 17399.22 |  | 17399.22 |  |  | 17399.22 | 11365 | 6034.22 | 2022-08-03 15:15 | 2023-01-29 | 2022-12-01 | 2023-05-31
75085 | FPIT | CS2200006 | CS2200006 - VERINT UPGRADE | 78343.89 |  | 78343.89 |  |  | 78343.89 | 114426 | -36082.11 | 2022-11-04 16:06 | 2024-03-31 | 2022-11-01 | 2024-03-31
75085 | FPIT | CS2200007 | CS2200007 - FND LICENSES ADDITIONAL ENDPOINTS | 11172.94 |  | 11172.94 |  |  | 11172.94 | 10971 | 201.94 | 2022-11-01 10:25 | 2023-03-30 | 2022-12-01 | 2023-03-22
75085 | FPIT | CS2200008 | CS2200008 - AVAYA PLATFORM UPGRADE - SERVER | 20720.62 |  | 20720.62 |  |  | 20720.62 | 63481 | -42760.38 | 2022-11-14 12:04 | 2024-03-31 | 2022-11-01 | 2024-03-31
75085 | FPIT | CS220SW04 | CS220SW04 - OPENWAY ENDPOINT SOFTWARE LICENSES | 2877.85 |  | 2877.85 |  |  | 2877.85 | 2935 | -57.15 | 2022-09-07 09:23 | 2023-03-31 | 2022-10-01 | 2023-01-10
75082 | WDCM0071 | CWDIC22 | CWDIC22 - INSTRUMENTATION & CONTROLS (GMA) | 35042.53 |  | 35042.53 |  |  | 35042.53 | 55518.04 | -20475.51 | 2022-10-31 12:19 | 2023-03-01 | 2022-10-01 | 2023-03-31
75082 | WG048C | CWDVLV21 | CWDVLV21 - 2021 MISCELLANEOUS VALVES (GMA) | -548.08 |  | -548.08 |  |  | 36039.61 | 44961 | -8921.39 | 2021-02-04 13:34 | 2022-03-30 | 2021-06-01 | open
75082 | WG048C | CWDVLV22 | CWDVLV22 - WOODSDALE 2022 MISCELLANEOUS VALVES | 229719.35 |  | 229719.35 |  |  | 229719.35 | 192299.83 | 37419.52 | 2022-02-08 14:20 | 2030-12-30 | 2022-06-01 | 2023-03-31
75082 | WG047C | CWG047C | CWG047C - WGS GENERAL EQUIPMENT | 33388.34 |  | 33388.34 |  |  | 393291.72 | 395167.47 | -1875.75 | 2005-08-28 | 2030-12-30 | 2008-07-01 | open
75080 | FPIT | CY190HW13 | CY190HW13 - IT-OT ANA WORKSTREAM HW | 638019.41 |  | 638019.41 |  |  | 3038006.04 | 2784426 | 253580.04 | 2019-12-05 14:44 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | CY190SW13 | CY190SW13 - IT-OT ANA WORKSTREAM SW | 76669.51 |  | 76669.51 |  |  | 95466.68 | 70000 | 25466.68 | 2019-12-05 14:32 | 2022-10-28 | 2019-12-01 | 2022-10-18
75080 | FPIT | CY190SW16 | CY190SW16 - ITOT ANA WORKSTREAM TUFIN SW | 476.13 |  | 476.13 |  |  | 43312.82 | 50484 | -7171.18 | 2020-11-30 19:55 | 2022-10-28 | 2020-12-01 | 2022-10-18
75084 | DKY1931 | D1931DL1 | D1931DL1 - AM 10894240 GENERAL DRIVE PART 1 | 32851.71 |  | 32851.71 |  |  | 228120.84 | 87223.94 | 140896.9 | 2016-07-29 14:11 | 2018-03-15 | 2016-08-01 | 2017-08-18
75084 | DKY2017 | D2017DL3 | D2017DL3 - AM 21113304 DAVIDSON HWY - DKY2017 | 13401.24 |  | 13401.24 |  |  | 173897.13 | 84795.32 | 89101.81 | 2017-04-17 15:00 | 2020-12-18 | 2017-07-01 | 2020-10-26
75084 | DKY2017 | D2017DL5 | D2017DL5 - RUSD DONALDSON HWY RETIRE - DKY2017 | 121.61 |  | 121.61 |  |  | 18839.74 | 29216.85 | -10377.11 | 2017-04-25 11:29 | 2023-04-30 | 2017-12-01 | 2023-04-23
75084 | DKY2210 | D2210DL1 | D2210DL1 - AM 21520192 DONALDSON 45 | -479658.82 |  | -479658.82 |  |  | 708367.09 | 1344202.77 | -635835.68 | 2017-06-15 14:35 | 2020-08-15 | 2019-05-01 | 2020-08-12
75080 | CAPBUDK | DISOHDK | DISOHDK - DEK DISTRIBUTION OVERHEAD POOL | -27217.96 |  | -27217.96 |  |  | -18798.9 | 0 | -18798.9 | 2017-07-31 11:00 | 2026-03-31 | 2018-01-01 | open
75084 | DKY2125 | DKY212501 | DKY212501 - NEW 69KV V STRUCTURE | 41574.64 |  | 41574.64 |  |  | 831996 | 904914.56 | -72918.56 | 2019-02-22 10:01 | 2022-02-15 | 2019-03-01 | 2022-03-16
75084 | DKY2125 | DKY212503 | DKY212503 - DRY RIDGE BK 2 | 90356.2 |  | 90356.2 |  |  | 1294372.96 | 1629020 | -334647.04 | 2019-02-22 10:01 | 2022-02-15 | 2019-04-01 | 2022-03-16
75084 | DKY2125 | DKY212504 | DKY212504 - DRY RIDGE F3568 LOOP TL | -12418.7 |  | -12418.7 |  |  | 301908.25 | 166179.8 | 135728.45 | 2019-02-22 10:01 | 2022-02-15 | 2019-06-01 | 2022-03-16
75084 | DKY2135 | DKY213501 | DKY213501 - TAYLOR MILL SUB 69KV TAKE OFF | 99442.76 |  | 99442.76 |  |  | 102015.72 | 2065388.84 | -1963373.12 | 2021-06-04 14:02 | 2025-07-29 | 2021-06-01 | open
75084 | DKY2135 | DKY213502 | DKY213502 - TAYLOR MILL SUB INSTALL | 489216.02 |  | 489216.02 |  |  | 509984.26 | 6087134 | -5577149.74 | 2021-06-04 14:02 | 2025-08-01 | 2021-06-01 | open
75084 | DKY2135 | DKY213503 | DKY213503 - F5967 LOOP THRU TAYLOR MILL | 40225.63 |  | 40225.63 |  |  | 41518.15 | 939598.78 | -898080.63 | 2021-06-04 14:02 | 2025-01-31 | 2021-07-01 | open
75084 | DKY2135 | DKY213504 | DKY213504 - BLDG DEMO | -1.36 |  | -1.36 |  |  | 0 | 0 | 0 | 2021-06-08 10:18 | 2022-03-01 | 2021-10-01 | 2022-03-27
75080 | KYPYACCR | E1214 | E1214 - KENTUCKY QUARTERLY PAYROLL ACCRUAL | -28000 |  | -28000 |  |  | 69000 | 0 | 69000 | 2008-09-19 | 2050-12-31 | 2008-09-01 | open
75081 | EB020350 | EB020350X | EB020350X - UNDERGROUND FUEL OIL DAY TANK (EF) | 37467.08 |  | 37467.08 |  |  | 4344214.3 | 4429197.46 | -84983.16 | 2019-11-25 10:02 | 2022-02-21 | 2019-12-01 | 2022-03-25
75081 | EB020394 | EB020394X | EB020394X - HCAD REPLACE RECLAIM CHUTES | 104475.84 |  | 104475.84 |  |  | 104475.84 | 3332634.76 | -3228158.92 | 2022-12-21 10:11 | 2024-03-30 | 2022-12-01 | 2024-02-05
75081 | EB020641 | EB020641X | EB020641X - REPLACE STACK LADDER | 217849.21 |  | 217849.21 |  |  | 217849.21 | 220386.99 | -2537.78 | 2022-06-06 13:37 | 2023-01-28 | 2022-06-01 | 2022-12-31
75081 | EB020680 | EB020680X | EB020680X - EVERGREEN UPGRADE | 425453.67 |  | 425453.67 |  |  | 5200310.55 | 5283667.5 | -83356.95 | 2020-09-28 13:02 | 2021-12-31 | 2020-10-01 | 2022-03-25
75081 | EB020684 | EB020684X | EB020684X - HYDRAZINE AND AMMONIA CONTROLS | 6063.01 |  | 6063.01 |  |  | 6063.01 | 1161418.87 | -1155355.86 | 2022-07-25 15:59 | 2025-08-31 | 2022-08-01 | open
75081 | EB020687 | EB020687X | EB020687X - REPLACE CRUSHER HOUSE BOILER | 40018.41 |  | 40018.41 |  |  | 40018.41 | 556282.6 | -516264.19 | 2022-04-08 14:58 | 2024-12-31 | 2022-06-01 | open
75081 | EB020701 | EB020701X | EB020701X - LBU DUST MITIGATION | 29507.84 |  | 29507.84 |  |  | 1696338.64 | 1656005.53 | 40333.11 | 2019-09-13 09:37 | 2022-02-28 | 2019-11-01 | 2022-03-18
75081 | EB020818 | EB020818X | EB020818X - FGD BIOCIDE SYSTEM H2S MITIGATION | 65981.72 |  | 65981.72 |  |  | 303128.92 | 331027.09 | -27898.17 | 2020-07-01 14:25 | 2022-09-30 | 2020-07-01 | 2022-09-15
75081 | EB020821 | EB020821X | EB020821X - REPLACE F CONVEYOR BELT | 2430.11 |  | 2430.11 |  |  | 2430.11 | 232209.26 | -229779.15 | 2022-07-26 09:19 | 2023-07-12 | 2022-08-01 | 2023-07-28
75081 | EB020826 | EB020826X | EB020826X - REPLACE FLAME SCANNERS & IGNITERS | 7705.36 |  | 7705.36 |  |  | 708307.05 | 707956.32 | 350.73 | 2020-12-07 08:55 | 2022-02-28 | 2021-01-01 | 2022-03-25
75081 | EB020863 | EB020863X | EB020863X - SCR REPLACE 3RD LAYER CATALYST | 1721465.99 |  | 1721465.99 |  |  | 1721465.99 | 1769561.89 | -48095.9 | 2022-03-15 13:02 | 2023-01-22 | 2022-03-01 | 2023-02-03
75081 | EB020879 | EB020879X | EB020879X - REPL 2-4 CT FAN BRKR ARC FLASH MITG | 13589.96 |  | 13589.96 |  |  | 102938.62 | 155881.11 | -52942.49 | 2020-12-18 12:48 | 2021-12-31 | 2020-12-01 | 2022-03-25
75081 | EB020890 | EB020890X | EB020890X - GENERATOR STATOR REWIND | -520415.73 |  | -520415.73 |  |  | 13095283.91 | 13504143.66 | -408859.75 | 2020-08-06 11:19 | 2022-02-28 | 2020-08-01 | 2022-03-25
75081 | EB021014 | EB021014X | EB021014X - VOLTAGE REGULATOR BATTERY REPL | 56919.85 |  | 56919.85 |  |  | 56919.85 | 56676.65 | 243.2 | 2022-05-12 09:27 | 2023-01-31 | 2022-05-01 | 2023-02-15
75081 | EB021161 | EB021161X | EB021161X - SCR EXPANSION JOINTS | 7947.49 |  | 7947.49 |  |  | 348787.38 | 390055.54 | -41268.16 | 2019-12-18 12:53 | 2022-02-28 | 2020-01-01 | 2022-02-01
75081 | EB021162 | EB021162X | EB021162X - ECONOMIZER EXPANSION JOINT | -18214.85 |  | -18214.85 |  |  | 179349.27 | 164533.23 | 14816.04 | 2019-12-18 13:13 | 2022-02-28 | 2020-01-01 | 2022-02-01
75081 | EB021199 | EB021199X | EB021199X - WSP 2ST2 6.9KV TRANSFORMER REPL | 122641.42 |  | 122641.42 |  |  | 207142.32 | 185057.23 | 22085.09 | 2021-10-26 15:05 | 2022-06-30 | 2021-10-01 | 2022-07-25
75081 | EB021215 | EB021215X | EB021215X - OWEN ELECTRIC FEED REPLACEMENT | 163899.05 |  | 163899.05 |  |  | 163899.05 | 1776134.31 | -1612235.26 | 2022-07-08 13:20 | 2024-12-31 | 2022-07-01 | 2025-01-17
75081 | EB021307 | EB021307X | EB021307X - 2-6 PULV ROLL WHEEL REPL | 85909.41 |  | 85909.41 |  |  | 1200390.58 | 1197370.95 | 3019.63 | 2020-12-29 14:38 | 2021-12-31 | 2020-12-01 | 2022-03-25
75081 | EB021311 | EB021311X | EB021311X - 2-5 PULV ROLL WHEEL REPL 2022 | 762022.78 |  | 762022.78 |  |  | 762022.78 | 930314.07 | -168291.29 | 2022-03-15 08:36 | 2023-02-28 | 2022-07-01 | 2023-02-04
75081 | EB021320 | EB021320X | EB021320X - REPLACE CRUSHER HOUSE ELEVATOR | 136047.52 |  | 136047.52 |  |  | 136047.52 | 812337.07 | -676289.55 | 2022-06-23 08:15 | 2023-10-31 | 2022-06-01 | 2023-10-27
75081 | EB021371 | EB021371X | EB021371X - SMARTGEN-EBS U2 T/G VIB MONITOR EOL | 0.24 |  | 0.24 |  |  | 429.1 | 34661.94 | -34232.84 | 2021-05-20 13:35 | 2023-12-31 | 2021-06-01 | 2024-01-13
75081 | EB021379 | EB021379X | EB021379X - REPLACE GEN/GSU/UAT PROT RELAYS | -5873.99 |  | -5873.99 |  |  | 1223572.55 | 1263954.92 | -40382.37 | 2020-05-05 07:34 | 2022-02-28 | 2020-05-01 | 2022-03-25
75081 | EB021392 | EB021392X | EB021392X - RELAY REPLACEMENT PH. II RATS | 21265.53 |  | 21265.53 |  |  | 21265.53 | 603768 | -582502.47 | 2022-02-23 08:39 | 2025-12-31 | 2022-03-01 | open
75081 | EB021449 | EB021449X | EB021449X - REPLACE A MODULE INLET EXP JOIN | 51286.12 |  | 51286.12 |  |  | 51286.12 | 68903.04 | -17616.92 | 2022-03-09 14:39 | 2022-08-08 | 2022-05-01 | 2022-08-07
75081 | EB021598 | EB021598X | EB021598X - LPA AND LPB L-2 BLADE REPLACEMENT | 188721.65 |  | 188721.65 |  |  | 4200206.89 | 4499980.22 | -299773.33 | 2020-12-18 15:58 | 2022-02-28 | 2020-12-01 | 2022-03-25
75081 | EB021604 | EB021604X | EB021604X - FGD LIMESTONE CONVERSION | 9430.24 |  | 9430.24 |  |  | 9430.24 | 397974.18 | -388543.94 | 2022-02-16 14:48 | 2025-06-01 | 2022-02-01 | cancelled
75081 | EB021688 | EB021688X | EB021688X - SCR NOX ANALYZERS | 854544.73 |  | 854544.73 |  |  | 854544.73 | 816057.48 | 38487.25 | 2022-01-27 14:08 | 2022-10-31 | 2022-02-01 | 2022-11-08
75081 | EB021722 | EB021722X | EB021722X - NORTH THICKENER TANK REPLACEMENT | 2234595.49 |  | 2234595.49 |  |  | 2271754.99 | 2672404.4 | -400649.41 | 2021-10-08 15:33 | 2023-08-30 | 2021-10-01 | 2023-09-14
75081 | EB021751 | EB021751X | EB021751X - PHYSICAL LOCK PILOT | 39766.83 |  | 39766.83 |  |  | 193256.3 | 216857.16 | -23600.86 | 2021-05-07 07:34 | 2022-11-30 | 2021-06-01 | 2022-11-08
75081 | EB021752 | EB021752X | EB021752X - TURBINE VENTILATING VALVE SV-2 | 80.01 |  | 80.01 |  |  | 93794.45 | 68851.4 | 24943.05 | 2021-05-18 10:36 | 2021-12-30 | 2021-05-01 | 2022-03-26
75081 | EB021763 | EB021763X | EB021763X - REPL SCR SONIC HORN AIR COMPRESSOR | -6.75 |  | -6.75 |  |  | 18043.63 | 14352.65 | 3690.98 | 2021-05-18 11:26 | 2021-12-31 | 2021-06-01 | 2022-03-25
75081 | EB021772 | EB021772X | EB021772X - 2-2 PA OUTLET DAMPER CABLE REPLACE | -4.85 |  | -4.85 |  |  | 12956.11 | 18879.68 | -5923.57 | 2021-06-30 07:28 | 2022-02-19 | 2021-08-01 | 2022-03-25
75081 | EB021785 | EB021785X | EB021785X - REPLACE IK SOOTBLOWER | 39851.05 |  | 39851.05 |  |  | 74059.14 | 45209.18 | 28849.96 | 2021-07-12 09:35 | 2022-11-30 | 2021-12-01 | 2022-12-06
75081 | EB021787 | EB021787X | EB021787X - WSP CAKE TRANSFER CONVEYOR BELT REP | 830.31 |  | 830.31 |  |  | 34090.95 | 24421.3 | 9669.65 | 2021-08-30 08:26 | 2022-02-21 | 2021-10-01 | 2022-03-25
75081 | EB021788 | EB021788X | EB021788X - RADIAL STACKER BELT REPLACEMENT | 36937.71 |  | 36937.71 |  |  | 36937.71 | 42284.65 | -5346.94 | 2022-12-12 19:17 | 2023-03-31 | 2022-12-01 | 2023-04-11
75081 | EB021789 | EB021789X | EB021789X - 2021 CBU INSHORE LADDER HEAD SHAFT | -124.99 |  | -124.99 |  |  | 237755.69 | 301706.69 | -63951 | 2021-08-30 09:05 | 2022-02-10 | 2021-09-01 | 2022-03-01
75081 | EB021793 | EB021793X | EB021793X - ORIENTATION TRAINING TRAILER HVAC | 24008.25 |  | 24008.25 |  |  | 24008.25 | 20244.31 | 3763.94 | 2021-09-29 08:56 | 2022-06-30 | 2022-04-01 | 2022-07-06
75081 | EB021794 | EB021794X | EB021794X - 2-1 & 2-2 PA FAN SHAFTS | -49.19 |  | -49.19 |  |  | 204386.1 | 186816.31 | 17569.79 | 2021-09-29 09:48 | 2022-01-31 | 2021-10-01 | 2022-03-26
75081 | EB021799 | EB021799X | EB021799X - 2A & 2C MODULE OUTLET EXP JNT | 235174.64 |  | 235174.64 |  |  | 253526.3 | 59085.12 | 194441.18 | 2021-10-26 15:18 | 2022-12-31 | 2021-12-01 | 2023-02-03
75081 | EB021813 | EB021813X | EB021813X - MAIN OIL TANK EARTHEN BERM LINER | 128627.28 |  | 128627.28 |  |  | 385136.39 | 383562 | 1574.39 | 2021-12-10 10:31 | 2022-03-31 | 2021-12-01 | 2022-02-25
75081 | EB021815 | EB021815X | EB021815X - MAIN & NEUTRAL FLEX LINK REPL | 62821.68 |  | 62821.68 |  |  | 278531.37 | 288750.1 | -10218.73 | 2021-12-21 10:46 | 2022-03-31 | 2021-12-01 | 2022-03-25
75081 | EB021823 | EB021823X | EB021823X - GOVERNOR VALVE REPL 2021 | -59706.59 |  | -59706.59 |  |  | 267394.51 | 292616.54 | -25222.03 | 2021-12-27 09:00 | 2022-03-31 | 2021-12-01 | 2022-03-25
75081 | EB021829 | EB021829X | EB021829X - REPLACE 2A2 6.9KV-480V TRANSFORMER | 84494.62 |  | 84494.62 |  |  | 84494.62 | 168393.78 | -83899.16 | 2022-05-12 11:12 | 2023-07-23 | 2022-05-01 | 2023-06-20
75081 | EB021894 | EB021894X | EB021894X - 2-2 PULVERIZER MOTOR REWIND | 73209.87 |  | 73209.87 |  |  | 73209.87 | 73105.16 | 104.71 | 2022-02-17 14:36 | 2022-06-15 | 2022-03-01 | 2022-05-17
75081 | EB021895 | EB021895X | EB021895X - 2-10 CT MOTOR AND GEARBOX REPLACEME | 183020.04 |  | 183020.04 |  |  | 183020.04 | 225852.1 | -42832.06 | 2022-02-23 09:47 | 2022-05-28 | 2022-02-01 | 2022-05-07
75081 | EB021903 | EB021903X | EB021903X - ESCAPE RESPIRATORS | 21740.16 |  | 21740.16 |  |  | 21740.16 | 76042.4 | -54302.24 | 2022-03-01 15:37 | 2023-12-30 | 2022-07-01 | 2024-01-31
75081 | EB021910 | EB021910X | EB021910X - PAH OUTLET EXPANSION JOINT | 64380.18 |  | 64380.18 |  |  | 64380.18 | 38314.97 | 26065.21 | 2022-03-01 13:19 | 2022-08-08 | 2022-04-01 | 2022-08-07
75081 | EB021928 | EB021928X | EB021928X - TURBINE VENTILATING VALVE SV-1 | 104704.01 |  | 104704.01 |  |  | 104704.01 | 94388.12 | 10315.89 | 2022-03-09 16:00 | 2023-01-31 | 2022-10-01 | 2023-02-03
75081 | EB021947 | EB021947X | EB021947X - REPL WSP MIXER DISCHARGE BELT | 26920.49 |  | 26920.49 |  |  | 26920.49 | 23544.95 | 3375.54 | 2022-03-15 08:53 | 2022-08-31 | 2022-04-01 | 2022-08-07
75081 | EB021948 | EB021948X | EB021948X - REPL ABS BUILDING SUMP PUMPS | 1364.83 |  | 1364.83 |  |  | 1364.83 | 70991.48 | -69626.65 | 2022-03-15 07:44 | 2024-05-15 | 2022-08-01 | 2024-04-11
75081 | EB021956 | EB021956X | EB021956X - 2-1 WSP VACUUM PUMP REPLACEMENT | 72513.27 |  | 72513.27 |  |  | 72513.27 | 76997.82 | -4484.55 | 2022-03-31 14:44 | 2022-06-30 | 2022-04-01 | 2022-06-29
75081 | EB021960 | EB021960X | EB021960X - SAH 2-1 BASKET REPLACEMENT | 1618017.06 |  | 1618017.06 |  |  | 1618017.06 | 2139212.81 | -521195.75 | 2022-08-18 10:38 | 2023-01-31 | 2022-08-01 | 2023-02-03
75081 | EB021966 | EB021966X | EB021966X - WSP MIXER FEED CONVEYOR BELT | 15503.97 |  | 15503.97 |  |  | 15503.97 | 16687.75 | -1183.78 | 2022-04-19 11:01 | 2022-08-08 | 2022-07-01 | 2022-08-29
75081 | EB021968 | EB021968X | EB021968X - 2-4 CT GEARBOX REPLACEMENT | 229454.77 |  | 229454.77 |  |  | 229454.77 | 190824.07 | 38630.7 | 2022-05-12 12:08 | 2022-12-31 | 2022-05-01 | 2022-11-02
75081 | EB021969 | EB021969X | EB021969X - SEWAGE TREATMENT LEVEL TRANSMITTER | 40723.23 |  | 40723.23 |  |  | 40723.23 | 60858.98 | -20135.75 | 2022-05-12 13:11 | 2024-12-31 | 2022-06-01 | open
75081 | EB021980 | EB021980X | EB021980X - REPLACE 4 FIRE HYDRANTS | 56055.23 |  | 56055.23 |  |  | 56055.23 | 50892.72 | 5162.51 | 2022-06-06 14:09 | 2022-10-30 | 2022-09-01 | 2022-11-16
75081 | EB021992 | EB021992X | EB021992X - SAFETY SHOWER REPLACEMENT | 5052.16 |  | 5052.16 |  |  | 5052.16 | 13538.67 | -8486.51 | 2022-07-08 14:01 | 2023-03-31 | 2022-12-01 | 2023-04-20
75081 | EB022000 | EB022000X | EB022000X - 2-4 PULVERIZER MOTOR REWIND | 69100.69 |  | 69100.69 |  |  | 69100.69 | 73099.99 | -3999.3 | 2022-07-26 07:43 | 2022-11-30 | 2022-08-01 | 2022-12-06
75081 | EB022004 | EB022004X | EB022004X - STORM WATER - ZINC MITIGATION | 1762455.57 |  | 1762455.57 |  |  | 1762455.57 | 2265228.55 | -502772.98 | 2022-08-19 07:52 | 2023-06-30 | 2022-09-01 | 2023-06-30
75081 | EB022011 | EB022011X | EB022011X - REPL 2-1 FLYASH SILO DIFFUSER BLWR | 52328.29 |  | 52328.29 |  |  | 52328.29 | 41764.93 | 10563.36 | 2022-10-07 16:03 | 2023-02-28 | 2022-11-01 | 2023-02-10
75081 | EB022012 | EB022012X | EB022012X - REPLACE DIESEL FP PUMP | 46475.53 |  | 46475.53 |  |  | 46475.53 | 49207.05 | -2731.52 | 2022-10-12 09:04 | 2023-02-28 | 2022-11-01 | 2023-02-04
75081 | EB022013 | EB022013X | EB022013X - REPL GAS PUMP AND FUEL TANK | 41380.57 |  | 41380.57 |  |  | 41380.57 | 28028.62 | 13351.95 | 2022-09-28 14:10 | 2023-01-30 | 2022-10-01 | 2023-03-09
75081 | EB022014 | EB022014X | EB022014X - 2-2 PA FAN BEARING REPLACEMENT | 306780.91 |  | 306780.91 |  |  | 306780.91 | 306061.96 | 718.95 | 2022-10-25 10:27 | 2023-02-28 | 2022-10-01 | 2023-02-09
75081 | EB022015 | EB022015X | EB022015X - REPLACE VOLTAGE REG EXCITATION XFMR | 2674.21 |  | 2674.21 |  |  | 2674.21 | 2948.39 | -274.18 | 2022-10-12 07:29 | 2023-02-28 | 2022-12-01 | 2023-02-28
75081 | EB022016 | EB022016X | EB022016X - INSTALL HCAD TRANSFER HOUSE VACUUM | 90291.88 |  | 90291.88 |  |  | 90291.88 | 41749.66 | 48542.22 | 2022-09-28 13:31 | 2023-02-28 | 2022-11-01 | 2023-03-23
75081 | EB022017 | EB022017X | EB022017X - REPL CBU BREASTING CABLE | 34152.18 |  | 34152.18 |  |  | 34152.18 | 405985.22 | -371833.04 | 2022-11-28 11:46 | 2024-12-31 | 2022-12-01 | 2025-02-05
75081 | EB022019 | EB022019X | EB022019X - 2-3 & 2-6 PULVERIZER FEEDER BELT | 16651.79 |  | 16651.79 |  |  | 16651.79 | 6228.58 | 10423.21 | 2022-09-15 15:41 | 2023-02-28 | 2022-09-01 | 2023-01-06
75081 | EB022025 | EB022025X | EB022025X - 2-2 FGD SERVICE WATER PUMP REWIND | 22108.58 |  | 22108.58 |  |  | 22108.58 | 30227.79 | -8119.21 | 2022-09-28 13:00 | 2023-01-31 | 2022-10-01 | 2023-01-31
75081 | EB022026 | EB022026X | EB022026X - F1-2 CRUSHER MOTOR REWIND | 228361.56 |  | 228361.56 |  |  | 228361.56 | 45584 | 182777.56 | 2022-09-28 12:06 | 2023-01-15 | 2022-10-01 | 2023-04-03
75081 | EB022027 | EB022027X | EB022027X - LBU HOPPER BELT & SKIRTING | 57864.02 |  | 57864.02 |  |  | 57864.02 | 30665.6 | 27198.42 | 2022-10-11 16:29 | 2023-01-10 | 2022-10-01 | 2023-02-03
75081 | EB022029 | EB022029X | EB022029X - HG CEMS STACK PROBE STINGER | 13852.84 |  | 13852.84 |  |  | 13852.84 | 12886.8 | 966.04 | 2022-10-20 09:43 | 2023-12-31 | 2022-11-01 | 2023-10-19
75081 | EB022030 | EB022030X | EB022030X - REPL 2-1 CONDENSATE TRANSFER PUMP | 13156.32 |  | 13156.32 |  |  | 13156.32 | 12210.5 | 945.82 | 2022-10-07 15:38 | 2023-01-31 | 2022-11-01 | 2023-02-17
75081 | EB022031 | EB022031X | EB022031X - 3R & 8R COAL NOZZLE REPLACEMENT | 65200.34 |  | 65200.34 |  |  | 65200.34 | 18648 | 46552.34 | 2022-10-07 16:18 | 2023-01-31 | 2022-10-01 | 2023-02-03
75081 | EB022034 | EB022034X | EB022034X - CRUSHER HOUSE & TRACTOR GAR LIGHTS | 17935.84 |  | 17935.84 |  |  | 17935.84 | 46717.52 | -28781.68 | 2022-10-25 09:48 | 2023-02-28 | 2022-10-01 | 2023-01-25
75081 | EB022037 | EB022037X | EB022037X - TRIPPER ROOM CAMERA SYSTEM | 81004.95 |  | 81004.95 |  |  | 81004.95 | 77700 | 3304.95 | 2022-10-25 08:44 | 2023-07-31 | 2022-11-01 | 2023-08-30
75081 | EB022040 | EB022040X | EB022040X - FGD H2S MONITOR CABLE | 24567.82 |  | 24567.82 |  |  | 24567.82 | 36543.48 | -11975.66 | 2022-10-20 12:37 | 2023-02-28 | 2022-11-01 | 2023-01-30
75081 | EB022042 | EB022042X | EB022042X - PURCHASE VACUUM TRUCK | 516444.04 |  | 516444.04 |  |  | 516444.04 | 517104.01 | -659.97 | 2022-10-25 07:41 | 2023-03-15 | 2022-11-01 | 2023-03-16
75081 | EB022043 | EB022043X | EB022043X - 2023 OPTIM ST VALVE CVGV U2 | 1949.97 |  | 1949.97 |  |  | 1949.97 | 5171070.43 | -5169120.46 | 2022-12-09 16:12 | 2023-12-31 | 2022-12-01 | 2024-02-05
75081 | EB022048 | EB022048X | EB022048X - MSP FA SILO DOOR & PLATFORM | 36463.91 |  | 36463.91 |  |  | 36463.91 | 81161.76 | -44697.85 | 2022-12-12 11:34 | 2025-02-28 | 2022-12-01 | 2023-01-31
75081 | EB022050 | EB022050X | EB022050X - FGD COMMON OUTLET DUCT PLATFORM | 4625.41 |  | 4625.41 |  |  | 4625.41 | 29170.49 | -24545.08 | 2022-11-28 10:53 | 2023-03-31 | 2022-11-01 | 2023-02-03
75081 | EB022052 | EB022052X | EB022052X - COMMON FLY ASH SEPARATOR BAGS | 33158.77 |  | 33158.77 |  |  | 33158.77 | 28030.58 | 5128.19 | 2022-11-21 08:26 | 2023-03-31 | 2022-11-01 | 2022-12-05
75081 | EB022054 | EB022054X | EB022054X - 2-1 SBAC COOLER REPLACEMENT | 226170.47 |  | 226170.47 |  |  | 226170.47 | 220990.47 | 5180 | 2022-11-28 11:20 | 2023-03-31 | 2022-11-01 | 2023-02-14
75081 | EB022056 | EB022056X | EB022056X - 2-1 SERVICE WATER PUMP OVERHAUL | 242817.03 |  | 242817.03 |  |  | 242817.03 | 233100 | 9717.03 | 2022-11-29 16:24 | 2023-02-28 | 2022-11-01 | 2023-03-15
75081 | EB022059 | EB022059X | EB022059X - REPLACE FGD 2C2 MIXER | 101814.43 |  | 101814.43 |  |  | 101814.43 | 98879.14 | 2935.29 | 2022-12-12 18:02 | 2023-03-15 | 2022-12-01 | 2023-01-30
75081 | EB022060 | EB022060X | EB022060X - REPLACE CBU HOIST CABLE | 38531.93 |  | 38531.93 |  |  | 38531.93 | 91183.77 | -52651.84 | 2022-12-28 15:10 | 2023-03-15 | 2022-12-01 | 2023-04-04
75081 | EB022065 | EB022065X | EB022065X - REPLACE 2-3 WSP VACUUM PUMP | 81188.96 |  | 81188.96 |  |  | 81188.96 | 56675.2 | 24513.76 | 2022-12-22 14:22 | 2023-03-31 | 2022-12-01 | 2023-03-15
75081 | EBS01262 | EBS01262X | EBS01262X - SAH 2-2 BASKET REPLACEMENT | 2366051.48 |  | 2366051.48 |  |  | 2366051.48 | 2781919.6 | -415868.12 | 2022-04-05 07:50 | 2023-01-31 | 2022-04-01 | 2023-02-03
75081 | EBS01302 | EBS01302X | EBS01302X - WSP RADIAL STACKER | 155763.41 |  | 155763.41 |  |  | 155763.41 | 3891176.02 | -3735412.61 | 2022-12-21 09:49 | 2024-02-05 | 2022-12-01 | 2024-02-05
75081 | EBS01342 | EBS01342X | EBS01342X - REPLACE BFPT CONTROLS | 834172.15 |  | 834172.15 |  |  | 834172.15 | 4290008.28 | -3455836.13 | 2022-10-12 15:04 | 2024-03-31 | 2022-12-01 | 2024-02-12
75081 | EBS01378 | EBS01378X | EBS01378X - REPL TURB TRIP SYSTEM CONTROL | 220130.25 |  | 220130.25 |  |  | 220130.25 | 1944299.99 | -1724169.74 | 2022-09-02 12:45 | 2024-03-31 | 2022-09-01 | 2024-02-12
75080 | FLKY0249G | EDUKEKY22 | EDUKEKY22 - ELECTRIC EQUIPMENT PURCHASES - KY | 200512.25 |  | 200512.25 |  |  | 200512.25 | 50000 | 150512.25 | 2022-01-26 12:17 | 2025-12-15 | 2022-02-01 | open
75080 | FIDNEL10K | G1371 | G1371 - MW IDEN RADIO UNITS & PARTS | 24893.88 |  | 24893.88 |  |  | 3.638e-12 | 73140 | -73140 | 2010-10-22 | 2010-12-31 | 2010-12-01 | cancelled
75084 | VMTDFA | GGARKY | GGARKY - TVM REACTIVE CAP - DEK | 50443.67 |  | 50443.67 |  |  | 77780.91 | 0 | 77780.91 | 2019-10-16 15:20 | 2050-12-31 | 2020-03-01 | open
75080 | CAPBUDK | GPACCRUAL | GPACCRUAL - MIDWEST VACATION ACCRUAL | 2253.23 |  | 2253.23 |  |  | 46872.22 | 0 | 46872.22 | 2021-03-18 08:47 | 2051-03-31 | 2021-03-01 | open
75084 | ICPRJDSTR | ICCONSTRD | ICCONSTRD - INTERCONNECTION CAPITAL PROJECT | 20.29 |  | 20.29 |  |  | 6.402e-12 | 0 | 6.402e-12 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01 | open
75084 | ICPRJDSTR | ICCONSTRT | ICCONSTRT - INTERCONNECTION CAPITAL PROJECT | 8.24 |  | 8.24 |  |  | -1.8847e-12 | 0 | -1.8847e-12 | 2017-09-28 12:05 | 2030-09-30 | 2017-10-01 | open
75084 | NBFA | IKKY2015 | IKKY2015 - 2015 KY DIST LINES (IK) ROLL | -3031027.72 |  | -3031027.72 |  |  | 2168063.49 | 0 | 2168063.49 | 2014-12-18 | 2015-12-31 | 2014-12-01 | 2016-03-31
75080 | GENERIC | INCENTIVE | INCENTIVE - INCENTIVE TRUE-UP | -319247.28 |  | -319247.28 |  |  | 179836.29 | 0 | 179836.29 | 2019-11-22 10:36 | 2050-12-31 | 2019-11-01 | open
75081 | FPITF | IT2000019 | IT2000019 - MOBILE COMPONENT ASSESSMENT APPLICA | 5462.23 |  | 5462.23 |  |  | 32355.38 | 35260 | -2904.62 | 2020-06-09 15:59 | 2022-07-30 | 2020-06-01 | 2022-07-31
75082 | FPITF | IT2000019 | IT2000019 - MOBILE COMPONENT ASSESSMENT APPLICA | 4095.11 |  | 4095.11 |  |  | 24278.4 | 26389 | -2110.6 | 2020-06-09 16:08 | 2022-07-30 | 2020-06-01 | 2022-07-31
75084 | FPIT | IT20SW08D | IT20SW08D - ITOA 2020 PRODUCT ENHANCEMENTS | 6721.48 |  | 6721.48 |  |  | 60165.25 | 34187 | 25978.25 | 2020-03-26 08:44 | 2022-03-01 | 2020-03-01 | 2022-01-08
75084 | FPIT | IT2100088 | IT2100088 - OAM - ORACLE ACCESS HW | -664.72 |  | -664.72 |  |  | 1.6 | 107 | -105.4 | 2021-08-26 12:20 | 2022-03-01 | 2021-11-01 | 2022-03-31
75084 | FPIT | IT2100108 | IT2100108 - CIP LOCAL PASSWORD TOOL (CLPT) | 3922.68 |  | 3922.68 |  |  | 16410.94 | 29845 | -13434.06 | 2021-11-03 14:41 | 2025-03-31 | 2021-11-01 | open
75084 | FPIT | IT2100120 | IT2100120 - OSI PI SOFTWARE LICENSE RENEWAL | -0.8 |  | -0.8 |  |  | 30024.1 | 30225 | -200.9 | 2021-12-17 11:42 | 2022-06-29 | 2021-12-01 | 2022-03-31
75084 | FPIT | IT2200029 | IT2200029 - DCC SATELLITE PHONES | 2440.7 |  | 2440.7 |  |  | 2440.7 | 2187 | 253.7 | 2022-02-24 09:24 | 2022-07-30 | 2022-03-01 | 2022-12-01
75080 | FPIT | IT2200035 | IT2200035 - 2022 SERVER EOL PROJECT - ERLANGER | 9798.43 |  | 9798.43 |  |  | 9798.43 | 12597 | -2798.57 | 2022-03-17 10:40 | 2023-03-30 | 2022-04-01 | 2022-08-05
75082 | FPITF | IT2200052 | IT2200052 - 2022 SERVER EOL REPLACEMENT PROJECT | 9871.11 |  | 9871.11 |  |  | 9871.11 | 12597 | -2725.89 | 2022-03-14 11:13 | 2023-03-30 | 2022-04-01 | 2022-10-20
75084 | FPIT | IT2200053 | IT2200053 - TGIS ENHANCEMENTS 2022 | 5110.76 |  | 5110.76 |  |  | 5110.76 | 9240 | -4129.24 | 2022-03-30 07:51 | 2023-08-17 | 2022-06-01 | 2023-08-10
75080 | FPIT | IT2200054 | IT2200054 - CONSOLIDATE BPM REPORTING | 78024.08 |  | 78024.08 |  |  | 78024.08 | 62342 | 15682.08 | 2022-06-21 09:00 | 2023-03-30 | 2022-07-01 | 2023-03-13
75081 | FPITF | IT2200064 | IT2200064 - OPTIM UPLIFT | 13816.41 |  | 13816.41 |  |  | 13816.41 | 37717 | -23900.59 | 2022-05-05 15:50 | 2024-03-29 | 2022-05-01 | 2024-03-29
75082 | FPITF | IT2200064 | IT2200064 - OPTIM UPLIFT | 10291.45 |  | 10291.45 |  |  | 10291.45 | 28228 | -17936.55 | 2022-05-05 15:54 | 2024-03-29 | 2022-05-01 | 2024-03-29
75080 | FPIT | IT2200066 | IT2200066 - COMPASS TO AWS | 19146.03 |  | 19146.03 |  |  | 19146.03 | 19126 | 20.03 | 2022-05-20 08:13 | 2023-01-29 | 2022-05-01 | 2023-02-17
75084 | FPIT | IT2200069 | IT2200069 - HRM PORTAL - CLOUD UPDATE - PHASE 1 | 5363.04 |  | 5363.04 |  |  | 5363.04 | 3577 | 1786.04 | 2022-07-01 12:24 | 2023-03-30 | 2022-08-01 | 2023-03-31
75081 | FPITF | IT2200089 | IT2200089 - ESRA - AVAMAR SINGLE NODE PURCHASE | 50641.34 |  | 50641.34 |  |  | 50641.34 | 42538 | 8103.34 | 2022-06-29 09:44 | 2023-09-30 | 2022-07-01 | 2023-09-30
75082 | FPITF | IT2200105 | IT2200105 - ESRA - AVAMAR SINGLE NODE PURCHASE | 31882.51 |  | 31882.51 |  |  | 31882.51 | 43575 | -11692.49 | 2022-06-27 16:02 | 2023-09-30 | 2022-07-01 | 2023-09-30
75081 | FPITF | IT2200106 | IT2200106 - ACT REPORTING PLATFORM MODERNIZATIO | 5223.91 |  | 5223.91 |  |  | 5223.91 | 11706 | -6482.09 | 2022-08-30 10:34 | 2024-01-27 | 2022-09-01 | 2024-01-27
75082 | FPITF | IT2200106 | IT2200106 - ACT REPORTING PLATFORM MODERNIZATIO | 4104.62 |  | 4104.62 |  |  | 4104.62 | 8761 | -4656.38 | 2022-08-30 10:40 | 2024-01-27 | 2022-09-01 | 2024-01-27
75084 | FPIT | IT2200122 | IT2200122 - ACQUIRE TUFIN & NPVIEW FIREWALL LIC | 6993.63 |  | 6993.63 |  |  | 6993.63 | 10558 | -3564.37 | 2022-09-01 07:14 | 2024-05-29 | 2022-12-01 | 2024-06-28
75081 | FPITF | IT2200149 | IT2200149 - RRE HEAT RATE SOLUTION | 1001.13 |  | 1001.13 |  |  | 1001.13 | 10191 | -9189.87 | 2022-11-18 09:12 | 2023-10-31 | 2022-12-01 | 2023-10-24
75082 | FPITF | IT2200149 | IT2200149 - RRE HEAT RATE SOLUTION | 749.39 |  | 749.39 |  |  | 749.39 | 7627 | -6877.61 | 2022-11-18 09:25 | 2023-10-31 | 2022-12-01 | 2023-10-24
75084 | FPIT | IT2200153 | IT2200153 - RM TO AMAZON CLOUD REARCHITECT | 1108.79 |  | 1108.79 |  |  | 1108.79 | 17398 | -16289.21 | 2022-11-03 14:35 | 2024-02-29 | 2022-12-01 | 2024-02-29
75084 | FPIT | IT2200158 | IT2200158 - HRM ROADMAP UPGRADES 2023 | 9838.88 |  | 9838.88 |  |  | 9838.88 | 43140 | -33301.12 | 2022-11-04 14:05 | 2024-06-30 | 2022-12-01 | 2024-04-09
75081 | FPITF | IT2200162 | IT2200162 - ACT (FACILEX) UPGRADE TO VERSION 7. | 2585.09 |  | 2585.09 |  |  | 2585.09 | 2600 | -14.91 | 2022-11-16 13:59 | 2022-11-17 | 2022-12-01 | 2022-11-30
75082 | FPITF | IT2200162 | IT2200162 - ACT (FACILEX) UPGRADE TO VERSION 7. | 1934.74 |  | 1934.74 |  |  | 1934.74 | 1946 | -11.26 | 2022-11-16 14:08 | 2022-11-17 | 2022-12-01 | 2022-11-30
75084 | FPIT | IT220082D | IT220082D - ITOA ENHANCEMENTS 2022 | 7395.03 |  | 7395.03 |  |  | 7395.03 | 20349 | -12953.97 | 2022-06-29 09:37 | 2024-03-31 | 2022-07-01 | 2024-03-12
75084 | 20550043A | K2055SURK | K2055SURK - SUB OPT - SUR - DONALDSON - 2055 | 7057.69 |  | 7057.69 |  |  | 29819.59 | 0 | 29819.59 | 2021-05-20 09:31 | 2024-12-31 | 2021-11-01 | open
75084 | 21520041A | K2152SURK | K2152SURK - SUB OPT - SUR - HEBRON - 152 | 41252.28 |  | 41252.28 |  |  | 41252.28 | 0 | 41252.28 | 2021-05-20 11:22 | 2025-03-31 | 2022-02-01 | open
75084 | 22100041A | K2210SURK | K2210SURK - TBC SUB OPT - SUR - OAKBROOK STA - | 15267.51 |  | 15267.51 |  |  | 15267.51 | 0 | 15267.51 | 2021-05-20 11:33 | 2024-03-01 | 2022-02-01 | cancelled
75084 | 22410042A | K2241SURK | K2241SURK - SUB OPT - SUR - FLORENCE - 241 | 18870.84 |  | 18870.84 |  |  | 53369.13 | 0 | 53369.13 | 2021-05-04 12:07 | 2024-12-31 | 2021-11-01 | open
75084 | 75084IL | KALRPL | KALRPL - AREA LIGHT REPLACEMENTS | 61372.34 |  | 61372.34 |  |  | 203262.2 | 0 | 203262.2 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01 | open
75084 | 75084IL | KCAL | KCAL - AREA LIGHT NEW INSTALLS | 510999.16 |  | 510999.16 |  |  | 1524970.42 | 0 | 1524970.42 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01 | open
75084 | 75084IK | KCAPAUTO | KCAPAUTO - CAPACITOR AUTOMATION UPGRADE | -3896.15 |  | -3896.15 |  |  | 1906603.54 | 0 | 1906603.54 | 2017-03-24 15:35 | 2067-12-31 | 2018-01-01 | open
75084 | 75084IK | KCIPOH | KCIPOH - C&I CUSTOMER ADDITIONS OH | 588805.04 |  | 588805.04 |  |  | 5381516.93 | 0 | 5381516.93 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KCIUPOH | KCIUPOH - C&I CUSTOMER UPGRADE OH | 144562.71 |  | 144562.71 |  |  | 699503.5 | 0 | 699503.5 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCDT | KCMCDT - NON-EMERG DTUG CORRECTIVE REPLACE | 9856.04 |  | 9856.04 |  |  | 11017.7 | 0 | 11017.7 | 2017-03-24 15:45 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KCMCEDT | KCMCEDT - EMERG DTUG CORRECTIVE REPLACEMENTS | 3642.48 |  | 3642.48 |  |  | 223638.26 | 0 | 223638.26 | 2017-03-24 15:47 | 2067-12-31 | 2018-06-01 | open
75084 | 75084IK | KCMCEOH | KCMCEOH - EMERGENCY OH CORRECTIVE REPLACEMENT | 308342.75 |  | 308342.75 |  |  | 1435522.16 | 0 | 1435522.16 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCEUG | KCMCEUG - EMERGENCY UG CORRECTIVE REPLACEMENT | 114463.21 |  | 114463.21 |  |  | 597495.48 | 0 | 597495.48 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCOH | KCMCOH - NON-EMERGENCY OH CORRECTIVE REPLACE | 119289.26 |  | 119289.26 |  |  | 292402.34 | 0 | 292402.34 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCOWS | KCMCOWS - SECONDARY OH WIRE CORR REPLACEMENT | 6061.17 |  | 6061.17 |  |  | 27591.74 | 0 | 27591.74 | 2017-03-27 11:47 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KCMCUG | KCMCUG - NON-EMERGENCY UG CORRECTIVE REPL | 49690.73 |  | 49690.73 |  |  | 202662.48 | 0 | 202662.48 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01 | open
75084 | 75084HW | KCOU | KCOU - MAKE READY OTHER UTIL ATTACHMENTS | -108611.27 |  | -108611.27 |  |  | 589414.48 | 0 | 589414.48 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01 | open
75084 | 75084HW | KCRFN | KCRFN - CUSTOMER REQUESTED MODS NONREIMB | 38352.77 |  | 38352.77 |  |  | 226348.63 | 0 | 226348.63 | 2017-03-24 15:19 | 2067-12-31 | 2018-06-01 | open
75084 | 75084HW | KCRFR | KCRFR - CUSTOMER REQUESTED MODS REIMB | -3126.96 |  | -3126.96 |  |  | 6906.24 | 0 | 6906.24 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01 | open
75084 | 75084IL | KCSL | KCSL - STREET LIGHT NEW INSTALLS | 4271.13 |  | 4271.13 |  |  | 4376.44 | 0 | 4376.44 | 2017-03-28 09:32 | 2067-04-01 | 2021-11-01 | open
75084 | KCTFOOL | KCTOOL | KCTOOL - TOOLS BLANKET | 97783.42 |  | 97783.42 |  |  | 676107.68 | 0 | 676107.68 | 2018-07-27 15:23 | 2069-04-01 | 2018-11-01 | open
75084 | KECF20155 | KEC920155 | KEC920155 - DEC 8920155 OAKBROOK 41 | 626.91 |  | 626.91 |  |  | 93583.08 | 18342.29 | 75240.79 | 2015-10-26 18:05 | 2020-10-20 | 2016-09-01 | 2020-10-07
75084 | 75084IK | KELT3PH | KELT3PH - END OF LIFE PAD TRANSF 3PH NON LEAK | 913123.94 |  | 913123.94 |  |  | 2577320.27 | 0 | 2577320.27 | 2020-01-09 15:04 | 2067-12-31 | 2020-02-01 | open
75084 | 75084HW | KHWYN | KHWYN - HIGHWAY RELOCATIONS NONREIMB | 259975.41 |  | 259975.41 |  |  | 1220053.36 | 0 | 1220053.36 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01 | open
75084 | 75084HW | KHWYR | KHWYR - HIGHWAY RELOCATIONS REIMB | 49781.38 |  | 49781.38 |  |  | 106184.16 | 0 | 106184.16 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IL | KLEDSL | KLEDSL - LED STREET LIGHT RETROFIT | 307938.05 |  | 307938.05 |  |  | 378573.7 | 0 | 378573.7 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01 | open
75084 | 75084IK | KLPF | KLPF - LINE PATROL FOLLOW UP | 176711.63 |  | 176711.63 |  |  | 1660585.92 | 0 | 1660585.92 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KMHR | KMHR - MANHOLE LID RETROFIT REPLACEMENT | 18.46 |  | 18.46 |  |  | 1362.9 | 0 | 1362.9 | 2017-07-27 14:56 | 2067-12-31 | 2019-12-01 | open
75084 | 75084HW | KMODC | KMODC - OTHER CAPITAL MODIFICATIONS | 29553.44 |  | 29553.44 |  |  | 175004.91 | 0 | 175004.91 | 2017-03-24 15:33 | 2067-12-31 | 2018-07-01 | open
75084 | 75084 | KMTRNOS | KMTRNOS - KY METERS-NOT AMI-SELFCONTAINED | 106434.09 |  | 106434.09 |  |  | 187421.55 | 5461.31 | 181960.24 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01 | open
75084 | 75084 | KMTRNOT | KMTRNOT - KY - METERS-NOT AMI- T RATED | 114619.24 |  | 114619.24 |  |  | 333878.44 | 520.12 | 333358.32 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01 | open
75084 | 75084 | KMTROWR2 | KMTROWR2 - KY SALVAGE CREDIT FOR METERS | -47723.58 |  | -47723.58 |  |  | -47723.58 | 0 | -47723.58 | 2022-04-28 10:56 | 2026-03-31 | 2022-05-01 | open
75084 | 75084 | KMTROWS | KMTROWS - KY - METERS-AMI-SELF CONTAINED | 706100.24 |  | 706100.24 |  |  | 2263675.1 | 99863.96 | 2163811.14 | 2018-11-02 18:04 | 2026-03-31 | 2018-12-01 | open
75084 | 75084 | KMTROWT | KMTROWT - KY - METERS-AMI-T RATED | 316422.68 |  | 316422.68 |  |  | 1119315.66 | 11182.68 | 1108132.98 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01 | open
75080 | RESBLDKY | KMW211076 | KMW211076 - HVAC REPLACEMENT | 7233.9 |  | 7233.9 |  |  | 7719.51 | 12463 | -4743.49 | 2021-12-02 10:05 | 2022-04-07 | 2021-12-01 | 2022-05-24
75080 | RESBLDKY | KMW221271 | KMW221271 - AUGUSTINE OPS LOCKER ROOM AND PLUMB | 78300.1 |  | 78300.1 |  |  | 78300.1 | 61200 | 17100.1 | 2022-04-21 12:10 | 2022-10-27 | 2022-04-01 | 2022-12-23
75084 | RES75084 | KMW221289 | KMW221289 - WILDER SUBSTATION 59 HVAC REPLACEME | 13137.03 |  | 13137.03 |  |  | 13137.03 | 15219 | -2081.97 | 2022-04-28 11:08 | 2022-11-24 | 2022-07-01 | 2022-11-01
75080 | RESBLDKY | KMW221422 | KMW221422 - GENERATOR MONITORING EQUIP | 39869.18 |  | 39869.18 |  |  | 39869.18 | 79538 | -39668.82 | 2022-07-05 11:00 | 2023-03-31 | 2022-09-01 | 2024-02-07
75080 | RESBLDKY | KMW3CEB80 | KMW3CEB80 - ERLANGER OPS CENTER RENOVATION | 2193843.54 |  | 2193843.54 |  |  | 2217741.02 | 9223149 | -7005407.98 | 2021-02-03 10:15 | 2023-11-08 | 2021-02-01 | 2023-11-10
75080 | RESBLDKY | KMW3F3417 | KMW3F3417 - FIRE MAIN REPLACEMENT | 6928.1 |  | 6928.1 |  |  | 106247.78 | 130480 | -24232.22 | 2021-09-20 08:53 | 2022-03-31 | 2021-09-01 | 2022-03-21
75084 | 75084RR | KNANC | KNANC - NEIGHBORHOOD AREA NTWK REPLACEMENTS | 14310.69 |  | 14310.69 |  |  | 86006.42 | 0 | 86006.42 | 2017-03-27 14:46 | 2067-04-01 | 2019-05-01 | open
75084 | 75084IK | KOUTOH | KOUTOH - OUTAGE RELATED OH CAP REPLACEMENTS | 347327.27 |  | 347327.27 |  |  | 2504201.04 | 0 | 2504201.04 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KOUTUG | KOUTUG - OUTAGE RELATED UG CAP REPLACEMENTS | 628370.26 |  | 628370.26 |  |  | 3339073.73 | 0 | 3339073.73 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KPDMCAP | KPDMCAP - PUBLIC DAMAGE OH CAPITAL REPLACEMEN | 260381.77 |  | 260381.77 |  |  | 1082333.99 | 0 | 1082333.99 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KPDMCPU | KPDMCPU - PUBLIC DAMAGE UG CAPITAL REPLACEMNT | 238808.87 |  | 238808.87 |  |  | 607757.08 | 0 | 607757.08 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01 | open
75084 | 75084IK | KPOLCM | KPOLCM - REACTIVE POLE REPLACEMENTS | 552217.56 |  | 552217.56 |  |  | 2144167.46 | 0 | 2144167.46 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01 | open
75084 | 75084IK | KPOLIR | KPOLIR - NON EMERG POLE REPLACE INSP BASED | 1353757.52 |  | 1353757.52 |  |  | 2627742.05 | 0 | 2627742.05 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KPOLOTH | KPOLOTH - OTH UOP REPL FOUND THRU POLE INSP | 9823.8 |  | 9823.8 |  |  | 19326.94 | 0 | 19326.94 | 2017-03-27 12:30 | 2067-12-31 | 2021-07-01 | open
75084 | 75084IK | KPPL | KPPL - STUB POLE REMOVAL ONLY | 7303.28 |  | 7303.28 |  |  | 43826.09 | 0 | 43826.09 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01 | open
75084 | 75084IL | KPPLLGT | KPPLLGT - PURPLE LIGHT REPLACE | 7353.64 |  | 7353.64 |  |  | 31720.07 | 440 | 31280.07 | 2021-04-16 11:58 | 2069-12-31 | 2021-07-01 | open
75084 | 75084IK | KRCR | KRCR - CAPACITOR REPLACEMENTS & ASSOC UOP | 79182.57 |  | 79182.57 |  |  | 617986.58 | 0 | 617986.58 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRFSCM | KRFSCM - CD - CIRC SECT - REACTIVE | 19979.5 |  | 19979.5 |  |  | 24626.42 | 0 | 24626.42 | 2019-03-21 15:28 | 2068-03-31 | 2021-05-01 | open
75084 | 75084IK | KRIOTCO | KRIOTCO - OH IMPRVMNT FROM PQRI OUTAGE INVEST | 14308.35 |  | 14308.35 |  |  | 448547.39 | 0 | 448547.39 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRIOTCU | KRIOTCU - UG IMPRVMNT FROM PQRI OUTAGE INVEST | 47.41 |  | 47.41 |  |  | 65027.22 | 0 | 65027.22 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRMOH | KRMOH - RESIDENTIAL CUST ADDS MULTI FAM OH | 2985.6 |  | 2985.6 |  |  | 181541.51 | 0 | 181541.51 | 2017-03-27 13:07 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRNUIF | KRNUIF - REMOVAL OF NON-UTILIZED INFRASTRUCT | 4292.39 |  | 4292.39 |  |  | 10933.07 | 0 | 10933.07 | 2017-12-13 12:01 | 2068-03-31 | 2020-07-01 | open
75084 | 75084IK | KROC | KROC - OH DETERIORATED CONDUCTOR REPLACE | -5080.89 |  | -5080.89 |  |  | 140833.25 | 0 | 140833.25 | 2018-07-11 10:07 | 2067-12-31 | 2018-11-01 | open
75084 | 75084IK | KROWCAP | KROWCAP - DEK CAPACITY EASEMENT/ROW BLANKET | 165.16 |  | 165.16 |  |  | 165.16 | 3600000 | -3599834.84 | 2021-04-26 21:47 | 2036-10-17 | 2022-04-01 | open
75084 | 75084IK | KROWCONS | KROWCONS - DEK CONSTRUCT EASEMENT/ROW BLANKET | 265434.45 |  | 265434.45 |  |  | 265434.45 | 3600000 | -3334565.55 | 2021-04-26 22:06 | 2036-10-17 | 2022-04-01 | open
75084 | 75084IK | KROWMAJ | KROWMAJ - DEK MAJ PROJ EASEMENT/ROW BLANKET | 49434.8 |  | 49434.8 |  |  | 49434.8 | 3600000 | -3550565.2 | 2021-04-26 22:20 | 2036-10-17 | 2022-04-01 | open
75084 | 75084IK | KRRRCM | KRRRCM - CD - RECL ELEC REPL - REACTIVE | 116018.02 |  | 116018.02 |  |  | 372184.9 | 0 | 372184.9 | 2019-03-21 15:37 | 2068-03-31 | 2019-06-01 | open
75084 | 75084IK | KRSOH | KRSOH - RESIDENTIAL CUST ADDS SINGLE FAM OH | 957971.65 |  | 957971.65 |  |  | 6057450.13 | 0 | 6057450.13 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRTP1PH | KRTP1PH - SINGLE PH TRANSFORMER REPLAC LEAKER | 17290.74 |  | 17290.74 |  |  | 73833.53 | 0 | 73833.53 | 2017-03-27 13:17 | 2067-12-31 | 2018-07-01 | open
75084 | 75084IK | KRTP3PH | KRTP3PH - THREE PH TRANSFORMER REPLACE LEAKER | 82740.83 |  | 82740.83 |  |  | 259920.32 | 0 | 259920.32 | 2017-03-27 13:19 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KRTR1PH | KRTR1PH - SINGLE PH TRANSFORMER REPLACE DRY | 19735.77 |  | 19735.77 |  |  | 79331.9 | 0 | 79331.9 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01 | open
75084 | 75084IK | KRTR3PH | KRTR3PH - THREE PH TRANSFORMER REPLACE DRY | 57693.25 |  | 57693.25 |  |  | 114457.36 | 0 | 114457.36 | 2017-03-27 13:26 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRTXLFCM | KRTXLFCM - CD - UPGD LIVE FRONT TRSFR REACTIVE | 968.23 |  | 968.23 |  |  | 193520.97 | 0 | 193520.97 | 2019-03-21 16:21 | 2068-03-31 | 2019-06-01 | open
75084 | 75084IK | KRTXO | KRTXO - OVERHEAD TRANSFORMER REPLACEMENT | 96482.23 |  | 96482.23 |  |  | 288204.95 | 0 | 288204.95 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRUCLGCM | KRUCLGCM - CD - UG CABLE REPL LG REACTIVE | 5142.29 |  | 5142.29 |  |  | 43108.58 | 0 | 43108.58 | 2019-03-21 16:28 | 2068-03-31 | 2019-09-01 | open
75084 | 75084IK | KRUCSEC | KRUCSEC - UG SEC/SERVICE CABLE REPLACEMENT | 136187.64 |  | 136187.64 |  |  | 473360.53 | 0 | 473360.53 | 2017-03-27 13:33 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KRUCSM | KRUCSM - UG PRIMARY SMALL CABLE REPLACEMENT | -1018.86 |  | -1018.86 |  |  | 320246.96 | 0 | 320246.96 | 2017-03-27 14:22 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRUCSMCM | KRUCSMCM - CD - UG CABLE REPL REACTIVE | 452323 |  | 452323 |  |  | 1320873.54 | 0 | 1320873.54 | 2019-03-21 16:34 | 2068-03-31 | 2019-06-01 | open
75084 | 75084IL | KRUL | KRUL - UG CABLE LIGHTING REPLACEMENTS | 49383.21 |  | 49383.21 |  |  | 68997.85 | 0 | 68997.85 | 2017-03-28 09:39 | 2067-04-01 | 2018-05-01 | open
75084 | 75084IK | KRUPOH | KRUPOH - RESIDENTIAL CUSTOMER UPGRADE OH | 238505.45 |  | 238505.45 |  |  | 1481574.58 | 0 | 1481574.58 | 2017-03-27 14:26 | 2067-12-31 | 2017-11-01 | open
75084 | 75084IK | KRXR | KRXR - TRANSFORMER RETROFIT | 926.45 |  | 926.45 |  |  | 437374.98 | 0 | 437374.98 | 2017-03-27 14:28 | 2067-12-31 | 2018-01-01 | open
75084 | 75084IK | KRXRCM | KRXRCM - CD - TRANSF RETROFIT - REACTIVE | 63.04 |  | 63.04 |  |  | 72323.97 | 0 | 72323.97 | 2019-03-21 15:58 | 2068-03-31 | 2020-01-01 | open
75084 | 75084IK | KSBDUG | KSBDUG - NEW CUSTOMER WORK - RES SUBDIV INFR | 701180.25 |  | 701180.25 |  |  | 1586175.08 | 0 | 1586175.08 | 2019-09-26 10:05 | 2028-04-01 | 2020-01-01 | open
75084 | 75084IL | KSLRPL | KSLRPL - STREET LIGHT REPLACEMENTS | 204931.04 |  | 204931.04 |  |  | 842163.21 | 0 | 842163.21 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01 | open
75084 | 75084IK | KSMF | KSMF - CAPITAL REPLACEMENTS FROM SMEI INSP | 10967.53 |  | 10967.53 |  |  | 26472.85 | 0 | 26472.85 | 2017-03-27 14:35 | 2067-12-31 | 2018-03-01 | open
75084 | KUCF34911 | KUC234911 | KUC234911 - UG 6234911 HANDS 44 URD | 273.25 |  | 273.25 |  |  | 723551.56 | 349210.8 | 374340.76 | 2015-11-23 14:07 | 2017-07-15 | 2016-01-01 | 2017-04-26
75084 | KUCF61112 | KUC261112 | KUC261112 - UG 10261112 CONSTANCE 42 | 133.84 |  | 133.84 |  |  | 802788.64 | 360637.32 | 442151.32 | 2017-01-10 14:04 | 2019-03-19 | 2017-03-01 | 2018-08-10
75084 | KYGLT20 | KYGLT2001 | KYGLT2001 - GLT F965 RPL POLES | 137138.28 |  | 137138.28 |  |  | 180331.92 | 784349.09 | -604017.17 | 2020-09-09 14:01 | 2024-03-16 | 2020-09-01 | 2024-04-02
75084 | KYGLT20 | KYGLT2003 | KYGLT2003 - GLT 965 RPL POLE AT SPORTS COMPLEX | 18262.33 |  | 18262.33 |  |  | 18262.33 | 199818.87 | -181556.54 | 2022-04-22 14:01 | 2024-09-08 | 2022-08-01 | cancelled
75084 | KYGLT21 | KYGLT2101 | KYGLT2101 - GLT F5967/F965 RPL 1 CROSSARM | 5615.78 |  | 5615.78 |  |  | 5615.78 | 5456.75 | 159.03 | 2022-01-19 14:02 | 2023-01-29 | 2022-03-01 | 2022-11-13
75084 | KYGLT21 | KYGLT2102 | KYGLT2102 - GLT F5962 RPL 12-POLES AND REPAIR 1 | 31403.7 |  | 31403.7 |  |  | 31403.7 | 1763246.58 | -1731842.88 | 2022-01-19 14:02 | 2024-09-28 | 2022-02-01 | 2024-08-14
75084 | KYGLT21 | KYGLT2103 | KYGLT2103 - GLT 2021 KENTUCKY PROJECTS REAL EST | 590.79 |  | 590.79 |  |  | 590.79 | 590.79 | 0 | 2022-01-19 14:02 | 2024-11-19 | 2022-02-01 | 2024-08-14
75084 | KYGLT21 | KYGLT2104 | KYGLT2104 - GLT F6761 RPL CROSS ARM AND DOWN GU | 69933.14 |  | 69933.14 |  |  | 69933.14 | 116248 | -46314.86 | 2022-07-14 10:01 | 2023-02-19 | 2022-07-01 | 2023-03-29
75084 | KYRELT | KYRELT02 | KYRELT02 - F6761 RICHWOOD EO 71/75 | 64514.22 |  | 64514.22 |  |  | 68472.58 | 622079.91 | -553607.33 | 2018-09-04 10:02 | 2019-09-04 | 2018-09-01 | 2019-08-10
75084 | FPIT | LTHCDDSLT | LTHCDDSLT - LIGHTHOUSE CUSTOMER DELIVERY DESIGN | 1213.77 |  | 1213.77 |  |  | 1213.77 | 115970 | -114756.23 | 2022-10-13 15:30 | 2025-09-30 | 2022-11-01 | open
75084 | FPIT | LTHCDPJBS | LTHCDPJBS - LIGHTHOUSE CUSTOMER DELIVERY PRE-JO | 5529.91 |  | 5529.91 |  |  | 5529.91 | 11777 | -6247.09 | 2022-09-29 10:38 | 2024-02-01 | 2022-10-01 | 2023-12-25
75080 | FPIT | LTHCESCS | LTHCESCS - WO OPTIMIZATION WORK INPUT/CALL-SW | 234.42 |  | 234.42 |  |  | 9812.62 | 27500 | -17687.38 | 2021-02-25 18:39 | 2022-03-31 | 2021-02-01 | 2021-03-31
75084 | FPIT | LTHESPOTS | LTHESPOTS - LH EQUIP STRATEGY PLANNG & OPTIM SW | 37888.27 |  | 37888.27 |  |  | 37888.27 | 36161 | 1727.27 | 2021-06-28 08:22 | 2022-11-01 | 2022-10-01 | 2022-11-01
75084 | FPIT | LTHITTAMO | LTHITTAMO - LTH - IT TELECOM ASSET MANAGEMT | 36304.35 |  | 36304.35 |  |  | 96537.39 | 96831 | -293.61 | 2020-07-28 14:30 | 2022-12-30 | 2020-10-01 | 2022-09-30
75081 | FPITF | LTHRROBTS | LTHRROBTS - LIGHTHOUSE: RRE ORBIT2 | 24028.09 |  | 24028.09 |  |  | 37673.72 | 87364.58 | -49690.86 | 2021-08-26 20:52 | 2024-08-10 | 2021-08-01 | 2024-08-15
75082 | FPITF | LTHRROBTS | LTHRROBTS - LIGHTHOUSE: RRE ORBIT2 | 18103.95 |  | 18103.95 |  |  | 28312.57 | 65523.44 | -37210.87 | 2021-08-26 21:00 | 2024-08-10 | 2021-08-01 | 2024-08-15
75081 | FPITF | LTHRUNITY | LTHRUNITY - LIGHTHOUSE RRE UNITY | 18460.2 |  | 18460.2 |  |  | 18460.2 | 65354 | -46893.8 | 2022-04-20 09:09 | 2024-11-30 | 2022-05-01 | open
75082 | FPITF | LTHRUNITY | LTHRUNITY - LIGHTHOUSE RRE UNITY | 14075.6 |  | 14075.6 |  |  | 14075.6 | 48917 | -34841.4 | 2022-04-20 09:15 | 2024-11-30 | 2022-05-01 | open
75084 | FPIT | LTHTASDBS | LTHTASDBS - LIGHTHOUSE: TITUS - ASPEN DB FEATUR | 61583.11 |  | 61583.11 |  |  | 61583.11 | 9159 | 52424.11 | 2021-08-10 12:42 | 2023-06-30 | 2022-02-01 | 2023-06-30
75084 | FPIT | LTHTNEXS | LTHTNEXS - LH EQUIP STRATEGY PLANNG & OPTIM SW | 3690.94 |  | 3690.94 |  |  | 3690.94 | 3121 | 569.94 | 2021-06-28 10:31 | 2022-08-31 | 2022-10-01 | 2022-08-30
75084 | FPIT | LTHTPVEZE | LTHTPVEZE - LIGHTHOUSE TRANSMISSION PLANTIEW EZ | 2397.28 |  | 2397.28 |  |  | 2397.28 | 1207 | 1190.28 | 2022-05-06 09:52 | 2022-12-29 | 2022-05-01 | 2022-12-31
75084 | FPIT | LTHTRFELD | LTHTRFELD - LIGHTHOUSE TRANSMISSION TITUS FIELD | 19407.4 |  | 19407.4 |  |  | 19407.4 | 33157 | -13749.6 | 2022-05-10 12:02 | 2024-12-30 | 2022-05-01 | open
75084 | FPIT | LTHTRLIVS | LTHTRLIVS - LIGHTHOUSE: TRANSMISSION LIVE LIDAR | 18077.57 |  | 18077.57 |  |  | 18893.51 | 29192 | -10298.49 | 2021-10-28 16:21 | 2024-06-30 | 2021-11-01 | 2024-07-02
75084 | FPIT | LTHTRMTLS | LTHTRMTLS - LIGHTHOUSE: TRANSMISSION TITUS | 14279.09 |  | 14279.09 |  |  | 18122.87 | 34698 | -16575.13 | 2021-10-26 10:52 | 2024-08-30 | 2021-11-01 | 2024-07-09
75084 | FPIT | LTHTRQKO | LTHTRQKO - LTH TRANSMISSION ESPO QUICK SW | 2412.55 |  | 2412.55 |  |  | 2412.55 | 2420 | -7.45 | 2021-06-28 10:43 | 2022-08-31 | 2022-05-01 | 2022-09-15
75084 | FPIT | LTHTRTVMT | LTHTRTVMT - LIGHTHOUSE TRANSMISSION TVM 2.0 | 6895.54 |  | 6895.54 |  |  | 6895.54 | 48665 | -41769.46 | 2022-05-19 10:22 | 2024-09-28 | 2022-05-01 | 2024-09-30
75084 | FPIT | LTHTTVMSG | LTHTTVMSG - LIGHTHOUSE TRANSMISSION TVM 2.0 | 6853.84 |  | 6853.84 |  |  | 6853.84 | 9360 | -2506.16 | 2022-05-19 08:22 | 2024-09-01 | 2022-05-01 | 2024-09-30
75084 | M170111 | M17011101 | M17011101 - LITTON SUB PROP PURCH | 2027993.13 |  | 2027993.13 |  |  | 3774782.48 | 1873674 | 1901108.48 | 2018-08-20 18:03 | 2022-02-05 | 2018-08-01 | 2021-10-09
75084 | M180095 | M18009501 | M18009501 - KENTON XTR 1 RPL | 136968.23 |  | 136968.23 |  |  | 291841.48 | 753175.59 | -461334.11 | 2019-03-07 10:01 | 2024-01-05 | 2019-03-01 | 2024-01-28
75084 | M180375 | M18037501 | M18037501 - LITTON SUB- CONSTRUCT SUB | 462767.57 |  | 462767.57 |  |  | 463208.61 | 8698488.61 | -8235280 | 2021-10-29 14:02 | 2025-04-04 | 2021-11-01 | open
75084 | M180375 | M18037502 | M18037502 - LITTON SUB- EXT XMISSION | 60223.35 |  | 60223.35 |  |  | 60885.64 | 1336460 | -1275574.36 | 2021-10-29 14:02 | 2024-07-01 | 2021-12-01 | 2024-07-31
75084 | M180375 | M18037503 | M18037503 - LITTON SUB- CONSTRUCT TRANS LOOP | 87727.88 |  | 87727.88 |  |  | 87727.88 | 1952021.1 | -1864293.22 | 2021-10-29 14:02 | 2024-06-30 | 2022-01-01 | 2024-07-31
75084 | M180375 | M18037504 | M18037504 - LITTON SUB TLINE RLE | 557.11 |  | 557.11 |  |  | 557.11 | 63208 | -62650.89 | 2021-10-29 14:02 | 2023-07-01 | 2022-07-01 | cancelled
75084 | M180378 | M18037801 | M18037801 - RICHWOOD BK 4- INSTALL | 3139532.04 |  | 3139532.04 |  |  | 3487296.59 | 5498141.33 | -2010844.74 | 2019-09-12 14:01 | 2023-07-10 | 2019-10-01 | 2023-07-13
75084 | M180378 | M18037802 | M18037802 - RICHWOOD BK 4- MOD XMISSION STRUCTU | 318932.13 |  | 318932.13 |  |  | 441877.41 | 827126.64 | -385249.23 | 2019-09-16 18:01 | 2023-07-11 | 2019-10-01 | 2023-08-09
75084 | M180378 | M18037803 | M18037803 - F6761 LOOP | 12328.82 |  | 12328.82 |  |  | 15317.05 | 91093.62 | -75776.57 | 2019-09-12 14:01 | 2023-06-11 | 2020-06-01 | 2023-07-11
75084 | M180383 | M18038301 | M18038301 - WHITE TOWER INSTALL SECOND V-STRUCT | 52455.93 |  | 52455.93 |  |  | 52455.93 | 1174045.45 | -1121589.52 | 2022-03-04 14:01 | 2024-09-30 | 2022-04-01 | 2024-10-01
75084 | M180383 | M18038302 | M18038302 - WHITE TOWER BK 2 RPL | 105022.28 |  | 105022.28 |  |  | 105022.28 | 4007317 | -3902294.72 | 2022-03-04 14:01 | 2024-09-30 | 2022-04-01 | 2024-10-01
75084 | M180383 | M18038303 | M18038303 - WHITE TOWER 5967 POLE RELO | 1097.54 |  | 1097.54 |  |  | 1097.54 | 245670 | -244572.46 | 2022-03-04 14:01 | 2024-10-13 | 2022-10-01 | 2024-10-01
75084 | M180383 | M18038304 | M18038304 - WHITE TOWER 5967 POLE EASEMENT | 4865.12 |  | 4865.12 |  |  | 4865.12 | 84792 | -79926.88 | 2022-03-04 14:01 | 2023-10-03 | 2022-06-01 | 2023-11-02
75084 | M180384 | M18038401 | M18038401 - WHITE TOWER TB 1 REBUILD | 19757.37 |  | 19757.37 |  |  | 19757.37 | 1229270.12 | -1209512.75 | 2022-03-07 14:01 | 2025-02-01 | 2022-04-01 | 2025-02-26
75084 | M180387 | M18038701 | M18038701 - COLD SPRING TB 9 LS UPGD | 1064731.97 |  | 1064731.97 |  |  | 1224876.65 | 1422585 | -197708.35 | 2021-02-16 18:02 | 2023-01-27 | 2021-03-01 | 2023-02-21
75084 | M190153 | M19015301 | M19015301 - GLT F6763 RPL - LIMABURG TO OAKBROO | 2917.18 |  | 2917.18 |  |  | 660139.24 | 647545.95 | 12593.29 | 2019-10-03 14:14 | 2021-01-05 | 2019-10-01 | 2020-10-08
75084 | M190167 | M19016706 | M19016706 - VILLA 2019 DMVPN UPGRADE 2 | -548.57 |  | -548.57 |  |  | -244.96 | 85275 | -85519.96 | 2020-01-28 10:01 | 2027-02-08 | 2020-01-01 | cancelled
75084 | M190194 | M19019401 | M19019401 - TURFWAY SUB | 7624.62 |  | 7624.62 |  |  | 11048.64 | 4551557.9 | -4540509.26 | 2020-12-08 14:19 | 2028-06-19 | 2020-12-01 | open
75084 | M190226 | M19022601 | M19022601 - 138 KV F23983 WOODSPOINT TO AERO | 395935.53 |  | 395935.53 |  |  | 9559395.35 | 10187073.43 | -627678.08 | 2019-10-08 14:01 | 2023-06-30 | 2019-11-01 | 2023-07-25
75084 | M190226 | M19022602 | M19022602 - F23983 T LINE RLE | 912193.64 |  | 912193.64 |  |  | 7498514.04 | 7486323 | 12191.04 | 2019-10-08 14:01 | 2023-03-10 | 2020-01-01 | 2023-03-20
75084 | M190297 | M19029701 | M19029701 - 5967 RBLD CLARYVILLE TO HL 864 | 3301222.85 |  | 3301222.85 |  |  | 3629602.87 | 9990283.16 | -6360680.29 | 2020-11-11 14:01 | 2024-01-16 | 2020-11-01 | 2024-02-18
75084 | M190297 | M19029702 | M19029702 - F5967 LINE RLE | 40820.37 |  | 40820.37 |  |  | 41071.4 | 41413.31 | -341.91 | 2020-11-11 14:01 | 2024-02-02 | 2021-03-01 | 2023-05-28
75084 | M190298 | M19029801 | M19029801 - F5967 RBLD HL 864 TO HL 801 | 3386881.81 |  | 3386881.81 |  |  | 3430825.43 | 4535186.12 | -1104360.69 | 2021-06-07 18:02 | 2023-07-15 | 2021-06-01 | 2023-07-09
75084 | M190298 | M19029802 | M19029802 - F5967 LINE RLE RBLD LAYDOWN AREA | 54172.87 |  | 54172.87 |  |  | 54172.87 | 105355 | -51182.13 | 2021-06-07 18:02 | 2023-06-30 | 2022-04-01 | 2023-05-28
75084 | M190298 | M19029803 | M19029803 - F5967 RBLD HL801 - HL746 - HL736 | 1363764.28 |  | 1363764.28 |  |  | 1369682.23 | 998899.36 | 370782.87 | 2021-06-07 18:02 | 2023-04-11 | 2021-08-01 | 2023-02-17
75084 | M190299 | M19029901 | M19029901 - F5967 RBLD POLE HL736 TO HL 661 | 3291.3 |  | 3291.3 |  |  | 37536.78 | 19421209.13 | -19383672.35 | 2021-06-07 18:02 | 2025-07-22 | 2021-07-01 | open
75084 | M190300 | M19030001 | M19030001 - F5967 RBLD HL 661 TO DECOURSEY | 3900.08 |  | 3900.08 |  |  | 34332.03 | 12892712.42 | -12858380.39 | 2021-06-07 18:02 | 2025-07-11 | 2021-07-01 | open
75084 | M190309 | M19030901 | M19030901 - HEBRON-INSTALL 69 KV CB | 20690.23 |  | 20690.23 |  |  | 20690.23 | 2708286.91 | -2687596.68 | 2022-02-23 10:01 | 2027-09-07 | 2022-03-01 | open
75084 | M200011 | M20001101 | M20001101 - ALEXANDRIA SOUTH INSTALL BATTERY CA | 123955.12 |  | 123955.12 |  |  | 123955.12 | 119805.52 | 4149.6 | 2022-02-17 18:01 | 2023-03-12 | 2022-03-01 | 2023-03-09
75084 | M200039 | M20003901 | M20003901 - ATLAS CAMBIUM RADIO UPGRADE | 6390.61 |  | 6390.61 |  |  | 125714.18 | 232638 | -106923.82 | 2020-03-23 18:01 | 2022-01-29 | 2020-03-01 | 2022-03-03
75084 | M200039 | M20003904 | M20003904 - HEBRON CAMBIUM RADIO UPGRADE | 1553.69 |  | 1553.69 |  |  | 124953.16 | 120284 | 4669.16 | 2020-03-23 18:01 | 2021-08-30 | 2020-03-01 | 2021-07-08
75084 | M200039 | M20003905 | M20003905 - DRY RIDGE CAMBIUM RADIO UPGRADE | 20118.62 |  | 20118.62 |  |  | 148154.5 | 193637 | -45482.5 | 2020-03-23 18:01 | 2022-06-27 | 2020-03-01 | 2022-03-03
75084 | M200056 | M20005601 | M20005601 - GLT 5967 RPL POLES WILDER SUB ABS | 14181.9 |  | 14181.9 |  |  | 92249.14 | 412343.91 | -320094.77 | 2020-12-21 18:01 | 2023-12-04 | 2020-12-01 | 2023-12-28
75084 | M200056 | M20005603 | M20005603 - GLT 5967 RPL POLES WHITE TOWER SUB | 853.37 |  | 853.37 |  |  | 5552.5 | 1696206.56 | -1690654.06 | 2020-12-21 18:01 | 2023-12-04 | 2020-12-01 | 2023-12-28
75084 | M200056 | M20005604 | M20005604 - GLT 5967 RPL POLES, INSP YR 2016RLE | 416.14 |  | 416.14 |  |  | 1306.05 | 1936.86 | -630.81 | 2020-12-21 18:01 | 2024-01-29 | 2021-02-01 | 2023-12-28
75084 | M200148 | M20014801 | M20014801 - F6761 MT ZION ROAD RELOCATION | 20517.45 |  | 20517.45 |  |  | 907657.04 | 844710.61 | 62946.43 | 2020-05-19 10:24 | 2021-08-13 | 2020-05-01 | 2021-09-02
75084 | M200290 | M20029001 | M20029001 - F5983 KY SD1 RELOCATION | 16.2 |  | 16.2 |  |  | 28052.39 | 27997.35 | 55.04 | 2020-09-15 14:01 | 2021-11-08 | 2020-09-01 | 2021-12-06
75084 | M200326 | M20032601 | M20032601 - EMGT - HANDS FLOOD MITIGATION | 6871.82 |  | 6871.82 |  |  | 50044.12 | 168205.24 | -118161.12 | 2021-02-16 18:02 | 2027-09-30 | 2021-02-01 | open
75084 | M200335 | M20033501 | M20033501 - HANDS RPL ABS 837 AND ABS 839 | -169928.47 |  | -169928.47 |  |  | 340938.04 | 455488.1 | -114550.06 | 2021-02-03 14:01 | 2022-03-22 | 2021-02-01 | 2022-03-17
75084 | M200376 | M20037601 | M20037601 - EMR - CIR 5967 RPL HWY CROSSING | -395157.01 |  | -395157.01 |  |  | 1876923.95 | 2354434 | -477510.05 | 2020-12-03 14:02 | 2022-02-21 | 2021-02-01 | 2022-03-03
75084 | M200382 | M20038201 | M20038201 - EMR - BELLEVUE TB 2 ETM | 21333.67 |  | 21333.67 |  |  | 38410.55 | 54602 | -16191.45 | 2021-01-19 18:02 | 2022-10-21 | 2021-03-01 | 2022-08-05
75084 | M200444 | M20044401 | M20044401 - DIXIE RPL BUS 2 SWGR & TB2 | 8513.47 |  | 8513.47 |  |  | 8513.47 | 4246746.6 | -4238233.13 | 2022-08-15 18:01 | 2026-02-03 | 2022-08-01 | open
75084 | M210146 | M21014601 | M21014601 - EMERGENT - WILDER TB 3 INSTALL POWE | 771868.71 |  | 771868.71 |  |  | 1100637.43 | 377777 | 722860.43 | 2021-03-18 18:03 | 2022-06-28 | 2021-03-01 | 2022-05-22
75084 | M210251 | M21025101 | M21025101 - GRANT CAMBIUM RADIO | 156129.29 |  | 156129.29 |  |  | 174634.48 | 128087 | 46547.48 | 2021-07-20 18:02 | 2023-02-07 | 2021-07-01 | 2023-01-19
75084 | M210257 | M21025701 | M21025701 - EMR COLD SPRINGS TO WILDER - 69KV H | 1775007.44 |  | 1775007.44 |  |  | 1808204.09 | 2407350 | -599145.91 | 2021-05-05 10:02 | 2022-07-30 | 2021-05-01 | 2022-08-25
75084 | M210257 | M21025702 | M21025702 - EMR 5962 RLE | 2135.01 |  | 2135.01 |  |  | 2135.01 | 9703 | -7567.99 | 2022-09-23 18:01 | 2022-12-13 | 2022-09-01 | 2023-01-08
75084 | M210258 | M21025801 | M21025801 - EMR CIR 15268 RPL I-275 HWY CROSSI | 14361.64 |  | 14361.64 |  |  | 14958.38 | 239226.98 | -224268.6 | 2021-05-13 14:02 | 2023-12-24 | 2021-06-01 | 2024-01-11
75084 | M210280 | M21028001 | M21028001 - EMERGENT - HANDS SUBSTATION REPLACE | 71865.49 |  | 71865.49 |  |  | 85643.94 | 105658 | -20014.06 | 2021-05-12 18:02 | 2022-06-17 | 2021-06-01 | 2022-07-15
75084 | M210323 | M21032301 | M21032301 - EMR - CIRCUIT 965 REPLACE ABS 346 | 416474.37 |  | 416474.37 |  |  | 424561.77 | 139856 | 284705.77 | 2021-11-12 14:01 | 2022-08-29 | 2021-12-01 | 2022-08-29
75084 | M210374 | M21037401 | M21037401 - LIMABURG-OAKBROOK RLE | 10058.61 |  | 10058.61 |  |  | 12163.48 | 185590.81 | -173427.33 | 2021-08-04 14:03 | 2026-07-06 | 2021-08-01 | open
75084 | M210374 | M21037402 | M21037402 - HEBRON-ROUTE 237 RLE | 171672.46 |  | 171672.46 |  |  | 193202.95 | 4748160.48 | -4554957.53 | 2021-08-04 14:03 | 2026-03-03 | 2021-08-01 | open
75084 | M210391 | M21039101 | M21039101 - EMERGENT - BELLEVUE SUBSTATION REPL | 34189.04 |  | 34189.04 |  |  | 1090887.62 | 1501567 | -410679.38 | 2021-08-19 18:04 | 2022-03-22 | 2021-08-01 | 2022-04-20
75084 | M210413 | M21041301 | M21041301 - EMERGENT - REPLACE CLARYVILLE TB 3 | 327591.31 |  | 327591.31 |  |  | 1061575.78 | 1960120 | -898544.22 | 2021-09-03 10:01 | 2022-04-03 | 2021-09-01 | 2022-03-17
75084 | M210428 | M21042801 | M21042801 - BUFFINGTON SUBSTATION - DISCONNECT | 82560.64 |  | 82560.64 |  |  | 89436.9 | 104596 | -15159.1 | 2021-10-12 10:02 | 2022-08-05 | 2021-11-01 | 2022-07-29
75084 | M210429 | M21042901 | M21042901 - AERO SUBSTATION BERM INSTALL | 47505.29 |  | 47505.29 |  |  | 47505.29 | 45532 | 1973.29 | 2022-01-13 18:01 | 2022-05-29 | 2022-02-01 | 2022-02-26
75084 | M210464 | M21046401 | M21046401 - CONSTANCE BUS 1 SWGR AND TB 1 RPL | 168666.02 |  | 168666.02 |  |  | 168666.02 | 5765552.98 | -5596886.96 | 2022-11-30 18:02 | 2028-08-06 | 2022-12-01 | open
75084 | M210491 | M21049101 | M21049101 - FEEDER 6765 RELOCATION | 11891.6 |  | 11891.6 |  |  | 11891.6 | 1306917.69 | -1295026.09 | 2022-07-12 14:01 | 2024-05-14 | 2022-07-01 | 2024-06-12
75084 | M210504 | M21050401 | M21050401 - FEEDER 15268 RELOCATION | -52454.93 |  | -52454.93 |  |  | -52454.93 | 704098.77 | -756553.7 | 2022-01-14 10:04 | 2025-12-23 | 2022-01-01 | open
75084 | M220022 | M22002201 | M22002201 - LONGBRANCH SUBSTATION - TRANSFORMER | 21625.7 |  | 21625.7 |  |  | 21625.7 | 80000 | -58374.3 | 2022-02-16 18:01 | 2022-10-14 | 2022-03-01 | 2022-08-16
75084 | M220195 | M22019501 | M22019501 - EMERGENT COLD SPRING SUBSTATION - R | 17257.33 |  | 17257.33 |  |  | 17257.33 | 29801.43 | -12544.1 | 2022-07-26 10:02 | 2023-08-12 | 2022-08-01 | 2023-08-09
75084 | M220205 | M22020501 | M22020501 - 5966 RT9 & STEEL PLANT RD RELO | 5281.51 |  | 5281.51 |  |  | 5281.51 | 244345.07 | -239063.56 | 2022-06-27 10:05 | 2023-07-08 | 2022-06-01 | 2023-08-06
75084 | M220278 | M22027801 | M22027801 - HANDS SUBSTATION-NEW SECONDARY CONT | 257788.48 |  | 257788.48 |  |  | 257788.48 | 257788.48 | 0 | 2022-11-30 10:01 | 2023-01-31 | 2022-12-01 | 2023-03-02
75084 | M220344 | M22034401 | M22034401 - LONGBRANCH SUBSTATION - REPLACE VR | 45848.37 |  | 45848.37 |  |  | 45848.37 | 59349.78 | -13501.41 | 2022-11-30 10:08 | 2023-03-04 | 2022-12-01 | 2023-03-12
75084 | TOT00002 | MWEMSKY | MWEMSKY - MIDWEST EMS REPLACEMENT PROJECT | 57549.78 |  | 57549.78 |  |  | 605120.15 | 679701.48 | -74581.33 | 2019-07-22 08:59 | 2023-03-30 | 2019-07-01 | 2023-03-31
75084 | TOT00002 | MWEMSKY2 | MWEMSKY2 - DEK EMS REPLACEMENT PROJECT | 568375.53 |  | 568375.53 |  |  | 876912.62 | 1646591 | -769678.38 | 2020-12-17 11:46 | 2024-12-31 | 2020-12-01 | 2023-03-31
75084 | SG000685F | MX0000632 | MX0000632 - TBC 2020 TUG 25990991 TONYA DR INS | -847.75 |  | -847.75 |  |  | -1.1369e-13 | 228.31 | -228.31 | 2019-06-19 14:01 | 2022-09-01 | 2019-08-01 | cancelled
75084 | 20550044A | MX0002132 | MX0002132 - SUB OPT 2022 TUG 25994114 N TALBOT | 1554 |  | 1554 |  |  | 1554 | 11299.74 | -9745.74 | 2022-02-03 14:01 | 2025-03-13 | 2022-05-01 | open
75084 | 20550044A | MX0002133 | MX0002133 - SUB OPT 2022 TUG 25994114 N TALBOT | 79233.4 |  | 79233.4 |  |  | 79233.4 | 287654.23 | -208420.83 | 2022-02-03 10:02 | 2025-03-13 | 2022-02-01 | open
75084 | 20550044A | MX0002134 | MX0002134 - SUB OPT 2022 TUG 26062514 N TALBOT | 64752.18 |  | 64752.18 |  |  | 64752.18 | 156777.97 | -92025.79 | 2022-02-03 14:01 | 2025-03-13 | 2022-05-01 | open
75084 | 22410045A | MX0002522 | MX0002522 - TBC 2023 SUB OPT TUG - PHEASANT DR | 46000.26 |  | 46000.26 |  |  | 46571.59 | 228.31 | 46343.28 | 2021-12-13 14:11 | 2024-12-29 | 2021-12-01 | cancelled
75084 | 22410045A | MX0002524 | MX0002524 - TBC 2023 SUB OPT TUG - PHEASANT DR | 35308.96 |  | 35308.96 |  |  | 39708.55 | 228.31 | 39480.24 | 2021-12-13 14:11 | 2024-12-29 | 2021-12-01 | cancelled
75084 | 22410045A | MX0002526 | MX0002526 - TBC 2023 SUB OPT TUG - PHEASANT DR | 5340.49 |  | 5340.49 |  |  | 5340.49 | 228.31 | 5112.18 | 2021-12-13 18:02 | 2024-12-29 | 2022-01-01 | cancelled
75084 | 75084IK | MX0090253 | MX0090253 - MXCONV-TRANSFORMER RETROFIT KENTON | 6556.27 |  | 6556.27 |  |  | 53655.89 | 66741.76 | -13085.87 | 2018-04-18 10:02 | 2019-06-01 | 2018-06-01 | 2019-01-21
75084 | 75084IK | MX0090259 | MX0090259 - MXCONV-TRANSFORMER RETROFIT YORK 42 | 6310.09 |  | 6310.09 |  |  | 38685.35 | 42782.63 | -4097.28 | 2018-04-18 14:01 | 2018-12-28 | 2018-06-01 | 2018-11-09
75084 | DKY1931 | MX0240701 | MX0240701 - AUGUSTINE 46 - GENERAL DRIVE OH TO | 292796.85 |  | 292796.85 |  |  | 315514.21 | 285970.72 | 29543.49 | 2021-03-16 14:02 | 2023-03-16 | 2021-03-01 | 2023-03-30
75084 | 75084IK | MX0291269 | MX0291269 - COMMERCIAL SERVICE FOR SOLAR/WIND/M | -213568.07 |  | -213568.07 |  |  | 11092.11 | 297921.33 | -286829.22 | 2021-05-26 14:02 | 2023-05-01 | 2021-06-01 | 2023-04-25
75084 | 75084IK | MX0305398 | MX0305398 - KSL; BOONE COUNTY HIGHSCHOOL; 8330 | 7476.57 |  | 7476.57 |  |  | 24885.63 | 51972.86 | -27087.23 | 2021-07-30 10:02 | 2022-02-03 | 2021-08-01 | 2022-01-30
75084 | 23040041A | MX0319569 | MX0319569 - SUB OPT -UPGRADE OF CAPACITORS BY A | 13802.39 |  | 13802.39 |  |  | 14466.64 | 14762.51 | -295.87 | 2021-08-10 10:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX0319570 | MX0319570 - SUB OPT -UPGRADE OF CAPACITORS BY A | 14887.65 |  | 14887.65 |  |  | 15572.51 | 16439.26 | -866.75 | 2021-08-10 10:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX0319571 | MX0319571 - SUB OPT -UPGRADE OF CAPACITORS BY A | 15329.07 |  | 15329.07 |  |  | 15950.42 | 14384.29 | 1566.13 | 2021-08-10 10:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX0319572 | MX0319572 - SUB OPT -UPGRADE OF CAPACITORS BY A | 28962.08 |  | 28962.08 |  |  | 30308.66 | 21002.93 | 9305.73 | 2021-08-06 14:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040042A | MX0319573 | MX0319573 - SUB OPT -UPGRADE OF CAPACITORS BY A | 19222.86 |  | 19222.86 |  |  | 20685.43 | 16539.05 | 4146.38 | 2021-08-06 14:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040043A | MX0319574 | MX0319574 - SUB OPT -UPGRADE OF CAPACITORS BY A | 13660.98 |  | 13660.98 |  |  | 15074.93 | 14639.02 | 435.91 | 2021-08-06 14:02 | 2025-05-29 | 2021-08-01 | open
75084 | 75084IK | MX0322031 | MX0322031 - LOAD GROWTH, LOAD TRANSFER AND TIE | 6504.63 |  | 6504.63 |  |  | -1.0004e-11 | 118358.51 | -118358.51 | 2019-06-04 10:02 | 2019-11-28 | 2019-06-01 | 2019-11-14
75084 | DKY2618 | MX0541691 | MX0541691 - PRIMARY SERVICE 2 - AMAZON - DKY261 | 58753.33 |  | 58753.33 |  |  | 1619.53 | 42750.1 | -41130.57 | 2021-05-18 14:02 | 2021-12-29 | 2021-05-01 | 2021-12-14
75084 | 75084IK | MX0604532 | MX0604532 - TRANSFORMER RETROFIT HANDS 43 | -33534.28 |  | -33534.28 |  |  | 110633.44 | 119596.25 | -8962.81 | 2021-04-22 10:02 | 2022-01-27 | 2021-07-01 | 2022-01-18
75084 | 75084HW | MX0630129 | MX0630129 - WILBERS LN RECONSTRUCTION | -18145.7 |  | -18145.7 |  |  | 55309.18 | 78840.75 | -23531.57 | 2021-06-09 10:02 | 2022-03-23 | 2021-07-01 | 2022-03-06
75084 | 75084IK | MX0705679 | MX0705679 - TBC MXCONV-CAPACITOR AUTOMATION CRE | -9283.29 |  | -9283.29 |  |  | -3.638e-12 | 79086.82 | -79086.82 | 2018-04-09 18:02 | 2022-09-01 | 2020-04-01 | cancelled
75084 | 75084IK | MX0705681 | MX0705681 - TBC MXCONV-CAPACITOR AUTOMATION CRE | -3492.66 |  | -3492.66 |  |  | -9.0949e-13 | 61400.33 | -61400.33 | 2018-05-10 10:01 | 2022-09-01 | 2020-04-01 | cancelled
75084 | 75084IK | MX0817561 | MX0817561 - LIMABURG 43 - PILC REPLACEMENT | -43.22 |  | -43.22 |  |  | 414284.86 | 353340.8 | 60944.06 | 2021-08-26 14:01 | 2022-01-01 | 2021-09-01 | 2021-12-20
75084 | 75084HW | MX0867359 | MX0867359 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -96568.16 |  | -96568.16 |  |  | -96568.16 | 67314.36 | -163882.52 | 2022-09-22 14:01 | 2026-02-26 | 2022-10-01 | open
75084 | 75084HW | MX0880544 | MX0880544 - AERO PARKWAY TURN LANE RELOCATION | 16011.48 |  | 16011.48 |  |  | -22844.87 | 82588.18 | -105433.05 | 2021-05-13 14:02 | 2021-12-30 | 2021-06-01 | 2021-11-01
75084 | 75084HW | MX0915506 | MX0915506 - DEN,ELECTRIC RESIDENTIAL RELOCATION | 80685.92 |  | 80685.92 |  |  | 80685.92 | 31977.77 | 48708.15 | 2022-03-21 10:01 | 2022-07-28 | 2022-04-01 | 2022-07-27
75084 | 75084IK | MX0924912 | MX0924912 - MXCONV-JT- E TRIPLE CROWN SUBD SEC | 3621.78 |  | 3621.78 |  |  | 48562.68 | 213849.76 | -165287.08 | 2017-11-03 14:01 | 2018-03-01 | 2017-11-01 | 2018-05-07
75084 | 75084IK | MX1006763 | MX1006763 - MT ZION - CORRECT CIRCUITS CONFIG- | 19.15 |  | 19.15 |  |  | 17466.8 | 28930.12 | -11463.32 | 2021-05-20 10:02 | 2023-05-01 | 2021-06-01 | 2023-04-17
75084 | 20550043A | MX1064765 | MX1064765 - TBC SUB OPT - DONALDSON 43 CVG SOUT | 12896.28 |  | 12896.28 |  |  | 21402.47 | 228.31 | 21174.16 | 2021-11-01 10:01 | 2024-03-30 | 2021-11-01 | cancelled
75084 | 75084HW | MX1072480 | MX1072480 - CHAPMAN LN STREET RECONSTRUCTION | -10952.76 |  | -10952.76 |  |  | 54540.9 | 60940.85 | -6399.95 | 2021-08-18 14:03 | 2022-02-20 | 2021-09-01 | 2022-02-20
75084 | 21520042A | MX1089667 | MX1089667 - SUB OPT HEBRON 42 RECO PART 1 - 215 | 12915.47 |  | 12915.47 |  |  | 50468.57 | 718305.23 | -667836.66 | 2021-11-02 10:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX1089713 | MX1089713 - SUB OPT HEBRON 42 RECO PT 2 - 21520 | 1970.47 |  | 1970.47 |  |  | 33962.07 | 643727.99 | -609765.92 | 2021-11-02 10:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX1089758 | MX1089758 - SUB OPT HEBRON 42 RECO PART 1 - 215 | 488095.49 |  | 488095.49 |  |  | 529727.03 | 403119.11 | 126607.92 | 2021-11-02 10:02 | 2025-05-29 | 2021-11-01 | open
75084 | 75084HW | MX1096567 | MX1096567 - EXHIBIT A DEK 1812MCI0545DEK, MAKE- | -495.53 |  | -495.53 |  |  | -17006.78 | 49290.4 | -66297.18 | 2019-08-23 14:01 | 2020-02-23 | 2019-08-01 | 2020-01-26
75084 | 22100041A | MX1157551 | MX1157551 - SUB OPT -TRANSFORMER UG THREE PHASE | 34539.82 |  | 34539.82 |  |  | 34539.82 | 20043.46 | 14496.36 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 75084IK | MX1187308 | MX1187308 - DETERIORATED CONDUCTOR - WHITE TOWE | -20638.95 |  | -20638.95 |  |  | 192447.91 | 130833 | 61614.91 | 2020-08-05 10:01 | 2021-11-11 | 2020-08-01 | 2021-11-02
75084 | 23040041A | MX1193729 | MX1193729 - SUB OPT - WHITE TOWER 41 RECO - 230 | 6102.05 |  | 6102.05 |  |  | 6102.05 | 133702.6 | -127600.55 | 2022-02-21 14:01 | 2025-05-29 | 2022-08-01 | open
75084 | 75084HW | MX1204044 | MX1204044 - 7TH AVE LANDSLIDE RELOCATION | 67983.77 |  | 67983.77 |  |  | 67983.77 | 27912.1 | 40071.67 | 2022-02-09 18:01 | 2022-10-18 | 2022-02-01 | 2022-07-27
75084 | 75084IK | MX1261517 | MX1261517 - RLM: 1431 DIXIE: MULTIFAMILY PRIMAR | 27488.55 |  | 27488.55 |  |  | 71413.97 | 48426.64 | 22987.33 | 2021-09-22 10:01 | 2022-07-27 | 2021-10-01 | 2022-06-13
75084 | DEMERKY | MX1264996 | MX1264996 - CAPITAL FLORENCE TB2 REPLACE FAN | -15.62 |  | -15.62 |  |  | 949.56 | 5509.56 | -4560 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01 | 2021-11-07
75084 | TEMERKY | MX1266171 | MX1266171 - CAPITAL SILVER GROVE TB23 REPLACE F | 0.81 |  | 0.81 |  |  | 880.93 | 1613.31 | -732.38 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01 | 2021-11-05
75084 | SG000438F | MX1277606 | MX1277606 - LONGBRANCH 44 PT 2 - RECL 1 MOUNT Z | 3745.5 |  | 3745.5 |  |  | 64505.09 | 47359.32 | 17145.77 | 2021-10-28 14:01 | 2023-03-15 | 2021-11-01 | 2023-03-01
75084 | SG000438F | MX1278018 | MX1278018 - LONGBRANCH 44 PT 2 - RECL 2 MOUNT Z | 4721.67 |  | 4721.67 |  |  | 67843.73 | 46482.63 | 21361.1 | 2021-10-28 14:01 | 2023-01-29 | 2021-11-01 | 2023-01-26
75084 | SG000438F | MX1278081 | MX1278081 - LONGBRANCH 44 PT 2 - RECL 3 MOUNT Z | 50899.82 |  | 50899.82 |  |  | 66454.54 | 46603.9 | 19850.64 | 2021-10-28 14:01 | 2023-03-15 | 2021-11-01 | 2023-03-06
75084 | 75084HW | MX1330863 | MX1330863 - DKY2927 WESTERN AVE STABILIZATION P | 191462.36 |  | 191462.36 |  |  | 205449.1 | 118278.11 | 87170.99 | 2021-12-09 18:02 | 2022-06-09 | 2021-12-01 | 2022-05-22
75084 | 75084HW | MX1386064 | MX1386064 - RLM: 535 MADISON: OH CABLE CLEARS I | 76730.86 |  | 76730.86 |  |  | 121232.67 | 60952.97 | 60279.7 | 2021-09-22 10:01 | 2022-03-17 | 2021-09-01 | 2022-03-16
75084 | 20670041A | MX1393377 | MX1393377 - 0670041A: BUFFINGTON 41 K106-57 INS | 41929.62 |  | 41929.62 |  |  | 43093.63 | 47518.94 | -4425.31 | 2021-11-16 10:01 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | 20670041A | MX1393379 | MX1393379 - 0670041A: BUFFINGTON 41 K106-470 IN | 56822.13 |  | 56822.13 |  |  | 58049.03 | 51507.07 | 6541.96 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1393380 | MX1393380 - 0670045A: BUFFINGTON 45 K106-490 IN | 76939.94 |  | 76939.94 |  |  | 78365.7 | 44782.02 | 33583.68 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1393381 | MX1393381 - 0670045A: BUFFINGTON 45 K117-177 IN | 65791.25 |  | 65791.25 |  |  | 67469.94 | 43388.09 | 24081.85 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393382 | MX1393382 - 0670047A: BUFFINGTON 47 26BN-58 INS | 66362.82 |  | 66362.82 |  |  | 67890.62 | 43289.81 | 24600.81 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393383 | MX1393383 - 0670047A: BUFFINGTON 47 K116-210 IN | 59557.56 |  | 59557.56 |  |  | 61387.69 | 45647.76 | 15739.93 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393384 | MX1393384 - 0670047A: BUFFINGTON 47 K116-611 IN | 61032.49 |  | 61032.49 |  |  | 61935.93 | 47387.16 | 14548.77 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393385 | MX1393385 - 0670047A: BUFFINGTON 47 K116-25 INS | 46484.75 |  | 46484.75 |  |  | 48449.6 | 47908.94 | 540.66 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 22100041A | MX1393386 | MX1393386 - 2100041A: OAKBROOK 41 BNK-8851 INST | 47995.36 |  | 47995.36 |  |  | 47995.36 | 42925.51 | 5069.85 | 2021-10-22 09:12 | 2023-10-26 | 2022-03-01 | 2024-01-21
75084 | DKY2633 | MX1423978 | MX1423978 - VERONA 41 EADS RD RECO - SOG - DKY2 | 211825.36 |  | 211825.36 |  |  | 499942.74 | 292475.66 | 207467.08 | 2020-10-05 18:05 | 2022-05-26 | 2020-11-01 | 2022-05-25
75084 | DKY2447 | MX1424546 | MX1424546 - CONSTANCE 43 LN EXT DKY2447 | 150.87 |  | 150.87 |  |  | 1572877.89 | 1614619.88 | -41741.99 | 2019-06-17 18:02 | 2021-10-18 | 2019-09-01 | 2021-10-17
75084 | DKY2214 | MX1424737 | MX1424737 - CONSTANCE 43 SG DKY2214 | -3055.23 |  | -3055.23 |  |  | 308161.61 | 122817.78 | 185343.83 | 2019-07-25 14:01 | 2021-10-06 | 2019-09-01 | 2021-09-28
75084 | DKY2451 | MX1425894 | MX1425894 - HEBRON 45 LN EXT DKY2451 | 6771.96 |  | 6771.96 |  |  | 496570.63 | 337458.92 | 159111.71 | 2019-10-02 14:01 | 2022-03-22 | 2019-12-01 | 2022-03-15
75084 | CP18SUBK | MX1450766 | MX1450766 - CAPITAL CONSTANCE TB2 REPLACE HS AR | 9423.67 |  | 9423.67 |  |  | 12960.13 | 15137 | -2176.87 | 2019-02-12 14:01 | 2023-09-30 | 2019-04-01 | 2022-11-03
75084 | CP18SUBK | MX1464324 | MX1464324 - CAPITAL RICHWOOD TB3 REPLACE HS ARR | 3347.98 |  | 3347.98 |  |  | 4882.59 | 2837.22 | 2045.37 | 2019-02-12 14:01 | 2022-03-31 | 2019-06-01 | 2022-08-31
75084 | 20550044A | MX1473561 | MX1473561 - 0550044A: DONALDSON 44 26BN-1308 RE | 58281.51 |  | 58281.51 |  |  | 58862.11 | 45686.85 | 13175.26 | 2021-10-21 14:01 | 2025-03-13 | 2021-12-01 | open
75084 | 22410047A | MX1473566 | MX1473566 - 2410047A: FLORENCE 47 BNK-8073 INST | 59758.51 |  | 59758.51 |  |  | 61354.06 | 44184.22 | 17169.84 | 2021-10-21 14:01 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 75084HW | MX1478604 | MX1478604 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 1894.49 |  | 1894.49 |  |  | 4103.73 | 9623.67 | -5519.94 | 2021-06-29 18:02 | 2022-06-23 | 2021-07-01 | 2022-06-21
75084 | CP18SUBK | MX1488550 | MX1488550 - CAPITAL WILDER TB4 REPLACE X0, X1, | 35225.6 |  | 35225.6 |  |  | 57013.86 | 17460.92 | 39552.94 | 2019-02-12 14:01 | 2022-03-31 | 2019-03-01 | 2023-02-28
75084 | 20550043A | MX1518649 | MX1518649 - TBC SUB OPT - AUTOMATED SWITCHGEAR | 4838.47 |  | 4838.47 |  |  | 12177.74 | 66198.38 | -54020.64 | 2021-11-01 10:01 | 2024-03-30 | 2021-11-01 | cancelled
75084 | 20550043A | MX1518718 | MX1518718 - TBC SUB OPT - AUTOMATED SWITCHGEAR | 3710.95 |  | 3710.95 |  |  | 3777.62 | 266431.08 | -262653.46 | 2021-11-01 14:01 | 2024-03-30 | 2021-11-01 | cancelled
75084 | DKY2748 | MX1561891 | MX1561891 - AERO TO CVG SOUTH LN EXT - NEW GEAR | 2969322.09 |  | 2969322.09 |  |  | 2996851.15 | 3423723.84 | -426872.69 | 2021-07-08 08:01 | 2023-10-29 | 2021-08-01 | 2023-09-26
75084 | DEMERKY | MX1593217 | MX1593217 - CAPITAL VILLA TB 1 REPLACE RADIATOR | 84688.94 |  | 84688.94 |  |  | 86603.57 | 69980.49 | 16623.08 | 2021-07-14 10:02 | 2022-03-31 | 2021-10-01 | 2023-03-12
75084 | 20670047A | MX1601007 | MX1601007 - TRANSFORMER UG 3-PHASE END OF LIFE | 26372.36 |  | 26372.36 |  |  | 26372.36 | 18579.03 | 7793.33 | 2022-01-18 18:01 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 20670041A | MX1601008 | MX1601008 - TRANSFORMER UG 3-PHASE END OF LIFE | 45462.77 |  | 45462.77 |  |  | 45462.77 | 34548.66 | 10914.11 | 2021-11-02 10:02 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 20670045A | MX1601009 | MX1601009 - TRANSFORMER UG 3-PHASE END OF LIFE | 25288.07 |  | 25288.07 |  |  | 25288.07 | 18468.23 | 6819.84 | 2022-01-18 18:01 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 22100042A | MX1601011 | MX1601011 - TRANSFORMER UG 3-PHASE END OF LIFE | 26727.18 |  | 26727.18 |  |  | 26727.18 | 18487.57 | 8239.61 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100042A | MX1601014 | MX1601014 - TRANSFORMER UG 3-PHASE END OF LIFE | 23302.14 |  | 23302.14 |  |  | 23302.14 | 17550.06 | 5752.08 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601015 | MX1601015 - TRANSFORMER UG 3-PHASE END OF LIFE | 27359.27 |  | 27359.27 |  |  | 27359.27 | 19732.28 | 7626.99 | 2022-02-21 10:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601017 | MX1601017 - TRANSFORMER UG 3-PHASE END OF LIFE | 33399.03 |  | 33399.03 |  |  | 33399.03 | 17486.11 | 15912.92 | 2022-01-26 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601018 | MX1601018 - TRANSFORMER UG 3-PHASE END OF LIFE | 26414.96 |  | 26414.96 |  |  | 26414.96 | 14965.23 | 11449.73 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22410044A | MX1601020 | MX1601020 - TRANSFORMER UG 3-PHASE END OF LIFE | 892.33 |  | 892.33 |  |  | 892.33 | 17578.41 | -16686.08 | 2022-04-27 10:01 | 2025-07-29 | 2022-04-01 | 2024-04-22
75084 | 22100041A | MX1601021 | MX1601021 - TRANSFORMER UG 3-PHASE END OF LIFE | 20341.79 |  | 20341.79 |  |  | 20341.79 | 15729.91 | 4611.88 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601022 | MX1601022 - TRANSFORMER UG 3-PHASE END OF LIFE | 20567.49 |  | 20567.49 |  |  | 20567.49 | 18253.6 | 2313.89 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601023 | MX1601023 - TRANSFORMER UG 3-PHASE END OF LIFE | 19466.49 |  | 19466.49 |  |  | 19466.49 | 16993.33 | 2473.16 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601025 | MX1601025 - TRANSFORMER UG 3-PHASE END OF LIFE | 22273.01 |  | 22273.01 |  |  | 22273.01 | 17461.9 | 4811.11 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22410042A | MX1601026 | MX1601026 - TRANSFORMER UG 3-PHASE END OF LIFE | 44156.25 |  | 44156.25 |  |  | 44156.25 | 25431.13 | 18725.12 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410046A | MX1601027 | MX1601027 - TRANSFORMER UG 3-PHASE END OF LIFE | 28582.11 |  | 28582.11 |  |  | 28582.11 | 20599.15 | 7982.96 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410044A | MX1601029 | MX1601029 - TRANSFORMER UG 3-PHASE END OF LIFE | 27198.93 |  | 27198.93 |  |  | 27198.93 | 18243.28 | 8955.65 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410044A | MX1601030 | MX1601030 - TRANSFORMER UG 3-PHASE END OF LIFE | 21561.84 |  | 21561.84 |  |  | 21561.84 | 17156.03 | 4405.81 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410046A | MX1601031 | MX1601031 - TRANSFORMER UG 3-PHASE END OF LIFE | 26598.99 |  | 26598.99 |  |  | 26598.99 | 18122.37 | 8476.62 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 20670043A | MX1601032 | MX1601032 - TRANSFORMER UG 3-PHASE END OF LIFE | 18252.54 |  | 18252.54 |  |  | 18252.54 | 16333.77 | 1918.77 | 2022-01-18 18:01 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 20670043A | MX1601033 | MX1601033 - TRANSFORMER UG 3-PHASE END OF LIFE | 20896.95 |  | 20896.95 |  |  | 20896.95 | 16010.57 | 4886.38 | 2022-01-18 18:01 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 75084HW | MX1642381 | MX1642381 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -7205.16 |  | -7205.16 |  |  | 105477 | 97249.08 | 8227.92 | 2021-07-15 14:02 | 2021-11-29 | 2021-07-01 | 2021-10-31
75084 | 75084IK | MX1655106 | MX1655106 - INFRASTRUCTIURE FOR SUBDIVISION D | 112.12 |  | 112.12 |  |  | 22682.49 | 12852.14 | 9830.35 | 2017-11-03 14:01 | 2018-05-18 | 2018-01-01 | 2018-06-15
75084 | 22410044A | MX1701448 | MX1701448 - 2410044A: FLORENCE 44 BNK-6116 REPR | 658.4 |  | 658.4 |  |  | 696.99 | 228.31 | 468.68 | 2021-10-22 13:47 | 2025-07-29 | 2021-11-01 | 2024-04-22
75084 | 20670041A | MX1701449 | MX1701449 - 0670041A: BUFFINGTON 41 K106-488 IN | 44259.99 |  | 44259.99 |  |  | 46305.87 | 40620.48 | 5685.39 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701450 | MX1701450 - 0670041A: BUFFINGTON 41 K107-316 IN | 81219.35 |  | 81219.35 |  |  | 81891.82 | 89359.68 | -7467.86 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670044A | MX1701451 | MX1701451 - 0670044A: BUFFINGTON 44 K105-368 IN | 60988.4 |  | 60988.4 |  |  | 63198.39 | 53559.03 | 9639.36 | 2021-10-01 14:01 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670044A | MX1701452 | MX1701452 - TBC 0670044A: BUFFINGTON 44 K106-11 | 634.23 |  | 634.23 |  |  | 734.11 | 228.31 | 505.8 | 2021-10-21 10:02 | 2023-10-01 | 2021-11-01 | cancelled
75084 | 20670044A | MX1701453 | MX1701453 - 0670044A: BUFFINGTON 44 K106-284 IN | 86095.71 |  | 86095.71 |  |  | 87970.47 | 46702.95 | 41267.52 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670044A | MX1701455 | MX1701455 - 0670044A: BUFFINGTON 44 K107-430 IN | 48250.05 |  | 48250.05 |  |  | 49759 | 41765.51 | 7993.49 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701456 | MX1701456 - TBC 0670045A: BUFFINGTON 45 BNK-562 | 5037.09 |  | 5037.09 |  |  | 5059.81 | 228.31 | 4831.5 | 2021-10-21 10:02 | 2023-10-01 | 2021-12-01 | cancelled
75084 | 20670045A | MX1701457 | MX1701457 - TBC 0670045A: BUFFINGTON 45 BNK-562 | 5557.02 |  | 5557.02 |  |  | 5579.74 | 228.31 | 5351.43 | 2021-10-21 10:02 | 2023-10-01 | 2021-12-01 | cancelled
75084 | 20670045A | MX1701461 | MX1701461 - 0670045A: BUFFINGTON 45 K116-472 IN | 72427.29 |  | 72427.29 |  |  | 73549.49 | 44901.57 | 28647.92 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701462 | MX1701462 - 0670045A: BUFFINGTON 45 K117-112 IN | 60524.18 |  | 60524.18 |  |  | 62530.75 | 44552.1 | 17978.65 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701463 | MX1701463 - 0670045A: BUFFINGTON 45 K117-114 IN | 71127.17 |  | 71127.17 |  |  | 72668.76 | 44985.64 | 27683.12 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701464 | MX1701464 - TBC 0670045A: BUFFINGTON 45 K117-66 | 1.13 |  | 1.13 |  |  | 34.44 | 228.31 | -193.87 | 2021-10-21 10:02 | 2023-10-01 | 2021-10-01 | cancelled
75084 | 20670047A | MX1701466 | MX1701466 - TBC 0670047A: BUFFINGTON 47 K107-31 | 663.22 |  | 663.22 |  |  | 696.53 | 228.31 | 468.22 | 2021-10-21 10:02 | 2023-10-01 | 2021-10-01 | cancelled
75084 | 20670047A | MX1701467 | MX1701467 - 0670047A: BUFFINGTON 47 K116-195 IN | 57177.05 |  | 57177.05 |  |  | 58929.04 | 44567.74 | 14361.3 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1701468 | MX1701468 - 0670047A: BUFFINGTON 47 K116-409 IN | 60906.48 |  | 60906.48 |  |  | 63011.77 | 43947.82 | 19063.95 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701469 | MX1701469 - TBC 0670041A: BUFFINGTON 41 K116-9 | 1669.28 |  | 1669.28 |  |  | 1702.59 | 228.31 | 1474.28 | 2021-10-21 10:02 | 2023-02-28 | 2021-10-01 | open
75084 | 22410042A | MX1701471 | MX1701471 - 2410042A: FLORENCE 42 26BN-1037 REP | 165.91 |  | 165.91 |  |  | 165.91 | 228.31 | -62.4 | 2021-10-22 13:47 | 2025-07-29 | 2022-06-01 | 2024-04-22
75084 | 22410042A | MX1701474 | MX1701474 - 2410042A: FLORENCE 42 26BN-20 INSTA | 54965.07 |  | 54965.07 |  |  | 54965.07 | 42911.98 | 12053.09 | 2021-10-22 13:47 | 2025-07-29 | 2022-03-01 | 2024-04-22
75084 | 22410042A | MX1701475 | MX1701475 - 2410042A: FLORENCE 42 26BN-937 INST | 381.32 |  | 381.32 |  |  | 381.32 | 49631.69 | -49250.37 | 2021-10-22 13:47 | 2025-07-29 | 2022-03-01 | 2024-04-22
75084 | 22410045A | MX1701478 | MX1701478 - TBC 2410045A: FLORENCE 45 BNK-598 | 3371.42 |  | 3371.42 |  |  | 3371.42 | 228.31 | 3143.11 | 2021-10-21 10:02 | 2025-07-29 | 2022-04-01 | open
75084 | 22410045A | MX1701479 | MX1701479 - TBC 2410045A: FLORENCE 45 BTW 25BN | -1010.27 |  | -1010.27 |  |  | 2.8422e-13 | 43634.32 | -43634.32 | 2021-10-21 10:02 | 2024-03-30 | 2021-12-01 | cancelled
75084 | 22410046A | MX1701480 | MX1701480 - TBC 2410046A: FLORENCE 46 30BN-672 | 10669.89 |  | 10669.89 |  |  | 10805.69 | 0 | 10805.69 | 2021-12-07 10:01 | 2025-07-29 | 2021-12-01 | open
75084 | 22410046A | MX1701481 | MX1701481 - 2410046A: FLORENCE 46 31BN-1347 INS | 44481.31 |  | 44481.31 |  |  | 57810.79 | 45195.49 | 12615.3 | 2021-10-21 10:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22100042A | MX1701482 | MX1701482 - 2100042A: OAKBROOK 42 20BN-22 INSTA | 63156.05 |  | 63156.05 |  |  | 64167.39 | 53063.26 | 11104.13 | 2021-10-21 10:02 | 2023-10-26 | 2021-12-01 | 2024-01-21
75084 | 22100042A | MX1701483 | MX1701483 - TBC 2100042A: OAKBROOK 42 25BN-264 | -826.17 |  | -826.17 |  |  | 3.5527e-14 | 41130.11 | -41130.11 | 2021-10-21 10:02 | 2023-03-31 | 2021-12-01 | cancelled
75084 | 22100042A | MX1701485 | MX1701485 - TBC 2100042A: OAKBROOK 42 BTW 25BN | -1253.43 |  | -1253.43 |  |  | -7.4607e-14 | 43167.24 | -43167.24 | 2021-10-21 10:02 | 2023-03-31 | 2021-12-01 | cancelled
75084 | 20550041A | MX1701486 | MX1701486 - 0550041A: DONALDSON 41 26BN-1086 IN | 59936.12 |  | 59936.12 |  |  | 61684.11 | 44820.84 | 16863.27 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701487 | MX1701487 - 0670041A: BUFFINGTON 41 26BN-218 IN | 78634.94 |  | 78634.94 |  |  | 80502.02 | 43932.67 | 36569.35 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701488 | MX1701488 - 0670041A: BUFFINGTON 41 K106-544 IN | 60840.58 |  | 60840.58 |  |  | 62502.3 | 45212.76 | 17289.54 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 22100041A | MX1701489 | MX1701489 - 2100041A: OAKBROOK 41 26BN-1212 INS | 52347.02 |  | 52347.02 |  |  | 52347.02 | 42723.88 | 9623.14 | 2021-10-22 13:47 | 2023-10-26 | 2022-03-01 | 2024-01-21
75084 | 22100041A | MX1701490 | MX1701490 - 2100041A: OAKBROOK 41 BNK-8871 INST | 53967.98 |  | 53967.98 |  |  | 53967.98 | 44384.07 | 9583.91 | 2021-10-22 13:47 | 2023-10-26 | 2022-03-01 | 2024-01-21
75084 | 75084IK | MX1751337 | MX1751337 - JT-E-SANCTUARY VILLAGE PHASE 2 PART | 158942.95 |  | 158942.95 |  |  | 158942.95 | 99395.04 | 59547.91 | 2022-02-01 10:01 | 2022-10-03 | 2022-03-01 | 2022-09-25
75084 | 75084IK | MX1788880 | MX1788880 - JT-E-RESERVE AT BELLEVUE | 203446.72 |  | 203446.72 |  |  | 203446.72 | 122201.43 | 81245.29 | 2022-01-13 14:01 | 2023-03-29 | 2022-04-01 | 2023-02-27
75084 | 75084IK | MX1793644 | MX1793644 - TBC TRANSFORMER RETROFIT - CRESCENT | 15564.12 |  | 15564.12 |  |  | 17851 | 53485.55 | -35634.55 | 2021-09-13 10:02 | 2023-07-01 | 2021-11-01 | cancelled
75084 | SG000435F | MX1848370 | MX1848370 - TBC MXCONV-CAPACITOR AUTOMATION HAN | -2243.59 |  | -2243.59 |  |  | -4.5475e-13 | 69933.97 | -69933.97 | 2019-05-01 10:02 | 2022-09-01 | 2019-06-01 | cancelled
75084 | 75084IK | MX1848383 | MX1848383 - TBC MXCONV-CAPACITOR AUTOMATION MT. | -33190.84 |  | -33190.84 |  |  | -9.0949e-13 | 57824.65 | -57824.65 | 2018-03-12 14:01 | 2022-09-01 | 2018-08-01 | cancelled
75084 | 75084IK | MX1898562 | MX1898562 - JT-E-TRAEMORE PHASE C PART 1B | 98901.31 |  | 98901.31 |  |  | 98901.31 | 55287.54 | 43613.77 | 2021-12-16 10:02 | 2022-08-27 | 2022-01-01 | 2022-07-24
75084 | 75084HW | MX1917337 | MX1917337 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -786.02 |  | -786.02 |  |  | -786.02 | 7317.29 | -8103.31 | 2021-08-10 18:03 | 2022-05-26 | 2021-10-01 | 2022-05-24
75084 | 75084IK | MX1936350 | MX1936350 - JT-E-VILLAGE OF DECOURSEY CREEK | 264451.77 |  | 264451.77 |  |  | 264451.77 | 174468.65 | 89983.12 | 2022-07-27 18:01 | 2023-05-07 | 2022-09-01 | 2023-03-12
75084 | DKY2645 | MX1975019 | MX1975019 - WILDER 43 LN EXT- DKY2645 | 5199.7 |  | 5199.7 |  |  | 69175.04 | 256821.89 | -187646.85 | 2019-07-25 14:01 | 2026-06-29 | 2019-10-01 | open
75084 | DKY2645 | MX1975744 | MX1975744 - WILDER 43 LN EXT RT 9 TO CENTRAL - | 25.25 |  | 25.25 |  |  | 18868.95 | 311628.4 | -292759.45 | 2020-10-09 10:01 | 2026-08-27 | 2021-06-01 | open
75084 | 75084IK | MX1977350 | MX1977350 - OAKBROOK 42 DKY2769 - PART 2 RECOND | 26696.35 |  | 26696.35 |  |  | 30520.17 | 81480.75 | -50960.58 | 2021-08-13 10:12 | 2023-06-04 | 2021-10-01 | 2023-06-04
75084 | 75084IL | MX1977699 | MX1977699 - BBB, NOTRE DAME ACADEMY LIGHTI | 2546.97 |  | 2546.97 |  |  | 165800.74 | 61644.58 | 104156.16 | 2017-11-15 14:01 | 2018-04-03 | 2017-12-01 | 2018-06-03
75084 | 75084IK | MX1998755 | MX1998755 - UG CABLE REPLACE SMALL - REACTIVE ; | 2835.49 |  | 2835.49 |  |  | 2835.49 | 59786.15 | -56950.66 | 2022-10-05 14:01 | 2023-07-06 | 2022-10-01 | 2023-06-13
75084 | 75084HW | MX2030474 | MX2030474 - 145 RICHWOOD; ZKH; COMMERCIAL RELOC | -36733 |  | -36733 |  |  | -36733 | 81325.26 | -118058.26 | 2021-12-09 14:02 | 2023-12-07 | 2022-07-01 | 2023-12-10
75084 | 75084IK | MX2084151 | MX2084151 - DETERIORATED CONDUCTOR - CLARYVILLE | -118477.45 |  | -118477.45 |  |  | 253152.54 | 244553.23 | 8599.31 | 2021-03-24 10:02 | 2022-03-30 | 2021-04-01 | 2022-03-08
75084 | 75084HW | MX2120706 | MX2120706 - TMG- 614 MADISON AVE.-INSTALL - CO | 108787.27 |  | 108787.27 |  |  | 39730.43 | 72130.02 | -32399.59 | 2021-10-08 18:02 | 2022-05-05 | 2021-10-01 | 2022-05-04
75084 | 75084HW | MX2153094 | MX2153094 - KENTABOO AVE RECO PH 2 | 103145.23 |  | 103145.23 |  |  | 103145.23 | 59180.04 | 43965.19 | 2022-03-03 10:01 | 2022-09-08 | 2022-03-01 | 2022-08-09
75084 | 75084HW | MX2156340 | MX2156340 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 4858.31 |  | 4858.31 |  |  | 5288.16 | 1894.7 | 3393.46 | 2019-04-24 14:01 | 2022-03-31 | 2020-10-01 | 2022-03-09
75084 | 20670041A | MX2157464 | MX2157464 - SUB OPT - KY 2020 LINE PATROL UG MI | 1287.09 |  | 1287.09 |  |  | 1287.09 | 1413.68 | -126.59 | 2021-08-31 10:02 | 2023-02-02 | 2022-08-01 | 2023-02-05
75084 | 20670041A | MX2157510 | MX2157510 - SUB OPT - KY 2020 LINE PATROL UG MI | 5404.67 |  | 5404.67 |  |  | 5404.67 | 1413.68 | 3990.99 | 2021-08-31 10:02 | 2023-02-02 | 2022-07-01 | 2023-02-05
75084 | 20670041A | MX2157534 | MX2157534 - SUB OPT - KY 2020 LINE PATROL UG MI | 1797.41 |  | 1797.41 |  |  | 1797.41 | 1413.68 | 383.73 | 2021-08-31 10:02 | 2023-02-02 | 2022-07-01 | 2023-02-05
75084 | 20670041A | MX2157572 | MX2157572 - SUB OPT - KY 2020 LINE PATROL UG MI | 880.47 |  | 880.47 |  |  | 880.47 | 1413.68 | -533.21 | 2021-08-31 10:02 | 2023-02-02 | 2022-06-01 | 2023-02-05
75084 | 20670041A | MX2157620 | MX2157620 - SUB OPT - KY 2020 LINE PATROL UG MI | 1797.41 |  | 1797.41 |  |  | 1797.41 | 1413.68 | 383.73 | 2021-08-31 10:02 | 2023-02-02 | 2022-07-01 | 2023-02-05
75084 | 20670043A | MX2158154 | MX2158154 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 5428.61 |  | 5428.61 |  |  | 22128.3 | 21526.42 | 601.88 | 2021-09-01 10:01 | 2023-02-02 | 2021-12-01 | 2023-02-05
75084 | 20670043A | MX2158161 | MX2158161 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 5999.73 |  | 5999.73 |  |  | 22813.86 | 19560.85 | 3253.01 | 2021-09-01 14:02 | 2023-02-02 | 2021-12-01 | 2023-02-05
75084 | 20670043A | MX2158166 | MX2158166 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 29097.62 |  | 29097.62 |  |  | 29097.62 | 23525.7 | 5571.92 | 2021-09-01 14:02 | 2023-02-02 | 2022-04-01 | 2023-02-05
75084 | 20670047A | MX2158176 | MX2158176 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 37465.51 |  | 37465.51 |  |  | 37465.51 | 26548.65 | 10916.86 | 2021-09-01 14:02 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 22410042A | MX2158190 | MX2158190 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 24204.58 |  | 24204.58 |  |  | 26475.92 | 15692.92 | 10783 | 2021-09-01 14:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410042A | MX2158197 | MX2158197 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 28848.47 |  | 28848.47 |  |  | 28848.47 | 17838.5 | 11009.97 | 2021-09-01 14:02 | 2025-07-29 | 2022-08-01 | 2024-04-22
75084 | 22410044A | MX2158204 | MX2158204 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 9061.82 |  | 9061.82 |  |  | 24006.71 | 20181.62 | 3825.09 | 2021-09-01 14:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410046A | MX2158210 | MX2158210 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 17147.23 |  | 17147.23 |  |  | 36222.87 | 23199.72 | 13023.15 | 2021-09-01 14:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410046A | MX2158216 | MX2158216 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 20057.38 |  | 20057.38 |  |  | 20057.38 | 15237.7 | 4819.68 | 2021-09-01 14:02 | 2025-07-29 | 2022-04-01 | 2024-04-22
75084 | DKY2133 | MX2167975 | MX2167975 - MT ZION RBLD WEAVER RD - DKY2133 | -181748.86 |  | -181748.86 |  |  | 1496988.38 | 2050634.55 | -553646.17 | 2017-10-05 10:01 | 2021-07-29 | 2017-10-01 | 2021-01-28
75084 | 75084IL | MX2173036 | MX2173036 - LED CONVERSION - VILLA HILLS, KY P | 153854.81 |  | 153854.81 |  |  | 282676.03 | 237221.08 | 45454.95 | 2021-07-15 14:02 | 2022-05-26 | 2021-10-01 | 2022-05-16
75084 | 75084IL | MX2174696 | MX2174696 - LED CONVERSION - VILLA HILLS, KY PA | -35091.96 |  | -35091.96 |  |  | 167109.96 | 150836.84 | 16273.12 | 2021-07-15 10:02 | 2022-02-24 | 2021-10-01 | 2022-02-21
75084 | DKY2019 | MX2239971 | MX2239971 - DIXIE 45 LN EXT - DKY2019 | 1868.04 |  | 1868.04 |  |  | 4503.84 | 2882.75 | 1621.09 | 2017-10-18 18:02 | 2021-03-31 | 2018-01-01 | 2021-03-14
75084 | DKY2019 | MX2240623 | MX2240623 - BUFFINGTON 42 UB TRNSFR - DKY2019 | -848.95 |  | -848.95 |  |  | 242575.38 | 11564.24 | 231011.14 | 2017-10-18 18:02 | 2020-10-29 | 2018-01-01 | 2020-10-19
75084 | 22100041A | MX2278295 | MX2278295 - SUB OPT -UG CABLE REPLACE SMALL - P | 286976.58 |  | 286976.58 |  |  | 286976.58 | 201579.18 | 85397.4 | 2022-01-04 14:02 | 2023-10-26 | 2022-01-01 | 2024-01-21
75084 | 75084IK | MX2345743 | MX2345743 - JT, E-EAGLE RIDGE PH. 2 PT. 2 | 23.02 |  | 23.02 |  |  | 8544.81 | 13650.65 | -5105.84 | 2017-12-18 14:01 | 2018-08-31 | 2017-12-01 | 2018-08-02
75084 | 75084IK | MX2370776 | MX2370776 - JT-E-RIFFLE RIDGE PHASE 1B | 55612.92 |  | 55612.92 |  |  | 55612.92 | 62681.31 | -7068.39 | 2022-09-29 14:01 | 2023-05-22 | 2022-11-01 | 2023-06-25
75084 | 75084HW | MX2388911 | MX2388911 - RSC - DESIGN - 602 ALTAMONT AVE | -36795.13 |  | -36795.13 |  |  | 196077.91 | 457249.45 | -261171.54 | 2019-07-23 14:01 | 2020-02-13 | 2019-08-01 | 2020-03-26
75084 | K22BCRHB | MX2498951 | MX2498951 - CAPITAL COVINGTON REPLACE BATTERY B | 16578.56 |  | 16578.56 |  |  | 16578.56 | 16942.46 | -363.9 | 2022-04-12 18:01 | 2023-03-31 | 2022-10-01 | 2023-03-15
75084 | 75084HW | MX2506723 | MX2506723 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 285493.27 |  | 285493.27 |  |  | 289808.43 | 173052.3 | 116756.13 | 2021-10-07 10:02 | 2022-07-28 | 2021-10-01 | 2022-06-13
75084 | 75084 | MX2586486 | MX2586486 - OLD TWENHOFEL MIDDLE SCHOOL | 6480.43 |  | 6480.43 |  |  | 22816.65 | 37465.22 | -14648.57 | 2018-01-09 14:01 | 2018-02-16 | 2018-01-01 | 2018-08-23
75084 | 75084IK | MX2636418 | MX2636418 - RESIDENTIAL PRIMARY/SECONDARY/SVC P | 13162.53 |  | 13162.53 |  |  | 13162.53 | 35816.35 | -22653.82 | 2022-01-18 10:02 | 2022-07-28 | 2022-01-01 | 2022-07-26
75084 | 21890042A | MX2725024 | MX2725024 - CAP UPGRADE, 20BN-92, LIMABURG (189 | 24990.39 |  | 24990.39 |  |  | 24990.39 | 30344.18 | -5353.79 | 2022-03-21 14:01 | 2025-05-01 | 2022-04-01 | 2025-01-01
75084 | 21890043A | MX2725025 | MX2725025 - CAP UPGRADE, 20BN-630, LIMABURG (18 | 26.98 |  | 26.98 |  |  | 26.98 | 28105.61 | -28078.63 | 2022-05-04 10:03 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21990042A | MX2725026 | MX2725026 - CAP UPGRADE, 35BN-330, RICHWOOD (19 | 11.88 |  | 11.88 |  |  | 11.88 | 29461.39 | -29449.51 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX2725027 | MX2725027 - CAP UPGRADE, 41BN-196, RICHWOOD (19 | 40.97 |  | 40.97 |  |  | 40.97 | 19233.66 | -19192.69 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX2725028 | MX2725028 - CAP UPGRADE, 41BN-710, RICHWOOD (19 | 23.77 |  | 23.77 |  |  | 23.77 | 28103.91 | -28080.14 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990043A | MX2725029 | MX2725029 - CAP UPGRADE, 41BN-38, RICHWOOD (199 | 23.77 |  | 23.77 |  |  | 23.77 | 3148.35 | -3124.58 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990043A | MX2725030 | MX2725030 - CAP UPGRADE, BNK-4204, RICHWOOD (19 | 23.77 |  | 23.77 |  |  | 23.77 | 13973.94 | -13950.17 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 22990041A | MX2725052 | MX2725052 - CAP UPGRADE, 11K-34, DECOURSEY (299 | 26.99 |  | 26.99 |  |  | 26.99 | 49209.76 | -49182.77 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX2725053 | MX2725053 - CAP UPGRADE, 11K-613, DECOURSEY (29 | 26.99 |  | 26.99 |  |  | 26.99 | 38928.48 | -38901.49 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX2725055 | MX2725055 - CAP UPGRADE, 11K-654, DECOURSEY (29 | 11.89 |  | 11.89 |  |  | 11.89 | 19513.01 | -19501.12 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX2725056 | MX2725056 - CAP UPGRADE, 11K-69, DECOURSEY (299 | 26.99 |  | 26.99 |  |  | 26.99 | 31166.61 | -31139.62 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 21890042A | MX2725066 | MX2725066 - CAP UPGRADE, 20BN-35, LIMABURG (189 | 23.77 |  | 23.77 |  |  | 23.77 | 29237.95 | -29214.18 | 2022-05-04 10:03 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | DEMERKY | MX2831125 | MX2831125 - CAPITAL WHITE TOWER CB 223 REPLACE | 79.2 |  | 79.2 |  |  | 12260.6 | 14066 | -1805.4 | 2021-11-02 14:02 | 2023-09-30 | 2021-11-01 | 2022-02-27
75084 | 75084IK | MX2866326 | MX2866326 - KENTUCKY 2019 LINE PATROL OH REPLAC | 9792.33 |  | 9792.33 |  |  | 10176.84 | 9381.5 | 795.34 | 2020-09-09 10:01 | 2023-01-13 | 2020-10-01 | 2023-01-30
75084 | 75084HW | MX2869961 | MX2869961 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 12293.68 |  | 12293.68 |  |  | 12293.68 | 327020.35 | -314726.67 | 2021-11-02 18:02 | 2023-03-30 | 2022-05-01 | 2023-03-06
75084 | 75084HW | MX2871461 | MX2871461 - EWD - 1301 4TH - DAYTON 42 - MARINA | -75795.35 |  | -75795.35 |  |  | -75795.35 | 58196.98 | -133992.33 | 2022-10-24 10:02 | 2023-09-28 | 2022-12-01 | 2023-10-04
75084 | 75084HW | MX2972789 | MX2972789 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -26726.51 |  | -26726.51 |  |  | 758456.93 | 304950.18 | 453506.75 | 2019-10-21 18:01 | 2021-08-05 | 2020-04-01 | 2021-08-05
75084 | 75084IK | MX3045963 | MX3045963 - DECLARED CIRCUIT - DONALDSON 41 - 2 | 968.5 |  | 968.5 |  |  | 149923.74 | 510594.76 | -360671.02 | 2019-09-09 14:01 | 2031-02-27 | 2019-11-01 | open
75084 | DEMERKY | MX3062206 | MX3062206 - CAPITAL CRITTENDEN TB 2 REPLACE 3 H | 3.12 |  | 3.12 |  |  | 482.86 | 10342.05 | -9859.19 | 2021-11-22 10:01 | 2023-09-30 | 2021-11-01 | 2023-07-18
75084 | DKYHW2672 | MX3146693 | MX3146693 - HEBRON POLE INST - DKYHW2672 | -196110.71 |  | -196110.71 |  |  | -212376.05 | 263392.57 | -475768.62 | 2019-06-26 14:01 | 2020-09-28 | 2019-07-01 | 2020-07-22
75084 | DKYHW2672 | MX3147011 | MX3147011 - HEBRON OH WORK - DKYHW2672 | -126888.16 |  | -126888.16 |  |  | -154178.57 | 221633.49 | -375812.06 | 2019-06-26 14:01 | 2021-12-29 | 2019-08-01 | 2021-11-21
75084 | 75084HW | MX3147077 | MX3147077 - HW CROSSING REMOVAL - DKYHW2672 | -168.27 |  | -168.27 |  |  | 14.02 | 436.56 | -422.54 | 2019-06-26 14:01 | 2020-08-01 | 2019-08-01 | 2020-10-06
75084 | DKYHW2672 | MX3147307 | MX3147307 - HEBRON 41 42 OH RELO - DKYHW2672 | 26451.04 |  | 26451.04 |  |  | 26285.4 | 38243.38 | -11957.98 | 2019-06-26 14:01 | 2020-10-13 | 2019-08-01 | 2020-10-19
75084 | M210520 | MX3170570 | MX3170570 - F6782 (M21044201) EMERGENT BUFF-FLO | 18318.06 |  | 18318.06 |  |  | 18318.06 | 13640.52 | 4677.54 | 2021-12-13 10:02 | 2022-07-29 | 2022-01-01 | 2022-07-26
75084 | 75084IK | MX3188132 | MX3188132 - BBB-TAPESTRY AT TURFWAY - ARLINGTON | 195277.98 |  | 195277.98 |  |  | 195277.98 | 233096.92 | -37818.94 | 2022-07-13 10:01 | 2022-12-11 | 2022-08-01 | 2022-11-29
75084 | DEMERKY | MX3192862 | MX3192862 - CAPITAL WHITE TOWER CIR 42 REPLACE | 0.7 |  | 0.7 |  |  | 109.05 | 4853.76 | -4744.71 | 2021-12-13 14:02 | 2024-03-30 | 2021-12-01 | 2023-11-19
75084 | DEMERKY | MX3194100 | MX3194100 - CAPITAL ATLAS REPLACE BANK 1 BATTER | 3320.55 |  | 3320.55 |  |  | 3320.55 | 6436.15 | -3115.6 | 2021-12-08 10:06 | 2023-03-31 | 2022-07-01 | 2022-10-26
75084 | 75084IK | MX3222426 | MX3222426 - JT-E-TUSCANY SECTION 021 | 106488.07 |  | 106488.07 |  |  | 106488.07 | 56036.05 | 50452.02 | 2022-03-08 14:24 | 2022-10-23 | 2022-04-01 | 2022-10-30
75084 | DKY2211 | MX3375944 | MX3375944 - COLD SPRING 49 - NEW UG EXIT/TERMIN | 38001.57 |  | 38001.57 |  |  | 38001.57 | 22488.76 | 15512.81 | 2022-04-25 14:01 | 2023-02-28 | 2022-04-01 | 2023-02-19
75084 | 75084IL | MX3586213 | MX3586213 - CITY OF WILDER STREET LIGHT UPGRADE | 78573.43 |  | 78573.43 |  |  | 54905.78 | 58334.47 | -3428.69 | 2020-02-20 10:01 | 2020-08-06 | 2020-02-01 | 2020-06-28
75084 | DEMERKY | MX3826243 | MX3826243 - CAPITAL RICHWOOD TB1 REPLACE FAN | 2210.34 |  | 2210.34 |  |  | 2210.34 | 5524.97 | -3314.63 | 2022-01-19 10:01 | 2023-03-31 | 2022-04-01 | 2022-08-16
75084 | DKY2645 | MX3890113 | MX3890113 - SG-CAPACITY NEEDS OUTSIDE THE SUBST | 54946.12 |  | 54946.12 |  |  | 54946.12 | 48733.93 | 6212.19 | 2022-03-25 18:01 | 2023-01-29 | 2022-04-01 | 2023-02-14
75084 | DKY2645 | MX3891718 | MX3891718 - WILDER 43 RECLOSER 2 - N/O NEAR POL | 46843.19 |  | 46843.19 |  |  | 46843.19 | 43668.27 | 3174.92 | 2022-03-30 14:01 | 2023-01-29 | 2022-04-01 | 2023-02-16
75084 | DKY2645 | MX3893236 | MX3893236 - WILDER 43 RECLOSER 3 - N/O NEAR POL | 50118.21 |  | 50118.21 |  |  | 50118.21 | 44282.29 | 5835.92 | 2022-03-30 14:01 | 2023-01-29 | 2022-04-01 | 2023-03-06
75084 | 75084IK | MX3953933 | MX3953933 - COMMERCIAL PRIMARY/SECONDARY/SVC | 97613.56 |  | 97613.56 |  |  | 97613.56 | 138617.24 | -41003.68 | 2022-02-22 10:01 | 2022-11-17 | 2022-03-01 | 2022-11-09
75084 | 20550043A | MX3999738 | MX3999738 - SUB OPT - DONALDSON 43 CVG SOUTH RE | 705228.48 |  | 705228.48 |  |  | 705228.48 | 858671.15 | -153442.67 | 2022-02-24 18:01 | 2025-03-13 | 2022-02-01 | open
75084 | 75084IK | MX4074648 | MX4074648 - KSL; 7435 INDUSTRIAL; DIXIE 41; PER | 121812.36 |  | 121812.36 |  |  | 121812.36 | 115672.98 | 6139.38 | 2022-08-10 14:06 | 2023-02-09 | 2022-08-01 | 2023-01-23
75084 | 75084IL | MX4076157 | MX4076157 - CITY OF UNION, DECORATIVE UPGRADE 2 | 56972.22 |  | 56972.22 |  |  | 56972.22 | 53134.23 | 3837.99 | 2022-04-07 14:01 | 2022-09-29 | 2022-05-01 | 2022-09-01
75084 | 75084IK | MX4092751 | MX4092751 - JT-E-ALEXANDRIA FLATS PHASE 2; BLDG | 103820.97 |  | 103820.97 |  |  | 103820.97 | 66216.2 | 37604.77 | 2022-06-23 14:01 | 2022-12-29 | 2022-08-01 | 2022-12-25
75084 | 75084IK | MX4092859 | MX4092859 - JT-E-ALEXANDRIA FLATS PHASE 3; BLDG | 66194.72 |  | 66194.72 |  |  | 66194.72 | 79797.38 | -13602.66 | 2022-06-28 14:01 | 2024-01-29 | 2022-11-01 | 2024-02-04
75084 | M190298 | MX4154102 | MX4154102 - F5967 - REBUILD MARSHALL RD - M1902 | 397977.78 |  | 397977.78 |  |  | 397977.78 | 287220.92 | 110756.86 | 2022-02-18 14:01 | 2022-10-27 | 2022-04-01 | 2022-11-06
75084 | 75084IK | MX4154470 | MX4154470 - OPEN LOOP - CABLE UG REPLACE SMALL- | 786893.94 |  | 786893.94 |  |  | 795749.42 | 74076.7 | 721672.72 | 2021-10-06 10:02 | 2023-05-16 | 2021-12-01 | 2023-03-09
75084 | M190298 | MX4193270 | MX4193270 - F5967 - REBUILD - MARSHALL @ 3 POIN | 22274.02 |  | 22274.02 |  |  | 22274.02 | 60150.53 | -37876.51 | 2022-02-18 14:01 | 2023-04-27 | 2022-04-01 | 2023-04-25
75084 | M190298 | MX4194121 | MX4194121 - F5967 (M190298) - REBUILD - 10768 M | 8492.44 |  | 8492.44 |  |  | 8492.44 | 47328.8 | -38836.36 | 2022-02-18 14:01 | 2024-07-29 | 2022-04-01 | 2024-07-23
75084 | M190298 | MX4194619 | MX4194619 - F5967 REBUILD DECOURSEY TO MANN RD | 16571.1 |  | 16571.1 |  |  | 16571.1 | 169874.43 | -153303.33 | 2022-02-18 14:01 | 2024-03-30 | 2022-04-01 | 2024-03-12
75084 | M190297 | MX4194871 | MX4194871 - F5967 - REBUILD - CLARYVILLE TO SR | 228190.43 |  | 228190.43 |  |  | 228190.43 | 870687.63 | -642497.2 | 2022-02-18 14:01 | 2024-03-30 | 2022-04-01 | 2024-03-12
75084 | 75084HW | MX4216127 | MX4216127 - US RT 25 ROADWAY WIDENING - WALTON | 96899.68 |  | 96899.68 |  |  | 96899.68 | 93722.34 | 3177.34 | 2022-04-29 10:01 | 2022-12-29 | 2022-04-01 | 2023-01-11
75084 | DEMERKY | MX4267484 | MX4267484 - CAPITAL VERONA REPLACE COMM & CONTR | 32155.72 |  | 32155.72 |  |  | 32155.72 | 39198.94 | -7043.22 | 2022-03-09 10:01 | 2024-03-30 | 2022-04-01 | 2023-09-04
75084 | 75084IK | MX4279989 | MX4279989 - WHISTLER COVE - INFRASTRUCTURE WORK | 810.13 |  | 810.13 |  |  | 810.13 | 268291.37 | -267481.24 | 2022-04-21 18:02 | 2025-09-11 | 2022-04-01 | open
75084 | 75084IK | MX4300672 | MX4300672 - COMMERCIAL PRIMARY/SECONDARY/SVC | 22638.39 |  | 22638.39 |  |  | 22638.39 | 78997.11 | -56358.72 | 2022-03-16 18:01 | 2022-12-08 | 2022-05-01 | 2022-11-29
75084 | DEMERKY | MX4338188 | MX4338188 - CAPITAL DIXIE TB2 REPLACE FANS | 7526.32 |  | 7526.32 |  |  | 7526.32 | 8886.27 | -1359.95 | 2022-03-03 10:01 | 2023-03-31 | 2022-05-01 | 2022-09-07
75084 | 75084IK | MX4412975 | MX4412975 - DETERIORATED CONDUCTOR (WILDER 42) | 35146.61 |  | 35146.61 |  |  | 134825.05 | 55221.15 | 79603.9 | 2020-07-02 10:01 | 2022-12-15 | 2020-07-01 | 2022-11-23
75084 | 75084HW | MX4426943 | MX4426943 - RELOCATION HIGHWAY DOT NOT BILLABLE | 53120.77 |  | 53120.77 |  |  | 53120.77 | 51328.14 | 1792.63 | 2022-03-28 14:01 | 2022-10-03 | 2022-04-01 | 2022-08-14
75084 | 75084IK | MX4497255 | MX4497255 - OPEN LOOP - CABLE UG REPLACE SMALL- | 102041.41 |  | 102041.41 |  |  | 107897.75 | 57496.83 | 50400.92 | 2021-10-06 10:02 | 2022-06-29 | 2021-12-01 | 2022-06-13
75084 | M190259 | MX4517175 | MX4517175 - F6782 X-FER UB FOR 8 WOOD TO STEEL | 122656.34 |  | 122656.34 |  |  | 183559.8 | 89534.31 | 94025.49 | 2019-11-26 18:01 | 2022-10-13 | 2020-07-01 | 2022-10-16
75084 | SG990022F | MX4546275 | MX4546275 - 2021 PROACTIVE RECL RPL, KNK-5759, | 2793.35 |  | 2793.35 |  |  | 66077.3 | 53891.15 | 12186.15 | 2021-03-25 10:02 | 2022-12-29 | 2021-04-01 | 2022-11-28
75084 | 75084IK | MX4684560 | MX4684560 - EWD; 7900 FOUNDATION DR; BUFFINGTON | 61980.3 |  | 61980.3 |  |  | 61980.3 | 50059.55 | 11920.75 | 2022-07-29 10:01 | 2022-12-08 | 2022-08-01 | 2022-12-05
75084 | 75084HW | MX4698193 | MX4698193 - MAKE-READY, 2203MCI0285DEK - MCI PR | -10588.53 |  | -10588.53 |  |  | -10588.53 | 46988.34 | -57576.87 | 2022-09-12 10:01 | 2023-03-22 | 2022-09-01 | 2023-02-21
75084 | 75084HW | MX4698796 | MX4698796 - MAKE-READY, 2203MCI0287DEK, MCI PRO | -19876.08 |  | -19876.08 |  |  | -19876.08 | 38488.98 | -58365.06 | 2022-09-22 14:01 | 2023-04-06 | 2022-09-01 | 2023-03-05
75084 | 75084IL | MX4765729 | MX4765729 - 7050 NEW BUFFINGTON RD AREA LIGHT P | 86226.16 |  | 86226.16 |  |  | 86226.16 | 83809.8 | 2416.36 | 2022-05-06 10:01 | 2023-02-28 | 2022-08-01 | 2023-02-20
75084 | DKY2754 | MX4778133 | MX4778133 - THOMAS MORE 41 LN EXT DKY2754 - N/C | 35707.21 |  | 35707.21 |  |  | 35707.21 | 47092.97 | -11385.76 | 2022-04-13 10:01 | 2023-05-29 | 2022-06-01 | 2023-05-29
75084 | DKY2754 | MX4778303 | MX4778303 - THOMAS MORE 41 LN EXT DKY2754 - N/O | 35866.46 |  | 35866.46 |  |  | 35866.46 | 48376.69 | -12510.23 | 2022-04-13 10:01 | 2023-05-29 | 2022-08-01 | 2023-05-29
75084 | DKY2754 | MX4778407 | MX4778407 - THOMAS MORE 41 LN EXT DKY2754 - ATO | 5733 |  | 5733 |  |  | 5733 | 128549.24 | -122816.24 | 2022-04-13 14:01 | 2024-02-15 | 2022-06-01 | 2024-02-05
75084 | M190233 | MX4864988 | MX4864988 - F5983 DAYTON TO LAFARGE X-FER UB FO | 252291.62 |  | 252291.62 |  |  | 382136.06 | 222076.22 | 160059.84 | 2019-11-26 18:01 | 2023-01-29 | 2020-12-01 | 2022-11-09
75084 | M190233 | MX4865782 | MX4865782 - F5983 LAFARGE TO SILVER GROVE X-FER | -4448.99 |  | -4448.99 |  |  | 36275.25 | 25682.58 | 10592.67 | 2019-11-26 14:01 | 2022-03-31 | 2020-09-01 | 2022-03-01
75084 | 75084IK | MX4866781 | MX4866781 - DETERIORATED CONDUCTOR - CLARYVILLE | -95140.08 |  | -95140.08 |  |  | 305535.03 | 254760.91 | 50774.12 | 2021-03-24 10:02 | 2022-02-28 | 2021-04-01 | 2022-02-13
75084 | 75084IK | MX4866850 | MX4866850 - DETERIORATED CONDUCTOR - CLARYVILLE | -12208.97 |  | -12208.97 |  |  | 8551.89 | 27702.32 | -19150.43 | 2021-05-07 18:02 | 2022-02-24 | 2021-05-01 | 2021-11-03
75084 | M190244 | MX4876167 | MX4876167 - F2166 WEST END TO COVINGTON X-FER U | 1324.8 |  | 1324.8 |  |  | 61020.02 | 25239.31 | 35780.71 | 2019-11-27 14:01 | 2021-11-29 | 2020-12-01 | 2021-08-09
75084 | M190244 | MX4877019 | MX4877019 - F2166 COVINGTON TO NEWPORT STEEL X- | 18171.67 |  | 18171.67 |  |  | 41418.03 | 33025.21 | 8392.82 | 2019-11-27 14:01 | 2022-07-29 | 2020-10-01 | 2022-06-09
75084 | 75084IL | MX4930891 | MX4930891 - MAIN ST FLORENCE KY STREET LIGHT IN | 84814.5 |  | 84814.5 |  |  | 84814.5 | 160076.63 | -75262.13 | 2022-06-29 18:01 | 2023-09-28 | 2022-07-01 | 2023-09-05
75084 | 75084IK | MX4984124 | MX4984124 - LONGBRANCH 44 PT 2 C- DKY2132 | 106735.77 |  | 106735.77 |  |  | 106735.77 | 35300.69 | 71435.08 | 2022-05-02 14:01 | 2023-03-31 | 2022-06-01 | 2023-03-05
75084 | 75084IK | MX5069648 | MX5069648 - JT-E-THE RESERVE AT MEADOWOOD II PH | 68069.24 |  | 68069.24 |  |  | 68069.24 | 88433 | -20363.76 | 2022-10-31 14:02 | 2023-05-30 | 2022-11-01 | 2023-05-24
75084 | 75084IK | MX5095589 | MX5095589 - JT-E-WESTBROOK ESTATES PHASE 4 | 40577.69 |  | 40577.69 |  |  | 40577.69 | 68663.84 | -28086.15 | 2022-11-10 10:02 | 2023-05-31 | 2022-12-01 | 2023-08-14
75084 | 22410047A | MX5222181 | MX5222181 - TBC 2410047A: FLORENCE 47 BNK-6158 | 777.33 |  | 777.33 |  |  | 777.33 | 0 | 777.33 | 2022-05-27 10:01 | 2025-07-29 | 2022-10-01 | open
75084 | 75084IL | MX5231051 | MX5231051 - 1590 WORLDWIDE BLVD LIGHT INSTALL | 37081.56 |  | 37081.56 |  |  | 37081.56 | 53243.59 | -16162.03 | 2022-05-24 18:01 | 2023-05-29 | 2022-11-01 | 2023-04-24
75084 | DEMERKY | MX5232305 | MX5232305 - CAPITAL HEBRON VR2 REPLACE 3 LA'S | 4265.66 |  | 4265.66 |  |  | 4265.66 | 4259 | 6.66 | 2022-05-31 18:01 | 2024-03-30 | 2022-06-01 | 2022-08-25
75084 | 22050041A | MX5254697 | MX5254697 - TBC 22050041A: ALEXANDRIA SOUTH 41 | 127.03 |  | 127.03 |  |  | 127.03 | 228.31 | -101.28 | 2022-06-01 10:05 | 2024-09-28 | 2022-09-01 | cancelled
75084 | 22050041A | MX5254698 | MX5254698 - 0670041A: ALEXANDRIA SOUTH 43 43CA- | 920.49 |  | 920.49 |  |  | 920.49 | 46123.82 | -45203.33 | 2022-06-01 10:05 | 2025-07-29 | 2022-09-01 | 2023-12-18
75084 | 20700041A | MX5254699 | MX5254699 - 20700041A: CRESCENT 41 K84-49 INST | 31939.89 |  | 31939.89 |  |  | 31939.89 | 49684.85 | -17744.96 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700041A | MX5254700 | MX5254700 - TBC 20700041A: CRESCENT 41 K84-264 | 170.21 |  | 170.21 |  |  | 170.21 | 53550.62 | -53380.41 | 2022-06-01 14:01 | 2024-12-29 | 2022-09-01 | cancelled
75084 | 20700043A | MX5254701 | MX5254701 - 20700043A: CRESCENT 43 KNK-2979 IN | 1162.41 |  | 1162.41 |  |  | 1162.41 | 45553.52 | -44391.11 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5254702 | MX5254702 - 20700043A: CRESCENT 43 KNK-4875 IN | 10542.13 |  | 10542.13 |  |  | 10542.13 | 39758.75 | -29216.62 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5254704 | MX5254704 - 20700043A: CRESCENT 43 K73-477 INS | 10213.86 |  | 10213.86 |  |  | 10213.86 | 45415.87 | -35202.01 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20090041A | MX5254705 | MX5254705 - 20090041A: KENTON 41 K84-242 INSTA | 1362.78 |  | 1362.78 |  |  | 1362.78 | 48874.89 | -47512.11 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20090041A | MX5254707 | MX5254707 - 20090041A: KENTON 41 K84-378 INSTA | 1817.72 |  | 1817.72 |  |  | 1817.72 | 46271.61 | -44453.89 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20090041A | MX5254708 | MX5254708 - 20090041A: KENTON 41 KNK-1583 INST | 1322.01 |  | 1322.01 |  |  | 1322.01 | 46394.69 | -45072.68 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 22430041A | MX5254711 | MX5254711 - 22430041A: VILLA 41 K84-96 INSTALL | 1437.79 |  | 1437.79 |  |  | 1437.79 | 49317.89 | -47880.1 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 22430041A | MX5254713 | MX5254713 - 22430041A: VILLA 41 K84-71 INSTALL | 1508.22 |  | 1508.22 |  |  | 1508.22 | 46249.42 | -44741.2 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20700045A | MX5254714 | MX5254714 - 20700045A: CRESCENT 45 K92-315 INST | 1404.63 |  | 1404.63 |  |  | 1404.63 | 48778.18 | -47373.55 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20700045A | MX5254717 | MX5254717 - 20700045A: CRESCENT 45 K92-29 INSTA | 1836.69 |  | 1836.69 |  |  | 1836.69 | 52757.22 | -50920.53 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20700045A | MX5254718 | MX5254718 - 20700045A: CRESCENT 45 K92-191 INS | 1424.25 |  | 1424.25 |  |  | 1424.25 | 51151.19 | -49726.94 | 2022-11-15 18:02 | 2025-07-29 | 2022-11-01 | open
75084 | 21520041A | MX5254719 | MX5254719 - 21520041A: HEBRON 41 13BN-79 INSTAL | 951.45 |  | 951.45 |  |  | 951.45 | 53783.36 | -52831.91 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254720 | MX5254720 - 21520041A: HEBRON 41 13BN-31 INSTAL | 696.37 |  | 696.37 |  |  | 696.37 | 54720.38 | -54024.01 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254721 | MX5254721 - 21520041A: HEBRON 41 14BN-576 INSTA | 696.37 |  | 696.37 |  |  | 696.37 | 52135.28 | -51438.91 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254722 | MX5254722 - 21520041A: HEBRON 41 14BN-618 INSTA | 431.78 |  | 431.78 |  |  | 431.78 | 46384.27 | -45952.49 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254725 | MX5254725 - 21520041A: HEBRON 41 BNK-2081 INSTA | 642.78 |  | 642.78 |  |  | 642.78 | 44227.55 | -43584.77 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21890041A | MX5254726 | MX5254726 - 21890041A: LIMABURG 41 14BN-28 INST | 198.02 |  | 198.02 |  |  | 198.02 | 52320.45 | -52122.43 | 2022-06-01 18:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX5254727 | MX5254727 - 21890042A: LIMABURG 42 19BN-229 INS | 1822.96 |  | 1822.96 |  |  | 1822.96 | 51529.71 | -49706.75 | 2022-06-06 10:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX5254728 | MX5254728 - 21890042A: LIMABURG 42 19BN-224 INS | 11.88 |  | 11.88 |  |  | 11.88 | 47841.9 | -47830.02 | 2022-06-01 18:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21990041A | MX5254732 | MX5254732 - 21990041A: RICHWOOD 41 BNK-8296 IN | 102.61 |  | 102.61 |  |  | 102.61 | 55897.38 | -55794.77 | 2022-06-06 10:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990042A | MX5254734 | MX5254734 - 21990042A: RICHWOOD 42 36BN-343 IN | 26.99 |  | 26.99 |  |  | 26.99 | 82506.84 | -82479.85 | 2022-06-06 10:01 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX5254737 | MX5254737 - 21990042A: RICHWOOD 42 36BN-313 IN | 11.89 |  | 11.89 |  |  | 11.89 | 59573.72 | -59561.83 | 2022-06-06 10:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040041A | MX5254738 | MX5254738 - 23040041A: WHITE TOWER 41 22K-172 | 26.99 |  | 26.99 |  |  | 26.99 | 46046.05 | -46019.06 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040041A | MX5254739 | MX5254739 - 23040041A: WHITE TOWER 41 15K-316 | 26.99 |  | 26.99 |  |  | 26.99 | 47655.21 | -47628.22 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040043A | MX5254741 | MX5254741 - 23040043A: WHITE TOWER 43 19K-776 | 26.99 |  | 26.99 |  |  | 26.99 | 46320.4 | -46293.41 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040043A | MX5254742 | MX5254742 - 23040043A: WHITE TOWER 43 15K-702 | 11.89 |  | 11.89 |  |  | 11.89 | 56540.68 | -56528.79 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 20700043A | MX5254743 | MX5254743 - 20700043A: CRESCENT 43 K83-332 REM | 10892.73 |  | 10892.73 |  |  | 10892.73 | 42896.55 | -32003.82 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 23040043A | MX5254744 | MX5254744 - TBC 23040041A: WHITE TOWER 43 KNK- | 1750.42 |  | 1750.42 |  |  | 1750.42 | 228.31 | 1522.11 | 2022-06-07 14:01 | 2024-03-30 | 2022-11-01 | cancelled
75084 | KYGLT21 | MX5261357 | MX5261357 - GLT F5962 (KYGLT2102) 14-POLES | 6014.35 |  | 6014.35 |  |  | 6014.35 | 133247.71 | -127233.36 | 2022-08-05 14:01 | 2025-03-31 | 2022-08-01 | 2024-12-24
75084 | 20550043A | MX5291241 | MX5291241 - SUB OPT - DONALDSON 43 NC SWITCH - | 11576.76 |  | 11576.76 |  |  | 11576.76 | 7347.08 | 4229.68 | 2022-05-31 14:01 | 2025-01-29 | 2022-08-01 | open
75084 | 75084HW | MX5301338 | MX5301338 - KENTABOO AVE RECONSTRUCTION - PHASE | -4812.28 |  | -4812.28 |  |  | 137068.49 | 202549.12 | -65480.63 | 2020-07-08 18:01 | 2021-05-04 | 2020-07-01 | 2021-04-28
75084 | 21890042A | MX5313258 | MX5313258 - SUB-OPT - 21890042A: LIMABURG 42 FL | 2068.85 |  | 2068.85 |  |  | 2068.85 | 261724.52 | -259655.67 | 2022-06-02 14:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | TLRKY22 | MX5322324 | MX5322324 - GLT F3568 TLRKY2201 - FIF RPL 20G-3 | 8815.44 |  | 8815.44 |  |  | 8815.44 | 7472.73 | 1342.71 | 2022-06-03 10:01 | 2022-12-30 | 2022-10-01 | 2023-01-23
75084 | 75084HW | MX5322977 | MX5322977 - EMERGENT CVG-7 RELOCATION - LIMABUR | 29869.53 |  | 29869.53 |  |  | 29869.53 | 311090.78 | -281221.25 | 2022-06-02 14:01 | 2025-05-29 | 2022-07-01 | open
75084 | DEMERKY | MX5324522 | MX5324522 - CAPITAL RICHWOOD CIR 42 REPLACE HOO | 7125.74 |  | 7125.74 |  |  | 7125.74 | 6727.96 | 397.78 | 2022-06-02 14:01 | 2023-03-31 | 2022-06-01 | 2022-11-03
75084 | 21990042A | MX5352573 | MX5352573 - SUB OPT - 21990042A- RECLOSER - 41B | 925.03 |  | 925.03 |  |  | 925.03 | 45552.6 | -44627.57 | 2022-06-07 14:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990043A | MX5353113 | MX5353113 - SUB OPT -21990043A - RECLOSER 41BN- | 846.94 |  | 846.94 |  |  | 846.94 | 45749.7 | -44902.76 | 2022-06-07 14:01 | 2025-02-28 | 2022-11-01 | open
75084 | DKY2618 | MX5358828 | MX5358828 - PERMANENT PRIMARY SERVICE - DKY2618 | 156064.41 |  | 156064.41 |  |  | 1671211.93 | 326336.3 | 1344875.63 | 2020-01-16 10:01 | 2023-09-28 | 2020-10-01 | 2023-09-11
75084 | 22410042A | MX5441962 | MX5441962 - 2410042A: FLORENCE 42 26BN-1083 INS | 50066.94 |  | 50066.94 |  |  | 50066.94 | 52442.19 | -2375.25 | 2022-07-26 14:01 | 2025-07-29 | 2022-07-01 | 2024-04-22
75084 | 75084HW | MX5609466 | MX5609466 - TMG- COMM. RELOCATION CAPITAL CIAC | -6595.66 |  | -6595.66 |  |  | -6595.66 | 52404.59 | -59000.25 | 2022-09-19 10:01 | 2023-05-04 | 2022-10-01 | 2023-03-16
75084 | 75084IK | MX5630972 | MX5630972 - MAKE READY - BALLYSHANNON SUB ~ HAT | 5731.14 |  | 5731.14 |  |  | 5731.14 | 304318.93 | -298587.79 | 2022-09-15 10:01 | 2023-08-29 | 2022-09-01 | 2023-08-08
75084 | KFP738034 | MX5738034 | MX5738034 - SG-CAPACITY NEEDS OUTSIDE THE SUBST | 4607.49 |  | 4607.49 |  |  | 4607.49 | 20482.63 | -15875.14 | 2022-07-15 18:01 | 2023-01-11 | 2022-10-01 | 2023-01-24
75084 | 75084IK | MX5744215 | MX5744215 - JT-E-THE HILLS OF CRESCENT SPRINGS | 112541.36 |  | 112541.36 |  |  | 112541.36 | 88777.38 | 23763.98 | 2022-10-26 14:02 | 2023-04-09 | 2022-11-01 | 2023-03-22
75084 | DKY2131 | MX5764593 | MX5764593 - KENTON 42 - HIGHWAY CROSSING | 24387.5 |  | 24387.5 |  |  | 38397.4 | 75452.28 | -37054.88 | 2020-05-06 14:01 | 2025-05-01 | 2020-10-01 | open
75084 | 75084IK | MX5778428 | MX5778428 - MAKE READY FOR MEMORIAL PT PHASE 1 | 17233.67 |  | 17233.67 |  |  | 17233.67 | 37851.61 | -20617.94 | 2022-11-03 18:02 | 2023-05-29 | 2022-11-01 | 2023-03-13
75084 | 22100042A | MX5820935 | MX5820935 - SUB OPT -TRANSFORMER UG THREE PHASE | 1174.8 |  | 1174.8 |  |  | 1174.8 | 18173.93 | -16999.13 | 2022-09-06 14:01 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 20550043A | MX5820950 | MX5820950 - SUB OPT -TRANSFORMER UG THREE PHASE | 1126.76 |  | 1126.76 |  |  | 1126.76 | 18503.79 | -17377.03 | 2022-09-09 10:01 | 2025-03-13 | 2022-09-01 | open
75084 | 22410045A | MX5820993 | MX5820993 - SUB OPT -TRANSFORMER UG THREE PHASE | 1278.58 |  | 1278.58 |  |  | 1278.58 | 17674.38 | -16395.8 | 2022-09-22 14:01 | 2025-07-29 | 2022-09-01 | 2024-04-22
75084 | 22410046A | MX5820998 | MX5820998 - SUB OPT -TRANSFORMER UG THREE PHASE | 1742.89 |  | 1742.89 |  |  | 1742.89 | 17804.27 | -16061.38 | 2022-09-06 14:01 | 2025-07-29 | 2022-09-01 | 2024-04-22
75084 | 22410045A | MX5821004 | MX5821004 - TBC SUB OPT -TRANSFORMER UG THREE | 1092.43 |  | 1092.43 |  |  | 1092.43 | 228.31 | 864.12 | 2022-09-06 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20550044A | MX5821049 | MX5821049 - SUB OPT -TRANSFORMER UG 3-PHASE END | 1831.58 |  | 1831.58 |  |  | 1831.58 | 25666.49 | -23834.91 | 2022-09-09 10:01 | 2025-03-13 | 2022-09-01 | open
75084 | 20700041A | MX5821149 | MX5821149 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 1138.06 |  | 1138.06 |  |  | 1138.06 | 27383.22 | -26245.16 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700041A | MX5821151 | MX5821151 - SUB OPT-TRANSFORMER UG 3-PHASE END | 275.41 |  | 275.41 |  |  | 275.41 | 329.87 | -54.46 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5821155 | MX5821155 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 2112.46 |  | 2112.46 |  |  | 2112.46 | 22543.76 | -20431.3 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5821163 | MX5821163 - SUB OPT-TRANSFORMER UG 3-PHASE END | 1449.32 |  | 1449.32 |  |  | 1449.32 | 20303.86 | -18854.54 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5821165 | MX5821165 - SUB OPT-TRANSFORMER UG 3-PHASE END | 1324.74 |  | 1324.74 |  |  | 1324.74 | 21932.73 | -20607.99 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821167 | MX5821167 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 2643.97 |  | 2643.97 |  |  | 2643.97 | 26237.78 | -23593.81 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821168 | MX5821168 - SUB OPT-TRANSFORMER UG 3-PHASE END | 3004.81 |  | 3004.81 |  |  | 3004.81 | 20303.86 | -17299.05 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821171 | MX5821171 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 1815.61 |  | 1815.61 |  |  | 1815.61 | 18328.29 | -16512.68 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821182 | MX5821182 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 895.53 |  | 895.53 |  |  | 895.53 | 19039.09 | -18143.56 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700044A | MX5821185 | MX5821185 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 2484.74 |  | 2484.74 |  |  | 2484.74 | 30090.26 | -27605.52 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700045A | MX5821188 | MX5821188 - SUB OPT-TRANSFORMER UG 3-PHASE END | 844.23 |  | 844.23 |  |  | 844.23 | 19788.51 | -18944.28 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 21890042A | MX5821189 | MX5821189 - SUB OPT-TRANSFORMER UG 3-PHASE END | 85.07 |  | 85.07 |  |  | 85.07 | 329.87 | -244.8 | 2022-08-16 14:01 | 2025-05-01 | 2022-10-01 | 2025-01-01
75084 | 21890042A | MX5821190 | MX5821190 - SUB OPT-TRANSFORMER UG 3-PHASE END | 2029.02 |  | 2029.02 |  |  | 2029.02 | 33264.63 | -31235.61 | 2022-08-16 14:01 | 2025-05-01 | 2022-10-01 | 2025-01-01
75084 | 21990042A | MX5821193 | MX5821193 - SUB OPT-TRANSFORMER UG 3-PHASE END | 3106.45 |  | 3106.45 |  |  | 3106.45 | 29369.17 | -26262.72 | 2022-08-16 14:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990042A | MX5821196 | MX5821196 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 926.58 |  | 926.58 |  |  | 926.58 | 19784.72 | -18858.14 | 2022-08-16 14:01 | 2025-01-29 | 2022-10-01 | cancelled
75084 | 21990042A | MX5821208 | MX5821208 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 892.03 |  | 892.03 |  |  | 892.03 | 19538.85 | -18646.82 | 2022-11-09 18:01 | 2025-01-29 | 2022-11-01 | cancelled
75084 | 21990042A | MX5821211 | MX5821211 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 142.07 |  | 142.07 |  |  | 142.07 | 228.31 | -86.24 | 2022-08-24 10:10 | 2024-12-29 | 2022-10-01 | cancelled
75084 | 21990042A | MX5821218 | MX5821218 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 142.07 |  | 142.07 |  |  | 142.07 | 228.31 | -86.24 | 2022-08-24 10:10 | 2024-12-29 | 2022-10-01 | cancelled
75084 | 21990042A | MX5821220 | MX5821220 - SUB OPT-TRANSFORMER UG 3-PHASE END | 1108.01 |  | 1108.01 |  |  | 1108.01 | 31326.88 | -30218.87 | 2022-08-24 10:10 | 2025-02-28 | 2022-09-01 | open
75084 | 21990043A | MX5821223 | MX5821223 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 866.91 |  | 866.91 |  |  | 866.91 | 20257.25 | -19390.34 | 2022-08-24 10:10 | 2025-01-29 | 2022-11-01 | cancelled
75084 | 22050041A | MX5821228 | MX5821228 - SUB OPT-TRANSFORMER UG 3-PHASE END | 1245.32 |  | 1245.32 |  |  | 1245.32 | 18503.79 | -17258.47 | 2022-08-05 14:01 | 2025-07-29 | 2022-09-01 | 2023-12-18
75084 | 22050041A | MX5821234 | MX5821234 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 1273.24 |  | 1273.24 |  |  | 1273.24 | 44318.04 | -43044.8 | 2022-08-05 14:01 | 2025-07-29 | 2022-09-01 | cancelled
75084 | 20700041A | MX5821349 | MX5821349 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 760.77 |  | 760.77 |  |  | 760.77 | 20791.11 | -20030.34 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700041A | MX5821351 | MX5821351 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 318.14 |  | 318.14 |  |  | 318.14 | 228.31 | 89.83 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700041A | MX5821352 | MX5821352 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 245.97 |  | 245.97 |  |  | 245.97 | 228.31 | 17.66 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700041A | MX5821358 | MX5821358 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 96.2 |  | 96.2 |  |  | 96.2 | 228.31 | -132.11 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | DEMERKY | MX5888071 | MX5888071 - CAPITAL CRESCENT TB1 REPLACE 1 FAN | 1670.36 |  | 1670.36 |  |  | 1670.36 | 3686.73 | -2016.37 | 2022-07-26 10:02 | 2023-03-31 | 2022-08-01 | 2022-11-22
75084 | DEMERKY | MX5888442 | MX5888442 - CAPITAL DRY RIDGE TB1 REPLACE 1 FAN | 1235.43 |  | 1235.43 |  |  | 1235.43 | 3462.66 | -2227.23 | 2022-07-26 10:02 | 2023-03-31 | 2022-11-01 | 2023-02-28
75084 | DEMERKY | MX5888601 | MX5888601 - CAPITAL WILDER TB4 REPLACE 1 FAN | 1241.5 |  | 1241.5 |  |  | 1241.5 | 3487.93 | -2246.43 | 2022-07-26 10:02 | 2023-03-31 | 2022-11-01 | 2023-02-28
75084 | 75084IK | MX5906912 | MX5906912 - KEG - 2045 DECLARATION - WHITE TOWE | 247.14 |  | 247.14 |  |  | 247.14 | 60402.1 | -60154.96 | 2022-09-21 14:01 | 2023-08-31 | 2022-10-01 | 2023-08-31
75084 | 75084HW | MX5931078 | MX5931078 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -48676.42 |  | -48676.42 |  |  | -35532.82 | 93079.74 | -128612.56 | 2020-04-02 18:01 | 2023-01-26 | 2020-09-01 | 2023-01-17
75084 | KYGLPRT | MX5944931 | MX5944931 - TBC GLT F6763 (M19015301) TRAN_UB | -21107.76 |  | -21107.76 |  |  | -7.276e-12 | 21608 | -21608 | 2020-02-27 18:01 | 2022-07-01 | 2020-03-01 | cancelled
75084 | 21990043A | MX5971474 | MX5971474 - SUB OPT - 21990043A - RICHWOOD 43 - | 754.65 |  | 754.65 |  |  | 754.65 | 49101.51 | -48346.86 | 2022-08-02 14:06 | 2025-02-28 | 2022-11-01 | open
75084 | 75084IK | MX5977873 | MX5977873 - AERO SUB LN EXT TO BOSCH | 77299.7 |  | 77299.7 |  |  | 252245.34 | 940120.82 | -687875.48 | 2021-01-08 18:02 | 2025-05-01 | 2021-01-01 | open
75084 | 75084IK | MX5977890 | MX5977890 - FLORENCE 46 LN EXT TO AERO | 2317.95 |  | 2317.95 |  |  | 24739.49 | 895205.63 | -870466.14 | 2021-01-27 10:02 | 2025-03-27 | 2021-01-01 | open
75084 | M190153 | MX6012113 | MX6012113 - T-GLT F6763 (T-DPN M19015302) TRANS | 86884.64 |  | 86884.64 |  |  | 318645.99 | 126803.97 | 191842.02 | 2020-03-04 14:01 | 2022-02-13 | 2020-05-01 | 2022-03-14
75084 | 75084IK | MX6121915 | MX6121915 - APR; 1710 LAKELAND PARK DR, LIMABUR | -188031.81 |  | -188031.81 |  |  | -188031.81 | 189238.3 | -377270.11 | 2022-11-16 18:02 | 2023-07-20 | 2022-12-01 | 2023-08-17
75084 | 20780041A | MX6180900 | MX6180900 - 20780041A: AUGUSTINE 41 K60-222 REM | 26.99 |  | 26.99 |  |  | 26.99 | 56196.11 | -56169.12 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180901 | MX6180901 - 20780041A: AUGUSTINE 41 K60-238 NEW | 26.99 |  | 26.99 |  |  | 26.99 | 55470.29 | -55443.3 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180906 | MX6180906 - 20780041A: AUGUSTINE 41 K60-39 NEW | 62.08 |  | 62.08 |  |  | 62.08 | 50416.66 | -50354.58 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180910 | MX6180910 - 20780041A: AUGUSTINE 41 K71-59 NEW | 11.89 |  | 11.89 |  |  | 11.89 | 42733.45 | -42721.56 | 2022-09-22 14:01 | 2025-08-28 | 2022-12-01 | open
75084 | 20780041A | MX6180911 | MX6180911 - 20780041A: AUGUSTINE 41 K70-258 NEW | 26.99 |  | 26.99 |  |  | 26.99 | 45077.17 | -45050.18 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180912 | MX6180912 - 20780041A: AUGUSTINE 41 K60-64 NEW | 26.99 |  | 26.99 |  |  | 26.99 | 54242.46 | -54215.47 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180914 | MX6180914 - 20780041A: AUGUSTINE 41 K70-232 NEW | 26.99 |  | 26.99 |  |  | 26.99 | 128047.72 | -128020.73 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180915 | MX6180915 - 20780041A: AUGUSTINE 41 K61-759 NEW | 20 |  | 20 |  |  | 20 | 56338.64 | -56318.64 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780042A | MX6180916 | MX6180916 - 20780042A: AUGUSTINE 42 K52-147 NEW | 20 |  | 20 |  |  | 20 | 62709.76 | -62689.76 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180918 | MX6180918 - 20780041A: AUGUSTINE 41 K60-204 NEW | 31.89 |  | 31.89 |  |  | 31.89 | 51809.13 | -51777.24 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6180921 | MX6180921 - 20780044A: AUGUSTINE 44 K54-197 NEW | 20 |  | 20 |  |  | 20 | 48482.38 | -48462.38 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6180924 | MX6180924 - 20780044A: AUGUSTINE 44 K54-776 NEW | 20 |  | 20 |  |  | 20 | 66706.01 | -66686.01 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6180925 | MX6180925 - 20780044A: AUGUSTINE 44 BTW K54-300 | 20 |  | 20 |  |  | 20 | 48963.37 | -48943.37 | 2022-09-22 14:01 | 2025-08-28 | 2022-12-01 | open
75084 | 20780044A | MX6180926 | MX6180926 - 20780044A: AUGUSTINE 44 K54-303 NEW | 20 |  | 20 |  |  | 20 | 49795.43 | -49775.43 | 2022-09-22 14:01 | 2025-08-28 | 2022-12-01 | open
75084 | 20780044A | MX6180927 | MX6180927 - 20780044A: AUGUSTINE 44 K54-916 NEW | 20 |  | 20 |  |  | 20 | 46339.94 | -46319.94 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780045A | MX6200358 | MX6200358 - CAP UPGRADE, K52-1126, AUGUSTINE (7 | 11.89 |  | 11.89 |  |  | 11.89 | 39674.52 | -39662.63 | 2022-09-09 10:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6200359 | MX6200359 - CAP UPGRADE, K54-27, AUGUSTINE (78) | 35.67 |  | 35.67 |  |  | 35.67 | 30820.03 | -30784.36 | 2022-09-09 10:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780043A | MX6200360 | MX6200360 - CAP UPGRADE, K52-1373, AUGUSTINE (7 | 11.89 |  | 11.89 |  |  | 11.89 | 34509.15 | -34497.26 | 2022-09-09 10:01 | 2025-12-29 | 2022-12-01 | open
75084 | 75084HW | MX6240781 | MX6240781 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 32312.92 |  | 32312.92 |  |  | 316919.05 | 185360.78 | 131558.27 | 2020-04-02 18:01 | 2022-06-30 | 2020-04-01 | 2022-07-18
75084 | 75084IK | MX6266041 | MX6266041 - KEG - 200 W 3RD - OVATION - WILDER | 45906.86 |  | 45906.86 |  |  | 45906.86 | 46062.08 | -155.22 | 2022-09-20 10:01 | 2023-01-19 | 2022-09-01 | 2023-01-08
75084 | 75084HW | MX6277290 | MX6277290 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 11860.6 |  | 11860.6 |  |  | 32021.63 | 228.31 | 31793.32 | 2020-04-02 18:01 | 2025-05-01 | 2020-04-01 | open
75084 | 21890042A | MX6282574 | MX6282574 - SUB OPT -DPZ LIMABURG 42 H93218900 | 1658.03 |  | 1658.03 |  |  | 1658.03 | 138098.89 | -136440.86 | 2022-09-13 14:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21990041A | MX6293612 | MX6293612 - SUB-OPT - TRANSFORMER RETROFIT RIC | 1097.58 |  | 1097.58 |  |  | 1097.58 | 15049.49 | -13951.91 | 2022-09-22 14:01 | 2025-02-28 | 2022-12-01 | open
75084 | 75084HW | MX6295185 | MX6295185 - RI-KY 338 RECONSTRUCTION & SIDEWALK | 8957.34 |  | 8957.34 |  |  | 96414.71 | 62118.25 | 34296.46 | 2018-02-09 14:01 | 2018-03-23 | 2018-02-01 | 2018-06-24
75084 | 75084IK | MX6321063 | MX6321063 - LONGBRANCH 44 PT 2 | 99442.38 |  | 99442.38 |  |  | 400729.85 | 279083.39 | 121646.46 | 2021-04-06 18:02 | 2023-02-16 | 2021-04-01 | 2023-01-16
75084 | 75084IK | MX6321718 | MX6321718 - LONGBRANCH 44 PART 3 - DKY2747 | 253022.39 |  | 253022.39 |  |  | 729208.96 | 377643.13 | 351565.83 | 2020-12-10 18:02 | 2023-01-29 | 2020-12-01 | 2023-02-13
75084 | DKY2754 | MX6322062 | MX6322062 - THOMAS MORE 41 LN EXT DKY2754 | 961810.2 |  | 961810.2 |  |  | 994735.71 | 472926.98 | 521808.73 | 2021-01-07 18:02 | 2024-02-15 | 2021-03-01 | 2024-02-06
75084 | DKY2748 | MX6322098 | MX6322098 - AERO TO CVG SOUTH LN EXT | 2568.23 |  | 2568.23 |  |  | 50986.01 | 27295.06 | 23690.95 | 2021-07-08 08:01 | 2021-12-02 | 2021-07-01 | 2021-11-28
75084 | 75084HW | MX6342340 | MX6342340 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 14836.76 |  | 14836.76 |  |  | 158035.17 | 109582.18 | 48452.99 | 2017-11-28 14:01 | 2018-07-01 | 2017-12-01 | 2018-07-25
75084 | 75084IK | MX6366847 | MX6366847 - SHT 48 NOVA TO VIP RECLOSER RPL, K | 11101.04 |  | 11101.04 |  |  | 11101.04 | 47372.39 | -36271.35 | 2022-11-18 14:01 | 2023-05-18 | 2022-11-01 | 2023-05-03
75084 | M190153 | MX6488060 | MX6488060 - TRANSFER D-LINE UB ON F6763 GLT F67 | 11165.38 |  | 11165.38 |  |  | 118640.31 | 13735.39 | 104904.92 | 2020-04-22 14:01 | 2021-11-29 | 2020-08-01 | 2021-12-14
75084 | 20670044A | MX6491994 | MX6491994 - SUB OPT -LINE PATROL NORMAL PRIORIT | 6178.88 |  | 6178.88 |  |  | 6178.88 | 5720.24 | 458.64 | 2021-12-10 10:01 | 2023-02-02 | 2022-01-01 | 2023-02-05
75084 | 20780041A | MX6518423 | MX6518423 - 20780041A: AUGUSTINE 41 K60-446 NEW | 31.89 |  | 31.89 |  |  | 31.89 | 45977.76 | -45945.87 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 75084IK | MX6590208 | MX6590208 - JT-E-REDWOOD LIVING (APTS) | 158788.27 |  | 158788.27 |  |  | 158788.27 | 120985.65 | 37802.62 | 2022-03-22 10:02 | 2022-11-29 | 2022-05-01 | 2023-01-09
75084 | M180378 | MX6610978 | MX6610978 - M18037801.RICHWOOD - DISTRIBUTION L | 2221.91 |  | 2221.91 |  |  | 2221.91 | 3935 | -1713.09 | 2022-10-18 18:01 | 2023-02-21 | 2022-11-01 | 2023-02-20
75084 | 75084IL | MX6643892 | MX6643892 - MAIN ST BROMLEY STREET LIGHTING | 704.64 |  | 704.64 |  |  | 83002.99 | 56625.21 | 26377.78 | 2020-05-21 10:01 | 2022-01-27 | 2021-06-01 | 2022-01-09
75084 | DEMERKY | MX6665010 | MX6665010 - CAPITAL CONSTANCE TB2 REPLACE FAN | 2363.46 |  | 2363.46 |  |  | 2363.46 | 3505.97 | -1142.51 | 2022-10-04 14:12 | 2023-08-30 | 2022-12-01 | 2023-03-21
75084 | 75084IK | MX6835995 | MX6835995 - POLE REPLACEMENT - NON-INSPECTION B | 63181.37 |  | 63181.37 |  |  | 63181.37 | 59093.93 | 4087.44 | 2022-10-18 18:01 | 2023-05-04 | 2022-10-01 | 2023-04-09
75084 | 75084HW | MX7090228 | MX7090228 - RI-6TH ST BEAUTIFICATION, UNDERGROU | -33935.97 |  | -33935.97 |  |  | 64557.33 | 201070.44 | -136513.11 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-05-22
75084 | 75084HW | MX7090285 | MX7090285 - RI-6TH ST BEAUTIFICATION, OVERHEAD | 20576.18 |  | 20576.18 |  |  | 86000.16 | 188091.33 | -102091.17 | 2018-04-10 10:01 | 2022-03-31 | 2018-04-01 | 2022-03-09
75084 | 75084IK | MX7103196 | MX7103196 - 35 W PIKE EMERGENCY TRANFORMER REPL | 186.8 |  | 186.8 |  |  | 20182.2 | 7421.26 | 12760.94 | 2020-06-11 10:01 | 2020-10-20 | 2020-06-01 | 2020-10-11
75084 | KYGLPRT | MX7109799 | MX7109799 - T-EMERGENT GLT TR_UB F5985 TRANSFER | -207.61 |  | -207.61 |  |  | 18249.61 | 8337.94 | 9911.67 | 2020-06-10 18:01 | 2022-02-28 | 2020-07-01 | 2021-12-07
75084 | 75084IK | MX7270217 | MX7270217 - LVG - TRANSFORMER REPLACEMENT - PAR | 50647.17 |  | 50647.17 |  |  | 50647.17 | 52013.92 | -1366.75 | 2022-11-22 10:02 | 2023-04-27 | 2022-11-01 | 2023-03-15
75084 | 75084IK | MX7275238 | MX7275238 - JT-E-SANCTUARY VILLAGE PH 1, PART 3 | 67.89 |  | 67.89 |  |  | 109339.81 | 98255.74 | 11084.07 | 2021-02-10 18:02 | 2021-11-18 | 2021-03-01 | 2021-09-08
75084 | 20550043A | MX7372041 | MX7372041 - 0550043A: DONALDSON 43 21BN-302 REM | 41538.7 |  | 41538.7 |  |  | 44667.67 | 38388.05 | 6279.62 | 2021-10-22 09:12 | 2025-03-13 | 2021-10-01 | open
75084 | 22100041A | MX7372042 | MX7372042 - 2100041A: OAKBROOK 41 20BN-327 INST | 37386.43 |  | 37386.43 |  |  | 37386.43 | 40250.51 | -2864.08 | 2022-03-25 14:04 | 2023-10-26 | 2022-05-01 | 2024-01-21
75084 | 22100041A | MX7372044 | MX7372044 - TBC 2100041A: OAKBROOK 41 25BN-351 | 2101.07 |  | 2101.07 |  |  | 2101.07 | 228.31 | 1872.76 | 2021-10-22 09:12 | 2023-10-26 | 2022-06-01 | open
75084 | 22410044A | MX7372045 | MX7372045 - 2410044A: FLORENCE 44 25BN-725 INST | 15512.14 |  | 15512.14 |  |  | 17734.2 | 48180.86 | -30446.66 | 2021-10-21 14:01 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410044A | MX7372046 | MX7372046 - 2410044A: FLORENCE 44 26BN-1111 INS | 90966.76 |  | 90966.76 |  |  | 90966.76 | 42737.66 | 48229.1 | 2022-03-16 10:01 | 2025-07-29 | 2022-05-01 | 2024-04-22
75084 | 22410044A | MX7372047 | MX7372047 - 2410044A: FLORENCE 44 31BN-1326 INS | 61707.27 |  | 61707.27 |  |  | 64249.46 | 43984.74 | 20264.72 | 2021-10-22 09:12 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410044A | MX7372048 | MX7372048 - 2410044A: FLORENCE 44 BNK-2793 INST | 52479.68 |  | 52479.68 |  |  | 53808.32 | 48817.22 | 4991.1 | 2021-10-22 09:12 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410044A | MX7372049 | MX7372049 - TBC 2410044A: FLORENCE 44 BNK-6117 | 589.99 |  | 589.99 |  |  | 589.99 | 228.31 | 361.68 | 2021-10-22 09:12 | 2025-07-29 | 2022-06-01 | open
75084 | 22410047A | MX7372050 | MX7372050 - TBC 2410047A: FLORENCE 47 BNK-6124 | 681.92 |  | 681.92 |  |  | 681.92 | 228.31 | 453.61 | 2021-10-22 09:12 | 2025-07-29 | 2022-06-01 | open
75084 | 22410047A | MX7372051 | MX7372051 - 2410047A: FLORENCE 47 BNK-2806 INST | 78008.79 |  | 78008.79 |  |  | 80242.64 | 56141.81 | 24100.83 | 2021-10-22 09:12 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410047A | MX7372052 | MX7372052 - TBC 2410047A: FLORENCE 47 BNK-6156 | 691.66 |  | 691.66 |  |  | 691.66 | 228.31 | 463.35 | 2021-10-22 09:12 | 2025-07-29 | 2022-08-01 | open
75084 | 20420044A | MX7372054 | MX7372054 - 20420044A: CONSTANCE 44 21BN-635 I | 66418.44 |  | 66418.44 |  |  | 70002.42 | 43253.26 | 26749.16 | 2021-10-22 09:12 | 2025-03-13 | 2021-10-01 | open
75084 | 20420044A | MX7372055 | MX7372055 - 0420044A: CONSTANCE 44 21BN-625 INS | 48628.45 |  | 48628.45 |  |  | 50379.98 | 44205.38 | 6174.6 | 2021-10-22 09:12 | 2025-03-13 | 2021-12-01 | open
75084 | 20420044A | MX7372056 | MX7372056 - 0420044A: CONSTANCE 44 21BN-396 INS | 48249.58 |  | 48249.58 |  |  | 50036.54 | 44441.08 | 5595.46 | 2021-10-22 09:12 | 2025-03-13 | 2021-10-01 | open
75084 | 20420044A | MX7372057 | MX7372057 - 0420044A: CONSTANCE 44 21BN-387 INS | 51062.22 |  | 51062.22 |  |  | 51062.22 | 45284.9 | 5777.32 | 2022-02-09 18:01 | 2025-03-13 | 2022-04-01 | open
75084 | 20420044A | MX7372058 | MX7372058 - 0420044A: CONSTANCE 44 BNK-6125 REP | 834 |  | 834 |  |  | 834 | 228.31 | 605.69 | 2021-10-22 09:12 | 2025-03-13 | 2022-06-01 | open
75084 | 20420044A | MX7372059 | MX7372059 - 0420044A: CONSTANCE 44 K103-119 REP | 8528.06 |  | 8528.06 |  |  | 8528.06 | 0 | 8528.06 | 2021-12-16 18:02 | 2025-03-13 | 2022-07-01 | open
75084 | 20550041A | MX7372063 | MX7372063 - 0550041A: DONALDSON 41 K116-982 IN | 59273.18 |  | 59273.18 |  |  | 60482.71 | 47524.19 | 12958.52 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX7372064 | MX7372064 - 0550041A: DONALDSON 41 BNK-1184 INS | 60119.78 |  | 60119.78 |  |  | 61228.83 | 44050.59 | 17178.24 | 2021-10-21 10:02 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | 20550041A | MX7372065 | MX7372065 - SUB OPT - INSTALLATION OF SELF HEAL | 42930.18 |  | 42930.18 |  |  | 43558.54 | 41759.97 | 1798.57 | 2021-08-23 10:01 | 2023-02-02 | 2021-09-01 | 2023-02-05
75084 | 20550041A | MX7372067 | MX7372067 - 0550041A: DONALDSON 41 26BN-246 INS | 53352.72 |  | 53352.72 |  |  | 54573.18 | 45568.45 | 9004.73 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX7372068 | MX7372068 - 0550041A: DONALDSON 41 26BN-616 INS | 60181.02 |  | 60181.02 |  |  | 61913.82 | 41285.61 | 20628.21 | 2021-10-22 09:12 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | SG000438F | MX7372069 | MX7372069 - VILLA 43 K95-22 INSTALL SEG SHT 112 | 32.95 |  | 32.95 |  |  | 65531.58 | 55339.47 | 10192.11 | 2021-04-12 10:02 | 2022-02-13 | 2021-06-01 | 2022-02-15
75084 | 75084HW | MX7426786 | MX7426786 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 132.02 |  | 132.02 |  |  | 132.02 | 210726.69 | -210594.67 | 2022-12-13 14:01 | 2023-11-23 | 2022-12-01 | 2023-10-10
75084 | 75084IK | MX7473884 | MX7473884 - OAKBROOK 42 LN EXT DKY2769 | 29748.15 |  | 29748.15 |  |  | 175563.3 | 81818.3 | 93745 | 2020-09-16 18:01 | 2022-12-29 | 2020-10-01 | 2022-10-17
75084 | M190226 | MX7488872 | MX7488872 - D-CONST RECO WOODSPOINT-AERO - M190 | 15.94 |  | 15.94 |  |  | 11917.74 | 184107.64 | -172189.9 | 2020-07-20 10:01 | 2024-05-29 | 2020-09-01 | 2024-05-12
75084 | DKY2451 | MX7616715 | MX7616715 - HEBRON 45 RECLOSER INSTALL - SOG - | 57.36 |  | 57.36 |  |  | 57165.6 | 42085.66 | 15079.94 | 2020-10-14 10:01 | 2022-03-22 | 2020-10-01 | 2022-03-15
75084 | 75084IL | MX7650909 | MX7650909 - OVATION MUSIC VENUE LIGHTING 4TH & | 150.94 |  | 150.94 |  |  | 7.276e-12 | 40929.04 | -40929.04 | 2020-08-27 14:01 | 2021-03-18 | 2020-10-01 | 2021-03-01
75084 | DKY2198 | MX7724526 | MX7724526 - CONSTANCE 41 LN EXT PT1 - DKY2198 | 445.22 |  | 445.22 |  |  | 1672257.82 | 493568.59 | 1178689.23 | 2018-03-20 18:02 | 2019-09-01 | 2018-04-01 | 2018-07-27
75084 | 75084IK | MX7791895 | MX7791895 - JT-E-PARKWAY TRAILS | 133944 |  | 133944 |  |  | 133944 | 82809.53 | 51134.47 | 2022-01-04 10:01 | 2022-08-07 | 2022-01-01 | 2022-06-29
75084 | 75084IK | MX7890923 | MX7890923 - UPGRADE TO EXISTING SERVICE COMMERC | 7892.65 |  | 7892.65 |  |  | 367600.03 | 246708.65 | 120891.38 | 2020-11-17 10:01 | 2022-11-24 | 2020-11-01 | 2022-10-30
75084 | 21520042A | MX7891191 | MX7891191 - SUB OPT -REPLACEMENT OF EXISTING RE | 4660.29 |  | 4660.29 |  |  | 6069.41 | 4968.19 | 1101.22 | 2021-10-20 14:02 | 2025-05-29 | 2021-11-01 | open
75084 | SG000437F | MX7891196 | MX7891196 - 2022 RECL RPL, KNK-5766, KENTON (9) | 11817.12 |  | 11817.12 |  |  | 11817.12 | 18815.81 | -6998.69 | 2021-11-16 14:01 | 2023-02-02 | 2022-02-01 | 2022-11-20
75084 | SG000437F | MX7891197 | MX7891197 - 2022 RECL RPL, BNK-6100, LIMABURG ( | 4438.96 |  | 4438.96 |  |  | 4438.96 | 5044.87 | -605.91 | 2021-11-16 14:01 | 2023-02-02 | 2022-08-01 | 2022-11-21
75084 | SG000437F | MX7891200 | MX7891200 - 2022 RECL RPL, CAK-4275, YORK (77) | 13135.85 |  | 13135.85 |  |  | 13135.85 | 16093.63 | -2957.78 | 2021-11-16 14:01 | 2023-02-02 | 2022-08-01 | 2022-12-01
75084 | 23040041A | MX7891201 | MX7891201 - SUB OP 2022 RECL RPL, KNK-5687, WHI | 13844.78 |  | 13844.78 |  |  | 13844.78 | 19631.86 | -5787.08 | 2022-01-03 10:01 | 2025-05-29 | 2022-01-01 | open
75084 | 21520042A | MX7891216 | MX7891216 - SUB OPT -REPLACEMENT OF EXISTING RE | 4427.78 |  | 4427.78 |  |  | 5619.78 | 5005.02 | 614.76 | 2021-11-04 14:01 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX7891217 | MX7891217 - SUB OPT -REPLACEMENT OF EXISTING RE | 6307.04 |  | 6307.04 |  |  | 7663.39 | 0 | 7663.39 | 2021-11-22 18:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520041A | MX7891218 | MX7891218 - SUB OPT -REPLACEMENT OF EXISTING RE | 4369.97 |  | 4369.97 |  |  | 5413.25 | 4505.46 | 907.79 | 2021-10-20 14:02 | 2025-05-29 | 2021-11-01 | open
75084 | 23040043A | MX7891230 | MX7891230 - TBC SUB OP 2022 RECL RPL, KNK-5686, | -683.42 |  | -683.42 |  |  | 0 | 11695.81 | -11695.81 | 2021-11-15 14:01 | 2024-03-30 | 2021-12-01 | cancelled
75084 | 75084IK | MX8022852 | MX8022852 - PERM ELEC SERV;COMM/INDUST;OTHER;CI | 28578.37 |  | 28578.37 |  |  | 26260.52 | 23793.81 | 2466.71 | 2021-06-04 10:02 | 2022-08-08 | 2021-06-01 | 2022-09-18
75084 | 75084IK | MX8107799 | MX8107799 - DETERIORATED CONDUCTOR - HEBRON (15 | 968.68 |  | 968.68 |  |  | 49559.65 | 46119.96 | 3439.69 | 2021-03-03 10:02 | 2022-03-16 | 2021-03-01 | 2022-03-16
75084 | 21520042A | MX8137212 | MX8137212 - SUB OPT -LINE PATROL NORMAL PRIORIT | 3068.28 |  | 3068.28 |  |  | 3068.28 | 1664.41 | 1403.87 | 2022-02-07 10:01 | 2025-05-29 | 2022-08-01 | open
75084 | 23040043A | MX8137236 | MX8137236 - SUB OPT -LINE PATROL NORMAL PRIORIT | 5642.02 |  | 5642.02 |  |  | 5642.02 | 5035.07 | 606.95 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 23040041A | MX8137248 | MX8137248 - SUB OPT -LINE PATROL NORMAL PRIORIT | 6560.63 |  | 6560.63 |  |  | 6560.63 | 5959.06 | 601.57 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 23040041A | MX8137256 | MX8137256 - SUB OPT -LINE PATROL NORMAL PRIORIT | 4290.31 |  | 4290.31 |  |  | 4290.31 | 1762.16 | 2528.15 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 23040041A | MX8137265 | MX8137265 - SUB OPT -LINE PATROL NORMAL PRIORIT | 3880.27 |  | 3880.27 |  |  | 3880.27 | 4518.51 | -638.24 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | KYGLT20 | MX8203329 | MX8203329 - GLT TR_UB F6785 T-LINE OHGLT2010 | 51162.84 |  | 51162.84 |  |  | 57861.93 | 36544.94 | 21316.99 | 2020-10-21 14:01 | 2022-12-29 | 2021-01-01 | 2022-12-18
75084 | KYGLT20 | MX8204271 | MX8204271 - GLT TR_UB F965 T-LINE KYGLT2001 TRA | 26258.03 |  | 26258.03 |  |  | 28205.36 | 25351.75 | 2853.61 | 2020-09-24 10:01 | 2023-09-28 | 2021-03-01 | 2023-04-09
75084 | 75084IK | MX8250982 | MX8250982 - DETERIORATED CONDUCTOR - CRITTENDEN | 681807.68 |  | 681807.68 |  |  | 1183075.21 | 508337.93 | 674737.28 | 2021-03-24 10:02 | 2022-12-01 | 2021-04-01 | 2022-11-30
75084 | 75084IK | MX8299291 | MX8299291 - JT-E-INDIAN RIDGE APARTMENTS | 93141.4 |  | 93141.4 |  |  | 93141.4 | 50836.86 | 42304.54 | 2022-03-22 10:02 | 2022-11-27 | 2022-04-01 | 2022-11-23
75084 | 75084IK | MX8373261 | MX8373261 - JT-E-SAWGRASS PH C, PART 1 | -165.52 |  | -165.52 |  |  | 76477.48 | 64179.94 | 12297.54 | 2021-07-20 14:02 | 2022-02-02 | 2021-08-01 | 2021-12-19
75084 | 75084IK | MX8452455 | MX8452455 - TBC D-LINE PORTION:SOGHANDSWHITETOW | -833.68 |  | -833.68 |  |  | 0 | 76145.04 | -76145.04 | 2019-12-23 18:01 | 2022-10-01 | 2020-01-01 | cancelled
75084 | 22410046A | MX8564271 | MX8564271 - SUB OPT -TRANSFORMER UG THREE PHASE | 13263.17 |  | 13263.17 |  |  | 15482.43 | 18984.91 | -3502.48 | 2021-07-06 10:03 | 2025-07-29 | 2021-08-01 | 2024-04-22
75084 | 22100041A | MX8564274 | MX8564274 - SUB OPT -TRANSFORMER UG THREE PHASE | 19311.93 |  | 19311.93 |  |  | 19311.93 | 22707.29 | -3395.36 | 2022-02-18 18:01 | 2023-10-26 | 2022-05-01 | 2024-01-21
75084 | 75084IK | MX8566565 | MX8566565 - ZKH - 101 ANDREWS WAY - SD1 - WILDE | 67576.33 |  | 67576.33 |  |  | -31526.47 | 58280.63 | -89807.1 | 2021-07-23 18:03 | 2022-10-27 | 2021-08-01 | 2022-10-11
75084 | CP18SUBK | MX8693627 | MX8693627 - CAPITAL RICHWOOD TB3 REPLACE X3 BUS | 2708.42 |  | 2708.42 |  |  | 11489.12 | 5552.31 | 5936.81 | 2018-06-08 10:02 | 2022-03-31 | 2018-10-01 | 2022-08-31
75084 | 75084IK | MX8701723 | MX8701723 - JT-E-ALEXANDRIA FLATS, SEC 1 | 130396.03 |  | 130396.03 |  |  | 125315.84 | 75038.83 | 50277.01 | 2021-08-24 10:01 | 2022-11-01 | 2021-08-01 | 2022-09-21
75084 | DKY2132 | MX8762834 | MX8762834 - LONGBRANCH 43 - DKY2132 | -2.43 |  | -2.43 |  |  | 33092.14 | 6612.52 | 26479.62 | 2018-07-05 10:02 | 2021-01-29 | 2020-06-01 | 2020-12-30
75084 | DKY2132 | MX8762998 | MX8762998 - LONGBRANCH 44 PART 1 - DKY2132 | 11146.46 |  | 11146.46 |  |  | 143089.87 | 90094.12 | 52995.75 | 2018-12-07 10:01 | 2022-06-29 | 2020-06-01 | 2022-05-30
75084 | DKY2132 | MX8763054 | MX8763054 - LONGBRANCH 43-44 UG - DKY2132 | 45616.25 |  | 45616.25 |  |  | 619733.87 | 181991.33 | 437742.54 | 2018-07-05 10:02 | 2023-05-01 | 2020-06-01 | 2023-04-03
75084 | DKY2125 | MX8804068 | MX8804068 - REMOVE CABLE FOR GRANT CAP BANK - D | -13.43 |  | -13.43 |  |  | 0 | 0 | 0 | 2020-11-30 10:02 | 2021-03-18 | 2020-12-01 | 2021-03-14
75084 | 75084IK | MX8924352 | MX8924352 - JT-E- NEWPORT CLIFTON - 13TH STREET | 27777.69 |  | 27777.69 |  |  | 27777.69 | 65653.3 | -37875.61 | 2022-07-26 14:01 | 2023-04-05 | 2022-07-01 | 2023-04-10
75084 | 75084IK | MX8940536 | MX8940536 - UG CABLE REPLACE SMALL - PROACTIVE | 96036.8 |  | 96036.8 |  |  | 114612.94 | 71645.53 | 42967.41 | 2021-02-10 18:02 | 2021-08-26 | 2021-02-01 | 2021-08-01
75084 | DKY2132 | MX9015414 | MX9015414 - LONGBRANCH 44 PART 2 - DKY2132 | 825892.02 |  | 825892.02 |  |  | 1030946.23 | 529298.87 | 501647.36 | 2018-12-07 10:01 | 2022-11-29 | 2020-06-01 | 2022-12-18
75084 | 75084IK | MX9048687 | MX9048687 - MCCULLUM PK-COMMERCIAL PRIMARY/SECO | 656.27 |  | 656.27 |  |  | 191898.39 | 138789.09 | 53109.3 | 2021-01-14 12:13 | 2022-11-30 | 2021-01-01 | 2023-05-16
75084 | DKY2645 | MX9064744 | MX9064744 - WILDER 43 RT9 OVERHEAD WORK - SOG D | 16.84 |  | 16.84 |  |  | 12581.4 | 37163.44 | -24582.04 | 2021-06-28 10:02 | 2026-07-29 | 2021-06-01 | open
75084 | 75084HW | MX9147524 | MX9147524 - MT. ZION ROAD TRANSMISSION UNDERBUI | -14078.53 |  | -14078.53 |  |  | 72036.08 | 79912.7 | -7876.62 | 2021-01-19 10:02 | 2022-05-16 | 2021-04-01 | 2022-03-16
75084 | DKY2020 | MX9210067 | MX9210067 - BELLEVUE 43 RECO - KYLES LN - SOG - | 17561.73 |  | 17561.73 |  |  | 320060.4 | 218110.22 | 101950.18 | 2021-01-04 10:02 | 2022-02-17 | 2021-01-01 | 2022-02-15
75084 | DKY2020 | MX9210584 | MX9210584 - WILDER 42 ROW REM - SOG DKY2020 | 26503.46 |  | 26503.46 |  |  | 34741.24 | 13934.21 | 20807.03 | 2021-01-04 10:02 | 2022-08-04 | 2021-08-01 | 2022-07-27
75084 | DKY2722 | MX9365045 | MX9365045 - VILLA 43 LN EXT TO THOM MORE 41 - D | 49557.55 |  | 49557.55 |  |  | 61570.07 | 763815.04 | -702244.97 | 2021-01-07 14:02 | 2025-03-31 | 2021-03-01 | open
75084 | 75084IL | MX9409958 | MX9409958 - C5 75/71 NORTHERN KENTUCKY LOGISTIC | -3111.99 |  | -3111.99 |  |  | 252566.42 | 191574.58 | 60991.84 | 2021-03-16 10:03 | 2022-01-02 | 2021-05-01 | 2021-10-26
75084 | SG000439F | MX9412214 | MX9412214 - 20BN-1300 - SWITCHGEAR MANUAL OTHER | 9234.66 |  | 9234.66 |  |  | 206259.71 | 103867.86 | 102391.85 | 2019-12-13 10:01 | 2022-01-28 | 2020-07-01 | 2022-01-11
75084 | SG000439F | MX9412328 | MX9412328 - 20BN-1298 - SWITCHGEAR MANUAL OTHER | 2035.66 |  | 2035.66 |  |  | 106307.68 | 75779.98 | 30527.7 | 2019-12-13 10:01 | 2022-01-28 | 2021-08-01 | 2022-01-09
75084 | DKY2198 | MX9545158 | MX9545158 - CONSTANCE REMOVE EXISTING OH - DKY2 | 42689.7 |  | 42689.7 |  |  | 268806.82 | 260622.82 | 8184 | 2018-08-22 10:02 | 2022-06-29 | 2019-11-01 | 2022-06-16
75084 | TEMERKY | MX9649928 | MX9649928 - CAPITAL BUFFINGTON TB3 REPLACE ETM | 6667.28 |  | 6667.28 |  |  | 12333.98 | 16341 | -4007.02 | 2021-02-02 14:02 | 2023-09-30 | 2021-02-01 | 2022-09-28
75084 | TEMERKY | MX9650032 | MX9650032 - CAPITAL VILLA CB 635 REPLACE 2 BUSH | -156.2 |  | -156.2 |  |  | 355.48 | 16215.11 | -15859.63 | 2021-02-02 14:02 | 2023-06-30 | 2021-06-01 | 2021-09-15
75084 | DKY2125 | MX9769240 | MX9769240 - DRY RIDGE SUB EXPANSION - FALL 2021 | 11579.85 |  | 11579.85 |  |  | 18566.51 | 2060.15 | 16506.36 | 2021-03-08 10:03 | 2022-02-07 | 2021-04-01 | 2022-02-02
75084 | 75084IK | MX9792877 | MX9792877 - JT-E-ELEVATION 800 | 108957.11 |  | 108957.11 |  |  | 108957.11 | 73814.69 | 35142.42 | 2022-03-01 14:01 | 2022-12-29 | 2022-03-01 | 2022-12-07
75084 | 75084IK | MX9815429 | MX9815429 - KSL; 7900 FOUNDATION DR; BUFFINGTON | 8944.51 |  | 8944.51 |  |  | -161623.84 | 164557.11 | -326180.95 | 2021-11-15 14:01 | 2022-04-28 | 2021-11-01 | 2022-04-11
75084 | 75084IK | MX9852485 | MX9852485 - 12000 OLD LEXINGTON PIKE LINE EXTEN | -40287.69 |  | -40287.69 |  |  | 182722.82 | 151333.27 | 31389.55 | 2021-03-15 10:02 | 2022-03-31 | 2021-07-01 | 2022-02-20
75084 | 75084IK | MX9918857 | MX9918857 - STEFFEN RD-POLE REPLACEMENTS - NON- | 35329.57 |  | 35329.57 |  |  | 54951.93 | 52484.49 | 2467.44 | 2021-03-18 14:02 | 2024-05-30 | 2021-03-01 | open
75084 | 20670045A | MX9919639 | MX9919639 - SUB OPT -UPGRADE OF CAPACITORS BY A | 31111.96 |  | 31111.96 |  |  | 32550.78 | 14661.57 | 17889.21 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20670045A | MX9919640 | MX9919640 - SUB OPT -UPGRADE OF CAPACITORS BY A | 29761.5 |  | 29761.5 |  |  | 30628.23 | 18001.27 | 12626.96 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20670045A | MX9919641 | MX9919641 - SUB OPT -UPGRADE OF CAPACITORS BY A | 18588.31 |  | 18588.31 |  |  | 19297.58 | 14787.19 | 4510.39 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20670046A | MX9919642 | MX9919642 - SUB OPT -UPGRADE OF CAPACITORS BY A | 32911.32 |  | 32911.32 |  |  | 33537.89 | 16604.23 | 16933.66 | 2021-08-06 14:02 | 2023-02-02 | 2021-08-01 | 2023-02-05
75084 | 20550043A | MX9919684 | MX9919684 - SUB OPT -UPGRADE OF CAPACITORS BY A | 15320.53 |  | 15320.53 |  |  | 16043.34 | 14257.76 | 1785.58 | 2021-08-10 10:02 | 2025-03-13 | 2021-08-01 | open
75084 | 20550043A | MX9919685 | MX9919685 - SUB OPT -UPGRADE OF CAPACITORS BY A | 16904.82 |  | 16904.82 |  |  | 18774.95 | 17251.93 | 1523.02 | 2021-08-10 10:02 | 2025-03-13 | 2021-08-01 | open
75084 | 20550044A | MX9919686 | MX9919686 - SUB OPT -UPGRADE OF CAPACITORS BY A | 13988.76 |  | 13988.76 |  |  | 13988.76 | 18161.63 | -4172.87 | 2021-09-28 14:02 | 2025-03-13 | 2022-10-01 | open
75084 | 22100041A | MX9919687 | MX9919687 - SUB OPT -A CAP UPGRADE, 25BN-397, O | 13991.93 |  | 13991.93 |  |  | 13991.93 | 15425.53 | -1433.6 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100041A | MX9919688 | MX9919688 - SUB OPT -A CAP UPGRADE, BNK-2661, O | 15122.18 |  | 15122.18 |  |  | 15122.18 | 18204.24 | -3082.06 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100042A | MX9919691 | MX9919691 - SUB OPT -CAP UPGRADE, 20BN-454, OAK | 14108.24 |  | 14108.24 |  |  | 14108.24 | 12133.8 | 1974.44 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100042A | MX9919693 | MX9919693 - SUB OPT -A CAP UPGRADE, 25BN-272, O | 23679.9 |  | 23679.9 |  |  | 23679.9 | 26268.86 | -2588.96 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | DKY2618 | MX9992812 | MX9992812 - PRIMARY SERVICE 2 - AMAZON - DKY261 | 1726.9 |  | 1726.9 |  |  | 267326 | 156473.13 | 110852.87 | 2021-02-25 14:02 | 2023-04-20 | 2021-03-01 | 2023-04-11
75084 | DKY2210 | MXA120786 | MXA120786 - DONALDSON 45/47 EXT | 195.36 |  | 195.36 |  |  | 32775.09 | 13831.5 | 18943.59 | 2020-01-16 10:01 | 2020-06-04 | 2020-02-01 | 2020-06-09
75084 | 21990043A | MXA352205 | MXA352205 - SUB OPT - 21990043A - RICHWOOD 43 E | 216.28 |  | 216.28 |  |  | 216.28 | 93915.68 | -93699.4 | 2022-06-07 14:01 | 2025-02-28 | 2022-12-01 | open
75084 | 22410045A | MXA701477 | MXA701477 - TBC 2410045A: FLORENCE 45 25BN-507 | -1974.22 |  | -1974.22 |  |  | 1.1369e-13 | 73972.87 | -73972.87 | 2021-10-22 13:47 | 2024-03-30 | 2021-10-01 | cancelled
75084 | 20700043A | MXA821161 | MXA821161 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 1459.77 |  | 1459.77 |  |  | 1459.77 | 28071.42 | -26611.65 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | OLE08FA | OLEKY | OLEKY - KENTUCKY NEW LIGHTING INSTALL - OLE | 3386.86 |  | 3386.86 |  |  | 780191.45 | 0 | 780191.45 | 2014-08-04 | 2020-12-31 | 2015-01-01 | open
75084 | ORDFA | ORDKY | ORDKY - OUTAGE RESTORATION CAP-D | 8779.98 |  | 8779.98 |  |  | 137649.76 | 200 | 137449.76 | 2008-07-01 | 2050-12-31 | 2008-07-01 | open
75084 | TOUTKY | OUT69KY | OUT69KY - KY T-LINE EMERGENCY REPL ON 69KV | 83676.46 |  | 83676.46 |  |  | 330011.21 | 420345.37 | -90334.16 | 2017-01-17 10:23 | 2027-12-31 | 2017-01-01 | 2024-06-13
75084 | ORDFA | PDOHRPLKY | PDOHRPLKY - PUBLIC DAMAGE REPLACE OH - KENTUCKY | 106.85 |  | 106.85 |  |  | 111095.32 | 0 | 111095.32 | 2015-06-13 14:43 | 2025-12-31 | 2016-02-01 | open
75085 | IGSSOFTWR | RCTSOFTWR | RCTSOFTWR - RESIDENTIAL CARBON TOOL SOFTWARE | 5369.08 |  | 5369.08 |  |  | 5369.08 | 3017 | 2352.08 | 2022-02-21 13:59 | 2025-03-31 | 2022-04-01 | open
75084 | 22410045A | RW2241A | RW2241A - FLORENCE SO - TUG ROW | 2186.09 |  | 2186.09 |  |  | 2186.09 | 0 | 2186.09 | 2022-04-13 08:57 | 2024-10-31 | 2022-04-01 | 2024-11-21
75084 | 20550044A | RWT055A | RWT055A - ROW - DONALDSON - H9320550044 | 630.39 |  | 630.39 |  |  | 1717.21 | 5000 | -3282.79 | 2021-06-16 08:35 | 2024-09-30 | 2021-07-01 | 2024-09-30
75080 | FPIT | SE2100003 | SE2100003 - END OF LIFE REPL FOR FIREWALLS | -74.47 |  | -74.47 |  |  | 14153.05 | 6180 | 7973.05 | 2021-04-14 21:48 | 2022-03-31 | 2021-04-01 | 2022-03-31
75080 | FPIT | SE2200001 | SE2200001 - END OF LIFE REPLACEMENT FOR FIREWAL | 7854.23 |  | 7854.23 |  |  | 7854.23 | 28592 | -20737.77 | 2022-01-20 11:07 | 2023-03-30 | 2022-02-01 | 2023-03-30
75080 | FPIT | SE2200006 | SE2200006 - ESCA - IT-OT CYBER DEPLOYMENT PROJ | 159864.84 |  | 159864.84 |  |  | 159864.84 | 306443 | -146578.16 | 2022-03-08 09:30 | 2023-06-09 | 2022-06-01 | 2023-05-23
75080 | FPIT | SE2200048 | SE2200048 - ESCA - CDP TUFIN | 8936.39 |  | 8936.39 |  |  | 8936.39 | 9142 | -205.61 | 2022-09-06 16:10 | 2023-06-29 | 2022-12-01 | 2023-03-31
75082 | FPIT | SE22027WD | SE22027WD - SECURITY SYSTEM-MW | 594.26 |  | 594.26 |  |  | 594.26 | 106091 | -105496.74 | 2022-08-09 15:06 | 2023-03-30 | 2022-09-01 | 2023-04-24
75081 | FPITF | SE22028EB | SE22028EB - SECURITY SYSTEM-EAST BEND | 1150.51 |  | 1150.51 |  |  | 1150.51 | 106092 | -104941.49 | 2022-08-09 08:25 | 2023-03-30 | 2022-09-01 | 2023-04-27
75084 | SG001117F | SG001117 | SG001117 - DEE LMR CONSOLES | 21536.08 |  | 21536.08 |  |  | 766516.05 | 874447 | -107930.95 | 2021-08-25 19:52 | 2023-03-31 | 2021-09-01 | 2022-11-30
75084 | SG001145F | SG001145 | SG001145 - DEE POWER MONITORING & MGMNT SYSTEM | 1244.46 |  | 1244.46 |  |  | 5680.71 | 5173 | 507.71 | 2021-07-08 15:45 | 2022-11-30 | 2021-07-01 | 2022-06-18
75084 | SG001176F | SG001176 | SG001176 - DEE CITRIX API VPS GEMS GATEWAY | 6759.93 |  | 6759.93 |  |  | 6759.93 | 10117 | -3357.07 | 2022-06-22 11:47 | 2024-04-30 | 2022-06-01 | 2023-08-31
75084 | SG001001F | SG1001SW | SG1001SW - DEE IOT PLATFORM ASSESSMENT POC | 7609.25 |  | 7609.25 |  |  | 12063.7 | 27663.6 | -15599.9 | 2020-09-11 18:40 | 2022-12-31 | 2020-09-01 | 2023-09-01
75084 | SG001006F | SG1006SW | SG1006SW - DEK FISR PRE-SCALE - SOFTWARE | 1213.12 |  | 1213.12 |  |  | 319642.99 | 384800 | -65157.01 | 2019-10-22 10:44 | 2022-03-31 | 2019-10-01 | 2022-02-09
75080 | SG001011F | SG1009Z1L | SG1009Z1L - DEK LMR - OHIO/KENTUCKY - ERLANGER | -3.07 |  | -3.07 |  |  | 5.862e-14 | 5597208.53 | -5597208.53 | 2019-09-24 12:15 | 2021-03-10 | 2019-10-01 | cancelled
75080 | SG001011F | SG1009Z1O | SG1009Z1O - DEK LMR - OHIO/KENTUCKY - ERLANGER | -2.2 |  | -2.2 |  |  | 1.0214e-13 | 1399302.13 | -1399302.13 | 2019-09-24 11:58 | 2021-03-10 | 2019-10-01 | cancelled
75080 | SG001010F | SG1010Z1L | SG1010Z1L - DEK LMR - OHIO/KENTUCKY - ERLANGER | 502378.59 |  | 502378.59 |  |  | 2044359.2 | 5597208.53 | -3552849.33 | 2019-11-01 12:38 | 2024-03-31 | 2019-11-01 | 2023-05-31
75080 | SG001010F | SG1010Z1O | SG1010Z1O - DEK LMR - OHIO/KENTUCKY - ERLANGER | 588077.76 |  | 588077.76 |  |  | 945467.16 | 1399302.13 | -453834.97 | 2019-11-01 12:28 | 2024-03-31 | 2019-11-01 | 2023-05-31
75084 | SG001024F | SG1024SW | SG1024SW - DEK CLOSED LOOP FISR FULL SCALE | 3120.28 |  | 3120.28 |  |  | 3120.28 | 283358 | -280237.72 | 2022-04-01 15:10 | 2024-04-30 | 2022-06-01 | 2024-03-27
75084 | SG001037F | SG1037SW | SG1037SW - BULK DEVICE MANAGEMENT (BDM) | 3250.72 |  | 3250.72 |  |  | 3250.72 | 77982 | -74731.28 | 2022-01-04 00:59 | 2024-01-31 | 2022-01-01 | open
75084 | SG001041F | SG1041SW | SG1041SW - DEE ADP SOG AUTOMATION TOOL | 306.22 |  | 306.22 |  |  | 34927.25 | 32007.13 | 2920.12 | 2020-06-08 08:52 | 2021-12-31 | 2020-06-01 | 2022-03-31
75084 | SG001057F | SG1057SVR | SG1057SVR - DEE CUSTOMER MAPPING ENGINE | 14.41 |  | 14.41 |  |  | 13136.66 | 7291 | 5845.66 | 2020-08-26 21:08 | 2023-10-31 | 2020-12-01 | 2022-12-15
75084 | SG001057F | SG1057SW | SG1057SW - DEE CUSTOMER MAPPING ENGINE | 33937.96 |  | 33937.96 |  |  | 77335.89 | 150716 | -73380.11 | 2020-08-27 15:29 | 2023-10-31 | 2020-09-01 | 2022-12-15
75084 | SG001059F | SG1059HW | SG1059HW - HARDWARE IN-LOOP HIL LAB | 19864.6 |  | 19864.6 |  |  | 19864.6 | 74157.59 | -54292.99 | 2022-09-22 16:56 | 2025-03-31 | 2022-09-01 | 2024-11-30
75084 | SG001069F | SG1069GDQ | SG1069GDQ - DEE GRID DATA QUALITY GDQ | 64611.36 |  | 64611.36 |  |  | 145729.18 | 195874 | -50144.82 | 2020-10-26 14:01 | 2024-03-31 | 2020-11-01 | 2023-01-31
75084 | SG001076F | SG1076OCT | SG1076OCT - DEE CAPITAL INVESTMENT PLANNING | 37133.81 |  | 37133.81 |  |  | 168207.65 | 231176 | -62968.35 | 2020-11-11 10:19 | 2023-03-31 | 2020-12-01 | 2023-03-12
75084 | SG001081F | SG1081SW | SG1081SW - DEK SCADA DMS UPGRADE | 286672.23 |  | 286672.23 |  |  | 1430891.4 | 1215071 | 215820.4 | 2021-05-14 14:27 | 2022-04-30 | 2021-05-01 | 2022-05-20
75084 | SG001092F | SG1092SLR | SG1092SLR - DEK AERO SOLAR | 2693662.11 |  | 2693662.11 |  |  | 6150414.3 | 4976446 | 1173968.3 | 2021-03-12 10:30 | 2022-10-15 | 2021-03-01 | cancelled
75084 | SG001093F | SG1093SW | SG1093SW - GRID HOSTING CAPACITY PROJECT | 101852.92 |  | 101852.92 |  |  | 126561.21 | 346175 | -219613.79 | 2021-11-19 17:02 | 2025-01-26 | 2021-11-01 | open
75084 | SG001094F | SG1094OTA | SG1094OTA - DEE OUTAGE TIMESTAMP ACCURACY | 24286.27 |  | 24286.27 |  |  | 26208.02 | 34685 | -8476.98 | 2021-11-30 18:05 | 2023-01-31 | 2021-12-01 | 2023-01-31
75084 | SG001105F | SG1105SW | SG1105SW - POWER FLOW ANALYSIS | 4121.62 |  | 4121.62 |  |  | 4121.62 | 52971 | -48849.38 | 2022-12-16 14:26 | 2025-11-30 | 2022-12-01 | open
75084 | SG001131F | SG1131POC | SG1131POC - DEK SMALL HYDRAULIC REPLACEMENT MID | 67478.16 |  | 67478.16 |  |  | 67478.16 | 96026 | -28547.84 | 2021-09-22 14:57 | 2022-12-31 | 2022-03-01 | 2022-09-30
75084 | SG001133F | SG1133HW | SG1133HW - DEE MOBILE CONNECT PRE SCALE | 250210.1 |  | 250210.1 |  |  | 250210.1 | 141239 | 108971.1 | 2022-03-08 01:44 | 2023-03-31 | 2022-03-01 | 2023-11-01
75084 | SG001133F | SG1133SW | SG1133SW - DEE MOBILE CONNECT PRE SCALE | 14408.68 |  | 14408.68 |  |  | 14408.68 | 141727 | -127318.32 | 2022-03-08 02:08 | 2023-03-31 | 2022-07-01 | 2023-11-01
75084 | SG001140F | SG1140M21 | SG1140M21 - DEK EOL MODEM REPLACEMENTS | 72193.14 |  | 72193.14 |  |  | 96913.78 | 71805 | 25108.78 | 2021-12-17 11:34 | 2022-07-31 | 2021-12-01 | 2023-03-31
75084 | SG001170F | SG1170M01 | SG1170M01 - END OF LIFE MODEM REPLACEMENT - B | 20008.68 |  | 20008.68 |  |  | 20008.68 | 133098 | -113089.32 | 2022-05-09 19:13 | 2030-03-31 | 2022-05-01 | open
75084 | SG000223F | SG223SW | SG223SW - DEE TRANSMISSION HEALTH & RISK MGT | 57680.44 |  | 57680.44 |  |  | 675028.84 | 1016639 | -341610.16 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01 | 2023-03-15
75084 | SG000336F | SG336SW | SG336SW - SG DEE DMS ADMS - SOFTWARE | 409942.95 |  | 409942.95 |  |  | 1849850.73 | 1049863.37 | 799987.36 | 2016-09-06 17:51 | 2026-06-01 | 2016-09-01 | open
75084 | SG00359F | SG359SW | SG359SW - SG SADM SOFTWARE - 359 | 63507.23 |  | 63507.23 |  |  | 183713.22 | 227863.84 | -44150.62 | 2018-09-27 06:52 | 2024-06-30 | 2018-09-01 | 2024-03-20
75084 | SG00359F | SG359SW2 | SG359SW2 - SG SADM SOFTWARE - 359 | 7196.91 |  | 7196.91 |  |  | 83280.92 | 227863.84 | -144582.92 | 2019-08-15 08:00 | 2023-11-30 | 2019-09-01 | 2023-04-01
75084 | SG000468F | SG468MDM | SG468MDM - SG DEK NEXT GEN CELLULAR | 25161.87 |  | 25161.87 |  |  | 858990.45 | 1684462.49 | -825472.04 | 2017-10-10 12:47 | 2026-03-31 | 2018-01-01 | 2022-08-24
75084 | SG000502F | SG502SW | SG502SW - SG DEE DEVICE ENTRY ALERT SYS - 502 | 35.76 |  | 35.76 |  |  | 12331.81 | 69968.07 | -57636.26 | 2018-08-31 13:48 | 2020-12-31 | 2019-01-01 | 2020-09-30
75084 | SG000551F | SG551NOK | SG551NOK - NOKIA NETWORK SERVICES PLATFORM | 4935.66 |  | 4935.66 |  |  | 17164.18 | 17998 | -833.82 | 2020-12-07 17:22 | 2023-12-30 | 2020-12-01 | 2023-10-31
75084 | SG000564F | SG564LC&I | SG564LC&I - DEK LARGE CI FOLLOW ON PROJECT | 1442.75 |  | 1442.75 |  |  | 75895.19 | 121743 | -45847.81 | 2020-10-09 17:10 | 2021-10-31 | 2020-11-01 | 2021-12-01
75084 | SG000601F | SG601SW | SG601SW - DEE ADP SOFTWARE - 601 | 230994.84 |  | 230994.84 |  |  | 562364.24 | 42090 | 520274.24 | 2017-06-21 17:55 | 2025-03-31 | 2017-06-01 | open
75084 | SG000685F | SG685TUGK | SG685TUGK - DEK TUG EASEMENT/ROW BLANKET | 1995.77 |  | 1995.77 |  |  | 137938.39 | 400000 | -262061.61 | 2019-10-22 11:24 | 2026-03-31 | 2020-01-01 | open
75084 | SG000723F | SG723SW | SG723SW - DEE AMI OPERATIONS TOOL | 5187.41 |  | 5187.41 |  |  | 46553.46 | 38014 | 8539.46 | 2020-01-15 11:35 | 2022-07-30 | 2020-04-01 | 2022-07-31
75084 | SG000732F | SG732BTR | SG732BTR - SG DEK BATTERY REPLACEMENT | 1176.29 |  | 1176.29 |  |  | 76602.78 | 33850 | 42752.78 | 2017-10-11 15:39 | 2026-03-31 | 2018-02-01 | open
75084 | SG000732F | SG732TR01 | SG732TR01 - DEK TOWERS & SHELTERS - VERONA | 3216.98 |  | 3216.98 |  |  | 1561211.42 | 968336.2 | 592875.22 | 2018-09-11 15:00 | 2021-09-30 | 2018-09-01 | 2021-04-15
75084 | SG000732F | SG732TR02 | SG732TR02 - TBC -TOWER & SHELTER - VERONA 2 | -20523.48 |  | -20523.48 |  |  | -466.32 | 968336 | -968802.32 | 2019-01-23 11:05 | 2022-03-31 | 2019-02-01 | cancelled
75084 | SG000732F | SG732TR03 | SG732TR03 - COMMUNICATION TOWER , SHELTER AND S | 1823996.69 |  | 1823996.69 |  |  | 1875659.51 | 1519055 | 356604.51 | 2020-10-30 10:38 | 2023-03-31 | 2020-12-01 | 2023-11-30
75084 | SG000732F | SG732TR04 | SG732TR04 - DEK TWR,SHELTR,PWRSUP_SPARTA MW | 50205.5 |  | 50205.5 |  |  | 54737.84 | 1519055 | -1464317.16 | 2021-02-05 14:19 | 2026-03-20 | 2021-02-01 | open
75084 | SG000732F | SG732TR05 | SG732TR05 - COMM TOWERS,SHELTERS-RYLAND HEIGHTS | 32540.95 |  | 32540.95 |  |  | 35591.38 | 1519055 | -1483463.62 | 2021-03-11 16:09 | 2027-03-31 | 2021-05-01 | open
75084 | SG000732F | SG732TR06 | SG732TR06 - COMMUNICATION TOWER, SHELTER AND SY | 419896.59 |  | 419896.59 |  |  | 1550133.62 | 1777260 | -227126.38 | 2021-06-10 07:49 | 2022-11-15 | 2021-06-01 | 2022-11-30
75084 | SG000744F | SG744BLK | SG744BLK - DEK GRIDWAN | 105044.7 |  | 105044.7 |  |  | 358200.11 | 249086.72 | 109113.39 | 2018-05-25 13:54 | 2031-03-31 | 2018-11-01 | 2023-03-31
75084 | SG000744F | SG744MTR | SG744MTR - DEK GRIDWAN | 36434.32 |  | 36434.32 |  |  | 51192.69 | 248821.93 | -197629.24 | 2018-05-25 13:28 | 2021-12-31 | 2018-07-01 | 2023-03-31
75084 | SG000764F | SG764BLK1 | SG764BLK1 - DEK 2019-2020 MICROWAVE UPGRADES | 605813.53 |  | 605813.53 |  |  | 2064398.5 | 217462.26 | 1846936.24 | 2019-02-25 09:15 | 2030-03-31 | 2019-04-01 | open
75084 | SG000764F | SG764MAT1 | SG764MAT1 - DEK 2019-2020 MICROWAVE UPGRADES | 41762.22 |  | 41762.22 |  |  | 486681.98 | 217462.26 | 269219.72 | 2019-02-25 08:41 | 2030-03-31 | 2019-10-01 | open
75084 | SG000770F | SG770MAS | SG770MAS - 2018 MAS RADIO | 51881.96 |  | 51881.96 |  |  | 315973.91 | 112986 | 202987.91 | 2018-02-13 17:18 | 2019-03-31 | 2018-02-01 | open
75084 | SG000776F | SG776OP1 | SG776OP1 - DEK OPTICAL ELECTRONICS | -9.77 |  | -9.77 |  |  | -9.77 | 542269.02 | -542278.79 | 2022-06-08 08:16 | 2030-03-31 | 2022-06-01 | open
75084 | SG000781F | SG781SW | SG781SW - SG DEE PPM PIMS PHASE 2 BUILD OUT | 788.77 |  | 788.77 |  |  | 112348.78 | 110269.74 | 2079.04 | 2018-07-12 09:08 | 2021-03-31 | 2018-07-01 | 2021-03-31
75084 | SG000794F | SG794ETOS | SG794ETOS - DEE LMR PROJECT 1 CORES | 25777.793 |  | 25777.793 |  |  | 33793.63 | 11229.12 | 22564.51 | 2020-12-17 12:45 | 2024-03-31 | 2021-01-01 | 2023-09-28
75084 | SG000838F | SG838BTR | SG838BTR - DEK EOL POWER SUPPLIES | 12220.93 |  | 12220.93 |  |  | 170795.58 | 81484 | 89311.58 | 2019-01-22 08:29 | 2022-03-31 | 2019-04-01 | open
75084 | SG000493F | SG943MAIF | SG943MAIF - ADVANCED RELIABILITY METRICS | 171.25 |  | 171.25 |  |  | 27625.28 | 52359 | -24733.72 | 2020-06-29 17:04 | 2022-03-31 | 2020-07-01 | 2022-01-15
75084 | SG000946F | SG946CONN | SG946CONN - ESTABLISH T&D CONNECTIVITY SW | 53.88 |  | 53.88 |  |  | 13180.84 | 33939 | -20758.16 | 2020-07-27 11:21 | 2022-01-03 | 2020-08-01 | 2022-03-31
75084 | SG000949F | SG949MTLD | SG949MTLD - DEE MAINTAIN LOAD & GENERATION | 74.29 |  | 74.29 |  |  | 23346.63 | 13378 | 9968.63 | 2020-08-17 12:31 | 2022-04-30 | 2020-08-01 | 2022-03-15
75084 | SG000954F | SG954KYFR | SG954KYFR - DEK FUSE REPLACEMENT AFWS | 220704.98 |  | 220704.98 |  |  | 514030.52 | 3940594 | -3426563.48 | 2019-10-22 15:06 | 2026-03-31 | 2021-01-01 | open
75084 | SG000960F | SG960DASH | SG960DASH - DER DISPATCH - DASHBOARD | 50620.89 |  | 50620.89 |  |  | 53922.68 | 179000 | -125077.32 | 2021-09-14 11:49 | 2026-09-30 | 2021-09-01 | open
75084 | SG000960F | SG960ORCH | SG960ORCH - DER DISPATCH ORCHESTRATION | 115904.19 |  | 115904.19 |  |  | 133234.61 | 939747 | -806512.39 | 2021-09-13 16:54 | 2026-09-30 | 2021-09-01 | open
75084 | SG000977F | SG977LAB | SG977LAB - THE CYBERSECURITY TESTING OF THE NE | 2133.51 |  | 2133.51 |  |  | 2133.51 | 26064 | -23930.49 | 2022-03-29 08:06 | 2023-03-31 | 2022-10-01 | 2023-03-31
75084 | SG000983F | SG983TMT2 | SG983TMT2 - SG DEE TMT PHASE II | 8.59 |  | 8.59 |  |  | 29519.54 | 44390.63 | -14871.09 | 2019-08-14 14:04 | 2021-11-02 | 2019-09-01 | 2022-01-01
75084 | SG000998F | SG998SHR | SG998SHR - DEE SMALL HYDRAULIC REPLACEMENT PRE | 9148.42 |  | 9148.42 |  |  | 9148.42 | 0 | 9148.42 | 2021-07-20 08:47 | 2022-12-31 | 2022-05-01 | open
75084 | SG000586F | SGDLSKY | SGDLSKY - RUSD DEK D-LINE SWITCH REPLACEMENT | -961.14 |  | -961.14 |  |  | 324249.57 | 0 | 324249.57 | 2016-12-19 11:23 | 2025-12-31 | 2017-05-01 | open
75084 | SG000437F | SGHYDRKY | SGHYDRKY - DEK RECLOSER REPLACEMENTS | 241545.49 |  | 241545.49 |  |  | 530787.56 | 0 | 530787.56 | 2016-05-16 10:20 | 2025-12-31 | 2016-10-01 | open
75084 | SG000438F | SGSELFKY | SGSELFKY - DEK SEGMENTATION & AUTOMATION | 2199.65 |  | 2199.65 |  |  | 1481419.26 | 0 | 1481419.26 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01 | open
75084 | ORDFA | SKY2103DC | SKY2103DC - TO CAPTURE 2021 CAPITAL STORM #3 | -3667.28 |  | -3667.28 |  |  | 9.0949e-13 | 0 | 9.0949e-13 | 2020-12-07 16:50 | 2022-03-31 | 2021-03-01 | cancelled
75084 | ORDFA | SKY2104DC | SKY2104DC - TO CAPTURE 2021 CAPITAL STORM #4 | -6333.74 |  | -6333.74 |  |  | -1.819e-12 | 0 | -1.819e-12 | 2020-12-07 16:53 | 2022-03-31 | 2021-06-01 | cancelled
75084 | ORDFA | SKY2105DC | SKY2105DC - TO CAPTURE 2021 CAPITAL STORM #5 | -172.66 |  | -172.66 |  |  | 6621.82 | 5176.57 | 1445.25 | 2020-12-07 16:57 | 2022-03-31 | 2021-06-01 | 2021-09-30
75084 | ORDFA | SKY2106DC | SKY2106DC - TBC TO CAPTURE 2021 CAPITAL STOR | -2035.35 |  | -2035.35 |  |  | -1.0003e-13 | 0 | -1.0003e-13 | 2020-12-07 16:59 | 2022-10-01 | 2021-07-01 | cancelled
75084 | ORDFA | SKY2108DC | SKY2108DC - TBC TO CAPTURE 2021 CAPITAL STOR | -2143.6 |  | -2143.6 |  |  | 5.6388e-13 | 0 | 5.6388e-13 | 2021-05-04 14:31 | 2022-10-01 | 2021-10-01 | cancelled
75084 | ORDFA | SKY2109DC | SKY2109DC - TO CAPTURE 2021 CAPITAL STORM #9 | -1207.77 |  | -1207.77 |  |  | 19498.26 | 18008.29 | 1489.97 | 2021-05-04 14:34 | 2022-03-31 | 2021-12-01 | 2022-03-30
75084 | ORDFA | SKY2201DC | SKY2201DC - TO CAPTURE 2022 CAPITAL STORM #1 | 48072.01 |  | 48072.01 |  |  | 48072.01 | 0 | 48072.01 | 2021-12-17 16:53 | 2022-09-30 | 2022-02-01 | open
75084 | ORDFA | SKY2202DC | SKY2202DC - TO CAPTURE 2022 CAPITAL STORM #2 | 45064.93 |  | 45064.93 |  |  | 45064.93 | 0 | 45064.93 | 2021-12-17 16:55 | 2022-09-30 | 2022-03-01 | open
75084 | ORDFA | SKY2203DC | SKY2203DC - TO CAPTURE 2022 CAPITAL STORM #3 | 39678.29 |  | 39678.29 |  |  | 39678.29 | 0 | 39678.29 | 2021-12-17 16:59 | 2022-09-30 | 2022-05-01 | open
75084 | ORDFA | SKY2204DC | SKY2204DC - TO CAPTURE 2022 CAPITAL STORM #4 | 3724.04 |  | 3724.04 |  |  | 3724.04 | 0 | 3724.04 | 2022-03-21 18:20 | 2022-09-30 | 2022-06-01 | open
75084 | ORDFA | SKY2205DC | SKY2205DC - TO CAPTURE 2022 CAPITAL STORM #5 | 7513.1 |  | 7513.1 |  |  | 7513.1 | 0 | 7513.1 | 2022-03-21 18:22 | 2022-09-30 | 2022-06-01 | open
75084 | ORDFA | SKY2206DC | SKY2206DC - TO CAPTURE 2022 CAPITAL STORM #6 | 41459.04 |  | 41459.04 |  |  | 41459.04 | 0 | 41459.04 | 2022-03-21 18:24 | 2022-09-30 | 2022-06-01 | open
75084 | ORDFA | SKY2207DC | SKY2207DC - TO CAPTURE 2022 CAPITAL STORM #7 | 14925.75 |  | 14925.75 |  |  | 14925.75 | 0 | 14925.75 | 2022-03-21 18:26 | 2022-09-30 | 2022-06-01 | open
75084 | ORDFA | SKY2208DC | SKY2208DC - TO CAPTURE 2022 CAPITAL STORM #8 | 140103.24 |  | 140103.24 |  |  | 140103.24 | 0 | 140103.24 | 2022-03-21 18:27 | 2022-09-30 | 2022-07-01 | open
75084 | ORDFA | SKY2209DC | SKY2209DC - TO CAPTURE 2022 CAPITAL STORM #9 IT | 4247.48 |  | 4247.48 |  |  | 4247.48 | 0 | 4247.48 | 2022-03-21 18:29 | 2022-09-30 | 2022-07-01 | open
75084 | ORDFA | SKY2210DC | SKY2210DC - TO CAPTURE 2022 CAPITAL STORM #10 I | 44507.2 |  | 44507.2 |  |  | 44507.2 | 0 | 44507.2 | 2022-03-21 18:31 | 2022-09-30 | 2022-12-01 | open
75084 | SG990098F | SPOLCMKY | SPOLCMKY - SG- REACTIVE POLE REPLCMNTS DMWKY | 1022.73 |  | 1022.73 |  |  | 1022.73 | 0 | 1022.73 | 2017-04-04 08:57 | 2050-12-31 | 2022-07-01 | open
75084 | SG990022F | SRRRKY | SRRRKY - SG - RECLOSURE REPLACEMENTS DMWKY | 175137 |  | 175137 |  |  | 715046.28 | 0 | 715046.28 | 2017-04-04 13:14 | 2050-12-31 | 2019-03-01 | open
75084 | TKY1791 | T1791DL2 | T1791DL2 - AM 22674438 VILLA 42. | 59.26 |  | 59.26 |  |  | -1.5876e-14 | 0 | -1.5876e-14 | 2017-11-02 14:30 | 2020-08-31 | 2020-01-01 | 2020-06-09
75080 | FPIT | TC210HW57 | TC210HW57 - CIOPS NERC CIP CYBERARK HW | 1805.51 |  | 1805.51 |  |  | 1805.51 | 1538 | 267.51 | 2021-12-10 15:13 | 2024-09-30 | 2022-01-01 | cancelled
75080 | FPIT | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | 9186.18 |  | 9186.18 |  |  | 9186.18 | 16982 | -7795.82 | 2021-12-10 14:04 | 2024-03-31 | 2022-02-01 | 2024-03-01
75084 | FTDITKE | TDITKE | TDITKE - PD KENTUCKY IT HARDWARE | 56.21 |  | 56.21 |  |  | 2886.84 | 0 | 2886.84 | 2010-07-01 | 2025-12-25 | 2016-05-01 | open
75084 | TKY1999 | TKY199903 | TKY199903 - CONSTANCE BUS 1 SWGR CB RPL | -77009.75 |  | -77009.75 |  |  | 8002.78 | 2390612 | -2382609.22 | 2018-07-06 10:02 | 2024-06-21 | 2019-02-01 | cancelled
75084 | TLRKY22 | TLRKY2201 | TLRKY2201 - TLRKY22 -FIF POLE 20G-301/HL667 F35 | 27185.25 |  | 27185.25 |  |  | 27185.25 | 27180.1 | 5.15 | 2022-04-25 10:01 | 2022-11-28 | 2022-06-01 | 2022-12-28
75084 | TOUTKY | TOUTKY05 | TOUTKY05 - F5967 AUTODAMAGE 1 P1 POLE REPLACE | -18290.3 |  | -18290.3 |  |  | 20213.2 | 55812 | -35598.8 | 2019-03-07 14:01 | 2020-01-18 | 2019-03-01 | 2019-06-29
75084 | 75084 | TPO00170 | TPO00170 - OUA SUSTAINABILITY UPLIFT | 39699.08 |  | 39699.08 |  |  | 39699.08 | 72918 | -33218.92 | 2022-08-23 14:07 | 2023-08-31 | 2022-08-01 | 2023-09-30
75084 | VMTDFA | TVMBLLVKY | TVMBLLVKY - TVM NONNERC CAP - DEK | 25669.84 |  | 25669.84 |  |  | 234984.73 | 0 | 234984.73 | 2019-10-16 14:36 | 2050-12-31 | 2020-03-01 | open
75085 | FPUISFTWR | UIRATEDES | UIRATEDES - IU RATE DESIGN TOOL | 36499.27 |  | 36499.27 |  |  | 122114.2 | 213693 | -91578.8 | 2021-01-29 09:45 | 2026-03-31 | 2021-02-01 | open
75084 | 22100041A | V2210HAZK | V2210HAZK - SUB OPT - HAZ - OAKBROOK STA - 2210 | 5378.78 |  | 5378.78 |  |  | 5378.78 | 0 | 5378.78 | 2021-12-20 14:05 | 2025-03-31 | 2022-03-01 | 2024-01-23
75084 | 75084VM | VDEXTCUKY | VDEXTCUKY - VDEXTCUKY | 9358.48 |  | 9358.48 |  |  | 16289.29 | 0 | 16289.29 | 2017-07-13 12:51 | 2050-12-31 | 2021-01-01 | open
75084 | 75084VM | VDHAZL2KY | VDHAZL2KY - VDHAZL2KY | 56658.77 |  | 56658.77 |  |  | 276362.47 | 0 | 276362.47 | 2020-12-22 15:04 | 2050-12-31 | 2021-02-01 | open
75084 | 75084VM | VDHAZPGKY | VDHAZPGKY - VDHAZPGKY | 320810.38 |  | 320810.38 |  |  | 1273784.72 | 0 | 1273784.72 | 2017-05-25 15:32 | 2050-12-31 | 2018-01-01 | open
75084 | 75084VM | VDREMVCKY | VDREMVCKY - VDREMVCKY | 223965.42 |  | 223965.42 |  |  | 1901997.47 | 0 | 1901997.47 | 2017-05-25 11:52 | 2050-12-30 | 2018-01-01 | open
75084 | VMDDTFA | VMDDTKY | VMDDTKY - DISTR LINE CLR REMOVAL | 2447.65 |  | 2447.65 |  |  | 2114753.07 | 0 | 2114753.07 | 2008-07-01 | 2050-12-31 | 2008-07-01 | open
75084 | VMTDFA | VMTDKY | VMTDKY - TRANS LINE CLR REMOVAL | 122708.98 |  | 122708.98 |  |  | 1960287.58 | 0 | 1960287.58 | 2008-07-01 | 2050-12-31 | 2008-07-01 | open
75082 | WD010053 | WD010053X | WD010053X - SMARTGEN-WDC U1 T/G VIB MONITOR EOL | 0.12 |  | 0.12 |  |  | 219.56 | 6824.07 | -6604.51 | 2021-05-18 08:46 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD010059 | WD010059I | WD010059I - WD01 EMERGENT OUTAGE-(INS CLAIM) | 961.68 |  | 961.68 |  |  | -3308740.46 | 0 | -3308740.46 | 2021-09-21 07:19 | 2021-11-15 | 2021-09-01 | 2021-11-19
75082 | WD010061 | WD01006X | WD01006X - 125 VDC BATTERY CHARGER REPLACEMENT | 186.29 |  | 186.29 |  |  | 186.29 | 63280.01 | -63093.72 | 2022-11-29 09:32 | 2023-10-25 | 2022-12-01 | 2024-01-01
75082 | WD020008 | WD020008X | WD020008X - U2 AA MODULE HVAC REPLACEMENT | 31957.1 |  | 31957.1 |  |  | 33186.75 | 30620.34 | 2566.41 | 2021-09-23 12:50 | 2022-06-04 | 2021-09-01 | 2022-05-25
75082 | WD020021 | WD020021X | WD020021X - SMARTGEN-WDC U2 T/G VIB MONITOR EOL | 0.12 |  | 0.12 |  |  | 225.85 | 6824.07 | -6598.22 | 2021-05-18 09:21 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD030008 | WD030008X | WD030008X - OPTIM U3 GEN FIELD REWIND | 1911681.86 |  | 1911681.86 |  |  | 1911681.86 | 3043385.08 | -1131703.22 | 2022-01-25 10:13 | 2023-09-30 | 2022-01-01 | 2023-10-25
75082 | WD030013 | WD030013X | WD030013X - SMARTGEN-WDC U3 T/G VIB MONITOR EOL | 0.09 |  | 0.09 |  |  | 149.83 | 6824.07 | -6674.24 | 2021-05-18 09:33 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD030014 | WD030014X | WD030014X - SSMARTGEN WDC U3 MONITOR GFM | 65520.23 |  | 65520.23 |  |  | 65520.23 | 128769.43 | -63249.2 | 2022-06-07 17:51 | 2023-09-30 | 2022-06-01 | 2024-01-13
75082 | WD040020 | WD040020X | WD040020X - SMARTGEN-WDC U4 T/G VIB MONITOR EOL | 0.08 |  | 0.08 |  |  | 139.42 | 6824.07 | -6684.65 | 2021-05-18 09:43 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD050019 | WD050019X | WD050019X - SMARTGEN-WDC U5 T/G VIB MONITOR EOL | 0.09 |  | 0.09 |  |  | 149.83 | 6824.07 | -6674.24 | 2021-05-18 09:51 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD060018 | WD060018X | WD060018X - SMARTGEN-WDC U6 T/G VIB MONITOR EOL | 0.12 |  | 0.12 |  |  | 204.16 | 6824.07 | -6619.91 | 2021-05-18 09:57 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WDC00020 | WDC00020X | WDC00020X - WDC CONTROL ROOM HVAC REPLACEMENT | 282438.19 |  | 282438.19 |  |  | 282438.19 | 361717.68 | -79279.49 | 2022-04-19 12:06 | 2023-03-31 | 2022-06-01 | 2023-03-28
75082 | WDC00085 | WDC00085X | WDC00085X - REPLACE OVATION GPS CLOCK | 15826.72 |  | 15826.72 |  |  | 15826.72 | 17755.2 | -1928.48 | 2022-07-06 15:37 | 2022-12-31 | 2022-10-01 | 2022-10-29
75082 | WDCM0068 | WDCM0068X | WDCM0068X - FP NOTIFICATION SYSTEM | 33712.17 |  | 33712.17 |  |  | 33712.17 | 18551.31 | 15160.86 | 2022-07-07 09:22 | 2023-03-15 | 2022-10-01 | 2023-03-15
75082 | WDCM0070 | WDCM0070X | WDCM0070X - REPLACE LEVEL TRANSMITTER SYSTEMS | 27808.22 |  | 27808.22 |  |  | 27808.22 | 70025.28 | -42217.06 | 2022-09-15 12:18 | 2023-07-31 | 2022-09-01 | 2023-08-12
75084 | TOT00003 | WEBFG | WEBFG - WEBFG REPLACEMENT | 1639.35 |  | 1639.35 |  |  | 23416.52 | 79688 | -56271.48 | 2019-10-18 07:58 | 2022-03-31 | 2019-10-01 | 2022-04-14
|  |  |  | 88817826.034 | 82364337.4199 | -6453488.6141 | -7.835% | 0

## 2023
Duke Energy Kentucky Electric
Year 2023
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75081 | EB1922 | CEB1922 | CEB1922 - EBS-2 GENERAL EQUIPMENT | 102050.44 |  | 102050.44 |  |  | 2492007.94 | 2211650.74 | 280357.2 | 2005-08-10 | 2028-12-31 | 2008-07-01 | 2001-05-01
75084 | 75084IK | MX0924912 | MX0924912 - MXCONV-JT- E TRIPLE CROWN SUBD SEC | -1911.47 |  | -1911.47 |  |  | 46651.21 | 213849.76 | -167198.55 | 2017-11-03 14:01 | 2018-03-01 | 2017-11-01 | 2018-05-07
75084 | KHRF51720 | KHR851720 | KHR851720 - RI 11851720 RICE PIKE | 121770 |  | 121770 |  |  | 440966.74 | 75014.92 | 365951.82 | 2017-04-13 14:02 | 2018-05-01 | 2017-04-01 | 2018-07-04
75084 | DKY1912 | D1912DS1 | D1912DS1 - COVINGTON XTR 2_RUSD - DKY1912 | -253.05 |  | -253.05 |  |  | 3040137.55 | 3043244.61 | -3107.06 | 2016-08-19 09:12 | 2017-09-01 | 2016-09-01 | 2018-08-19
75084 | KYRELT | KYRELT02 | KYRELT02 - F6761 RICHWOOD EO 71/75 | -64335.59 |  | -64335.59 |  |  | 4136.99 | 622079.91 | -617942.92 | 2018-09-04 10:02 | 2019-09-04 | 2018-09-01 | 2019-08-10
75084 | DEMERKY | MX4946544 | MX4946544 - CAPITAL ALEXANDRIA SOUTH TB1 REPLAC | -28.1 |  | -28.1 |  |  | 2687.9 | 7569.04 | -4881.14 | 2019-12-04 14:01 | 2023-09-30 | 2020-08-01 | 2020-09-28
75084 | 75084IL | MX7650909 | MX7650909 - OVATION MUSIC VENUE LIGHTING 4TH & | 1 |  | 1 |  |  | 1 | 40929.04 | -40928.04 | 2020-08-27 14:01 | 2021-03-18 | 2020-10-01 | 2021-03-01
75084 | TEMERKY | MX1266171 | MX1266171 - CAPITAL SILVER GROVE TB23 REPLACE F | 621.65 |  | 621.65 |  |  | 1502.58 | 1613.31 | -110.73 | 2021-06-11 18:02 | 2022-03-31 | 2021-07-01 | 2021-11-05
75084 | 75084IK | MX0604532 | MX0604532 - TRANSFORMER RETROFIT HANDS 43 | 745.97 |  | 745.97 |  |  | 111379.41 | 119596.25 | -8216.84 | 2021-04-22 10:02 | 2022-01-27 | 2021-07-01 | 2022-01-18
75084 | DEMERKY | MX2831125 | MX2831125 - CAPITAL WHITE TOWER CB 223 REPLACE | 477.59 |  | 477.59 |  |  | 12738.19 | 14066 | -1327.81 | 2021-11-02 14:02 | 2023-09-30 | 2021-11-01 | 2022-02-27
75084 | 75084HW | MX2120706 | MX2120706 - TMG- 614 MADISON AVE.-INSTALL - CO | 636.82 |  | 636.82 |  |  | 40367.25 | 72130.02 | -31762.77 | 2021-10-08 18:02 | 2022-05-05 | 2021-10-01 | 2022-05-04
75084 | 75084HW | MX1330863 | MX1330863 - DKY2927 WESTERN AVE STABILIZATION P | 8796.49 |  | 8796.49 |  |  | 214245.59 | 118278.11 | 95967.48 | 2021-12-09 18:02 | 2022-06-09 | 2021-12-01 | 2022-05-22
75084 | 75084HW | MX1917337 | MX1917337 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 436.32 |  | 436.32 |  |  | -349.7 | 7317.29 | -7666.99 | 2021-08-10 18:03 | 2022-05-26 | 2021-10-01 | 2022-05-24
75084 | 75084HW | MX2506723 | MX2506723 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 717.53 |  | 717.53 |  |  | 290525.96 | 173052.3 | 117473.66 | 2021-10-07 10:02 | 2022-07-28 | 2021-10-01 | 2022-06-13
75084 | 75084IK | MX1261517 | MX1261517 - RLM: 1431 DIXIE: MULTIFAMILY PRIMAR | 2502.97 |  | 2502.97 |  |  | 73916.94 | 48426.64 | 25490.3 | 2021-09-22 10:01 | 2022-07-27 | 2021-10-01 | 2022-06-13
75085 | CUSTCONN | 315986F | 315986F - CUSTOMER CONNECT- R6-8 SCOPE | 32.39 |  | 32.39 |  |  | 658843.39 | 76898 | 581945.39 | 2021-03-30 10:43 | 2022-06-30 | 2021-04-01 | 2022-07-06
75084 | 75084IK | MX1898562 | MX1898562 - JT-E-TRAEMORE PHASE C PART 1B | 10.19 |  | 10.19 |  |  | 98911.5 | 55287.54 | 43623.96 | 2021-12-16 10:02 | 2022-08-27 | 2022-01-01 | 2022-07-24
75084 | 75084IK | MX2636418 | MX2636418 - RESIDENTIAL PRIMARY/SECONDARY/SVC P | 1809.61 |  | 1809.61 |  |  | 14972.14 | 35816.35 | -20844.21 | 2022-01-18 10:02 | 2022-07-28 | 2022-01-01 | 2022-07-26
75084 | DKY2020 | MX9210584 | MX9210584 - WILDER 42 ROW REM - SOG DKY2020 | 29453.83 |  | 29453.83 |  |  | 64195.07 | 13934.21 | 50260.86 | 2021-01-04 10:02 | 2022-08-04 | 2021-08-01 | 2022-07-27
75084 | SG000723F | SG723SW | SG723SW - DEE AMI OPERATIONS TOOL | 94.72 |  | 94.72 |  |  | 46648.18 | 38014 | 8634.18 | 2020-01-15 11:35 | 2022-07-30 | 2020-04-01 | 2022-07-31
75084 | 75084HW | MX2153094 | MX2153094 - KENTABOO AVE RECO PH 2 | 4019.38 |  | 4019.38 |  |  | 107164.61 | 59180.04 | 47984.57 | 2022-03-03 10:01 | 2022-09-08 | 2022-03-01 | 2022-08-09
75084 | DEMERKY | MX5232305 | MX5232305 - CAPITAL HEBRON VR2 REPLACE 3 LA'S | -95.88 |  | -95.88 |  |  | 4169.78 | 4259 | -89.22 | 2022-05-31 18:01 | 2024-03-30 | 2022-06-01 | 2022-08-25
75084 | M210257 | M21025701 | M21025701 - EMR COLD SPRINGS TO WILDER - 69KV H | 53334.4 |  | 53334.4 |  |  | 1861538.49 | 2407350 | -545811.51 | 2021-05-05 10:02 | 2022-07-30 | 2021-05-01 | 2022-08-25
75084 | M210323 | M21032301 | M21032301 - EMR - CIRCUIT 965 REPLACE ABS 346 | 9892.91 |  | 9892.91 |  |  | 434454.68 | 139856 | 294598.68 | 2021-11-12 14:01 | 2022-08-29 | 2021-12-01 | 2022-08-29
75084 | FPIT | LTHTNEXS | LTHTNEXS - LH EQUIP STRATEGY PLANNG & OPTIM SW | -733.15 |  | -733.15 |  |  | 2957.79 | 3121 | -163.21 | 2021-06-28 10:31 | 2022-08-31 | 2022-10-01 | 2022-08-30
75081 | EB020818 | EB020818X | EB020818X - FGD BIOCIDE SYSTEM H2S MITIGATION | 30187.61 |  | 30187.61 |  |  | 333316.53 | 331027.09 | 2289.44 | 2020-07-01 14:25 | 2022-09-30 | 2020-07-01 | 2022-09-15
75084 | FPIT | LTHTRQKO | LTHTRQKO - LTH TRANSMISSION ESPO QUICK SW | -90.54 |  | -90.54 |  |  | 2322.01 | 2420 | -97.99 | 2021-06-28 10:43 | 2022-08-31 | 2022-05-01 | 2022-09-15
75085 | CUSTCONN | 315986HW8 | 315986HW8 - CUSTOMER CONNECT- HARDWARE PROJ 6 | -17.06 |  | -17.06 |  |  | 53230.8 | 96250 | -43019.2 | 2021-09-27 15:14 | 2022-06-30 | 2021-10-01 | 2022-09-15
75084 | 75084IK | MX8022852 | MX8022852 - PERM ELEC SERV;COMM/INDUST;OTHER;CI | -3962.16 |  | -3962.16 |  |  | 22298.36 | 23793.81 | -1495.45 | 2021-06-04 10:02 | 2022-08-08 | 2021-06-01 | 2022-09-18
75084 | TEMERKY | MX9649928 | MX9649928 - CAPITAL BUFFINGTON TB3 REPLACE ETM | 2476.06 |  | 2476.06 |  |  | 14810.04 | 16341 | -1530.96 | 2021-02-02 14:02 | 2023-09-30 | 2021-02-01 | 2022-09-28
75084 | 75084IK | MX7473884 | MX7473884 - OAKBROOK 42 LN EXT DKY2769 | 11416.63 |  | 11416.63 |  |  | 186979.93 | 81818.3 | 105161.63 | 2020-09-16 18:01 | 2022-12-29 | 2020-10-01 | 2022-10-17
75084 | 75084IK | MX3222426 | MX3222426 - JT-E-TUSCANY SECTION 021 | -18287.41 |  | -18287.41 |  |  | 88200.66 | 56036.05 | 32164.61 | 2022-03-08 14:24 | 2022-10-23 | 2022-04-01 | 2022-10-30
75084 | 75084IK | MX7890923 | MX7890923 - UPGRADE TO EXISTING SERVICE COMMERC | -206975.52 |  | -206975.52 |  |  | 160624.51 | 246708.65 | -86084.14 | 2020-11-17 10:01 | 2022-11-24 | 2020-11-01 | 2022-10-30
75084 | EAMHPBU | 349472022 | 349472022 - NEW BOUD SERVERS | 980.4 |  | 980.4 |  |  | 980.4 | 166 | 814.4 | 2022-05-20 14:28 | 2023-03-31 | 2023-05-01 | 2022-10-30
75084 | FPIT | LTHESPOTS | LTHESPOTS - LH EQUIP STRATEGY PLANNG & OPTIM SW | 2770.26 |  | 2770.26 |  |  | 40658.53 | 36161 | 4497.53 | 2021-06-28 08:22 | 2022-11-01 | 2022-10-01 | 2022-11-01
75084 | CP18SUBK | MX1450766 | MX1450766 - CAPITAL CONSTANCE TB2 REPLACE HS AR | 1926.62 |  | 1926.62 |  |  | 14886.75 | 15137 | -250.25 | 2019-02-12 14:01 | 2023-09-30 | 2019-04-01 | 2022-11-03
75084 | DEMERKY | MX5324522 | MX5324522 - CAPITAL RICHWOOD CIR 42 REPLACE HOO | -518.75 |  | -518.75 |  |  | 6606.99 | 6727.96 | -120.97 | 2022-06-02 14:01 | 2023-03-31 | 2022-06-01 | 2022-11-03
75084 | M190298 | MX4154102 | MX4154102 - F5967 - REBUILD MARSHALL RD - M1902 | 81468.08 |  | 81468.08 |  |  | 479445.86 | 287220.92 | 192224.94 | 2022-02-18 14:01 | 2022-10-27 | 2022-04-01 | 2022-11-06
75081 | EB021751 | EB021751X | EB021751X - PHYSICAL LOCK PILOT | 1353.71 |  | 1353.71 |  |  | 194610.01 | 216857.16 | -22247.15 | 2021-05-07 07:34 | 2022-11-30 | 2021-06-01 | 2022-11-08
75080 | MRTP2022 | 400098004 | 400098004 - 2022 TELECOM LMR HARRIS RADIO TEST | -15.69 |  | -15.69 |  |  | 45682.79 | 54910 | -9227.21 | 2022-05-27 11:22 | 2022-10-28 | 2022-07-01 | 2022-11-08
75084 | 75084IK | MX3953933 | MX3953933 - COMMERCIAL PRIMARY/SECONDARY/SVC | -24832.91 |  | -24832.91 |  |  | 72780.65 | 138617.24 | -65836.59 | 2022-02-22 10:01 | 2022-11-17 | 2022-03-01 | 2022-11-09
75084 | M190233 | MX4864988 | MX4864988 - F5983 DAYTON TO LAFARGE X-FER UB FO | -36279.7 |  | -36279.7 |  |  | 345856.36 | 222076.22 | 123780.14 | 2019-11-26 18:01 | 2023-01-29 | 2020-12-01 | 2022-11-09
75084 | SG000437F | MX7891196 | MX7891196 - 2022 RECL RPL, KNK-5766, KENTON (9) | -36.83 |  | -36.83 |  |  | 11780.29 | 18815.81 | -7035.52 | 2021-11-16 14:01 | 2023-02-02 | 2022-02-01 | 2022-11-20
75084 | 75084IK | MX4412975 | MX4412975 - DETERIORATED CONDUCTOR (WILDER 42) | -28796.47 |  | -28796.47 |  |  | 106028.58 | 55221.15 | 50807.43 | 2020-07-02 10:01 | 2022-12-15 | 2020-07-01 | 2022-11-23
75084 | 75084IK | MX8299291 | MX8299291 - JT-E-INDIAN RIDGE APARTMENTS | -16935.91 |  | -16935.91 |  |  | 76205.49 | 50836.86 | 25368.63 | 2022-03-22 10:02 | 2022-11-27 | 2022-04-01 | 2022-11-23
75084 | SG990022F | MX4546275 | MX4546275 - 2021 PROACTIVE RECL RPL, KNK-5759, | -61.04 |  | -61.04 |  |  | 66016.26 | 53891.15 | 12125.11 | 2021-03-25 10:02 | 2022-12-29 | 2021-04-01 | 2022-11-28
75084 | 75084IK | MX3188132 | MX3188132 - BBB-TAPESTRY AT TURFWAY - ARLINGTON | 43157.26 |  | 43157.26 |  |  | 238435.24 | 233096.92 | 5338.32 | 2022-07-13 10:01 | 2022-12-11 | 2022-08-01 | 2022-11-29
75081 | FPITF | IT2200162 | IT2200162 - ACT (FACILEX) UPGRADE TO VERSION 7. | -5.08 |  | -5.08 |  |  | 2580.01 | 2600 | -19.99 | 2022-11-16 13:59 | 2022-11-17 | 2022-12-01 | 2022-11-30
75082 | FPITF | IT2200162 | IT2200162 - ACT (FACILEX) UPGRADE TO VERSION 7. | -3.8 |  | -3.8 |  |  | 1930.94 | 1946 | -15.06 | 2022-11-16 14:08 | 2022-11-17 | 2022-12-01 | 2022-11-30
75084 | SG000732F | SG732TR06 | SG732TR06 - COMMUNICATION TOWER, SHELTER AND SY | 964.11 |  | 964.11 |  |  | 1551097.73 | 1777260 | -226162.27 | 2021-06-10 07:49 | 2022-11-15 | 2021-06-01 | 2022-11-30
75084 | SG001117F | SG001117 | SG001117 - DEE LMR CONSOLES | -12692.05 |  | -12692.05 |  |  | 753824 | 874447 | -120623 | 2021-08-25 19:52 | 2023-03-31 | 2021-09-01 | 2022-11-30
75084 | 75084IK | MX8250982 | MX8250982 - DETERIORATED CONDUCTOR - CRITTENDEN | -210213.95 |  | -210213.95 |  |  | 972861.26 | 508337.93 | 464523.33 | 2021-03-24 10:02 | 2022-12-01 | 2021-04-01 | 2022-11-30
75084 | FPIT | IT2200029 | IT2200029 - DCC SATELLITE PHONES | 1105.04 |  | 1105.04 |  |  | 3545.74 | 2187 | 1358.74 | 2022-02-24 09:24 | 2022-07-30 | 2022-03-01 | 2022-12-01
75081 | EB022052 | EB022052X | EB022052X - COMMON FLY ASH SEPARATOR BAGS | -183.22 |  | -183.22 |  |  | 32975.55 | 28030.58 | 4944.97 | 2022-11-21 08:26 | 2023-03-31 | 2022-11-01 | 2022-12-05
75084 | 75084IK | MX4684560 | MX4684560 - EWD; 7900 FOUNDATION DR; BUFFINGTON | -4351 |  | -4351 |  |  | 57629.3 | 50059.55 | 7569.75 | 2022-07-29 10:01 | 2022-12-08 | 2022-08-01 | 2022-12-05
75084 | 75084IK | MX9792877 | MX9792877 - JT-E-ELEVATION 800 | -6701.84 |  | -6701.84 |  |  | 102255.27 | 73814.69 | 28440.58 | 2022-03-01 14:01 | 2022-12-29 | 2022-03-01 | 2022-12-07
75084 | DKY2132 | MX9015414 | MX9015414 - LONGBRANCH 44 PART 2 - DKY2132 | -86872.38 |  | -86872.38 |  |  | 944073.85 | 529298.87 | 414774.98 | 2018-12-07 10:01 | 2022-11-29 | 2020-06-01 | 2022-12-18
75084 | KYGLT20 | MX8203329 | MX8203329 - GLT TR_UB F6785 T-LINE OHGLT2010 | -9791.85 |  | -9791.85 |  |  | 48070.08 | 36544.94 | 11525.14 | 2020-10-21 14:01 | 2022-12-29 | 2021-01-01 | 2022-12-18
75080 | RESBLDKY | KMW221271 | KMW221271 - AUGUSTINE OPS LOCKER ROOM AND PLUMB | -18668.93 |  | -18668.93 |  |  | 59631.17 | 61200 | -1568.83 | 2022-04-21 12:10 | 2022-10-27 | 2022-04-01 | 2022-12-23
75084 | 75084IK | MX4092751 | MX4092751 - JT-E-ALEXANDRIA FLATS PHASE 2; BLDG | -13953.02 |  | -13953.02 |  |  | 89867.95 | 66216.2 | 23651.75 | 2022-06-23 14:01 | 2022-12-29 | 2022-08-01 | 2022-12-25
75084 | FPIT | LTHTPVEZE | LTHTPVEZE - LIGHTHOUSE TRANSMISSION PLANTIEW EZ | 192.35 |  | 192.35 |  |  | 2589.63 | 1207 | 1382.63 | 2022-05-06 09:52 | 2022-12-29 | 2022-05-01 | 2022-12-31
75081 | EB022019 | EB022019X | EB022019X - 2-3 & 2-6 PULVERIZER FEEDER BELT | -98.02 |  | -98.02 |  |  | 16553.77 | 6228.58 | 10325.19 | 2022-09-15 15:41 | 2023-02-28 | 2022-09-01 | 2023-01-06
75085 | FPIT | CS2100010 | CS2100010 - CONTACT CENTER WORK FROM HOME | 1685.42 |  | 1685.42 |  |  | 3340.34 | 6922 | -3581.66 | 2022-01-26 14:18 | 2022-11-28 | 2022-02-01 | 2023-01-06
75084 | 75084IK | MX6266041 | MX6266041 - KEG - 200 W 3RD - OVATION - WILDER | 4684.77 |  | 4684.77 |  |  | 50591.63 | 46062.08 | 4529.55 | 2022-09-20 10:01 | 2023-01-19 | 2022-09-01 | 2023-01-08
75084 | 75084IK | MX6590208 | MX6590208 - JT-E-REDWOOD LIVING (APTS) | -12991.12 |  | -12991.12 |  |  | 145797.15 | 120985.65 | 24811.5 | 2022-03-22 10:02 | 2022-11-29 | 2022-05-01 | 2023-01-09
75084 | 75084HW | MX4216127 | MX4216127 - US RT 25 ROADWAY WIDENING - WALTON | 12755.43 |  | 12755.43 |  |  | 109655.11 | 93722.34 | 15932.77 | 2022-04-29 10:01 | 2022-12-29 | 2022-04-01 | 2023-01-11
75084 | 75084IK | MX6321063 | MX6321063 - LONGBRANCH 44 PT 2 | 39722.37 |  | 39722.37 |  |  | 440452.22 | 279083.39 | 161368.83 | 2021-04-06 18:02 | 2023-02-16 | 2021-04-01 | 2023-01-16
75084 | 75084IK | MX4074648 | MX4074648 - KSL; 7435 INDUSTRIAL; DIXIE 41; PER | 4102.21 |  | 4102.21 |  |  | 125914.57 | 115672.98 | 10241.59 | 2022-08-10 14:06 | 2023-02-09 | 2022-08-01 | 2023-01-23
75084 | TLRKY22 | MX5322324 | MX5322324 - GLT F3568 TLRKY2201 - FIF RPL 20G-3 | 2295.76 |  | 2295.76 |  |  | 11111.2 | 7472.73 | 3638.47 | 2022-06-03 10:01 | 2022-12-30 | 2022-10-01 | 2023-01-23
75081 | EB022034 | EB022034X | EB022034X - CRUSHER HOUSE & TRACTOR GAR LIGHTS | -150.5 |  | -150.5 |  |  | 17785.34 | 46717.52 | -28932.18 | 2022-10-25 09:48 | 2023-02-28 | 2022-10-01 | 2023-01-25
75084 | SG000438F | MX1278018 | MX1278018 - LONGBRANCH 44 PT 2 - RECL 2 MOUNT Z | 871.4 |  | 871.4 |  |  | 68715.13 | 46482.63 | 22232.5 | 2021-10-28 14:01 | 2023-01-29 | 2021-11-01 | 2023-01-26
75081 | EB022040 | EB022040X | EB022040X - FGD H2S MONITOR CABLE | -147.74 |  | -147.74 |  |  | 24420.08 | 36543.48 | -12123.4 | 2022-10-20 12:37 | 2023-02-28 | 2022-11-01 | 2023-01-30
75084 | 75084IK | MX2866326 | MX2866326 - KENTUCKY 2019 LINE PATROL OH REPLAC | -2104.59 |  | -2104.59 |  |  | 8072.25 | 9381.5 | -1309.25 | 2020-09-09 10:01 | 2023-01-13 | 2020-10-01 | 2023-01-30
75081 | EB020813 | CEB020813 | CEB020813 - SMARTGEN EBS XFMR IR MONITORING | -681.41 |  | -681.41 |  |  | 88984.37 | 114305.77 | -25321.4 | 2019-03-18 15:37 | 2022-12-31 | 2019-07-01 | 2023-01-31
75081 | EB022048 | EB022048X | EB022048X - MSP FA SILO DOOR & PLATFORM | 9852.54 |  | 9852.54 |  |  | 46316.45 | 81161.76 | -34845.31 | 2022-12-12 11:34 | 2025-02-28 | 2022-12-01 | 2023-01-31
75084 | SG001069F | SG1069GDQ | SG1069GDQ - DEE GRID DATA QUALITY GDQ | 274.22 |  | 274.22 |  |  | 146003.4 | 195874 | -49870.6 | 2020-10-26 14:01 | 2024-03-31 | 2020-11-01 | 2023-01-31
75084 | SG001094F | SG1094OTA | SG1094OTA - DEE OUTAGE TIMESTAMP ACCURACY | -44.73 |  | -44.73 |  |  | 26163.29 | 34685 | -8521.71 | 2021-11-30 18:05 | 2023-01-31 | 2021-12-01 | 2023-01-31
75081 | EB020863 | EB020863X | EB020863X - SCR REPLACE 3RD LAYER CATALYST | 3765.44 |  | 3765.44 |  |  | 1725231.43 | 1769561.89 | -44330.46 | 2022-03-15 13:02 | 2023-01-22 | 2022-03-01 | 2023-02-03
75081 | EB021799 | EB021799X | EB021799X - 2A & 2C MODULE OUTLET EXP JNT | 26.7 |  | 26.7 |  |  | 253553 | 59085.12 | 194467.88 | 2021-10-26 15:18 | 2022-12-31 | 2021-12-01 | 2023-02-03
75081 | EB021960 | EB021960X | EB021960X - SAH 2-1 BASKET REPLACEMENT | 2885.9 |  | 2885.9 |  |  | 1620902.96 | 2139212.81 | -518309.85 | 2022-08-18 10:38 | 2023-01-31 | 2022-08-01 | 2023-02-03
75081 | EB022050 | EB022050X | EB022050X - FGD COMMON OUTLET DUCT PLATFORM | -25.84 |  | -25.84 |  |  | 4599.57 | 29170.49 | -24570.92 | 2022-11-28 10:53 | 2023-03-31 | 2022-11-01 | 2023-02-03
75081 | EBS01262 | EBS01262X | EBS01262X - SAH 2-2 BASKET REPLACEMENT | 5137.24 |  | 5137.24 |  |  | 2371188.72 | 2781919.6 | -410730.88 | 2022-04-05 07:50 | 2023-01-31 | 2022-04-01 | 2023-02-03
75081 | EB021311 | EB021311X | EB021311X - 2-5 PULV ROLL WHEEL REPL 2022 | -6028.84 |  | -6028.84 |  |  | 755993.94 | 930314.07 | -174320.13 | 2022-03-15 08:36 | 2023-02-28 | 2022-07-01 | 2023-02-04
75081 | EB022012 | EB022012X | EB022012X - REPLACE DIESEL FP PUMP | -233.06 |  | -233.06 |  |  | 46242.47 | 49207.05 | -2964.58 | 2022-10-12 09:04 | 2023-02-28 | 2022-11-01 | 2023-02-04
75084 | 20670044A | MX6491994 | MX6491994 - SUB OPT -LINE PATROL NORMAL PRIORIT | -41.8 |  | -41.8 |  |  | 6137.08 | 5720.24 | 416.84 | 2021-12-10 10:01 | 2023-02-02 | 2022-01-01 | 2023-02-05
75084 | 20550041A | MX7372064 | MX7372064 - 0550041A: DONALDSON 41 BNK-1184 INS | -11.92 |  | -11.92 |  |  | 61216.91 | 44050.59 | 17166.32 | 2021-10-21 10:02 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | 20550041A | MX7372067 | MX7372067 - 0550041A: DONALDSON 41 26BN-246 INS | -9197.66 |  | -9197.66 |  |  | 45375.52 | 45568.45 | -192.93 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX7372068 | MX7372068 - 0550041A: DONALDSON 41 26BN-616 INS | 1166.69 |  | 1166.69 |  |  | 63080.51 | 41285.61 | 21794.9 | 2021-10-22 09:12 | 2023-02-02 | 2021-11-01 | 2023-02-05
75084 | 20670041A | MX1601008 | MX1601008 - TRANSFORMER UG 3-PHASE END OF LIFE | -621.22 |  | -621.22 |  |  | 44841.55 | 34548.66 | 10292.89 | 2021-11-02 10:02 | 2023-02-02 | 2022-02-01 | 2023-02-05
75084 | 20670041A | MX1701450 | MX1701450 - 0670041A: BUFFINGTON 41 K107-316 IN | 9694.53 |  | 9694.53 |  |  | 91586.35 | 89359.68 | 2226.67 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX1701488 | MX1701488 - 0670041A: BUFFINGTON 41 K106-544 IN | 1091.44 |  | 1091.44 |  |  | 63593.74 | 45212.76 | 18380.98 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | MX2157464 | MX2157464 - SUB OPT - KY 2020 LINE PATROL UG MI | 112.01 |  | 112.01 |  |  | 1399.1 | 1413.68 | -14.58 | 2021-08-31 10:02 | 2023-02-02 | 2022-08-01 | 2023-02-05
75084 | 20670041A | MX2157510 | MX2157510 - SUB OPT - KY 2020 LINE PATROL UG MI | -157.29 |  | -157.29 |  |  | 5247.38 | 1413.68 | 3833.7 | 2021-08-31 10:02 | 2023-02-02 | 2022-07-01 | 2023-02-05
75084 | 20670041A | MX2157534 | MX2157534 - SUB OPT - KY 2020 LINE PATROL UG MI | -12.16 |  | -12.16 |  |  | 1785.25 | 1413.68 | 371.57 | 2021-08-31 10:02 | 2023-02-02 | 2022-07-01 | 2023-02-05
75084 | 20670041A | MX2157572 | MX2157572 - SUB OPT - KY 2020 LINE PATROL UG MI | -5.96 |  | -5.96 |  |  | 874.51 | 1413.68 | -539.17 | 2021-08-31 10:02 | 2023-02-02 | 2022-06-01 | 2023-02-05
75084 | 20670041A | MX2157620 | MX2157620 - SUB OPT - KY 2020 LINE PATROL UG MI | -12.16 |  | -12.16 |  |  | 1785.25 | 1413.68 | 371.57 | 2021-08-31 10:02 | 2023-02-02 | 2022-07-01 | 2023-02-05
75084 | 20670045A | MX1393380 | MX1393380 - 0670045A: BUFFINGTON 45 K106-490 IN | -565.06 |  | -565.06 |  |  | 77800.64 | 44782.02 | 33018.62 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1393381 | MX1393381 - 0670045A: BUFFINGTON 45 K117-177 IN | 1714.08 |  | 1714.08 |  |  | 69184.02 | 43388.09 | 25795.93 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701461 | MX1701461 - 0670045A: BUFFINGTON 45 K116-472 IN | 1130.54 |  | 1130.54 |  |  | 74680.03 | 44901.57 | 29778.46 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670045A | MX1701463 | MX1701463 - 0670045A: BUFFINGTON 45 K117-114 IN | 2071.2 |  | 2071.2 |  |  | 74739.96 | 44985.64 | 29754.32 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393382 | MX1393382 - 0670047A: BUFFINGTON 47 26BN-58 INS | 212.27 |  | 212.27 |  |  | 68102.89 | 43289.81 | 24813.08 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393383 | MX1393383 - 0670047A: BUFFINGTON 47 K116-210 IN | 779.13 |  | 779.13 |  |  | 62166.82 | 45647.76 | 16519.06 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1393384 | MX1393384 - 0670047A: BUFFINGTON 47 K116-611 IN | -10298.17 |  | -10298.17 |  |  | 51637.76 | 47387.16 | 4250.6 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670047A | MX1701467 | MX1701467 - 0670047A: BUFFINGTON 47 K116-195 IN | 949.97 |  | 949.97 |  |  | 59879.01 | 44567.74 | 15311.27 | 2021-10-22 09:12 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20550041A | MX1701486 | MX1701486 - 0550041A: DONALDSON 41 26BN-1086 IN | 1381.51 |  | 1381.51 |  |  | 63065.62 | 44820.84 | 18244.78 | 2021-10-21 10:02 | 2023-02-02 | 2021-10-01 | 2023-02-05
75084 | 20670041A | V2067HAZK | V2067HAZK - SUB OPT - HAZ - BUFFINGTON - 2067 | 1769.72 |  | 1769.72 |  |  | 1769.72 | 0 | 1769.72 | 2021-12-17 11:52 | 2025-03-31 | 2023-05-01 | 2023-02-07
75081 | EB022014 | EB022014X | EB022014X - 2-2 PA FAN BEARING REPLACEMENT | -37623.39 |  | -37623.39 |  |  | 269157.52 | 306061.96 | -36904.44 | 2022-10-25 10:27 | 2023-02-28 | 2022-10-01 | 2023-02-09
75081 | EB022011 | EB022011X | EB022011X - REPL 2-1 FLYASH SILO DIFFUSER BLWR | -269.35 |  | -269.35 |  |  | 52058.94 | 41764.93 | 10294.01 | 2022-10-07 16:03 | 2023-02-28 | 2022-11-01 | 2023-02-10
75084 | 75084IK | MX6321718 | MX6321718 - LONGBRANCH 44 PART 3 - DKY2747 | -69589.81 |  | -69589.81 |  |  | 659619.15 | 377643.13 | 281976.02 | 2020-12-10 18:02 | 2023-01-29 | 2020-12-01 | 2023-02-13
75081 | EB022054 | EB022054X | EB022054X - 2-1 SBAC COOLER REPLACEMENT | -3693.64 |  | -3693.64 |  |  | 222476.83 | 220990.47 | 1486.36 | 2022-11-28 11:20 | 2023-03-31 | 2022-11-01 | 2023-02-14
75084 | DKY2645 | MX3890113 | MX3890113 - SG-CAPACITY NEEDS OUTSIDE THE SUBST | 2700.21 |  | 2700.21 |  |  | 57646.33 | 48733.93 | 8912.4 | 2022-03-25 18:01 | 2023-01-29 | 2022-04-01 | 2023-02-14
75081 | EB021014 | EB021014X | EB021014X - VOLTAGE REGULATOR BATTERY REPL | 12079.26 |  | 12079.26 |  |  | 68999.11 | 56676.65 | 12322.46 | 2022-05-12 09:27 | 2023-01-31 | 2022-05-01 | 2023-02-15
75084 | DKY2645 | MX3891718 | MX3891718 - WILDER 43 RECLOSER 2 - N/O NEAR POL | 4203.15 |  | 4203.15 |  |  | 51046.34 | 43668.27 | 7378.07 | 2022-03-30 14:01 | 2023-01-29 | 2022-04-01 | 2023-02-16
75080 | FPIT | IT2200066 | IT2200066 - COMPASS TO AWS | 591.69 |  | 591.69 |  |  | 19737.72 | 19126 | 611.72 | 2022-05-20 08:13 | 2023-01-29 | 2022-05-01 | 2023-02-17
75084 | M190298 | M19029803 | M19029803 - F5967 RBLD HL801 - HL746 - HL736 | 35068.92 |  | 35068.92 |  |  | 1404751.15 | 998899.36 | 405851.79 | 2021-06-07 18:02 | 2023-04-11 | 2021-08-01 | 2023-02-17
75084 | DKY2211 | MX3375944 | MX3375944 - COLD SPRING 49 - NEW UG EXIT/TERMIN | 7479.67 |  | 7479.67 |  |  | 45481.24 | 22488.76 | 22992.48 | 2022-04-25 14:01 | 2023-02-28 | 2022-04-01 | 2023-02-19
75084 | 75084IL | MX4765729 | MX4765729 - 7050 NEW BUFFINGTON RD AREA LIGHT P | 37468.04 |  | 37468.04 |  |  | 123694.2 | 83809.8 | 39884.4 | 2022-05-06 10:01 | 2023-02-28 | 2022-08-01 | 2023-02-20
75084 | M180378 | MX6610978 | MX6610978 - M18037801.RICHWOOD - DISTRIBUTION L | 1367.91 |  | 1367.91 |  |  | 3589.82 | 3935 | -345.18 | 2022-10-18 18:01 | 2023-02-21 | 2022-11-01 | 2023-02-20
75084 | 75084HW | MX4698193 | MX4698193 - MAKE-READY, 2203MCI0285DEK - MCI PR | 4281.63 |  | 4281.63 |  |  | -6306.9 | 46988.34 | -53295.24 | 2022-09-12 10:01 | 2023-03-22 | 2022-09-01 | 2023-02-21
75084 | M180387 | M18038701 | M18038701 - COLD SPRING TB 9 LS UPGD | -76371.08 |  | -76371.08 |  |  | 1148505.57 | 1422585 | -274079.43 | 2021-02-16 18:02 | 2023-01-27 | 2021-03-01 | 2023-02-21
75084 | 75084IK | MX1788880 | MX1788880 - JT-E-RESERVE AT BELLEVUE | -34854.78 |  | -34854.78 |  |  | 168591.94 | 122201.43 | 46390.51 | 2022-01-13 14:01 | 2023-03-29 | 2022-04-01 | 2023-02-27
75081 | EB022015 | EB022015X | EB022015X - REPLACE VOLTAGE REG EXCITATION XFMR | 209.51 |  | 209.51 |  |  | 2883.72 | 2948.39 | -64.67 | 2022-10-12 07:29 | 2023-02-28 | 2022-12-01 | 2023-02-28
75084 | SG000438F | MX1277606 | MX1277606 - LONGBRANCH 44 PT 2 - RECL 1 MOUNT Z | 74 |  | 74 |  |  | 64579.09 | 47359.32 | 17219.77 | 2021-10-28 14:01 | 2023-03-15 | 2021-11-01 | 2023-03-01
75084 | 75084HW | MX4698796 | MX4698796 - MAKE-READY, 2203MCI0287DEK, MCI PRO | 743.53 |  | 743.53 |  |  | -19132.55 | 38488.98 | -57621.53 | 2022-09-22 14:01 | 2023-04-06 | 2022-09-01 | 2023-03-05
75084 | 75084IK | MX4984124 | MX4984124 - LONGBRANCH 44 PT 2 C- DKY2132 | -38654.92 |  | -38654.92 |  |  | 68080.85 | 35300.69 | 32780.16 | 2022-05-02 14:01 | 2023-03-31 | 2022-06-01 | 2023-03-05
75084 | 75084HW | MX2869961 | MX2869961 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 69641.94 |  | 69641.94 |  |  | 81935.62 | 327020.35 | -245084.73 | 2021-11-02 18:02 | 2023-03-30 | 2022-05-01 | 2023-03-06
75084 | DKY2645 | MX3893236 | MX3893236 - WILDER 43 RECLOSER 3 - N/O NEAR POL | 524.32 |  | 524.32 |  |  | 50642.53 | 44282.29 | 6360.24 | 2022-03-30 14:01 | 2023-01-29 | 2022-04-01 | 2023-03-06
75084 | SG000438F | MX1278081 | MX1278081 - LONGBRANCH 44 PT 2 - RECL 3 MOUNT Z | 1429.84 |  | 1429.84 |  |  | 67884.38 | 46603.9 | 21280.48 | 2021-10-28 14:01 | 2023-03-15 | 2021-11-01 | 2023-03-06
75084 | 75084IK | MX4154470 | MX4154470 - OPEN LOOP - CABLE UG REPLACE SMALL- | -1732.83 |  | -1732.83 |  |  | 794016.59 | 74076.7 | 719939.89 | 2021-10-06 10:02 | 2023-05-16 | 2021-12-01 | 2023-03-09
75081 | EB022013 | EB022013X | EB022013X - REPL GAS PUMP AND FUEL TANK | -1847.13 |  | -1847.13 |  |  | 39533.44 | 28028.62 | 11504.82 | 2022-09-28 14:10 | 2023-01-30 | 2022-10-01 | 2023-03-09
75084 | M200011 | M20001101 | M20001101 - ALEXANDRIA SOUTH INSTALL BATTERY CA | -4149.6 |  | -4149.6 |  |  | 119805.52 | 119805.52 | 0 | 2022-02-17 18:01 | 2023-03-12 | 2022-03-01 | 2023-03-09
75084 | SG001076F | SG1076OCT | SG1076OCT - DEE CAPITAL INVESTMENT PLANNING | 1626.41 |  | 1626.41 |  |  | 169834.06 | 231176 | -61341.94 | 2020-11-11 10:19 | 2023-03-31 | 2020-12-01 | 2023-03-12
75084 | 75084IK | MX1936350 | MX1936350 - JT-E-VILLAGE OF DECOURSEY CREEK | 51932.66 |  | 51932.66 |  |  | 316384.43 | 174468.65 | 141915.78 | 2022-07-27 18:01 | 2023-05-07 | 2022-09-01 | 2023-03-12
75084 | M220344 | M22034401 | M22034401 - LONGBRANCH SUBSTATION - REPLACE VR | 10810.05 |  | 10810.05 |  |  | 56658.42 | 59349.78 | -2691.36 | 2022-11-30 10:08 | 2023-03-04 | 2022-12-01 | 2023-03-12
75084 | 75084IK | MX5778428 | MX5778428 - MAKE READY FOR MEMORIAL PT PHASE 1 | -10577.01 |  | -10577.01 |  |  | 6656.66 | 37851.61 | -31194.95 | 2022-11-03 18:02 | 2023-05-29 | 2022-11-01 | 2023-03-13
75080 | FPIT | IT2200054 | IT2200054 - CONSOLIDATE BPM REPORTING | -3882.67 |  | -3882.67 |  |  | 74141.41 | 62342 | 11799.41 | 2022-06-21 09:00 | 2023-03-30 | 2022-07-01 | 2023-03-13
75080 | FPIT | CO2200002 | CO2200002 - UTILITY ASSISTANCE MODERN ARCHITECT | 257.69 |  | 257.69 |  |  | 1927.86 | 6593 | -4665.14 | 2022-06-30 10:29 | 2022-12-29 | 2022-07-01 | 2023-03-15
75081 | EB022056 | EB022056X | EB022056X - 2-1 SERVICE WATER PUMP OVERHAUL | -14261.39 |  | -14261.39 |  |  | 228555.64 | 233100 | -4544.36 | 2022-11-29 16:24 | 2023-02-28 | 2022-11-01 | 2023-03-15
75082 | WDCM0068 | WDCM0068X | WDCM0068X - FP NOTIFICATION SYSTEM | -47.3 |  | -47.3 |  |  | 33664.87 | 18551.31 | 15113.56 | 2022-07-07 09:22 | 2023-03-15 | 2022-10-01 | 2023-03-15
75084 | 75084IK | MX7270217 | MX7270217 - LVG - TRANSFORMER REPLACEMENT - PAR | 416.81 |  | 416.81 |  |  | 51063.98 | 52013.92 | -949.94 | 2022-11-22 10:02 | 2023-04-27 | 2022-11-01 | 2023-03-15
75084 | SG000223F | SG223SW | SG223SW - DEE TRANSMISSION HEALTH & RISK MGT | 430.58 |  | 430.58 |  |  | 675459.42 | 1016639 | -341179.58 | 2017-04-13 10:27 | 2023-02-28 | 2017-05-01 | 2023-03-15
75081 | EB022042 | EB022042X | EB022042X - PURCHASE VACUUM TRUCK | -1006.24 |  | -1006.24 |  |  | 515437.8 | 517104.01 | -1666.21 | 2022-10-25 07:41 | 2023-03-15 | 2022-11-01 | 2023-03-16
75084 | 75084HW | MX5609466 | MX5609466 - TMG- COMM. RELOCATION CAPITAL CIAC | 16276.34 |  | 16276.34 |  |  | 9680.68 | 52404.59 | -42723.91 | 2022-09-19 10:01 | 2023-05-04 | 2022-10-01 | 2023-03-16
75084 | M190226 | M19022602 | M19022602 - F23983 T LINE RLE | 240190.12 |  | 240190.12 |  |  | 7738704.16 | 7486323 | 252381.16 | 2019-10-08 14:01 | 2023-03-10 | 2020-01-01 | 2023-03-20
75084 | 75084IK | MX5744215 | MX5744215 - JT-E-THE HILLS OF CRESCENT SPRINGS | 10963.21 |  | 10963.21 |  |  | 123504.57 | 88777.38 | 34727.19 | 2022-10-26 14:02 | 2023-04-09 | 2022-11-01 | 2023-03-22
75085 | FPIT | CS2200007 | CS2200007 - FND LICENSES ADDITIONAL ENDPOINTS | -7.08 |  | -7.08 |  |  | 11165.86 | 10971 | 194.86 | 2022-11-01 10:25 | 2023-03-30 | 2022-12-01 | 2023-03-22
75081 | EB022016 | EB022016X | EB022016X - INSTALL HCAD TRANSFER HOUSE VACUUM | 9866.43 |  | 9866.43 |  |  | 100158.31 | 41749.66 | 58408.65 | 2022-09-28 13:31 | 2023-02-28 | 2022-11-01 | 2023-03-23
75082 | WDC00020 | WDC00020X | WDC00020X - WDC CONTROL ROOM HVAC REPLACEMENT | 90210.14 |  | 90210.14 |  |  | 372648.33 | 361717.68 | 10930.65 | 2022-04-19 12:06 | 2023-03-31 | 2022-06-01 | 2023-03-28
75084 | KYGLT21 | KYGLT2104 | KYGLT2104 - GLT F6761 RPL CROSS ARM AND DOWN GU | 31185.74 |  | 31185.74 |  |  | 101118.88 | 116248 | -15129.12 | 2022-07-14 10:01 | 2023-02-19 | 2022-07-01 | 2023-03-29
75084 | DKY1931 | MX0240701 | MX0240701 - AUGUSTINE 46 - GENERAL DRIVE OH TO | 449661.84 |  | 449661.84 |  |  | 765176.05 | 285970.72 | 479205.33 | 2021-03-16 14:02 | 2023-03-16 | 2021-03-01 | 2023-03-30
75080 | FPIT | SE2200001 | SE2200001 - END OF LIFE REPLACEMENT FOR FIREWAL | -1.99 |  | -1.99 |  |  | 7852.24 | 28592 | -20739.76 | 2022-01-20 11:07 | 2023-03-30 | 2022-02-01 | 2023-03-30
75081 | EB022045 | CEBIC22 | CEBIC22 - INSTRUMENTATION & CONTROLS (GMA) | 40255.68 |  | 40255.68 |  |  | 311443.77 | 93970.32 | 217473.45 | 2022-10-31 15:40 | 2023-03-01 | 2022-10-01 | 2023-03-31
75081 | EB1912 | CEBVLV22 | CEBVLV22 - 2022 MISC VALVE BLANKET | 91079.59 |  | 91079.59 |  |  | 632213.21 | 451928.08 | 180285.13 | 2022-01-24 12:30 | 2023-03-31 | 2022-03-01 | 2023-03-31
75082 | KYSC0016 | CCRIC22 | CCRIC22 - INSTRUMENTATION & CONTROLS (GMA) | -0.44 |  | -0.44 |  |  | 3441.56 | 7459.2 | -4017.64 | 2022-10-31 13:09 | 2023-03-01 | 2022-10-01 | 2023-03-31
75082 | WDCM0071 | CWDIC22 | CWDIC22 - INSTRUMENTATION & CONTROLS (GMA) | 84307.91 |  | 84307.91 |  |  | 119350.44 | 55518.04 | 63832.4 | 2022-10-31 12:19 | 2023-03-01 | 2022-10-01 | 2023-03-31
75082 | WG048C | CWDVLV22 | CWDVLV22 - WOODSDALE 2022 MISCELLANEOUS VALVES | 5341.75 |  | 5341.75 |  |  | 235061.1 | 192299.83 | 42761.27 | 2022-02-08 14:20 | 2030-12-30 | 2022-06-01 | 2023-03-31
75084 | SG000744F | SG744BLK | SG744BLK - DEK GRIDWAN | 74359.81 |  | 74359.81 |  |  | 420784.16 | 249086.72 | 171697.44 | 2018-05-25 13:54 | 2031-03-31 | 2018-11-01 | 2023-03-31
75084 | SG000744F | SG744MTR | SG744MTR - DEK GRIDWAN | -50232.26 |  | -50232.26 |  |  | 12736.19 | 248821.93 | -236085.74 | 2018-05-25 13:28 | 2021-12-31 | 2018-07-01 | 2023-03-31
75084 | SG001140F | SG1140M21 | SG1140M21 - DEK EOL MODEM REPLACEMENTS | 240.29 |  | 240.29 |  |  | 97154.07 | 71805 | 25349.07 | 2021-12-17 11:34 | 2022-07-31 | 2021-12-01 | 2023-03-31
75080 | DVV2022 | 400098002 | 400098002 - TELECOM NETWORK TRANSFORMATION PROG | 1291.81 |  | 1291.81 |  |  | 324677.2 | 380661 | -55983.8 | 2021-11-17 10:14 | 2023-03-31 | 2022-01-01 | 2023-03-31
75080 | FPIT | 307482003 | 307482003 - CUSTOMER MOBILE APP - PHASE 4 | 382.21 |  | 382.21 |  |  | 47744.17 | 49782 | -2037.83 | 2021-12-30 09:25 | 2023-03-31 | 2022-01-01 | 2023-03-31
75080 | FPIT | 400055007 | 400055007 - USAGE ALERTS | 2223.82 |  | 2223.82 |  |  | 52252.76 | 47004 | 5248.76 | 2021-03-04 16:42 | 2024-03-31 | 2021-03-01 | 2023-03-31
75080 | FPIT | 400055019 | 400055019 - PING IT 2022 ENHANCEMENTS | 3444.46 |  | 3444.46 |  |  | 8733.89 | 8094 | 639.89 | 2022-05-24 14:49 | 2023-03-31 | 2022-09-01 | 2023-03-31
75080 | FPIT | 400055022 | 400055022 - BUSINESS OUTBOUND NOTIFICATION PLAT | -38.5 |  | -38.5 |  |  | 1.4155e-15 | 11897 | -11897 | 2022-05-19 11:25 | 2023-03-31 | 2022-10-01 | 2023-03-31
75084 | FPIT | IT2200069 | IT2200069 - HRM PORTAL - CLOUD UPDATE - PHASE 1 | 13.71 |  | 13.71 |  |  | 5376.75 | 3577 | 1799.75 | 2022-07-01 12:24 | 2023-03-30 | 2022-08-01 | 2023-03-31
75084 | SG000977F | SG977LAB | SG977LAB - THE CYBERSECURITY TESTING OF THE NE | -0.27 |  | -0.27 |  |  | 2133.24 | 26064 | -23930.76 | 2022-03-29 08:06 | 2023-03-31 | 2022-10-01 | 2023-03-31
75084 | TOT00002 | MWEMSKY | MWEMSKY - MIDWEST EMS REPLACEMENT PROJECT | 2910.37 |  | 2910.37 |  |  | 608030.52 | 679701.48 | -71670.96 | 2019-07-22 08:59 | 2023-03-30 | 2019-07-01 | 2023-03-31
75084 | TOT00002 | MWEMSKY2 | MWEMSKY2 - DEK EMS REPLACEMENT PROJECT | 95732.31 |  | 95732.31 |  |  | 972644.93 | 1646591 | -673946.07 | 2020-12-17 11:46 | 2024-12-31 | 2020-12-01 | 2023-03-31
75080 | FPIT | SE2200048 | SE2200048 - ESCA - CDP TUFIN | -0.57 |  | -0.57 |  |  | 8935.82 | 9142 | -206.18 | 2022-09-06 16:10 | 2023-06-29 | 2022-12-01 | 2023-03-31
75084 | SG00359F | SG359SW2 | SG359SW2 - SG SADM SOFTWARE - 359 | 9552 |  | 9552 |  |  | 92832.92 | 227863.84 | -135030.92 | 2019-08-15 08:00 | 2023-11-30 | 2019-09-01 | 2023-04-01
75081 | EB022026 | EB022026X | EB022026X - F1-2 CRUSHER MOTOR REWIND | 4093.91 |  | 4093.91 |  |  | 232455.47 | 45584 | 186871.47 | 2022-09-28 12:06 | 2023-01-15 | 2022-10-01 | 2023-04-03
75084 | DKY2132 | MX8763054 | MX8763054 - LONGBRANCH 43-44 UG - DKY2132 | -98395.77 |  | -98395.77 |  |  | 521338.1 | 181991.33 | 339346.77 | 2018-07-05 10:02 | 2023-05-01 | 2020-06-01 | 2023-04-03
75081 | EB022060 | EB022060X | EB022060X - REPLACE CBU HOIST CABLE | 866.23 |  | 866.23 |  |  | 39398.16 | 91183.77 | -51785.61 | 2022-12-28 15:10 | 2023-03-15 | 2022-12-01 | 2023-04-04
75084 | 75084IK | MX6835995 | MX6835995 - POLE REPLACEMENT - NON-INSPECTION B | 35476.84 |  | 35476.84 |  |  | 98658.21 | 59093.93 | 39564.28 | 2022-10-18 18:01 | 2023-05-04 | 2022-10-01 | 2023-04-09
75084 | KYGLT20 | MX8204271 | MX8204271 - GLT TR_UB F965 T-LINE KYGLT2001 TRA | 13179.38 |  | 13179.38 |  |  | 41384.74 | 25351.75 | 16032.99 | 2020-09-24 10:01 | 2023-09-28 | 2021-03-01 | 2023-04-09
75084 | 75084IK | MX8924352 | MX8924352 - JT-E- NEWPORT CLIFTON - 13TH STREET | -2212.73 |  | -2212.73 |  |  | 25564.96 | 65653.3 | -40088.34 | 2022-07-26 14:01 | 2023-04-05 | 2022-07-01 | 2023-04-10
75081 | EB021788 | EB021788X | EB021788X - RADIAL STACKER BELT REPLACEMENT | -1846.2 |  | -1846.2 |  |  | 35091.51 | 42284.65 | -7193.14 | 2022-12-12 19:17 | 2023-03-31 | 2022-12-01 | 2023-04-11
75084 | DKY2618 | MX9992812 | MX9992812 - PRIMARY SERVICE 2 - AMAZON - DKY261 | -133403.2 |  | -133403.2 |  |  | 133922.8 | 156473.13 | -22550.33 | 2021-02-25 14:02 | 2023-04-20 | 2021-03-01 | 2023-04-11
75080 | FPIT | 400113002 | 400113002 - WORKSTATION REFRESH 2023-2024 | 35160.96 |  | 35160.96 |  |  | 50106.92 | 46939 | 3167.92 | 2022-07-29 09:26 | 2023-03-30 | 2022-08-01 | 2023-04-17
75084 | 75084IK | MX1006763 | MX1006763 - MT ZION - CORRECT CIRCUITS CONFIG- | 94206.1 |  | 94206.1 |  |  | 111672.9 | 28930.12 | 82742.78 | 2021-05-20 10:02 | 2023-05-01 | 2021-06-01 | 2023-04-17
75081 | EB021992 | EB021992X | EB021992X - SAFETY SHOWER REPLACEMENT | 2879.78 |  | 2879.78 |  |  | 7931.94 | 13538.67 | -5606.73 | 2022-07-08 14:01 | 2023-03-31 | 2022-12-01 | 2023-04-20
75082 | FPIT | SE22027WD | SE22027WD - SECURITY SYSTEM-MW | 119286 |  | 119286 |  |  | 119880.26 | 106091 | 13789.26 | 2022-08-09 15:06 | 2023-03-30 | 2022-09-01 | 2023-04-24
75084 | 75084IL | MX5231051 | MX5231051 - 1590 WORLDWIDE BLVD LIGHT INSTALL | 51983.19 |  | 51983.19 |  |  | 89064.75 | 53243.59 | 35821.16 | 2022-05-24 18:01 | 2023-05-29 | 2022-11-01 | 2023-04-24
75084 | 75084IK | MX0291269 | MX0291269 - COMMERCIAL SERVICE FOR SOLAR/WIND/M | 4580.57 |  | 4580.57 |  |  | 15672.68 | 297921.33 | -282248.65 | 2021-05-26 14:02 | 2023-05-01 | 2021-06-01 | 2023-04-25
75084 | M190298 | MX4193270 | MX4193270 - F5967 - REBUILD - MARSHALL @ 3 POIN | 50154.83 |  | 50154.83 |  |  | 72428.85 | 60150.53 | 12278.32 | 2022-02-18 14:01 | 2023-04-27 | 2022-04-01 | 2023-04-25
75081 | FPITF | SE22028EB | SE22028EB - SECURITY SYSTEM-EAST BEND | 139989.51 |  | 139989.51 |  |  | 141140.02 | 106092 | 35048.02 | 2022-08-09 08:25 | 2023-03-30 | 2022-09-01 | 2023-04-27
75084 | FPIT | 349472025 | 349472025 - BENTLEY SUBSCRIPTION LICENSE AGREEM | 190054 |  | 190054 |  |  | 190054 | 192430 | -2376 | 2022-12-21 11:14 | 2023-05-01 | 2023-02-01 | 2023-04-30
75085 | FPIT | CS2200002 | CS2200002 - IVR ENHANCEMENTS 2022 | 411.52 |  | 411.52 |  |  | 6105.13 | 6837 | -731.87 | 2022-05-05 12:49 | 2023-05-01 | 2022-05-01 | 2023-04-30
75084 | FPIT | 349472026 | 349472026 - HITACHI SERVICE SUITE 9-5 YEAR SUBS | 90461.9 |  | 90461.9 |  |  | 90461.9 | 91366 | -904.1 | 2023-01-26 13:23 | 2023-05-02 | 2023-02-01 | 2023-05-01
75081 | EB022066 | EB022066X | EB022066X - REPLACE B CONVEYOR GEARBOX | 137377.04 |  | 137377.04 |  |  | 137377.04 | 139021.22 | -1644.18 | 2023-01-17 13:56 | 2023-04-30 | 2023-12-01 | 2023-05-02
75084 | 75084IK | MX6366847 | MX6366847 - SHT 48 NOVA TO VIP RECLOSER RPL, K | 45835.09 |  | 45835.09 |  |  | 56936.13 | 47372.39 | 9563.74 | 2022-11-18 14:01 | 2023-05-18 | 2022-11-01 | 2023-05-03
75084 | 75084IK | MX9048687 | MX9048687 - MCCULLUM PK-COMMERCIAL PRIMARY/SECO | 19483.82 |  | 19483.82 |  |  | 211382.21 | 138789.09 | 72593.12 | 2021-01-14 12:13 | 2022-11-30 | 2021-01-01 | 2023-05-16
75084 | 75084IK | MX7948840 | MX7948840 - KEG - 201 W 4TH - WILDER 48 - COMME | 231150.16 |  | 231150.16 |  |  | 231150.16 | 148660.39 | 82489.77 | 2022-12-06 10:02 | 2023-06-01 | 2023-02-01 | 2023-05-18
75080 | FPIT | SE2200006 | SE2200006 - ESCA - IT-OT CYBER DEPLOYMENT PROJ | 92539.49 |  | 92539.49 |  |  | 252404.33 | 306443 | -54038.67 | 2022-03-08 09:30 | 2023-06-09 | 2022-06-01 | 2023-05-23
75084 | 75084IK | MX5069648 | MX5069648 - JT-E-THE RESERVE AT MEADOWOOD II PH | 24933.75 |  | 24933.75 |  |  | 93002.99 | 88433 | 4569.99 | 2022-10-31 14:02 | 2023-05-30 | 2022-11-01 | 2023-05-24
75084 | M190297 | M19029702 | M19029702 - F5967 LINE RLE | 341.91 |  | 341.91 |  |  | 41413.31 | 41413.31 | 0 | 2020-11-11 14:01 | 2024-02-02 | 2021-03-01 | 2023-05-28
75084 | M190298 | M19029802 | M19029802 - F5967 LINE RLE RBLD LAYDOWN AREA | 18069.38 |  | 18069.38 |  |  | 72242.25 | 105355 | -33112.75 | 2021-06-07 18:02 | 2023-06-30 | 2022-04-01 | 2023-05-28
75084 | DKY2754 | MX4778133 | MX4778133 - THOMAS MORE 41 LN EXT DKY2754 - N/C | 17185.75 |  | 17185.75 |  |  | 52892.96 | 47092.97 | 5799.99 | 2022-04-13 10:01 | 2023-05-29 | 2022-06-01 | 2023-05-29
75084 | DKY2754 | MX4778303 | MX4778303 - THOMAS MORE 41 LN EXT DKY2754 - N/O | 17748.81 |  | 17748.81 |  |  | 53615.27 | 48376.69 | 5238.58 | 2022-04-13 10:01 | 2023-05-29 | 2022-08-01 | 2023-05-29
75080 | SG001010F | SG1010Z1L | SG1010Z1L - DEK LMR - OHIO/KENTUCKY - ERLANGER | 110434.67 |  | 110434.67 |  |  | 2154793.87 | 5597208.53 | -3442414.66 | 2019-11-01 12:38 | 2024-03-31 | 2019-11-01 | 2023-05-31
75080 | SG001010F | SG1010Z1O | SG1010Z1O - DEK LMR - OHIO/KENTUCKY - ERLANGER | 105199.24 |  | 105199.24 |  |  | 1050666.4 | 1399302.13 | -348635.73 | 2019-11-01 12:28 | 2024-03-31 | 2019-11-01 | 2023-05-31
75085 | FPIT | CS2200005 | CS2200005 - UPLAND RIGHT ANSWER LICENSE PURCHAS | -6006.19 |  | -6006.19 |  |  | 11393.03 | 11365 | 28.03 | 2022-08-03 15:15 | 2023-01-29 | 2022-12-01 | 2023-05-31
75084 | 75084IK | MX1977350 | MX1977350 - OAKBROOK 42 DKY2769 - PART 2 RECOND | 95405.62 |  | 95405.62 |  |  | 125925.79 | 81480.75 | 44445.04 | 2021-08-13 10:12 | 2023-06-04 | 2021-10-01 | 2023-06-04
75084 | KSTORM23 | MX8239349 | MX8239349 - STORM REPAIR ON F6761 @ POLE 36BN-4 | 35945.27 |  | 35945.27 |  |  | 35945.27 | 14313.51 | 21631.76 | 2023-02-10 18:01 | 2024-03-31 | 2023-02-01 | 2023-06-08
75081 | EB022162 | EB022162X | EB022162X - 2-1 ID FAN VFD CELL | 114105.7 |  | 114105.7 |  |  | 114105.7 | 72532.24 | 41573.46 | 2023-02-28 13:20 | 2023-06-30 | 2023-05-01 | 2023-06-10
75084 | 75084IK | MX1998755 | MX1998755 - UG CABLE REPLACE SMALL - REACTIVE ; | 100095.05 |  | 100095.05 |  |  | 102930.54 | 59786.15 | 43144.39 | 2022-10-05 14:01 | 2023-07-06 | 2022-10-01 | 2023-06-13
75084 | 75084IK | MX6772276 | MX6772276 - DKA; 7455 EMPIRE DR; DIXIE 42; COMM | 50412.48 |  | 50412.48 |  |  | 50412.48 | 59758.74 | -9346.26 | 2022-12-15 10:03 | 2023-06-18 | 2023-09-01 | 2023-06-13
75084 | K23DEMERG | MX8548742 | MX8548742 - CAPITAL ATLAS TB1 REPLACE HIGH SIDE | 2392.12 |  | 2392.12 |  |  | 2392.12 | 3742.8 | -1350.68 | 2023-03-06 18:01 | 2024-03-30 | 2023-04-01 | 2023-06-18
75081 | EB021829 | EB021829X | EB021829X - REPLACE 2A2 6.9KV-480V TRANSFORMER | 70023.95 |  | 70023.95 |  |  | 154518.57 | 168393.78 | -13875.21 | 2022-05-12 11:12 | 2023-07-23 | 2022-05-01 | 2023-06-20
75082 | SG001092F | SG1092SLR | SG1092SLR - DEK AERO SOLAR - GENERATION | 6343890.39 |  | 6343890.39 |  |  | 6343890.39 | 6343890.4 | -0.01 | 2023-06-29 15:23 | 2022-10-15 | 2023-10-01 | 2023-06-22
75084 | 75084IK | MX2370776 | MX2370776 - JT-E-RIFFLE RIDGE PHASE 1B | 17507.85 |  | 17507.85 |  |  | 73120.77 | 62681.31 | 10439.46 | 2022-09-29 14:01 | 2023-05-22 | 2022-11-01 | 2023-06-25
75084 | M180378 | MX8340687 | MX8340687 - M18037801.RICHWOOD - TB4 POWER CABL | 21815.62 |  | 21815.62 |  |  | 21815.62 | 18719.48 | 3096.14 | 2023-02-28 18:01 | 2023-07-20 | 2023-12-01 | 2023-06-25
75081 | EB022078 | EB022078X | EB022078X - 2-2 CT GEARBOX REPLACEMENT | 150792.55 |  | 150792.55 |  |  | 150792.55 | 233691.42 | -82898.87 | 2023-02-07 10:55 | 2023-07-31 | 2023-02-01 | 2023-06-28
75084 | M220331 | M22033101 | M22033101 - EMERGENT - RETIRE ERLANGER GAS SUB | 7818.84 |  | 7818.84 |  |  | 7818.84 | 7478.37 | 340.47 | 2022-11-26 13:20 | 2023-05-22 | 2023-12-01 | 2023-06-29
75080 | FPIT | 400055018 | 400055018 - PING IT AUTOMATION 2022 | 12803.08 |  | 12803.08 |  |  | 36274.31 | 33084 | 3190.31 | 2022-02-10 18:02 | 2023-06-30 | 2022-03-01 | 2023-06-30
75081 | EB022004 | EB022004X | EB022004X - STORM WATER - ZINC MITIGATION | 269374.04 |  | 269374.04 |  |  | 2031829.61 | 2265228.55 | -233398.94 | 2022-08-19 07:52 | 2023-06-30 | 2022-09-01 | 2023-06-30
75084 | FPIT | LTHTASDBS | LTHTASDBS - LIGHTHOUSE: TITUS - ASPEN DB FEATUR | -53053.88 |  | -53053.88 |  |  | 8529.23 | 9159 | -629.77 | 2021-08-10 12:42 | 2023-06-30 | 2022-02-01 | 2023-06-30
75080 | FPIT | 400055017 | 400055017 - DIGITAL ASSISTANT PLATFORM 2022 ENH | 10272.28 |  | 10272.28 |  |  | 40202.45 | 30300 | 9902.45 | 2021-12-20 10:18 | 2023-06-30 | 2022-01-01 | 2023-07-04
75084 | M190298 | M19029801 | M19029801 - F5967 RBLD HL 864 TO HL 801 | 1064991.71 |  | 1064991.71 |  |  | 4495817.14 | 4535186.12 | -39368.98 | 2021-06-07 18:02 | 2023-07-15 | 2021-06-01 | 2023-07-09
75084 | 75084IK | MX8027908 | MX8027908 - RICHWOOD 42 STATION EXIT REMOVAL-IN | 15237.2 |  | 15237.2 |  |  | 15237.2 | 3208.65 | 12028.55 | 2023-01-25 14:01 | 2023-07-12 | 2023-12-01 | 2023-07-10
75084 | 75084IK | MX6247948 | MX6247948 - DETERIORATED CONDUCTOR - CRITTENDEN | 6856.82 |  | 6856.82 |  |  | 6856.82 | 10558.61 | -3701.79 | 2022-08-26 14:01 | 2023-08-29 | 2023-12-01 | 2023-07-11
75084 | M180378 | M18037803 | M18037803 - F6761 LOOP | 71360.39 |  | 71360.39 |  |  | 86677.44 | 91093.62 | -4416.18 | 2019-09-12 14:01 | 2023-06-11 | 2020-06-01 | 2023-07-11
75084 | 75084HW | MX7882980 | MX7882980 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 30727.77 |  | 30727.77 |  |  | 30727.77 | 37848.92 | -7121.15 | 2023-01-17 14:01 | 2023-10-24 | 2023-12-01 | 2023-07-12
75084 | K23NPWHB | MX6303375 | MX6303375 - WILDER TB 3 REPLACE ARRESTERS 23PRO | 9398.14 |  | 9398.14 |  |  | 9398.14 | 6772.12 | 2626.02 | 2023-01-31 18:01 | 2024-03-30 | 2023-02-01 | 2023-07-12
75084 | M180378 | M18037801 | M18037801 - RICHWOOD BK 4- INSTALL | 2137998.23 |  | 2137998.23 |  |  | 5625294.82 | 5498141.33 | 127153.49 | 2019-09-12 14:01 | 2023-07-10 | 2019-10-01 | 2023-07-13
75084 | EAMHPBU | 349472018 | 349472018 - EAM 2022 MAXIMO DURABLE TEAM | 5234.96 |  | 5234.96 |  |  | 21304.77 | 13250 | 8054.77 | 2022-01-04 15:40 | 2023-05-30 | 2022-01-01 | 2023-07-17
75084 | DEMERKY | MX3062206 | MX3062206 - CAPITAL CRITTENDEN TB 2 REPLACE 3 H | 8490.15 |  | 8490.15 |  |  | 8973.01 | 10342.05 | -1369.04 | 2021-11-22 10:01 | 2023-09-30 | 2021-11-01 | 2023-07-18
75084 | M190226 | M19022601 | M19022601 - 138 KV F23983 WOODSPOINT TO AERO | 627708.38 |  | 627708.38 |  |  | 10187103.73 | 10187073.43 | 30.3 | 2019-10-08 14:01 | 2023-06-30 | 2019-11-01 | 2023-07-25
75080 | DVV2022 | 400098001 | 400098001 - 2022 CISCO VIPTELA SDWAN SOLUTION | 141806.1 |  | 141806.1 |  |  | 254262.83 | 30621 | 223641.83 | 2021-11-17 12:35 | 2023-09-30 | 2022-02-01 | 2023-07-25
75081 | EB022243 | EB022243X | EB022243X - CRUSHER HOUSE WIRE ROPE REPLACEMENT | 13433.6 |  | 13433.6 |  |  | 13433.6 | 9862.59 | 3571.01 | 2023-04-12 09:36 | 2023-07-31 | 2023-05-01 | 2023-07-25
75081 | EB022247 | EB022247X | EB022247X - 2-1 SFC HPU PUMP | 12642.59 |  | 12642.59 |  |  | 12642.59 | 13800.35 | -1157.76 | 2023-04-13 15:27 | 2023-07-31 | 2023-05-01 | 2023-07-26
75081 | EB020821 | EB020821X | EB020821X - REPLACE F CONVEYOR BELT | 183206.85 |  | 183206.85 |  |  | 185636.96 | 232209.26 | -46572.3 | 2022-07-26 09:19 | 2023-07-12 | 2022-08-01 | 2023-07-28
75084 | 75084HW | MX2506780 | MX2506780 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 1462.71 |  | 1462.71 |  |  | 1462.71 | 1212.32 | 250.39 | 2021-10-07 10:02 | 2023-07-29 | 2023-05-01 | 2023-07-30
75084 | 75084IK | MX7830454 | MX7830454 - CBT2212DUK1289 - REQUARDT LN RECONS | 81050.55 |  | 81050.55 |  |  | 81050.55 | 46578.93 | 34471.62 | 2023-02-04 13:28 | 2023-08-24 | 2023-12-01 | 2023-07-30
75080 | FPIT | 400055004 | 400055004 - INSPECTION PORTAL 2021 | 4636.97 |  | 4636.97 |  |  | 23270.02 | 21453 | 1817.02 | 2020-12-16 11:28 | 2023-07-03 | 2022-01-01 | 2023-07-31
75081 | EB022102 | EB022102X | EB022102X - EBS SALT BUILDING | 33946.92 |  | 33946.92 |  |  | 33946.92 | 21756 | 12190.92 | 2023-02-28 09:28 | 2023-05-31 | 2023-05-01 | 2023-07-31
75084 | M220205 | M22020501 | M22020501 - 5966 RT9 & STEEL PLANT RD RELO | 242305.94 |  | 242305.94 |  |  | 247587.45 | 244345.07 | 3242.38 | 2022-06-27 10:05 | 2023-07-08 | 2022-06-01 | 2023-08-06
75081 | EB022089 | EB022089X | EB022089X - REPLACE C MODULE INLET EXP JOIN | 49007.07 |  | 49007.07 |  |  | 49007.07 | 53787.44 | -4780.37 | 2023-02-03 09:21 | 2023-07-31 | 2023-12-01 | 2023-08-07
75081 | EB022232 | EB022232X | EB022232X - REPLACE 2-1 IDBF COUPLING | 278591.23 |  | 278591.23 |  |  | 278591.23 | 263365.47 | 15225.76 | 2023-04-14 12:17 | 2023-07-31 | 2023-05-01 | 2023-08-07
75084 | 75084IK | MX5630972 | MX5630972 - MAKE READY - BALLYSHANNON SUB ~ HAT | 544033.88 |  | 544033.88 |  |  | 549765.02 | 304318.93 | 245446.09 | 2022-09-15 10:01 | 2023-08-29 | 2022-09-01 | 2023-08-08
75084 | FPIT | 349472024 | 349472024 - NEW PRIMAVERA OAM SERVERS | 1 |  | 1 |  |  | 75.86 | 345 | -269.14 | 2022-09-29 16:22 | 2023-08-08 | 2022-10-01 | 2023-08-08
75084 | M180378 | M18037802 | M18037802 - RICHWOOD BK 4- MOD XMISSION STRUCTU | 286501.23 |  | 286501.23 |  |  | 728378.64 | 827126.64 | -98748 | 2019-09-16 18:01 | 2023-07-11 | 2019-10-01 | 2023-08-09
75084 | M220195 | M22019501 | M22019501 - EMERGENT COLD SPRING SUBSTATION - R | 12593.62 |  | 12593.62 |  |  | 29850.95 | 29801.43 | 49.52 | 2022-07-26 10:02 | 2023-08-12 | 2022-08-01 | 2023-08-09
75084 | FPIT | IT2200053 | IT2200053 - TGIS ENHANCEMENTS 2022 | 1290.75 |  | 1290.75 |  |  | 6401.51 | 9240 | -2838.49 | 2022-03-30 07:51 | 2023-08-17 | 2022-06-01 | 2023-08-10
75081 | EB022240 | EB022240X | EB022240X - GUARD SHACK READER REPLACEMENT | 15383.97 |  | 15383.97 |  |  | 15383.97 | 16681.37 | -1297.4 | 2023-04-12 10:29 | 2023-09-30 | 2023-05-01 | 2023-08-11
75081 | EB022259 | EB022259X | EB022259X - REPL WSP MIXER DISCHARGE BELT | 36411.78 |  | 36411.78 |  |  | 36411.78 | 28085.08 | 8326.7 | 2023-05-12 10:16 | 2023-08-31 | 2023-05-01 | 2023-08-12
75082 | WDCM0070 | WDCM0070X | WDCM0070X - REPLACE LEVEL TRANSMITTER SYSTEMS | 75254.94 |  | 75254.94 |  |  | 103063.16 | 70025.28 | 33037.88 | 2022-09-15 12:18 | 2023-07-31 | 2022-09-01 | 2023-08-12
75084 | 75084IK | MX5095589 | MX5095589 - JT-E-WESTBROOK ESTATES PHASE 4 | 58971.53 |  | 58971.53 |  |  | 99549.22 | 68663.84 | 30885.38 | 2022-11-10 10:02 | 2023-05-31 | 2022-12-01 | 2023-08-14
75084 | 75084IK | MX6121915 | MX6121915 - APR; 1710 LAKELAND PARK DR, LIMABUR | 260801.45 |  | 260801.45 |  |  | 72769.64 | 189238.3 | -116468.66 | 2022-11-16 18:02 | 2023-07-20 | 2022-12-01 | 2023-08-17
75080 | MRTP2023 | 400123002 | 400123002 - FIBER CONDUIT REPLACEMENT AT DIXIE | 18623.12 |  | 18623.12 |  |  | 18623.12 | 21158 | -2534.88 | 2023-05-24 07:27 | 2023-08-16 | 2023-05-01 | 2023-08-18
75082 | WD050029 | WD050029X | WD050029X - FIRE PROTECTION SENSOR ADDITION | 75087.2 |  | 75087.2 |  |  | 75087.2 | 50144.75 | 24942.45 | 2023-02-07 11:19 | 2023-10-01 | 2023-12-01 | 2023-08-21
75081 | EB022133 | EB022133X | EB022133X - 7R COAL NOZZLE REPLACEMENT | 24345.32 |  | 24345.32 |  |  | 24345.32 | 33469.94 | -9124.62 | 2023-03-30 15:07 | 2023-06-30 | 2023-06-01 | 2023-08-22
75084 | KSTORM23 | MX8534364 | MX8534364 - MIDWEST - ODD YR STORM FAILURE - LI | 12150.41 |  | 12150.41 |  |  | 12150.41 | 13445.19 | -1294.78 | 2023-03-06 18:01 | 2024-01-31 | 2023-12-01 | 2023-08-24
75084 | DEMERKY | MX4924117 | MX4924117 - CAPITAL ATLAS REPLACE BATTERIES | 315.58 |  | 315.58 |  |  | 315.58 | 2943.41 | -2627.83 | 2022-06-02 10:01 | 2023-11-29 | 2023-05-01 | 2023-08-28
75081 | EB022037 | EB022037X | EB022037X - TRIPPER ROOM CAMERA SYSTEM | 36873.17 |  | 36873.17 |  |  | 117878.12 | 77700 | 40178.12 | 2022-10-25 08:44 | 2023-07-31 | 2022-11-01 | 2023-08-30
75084 | 75084IK | MX5906912 | MX5906912 - KEG - 2045 DECLARATION - WHITE TOWE | 86310.84 |  | 86310.84 |  |  | 86557.98 | 60402.1 | 26155.88 | 2022-09-21 14:01 | 2023-08-31 | 2022-10-01 | 2023-08-31
75084 | SG001176F | SG001176 | SG001176 - DEE CITRIX API VPS GEMS GATEWAY | 300.11 |  | 300.11 |  |  | 7060.04 | 10117 | -3056.96 | 2022-06-22 11:47 | 2024-04-30 | 2022-06-01 | 2023-08-31
75085 | FPIT | CS2200001 | CS2200001 - REVENUE ASSURANCE ART TOOL | 3484.87 |  | 3484.87 |  |  | 23377.41 | 16175 | 7202.41 | 2022-04-07 10:19 | 2023-08-31 | 2022-04-01 | 2023-08-31
75081 | EB022250 | EB022250X | EB022250X - REWIND SPARE PA FAN PUMP MOTOR | 126170.03 |  | 126170.03 |  |  | 126170.03 | 97500 | 28670.03 | 2023-04-14 12:44 | 2023-08-31 | 2023-05-01 | 2023-09-01
75084 | SG001001F | SG1001SW | SG1001SW - DEE IOT PLATFORM ASSESSMENT POC | 4416.42 |  | 4416.42 |  |  | 16480.12 | 27663.6 | -11183.48 | 2020-09-11 18:40 | 2022-12-31 | 2020-09-01 | 2023-09-01
75084 | DEMERKY | MX4267484 | MX4267484 - CAPITAL VERONA REPLACE COMM & CONTR | 77576.69 |  | 77576.69 |  |  | 109732.41 | 39198.94 | 70533.47 | 2022-03-09 10:01 | 2024-03-30 | 2022-04-01 | 2023-09-04
75084 | 75084IL | MX4930891 | MX4930891 - MAIN ST FLORENCE KY STREET LIGHT IN | 146807.32 |  | 146807.32 |  |  | 231621.82 | 160076.63 | 71545.19 | 2022-06-29 18:01 | 2023-09-28 | 2022-07-01 | 2023-09-05
75084 | M230055 | M23005501 | M23005501 - F6763/6761 FIF REPLACE (3) POLES | 310720.25 |  | 310720.25 |  |  | 310720.25 | 294119.76 | 16600.49 | 2023-03-16 14:08 | 2023-08-27 | 2023-12-01 | 2023-09-05
75084 | M230055 | MX8671473 | MX8671473 - GLT FIF F6763/F6761 M23005501, RPL | 22592.1 |  | 22592.1 |  |  | 22592.1 | 29907.98 | -7315.88 | 2023-04-21 14:01 | 2023-09-01 | 2023-12-01 | 2023-09-05
75084 | 75084IK | MX7505607 | MX7505607 - DKA; 3932 DIXIE HWY;ERLANGER; DONAL | 19024.03 |  | 19024.03 |  |  | 19024.03 | 17746.61 | 1277.42 | 2023-04-24 10:01 | 2023-09-10 | 2023-12-01 | 2023-09-06
75084 | DKY2618 | MX5358828 | MX5358828 - PERMANENT PRIMARY SERVICE - DKY2618 | 10931.91 |  | 10931.91 |  |  | 1682143.84 | 326336.3 | 1355807.54 | 2020-01-16 10:01 | 2023-09-28 | 2020-10-01 | 2023-09-11
75081 | EB021722 | EB021722X | EB021722X - NORTH THICKENER TANK REPLACEMENT | 421815.51 |  | 421815.51 |  |  | 2693570.5 | 2672404.4 | 21166.1 | 2021-10-08 15:33 | 2023-08-30 | 2021-10-01 | 2023-09-14
75084 | 75084HW | MX4699775 | MX4699775 - MAKE-READY,2203MCI0446DEK, MCI PROJ | 28412.16 |  | 28412.16 |  |  | 28412.16 | 42291.95 | -13879.79 | 2022-12-13 14:01 | 2023-09-10 | 2022-12-01 | 2023-09-14
75084 | K23BCRHB | MX6367704 | MX6367704 - DRY RIDGE REPLACE BATTERY SRP 1011 | 8439.61 |  | 8439.61 |  |  | 8439.61 | 7190.89 | 1248.72 | 2023-01-24 10:01 | 2024-03-30 | 2023-12-01 | 2023-09-17
75084 | M230070 | M23007001 | M23007001 - F6761 SERVICE RD POLE REPLACEMENT | 12354.18 |  | 12354.18 |  |  | 12354.18 | 14585.48 | -2231.3 | 2023-04-26 10:01 | 2024-12-01 | 2023-05-01 | 2023-09-20
75084 | M220345 | M22034501 | M22034501 - EMERGENT - WILDER TB 4 REPLACE ETM | 37810.95 |  | 37810.95 |  |  | 37810.95 | 37688.99 | 121.96 | 2022-12-07 10:02 | 2024-01-29 | 2023-11-01 | 2023-09-20
75081 | EB022092 | EB022092X | EB022092X - REPLACE PALL OIL FILTERING UNIT | 49410.62 |  | 49410.62 |  |  | 49410.62 | 51333.15 | -1922.53 | 2023-02-07 16:59 | 2023-09-30 | 2023-02-01 | 2023-09-21
75084 | SG000438F | MX6446377 | MX6446377 - [CUSTOMER] LONGBRANCH 42 35BN-390 I | 52837.45 |  | 52837.45 |  |  | 52837.45 | 48200.38 | 4637.07 | 2023-02-08 10:01 | 2023-09-28 | 2023-12-01 | 2023-09-21
75080 | FPIT | TC2300028 | TC2300028 - 3 YR NEWS GOTHIC FONT LICENSE | 4518.71 |  | 4518.71 |  |  | 4518.71 | 4554 | -35.29 | 2023-06-06 15:26 | 2023-09-24 | 2023-08-01 | 2023-09-26
75084 | 75084IK | MX4447390 | MX4447390 - JT-E-TUSCANY SECTION 026 | 134393.74 |  | 134393.74 |  |  | 134393.74 | 79150.97 | 55242.77 | 2023-01-10 14:01 | 2023-10-30 | 2023-12-01 | 2023-09-26
75084 | DKY2748 | MX1561891 | MX1561891 - AERO TO CVG SOUTH LN EXT - NEW GEAR | 422121.64 |  | 422121.64 |  |  | 3418972.79 | 3423723.84 | -4751.05 | 2021-07-08 08:01 | 2023-10-29 | 2021-08-01 | 2023-09-26
75084 | 75084IK | MX4446732 | MX4446732 - JT-E-TUSCANY SECTION 022 | 76314.79 |  | 76314.79 |  |  | 76314.79 | 52078.49 | 24236.3 | 2022-10-19 14:01 | 2023-09-19 | 2023-12-01 | 2023-09-26
75084 | 75084IK | MX3357339 | MX3357339 - JT-E- MEMORIAL POINTE PHASE 1 PART | 343673.64 |  | 343673.64 |  |  | 343673.64 | 204527.82 | 139145.82 | 2023-01-05 14:01 | 2023-11-05 | 2023-12-01 | 2023-09-27
75084 | SG000794F | SG794ETOS | SG794ETOS - DEE LMR PROJECT 1 CORES | 9320.46 |  | 9320.46 |  |  | 43114.09 | 11229.12 | 31884.97 | 2020-12-17 12:45 | 2024-03-31 | 2021-01-01 | 2023-09-28
75080 | FPIT | 400055005 | 400055005 - BUILDER PORTAL 2021 | 6150.75 |  | 6150.75 |  |  | 30551.98 | 35647 | -5095.02 | 2020-12-10 17:46 | 2023-09-30 | 2021-01-01 | 2023-09-30
75081 | EB021995 | EB021995X | EB021995X - G CONVEYOR FLUID DRIVE | 161380.93 |  | 161380.93 |  |  | 161380.93 | 158621.84 | 2759.09 | 2022-08-11 13:39 | 2023-09-30 | 2023-12-01 | 2023-09-30
75081 | FPITF | IT2200089 | IT2200089 - ESRA - AVAMAR SINGLE NODE PURCHASE | 21732.33 |  | 21732.33 |  |  | 72373.67 | 42538 | 29835.67 | 2022-06-29 09:44 | 2023-09-30 | 2022-07-01 | 2023-09-30
75082 | FPITF | IT2200105 | IT2200105 - ESRA - AVAMAR SINGLE NODE PURCHASE | 11574.93 |  | 11574.93 |  |  | 43457.44 | 43575 | -117.56 | 2022-06-27 16:02 | 2023-09-30 | 2022-07-01 | 2023-09-30
75084 | 75084 | TPO00170 | TPO00170 - OUA SUSTAINABILITY UPLIFT | 39982.11 |  | 39982.11 |  |  | 79681.19 | 72918 | 6763.19 | 2022-08-23 14:07 | 2023-08-31 | 2022-08-01 | 2023-09-30
75084 | 75084IK | MX6751888 | MX6751888 - UG CABLE REPLACE SMALL - REACTIVE | 131934.98 |  | 131934.98 |  |  | 131934.98 | 54291.96 | 77643.02 | 2023-04-13 14:01 | 2023-11-29 | 2023-12-01 | 2023-10-03
75084 | 75084HW | MX2871461 | MX2871461 - EWD - 1301 4TH - DAYTON 42 - MARINA | 113418.24 |  | 113418.24 |  |  | 37622.89 | 58196.98 | -20574.09 | 2022-10-24 10:02 | 2023-09-28 | 2022-12-01 | 2023-10-04
75084 | K23NPWHB | MX6303440 | MX6303440 - HEBRON TB1 ARRESTERS SRP CAPITAL NO | 12392.66 |  | 12392.66 |  |  | 12392.66 | 6848.54 | 5544.12 | 2023-02-06 18:01 | 2024-03-30 | 2023-12-01 | 2023-10-09
75084 | 75084HW | MX7426786 | MX7426786 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 330094.54 |  | 330094.54 |  |  | 330226.56 | 210726.69 | 119499.87 | 2022-12-13 14:01 | 2023-11-23 | 2022-12-01 | 2023-10-10
75084 | 75084IK | MX9491996 | MX9491996 - CAD,322 ELM ST, AUGUSTINE 41 OVERHE | 8941.65 |  | 8941.65 |  |  | 8941.65 | 8493.11 | 448.54 | 2023-07-05 18:01 | 2023-11-29 | 2023-12-01 | 2023-10-16
75084 | 75084IK | MX5894909 | MX5894909 - JT-E-TUSCANY SECTIONS 39 & 40 | 38874.82 |  | 38874.82 |  |  | 38874.82 | 19550.76 | 19324.06 | 2023-02-06 18:01 | 2023-10-29 | 2023-12-01 | 2023-10-17
75084 | K23DEMERG | MX8052768 | MX8052768 - CAPITAL AUGUSTINE REPLACE 3 LA'S NE | 8736.38 |  | 8736.38 |  |  | 8736.38 | 2738.74 | 5997.64 | 2023-01-26 18:01 | 2024-03-30 | 2023-05-01 | 2023-10-17
75081 | EB022029 | EB022029X | EB022029X - HG CEMS STACK PROBE STINGER | 959.33 |  | 959.33 |  |  | 14812.17 | 12886.8 | 1925.37 | 2022-10-20 09:43 | 2023-12-31 | 2022-11-01 | 2023-10-19
75082 | WD010053 | WD010053X | WD010053X - SMARTGEN-WDC U1 T/G VIB MONITOR EOL | 5782.1 |  | 5782.1 |  |  | 6001.66 | 6824.07 | -822.41 | 2021-05-18 08:46 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD020021 | WD020021X | WD020021X - SMARTGEN-WDC U2 T/G VIB MONITOR EOL | 5927.24 |  | 5927.24 |  |  | 6153.09 | 6824.07 | -670.98 | 2021-05-18 09:21 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD030013 | WD030013X | WD030013X - SMARTGEN-WDC U3 T/G VIB MONITOR EOL | 9245.37 |  | 9245.37 |  |  | 9395.2 | 6824.07 | 2571.13 | 2021-05-18 09:33 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD040020 | WD040020X | WD040020X - SMARTGEN-WDC U4 T/G VIB MONITOR EOL | 6249.92 |  | 6249.92 |  |  | 6389.34 | 6824.07 | -434.73 | 2021-05-18 09:43 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD050019 | WD050019X | WD050019X - SMARTGEN-WDC U5 T/G VIB MONITOR EOL | 5928.56 |  | 5928.56 |  |  | 6078.39 | 6824.07 | -745.68 | 2021-05-18 09:51 | 2023-12-31 | 2021-06-01 | 2023-10-19
75082 | WD060018 | WD060018X | WD060018X - SMARTGEN-WDC U6 T/G VIB MONITOR EOL | 5907.72 |  | 5907.72 |  |  | 6111.88 | 6824.07 | -712.19 | 2021-05-18 09:57 | 2023-12-31 | 2021-06-01 | 2023-10-19
75084 | 75084IK | MX3450067 | MX3450067 - JT-E-SAWGRASS PHASE D PART 2 | 150740.73 |  | 150740.73 |  |  | 150740.73 | 90090.6 | 60650.13 | 2023-01-30 18:01 | 2023-10-15 | 2023-12-01 | 2023-10-22
75081 | FPITF | IT2200149 | IT2200149 - RRE HEAT RATE SOLUTION | 8429.89 |  | 8429.89 |  |  | 9431.02 | 10191 | -759.98 | 2022-11-18 09:12 | 2023-10-31 | 2022-12-01 | 2023-10-24
75082 | FPITF | IT2200149 | IT2200149 - RRE HEAT RATE SOLUTION | 6467.65 |  | 6467.65 |  |  | 7217.04 | 7627 | -409.96 | 2022-11-18 09:25 | 2023-10-31 | 2022-12-01 | 2023-10-24
75082 | WD030008 | WD030008X | WD030008X - OPTIM U3 GEN FIELD REWIND | 878072.55 |  | 878072.55 |  |  | 2789754.41 | 3043385.08 | -253630.67 | 2022-01-25 10:13 | 2023-09-30 | 2022-01-01 | 2023-10-25
75081 | EB021320 | EB021320X | EB021320X - REPLACE CRUSHER HOUSE ELEVATOR | 665542.49 |  | 665542.49 |  |  | 801590.01 | 812337.07 | -10747.06 | 2022-06-23 08:15 | 2023-10-31 | 2022-06-01 | 2023-10-27
75084 | 75084IL | MX7840678 | MX7840678 - CITY OF CRESTVIEW HILLS PH 2 | 10379.11 |  | 10379.11 |  |  | 10379.11 | 61881.61 | -51502.5 | 2023-02-28 18:01 | 2023-11-02 | 2023-12-01 | 2023-10-30
75080 | FPIT | 400055016 | 400055016 - TITAN (VOICE OF THE CUSTOMER ENGAGE | 4012.26 |  | 4012.26 |  |  | 19066.32 | 22207 | -3140.68 | 2021-12-20 13:20 | 2023-10-31 | 2022-01-01 | 2023-10-31
75084 | SG000551F | SG551NOK | SG551NOK - NOKIA NETWORK SERVICES PLATFORM | 583.27 |  | 583.27 |  |  | 17747.45 | 17998 | -250.55 | 2020-12-07 17:22 | 2023-12-30 | 2020-12-01 | 2023-10-31
75084 | SG001133F | SG1133HW | SG1133HW - DEE MOBILE CONNECT PRE SCALE | 92996.41 |  | 92996.41 |  |  | 343206.51 | 141239 | 201967.51 | 2022-03-08 01:44 | 2023-03-31 | 2022-03-01 | 2023-11-01
75084 | SG001133F | SG1133SW | SG1133SW - DEE MOBILE CONNECT PRE SCALE | 59.07 |  | 59.07 |  |  | 14467.75 | 141727 | -127259.25 | 2022-03-08 02:08 | 2023-03-31 | 2022-07-01 | 2023-11-01
75084 | M180383 | M18038304 | M18038304 - WHITE TOWER 5967 POLE EASEMENT | 54957.99 |  | 54957.99 |  |  | 59823.11 | 84792 | -24968.89 | 2022-03-04 14:01 | 2023-10-03 | 2022-06-01 | 2023-11-02
75084 | 75084IK | MX4376559 | MX4376559 - KEG - 3 MARY INGLES - DAYTON 42 - M | 130876.92 |  | 130876.92 |  |  | 130876.92 | 126131.26 | 4745.66 | 2023-06-21 14:01 | 2023-10-19 | 2023-12-01 | 2023-11-07
75080 | RESBLDKY | KMW3CEB80 | KMW3CEB80 - ERLANGER OPS CENTER RENOVATION | 5806141.46 |  | 5806141.46 |  |  | 8023882.48 | 9223149 | -1199266.52 | 2021-02-03 10:15 | 2023-11-08 | 2021-02-01 | 2023-11-10
75084 | K23DEMERG | MX0149912 | MX0149912 - EMERGT E1 LONGBRANCH TB 1 REPLACE 2 | 2926.87 |  | 2926.87 |  |  | 2926.87 | 8595.09 | -5668.22 | 2023-07-24 10:01 | 2024-03-30 | 2023-08-01 | 2023-11-15
75084 | K23DEMERG | MX0405846 | MX0405846 - EMERGT E1 KENTON CIR 42 REPLACE 3 L | 6738.39 |  | 6738.39 |  |  | 6738.39 | 7173.58 | -435.19 | 2023-08-11 18:01 | 2024-05-29 | 2023-08-01 | 2023-11-15
75084 | DEMERKY | MX3192862 | MX3192862 - CAPITAL WHITE TOWER CIR 42 REPLACE | 3918.76 |  | 3918.76 |  |  | 4027.81 | 4853.76 | -825.95 | 2021-12-13 14:02 | 2024-03-30 | 2021-12-01 | 2023-11-19
75084 | DEMERKY | MX5324313 | MX5324313 - CAPITAL HEBRON CIR 41 & VR1 REPLACE | 9809.15 |  | 9809.15 |  |  | 9809.15 | 6795.17 | 3013.98 | 2022-06-02 14:01 | 2024-03-31 | 2023-12-01 | 2023-11-19
75084 | K23DEMERG | MX0281111 | MX0281111 - EMERGT E1 KENTON REPLACE CONTROL CA | 29768.87 |  | 29768.87 |  |  | 29768.87 | 9575.43 | 20193.44 | 2023-08-02 18:01 | 2024-03-30 | 2023-09-01 | 2023-11-19
75084 | 75084IK | MX5294680 | MX5294680 - JT-E-BALLYSHANNON SECTION 520 | 298180.57 |  | 298180.57 |  |  | 298180.57 | 222675.29 | 75505.28 | 2023-04-11 10:01 | 2024-01-29 | 2023-12-01 | 2023-11-27
75084 | DEMERKY | MX5888950 | MX5888950 - CAPITAL CRESCENT TB1 REPLACE ETM | 21332.98 |  | 21332.98 |  |  | 21332.98 | 8803.78 | 12529.2 | 2022-07-26 10:02 | 2024-03-30 | 2023-02-01 | 2023-11-28
75081 | EB022285 | EB022285X | EB022285X - GUARD HOUSE HVAC UNIT | 3198.24 |  | 3198.24 |  |  | 3198.24 | 4092.2 | -893.96 | 2023-08-29 14:01 | 2023-10-31 | 2023-12-01 | 2023-11-29
75084 | 75084IL | MX5045747 | MX5045747 - 514 6TH AVE CITY OF DAYTON UG STREE | 6907.18 |  | 6907.18 |  |  | 6907.18 | 65305.49 | -58398.31 | 2023-02-07 14:01 | 2023-09-26 | 2023-11-01 | 2023-11-29
75084 | SG000732F | SG732TR03 | SG732TR03 - COMMUNICATION TOWER , SHELTER AND S | 425172.85 |  | 425172.85 |  |  | 2300832.36 | 1519055 | 781777.36 | 2020-10-30 10:38 | 2023-03-31 | 2020-12-01 | 2023-11-30
75084 | 75084IK | MX6118387 | MX6118387 - JT-E-HARMONY PHASE E | 53124.79 |  | 53124.79 |  |  | 53124.79 | 65001.44 | -11876.65 | 2023-04-20 14:01 | 2024-01-02 | 2023-12-01 | 2023-12-05
75084 | K23DEMERG | MX8189410 | MX8189410 - CAPITAL CRITTENDEN REPLACE STATION | 6663.45 |  | 6663.45 |  |  | 6663.45 | 4796.97 | 1866.48 | 2023-02-06 18:01 | 2024-03-30 | 2023-09-01 | 2023-12-06
75084 | 75084HW | MX2030474 | MX2030474 - 145 RICHWOOD; ZKH; COMMERCIAL RELOC | 109403.74 |  | 109403.74 |  |  | 72670.74 | 81325.26 | -8654.52 | 2021-12-09 14:02 | 2023-12-07 | 2022-07-01 | 2023-12-10
75084 | 75084HW | MX7847716 | MX7847716 - TRANSMISSION "5966" UNDERBUILD RELO | 102835.68 |  | 102835.68 |  |  | 102835.68 | 37904.99 | 64930.69 | 2023-01-25 14:01 | 2023-12-21 | 2023-12-01 | 2023-12-10
75084 | K23DEMERG | MX0537117 | MX0537117 - EMERGT E1 DRY RIDGE REPLACE 300 FT | 8505.93 |  | 8505.93 |  |  | 8505.93 | 12759.47 | -4253.54 | 2023-08-23 14:01 | 2024-05-29 | 2023-10-01 | 2023-12-10
75084 | M220356 | M22035601 | M22035601 - F15268 69KV 2022 POLE INSPECTION | 49904.74 |  | 49904.74 |  |  | 49904.74 | 50463.37 | -558.63 | 2023-02-24 10:01 | 2023-11-14 | 2023-12-01 | 2023-12-10
75084 | 75084IK | MX6682367 | MX6682367 - JT-E-TRIPLE CROWN COUNTRY CLUB SECT | 141096.77 |  | 141096.77 |  |  | 141096.77 | 80522.01 | 60574.76 | 2023-02-23 14:01 | 2023-12-05 | 2023-12-01 | 2023-12-11
75084 | 75084HW | MX6146811 | MX6146811 - MAKE READY, 2208MCI0104DEK, MCI PRO | -36460.2 |  | -36460.2 |  |  | -36460.2 | 43958.34 | -80418.54 | 2023-03-01 10:01 | 2023-12-28 | 2023-12-01 | 2023-12-12
75084 | K23NPWHB | MX6303476 | MX6303476 - CLARYVILLE TB1 ARRESTERS SRP CAPITA | 10585.92 |  | 10585.92 |  |  | 10585.92 | 5577.31 | 5008.61 | 2023-01-31 18:01 | 2024-03-30 | 2023-02-01 | 2023-12-13
75084 | 75084HW | MX1331746 | MX1331746 - F5983 SILVER GROVE TRANSMISSION REL | 204982.36 |  | 204982.36 |  |  | 204982.36 | 107002.63 | 97979.73 | 2022-09-21 10:01 | 2023-12-28 | 2023-12-01 | 2023-12-17
75084 | K23DEMERG | MX0209744 | MX0209744 - EMERGT E1 GRANT TB 1 REPLACE FAN | 1451.15 |  | 1451.15 |  |  | 1451.15 | 10669.7 | -9218.55 | 2023-07-27 10:01 | 2024-03-30 | 2023-10-01 | 2023-12-17
75084 | 22050041A | MX5254698 | MX5254698 - 0670041A: ALEXANDRIA SOUTH 43 43CA- | 55265.31 |  | 55265.31 |  |  | 56185.8 | 46123.82 | 10061.98 | 2022-06-01 10:05 | 2025-07-29 | 2022-09-01 | 2023-12-18
75081 | FPITF | IT2300041 | IT2300041 - TAGSPRO UPGRADE TO SUPPORT PHYSICAL | 2486.2 |  | 2486.2 |  |  | 2486.2 | 2449 | 37.2 | 2023-06-27 17:04 | 2023-12-17 | 2023-10-01 | 2023-12-18
75082 | FPITF | IT2300041 | IT2300041 - TAGSPRO UPGRADE TO SUPPORT PHYSICAL | 1860.73 |  | 1860.73 |  |  | 1860.73 | 1833 | 27.73 | 2023-06-27 17:10 | 2023-12-17 | 2023-10-01 | 2023-12-18
75084 | 22050041A | MX5821228 | MX5821228 - SUB OPT-TRANSFORMER UG 3-PHASE END | 22002.2 |  | 22002.2 |  |  | 23247.52 | 18503.79 | 4743.73 | 2022-08-05 14:01 | 2025-07-29 | 2022-09-01 | 2023-12-18
75084 | 75084HW | MX9234318 | MX9234318 - TMG- 135 W. 38TH ST. LATONIA - RELO | 32403.33 |  | 32403.33 |  |  | 32403.33 | 77634 | -45230.67 | 2023-06-22 14:01 | 2023-12-14 | 2023-12-01 | 2023-12-18
75084 | 22050041A | V2205REMK | V2205REMK - SUB OPT - REM - ALEXANDRIA SOUTH - | 7475.02 |  | 7475.02 |  |  | 7475.02 | 0 | 7475.02 | 2022-10-20 13:42 | 2025-03-31 | 2023-12-01 | 2023-12-19
75084 | 75084HW | MX6146668 | MX6146668 - MAKE READY, 2208MCI0070DEK, MCI PRO | -18877.05 |  | -18877.05 |  |  | -18877.05 | 47961.6 | -66838.65 | 2023-01-26 14:01 | 2023-12-28 | 2023-12-01 | 2023-12-24
75084 | FPIT | LTHCDPJBS | LTHCDPJBS - LIGHTHOUSE CUSTOMER DELIVERY PRE-JO | 6804.76 |  | 6804.76 |  |  | 12334.67 | 11777 | 557.67 | 2022-09-29 10:38 | 2024-02-01 | 2022-10-01 | 2023-12-25
75084 | M200056 | M20005602 | M20005602 - GLT 5967 RPL POLES ABS 436 WHITE T | 488257.8 |  | 488257.8 |  |  | 489123.44 | 491444.32 | -2320.88 | 2020-12-21 18:01 | 2023-12-04 | 2020-12-01 | 2023-12-28
75084 | M200056 | M20005603 | M20005603 - GLT 5967 RPL POLES WHITE TOWER SUB | 1776854.27 |  | 1776854.27 |  |  | 1782406.77 | 1696206.56 | 86200.21 | 2020-12-21 18:01 | 2023-12-04 | 2020-12-01 | 2023-12-28
75084 | 75084IK | MX5915712 | MX5915712 - APR, 4805 AERO, OAKBROOK41, PERM, C | 52538.3 |  | 52538.3 |  |  | 52538.3 | 178048.11 | -125509.81 | 2023-01-03 18:02 | 2024-01-11 | 2023-12-01 | 2023-12-28
75084 | M200056 | M20005601 | M20005601 - GLT 5967 RPL POLES WILDER SUB ABS | 301131.49 |  | 301131.49 |  |  | 393380.63 | 412343.91 | -18963.28 | 2020-12-21 18:01 | 2023-12-04 | 2020-12-01 | 2023-12-28
75084 | M200056 | M20005604 | M20005604 - GLT 5967 RPL POLES, INSP YR 2016RLE | 630.81 |  | 630.81 |  |  | 1936.86 | 1936.86 | 0 | 2020-12-21 18:01 | 2024-01-29 | 2021-02-01 | 2023-12-28
75082 | WDC00095 | WDC00095X | WDC00095X - LOTO LOCKS | 70744.56 |  | 70744.56 |  |  | 70744.56 | 47000.97 | 23743.59 | 2023-03-31 10:10 | 2023-11-30 | 2023-12-01 | 2023-12-31
75084 | FPIT | IT2300027 | IT2300027 - MOS STORM REPORTING | 3683.54 |  | 3683.54 |  |  | 3683.54 | 5887 | -2203.46 | 2023-05-24 08:27 | 2024-06-29 | 2023-12-01 | 2023-12-31
75080 | FPIT | 400055015 | 400055015 - ATLANTIS (CUSTOMER ANALYTICS ENGINE | 17506.56 |  | 17506.56 |  |  | 43273.34 | 45663 | -2389.66 | 2021-12-29 10:29 | 2023-12-30 | 2022-01-01 | 2024-01-01
75082 | WD010061 | WD01006X | WD01006X - 125 VDC BATTERY CHARGER REPLACEMENT | 98348.32 |  | 98348.32 |  |  | 98534.61 | 63280.01 | 35254.6 | 2022-11-29 09:32 | 2023-10-25 | 2022-12-01 | 2024-01-01
75084 | M230150 | MX9775617 | MX9775617 - GLT F5985 (M2301501) 4-POLES | 25902.01 |  | 25902.01 |  |  | 25902.01 | 19346.24 | 6555.77 | 2023-06-20 18:01 | 2024-02-17 | 2023-12-01 | 2024-01-01
75084 | 75084IK | MX5377535 | MX5377535 - JT-E-ARCADIA PHASES 011 & 013 | 170632.57 |  | 170632.57 |  |  | 170632.57 | 91432.85 | 79199.72 | 2023-03-01 18:01 | 2024-01-24 | 2023-12-01 | 2024-01-02
75084 | SG000954F | MX9791884 | MX9791884 - TRIP SAVER II REPLACEMENT ONLY H932 | 12772.49 |  | 12772.49 |  |  | 12772.49 | 12673.29 | 99.2 | 2023-10-03 10:01 | 2024-01-11 | 2023-12-01 | 2024-01-07
75084 | M210258 | M21025801 | M21025801 - EMR CIR 15268 RPL I-275 HWY CROSSI | 173294.93 |  | 173294.93 |  |  | 188253.31 | 239226.98 | -50973.67 | 2021-05-13 14:02 | 2023-12-24 | 2021-06-01 | 2024-01-11
75081 | EB021371 | EB021371X | EB021371X - SMARTGEN-EBS U2 T/G VIB MONITOR EOL | 32924.15 |  | 32924.15 |  |  | 33353.25 | 34661.94 | -1308.69 | 2021-05-20 13:35 | 2023-12-31 | 2021-06-01 | 2024-01-13
75082 | WD030014 | WD030014X | WD030014X - SSMARTGEN WDC U3 MONITOR GFM | 86691.89 |  | 86691.89 |  |  | 152212.12 | 128769.43 | 23442.69 | 2022-06-07 17:51 | 2023-09-30 | 2022-06-01 | 2024-01-13
75082 | WD050028 | WD050028X | WD050028X - 125 VDC BATTERY CHARGER REPLACEMENT | 76132.81 |  | 76132.81 |  |  | 76132.81 | 68721.39 | 7411.42 | 2023-06-15 15:04 | 2023-12-25 | 2023-12-01 | 2024-01-20
75082 | WD060026 | WD060026X | WD060026X - 125 VDC BATERY CHARGER REPLACEMENT | 92620.62 |  | 92620.62 |  |  | 92620.62 | 67982.29 | 24638.33 | 2023-06-15 15:35 | 2023-12-25 | 2023-12-01 | 2024-01-20
75084 | 22100041A | MX1701490 | MX1701490 - 2100041A: OAKBROOK 41 BNK-8871 INST | 3044.6 |  | 3044.6 |  |  | 57012.58 | 44384.07 | 12628.51 | 2021-10-22 13:47 | 2023-10-26 | 2022-03-01 | 2024-01-21
75084 | 22100041A | MX2278295 | MX2278295 - SUB OPT -UG CABLE REPLACE SMALL - P | 21057.49 |  | 21057.49 |  |  | 308034.07 | 201579.18 | 106454.89 | 2022-01-04 14:02 | 2023-10-26 | 2022-01-01 | 2024-01-21
75084 | 22100041A | MX1157551 | MX1157551 - SUB OPT -TRANSFORMER UG THREE PHASE | 1982.33 |  | 1982.33 |  |  | 36522.15 | 20043.46 | 16478.69 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1393386 | MX1393386 - 2100041A: OAKBROOK 41 BNK-8851 INST | 5870.6 |  | 5870.6 |  |  | 53865.96 | 42925.51 | 10940.45 | 2021-10-22 09:12 | 2023-10-26 | 2022-03-01 | 2024-01-21
75084 | 22100041A | MX1601015 | MX1601015 - TRANSFORMER UG 3-PHASE END OF LIFE | 1552.89 |  | 1552.89 |  |  | 28912.16 | 19732.28 | 9179.88 | 2022-02-21 10:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601017 | MX1601017 - TRANSFORMER UG 3-PHASE END OF LIFE | 1760.16 |  | 1760.16 |  |  | 35159.19 | 17486.11 | 17673.08 | 2022-01-26 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601018 | MX1601018 - TRANSFORMER UG 3-PHASE END OF LIFE | 1470.33 |  | 1470.33 |  |  | 27885.29 | 14965.23 | 12920.06 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601021 | MX1601021 - TRANSFORMER UG 3-PHASE END OF LIFE | 1137.38 |  | 1137.38 |  |  | 21479.17 | 15729.91 | 5749.26 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601022 | MX1601022 - TRANSFORMER UG 3-PHASE END OF LIFE | 1156.32 |  | 1156.32 |  |  | 21723.81 | 18253.6 | 3470.21 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601023 | MX1601023 - TRANSFORMER UG 3-PHASE END OF LIFE | 1081.3 |  | 1081.3 |  |  | 20547.79 | 16993.33 | 3554.46 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1601025 | MX1601025 - TRANSFORMER UG 3-PHASE END OF LIFE | 1238.08 |  | 1238.08 |  |  | 23511.09 | 17461.9 | 6049.19 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100041A | MX1701489 | MX1701489 - 2100041A: OAKBROOK 41 26BN-1212 INS | 1793.81 |  | 1793.81 |  |  | 54140.83 | 42723.88 | 11416.95 | 2021-10-22 13:47 | 2023-10-26 | 2022-03-01 | 2024-01-21
75084 | 22100041A | MX7372042 | MX7372042 - 2100041A: OAKBROOK 41 20BN-327 INST | 10315.42 |  | 10315.42 |  |  | 47701.85 | 40250.51 | 7451.34 | 2022-03-25 14:04 | 2023-10-26 | 2022-05-01 | 2024-01-21
75084 | 22100041A | MX8564274 | MX8564274 - SUB OPT -TRANSFORMER UG THREE PHASE | 1312.68 |  | 1312.68 |  |  | 20624.61 | 22707.29 | -2082.68 | 2022-02-18 18:01 | 2023-10-26 | 2022-05-01 | 2024-01-21
75084 | 22100041A | MX9919687 | MX9919687 - SUB OPT -A CAP UPGRADE, 25BN-397, O | 2178.95 |  | 2178.95 |  |  | 16170.88 | 15425.53 | 745.35 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100041A | MX9919688 | MX9919688 - SUB OPT -A CAP UPGRADE, BNK-2661, O | 1134.92 |  | 1134.92 |  |  | 16257.1 | 18204.24 | -1947.14 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100042A | MX1601011 | MX1601011 - TRANSFORMER UG 3-PHASE END OF LIFE | 1508 |  | 1508 |  |  | 28235.18 | 18487.57 | 9747.61 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100042A | MX1601014 | MX1601014 - TRANSFORMER UG 3-PHASE END OF LIFE | 1660.49 |  | 1660.49 |  |  | 24962.63 | 17550.06 | 7412.57 | 2022-01-18 18:01 | 2023-10-26 | 2022-02-01 | 2024-01-21
75084 | 22100042A | MX1701482 | MX1701482 - 2100042A: OAKBROOK 42 20BN-22 INSTA | 3646.93 |  | 3646.93 |  |  | 67814.32 | 53063.26 | 14751.06 | 2021-10-21 10:02 | 2023-10-26 | 2021-12-01 | 2024-01-21
75084 | 22100042A | MX9919691 | MX9919691 - SUB OPT -CAP UPGRADE, 20BN-454, OAK | 868.56 |  | 868.56 |  |  | 14976.8 | 12133.8 | 2843 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100042A | MX9919693 | MX9919693 - SUB OPT -A CAP UPGRADE, 25BN-272, O | 1708.52 |  | 1708.52 |  |  | 25388.42 | 26268.86 | -880.44 | 2021-11-15 18:02 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | DEMERKY | MX4906508 | MX4906508 - CAPITAL WHITE TOWER CIR 43 REPLACE | 1528.46 |  | 1528.46 |  |  | 1528.46 | 2693.82 | -1165.36 | 2022-04-25 14:01 | 2024-02-28 | 2023-10-01 | 2024-01-21
75084 | 22100042A | MX5820935 | MX5820935 - SUB OPT -TRANSFORMER UG THREE PHASE | 26864.91 |  | 26864.91 |  |  | 28039.71 | 18173.93 | 9865.78 | 2022-09-06 14:01 | 2023-10-26 | 2022-09-01 | 2024-01-21
75084 | 22100042A | MX8892977 | MX8892977 - SUB OPT -UG CABLE REPLACE SMALL - P | 595515.26 |  | 595515.26 |  |  | 595515.26 | 136903.28 | 458611.98 | 2023-04-05 10:01 | 2024-02-08 | 2023-12-01 | 2024-01-21
75084 | 75084IK | MX8686355 | MX8686355 - F15268 (M210258) REPL 2 POLES FOR | 54353.42 |  | 54353.42 |  |  | 54353.42 | 31366.38 | 22987.04 | 2023-03-20 18:01 | 2024-01-14 | 2023-12-01 | 2024-01-22
75084 | 22100041A | V2210HAZK | V2210HAZK - SUB OPT - HAZ - OAKBROOK STA - 2210 | 244.41 |  | 244.41 |  |  | 5623.19 | 0 | 5623.19 | 2021-12-20 14:05 | 2025-03-31 | 2022-03-01 | 2024-01-23
75084 | 75084IK | MX4250117 | MX4250117 - ZKH; OLD LEXINGTON COMM DEV; COMMER | 68992.8 |  | 68992.8 |  |  | 68992.8 | 224050.78 | -155057.98 | 2023-03-03 10:01 | 2024-02-22 | 2023-12-01 | 2024-01-23
75084 | 75084IL | MX9649357 | MX9649357 - 9520 UNION PROMENADE UDF LOT 1 AREA | 13366.84 |  | 13366.84 |  |  | 13366.84 | 77760.35 | -64393.51 | 2023-06-14 14:01 | 2023-12-28 | 2023-12-01 | 2024-01-23
75084 | 75084IK | MXA766032 | MXA766032 - JT-E-TUSCANY SECTIONS 27 & 28 | 88052.75 |  | 88052.75 |  |  | 88052.75 | 54658.04 | 33394.71 | 2023-06-08 10:01 | 2024-01-22 | 2023-12-01 | 2024-01-24
75084 | 75084IK | MX8765107 | MX8765107 - JT-E-TUSCANY SECTIONS 39 & 44 | 156666.01 |  | 156666.01 |  |  | 156666.01 | 88621.71 | 68044.3 | 2023-06-22 18:01 | 2024-02-13 | 2023-12-01 | 2024-01-24
75081 | EB022295 | EB022295X | EB022295X - REPLACE F CONVEYOR SCRAPER | 14798.95 |  | 14798.95 |  |  | 14798.95 | 14017.58 | 781.37 | 2023-09-28 09:02 | 2023-12-30 | 2023-12-01 | 2024-01-25
75085 | CUSTCONN | 400109 | 400109 - CUST ENHANCEMENT AND OPTIMIZATION | 440421.54 |  | 440421.54 |  |  | 623190.08 | 685559 | -62368.92 | 2022-06-20 14:22 | 2024-01-19 | 2022-07-01 | 2024-01-26
75081 | FPITF | IT2200106 | IT2200106 - ACT REPORTING PLATFORM MODERNIZATIO | 7770.5 |  | 7770.5 |  |  | 12994.41 | 11706 | 1288.41 | 2022-08-30 10:34 | 2024-01-27 | 2022-09-01 | 2024-01-27
75082 | FPITF | IT2200106 | IT2200106 - ACT REPORTING PLATFORM MODERNIZATIO | 6369.57 |  | 6369.57 |  |  | 10474.19 | 8761 | 1713.19 | 2022-08-30 10:40 | 2024-01-27 | 2022-09-01 | 2024-01-27
75084 | M180095 | M18009501 | M18009501 - KENTON XTR 1 RPL | 293590.75 |  | 293590.75 |  |  | 585432.23 | 753175.59 | -167743.36 | 2019-03-07 10:01 | 2024-01-05 | 2019-03-01 | 2024-01-28
75084 | 75084HW | MX9147798 | MX9147798 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 49184.66 |  | 49184.66 |  |  | 49184.66 | 32252.81 | 16931.85 | 2023-08-29 14:01 | 2024-02-15 | 2023-12-01 | 2024-01-30
75081 | EB022433 | EB022433X | EB022433X - E SPLITTER GATE REPLACEMENT | 111850.52 |  | 111850.52 |  |  | 111850.52 | 114659.2 | -2808.68 | 2023-11-26 14:08 | 2024-02-06 | 2023-12-01 | 2024-01-30
75084 | K23NPWHB | MX6303272 | MX6303272 - BUFFINGTON TB 3 RPL ARRESTERS | 8388.94 |  | 8388.94 |  |  | 8388.94 | 10772.13 | -2383.19 | 2023-02-06 18:01 | 2024-03-30 | 2023-11-01 | 2024-01-30
75081 | EB021903 | EB021903X | EB021903X - ESCAPE RESPIRATORS | 83736.87 |  | 83736.87 |  |  | 105477.03 | 76042.4 | 29434.63 | 2022-03-01 15:37 | 2023-12-30 | 2022-07-01 | 2024-01-31
75084 | 75084IK | MX9774313 | MX9774313 - ASSIGNED TO EN-RETURN 7-21-23_SHT 1 | 45296.48 |  | 45296.48 |  |  | 45296.48 | 40019.89 | 5276.59 | 2023-07-26 10:01 | 2024-02-22 | 2023-12-01 | 2024-01-31
75084 | DVV2021 | 400051013 | 400051013 - CIP-012 OHIO/KY | 3370.46 |  | 3370.46 |  |  | 37059.18 | 91312 | -54252.82 | 2021-06-18 17:14 | 2024-03-31 | 2021-06-01 | 2024-01-31
75085 | FPIT | CS2300001 | CS2300001 - CCO REMOTE WORKSTATION EQUIPMENT | 10476.63 |  | 10476.63 |  |  | 10476.63 | 11822 | -1345.37 | 2023-02-03 15:44 | 2024-01-31 | 2023-12-01 | 2024-01-31
75081 | EB022068 | EB022068X | EB022068X - REPL GEN H2&AIR SIDE SEAL OIL CLR | 488453.55 |  | 488453.55 |  |  | 488453.55 | 474613.18 | 13840.37 | 2023-02-07 15:38 | 2024-02-15 | 2023-12-01 | 2024-02-01
75081 | EB022435 | EB022435X | EB022435X - G CONVEYOR GEARBOX & FLUID DRIVE | 41252.66 |  | 41252.66 |  |  | 41252.66 | 41822.17 | -569.51 | 2023-12-15 15:21 | 2024-02-28 | 2023-12-01 | 2024-02-03
75081 | EB022067 | EB022067X | EB022067X - REPL FGD C MODULE UPPER HDR NOZZLES | 37309.79 |  | 37309.79 |  |  | 37309.79 | 40127.02 | -2817.23 | 2023-01-10 09:29 | 2023-12-31 | 2023-12-01 | 2024-02-04
75084 | 75084IK | MX4092859 | MX4092859 - JT-E-ALEXANDRIA FLATS PHASE 3; BLDG | 68280.91 |  | 68280.91 |  |  | 134475.63 | 79797.38 | 54678.25 | 2022-06-28 14:01 | 2024-01-29 | 2022-11-01 | 2024-02-04
75081 | EB022043 | EB022043X | EB022043X - 2023 OPTIM ST VALVE CVGV U2 | 4846012.66 |  | 4846012.66 |  |  | 4847962.63 | 5171070.43 | -323107.8 | 2022-12-09 16:12 | 2023-12-31 | 2022-12-01 | 2024-02-05
75081 | EB022047 | EB022047X | EB022047X - REPL FGD BC MODULE DUCTWORK | 3804288.84 |  | 3804288.84 |  |  | 3804288.84 | 3621065.97 | 183222.87 | 2023-06-15 14:47 | 2024-02-05 | 2023-12-01 | 2024-02-05
75081 | EBS01302 | EBS01302X | EBS01302X - WSP RADIAL STACKER | 3707448.13 |  | 3707448.13 |  |  | 3863211.54 | 3891176.02 | -27964.48 | 2022-12-21 09:49 | 2024-02-05 | 2022-12-01 | 2024-02-05
75084 | DKY2754 | MX4778407 | MX4778407 - THOMAS MORE 41 LN EXT DKY2754 - ATO | 172952.91 |  | 172952.91 |  |  | 178685.91 | 128549.24 | 50136.67 | 2022-04-13 14:01 | 2024-02-15 | 2022-06-01 | 2024-02-05
75081 | EB020394 | EB020394X | EB020394X - HCAD REPLACE RECLAIM CHUTES | 2266511.81 |  | 2266511.81 |  |  | 2370987.65 | 3332634.76 | -961647.11 | 2022-12-21 10:11 | 2024-03-30 | 2022-12-01 | 2024-02-05
75081 | EB021349 | EB021349X | EB021349X - REPL CIRC PIP SAC ANODES | 265131.87 |  | 265131.87 |  |  | 265131.87 | 288066.18 | -22934.31 | 2023-06-23 14:26 | 2024-02-05 | 2023-12-01 | 2024-02-06
75081 | EB022424 | EB022424X | EB022424X - 2-4 6F COAL NOZZLE REPLACEMENT | 23537.7 |  | 23537.7 |  |  | 23537.7 | 31283.27 | -7745.57 | 2023-11-06 17:51 | 2024-02-05 | 2023-12-01 | 2024-02-06
75084 | 75084IK | MX9251908 | MX9251908 - JT-E-WALTON TOWNE CENTER LOT 30 PHA | 95128.69 |  | 95128.69 |  |  | 95128.69 | 59569.22 | 35559.47 | 2023-08-08 10:01 | 2024-02-25 | 2023-12-01 | 2024-02-06
75084 | DKY2754 | MX6322062 | MX6322062 - THOMAS MORE 41 LN EXT DKY2754 | 709019.87 |  | 709019.87 |  |  | 1703755.58 | 472926.98 | 1230828.6 | 2021-01-07 18:02 | 2024-02-15 | 2021-03-01 | 2024-02-06
75081 | EB022434 | EB022434X | EB022434X - PRECIP 2-1 2-2 INLET GUTTER SYSTEM | 322830.85 |  | 322830.85 |  |  | 322830.85 | 295371.25 | 27459.6 | 2023-11-26 14:17 | 2024-02-28 | 2023-12-01 | 2024-02-06
75081 | EB022204 | EB022204X | EB022204X - 2-2 PULV ROLL WHEEL | 860752.96 |  | 860752.96 |  |  | 860752.96 | 962152.87 | -101399.91 | 2023-03-30 16:00 | 2023-11-30 | 2023-12-01 | 2024-02-07
75080 | RESBLDKY | KMW221422 | KMW221422 - GENERATOR MONITORING EQUIP | 5513.7 |  | 5513.7 |  |  | 45382.88 | 79538 | -34155.12 | 2022-07-05 11:00 | 2023-03-31 | 2022-09-01 | 2024-02-07
75081 | EB022423 | EB022423X | EB022423X - 2-1 PULVERIZER FEEDER BELT | 6208.6 |  | 6208.6 |  |  | 6208.6 | 3785.34 | 2423.26 | 2023-11-06 17:13 | 2024-02-05 | 2023-12-01 | 2024-02-07
75081 | EB022046 | EB022046X | EB022046X - 2-1 SBAC OVERHAUL | 613685.43 |  | 613685.43 |  |  | 613685.43 | 613685.43 | 0 | 2023-03-30 14:05 | 2024-02-28 | 2023-12-01 | 2024-02-09
75081 | EB022058 | EB022058X | EB022058X - 2-4 PULV ROLL WHEEL REPL | 848321.58 |  | 848321.58 |  |  | 848321.58 | 958839.56 | -110517.98 | 2023-03-30 14:39 | 2024-02-05 | 2023-12-01 | 2024-02-09
75081 | EB022313 | EB022313X | EB022313X - 2A-2 ABSORBER PUMP REPLACEMENT | 63260.14 |  | 63260.14 |  |  | 63260.14 | 62033.07 | 1227.07 | 2023-11-26 12:43 | 2023-11-30 | 2023-12-01 | 2024-02-09
75081 | EB022177 | EB022177X | EB022177X - REWIND SPARE CONDENSATE PUMP MOTOR | 200673.23 |  | 200673.23 |  |  | 200673.23 | 66492.8 | 134180.43 | 2023-03-30 15:24 | 2023-07-30 | 2023-05-01 | 2024-02-10
75081 | EB022427 | EB022427X | EB022427X - REPLACE WEST MILL BAY ROLLUP DOOR | 12869.5 |  | 12869.5 |  |  | 12869.5 | 12977.09 | -107.59 | 2023-11-26 13:35 | 2024-02-28 | 2023-12-01 | 2024-02-10
75081 | EB022437 | EB022437X | EB022437X - CT OIL PIPING REPLACEMENT | 110032.65 |  | 110032.65 |  |  | 110032.65 | 181797.08 | -71764.43 | 2023-11-26 15:01 | 2024-02-28 | 2023-12-01 | 2024-02-10
75084 | K23FNDFLD | MX0442133 | MX0442133 - REPLACE CROSSARMS @ 6761 POLE 46BN- | 4460.44 |  | 4460.44 |  |  | 4460.44 | 7545.16 | -3084.72 | 2023-08-17 18:01 | 2023-11-20 | 2023-12-01 | 2024-02-11
75084 | K23FNDFLD | MX8959199 | MX8959199 - FIF F2166 CROSSARM REPLACEMENT AT K | 5839.4 |  | 5839.4 |  |  | 5839.4 | 8519.94 | -2680.54 | 2023-04-20 10:01 | 2024-02-17 | 2023-11-01 | 2024-02-11
75084 | 75084IK | MX0805717 | MX0805717 - DETERIORATED CONDUCTOR - KENTON 42 | 570549.02 |  | 570549.02 |  |  | 570549.02 | 375023.69 | 195525.33 | 2023-01-26 10:01 | 2024-01-24 | 2023-12-01 | 2024-02-11
75081 | EB020861 | EB020861X | EB020861X - INSTALL WSP UPS | 169096.35 |  | 169096.35 |  |  | 169096.35 | 379697.28 | -210600.93 | 2023-02-28 09:05 | 2024-02-09 | 2023-12-01 | 2024-02-12
75081 | EBS01342 | EBS01342X | EBS01342X - REPLACE BFPT CONTROLS | 2967623.42 |  | 2967623.42 |  |  | 3801795.57 | 4290008.28 | -488212.71 | 2022-10-12 15:04 | 2024-03-31 | 2022-12-01 | 2024-02-12
75081 | EBS01378 | EBS01378X | EBS01378X - REPL TURB TRIP SYSTEM CONTROL | 1493216.96 |  | 1493216.96 |  |  | 1713347.21 | 1944299.99 | -230952.78 | 2022-09-02 12:45 | 2024-03-31 | 2022-09-01 | 2024-02-12
75084 | M230059 | MX0926836 | MX0926836 - M23005901 - AUGUSTINE TB5 TO BUS 2 | 24693.04 |  | 24693.04 |  |  | 24693.04 | 12086.78 | 12606.26 | 2023-09-21 18:01 | 2024-05-09 | 2023-12-01 | 2024-02-13
75084 | 75084IK | MX9643472 | MX9643472 - TMG- 135 W. 38TH ST. LATONIA - COMM | -35532.79 |  | -35532.79 |  |  | -35532.79 | 26039.33 | -61572.12 | 2023-07-19 18:01 | 2024-02-22 | 2023-12-01 | 2024-02-13
75084 | M230059 | M23005901 | M23005901 - AUGUSTINE 138KV - TB 5 TO BUS 2 CAB | 94229.52 |  | 94229.52 |  |  | 94229.52 | 91635.47 | 2594.05 | 2023-07-27 18:01 | 2024-01-16 | 2023-12-01 | 2024-02-14
75080 | FPIT | 359140001 | 359140001 - ISOP DATA MANAGEMENT | 18926.82 |  | 18926.82 |  |  | 148868.2 | 289733 | -140864.8 | 2018-12-19 15:02 | 2024-02-15 | 2019-01-01 | 2024-02-17
75084 | M190297 | M19029701 | M19029701 - 5967 RBLD CLARYVILLE TO HL 864 | 6251282.75 |  | 6251282.75 |  |  | 9880885.62 | 9990283.16 | -109397.54 | 2020-11-11 14:01 | 2024-01-16 | 2020-11-01 | 2024-02-18
75084 | 75084IK | MX6316067 | MX6316067 - JT-E-PROVISION LIVING RICHWOOD | 122175.98 |  | 122175.98 |  |  | 122175.98 | 91703.9 | 30472.08 | 2023-07-11 14:01 | 2024-02-28 | 2023-12-01 | 2024-02-18
75084 | K23DEMERG | MX0495084 | MX0495084 - EMERGT E1 OAKBROOK TB1 REPLACE FAN | 1397.65 |  | 1397.65 |  |  | 1397.65 | 7440.41 | -6042.76 | 2023-08-21 10:01 | 2024-05-29 | 2023-12-01 | 2024-02-19
75084 | 75084IK | MX6583961 | MX6583961 - OPEN LOOP - UG CABLE REPLACE SMALL | 69054.34 |  | 69054.34 |  |  | 69054.34 | 63085.45 | 5968.89 | 2023-10-09 14:01 | 2024-03-30 | 2023-12-01 | 2024-02-25
75084 | K23DEMERG | MX0698823 | MX0698823 - EMERGT E1 LIMABURG ABS 610 REPLACE | 18039.02 |  | 18039.02 |  |  | 18039.02 | 13342.56 | 4696.46 | 2023-09-04 20:01 | 2024-06-29 | 2023-12-01 | 2024-02-26
75084 | K23DEMERG | MX1343742 | MX1343742 - EMERGT E1 SILVER GROVE CIR 6282 REP | 26001.91 |  | 26001.91 |  |  | 26001.91 | 42265.14 | -16263.23 | 2023-10-25 10:01 | 2024-10-29 | 2023-12-01 | 2024-02-26
75082 | FPITF | IT2300064 | IT2300064 - 2023 SERVER REPLACEMENT PROJECT | 16341.26 |  | 16341.26 |  |  | 16341.26 | 19231 | -2889.74 | 2023-07-18 15:38 | 2024-03-28 | 2023-11-01 | 2024-02-29
75082 | FPITF | IT2300072 | IT2300072 - 2023 SERVER EOL REPLACEMENT PROJECT | 16267.39 |  | 16267.39 |  |  | 16267.39 | 19323 | -3055.61 | 2023-08-02 16:14 | 2024-03-28 | 2023-11-01 | 2024-02-29
75084 | FPIT | IT2200153 | IT2200153 - RM TO AMAZON CLOUD REARCHITECT | 15915.94 |  | 15915.94 |  |  | 17024.73 | 17398 | -373.27 | 2022-11-03 14:35 | 2024-02-29 | 2022-12-01 | 2024-02-29
75085 | FPIT | 400055028 | 400055028 - PLANNED OUTAGE PORTAL 2.0 | 6584.96 |  | 6584.96 |  |  | 6584.96 | 7327 | -742.04 | 2023-09-12 12:53 | 2024-02-28 | 2023-12-01 | 2024-02-29
75080 | FPIT | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | 8131.05 |  | 8131.05 |  |  | 17317.23 | 16982 | 335.23 | 2021-12-10 14:04 | 2024-03-31 | 2022-02-01 | 2024-03-01
75084 | K23DEMERG | MX1760006 | MX1760006 - EMERGT E1 HEBRON STATION POWER 4 | 537.12 |  | 537.12 |  |  | 537.12 | 5087.28 | -4550.16 | 2023-11-30 18:01 | 2024-11-29 | 2023-12-01 | 2024-03-04
75084 | FPIT | 349472H14 | 349472H14 - NEW ESRI INTEGRATIONS AND INFRASTRU | 17.12 |  | 17.12 |  |  | 17.12 | 1556 | -1538.88 | 2021-02-09 13:49 | 2023-11-30 | 2023-11-01 | 2024-03-06
75084 | FPIT | 349472S14 | 349472S14 - NEW ESRI INTEGRATIONS AND INFRA | 7561.92 |  | 7561.92 |  |  | 67219.22 | 532359 | -465139.78 | 2021-02-09 12:29 | 2023-11-30 | 2021-03-01 | 2024-03-06
75084 | KYGLT20 | MX7809659 | MX7809659 - GLT F965 (KYGLT2001) REPLACE 1 POLE | 4769.62 |  | 4769.62 |  |  | 4769.62 | 8263.27 | -3493.65 | 2023-01-11 18:01 | 2024-03-01 | 2023-12-01 | 2024-03-06
75084 | M190297 | MX4194871 | MX4194871 - F5967 - REBUILD - CLARYVILLE TO SR | 396967.22 |  | 396967.22 |  |  | 625157.65 | 870687.63 | -245529.98 | 2022-02-18 14:01 | 2024-03-30 | 2022-04-01 | 2024-03-12
75084 | FPIT | IT220082D | IT220082D - ITOA ENHANCEMENTS 2022 | 20358.55 |  | 20358.55 |  |  | 27753.58 | 20349 | 7404.58 | 2022-06-29 09:37 | 2024-03-31 | 2022-07-01 | 2024-03-12
75084 | M190298 | MX4194619 | MX4194619 - F5967 REBUILD DECOURSEY TO MANN RD | 183419.73 |  | 183419.73 |  |  | 199990.83 | 169874.43 | 30116.4 | 2022-02-18 14:01 | 2024-03-30 | 2022-04-01 | 2024-03-12
75084 | M200056 | MX9945302 | MX9945302 - GLT TR_UB F5967 T-LINE M20005602M20 | 20824.42 |  | 20824.42 |  |  | 20824.42 | 52998.85 | -32174.43 | 2021-02-22 18:02 | 2024-03-31 | 2023-12-01 | 2024-03-13
75084 | M230292 | M23029201 | M23029201 - YORK SUBSTATION - REPLACE TB 1 ETM | 43172.12 |  | 43172.12 |  |  | 43172.12 | 45440.14 | -2268.02 | 2023-08-22 10:01 | 2024-02-12 | 2023-12-01 | 2024-03-13
75082 | WD050032 | WD050032X | WD050032X - U5 BREAKER OVERHAUL | 223916.42 |  | 223916.42 |  |  | 223916.42 | 295639.68 | -71723.26 | 2023-12-14 17:41 | 2024-02-28 | 2023-12-01 | 2024-03-14
75082 | WD060028 | WD060028X | WD060028X - U6 BREAKER OVERHAUL | 223916.42 |  | 223916.42 |  |  | 223916.42 | 223916.42 | 0 | 2023-12-14 17:42 | 2024-02-28 | 2023-12-01 | 2024-03-14
75080 | SG001010F | SG1010Z1R | SG1010Z1R - LMR DEK LMR PROJECT 2 DEM | 18.1 |  | 18.1 |  |  | 18.1 | 0 | 18.1 | 2023-05-09 14:20 | 2024-01-23 | 2023-10-01 | 2024-03-15
75084 | DKY2722 | MX8342093 | MX8342093 - VILLA 43 LN EXT TO THOM MORE 41 - A | 271479.73 |  | 271479.73 |  |  | 271479.73 | 163444.64 | 108035.09 | 2023-02-16 18:01 | 2024-03-30 | 2023-12-01 | 2024-03-17
75084 | 75084IK | MX9258781 | MX9258781 - MEMORIAL POINTE APARTMENTS | 78250.89 |  | 78250.89 |  |  | 78250.89 | 67728.86 | 10522.03 | 2023-06-08 18:01 | 2024-05-05 | 2023-12-01 | 2024-03-17
75084 | 75084IK | MX0057005 | MX0057005 - APR, 4805 AERO, NE TRANSFORMERS , O | 228235.27 |  | 228235.27 |  |  | 228235.27 | 199408.66 | 28826.61 | 2023-07-18 14:01 | 2024-03-21 | 2023-12-01 | 2024-03-19
75084 | DEMERKY | MX0059447 | MX0059447 - CAPITAL CRESCENT ABS 839 INSTALL VA | 14742.1 |  | 14742.1 |  |  | 14742.1 | 16415.88 | -1673.78 | 2021-03-10 14:02 | 2024-03-19 | 2023-12-01 | 2024-03-20
75084 | SG00359F | SG359SW | SG359SW - SG SADM SOFTWARE - 359 | 70246.94 |  | 70246.94 |  |  | 253960.16 | 227863.84 | 26096.32 | 2018-09-27 06:52 | 2024-06-30 | 2018-09-01 | 2024-03-20
75081 | EB022459 | EB022459X | EB022459X - REPLACE 24SR1 SWGR 4KV BUS | 62977.07 |  | 62977.07 |  |  | 62977.07 | 72237.6 | -9260.53 | 2023-12-21 12:55 | 2024-01-31 | 2023-12-01 | 2024-03-21
75084 | SG001024F | SG1024SW | SG1024SW - DEK CLOSED LOOP FISR FULL SCALE | 148650.73 |  | 148650.73 |  |  | 151771.01 | 283358 | -131586.99 | 2022-04-01 15:10 | 2024-04-30 | 2022-06-01 | 2024-03-27
75081 | EB022079 | EB022079X | EB022079X - 2-2 SERVICE WATER PUMP OVERHAUL | 432343.04 |  | 432343.04 |  |  | 432343.04 | 459188.75 | -26845.71 | 2023-02-07 16:21 | 2024-02-15 | 2023-12-01 | 2024-03-29
75080 | FPIT | IT2300010 | IT2300010 - MOVES TO AWS | 18928.75 |  | 18928.75 |  |  | 18928.75 | 28680 | -9751.25 | 2023-02-22 12:44 | 2024-03-29 | 2023-12-01 | 2024-03-29
75081 | FPITF | IT2200064 | IT2200064 - OPTIM UPLIFT | 21632.07 |  | 21632.07 |  |  | 35448.48 | 37717 | -2268.52 | 2022-05-05 15:50 | 2024-03-29 | 2022-05-01 | 2024-03-29
75082 | FPITF | IT2200064 | IT2200064 - OPTIM UPLIFT | 16178 |  | 16178 |  |  | 26469.45 | 28228 | -1758.55 | 2022-05-05 15:54 | 2024-03-29 | 2022-05-01 | 2024-03-29
75080 | FLKY0249G | DUKTKYE23 | DUKTKYE23 - PURCHASES OF VEHICLES AND EQUIPMENT | 181018.1 |  | 181018.1 |  |  | 181018.1 | 50000 | 131018.1 | 2022-12-15 15:20 | 2023-03-01 | 2023-12-01 | 2024-03-31
75080 | FLKY0249G | EDUKEKY23 | EDUKEKY23 - ELECTRIC EQUIPMENT PURCHASES - KY | 249102.27 |  | 249102.27 |  |  | 249102.27 | 50000 | 199102.27 | 2023-03-15 13:19 | 2024-03-31 | 2023-12-01 | 2024-03-31
75081 | EB022045 | CEBIC23 | CEBIC23 - INSTRUMENTATION & CONTROLS (GMA) | 348280.56 |  | 348280.56 |  |  | 348280.56 | 93970.32 | 254310.24 | 2023-01-25 12:32 | 2024-03-31 | 2023-12-01 | 2024-03-31
75081 | EB1912 | CEBVLV23 | CEBVLV23 - 2023 MISC VALVE BLANKET | 652426.43 |  | 652426.43 |  |  | 652426.43 | 606044.09 | 46382.34 | 2022-10-28 09:52 | 2024-03-31 | 2023-12-01 | 2024-03-31
75082 | WDCM0071 | CWDIC23 | CWDIC23 - INSTRUMENTATION & CONTROLS (GMA) | 41318.41 |  | 41318.41 |  |  | 41318.41 | 55518.04 | -14199.63 | 2023-01-25 12:43 | 2024-03-01 | 2023-12-01 | 2024-03-31
75082 | WG048C | CWDVLV23 | CWDVLV23 - WOODSDALE 2023 MISCELLANEOUS VALVES | 1552.4 |  | 1552.4 |  |  | 1552.4 | 212857 | -211304.6 | 2023-01-25 11:08 | 2024-12-30 | 2023-12-01 | 2024-03-31
75080 | DVV2023 | 400123001 | 400123001 - TELECOM NETWORK TRANSFORMATION PROG | 226770.48 |  | 226770.48 |  |  | 226770.48 | 236288 | -9517.52 | 2023-01-05 07:34 | 2024-03-30 | 2023-12-01 | 2024-03-31
75080 | FPIT | 400113003 | 400113003 - WORKSTATION REFRESH 2023/24 | 6340.99 |  | 6340.99 |  |  | 47940.83 | 46831 | 1109.83 | 2022-12-13 13:19 | 2024-03-28 | 2022-12-01 | 2024-03-31
75080 | FPIT | 400113004 | 400113004 - WORKSTATION REFRESH 2023/24 | 21274.662 |  | 21274.662 |  |  | 21274.66 | 11334 | 9940.66 | 2023-01-31 15:54 | 2024-03-30 | 2023-12-01 | 2024-03-31
75081 | FPITF | IT2300078 | IT2300078 - KMS SUBSCRIPTION LICENSE CONVERSION | 4650.55 |  | 4650.55 |  |  | 4650.55 | 4724 | -73.45 | 2023-08-22 15:48 | 2024-11-30 | 2023-12-01 | 2024-03-31
75081 | FPITF | IT2300121 | IT2300121 - CUTSFORTH DEPLOYED MONITORING | 8161.43 |  | 8161.43 |  |  | 8161.43 | 8212 | -50.57 | 2023-12-22 04:40 | 2024-03-31 | 2023-12-01 | 2024-03-31
75082 | FPITF | IT2300078 | IT2300078 - KMS SUBSCRIPTION LICENSE CONVERSION | 3470.03 |  | 3470.03 |  |  | 3470.03 | 3535 | -64.97 | 2023-08-22 15:54 | 2024-11-30 | 2023-12-01 | 2024-03-31
75082 | FPITF | IT2300121 | IT2300121 - CUTSFORTH DEPLOYED MONITORING | 6105.96 |  | 6105.96 |  |  | 6105.96 | 6146 | -40.04 | 2023-12-22 04:52 | 2024-03-31 | 2023-12-01 | 2024-03-31
75084 | FPIT | 349472023 | 349472023 - SMALLWORLD ENHANCEMENTS | 30394.26 |  | 30394.26 |  |  | 32204.43 | 8782 | 23422.43 | 2022-09-29 18:15 | 2025-03-30 | 2022-11-01 | 2024-03-31
75084 | FPIT | 349472027 | 349472027 - NEW EAM SERVERS | 2.35 |  | 2.35 |  |  | 2.35 | 1242 | -1239.65 | 2023-02-03 21:40 | 2024-03-30 | 2023-12-01 | 2024-03-31
75084 | FPIT | IT2300114 | IT2300114 - SUBNET CCE SOFTWARE | 28920.56 |  | 28920.56 |  |  | 28920.56 | 29036 | -115.44 | 2023-12-14 03:21 | 2024-03-30 | 2023-12-01 | 2024-03-31
75085 | FPIT | 400055025 | 400055025 - DIGITAL CARE PLATFORM | 64316.74 |  | 64316.74 |  |  | 64316.74 | 50822 | 13494.74 | 2023-03-14 09:51 | 2024-03-31 | 2023-12-01 | 2024-03-31
75085 | FPIT | 400055026 | 400055026 - INSPECTOR PORTAL PHASE 3 | 6878.38 |  | 6878.38 |  |  | 6878.38 | 4982 | 1896.38 | 2023-06-28 10:17 | 2024-03-29 | 2023-12-01 | 2024-03-31
75085 | FPIT | CS2200006 | CS2200006 - VERINT UPGRADE | 34600.83 |  | 34600.83 |  |  | 112944.72 | 114426 | -1481.28 | 2022-11-04 16:06 | 2024-03-31 | 2022-11-01 | 2024-03-31
75085 | FPIT | CS2200008 | CS2200008 - AVAYA PLATFORM UPGRADE - SERVER | 44510.14 |  | 44510.14 |  |  | 65230.76 | 63481 | 1749.76 | 2022-11-14 12:04 | 2024-03-31 | 2022-11-01 | 2024-03-31
75085 | FPIT | TC2300037 | TC2300037 - SAP ENABLE NOW APPLICATION | 8177.31 |  | 8177.31 |  |  | 8177.31 | 7170 | 1007.31 | 2023-08-09 16:41 | 2024-03-30 | 2023-12-01 | 2024-03-31
75084 | FPIT | 349472030 | 349472030 - ESRI UPGRADE TO 10.9 | 33238.38 |  | 33238.38 |  |  | 33238.38 | 13476 | 19762.38 | 2023-04-21 12:44 | 2024-03-30 | 2023-12-01 | 2024-03-31
75084 | KYGLT20 | KYGLT2001 | KYGLT2001 - GLT F965 RPL POLES | 566366.66 |  | 566366.66 |  |  | 746698.58 | 784349.09 | -37650.51 | 2020-09-09 14:01 | 2024-03-16 | 2020-09-01 | 2024-04-02
75084 | KYGLT20 | KYGLT2004 | KYGLT2004 - REAL ESTATE FOR KYGLT20 | 19286.84 |  | 19286.84 |  |  | 19286.84 | 2568 | 16718.84 | 2023-10-10 10:01 | 2024-05-17 | 2023-12-01 | 2024-04-02
75084 | 75084IK | MX5969210 | MX5969210 - JT-E-ENCLAVE SUBDIVISION | 141985.82 |  | 141985.82 |  |  | 141985.82 | 125621.41 | 16364.41 | 2023-08-03 10:01 | 2024-04-23 | 2023-12-01 | 2024-04-03
75084 | 75084IK | MX2832645 | MX2832645 - KEG - 200 W 3RD - OVATION PHASE 2 - | 825234.43 |  | 825234.43 |  |  | 825234.43 | 656525.76 | 168708.67 | 2022-03-23 14:01 | 2024-04-18 | 2022-07-01 | 2024-04-03
75080 | RESBLDKY | KMW23089 | KMW23089 - ERLANGER OPS CTR FENCE SYSTEM REPLA | 13694.3 |  | 13694.3 |  |  | 13694.3 | 10957 | 2737.3 | 2023-07-14 16:11 | 2023-12-31 | 2023-12-01 | 2024-04-04
75080 | RESBLDKY | KMW23256 | KMW23256 - DOOR REPLACEMENT | 31598 |  | 31598 |  |  | 31598 | 30820 | 778 | 2023-09-18 10:56 | 2024-03-30 | 2023-12-01 | 2024-04-04
75084 | 75084IL | MX9478509 | MX9478509 - 9232 US-42 LOT 6 UNION PROMENADE LI | 72907.09 |  | 72907.09 |  |  | 72907.09 | 72622.48 | 284.61 | 2023-07-19 18:01 | 2024-02-28 | 2023-12-01 | 2024-04-09
75084 | FPIT | IT2200158 | IT2200158 - HRM ROADMAP UPGRADES 2023 | 36323.08 |  | 36323.08 |  |  | 46161.96 | 43140 | 3021.96 | 2022-11-04 14:05 | 2024-06-30 | 2022-12-01 | 2024-04-09
75084 | M200056 | MX9945169 | MX9945169 - GLT TR_UB F5967 T-LINE M20005603 | 198060.6 |  | 198060.6 |  |  | 198060.6 | 200327.9 | -2267.3 | 2023-05-22 14:02 | 2024-04-30 | 2023-12-01 | 2024-04-09
75084 | M230335 | M23033501 | M23033501 - EMPIRE SUBSTATION - REPLACE CB 211 | 96519.79 |  | 96519.79 |  |  | 96519.79 | 168488.69 | -71968.9 | 2023-09-28 14:01 | 2024-03-22 | 2023-12-01 | 2024-04-10
75081 | EB021948 | EB021948X | EB021948X - REPL ABS BUILDING SUMP PUMPS | 135961.71 |  | 135961.71 |  |  | 137326.54 | 70991.48 | 66335.06 | 2022-03-15 07:44 | 2024-05-15 | 2022-08-01 | 2024-04-11
75084 | DEMERKY | MX0059480 | MX0059480 - CAPITAL CRESCENT ABS 852 INSTALL VA | 8542.02 |  | 8542.02 |  |  | 8542.02 | 16415.88 | -7873.86 | 2021-06-28 14:02 | 2024-04-09 | 2023-11-01 | 2024-04-15
75084 | 22410042A | MX1701471 | MX1701471 - 2410042A: FLORENCE 42 26BN-1037 REP | 9.5 |  | 9.5 |  |  | 175.41 | 228.31 | -52.9 | 2021-10-22 13:47 | 2025-07-29 | 2022-06-01 | 2024-04-22
75084 | 22410044A | MX1601020 | MX1601020 - TRANSFORMER UG 3-PHASE END OF LIFE | 3615.33 |  | 3615.33 |  |  | 4507.66 | 17578.41 | -13070.75 | 2022-04-27 10:01 | 2025-07-29 | 2022-04-01 | 2024-04-22
75084 | 22410044A | MX1701448 | MX1701448 - 2410044A: FLORENCE 44 BNK-6116 REPR | 39.86 |  | 39.86 |  |  | 736.85 | 228.31 | 508.54 | 2021-10-22 13:47 | 2025-07-29 | 2021-11-01 | 2024-04-22
75084 | 22410044A | MX7372045 | MX7372045 - 2410044A: FLORENCE 44 25BN-725 INST | 31896.94 |  | 31896.94 |  |  | 49631.14 | 48180.86 | 1450.28 | 2021-10-21 14:01 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410044A | MX7372047 | MX7372047 - 2410044A: FLORENCE 44 31BN-1326 INS | 4492.21 |  | 4492.21 |  |  | 68741.67 | 43984.74 | 24756.93 | 2021-10-22 09:12 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410044A | MX7372048 | MX7372048 - 2410044A: FLORENCE 44 BNK-2793 INST | 3305.55 |  | 3305.55 |  |  | 57113.87 | 48817.22 | 8296.65 | 2021-10-22 09:12 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410042A | MX1601026 | MX1601026 - TRANSFORMER UG 3-PHASE END OF LIFE | 2524.67 |  | 2524.67 |  |  | 46680.92 | 25431.13 | 21249.79 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410042A | MX1701474 | MX1701474 - 2410042A: FLORENCE 42 26BN-20 INSTA | 3406.3 |  | 3406.3 |  |  | 58371.37 | 42911.98 | 15459.39 | 2021-10-22 13:47 | 2025-07-29 | 2022-03-01 | 2024-04-22
75084 | 22410042A | MX1701475 | MX1701475 - 2410042A: FLORENCE 42 26BN-937 INST | 83137.51 |  | 83137.51 |  |  | 83518.83 | 49631.69 | 33887.14 | 2021-10-22 13:47 | 2025-07-29 | 2022-03-01 | 2024-04-22
75084 | 22410042A | MX2158190 | MX2158190 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 1513.79 |  | 1513.79 |  |  | 27989.71 | 15692.92 | 12296.79 | 2021-09-01 14:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410042A | MX2158197 | MX2158197 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 1799.91 |  | 1799.91 |  |  | 30648.38 | 17838.5 | 12809.88 | 2021-09-01 14:02 | 2025-07-29 | 2022-08-01 | 2024-04-22
75084 | 22410042A | MX5441962 | MX5441962 - 2410042A: FLORENCE 42 26BN-1083 INS | 5580.84 |  | 5580.84 |  |  | 55647.78 | 52442.19 | 3205.59 | 2022-07-26 14:01 | 2025-07-29 | 2022-07-01 | 2024-04-22
75084 | 22410044A | MX1601029 | MX1601029 - TRANSFORMER UG 3-PHASE END OF LIFE | 1555.12 |  | 1555.12 |  |  | 28754.05 | 18243.28 | 10510.77 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410044A | MX1601030 | MX1601030 - TRANSFORMER UG 3-PHASE END OF LIFE | 1232.8 |  | 1232.8 |  |  | 22794.64 | 17156.03 | 5638.61 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410044A | MX2158204 | MX2158204 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 1372.6 |  | 1372.6 |  |  | 25379.31 | 20181.62 | 5197.69 | 2021-09-01 14:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410044A | MX7372046 | MX7372046 - 2410044A: FLORENCE 44 26BN-1111 INS | -7777.81 |  | -7777.81 |  |  | 83188.95 | 42737.66 | 40451.29 | 2022-03-16 10:01 | 2025-07-29 | 2022-05-01 | 2024-04-22
75084 | 22410045A | MX5820993 | MX5820993 - SUB OPT -TRANSFORMER UG THREE PHASE | 31543.59 |  | 31543.59 |  |  | 32822.17 | 17674.38 | 15147.79 | 2022-09-22 14:01 | 2025-07-29 | 2022-09-01 | 2024-04-22
75084 | 22410046A | MX1601027 | MX1601027 - TRANSFORMER UG 3-PHASE END OF LIFE | 1634.23 |  | 1634.23 |  |  | 30216.34 | 20599.15 | 9617.19 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410046A | MX1701481 | MX1701481 - 2410046A: FLORENCE 46 31BN-1347 INS | 3305.38 |  | 3305.38 |  |  | 61116.17 | 45195.49 | 15920.68 | 2021-10-21 10:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410046A | MX5820998 | MX5820998 - SUB OPT -TRANSFORMER UG THREE PHASE | 24218.78 |  | 24218.78 |  |  | 25961.67 | 17804.27 | 8157.4 | 2022-09-06 14:01 | 2025-07-29 | 2022-09-01 | 2024-04-22
75084 | 22410046A | MX8564271 | MX8564271 - SUB OPT -TRANSFORMER UG THREE PHASE | 8721.68 |  | 8721.68 |  |  | 24204.11 | 18984.91 | 5219.2 | 2021-07-06 10:03 | 2025-07-29 | 2021-08-01 | 2024-04-22
75084 | 22410047A | MX1473566 | MX1473566 - 2410047A: FLORENCE 47 BNK-8073 INST | 6110.39 |  | 6110.39 |  |  | 67464.45 | 44184.22 | 23280.23 | 2021-10-21 14:01 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | 22410047A | MX7372051 | MX7372051 - 2410047A: FLORENCE 47 BNK-2806 INST | 67362.58 |  | 67362.58 |  |  | 147605.22 | 56141.81 | 91463.41 | 2021-10-22 09:12 | 2025-07-29 | 2021-10-01 | 2024-04-22
75084 | 22410046A | MX2158216 | MX2158216 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 1146.8 |  | 1146.8 |  |  | 21204.18 | 15237.7 | 5966.48 | 2021-09-01 14:02 | 2025-07-29 | 2022-04-01 | 2024-04-22
75084 | 22410046A | MX1601031 | MX1601031 - TRANSFORMER UG 3-PHASE END OF LIFE | 1520.81 |  | 1520.81 |  |  | 28119.8 | 18122.37 | 9997.43 | 2022-01-18 18:01 | 2025-07-29 | 2022-02-01 | 2024-04-22
75084 | 22410046A | MX2158210 | MX2158210 - SUB OPT - TRANSFORMER UG 3-PHASE EN | 2071.1 |  | 2071.1 |  |  | 38293.97 | 23199.72 | 15094.25 | 2021-09-01 14:02 | 2025-07-29 | 2021-12-01 | 2024-04-22
75084 | M230288 | M23028801 | M23028801 - BLACKWELL SUBSTATION - REPLACE TB 1 | 15282.08 |  | 15282.08 |  |  | 15282.08 | 42450.48 | -27168.4 | 2023-08-17 14:13 | 2024-04-29 | 2023-12-01 | 2024-04-25
75084 | 75084HW | MX0384263 | MX0384263 - TOWER PARK ATHLETIC COMPLEX RENOVAT | 10033.95 |  | 10033.95 |  |  | 10033.95 | 58715.91 | -48681.96 | 2023-11-16 14:01 | 2024-05-09 | 2023-12-01 | 2024-04-28
75084 | 75084HW | MX0197455 | MX0197455 - UNION PROMENADE/US-42 SIGNAL INSTAL | -44244.99 |  | -44244.99 |  |  | -44244.99 | 40668.06 | -84913.05 | 2023-11-14 14:01 | 2024-05-09 | 2023-12-01 | 2024-05-06
75084 | 75084IK | MX6184723 | MX6184723 - UNION PROMENADE BACKBONE: COMMERCIA | 357344.26 |  | 357344.26 |  |  | 357344.26 | 177076.29 | 180267.97 | 2022-12-16 10:02 | 2024-05-16 | 2023-12-01 | 2024-05-08
75084 | M190226 | MX7488872 | MX7488872 - D-CONST RECO WOODSPOINT-AERO - M190 | 124108.07 |  | 124108.07 |  |  | 136025.81 | 184107.64 | -48081.83 | 2020-07-20 10:01 | 2024-05-29 | 2020-09-01 | 2024-05-12
75084 | M190226 | MX7488839 | MX7488839 - D-CONST UG TRANSFERS - M190226 | 550.78 |  | 550.78 |  |  | 3658.89 | 5697.77 | -2038.88 | 2020-07-20 10:01 | 2024-05-29 | 2020-09-01 | 2024-05-12
75084 | 75084IK | MX6281598 | MX6281598 - JT-E-UNION PROMENADE CONDOMINIUM | 84031.54 |  | 84031.54 |  |  | 84031.54 | 48623.89 | 35407.65 | 2023-02-13 10:13 | 2024-05-29 | 2023-12-01 | 2024-05-14
75084 | 75084IK | MX9407205 | MX9407205 - JT-E-VILLAGE OF DECOURSEY CREEK PHA | 97477.63 |  | 97477.63 |  |  | 97477.63 | 160851.63 | -63374 | 2023-10-06 10:01 | 2024-06-13 | 2023-12-01 | 2024-05-15
75084 | 75084IK | MX0670131 | MX0670131 - NOVA TO VIPER RECLOSER RPL, BNK-562 | 15805.42 |  | 15805.42 |  |  | 15805.42 | 48868.69 | -33063.27 | 2023-11-16 14:01 | 2024-06-28 | 2023-12-01 | 2024-05-22
75081 | EB022230 | EB022230X | EB022230X - REPLACE RECLAIM PIT LIGHTING | 54969.33 |  | 54969.33 |  |  | 54969.33 | 77067.19 | -22097.86 | 2023-04-13 15:54 | 2023-09-30 | 2023-12-01 | 2024-05-23
75084 | M220085 | M22008501 | M22008501 - EMPIRE INSTALL BATTERY CABINET | 78485.2 |  | 78485.2 |  |  | 78485.2 | 205738.18 | -127252.98 | 2022-12-14 18:01 | 2024-04-30 | 2023-12-01 | 2024-05-26
75084 | 75084HW | MX9418070 | MX9418070 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 58650.13 |  | 58650.13 |  |  | 58650.13 | 277974.08 | -219323.95 | 2023-05-22 10:02 | 2024-05-30 | 2023-12-01 | 2024-05-28
75084 | 75084IL | MX6891483 | MX6891483 - CITY OF INDEPENDENCE, PH 21 | -113695.09 |  | -113695.09 |  |  | -113695.09 | 89036 | -202731.09 | 2023-10-25 10:01 | 2024-07-18 | 2023-10-01 | 2024-05-29
75081 | FPITF | IT2300068 | IT2300068 - PRIMAVERA UPGRADE TO VERSION 22.12 | 606.48 |  | 606.48 |  |  | 606.48 | 5006 | -4399.52 | 2023-08-04 16:14 | 2024-05-29 | 2023-12-01 | 2024-05-31
75082 | FPITF | IT2300068 | IT2300068 - PRIMAVERA UPGRADE TO VERSION 22.12 | 452.84 |  | 452.84 |  |  | 452.84 | 3747 | -3294.16 | 2023-08-04 16:24 | 2024-05-29 | 2023-12-01 | 2024-05-31
75085 | FPIT | CS2300002 | CS2300002 - MESH NETWORK OPTIMIZATION | 5814.966 |  | 5814.966 |  |  | 5814.97 | 17727 | -11912.03 | 2023-04-03 12:15 | 2024-05-29 | 2023-12-01 | 2024-05-31
75084 | 75084IK | MX9171230 | MX9171230 - JT-E-THE OVERLOOK AT SUNROCK PHASE | 8795.67 |  | 8795.67 |  |  | 8795.67 | 50328.64 | -41532.97 | 2023-08-17 10:01 | 2024-08-22 | 2023-12-01 | 2024-06-02
75084 | 75084IL | MX7058120 | MX7058120 - CITY OF INDEPENDENCE COBRAHEAD UPGR | -62984.21 |  | -62984.21 |  |  | -62984.21 | 42805.25 | -105789.46 | 2023-10-25 14:01 | 2024-07-18 | 2023-10-01 | 2024-06-04
75084 | 75084IL | MX7057150 | MX7057150 - CITY OF INDEPENDENCE COBRAHEAD UPGR | -59851.14 |  | -59851.14 |  |  | -59851.14 | 38463.2 | -98314.34 | 2023-10-25 14:01 | 2024-07-18 | 2023-10-01 | 2024-06-10
75084 | K23DEMERG | MX0619837 | MX0619837 - EMERGT E1 ALEXANDRIA SOUTH REPLACE | 3288.03 |  | 3288.03 |  |  | 3288.03 | 13193.4 | -9905.37 | 2023-09-07 10:01 | 2024-05-29 | 2023-12-01 | 2024-06-11
75084 | M210491 | M21049101 | M21049101 - FEEDER 6765 RELOCATION | 41241.4 |  | 41241.4 |  |  | 53133 | 1306917.69 | -1253784.69 | 2022-07-12 14:01 | 2024-05-14 | 2022-07-01 | 2024-06-12
75084 | TOUTKY | OUT69KY | OUT69KY - KY T-LINE EMERGENCY REPL ON 69KV | 20579.93 |  | 20579.93 |  |  | 350591.14 | 420345.37 | -69754.23 | 2017-01-17 10:23 | 2027-12-31 | 2017-01-01 | 2024-06-13
75084 | K23FNDFLD | MX9383139 | MX9383139 - RPL 31BN-529 (STUB) F6763 | 17960.48 |  | 17960.48 |  |  | 17960.48 | 16646.01 | 1314.47 | 2023-05-16 10:01 | 2024-03-21 | 2023-12-01 | 2024-06-16
75084 | M220084 | M22008401 | M22008401 - ATLAS INSTALL BATTERY CABINET | 85180.68 |  | 85180.68 |  |  | 85180.68 | 201746.95 | -116566.27 | 2022-12-14 18:01 | 2024-04-30 | 2023-12-01 | 2024-06-20
75084 | 75084HW | MX9101587 | MX9101587 - 06-8916 - HOUSTON ROAD EXTENSION TO | 117477.48 |  | 117477.48 |  |  | 117477.48 | 271524.36 | -154046.88 | 2023-05-22 10:02 | 2024-08-01 | 2023-12-01 | 2024-06-27
75084 | FPIT | IT2200122 | IT2200122 - ACQUIRE TUFIN & NPVIEW FIREWALL LIC | 162.63 |  | 162.63 |  |  | 7156.26 | 10558 | -3401.74 | 2022-09-01 07:14 | 2024-05-29 | 2022-12-01 | 2024-06-28
75084 | FPIT | 349472020 | 349472020 - SLATE - EAM WORK MGMT SCHEDULING TO | 26619.73 |  | 26619.73 |  |  | 43424.42 | 44680 | -1255.58 | 2022-03-18 16:07 | 2024-06-30 | 2022-03-01 | 2024-06-30
75084 | FPIT | 349472031 | 349472031 - MATERIAL ISSUE LIGHTING APPLICATION | 1831.06 |  | 1831.06 |  |  | 1831.06 | 9033 | -7201.94 | 2023-10-20 11:35 | 2024-06-30 | 2023-12-01 | 2024-06-30
75085 | FPIT | 400055023 | 400055023 - USAGE ALERTS PHASE 2 | 34367.1 |  | 34367.1 |  |  | 34367.1 | 46597 | -12229.9 | 2022-12-15 18:59 | 2024-06-29 | 2023-12-01 | 2024-06-30
75085 | FPIT | 400055027 | 400055027 - PEAK DEMAND EVENT MANAGEMENT PLATFO | 9260.17 |  | 9260.17 |  |  | 9260.17 | 13069 | -3808.83 | 2023-08-01 14:45 | 2024-06-30 | 2023-12-01 | 2024-06-30
75084 | FPIT | LTHTRLIVS | LTHTRLIVS - LIGHTHOUSE: TRANSMISSION LIVE LIDAR | 23076.86 |  | 23076.86 |  |  | 41970.37 | 29192 | 12778.37 | 2021-10-28 16:21 | 2024-06-30 | 2021-11-01 | 2024-07-02
75084 | FPIT | LTHTRMTLS | LTHTRMTLS - LIGHTHOUSE: TRANSMISSION TITUS | 16949.97 |  | 16949.97 |  |  | 35072.84 | 34698 | 374.84 | 2021-10-26 10:52 | 2024-08-30 | 2021-11-01 | 2024-07-09
75084 | 75084HW | MX9907616 | MX9907616 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -139050.16 |  | -139050.16 |  |  | -139050.16 | 143761.65 | -282811.81 | 2023-07-14 18:01 | 2024-11-14 | 2023-12-01 | 2024-07-23
75084 | M190298 | MX4194121 | MX4194121 - F5967 (M190298) - REBUILD - 10768 M | 7570.01 |  | 7570.01 |  |  | 16062.45 | 47328.8 | -31266.35 | 2022-02-18 14:01 | 2024-07-29 | 2022-04-01 | 2024-07-23
75084 | M190226 | MX0535898 | MX0535898 - DMM - WOODSPOINT D-REBUILD - M19022 | 25170.93 |  | 25170.93 |  |  | 25170.93 | 116527.59 | -91356.66 | 2023-08-23 14:01 | 2024-07-29 | 2023-12-01 | 2024-07-23
75081 | EB022267 | EB022267X | EB022267X - REPLACE 2-2 FLY ASH EXHAUSTER | 64271.74 |  | 64271.74 |  |  | 64271.74 | 74721.99 | -10450.25 | 2023-06-08 07:48 | 2024-03-15 | 2023-12-01 | 2024-07-26
75084 | K23DEMERG | MX9635259 | MX9635259 - EMERGT E1 MARSHALL REPLACE PHASE B | 812.65 |  | 812.65 |  |  | 812.65 | 7637.15 | -6824.5 | 2023-06-08 10:01 | 2024-03-30 | 2023-12-01 | 2024-07-30
75084 | M180375 | M18037502 | M18037502 - LITTON SUB- EXT XMISSION | 376028.51 |  | 376028.51 |  |  | 436914.15 | 1336460 | -899545.85 | 2021-10-29 14:02 | 2024-07-01 | 2021-12-01 | 2024-07-31
75084 | M180375 | M18037503 | M18037503 - LITTON SUB- CONSTRUCT TRANS LOOP | 1243618.87 |  | 1243618.87 |  |  | 1331346.75 | 1952021.1 | -620674.35 | 2021-10-29 14:02 | 2024-06-30 | 2022-01-01 | 2024-07-31
75085 | FPIT | 400055001 | 400055001 - ENTERPRISE FEEDBACK TOOL | 1970.29 |  | 1970.29 |  |  | 1970.29 | 10056 | -8085.71 | 2023-05-02 13:28 | 2024-07-30 | 2023-12-01 | 2024-07-31
75085 | FPIT | 400055024 | 400055024 - SERVICE NAVIGATOR | 31871.7 |  | 31871.7 |  |  | 31871.7 | 44849 | -12977.3 | 2022-12-20 19:39 | 2024-06-30 | 2023-12-01 | 2024-07-31
75084 | 75084HW | MX8555714 | MX8555714 - DONALDSON HIGHWAY UNDERGROUND RELOC | 245863.83 |  | 245863.83 |  |  | 245863.83 | 463620.04 | -217756.21 | 2023-08-04 10:01 | 2024-09-26 | 2023-12-01 | 2024-08-07
75084 | 75084IK | MX9197324 | MX9197324 - JT-E-AOSTA VALLEY PHASE 10 | 84146.19 |  | 84146.19 |  |  | 84146.19 | 80300.9 | 3845.29 | 2023-11-17 10:01 | 2024-07-25 | 2023-12-01 | 2024-08-11
75084 | 75084IK | MX6246270 | MX6246270 - JT-E-MEMORIAL POINTE APARTMENTS | 232325.77 |  | 232325.77 |  |  | 232325.77 | 233686.87 | -1361.1 | 2023-04-25 18:01 | 2024-09-27 | 2023-12-01 | 2024-08-12
75084 | KYGLT21 | KYGLT2102 | KYGLT2102 - GLT F5962 RPL 12-POLES AND REPAIR 1 | 480381.99 |  | 480381.99 |  |  | 511785.69 | 1763246.58 | -1251460.89 | 2022-01-19 14:02 | 2024-09-28 | 2022-02-01 | 2024-08-14
75081 | FPITF | LTHRROBTS | LTHRROBTS - LIGHTHOUSE: RRE ORBIT2 | 27699.04 |  | 27699.04 |  |  | 65372.76 | 87364.58 | -21991.82 | 2021-08-26 20:52 | 2024-08-10 | 2021-08-01 | 2024-08-15
75082 | FPITF | LTHRROBTS | LTHRROBTS - LIGHTHOUSE: RRE ORBIT2 | 20945.26 |  | 20945.26 |  |  | 49257.83 | 65523.44 | -16265.61 | 2021-08-26 21:00 | 2024-08-10 | 2021-08-01 | 2024-08-15
75082 | WD010068 | WD010068X | WD010068X - U1 TURBINE BLADES | 7067.57 |  | 7067.57 |  |  | 7067.57 | 6121947.01 | -6114879.44 | 2023-06-27 08:31 | 2024-12-31 | 2023-12-01 | 2024-08-24
75082 | WD010070 | WD010070X | WD010070X - WDC U1 WATER INJECTION PUMP | 53368 |  | 53368 |  |  | 53368 | 114975.98 | -61607.98 | 2023-04-14 13:10 | 2024-08-31 | 2023-12-01 | 2024-08-28
75084 | FPIT | LTHCDEPJB | LTHCDEPJB - PRE JOB BRIEF SOFTWARE | 803.75 |  | 803.75 |  |  | 803.75 | 3247 | -2443.25 | 2023-11-22 08:40 | 2024-08-30 | 2023-12-01 | 2024-08-30
75081 | EBS01303 | EBS01303X | EBS01303X - WSP VACUUM DRUM FILTER | 1154267.39 |  | 1154267.39 |  |  | 1154267.39 | 1773362.83 | -619095.44 | 2022-12-12 17:21 | 2024-06-30 | 2023-12-01 | 2024-08-31
75085 | FPIT | TC2300036 | TC2300036 - SAP CUSTOMER SYSTEM CHANGES AND ENH | 13221.78 |  | 13221.78 |  |  | 13221.78 | 33852 | -20630.22 | 2023-08-07 15:02 | 2024-08-29 | 2023-12-01 | 2024-08-31
75084 | M230090 | MX9780049 | MX9780049 - GLT F5983/ M23009001/ REPLACE 15 PO | 45.71 |  | 45.71 |  |  | 45.71 | 107515.13 | -107469.42 | 2023-06-21 10:01 | 2024-11-14 | 2023-12-01 | 2024-09-09
75084 | 75084IL | MX9160207 | MX9160207 - MAIN ST CITY OF FLORENCE PH 2 LED S | -37231.17 |  | -37231.17 |  |  | -37231.17 | 177328.14 | -214559.31 | 2023-05-24 18:01 | 2024-10-29 | 2023-12-01 | 2024-09-17
75084 | 75084HW | MX8659310 | MX8659310 - TMG- 4397 BORON AVE. -COMM. RELOCAT | -32849.43 |  | -32849.43 |  |  | -32849.43 | 48662.3 | -81511.73 | 2023-09-18 10:01 | 2024-05-09 | 2023-12-01 | 2024-09-22
75084 | 75084HW | MX9851050 | MX9851050 - RI-KY-236 (DONALDSON ROAD) FROM HOU | 826326.5 |  | 826326.5 |  |  | 826326.5 | 831587.68 | -5261.18 | 2023-03-29 14:01 | 2024-12-26 | 2023-12-01 | 2024-09-22
75084 | 20550044A | RWT055A | RWT055A - ROW - DONALDSON - H9320550044 | 98.18 |  | 98.18 |  |  | 1815.39 | 5000 | -3184.61 | 2021-06-16 08:35 | 2024-09-30 | 2021-07-01 | 2024-09-30
75084 | FPIT | IT2300085 | IT2300085 - HOTLINETAG MOBILE WEB APPLICATION | 3069.13 |  | 3069.13 |  |  | 3069.13 | 7650 | -4580.87 | 2023-10-18 05:22 | 2024-09-30 | 2023-12-01 | 2024-09-30
75084 | FPIT | LTHTRTVMT | LTHTRTVMT - LIGHTHOUSE TRANSMISSION TVM 2.0 | 38638.6 |  | 38638.6 |  |  | 45534.14 | 48665 | -3130.86 | 2022-05-19 10:22 | 2024-09-28 | 2022-05-01 | 2024-09-30
75084 | FPIT | LTHTTVMSG | LTHTTVMSG - LIGHTHOUSE TRANSMISSION TVM 2.0 | 3003.31 |  | 3003.31 |  |  | 9857.15 | 9360 | 497.15 | 2022-05-19 08:22 | 2024-09-01 | 2022-05-01 | 2024-09-30
75084 | M180383 | M18038301 | M18038301 - WHITE TOWER INSTALL SECOND V-STRUCT | 95490.12 |  | 95490.12 |  |  | 147946.05 | 1174045.45 | -1026099.4 | 2022-03-04 14:01 | 2024-09-30 | 2022-04-01 | 2024-10-01
75084 | M180383 | M18038302 | M18038302 - WHITE TOWER BK 2 RPL | 826902.4 |  | 826902.4 |  |  | 931924.68 | 4007317 | -3075392.32 | 2022-03-04 14:01 | 2024-09-30 | 2022-04-01 | 2024-10-01
75084 | M180383 | M18038303 | M18038303 - WHITE TOWER 5967 POLE RELO | 20009.11 |  | 20009.11 |  |  | 21106.65 | 245670 | -224563.35 | 2022-03-04 14:01 | 2024-10-13 | 2022-10-01 | 2024-10-01
75084 | 22990041A | MX2725052 | MX2725052 - CAP UPGRADE, 11K-34, DECOURSEY (299 | 48582.67 |  | 48582.67 |  |  | 48609.66 | 49209.76 | -600.1 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX2725053 | MX2725053 - CAP UPGRADE, 11K-613, DECOURSEY (29 | 1082.4 |  | 1082.4 |  |  | 1109.39 | 38928.48 | -37819.09 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX2725055 | MX2725055 - CAP UPGRADE, 11K-654, DECOURSEY (29 | 2141.16 |  | 2141.16 |  |  | 2153.05 | 19513.01 | -17359.96 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX2725056 | MX2725056 - CAP UPGRADE, 11K-69, DECOURSEY (299 | 2439.81 |  | 2439.81 |  |  | 2466.8 | 31166.61 | -28699.81 | 2022-09-22 14:01 | 2024-06-27 | 2022-12-01 | 2024-10-07
75084 | 22990041A | MX6490130 | MX6490130 - SUB OPT- 2990041A- DECOURSEY 41- TA | 15703.94 |  | 15703.94 |  |  | 15703.94 | 393560.66 | -377856.72 | 2022-09-22 14:01 | 2024-06-27 | 2023-12-01 | 2024-10-07
75084 | 22990041A | MX9353338 | MX9353338 - JTD - 22990041A: DECOURSEY 41 8K-48 | 16046.9 |  | 16046.9 |  |  | 16046.9 | 47886.64 | -31839.74 | 2023-07-10 18:01 | 2024-06-27 | 2023-12-01 | 2024-10-07
75084 | 22990041A | MX9353339 | MX9353339 - JTD - 22990041A: DECOURSEY 41 11K-4 | 17285.26 |  | 17285.26 |  |  | 17285.26 | 50662.77 | -33377.51 | 2023-07-10 14:01 | 2024-06-27 | 2023-12-01 | 2024-10-07
75084 | 22990041A | MX9353335 | MX9353335 - JTD - 22990041A: DECOURSEY 41 11K-7 | 16660.79 |  | 16660.79 |  |  | 16660.79 | 47143.65 | -30482.86 | 2023-07-10 18:01 | 2024-06-27 | 2023-12-01 | 2024-10-07
75084 | 22990041A | MX9353336 | MX9353336 - JTD - 22990041A: DECOURSEY 41 11K-1 | 15931.99 |  | 15931.99 |  |  | 15931.99 | 50046.74 | -34114.75 | 2023-07-10 14:01 | 2024-06-27 | 2023-12-01 | 2024-10-07
75084 | 22990041A | MX9353337 | MX9353337 - JTD - 22990041A: DECOURSEY 41 11K-7 | 16108.94 |  | 16108.94 |  |  | 16108.94 | 48410.34 | -32301.4 | 2023-07-10 14:01 | 2024-06-27 | 2023-12-01 | 2024-10-07
75084 | 22990041A | V2299REMK | V2299REMK - SUB OPT - REM - DECOURSEY - 0041 | 8053.58 |  | 8053.58 |  |  | 8053.58 | 0 | 8053.58 | 2022-10-24 12:04 | 2025-03-31 | 2023-12-01 | 2024-10-09
75084 | 75084IL | MX9804712 | MX9804712 - 9196 US HIGHWAY 42 UNION PROMENADE | 69690.35 |  | 69690.35 |  |  | 69690.35 | 70232.74 | -542.39 | 2023-07-05 14:01 | 2024-11-28 | 2023-12-01 | 2024-10-13
75084 | 22410045A | RW2241A | RW2241A - FLORENCE SO - TUG ROW | 124.97 |  | 124.97 |  |  | 2311.06 | 0 | 2311.06 | 2022-04-13 08:57 | 2024-10-31 | 2022-04-01 | 2024-11-21
75084 | SG001059F | SG1059HW | SG1059HW - HARDWARE IN-LOOP HIL LAB | 17416.97 |  | 17416.97 |  |  | 37281.57 | 74157.59 | -36876.02 | 2022-09-22 16:56 | 2025-03-31 | 2022-09-01 | 2024-11-30
75084 | FPIT | IT2300069 | IT2300069 - THE GOODS APP - INVENTORY MANAGEMEN | 4246.45 |  | 4246.45 |  |  | 4246.45 | 9623 | -5376.55 | 2023-08-08 07:51 | 2024-09-29 | 2023-12-01 | 2024-11-30
75084 | M230095 | M23009501 | M23009501 - F6763 69KV POLE REPLACEMENT | 411.66 |  | 411.66 |  |  | 411.66 | 119394.16 | -118982.5 | 2023-08-10 18:01 | 2024-11-03 | 2023-12-01 | 2024-12-03
75084 | M230224 | M23022401 | M23022401 - CRITTENDEN INSTALL BATTERY CABINET | 1263.8 |  | 1263.8 |  |  | 1263.8 | 154624.01 | -153360.21 | 2023-08-08 14:01 | 2025-01-10 | 2023-12-01 | 2024-12-17
75084 | KYGLT21 | MX5261357 | MX5261357 - GLT F5962 (KYGLT2102) 14-POLES | 16356.1 |  | 16356.1 |  |  | 22370.45 | 133247.71 | -110877.26 | 2022-08-05 14:01 | 2025-03-31 | 2022-08-01 | 2024-12-24
75084 | 21890041A | MX5254726 | MX5254726 - 21890041A: LIMABURG 41 14BN-28 INST | 76505.93 |  | 76505.93 |  |  | 76703.95 | 52320.45 | 24383.5 | 2022-06-01 18:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX5254728 | MX5254728 - 21890042A: LIMABURG 42 19BN-224 INS | 111713.58 |  | 111713.58 |  |  | 111725.46 | 47841.9 | 63883.56 | 2022-06-01 18:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX5254729 | MX5254729 - 21890042A: LIMABURG 42 20BN-855 INS | 72914.57 |  | 72914.57 |  |  | 72914.57 | 52170.53 | 20744.04 | 2022-06-01 18:01 | 2025-05-01 | 2023-12-01 | 2025-01-01
75084 | 21890042A | MX5254730 | MX5254730 - 21890042A: LIMABURG 42 19BN-485 INS | 76586.94 |  | 76586.94 |  |  | 76586.94 | 52334.52 | 24252.42 | 2022-06-01 18:01 | 2025-05-01 | 2023-12-01 | 2025-01-01
75084 | 21890042A | MX5313258 | MX5313258 - SUB-OPT - 21890042A: LIMABURG 42 FL | 360116.5 |  | 360116.5 |  |  | 362185.35 | 261724.52 | 100460.83 | 2022-06-02 14:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX5821189 | MX5821189 - SUB OPT-TRANSFORMER UG 3-PHASE END | 1434.49 |  | 1434.49 |  |  | 1519.56 | 329.87 | 1189.69 | 2022-08-16 14:01 | 2025-05-01 | 2022-10-01 | 2025-01-01
75084 | 21890042A | MX5821190 | MX5821190 - SUB OPT-TRANSFORMER UG 3-PHASE END | 573.34 |  | 573.34 |  |  | 2602.36 | 33264.63 | -30662.27 | 2022-08-16 14:01 | 2025-05-01 | 2022-10-01 | 2025-01-01
75084 | 21890042A | MX6282574 | MX6282574 - SUB OPT -DPZ LIMABURG 42 H93218900 | 105100.74 |  | 105100.74 |  |  | 106758.77 | 138098.89 | -31340.12 | 2022-09-13 14:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890043A | MX2725025 | MX2725025 - CAP UPGRADE, 20BN-630, LIMABURG (18 | 30087.72 |  | 30087.72 |  |  | 30114.7 | 28105.61 | 2009.09 | 2022-05-04 10:03 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX2725024 | MX2725024 - CAP UPGRADE, 20BN-92, LIMABURG (189 | 2172.45 |  | 2172.45 |  |  | 27162.84 | 30344.18 | -3181.34 | 2022-03-21 14:01 | 2025-05-01 | 2022-04-01 | 2025-01-01
75084 | 21890042A | MX2725066 | MX2725066 - CAP UPGRADE, 20BN-35, LIMABURG (189 | 16918.61 |  | 16918.61 |  |  | 16942.38 | 29237.95 | -12295.57 | 2022-05-04 10:03 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | MX5254727 | MX5254727 - 21890042A: LIMABURG 42 19BN-229 INS | 80571.62 |  | 80571.62 |  |  | 82394.58 | 51529.71 | 30864.87 | 2022-06-06 10:01 | 2025-05-01 | 2022-12-01 | 2025-01-01
75084 | 21890042A | V2189HAZK | V2189HAZK - SUB OPT - HAZ - LIMABURG - 0042 | 61643.7 |  | 61643.7 |  |  | 61643.7 | 0 | 61643.7 | 2022-10-24 11:47 | 2025-03-31 | 2023-12-01 | 2025-01-03
75085 | CUSTCONN | 400109M | 400109M - MY ACCOUNT MODERNIZATION | 54010.44 |  | 54010.44 |  |  | 54010.44 | 194169 | -140158.56 | 2023-06-09 11:45 | 2025-03-31 | 2023-12-01 | 2025-01-16
75081 | EB021215 | EB021215X | EB021215X - OWEN ELECTRIC FEED REPLACEMENT | 1092366.41 |  | 1092366.41 |  |  | 1256265.46 | 1776134.31 | -519868.85 | 2022-07-08 13:20 | 2024-12-31 | 2022-07-01 | 2025-01-17
75081 | EB022238 | HROPTEB | HROPTEB - HEAT RATE OPTIMIZATION TOOL - DEK | 247681.23 |  | 247681.23 |  |  | 247681.23 | 295000 | -47318.77 | 2023-06-07 17:15 | 2024-10-31 | 2023-12-01 | 2025-01-21
75081 | EB021551 | EB021551X | EB021551X - REPLACE LBU BARGE & TROLLEY DRIVE | 73295.84 |  | 73295.84 |  |  | 73295.84 | 272875.06 | -199579.22 | 2023-01-26 15:44 | 2024-12-31 | 2023-12-01 | 2025-01-29
75084 | M210330 | M21033001 | M21033001 - COVINGTON INSTALL RTU | 38452.7 |  | 38452.7 |  |  | 38452.7 | 215281.9 | -176829.2 | 2022-10-07 14:01 | 2025-01-13 | 2023-12-01 | 2025-01-29
75080 | FPIT | CO2300002 | CO2300002 - GIFT CARD INVENTORY MODERN ARCHITEC | 2232.98 |  | 2232.98 |  |  | 2232.98 | 3645 | -1412.02 | 2023-05-31 13:16 | 2024-10-30 | 2023-12-01 | 2025-01-30
75085 | FPIT | 400055029 | 400055029 - IVR VOICE AUTHENTICATION | 110219.17 |  | 110219.17 |  |  | 110219.17 | 155712 | -45492.83 | 2023-10-19 13:09 | 2025-06-29 | 2023-12-01 | 2025-01-31
75084 | M230100 | M23010001 | M23010001 - F6765 69KV 2022 POLE INSPECTION KY | 1706.52 |  | 1706.52 |  |  | 1706.52 | 476227.88 | -474521.36 | 2023-08-10 18:01 | 2025-02-03 | 2023-12-01 | 2025-02-03
75081 | EB022017 | EB022017X | EB022017X - REPL CBU BREASTING CABLE | 171021.97 |  | 171021.97 |  |  | 205174.15 | 405985.22 | -200811.07 | 2022-11-28 11:46 | 2024-12-31 | 2022-12-01 | 2025-02-05
75081 | EB022070 | EB022070X | EB022070X - REPLACE WSP FILTER FEED PUMPS | 88187.02 |  | 88187.02 |  |  | 88187.02 | 86865.14 | 1321.88 | 2023-02-07 17:11 | 2024-12-31 | 2023-12-01 | 2025-02-05
75081 | EB022168 | EB022168X | EB022168X - REPL FGD A MOD INLET & HUMP DUCT | 108273.97 |  | 108273.97 |  |  | 108273.97 | 4419813.09 | -4311539.12 | 2023-11-06 15:02 | 2025-03-15 | 2023-12-01 | 2025-02-05
75081 | EB022421 | EB022421X | EB022421X - REPL FGD DUCTWORK B INLET & C HUMP | 106256.15 |  | 106256.15 |  |  | 106256.15 | 4420559.96 | -4314303.81 | 2023-11-27 11:11 | 2025-03-15 | 2023-12-01 | 2025-02-05
75081 | EB020345 | EB020345X | EB020345X - CBU REPLACE BUCKETS AND CHAINS | 152992.11 |  | 152992.11 |  |  | 152992.11 | 1970524.89 | -1817532.78 | 2023-02-28 08:13 | 2024-12-31 | 2023-12-01 | 2025-02-06
75084 | 75084HW | MX0935094 | MX0935094 - KEG - 2072 CLARKSTON - LONGBRANCH 4 | -1583424.02 |  | -1583424.02 |  |  | -1583424.02 | 37302.43 | -1620726.45 | 2023-11-17 14:01 | 2025-02-23 | 2023-12-01 | 2025-02-18
75084 | 20760041A | MX9353388 | MX9353388 - JTD - 20760041A: DAYTON 41 CA4-360 | 1445.04 |  | 1445.04 |  |  | 1445.04 | 46935.96 | -45490.92 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760041A | MX9353389 | MX9353389 - JTD - 20760041A: DAYTON 41 CA4-411 | 1362.03 |  | 1362.03 |  |  | 1362.03 | 46879.18 | -45517.15 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760041A | MX9353391 | MX9353391 - JTD - 20760041A: DAYTON 41 CA4-592 | 1522.72 |  | 1522.72 |  |  | 1522.72 | 54035.97 | -52513.25 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760041A | MX9353392 | MX9353392 - JTD - 20760041A: DAYTON 41 CA3-529 | 875.58 |  | 875.58 |  |  | 875.58 | 51961.32 | -51085.74 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760042A | MX9353393 | MX9353393 - JTD - 20760042A: DAYTON 42 CA1-886 | 745.1 |  | 745.1 |  |  | 745.1 | 59065.74 | -58320.64 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760042A | MX9353394 | MX9353394 - JTD - 20760042A: DAYTON 42 CA1-712 | 364.19 |  | 364.19 |  |  | 364.19 | 47534.66 | -47170.47 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760042A | MX9353397 | MX9353397 - JTD - 20760042A: DAYTON 42 CA5-226 | 810.11 |  | 810.11 |  |  | 810.11 | 51834.92 | -51024.81 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760043A | MX2725051 | MX2725051 - CAP UPGRADE, CA3-500, DAYTON (76) 7 | 1095.97 |  | 1095.97 |  |  | 1095.97 | 35530.49 | -34434.52 | 2023-06-05 14:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 21470042A | MX9353342 | MX9353342 - JTD - 21470042A: CLARYVILLE 42 47CA | 1718.92 |  | 1718.92 |  |  | 1718.92 | 61998.75 | -60279.83 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 21470042A | MX9382916 | MX9382916 - JTD - 21470042A: CLARYVILLE 42 47CA | 15814.82 |  | 15814.82 |  |  | 15814.82 | 44707.63 | -28892.81 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | 20760042A | MX9353395 | MX9353395 - JTD - 20760042A: DAYTON 42 CA1-734 | 382.84 |  | 382.84 |  |  | 382.84 | 63509.75 | -63126.91 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | 2025-02-25
75084 | M180384 | M18038401 | M18038401 - WHITE TOWER TB 1 REBUILD | 28088.61 |  | 28088.61 |  |  | 47845.98 | 1229270.12 | -1181424.14 | 2022-03-07 14:01 | 2025-02-01 | 2022-04-01 | 2025-02-26
75080 | FPIT | TC210HW57 | TC210HW57 - CIOPS NERC CIP CYBERARK HW | -1805.51 |  | -1805.51 |  |  | -3.1264e-13 | 1538 | -1538 | 2021-12-10 15:13 | 2024-09-30 | 2022-01-01 | cancelled
75081 | EB021604 | EB021604X | EB021604X - FGD LIMESTONE CONVERSION | -9430.24 |  | -9430.24 |  |  | 1.819e-12 | 397974.18 | -397974.18 | 2022-02-16 14:48 | 2025-06-01 | 2022-02-01 | cancelled
75081 | FPITF | IT2300106 | IT2300106 - CANCEL - HARTIGEN POWER OPTIX | 10486.43 |  | 10486.43 |  |  | 10486.43 | 17801 | -7314.57 | 2023-12-15 01:48 | 2024-11-01 | 2023-12-01 | cancelled
75082 | FPITF | IT2300106 | IT2300106 - CANCEL - HARTIGEN POWER OPTIX | 7848.33 |  | 7848.33 |  |  | 7848.33 | 13323 | -5474.67 | 2023-12-15 02:36 | 2024-11-01 | 2023-12-01 | cancelled
75084 | 20550043A | MX1064765 | MX1064765 - TBC SUB OPT - DONALDSON 43 CVG SOUT | -21402.47 |  | -21402.47 |  |  | 0 | 228.31 | -228.31 | 2021-11-01 10:01 | 2024-03-30 | 2021-11-01 | cancelled
75084 | 20550043A | MX1518649 | MX1518649 - TBC SUB OPT - AUTOMATED SWITCHGEAR | -12177.74 |  | -12177.74 |  |  | 2.9132e-13 | 66198.38 | -66198.38 | 2021-11-01 10:01 | 2024-03-30 | 2021-11-01 | cancelled
75084 | 20550043A | MX1518718 | MX1518718 - TBC SUB OPT - AUTOMATED SWITCHGEAR | -3777.62 |  | -3777.62 |  |  | 1.5632e-13 | 266431.08 | -266431.08 | 2021-11-01 14:01 | 2024-03-30 | 2021-11-01 | cancelled
75084 | 20670044A | MX1701452 | MX1701452 - TBC 0670044A: BUFFINGTON 44 K106-11 | -734.11 |  | -734.11 |  |  | -2.0917e-13 | 228.31 | -228.31 | 2021-10-21 10:02 | 2023-10-01 | 2021-11-01 | cancelled
75084 | 20670045A | MX1701456 | MX1701456 - TBC 0670045A: BUFFINGTON 45 BNK-562 | -5059.81 |  | -5059.81 |  |  | 1.2659e-12 | 228.31 | -228.31 | 2021-10-21 10:02 | 2023-10-01 | 2021-12-01 | cancelled
75084 | 20670045A | MX1701457 | MX1701457 - TBC 0670045A: BUFFINGTON 45 BNK-562 | -5579.74 |  | -5579.74 |  |  | 1.819e-12 | 228.31 | -228.31 | 2021-10-21 10:02 | 2023-10-01 | 2021-12-01 | cancelled
75084 | 20670045A | MX1701464 | MX1701464 - TBC 0670045A: BUFFINGTON 45 K117-66 | -34.44 |  | -34.44 |  |  | 3.5805e-15 | 228.31 | -228.31 | 2021-10-21 10:02 | 2023-10-01 | 2021-10-01 | cancelled
75084 | 20670047A | MX1701466 | MX1701466 - TBC 0670047A: BUFFINGTON 47 K107-31 | -696.53 |  | -696.53 |  |  | -1.3767e-14 | 228.31 | -228.31 | 2021-10-21 10:02 | 2023-10-01 | 2021-10-01 | cancelled
75084 | 20700041A | MX5254700 | MX5254700 - TBC 20700041A: CRESCENT 41 K84-264 | -170.21 |  | -170.21 |  |  | -1.0914e-11 | 53550.62 | -53550.62 | 2022-06-01 14:01 | 2024-12-29 | 2022-09-01 | cancelled
75084 | 20780046A | MX9353381 | MX9353381 - TBC JTD - 20780046A: AUGUSTINE 46 K | 730.41 |  | 730.41 |  |  | 730.41 | 45172.42 | -44442.01 | 2023-07-10 14:01 | 2025-08-28 | 2023-12-01 | cancelled
75084 | 21320041A | MX9353369 | MX9353369 - TBC JTD - 21320041A: COLD SPRING 41 | 2128.15 |  | 2128.15 |  |  | 2128.15 | 57505.61 | -55377.46 | 2023-06-05 14:01 | 2025-03-01 | 2023-12-01 | cancelled
75084 | 21320042A | MX9353353 | MX9353353 - TBC JTD - 21320042A: COLD SPRING 42 | 2.49 |  | 2.49 |  |  | 2.49 | 228.31 | -225.82 | 2023-06-05 14:01 | 2025-03-01 | 2023-12-01 | cancelled
75084 | 21990042A | MX5821196 | MX5821196 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 52.98 |  | 52.98 |  |  | 979.56 | 19784.72 | -18805.16 | 2022-08-16 14:01 | 2025-01-29 | 2022-10-01 | cancelled
75084 | 21990042A | MX5821208 | MX5821208 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 458.46 |  | 458.46 |  |  | 1350.49 | 19538.85 | -18188.36 | 2022-11-09 18:01 | 2025-01-29 | 2022-11-01 | cancelled
75084 | 21990042A | MX5821211 | MX5821211 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | -133.14 |  | -133.14 |  |  | 8.93 | 228.31 | -219.38 | 2022-08-24 10:10 | 2024-12-29 | 2022-10-01 | cancelled
75084 | 21990042A | MX5821218 | MX5821218 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | -133.14 |  | -133.14 |  |  | 8.93 | 228.31 | -219.38 | 2022-08-24 10:10 | 2024-12-29 | 2022-10-01 | cancelled
75084 | 21990043A | MX5821223 | MX5821223 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 457.02 |  | 457.02 |  |  | 1323.93 | 20257.25 | -18933.32 | 2022-08-24 10:10 | 2025-01-29 | 2022-11-01 | cancelled
75084 | 22050041A | MX5254697 | MX5254697 - TBC 22050041A: ALEXANDRIA SOUTH 41 | -34.38 |  | -34.38 |  |  | 92.65 | 228.31 | -135.66 | 2022-06-01 10:05 | 2024-09-28 | 2022-09-01 | cancelled
75084 | 22050041A | MX5821234 | MX5821234 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 4108.06 |  | 4108.06 |  |  | 5381.3 | 44318.04 | -38936.74 | 2022-08-05 14:01 | 2025-07-29 | 2022-09-01 | cancelled
75084 | 22100041A | K2210SURK | K2210SURK - TBC SUB OPT - SUR - OAKBROOK STA - | -14093.3 |  | -14093.3 |  |  | 1174.21 | 0 | 1174.21 | 2021-05-20 11:33 | 2024-03-01 | 2022-02-01 | cancelled
75084 | 22410045A | MX0002522 | MX0002522 - TBC 2023 SUB OPT TUG - PHEASANT DR | -46554.63 |  | -46554.63 |  |  | 16.96 | 228.31 | -211.35 | 2021-12-13 14:11 | 2024-12-29 | 2021-12-01 | cancelled
75084 | 22410045A | MX0002524 | MX0002524 - TBC 2023 SUB OPT TUG - PHEASANT DR | -39693.94 |  | -39693.94 |  |  | 14.61 | 228.31 | -213.7 | 2021-12-13 14:11 | 2024-12-29 | 2021-12-01 | cancelled
75084 | 22410045A | MX0002526 | MX0002526 - TBC 2023 SUB OPT TUG - PHEASANT DR | -5340.49 |  | -5340.49 |  |  | 2.0606e-13 | 228.31 | -228.31 | 2021-12-13 18:02 | 2024-12-29 | 2022-01-01 | cancelled
75084 | 23040043A | MX5254744 | MX5254744 - TBC 23040041A: WHITE TOWER 43 KNK- | -1750.42 |  | -1750.42 |  |  | 2.2737e-13 | 228.31 | -228.31 | 2022-06-07 14:01 | 2024-03-30 | 2022-11-01 | cancelled
75084 | 75084IK | MX0494865 | MX0494865 - TBC MXCONV-TRANSFORMER RETROFIT H | -745.97 |  | -745.97 |  |  | -1.8208e-14 | 104991.78 | -104991.78 | 2019-11-18 18:01 | 2023-05-01 | 2019-11-01 | cancelled
75084 | 75084IK | MX0675382 | MX0675382 - TBC WESTPACK CUSTOMER STATION | -1423.05 |  | -1423.05 |  |  | -3.1308e-14 | 10800.23 | -10800.23 | 2017-12-15 14:01 | 2023-08-01 | 2018-03-01 | cancelled
75084 | 75084IK | MX1793644 | MX1793644 - TBC TRANSFORMER RETROFIT - CRESCENT | -17851 |  | -17851 |  |  | 1.3074e-12 | 53485.55 | -53485.55 | 2021-09-13 10:02 | 2023-07-01 | 2021-11-01 | cancelled
75084 | 75084IK | MX9998915 | MX9998915 - TBC URD WILDER 41 | -15488.37 |  | -15488.37 |  |  | 964.45 | 228.31 | 736.14 | 2018-04-27 10:01 | 2024-07-26 | 2018-05-01 | cancelled
75084 | 75084IK | MX9998916 | MX9998916 - TBC TRANSFORMER REPLACEMENT KENTO | -236.08 |  | -236.08 |  |  | 9.1038e-15 | 228.31 | -228.31 | 2018-03-26 10:02 | 2027-10-28 | 2018-05-01 | cancelled
75084 | GLPRTFA | KYGLPR5 | KYGLPR5 - GLT CIR 2862B P1-P2 | -51607.88 |  | -51607.88 |  |  | 4617.39 | 160000 | -155382.61 | 2016-06-13 16:14 | 2024-12-31 | 2016-07-01 | cancelled
75084 | KUCF48474 | KUC348474 | KUC348474 - TBC UG 10348474 OAKBROOK '42' | -649.31 |  | -649.31 |  |  | -1.1369e-13 | 190407.95 | -190407.95 | 2017-02-15 14:04 | 2023-12-01 | 2017-07-01 | cancelled
75084 | KYGLPRT | MX1325365 | MX1325365 - TBC F5983 X-FER UB FOR 6 - P2 WOOD | -9538.14 |  | -9538.14 |  |  | -2.2737e-13 | 78426.11 | -78426.11 | 2019-04-23 18:01 | 2023-11-01 | 2019-07-01 | cancelled
75084 | KYGLT20 | KYGLT2003 | KYGLT2003 - GLT 965 RPL POLE AT SPORTS COMPLEX | 25214.23 |  | 25214.23 |  |  | 43476.56 | 199818.87 | -156342.31 | 2022-04-22 14:01 | 2024-09-08 | 2022-08-01 | cancelled
75084 | M180375 | M18037504 | M18037504 - LITTON SUB TLINE RLE | -507.02 |  | -507.02 |  |  | 50.09 | 63208 | -63157.91 | 2021-10-29 14:02 | 2023-07-01 | 2022-07-01 | cancelled
75084 | M220358 | M22035801 | M22035801 - F5489 138KV 2022 POLE INSPECTIONS | 0.01 |  | 0.01 |  |  | 0.01 | 695367.65 | -695367.64 | 2023-02-24 10:01 | 2024-01-20 | 2023-05-01 | cancelled
75084 | SG000685F | MX0000476 | MX0000476 - TBC 2021 TUG 2606514 N TALBOT AVE P | -7861.18 |  | -7861.18 |  |  | -1.4566e-13 | 228.31 | -228.31 | 2019-05-31 14:01 | 2023-05-01 | 2019-07-01 | cancelled
75084 | SG000685F | MX0000477 | MX0000477 - TBC 2020 TUG 26062514 N TALBOT AVE | -2749.06 |  | -2749.06 |  |  | -1.2008e-12 | 228.31 | -228.31 | 2019-05-31 14:01 | 2023-05-01 | 2019-08-01 | cancelled
75084 | SG000732F | SG732TR02 | SG732TR02 - TBC -TOWER & SHELTER - VERONA 2 | 3643.45 |  | 3643.45 |  |  | 3177.13 | 968336 | -965158.87 | 2019-01-23 11:05 | 2022-03-31 | 2019-02-01 | cancelled
75084 | SG001092F | SG1092SLR | SG1092SLR - DEK AERO SOLAR | -6150414.3 |  | -6150414.3 |  |  | 8.4401e-10 | 4976446 | -4976446 | 2021-03-12 10:30 | 2022-10-15 | 2021-03-01 | cancelled
75084 | TKY1999 | TKY199902 | TKY199902 - CONSTANCE 69KV TLS | -16883.6 |  | -16883.6 |  |  | -1.1369e-12 | 0 | -1.1369e-12 | 2018-07-06 10:02 | 2024-06-10 | 2019-02-01 | cancelled
75084 | TKY1999 | TKY199903 | TKY199903 - CONSTANCE BUS 1 SWGR CB RPL | -8002.81 |  | -8002.81 |  |  | -0.03 | 2390612 | -2390612.03 | 2018-07-06 10:02 | 2024-06-21 | 2019-02-01 | cancelled
75081 | FPITF | LTHRUNITY | LTHRUNITY - LIGHTHOUSE RRE UNITY | 26022.07 |  | 26022.07 |  |  | 44482.27 | 65354 | -20871.73 | 2022-04-20 09:09 | 2024-11-30 | 2022-05-01 | open
75082 | FPITF | LTHRUNITY | LTHRUNITY - LIGHTHOUSE RRE UNITY | 19790.34 |  | 19790.34 |  |  | 33865.94 | 48917 | -15051.06 | 2022-04-20 09:15 | 2024-11-30 | 2022-05-01 | open
75084 | FPIT | LTHTRFELD | LTHTRFELD - LIGHTHOUSE TRANSMISSION TITUS FIELD | 11124.73 |  | 11124.73 |  |  | 30532.13 | 33157 | -2624.87 | 2022-05-10 12:02 | 2024-12-30 | 2022-05-01 | open
75084 | SG000838F | SG838BTR | SG838BTR - DEK EOL POWER SUPPLIES | 18051.92 |  | 18051.92 |  |  | 188847.5 | 81484 | 107363.5 | 2019-01-22 08:29 | 2022-03-31 | 2019-04-01 | open
75084 | 20420044A | MX7372059 | MX7372059 - 0420044A: CONSTANCE 44 K103-119 REP | 487.6 |  | 487.6 |  |  | 9015.66 | 0 | 9015.66 | 2021-12-16 18:02 | 2025-03-13 | 2022-07-01 | open
75084 | 20670041A | MX1701469 | MX1701469 - TBC 0670041A: BUFFINGTON 41 K116-9 | 97.36 |  | 97.36 |  |  | 1799.95 | 228.31 | 1571.64 | 2021-10-21 10:02 | 2023-02-28 | 2021-10-01 | open
75084 | 20700041A | MX5821351 | MX5821351 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 18.2 |  | 18.2 |  |  | 336.34 | 228.31 | 108.03 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700041A | MX5821352 | MX5821352 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 14.07 |  | 14.07 |  |  | 260.04 | 228.31 | 31.73 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700041A | MX5821358 | MX5821358 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 5.51 |  | 5.51 |  |  | 101.71 | 228.31 | -126.6 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 22100041A | MX7372044 | MX7372044 - TBC 2100041A: OAKBROOK 41 25BN-351 | 120.12 |  | 120.12 |  |  | 2221.19 | 228.31 | 1992.88 | 2021-10-22 09:12 | 2023-10-26 | 2022-06-01 | open
75084 | 22410044A | MX7372049 | MX7372049 - TBC 2410044A: FLORENCE 44 BNK-6117 | 33.72 |  | 33.72 |  |  | 623.71 | 228.31 | 395.4 | 2021-10-22 09:12 | 2025-07-29 | 2022-06-01 | open
75084 | 22410045A | MX1701478 | MX1701478 - TBC 2410045A: FLORENCE 45 BNK-598 | 192.78 |  | 192.78 |  |  | 3564.2 | 228.31 | 3335.89 | 2021-10-21 10:02 | 2025-07-29 | 2022-04-01 | open
75084 | 22410045A | MX5821004 | MX5821004 - TBC SUB OPT -TRANSFORMER UG THREE | 62.47 |  | 62.47 |  |  | 1154.9 | 228.31 | 926.59 | 2022-09-06 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 22410046A | MX1701480 | MX1701480 - TBC 2410046A: FLORENCE 46 30BN-672 | 617.86 |  | 617.86 |  |  | 11423.55 | 0 | 11423.55 | 2021-12-07 10:01 | 2025-07-29 | 2021-12-01 | open
75084 | 22410047A | MX7372052 | MX7372052 - TBC 2410047A: FLORENCE 47 BNK-6156 | 39.54 |  | 39.54 |  |  | 731.2 | 228.31 | 502.89 | 2021-10-22 09:12 | 2025-07-29 | 2022-08-01 | open
75084 | 75084HW | MX6277290 | MX6277290 - RELOCATION HIGHWAY DOT SPECIFIC PRO | 9343.88 |  | 9343.88 |  |  | 41365.51 | 228.31 | 41137.2 | 2020-04-02 18:01 | 2025-05-01 | 2020-04-01 | open
75084 | 75084IK | KELT3PH | KELT3PH - END OF LIFE PAD TRANSF 3PH NON LEAK | 170209.86 |  | 170209.86 |  |  | 2747530.13 | 0 | 2747530.13 | 2020-01-09 15:04 | 2067-12-31 | 2020-02-01 | open
75084 | 75084IK | KMHR | KMHR - MANHOLE LID RETROFIT REPLACEMENT | 7087.7 |  | 7087.7 |  |  | 8450.6 | 0 | 8450.6 | 2017-07-27 14:56 | 2067-12-31 | 2019-12-01 | open
75084 | 75084IK | KROC | KROC - OH DETERIORATED CONDUCTOR REPLACE | 8894.69 |  | 8894.69 |  |  | 149727.94 | 0 | 149727.94 | 2018-07-11 10:07 | 2067-12-31 | 2018-11-01 | open
75084 | 75084IK | KSBDUG | KSBDUG - NEW CUSTOMER WORK - RES SUBDIV INFR | 1165360.48 |  | 1165360.48 |  |  | 2751535.56 | 0 | 2751535.56 | 2019-09-26 10:05 | 2028-04-01 | 2020-01-01 | open
75084 | 75084IL | KPPLLGT | KPPLLGT - PURPLE LIGHT REPLACE | -1876.38 |  | -1876.38 |  |  | 29843.69 | 440 | 29403.69 | 2021-04-16 11:58 | 2069-12-31 | 2021-07-01 | open
75084 | 75084IL | KSMCELL | KSMCELL - OUTDOOR LIGHTING SMALL CELL REGULTD | -683.52 |  | -683.52 |  |  | 12033.42 | 0 | 12033.42 | 2017-09-20 15:00 | 2067-04-01 | 2019-03-01 | open
75084 | 75084RR | KNANC | KNANC - NEIGHBORHOOD AREA NTWK REPLACEMENTS | 6113.4 |  | 6113.4 |  |  | 92119.82 | 0 | 92119.82 | 2017-03-27 14:46 | 2067-04-01 | 2019-05-01 | open
75084 | 75084VM | VDEXTCUKY | VDEXTCUKY - VDEXTCUKY | 4878.32 |  | 4878.32 |  |  | 21167.61 | 0 | 21167.61 | 2017-07-13 12:51 | 2050-12-31 | 2021-01-01 | open
75084 | K23NPWHB | MX6464431 | MX6464431 - CAPITAL CLARYVILLE REPLACE LS TB 2 | 6813.98 |  | 6813.98 |  |  | 6813.98 | 3306.33 | 3507.65 | 2023-01-31 18:01 | 2024-03-30 | 2023-12-01 | open
75084 | K241TUG1 | MX0006936 | MX0006936 - TUG - PHEASANT DR - WEST INSTALL | 49684.7 |  | 49684.7 |  |  | 49684.7 | 228.31 | 49456.39 | 2023-11-01 10:01 | 2026-09-28 | 2023-12-01 | open
75084 | K241TUG1 | MX0006937 | MX0006937 - TUG - PHEASANT DR - RETIRE | 5230.22 |  | 5230.22 |  |  | 5230.22 | 228.31 | 5001.91 | 2023-11-01 10:01 | 2027-01-28 | 2023-12-01 | open
75084 | KUCF48450 | KUC348450 | KUC348450 - UG 10348450 CRESCENT 44 | -2401.02 |  | -2401.02 |  |  | 165.62 | 0 | 165.62 | 2017-04-11 14:03 | 2022-06-30 | 2017-10-01 | open
75084 | ORDFA | SKY2003DC | SKY2003DC - TO CAPTURE 2020 CAPITAL STORM #3 | 772.54 |  | 772.54 |  |  | 10040.25 | 0 | 10040.25 | 2019-05-07 21:31 | 2020-12-31 | 2020-06-01 | open
75084 | ORDFA | SKY2206DC | SKY2206DC - TO CAPTURE 2022 CAPITAL STORM #6 | 2033.94 |  | 2033.94 |  |  | 43492.98 | 0 | 43492.98 | 2022-03-21 18:24 | 2022-09-30 | 2022-06-01 | open
75084 | ORDFA | SKY2207DC | SKY2207DC - TO CAPTURE 2022 CAPITAL STORM #7 | 797.14 |  | 797.14 |  |  | 15722.89 | 0 | 15722.89 | 2022-03-21 18:26 | 2022-09-30 | 2022-06-01 | open
75084 | ORDFA | SKY2208DC | SKY2208DC - TO CAPTURE 2022 CAPITAL STORM #8 | -1188.14 |  | -1188.14 |  |  | 138915.1 | 0 | 138915.1 | 2022-03-21 18:27 | 2022-09-30 | 2022-07-01 | open
75084 | ORDFA | SKY2210DC | SKY2210DC - TO CAPTURE 2022 CAPITAL STORM #10 I | 10087 |  | 10087 |  |  | 54594.2 | 0 | 54594.2 | 2022-03-21 18:31 | 2022-09-30 | 2022-12-01 | open
75084 | ORDFA | SKY2301DC | SKY2301DC - TO CAPTURE 2023 CAPITAL STORM #1 | 146957.62 |  | 146957.62 |  |  | 146957.62 | 0 | 146957.62 | 2022-09-30 09:34 | 2023-09-30 | 2023-02-01 | open
75084 | ORDFA | SKY2302DC | SKY2302DC - TO CAPTURE 2023 CAPITAL STORM #2 | 37626.09 |  | 37626.09 |  |  | 37626.09 | 0 | 37626.09 | 2022-09-30 09:44 | 2023-09-30 | 2023-02-01 | open
75084 | ORDFA | SKY2303DC | SKY2303DC - TO CAPTURE 2023 CAPITAL STORM #3 | 99400.83 |  | 99400.83 |  |  | 99400.83 | 0 | 99400.83 | 2022-09-30 09:52 | 2023-09-30 | 2023-05-01 | open
75084 | ORDFA | SKY2304DC | SKY2304DC - TO CAPTURE 2023 CAPITAL STORM #4 | 9237.44 |  | 9237.44 |  |  | 9237.44 | 0 | 9237.44 | 2022-09-30 09:55 | 2023-09-30 | 2023-04-01 | open
75084 | ORDFA | SKY2305DC | SKY2305DC - TO CAPTURE 2023 CAPITAL STORM #5 | 10823.53 |  | 10823.53 |  |  | 10823.53 | 0 | 10823.53 | 2022-09-30 09:58 | 2023-09-30 | 2023-05-01 | open
75084 | ORDFA | SKY2307DC | SKY2307DC - TO CAPTURE 2023 CAPITAL STORM #7 | 26211.31 |  | 26211.31 |  |  | 26211.31 | 0 | 26211.31 | 2022-09-30 10:05 | 2023-09-30 | 2023-12-01 | open
75084 | ORDFA | SKY2308DC | SKY2308DC - TO CAPTURE 2023 CAPITAL STORM #8 | 6112.98 |  | 6112.98 |  |  | 6112.98 | 0 | 6112.98 | 2022-09-30 10:08 | 2023-09-30 | 2023-12-01 | open
75084 | ORDFA | SKY2309DC | SKY2309DC - TO CAPTURE 2023 CAPITAL STORM #9 | 10893.93 |  | 10893.93 |  |  | 10893.93 | 0 | 10893.93 | 2022-09-30 10:11 | 2023-09-30 | 2023-12-01 | open
75084 | ORDFA | SKY2310DC | SKY2310DC - TO CAPTURE 2023 CAPITAL STORM #10 | 1033.79 |  | 1033.79 |  |  | 1033.79 | 0 | 1033.79 | 2022-09-30 10:14 | 2023-09-30 | 2023-12-01 | open
75084 | SG001135F | ALTMETVEN | ALTMETVEN - ALTERNATIVE METER VENDOR DEK | 39887.64 |  | 39887.64 |  |  | 39887.64 | 0 | 39887.64 | 2023-03-06 21:55 | 2050-12-31 | 2023-12-01 | open
75084 | SG001135F | CGRREPLA | CGRREPLA - CGR REPLACEMENT | 33233.487 |  | 33233.487 |  |  | 33233.49 | 50000 | -16766.51 | 2023-02-20 23:17 | 2050-12-31 | 2023-12-01 | open
75080 | ASSETCPAK | CPADEK | CPADEK - DEK CAPITAL CPA ALLOCATION | 22172.13 |  | 22172.13 |  |  | 35741.83 | 0 | 35741.83 | 2018-01-31 08:58 | 2050-12-31 | 2018-03-01 | open
75080 | CAPBUDK | DISOHDK | DISOHDK - DEK DISTRIBUTION OVERHEAD POOL | -21075.06 |  | -21075.06 |  |  | -39873.96 | 0 | -39873.96 | 2017-07-31 11:00 | 2026-03-31 | 2018-01-01 | open
75080 | CAPBUDK | ETSPDCAPK | ETSPDCAPK - ETS POWER DELIVERY CAP OVERHEAD | 1788.24 |  | 1788.24 |  |  | 1788.24 | 0 | 1788.24 | 2008-07-07 | 2050-12-31 | 2008-07-01 | open
75080 | CAPBUDK | GPACCRUAL | GPACCRUAL - MIDWEST VACATION ACCRUAL | 8077.15 |  | 8077.15 |  |  | 54949.37 | 0 | 54949.37 | 2021-03-18 08:47 | 2051-03-31 | 2021-03-01 | open
75080 | FPIT | 400113005 | 400113005 - WORKSTATION REFRESH 2023/24 | 275087.9 |  | 275087.9 |  |  | 275087.9 | 46812 | 228275.9 | 2023-09-29 06:00 | 2025-03-15 | 2023-12-01 | open
75080 | FPIT | 400149HW2 | 400149HW2 - ESCA - ITOT CYBER CARBON BLACK HW | 1791.53 |  | 1791.53 |  |  | 1791.53 | 6085 | -4293.47 | 2023-08-08 12:10 | 2026-03-31 | 2023-12-01 | open
75080 | FPIT | IT2300086 | IT2300086 - DET DATA MART MODERNIZATION | 1047.82 |  | 1047.82 |  |  | 1047.82 | 13994 | -12946.18 | 2023-11-03 07:11 | 2025-03-31 | 2023-12-01 | open
75080 | FPIT | IT2300094 | IT2300094 - PLANNING MODEL DATABASE | 423.06 |  | 423.06 |  |  | 423.06 | 10409 | -9985.94 | 2023-11-04 00:55 | 2026-03-31 | 2023-12-01 | open
75080 | FPIT | PH2ASPAHW | PH2ASPAHW - ESCA-OT ASSET,PATCH & VULNERABILITY | 705.93 |  | 705.93 |  |  | 705.93 | 8522 | -7816.07 | 2023-09-01 08:42 | 2026-03-31 | 2023-12-01 | open
75080 | FPIT | PH2ASPASW | PH2ASPASW - ESCA-OT ASSET,PATCH & VULNERABILITY | 67530.55 |  | 67530.55 |  |  | 67530.55 | 861642 | -794111.45 | 2023-08-31 09:52 | 2026-03-31 | 2023-12-01 | open
75080 | GENERIC | INCENTIVE | INCENTIVE - INCENTIVE TRUE-UP | -145801.001 |  | -145801.001 |  |  | 34035.29 | 0 | 34035.29 | 2019-11-22 10:36 | 2050-12-31 | 2019-11-01 | open
75080 | KYPYACCR | E1214 | E1214 - KENTUCKY QUARTERLY PAYROLL ACCRUAL | -14000 |  | -14000 |  |  | 55000 | 0 | 55000 | 2008-09-19 | 2050-12-31 | 2008-09-01 | open
75080 | MRTPBKFX | 400089001 | 400089001 - TELECOM BREAK-FIX | 2457.9 |  | 2457.9 |  |  | 2457.9 | 0 | 2457.9 | 2021-11-10 17:01 | 2027-03-31 | 2023-12-01 | open
75080 | RESBLDKY | ASDEKRO | ASDEKRO - ADMN SVCS BLANKET FOR REG OTHER DEK | 5553.01 |  | 5553.01 |  |  | 6081.1 | 0 | 6081.1 | 2022-07-11 16:51 | 2050-12-31 | 2022-09-01 | open
75080 | TOOLFA2 | BKYTOOL | BKYTOOL - TOOL & EQUIPMENT PURCHASES - DEK | 2208.28 |  | 2208.28 |  |  | 72490.76 | 50000 | 22490.76 | 2020-02-20 11:35 | 2050-12-31 | 2020-04-01 | open
75081 | EB020684 | EB020684X | EB020684X - HYDRAZINE AND AMMONIA CONTROLS | 260216.45 |  | 260216.45 |  |  | 266279.46 | 1161418.87 | -895139.41 | 2022-07-25 15:59 | 2025-08-31 | 2022-08-01 | open
75081 | EB020687 | EB020687X | EB020687X - REPLACE CRUSHER HOUSE BOILER | 735.92 |  | 735.92 |  |  | 40754.33 | 556282.6 | -515528.27 | 2022-04-08 14:58 | 2024-12-31 | 2022-06-01 | open
75081 | EB021392 | EB021392X | EB021392X - RELAY REPLACEMENT PH. II RATS | 2903.2 |  | 2903.2 |  |  | 24168.73 | 603768 | -579599.27 | 2022-02-23 08:39 | 2025-12-31 | 2022-03-01 | open
75081 | EB021749 | EB021749X | EB021749X - HCAD REPL TRIPPER RM DUST COLLECTOR | 31369.28 |  | 31369.28 |  |  | 31369.28 | 2542673.29 | -2511304.01 | 2023-10-11 15:10 | 2025-12-31 | 2023-12-01 | open
75081 | EB021969 | EB021969X | EB021969X - SEWAGE TREATMENT LEVEL TRANSMITTER | 10399.03 |  | 10399.03 |  |  | 51122.26 | 60858.98 | -9736.72 | 2022-05-12 13:11 | 2024-12-31 | 2022-06-01 | open
75081 | EB022007 | CEB022007 | CEB022007 - EASTBEND WEST LANDFILL CELL 3 | 104660.27 |  | 104660.27 |  |  | 116510.52 | 22801029 | -22684518.48 | 2022-09-28 09:23 | 2028-12-31 | 2022-11-01 | open
75081 | EB022062 | EB022062X | EB022062X - REPLACE 2-1 VERTIMILL GEARBOX | 29779.16 |  | 29779.16 |  |  | 29779.16 | 154610.57 | -124831.41 | 2022-12-22 11:06 | 2025-02-15 | 2023-11-01 | open
75081 | EB022083 | EB022083X | EB022083X - REPL CH SURGE BIN LOAD CELLS | 46120.12 |  | 46120.12 |  |  | 46120.12 | 71851.94 | -25731.82 | 2023-02-07 16:39 | 2025-12-31 | 2023-12-01 | open
75081 | FPITF | IT2200107 | IT2200107 - GENVISION PLATFORM MODERNIZATION | 343.99 |  | 343.99 |  |  | 343.99 | 24569 | -24225.01 | 2022-11-04 10:49 | 2025-05-28 | 2023-12-01 | open
75082 | FPITF | IT2200107 | IT2200107 - GENVISION PLATFORM MODERNIZATION | 254.31 |  | 254.31 |  |  | 254.31 | 18388 | -18133.69 | 2022-11-04 10:57 | 2025-05-28 | 2023-12-01 | open
75082 | WDC00087 | WDC00087X | WDC00087X - REPLACE RO PUMP | 6835.1 |  | 6835.1 |  |  | 6835.1 | 218251.33 | -211416.23 | 2023-02-07 11:39 | 2025-08-31 | 2023-12-01 | open
75082 | WG047C | CWG047C | CWG047C - WGS GENERAL EQUIPMENT | 12852.95 |  | 12852.95 |  |  | 406144.67 | 395167.47 | 10977.2 | 2005-08-28 | 2030-12-30 | 2008-07-01 | open
75084 | 20090041A | MX5254705 | MX5254705 - 20090041A: KENTON 41 K84-242 INSTA | 77186.93 |  | 77186.93 |  |  | 78549.71 | 48874.89 | 29674.82 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20090041A | MX5254707 | MX5254707 - 20090041A: KENTON 41 K84-378 INSTA | 74380.13 |  | 74380.13 |  |  | 76197.85 | 46271.61 | 29926.24 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20090041A | MX5254708 | MX5254708 - 20090041A: KENTON 41 KNK-1583 INST | 72341.64 |  | 72341.64 |  |  | 73663.65 | 46394.69 | 27268.96 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20420044A | MX7372054 | MX7372054 - 20420044A: CONSTANCE 44 21BN-635 I | 8212.97 |  | 8212.97 |  |  | 78215.39 | 43253.26 | 34962.13 | 2021-10-22 09:12 | 2025-03-13 | 2021-10-01 | open
75084 | 20420044A | MX7372055 | MX7372055 - 0420044A: CONSTANCE 44 21BN-625 INS | 3174.28 |  | 3174.28 |  |  | 53554.26 | 44205.38 | 9348.88 | 2021-10-22 09:12 | 2025-03-13 | 2021-12-01 | open
75084 | 20420044A | MX7372056 | MX7372056 - 0420044A: CONSTANCE 44 21BN-396 INS | 6110.37 |  | 6110.37 |  |  | 56146.91 | 44441.08 | 11705.83 | 2021-10-22 09:12 | 2025-03-13 | 2021-10-01 | open
75084 | 20420044A | MX7372057 | MX7372057 - 0420044A: CONSTANCE 44 21BN-387 INS | 4953.63 |  | 4953.63 |  |  | 56015.85 | 45284.9 | 10730.95 | 2022-02-09 18:01 | 2025-03-13 | 2022-04-01 | open
75084 | 20420044A | MX7372058 | MX7372058 - 0420044A: CONSTANCE 44 BNK-6125 REP | 47.71 |  | 47.71 |  |  | 881.71 | 228.31 | 653.4 | 2021-10-22 09:12 | 2025-03-13 | 2022-06-01 | open
75084 | 20550043A | K2055SURK | K2055SURK - SUB OPT - SUR - DONALDSON - 2055 | 1511.99 |  | 1511.99 |  |  | 31331.58 | 0 | 31331.58 | 2021-05-20 09:31 | 2024-12-31 | 2021-11-01 | open
75084 | 20550043A | MX3999738 | MX3999738 - SUB OPT - DONALDSON 43 CVG SOUTH RE | 2405590.33 |  | 2405590.33 |  |  | 3110818.81 | 858671.15 | 2252147.66 | 2022-02-24 18:01 | 2025-03-13 | 2022-02-01 | open
75084 | 20550043A | MX5291241 | MX5291241 - SUB OPT - DONALDSON 43 NC SWITCH - | 661.89 |  | 661.89 |  |  | 12238.65 | 7347.08 | 4891.57 | 2022-05-31 14:01 | 2025-01-29 | 2022-08-01 | open
75084 | 20550043A | MX5820950 | MX5820950 - SUB OPT -TRANSFORMER UG THREE PHASE | 30965.61 |  | 30965.61 |  |  | 32092.37 | 18503.79 | 13588.58 | 2022-09-09 10:01 | 2025-03-13 | 2022-09-01 | open
75084 | 20550043A | MX5999267 | MX5999267 - SUB OPT - AUTOMATED SWITCHGEAR (WES | 187299.76 |  | 187299.76 |  |  | 187299.76 | 140064.2 | 47235.56 | 2022-09-12 14:01 | 2025-03-13 | 2023-12-01 | open
75084 | 20550043A | MX5999394 | MX5999394 - SUB OPT - AUTOMATED SWITCHGEAR (EAS | 189309.44 |  | 189309.44 |  |  | 189309.44 | 123212.71 | 66096.73 | 2022-10-03 10:01 | 2025-03-13 | 2023-12-01 | open
75084 | 20550043A | MX7372041 | MX7372041 - 0550043A: DONALDSON 43 21BN-302 REM | 4810.29 |  | 4810.29 |  |  | 49477.96 | 38388.05 | 11089.91 | 2021-10-22 09:12 | 2025-03-13 | 2021-10-01 | open
75084 | 20550043A | MX9919684 | MX9919684 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1261.89 |  | 1261.89 |  |  | 17305.23 | 14257.76 | 3047.47 | 2021-08-10 10:02 | 2025-03-13 | 2021-08-01 | open
75084 | 20550043A | MX9919685 | MX9919685 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1883.37 |  | 1883.37 |  |  | 20658.32 | 17251.93 | 3406.39 | 2021-08-10 10:02 | 2025-03-13 | 2021-08-01 | open
75084 | 20550044A | MX0002132 | MX0002132 - SUB OPT 2022 TUG 25994114 N TALBOT | 27001.77 |  | 27001.77 |  |  | 28555.77 | 11299.74 | 17256.03 | 2022-02-03 14:01 | 2025-03-13 | 2022-05-01 | open
75084 | 20550044A | MX0002133 | MX0002133 - SUB OPT 2022 TUG 25994114 N TALBOT | 202293.13 |  | 202293.13 |  |  | 281526.53 | 287654.23 | -6127.7 | 2022-02-03 10:02 | 2025-03-13 | 2022-02-01 | open
75084 | 20550044A | MX0002134 | MX0002134 - SUB OPT 2022 TUG 26062514 N TALBOT | 241642.02 |  | 241642.02 |  |  | 306394.2 | 156777.97 | 149616.23 | 2022-02-03 14:01 | 2025-03-13 | 2022-05-01 | open
75084 | 20550044A | MX1473561 | MX1473561 - 0550044A: DONALDSON 44 26BN-1308 RE | 5278.84 |  | 5278.84 |  |  | 64140.95 | 45686.85 | 18454.1 | 2021-10-21 14:01 | 2025-03-13 | 2021-12-01 | open
75084 | 20550044A | MX5821049 | MX5821049 - SUB OPT -TRANSFORMER UG 3-PHASE END | 50189.93 |  | 50189.93 |  |  | 52021.51 | 25666.49 | 26355.02 | 2022-09-09 10:01 | 2025-03-13 | 2022-09-01 | open
75084 | 20550044A | MX9919686 | MX9919686 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1184.84 |  | 1184.84 |  |  | 15173.6 | 18161.63 | -2988.03 | 2021-09-28 14:02 | 2025-03-13 | 2022-10-01 | open
75084 | 20700041A | MX5254699 | MX5254699 - 20700041A: CRESCENT 41 K84-49 INST | 26455.84 |  | 26455.84 |  |  | 58395.73 | 49684.85 | 8710.88 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700041A | MX5821149 | MX5821149 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 65.06 |  | 65.06 |  |  | 1203.12 | 27383.22 | -26180.1 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700041A | MX5821151 | MX5821151 - SUB OPT-TRANSFORMER UG 3-PHASE END | -60.25 |  | -60.25 |  |  | 215.16 | 329.87 | -114.71 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700041A | MX5821349 | MX5821349 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 193.3 |  | 193.3 |  |  | 954.07 | 20791.11 | -19837.04 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700041A | V2070HAZK | V2070HAZK - SUB OPT - HAZ - CRESCENT - 0041 | 39470.91 |  | 39470.91 |  |  | 39470.91 | 0 | 39470.91 | 2022-10-24 11:34 | 2025-03-31 | 2023-12-01 | open
75084 | 20700041A | V2070REMK | V2070REMK - SUB OPT - REM - CRESCENT - 0041 | 991.64 |  | 991.64 |  |  | 991.64 | 0 | 991.64 | 2022-10-24 12:00 | 2025-03-31 | 2023-12-01 | open
75084 | 20700043A | MX5254701 | MX5254701 - 20700043A: CRESCENT 43 KNK-2979 IN | 57913.68 |  | 57913.68 |  |  | 59076.09 | 45553.52 | 13522.57 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5254702 | MX5254702 - 20700043A: CRESCENT 43 KNK-4875 IN | 41712.67 |  | 41712.67 |  |  | 52254.8 | 39758.75 | 12496.05 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5254704 | MX5254704 - 20700043A: CRESCENT 43 K73-477 INS | 69205.7 |  | 69205.7 |  |  | 79419.56 | 45415.87 | 34003.69 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5254743 | MX5254743 - 20700043A: CRESCENT 43 K83-332 REM | 43310.99 |  | 43310.99 |  |  | 54203.72 | 42896.55 | 11307.17 | 2022-06-01 14:01 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5821155 | MX5821155 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 253.02 |  | 253.02 |  |  | 2365.48 | 22543.76 | -20178.28 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5821163 | MX5821163 - SUB OPT-TRANSFORMER UG 3-PHASE END | 23350.56 |  | 23350.56 |  |  | 24799.88 | 20303.86 | 4496.02 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MX5821165 | MX5821165 - SUB OPT-TRANSFORMER UG 3-PHASE END | 75.75 |  | 75.75 |  |  | 1400.49 | 21932.73 | -20532.24 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700043A | MXA821161 | MXA821161 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 83.46 |  | 83.46 |  |  | 1543.23 | 28071.42 | -26528.19 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821167 | MX5821167 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 273.98 |  | 273.98 |  |  | 2917.95 | 26237.78 | -23319.83 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821168 | MX5821168 - SUB OPT-TRANSFORMER UG 3-PHASE END | 24952.6 |  | 24952.6 |  |  | 27957.41 | 20303.86 | 7653.55 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821171 | MX5821171 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 103.81 |  | 103.81 |  |  | 1919.42 | 18328.29 | -16408.87 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700044A | MX5821182 | MX5821182 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 272.3 |  | 272.3 |  |  | 1167.83 | 19039.09 | -17871.26 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20700044A | MX5821185 | MX5821185 - TBC SUB OPT-TRANSFORMER UG 3-PHASE | 142.09 |  | 142.09 |  |  | 2626.83 | 30090.26 | -27463.43 | 2022-08-15 10:03 | 2025-07-29 | 2022-09-01 | open
75084 | 20700045A | MX5254714 | MX5254714 - 20700045A: CRESCENT 45 K92-315 INST | 69274.75 |  | 69274.75 |  |  | 70679.38 | 48778.18 | 21901.2 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20700045A | MX5254717 | MX5254717 - 20700045A: CRESCENT 45 K92-29 INSTA | 79665.21 |  | 79665.21 |  |  | 81501.9 | 52757.22 | 28744.68 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 20700045A | MX5254718 | MX5254718 - 20700045A: CRESCENT 45 K92-191 INS | 90378.73 |  | 90378.73 |  |  | 91802.98 | 51151.19 | 40651.79 | 2022-11-15 18:02 | 2025-07-29 | 2022-11-01 | open
75084 | 20700045A | MX5821188 | MX5821188 - SUB OPT-TRANSFORMER UG 3-PHASE END | 24362.86 |  | 24362.86 |  |  | 25207.09 | 19788.51 | 5418.58 | 2022-08-15 10:03 | 2025-07-29 | 2022-10-01 | open
75084 | 20780041A | KK0078S22 | KK0078S22 - SUB OPT - SUR - AUGUSTINE - 78 | 14698.34 |  | 14698.34 |  |  | 14698.34 | 0 | 14698.34 | 2022-10-28 08:28 | 2025-12-31 | 2023-12-01 | open
75084 | 20780041A | MX6180900 | MX6180900 - 20780041A: AUGUSTINE 41 K60-222 REM | 63403.03 |  | 63403.03 |  |  | 63430.02 | 56196.11 | 7233.91 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180901 | MX6180901 - 20780041A: AUGUSTINE 41 K60-238 NEW | 56825.1 |  | 56825.1 |  |  | 56852.09 | 55470.29 | 1381.8 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180906 | MX6180906 - 20780041A: AUGUSTINE 41 K60-39 NEW | 56518.87 |  | 56518.87 |  |  | 56580.95 | 50416.66 | 6164.29 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180910 | MX6180910 - 20780041A: AUGUSTINE 41 K71-59 NEW | 47598.92 |  | 47598.92 |  |  | 47610.81 | 42733.45 | 4877.36 | 2022-09-22 14:01 | 2025-08-28 | 2022-12-01 | open
75084 | 20780041A | MX6180911 | MX6180911 - 20780041A: AUGUSTINE 41 K70-258 NEW | 59900.23 |  | 59900.23 |  |  | 59927.22 | 45077.17 | 14850.05 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180912 | MX6180912 - 20780041A: AUGUSTINE 41 K60-64 NEW | 63829.63 |  | 63829.63 |  |  | 63856.62 | 54242.46 | 9614.16 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180914 | MX6180914 - 20780041A: AUGUSTINE 41 K70-232 NEW | 69276.87 |  | 69276.87 |  |  | 69303.86 | 128047.72 | -58743.86 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180915 | MX6180915 - 20780041A: AUGUSTINE 41 K61-759 NEW | 60492.45 |  | 60492.45 |  |  | 60512.45 | 56338.64 | 4173.81 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6180918 | MX6180918 - 20780041A: AUGUSTINE 41 K60-204 NEW | 73331.98 |  | 73331.98 |  |  | 73363.87 | 51809.13 | 21554.74 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | MX6465684 | MX6465684 - SUB OPT- 20780041A- AUGUSTINE 41- S | 14540.95 |  | 14540.95 |  |  | 14540.95 | 267327.1 | -252786.15 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780041A | MX6518423 | MX6518423 - 20780041A: AUGUSTINE 41 K60-446 NEW | 55779.68 |  | 55779.68 |  |  | 55811.57 | 45977.76 | 9833.81 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780041A | V2078HAZK | V2078HAZK - SUB OPT - HAZ - AUGUSTINE - 0041 | 1077.34 |  | 1077.34 |  |  | 1077.34 | 0 | 1077.34 | 2022-10-24 11:28 | 2025-03-31 | 2023-12-01 | open
75084 | 20780041A | V2078REMK | V2078REMK - SUB OPT - REM - AUGUSTINE - 0041 | 5369.51 |  | 5369.51 |  |  | 5369.51 | 0 | 5369.51 | 2022-10-24 11:55 | 2025-03-31 | 2023-12-01 | open
75084 | 20780042A | MX6180916 | MX6180916 - 20780042A: AUGUSTINE 42 K52-147 NEW | 59052.2 |  | 59052.2 |  |  | 59072.2 | 62709.76 | -3637.56 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780043A | MX6200360 | MX6200360 - CAP UPGRADE, K52-1373, AUGUSTINE (7 | 1972.52 |  | 1972.52 |  |  | 1984.41 | 34509.15 | -32524.74 | 2022-09-09 10:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780043A | MX6451512 | MX6451512 - SUB OPT- 20780043A- AUGUSTINE 43- G | 5860.8 |  | 5860.8 |  |  | 5860.8 | 99303.03 | -93442.23 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780043A | MX6465585 | MX6465585 - SUB OPT- 20780043A- AUGUSTINE 43- S | 4760.95 |  | 4760.95 |  |  | 4760.95 | 36951.13 | -32190.18 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780044A | MX6180921 | MX6180921 - 20780044A: AUGUSTINE 44 K54-197 NEW | 55797.45 |  | 55797.45 |  |  | 55817.45 | 48482.38 | 7335.07 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6180924 | MX6180924 - 20780044A: AUGUSTINE 44 K54-776 NEW | 79680.4 |  | 79680.4 |  |  | 79700.4 | 66706.01 | 12994.39 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6180925 | MX6180925 - 20780044A: AUGUSTINE 44 BTW K54-300 | 61153.94 |  | 61153.94 |  |  | 61173.94 | 48963.37 | 12210.57 | 2022-09-22 14:01 | 2025-08-28 | 2022-12-01 | open
75084 | 20780044A | MX6180926 | MX6180926 - 20780044A: AUGUSTINE 44 K54-303 NEW | 55409.11 |  | 55409.11 |  |  | 55429.11 | 49795.43 | 5633.68 | 2022-09-22 14:01 | 2025-08-28 | 2022-12-01 | open
75084 | 20780044A | MX6180927 | MX6180927 - 20780044A: AUGUSTINE 44 K54-916 NEW | 66044.93 |  | 66044.93 |  |  | 66064.93 | 46339.94 | 19724.99 | 2022-09-22 14:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6200359 | MX6200359 - CAP UPGRADE, K54-27, AUGUSTINE (78) | 2013.9 |  | 2013.9 |  |  | 2049.57 | 30820.03 | -28770.46 | 2022-09-09 10:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780044A | MX6465474 | MX6465474 - SUB OPT- 20780044A- AUGUSTINE 44- S | 4027.15 |  | 4027.15 |  |  | 4027.15 | 43797.52 | -39770.37 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780045A | MX6200358 | MX6200358 - CAP UPGRADE, K52-1126, AUGUSTINE (7 | 2178.45 |  | 2178.45 |  |  | 2190.34 | 39674.52 | -37484.18 | 2022-09-09 10:01 | 2025-12-29 | 2022-12-01 | open
75084 | 20780045A | MX6465372 | MX6465372 - SUB OPT- 20780045A- AUGUSTINE 45- S | 1908.44 |  | 1908.44 |  |  | 1908.44 | 46493.46 | -44585.02 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX6453958 | MX6453958 - SUB OPT- 20780046A- AUGUSTINE 46- M | 18828.5 |  | 18828.5 |  |  | 18828.5 | 196195.52 | -177367.02 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX6465013 | MX6465013 - SUB OPT- 20780046A- AUGUSTINE 46- S | 28921.14 |  | 28921.14 |  |  | 28921.14 | 52251.63 | -23330.49 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX6497693 | MX6497693 - SUB OPT-20780046A- AUGUSTINE 46-PAR | 249.38 |  | 249.38 |  |  | 249.38 | 623651.47 | -623402.09 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX9353376 | MX9353376 - JTD - 20780046A: AUGUSTINE 46 K72-9 | 2290.76 |  | 2290.76 |  |  | 2290.76 | 47795.53 | -45504.77 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX9353377 | MX9353377 - JTD - 20780046A: AUGUSTINE 46 K72-2 | 2289.06 |  | 2289.06 |  |  | 2289.06 | 49892.36 | -47603.3 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX9353380 | MX9353380 - JTD - 20780046A: AUGUSTINE 46 K62-6 | 2173.18 |  | 2173.18 |  |  | 2173.18 | 54032.96 | -51859.78 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX9353383 | MX9353383 - JTD - 20780046A: AUGUSTINE 46 K62-7 | 2126.92 |  | 2126.92 |  |  | 2126.92 | 64140.35 | -62013.43 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX9353384 | MX9353384 - JTD - 20780046A: AUGUSTINE 46 BTWN | 1408.4 |  | 1408.4 |  |  | 1408.4 | 57988.67 | -56580.27 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MXA353386 | MXA353386 - JTD - 20780046A: AUGUSTINE 46 BTWN | 1911.41 |  | 1911.41 |  |  | 1911.41 | 48867.69 | -46956.28 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 21280041A | MX9353357 | MX9353357 - JTD - 21280041A: HANDS 41 14K-242 N | 2105.02 |  | 2105.02 |  |  | 2105.02 | 48168.93 | -46063.91 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280041A | MX9353358 | MX9353358 - JTD - 21280041A: HANDS 41 15K-163 N | 937.65 |  | 937.65 |  |  | 937.65 | 49981.32 | -49043.67 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280041A | MX9353364 | MX9353364 - JTD - 21280041A: HANDS 41 19K-32 NE | 2146.29 |  | 2146.29 |  |  | 2146.29 | 49258.44 | -47112.15 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280042A | MX9353398 | MX9353398 - JTD - 21280042A: HANDS 42 10K-797 N | 919.05 |  | 919.05 |  |  | 919.05 | 48078.46 | -47159.41 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280042A | MX9353399 | MX9353399 - JTD - 21280042A: HANDS 42 7K-492 NE | 1131.04 |  | 1131.04 |  |  | 1131.04 | 58077.86 | -56946.82 | 2023-06-08 10:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280042A | MX9353402 | MX9353402 - JTD - 21280042A: HANDS 42 K75-254 N | 466.11 |  | 466.11 |  |  | 466.11 | 50542.91 | -50076.8 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280043A | MX6327150 | MX6327150 - CAP UPGRADE,10K-451,HANDS (128) 128 | 1147.12 |  | 1147.12 |  |  | 1147.12 | 20557.86 | -19410.74 | 2023-06-08 10:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280044A | V2128HAZK | V2128HAZK - SUB OPT - HAZ - HANDS - 2128 | 16414.21 |  | 16414.21 |  |  | 16414.21 | 0 | 16414.21 | 2023-06-15 15:39 | 2026-03-31 | 2023-12-01 | open
75084 | 21280044A | V2128REMK | V2128REMK - SUB OPT - REM - HANDS - 2128 | 3983.58 |  | 3983.58 |  |  | 3983.58 | 0 | 3983.58 | 2023-06-15 15:47 | 2026-03-31 | 2023-12-01 | open
75084 | 21280045A | MX9353372 | MX9353372 - JTD - 21280045A: HANDS 45 KNK-5267 | 1633.31 |  | 1633.31 |  |  | 1633.31 | 56175.54 | -54542.23 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21280045A | MX9353374 | MX9353374 - JTD - 21280045A: HANDS 45 15K-188 N | 1409.29 |  | 1409.29 |  |  | 1409.29 | 47682.92 | -46273.63 | 2023-06-06 14:01 | 2025-02-27 | 2023-12-01 | open
75084 | 21320041A | MX6287625 | MX6287625 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1136.83 |  | 1136.83 |  |  | 1136.83 | 20935.44 | -19798.61 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320041A | MX6287635 | MX6287635 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1137.97 |  | 1137.97 |  |  | 1137.97 | 20995.68 | -19857.71 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320041A | MX6287643 | MX6287643 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1145.34 |  | 1145.34 |  |  | 1145.34 | 21409.77 | -20264.43 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320041A | MX9353370 | MX9353370 - JTD - 21320041A: COLD SPRING 41 43C | 2246.32 |  | 2246.32 |  |  | 2246.32 | 58819.72 | -56573.4 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320041A | MX9353371 | MX9353371 - JTD - 21320041A: COLD SPRING 41 39C | 1553.31 |  | 1553.31 |  |  | 1553.31 | 50903.11 | -49349.8 | 2023-06-05 14:01 | 2025-03-06 | 2023-12-01 | open
75084 | 21320041A | V2132REMK | V2132REMK - SUB OPT - REM - COLD SPRING - 2132 | 17389.09 |  | 17389.09 |  |  | 17389.09 | 0 | 17389.09 | 2023-08-28 17:07 | 2026-03-31 | 2023-12-01 | open
75084 | 21320042A | MX6207287 | MX6207287 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1145.14 |  | 1145.14 |  |  | 1145.14 | 21429.69 | -20284.55 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320042A | MX6287652 | MX6287652 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1041.58 |  | 1041.58 |  |  | 1041.58 | 32414.98 | -31373.4 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320042A | MX6287660 | MX6287660 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1165.92 |  | 1165.92 |  |  | 1165.92 | 21601.74 | -20435.82 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320042A | MX9353349 | MX9353349 - JTD - 21320042A: COLD SPRING 42 CAK | 16917.41 |  | 16917.41 |  |  | 16917.41 | 45244.96 | -28327.55 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320042A | MX9353351 | MX9353351 - JTD - 21320042A: COLD SPRING 42 36C | 1829.24 |  | 1829.24 |  |  | 1829.24 | 48051.61 | -46222.37 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320042A | MX9353352 | MX9353352 - JTD - 21320042A: COLD SPRING 42 36C | 17059.14 |  | 17059.14 |  |  | 17059.14 | 45843.09 | -28783.95 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320049A | MX0850305 | MX0850305 - JTD - 21320049A: COLD SPRING 49 36C | 981.02 |  | 981.02 |  |  | 981.02 | 53952.13 | -52971.11 | 2023-11-06 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320049A | MX6287677 | MX6287677 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1129.28 |  | 1129.28 |  |  | 1129.28 | 23519.88 | -22390.6 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320049A | MX6287686 | MX6287686 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1168.71 |  | 1168.71 |  |  | 1168.71 | 21421.96 | -20253.25 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320049A | MX9353366 | MX9353366 - JTD - 21320049A: COLD SPRING 49 36C | 920.02 |  | 920.02 |  |  | 920.02 | 61706.11 | -60786.09 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320049A | MX9353367 | MX9353367 - JTD - 21320049A: COLD SPRING 49 36C | 1364.31 |  | 1364.31 |  |  | 1364.31 | 58552.04 | -57187.73 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21320049A | MX9353368 | MX9353368 - JTD - 21320049A: COLD SPRING 49 39C | 882.94 |  | 882.94 |  |  | 882.94 | 58966.68 | -58083.74 | 2023-06-05 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21470041A | V2147HAZK | V2147HAZK - SUB OPT - HAZ - CLARYVILLE - 2147 | 103543.67 |  | 103543.67 |  |  | 103543.67 | 0 | 103543.67 | 2023-06-15 15:42 | 2026-03-31 | 2023-12-01 | open
75084 | 21470042A | MX9353345 | MX9353345 - JTD - 21470042A: CLARYVILLE 42 47CA | 15697.06 |  | 15697.06 |  |  | 15697.06 | 49110.89 | -33413.83 | 2023-06-14 18:01 | 2025-03-06 | 2023-12-01 | open
75084 | 21520041A | K2152SURK | K2152SURK - SUB OPT - SUR - HEBRON - 152 | 2101.37 |  | 2101.37 |  |  | 43353.65 | 0 | 43353.65 | 2021-05-20 11:22 | 2025-03-31 | 2022-02-01 | open
75084 | 21520041A | MX5254719 | MX5254719 - 21520041A: HEBRON 41 13BN-79 INSTAL | 67855.65 |  | 67855.65 |  |  | 68807.1 | 53783.36 | 15023.74 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254720 | MX5254720 - 21520041A: HEBRON 41 13BN-31 INSTAL | 69709.12 |  | 69709.12 |  |  | 70405.49 | 54720.38 | 15685.11 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254721 | MX5254721 - 21520041A: HEBRON 41 14BN-576 INSTA | 65067.25 |  | 65067.25 |  |  | 65763.62 | 52135.28 | 13628.34 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254722 | MX5254722 - 21520041A: HEBRON 41 14BN-618 INSTA | 70354.03 |  | 70354.03 |  |  | 70785.81 | 46384.27 | 24401.54 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX5254725 | MX5254725 - 21520041A: HEBRON 41 BNK-2081 INSTA | 65136.66 |  | 65136.66 |  |  | 65779.44 | 44227.55 | 21551.89 | 2022-06-02 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21520041A | MX7891218 | MX7891218 - SUB OPT -REPLACEMENT OF EXISTING RE | 309.5 |  | 309.5 |  |  | 5722.75 | 4505.46 | 1217.29 | 2021-10-20 14:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX1089667 | MX1089667 - SUB OPT HEBRON 42 RECO PART 1 - 215 | 35192.67 |  | 35192.67 |  |  | 85661.24 | 718305.23 | -632643.99 | 2021-11-02 10:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX1089713 | MX1089713 - SUB OPT HEBRON 42 RECO PT 2 - 21520 | 1003467.77 |  | 1003467.77 |  |  | 1037429.84 | 643727.99 | 393701.85 | 2021-11-02 10:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX1089758 | MX1089758 - SUB OPT HEBRON 42 RECO PART 1 - 215 | 140576.96 |  | 140576.96 |  |  | 670303.99 | 403119.11 | 267184.88 | 2021-11-02 10:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX7891191 | MX7891191 - SUB OPT -REPLACEMENT OF EXISTING RE | 347.03 |  | 347.03 |  |  | 6416.44 | 4968.19 | 1448.25 | 2021-10-20 14:02 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX7891216 | MX7891216 - SUB OPT -REPLACEMENT OF EXISTING RE | 321.31 |  | 321.31 |  |  | 5941.09 | 5005.02 | 936.07 | 2021-11-04 14:01 | 2025-05-29 | 2021-11-01 | open
75084 | 21520042A | MX8137212 | MX8137212 - SUB OPT -LINE PATROL NORMAL PRIORIT | 175.42 |  | 175.42 |  |  | 3243.7 | 1664.41 | 1579.29 | 2022-02-07 10:01 | 2025-05-29 | 2022-08-01 | open
75084 | 21520042A | MX9353348 | MX9353348 - JTD - 21520042A: HEBRON 42 7BN-12 N | 15807.83 |  | 15807.83 |  |  | 15807.83 | 48268.45 | -32460.62 | 2023-09-25 18:01 | 2025-05-29 | 2023-12-01 | open
75084 | 21990041A | MX5254732 | MX5254732 - 21990041A: RICHWOOD 41 BNK-8296 IN | 80597.55 |  | 80597.55 |  |  | 80700.16 | 55897.38 | 24802.78 | 2022-06-06 10:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990041A | MX6293612 | MX6293612 - SUB-OPT - TRANSFORMER RETROFIT RIC | 1488.18 |  | 1488.18 |  |  | 2585.76 | 15049.49 | -12463.73 | 2022-09-22 14:01 | 2025-02-28 | 2022-12-01 | open
75084 | 21990041A | V2199HAZK | V2199HAZK - SUB OPT - HAZ - RICHWOOD - 0041 | 3320.83 |  | 3320.83 |  |  | 3320.83 | 0 | 3320.83 | 2022-10-24 11:52 | 2025-03-31 | 2023-12-01 | open
75084 | 21990041A | V2199REMK | V2199REMK - SUB OPT - REM - RICHWOOD - 0041 | 13678.64 |  | 13678.64 |  |  | 13678.64 | 0 | 13678.64 | 2022-10-24 12:12 | 2025-03-31 | 2023-12-01 | open
75084 | 21990042A | MX2725026 | MX2725026 - CAP UPGRADE, 35BN-330, RICHWOOD (19 | 31166.63 |  | 31166.63 |  |  | 31178.51 | 29461.39 | 1717.12 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX2725027 | MX2725027 - CAP UPGRADE, 41BN-196, RICHWOOD (19 | 47371.21 |  | 47371.21 |  |  | 47412.18 | 19233.66 | 28178.52 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX5254734 | MX5254734 - 21990042A: RICHWOOD 42 36BN-343 IN | 52019.64 |  | 52019.64 |  |  | 52046.63 | 82506.84 | -30460.21 | 2022-06-06 10:01 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX5254737 | MX5254737 - 21990042A: RICHWOOD 42 36BN-313 IN | 74731.39 |  | 74731.39 |  |  | 74743.28 | 59573.72 | 15169.56 | 2022-06-06 10:01 | 2025-05-29 | 2022-12-01 | open
75084 | 21990042A | MX5352287 | MX5352287 - SUB OPT - 21990042A -RICHWOOD 44 ST | 59750.07 |  | 59750.07 |  |  | 59750.07 | 23936.03 | 35814.04 | 2022-06-07 14:01 | 2025-02-28 | 2023-12-01 | open
75084 | 21990042A | MX5352573 | MX5352573 - SUB OPT - 21990042A- RECLOSER - 41B | 14827.77 |  | 14827.77 |  |  | 15752.8 | 45552.6 | -29799.8 | 2022-06-07 14:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990042A | MX5821193 | MX5821193 - SUB OPT-TRANSFORMER UG 3-PHASE END | 1786.74 |  | 1786.74 |  |  | 4893.19 | 29369.17 | -24475.98 | 2022-08-16 14:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990042A | MX5821220 | MX5821220 - SUB OPT-TRANSFORMER UG 3-PHASE END | 43080.59 |  | 43080.59 |  |  | 44188.6 | 31326.88 | 12861.72 | 2022-08-24 10:10 | 2025-02-28 | 2022-09-01 | open
75084 | 21990043A | MX2725029 | MX2725029 - CAP UPGRADE, 41BN-38, RICHWOOD (199 | 9513.93 |  | 9513.93 |  |  | 9537.7 | 3148.35 | 6389.35 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990043A | MX2725030 | MX2725030 - CAP UPGRADE, BNK-4204, RICHWOOD (19 | 2054.94 |  | 2054.94 |  |  | 2078.71 | 13973.94 | -11895.23 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990043A | MX5353113 | MX5353113 - SUB OPT -21990043A - RECLOSER 41BN- | 70581.48 |  | 70581.48 |  |  | 71428.42 | 45749.7 | 25678.72 | 2022-06-07 14:01 | 2025-02-28 | 2022-11-01 | open
75084 | 21990043A | MX5971474 | MX5971474 - SUB OPT - 21990043A - RICHWOOD 43 - | 14184.99 |  | 14184.99 |  |  | 14939.64 | 49101.51 | -34161.87 | 2022-08-02 14:06 | 2025-02-28 | 2022-11-01 | open
75084 | 21990043A | MXA352205 | MXA352205 - SUB OPT - 21990043A - RICHWOOD 43 E | 28762.15 |  | 28762.15 |  |  | 28978.43 | 93915.68 | -64937.25 | 2022-06-07 14:01 | 2025-02-28 | 2022-12-01 | open
75084 | 22410042A | K2241SURK | K2241SURK - SUB OPT - SUR - FLORENCE - 241 | 2794.14 |  | 2794.14 |  |  | 56163.27 | 0 | 56163.27 | 2021-05-04 12:07 | 2024-12-31 | 2021-11-01 | open
75084 | 22430041A | MX5254711 | MX5254711 - 22430041A: VILLA 41 K84-96 INSTALL | 69709.26 |  | 69709.26 |  |  | 71147.05 | 49317.89 | 21829.16 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 22430041A | MX5254713 | MX5254713 - 22430041A: VILLA 41 K84-71 INSTALL | 55082.16 |  | 55082.16 |  |  | 56590.38 | 46249.42 | 10340.96 | 2022-06-01 18:01 | 2025-07-29 | 2022-11-01 | open
75084 | 22870042A | MX6327139 | MX6327139 - CAP UPGRADE,CAK-405,KENTUCKY UNIVER | 971.28 |  | 971.28 |  |  | 971.28 | 36730.97 | -35759.69 | 2023-06-05 14:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870042A | MX9353405 | MX9353405 - JTD - 22870042A: KENTUCKY UNIVERSIT | 490.28 |  | 490.28 |  |  | 490.28 | 58590.72 | -58100.44 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870042A | MX9353407 | MX9353407 - JTD - 22870042A: KENTUCKY UNIVERSIT | 453.68 |  | 453.68 |  |  | 453.68 | 59388.35 | -58934.67 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870042A | MX9353412 | MX9353412 - JTD - 22870042A: KENTUCKY UNIVERSIT | 477.46 |  | 477.46 |  |  | 477.46 | 49281.38 | -48803.92 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870042A | MX9353413 | MX9353413 - JTD - 22870042A: KENTUCKY UNIVERSIT | 900.12 |  | 900.12 |  |  | 900.12 | 49193.72 | -48293.6 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870042A | V2287REMK | V2287REMK - SUB OPT - REM - KENTUCKY UNIVERSITY | 8269.74 |  | 8269.74 |  |  | 8269.74 | 0 | 8269.74 | 2023-08-28 17:18 | 2026-03-31 | 2023-12-01 | open
75084 | 22870043A | MX9353404 | MX9353404 - JTD - 22870043A: KENTUCKY UNIVERSIT | 552.94 |  | 552.94 |  |  | 552.94 | 48624.24 | -48071.3 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22990041A | KK0299S22 | KK0299S22 - SUB OPT - SUR - DECORSEY - 299 | 5065.4 |  | 5065.4 |  |  | 5065.4 | 0 | 5065.4 | 2022-10-28 08:34 | 2024-12-31 | 2023-12-01 | open
75084 | 23040041A | MX0319569 | MX0319569 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1067.01 |  | 1067.01 |  |  | 15533.65 | 14762.51 | 771.14 | 2021-08-10 10:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX0319570 | MX0319570 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1227.12 |  | 1227.12 |  |  | 16799.63 | 16439.26 | 360.37 | 2021-08-10 10:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX0319571 | MX0319571 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1470.31 |  | 1470.31 |  |  | 17420.73 | 14384.29 | 3036.44 | 2021-08-10 10:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX0319572 | MX0319572 - SUB OPT -UPGRADE OF CAPACITORS BY A | 4226.79 |  | 4226.79 |  |  | 34535.45 | 21002.93 | 13532.52 | 2021-08-06 14:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040041A | MX1193729 | MX1193729 - SUB OPT - WHITE TOWER 41 RECO - 230 | 1211.79 |  | 1211.79 |  |  | 7313.84 | 133702.6 | -126388.76 | 2022-02-21 14:01 | 2025-05-29 | 2022-08-01 | open
75084 | 23040041A | MX5254738 | MX5254738 - 23040041A: WHITE TOWER 41 22K-172 | 67901.16 |  | 67901.16 |  |  | 67928.15 | 46046.05 | 21882.1 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040041A | MX5254739 | MX5254739 - 23040041A: WHITE TOWER 41 15K-316 | 70287.8 |  | 70287.8 |  |  | 70314.79 | 47655.21 | 22659.58 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040041A | MX7891201 | MX7891201 - SUB OP 2022 RECL RPL, KNK-5687, WHI | 791.61 |  | 791.61 |  |  | 14636.39 | 19631.86 | -4995.47 | 2022-01-03 10:01 | 2025-05-29 | 2022-01-01 | open
75084 | 23040041A | MX8137248 | MX8137248 - SUB OPT -LINE PATROL NORMAL PRIORIT | 375.1 |  | 375.1 |  |  | 6935.73 | 5959.06 | 976.67 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 23040041A | MX8137256 | MX8137256 - SUB OPT -LINE PATROL NORMAL PRIORIT | 245.32 |  | 245.32 |  |  | 4535.63 | 1762.16 | 2773.47 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 23040041A | MX8137265 | MX8137265 - SUB OPT -LINE PATROL NORMAL PRIORIT | 221.86 |  | 221.86 |  |  | 4102.13 | 4518.51 | -416.38 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 23040042A | MX0319573 | MX0319573 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1493.09 |  | 1493.09 |  |  | 22178.52 | 16539.05 | 5639.47 | 2021-08-06 14:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040043A | MX0319574 | MX0319574 - SUB OPT -UPGRADE OF CAPACITORS BY A | 1215.02 |  | 1215.02 |  |  | 16289.95 | 14639.02 | 1650.93 | 2021-08-06 14:02 | 2025-05-29 | 2021-08-01 | open
75084 | 23040043A | MX5254741 | MX5254741 - 23040043A: WHITE TOWER 43 19K-776 | 85385.46 |  | 85385.46 |  |  | 85412.45 | 46320.4 | 39092.05 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040043A | MX5254742 | MX5254742 - 23040043A: WHITE TOWER 43 15K-702 | 74354.39 |  | 74354.39 |  |  | 74366.28 | 56540.68 | 17825.6 | 2022-06-07 14:01 | 2025-05-29 | 2022-12-01 | open
75084 | 23040043A | MX8137236 | MX8137236 - SUB OPT -LINE PATROL NORMAL PRIORIT | 322.58 |  | 322.58 |  |  | 5964.6 | 5035.07 | 929.53 | 2022-02-21 14:01 | 2025-05-29 | 2022-09-01 | open
75084 | 4000156F | 04000156 | 04000156 - DEE EAM NEXTGEN GIS | 239960.28 |  | 239960.28 |  |  | 239960.28 | 1132805 | -892844.72 | 2022-12-17 12:25 | 2026-12-31 | 2023-12-01 | open
75084 | 75084 | FERC88123 | FERC88123 - FERC ORDER 881 - DEK | 633.23 |  | 633.23 |  |  | 633.23 | 6788 | -6154.77 | 2023-12-06 14:57 | 2025-12-31 | 2023-12-01 | open
75084 | 75084 | KMTRNOS | KMTRNOS - KY METERS-NOT AMI-SELFCONTAINED | 116485.72 |  | 116485.72 |  |  | 303907.27 | 5461.31 | 298445.96 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01 | open
75084 | 75084 | KMTRNOT | KMTRNOT - KY - METERS-NOT AMI- T RATED | 176092.9 |  | 176092.9 |  |  | 509971.34 | 520.12 | 509451.22 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01 | open
75084 | 75084 | KMTROWR2 | KMTROWR2 - KY SALVAGE CREDIT FOR METERS | -1520.15 |  | -1520.15 |  |  | -49243.73 | 0 | -49243.73 | 2022-04-28 10:56 | 2026-03-31 | 2022-05-01 | open
75084 | 75084 | KMTROWS | KMTROWS - KY - METERS-AMI-SELF CONTAINED | 767231.04 |  | 767231.04 |  |  | 3030906.14 | 99863.96 | 2931042.18 | 2018-11-02 18:04 | 2026-03-31 | 2018-12-01 | open
75084 | 75084 | KMTROWT | KMTROWT - KY - METERS-AMI-T RATED | 233292.68 |  | 233292.68 |  |  | 1352608.34 | 11182.68 | 1341425.66 | 2018-11-02 18:04 | 2026-03-31 | 2019-01-01 | open
75084 | 75084 | TPO000215 | TPO000215 - DEK POLEFOREMAN APPLICATION | 35440.89 |  | 35440.89 |  |  | 35440.89 | 49131.36 | -13690.47 | 2023-12-15 12:16 | 2026-03-31 | 2023-12-01 | open
75084 | 75084HW | KCOU | KCOU - MAKE READY OTHER UTIL ATTACHMENTS | -6711.49 |  | -6711.49 |  |  | 582702.99 | 0 | 582702.99 | 2017-03-24 15:14 | 2067-12-31 | 2017-08-01 | open
75084 | 75084HW | KCRFN | KCRFN - CUSTOMER REQUESTED MODS NONREIMB | 13579.6 |  | 13579.6 |  |  | 239928.23 | 0 | 239928.23 | 2017-03-24 15:19 | 2067-12-31 | 2018-06-01 | open
75084 | 75084HW | KCRFR | KCRFR - CUSTOMER REQUESTED MODS REIMB | -28423.67 |  | -28423.67 |  |  | -21517.43 | 0 | -21517.43 | 2017-03-24 15:21 | 2067-12-31 | 2017-11-01 | open
75084 | 75084HW | KHWYN | KHWYN - HIGHWAY RELOCATIONS NONREIMB | 419429.64 |  | 419429.64 |  |  | 1639483 | 0 | 1639483 | 2017-03-24 15:25 | 2067-12-31 | 2017-10-01 | open
75084 | 75084HW | KHWYR | KHWYR - HIGHWAY RELOCATIONS REIMB | 14204.39 |  | 14204.39 |  |  | 120388.55 | 0 | 120388.55 | 2017-03-24 15:28 | 2067-12-31 | 2017-08-01 | open
75084 | 75084HW | KMODC | KMODC - OTHER CAPITAL MODIFICATIONS | 85200.79 |  | 85200.79 |  |  | 260205.7 | 0 | 260205.7 | 2017-03-24 15:33 | 2067-12-31 | 2018-07-01 | open
75084 | 75084HW | MX0867359 | MX0867359 - RELOCATION HIGHWAY DOT SPECIFIC PRO | -18212.66 |  | -18212.66 |  |  | -114780.82 | 67314.36 | -182095.18 | 2022-09-22 14:01 | 2026-02-26 | 2022-10-01 | open
75084 | 75084HW | MX5322977 | MX5322977 - EMERGENT CVG-7 RELOCATION - LIMABUR | 1675.33 |  | 1675.33 |  |  | 31544.86 | 311090.78 | -279545.92 | 2022-06-02 14:01 | 2025-05-29 | 2022-07-01 | open
75084 | 75084IK | KCIPOH | KCIPOH - C&I CUSTOMER ADDITIONS OH | 732921.41 |  | 732921.41 |  |  | 6114438.34 | 0 | 6114438.34 | 2017-03-24 15:40 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KCIUPOH | KCIUPOH - C&I CUSTOMER UPGRADE OH | 120079.53 |  | 120079.53 |  |  | 819583.03 | 0 | 819583.03 | 2017-03-24 15:42 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCDT | KCMCDT - NON-EMERG DTUG CORRECTIVE REPLACE | 16289.9 |  | 16289.9 |  |  | 27307.6 | 0 | 27307.6 | 2017-03-24 15:45 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KCMCEDT | KCMCEDT - EMERG DTUG CORRECTIVE REPLACEMENTS | 17453.9 |  | 17453.9 |  |  | 241092.16 | 0 | 241092.16 | 2017-03-24 15:47 | 2067-12-31 | 2018-06-01 | open
75084 | 75084IK | KCMCEOH | KCMCEOH - EMERGENCY OH CORRECTIVE REPLACEMENT | 401643.16 |  | 401643.16 |  |  | 1837165.32 | 0 | 1837165.32 | 2017-03-24 15:50 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCEUG | KCMCEUG - EMERGENCY UG CORRECTIVE REPLACEMENT | 86476.37 |  | 86476.37 |  |  | 683971.85 | 0 | 683971.85 | 2017-03-24 15:52 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCOH | KCMCOH - NON-EMERGENCY OH CORRECTIVE REPLACE | 166723.5 |  | 166723.5 |  |  | 459125.84 | 0 | 459125.84 | 2017-03-24 15:55 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KCMCUG | KCMCUG - NON-EMERGENCY UG CORRECTIVE REPL | 88879.36 |  | 88879.36 |  |  | 291541.84 | 0 | 291541.84 | 2017-03-27 11:51 | 2067-12-31 | 2017-12-01 | open
75084 | 75084IK | KDLSCM | KDLSCM - CD - OH DLINE SWITCH REPL REACTIVE | 2346.68 |  | 2346.68 |  |  | 7491.38 | 0 | 7491.38 | 2019-03-21 16:06 | 2068-03-31 | 2019-07-01 | open
75084 | 75084IK | KHYDRCM | KHYDRCM - CD - HYDRO RECL REPL REACTIVE | 6570.56 |  | 6570.56 |  |  | 6570.56 | 0 | 6570.56 | 2019-03-21 15:49 | 2068-03-31 | 2023-12-01 | open
75084 | 75084IK | KLPF | KLPF - LINE PATROL FOLLOW UP | 104097.49 |  | 104097.49 |  |  | 1764683.41 | 0 | 1764683.41 | 2017-03-27 12:06 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KOUTOH | KOUTOH - OUTAGE RELATED OH CAP REPLACEMENTS | 516628.41 |  | 516628.41 |  |  | 3020829.45 | 0 | 3020829.45 | 2017-03-27 12:13 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KOUTUG | KOUTUG - OUTAGE RELATED UG CAP REPLACEMENTS | 569717.84 |  | 569717.84 |  |  | 3908791.57 | 0 | 3908791.57 | 2017-03-27 12:15 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KPDMCAP | KPDMCAP - PUBLIC DAMAGE OH CAPITAL REPLACEMEN | 196287.48 |  | 196287.48 |  |  | 1278621.47 | 0 | 1278621.47 | 2017-03-27 12:17 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KPDMCPU | KPDMCPU - PUBLIC DAMAGE UG CAPITAL REPLACEMNT | -54920.41 |  | -54920.41 |  |  | 552836.67 | 0 | 552836.67 | 2017-03-27 12:20 | 2067-12-31 | 2017-09-01 | open
75084 | 75084IK | KPOLCM | KPOLCM - REACTIVE POLE REPLACEMENTS | 600359.05 |  | 600359.05 |  |  | 2744526.51 | 0 | 2744526.51 | 2017-03-27 12:23 | 2067-12-31 | 2017-09-01 | open
75084 | 75084IK | KPOLIR | KPOLIR - NON EMERG POLE REPLACE INSP BASED | 927021.84 |  | 927021.84 |  |  | 3554763.89 | 0 | 3554763.89 | 2017-03-27 12:27 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KPOLOTH | KPOLOTH - OTH UOP REPL FOUND THRU POLE INSP | 197.39 |  | 197.39 |  |  | 19524.33 | 0 | 19524.33 | 2017-03-27 12:30 | 2067-12-31 | 2021-07-01 | open
75084 | 75084IK | KPOLRNF | KPOLRNF - POLE REINFORCEMENTS | 8459.13 |  | 8459.13 |  |  | 19205.16 | 0 | 19205.16 | 2017-03-27 12:32 | 2067-12-31 | 2020-10-01 | open
75084 | 75084IK | KPPL | KPPL - STUB POLE REMOVAL ONLY | 6782.63 |  | 6782.63 |  |  | 50608.72 | 0 | 50608.72 | 2017-03-29 09:53 | 2067-12-31 | 2017-12-01 | open
75084 | 75084IK | KRCR | KRCR - CAPACITOR REPLACEMENTS & ASSOC UOP | 96494.66 |  | 96494.66 |  |  | 714481.24 | 0 | 714481.24 | 2017-03-27 12:37 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRIOTCO | KRIOTCO - OH IMPRVMNT FROM PQRI OUTAGE INVEST | 127725.13 |  | 127725.13 |  |  | 576272.52 | 0 | 576272.52 | 2017-03-27 12:51 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRIOTCU | KRIOTCU - UG IMPRVMNT FROM PQRI OUTAGE INVEST | 16122.91 |  | 16122.91 |  |  | 81150.13 | 0 | 81150.13 | 2017-03-27 12:54 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRMOH | KRMOH - RESIDENTIAL CUST ADDS MULTI FAM OH | 94517.5 |  | 94517.5 |  |  | 276059.01 | 0 | 276059.01 | 2017-03-27 13:07 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRNUIF | KRNUIF - REMOVAL OF NON-UTILIZED INFRASTRUCT | 84.46 |  | 84.46 |  |  | 11017.53 | 0 | 11017.53 | 2017-12-13 12:01 | 2068-03-31 | 2020-07-01 | open
75084 | 75084IK | KROWCONS | KROWCONS - DEK CONSTRUCT EASEMENT/ROW BLANKET | 275968.6 |  | 275968.6 |  |  | 541403.05 | 3600000 | -3058596.95 | 2021-04-26 22:06 | 2036-10-17 | 2022-04-01 | open
75084 | 75084IK | KROWMAJ | KROWMAJ - DEK MAJ PROJ EASEMENT/ROW BLANKET | 20872.73 |  | 20872.73 |  |  | 70307.53 | 3600000 | -3529692.47 | 2021-04-26 22:20 | 2036-10-17 | 2022-04-01 | open
75084 | 75084IK | KRRR | KRRR - RECLOSER REPLACEMENTS | 6766.97 |  | 6766.97 |  |  | 1201772.61 | 0 | 1201772.61 | 2017-03-27 13:10 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRRRCM | KRRRCM - CD - RECL ELEC REPL - REACTIVE | 143542.25 |  | 143542.25 |  |  | 515727.15 | 0 | 515727.15 | 2019-03-21 15:37 | 2068-03-31 | 2019-06-01 | open
75084 | 75084IK | KRSOH | KRSOH - RESIDENTIAL CUST ADDS SINGLE FAM OH | 1298352.8 |  | 1298352.8 |  |  | 7355802.93 | 0 | 7355802.93 | 2017-03-27 13:15 | 2067-12-31 | 2017-08-01 | open
75084 | 75084IK | KRTP1PH | KRTP1PH - SINGLE PH TRANSFORMER REPLAC LEAKER | 22451.64 |  | 22451.64 |  |  | 96285.17 | 0 | 96285.17 | 2017-03-27 13:17 | 2067-12-31 | 2018-07-01 | open
75084 | 75084IK | KRTP3PH | KRTP3PH - THREE PH TRANSFORMER REPLACE LEAKER | 54959.21 |  | 54959.21 |  |  | 314879.53 | 0 | 314879.53 | 2017-03-27 13:19 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KRTR1PH | KRTR1PH - SINGLE PH TRANSFORMER REPLACE DRY | 19682.59 |  | 19682.59 |  |  | 99014.49 | 0 | 99014.49 | 2017-03-27 13:23 | 2067-12-31 | 2017-09-01 | open
75084 | 75084IK | KRTR3PH | KRTR3PH - THREE PH TRANSFORMER REPLACE DRY | 49998.9 |  | 49998.9 |  |  | 164456.26 | 0 | 164456.26 | 2017-03-27 13:26 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRTXO | KRTXO - OVERHEAD TRANSFORMER REPLACEMENT | 117690.02 |  | 117690.02 |  |  | 405894.97 | 0 | 405894.97 | 2017-03-27 13:28 | 2067-12-31 | 2017-10-01 | open
75084 | 75084IK | KRUCLGCM | KRUCLGCM - CD - UG CABLE REPL LG REACTIVE | 16712.13 |  | 16712.13 |  |  | 59820.71 | 0 | 59820.71 | 2019-03-21 16:28 | 2068-03-31 | 2019-09-01 | open
75084 | 75084IK | KRUCSEC | KRUCSEC - UG SEC/SERVICE CABLE REPLACEMENT | 166932.13 |  | 166932.13 |  |  | 640292.66 | 0 | 640292.66 | 2017-03-27 13:33 | 2067-12-31 | 2018-04-01 | open
75084 | 75084IK | KRUCSMCM | KRUCSMCM - CD - UG CABLE REPL REACTIVE | 363562.81 |  | 363562.81 |  |  | 1684436.35 | 0 | 1684436.35 | 2019-03-21 16:34 | 2068-03-31 | 2019-06-01 | open
75084 | 75084IK | KRUPOH | KRUPOH - RESIDENTIAL CUSTOMER UPGRADE OH | 189824.65 |  | 189824.65 |  |  | 1671399.23 | 0 | 1671399.23 | 2017-03-27 14:26 | 2067-12-31 | 2017-11-01 | open
75084 | 75084IK | KRXR | KRXR - TRANSFORMER RETROFIT | 781.04 |  | 781.04 |  |  | 438156.02 | 0 | 438156.02 | 2017-03-27 14:28 | 2067-12-31 | 2018-01-01 | open
75084 | 75084IK | KSMF | KSMF - CAPITAL REPLACEMENTS FROM SMEI INSP | 43333.26 |  | 43333.26 |  |  | 69806.11 | 0 | 69806.11 | 2017-03-27 14:35 | 2067-12-31 | 2018-03-01 | open
75084 | 75084IK | MX4279989 | MX4279989 - WHISTLER COVE - INFRASTRUCTURE WORK | 3.32 |  | 3.32 |  |  | 813.45 | 268291.37 | -267477.92 | 2022-04-21 18:02 | 2025-09-11 | 2022-04-01 | open
75084 | 75084IK | MX9369394 | MX9369394 - DPZ - SILVER GROVE (62) 6241 | 21143.49 |  | 21143.49 |  |  | 21143.49 | 122324.79 | -101181.3 | 2023-05-22 10:02 | 2025-07-29 | 2023-12-01 | open
75084 | 75084IK | MX9441824 | MX9441824 - DETERIORATED CONDUCTOR - WILDER 46 | 4007.61 |  | 4007.61 |  |  | 4007.61 | 101569.34 | -97561.73 | 2023-06-14 18:01 | 2030-07-29 | 2023-12-01 | open
75084 | 75084IK | MX9442677 | MX9442677 - DECLARED PROTECTION ZONE - BEAVER 4 | 13175.38 |  | 13175.38 |  |  | 13175.38 | 281178.68 | -268003.3 | 2023-06-15 10:01 | 2025-10-29 | 2023-12-01 | open
75084 | 75084IK | MX9660088 | MX9660088 - DPZ - SILVER GROVE (62) 6241 PART 2 | 17797.61 |  | 17797.61 |  |  | 17797.61 | 129301.59 | -111503.98 | 2023-06-14 14:01 | 2025-09-10 | 2023-12-01 | open
75084 | 75084IK | MX9660090 | MX9660090 - DPZ - SILVER GROVE (62) 6241 PART 3 | 7994.25 |  | 7994.25 |  |  | 7994.25 | 107779.86 | -99785.61 | 2023-06-14 14:01 | 2025-11-10 | 2023-12-01 | open
75084 | 75084IK | MX9726813 | MX9726813 - DECLARED PROTECTION ZONE - BEAVER 4 | 5318.63 |  | 5318.63 |  |  | 5318.63 | 277790.95 | -272472.32 | 2023-06-15 10:01 | 2025-12-29 | 2023-12-01 | open
75084 | 75084IK | MX9918857 | MX9918857 - STEFFEN RD-POLE REPLACEMENTS - NON- | 799.52 |  | 799.52 |  |  | 55751.45 | 52484.49 | 3266.96 | 2021-03-18 14:02 | 2024-05-30 | 2021-03-01 | open
75084 | 75084IL | KALRPL | KALRPL - AREA LIGHT REPLACEMENTS | 91243.41 |  | 91243.41 |  |  | 294505.61 | 0 | 294505.61 | 2017-03-28 09:23 | 2067-04-01 | 2017-10-01 | open
75084 | 75084IL | KCAL | KCAL - AREA LIGHT NEW INSTALLS | 997346.32 |  | 997346.32 |  |  | 2522316.74 | 0 | 2522316.74 | 2017-03-28 09:30 | 2067-04-01 | 2017-08-01 | open
75084 | 75084IL | KCSL | KCSL - STREET LIGHT NEW INSTALLS | 3621.44 |  | 3621.44 |  |  | 7997.88 | 0 | 7997.88 | 2017-03-28 09:32 | 2067-04-01 | 2021-11-01 | open
75084 | 75084IL | KLEDAL | KLEDAL - LED AREA LIGHT RETROFIT | 14344.23 |  | 14344.23 |  |  | 14366.51 | 0 | 14366.51 | 2017-03-28 09:35 | 2067-04-01 | 2020-04-01 | open
75084 | 75084IL | KLEDSL | KLEDSL - LED STREET LIGHT RETROFIT | -4738.33 |  | -4738.33 |  |  | 373835.37 | 0 | 373835.37 | 2017-03-28 09:37 | 2067-04-01 | 2017-12-01 | open
75084 | 75084IL | KRUL | KRUL - UG CABLE LIGHTING REPLACEMENTS | 59179.04 |  | 59179.04 |  |  | 128176.89 | 0 | 128176.89 | 2017-03-28 09:39 | 2067-04-01 | 2018-05-01 | open
75084 | 75084IL | KSLRPL | KSLRPL - STREET LIGHT REPLACEMENTS | 307799.31 |  | 307799.31 |  |  | 1149962.52 | 0 | 1149962.52 | 2017-03-28 09:43 | 2067-04-01 | 2017-08-01 | open
75084 | 75084VM | VDHAZL2KY | VDHAZL2KY - VDHAZL2KY | 15486.82 |  | 15486.82 |  |  | 291849.29 | 0 | 291849.29 | 2020-12-22 15:04 | 2050-12-31 | 2021-02-01 | open
75084 | 75084VM | VDHAZPGKY | VDHAZPGKY - VDHAZPGKY | 217499.06 |  | 217499.06 |  |  | 1491283.78 | 0 | 1491283.78 | 2017-05-25 15:32 | 2050-12-31 | 2018-01-01 | open
75084 | 75084VM | VDREMVCKY | VDREMVCKY - VDREMVCKY | 99971.01 |  | 99971.01 |  |  | 2001968.48 | 0 | 2001968.48 | 2017-05-25 11:52 | 2050-12-30 | 2018-01-01 | open
75084 | DKY2131 | MX5764593 | MX5764593 - KENTON 42 - HIGHWAY CROSSING | 97421.69 |  | 97421.69 |  |  | 135819.09 | 75452.28 | 60366.81 | 2020-05-06 14:01 | 2025-05-01 | 2020-10-01 | open
75084 | DKY2135 | DKY213501 | DKY213501 - TAYLOR MILL SUB 69KV TAKE OFF | 338251.44 |  | 338251.44 |  |  | 440267.16 | 2065388.84 | -1625121.68 | 2021-06-04 14:02 | 2025-07-29 | 2021-06-01 | open
75084 | DKY2135 | DKY213502 | DKY213502 - TAYLOR MILL SUB INSTALL | 487042.16 |  | 487042.16 |  |  | 997026.42 | 6087134 | -5090107.58 | 2021-06-04 14:02 | 2025-08-01 | 2021-06-01 | open
75084 | DKY2135 | DKY213503 | DKY213503 - F5967 LOOP THRU TAYLOR MILL | 35685.54 |  | 35685.54 |  |  | 77203.69 | 939598.78 | -862395.09 | 2021-06-04 14:02 | 2025-01-31 | 2021-07-01 | open
75084 | DKY2645 | MX1975019 | MX1975019 - WILDER 43 LN EXT- DKY2645 | 3898.15 |  | 3898.15 |  |  | 73073.19 | 256821.89 | -183748.7 | 2019-07-25 14:01 | 2026-06-29 | 2019-10-01 | open
75084 | DKY2722 | MX9365045 | MX9365045 - VILLA 43 LN EXT TO THOM MORE 41 - D | 15236.28 |  | 15236.28 |  |  | 76806.35 | 763815.04 | -687008.69 | 2021-01-07 14:02 | 2025-03-31 | 2021-03-01 | open
75084 | DKY2917 | MX6090364 | MX6090364 - DIXIE 45 - INDUSTRIAL RD RECO - DKY | 5018.37 |  | 5018.37 |  |  | 5018.37 | 87581.62 | -82563.25 | 2022-08-30 10:01 | 2025-05-01 | 2023-12-01 | open
75084 | FPIT | 346954001 | 346954001 - ISOP GRANULAR FORECASTING | 112733.44 |  | 112733.44 |  |  | 459979.1 | 572625 | -112645.9 | 2018-05-14 11:31 | 2025-03-31 | 2018-05-01 | open
75084 | FPIT | 348527125 | 348527125 - NON-RES FLEET ELECTRIC PLANING TOOL | 94940.46 |  | 94940.46 |  |  | 94940.46 | 366827 | -271886.54 | 2023-08-08 15:19 | 2025-06-29 | 2023-12-01 | open
75084 | FPIT | 349472021 | 349472021 - FMA ENHANCEMENTS | 3604.52 |  | 3604.52 |  |  | 7931.05 | 9426 | -1494.95 | 2022-05-18 12:21 | 2025-03-31 | 2022-06-01 | open
75084 | FPIT | 349472028 | 349472028 - NEW FMA ENHANCEMENTS | 16358.41 |  | 16358.41 |  |  | 16358.41 | 19340 | -2981.59 | 2023-04-14 17:42 | 2025-05-28 | 2023-12-01 | open
75084 | FPIT | 349472029 | 349472029 - MAXIMO INTEGRATIONS AND OTHER ENHAN | 22096.99 |  | 22096.99 |  |  | 22096.99 | 32592 | -10495.01 | 2023-04-06 12:26 | 2025-05-28 | 2023-12-01 | open
75084 | FPIT | IT2100108 | IT2100108 - CIP LOCAL PASSWORD TOOL (CLPT) | 5098.31 |  | 5098.31 |  |  | 21509.25 | 29845 | -8335.75 | 2021-11-03 14:41 | 2025-03-31 | 2021-11-01 | open
75084 | FPIT | LTHCDDSLT | LTHCDDSLT - LIGHTHOUSE CUSTOMER DELIVERY DESIGN | 34015.17 |  | 34015.17 |  |  | 35228.94 | 115970 | -80741.06 | 2022-10-13 15:30 | 2025-09-30 | 2022-11-01 | open
75084 | H9321520A | MX1490271 | MX1490271 - DMM - LEIDOS DUE 10/20/23 - H932152 | 472.75 |  | 472.75 |  |  | 472.75 | 37299.76 | -36827.01 | 2023-11-16 14:01 | 2025-05-29 | 2023-12-01 | open
75084 | H9321520A | MX8540456 | MX8540456 - SUB OPT -LOAD GROWTH, LOAD TRANSFER | 33576.66 |  | 33576.66 |  |  | 33576.66 | 206981.75 | -173405.09 | 2023-08-14 18:01 | 2025-05-29 | 2023-12-01 | open
75084 | ICPRJDSTR | ICCONSTRD | ICCONSTRD - INTERCONNECTION CAPITAL PROJECT | 26.04 |  | 26.04 |  |  | 26.04 | 0 | 26.04 | 2017-09-28 11:28 | 2030-09-30 | 2017-10-01 | open
75084 | K23TEMERG | MX9067337 | MX9067337 - EMERGT E1 VILLA CAP BANK 1 REPLACE | 4043.46 |  | 4043.46 |  |  | 4043.46 | 11315.6 | -7272.14 | 2023-04-26 10:01 | 2023-12-31 | 2023-05-01 | open
75084 | KCTFOOL | KCTOOL | KCTOOL - TOOLS BLANKET | 152048.55 |  | 152048.55 |  |  | 828156.23 | 0 | 828156.23 | 2018-07-27 15:23 | 2069-04-01 | 2018-11-01 | open
75084 | M190194 | M19019401 | M19019401 - TURFWAY SUB | 3374.36 |  | 3374.36 |  |  | 14423 | 4551557.9 | -4537134.9 | 2020-12-08 14:19 | 2028-06-19 | 2020-12-01 | open
75084 | M190299 | M19029901 | M19029901 - F5967 RBLD POLE HL736 TO HL 661 | 436802.13 |  | 436802.13 |  |  | 474338.91 | 19421209.13 | -18946870.22 | 2021-06-07 18:02 | 2025-07-22 | 2021-07-01 | open
75084 | M190299 | M19029902 | M19029902 - F5967 RLE RBLD HL736 TO HWY 177 LA | 10415.42 |  | 10415.42 |  |  | 10415.42 | 57738 | -47322.58 | 2021-06-07 18:02 | 2025-05-02 | 2023-12-01 | open
75084 | M190299 | MX9563131 | MX9563131 - F5967 (M190299) REBUILD MARSHALL RD | 11079.03 |  | 11079.03 |  |  | 11079.03 | 208304.51 | -197225.48 | 2023-06-08 10:01 | 2025-03-31 | 2023-12-01 | open
75084 | M190299 | MX9563302 | MX9563302 - F5967 (M190299) REBUILD MARSHALL | 14840.52 |  | 14840.52 |  |  | 14840.52 | 254623.51 | -239782.99 | 2023-06-08 14:01 | 2025-09-25 | 2023-12-01 | open
75084 | M190299 | MX9563423 | MX9563423 - F5967 (M190299) REBUILD KLETTE RD | 3195.43 |  | 3195.43 |  |  | 3195.43 | 256646.69 | -253451.26 | 2023-06-08 14:01 | 2025-05-15 | 2023-12-01 | open
75084 | M190300 | M19030001 | M19030001 - F5967 RBLD HL 661 TO DECOURSEY | 212694.6 |  | 212694.6 |  |  | 247026.63 | 12892712.42 | -12645685.79 | 2021-06-07 18:02 | 2025-07-11 | 2021-07-01 | open
75084 | M190309 | M19030901 | M19030901 - HEBRON-INSTALL 69 KV CB | 262068.05 |  | 262068.05 |  |  | 282758.28 | 2708286.91 | -2425528.63 | 2022-02-23 10:01 | 2027-09-07 | 2022-03-01 | open
75084 | M190309 | M19030902 | M19030902 - HEBRON TO 15268C TAP-INSTALL NEW 69 | 181249.53 |  | 181249.53 |  |  | 181249.53 | 12665914.62 | -12484665.09 | 2023-02-02 14:01 | 2027-07-23 | 2023-12-01 | open
75084 | M190309 | M19030903 | M19030903 - FEEDER 6763-RECONDUCTOR OAKBROOK TO | 111440 |  | 111440 |  |  | 111440 | 6146119.04 | -6034679.04 | 2023-02-02 14:01 | 2028-01-08 | 2023-12-01 | open
75084 | M190309 | M19030906 | M19030906 - LIMABURG STATION UPRATE | 9207.03 |  | 9207.03 |  |  | 9207.03 | 115011.19 | -105804.16 | 2023-02-02 14:01 | 2028-01-08 | 2023-12-01 | open
75084 | M190309 | M19030907 | M19030907 - LEVI STRAUSS STATION UPRATE | 20441.17 |  | 20441.17 |  |  | 20441.17 | 67966.06 | -47524.89 | 2023-02-02 10:08 | 2028-01-08 | 2023-12-01 | open
75084 | M190309 | M19030908 | M19030908 - OAKBROOK SUB 15264 CHANGES | 59236.91 |  | 59236.91 |  |  | 59236.91 | 150007.74 | -90770.83 | 2023-02-02 14:01 | 2028-01-08 | 2023-12-01 | open
75084 | M200289 | M20028901 | M20028901 - YORK TB 2 | 10361.1 |  | 10361.1 |  |  | 10361.1 | 5082666.34 | -5072305.24 | 2023-07-13 18:01 | 2027-01-01 | 2023-12-01 | open
75084 | M200444 | M20044401 | M20044401 - DIXIE RPL BUS 2 SWGR & TB2 | 115740.2 |  | 115740.2 |  |  | 124253.67 | 4246746.6 | -4122492.93 | 2022-08-15 18:01 | 2026-02-03 | 2022-08-01 | open
75084 | M210307 | M21030701 | M21030701 - THOMAS MORE INSTL RTU | 7626.38 |  | 7626.38 |  |  | 7626.38 | 217210.55 | -209584.17 | 2022-09-28 18:01 | 2025-11-24 | 2023-12-01 | open
75084 | M210344 | M21034401 | M21034401 - DAYTON INSTALL RTU | 4755.21 |  | 4755.21 |  |  | 4755.21 | 219089.5 | -214334.29 | 2022-09-28 18:01 | 2026-09-27 | 2023-12-01 | open
75084 | M210464 | M21046401 | M21046401 - CONSTANCE BUS 1 SWGR AND TB 1 RPL | -4724.14 |  | -4724.14 |  |  | 163941.88 | 5765552.98 | -5601611.1 | 2022-11-30 18:02 | 2028-08-06 | 2022-12-01 | open
75084 | M210499 | M21049902 | M21049902 - F30689 AT OAKBROOK | 806.61 |  | 806.61 |  |  | 806.61 | 40112.33 | -39305.72 | 2023-01-18 14:01 | 2025-12-09 | 2023-12-01 | open
75084 | M210500 | M21050001 | M21050001 - BUFFINGTON TB 8 | 41019.53 |  | 41019.53 |  |  | 41019.53 | 6061270.53 | -6020251 | 2023-05-11 18:01 | 2026-07-28 | 2023-12-01 | open
75084 | M210504 | M21050401 | M21050401 - FEEDER 15268 RELOCATION | 1807.04 |  | 1807.04 |  |  | -50647.89 | 704098.77 | -754746.66 | 2022-01-14 10:04 | 2025-12-23 | 2022-01-01 | open
75084 | M210531 | M21053101 | M21053101 - MARSHALL TB 1 LS REBLD | 391.54 |  | 391.54 |  |  | 391.54 | 1027215.33 | -1026823.79 | 2023-10-13 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | M220161 | M22016101 | M22016101 - 15268 DOLWICK DR - AMSTERDAM RD | 43043.91 |  | 43043.91 |  |  | 43043.91 | 4016574.4 | -3973530.49 | 2023-10-18 10:13 | 2030-07-16 | 2023-12-01 | open
75084 | M220161 | M22016102 | M22016102 - 15268 DOLWICK DR - AMSTERDAM RD RBL | 8605.74 |  | 8605.74 |  |  | 8605.74 | 10464 | -1858.26 | 2023-12-29 10:01 | 2029-12-24 | 2023-12-01 | open
75084 | M220313 | M22031301 | M22031301 - RICHWOOD TB 2 MOVE TO WHITE TOWER T | 23774.78 |  | 23774.78 |  |  | 23774.78 | 45454.72 | -21679.94 | 2023-01-25 10:08 | 2025-02-07 | 2023-12-01 | open
75084 | M220314 | M22031401 | M22031401 - WEAVER SUBSTATION SITE PURCHASE | 7989.16 |  | 7989.16 |  |  | 7989.16 | 1628922 | -1620932.84 | 2023-04-20 14:09 | 2025-08-31 | 2023-12-01 | open
75084 | M220347 | M22034701 | M22034701 - WILDER SUBSTATION REPLACE TB 2 DEK | 66719.88 |  | 66719.88 |  |  | 66719.88 | 5916671.46 | -5849951.58 | 2023-05-18 18:01 | 2027-01-18 | 2023-12-01 | open
75084 | M220347 | M22034702 | M22034702 - WILDER INST NEW 33.6 MVA | 6273.24 |  | 6273.24 |  |  | 6273.24 | 3874565.15 | -3868291.91 | 2023-05-18 18:01 | 2026-07-27 | 2023-12-01 | open
75084 | M220347 | M22034704 | M22034704 - WILDER 5962 CHANGES | 1151.51 |  | 1151.51 |  |  | 1151.51 | 537013.97 | -535862.46 | 2023-05-18 18:01 | 2026-01-06 | 2023-12-01 | open
75084 | M220347 | M22034705 | M22034705 - WILDER STATION POWER | 3743.25 |  | 3743.25 |  |  | 3743.25 | 129346.56 | -125603.31 | 2023-05-18 18:01 | 2025-12-29 | 2023-12-01 | open
75084 | M230067 | M23006701 | M23006701 - WILDER TPS | 2476.52 |  | 2476.52 |  |  | 2476.52 | 808187.73 | -805711.21 | 2023-10-26 18:01 | 2025-02-25 | 2023-12-01 | open
75084 | M230067 | M23006702 | M23006702 - BUFFINGTON TPS | 4354.5 |  | 4354.5 |  |  | 4354.5 | 1130021.67 | -1125667.17 | 2023-10-26 18:01 | 2025-02-15 | 2023-12-01 | open
75084 | M230067 | M23006703 | M23006703 - BLACKWELL TPS | 611.92 |  | 611.92 |  |  | 611.92 | 781242.89 | -780630.97 | 2023-10-26 18:01 | 2025-02-11 | 2023-12-01 | open
75084 | M230109 | M23010901 | M23010901 - F15268 69KV 2022 POLE INSPECTION KY | 82.22 |  | 82.22 |  |  | 82.22 | 636725.16 | -636642.94 | 2023-08-22 14:10 | 2025-08-16 | 2023-12-01 | open
75084 | M230295 | M23029501 | M23029501 - 965 NKY WTP TAP INTO NEW STATION | 2348.16 |  | 2348.16 |  |  | 2348.16 | 148601.3 | -146253.14 | 2023-09-14 18:02 | 2025-08-25 | 2023-12-01 | open
75084 | RES75084 | ASDEKCD | ASDEKCD - ADMN SVCS BLANKET FOR CUST DEL DEK | 121502.15 |  | 121502.15 |  |  | 164422.75 | 0 | 164422.75 | 2022-07-11 16:31 | 2050-12-31 | 2022-08-01 | open
75084 | SG000336F | SG336SW | SG336SW - SG DEE DMS ADMS - SOFTWARE | 186259.53 |  | 186259.53 |  |  | 2036110.26 | 1049863.37 | 986246.89 | 2016-09-06 17:51 | 2026-06-01 | 2016-09-01 | open
75084 | SG000438F | SGSELFKY | SGSELFKY - DEK SEGMENTATION & AUTOMATION | 65155.45 |  | 65155.45 |  |  | 1546574.71 | 0 | 1546574.71 | 2017-11-27 14:41 | 2025-12-31 | 2017-12-01 | open
75084 | SG000601F | SG601SW | SG601SW - DEE ADP SOFTWARE - 601 | 262690.53 |  | 262690.53 |  |  | 825054.77 | 42090 | 782964.77 | 2017-06-21 17:55 | 2025-03-31 | 2017-06-01 | open
75084 | SG000685F | SG685TUGK | SG685TUGK - DEK TUG EASEMENT/ROW BLANKET | 41912.53 |  | 41912.53 |  |  | 179850.92 | 400000 | -220149.08 | 2019-10-22 11:24 | 2026-03-31 | 2020-01-01 | open
75084 | SG000732F | SG732TR04 | SG732TR04 - DEK TWR,SHELTR,PWRSUP_SPARTA MW | 112474.35 |  | 112474.35 |  |  | 167212.19 | 1519055 | -1351842.81 | 2021-02-05 14:19 | 2026-03-20 | 2021-02-01 | open
75084 | SG000732F | SG732TR05 | SG732TR05 - COMM TOWERS,SHELTERS-RYLAND HEIGHTS | 16822.04 |  | 16822.04 |  |  | 52413.42 | 1519055 | -1466641.58 | 2021-03-11 16:09 | 2027-03-31 | 2021-05-01 | open
75084 | SG000744F | SG000744B | SG000744B - GRIDWAN EDGE BLANKET - DEK | 89073.49 |  | 89073.49 |  |  | 89073.49 | 128301 | -39227.51 | 2023-06-28 11:50 | 2032-03-31 | 2023-12-01 | open
75084 | SG000764F | SG764BLK1 | SG764BLK1 - DEK 2019-2020 MICROWAVE UPGRADES | 436664.59 |  | 436664.59 |  |  | 2501063.09 | 217462.26 | 2283600.83 | 2019-02-25 09:15 | 2030-03-31 | 2019-04-01 | open
75084 | SG000764F | SG764MAT1 | SG764MAT1 - DEK 2019-2020 MICROWAVE UPGRADES | 6526.16 |  | 6526.16 |  |  | 493208.14 | 217462.26 | 275745.88 | 2019-02-25 08:41 | 2030-03-31 | 2019-10-01 | open
75084 | SG000770F | SG770MAS | SG770MAS - 2018 MAS RADIO | 27420.39 |  | 27420.39 |  |  | 343394.3 | 112986 | 230408.3 | 2018-02-13 17:18 | 2019-03-31 | 2018-02-01 | open
75084 | SG000776F | SG776OP1 | SG776OP1 - DEK OPTICAL ELECTRONICS | 114659.28 |  | 114659.28 |  |  | 114649.51 | 542269.02 | -427619.51 | 2022-06-08 08:16 | 2030-03-31 | 2022-06-01 | open
75084 | SG000954F | SG954KYFR | SG954KYFR - DEK FUSE REPLACEMENT AFWS | 423399.06 |  | 423399.06 |  |  | 937429.58 | 3940594 | -3003164.42 | 2019-10-22 15:06 | 2026-03-31 | 2021-01-01 | open
75084 | SG000960F | SG960DASH | SG960DASH - DER DISPATCH - DASHBOARD | 78269.44 |  | 78269.44 |  |  | 132192.12 | 179000 | -46807.88 | 2021-09-14 11:49 | 2026-09-30 | 2021-09-01 | open
75084 | SG000960F | SG960ORCH | SG960ORCH - DER DISPATCH ORCHESTRATION | 239065.14 |  | 239065.14 |  |  | 372299.75 | 939747 | -567447.25 | 2021-09-13 16:54 | 2026-09-30 | 2021-09-01 | open
75084 | SG001037F | SG1037SW | SG1037SW - BULK DEVICE MANAGEMENT (BDM) | 75.59 |  | 75.59 |  |  | 3326.31 | 77982 | -74655.69 | 2022-01-04 00:59 | 2024-01-31 | 2022-01-01 | open
75084 | SG001093F | SG1093SW | SG1093SW - GRID HOSTING CAPACITY PROJECT | 86751.9 |  | 86751.9 |  |  | 213313.11 | 346175 | -132861.89 | 2021-11-19 17:02 | 2025-01-26 | 2021-11-01 | open
75084 | SG001105F | SG1105SW | SG1105SW - POWER FLOW ANALYSIS | 63389.04 |  | 63389.04 |  |  | 67510.66 | 52971 | 14539.66 | 2022-12-16 14:26 | 2025-11-30 | 2022-12-01 | open
75084 | SG001134F | SG1134HW | SG1134HW - MOBILE CONNECT HARDWARE | 12816.05 |  | 12816.05 |  |  | 12816.05 | 498485 | -485668.95 | 2023-02-02 18:29 | 2026-03-11 | 2023-12-01 | open
75084 | SG001165F | SG1165SW | SG1165SW - DEE VEGETATION MANAGEMENT | 97503.54 |  | 97503.54 |  |  | 97503.54 | 191389 | -93885.46 | 2022-12-30 13:44 | 2025-03-31 | 2023-12-01 | open
75084 | SG001170F | SG1170M01 | SG1170M01 - END OF LIFE MODEM REPLACEMENT - B | 288092.54 |  | 288092.54 |  |  | 308101.22 | 133098 | 175003.22 | 2022-05-09 19:13 | 2030-03-31 | 2022-05-01 | open
75084 | SG001181F | SG1181SW | SG1181SW - DEE FEEDER LEVEL PLNG & RPTG | 32912.31 |  | 32912.31 |  |  | 32912.31 | 85244 | -52331.69 | 2023-03-30 13:55 | 2025-03-31 | 2023-12-01 | open
75084 | SG990022F | SRRRKY | SRRRKY - SG - RECLOSURE REPLACEMENTS DMWKY | 15564.97 |  | 15564.97 |  |  | 730611.25 | 0 | 730611.25 | 2017-04-04 13:14 | 2050-12-31 | 2019-03-01 | open
75084 | SGDERF | SGDER02 | SGDER02 - DER RIDE IMPLEMENT-DEK | 94.1 |  | 94.1 |  |  | 94.1 | 4100 | -4005.9 | 2023-09-25 14:50 | 2026-12-31 | 2023-12-01 | open
75084 | TKY1904 | TKY190401 | TKY190401 - BUFFINGTON F6761 REL RPL | 68941.19 |  | 68941.19 |  |  | 84841.41 | 301535.47 | -216694.06 | 2018-08-30 14:02 | 2025-08-05 | 2019-01-01 | open
75084 | TKY1904 | TKY190402 | TKY190402 - BLACKWELL F6761 REL RPL | 2371.15 |  | 2371.15 |  |  | 12969.29 | 120674.34 | -107705.05 | 2018-08-30 14:02 | 2025-08-08 | 2018-12-01 | open
75084 | VMDDTFA | VMDDTKY | VMDDTKY - DISTR LINE CLR REMOVAL | 102.49 |  | 102.49 |  |  | 2114855.56 | 0 | 2114855.56 | 2008-07-01 | 2050-12-31 | 2008-07-01 | open
75084 | VMTDFA | GGARKY | GGARKY - TVM REACTIVE CAP - DEK | 209409.34 |  | 209409.34 |  |  | 287190.25 | 0 | 287190.25 | 2019-10-16 15:20 | 2050-12-31 | 2020-03-01 | open
75084 | VMTDFA | TVMBLLVKY | TVMBLLVKY - TVM NONNERC CAP - DEK | 112870 |  | 112870 |  |  | 347854.73 | 0 | 347854.73 | 2019-10-16 14:36 | 2050-12-31 | 2020-03-01 | open
75084 | VMTDFA | VMTDKY | VMTDKY - TRANS LINE CLR REMOVAL | 111897.17 |  | 111897.17 |  |  | 2072184.75 | 0 | 2072184.75 | 2008-07-01 | 2050-12-31 | 2008-07-01 | open
75085 | ENERGORCH | EOPLTFM | EOPLTFM - ENERGY ORCHESTRATION PLATFORM | 209042.1 |  | 209042.1 |  |  | 209042.1 | 210000 | -957.9 | 2023-02-07 09:52 | 2027-03-31 | 2023-12-01 | open
75085 | FPCNTRL | CONTROLS | CONTROLS - SMART CONTROLS SYSTEM MGMT. TOOL | 66313.44 |  | 66313.44 |  |  | 136861.35 | 61125 | 75736.35 | 2022-08-24 14:58 | 2027-03-31 | 2022-08-01 | open
75085 | FPIT | 400055030 | 400055030 - SAP & BUSINESS CUSTOMER WEB PORTAL | 39560.66 |  | 39560.66 |  |  | 39560.66 | 392547 | -352986.34 | 2023-10-31 11:50 | 2025-06-29 | 2023-12-01 | open
75085 | FPIT | 400055031 | 400055031 - D-E.COM/MY ACCOUNT WEB | 3183.43 |  | 3183.43 |  |  | 3183.43 | 45309 | -42125.57 | 2023-10-31 07:23 | 2025-06-29 | 2023-12-01 | open
75085 | FPIT | 400055032 | 400055032 - CUSTOMER - MOBILE APPLICATION | 15446.22 |  | 15446.22 |  |  | 15446.22 | 85440 | -69993.78 | 2023-10-31 04:33 | 2025-06-29 | 2023-12-01 | open
75085 | FPIT | IT2300007 | IT2300007 - CARBON TOOLS PLATFORM 2023 - CLEAN | 22605.83 |  | 22605.83 |  |  | 22605.83 | 75845 | -53239.17 | 2023-02-22 13:35 | 2026-03-31 | 2023-12-01 | open
75085 | FPIT | IT2300008 | IT2300008 - CLEAN ENERGY SOLUTIONS PORTFOLIO | 5371.23 |  | 5371.23 |  |  | 5371.23 | 10270 | -4898.77 | 2023-02-28 13:07 | 2025-03-31 | 2023-12-01 | open
75085 | FPUISFTWR | UIRATEDES | UIRATEDES - IU RATE DESIGN TOOL | 13247.27 |  | 13247.27 |  |  | 135361.47 | 213693 | -78331.53 | 2021-01-29 09:45 | 2026-03-31 | 2021-02-01 | open
75085 | IGSSOFTWR | RCTSOFTWR | RCTSOFTWR - RESIDENTIAL CARBON TOOL SOFTWARE | 1896.22 |  | 1896.22 |  |  | 7265.3 | 3017 | 4248.3 | 2022-02-21 13:59 | 2025-03-31 | 2022-04-01 | open
75084 | 21520042A | MX7891217 | MX7891217 - SUB OPT -REPLACEMENT OF EXISTING RE | 438.14 |  | 438.14 |  |  | 8101.53 | 0 | 8101.53 | 2021-11-22 18:02 | 2025-05-29 | 2021-11-01 | open
75084 | 22410047A | MX5222181 | MX5222181 - TBC 2410047A: FLORENCE 47 BNK-6158 | 44.43 |  | 44.43 |  |  | 821.76 | 0 | 821.76 | 2022-05-27 10:01 | 2025-07-29 | 2022-10-01 | open
75084 | 22410047A | MX7372050 | MX7372050 - TBC 2410047A: FLORENCE 47 BNK-6124 | 38.96 |  | 38.96 |  |  | 720.88 | 228.31 | 492.57 | 2021-10-22 09:12 | 2025-07-29 | 2022-06-01 | open
75084 | K241TUG1 | MX0006935 | MX0006935 - TUG - PHEASANT DR - EAST INSTALL | 58250.42 |  | 58250.42 |  |  | 58250.42 | 228.31 | 58022.11 | 2023-11-01 10:01 | 2026-09-28 | 2023-12-01 | open
75084 | 20780045A | MX6453758 | MX6453758 - SUB OPT- 20780045A- AUGUSTINE 45- G | 374.07 |  | 374.07 |  |  | 374.07 | 88972.6 | -88598.53 | 2022-09-22 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 20780046A | MX9353387 | MX9353387 - JTD - 20780046A: AUGUSTINE 46 K72-2 | 1503.81 |  | 1503.81 |  |  | 1503.81 | 48264.44 | -46760.63 | 2023-07-10 14:01 | 2025-12-29 | 2023-12-01 | open
75084 | 21990042A | MX2725028 | MX2725028 - CAP UPGRADE, 41BN-710, RICHWOOD (19 | 36171.84 |  | 36171.84 |  |  | 36195.61 | 28103.91 | 8091.7 | 2022-05-04 10:03 | 2025-02-28 | 2022-12-01 | open
75084 | 21990042A | MX5254733 | MX5254733 - 21990042A: RICHWOOD 42 BTW 35BN-53 | 61417.07 |  | 61417.07 |  |  | 61417.07 | 47911.68 | 13505.39 | 2022-06-06 10:01 | 2025-02-28 | 2023-12-01 | open
75084 | 22870042A | MX9353408 | MX9353408 - JTD - 22870042A: KENTUCKY UNIVERSIT | 758.58 |  | 758.58 |  |  | 758.58 | 48073.33 | -47314.75 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870043A | MX6327155 | MX6327155 - CAP UPGRADE,35CA-1605,KENTUCKY UNIV | 1194.7 |  | 1194.7 |  |  | 1194.7 | 30428.29 | -29233.59 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | 22870043A | MX9353403 | MX9353403 - JTD - 22870043A: KENTUCKY UNIVERSIT | 1009.42 |  | 1009.42 |  |  | 1009.42 | 46405.86 | -45396.44 | 2023-06-05 18:01 | 2025-08-29 | 2023-12-01 | open
75084 | M180375 | M18037501 | M18037501 - LITTON SUB- CONSTRUCT SUB | 4019664.19 |  | 4019664.19 |  |  | 4482872.8 | 8698488.61 | -4215615.81 | 2021-10-29 14:02 | 2025-04-04 | 2021-11-01 | open
75084 | M190299 | MX9114464 | MX9114464 - F5967 (M190299) REBUILD MARSHALL RD | 17809.17 |  | 17809.17 |  |  | 17809.17 | 215949.42 | -198140.25 | 2023-06-08 10:01 | 2025-06-29 | 2023-12-01 | open
75084 | M210374 | M21037401 | M21037401 - LIMABURG-OAKBROOK RLE | 9865.51 |  | 9865.51 |  |  | 22028.99 | 185590.81 | -163561.82 | 2021-08-04 14:03 | 2026-07-06 | 2021-08-01 | open
75084 | M210374 | M21037402 | M21037402 - HEBRON-ROUTE 237 RLE | 106085.61 |  | 106085.61 |  |  | 299288.56 | 4748160.48 | -4448871.92 | 2021-08-04 14:03 | 2026-03-03 | 2021-08-01 | open
75084 | M210499 | M21049901 | M21049901 - OAKBROOK TB 2 | 234533.82 |  | 234533.82 |  |  | 234533.82 | 7672303.06 | -7437769.24 | 2023-01-18 14:01 | 2026-01-16 | 2023-12-01 | open
75084 | M220347 | M22034703 | M22034703 - WILDER INST MOBILE | 719.04 |  | 719.04 |  |  | 719.04 | 613997.37 | -613278.33 | 2023-05-18 18:01 | 2026-07-27 | 2023-12-01 | open
|  |  |  | 108766748.704 | 114588457.9509 | 5821709.2469 | 5.081%