## Sheet1
Schedule C
South Kentucky RECC
Case No. 2024-00402
Construction Projects
For Five Years ended December 31, 2024
|  |  |  | Variance |  |  | Total | Total | Variance | Date | Date
|  | Actual Cost | Original Budget | In | Variance | Percent | Actual | Budget | In | Original | Original | Date | Date
Project | Project |  |  | Dollars | As | Of | Project | Project | Dollars | Budget | Budget | Actual | Actual
No. | Title/Description |  |  | Under/(Over) | Percent | Budget | Cost | Cost | Under/(Over) | Start | End | Start | End
30361 | SIEVERS RD TO NAOMI - 3PH Conductor Upgrade - 1.00 miles | 102042.79 | 141000 | 38957.21 | 27.63% | 72.37% | 102042.79 | 141000 | 38957.21 | 2020-01-01 | 2023-12-31 | 2021-06-11 | 2022-05-31
30362 | NANCY SIEVERS RD TO NAOMI | 65592.4 | 352500 | 286907.6 | 81.39% | 18.61% | 65592.4 | 352500 | 286907.6 | 2024-06-01 | 2025-12-31 | 2024-11-13 | TBD
32461 | HWY 1676/MT ZION | 24391.26 | 141000 | 116608.74 | 82.7% | 17.3% | 24391.26 | 141000 | 116608.74 | 2020-01-01 | 2023-12-31 | 2024-06-25 | TBD
32561 | SLATE BRANCH ROAD (SECT 1 & SECT 2) - 3PH Conductor Upgrade - 0.75 miles | 113757.69 | 104340 | -9417.69 | -9.026% | 109% | 113757.69 | 104340 | -9417.69 | 2020-01-01 | 2023-12-31 | 2017-09-27 | 2021-12-31
33361 | SOUTH HWY 235 - 3PH Conductor Upgrade - 1.00 miles | 150232.73 | 141000 | -9232.73 | -6.548% | 106.5% | 150232.73 | 141000 | -9232.73 | 2020-01-01 | 2023-12-31 | 2021-05-24 | 2022-09-15
60801 | WIBORG HOLLOW RD | 6797.21 | 24940 | 18142.79 | 72.75% | 27.25% | 6797.21 | 24940 | 18142.79 | 2020-01-01 | 2023-12-31 | 2023-03-10 | TBD
60802 | MARK NEW RD/KY 927 EAST - 1PH Conductor Replacement - 0.41 miles | 11388.53 | 23780 | 12391.47 | 52.11% | 47.89% | 11388.53 | 23780 | 12391.47 | 2020-01-01 | 2023-12-31 | 2022-05-12 | 2023-04-05
60803 | VALENTOUR RD/WALLACE RD - 1PH Conductor Replacement - 0.34 miles | 12859.41 | 19720 | 6860.59 | 34.79% | 65.21% | 12859.41 | 19720 | 6860.59 | 2020-01-01 | 2023-12-31 | 2020-01-28 | 2021-10-29
60804 | PONDEROSA RD - 1PH Conductor Replacement - 0.37 miles | 22602.18 | 21460 | -1142.18 | -5.322% | 105.3% | 22602.18 | 21460 | -1142.18 | 2020-01-01 | 2023-12-31 | 2024-02-26 | 2024-04-09
60805 | SANDHILL AND THUNDERSTRUCK RD - 1PH Conductor Replacement - 1.66 miles | 35965.95 | 96280 | 60314.05 | 62.64% | 37.36% | 35965.95 | 96280 | 60314.05 | 2020-01-01 | 2023-12-31 | 2023-03-10 | 2024-01-30
60806 | GABBY SHELTON RD - 1PH Conductor Replacement - 0.32 miles | 17074.77 | 18560 | 1485.23 | 8.002% | 92% | 17074.77 | 18560 | 1485.23 | 2020-01-01 | 2023-12-31 | 2024-02-26 | 2024-03-27
60807 | GORDON TAYLOR RD/KY 896 | 1496.02 | 75980 | 74483.98 | 98.03% | 1.969% | 1496.02 | 75980 | 74483.98 | 2020-01-01 | 2023-12-31 | 2024-09-19 | TBD
60808 | EVERETT NEAL RD/PRIVETT RD | 1361.31 | 58000 | 56638.69 | 97.65% | 2.347% | 1361.31 | 58000 | 56638.69 | 2020-01-01 | 2023-12-31 | 2024-02-26 | TBD
60809 | BEAR CREEK RD | 4485.47 | 84100 | 79614.53 | 94.67% | 5.333% | 4485.47 | 84100 | 79614.53 | 2020-01-01 | 2023-12-31 | 2024-05-01 | TBD
60810 | ROUNDTOP CHURCH/BOWMAN BRANCH RD | 732.52 | 17400 | 16667.48 | 95.79% | 4.21% | 732.52 | 17400 | 16667.48 | 2020-01-01 | 2023-12-31 | 2025-01-14 | TBD
60811 | BELL FARM | 383.28 | 81200 | 80816.72 | 99.53% | 0.472% | 383.28 | 81200 | 80816.72 | 2020-01-01 | 2023-12-31 | 2025-02-01 | TBD
60813 | CAVE SPRINGS N HWY 127 TO DAM | 1237.59 | 141000 | 139762.41 | 99.12% | 0.8777% | 1237.59 | 141000 | 139762.41 | 2020-01-01 | 2023-12-31 | 2024-09-13 | TBD
60814 | WEBSTER DR | 681.06 | 29000 | 28318.94 | 97.65% | 2.348% | 681.06 | 29000 | 28318.94 | 2020-01-01 | 2023-12-31 | 2024-03-15 | TBD
60815 | HILLARD AVE - 1PH Conductor Replacement - 0.20 miles | 10685.85 | 11600 | 914.15 | 7.881% | 92.12% | 10685.85 | 11600 | 914.15 | 2020-01-01 | 2023-12-31 | 2023-12-13 | 2024-01-31
60816 | WORSHAM LANE | 5584.68 | 40600 | 35015.32 | 86.24% | 13.76% | 5584.68 | 40600 | 35015.32 | 2020-01-01 | 2023-12-31 | 2024-08-15 | TBD
60817 | OLD HWY 90/HWY 294 - 3PH Conductor Replacement - 0.20 miles | 92905.12 | 28200 | -64705.12 | -229.5% | 329.5% | 92905.12 | 28200 | -64705.12 | 2020-01-01 | 2023-12-31 | 2024-01-16 | 2024-05-06
60818 | KENDRICK AVE | 5419.48 | 56400 | 50980.52 | 90.39% | 9.609% | 5419.48 | 56400 | 50980.52 | 2020-01-01 | 2023-12-31 | 2025-01-25
60819 | HWY 167 - 1PH Conductor Replacement - 0.30 miles | 44978.57 | 17400 | -27578.57 | -158.5% | 258.5% | 44978.57 | 17400 | -27578.57 | 2020-01-01 | 2023-12-31 | 2024-01-11 | 2024-04-05
60820 | CAMP EARL WALLACE - 1PH Conductor Replacement - 1.50 miles | 55251.63 | 87000 | 31748.37 | 36.49% | 63.51% | 55251.63 | 87000 | 31748.37 | 2020-01-01 | 2023-12-31 | 2021-09-13 | 2023-04-05
60821 | ELAM-GREGORY RD (w/ URD) - 1PH Conductor Replacement - 0.8 miles | 64093.54 | 46400 | -17693.54 | -38.13% | 138.1% | 64093.54 | 46400 | -17693.54 | 2020-01-01 | 2023-12-31 | 2024-04-03 | 2024-10-31
60822 | BRAMMER HILL TO ZION - 1PH Conductor Replacement - 0.30 miles | 29548.7 | 17400 | -12148.7 | -69.82% | 169.8% | 29548.7 | 17400 | -12148.7 | 2020-01-01 | 2023-12-31 | 2020-02-25 | 2021-08-27
60823 | AMY LN - 1PH Conductor Replacement - 0.80 miles | 15253.53 | 46400 | 31146.47 | 67.13% | 32.87% | 15253.53 | 46400 | 31146.47 | 2020-01-01 | 2023-12-31 | 2021-03-26 | 2021-05-19
60824 | FAWN RD (PT 1 & PT 2) - 1PH Conductor Replacement - 0.80 miles | 64976.59 | 46400 | -18576.59 | -40.04% | 140% | 64976.59 | 46400 | -18576.59 | 2020-01-01 | 2023-12-31 | 2021-07-13 | 2022-07-29
60825 | JOHNSON RD | 1475.91 | 54520 | 53044.09 | 97.29% | 2.707% | 1475.91 | 54520 | 53044.09 | 2020-01-01 | 2023-12-31 | 2023-12-20 | TBD
60826 | LICK CREEK RD | 3452.45 | 35380 | 31927.55 | 90.24% | 9.758% | 3452.45 | 35380 | 31927.55 | 2020-01-01 | 2023-12-31 | 2024-10-01 | TBD
60827 | KAY STRINGER RD | 42405.6 | 118320 | 75914.4 | 64.16% | 35.84% | 42405.6 | 118320 | 75914.4 | 2020-01-01 | 2023-12-31 | 2023-10-11 | TBD
60828 | NELSON VALLEY RD - 1PH Conductor Replacement - 1.54 miles | 56353.72 | 89320 | 32966.28 | 36.91% | 63.09% | 56353.72 | 89320 | 32966.28 | 2020-01-01 | 2023-12-31 | 2023-03-10 | 2023-08-02
60829 | WILLA DR - 1PH Conductor Replacement - 0.27 miles | 24078.27 | 15660 | -8418.27 | -53.76% | 153.8% | 24078.27 | 15660 | -8418.27 | 2020-01-01 | 2023-12-31 | 2020-01-06 | 2020-08-27
60830 | WOLF CREEK RD - 1PH Conductor Replacement - 1.30 miles | 35283.06 | 75400 | 40116.94 | 53.21% | 46.79% | 35283.06 | 75400 | 40116.94 | 2020-01-01 | 2023-12-31 | 2024-04-23 | 2024-06-19
60831 | COLO GRADE RD - 1PH Conductor Replacement - 0.25 miles | 46788.78 | 14500 | -32288.78 | -222.7% | 322.7% | 46788.78 | 14500 | -32288.78 | 2020-01-01 | 2023-12-31 | 2021-05-10 | 2022-01-27
60832 | STATE PARK ENTRANCE - 3PH Conductor Replacement - 0.38 miles | 56749.53 | 53580 | -3169.53 | -5.916% | 105.9% | 56749.53 | 53580 | -3169.53 | 2020-01-01 | 2023-12-31 | 2022-01-14 | 2022-08-09
60833 | KATHY HUGHES - 1PH Conductor Replacement - 0.52 miles | 24541.58 | 30160 | 5618.42 | 18.63% | 81.37% | 24541.58 | 30160 | 5618.42 | 2020-01-01 | 2023-12-31 | 2022-01-26 | 2024-05-14
60834 | DECKER RD - 1PH Conductor Replacement - 0.17 miles | 30555.37 | 9860 | -20695.37 | -209.9% | 309.9% | 30555.37 | 9860 | -20695.37 | 2020-01-01 | 2023-12-31 | 2024-04-29 | 2024-12-31
60835 | OCALA RD | 2362.88 | 97700 | 95337.12 | 97.58% | 2.419% | 2362.88 | 97700 | 95337.12 | 2020-01-01 | 2023-12-31 | 2024-09-09 | TBD
60836 | ACORN ANO RD | 1195.02 | 69600 | 68404.98 | 98.28% | 1.717% | 1195.02 | 69600 | 68404.98 | 2020-01-01 | 2023-12-31 | 2024-10-01 | TBD
|  | 1287022.03 | 2633060 | 1346037.97 |  |  | 1287022.03 | 2633060 | 1346037.97
Project | Project
No. | Title/Description | Reason for Variance
30361 | SIEVERS RD TO NAOMI - 3PH Conductor Upgrade - 1.00 miles
30362 | NANCY SIEVERS RD TO NAOMI | Engineering/Mapping model inaccuracy resulting in additional scope.
32461 | HWY 1676/MT ZION | Design delay due to period short staff.
32561 | SLATE BRANCH ROAD (SECT 1 & SECT 2) - 3PH Conductor Upgrade - 0.75 miles
33361 | SOUTH HWY 235 - 3PH Conductor Upgrade - 1.00 miles
60801 | WIBORG HOLLOW RD
60802 | MARK NEW RD/KY 927 EAST - 1PH Conductor Replacement - 0.41 miles | Overestimated quantity of material replacement needed.
60803 | VALENTOUR RD/WALLACE RD - 1PH Conductor Replacement - 0.34 miles | Overestimated quantity of material replacement needed.
60804 | PONDEROSA RD - 1PH Conductor Replacement - 0.37 miles
60805 | SANDHILL AND THUNDERSTRUCK RD - 1PH Conductor Replacement - 1.66 miles | Overestimated quantity of material replacement needed.
60806 | GABBY SHELTON RD - 1PH Conductor Replacement - 0.32 miles
60807 | GORDON TAYLOR RD/KY 896 | Design delay due to period short staff.
60808 | EVERETT NEAL RD/PRIVETT RD | Design delay due to period short staff.
60809 | BEAR CREEK RD | Design delay due to period short staff.
60810 | ROUNDTOP CHURCH/BOWMAN BRANCH RD | Design delay due to period short staff.
60811 | BELL FARM | Design delay due to period short staff. Currently being designed.
60813 | CAVE SPRINGS N HWY 127 TO DAM | Design delay due to period short staff.
60814 | WEBSTER DR | Design delay due to period short staff.
60815 | HILLARD AVE - 1PH Conductor Replacement - 0.20 miles
60816 | WORSHAM LANE
60817 | OLD HWY 90/HWY 294 | Multiple unexpected poles were replaced during contruction. Flagging crew costs.
60818 | KENDRICK AVE
60819 | HWY 167 | Inflationary pressures on material and labor. Flagging crew costs.
60820 | CAMP EARL WALLACE - 1PH Conductor Replacement - 1.50 miles | Overestimated quantity of material replacement needed.
60821 | ELAM-GREGORY RD (w/ URD) | Change of scope due to route. Also added Underground Primary under TVA Transmission Line crossing.
60822 | BRAMMER HILL TO ZION - 1PH Conductor Replacement - 0.30 miles
60823 | AMY LN - 1PH Conductor Replacement - 0.80 miles
60824 | FAWN RD (PT 1 & PT 2) | Change of scope to assist in route. Poor Quality work from staking consultant; no longer used.
60825 | JOHNSON RD | Design delay due to period short staff.
60826 | LICK CREED RD | Original design delay due to period short staff. Currently holding for permits from Dept of Fish & Wildlife and U.S. Forestry
60827 | KAY STRINGER RD | Design delay due to period short staff.
60828 | NELSON VALLEY RD - 1PH Conductor Replacement - 1.54 miles
60829 | WILLA DR | Several Poles were replaced during construction.
60830 | WOLF CREEK RD - 1PH Conductor Replacement - 1.30 miles | Overestimated quantity of material replacement needed.
60831 | COLO GRADE RD | Large change in Scope; Re-Staked.
60832 | STATE PARK ENTRANCE - 3PH Conductor Replacement - 0.38 miles
60833 | KATHY HUGHES - 1PH Conductor Replacement - 0.52 miles
60834 | DECKER RD | Change in Scope; Several Poles replaced during construction.
60835 | OCALA RD | Design delay due to period short staff.
60836 | ACORN ANO RD | Original design delay due to period short staff. Currently holding for permits from Dept of Fish & Wildlife and U.S. Forestry