## Sheet1
Schedule E
South Kentucky RECC
Case No. 2024-00402
Construction Work in Progress-Percent Complete
As of May 31, 2023
Original Budget
Line | Project | Date Construction | Estimated Project | Percent of |  | Most Recent | Total Project | Percent of
No. | No. | Work Began | Completion Date | Time Elapsed | Estimate | Budget Estimate | Expenditures | Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (H/G)
1 | 60802 | 2022-05-12 | 2023-12-31 | 66% | 23780 | 23780 | 11388.53 | 47.89%
2 | 60820 | 2021-09-13 | 2023-03-31 | 100% | 87000 | 87000 | 55251.63 | 63.51%
3 | 60828 | 2023-03-10 | 2023-09-30 | 40% | 89320 | 89320 | 56353.72 | 63.09%