## Sheet1
EB022450-1 East Bend, Limestone Conversion |  |  | MATs PortionTotal
Estimate Charge Type (Power Plan) | Description | Total
AFUDC Debt (99970) | Power Plan - calculated labor loadings | 0 | [9 empty] | Construction Indirects - Estimate
AFUDC Equity (99971) | Power Plan - calculated labor loadings | 0 |  | EPC Contract Labor - AECOM Estimate | [7 empty] | 467000 | Labor Supervision
Company Labor - Exempt (11000) | PM, PE, Env-SME-Plant Support (2024 thru 2027) | 3675000 | 690428.0618 | 3850000 | Material Handling | [6 empty] | 1525000 | Construction CM
Company Labor - Union (11002) | Plant Support, Startup, Training (2026 & 2027) | 438125 | 82311.2366 | 12250000 | Reagent Prep | EPC Contract Material - AECOM Estimate | [5 empty] | 652000 | Field Office Expenses
Company Material (21000) | Storeroom Supplies to Support Project, 2025 - 2027 (ie; valves, instr, flex conduit, piping & tubing fittings, ss tubing, elect matls, threaded rod, plugs, fire blanket, fire ext, safety supplies) | 375000 | 67300.5393 | 3950000 | FGD Area | 3810000 | Material Handling |  |  |  |  | 144000 | Pre-Operational Testing
|  |  |  | 975000 | Dewatering Area | 17375000 | Reagent Prep |  |  |  |  | 175000 | Site Services
Contract Labor (69000) | Engineering (AECOM), Scheduler, Elec Engr, Mech Engr, Ctls Engr - 2024 thru 2027 | 7250000 | 1362068.9655 | 9750000 | Fee and profit | 4825000 | FGD Area | Subcontract L&M - Estimate |  |  |  | 325000 | Temporary Facilities
|  |  |  | 4125000 | Construction Management | 875000 | Dewatering Area | 300000 | Civil Work |  |  | 150000 | Temporary Utilities
Contract Labor (69000) | Contract Labor-AECOM Est (Demo, Civil, Concrete, Architectural, Painting & Coating, Mech Eqpt, Piping-Valves-Supports, Insulation, Elec Eqpt, Raceway-Cable-Conduit, Cable, Control & Instr) | 34900000 | 6556718.1926 | 34900000 | Total | 750000 | Misc. Freight | 835000 | Concrete, Asphalt |  |  | 175000 | Mobilization/Demob
[6 empty] | 2525000 | Misc Ductwork and piping | 325000 | Mech Eqpt |  |  | 50000 | Legal Expenses/Claims
Contract Material (31000) | Contract Material-AECOM Est (Civil, Concrete. Architectural, Painting & Coating, Piping, Insulation, Elect Eqpt, Raceway-Cable Tray-Conduit, Cable, Control & Instr, Escalation) | 30160000 | 5412758.0435 |  |  | 30160000 | Total | 725000 | Piping |  |  | 125000 | Small Tools & Consumables
[8 empty] | 425000 | Insulation |  |  | 755000 | Scaffolding
[8 empty] | 450000 | Electrical Equipment |  |  | 450000 | Site Improvements
Labor Loadings - Exempt (18001) | Power Plan - calculated labor loadings | 2590000 | 486587.396 |  |  |  |  | 850000 | Tank Coatings |  |  | 75000 | General Liability Insurance
[8 empty] | 1825000 | Absorber Recirc Pump Rebuilds |  |  | 15000 | Constr. Equip. Mob/Demob.
Labor Loadings - Union (18001) | Power Plan - calculated labor loadings | 227500 | 42740.7848 |  |  |  |  | 325000 | PA System for Reagent Prep Building |  |  | 225000 | Freight on Material
[8 empty] | 275000 | Fire Protection Systems |  |  | 875000 | Quality Control
Labor Loadings (18000) | Power Plan - calculated labor loadings | 120 | 22.5446 |  |  |  |  | 85000 | FRP Plan & Permitting |  | Owners Engineering Support | 6183000 | Total
[8 empty] | 325000 | Escalation | 1825000 | Design Review |  |  | Contingency on Estimates
Contract Labor (69000) | Subcontract - Duke Managed Scope | 6745000 | 3325000 |  |  |  |  | 6745000 | Total | 550000 | Quality Control | Construction Indirects & Construction Oversight |  | 300000 | Contingency on Constr.Eqpt
[10 empty] | 1750000 | Construction Oversight | 6183000 | Construction Indirects | 6200000 | Contingency on Material
Contract Labor (69000) | Subcontract - Owners Engineering | 4125000 | 774970.2735 | [6 empty] | 4125000 | Total | 625000 | Safety Oversight | 8500000 | Contingency on Labor & SO
[12 empty] | 1800000 | IM - Performance Contractors | 1500000 | Contingency on Subcontr.
Contstruction Oversight | Construction Indirects, IM / Construction Management | 8608000 | 1617198.5731 | [8 empty] | 8608000 | Total | 300000 | Contingency on Process Eq.
[14 empty] | 1400000 | Contingency on Indirects
Contingency | Contingency - Duke | 18200000 | 3342791.1457 | [10 empty] | 18200000 | Total
Overhead (78000) | Power Plan - calculated overhead | 5456000 | 1025027.3484
Stores Loading Allocation (28002) | Power Plan - calculated overhead | 72000 | 13526.7539
Retirements - Overhead (78000) | Power Plan - calculated overhead | -2230.87 | -419.1171
Retirements | Demo Mag Lime Prep Eq.- Labor Cost + Constr Indirect & Contingency | 2750000
Retirements | Demo Agitators/Other- Subcontract Cost | 325000
Retirements - Salvage (99416) | Demo Mag Lime Equipment - Scrap Value | -81968.52
| Total Cost = | 125812545.61 | 24799030.7423
|  |  |  | EPC Contract Labor | EPC Contract Material
|  |  | FGD Area | 3950000 | 4825000
|  |  | % of FGD Area Scope | 0.18787 | 0.17947
|  |  | FGD Fee & Profit, Misc Freight | 1831747.9191 | 134601.0787
|  |  | FGD Const Mgmt, Misc Ductwork/Piping | 774970.2735 | 453156.9649
|  |  | Total | 6556718.1926 | 5412758.0435
Subcontract L&M
|  |  | Absorber Recirc Pump Rebuilds | 1825000
|  |  | Mech Eqpt | 325000
|  |  | Piping | 725000
|  |  | Electrical Equipment | 450000
|  |  | Total | 3325000