## Response 8
Schedule E
Farmers RECC
Case No. 2025-00107
Construction Work in Progress-Percent Complete
Original Budget
Line | Project | Date Construction | Estimated Project | Percent of |  | Most Recent | Total Project | Percent of
No. | No. | Work Began | Completion Date | Time Elapsed | Estimate | Budget Estimate | Expenditures | Total Expenditures
(A) | (B) | (C) | (D) | (E) | (F) | (G) | (H) | (I) = (H/G)
1 | 71303 | 2023-01-26 | 2023-06-02 | 100% | 63000 | 63000 | 25880 | 41.08%
2 | 68477 | 2022-03-16 | 2023-08-23 | 100% | 80400 | 80400 | 156813 | 195%
3 | 71408 | 2023-02-03 | 2024-01-22 | 90% | 28476 | 28476 | 28476 | 100%
4 | 69803 | 2022-05-23 | 2023-08-15 | 100% | 296159 | 296159 | 296159 | 100%
5 | 70035 | 2022-07-13 | 2023-01-30 | 100% | 94446 | 94446 | 94446 | 100%
6 | 72190 | 2023-03-03 | 2023-10-23 | 100% | 12808 | 12808 | 12808 | 100%
7 | 43684 | 2018-07-18 | 2023-11-27 | 100% | 451 | 451 | 451 | 100%