## Construction Projects
Schedule C
FARMERS RECC
Case No. 2025-00107
Construction Projects
For Five Years ended December 31, 2024
|  |  |  | Variance |  |  | Total | Total | Variance | Date | Date
|  | Actual Cost | Original Budget | In | Variance | Percent | Actual | Budget | In | Original | Original | Date | Date
Project | Project |  |  | Dollars | As | Of | Project | Project | Dollars | Budget | Budget | Actual | Actual
No. | Title/Description |  |  | Under/(Over) | Percent | Budget | Cost | Cost | Under/(Over) | Start | End | Start | End
303 / 0203 A | Conv 12.5/7.2KV to 25/14.4 KV Priceville | 608670.9 | 443800 | -164870.9 | -37.15% | 137.1% | 608670.9 | 443800 | -164870.9 | 2019-01-01 | 2019-12-31 | 2018-08-27 | 2020-11-23
304 / 0206 A | Conv 3Ph 1/0 ACSR to 3PH 397 ACSR Kessinger | 342586.48 | 303360 | -39226.48 | -12.93% | 112.9% | 342586.48 | 303360 | -39226.48 | 2020-01-01 | 2020-12-31 | 2021-10-22 | 2022-09-30
306 / 0301 A | Conv 12.5/7.2KV to 25/14.4 KV HWY 90 | 195780.9 | 255000 | 59219.1 | 23.22% | 76.78% | 195780.9 | 255000 | 59219.1 | 2019-01-01 | 2019-12-31 | 2020-09-09 | 2022-01-31
323 / 1203 A | Conv 3 Ph 1/0 ACSR to 3PH 397 ACSR (Glasgow Wire Change) | 521590.8 | 396000 | -125590.8 | -31.71% | 131.7% | 521590.8 | 396000 | -125590.8 | 2020-01-01 | 2020-12-31 | 2024-03-06 | TBD
335 / 0601 A | Conv 1 Feeder 12.5/7.2KV to 2 Feeder 12.5/7.2KV Cave City | 402180.9 | 333000 | -69180.9 | -20.78% | 120.8% | 402180.9 | 333000 | -69180.9 | 2019-01-01 | 2019-12-31 | 2018-10-03 | 2020-11-30
336 / 1703 C | Conv 7.2KV to 14.4KV Defries Road | 89553.13 | 128400 | 38846.87 | 30.25% | 69.75% | 89553.13 | 128400 | 38846.87 | 2020-01-01 | 2020-12-31 | 2021-04-06 | 2022-05-25
387 | Dog Creek Conversion Work Plan Number 387 | 114588.57 | 165060 | 50471.43 | 30.58% | 69.42% | 114588.57 | 165060 | 50471.43 | 2020-01-20 | 2020-12-31 | 2020-05-05 | 2020-11-30
390 / 0404 A | Conv 1Ph 4 ACSR to 3PH 1/0 ACSR Crail Hope Road Conversion | 34636.53 | 63000 | 28363.47 | 45.02% | 54.98% | 34636.53 | 63000 | 28363.47 | 2025-01-01 | 2025-12-31 | 2023-01-23 | 2023-04-30
391 / 0502 A | Conv 12.5/7.2KV to 25/14.4 KV Ralph Morris Road | 323295.16 | 178240 | -145055.16 | -81.38% | 181.4% | 323295.16 | 178240 | -145055.16 | 2023-01-01 | 2023-12-31 | 2024-06-21 | TBD
392 / 0502 B | Conv 12.5/7.2KV to 25/14.4KV Finney Rd (Ralph Morris West) | 10231.8 | 114160 | 103928.2 | 91.04% | 8.963% | TBD | 114160 |  | 2024-01-01 | 2024-12-31 | 2025-04-15 | TBD
395 / 1001 A | Conv 3Ph 1/0 ACSR to 3Ph 397 ACSR Donnelley Drive | 189885.6 | 80400 | -109485.6 | -136.2% | 236.2% | 189885.6 | 80400 | -109485.6 | 2025-01-01 | 2025-12-31 | 2022-03-16 | 2023-08-25
|  | 2833000.77 | 2460420 | -372580.77 |  |  | 2822768.97 | 2460420 | -476508.97
Project | Project
No. | Title/Description | Reason for Variance
303 / 0203 A | Conv 12.5/7.2KV to 25/14.4 KV Priceville | The project estimate was generated in 2017. During Covid, mateial supply chain became strained leading to substantial material cost increases. Transformers needed for a voltage conversion project experienced the largest cost increases. Also, labor increased at an inflated rate due to an increased need for lineworkers.
304 / 0206 A | Conv 3Ph 1/0 ACSR to 3PH 397 ACSR Kessinger | The project estimate was generated in 2017. During Covid, mateial supply chain became strained leading to substantial material cost increases. Also, labor increased at an inflated rate due to an increased need for lineworkers.
306 / 0301 A | Conv 12.5/7.2KV to 25/14.4 KV HWY 90 | This was a carryover project that spanned two construction work plans. A portion of the original estimate was captured during the previous one.
323 / 1203 A | Conv 3 Ph 1/0 ACSR to 3PH 397 ACSR (Glasgow Wire Change) | The project estimate was generated in 2017. During Covid, mateial supply chain became strained leading to substantial material cost increases. Also, labor increased at an inflated rate due to an increased need for lineworkers. In addition, this project experienced atypical expensed due to inclement weather and traffic control plans for road crossings.
335 / 0601 A | Conv 1 Feeder 12.5/7.2KV to 2 Feeder 12.5/7.2KV Cave City | The project estimate was generated in 2017. During Covid, mateial supply chain became strained leading to substantial material cost increases. Also, labor increased at an inflated rate due to an increased need for lineworkers. In addition, this was a double circuit project that we had little historical information on for estimating purposes.
336 / 1703 C | Conv 7.2KV to 14.4KV Defries Road | Final design changed slightly from the initial leading to a reduced as-built cost.
387 | Dog Creek Conversion Work Plan Number 387 | Final design changed slightly from the initial leading to a reduced as-built cost.
390 / 0404 A | Conv 1Ph 4 ACSR to 3PH 1/0 ACSR Crail Hope Road Conversion | Final design changed slightly from the initial leading to a reduced as-built cost.
391 / 0502 A | Conv 12.5/7.2KV to 25/14.4 KV Ralph Morris Road | The project estimate was generated in 2017. During Covid, mateial supply chain became strained leading to substantial material cost increases. Transformers needed for a voltage conversion project experienced the largest cost increases. Also, labor increased at an inflated rate due to an increased need for lineworkers.
392 / 0502 B | Conv 12.5/7.2KV to 25/14.4KV Finney Rd (Ralph Morris West) | Project under construction and expenses are not fully captured.
395 / 1001 A | Conv 3Ph 1/0 ACSR to 3Ph 397 ACSR Donnelley Drive | The project estimate was generated in 2017. During Covid, mateial supply chain became strained leading to substantial material cost increases. Also, labor increased at an inflated rate due to an increased need for lineworkers. In addition, this was a double circuit project that we had little historical information on for estimating purposes.