## KY RP Summary
Company Code | RP Lines | FY 2024
1012 | A-New Mains | 764999.4803 |  | As part of the new capital governance changes, we are requesting for RP Lines A, B, D, L, N, Q, and R that you identify all projects in those RP lines that are greater than $100K.
1012 | B-Replaced Mains | 21585199.6973
1012 | C-Unscheduled Mains | 1762000.6212 | 1. Potential Program Overruns
1012 | D-Relocated Mains | 700000.4716 | · As soon as an Operating Company determines that they may exceed their approved capital budget in the current or the next calendar year, they need to communicate details of the potential overrun to the OWE CPM team.
1012 | E-New Hydrants & Valves | 435500.096 | · If, upon consultation with OWE, it is determined that the likelihood of exceeding budget is less than 50%, then it will be put “On Radar” report that is presented monthly to the Corporate CPM Committee.
1012 | F-Replaced Hydrants & Valves | 2326801.1017 | · If it is determined that the likelihood of exceeding budget is greater than 50%, then the Operating Company must receive a Contingent Approval for additional budget from the Corporate CPM before additional capital spending is committed.
1012 | G-New Services | 1247500.1266 | · Contingent Approval request must include a variance correction plan. Variance correction plan should include a plan to mitigate the overrun in the current budget year (Plan A) or over the course of the current and next budget years (Plan B)
1012 | H-Replaced Services | 1205000.6146 | · Each month thereafter, the likelihood of a budget exceedance should be reassessed, and the variance correction plan updated and submitted to OWE for reporting to the Corporate CPM Committee
1012 | I-New Meters | 45500.4356 | · If/when the likelihood of a budget overrun reaches 80% or higher, then the Operating Company needs to receive Approval from the Corporate CPM Committee before any further capital spending can be committed.
1012 | J-Replaced Meters | 13352671.62
1012 | K-ITS Equipment | 401589.3832
1012 | L-SCADA | 1058999.6343
1012 | M-Security | 735000.1301
1012 | N-Offices & Facilities | 813000.755
1012 | O-Vehicles | 1465622.8383
1012 | P-Tools & Equipment | 2151099.9081
1012 | Q-Production | 3438999.6475
1012 | S-Engineering Studies | 75000.3768
1012 |  | 53564486.9382

## 1012-KY
Company Code | Type of Project | Unique ID | Title | Responsible person | Total (5YP) | FY 2024 | FY 2025 | FY 2026 | FY 2027 | FY 2028 | Asset Code 1 | Purpose Code 1 | Priority
1012 | RP | R1202A009 | Providence Place Loop | Tyler Well | 3866999.9574 | 134999.9574 | 100000 | 1112000 | 750000 | 1770000 | 331 - TRANS & DISTRIBUTION MAINS | GROWTH/CAP IN FRANCHISE <3 YRS | Priority B
1012 | RP | R1202B008 | B2 QIP Main Replacements | Krista Citron | 196810253.1923 | 20149999.8423 | 42197640 | 43694019.4 | 45031538.95 | 45737055 | 331 - TRANS & DISTRIBUTION MAINS | ASSET RENEWAL POOR CONDITION | Priority A2
1012 | RP | R1202B010 | Blanket Main Replacements (non-QIP) | Krista Citron | 900249.7286 | 900249.7286 | 0 | 0 | 0 | 0 | 331 - TRANS & DISTRIBUTION MAINS | ASSET RENEWAL POOR CONDITION | Priority B
1012 | RP | R1202D008 | KYTC - Various Relocation Projects | Austin Thore | 6401500.4716 | 700000.4716 | 1416000 | 1426000 | 1397500 | 1462000 | 331 - TRANS & DISTRIBUTION MAINS | ASSET RENEWAL PROACTIVE MEASURE | B
1012 | RP | R1202L015 | KRS2 Igniition Software | Rick Witherite | 3153999.5575 | 805999.5575 | 557000 | 600000 | 794000 | 397000 | 346 - COMMUNICATION EQUIPMENT | REL/QUAL IMPROVED TECHNOLOGY | Priority B
1012 | RP | R1202M011 | Physical Security Card Access Life Cycle Replacement | Robert | 2624999.7508 | 524999.7508 | 525000 | 525000 | 525000 | 525000 | 339 - OTHER PLANT & MISC EQUIPMENT | SAFE/SECURE SAFETY | Priority C
1012 | RP | R1202N011 | KRS - equipment/salt storage shed | Shelley Porter | 3613000.3946 | 693000.3946 | 530000 | 485000 | 505000 | 1400000 | 304 - STRUCTURES AND IMPROVEMENTS | ADMIN AND OPERATIONAL SUPPORT | Priority A2
1012 | RP | R1202Q008 | RRS Dry Chemical Storage Building | Rick Witherite | 15179999.61 | 3029499.61 | 2686000 | 2797000 | 3205000 | 3462500 | 320 - WATER TREATMENT PLANT EQUIP | ASSET RENEWAL POOR CONDITION | Priority A2
1012 | RP | R1202S013 | Emerging studies/permit requirements | Krista Citron | 335000.3768 | 75000.3768 | 65000 | 65000 | 65000 | 65000 | 339 - OTHER PLANT & MISC EQUIPMENT | ADMIN AND OPERATIONAL SUPPORT | Priority A2
1012 | RP | R1203L011 | Rockcastle SCADA Spare Parts | Rick Witherite | 328999.9805 | 32999.9805 | 106000 | 96000 | 40000 | 54000 | 346 - COMMUNICATION EQUIPMENT | REL/QUAL IMPROVED TECHNOLOGY | Priority A2
1012 | RP | R1203Q012 | Tank Site Altitude Valves | Rick Witherite | 194999.991 | 39999.991 | 40000 | 40000 | 40000 | 35000 | 320 - WATER TREATMENT PLANT EQUIP | ASSET RENEWAL POOR CONDITION | Priority C
1012 | RP | R1204M010 | Remote Site Motorized Gate | Robert | 500000.1327 | 100000.1327 | 100000 | 100000 | 100000 | 100000 | 339 - OTHER PLANT & MISC EQUIPMENT | SAFE/SECURE SAFETY | Priority C
1012 | RP | R1230A008 | Old Sweet Owen Rd - Phase 3 | Tyler Well | 1278549.5229 | 629999.5229 | 648550 | 0 | 0 | 0 | 331 - TRANS & DISTRIBUTION MAINS | GROWTH/CAP IN FRANCHISE <3 YRS | Priority B
1012 | RP | R1230B009 | B2 QIP Main Replacements | Krista Citron | 1273280.1264 | 534950.1264 | 280830 | 147500 | 152500 | 157500 | 331 - TRANS & DISTRIBUTION MAINS | ASSET RENEWAL POOR CONDITION | Priority A2
1012 | RP | R1230L008 | Tank site upgrades | Rick Witherite | 299999.9769 | 59999.9769 | 20000 | 60000 | 60000 | 100000 | 346 - COMMUNICATION EQUIPMENT | REL/QUAL IMPROVED TECHNOLOGY | Priority B
1012 | RP | R1230N010 | Structure for outside material | Shelley Porter | 180000.1327 | 100000.1327 | 20000 | 20000 | 20000 | 20000 | 304 - STRUCTURES AND IMPROVEMENTS | ADMIN AND OPERATIONAL SUPPORT | Priority A2
1012 | RP | R1230Q009 | Northern valve replacements | Rick Witherite | 734999.86 | 139999.86 | 140000 | 140000 | 140000 | 175000 | 320 - WATER TREATMENT PLANT EQUIP | ASSET RENEWAL POOR CONDITION | Priority B
1012 | RP | R1233L009 | Scada upgrades | Rick Witherite | 189999.8394 | 39999.8394 | 10000 | 40000 | 50000 | 50000 | 346 - COMMUNICATION EQUIPMENT | REL/QUAL IMPROVED TECHNOLOGY | Priority B
1012 | RP | R1233M008 | Owenton WWTP Gate | Robert | 220000.1327 | 100000.1327 | 30000 | 30000 | 30000 | 30000 | 339 - OTHER PLANT & MISC EQUIPMENT | SAFE/SECURE SAFETY | Priority C
1012 | RP | R1233Q010 | lift station pump replacement | Rick Witherite | 630999.8406 | 126999.8406 | 124000 | 115000 | 100000 | 165000 | 320 - WATER TREATMENT PLANT EQUIP | ASSET RENEWAL POOR CONDITION | Priority B
1012 | RP | R1260Q013 | Effluent Air Line | Rick Witherite | 112499.5322 | 12499.5322 | 100000 | 0 | 0 | 0 | 320 - WATER TREATMENT PLANT EQUIP | ASSET RENEWAL POOR CONDITION | Priority C
1012 | RP | R1270L010 | Scada upgrades | Rick Witherite | 100000.3566 | 45000.3566 | 0 | 5000 | 0 | 50000 | 346 - COMMUNICATION EQUIPMENT | REL/QUAL IMPROVED TECHNOLOGY | Priority B
1012 | RP | R1270Q011 | add bar screen to inlet | Rick Witherite | 100500.3431 | 80000.3431 | 0 | 8000 | 0 | 12500 | 320 - WATER TREATMENT PLANT EQUIP | ASSET RENEWAL POOR CONDITION | Priority B

## 1012-KY 2024
Line | District | Justification | Title | WBS | Est. In-service date | FY 2024 Actual | FY 2024 Budget | Tolerance Level | Responsible person | Comments
A-New Mains | 1230-KY-North | Short term hydraulic improvements | Old Sweet Owen Rd - Phase 3 | R12-30A1.22-P-0003 | 2024-10-01 | 0 | 625000 | -100% | Tyler Well | Changed from $530k to $625k
A-New Mains | 1202-KY-Central | Short term hydraulic improvements | Shannon Run RD Loop | R12-02A1.23-P-0003 | 2024-06-15 | 0 | 218500 | -100% |  | Changed from $135k to $218.5k, and name changed from Providence Place Loop to Shannon Run RD Loop
B-Replaced Mains | 1202-KY-Central | Coordination with others (e.g., road is being repaved) | Blanket Main Replacements (non-QIP) | Multiple WBS | 2024-12-31 | 0 | 900250 | -100% |  | Likely to be 1-2 miles of main replacements in 2024 outside of QIP
B2-Replaced Mains | 1202-KY-Central | Critical customer impact; no longer providing expected level of service | B2 QIP Main Replacements | Multiple WBS |  | 0 | 20150000 | -100% | Austin | Track with QIP Tracking (off cycle program)
B2-Replaced Mains | 1230-KY-North | Critical customer impact; no longer providing expected level of service | B2 QIP Main Replacements |  |  | 0 | 534950 | -100%
D-Relocated Mains | 1202-KY-Central | Project is speculative | KYTC - Various Relocation Projects |  |  | 0 | 700000 | -100% |  | $1.5M New circle with $800k deposit
E-New Hydrants & Valves | 1202-KY-Central | Requested by local government | Hydrant(s) |  |  | 0 | 0 |  |  | Blanket, removed $105k from the list
E-New Hydrants & Valves | 1202-KY-Central | Horse Park Vaults | Manhole(s) | R12-02E1.24-P-0004 | 2024-04-30 | 0 | 175000 | -100% | John M. | Changed from $125k to $175K on Horse park Vaults
L-SCADA | 1202-KY-Central | New equipment that improves productivity | Central pressure monitoring stations |  |  | 0 | 0 |  | Dorothy Rader | this will be three separate projects of $55k each, remove $165k from list
L-SCADA | 1202-KY-Central | New equipment that improves productivity | KRS2 Igniition Software |  |  | 0 | 0 |  |  | postponed until 2029, replacing with other smaller projects, remove $300k from list
N-Offices & Facilities | 1202-KY-Central | Has reached the end of its expected life | Paving (Ops Center) |  |  | 0 | 80000 | -100% | Shelley | $165k Paving performed in 2023
N-Offices & Facilities | 1202-KY-Central | For new (additional) employees, equipment, or vehicles | KRS - equipment/salt storage shed |  |  | 0 | 248000 | -100% | Dorothy Rader | likely use funds for different smaller projects
P-Tools & Equipment | 1202-KY-Central | Has reached the end of its expected life | Mini Excavator - Trailer and Att. | R12-02P1.24-P-0010 | 2024-05-30 | 0 | 125000 | -100% | Justin | Expected April 2024 for excavator / May 2024 for trailer / Not ordered trailer
P-Tools & Equipment | 1202-KY-Central | Has reached the end of its expected life | Backhoe - Trailer and Att. | R12-02P1.24-P-0011 | 2024-05-30 | 0 | 150000 | -100% |  | Expected April 2024 for backhoe / May 2024 for trailer / Not ordered trailer
P-Tools & Equipment | 1202-KY-Central | Has reached the end of its expected life | Vac Trailer | R12-02P1.24-P-0008 / R12-02P1.24-P-0009 / R12-30P1.24-P-0002 | 2024-04-30 | 0 | 240000 | -100% |  | Changed from $180k to $240k for 3 Trailers / Expected April 2024
P-Tools & Equipment | 1202-KY-Central | Has reached the end of its expected life | Pit Launcher |  | 2024-09-30 | 0 | 120000 | -100% |  | Expected to order May 2024 and receive September 2024
P-Tools & Equipment | 1202-KY-Central | Has reached the end of its expected life | EZ Valve - Equipment and Trailer |  | 2024-09-30 | 0 | 200000 | -100% |  | Expected to order May 2024 and receive September 2024
P-Tools & Equipment | 1230-KY-North | Physically fails and not repairable, or in imminent danger of failure | Bore Machine |  |  | 0 | 0 |  |  | Remove $110k since we received boring machine in 2023
P-Tools & Equipment | 1202-KY-Central | Required to comply with regulations | Cellular pressure monitors |  |  | 0 | 175000 | -100% |  | Not started
P-Tools & Equipment | 1202-KY-Central | Required to comply with regulations | Permanet Leak Loggers | R12-02P1.24-P-0006 | 2024-03-15 | 0 | 112500 | -100% |  | Received March 2024 / Partial part of larger PO with additional spend
Q-Production | 1202-KY-Central | Physically fails, not repairable, or in imminent danger of failure | KRS2 sludge pump replacement |  |  | 0 | 254000 | -100% | Dorothy Rader | likely use funds for different smaller projects
Q-Production | 1202-KY-Central | Addresses imminent health and/or safety issues | RRS Dry Chemical Storage Building |  |  | 0 | 250000 | -100% |  | would like to combine, do quick design meeting, and see if maintenance building can be started for these dollars in 2024 & completed with 2025 dollars.
Q-Production | 1202-KY-Central | Provides increased reliability or operating flexibility of critical assets | RRS Maintenance Building |  |  | 0 | 200000 | -100%
Q-Production | 1202-KY-Central | Physically fails, not repairable, or in imminent danger of failure | KRS Expand Supernatant Pit Capacity & Pumps |  |  | 0 | 200000 | -100% |  | likely use funds for different smaller projects
Q-Production | 1202-KY-Central | Proactive replacement based on age, condition, or new technology | KRS1 Low Service Pump Rebuilds |  |  | 0 | 150000 | -100% |  | likely use funds for different smaller projects
Q-Production | 1202-KY-Central | Proactive replacement based on age, condition, or new technology | Intake Pump/Motor KRS |  |  | 0 | 125000 | -100% |  | likely use funds for different smaller projects