## Sheet1
| DUKE ENERGY KENTUCKY | [6 empty] | SCHEDULE H
CASE NO. 2022-00125
CONSTRUCTION WORK IN PROGRESS - PERCENT COMPLETE
AS OF AUGUST 31, 2024
Line No. (A) | Project No. (B) | Date Construction Work Began (C) | Estimated Project Completion Date (D) | Percent of Elapsed Time (E) | Original Budget Estimate (F) | Most Recent Budget Estimate (G) | Total Project Expenditures (H) | Percent of Total Expenditures (I) = (H/G)
1 | 04000156 | 2023-01-01 | 2026-12-31 | 41.64% | 599758 | 599758 | 390531.76 | 65.11%
2 | 107GASCK | 2008-07-01 | 2050-12-31 | 38.04% | 0 | 0 | 3340284.274
3 | 315986HW6 | 2020-03-01 | 2021-03-15 | 100% | 21350 | 70339.6 | 1.79 | 0.002545%
4 | 315986HW7 | 2021-04-01 | 2021-12-31 | 100% | 62454 | 62454 | 4.89 | 0.00783%
5 | 315986HW8 | 2021-10-01 | 2022-06-30 | 100% | 67100 | 37341.41 | -11.85 | -0.03173%
6 | 344598001 | 2018-04-01 | 2020-01-28 | 100% | 197081 | 151374.22 | 1015.5 | 0.6709%
7 | 349472021 | 2022-06-01 | 2026-03-31 | 58.76% | 3263 | 4713 | 9747.93 | 206.8%
8 | 349472028 | 2023-04-01 | 2026-03-31 | 47.31% | 3108 | 9670 | 19477.15 | 201.4%
9 | 349472029 | 2023-04-01 | 2026-03-31 | 47.31% | 7238 | 19914 | 32870.57 | 165.1%
10 | 349472032 | 2024-02-01 | 2026-03-31 | 26.87% | 8290 | 8290 | 6595.38 | 79.56%
11 | 349472033 | 2024-01-01 | 2026-03-31 | 29.63% | 5175 | 4834 | 8460.29 | 175%
12 | 349472034 | 2024-02-01 | 2026-03-31 | 26.87% | 20523 | 31355 | 3674.68 | 11.72%
13 | 400055029 | 2023-10-01 | 2025-06-29 | 52.59% | 77856 | 77856 | 57362.5 | 73.68%
14 | 400055030 | 2023-11-01 | 2025-09-30 | 43.49% | 196273 | 212277 | 36612.73 | 17.25%
15 | 400055031 | 2023-11-01 | 2025-06-29 | 50.17% | 22654 | 22654 | 14494.41 | 63.98%
16 | 400055032 | 2023-11-01 | 2025-07-30 | 47.72% | 42720 | 42720 | 47279.92 | 110.7%
17 | 400055038 | 2024-05-01 | 2026-03-31 | 17.45% | 573597 | 573597 | 12660.43 | 2.207%
18 | 400055039 | 2024-07-01 | 2024-09-29 | 67.78% | 21907 | 21907 | 21774.54 | 99.4%
19 | 400055040 | 2024-06-01 | 2026-03-31 | 13.62% | 49003 | 49003 | 1111.85 | 2.269%
20 | 400055041 | 2024-06-01 | 2026-03-31 | 13.62% | 109160 | 109160 | 8019.48 | 7.347%
21 | 400109M | 2023-06-01 | 2025-03-31 | 68.31% | 135363 | 3629.56 | 15038.83 | 414.3%
22 | 400149HW2 | 2023-08-01 | 2026-03-31 | 40.7% | 2282 | 2282 | 1949.06 | 85.41%
23 | 400149SW2 | 2024-01-01 | 2026-03-31 | 29.63% | 4067 | 4067 | 1634.96 | 40.2%
24 | 400154001 | 2024-01-01 | 2025-12-29 | 33.38% | 97995 | 97995 | 43618.92 | 44.51%
25 | 400161002 | 2024-06-01 | 2025-01-30 | 37.45% | 28490 | 28490 | 25884.98 | 90.86%
26 | 43848219 | 2022-07-01 | 2026-03-31 | 57.85% | 40000 | 40000 | 3302.46 | 8.256%
27 | AW0938 | 2019-10-01 | 2021-03-02 | 100% | 64259 | 108082.22 | -1737.22 | -1.607%
28 | AW3186 | 2021-11-01 | 2025-11-27 | 69.54% | 948400 | 948400 | 633186.74 | 66.76%
29 | AW3192 | 2021-09-01 | 2025-12-30 | 69.26% | 538800 | 538800 | 602872.38 | 111.9%
30 | AW3224 | 2021-07-01 | 2025-10-30 | 73.14% | 732000 | 732000 | 913578.93 | 124.8%
31 | AW3227 | 2021-11-01 | 2025-10-30 | 70.87% | 1062400 | 1062400 | 1493803.72 | 140.6%
32 | AW3230 | 2021-08-01 | 2025-11-27 | 71.31% | 82500 | 82500 | 54588.89 | 66.17%
33 | AW3246 | 2021-04-01 | 2026-03-31 | 68.38% | 82500 | 82500 | 100129.12 | 121.4%
34 | AW3250 | 2021-06-01 | 2025-11-29 | 72.29% | 82500 | 82500 | 26609.83 | 32.25%
35 | AW3690 | 2021-06-01 | 2025-10-25 | 73.86% | 82500 | 82500 | 50383.96 | 61.07%
36 | AW4685 | 2021-11-01 | 2025-02-28 | 85.1% | 33015500 | 45768732.04 | 31008763.21 | 67.75%
37 | AW4691 | 2021-12-01 | 2022-06-30 | 100% | 120000 | 120000 | 346112.05 | 288.4%
38 | AW4778 | 2022-07-01 | 2026-11-30 | 49.1% | 926800 | 926800 | 163217.25 | 17.61%
39 | AW4796 | 2022-02-01 | 2026-11-30 | 53.43% | 7884400 | 7884400 | 713723.25 | 9.052%
40 | AW5064 | 2022-08-01 | 2025-09-30 | 65.83% | 272000 | 272000 | 237747.24 | 87.41%
41 | AW5957 | 2022-10-01 | 2025-02-28 | 79.46% | 9656000 | 9656000 | 45725.86 | 0.4735%
42 | AW6146 | 2022-10-01 | 2023-12-31 | 100% | 25000 | 25000 | 4447.69 | 17.79%
43 | AW6387 | 2023-01-01 | 2025-12-31 | 55.53% | 40828200 | 40828200 | 2562514.44 | 6.276%
44 | AW6388 | 2023-09-01 | 2025-12-31 | 42.84% | 4060000 | 4060000 | 1408493.53 | 34.69%
45 | AW6415 | 2023-01-01 | 2023-07-14 | 100% | 25000 | 25000 | 6739.46 | 26.96%
46 | AW6482 | 2023-02-01 | 2023-08-25 | 100% | 25000 | 25000 | 4176.01 | 16.7%
47 | AW6483 | 2023-02-01 | 2023-04-28 | 100% | 25000 | 25000 | 4227.19 | 16.91%
48 | AW6484 | 2023-02-01 | 2023-10-13 | 100% | 25000 | 25000 | 674.56 | 2.698%
49 | AW6694 | 2023-03-01 | 2023-06-09 | 100% | 25000 | 25000 | 2769.92 | 11.08%
50 | AW6846 | 2023-07-01 | 2025-09-30 | 51.95% | 180000 | 180000 | 373705.81 | 207.6%
51 | AW7013 | 2023-09-01 | 2025-04-18 | 61.34% | 4284600 | 4284600 | 334242.64 | 7.801%
52 | AW7772 | 2024-01-01 | 2025-12-31 | 33.29% | 4905200 | 4905200 | 546867.53 | 11.15%
53 | AW78502 | 2024-08-01 | 2024-12-05 | 23.81% | 99000 | 99000 | 159210.34 | 160.8%
54 | AW7866 | 2024-02-01 | 2027-03-30 | 18.39% | 60559700 | 60559700 | 361192.48 | 0.5964%
55 | AW8410 | 2024-07-01 | 2026-03-31 | 9.561% | 11169500 | 11169500 | 2088681.87 | 18.7%
56 | CGRREPLA | 2023-04-01 | 2050-12-31 | 5.11% | 0 | 0 | 55030.67
57 | G0224 | 2010-08-01 | 2018-10-01 | 100% | 99 | 482.48 | 482.48 | 100%
58 | GASKYIND | 2008-07-01 | 2050-12-31 | 38.04% | 0 | 0 | 822.78
59 | GCPBUDKY | 2023-05-01 | 2050-12-31 | 4.829% | 0 | 0 | 13358.45
60 | GCTA30062 | 2017-09-01 | 2019-10-30 | 100% | 133026 | 133026 | -10619.25 | -7.983%
61 | IT2200160 | 2023-01-01 | 2027-03-30 | 39.25% | 76081 | 185731.65 | 21616.83 | 11.64%
62 | IT2200165 | 2023-01-01 | 2026-03-31 | 51.31% | 57231 | 125985 | 7752.42 | 6.153%
63 | IT2300096 | 2024-01-01 | 2026-06-29 | 26.7% | 75811 | 75811 | 1918.75 | 2.531%
64 | IT2300097 | 2024-03-01 | 2025-03-31 | 46.33% | 15803 | 15803 | 7865.22 | 49.77%
65 | IT2300098 | 2024-01-01 | 2025-05-28 | 47.37% | 41810 | 41810 | 2777.92 | 6.644%
66 | IT2300102 | 2024-01-01 | 2026-06-29 | 26.7% | 336772 | 336772 | 58511.66 | 17.37%
67 | IT2300103 | 2024-02-01 | 2027-03-31 | 18.37% | 229894 | 229894 | 11813.96 | 5.139%
68 | IT2400006 | 2024-02-01 | 2025-03-31 | 50% | 50039 | 50039 | 201.13 | 0.4019%
69 | IT2400022 | 2024-05-01 | 2025-06-29 | 28.77% | 33919 | 33919 | 7494.31 | 22.09%
70 | IT2400024 | 2024-06-01 | 2025-04-30 | 27.33% | 22730 | 22730 | 4766.81 | 20.97%
71 | KYWSREF24 | 2024-06-01 | 2026-02-28 | 14.29% | 200000 | 200000 | 387282.43 | 193.6%
72 | LTHGIRFS | 2020-06-01 | 2025-03-01 | 89.5% | 0 | 218641 | 547882.7 | 250.6%
73 | LTHNGBUDP | 2024-01-01 | 2025-02-28 | 57.31% | 91438 | 91438 | 49579.1 | 54.22%
74 | MDTGAS20 | 2019-12-01 | 2021-03-31 | 100% | 403995 | 403995 | 368.55 | 0.09123%
75 | MX0356982 | 2024-02-01 | 2026-02-05 | 28.84% | 278044.58 | 278044.58 | 138276.04 | 49.73%
76 | MX1322454 | 2022-10-01 | 2025-10-29 | 62.28% | 786869.97 | 1018417.85 | 542965.79 | 53.31%
77 | MX1415972 | 2023-02-01 | 2025-06-26 | 65.87% | 2073615.27 | 4037204.03 | 1239456.52 | 30.7%
78 | MX2217622 | 2017-10-01 | 2025-11-30 | 84.71% | 87907.04 | 87907.04 | 436512.62 | 496.6%
79 | MX2334412 | 2024-03-01 | 2025-11-06 | 29.76% | 0 | 0 | 6456.52
80 | MX2532997 | 2024-02-01 | 2025-06-26 | 41.49% | 143363.15 | 190970.15 | 27800.65 | 14.56%
81 | MX2781786 | 2021-06-01 | 2023-11-22 | 100% | 70082.56 | 50203.96 | -539.07 | -1.074%
82 | MX3119117 | 2024-05-01 | 2025-02-20 | 41.36% | 33684.62 | 72084.78 | 5350.67 | 7.423%
83 | MX3471260 | 2024-08-01 | 2025-01-13 | 18.18% | 23780.45 | 38814.59 | 2255.69 | 5.811%
84 | MX3584545 | 2024-06-01 | 2025-04-13 | 28.8% | 131448.69 | 477776.21 | 66899.73 | 14%
85 | MX3848219 | 2024-05-01 | 2025-10-02 | 23.51% | 540783.33 | 540783.33 | 7387.91 | 1.366%
86 | MX4669122 | 2021-03-01 | 2027-03-04 | 58.3% | 765.33 | 765.33 | 161639.54 | 21120%
87 | MX6650945 | 2023-02-01 | 2025-02-27 | 76.22% | 251700.17 | 1114428.69 | 796445.12 | 71.47%
88 | MX7281845 | 2020-07-01 | 2021-03-31 | 100% | 44953.52 | 5000 | -59.88 | -1.198%
89 | MX8175168 | 2019-11-01 | 2021-03-31 | 100% | 62696 | 62696 | -1.19 | -0.001898%
90 | MX9219249 | 2022-11-01 | 2026-03-12 | 54.52% | 765.33 | 765.33 | 95433.66 | 12470%
91 | OMGPCVNTN | 2012-08-01 | 2026-12-31 | 83.82% | 0 | 0 | 225
92 | OMGPNWPRT | 2012-08-01 | 2051-03-31 | 31.25% | 0 | 0 | 270
93 | PH2ASPAHW | 2023-10-01 | 2026-03-31 | 36.73% | 3196 | 3196 | 1761.15 | 55.1%
94 | PH2ASPASW | 2023-09-01 | 2026-03-31 | 38.75% | 323116 | 323116 | 45494.89 | 14.08%
95 | R8822 | 2016-05-01 | 2017-08-01 | 100% | 67177.92 | 67177.92 | 176.97 | 0.2634%
96 | SG489SW | 2016-11-01 | 2018-12-31 | 100% | 16065.37 | 16065.37 | 46.58 | 0.2899%
97 | SG781SW | 2018-07-01 | 2021-03-31 | 100% | 76873.76 | 78060.75 | 143.54 | 0.1839%
98 | T9338 | 2017-09-01 | 2018-09-01 | 100% | 116006.88 | 116006.88 | 3334.83 | 2.875%
99 | V8967 | 2019-06-01 | 2020-10-30 | 100% | 244737.99 | 381376.84 | -2797.52 | -0.7335%