## 2020
Duke Energy Kentucky Natural Gas
Year 2020
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | FARCOSSW | ARCOS21 | ARCOS21 - ARCOS RENEWAL | 59326.81 |  | 59326.81 |  |  | 59326.81 | 59327 | -0.19 | 2020-12-17 10:40 | 2021-09-30 | 2020-12-01 | 2021-04-25
75086 | FENABLES | MOBS | MOBS - ENABLE MOBILITY SOFTWARE | -5.5 |  | -5.5 |  |  | 729169.83 | 649497 | 79672.83 | 2015-03-30 16:46 | 2017-10-31 | 2015-05-01 | 2017-11-07
75086 | FMDT2017 | MDTKE17 | MDTKE17 - CF53 PURCHASES FOR MDT REPLAC | 274.98 |  | 274.98 |  |  | 30922.55 | 33851 | -2928.45 | 2018-02-07 15:38 | 2020-06-01 | 2018-02-01 | 2020-05-01
75086 | FMDT2020 | MDTGAS20 | MDTGAS20 - INSTALL WIN 7 PANASONIC TOUGHBOOKS | 160648.5 |  | 160648.5 |  |  | 464843.86 | 403995 | 60848.86 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01 | 2021-03-31
75086 | FP647 | V5213 | V5213 - AM07 CASING REM 647 ERLANGER RD | 39887.14 |  | 39887.14 |  |  | 114174.86 | 115206.73 | -1031.87 | 2018-08-22 09:19 | 2019-03-30 | 2018-09-01 | 2018-11-23
75086 | FPIT | 338802003 | 338802003 - EAM PLATFORM OPTIMIZATION | 484.76 |  | 484.76 |  |  | 40924.68 | 147321.02 | -106396.34 | 2018-04-25 14:30 | 2020-05-30 | 2018-06-01 | 2020-03-31
75086 | FPIT | 338802004 | 338802004 - MOBILE DURABLE TEAM | 26076.87 |  | 26076.87 |  |  | 127363.93 | 52783 | 74580.93 | 2018-09-17 12:23 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802005 | 338802005 - MAXIMO DURABLE TEAM | 2415.54 |  | 2415.54 |  |  | 163191.11 | 33459 | 129732.11 | 2018-09-13 15:18 | 2020-05-28 | 2018-10-01 | 2020-05-28
75086 | FPIT | 338802006 | 338802006 - SMALLWORLD/MYWORLD DURABLE TEAM | -332.6 |  | -332.6 |  |  | 10.99 | 48911 | -48900.01 | 2018-09-06 13:43 | 2020-05-28 | 2018-10-01 | 2020-11-10
75086 | FPIT | 338802008 | 338802008 - ECOSYS DURABLE TEAM ACCIUNTING | -431.31 |  | -431.31 |  |  | 1196.89 | 52026 | -50829.11 | 2018-09-13 10:17 | 2020-03-30 | 2018-09-01 | 2020-03-30
75086 | FPIT | 338802HW3 | 338802HW3 - EAM PLATFORM OPTIMIZATION | 4.09 |  | 4.09 |  |  | 4.09 | 59872 | -59867.91 | 2018-04-25 14:36 | 2019-10-31 | 2020-07-01 | 2020-03-31
75086 | FPIT | 349472HW1 | 349472HW1 - MULTI-INSTANCE OF SERVICE SUITE | 5095.77 |  | 5095.77 |  |  | 5095.77 | 13125 | -8029.23 | 2020-03-06 11:31 | 2020-11-29 | 2020-03-01 | 2020-11-29
75086 | FPIT | 349472SW1 | 349472SW1 - MULTI-INSTANCE OF SERVICE SUITE | 17546.98 |  | 17546.98 |  |  | 17546.98 | 36419 | -18872.02 | 2020-03-06 09:55 | 2020-11-29 | 2020-03-01 | 2020-11-29
75086 | FPIT | 359990001 | 359990001 - FIELD TEST EQUIPMENT CALIBRATION SO | 438.56 |  | 438.56 |  |  | 67643.76 | 60858 | 6785.76 | 2019-02-26 15:25 | 2019-12-29 | 2019-03-01 | 2019-12-01
75086 | FPIT | CC2000001 | CC2000001 - NGBU COMMUNICATIONS PLATFORM | 24951.31 |  | 24951.31 |  |  | 24951.31 | 1242489 | -1217537.69 | 2020-03-30 13:53 | 2022-03-31 | 2020-04-01 | 2022-03-31
75086 | FPIT | GCTA30060 | GCTA30060 - CONSOLIDATED SCADA APP ANALYSIS | 54017.81 |  | 54017.81 |  |  | 277625.14 | 149205 | 128420.14 | 2017-04-11 15:19 | 2020-06-30 | 2017-04-01 | 2020-06-30
75086 | FPIT | GCTA3006K | GCTA3006K - INTGO_PI SCADA DATA IMPLEMENTATION | 991.52 |  | 991.52 |  |  | 89187 | 133026 | -43839 | 2019-11-15 07:17 | 2022-03-17 | 2019-11-01 | 2022-03-01
75086 | FPIT | GCTA30073 | GCTA30073 - PROJECT 2 GAS SUPPLY SYSTEM | 57553.73 |  | 57553.73 |  |  | 742883.59 | 853149 | -110265.41 | 2017-03-30 17:09 | 2021-03-31 | 2017-07-01 | 2021-03-31
75086 | FPIT | GCTA30114 | GCTA30114 - SALES FORCE AUTOMATION CONSO STRATE | 54387.33 |  | 54387.33 |  |  | 263901.12 | 0 | 263901.12 | 2017-06-21 11:37 | 2020-11-30 | 2017-10-01 | 2020-11-10
75086 | FPIT | GCTA30391 | GCTA30391 - INTGO_GAS MAJOR PROJECTS MGMT | 59027.81 |  | 59027.81 |  |  | 83440.11 | 224469 | -141028.89 | 2018-12-18 14:49 | 2020-12-30 | 2019-01-01 | 2020-12-31
75086 | FPIT | GCTA30436 | GCTA30436 - INTGO_GAS SCADA CONSOLIDATION PROGR | -733.27 |  | -733.27 |  |  | 607213.62 | 513619 | 93594.62 | 2018-05-21 15:50 | 2019-12-29 | 2018-06-01 | 2019-12-01
75086 | FPIT | GCTA33039 | GCTA33039 - INTGO_CONSOLIDATED CAD TOOLS | 51.42 |  | 51.42 |  |  | 56439.63 | 120205 | -63765.37 | 2018-06-19 11:18 | 2020-09-24 | 2018-08-01 | 2020-03-31
75086 | FPIT | GCTA47001 | GCTA47001 - INTGO_MATERIALS TRACEABILITY | 57723.94 |  | 57723.94 |  |  | 101557.81 | 120205 | -18647.19 | 2018-12-06 14:57 | 2022-03-31 | 2019-01-01 | 2020-05-31
75086 | FPIT | GCTA4700B | GCTA4700B - INTGO_TRACEABILITY FORM FDC | 23695.56 |  | 23695.56 |  |  | 105920.1 | 215691 | -109770.9 | 2018-12-06 13:26 | 2021-03-31 | 2018-12-01 | 2021-03-14
75086 | FPIT | IT1900021 | IT1900021 - GIS ALIGNMENT FOR PCS - MIDWEST | 120582.31 |  | 120582.31 |  |  | 237430.41 | 485841 | -248410.59 | 2019-08-01 11:16 | 2021-01-31 | 2019-09-01 | 2021-01-17
75086 | FPIT | IT1900065 | IT1900065 - GDPM PHASE 2 | 69068.69 |  | 69068.69 |  |  | 69068.69 | 87832 | -18763.31 | 2020-02-07 07:49 | 2021-03-31 | 2020-02-01 | 2021-03-31
75086 | FPIT | IT1900067 | IT1900067 - ARM TO MAXIMO INTEGRATION | 1053.21 |  | 1053.21 |  |  | 1053.21 | 0 | 1053.21 | 2020-10-12 17:08 | 2021-07-31 | 2020-10-01 | 2021-07-27
75086 | FPIT | IT1900069 | IT1900069 - TRG - WAM MEASUREMENT PROJECT | 27545.21 |  | 27545.21 |  |  | 27545.21 | 65041 | -37495.79 | 2020-02-21 15:10 | 2021-12-31 | 2020-03-01
75086 | FPIT | IT1900073 | IT1900073 - EAM 2020 MOBILE DURABLE TEAM | 73236.57 |  | 73236.57 |  |  | 73236.57 | 36572 | 36664.57 | 2020-01-20 08:44 | 2021-05-30 | 2020-01-01 | 2021-06-08
75086 | FPIT | IT1900074 | IT1900074 - EAM 2020 MAXIMO DURABLE TEAM | 184717.28 |  | 184717.28 |  |  | 184717.28 | 229288 | -44570.72 | 2020-01-20 10:57 | 2021-05-30 | 2020-01-01 | 2021-06-08
75086 | FPIT | LTHWOOPS | LTHWOOPS - LIGHTHOUSE:WO OPTIMIZATION GAS- SW | -3270.36 |  | -3270.36 |  |  | 28418.37 | 24900 | 3518.37 | 2019-03-12 15:21 | 2019-12-29 | 2019-03-01 | 2019-09-30
75086 | FPIT | V5136 | V5136 - COMMUNICATION RADIO INSTALL | 239.61 |  | 239.61 |  |  | 27590.03 | 23120 | 4470.03 | 2018-08-20 08:22 | 2018-12-31 | 2018-08-01 | 2019-07-31
75086 | FUNCTOHKY | 107GASCK | 107GASCK - GAS CAPITAL OVERHEAD | 316382.58 |  | 316382.58 |  |  | 531208.264 | 0 | 531208.264 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G71373 | AW0856 | AW0856 - 1373 US 27 BRIDGE ATTACHMENT | -3553.73 |  | -3553.73 |  |  | 67520.89 | 91770 | -24249.11 | 2019-07-30 08:26 | 2020-02-25 | 2019-11-01 | 2020-03-30
75086 | G7237BEAV | MX7783733 | MX7783733 - BEAVER RD INSTALL REPLACEMENT PROJE | 15890.83 |  | 15890.83 |  |  | 15890.83 | 48085 | -32194.17 | 2020-08-17 10:01 | 2020-10-30 | 2020-08-01 | 2021-01-10
75086 | G73701 | V8405 | V8405 - BRIDGE ATTACH 3701 NARROWS RD | -508.06 |  | -508.06 |  |  | 12718.01 | 11495.55 | 1222.46 | 2019-02-18 10:01 | 2020-02-25 | 2019-09-01 | 2019-12-18
75086 | G73MILES | T1437 | T1437 - STA 249: THREE MILE RD | 11898463.92 |  | 11898463.92 |  |  | 25443361.83 | 15406228 | 10037133.83 | 2017-01-05 11:19 | 2020-08-28 | 2017-01-01 | 2020-09-15
75086 | G73MILES | T1437LAND | T1437LAND - 3 MILE STATION (LAND) | 17706.6 |  | 17706.6 |  |  | 20326.12 | 40000 | -19673.88 | 2018-06-22 15:02 | 2020-07-28 | 2018-09-01 | 2020-09-15
75086 | G73MILES | T4422 | T4422 - AM07 BARLEYCORNS | -3189.46 |  | -3189.46 |  |  | 218355.9 | 190195.2 | 28160.7 | 2017-03-22 16:39 | 2020-07-28 | 2017-04-01 | 2019-12-01
75086 | G7AM07CUT | AW1330 | AW1330 - AM07 CUTOUT FIDELITY | 1298962.33 |  | 1298962.33 |  |  | 1607709.8 | 1236780 | 370929.8 | 2019-10-23 11:50 | 2019-12-30 | 2019-10-01 | 2020-02-02
75086 | G7AM07DIG | V8815 | V8815 - LINE AM07 INTEGRITY DIGS | 63305.46 |  | 63305.46 |  |  | 1306990.31 | 923350 | 383640.31 | 2019-04-02 12:33 | 2019-12-30 | 2019-06-01 | 2019-12-31
75086 | G7AM07ILI | 0233100 | 0233100 - LINE AM07 PIPELINE REPLACEMENT PHAS | 1433.07 |  | 1433.07 |  |  | 1433.07 | 37717000 | -37715566.93 | 2020-12-09 14:11 | 2023-12-31 | 2020-12-01 | 2024-03-18
75086 | G7ASDD | MX5515912 | MX5515912 - AMAZON SOUTHWEST DELIVERY DIST. PRO | 56387.87 |  | 56387.87 |  |  | 56387.87 | 307485 | -251097.13 | 2020-04-16 18:01 | 2020-10-11 | 2020-05-01 | 2021-04-04
75086 | G7ASRP | CMSP70 | CMSP70 - ASRP CURB TO METER 3" OR LESS | 8101.25 |  | 8101.25 |  |  | 8879432.76 | 20388002 | -11508569.24 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | G7ASRP | LCMSP70 | LCMSP70 - ASRP GREATER THAN 2" C-M INSTALL | 74283.42 |  | 74283.42 |  |  | -184758.65 | 10000000 | -10184758.65 | 2016-01-13 11:25 | 2019-12-31 | 2016-07-01
75086 | G7ASRP | MCSP70 | MCSP70 - ASRP MAIN TO CURB 3" OR LESS | 670516.98 |  | 670516.98 |  |  | 41392310.97 | 19954384 | 21437926.97 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | G7CAS106 | V7737 | V7737 - CASING#106 AM07 & MARTHA LAYNE | -187023.53 |  | -187023.53 |  |  | 1989733.46 | 1749344 | 240389.46 | 2018-11-28 14:40 | 2019-12-30 | 2018-12-01 | 2020-01-23
75086 | G7CAS106 | V7738 | V7738 - CASING#106 AM07 & MARTHA LAYNE(LAND | 16857.21 |  | 16857.21 |  |  | 113350.22 | 10000 | 103350.22 | 2018-11-28 14:46 | 2019-12-30 | 2019-01-01 | 2020-01-23
75086 | G7CAS112 | V4266 | V4266 - CASING 112 LINE AM07 | 9734.26 |  | 9734.26 |  |  | 263442.7 | 257083 | 6359.7 | 2018-08-02 14:00 | 2018-12-30 | 2018-08-01 | 2019-01-22
75086 | G7CAS22 | V4278 | V4278 - CASING 22 LINE AM07 | 9637.88 |  | 9637.88 |  |  | 251558.98 | 311445 | -59886.02 | 2018-08-02 16:45 | 2018-12-30 | 2018-08-01 | 2019-01-01
75086 | G7CAS42 | V7739 | V7739 - CASING#42 ABANDON- AM07 & HULBERT | -16773.81 |  | -16773.81 |  |  | 1698133.71 | 1939294 | -241160.29 | 2018-11-28 14:52 | 2019-11-30 | 2018-12-01 | 2019-11-15
75086 | G7CAS49 | V7902 | V7902 - CASING #49 ABANDON - AM07 & I-75 | 354155.85 |  | 354155.85 |  |  | 7336064.29 | 6131715 | 1204349.29 | 2018-12-14 14:26 | 2020-02-28 | 2019-01-01 | 2020-02-23
75086 | G7CAS53 | V5417 | V5417 - CASING 53 LINE AM07 | 2348.92 |  | 2348.92 |  |  | 88813.8 | 409578 | -320764.2 | 2018-08-29 07:10 | 2018-12-30 | 2018-10-01 | 2019-03-01
75086 | G7CAS717 | V7904 | V7904 - CASING #717 LINE AM07 -US RT 50 | 9389.43 |  | 9389.43 |  |  | 410518.55 | 2072166 | -1661647.45 | 2018-12-14 14:36 | 2019-07-25 | 2019-01-01 | 2019-08-21
75086 | G7CAS717 | V8640 | V8640 - CASING #717 LINEAM074-USRT50 LAND | 11229.28 |  | 11229.28 |  |  | 11229.28 | 15000 | -3770.72 | 2019-03-14 08:00 | 2020-09-25 | 2020-02-01 | 2019-08-21
75086 | G7ECOMPLX | V8967 | V8967 - ERLANGER MODULAR COMPLEX | 185878.01 |  | 185878.01 |  |  | 206914.85 | 244737.99 | -37823.14 | 2019-04-17 13:32 | 2020-10-30 | 2019-06-01 | 2022-01-30
75086 | G7EPROPAN | V9131 | V9131 - ERLANGER OPP | 11124.29 |  | 11124.29 |  |  | 323087.82 | 954130.54 | -631042.72 | 2019-05-03 10:23 | 2020-03-30 | 2019-08-01 | 2020-10-31
75086 | G7EQUIP | V8884 | V8884 - KET NGBU EQUIPMENT | 15878.16 |  | 15878.16 |  |  | 33332.67 | 150768 | -117435.33 | 2019-04-11 08:23 | 2020-03-30 | 2019-06-01 | 2020-02-29
75086 | G7ERLCP | AW1656 | AW1656 - ERLANGER MAG ANODES | 485978.94 |  | 485978.94 |  |  | 485978.94 | 2442881.69 | -1956902.75 | 2020-01-21 15:36 | 2026-12-31 | 2020-04-01
75086 | G7ERLCP19 | V9157 | V9157 - 2019 ERLANGER OPS MAG ANODES | 39694.74 |  | 39694.74 |  |  | 390344.41 | 350811.63 | 39532.78 | 2019-05-08 10:16 | 2020-07-30 | 2019-05-01 | 2020-09-08
75086 | G7ERLREC | AW1547 | AW1547 - ERLANGER RECTIFIER REMOTE MONITOR I | 56423.61 |  | 56423.61 |  |  | 56423.61 | 60320.29 | -3896.68 | 2019-12-11 14:42 | 2020-12-31 | 2020-02-01 | 2020-09-08
75086 | G7EUL06 | V5625 | V5625 - ECDA LINE UL06 | 25760.68 |  | 25760.68 |  |  | 327140.48 | 494420 | -167279.52 | 2018-09-10 09:20 | 2019-03-30 | 2018-10-01 | 2019-03-17
75086 | G7EUL47 | V6391 | V6391 - LINE UL47 SCHEDULED DIGS | 956.89 |  | 956.89 |  |  | 989422.73 | 724400 | 265022.73 | 2018-10-10 08:17 | 2019-03-30 | 2018-10-01 | 2019-03-14
75086 | G7FRAME | G9421 | G9421 - FRAME RELAY KENTUCKY | -1000.51 |  | -1000.51 |  |  | 47574.92 | 190202.72 | -142627.8 | 2013-02-01 | 2014-06-30 | 2013-02-01 | 2014-12-01
75086 | G7HMISTAT | AW0938 | AW0938 - HMI WORK STATION ERLANGER | 83932.99 |  | 83932.99 |  |  | 88911.33 | 64259 | 24652.33 | 2019-08-09 13:08 | 2021-03-02 | 2019-10-01 | 2021-08-15
75086 | G7IMPRPL | MX1996777 | MX1996777 - AM07 EXPOSURE-HORSEBRANCH RD. SEGME | -14794.79 |  | -14794.79 |  |  | 797515.02 | 436474.83 | 361040.19 | 2017-09-11 18:02 | 2019-07-31 | 2017-10-01 | 2019-09-10
75086 | G7IMPRPL | R0978 | R0978 - AM07 PRESSURE TEST WP18 | -1848.08 |  | -1848.08 |  |  | 2871251.41 | 105161.63 | 2766089.78 | 2015-07-06 16:33 | 2018-01-01 | 2015-09-01 | 2017-10-08
75086 | G7IMPRPL | R0981 | R0981 - WP23 "AM07" PRESSURE TEST | 139.83 |  | 139.83 |  |  | 841317.78 | 98206.56 | 743111.22 | 2015-07-06 16:45 | 2017-02-28 | 2016-02-01 | 2016-10-20
75086 | G7IMPRPL | R4858 | R4858 - AM-09 SEGMENT 3700 MAIN RPL | 3691.66 |  | 3691.66 |  |  | 1573982.22 | 367588.8 | 1206393.42 | 2015-12-02 14:32 | 2016-12-15 | 2015-12-01 | 2017-02-01
75086 | G7INTDIG | AW2017 | AW2017 - LINE UL06 INTEGRITY DIGS | 1388557.63 |  | 1388557.63 |  |  | 1388557.63 | 2024700 | -636142.37 | 2020-04-09 07:34 | 2021-01-30 | 2020-04-01 | 2021-01-05
75086 | G7INTDIG | AW2018 | AW2018 - LINE UL47 INTEGRITY DIGS | 837382.06 |  | 837382.06 |  |  | 837382.06 | 748000 | 89382.06 | 2020-04-09 07:40 | 2021-01-30 | 2020-04-01 | 2020-10-09
75086 | G7LGMR | B8625 | B8625 - REG-9 IMPROVEMENTS/CWA | -848.36 |  | -848.36 |  |  | -848.36 | 0 | -848.36 | 2004-07-11 | 2050-12-31 | 2004-08-01 | 2006-01-14
75086 | G7LGMR | D3747 | D3747 - REG 112K-WATERWORKS/CWA | -5400.3 |  | -5400.3 |  |  | 32561.53 | 0 | 32561.53 | 2008-06-26 | 2050-12-31 | 2008-07-01 | 2009-03-31
75086 | G7LGMR | E0472 | E0472 - STA 795 SANDMAN DR | -1140.29 |  | -1140.29 |  |  | 71391.09 | 71874 | -482.91 | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7LGMR | E4533 | E4533 - REG 111K - 5TH & CRAIG | -856.3 |  | -856.3 |  |  | 94852.3 | 103681 | -8828.7 | 2009-02-24 | 2014-02-23 | 2009-03-01 | 2010-03-08
75086 | G7LGMR | E4592 | E4592 - REG 108K - HWY & DAVID | -3472.04 |  | -3472.04 |  |  | 55608.83 | 96097 | -40488.17 | 2009-02-27 | 2014-02-24 | 2009-04-01 | 2010-01-28
75086 | G7LGMR | F2907 | F2907 - STA 804 LOOKAWAY DRIVE | 9840.88 |  | 9840.88 |  |  | 68369.54 | 39821 | 28548.54 | 2009-12-09 | 2012-06-30 | 2009-12-01 | 2011-06-24
75086 | G7LGMR | G0224 | G0224 - STA 809 - WATERWORKS RD- STATION | -5656.59 |  | -5656.59 |  |  | 482.48 | 99 | 383.48 | 2010-07-07 | 2018-10-01 | 2010-08-01
75086 | G7LGMR | G2537 | G2537 - RPL SCADA RADIO EQUIP KY | -12437 |  | -12437 |  |  | 267110.52 | 120750 | 146360.52 | 2011-03-04 | 2014-07-31 | 2011-03-01 | 2013-03-15
75086 | G7LGMR | G6976 | G6976 - CONCRETE STAIRWELL RPL | -833.56 |  | -833.56 |  |  | 13126.97 | 18897.6 | -5770.63 | 2012-03-07 | 2013-03-10 | 2012-07-01 | 2012-11-01
75086 | G7LGMR | H0264 | H0264 - REG 118K INLET & OUTLET PIPING | -811.51 |  | -811.51 |  |  | 79428.53 | 48938.56 | 30489.97 | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0350 | H0350 - STA 535K1 (UL33 TO HP) MODIFICATION | -692.76 |  | -692.76 |  |  | 22604.47 | 19577.76 | 3026.71 | 2013-07-02 | 2015-06-30 | 2013-11-01 | 2015-02-20
75086 | G7LGMR | MX0573301 | MX0573301 - REG 17 - FOOTE & FAIRFIELD DOWNSIZE | -248.31 |  | -248.31 |  |  | 10611.99 | 31485.84 | -20873.85 | 2018-11-19 14:01 | 2019-02-28 | 2019-04-01 | 2019-07-19
75086 | G7LGMR | MX0573477 | MX0573477 - REG 95 - BAUM & BURNET DOWNSIZE | -231.37 |  | -231.37 |  |  | 9541.17 | 26609.04 | -17067.87 | 2018-11-19 14:01 | 2019-02-28 | 2019-04-01 | 2019-07-11
75086 | G7LGMR | MX0671045 | MX0671045 - REG 101 - COVERT RUN & TAYLOR | -2343.63 |  | -2343.63 |  |  | 167976.08 | 81442.56 | 86533.52 | 2018-12-06 10:01 | 2019-08-30 | 2019-03-01 | 2019-10-27
75086 | G7LGMR | MX2218039 | MX2218039 - INSTALL SCADA EQ-THREE MILE RD STA | 322616.22 |  | 322616.22 |  |  | 548542.99 | 411228.18 | 137314.81 | 2017-09-21 14:01 | 2020-07-10 | 2017-10-01 | 2020-09-15
75086 | G7LGMR | MX2335804 | MX2335804 - STA 872 - OAKLAND VALVE HOUSE | 538294.42 |  | 538294.42 |  |  | 13791597.12 | 4268942.55 | 9522654.57 | 2017-10-06 18:03 | 2019-08-15 | 2017-11-01 | 2019-09-19
75086 | G7LGMR | MX2386654 | MX2386654 - STA 901 - MARY GRUBBS | -7701.92 |  | -7701.92 |  |  | 310586.15 | 357835.2 | -47249.05 | 2019-06-24 10:02 | 2019-10-31 | 2019-06-01 | 2020-02-19
75086 | G7LGMR | MX6693835 | MX6693835 - REGULATOR 412 - 9TH & OVERTON | 21618.78 |  | 21618.78 |  |  | 59230.82 | 106314.24 | -47083.42 | 2017-12-15 14:01 | 2021-03-31 | 2018-02-01
75086 | G7LGMR | MX6828172 | MX6828172 - REG 420 BELAIR AND SPICEWOOD | 572.64 |  | 572.64 |  |  | 29054.18 | 139842.24 | -110788.06 | 2018-04-04 10:01 | 2021-03-31 | 2019-01-01
75086 | G7LGMR | MX8672523 | MX8672523 - REG 119 BRISTOW AND RICHARDSON | 133.69 |  | 133.69 |  |  | 40673.75 | 262006.08 | -221332.33 | 2019-03-21 14:01 | 2020-08-31 | 2019-05-01
75086 | G7LGMR | R2900 | R2900 - COX RD STATION RPL | -827.74 |  | -827.74 |  |  | 29570.94 | 171480.48 | -141909.54 | 2015-09-10 16:08 | 2017-08-01 | 2016-02-01 | 2017-04-11
75086 | G7LGMR | R3460 | R3460 - STATION 577 (KY-17 & US-27) | -15060.2 |  | -15060.2 |  |  | 222104.95 | 79638.14 | 142466.81 | 2015-10-05 14:36 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7LGMR | S7568 | S7568 - STA 822 COX RD OUTLET | -422.66 |  | -422.66 |  |  | 29415.69 | 25054.56 | 4361.13 | 2016-06-08 12:42 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | S7572 | S7572 - STA 822 COX RD INLET | -960.33 |  | -960.33 |  |  | 66834.97 | 25054.56 | 41780.41 | 2016-06-08 12:51 | 2017-08-01 | 2016-08-01 | 2017-04-11
75086 | G7LGMR | T1465 | T1465 - STA 855 TAYLOR MILL RD - STATION | -2295.9 |  | -2295.9 |  |  | 202527.23 | 83246.98 | 119280.25 | 2017-01-06 16:24 | 2018-04-19 | 2017-03-01 | 2018-04-24
75086 | G7LGMR | T5473 | T5473 - SCAD 21012299 PRESSURE TRANSMIITTER | 5764.48 |  | 5764.48 |  |  | 56268.6 | 91500.96 | -35232.36 | 2017-03-31 07:27 | 2018-12-01 | 2017-06-01 | 2017-09-30
75086 | G7LGMR | T9338 | T9338 - STA 809 WATERWORKS DR - STATION | -482.36 |  | -482.36 |  |  | 3334.83 | 116006.88 | -112672.05 | 2017-07-14 10:03 | 2018-09-01 | 2017-09-01
75086 | G7LNLP03 | V5652 | V5652 - LINE LP03 | 11.25 |  | 11.25 |  |  | 886878.23 | 1325999 | -439120.77 | 2018-09-11 07:37 | 2019-02-28 | 2018-10-01 | 2019-02-15
75086 | G7LNUL57 | AW0832 | AW0832 - LINE UL57 MONOLITHIC INSULATORS | 1026789.49 |  | 1026789.49 |  |  | 1026789.49 | 564646 | 462143.49 | 2019-07-26 13:48 | 2020-12-25 | 2020-03-01 | 2020-12-03
75086 | G7LP3 | LP3LAND | LP3LAND - CANCEL EMERGENCY LINE LP-3 (LAND) | -11.25 |  | -11.25 |  |  | 0 | 110000 | -110000 | 2018-06-22 07:48 | 2018-11-30 | 2018-12-01 | 2018-11-29
75086 | G7LUL02 | AW2880 | AW2880 - LINE UL02 - MAOP REPLACEMENT | 21357.99 |  | 21357.99 |  |  | 21357.99 | 1717200 | -1695842.01 | 2020-10-07 12:58 | 2022-03-31 | 2020-10-01 | 2022-01-05
75086 | G7MAINS | E0469 | E0469 - STA 795 INLET PIPING | -242.16 |  | -242.16 |  |  | 6363.05 | 6569 | -205.95 | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7MAINS | MEAPJT70 | MEAPJT70 - JOINT TRENCH PLASITC MAIN EXTENSION | 785143.34 |  | 785143.34 |  |  | 3750563.27 | 10000000 | -6249436.73 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | G7MAINS | MX0270903 | MX0270903 - FARM TAP PROJ. 3 MILE RD | 6486.4 |  | 6486.4 |  |  | 414221.23 | 365844.57 | 48376.66 | 2019-03-21 14:01 | 2019-10-19 | 2019-04-01 | 2019-12-21
75086 | G7MAINS | MX0556249 | MX0556249 - FARM TAP PROJ; CALIFORNIA CROSSROAD | 3083.49 |  | 3083.49 |  |  | 277358.89 | 123394.12 | 153964.77 | 2019-01-14 10:01 | 2019-10-24 | 2019-05-01 | 2020-01-03
75086 | G7MAINS | MX0579746 | MX0579746 - JT-G-RIVERS POINTE ESTATES PHASE 1 | 25270.49 |  | 25270.49 |  |  | 25270.49 | 109259 | -83988.51 | 2020-03-09 14:01 | 2020-09-24 | 2020-11-01 | 2021-06-13
75086 | G7MAINS | MX0590999 | MX0590999 - FARM TAP; E LOW GAP RD ALEXANDRIA | 58282.71 |  | 58282.71 |  |  | 372791.12 | 359350.5 | 13440.62 | 2019-07-31 14:01 | 2022-10-19 | 2019-08-01 | 2020-05-21
75086 | G7MAINS | MX0602140 | MX0602140 - FARM TAP PROJ; ENZWEILER RD | 7227.47 |  | 7227.47 |  |  | 7227.47 | 83366.18 | -76138.71 | 2020-09-01 18:01 | 2021-10-17 | 2020-09-01 | 2021-10-06
75086 | G7MAINS | MX0602571 | MX0602571 - FARM TAP PROJ; JOHNS HILL RD | 231.99 |  | 231.99 |  |  | 16054.73 | 112220.53 | -96165.8 | 2019-07-16 10:02 | 2019-12-12 | 2019-07-01 | 2020-06-02
75086 | G7MAINS | MX1130180 | MX1130180 - FARM TAP PROJ; MARTHA LAYNE COLLINS | 940.49 |  | 940.49 |  |  | 74539.59 | 62900.69 | 11638.9 | 2019-02-07 10:02 | 2019-04-03 | 2019-03-01 | 2020-03-17
75086 | G7MAINS | MX1296075 | MX1296075 - INSTALL GAS ONLY APPROACH MAIN - NE | 3331.14 |  | 3331.14 |  |  | 41779.5 | 73554.85 | -31775.35 | 2019-07-24 10:01 | 2020-01-19 | 2019-08-01 | 2020-03-13
75086 | G7MAINS | MX1304901 | MX1304901 - FARM TAP PROJ; WAGONER RD CALIFORNI | 2255.03 |  | 2255.03 |  |  | 35105.79 | 46479.42 | -11373.63 | 2019-06-26 14:01 | 2019-11-14 | 2019-07-01 | 2020-01-22
75086 | G7MAINS | MX1307140 | MX1307140 - FARM TAP PROJ; BARRS BRANCH / E MAI | 118172.94 |  | 118172.94 |  |  | 389063.87 | 346753.22 | 42310.65 | 2019-09-11 14:01 | 2020-03-29 | 2019-09-01 | 2020-05-15
75086 | G7MAINS | MX1356700 | MX1356700 - FARM TAP PROJ; WINTERS LN HIGHLAND | 3685.09 |  | 3685.09 |  |  | 258522.85 | 147466.28 | 111056.57 | 2019-06-27 10:02 | 2019-12-26 | 2019-07-01 | 2020-03-11
75086 | G7MAINS | MX1370091 | MX1370091 - FARM TAP PROJ; MARY INGLES HWY | 253723.97 |  | 253723.97 |  |  | 510245.04 | 515675 | -5429.96 | 2019-10-25 18:01 | 2020-05-28 | 2019-10-01 | 2020-07-20
75086 | G7MAINS | MX1957438 | MX1957438 - FARM TAP PROJ; GRANDVIEW RD | 51623.05 |  | 51623.05 |  |  | 51623.05 | 161978.74 | -110355.69 | 2020-09-29 10:01 | 2021-12-16 | 2020-09-01 | 2022-01-10
75086 | G7MAINS | MX1958084 | MX1958084 - FARM TAP PROJ; FLAGG SPRINGS PIKE | 581074.43 |  | 581074.43 |  |  | 581074.43 | 541626 | 39448.43 | 2020-02-05 10:02 | 2020-05-22 | 2020-02-01 | 2020-10-30
75086 | G7MAINS | MX2142600 | MX2142600 - FARM TAP PROJ; THORNTON RD | 2386.94 |  | 2386.94 |  |  | 28086.4 | 54541.9 | -26455.5 | 2019-07-18 18:01 | 2019-12-19 | 2019-07-01 | 2020-01-26
75086 | G7MAINS | MX2143073 | MX2143073 - FARM TAP PROJ; REIDLIN RD | 413.07 |  | 413.07 |  |  | 37156.37 | 43437.77 | -6281.4 | 2019-05-21 18:01 | 2019-10-31 | 2019-06-01 | 2020-01-22
75086 | G7MAINS | MX2271880 | MX2271880 - MEA ~800 FT; 494 JONES RD | 28147.5 |  | 28147.5 |  |  | 242750.13 | 163070 | 79680.13 | 2019-07-30 10:01 | 2020-02-27 | 2019-08-01 | 2020-05-13
75086 | G7MAINS | MX2335879 | MX2335879 - CANCEL STA 872 - OAKLAND VALVE -IN | -444344.86 |  | -444344.86 |  |  | 0 | 380442 | -380442 | 2018-01-05 14:01 | 2019-08-30 | 2018-05-01 | 2019-09-19
75086 | G7MAINS | MX2335908 | MX2335908 - CANCEL OAKLAND VALVE HOUSE OUTLET | -84169.43 |  | -84169.43 |  |  | 0 | 515779 | -515779 | 2019-03-08 14:01 | 2019-06-28 | 2019-03-01 | 2019-09-19
75086 | G7MAINS | MX2424919 | MX2424919 - MEA ~550 FT; 2000 GATEWAY BLVD | 408.23 |  | 408.23 |  |  | 32354.07 | 50615.9 | -18261.83 | 2019-07-02 14:01 | 2019-12-12 | 2019-07-01 | 2020-01-18
75086 | G7MAINS | MX2562222 | MX2562222 - MEA ~600 FT - 400 KENTON LANDS RD | 106383.51 |  | 106383.51 |  |  | 192207.23 | 205184 | -12976.77 | 2019-10-04 14:01 | 2020-03-11 | 2019-11-01 | 2020-05-15
75086 | G7MAINS | MX2568722 | MX2568722 - MEA ~230 FT; 500 S MAIN ST | 100717.75 |  | 100717.75 |  |  | 147091.51 | 60768.22 | 86323.29 | 2019-08-27 18:01 | 2020-03-18 | 2019-09-01 | 2020-06-08
75086 | G7MAINS | MX2626372 | MX2626372 - ~675 FT MEA; 2344 AMSTERDAM RD | 47208.91 |  | 47208.91 |  |  | 52023.27 | 60345 | -8321.73 | 2019-11-19 10:01 | 2020-04-23 | 2019-12-01 | 2020-05-31
75086 | G7MAINS | MX2834473 | MX2834473 - MEA ~640 FT; 8519 US RT 42 | 606.98 |  | 606.98 |  |  | 55530.87 | 77219 | -21688.13 | 2019-09-30 15:56 | 2020-01-19 | 2019-10-01 | 2020-03-11
75086 | G7MAINS | MX2848811 | MX2848811 - INDEPENDENCE RD MEA - | 240.74 |  | 240.74 |  |  | 5551.81 | 35185 | -29633.19 | 2019-09-30 10:01 | 2020-01-30 | 2019-10-01 | 2020-02-02
75086 | G7MAINS | MX2866813 | MX2866813 - JT-G-ARCADIA PHASE I | 9202.26 |  | 9202.26 |  |  | 9202.26 | 57563 | -48360.74 | 2019-12-18 10:01 | 2020-03-31 | 2020-03-01 | 2020-08-19
75086 | G7MAINS | MX3354938 | MX3354938 - ~MEA 450 FT; 3845 TURFWAY RD | -525.3 |  | -525.3 |  |  | 35815.95 | 51274.67 | -15458.72 | 2019-08-28 14:01 | 2020-01-05 | 2019-09-01 | 2020-03-26
75086 | G7MAINS | MX3444104 | MX3444104 - MEA ~970 FT; ASHLEY DR | -1154.99 |  | -1154.99 |  |  | 49044.52 | 93363 | -44318.48 | 2019-09-13 14:01 | 2019-12-29 | 2019-09-01 | 2020-02-25
75086 | G7MAINS | MX3745351 | MX3745351 - MEA ~200 FT; LEE LN | 316.45 |  | 316.45 |  |  | 14418.31 | 34346 | -19927.69 | 2019-10-18 10:01 | 2020-02-02 | 2019-10-01 | 2020-04-02
75086 | G7MAINS | MX4018013 | MX4018013 - JOHNS HILL RD MEA | 192865.35 |  | 192865.35 |  |  | 209963.8 | 73344 | 136619.8 | 2019-11-13 10:01 | 2020-01-03 | 2019-11-01 | 2020-06-18
75086 | G7MAINS | MX4086064 | MX4086064 - MEA ~1400 FT; 479 ORPHANGE RD | 89837.87 |  | 89837.87 |  |  | 94079.99 | 95523.06 | -1443.07 | 2019-12-02 14:01 | 2020-04-22 | 2019-12-01 | 2020-08-16
75086 | G7MAINS | MX4108387 | MX4108387 - MEA ~ 270 FT; 950 WENSTRUP LN | 16717.98 |  | 16717.98 |  |  | 18581.39 | 41217 | -22635.61 | 2019-12-02 18:01 | 2021-04-02 | 2019-12-01 | 2020-06-18
75086 | G7MAINS | MX4125743 | MX4125743 - 2,000 FT MEA; DAMASCUS | 142604.75 |  | 142604.75 |  |  | 142604.75 | 152669 | -10064.25 | 2020-01-29 14:01 | 2020-06-10 | 2020-02-01 | 2020-12-16
75086 | G7MAINS | MX4146445 | MX4146445 - MEA ~ 25 FT; 411 COACHLIGHT DR | 1101.17 |  | 1101.17 |  |  | 3285.37 | 13325 | -10039.63 | 2019-10-01 14:01 | 2020-02-13 | 2019-11-01 | 2020-01-20
75086 | G7MAINS | MX4210795 | MX4210795 - JT-G-BALLYSHANNON SECTION 5 PHASE 6 | 37525.79 |  | 37525.79 |  |  | 37525.79 | 52790 | -15264.21 | 2019-12-19 10:01 | 2020-12-31 | 2020-01-01 | 2020-08-21
75086 | G7MAINS | MX4321381 | MX4321381 - JT-G-STEEPLECHASE SECTION 18 | 6861.87 |  | 6861.87 |  |  | 6861.87 | 51469 | -44607.13 | 2019-11-19 10:01 | 2021-01-11 | 2020-02-01 | 2020-08-02
75086 | G7MAINS | MX4355391 | MX4355391 - ~1,600 FT MEA; 300 RICHARD KNOCK HW | 251265.94 |  | 251265.94 |  |  | 251265.94 | 225972 | 25293.94 | 2020-05-27 10:01 | 2020-08-25 | 2020-06-01 | 2020-11-30
75086 | G7MAINS | MX4769285 | MX4769285 - ~985 FT MEA; OAKRIDGE DR | 67067.76 |  | 67067.76 |  |  | 67067.76 | 116703 | -49635.24 | 2020-02-17 14:01 | 2020-04-24 | 2020-02-01 | 2020-08-12
75086 | G7MAINS | MX4837396 | MX4837396 - JT-G-PARK POINTE | 298.02 |  | 298.02 |  |  | 298.02 | 81024 | -80725.98 | 2020-02-24 14:07 | 2021-02-24 | 2020-03-01 | 2021-07-14
75086 | G7MAINS | MX4861864 | MX4861864 - TERMINAL DR MEA-CVG CONRAC PROJECT | 159154.32 |  | 159154.32 |  |  | 159154.32 | 166549 | -7394.68 | 2020-06-12 14:01 | 2020-12-17 | 2020-06-01 | 2021-01-12
75086 | G7MAINS | MX4875568 | MX4875568 - FARM TAP PROJECT; E ALEXANDRIA / CA | 943847.01 |  | 943847.01 |  |  | 943847.01 | 1255100 | -311252.99 | 2020-03-03 10:01 | 2020-09-11 | 2020-03-01 | 2020-12-26
75086 | G7MAINS | MX5040349 | MX5040349 - GLENRIDGE DRIVE - MEA | 100239.48 |  | 100239.48 |  |  | 100239.48 | 114071 | -13831.52 | 2020-04-23 14:01 | 2020-07-10 | 2020-05-01 | 2020-11-24
75086 | G7MAINS | MX5373035 | MX5373035 - ~350 FT MEA; 390 MEIJER DR | 57401.87 |  | 57401.87 |  |  | 57401.87 | 44298 | 13103.87 | 2020-04-03 11:02 | 2020-10-21 | 2020-06-01 | 2020-11-27
75086 | G7MAINS | MX5652554 | MX5652554 - FARM TAP PROJ; MASON RD MEA | 5001.25 |  | 5001.25 |  |  | 5001.25 | 237226.07 | -232224.82 | 2020-12-16 10:17 | 2021-09-24 | 2020-12-01
75086 | G7MAINS | MX5653109 | MX5653109 - FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 778.47 |  | 778.47 |  |  | 778.47 | 194197.42 | -193418.95 | 2020-09-29 10:01 | 2023-07-13 | 2020-10-01 | 2023-11-15
75086 | G7MAINS | MX6180533 | MX6180533 - 440 FT MEA; MEDICAL VILLAGE DR | 104235.64 |  | 104235.64 |  |  | 104235.64 | 74687 | 29548.64 | 2020-07-29 14:01 | 2020-10-16 | 2020-08-01 | 2021-01-25
75086 | G7MAINS | MX6243694 | MX6243694 - ~400 FT MEA; DOLWICK DR | 59485.09 |  | 59485.09 |  |  | 59485.09 | 104176 | -44690.91 | 2020-06-18 10:01 | 2020-09-29 | 2020-07-01 | 2021-04-07
75086 | G7MAINS | MX6245365 | MX6245365 - ~425 FT MEA; SARAH LN | 10580.55 |  | 10580.55 |  |  | 10580.55 | 26839.9 | -16259.35 | 2020-08-31 14:01 | 2020-11-15 | 2020-09-01 | 2021-02-10
75086 | G7MAINS | MX6684040 | MX6684040 - ~1825 FTMEA; WRIGHT BLVD | 49898.59 |  | 49898.59 |  |  | 49898.59 | 117730.07 | -67831.48 | 2020-10-02 10:01 | 2020-12-18 | 2020-10-01 | 2021-03-08
75086 | G7MAINS | MX6835553 | MX6835553 - JT-G-SOUTHWICK PHASE B PART 1 | 57.88 |  | 57.88 |  |  | 57.88 | 46988.86 | -46930.98 | 2020-11-23 18:02 | 2021-08-19 | 2020-12-01 | 2021-07-25
75086 | G7MAINS | MX6842755 | MX6842755 - MAIN EXTENSION AARON DR-85 FT 2 IN- | 5099.04 |  | 5099.04 |  |  | 5099.04 | 25737 | -20637.96 | 2020-07-09 10:01 | 2020-08-28 | 2020-08-01 | 2020-12-15
75086 | G7MAINS | MX6891268 | MX6891268 - AMAZON SOUTHWEST DELIVERY DIST PROJ | 275739.24 |  | 275739.24 |  |  | 275739.24 | 319190 | -43450.76 | 2020-05-22 14:01 | 2021-03-31 | 2020-05-01
75086 | G7MAINS | MX7078370 | MX7078370 - CANCEL INVESTMENT WAY MEA | 255.01 |  | 255.01 |  |  | 255.01 | 39282 | -39026.99 | 2020-08-14 10:01 | 2020-10-16 | 2020-08-01
75086 | G7MAINS | MX7122512 | MX7122512 - 100 FT MEA; 10009 INDIAN HILL DR | 26071.71 |  | 26071.71 |  |  | 26071.71 | 21629.68 | 4442.03 | 2020-09-22 10:01 | 2020-11-27 | 2020-10-01 | 2021-03-12
75086 | G7MAINS | MX7231229 | MX7231229 - STONEWATER APPROACH MAIN | 4611.95 |  | 4611.95 |  |  | 4611.95 | 201665.76 | -197053.81 | 2020-12-15 10:01 | 2021-12-18 | 2020-12-01 | 2021-08-14
75086 | G7MAINS | MX7488442 | MX7488442 - SANCTUARY VILLAGE PHASE 1 PART 3 | 116.24 |  | 116.24 |  |  | 116.24 | 44181.42 | -44065.18 | 2020-09-23 10:01 | 2023-03-22 | 2020-10-01
75086 | G7MAINS | MX7752227 | MX7752227 - INSTALL GAS ONLY APPROACH MAIN - NE | 394.69 |  | 394.69 |  |  | 5054.88 | 3766.66 | 1288.22 | 2018-08-27 14:02 | 2018-11-20 | 2018-08-01 | 2018-12-26
75086 | G7MAINS | MX8030455 | MX8030455 - CAMP ERNST AND SOLOMON MAE | 32948.67 |  | 32948.67 |  |  | 32948.67 | 42778.64 | -9829.97 | 2020-10-19 18:01 | 2021-04-12 | 2020-11-01 | 2021-04-26
75086 | G7MAINS | MX8059955 | MX8059955 - ~440 FT MEA; 2 IN PL HP | 2480.81 |  | 2480.81 |  |  | 2480.81 | 29426.19 | -26945.38 | 2020-12-01 14:18 | 2021-05-11 | 2020-12-01 | 2021-05-06
75086 | G7MAINS | MX8377762 | MX8377762 - JT-G-TRIPLE CROWN SECTION 18 PHASE | 13339.15 |  | 13339.15 |  |  | 20163.17 | 57033 | -36869.83 | 2018-09-28 14:02 | 2019-01-25 | 2019-11-01 | 2020-07-06
75086 | G7MAINS | MX8451945 | MX8451945 - INVESTMENT WAY MEA | 26815.39 |  | 26815.39 |  |  | 26815.39 | 16224.75 | 10590.64 | 2020-10-16 10:01 | 2020-12-30 | 2020-11-01 | 2021-02-02
75086 | G7MAINS | MX8505395 | MX8505395 - ~350 FT MEA; 351 KENTON LANDS | 453.3 |  | 453.3 |  |  | 453.3 | 32683.85 | -32230.55 | 2020-12-01 14:18 | 2021-02-28 | 2020-12-01 | 2021-06-28
75086 | G7MAINS | MX8574441 | MX8574441 - GAS MAIN EXTENSION - 10177 BIG BONE | 1281.1 |  | 1281.1 |  |  | 101534.59 | 80515.92 | 21018.67 | 2018-08-22 14:02 | 2018-10-19 | 2018-08-01 | 2019-06-02
75086 | G7MAINS | MXA350358 | MXA350358 - FARM TAP PROJ; THOMAS MORE PKWY | 143321.64 |  | 143321.64 |  |  | 143321.64 | 131212 | 12109.64 | 2019-12-12 18:01 | 2020-06-11 | 2020-01-01 | 2020-08-05
75086 | G7MREG118 | MX2217622 | MX2217622 - STATION 873 - 5TH & PHILADELPHIA | 13060.87 |  | 13060.87 |  |  | 25442.42 | 87907.04 | -62464.62 | 2017-09-22 14:01 | 2025-11-30 | 2017-10-01
75086 | G7MRUPG | AW1568 | AW1568 - STATION 338 MR UPGRADE | 68188.66 |  | 68188.66 |  |  | 68188.66 | 190631 | -122442.34 | 2019-12-18 15:27 | 2022-03-30 | 2020-02-01
75086 | G7MRUPG | AW1569 | AW1569 - STATION 286 RILEY ROAD MR UPGRADE | 45326.33 |  | 45326.33 |  |  | 45326.33 | 190631 | -145304.67 | 2019-12-18 15:32 | 2022-03-30 | 2020-02-01
75086 | G7MSCPRD | L4115 | L4115 - REPLACE CONTROL VALVES AT CONSTANCE | -1280.91 |  | -1280.91 |  |  | 31357.45 | 58753.25 | -27395.8 | 2014-05-13 | 2015-06-30 | 2014-06-01 | 2014-11-01
75086 | G7MSCPRD | M6102 | M6102 - REPLACE COMPRESS 6&7 OIL LUBE SYS | -3833.96 |  | -3833.96 |  |  | 48948.69 | 30641.11 | 18307.58 | 2014-06-11 | 2016-06-30 | 2014-09-01 | 2015-01-14
75086 | G7MSCPRD | P8054 | P8054 - REPLACE BTU MEASUREMENT AT ERLANGER | -1260.77 |  | -1260.77 |  |  | 52326.6 | 49804.32 | 2522.28 | 2015-03-12 14:27 | 2016-04-30 | 2015-07-01 | 2016-01-30
75086 | G7PHMSA | V7283 | V7283 - PHMSA CRM PLAN | 407568.62 |  | 407568.62 |  |  | 1844151.93 | 416794 | 1427357.93 | 2018-11-14 14:31 | 2020-09-30 | 2018-12-01 | 2021-03-30
75086 | G7PRESIM | MX1640159 | MX1640159 - ELIJAH CREEK PRESSURE IMPROVEMENT P | -27117.24 |  | -27117.24 |  |  | 861604.74 | 760041.64 | 101563.1 | 2019-06-04 14:01 | 2020-02-26 | 2019-06-01 | 2020-01-15
75086 | G7PUBIMP | 30323 | 30323 - GRANDVIEW/GJH | 25.16 |  | 25.16 |  |  | 25.16 | 0 | 25.16 | 2000-04-13 | 2004-01-31 | 1997-02-01 | 1997-03-31
75086 | G7PUBIMP | C9131 | C9131 - PP620440/JOHN BETSCH | -336.56 |  | -336.56 |  |  | 27300.22 | 0 | 27300.22 | 2007-01-18 | 2012-12-31 | 2007-01-01 | 2007-07-16
75086 | G7PUBIMP | D3299 | D3299 - PP 978761/LLM | -263.05 |  | -263.05 |  |  | 90038.82 | 0 | 90038.82 | 2008-04-15 | 2050-12-31 | 2008-04-01 | 2008-08-28
75086 | G7PUBIMP | D3414 | D3414 - PP 967604/LAURA MATE | -590.29 |  | -590.29 |  |  | 133477.23 | 0 | 133477.23 | 2008-05-01 | 2050-12-31 | 2008-07-01 | 2008-11-28
75086 | G7PUBIMP | E0294 | E0294 - HILTON DR | -41.5 |  | -41.5 |  |  | 1157.44 | 6415 | -5257.56 | 2008-07-29 | 2009-12-31 | 2008-08-01 | 2009-04-15
75086 | G7PUBIMP | E4594 | E4594 - ROGERS RD VILLA HILLS | -245.2 |  | -245.2 |  |  | 119453.76 | 91099 | 28354.76 | 2009-02-27 | 2014-02-27 | 2009-04-01 | 2009-09-24
75086 | G7PUBIMP | G8241 | G8241 - SUNSET DRIVE - THREE MILE RD IMP | -472.76 |  | -472.76 |  |  | 153385.1 | 175201.13 | -21816.03 | 2012-08-16 | 2016-01-31 | 2015-02-01 | 2016-02-05
75086 | G7PUBIMP | MX0783884 | MX0783884 - PLEASANT VALLEY ROAD/CAMP ERNST ROA | 98763.06 |  | 98763.06 |  |  | 1955109.13 | 1689689.28 | 265419.85 | 2018-04-26 10:01 | 2018-08-25 | 2018-05-01 | 2019-01-22
75086 | G7PUBIMP | MX0790794 | MX0790794 - ARLINGTON RD. ROADWAY IMP | -43659.63 |  | -43659.63 |  |  | 353160.21 | 227712 | 125448.21 | 2018-01-23 20:20 | 2018-03-30 | 2018-03-01 | 2018-09-26
75086 | G7PUBIMP | MX0976110 | MX0976110 - INSTALL STREET IMPROVEMENT PROJECT | 86222.38 |  | 86222.38 |  |  | 572508.8 | 274447.64 | 298061.16 | 2018-07-19 18:03 | 2018-10-28 | 2018-07-01 | 2018-12-19
75086 | G7PUBIMP | MX1376296 | MX1376296 - LONGBRANCH RD. | 256216.47 |  | 256216.47 |  |  | 370025.75 | 70969.1 | 299056.65 | 2019-08-02 14:01 | 2020-03-05 | 2019-09-01 | 2020-09-15
75086 | G7PUBIMP | MX2362841 | MX2362841 - AMSTERDAM RD.IMPS.,FORT WRIGHT,KY.( | -3520.67 |  | -3520.67 |  |  | 137160.56 | 129952.9 | 7207.66 | 2018-05-14 14:02 | 2018-08-26 | 2018-05-01 | 2018-10-24
75086 | G7PUBIMP | MX2541899 | MX2541899 - KY-36/I-75 INTERCHANGE RECONSTRUCT | -1294.77 |  | -1294.77 |  |  | 1122765.41 | 906757 | 216008.41 | 2018-03-02 10:01 | 2018-06-03 | 2018-04-01 | 2018-11-02
75086 | G7PUBIMP | MX2624631 | MX2624631 - EWING BLVDI STREET IMPROVEMENT PROJ | 50130.67 |  | 50130.67 |  |  | 25728.63 | 101493.8 | -75765.17 | 2019-10-01 18:01 | 2020-02-27 | 2019-10-01 | 2020-04-09
75086 | G7PUBIMP | MX2698762 | MX2698762 - DOH PENDELTON/CAMPBELL INSTALL STRE | 288357.99 |  | 288357.99 |  |  | 309410.39 | 99383.99 | 210026.4 | 2019-09-20 14:01 | 2020-04-03 | 2019-12-01 | 2020-07-09
75086 | G7PUBIMP | MX2911494 | MX2911494 - UL 35 STREET IMPROVEMENT PROJECT | 6587.83 |  | 6587.83 |  |  | 28839.77 | 51296.38 | -22456.61 | 2019-08-02 14:01 | 2020-01-09 | 2019-09-01 | 2020-09-15
75086 | G7PUBIMP | MX3298765 | MX3298765 - RIDGE RD. & WEST ORCHARD FT MITCHEL | 57215.91 |  | 57215.91 |  |  | 57215.91 | 94800 | -37584.09 | 2020-07-28 10:01 | 2020-10-16 | 2020-07-01 | 2021-01-11
75086 | G7PUBIMP | MX6477976 | MX6477976 - CAMP ERNST STREET IMPROVEMENT PROJE | 179928.25 |  | 179928.25 |  |  | 179928.25 | 99251 | 80677.25 | 2020-04-29 14:01 | 2020-06-26 | 2020-05-01 | 2021-01-11
75086 | G7PUBIMP | MX6628393 | MX6628393 - PLEASANT VALLEY 2020 RELOCATION | 458429.77 |  | 458429.77 |  |  | 458429.77 | 399033 | 59396.77 | 2020-05-18 10:01 | 2020-10-29 | 2020-06-01 | 2020-11-17
75086 | G7PUBIMP | MX6770232 | MX6770232 - KYTC-06-0412.00 RICE PK & U.S.42 ST | -26325.58 |  | -26325.58 |  |  | 162909.26 | 279194 | -116284.74 | 2018-03-02 10:01 | 2018-05-25 | 2018-03-01 | 2018-10-25
75086 | G7PUBIMP | MX7035169 | MX7035169 - BUTTERMILK PIKE STREET IMPROVEMENT | 98905.75 |  | 98905.75 |  |  | 98905.75 | 74108 | 24797.75 | 2020-07-08 18:01 | 2020-11-26 | 2020-07-01 | 2020-12-07
75086 | G7PUBIMP | MX7507727 | MX7507727 - MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | 6382.24 |  | 6382.24 |  |  | 238643.31 | 238847.13 | -203.82 | 2018-04-06 18:03 | 2018-08-24 | 2018-04-01 | 2018-10-26
75086 | G7PUBIMP | MX7599942 | MX7599942 - INSTALL STREET IMPROVEMENT PROJECT | 117038.47 |  | 117038.47 |  |  | 166667.57 | 99125.15 | 67542.42 | 2019-08-02 10:01 | 2020-02-27 | 2019-08-01 | 2020-02-29
75086 | G7PUBIMP | MX7720357 | MX7720357 - BEECHWOOD RD STREET IMPROVEMENT PRO | 5288.84 |  | 5288.84 |  |  | 190727.42 | 183481.42 | 7246 | 2019-04-03 14:01 | 2019-07-14 | 2019-04-01 | 2019-10-03
75086 | G7PUBIMP | MX8175168 | MX8175168 - BUTTERMILK PIKE STREET IMPROVEMENT | 6060.22 |  | 6060.22 |  |  | 6857.45 | 62696 | -55838.55 | 2019-11-19 14:01 | 2021-03-31 | 2019-11-01
75086 | G7PUBIMP | MX8760866 | MX8760866 - WKIP ROADWAY IMPROVEMENT JONES RD | 214.95 |  | 214.95 |  |  | 369060.43 | 208010.18 | 161050.25 | 2018-06-14 14:01 | 2018-10-12 | 2018-06-01 | 2019-02-03
75086 | G7PUBIMP | MX8840782 | MX8840782 - INSTALL STREET IMPROVEMENT PROJECT- | 685.78 |  | 685.78 |  |  | 685.78 | 0 | 685.78 | 2020-02-06 18:01 | 2018-12-07 | 2020-02-01
75086 | G7PUBIMP | MX9244894 | MX9244894 - MT.ZION RD KY536 STI | 244141.81 |  | 244141.81 |  |  | 244141.81 | 1026778 | -782636.19 | 2019-11-08 10:01 | 2023-06-30 | 2020-01-01 | 2021-07-27
75086 | G7PUBIMP | O4165 | O4165 - DUDLEY RD IMPROVEMENT | -336 |  | -336 |  |  | 106898.72 | 145627.17 | -38728.45 | 2014-07-23 | 2015-03-01 | 2014-08-01 | 2014-11-01
75086 | G7PUBIMP | P6167 | P6167 - KYLES LN. @ DIXIE HWY FT. WRIGHT | -2442.37 |  | -2442.37 |  |  | 247251.61 | 60740.54 | 186511.07 | 2014-08-22 | 2015-06-28 | 2014-12-01 | 2015-08-05
75086 | G7PUBIMP | P6497 | P6497 - HAYES STATION RD | -320.09 |  | -320.09 |  |  | 10640.75 | 15956.89 | -5316.14 | 2014-10-03 | 2015-04-10 | 2014-10-01 | 2014-12-05
75086 | G7PUBIMP | P6551 | P6551 - DUDLEY RD - RELOCATION FOR STORM | -4891.56 |  | -4891.56 |  |  | 70848.38 | 60831.98 | 10016.4 | 2014-10-09 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7PUBIMP | P7280 | P7280 - GRAND AT FLORENCE ROADWAY IMPROVEME | -8797.74 |  | -8797.74 |  |  | 68022.04 | 27834.34 | 40187.7 | 2015-01-14 | 2015-09-25 | 2015-02-01 | 2015-06-20
75086 | G7PUBIMP | R6768 | R6768 - STI 9359472 ROBBINS AVE | -1029.42 |  | -1029.42 |  |  | 30408.52 | 20414.42 | 9994.1 | 2016-02-11 14:00 | 2016-09-30 | 2016-03-01 | 2016-07-15
75086 | G7PUBIMP | S4545 | S4545 - STI 10221124 ALTAVIA AVE | -121.56 |  | -121.56 |  |  | 43121.71 | 15146.09 | 27975.62 | 2016-05-10 07:49 | 2016-10-31 | 2016-05-01 | 2016-09-14
75086 | G7PUBIMP | S7874 | S7874 - STI 4844778 THOMAS MORE PKWY | -611.47 |  | -611.47 |  |  | 69933.58 | 11696.61 | 58236.97 | 2016-06-13 15:53 | 2017-06-30 | 2016-06-01 | 2017-01-03
75086 | G7PUBIMP | S8867 | S8867 - STI 10873483 MT ZION RD | -43839.97 |  | -43839.97 |  |  | 1232439.02 | 447690.24 | 784748.78 | 2016-07-26 13:07 | 2020-01-30 | 2017-01-01 | 2019-12-21
75086 | G7PUINEW | INSREGREL | INSREGREL - INSTALL OR REMOVE REGULATOR/RELIEF | 118213.44 |  | 118213.44 |  |  | 1230642.48 | 800000 | 430642.48 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | SETMETER | SETMETER - SET OR REMOVE METER | 1306156.64 |  | 1306156.64 |  |  | 7701279.68 | 2250000 | 5451279.68 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGLG | AGECHGLG - KENTUCKY AGE CHANGE LARGE METER | 58360.99 |  | 58360.99 |  |  | 532088.78 | 350000 | 182088.78 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | AGECHGSM - KENTUCKY AGE CHANGE SMALL METER | 315841.83 |  | 315841.83 |  |  | 5542617.6 | 14500000 | -8957382.4 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRLG | CHGMTRLG - CHANGE LARGE METER KENTUCKY | -22.45 |  | -22.45 |  |  | 164959.22 | 725000 | -560040.78 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | CHGMTRSM - CHANGE SMALL METER KENTUCKY | 228923.8 |  | 228923.8 |  |  | 2605848.9 | 1250000 | 1355848.9 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | CHGREGREL - CHANGE REGULATOR/RELIEF KENTUCKY | 2003.33 |  | 2003.33 |  |  | 155432.97 | 800000 | -644567.03 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7REG0026 | MX7281967 | MX7281967 - REG 0026 UPHIL AND HIGHWAY - REG SW | 8805.99 |  | 8805.99 |  |  | 8805.99 | 48953.52 | -40147.53 | 2020-07-07 10:01 | 2021-03-31 | 2020-08-01 | 2021-01-20
75086 | G7REG0048 | MX7282035 | MX7282035 - REG 0048 FIFTH AND PHILADELPHIA - R | 12794.79 |  | 12794.79 |  |  | 12794.79 | 48953.52 | -36158.73 | 2020-07-14 10:02 | 2021-03-31 | 2020-08-01 | 2020-10-28
75086 | G7REG0057 | MX7281845 | MX7281845 - REG 0057 SARATOGA AND ELEVENTH - OR | 2667.59 |  | 2667.59 |  |  | 2667.59 | 44953.52 | -42285.93 | 2020-07-07 10:01 | 2021-03-31 | 2020-07-01
75086 | G7REPL | 28051 | 28051 - SMALL REPL KY | 43877.38 |  | 43877.38 |  |  | 1189143.76 | 0 | 1189143.76 | 2000-04-13 | 2050-12-31 | 1999-12-01
75086 | G7REPL | G4517 | G4517 - F/L 'UL07' MCCULLUM RD SLIDE | -1832.85 |  | -1832.85 |  |  | 95659.21 | 76220.15 | 19439.06 | 2011-08-17 | 2012-06-01 | 2011-09-01 | 2012-03-17
75086 | G7REPL | G8159 | G8159 - REG 115K - INLET & OUTLET PIPING | -435.59 |  | -435.59 |  |  | 28810.93 | 39684.96 | -10874.03 | 2012-07-30 | 2013-06-30 | 2012-09-01 | 2013-03-05
75086 | G7REPL | MX0181170 | MX0181170 - CENTRAL AVE NEWPORT- REPLACEMENT PR | -19645.33 |  | -19645.33 |  |  | 22096.81 | 64213.24 | -42116.43 | 2018-12-12 18:01 | 2019-11-21 | 2018-12-01 | 2019-11-27
75086 | G7REPL | MX1233047 | MX1233047 - KY-9 FLOOD GATE-RPL | 190751.64 |  | 190751.64 |  |  | 195696.19 | 92509 | 103187.19 | 2019-10-23 18:01 | 2020-07-10 | 2019-10-01 | 2020-12-14
75086 | G7REPL | MX4065631 | MX4065631 - CALIFORNIA CROSSROADS REPLACEMENT | 7014.04 |  | 7014.04 |  |  | 39763.12 | 72427 | -32663.88 | 2019-10-11 10:01 | 2020-03-19 | 2019-10-01 | 2020-04-15
75086 | G7REPL | MX4342633 | MX4342633 - PLEASANT VALLEY STEEL REP (FOUNDERS | 359638.27 |  | 359638.27 |  |  | 386486.63 | 166756 | 219730.63 | 2019-10-18 10:01 | 2020-02-28 | 2019-10-01 | 2020-06-26
75086 | G7REPL | MX6840192 | MX6840192 - BEAVER RD INSTALL REPLACEMENT PROJE | 98.61 |  | 98.61 |  |  | 98.61 | 48085 | -47986.39 | 2020-08-13 18:01 | 2020-11-20 | 2020-08-01
75086 | G7REPL | MX9056339 | MX9056339 - ST. MATTHEWS CIRCLE REPLACEMENT | -12893.84 |  | -12893.84 |  |  | 81156.17 | 107808.25 | -26652.08 | 2018-09-25 14:02 | 2019-02-03 | 2018-10-01 | 2019-08-20
75086 | G7REPL | MX9545566 | MX9545566 - RICHWOOD RD REPLACEMENT PROJ KY-338 | 265087.55 |  | 265087.55 |  |  | 265087.55 | 1413710 | -1148622.45 | 2019-11-12 10:01 | 2022-06-14 | 2020-01-01 | 2022-03-01
75086 | G7REPL | P6335 | P6335 - DUDLEY RD - RELOCATION FOR RSTORM | -5228.42 |  | -5228.42 |  |  | 92992.87 | 74701.31 | 18291.56 | 2014-09-19 | 2015-04-30 | 2014-10-01 | 2015-02-19
75086 | G7REPL | R3316 | R3316 - GLENCOE - WEBSTER/RAILROAD ST | -385.25 |  | -385.25 |  |  | 8697.13 | 13545.31 | -4848.18 | 2015-09-28 09:36 | 2016-04-09 | 2015-10-01 | 2015-12-31
75086 | G7REPL | R3461 | R3461 - STATION 577 INLET PIPING | -437.01 |  | -437.01 |  |  | 6391.91 | 43879.01 | -37487.1 | 2015-10-05 15:02 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R3462 | R3462 - STATION 577 OUTLET PIPING | -468.57 |  | -468.57 |  |  | 2770.74 | 17739.36 | -14968.62 | 2015-10-05 15:10 | 2016-06-15 | 2015-10-01 | 2016-03-17
75086 | G7REPL | R4609 | R4609 - RP 8866200 RIPPLE CREEK | -3216 |  | -3216 |  |  | 71711.28 | 51984.25 | 19727.03 | 2015-11-19 12:28 | 2016-06-18 | 2015-12-01 | 2016-05-20
75086 | G7REPL | S8507 | S8507 - CANCEL STA 809 WATERWORKS RD OUTLET | 15.17 |  | 15.17 |  |  | 0 | 11917.68 | -11917.68 | 2016-06-30 10:57 | 2018-12-31 | 2016-10-01 | 2018-10-01
75086 | G7REPL | T1130 | T1130 - RPL 11859007 BALLYSHANNON - RELOCAT | 337.54 |  | 337.54 |  |  | 593.15 | 37387.77 | -36794.62 | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | G7S3300 | V7041 | V7041 - LINE UL02 SEG 3300 PLEASANT VALLEY | -1802822.22 |  | -1802822.22 |  |  | -47965.95 | 2643704 | -2691669.95 | 2018-11-06 14:02 | 2020-07-30 | 2019-01-01 | 2020-01-15
75086 | G7SECCON | V5175 | V5175 - ERLANGER PROPANE SECURITY UPGRADE | 29783.02 |  | 29783.02 |  |  | 2949390.48 | 950000 | 1999390.48 | 2018-08-21 17:03 | 2020-05-14 | 2019-02-01 | 2020-03-31
75086 | G7SERVMC | 28519 | 28519 - HOPEFUL RD 6302/DMG | 515.7 |  | 515.7 |  |  | 515.69 | 0 | 515.69 | 2000-04-13 | 2050-12-31 | 1996-04-01 | 1996-07-17
75086 | G7SERVMC | 28716 | 28716 - PARK PL 19/DMG | 182.52 |  | 182.52 |  |  | 182 | 0 | 182 | 2000-04-13 | 2050-12-31 | 1996-05-01 | 1996-05-30
75086 | G7SERVMC | 28718 | 28718 - ALLISON 212/DMG | 102.6 |  | 102.6 |  |  | 102.31 | 0 | 102.31 | 2000-04-13 | 2050-12-31 | 1996-05-01 | 1996-05-30
75086 | G7SERVMC | A1592 | A1592 - 2312 CASINO DR | 112.57 |  | 112.57 |  |  | 112.57 | 0 | 112.57 | 2000-05-25 | 2050-12-31 | 2000-06-01 | 2002-12-18
75086 | G7SERVMC | A2242 | A2242 - 0000265/11 SHELBY/RENEW M-C | 182.66 |  | 182.66 |  |  | 181.97 | 0 | 181.97 | 2000-07-21 | 2050-12-31 | 2000-07-01 | 2002-12-18
75086 | G7SERVMC | A2367 | A2367 - 11722 MADISON PK/RENEW M-C | 24.4 |  | 24.4 |  |  | 24.4 | 0 | 24.4 | 2000-08-01 | 2050-12-31 | 2000-08-01 | 2002-12-18
75086 | G7SERVMC | A2577 | A2577 - 0000299/7114 PRICE PK | 223.94 |  | 223.94 |  |  | 221.43 | 0 | 221.43 | 2000-08-20 | 2050-12-31 | 2000-08-01 | 2002-12-18
75086 | G7SERVMC | C7799 | C7799 - CIMOS C-M 070 START 20061001 | -3430.5 |  | -3430.5 |  |  | 221012.1 | 0 | 221012.1 | 2006-08-25 | 2012-12-31 | 2006-10-01 | 2007-04-01
75086 | G7SERVMC | CMRP70 | CMRP70 - REPLACE C-M PLASTIC 2 INCH AND UNDE | 203768.63 |  | 203768.63 |  |  | 12435228.22 | 0 | 12435228.22 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | LCMRP70 | LCMRP70 - GREATER THAN 2" C-M REPL PLASTIC | 7137.67 |  | 7137.67 |  |  | 23375.83 | 2500000 | -2476624.17 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | LMCRP70 - GREATER THAN 2" M-C REPL PLASTIC | 55359.16 |  | 55359.16 |  |  | 255421.35 | 2500000 | -2244578.65 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | MCRP70 | MCRP70 - REPLACE (NON-AMRP) M-C PLASTIC 2 IN | 1095778.75 |  | 1095778.75 |  |  | 16842982.58 | 0 | 16842982.58 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | MCRS70 - REPLACE M-C STEEL 2 INCH AND UNDER | 5523.08 |  | 5523.08 |  |  | 530530.4 | 0 | 530530.4 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | CMNEWP70 | CMNEWP70 - NEW C-M PLASTIC 2 INCH AND UNDER KY | 419805.6 |  | 419805.6 |  |  | 7668402.08 | 1 | 7668401.08 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | CMNEWS70 - 2" OR LESS STEEL NEW C-M | 1153.07 |  | 1153.07 |  |  | 282503.71 | 5000000 | -4717496.29 | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVNEW | LCMNEWP70 | LCMNEWP70 - GREATER THAN 2" C-M PLASTIC | 528.97 |  | 528.97 |  |  | 234133.15 | 2500000 | -2265866.85 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVNEW | LMCNEWP70 | LMCNEWP70 - GREATER THAN 2" M-C PLASTIC | 158343.86 |  | 158343.86 |  |  | 447351.68 | 2500000 | -2052648.32 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | LMCNEWS70 - GREATER THAN 2" M-C STEEL | 57673.89 |  | 57673.89 |  |  | 102206.05 | 2500000 | -2397793.95 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVNEW | MCNEWP70 | MCNEWP70 - NEW M-C PLASTIC 2 INCH AND UNDER KY | 2451660.13 |  | 2451660.13 |  |  | 15176561.94 | 1 | 15176560.94 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | MCNEWS70 - NEW M-C STEEL 2 INCH AND UNDER KY | 31171.62 |  | 31171.62 |  |  | 235539.39 | 1 | 235538.39 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7STA876 | MX6800938 | MX6800938 - STA 876 WARSAW TOWN BORDER- STATION | 44447.29 |  | 44447.29 |  |  | 83601.88 | 252984 | -169382.12 | 2018-01-10 18:02 | 2022-09-30 | 2018-01-01 | 2023-09-29
75086 | G7TAM00B | AW2146 | AW2146 - LINE AM00B RETROFIT REPL | 641732.44 |  | 641732.44 |  |  | 641732.44 | 6528636 | -5886903.56 | 2020-05-19 16:54 | 2022-10-15 | 2020-05-01 | 2022-09-17
75086 | G7TOOLS | 28073 | 28073 - PURCHASE GAS TOOLS BLANKET | 133314.63 |  | 133314.63 |  |  | 720613.61 | 0 | 720613.61 | 2000-04-13 | 2015-12-31 | 1999-12-01
75086 | G7TUL06 | AW1592 | AW1592 - LINE UL06 - PIPELINE REPLACEMENTS | 570464.62 |  | 570464.62 |  |  | 570464.62 | 10253358 | -9682893.38 | 2020-01-05 02:41 | 2021-12-30 | 2020-02-01 | 2021-12-03
75086 | G7TUL06 | AW2021 | AW2021 - LINE UL06 - PIPELINE REPLACEMENTS L | 88255.28 |  | 88255.28 |  |  | 88255.28 | 115000 | -26744.72 | 2020-04-13 10:21 | 2021-12-31 | 2020-07-01 | 2021-12-03
75086 | G7UL02PH1 | V8191 | V8191 - UL60 PIPELINE PHASE 1 (PIPE) | 36195166.34 |  | 36195166.34 |  |  | 37992003.48 | 26326195 | 11665808.48 | 2019-01-23 15:21 | 2021-03-30 | 2019-01-01 | 2021-02-25
75086 | G7UL02PH1 | V8351 | V8351 - UL60 PIPELINE PHASE 1 (STATION) | 1729006.09 |  | 1729006.09 |  |  | 1729350.24 | 6287827 | -4558476.76 | 2019-02-11 09:25 | 2021-03-30 | 2019-07-01 | 2021-03-13
75086 | G7UL02PH1 | V8352 | V8352 - UL60 PIPELINE P1 - LAND RIGHTS PROJ | 3798057.96 |  | 3798057.96 |  |  | 4852995.35 | 1941000 | 2911995.35 | 2019-02-11 09:32 | 2021-03-30 | 2019-03-01 | 2021-02-25
75086 | G7UL02PH2 | V9444 | V9444 - PHASE II UL60 BYPASS | 1526340 |  | 1526340 |  |  | 1597274.76 | 22514005 | -20916730.24 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01 | 2021-11-18
75086 | G7UL02PH2 | V9445 | V9445 - PHASE II UL60 (LAND RIGHTS) | 1604209.27 |  | 1604209.27 |  |  | 1713352.22 | 733000 | 980352.22 | 2019-06-12 08:04 | 2022-02-02 | 2019-07-01 | 2021-11-18
75086 | G7WFD | MX5518434 | MX5518434 - WENDELL FORD DIST. PROJ; | 48672.71 |  | 48672.71 |  |  | 48672.71 | 262528 | -213855.29 | 2020-04-16 18:01 | 2020-10-02 | 2020-05-01 | 2021-02-11
75086 | G7WFD | MX6889178 | MX6889178 - CANCEL WENDELL FORD | 295.34 |  | 295.34 |  |  | 295.34 | 274232 | -273936.66 | 2020-05-22 14:01 | 2020-08-21 | 2020-05-01 | 2021-02-16
75086 | GITKYCAP | GSMRTLKSV | GSMRTLKSV - GAS SMART - LEAK SURVEY LINE PATROL | -3861.59 |  | -3861.59 |  |  | 232168.39 | 136600 | 95568.39 | 2016-08-26 15:21 | 2018-03-31 | 2016-09-01 | 2019-08-30
75086 | GITKYCAP | SMARTPH2 | SMARTPH2 - GAS SMART DATA AVAILABILITY PHASE 2 | -1511.73 |  | -1511.73 |  |  | 0 | 0 | 0 | 2015-12-11 15:15 | 2018-06-30 | 2015-12-01
75086 | GMAINS | MX0225249 | MX0225249 - LITTON LN. PRESSURE IMPROVEMENT PRO | 4041.26 |  | 4041.26 |  |  | 174150.89 | 133009.25 | 41141.64 | 2018-12-06 18:01 | 2019-03-10 | 2018-12-01 | 2019-04-10
75086 | KYCIBS05 | B8011 | B8011 - 2005 KY CIBS MODULE 321/DJS | -37815.58 |  | -37815.58 |  |  | 437078.36 | 0 | 437078.36 | 2004-05-11 | 2050-12-31 | 2004-07-01 | 2009-02-17
75086 | KYCIBS07 | C7795 | C7795 - CIBS M-C 070 START20061001 | -165034.96 |  | -165034.96 |  |  | 3489886.69 | 0 | 3489886.69 | 2006-08-25 | 2012-12-31 | 2006-10-01 | 2007-04-01
75086 | KYCIBS07 | C7796 | C7796 - CIBS C-M 070 STARTING 20061001 | -34436.52 |  | -34436.52 |  |  | 2937187.48 | 0 | 2937187.48 | 2006-08-25 | 2012-12-31 | 2006-10-01 | 2007-04-01
75086 | PCTAITMWM | PCTAIT85B | PCTAIT85B - INT85B CTA MWMS CONSOLIDATION | 22.33 |  | 22.33 |  |  | 1730253.21 | 285463 | 1444790.21 | 2015-11-03 15:32 | 2017-09-30 | 2015-10-01 | 2017-07-31
75086 | SG000358F | SG358HW19 | SG358HW19 - SG DEE MDM SCALE HWRE PHASE 4 - 358 | -8.88 |  | -8.88 |  |  | 40182.05 | 21102.66 | 19079.39 | 2018-05-09 10:59 | 2019-08-18 | 2018-05-01 | 2019-09-24
75086 | SG000358F | SG358SVR | SG358SVR - DEE MDM SCALE | 998.71 |  | 998.71 |  |  | 1791.14 | 1048 | 743.14 | 2019-09-24 08:02 | 2020-01-31 | 2019-11-01 | 2020-03-31
75086 | SG000358F | SG358SVR2 | SG358SVR2 - DEE MDM SCALE | 1309.93 |  | 1309.93 |  |  | 1309.93 | 1378 | -68.07 | 2020-04-16 07:19 | 2020-08-31 | 2020-04-01 | 2020-07-31
75086 | SG000489F | SG489SVR2 | SG489SVR2 - DEE OPENWAY SCALE | 198.82 |  | 198.82 |  |  | 10946.3 | 15568 | -4621.7 | 2019-01-22 21:54 | 2020-03-31 | 2019-01-01 | 2019-09-30
75086 | SG000489F | SG489SVR3 | SG489SVR3 - DEE OPENWAY SCALE | 3508.69 |  | 3508.69 |  |  | 3515.91 | 1190 | 2325.91 | 2019-09-25 08:08 | 2020-10-31 | 2019-09-01 | 2020-10-26
75086 | SG000489F | SG489SVR4 | SG489SVR4 - DEE OPENWAY SCALE | 3.8 |  | 3.8 |  |  | 3.8 | 442 | -438.2 | 2020-01-29 21:42 | 2020-10-31 | 2020-03-01
75086 | SG000489F | SG489SVRS | SG489SVRS - SG DEE OPENWAY SCALE SERVERS | 0.06 |  | 0.06 |  |  | 29590.47 | 31329.67 | -1739.2 | 2017-04-24 18:13 | 2018-12-31 | 2017-05-01 | 2019-03-31
75086 | SG000489F | SG489SW2 | SG489SW2 - DEE OPENWAY SCALE | 4525.02 |  | 4525.02 |  |  | 4525.02 | 2008 | 2517.02 | 2020-02-03 09:12 | 2020-10-31 | 2020-01-01 | 2020-10-26
75086 | SG000540F | SG540HW | SG540HW - DEE VEHICLE AREA NETWORK | 7311.18 |  | 7311.18 |  |  | 64790.92 | 117926 | -53135.08 | 2018-04-13 13:13 | 2020-12-17 | 2018-09-01 | 2021-05-15
75086 | SG000540F | SG540SW | SG540SW - DEE VEHICLE AREA NETWORK | 0.02 |  | 0.02 |  |  | 106.98 | 107801 | -107694.02 | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01 | 2018-07-16
75086 | SG000723F | SG723SW | SG723SW - DEE AMI OPERATIONS TOOL | 12707.36 |  | 12707.36 |  |  | 12707.36 | 26599 | -13891.64 | 2020-03-03 09:59 | 2022-07-30 | 2020-03-01 | 2022-07-31
75086 | SG000724F | SG724SW | SG724SW - DEE MDM TECHNICAL HEALTH | 8509.02 |  | 8509.02 |  |  | 8509.02 | 15916 | -7406.98 | 2020-08-19 16:46 | 2021-06-24 | 2020-08-01 | 2021-09-30
75086 | SG000781F | SG781SW | SG781SW - SG DEE PPM PIMS PHASE 2 BUILD OUT | -512.91 |  | -512.91 |  |  | 77935.76 | 76873.76 | 1062 | 2018-07-12 09:17 | 2021-03-31 | 2018-07-01 | 2022-03-31
75086 | SG000940F | SG940SVR | SG940SVR - DEE EDMS PLATFORM UPGRADE | 11756.78 |  | 11756.78 |  |  | 11756.78 | 9477 | 2279.78 | 2020-04-24 15:54 | 2020-12-18 | 2020-05-01 | 2021-02-07
75086 | SG001040F | SG1040SW | SG1040SW - DEE SGG LICENSE EXTENSION | 5410.35 |  | 5410.35 |  |  | 5410.35 | 0 | 5410.35 | 2020-04-16 17:27 | 2020-05-31 | 2020-04-01 | 2020-07-21
75086 | SG001042F | SG1042SW | SG1042SW - DEE OPENWAY LICENSE EXTENSION | 12021.54 |  | 12021.54 |  |  | 12021.54 | 11784 | 237.54 | 2020-07-28 22:06 | 2020-10-30 | 2020-09-01 | 2020-12-31
75086 | SGKAMIF | SG169MTRS | SG169MTRS - SG KY AMI GAS METERS - 169 | 1416.17 |  | 1416.17 |  |  | 9375353.98 | 9563026 | -187672.02 | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75087 | CUSTCONN | 315986A | 315986A - CUSTOMER CONNECT - CORE | 1357935.72 |  | 1357935.72 |  |  | 2928651.18 | 2325960.3 | 602690.88 | 2017-08-10 10:55 | 2022-12-05 | 2017-08-01 | 2022-07-06
75087 | CUSTCONN | 315986C | 315986C - CUSTOMER CONNECT- RELEASE 2 | 4981.53 |  | 4981.53 |  |  | 306109.87 | 187946.4 | 118163.47 | 2017-08-10 14:30 | 2019-05-28 | 2017-08-01 | 2019-06-18
75087 | CUSTCONN | 315986D | 315986D - CUSTOMER CONNECT- RELEASE 3 | 399.64 |  | 399.64 |  |  | 193413.5 | 280416.54 | -87003.04 | 2017-08-10 15:35 | 2019-12-30 | 2017-08-01 | 2019-12-31
75087 | CUSTCONN | 315986E | 315986E - CUSTOMER CONNECT- UNIVERSAL BILL | 84172.15 |  | 84172.15 |  |  | 243783.94 | 117210.08 | 126573.86 | 2017-08-11 10:44 | 2020-09-01 | 2017-08-01 | 2020-09-01
75087 | CUSTCONN | 315986HW5 | 315986HW5 - CUSTOMER CONNECT- HARDWARE PROJ 3 | 12854.79 |  | 12854.79 |  |  | 76178.91 | 42700 | 33478.91 | 2019-09-03 14:48 | 2020-06-01 | 2019-09-01 | 2020-06-15
75087 | CUSTCONN | 315986HW6 | 315986HW6 - CUSTOMER CONNECT- HARDWARE PROJ 4 | 58411.03 |  | 58411.03 |  |  | 58411.03 | 21350 | 37061.03 | 2020-03-12 11:33 | 2021-03-15 | 2020-03-01 | 2021-06-01
75087 | FPIT | 307482001 | 307482001 - CUSTOMER MOBILE APP - PHASE 2 | 127.69 |  | 127.69 |  |  | 21367.29 | 28166 | -6798.71 | 2018-12-28 09:17 | 2020-03-31 | 2019-01-01 | 2020-03-20
75087 | FPIT | 307482002 | 307482002 - CUSTOMER MOBILE APP - PHASE 3 | 3036.26 |  | 3036.26 |  |  | 3036.26 | 26324 | -23287.74 | 2019-12-19 13:54 | 2022-03-15 | 2020-01-01 | 2022-03-31
75087 | FPIT | 307482SW2 | 307482SW2 - CUSTOMER MOBILE APP - PHASE 3 | 13533.33 |  | 13533.33 |  |  | 13533.33 | 30258 | -16724.67 | 2020-04-13 09:32 | 2022-03-15 | 2020-04-01 | 2022-03-31
75087 | FPIT | 336593019 | 336593019 - NEW CALL CTR SIP TRUNKS | 60.93 |  | 60.93 |  |  | 15792.79 | 10444 | 5348.79 | 2018-03-14 16:47 | 2020-03-31 | 2018-03-01 | 2020-03-31
75087 | FPIT | 344598001 | 344598001 - DUKE CUSTOMER IVR REPLACEMENT | 9285.23 |  | 9285.23 |  |  | 151374.22 | 197081 | -45706.78 | 2018-04-10 15:29 | 2020-01-28 | 2018-04-01 | 2020-01-30
75087 | FPIT | 348527007 | 348527007 - MY DUKE REPLACEMENT | 4708.09 |  | 4708.09 |  |  | 68806.85 | 51758 | 17048.85 | 2019-10-02 08:40 | 2020-03-31 | 2019-10-01 | 2020-02-15
75087 | FPIT | 354154002 | 354154002 - DURABLE TEAM - DXT | 3252.22 |  | 3252.22 |  |  | 3252.22 | 20684 | -17431.78 | 2020-03-05 14:57 | 2020-09-28 | 2020-03-01 | 2020-09-30
75087 | FPIT | 354299001 | 354299001 - OUTAGE MAP REFRESH | 1552.87 |  | 1552.87 |  |  | 20759.85 | 21192.7 | -432.85 | 2019-10-02 10:55 | 2020-04-30 | 2019-10-01 | 2020-04-30
75087 | FPIT | CC1900001 | CC1900001 - CUSTOMER ANALYTICS ENGINE | 15571.32 |  | 15571.32 |  |  | 15571.32 | 26306 | -10734.68 | 2020-01-27 08:12 | 2022-03-31 | 2020-02-01 | 2022-03-31
75087 | FPIT | CC2000003 | CC2000003 - SITECORE JSS FRONT END MODERNIZATIO | 13423.97 |  | 13423.97 |  |  | 13423.97 | 28721 | -15297.03 | 2020-06-25 21:36 | 2022-05-30 | 2020-08-01 | 2022-05-31
75087 | FPIT | CS1900001 | CS1900001 - VOICE OF THE CUSTOMER ENGAGEMENT PL | 17478.27 |  | 17478.27 |  |  | 17478.27 | 13742 | 3736.27 | 2020-01-29 16:09 | 2022-03-31 | 2020-02-01 | 2022-03-31
75088 | CY1900015 | 349395006 | 349395006 - ITOT OT SIEM PHASE 2 WORKSTREAM | 120149.71 |  | 120149.71 |  |  | 120149.71 | 5497 | 114652.71 | 2020-04-13 16:35 | 2022-10-28 | 2020-05-01
75088 | CY1900015 | CY190HW15 | CY190HW15 - IT-OT ANA WORKSTREAM HW | 91.94 |  | 91.94 |  |  | 91.94 | 113909 | -113817.06 | 2019-12-11 08:05 | 2022-10-28 | 2020-01-01
|  |  |  | 81080369.51 | 64205603.6775 | 16874765.8325 | 20.81%

## 2021
Duke Energy Kentucky Natural Gas
Year 2021
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | EAMHPBU | 349472008 | 349472008 - EAM 2021 MAXIMO DURABLE TEAM | 41000.36 |  | 41000.36 |  |  | 41000.36 | 84630 | -43629.64 | 2021-01-22 15:11 | 2022-05-30 | 2021-02-01 | 2022-08-15
75086 | EAMHPBU | 349472009 | 349472009 - NEW EAM 2021 MOBILE DURABLE TEAM | 1734.55 |  | 1734.55 |  |  | 1734.55 | 39130 | -37395.45 | 2021-01-13 13:03 | 2022-05-30 | 2021-02-01 | 2022-08-15
75086 | FARCOSSW | ARCOS21 | ARCOS21 - ARCOS RENEWAL | 15.29 |  | 15.29 |  |  | 59342.1 | 59327 | 15.1 | 2020-12-17 10:40 | 2021-09-30 | 2020-12-01 | 2021-04-25
75086 | FMDT2020 | MDTGAS20 | MDTGAS20 - INSTALL WIN 7 PANASONIC TOUGHBOOKS | 31119.39 |  | 31119.39 |  |  | 495963.25 | 403995 | 91968.25 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01 | 2021-03-31
75086 | FPIT | 338802006 | 338802006 - SMALLWORLD/MYWORLD DURABLE TEAM | -10.99 |  | -10.99 |  |  | 0 | 48911 | -48911 | 2018-09-06 13:43 | 2020-05-28 | 2018-10-01 | 2020-11-10
75086 | FPIT | 338802HW3 | 338802HW3 - EAM PLATFORM OPTIMIZATION | -4.09 |  | -4.09 |  |  | 0 | 59872 | -59872 | 2018-04-25 14:36 | 2019-10-31 | 2020-07-01 | 2020-03-31
75086 | FPIT | 349472005 | 349472005 - ESRI SUBSCRIPTION LICENSE AGREEMENT | 91331.89 |  | 91331.89 |  |  | 91331.89 | 1153589 | -1062257.11 | 2020-12-15 19:05 | 2021-05-30 | 2021-01-01 | 2021-04-01
75086 | FPIT | 349472010 | 349472010 - NEW SMALLWORLD STORAGE SERVERS | 1337.96 |  | 1337.96 |  |  | 1337.96 | 17389 | -16051.04 | 2020-12-29 09:39 | 2022-03-31 | 2021-02-01 | 2022-03-31
75086 | FPIT | 349472016 | 349472016 - AUTODESK SUBSCRIPTION AGREEMENT | 11785.61 |  | 11785.61 |  |  | 11785.61 | 11803 | -17.39 | 2021-10-29 14:51 | 2022-03-20 | 2021-11-01 | 2022-03-20
75086 | FPIT | 349472S13 | 349472S13 - JUMP APPLICATION | 2432.81 |  | 2432.81 |  |  | 2432.81 | 2199.41 | 233.4 | 2021-02-08 08:20 | 2022-07-30 | 2021-06-01 | 2022-10-01
75086 | FPIT | 349472S14 | 349472S14 - NEW ESRI INTEGRATIONS AND INFRA | 4759.06 |  | 4759.06 |  |  | 4759.06 | 532359 | -527599.94 | 2021-02-09 13:04 | 2023-11-30 | 2021-03-01 | 2024-03-06
75086 | FPIT | 349472SW6 | 349472SW6 - EAM-SC NEXT GEN MOBILE PLATFORM SW | 8266.32 |  | 8266.32 |  |  | 8266.32 | 12210 | -3943.68 | 2020-12-15 21:01 | 2022-07-29 | 2021-01-01 | 2022-09-27
75086 | FPIT | CC2000001 | CC2000001 - NGBU COMMUNICATIONS PLATFORM | 33475.35 |  | 33475.35 |  |  | 58426.66 | 1242489 | -1184062.34 | 2020-03-30 13:53 | 2022-03-31 | 2020-04-01 | 2022-03-31
75086 | FPIT | GCTA30060 | GCTA30060 - CONSOLIDATED SCADA APP ANALYSIS | -1856.2 |  | -1856.2 |  |  | 275768.94 | 149205 | 126563.94 | 2017-04-11 15:19 | 2020-06-30 | 2017-04-01 | 2020-06-30
75086 | FPIT | GCTA3006K | GCTA3006K - INTGO_PI SCADA DATA IMPLEMENTATION | 1887.97 |  | 1887.97 |  |  | 91074.97 | 133026 | -41951.03 | 2019-11-15 07:17 | 2022-03-17 | 2019-11-01 | 2022-03-01
75086 | FPIT | GCTA47001 | GCTA47001 - INTGO_MATERIALS TRACEABILITY | -1028.35 |  | -1028.35 |  |  | 100529.46 | 120205 | -19675.54 | 2018-12-06 14:57 | 2022-03-31 | 2019-01-01 | 2020-05-31
75086 | FPIT | GCTA4700A | GCTA4700A - INTGO_TRACEABILITY FORM EAM | 58759.37 |  | 58759.37 |  |  | 58759.37 | 29280 | 29479.37 | 2018-12-04 14:21 | 2021-03-31 | 2019-01-01 | 2021-03-14
75086 | FPIT | GCTA4700B | GCTA4700B - INTGO_TRACEABILITY FORM FDC | 1741.91 |  | 1741.91 |  |  | 107662.01 | 215691 | -108028.99 | 2018-12-06 13:26 | 2021-03-31 | 2018-12-01 | 2021-03-14
75086 | FPIT | IT1900065 | IT1900065 - GDPM PHASE 2 | 5686.46 |  | 5686.46 |  |  | 74755.15 | 87832 | -13076.85 | 2020-02-07 07:49 | 2021-03-31 | 2020-02-01 | 2021-03-31
75086 | FPIT | IT1900067 | IT1900067 - ARM TO MAXIMO INTEGRATION | -1039.32 |  | -1039.32 |  |  | 13.89 | 0 | 13.89 | 2020-10-12 17:08 | 2021-07-31 | 2020-10-01 | 2021-07-27
75086 | FPIT | IT1900069 | IT1900069 - TRG - WAM MEASUREMENT PROJECT | -27329.92 |  | -27329.92 |  |  | 215.29 | 65041 | -64825.71 | 2020-02-21 15:10 | 2021-12-31 | 2020-03-01
75086 | FPIT | IT1900073 | IT1900073 - EAM 2020 MOBILE DURABLE TEAM | 11134.16 |  | 11134.16 |  |  | 84370.73 | 36572 | 47798.73 | 2020-01-20 08:44 | 2021-05-30 | 2020-01-01 | 2021-06-08
75086 | FPIT | IT1900074 | IT1900074 - EAM 2020 MAXIMO DURABLE TEAM | 3480.67 |  | 3480.67 |  |  | 188197.95 | 229288 | -41090.05 | 2020-01-20 10:57 | 2021-05-30 | 2020-01-01 | 2021-06-08
75086 | FPIT | IT2000091 | IT2000091 - GIM TOOL ENHANCEMENTS AND NOTIFICAT | 23799.98 |  | 23799.98 |  |  | 23799.98 | 37595 | -13795.02 | 2020-12-14 16:03 | 2022-03-31 | 2021-03-01 | 2022-06-25
75086 | FPIT | IT2000092 | IT2000092 - GTIS ENHANCEMENT AND ACOG | 93022.82 |  | 93022.82 |  |  | 93022.82 | 111184 | -18161.18 | 2020-12-22 10:20 | 2023-03-31 | 2021-01-01 | 2022-12-26
75086 | FPIT | IT2000093 | IT2000093 - NG SCADA TRAINING SIMULATOR | 2837.49 |  | 2837.49 |  |  | 2837.49 | 91646 | -88808.51 | 2020-12-29 14:47 | 2022-01-29 | 2021-02-01 | 2022-03-20
75086 | FPIT | IT2000095 | IT2000095 - TRACEABILITY PHASE 2 | 88056.54 |  | 88056.54 |  |  | 88056.54 | 275326 | -187269.46 | 2021-01-05 09:17 | 2022-03-31 | 2021-01-01 | 2022-03-31
75086 | FPIT | IT2000098 | IT2000098 - GAS SALES PLATFORM PHASE 2 | 224637 |  | 224637 |  |  | 224637 | 254148 | -29511 | 2021-01-21 10:30 | 2023-03-31 | 2021-01-01 | 2022-03-31
75086 | FPIT | IT2000111 | IT2000111 - KEY CONTROL SYSTEM | 31351.34 |  | 31351.34 |  |  | 31351.34 | 30928 | 423.34 | 2021-01-13 16:01 | 2022-03-31 | 2021-02-01 | 2022-05-31
75086 | FPIT | IT2100084 | IT2100084 - DEVONWAY LICENSE RENEWAL | 7509.41 |  | 7509.41 |  |  | 7509.41 | 47034 | -39524.59 | 2021-08-13 09:22 | 2022-08-31 | 2021-08-01 | 2022-08-31
75086 | FPIT | LTHGCHTRS | LTHGCHTRS - LIGHTHOUSE: GAS OPS CHARTER | 59810.52 |  | 59810.52 |  |  | 59810.52 | 86372 | -26561.48 | 2021-03-17 12:28 | 2022-09-30 | 2021-04-01 | 2022-06-30
75086 | FPIT | LTHGDBS | LTHGDBS - LIGHTHOUSE: GAS OPS - DAMAGE BILLIN | 1531.1 |  | 1531.1 |  |  | 1531.1 | 70748 | -69216.9 | 2020-11-19 07:31 | 2022-10-30 | 2021-01-01 | 2022-07-31
75086 | FPIT | TC2000057 | TC2000057 - PNG TELECOM - LNG AND COMPRESSOR ST | 54216.16 |  | 54216.16 |  |  | 54216.16 | 216847 | -162630.84 | 2020-12-22 09:43 | 2022-03-31 | 2021-01-01 | 2022-05-15
75086 | FPIT | V5136 | V5136 - COMMUNICATION RADIO INSTALL | -584.7 |  | -584.7 |  |  | 27005.33 | 23120 | 3885.33 | 2018-08-20 08:22 | 2018-12-31 | 2018-08-01 | 2019-07-31
75086 | FUNCTOHKY | 107GASCK | 107GASCK - GAS CAPITAL OVERHEAD | 490106.21 |  | 490106.21 |  |  | 1021314.474 | 0 | 1021314.474 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G701660 | AW4645 | AW4645 - EMERGENT AM01 COVINGTON LEVEE PH 1 | 57110.35 |  | 57110.35 |  |  | 57110.35 | 3601200 | -3544089.65 | 2021-10-01 08:50 | 2023-01-30 | 2021-10-01 | 2023-02-28
75086 | G701662 | AW4673 | AW4673 - EMERGENT - CASING 34 - TAYLOR MILL | 1881.13 |  | 1881.13 |  |  | 1881.13 | 3207100 | -3205218.87 | 2021-10-13 11:13 | 2023-02-28 | 2021-11-01 | 2023-01-07
75086 | G712237 | MX4669122 | MX4669122 - HEBRON LOOP PH 2 PRESSURE IMPROVEME | 31795.02 |  | 31795.02 |  |  | 31795.02 | 765.33 | 31029.69 | 2021-03-01 14:01 | 2027-03-04 | 2021-03-01
75086 | G71373 | AW0856 | AW0856 - 1373 US 27 BRIDGE ATTACHMENT | 3553.73 |  | 3553.73 |  |  | 71074.62 | 91770 | -20695.38 | 2019-07-30 08:26 | 2020-02-25 | 2019-11-01 | 2020-03-30
75086 | G7237BEAV | MX7783733 | MX7783733 - BEAVER RD INSTALL REPLACEMENT PROJE | -29.45 |  | -29.45 |  |  | 15861.38 | 48085 | -32223.62 | 2020-08-17 10:01 | 2020-10-30 | 2020-08-01 | 2021-01-10
75086 | G73701 | V8405 | V8405 - BRIDGE ATTACH 3701 NARROWS RD | 331.9 |  | 331.9 |  |  | 13049.91 | 11495.55 | 1554.36 | 2019-02-18 10:01 | 2020-02-25 | 2019-09-01 | 2019-12-18
75086 | G73MILES | T1437 | T1437 - STA 249: THREE MILE RD | -78.07 |  | -78.07 |  |  | 25443283.76 | 15406228 | 10037055.76 | 2017-01-05 11:19 | 2020-08-28 | 2017-01-01 | 2020-09-15
75086 | G74426 | AW4587 | AW4587 - CANCEL -GWUT DIGS ON AM07 (DUKE KY) | 182.47 |  | 182.47 |  |  | 182.47 | 491352 | -491169.53 | 2021-09-15 16:10 | 2022-03-31 | 2021-09-01
75086 | G7575RBA | AW3396 | AW3396 - 575 ROSSFORD BRIDGE ATTACHMENT | 13988.05 |  | 13988.05 |  |  | 13988.05 | 4495.62 | 9492.43 | 2021-01-20 09:57 | 2022-03-31 | 2021-03-01 | 2021-07-13
75086 | G7AM00ACR | AW3397 | AW3397 - LINE AM00A CORROSION REMEDIATION | 132680.26 |  | 132680.26 |  |  | 132680.26 | 180372.32 | -47692.06 | 2021-01-20 10:04 | 2022-03-31 | 2021-12-01 | 2022-03-20
75086 | G7AM07IL2 | AW4685 | AW4685 - LINE AM07 PIPELINE REPLACEMENT PHAS | 40203.98 |  | 40203.98 |  |  | 40203.98 | 33015500 | -32975296.02 | 2021-10-18 16:29 | 2025-02-28 | 2021-11-01 | 2025-02-06
75086 | G7AM07ILI | 0233100 | 0233100 - LINE AM07 PIPELINE REPLACEMENT PHAS | 771563.52 |  | 771563.52 |  |  | 772996.59 | 37717000 | -36944003.41 | 2020-12-09 14:11 | 2023-12-31 | 2020-12-01 | 2024-03-18
75086 | G7AM07ILI | AW3074 | AW3074 - LINE AM07 PIPELINE REPLACE LAND | 104336.53 |  | 104336.53 |  |  | 104336.53 | 6089500 | -5985163.47 | 2020-12-03 12:25 | 2023-12-31 | 2021-02-01 | 2024-03-18
75086 | G7AM07ILI | AW3138 | AW3138 - LINE AM07 PIPELINE REPLACEMENT-STN | 12927.68 |  | 12927.68 |  |  | 12927.68 | 6278300 | -6265372.32 | 2020-12-18 13:08 | 2024-04-30 | 2021-05-01 | 2024-09-28
75086 | G7ASDD | MX5515912 | MX5515912 - AMAZON SOUTHWEST DELIVERY DIST. PRO | 1349.31 |  | 1349.31 |  |  | 57737.18 | 307485 | -249747.82 | 2020-04-16 18:01 | 2020-10-11 | 2020-05-01 | 2021-04-04
75086 | G7ASRP | CMSP70 | CMSP70 - ASRP CURB TO METER 3" OR LESS | 1131.25 |  | 1131.25 |  |  | 8880564.01 | 20388002 | -11507437.99 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | G7ASRP | MCSP70 | MCSP70 - ASRP MAIN TO CURB 3" OR LESS | 631976.82 |  | 631976.82 |  |  | 42024287.79 | 19954384 | 22069903.79 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | G7CAS103 | MX6366123 | MX6366123 - 700 US RT 27 CASING #103 REMEDIATIO | 72847.71 |  | 72847.71 |  |  | 72847.71 | 19396.81 | 53450.9 | 2021-03-02 18:02 | 2020-12-18 | 2021-03-01 | 2021-11-12
75086 | G7CAS53 | V5417 | V5417 - CASING 53 LINE AM07 | -1050 |  | -1050 |  |  | 87763.8 | 409578 | -321814.2 | 2018-08-29 07:10 | 2018-12-30 | 2018-10-01 | 2019-03-01
75086 | G7CAS718 | V8637 | V8637 - CASING #718 AM07C US RT 50 | 36416.64 |  | 36416.64 |  |  | 36416.64 | 723819 | -687402.36 | 2019-03-13 15:45 | 2019-12-30 | 2019-04-01 | 2019-12-06
75086 | G7ECOMPLX | V8967 | V8967 - ERLANGER MODULAR COMPLEX | 174031.12 |  | 174031.12 |  |  | 380945.97 | 244737.99 | 136207.98 | 2019-04-17 13:32 | 2020-10-30 | 2019-06-01 | 2022-01-30
75086 | G7ENCC | AW3484 | AW3484 - ERLANGER CASINGS 2021 | 213742.1 |  | 213742.1 |  |  | 213742.1 | 181501.63 | 32240.47 | 2021-01-27 13:42 | 2022-03-31 | 2021-12-01 | 2022-04-13
75086 | G7ERGEMER | AW4046 | AW4046 - EMERGENCY ERLANGER GAS CUT OUT | 296125.86 |  | 296125.86 |  |  | 296125.86 | 95000 | 201125.86 | 2021-07-06 10:44 | 2021-10-30 | 2021-07-01 | 2021-11-06
75086 | G7ERLCP | AW1656 | AW1656 - ERLANGER MAG ANODES | 378991 |  | 378991 |  |  | 864969.94 | 2442881.69 | -1577911.75 | 2020-01-21 15:36 | 2026-12-31 | 2020-04-01
75086 | G7HICKSP | MX5739585 | MX5739585 - HICKS PIKE PRESSURE IMPROVEMENT PRO | 747187.31 |  | 747187.31 |  |  | 747187.31 | 254017.35 | 493169.96 | 2021-04-20 18:02 | 2022-02-24 | 2021-05-01 | 2022-02-02
75086 | G7HMISTAT | AW0938 | AW0938 - HMI WORK STATION ERLANGER | 3864.36 |  | 3864.36 |  |  | 92775.69 | 64259 | 28516.69 | 2019-08-09 13:08 | 2021-03-02 | 2019-10-01 | 2021-08-15
75086 | G7IMPRPL | R0964 | R0964 - REPLACE BANKLICK RD STATION INLET P | -395894.89 |  | -395894.89 |  |  | -395894.89 | 198120 | -594014.89 | 2015-07-06 15:00 | 2016-09-10 | 2015-07-01 | 2016-08-27
75086 | G7INTDIG | AW2017 | AW2017 - LINE UL06 INTEGRITY DIGS | -62553.62 |  | -62553.62 |  |  | 1326004.01 | 2024700 | -698695.99 | 2020-04-09 07:34 | 2021-01-30 | 2020-04-01 | 2021-01-05
75086 | G7INTDIG | AW2018 | AW2018 - LINE UL47 INTEGRITY DIGS | -25879.82 |  | -25879.82 |  |  | 811502.24 | 748000 | 63502.24 | 2020-04-09 07:40 | 2021-01-30 | 2020-04-01 | 2020-10-09
75086 | G7LGMR | C9523 | C9523 - PP864309/CWA | -2677.75 |  | -2677.75 |  |  | -2677.75 | 0 | -2677.75 | 2007-03-29 | 2050-12-31 | 2007-04-01 | 2007-10-08
75086 | G7LGMR | C9571 | C9571 - CANCEL 2 STA 781-NUNN & UNV/CWA | -288.22 |  | -288.22 |  |  | -288.22 | 0 | -288.22 | 2007-04-10 | 2050-12-31 | 2007-04-01 | 2008-05-05
75086 | G7LGMR | E4656 | E4656 - ABANDON SYSTEM STA 58 | -1240 |  | -1240 |  |  | -1240 | 0 | -1240 | 2009-03-03 | 2011-04-30 | 2010-03-01 | 2009-11-24
75086 | G7LGMR | H0265 | H0265 - REG 118K INSTALLATION | 4197.28 |  | 4197.28 |  |  | 4197.28 | 77199.74 | -73002.46 | 2013-06-14 | 2016-06-30 | 2014-10-01 | 2016-01-25
75086 | G7LGMR | H0485 | H0485 - REG 21K IMPROVEMENTS-GRAND & FT THO | -2730 |  | -2730 |  |  | -2730 | 30577.41 | -33307.41 | 2013-07-29 | 2015-06-30 | 2013-11-01 | 2014-02-11
75086 | G7LGMR | MX2218039 | MX2218039 - INSTALL SCADA EQ-THREE MILE RD STA | 52619.65 |  | 52619.65 |  |  | 601162.64 | 411228.18 | 189934.46 | 2017-09-21 14:01 | 2020-07-10 | 2017-10-01 | 2020-09-15
75086 | G7LGMR | MX6693835 | MX6693835 - (CANCEL) REG 412 - 9TH & OVERTON | -59230.8 |  | -59230.8 |  |  | 0.02 | 106314.24 | -106314.22 | 2017-12-15 14:01 | 2021-03-31 | 2018-02-01
75086 | G7LGMR | MX8652267 | MX8652267 - OAKLAND VALVE HOUSE SCADA INSTALL | 22250.57 |  | 22250.57 |  |  | 22250.57 | 107193 | -84942.43 | 2018-12-11 10:01 | 2019-09-30 | 2019-03-01 | 2019-10-24
75086 | G7LGMR | MX8672523 | MX8672523 - (CANCEL)REG 119 BRISTOW RICHARDSON | -40673.75 |  | -40673.75 |  |  | 0 | 262006.08 | -262006.08 | 2019-03-21 14:01 | 2020-08-31 | 2019-05-01
75086 | G7LGMR | T4002 | T4002 - (CANCEL) STA 20933317 ERLANGER CP | -2330.43 |  | -2330.43 |  |  | -2330.43 | 31943.04 | -34273.47 | 2017-03-17 11:42 | 2018-12-30 | 2017-08-01
75086 | G7LGMR | T7778 | T7778 - CANCEL-SCAD 21153712 KY | -1005.94 |  | -1005.94 |  |  | -1005.94 | 165811.2 | -166817.14 | 2017-05-03 08:00 | 2018-06-29 | 2017-05-01
75086 | G7LNUL57 | AW0832 | AW0832 - LINE UL57 MONOLITHIC INSULATORS | 1941.31 |  | 1941.31 |  |  | 1028730.8 | 564646 | 464084.8 | 2019-07-26 13:48 | 2020-12-25 | 2020-03-01 | 2020-12-03
75086 | G7LUL02 | AW2880 | AW2880 - LINE UL02 - MAOP REPLACEMENT | 3211918.51 |  | 3211918.51 |  |  | 3233276.5 | 1717200 | 1516076.5 | 2020-10-07 12:58 | 2022-03-31 | 2020-10-01 | 2022-01-05
75086 | G7LUL02 | AW3546 | AW3546 - LINE UL 02 MAOP REPL LAND | 56529.92 |  | 56529.92 |  |  | 56529.92 | 50000 | 6529.92 | 2021-02-04 13:42 | 2022-03-31 | 2021-02-01 | 2022-01-05
75086 | G7MAINS | C9770 | C9770 - CANCEL 2 STA 781-INLET/CWA | -108.41 |  | -108.41 |  |  | -108.41 | 0 | -108.41 | 2007-05-06 | 2050-12-31 | 2007-05-01 | 2008-05-05
75086 | G7MAINS | D1230 | D1230 - CANCEL 2 844337/CHRIS AMPHER | -1625.16 |  | -1625.16 |  |  | -1625.16 | 0 | -1625.16 | 2007-07-23 | 2050-12-31 | 2007-09-01 | 2008-08-12
75086 | G7MAINS | E0351 | E0351 - CANCEL 2 REG 51 INLET & OUTLET | -295.38 |  | -295.38 |  |  | -295.38 | 62278 | -62573.38 | 2008-08-06 | 2009-12-31 | 2009-06-01 | 2008-08-06
75086 | G7MAINS | E0468 | E0468 - STA 795 OUTLET PIPING | -304.8 |  | -304.8 |  |  | -304.8 | 12659 | -12963.8 | 2008-08-12 | 2050-12-31 | 2008-09-01 | 2009-01-15
75086 | G7MAINS | E4954 | E4954 - PP#1055138 2344 AMSTERDAM RD | -443.97 |  | -443.97 |  |  | -443.97 | 1 | -444.97 | 2009-03-19 | 2010-12-31 | 2009-06-01 | 2009-10-01
75086 | G7MAINS | E5278 | E5278 - STA 793 INLET PIPING | -889.74 |  | -889.74 |  |  | -889.74 | 28188 | -29077.74 | 2009-03-30 | 2014-03-10 | 2009-04-01 | 2010-02-24
75086 | G7MAINS | E5285 | E5285 - STA 793 - OUTLET PIPING | -706.2 |  | -706.2 |  |  | -706.2 | 21068 | -21774.2 | 2009-03-31 | 2014-03-11 | 2009-04-01 | 2010-02-24
75086 | G7MAINS | G1999 | G1999 - STA 810 OUTLET PIPING F/L AM3 | -501.43 |  | -501.43 |  |  | -501.43 | 15532 | -16033.43 | 2011-01-27 | 2013-06-01 | 2011-04-01 | 2012-02-04
75086 | G7MAINS | G3688 | G3688 - STA 806 OUTLET PIPING | -2367.75 |  | -2367.75 |  |  | -2367.75 | 10521.7 | -12889.45 | 2011-06-15 | 2012-06-30 | 2011-07-01 | 2012-01-28
75086 | G7MAINS | G3690 | G3690 - STA 806 INLET PIPING | -1128.96 |  | -1128.96 |  |  | -1128.96 | 20049.74 | -21178.7 | 2011-06-15 | 2012-03-31 | 2011-07-01 | 2012-01-28
75086 | G7MAINS | G5113 | G5113 - REG 110K INLET & OUTLET PIPING | -2697.37 |  | -2697.37 |  |  | -2697.37 | 46957.49 | -49654.86 | 2011-09-28 | 2013-02-10 | 2012-06-01 | 2012-11-17
75086 | G7MAINS | G8058 | G8058 - CANCEL 2 JT EMAX 3298935 ARCADIA | 338.59 |  | 338.59 |  |  | 338.59 | 49594.21 | -49255.62 | 2012-07-13 | 2014-11-30 | 2013-07-01 | 2014-02-26
75086 | G7MAINS | H1364 | H1364 - CANCEL 2 SUTTER DRIVE MN EXTENSION | -550.46 |  | -550.46 |  |  | -550.46 | 1 | -551.46 | 2013-12-02 | 2014-11-30 | 2015-08-01 | 2015-12-09
75086 | G7MAINS | MEAPJT70 | MEAPJT70 - JOINT TRENCH PLASITC MAIN EXTENSION | 1126598.77 |  | 1126598.77 |  |  | 4877162.04 | 10000000 | -5122837.96 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | G7MAINS | MX0245370 | MX0245370 - REDWOOD LIVING APARTMENTS - APPROAC | 11138.38 |  | 11138.38 |  |  | 11138.38 | 53405.95 | -42267.57 | 2021-09-07 10:02 | 2022-05-29 | 2021-09-01 | 2022-04-20
75086 | G7MAINS | MX0270903 | MX0270903 - FARM TAP PROJ. 3 MILE RD | -11094.01 |  | -11094.01 |  |  | 403127.22 | 365844.57 | 37282.65 | 2019-03-21 14:01 | 2019-10-19 | 2019-04-01 | 2019-12-21
75086 | G7MAINS | MX0536654 | MX0536654 - CANCEL-NEWPORT CLIFTON SU - HOME | 35.46 |  | 35.46 |  |  | 35.46 | 765.33 | -729.87 | 2021-04-12 14:03 | 2024-08-13 | 2021-06-01
75086 | G7MAINS | MX0556249 | MX0556249 - FARM TAP PROJ; CALIFORNIA CROSSROAD | -6460.46 |  | -6460.46 |  |  | 270898.43 | 123394.12 | 147504.31 | 2019-01-14 10:01 | 2019-10-24 | 2019-05-01 | 2020-01-03
75086 | G7MAINS | MX0579746 | MX0579746 - JT-G-RIVERS POINTE ESTATES PHASE 1 | 50228.34 |  | 50228.34 |  |  | 75498.83 | 109259 | -33760.17 | 2020-03-09 14:01 | 2020-09-24 | 2020-11-01 | 2021-06-13
75086 | G7MAINS | MX0590999 | MX0590999 - FARM TAP; E LOW GAP RD ALEXANDRIA | 14074 |  | 14074 |  |  | 386865.12 | 359350.5 | 27514.62 | 2019-07-31 14:01 | 2022-10-19 | 2019-08-01 | 2020-05-21
75086 | G7MAINS | MX0602140 | MX0602140 - FARM TAP PROJ; ENZWEILER RD | 192857.58 |  | 192857.58 |  |  | 200085.05 | 83366.18 | 116718.87 | 2020-09-01 18:01 | 2021-10-17 | 2020-09-01 | 2021-10-06
75086 | G7MAINS | MX0602571 | MX0602571 - FARM TAP PROJ; JOHNS HILL RD | -279.69 |  | -279.69 |  |  | 15775.04 | 112220.53 | -96445.49 | 2019-07-16 10:02 | 2019-12-12 | 2019-07-01 | 2020-06-02
75086 | G7MAINS | MX0610527 | MX0610527 - JT-G-BALLYSHANNON SECTION 5 PHASE 9 | 135.22 |  | 135.22 |  |  | 135.22 | 42242.95 | -42107.73 | 2021-11-30 14:02 | 2022-11-20 | 2021-12-01 | 2022-09-09
75086 | G7MAINS | MX0864994 | MX0864994 - MADONNA MANOR PH 2 MEA, VILLA HILLS | 14629.5 |  | 14629.5 |  |  | 14629.5 | 72524.38 | -57894.88 | 2021-09-24 14:02 | 2021-12-21 | 2021-10-01 | 2022-05-13
75086 | G7MAINS | MX0938445 | MX0938445 - JT-G-AUTUMN RIDGE PHASE 1 PART B | 8732.37 |  | 8732.37 |  |  | 8732.37 | 45429 | -36696.63 | 2021-11-16 14:01 | 2022-08-17 | 2021-12-01 | 2022-04-22
75086 | G7MAINS | MX0964990 | MX0964990 - 425' PLASTIC GAS MAIN EXTENSION. SA | 68974.5 |  | 68974.5 |  |  | 68974.5 | 26396.88 | 42577.62 | 2021-07-19 14:02 | 2024-12-24 | 2021-08-01 | 2022-02-02
75086 | G7MAINS | MX1062851 | MX1062851 - HOGREFE RD MEA-171 FT 4 INCH PL HP | 17072.49 |  | 17072.49 |  |  | 17072.49 | 18025.99 | -953.5 | 2021-07-26 14:02 | 2024-12-17 | 2021-08-01 | 2021-12-21
75086 | G7MAINS | MX1130180 | MX1130180 - FARM TAP PROJ; MARTHA LAYNE COLLINS | -1091.34 |  | -1091.34 |  |  | 73448.25 | 62900.69 | 10547.56 | 2019-02-07 10:02 | 2019-04-03 | 2019-03-01 | 2020-03-17
75086 | G7MAINS | MX1289118 | MX1289118 - CENTRE VIEW FARM TAP PROJECT - CRES | 36067.08 |  | 36067.08 |  |  | 36067.08 | 53119.94 | -17052.86 | 2021-03-19 10:02 | 2021-07-04 | 2021-03-01 | 2021-09-16
75086 | G7MAINS | MX1304901 | MX1304901 - FARM TAP PROJ; WAGONER RD CALIFORNI | -973.48 |  | -973.48 |  |  | 34132.31 | 46479.42 | -12347.11 | 2019-06-26 14:01 | 2019-11-14 | 2019-07-01 | 2020-01-22
75086 | G7MAINS | MX1356700 | MX1356700 - FARM TAP PROJ; WINTERS LN HIGHLAND | -4275.56 |  | -4275.56 |  |  | 254247.29 | 147466.28 | 106781.01 | 2019-06-27 10:02 | 2019-12-26 | 2019-07-01 | 2020-03-11
75086 | G7MAINS | MX1688384 | MX1688384 - NEW BUFFINGTON PH 2 EXTENSION; ELSE | 21997.82 |  | 21997.82 |  |  | 21997.82 | 25500.96 | -3503.14 | 2021-09-08 10:01 | 2024-04-23 | 2021-09-01 | 2022-02-03
75086 | G7MAINS | MX1811415 | MX1811415 - 137 PLAZA DR. FARM TAP,HIGHLAND HEI | 22852.36 |  | 22852.36 |  |  | 22852.36 | 34481.14 | -11628.78 | 2021-09-24 14:02 | 2022-03-03 | 2021-10-01 | 2022-02-08
75086 | G7MAINS | MX1921442 | MX1921442 - FARM TAP PROJECT REDSTONE RD - ALEX | 194716.98 |  | 194716.98 |  |  | 194716.98 | 74423.61 | 120293.37 | 2021-03-24 10:02 | 2024-10-07 | 2021-04-01 | 2021-11-30
75086 | G7MAINS | MX1957438 | MX1957438 - FARM TAP PROJ; GRANDVIEW RD | 468420.76 |  | 468420.76 |  |  | 520043.81 | 161978.74 | 358065.07 | 2020-09-29 10:01 | 2021-12-16 | 2020-09-01 | 2022-01-10
75086 | G7MAINS | MX1957677 | MX1957677 - FARM TAP PROJECT; UPPER LICK BRANCH | 132281.64 |  | 132281.64 |  |  | 132281.64 | 88637.51 | 43644.13 | 2021-10-12 14:01 | 2022-06-16 | 2021-10-01 | 2022-05-08
75086 | G7MAINS | MX1958084 | MX1958084 - FARM TAP PROJ; FLAGG SPRINGS PIKE | -6088.57 |  | -6088.57 |  |  | 574985.86 | 541626 | 33359.86 | 2020-02-05 10:02 | 2020-05-22 | 2020-02-01 | 2020-10-30
75086 | G7MAINS | MX2043872 | MX2043872 - FARM TAP PROJ; BARRS BRANCH RD | 134575.86 |  | 134575.86 |  |  | 134575.86 | 83717.7 | 50858.16 | 2021-08-20 10:02 | 2022-06-23 | 2021-08-01 | 2022-05-29
75086 | G7MAINS | MX2142600 | MX2142600 - FARM TAP PROJ; THORNTON RD | -625.83 |  | -625.83 |  |  | 27460.57 | 54541.9 | -27081.33 | 2019-07-18 18:01 | 2019-12-19 | 2019-07-01 | 2020-01-26
75086 | G7MAINS | MX2143073 | MX2143073 - FARM TAP PROJ; REIDLIN RD | -776.77 |  | -776.77 |  |  | 36379.6 | 43437.77 | -7058.17 | 2019-05-21 18:01 | 2019-10-31 | 2019-06-01 | 2020-01-22
75086 | G7MAINS | MX2271880 | MX2271880 - MEA ~800 FT; 494 JONES RD | 178.68 |  | 178.68 |  |  | 242928.81 | 163070 | 79858.81 | 2019-07-30 10:01 | 2020-02-27 | 2019-08-01 | 2020-05-13
75086 | G7MAINS | MX2331188 | MX2331188 - MEA, MASON ROAD FARM TAP-TAYLOW MIL | 351566.99 |  | 351566.99 |  |  | 351566.99 | 240393.36 | 111173.63 | 2021-09-15 18:02 | 2022-08-25 | 2021-10-01 | 2022-08-02
75086 | G7MAINS | MX2424919 | MX2424919 - MEA ~550 FT; 2000 GATEWAY BLVD | -726.49 |  | -726.49 |  |  | 31627.58 | 50615.9 | -18988.32 | 2019-07-02 14:01 | 2019-12-12 | 2019-07-01 | 2020-01-18
75086 | G7MAINS | MX2848811 | MX2848811 - INDEPENDENCE RD MEA - | -104.77 |  | -104.77 |  |  | 5447.04 | 35185 | -29737.96 | 2019-09-30 10:01 | 2020-01-30 | 2019-10-01 | 2020-02-02
75086 | G7MAINS | MX3351619 | MX3351619 - HIGHLAND AVE AND WOODLAND PL MAE - | 3361.48 |  | 3361.48 |  |  | 3361.48 | 19811.35 | -16449.87 | 2021-12-10 14:02 | 2022-05-19 | 2021-12-01 | 2022-03-27
75086 | G7MAINS | MX4146445 | MX4146445 - MEA ~ 25 FT; 411 COACHLIGHT DR | 93.76 |  | 93.76 |  |  | 3379.13 | 13325 | -9945.87 | 2019-10-01 14:01 | 2020-02-13 | 2019-11-01 | 2020-01-20
75086 | G7MAINS | MX4210795 | MX4210795 - JT-G-BALLYSHANNON SECTION 5 PHASE 6 | -452.71 |  | -452.71 |  |  | 37073.08 | 52790 | -15716.92 | 2019-12-19 10:01 | 2020-12-31 | 2020-01-01 | 2020-08-21
75086 | G7MAINS | MX4837396 | MX4837396 - JT-G-PARK POINTE | 53080.59 |  | 53080.59 |  |  | 53378.61 | 81024 | -27645.39 | 2020-02-24 14:07 | 2021-02-24 | 2020-03-01 | 2021-07-14
75086 | G7MAINS | MX4861864 | MX4861864 - TERMINAL DR MEA-CVG CONRAC PROJECT | 8400.86 |  | 8400.86 |  |  | 167555.18 | 166549 | 1006.18 | 2020-06-12 14:01 | 2020-12-17 | 2020-06-01 | 2021-01-12
75086 | G7MAINS | MX4875568 | MX4875568 - FARM TAP PROJECT; E ALEXANDRIA / CA | 108573.85 |  | 108573.85 |  |  | 1052420.86 | 1255100 | -202679.14 | 2020-03-03 10:01 | 2020-09-11 | 2020-03-01 | 2020-12-26
75086 | G7MAINS | MX5652554 | MX5652554 - CANCEL-MASON-TAYLOR MILL-4IN PE 6IN | -4977.79 |  | -4977.79 |  |  | 23.46 | 237226.07 | -237202.61 | 2020-12-16 10:17 | 2021-09-24 | 2020-12-01
75086 | G7MAINS | MX5653109 | MX5653109 - FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 372181.52 |  | 372181.52 |  |  | 372959.99 | 194197.42 | 178762.57 | 2020-09-29 10:01 | 2023-07-13 | 2020-10-01 | 2023-11-15
75086 | G7MAINS | MX5709107 | MX5709107 - CANCEL-FARM TAP PROJ; BRANCH RD | 9.49 |  | 9.49 |  |  | 9.49 | 83287.78 | -83278.29 | 2021-02-25 18:02 | 2021-12-16 | 2021-02-01
75086 | G7MAINS | MX5913989 | MX5913989 - JT-G-AUTUMN RIDGE PHASE 1 PART A | 39027.32 |  | 39027.32 |  |  | 39027.32 | 49557.87 | -10530.55 | 2020-12-17 14:02 | 2021-05-31 | 2021-01-01 | 2021-06-22
75086 | G7MAINS | MX5924338 | MX5924338 - JT-G-RIVERS POINTE ESTATES PHASE 1B | 40856.91 |  | 40856.91 |  |  | 40856.91 | 58425.01 | -17568.1 | 2021-03-11 14:10 | 2020-09-28 | 2021-03-01 | 2021-08-30
75086 | G7MAINS | MX6180533 | MX6180533 - 440 FT MEA; MEDICAL VILLAGE DR | 1733.89 |  | 1733.89 |  |  | 105969.53 | 74687 | 31282.53 | 2020-07-29 14:01 | 2020-10-16 | 2020-08-01 | 2021-01-25
75086 | G7MAINS | MX6243694 | MX6243694 - ~400 FT MEA; DOLWICK DR | 1346.16 |  | 1346.16 |  |  | 60831.25 | 104176 | -43344.75 | 2020-06-18 10:01 | 2020-09-29 | 2020-07-01 | 2021-04-07
75086 | G7MAINS | MX6245365 | MX6245365 - ~425 FT MEA; SARAH LN | 154.79 |  | 154.79 |  |  | 10735.34 | 26839.9 | -16104.56 | 2020-08-31 14:01 | 2020-11-15 | 2020-09-01 | 2021-02-10
75086 | G7MAINS | MX6684040 | MX6684040 - ~1825 FTMEA; WRIGHT BLVD | 93530.96 |  | 93530.96 |  |  | 143429.55 | 117730.07 | 25699.48 | 2020-10-02 10:01 | 2020-12-18 | 2020-10-01 | 2021-03-08
75086 | G7MAINS | MX6835553 | MX6835553 - JT-G-SOUTHWICK PHASE B PART 1 | 52091.14 |  | 52091.14 |  |  | 52149.02 | 46988.86 | 5160.16 | 2020-11-23 18:02 | 2021-08-19 | 2020-12-01 | 2021-07-25
75086 | G7MAINS | MX6891268 | MX6891268 - CANCEL AMAZON SOUTHWEST DELIVERY | -5684.98 |  | -5684.98 |  |  | 270054.26 | 319190 | -49135.74 | 2020-05-22 14:01 | 2021-03-31 | 2020-05-01
75086 | G7MAINS | MX7078370 | MX7078370 - CANCEL INVESTMENT WAY MEA | -255.01 |  | -255.01 |  |  | 0 | 39282 | -39282 | 2020-08-14 10:01 | 2020-10-16 | 2020-08-01
75086 | G7MAINS | MX7122512 | MX7122512 - 100 FT MEA; 10009 INDIAN HILL DR | 1554.76 |  | 1554.76 |  |  | 27626.47 | 21629.68 | 5996.79 | 2020-09-22 10:01 | 2020-11-27 | 2020-10-01 | 2021-03-12
75086 | G7MAINS | MX7231229 | MX7231229 - STONEWATER APPROACH MAIN | 573471.27 |  | 573471.27 |  |  | 578083.22 | 201665.76 | 376417.46 | 2020-12-15 10:01 | 2021-12-18 | 2020-12-01 | 2021-08-14
75086 | G7MAINS | MX7488442 | MX7488442 - CANCEL-UARY VILLAGE PHASE 1 PART 3 | -75.39 |  | -75.39 |  |  | 40.85 | 44181.42 | -44140.57 | 2020-09-23 10:01 | 2023-03-22 | 2020-10-01
75086 | G7MAINS | MX7900133 | MX7900133 - NORTH DILCREST - FLORENCE - 2" PE - | 57298.63 |  | 57298.63 |  |  | 57298.63 | 31910.76 | 25387.87 | 2021-01-22 14:01 | 2021-07-22 | 2021-02-01 | 2021-07-22
75086 | G7MAINS | MX8030455 | MX8030455 - CAMP ERNST AND SOLOMON MAE | 9406.69 |  | 9406.69 |  |  | 42355.36 | 42778.64 | -423.28 | 2020-10-19 18:01 | 2021-04-12 | 2020-11-01 | 2021-04-26
75086 | G7MAINS | MX8059955 | MX8059955 - ~440 FT MEA; 2 IN PL HP | 35392.51 |  | 35392.51 |  |  | 37873.32 | 29426.19 | 8447.13 | 2020-12-01 14:18 | 2021-05-11 | 2020-12-01 | 2021-05-06
75086 | G7MAINS | MX8197104 | MX8197104 - JT-G-REDWOOD LIVING APARTMENTS | 219.48 |  | 219.48 |  |  | 219.48 | 95065.91 | -94846.43 | 2021-03-26 18:02 | 2022-12-30 | 2021-04-01 | 2022-12-19
75086 | G7MAINS | MX8230937 | MX8230937 - JT-G-ARCADIA PHASE K & L | 34547.5 |  | 34547.5 |  |  | 34547.5 | 80397.42 | -45849.92 | 2021-01-05 14:02 | 2021-12-28 | 2021-01-01 | 2021-07-26
75086 | G7MAINS | MX8451945 | MX8451945 - INVESTMENT WAY MEA | 503.87 |  | 503.87 |  |  | 27319.26 | 16224.75 | 11094.51 | 2020-10-16 10:01 | 2020-12-30 | 2020-11-01 | 2021-02-02
75086 | G7MAINS | MX8505395 | MX8505395 - ~350 FT MEA; 351 KENTON LANDS | 65911.81 |  | 65911.81 |  |  | 66365.11 | 32683.85 | 33681.26 | 2020-12-01 14:18 | 2021-02-28 | 2020-12-01 | 2021-06-28
75086 | G7MAINS | MX8574441 | MX8574441 - GAS MAIN EXTENSION - 10177 BIG BONE | -3913.87 |  | -3913.87 |  |  | 97620.72 | 80515.92 | 17104.8 | 2018-08-22 14:02 | 2018-10-19 | 2018-08-01 | 2019-06-02
75086 | G7MAINS | MX8593433 | MX8593433 - JT-G-BATTLERIDGE PHASE G PART 2 | 19742.01 |  | 19742.01 |  |  | 19742.01 | 57245.07 | -37503.06 | 2020-12-17 14:02 | 2022-02-02 | 2021-01-01 | 2021-07-14
75086 | G7MAINS | MX8822845 | MX8822845 - NEW BUFFINGTON RD - ELSMERE - 6" PE | 100011.36 |  | 100011.36 |  |  | 100011.36 | 84635.35 | 15376.01 | 2021-01-25 10:02 | 2021-04-23 | 2021-02-01 | 2021-08-09
75086 | G7MAINS | MX9801147 | MX9801147 - ELIJAH CREEK LOOP; NEYER DEVELOPMEN | 3232.35 |  | 3232.35 |  |  | 3232.35 | 88032.99 | -84800.64 | 2021-11-30 14:02 | 2022-07-07 | 2021-12-01 | 2022-06-27
75086 | G7MAINS | MX9803235 | MX9803235 - MARY GRUBS HWY - WALTON - 4" PE - M | 33616.61 |  | 33616.61 |  |  | 33616.61 | 20070.03 | 13546.58 | 2021-05-10 10:02 | 2024-10-21 | 2021-06-01 | 2022-01-20
75086 | G7MAINS | P6888 | P6888 - 201 STEELMAN MEA | -638.93 |  | -638.93 |  |  | -638.93 | 11920.73 | -12559.66 | 2014-11-20 | 2015-08-20 | 2015-02-01 | 2015-06-14
75086 | G7MAINS | S2732 | S2732 - GO 9691430 STA 836 INLET PIPING | -17842.45 |  | -17842.45 |  |  | -17842.45 | 91976.45 | -109818.9 | 2016-04-29 10:50 | 2018-12-11 | 2016-05-01 | 2016-12-28
75086 | G7MAINS | S2752 | S2752 - GO 9691542 STA 836 OUTLET PIPING | 188728.07 |  | 188728.07 |  |  | 188728.07 | 48219.36 | 140508.71 | 2016-04-29 11:23 | 2018-05-11 | 2016-05-01 | 2016-12-28
75086 | G7MASOINT | AW3449 | AW3449 - DUKE MASON INTERCONNECT (KY) | 891362.09 |  | 891362.09 |  |  | 891362.09 | 2000000 | -1108637.91 | 2021-01-26 10:39 | 2021-12-30 | 2021-01-01 | 2022-03-05
75086 | G7MREG118 | MX2217622 | MX2217622 - STATION 873 - 5TH & PHILADELPHIA | 609.67 |  | 609.67 |  |  | 26052.09 | 87907.04 | -61854.95 | 2017-09-22 14:01 | 2025-11-30 | 2017-10-01
75086 | G7MRUPG | AW1568 | AW1568 - (CANCEL) STATION 338 MR UPGRADE | -68188.66 |  | -68188.66 |  |  | 0 | 190631 | -190631 | 2019-12-18 15:27 | 2022-03-30 | 2020-02-01
75086 | G7MRUPG | AW1569 | AW1569 - (CANCEL) STATION286 RILEY RD MR UPG | -45326.33 |  | -45326.33 |  |  | 0 | 190631 | -190631 | 2019-12-18 15:32 | 2022-03-30 | 2020-02-01
75086 | G7MSCPRD | G1322 | G1322 - REPLACE AIR DRYER ERLANGER | -741.3 |  | -741.3 |  |  | -741.3 | 32187 | -32928.3 | 2010-10-13 | 2012-06-30 | 2010-12-01 | 2011-05-11
75086 | G7PHMSA | V7283 | V7283 - PHMSA CRM PLAN | 144756.82 |  | 144756.82 |  |  | 1988908.75 | 416794 | 1572114.75 | 2018-11-14 14:31 | 2020-09-30 | 2018-12-01 | 2021-03-30
75086 | G7PRESIM | E7028 | E7028 - COVINGTON AVE MAIN RPLC | -2414.63 |  | -2414.63 |  |  | -2414.63 | 43788 | -46202.63 | 2009-06-11 | 2014-06-11 | 2009-06-01 | 2010-01-09
75086 | G7PRESIM | G6396 | G6396 - TURKEYFOOT RD @ AUTUMN | -2314.16 |  | -2314.16 |  |  | -2314.16 | 206055.49 | -208369.65 | 2012-01-04 | 2013-01-03 | 2012-04-01 | 2012-09-29
75086 | G7PRESIM | MX9177637 | MX9177637 - INSTALL PRESSURE IMPROVEMENT PROJEC | -2376.82 |  | -2376.82 |  |  | -2376.82 | 0 | -2376.82 | 2018-09-24 14:02 | 2018-11-16 | 2018-12-01 | 2019-04-03
75086 | G7PUBIMP | 30581 | 30581 - CANCEL- US 25 @ DRY RIDGE/GJH | -6906.26 |  | -6906.26 |  |  | -6906.26 | 0 | -6906.26 | 2000-04-13 | 2003-12-31 | 1997-07-01 | 1997-08-31
75086 | G7PUBIMP | A5943 | A5943 - WATER WORKS RD BRIDGE/WJR | -6511.34 |  | -6511.34 |  |  | -6511.34 | 0 | -6511.34 | 2001-05-30 | 2050-12-31 | 2001-06-01 | 2009-05-04
75086 | G7PUBIMP | B1252 | B1252 - CANCEL- BULLITSVILLE RD CONN/CWA | -6945.58 |  | -6945.58 |  |  | -6945.58 | 0 | -6945.58 | 2002-06-28 | 2050-12-31 | 2002-07-01
75086 | G7PUBIMP | B2088 | B2088 - 00-7015-1/CWA | -11198.5 |  | -11198.5 |  |  | -11198.5 | 0 | -11198.5 | 2002-09-20 | 2050-12-31 | 2005-08-01 | 2009-01-09
75086 | G7PUBIMP | B2469 | B2469 - WILLIAMSTWN SERV ABAN/CWA | -2430.53 |  | -2430.53 |  |  | -2430.53 | 0 | -2430.53 | 2002-10-13 | 2050-12-31 | 2002-11-01 | 2002-11-11
75086 | G7PUBIMP | D2337 | D2337 - PP495735/LAURA MATE | -7911.24 |  | -7911.24 |  |  | -7911.24 | 0 | -7911.24 | 2007-12-12 | 2009-12-31 | 2009-02-01 | 2009-10-23
75086 | G7PUBIMP | E6024 | E6024 - SPILLMAN DR | -2139.81 |  | -2139.81 |  |  | -2139.81 | 128455 | -130594.81 | 2009-04-29 | 2014-04-28 | 2009-05-01 | 2009-09-01
75086 | G7PUBIMP | G0795 | G0795 - EDGECLIFF RD | -1205.51 |  | -1205.51 |  |  | -1205.51 | 40331 | -41536.51 | 2010-08-26 | 2011-08-01 | 2010-09-01 | 2011-04-11
75086 | G7PUBIMP | G0796 | G0796 - HAY & WILLOW STS | -814.92 |  | -814.92 |  |  | -814.92 | 15203 | -16017.92 | 2010-08-26 | 2011-03-31 | 2010-09-01 | 2010-12-13
75086 | G7PUBIMP | G0965 | G0965 - JOHNS HILL RD | -2038.93 |  | -2038.93 |  |  | -2038.93 | 173187 | -175225.93 | 2010-09-13 | 2013-04-01 | 2011-09-01 | 2012-09-13
75086 | G7PUBIMP | MX0073622 | MX0073622 - CANCEL - NEWPORT CLIFTON STI | 38.15 |  | 38.15 |  |  | 38.15 | 0 | 38.15 | 2021-03-04 10:02 | 2021-07-20 | 2021-05-01
75086 | G7PUBIMP | MX0129552 | MX0129552 - CHAPMAN LN. - ROAD RECONSTRUCTION - | 16295.34 |  | 16295.34 |  |  | 16295.34 | 73592.68 | -57297.34 | 2021-03-30 10:09 | 2025-02-17 | 2021-04-01 | 2022-06-29
75086 | G7PUBIMP | MX0503657 | MX0503657 - JOYCE AVE STI-NEWPORT KY - 300' OF | 129066.01 |  | 129066.01 |  |  | 129066.01 | 50388.91 | 78677.1 | 2021-06-22 18:02 | 2024-11-19 | 2021-06-01 | 2022-01-27
75086 | G7PUBIMP | MX0783884 | MX0783884 - PLEASANT VALLEY ROAD/CAMP ERNST ROA | 23710.27 |  | 23710.27 |  |  | 1978819.4 | 1689689.28 | 289130.12 | 2018-04-26 10:01 | 2018-08-25 | 2018-05-01 | 2019-01-22
75086 | G7PUBIMP | MX0790794 | MX0790794 - ARLINGTON RD. ROADWAY IMP | -22613.42 |  | -22613.42 |  |  | 330546.79 | 227712 | 102834.79 | 2018-01-23 20:20 | 2018-03-30 | 2018-03-01 | 2018-09-26
75086 | G7PUBIMP | MX1376296 | MX1376296 - LONGBRANCH RD. | -9894.69 |  | -9894.69 |  |  | 360131.06 | 70969.1 | 289161.96 | 2019-08-02 14:01 | 2020-03-05 | 2019-09-01 | 2020-09-15
75086 | G7PUBIMP | MX1682120 | MX1682120 - CANCEL-*TEST HOLES* MADISON ST | 2948.97 |  | 2948.97 |  |  | 2948.97 | 0 | 2948.97 | 2021-08-18 14:03 | 2024-12-18 | 2021-09-01
75086 | G7PUBIMP | MX2442598 | MX2442598 - BROMLEY-CR. SPRINGS RD (KY 2373) | 96954.66 |  | 96954.66 |  |  | 96954.66 | 90736.42 | 6218.24 | 2021-08-02 14:02 | 2022-02-06 | 2021-08-01 | 2022-01-31
75086 | G7PUBIMP | MX2624631 | MX2624631 - EWING BLVDI STREET IMPROVEMENT PROJ | -290.47 |  | -290.47 |  |  | 25438.16 | 101493.8 | -76055.64 | 2019-10-01 18:01 | 2020-02-27 | 2019-10-01 | 2020-04-09
75086 | G7PUBIMP | MX2698762 | MX2698762 - DOH PENDELTON/CAMPBELL INSTALL STRE | 1760.85 |  | 1760.85 |  |  | 311171.24 | 99383.99 | 211787.25 | 2019-09-20 14:01 | 2020-04-03 | 2019-12-01 | 2020-07-09
75086 | G7PUBIMP | MX2778391 | MX2778391 - STI JAQUELINE DR ERLANGER 80' 4" ST | 11835.29 |  | 11835.29 |  |  | 11835.29 | 20092.61 | -8257.32 | 2021-10-26 18:02 | 2022-05-22 | 2021-11-01 | 2022-03-06
75086 | G7PUBIMP | MX2781786 | MX2781786 - CANCEL_KYTC 19-9001 I-275 GRAVES RD | 91398.99 |  | 91398.99 |  |  | 91398.99 | 70082.56 | 21316.43 | 2020-12-09 10:02 | 2023-11-22 | 2021-06-01
75086 | G7PUBIMP | MX2911494 | MX2911494 - UL 35 STREET IMPROVEMENT PROJECT | -82.92 |  | -82.92 |  |  | 28756.85 | 51296.38 | -22539.53 | 2019-08-02 14:01 | 2020-01-09 | 2019-09-01 | 2020-09-15
75086 | G7PUBIMP | MX3298765 | MX3298765 - RIDGE RD. & WEST ORCHARD FT MITCHEL | -7182.05 |  | -7182.05 |  |  | 50033.86 | 94800 | -44766.14 | 2020-07-28 10:01 | 2020-10-16 | 2020-07-01 | 2021-01-11
75086 | G7PUBIMP | MX3359474 | MX3359474 - KYTC - RICHWOOD RD STI - BEAVERLICK | 28498.51 |  | 28498.51 |  |  | 28498.51 | 24088.21 | 4410.3 | 2021-12-13 14:02 | 2024-12-31 | 2021-12-01 | 2022-06-22
75086 | G7PUBIMP | MX6477976 | MX6477976 - CAMP ERNST STREET IMPROVEMENT PROJE | -17776.22 |  | -17776.22 |  |  | 162152.03 | 99251 | 62901.03 | 2020-04-29 14:01 | 2020-06-26 | 2020-05-01 | 2021-01-11
75086 | G7PUBIMP | MX6628393 | MX6628393 - PLEASANT VALLEY 2020 RELOCATION | -68737.06 |  | -68737.06 |  |  | 389692.71 | 399033 | -9340.29 | 2020-05-18 10:01 | 2020-10-29 | 2020-06-01 | 2020-11-17
75086 | G7PUBIMP | MX7035169 | MX7035169 - BUTTERMILK PIKE STREET IMPROVEMENT | -8221.61 |  | -8221.61 |  |  | 90684.14 | 74108 | 16576.14 | 2020-07-08 18:01 | 2020-11-26 | 2020-07-01 | 2020-12-07
75086 | G7PUBIMP | MX7507727 | MX7507727 - MXCONV-BROOKWOOD DR STI-EDGEWOOD, K | -21357.28 |  | -21357.28 |  |  | 217286.03 | 238847.13 | -21561.1 | 2018-04-06 18:03 | 2018-08-24 | 2018-04-01 | 2018-10-26
75086 | G7PUBIMP | MX7599942 | MX7599942 - INSTALL STREET IMPROVEMENT PROJECT | -1611 |  | -1611 |  |  | 165056.57 | 99125.15 | 65931.42 | 2019-08-02 10:01 | 2020-02-27 | 2019-08-01 | 2020-02-29
75086 | G7PUBIMP | MX7625297 | MX7625297 - STREET IMPROVEMENT PROJECT KY-338 J | 30941.18 |  | 30941.18 |  |  | 30941.18 | 45950.78 | -15009.6 | 2018-04-04 14:01 | 2018-08-24 | 2018-04-01 | 2018-09-05
75086 | G7PUBIMP | MX7832792 | MX7832792 - BROOKWOOD DR. SOUTH - EDGEWOOD - 4" | 108439.15 |  | 108439.15 |  |  | 108439.15 | 75946.23 | 32492.92 | 2020-09-09 10:01 | 2021-05-21 | 2021-03-01 | 2021-09-07
75086 | G7PUBIMP | MX8175168 | MX8175168 - CANCEL BUTTERMILK PIKE STR IMPROV | -6858.64 |  | -6858.64 |  |  | -1.19 | 62696 | -62697.19 | 2019-11-19 14:01 | 2021-03-31 | 2019-11-01
75086 | G7PUBIMP | MX8662697 | MX8662697 - CANCEL-PLEAST VALY PT 3 INSL STREET | 12.54 |  | 12.54 |  |  | 12.54 | 0 | 12.54 | 2020-11-04 18:02 | 2021-05-02 | 2021-06-01
75086 | G7PUBIMP | MX8760866 | MX8760866 - WKIP ROADWAY IMPROVEMENT JONES RD | -17875.01 |  | -17875.01 |  |  | 351185.42 | 208010.18 | 143175.24 | 2018-06-14 14:01 | 2018-10-12 | 2018-06-01 | 2019-02-03
75086 | G7PUBIMP | MX8840782 | MX8840782 - CANCEL INSTALL STREET IMPROVEMENT | -678.59 |  | -678.59 |  |  | 7.19 | 0 | 7.19 | 2020-02-06 18:01 | 2018-12-07 | 2020-02-01
75086 | G7PUBIMP | MX9244894 | MX9244894 - KYTC - MT.ZION RD KY536 STI | 44221.57 |  | 44221.57 |  |  | 288363.38 | 1026778 | -738414.62 | 2019-11-08 10:01 | 2023-06-30 | 2020-01-01 | 2021-07-27
75086 | G7PUBIMP | MX9853572 | MX9853572 - GRAVES AND NORTHBEND ROUNDABOUT PRO | 236245.38 |  | 236245.38 |  |  | 236245.38 | 109422.27 | 126823.11 | 2021-02-16 18:02 | 2023-12-28 | 2021-02-01 | 2022-02-14
75086 | G7PUBIMP | MX9948553 | MX9948553 - WILBERS LN - FORT THOMAS - 2" PE - | 99979.6 |  | 99979.6 |  |  | 99979.6 | 75860.65 | 24118.95 | 2021-07-13 18:02 | 2024-12-16 | 2021-07-01 | 2023-02-21
75086 | G7PUBIMP | S8867 | S8867 - STI 10873483 MT ZION RD | 1172544.89 |  | 1172544.89 |  |  | 2404983.91 | 447690.24 | 1957293.67 | 2016-07-26 13:07 | 2020-01-30 | 2017-01-01 | 2019-12-21
75086 | G7PUINEW | INSREGREL | INSREGREL - INSTALL OR REMOVE REGULATOR/RELIEF | 155369.03 |  | 155369.03 |  |  | 1386011.51 | 800000 | 586011.51 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | MX8375093 | MX8375093 - M&R; 3087 TERMINAL DR; CVG AIRPORT | 51256.23 |  | 51256.23 |  |  | 51256.23 | 51696.38 | -440.15 | 2021-05-04 18:02 | 2021-08-24 | 2021-06-01 | 2022-06-27
75086 | G7PUINEW | SETMETER | SETMETER - SET OR REMOVE METER | 2145871.93 |  | 2145871.93 |  |  | 9847151.61 | 2250000 | 7597151.61 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | T2904 | T2904 - CANCEL-MTR 11540114 1 CARBON WAY | -2055.94 |  | -2055.94 |  |  | -2055.94 | 29846.02 | -31901.96 | 2017-03-08 13:44 | 2018-12-31 | 2017-12-01
75086 | G7PUINMR | AGECHGLG | AGECHGLG - KENTUCKY AGE CHANGE LARGE METER | 71871.69 |  | 71871.69 |  |  | 603960.47 | 350000 | 253960.47 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | AGECHGSM - KENTUCKY AGE CHANGE SMALL METER | 1328828.58 |  | 1328828.58 |  |  | 6871446.18 | 14500000 | -7628553.82 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRLG | CHGMTRLG - CHANGE LARGE METER KENTUCKY | 66.94 |  | 66.94 |  |  | 165026.16 | 725000 | -559973.84 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | CHGMTRSM - CHANGE SMALL METER KENTUCKY | 347212.74 |  | 347212.74 |  |  | 2953061.64 | 1250000 | 1703061.64 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | CHGREGREL - CHANGE REGULATOR/RELIEF KENTUCKY | 12590.49 |  | 12590.49 |  |  | 168023.46 | 800000 | -631976.54 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7REG0026 | MX7281967 | MX7281967 - REG 0026 UPHIL AND HIGHWAY - REG SW | -52.8 |  | -52.8 |  |  | 8753.19 | 48953.52 | -40200.33 | 2020-07-07 10:01 | 2021-03-31 | 2020-08-01 | 2021-01-20
75086 | G7REG0031 | MX2737090 | MX2737090 - REG 0031 - NINTH AND YORK - ABANDON | 121.17 |  | 121.17 |  |  | 121.17 | 0 | 121.17 | 2021-11-02 14:02 | 2022-03-15 | 2021-12-01 | 2022-03-29
75086 | G7REG0048 | MX7282035 | MX7282035 - REG 0048 FIFTH AND PHILADELPHIA - R | 8.51 |  | 8.51 |  |  | 12803.3 | 48953.52 | -36150.22 | 2020-07-14 10:02 | 2021-03-31 | 2020-08-01 | 2020-10-28
75086 | G7REG0057 | MX7281845 | MX7281845 - CANCEL -REG 0057 SARATOGA 11TH - OR | -27.56 |  | -27.56 |  |  | 2640.03 | 44953.52 | -42313.49 | 2020-07-07 10:01 | 2021-03-31 | 2020-07-01
75086 | G7REG0089 | AW3224 | AW3224 - REG 0427 EMPIRE DR | 287988.06 |  | 287988.06 |  |  | 287988.06 | 732000 | -444011.94 | 2020-12-30 15:41 | 2025-10-30 | 2021-07-01
75086 | G7REG0089 | AW3246 | AW3246 - REG 0427 EMPIRE DR LAND | 48524.61 |  | 48524.61 |  |  | 48524.61 | 82500 | -33975.39 | 2021-01-02 13:48 | 2026-03-31 | 2021-04-01
75086 | G7REG010 | AW3280 | AW3280 - REG 0010 STEVENSON AND LEXINGTON RE | 27568.53 |  | 27568.53 |  |  | 27568.53 | 58000 | -30431.47 | 2021-01-06 11:52 | 2022-03-31 | 2021-06-01 | 2021-11-02
75086 | G7REG013 | AW3273 | AW3273 - REG 0013 SIXTEENTH AND HOLMAN REPAI | 22175.63 |  | 22175.63 |  |  | 22175.63 | 39300 | -17124.37 | 2021-01-06 08:46 | 2022-03-31 | 2021-07-01 | 2021-11-24
75086 | G7REG017 | AW3195 | AW3195 - REG 0017 FOOTE AND FAIRFIELD REPAIR | 23265.92 |  | 23265.92 |  |  | 23265.92 | 429700 | -406434.08 | 2020-12-29 08:23 | 2023-03-31 | 2021-09-01 | 2021-12-17
75086 | G7REG021 | AW3278 | AW3278 - REG 0021 GRAND AND S FT THOMAS REPA | 13851.88 |  | 13851.88 |  |  | 13851.88 | 56400 | -42548.12 | 2021-01-06 10:47 | 2022-03-31 | 2021-07-01 | 2021-10-23
75086 | G7REG026 | AW3184 | AW3184 - REG 0437 UPHILL & HIGHWAY | 8595.63 |  | 8595.63 |  |  | 8595.63 | 507300 | -498704.37 | 2020-12-28 11:30 | 2023-03-31 | 2021-12-01 | 2023-02-08
75086 | G7REG045 | AW3228 | AW3228 - REG 0432 TENTH & BRIGHTON | 5651.93 |  | 5651.93 |  |  | 5651.93 | 660800 | -655148.07 | 2020-12-30 16:28 | 2021-03-31 | 2021-11-01 | 2023-07-11
75086 | G7REG045 | AW3356 | AW3356 - CANCEL- REG0432 TENTH-BRIGHTON LAND | 16.62 |  | 16.62 |  |  | 16.62 | 82500 | -82483.38 | 2021-01-13 10:52 | 2023-03-31 | 2021-09-01
75086 | G7REG049 | AW3290 | AW3290 - REG 0049 PEARL AND TWENTIETH REPAIR | 25122.07 |  | 25122.07 |  |  | 25122.07 | 58000 | -32877.93 | 2021-01-06 14:56 | 2022-03-31 | 2021-06-01 | 2021-10-24
75086 | G7REG051 | AW3919 | AW3919 - REG 0051 WALNUT AND ELECTRIC REPAIR | 31047.97 |  | 31047.97 |  |  | 31047.97 | 175200 | -144152.03 | 2021-05-25 08:51 | 2022-03-31 | 2021-08-01 | 2021-11-23
75086 | G7REG053 | MX9751457 | MX9751457 - REG 0053 - OVERTON AND NINTH - REG | 63003.22 |  | 63003.22 |  |  | 63003.22 | 43953.52 | 19049.7 | 2021-02-08 18:02 | 2022-03-31 | 2021-06-01 | 2021-10-28
75086 | G7REG055 | AW3288 | AW3288 - REG 0055 WRIGHT AND SPRING REPAIR | 12938.06 |  | 12938.06 |  |  | 12938.06 | 56400 | -43461.94 | 2021-01-06 14:20 | 2022-03-31 | 2021-07-01 | 2021-10-23
75086 | G7REG057 | AW3180 | AW3180 - REG 0431 SARATOGA & ELEVENTH | 8665.36 |  | 8665.36 |  |  | 8665.36 | 796400 | -787734.64 | 2020-12-28 10:43 | 2023-03-31 | 2021-11-01 | 2023-11-08
75086 | G7REG057 | AW3354 | AW3354 - CANCEL-REG431 SARATOGA-ELEVENTH ROW | 10.94 |  | 10.94 |  |  | 10.94 | 82500 | -82489.06 | 2021-01-13 10:19 | 2023-03-31 | 2021-06-01
75086 | G7REG059 | AW3177 | AW3177 - REG 0059 HIGHLAND AND GRAND RS REPL | 251346.81 |  | 251346.81 |  |  | 251346.81 | 746000 | -494653.19 | 2020-12-28 10:15 | 2022-09-30 | 2021-06-01 | 2023-02-09
75086 | G7REG059 | AW3353 | AW3353 - REG 0059 HIGHLAND AND GRAND LAND | 6870.48 |  | 6870.48 |  |  | 6870.48 | 82500 | -75629.52 | 2021-01-13 10:02 | 2022-09-30 | 2021-04-01 | 2023-02-09
75086 | G7REG069 | AW3287 | AW3287 - REG 0069 JEFFERSON AND HAWTHORNE RE | 22091.16 |  | 22091.16 |  |  | 22091.16 | 56400 | -34308.84 | 2021-01-06 14:06 | 2022-03-31 | 2021-07-01 | 2021-11-14
75086 | G7REG073 | AW3286 | AW3286 - REG 0073 GRAVES AND HULBERT REPAIR | 43814.21 |  | 43814.21 |  |  | 43814.21 | 58000 | -14185.79 | 2021-01-06 13:49 | 2022-03-31 | 2021-06-01 | 2021-11-28
75086 | G7REG093 | AW3284 | AW3284 - REG 0093 ALEXANDRIA AND BLOSSUM REP | 35301.61 |  | 35301.61 |  |  | 35301.61 | 61000 | -25698.39 | 2021-01-06 13:22 | 2022-03-31 | 2021-07-01 | 2021-11-20
75086 | G7REG095 | AW3283 | AW3283 - REG 0095 BAUM AND BURNET | 36592.68 |  | 36592.68 |  |  | 36592.68 | 402900 | -366307.32 | 2021-01-06 13:08 | 2022-03-31 | 2021-08-01 | 2021-11-20
75086 | G7REG097 | AW3282 | AW3282 - REG 0097 HOME AND MAIN REPAIR | 38578.25 |  | 38578.25 |  |  | 38578.25 | 73500 | -34921.75 | 2021-01-06 12:55 | 2022-03-31 | 2021-07-01 | 2022-01-13
75086 | G7REG684 | MX9167642 | MX9167642 - (CANCEL) REG0684-SHAW BLVD-REG UPG | 46.06 |  | 46.06 |  |  | 46.06 | 51953.52 | -51907.46 | 2021-01-08 14:01 | 2021-04-29 | 2021-02-01
75086 | G7REG713 | MX9168019 | MX9168019 - REG 0713 - STATE RT 9 - REG UPGRADE | 6278.24 |  | 6278.24 |  |  | 6278.24 | 43953.52 | -37675.28 | 2020-12-17 18:02 | 2021-04-29 | 2021-02-01 | 2021-05-12
75086 | G7REG74K | AW3285 | AW3285 - REG 0074 MCALPIN N OF HOPE LN REPAI | 40503.97 |  | 40503.97 |  |  | 40503.97 | 54100 | -13596.03 | 2021-01-06 13:36 | 2022-03-31 | 2021-07-01 | 2021-12-24
75086 | G7REPL | 28051 | 28051 - SMALL REPL KY | 140084.12 |  | 140084.12 |  |  | 1329227.88 | 0 | 1329227.88 | 2000-04-13 | 2050-12-31 | 1999-12-01
75086 | G7REPL | C6990 | C6990 - CANCEL 2 R/W FOR STA 761/CWA | -10613.11 |  | -10613.11 |  |  | -10613.11 | 0 | -10613.11 | 2006-06-16 | 2011-12-31 | 2006-06-01 | 2007-09-18
75086 | G7REPL | E4280 | E4280 - CANCEL 2 DRY CREEK LP03 R/W | -11.86 |  | -11.86 |  |  | -11.86 | 9510 | -9521.86 | 2009-02-11 | 2014-02-11 | 2009-05-01 | 2009-09-10
75086 | G7REPL | G2962 | G2962 - CANCEL-MOORE ST | -200.54 |  | -200.54 |  |  | -200.54 | 21531 | -21731.54 | 2011-04-08 | 2011-10-15 | 2011-11-01 | 2010-11-03
75086 | G7REPL | MX0181170 | MX0181170 - CENTRAL AVE NEWPORT- REPLACEMENT PR | -595.33 |  | -595.33 |  |  | 21501.48 | 64213.24 | -42711.76 | 2018-12-12 18:01 | 2019-11-21 | 2018-12-01 | 2019-11-27
75086 | G7REPL | MX1233047 | MX1233047 - KY-9 FLOOD GATE-RPL | -32724.03 |  | -32724.03 |  |  | 162972.16 | 92509 | 70463.16 | 2019-10-23 18:01 | 2020-07-10 | 2019-10-01 | 2020-12-14
75086 | G7REPL | MX1379992 | MX1379992 - WEST 13TH ST RPL PROJECT, NEWPORT, | 13823.68 |  | 13823.68 |  |  | 13823.68 | 44018.51 | -30194.83 | 2021-09-13 10:02 | 2024-04-15 | 2021-09-01 | 2022-09-28
75086 | G7REPL | MX2163251 | MX2163251 - CANCEL HIGHLAND AVE WOODLAND PL | 7127.88 |  | 7127.88 |  |  | 7127.88 | 24723.49 | -17595.61 | 2021-09-30 14:01 | 2022-05-12 | 2021-10-01
75086 | G7REPL | MX6840192 | MX6840192 - CANCEL BEAVER RD INSTALL REPLACE | -98.61 |  | -98.61 |  |  | 0 | 48085 | -48085 | 2020-08-13 18:01 | 2020-11-20 | 2020-08-01
75086 | G7REPL | MX8171793 | MX8171793 - 2 INSTALL REPLACE | 272.73 |  | 272.73 |  |  | 272.73 | 84327.5 | -84054.77 | 2018-08-03 18:04 | 2018-09-28 | 2018-08-01 | 2019-01-16
75086 | G7REPL | MX9545566 | MX9545566 - RICHWOOD RD REPLACEMENT PROJ KY-338 | 575955.5 |  | 575955.5 |  |  | 841043.05 | 1413710 | -572666.95 | 2019-11-12 10:01 | 2022-06-14 | 2020-01-01 | 2022-03-01
75086 | G7REPL | MX9817206 | MX9817206 - DUVENECK SQUARE RPL/MAE - COVINGTON | 383111.75 |  | 383111.75 |  |  | 383111.75 | 101691.72 | 281420.03 | 2021-04-08 10:02 | 2024-10-01 | 2021-05-01 | 2021-12-14
75086 | G7REPL | T1130 | T1130 - RPL 11859007 BALLYSHANNON - RELOCAT | -593.15 |  | -593.15 |  |  | 0 | 37387.77 | -37387.77 | 2016-12-20 11:51 | 2017-07-01 | 2016-12-01 | 2017-06-11
75086 | G7REPL | T2230 | T2230 - RPL 20745900 HUDSON AVE | 1375.38 |  | 1375.38 |  |  | 1375.38 | 105241.34 | -103865.96 | 2017-02-16 14:11 | 2018-03-31 | 2017-02-01 | 2017-09-28
75086 | G7REPL | T9340 | T9340 - CANCEL RPL WATERWORKS RD. INLET | -2647.53 |  | -2647.53 |  |  | -2647.53 | 28102.56 | -30750.09 | 2017-07-14 10:10 | 2018-09-01 | 2018-04-01
75086 | G7REPL | T9341 | T9341 - CANCEL RPL WATERWORKS RD. OUTLET | -2935.98 |  | -2935.98 |  |  | -2935.98 | 28102.56 | -31038.54 | 2017-07-14 10:19 | 2018-09-01 | 2018-04-01
75086 | G7RGPI | MX9217475 | MX9217475 - GARVEY AVE. PRI, ELSMERE, 9400' 8" | 748257.27 |  | 748257.27 |  |  | 748257.27 | 507691.08 | 240566.19 | 2021-08-16 18:02 | 2022-12-01 | 2021-09-01 | 2022-11-21
75086 | G7S3300 | V7041 | V7041 - LINE UL02 SEG 3300 PLEASANT VALLEY | 60725.34 |  | 60725.34 |  |  | 12759.39 | 2643704 | -2630944.61 | 2018-11-06 14:02 | 2020-07-30 | 2019-01-01 | 2020-01-15
75086 | G7SECCON | V5175 | V5175 - ERLANGER PROPANE SECURITY UPGRADE | -147469.52 |  | -147469.52 |  |  | 2801920.96 | 950000 | 1851920.96 | 2018-08-21 17:03 | 2020-05-14 | 2019-02-01 | 2020-03-31
75086 | G7SERVMC | 28763 | 28763 - CANCEL 2 LAKEVIEW DR/DMG | -366.22 |  | -366.22 |  |  | -366.22 | 0 | -366.22 | 2000-04-13 | 2050-12-31 | 1996-06-01 | 1996-06-11
75086 | G7SERVMC | 30144 | 30144 - CANCEL-OAKMONT 821/DMG | -67.13 |  | -67.13 |  |  | -67.13 | 0 | -67.13 | 2000-04-13 | 2050-12-31 | 1996-11-01 | 1996-11-05
75086 | G7SERVMC | 34524 | 34524 - 00-3054-4/KGA | -76.53 |  | -76.53 |  |  | -76.53 | 0 | -76.53 | 2000-04-13 | 2005-12-31 | 2000-10-01 | 2000-10-18
75086 | G7SERVMC | A2242 | A2242 - 0000265/11 SHELBY/RENEW M-C | -813.8 |  | -813.8 |  |  | -631.83 | 0 | -631.83 | 2000-07-21 | 2050-12-31 | 2000-07-01 | 2002-12-18
75086 | G7SERVMC | A2577 | A2577 - 0000299/7114 PRICE PK | -309.04 |  | -309.04 |  |  | -87.61 | 0 | -87.61 | 2000-08-20 | 2050-12-31 | 2000-08-01 | 2002-12-18
75086 | G7SERVMC | C9839 | C9839 - CANCEL 2 PP896043/CWA | -99.41 |  | -99.41 |  |  | -99.41 | 0 | -99.41 | 2007-05-17 | 2050-12-31 | 2007-05-01 | 2007-09-22
75086 | G7SERVMC | CMRP70 | CMRP70 - REPLACE C-M PLASTIC 2 INCH AND UNDE | 212023.47 |  | 212023.47 |  |  | 12647251.69 | 0 | 12647251.69 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | CMRS70 - 2" OR LESS STEEL C-M REPLACE | 10359.11 |  | 10359.11 |  |  | 10359.11 | 1000000 | -989640.89 | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVMC | LCMRP70 | LCMRP70 - GREATER THAN 2" C-M REPL PLASTIC | 17763.19 |  | 17763.19 |  |  | 41139.02 | 2500000 | -2458860.98 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | LMCRP70 - GREATER THAN 2" M-C REPL PLASTIC | 56771.07 |  | 56771.07 |  |  | 312192.42 | 2500000 | -2187807.58 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | LMCRS70 - GREATER THAN 2" M-C REPL STEEL | 10041.26 |  | 10041.26 |  |  | 10041.26 | 1000000 | -989958.74 | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | G7SERVMC | MCRP70 | MCRP70 - REPLACE (NON-AMRP) M-C PLASTIC 2 IN | 2521083.23 |  | 2521083.23 |  |  | 19364065.81 | 0 | 19364065.81 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | MCRS70 - REPLACE M-C STEEL 2 INCH AND UNDER | 20239.57 |  | 20239.57 |  |  | 550769.97 | 0 | 550769.97 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | CMNEWP70 | CMNEWP70 - NEW C-M PLASTIC 2 INCH AND UNDER KY | 256154.57 |  | 256154.57 |  |  | 7924556.65 | 1 | 7924555.65 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | LMCNEWP70 | LMCNEWP70 - GREATER THAN 2" M-C PLASTIC | 33159.41 |  | 33159.41 |  |  | 480511.09 | 2500000 | -2019488.91 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | LMCNEWS70 - GREATER THAN 2" M-C STEEL | 7010.39 |  | 7010.39 |  |  | 109216.44 | 2500000 | -2390783.56 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVNEW | MCNEWP70 | MCNEWP70 - NEW M-C PLASTIC 2 INCH AND UNDER KY | 2652516.81 |  | 2652516.81 |  |  | 17829078.75 | 1 | 17829077.75 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | MCNEWS70 - NEW M-C STEEL 2 INCH AND UNDER KY | 14364.07 |  | 14364.07 |  |  | 249903.46 | 1 | 249902.46 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7STA001 | AW3315 | AW3315 - STA 0001 ALEXANDRIA AM4 REPAIR | 32629.89 |  | 32629.89 |  |  | 32629.89 | 39700 | -7070.11 | 2021-01-07 12:39 | 2023-03-31 | 2021-07-01 | 2021-12-29
75086 | G7STA011 | AW3227 | AW3227 - STA 0949 DAYTON VALVE HOUSE | 33512.85 |  | 33512.85 |  |  | 33512.85 | 1062400 | -1028887.15 | 2020-12-30 16:17 | 2025-10-30 | 2021-11-01
75086 | G7STA011 | AW3250 | AW3250 - STA 0949 DAYTON VALVE HOUSE LAND | 19.4 |  | 19.4 |  |  | 19.4 | 82500 | -82480.6 | 2021-01-02 14:55 | 2025-11-29 | 2021-06-01
75086 | G7STA014 | AW3251 | AW3251 - CANCEL_STA 0014 EAST ALEXANDRIAPIKE | 6.86 |  | 6.86 |  |  | 6.86 | 82500 | -82493.14 | 2021-01-03 09:43 | 2023-03-31 | 2021-06-01
75086 | G7STA034 | AW3313 | AW3313 - STA 0034 WILDERS PLANT REPAIR | 41319.66 |  | 41319.66 |  |  | 41319.66 | 76500 | -35180.34 | 2021-01-07 12:19 | 2022-03-31 | 2021-07-01 | 2021-11-02
75086 | G7STA0375 | AW3193 | AW3193 - STA 0375 ELECTRIC AVE RS REPLACEMEN | 1380350.26 |  | 1380350.26 |  |  | 1380350.26 | 829000 | 551350.26 | 2020-12-28 13:59 | 2022-04-22 | 2021-05-01 | 2022-05-09
75086 | G7STA0375 | AW3691 | AW3691 - STA 00375 LAND ELECTRIC | 233918.37 |  | 233918.37 |  |  | 233918.37 | 82500 | 151418.37 | 2021-02-27 09:31 | 2022-02-28 | 2021-04-01 | 2021-11-27
75086 | G7STA056 | AW3310 | AW3310 - STA 0056 BURLINGTON PIKE REPAIR | 27319.37 |  | 27319.37 |  |  | 27319.37 | 56400 | -29080.63 | 2021-01-07 11:42 | 2022-03-31 | 2021-08-01 | 2021-11-23
75086 | G7STA064 | AW3217 | AW3217 - STA 0940 GLECOE TB | 19317.47 |  | 19317.47 |  |  | 19317.47 | 510900 | -491582.53 | 2020-12-30 13:22 | 2021-03-31 | 2021-11-01 | 2023-09-27
75086 | G7STA064 | AW3268 | AW3268 - STA 0940 STA GLENCOE TB LAND | 18.14 |  | 18.14 |  |  | 18.14 | 82500 | -82481.86 | 2021-01-05 14:36 | 2023-03-31 | 2021-08-01 | 2023-09-27
75086 | G7STA072 | AW3308 | AW3308 - STA 0072 TENTH AND BRIGHTON REPAIR | 21787.32 |  | 21787.32 |  |  | 21787.32 | 58000 | -36212.68 | 2021-01-07 11:18 | 2022-03-31 | 2021-06-01 | 2021-10-22
75086 | G7STA074 | AW3307 | AW3307 - STA 0074 LOUIS B NUNN REPAIR | 32323.38 |  | 32323.38 |  |  | 32323.38 | 59300 | -26976.62 | 2021-01-07 11:09 | 2022-03-31 | 2021-06-01 | 2021-11-21
75086 | G7STA0836 | AW3191 | AW3191 - STA 0838 ROSSFORD AVE RS REPLACEMEN | 1367466.43 |  | 1367466.43 |  |  | 1367466.43 | 539500 | 827966.43 | 2020-12-28 13:11 | 2022-04-30 | 2021-05-01 | 2022-05-22
75086 | G7STA0836 | AW3686 | AW3686 - STA 0836 - LAND ROSSFORD AVE | 54181.21 |  | 54181.21 |  |  | 54181.21 | 82500 | -28318.79 | 2021-02-26 22:00 | 2022-02-28 | 2021-04-01 | 2021-11-27
75086 | G7STA100 | AW3306 | AW3306 - STA 0100 CHESAPEAKE AND KYLE REPAIR | 32927.64 |  | 32927.64 |  |  | 32927.64 | 106700 | -73772.36 | 2021-01-07 10:58 | 2022-03-31 | 2021-08-01 | 2022-01-13
75086 | G7STA117 | AW3305 | AW3305 - STA 0117 AMSTERDAM AND REDWOOD REPA | 23605.73 |  | 23605.73 |  |  | 23605.73 | 56400 | -32794.27 | 2021-01-07 10:45 | 2022-03-31 | 2021-07-01 | 2021-10-27
75086 | G7STA276 | AW3212 | AW3212 - STA 0276 MARY INGLES HWY RS ABANDON | 25788.55 |  | 25788.55 |  |  | 25788.55 | 553900 | -528111.45 | 2020-12-30 11:32 | 2021-03-31 | 2021-11-01 | 2022-11-18
75086 | G7STA276 | AW3689 | AW3689 - CANCEL-STA 0276 MARY IGLES HWY LAND | 2288.49 |  | 2288.49 |  |  | 2288.49 | 82500 | -80211.51 | 2021-02-26 23:34 | 2023-03-31 | 2021-06-01
75086 | G7STA280 | AW3213 | AW3213 - STA 0938 TAYLOR MILL & LONE OAK | 10337.26 |  | 10337.26 |  |  | 10337.26 | 562000 | -551662.74 | 2020-12-30 11:55 | 2023-09-30 | 2021-11-01 | 2023-09-08
75086 | G7STA280 | AW3272 | AW3272 - STA0938 TAYLOR MILL & LONE OAK LAND | 4629.57 |  | 4629.57 |  |  | 4629.57 | 82500 | -77870.43 | 2021-01-05 15:40 | 2023-03-31 | 2021-08-01 | 2023-09-08
75086 | G7STA286 | AW3216 | AW3216 - STA 0929 RILEY RD | 67591.88 |  | 67591.88 |  |  | 67591.88 | 635200 | -567608.12 | 2020-12-30 13:11 | 2021-03-31 | 2021-09-01 | 2023-06-28
75086 | G7STA286 | AW3271 | AW3271 - STA 0929 RILEY RD LAND | 17.87 |  | 17.87 |  |  | 17.87 | 82500 | -82482.13 | 2021-01-05 15:21 | 2023-03-31 | 2021-06-01 | 2023-06-28
75086 | G7STA338 | AW3192 | AW3192 - STA 0941 GUBSER MILL | 107777.63 |  | 107777.63 |  |  | 107777.63 | 538800 | -431022.37 | 2020-12-28 13:44 | 2025-12-30 | 2021-09-01
75086 | G7STA338 | AW3690 | AW3690 - STA 0941 GUBSER MILL LAND | 3163.39 |  | 3163.39 |  |  | 3163.39 | 82500 | -79336.61 | 2021-02-27 08:54 | 2025-10-25 | 2021-06-01
75086 | G7STA444 | AW3186 | AW3186 - STA 0948 THIRD & CRESCENT | 32074.74 |  | 32074.74 |  |  | 32074.74 | 948400 | -916325.26 | 2020-12-28 11:59 | 2025-11-27 | 2021-11-01
75086 | G7STA444 | AW3230 | AW3230 - STA 0948 THIRD & CRESCENT LAND | 2.29 |  | 2.29 |  |  | 2.29 | 82500 | -82497.71 | 2020-12-31 08:30 | 2025-11-27 | 2021-08-01
75086 | G7STA535 | AW3299 | AW3299 - STA 0535 DRY RIDGE EAST REPAIR | 29748.85 |  | 29748.85 |  |  | 29748.85 | 56400 | -26651.15 | 2021-01-07 09:12 | 2022-08-31 | 2021-06-01 | 2022-12-02
75086 | G7STA750 | AW3296 | AW3296 - STA 0750 TURFWAY STATION REPAIR | 17649.37 |  | 17649.37 |  |  | 17649.37 | 112700 | -95050.63 | 2021-01-07 08:29 | 2022-03-31 | 2021-07-01 | 2021-11-19
75086 | G7STA793 | AW3188 | AW3188 - STA 0942 CAMP ERNST RD | 9538.16 |  | 9538.16 |  |  | 9538.16 | 887300 | -877761.84 | 2020-12-28 12:16 | 2023-09-30 | 2021-11-01 | 2024-01-18
75086 | G7STA793 | AW3767 | AW3767 - STA 0942 CAMP ERNST RD LAND | 1959.06 |  | 1959.06 |  |  | 1959.06 | 82500 | -80540.94 | 2021-03-16 18:53 | 2023-03-31 | 2021-06-01 | 2024-01-18
75086 | G7STA822 | AW3189 | AW3189 - STA 0822 COX RD RS REPAIR | 54513.84 |  | 54513.84 |  |  | 54513.84 | 541600 | -487086.16 | 2020-12-28 12:29 | 2022-12-31 | 2021-11-01 | 2022-11-18
75086 | G7STA822 | AW3685 | AW3685 - CANCEL 0822 - COX RD. RS REP - LAND | 2234.96 |  | 2234.96 |  |  | 2234.96 | 82500 | -80265.04 | 2021-02-26 18:47 | 2022-12-31 | 2021-06-01
75086 | G7STA876 | MX6800938 | MX6800938 - STA 876 WARSAW TOWN BORDER- STATION | 62633.84 |  | 62633.84 |  |  | 146235.72 | 252984 | -106748.28 | 2018-01-10 18:02 | 2022-09-30 | 2018-01-01 | 2023-09-29
75086 | G7TAM00B | AW2146 | AW2146 - LINE AM00B RETROFIT REPL | 1101920.07 |  | 1101920.07 |  |  | 1743652.51 | 6528636 | -4784983.49 | 2020-05-19 16:54 | 2022-10-15 | 2020-05-01 | 2022-09-17
75086 | G7TAM00B | AW3634 | AW3634 - LINE AM00B ILI RETROFIT-LAND | 36480.19 |  | 36480.19 |  |  | 36480.19 | 127500 | -91019.81 | 2021-02-17 09:27 | 2022-10-15 | 2021-10-01 | 2022-09-17
75086 | G7TOOLS | 28073 | 28073 - PURCHASE GAS TOOLS BLANKET | 120816.57 |  | 120816.57 |  |  | 841430.18 | 0 | 841430.18 | 2000-04-13 | 2015-12-31 | 1999-12-01
75086 | G7TOOLS | 8SFYTOOLS | 8SFYTOOLS - KENTUCKY HIGH RISK TOOLS | 11702.53 |  | 11702.53 |  |  | 11702.53 | 100000 | -88297.47 | 2020-10-13 07:30 | 2021-12-30 | 2021-02-01 | 2022-03-31
75086 | G7TOOLS | AW4691 | AW4691 - CGI UPGRADE KENTUCKY | 53130.23 |  | 53130.23 |  |  | 53130.23 | 120000 | -66869.77 | 2021-10-22 07:34 | 2022-06-30 | 2021-12-01
75086 | G7TUL06 | AW1592 | AW1592 - LINE UL06 - PIPELINE REPLACEMENTS | 9110490.94 |  | 9110490.94 |  |  | 9680955.56 | 10253358 | -572402.44 | 2020-01-05 02:41 | 2021-12-30 | 2020-02-01 | 2021-12-03
75086 | G7TUL06 | AW2021 | AW2021 - LINE UL06 - PIPELINE REPLACEMENTS L | 13094.39 |  | 13094.39 |  |  | 101349.67 | 115000 | -13650.33 | 2020-04-13 10:21 | 2021-12-31 | 2020-07-01 | 2021-12-03
75086 | G7UL02PH1 | V8191 | V8191 - UL60 PIPELINE PHASE 1 (PIPE) | 624616.54 |  | 624616.54 |  |  | 38616620.02 | 26326195 | 12290425.02 | 2019-01-23 15:21 | 2021-03-30 | 2019-01-01 | 2021-02-25
75086 | G7UL02PH1 | V8351 | V8351 - UL60 PIPELINE PHASE 1 (STATION) | 64939.22 |  | 64939.22 |  |  | 1794289.46 | 6287827 | -4493537.54 | 2019-02-11 09:25 | 2021-03-30 | 2019-07-01 | 2021-03-13
75086 | G7UL02PH1 | V8352 | V8352 - UL60 PIPELINE P1 - LAND RIGHTS PROJ | 43897.66 |  | 43897.66 |  |  | 4896893.01 | 1941000 | 2955893.01 | 2019-02-11 09:32 | 2021-03-30 | 2019-03-01 | 2021-02-25
75086 | G7UL02PH2 | AW3877 | AW3877 - UL60 PIPELINE PHASE II - STATION | 83744.29 |  | 83744.29 |  |  | 83744.29 | 1004152 | -920407.71 | 2021-04-29 15:15 | 2022-03-30 | 2021-05-01 | 2021-11-18
75086 | G7UL02PH2 | V9444 | V9444 - UL60 PIPELINE PHASE II - PIPE | 23821699.9 |  | 23821699.9 |  |  | 25418974.66 | 22514005 | 2904969.66 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01 | 2021-11-18
75086 | G7UL02PH2 | V9445 | V9445 - UL60 PIPELINE PHASE II- LAND RIGHTS | 793256.92 |  | 793256.92 |  |  | 2506609.14 | 733000 | 1773609.14 | 2019-06-12 08:04 | 2022-02-02 | 2019-07-01 | 2021-11-18
75086 | G7WFD | MX5518434 | MX5518434 - WENDELL FORD DIST. PROJ; | 1109.39 |  | 1109.39 |  |  | 49782.1 | 262528 | -212745.9 | 2020-04-16 18:01 | 2020-10-02 | 2020-05-01 | 2021-02-11
75086 | G7WFD | MX6889178 | MX6889178 - CANCEL WENDELL FORD | -295.34 |  | -295.34 |  |  | 0 | 274232 | -274232 | 2020-05-22 14:01 | 2020-08-21 | 2020-05-01 | 2021-02-16
75086 | G7WOODINT | AW3137 | AW3137 - DUKE WOODSDALE INTERCONNECT (KY) | 208821.51 |  | 208821.51 |  |  | 208821.51 | 2000000 | -1791178.49 | 2020-12-18 12:10 | 2021-12-31 | 2021-01-01 | 2022-01-31
75086 | GITKYCAP | F7146 | F7146 - ITRON FCS KENTUCKY GAS | -421.64 |  | -421.64 |  |  | -421.64 | 3165 | -3586.64 | 2010-04-12 | 2013-05-15 | 2012-01-01 | 2012-02-07
75086 | GITKYCAP | R4959 | R4959 - CANCEL 2 RICK ANALYSIS GAS TRANSMIS | -273.33 |  | -273.33 |  |  | -273.33 | 2431 | -2704.33 | 2015-12-07 16:48 | 2017-01-01 | 2016-04-01 | 2016-12-29
75086 | PEACHTRE | C5396 | C5396 - CANCEL 2 PEACH TREE-R/W/PPW | -10163.32 |  | -10163.32 |  |  | -10163.32 | 0 | -10163.32 | 2006-01-22 | 2011-12-31 | 2006-08-01 | 2007-12-25
75086 | SG000489F | SG489SVR3 | SG489SVR3 - DEE OPENWAY SCALE | 3.76 |  | 3.76 |  |  | 3519.67 | 1190 | 2329.67 | 2019-09-25 08:08 | 2020-10-31 | 2019-09-01 | 2020-10-26
75086 | SG000489F | SG489SVR4 | SG489SVR4 - DEE OPENWAY SCALE | -3.8 |  | -3.8 |  |  | 0 | 442 | -442 | 2020-01-29 21:42 | 2020-10-31 | 2020-03-01
75086 | SG000540F | SG540HW | SG540HW - DEE VEHICLE AREA NETWORK | 7424.55 |  | 7424.55 |  |  | 72215.47 | 117926 | -45710.53 | 2018-04-13 13:13 | 2020-12-17 | 2018-09-01 | 2021-05-15
75086 | SG000540F | SG540SW | SG540SW - DEE VEHICLE AREA NETWORK | -106.98 |  | -106.98 |  |  | 0 | 107801 | -107801 | 2017-04-13 09:30 | 2020-12-17 | 2017-04-01 | 2018-07-16
75086 | SG000723F | SG723SW | SG723SW - DEE AMI OPERATIONS TOOL | 16110.21 |  | 16110.21 |  |  | 28817.57 | 26599 | 2218.57 | 2020-03-03 09:59 | 2022-07-30 | 2020-03-01 | 2022-07-31
75086 | SG000724F | SG724SW | SG724SW - DEE MDM TECHNICAL HEALTH | 3417.47 |  | 3417.47 |  |  | 11926.49 | 15916 | -3989.51 | 2020-08-19 16:46 | 2021-06-24 | 2020-08-01 | 2021-09-30
75086 | SG000781F | SG781SW | SG781SW - SG DEE PPM PIMS PHASE 2 BUILD OUT | -0.05 |  | -0.05 |  |  | 77935.71 | 76873.76 | 1061.95 | 2018-07-12 09:17 | 2021-03-31 | 2018-07-01 | 2022-03-31
75086 | SG000940F | SG940SVR | SG940SVR - DEE EDMS PLATFORM UPGRADE | -61.89 |  | -61.89 |  |  | 11694.89 | 9477 | 2217.89 | 2020-04-24 15:54 | 2020-12-18 | 2020-05-01 | 2021-02-07
75086 | SG001042F | SG1042SW | SG1042SW - DEE OPENWAY LICENSE EXTENSION | -107.44 |  | -107.44 |  |  | 11914.1 | 11784 | 130.1 | 2020-07-28 22:06 | 2020-10-30 | 2020-09-01 | 2020-12-31
75086 | SG001117F | SG001117 | SG001117 - DEE LMR CONSOLES | 92728.97 |  | 92728.97 |  |  | 92728.97 | 124921 | -32192.03 | 2021-08-25 20:43 | 2023-03-31 | 2021-10-01 | 2022-11-30
75086 | SGKAMIF | SG169MTRS | SG169MTRS - SG KY AMI GAS METERS - 169 | 395.23 |  | 395.23 |  |  | 9375749.21 | 9563026 | -187276.79 | 2017-06-07 15:39 | 2019-02-28 | 2017-06-01
75087 | CUSTCONN | 315986A | 315986A - CUSTOMER CONNECT - CORE | 655234.63 |  | 655234.63 |  |  | 3583885.81 | 2325960.3 | 1257925.51 | 2017-08-10 10:55 | 2022-12-05 | 2017-08-01 | 2022-07-06
75087 | CUSTCONN | 315986E | 315986E - CUSTOMER CONNECT- UNIVERSAL BILL | 48.17 |  | 48.17 |  |  | 243832.11 | 117210.08 | 126622.03 | 2017-08-11 10:44 | 2020-09-01 | 2017-08-01 | 2020-09-01
75087 | CUSTCONN | 315986F | 315986F - CUSTOMER CONNECT- R6-8 SCOPE | 272168.37 |  | 272168.37 |  |  | 272168.37 | 53917 | 218251.37 | 2021-03-30 10:49 | 2022-06-30 | 2021-04-01 | 2022-07-06
75087 | CUSTCONN | 315986HW6 | 315986HW6 - CUSTOMER CONNECT- HARDWARE PROJ 4 | 11926.23 |  | 11926.23 |  |  | 70337.26 | 21350 | 48987.26 | 2020-03-12 11:33 | 2021-03-15 | 2020-03-01 | 2021-06-01
75087 | CUSTCONN | 315986HW7 | 315986HW7 - CUSTOMER CONNECT - HARDWARE PROJ 5 | 28428.01 |  | 28428.01 |  |  | 28428.01 | 62454 | -34025.99 | 2021-04-21 14:12 | 2021-12-31 | 2021-04-01 | 2021-12-31
75087 | CUSTCONN | 315986HW8 | 315986HW8 - CUSTOMER CONNECT- HARDWARE PROJ 6 | 19940.69 |  | 19940.69 |  |  | 19940.69 | 67100 | -47159.31 | 2021-09-27 15:20 | 2022-06-30 | 2021-10-01 | 2022-09-15
75087 | FPIT | 307482002 | 307482002 - CUSTOMER MOBILE APP - PHASE 3 | 69.59 |  | 69.59 |  |  | 3105.85 | 26324 | -23218.15 | 2019-12-19 13:54 | 2022-03-15 | 2020-01-01 | 2022-03-31
75087 | FPIT | 307482SW2 | 307482SW2 - CUSTOMER MOBILE APP - PHASE 3 | 16708.5 |  | 16708.5 |  |  | 30241.83 | 30258 | -16.17 | 2020-04-13 09:32 | 2022-03-15 | 2020-04-01 | 2022-03-31
75087 | FPIT | 344598001 | 344598001 - DUKE CUSTOMER IVR REPLACEMENT | 1015.5 |  | 1015.5 |  |  | 152389.72 | 197081 | -44691.28 | 2018-04-10 15:29 | 2020-01-28 | 2018-04-01 | 2020-01-30
75087 | FPIT | 344637001 | 344637001 - MW TEST DATA ENHANCEMENT | -0.05 |  | -0.05 |  |  | -0.05 | 1828 | -1828.05 | 2018-03-14 11:07 | 2018-12-28 | 2018-03-01 | 2018-12-28
75087 | FPIT | 400055002 | 400055002 - CHATBOT CHANNELS | 17978.99 |  | 17978.99 |  |  | 17978.99 | 6219 | 11759.99 | 2020-12-08 09:37 | 2022-03-31 | 2021-01-01 | 2022-03-31
75087 | FPIT | 400055005 | 400055005 - BUILDER PORTAL 2021 | 6696.84 |  | 6696.84 |  |  | 6696.84 | 17824 | -11127.16 | 2020-12-10 18:21 | 2023-09-30 | 2021-01-01 | 2023-09-30
75087 | FPIT | 400055008 | 400055008 - PNG - CRT | 901.5 |  | 901.5 |  |  | 901.5 | 11377 | -10475.5 | 2021-04-30 16:58 | 2022-02-28 | 2021-05-01 | 2022-03-31
75087 | FPIT | 400055009 | 400055009 - CALL CENTER ANALYTICS SW | 57180.49 |  | 57180.49 |  |  | 57180.49 | 5888 | 51292.49 | 2021-05-26 09:23 | 2022-09-30 | 2021-06-01 | 2022-09-30
75087 | FPIT | 400055010 | 400055010 - DIGITAL ASSISTANT PLATFORM PH 1 | 1445.77 |  | 1445.77 |  |  | 1445.77 | 6670 | -5224.23 | 2021-07-26 15:04 | 2022-03-15 | 2021-10-01 | 2022-03-31
75087 | FPIT | CC1900001 | CC1900001 - CUSTOMER ANALYTICS ENGINE | 19856.96 |  | 19856.96 |  |  | 35428.28 | 26306 | 9122.28 | 2020-01-27 08:12 | 2022-03-31 | 2020-02-01 | 2022-03-31
75087 | FPIT | CC2000003 | CC2000003 - SITECORE JSS FRONT END MODERNIZATIO | 16986.37 |  | 16986.37 |  |  | 30410.34 | 28721 | 1689.34 | 2020-06-25 21:36 | 2022-05-30 | 2020-08-01 | 2022-05-31
75087 | FPIT | CS1900001 | CS1900001 - VOICE OF THE CUSTOMER ENGAGEMENT PL | 14018.16 |  | 14018.16 |  |  | 31496.43 | 13742 | 17754.43 | 2020-01-29 16:09 | 2022-03-31 | 2020-02-01 | 2022-03-31
75087 | FPIT | CS2100003 | CS2100003 - ASPECT LICENSE PURCHASE | 5847.96 |  | 5847.96 |  |  | 5847.96 | 5845 | 2.96 | 2021-04-26 16:47 | 2021-08-29 | 2021-06-01 | 2021-09-30
75087 | FPIT | CS2100004 | CS2100004 - AVAYA LICENSE PURCHASE | 22258.74 |  | 22258.74 |  |  | 22258.74 | 22443 | -184.26 | 2021-05-12 09:10 | 2021-09-28 | 2021-05-01 | 2021-09-30
75087 | FPIT | CS2100005 | CS2100005 - INFRASTRUCTURE FOR 24/7 INTOUCH | 1962.85 |  | 1962.85 |  |  | 1962.85 | 1954 | 8.85 | 2021-05-27 11:53 | 2022-01-31 | 2021-06-01 | 2022-02-28
75087 | FPIT | CS2100006 | CS2100006 - UPLAND RIGHT ANSWER LICENSE PURCHAS | 3912.89 |  | 3912.89 |  |  | 3912.89 | 6007 | -2094.11 | 2021-06-16 11:03 | 2022-01-31 | 2021-07-01 | 2022-01-31
75087 | FPIT | CS2100007 | CS2100007 - VERINT LICENSE PURCHASE | 10156.396 |  | 10156.396 |  |  | 10156.396 | 17714 | -7557.604 | 2021-07-20 09:45 | 2021-12-29 | 2021-09-01 | 2021-12-31
75087 | FPIT | CS2100008 | CS2100008 - NUANCE IVR ENHANCEMENTS | 2737.03 |  | 2737.03 |  |  | 2737.03 | 4174 | -1436.97 | 2021-07-16 11:40 | 2022-08-31 | 2021-08-01 | 2022-08-31
75087 | FPIT | CS2100009 | CS2100009 - AVAYA LICENSE PURCHASE #2 | 10838.82 |  | 10838.82 |  |  | 10838.82 | 18874 | -8035.18 | 2021-07-27 16:32 | 2021-11-29 | 2021-09-01 | 2021-12-31
75087 | FPIT | LTHCESCS | LTHCESCS - WO OPTIMIZATION WORK INPUT/CALL-SW | 4789.14 |  | 4789.14 |  |  | 4789.14 | 13750 | -8960.86 | 2021-02-25 18:47 | 2022-03-31 | 2021-02-01 | 2021-03-31
75088 | CY1900015 | 349395006 | 349395006 - ITOT OT SIEM PHASE 2 HW WORKSTREAM | -68641.98 |  | -68641.98 |  |  | 51507.73 | 5497 | 46010.73 | 2020-04-13 16:35 | 2022-10-28 | 2020-05-01
75088 | CY1900015 | 349395SW6 | 349395SW6 - ITOT OT SIEM SW WORKSTREAM | 74358.34 |  | 74358.34 |  |  | 74358.34 | 6089 | 68269.34 | 2021-12-09 13:04 | 2022-10-28 | 2021-12-01
75088 | CY1900015 | CY190HW15 | CY190HW15 - IT-OT ANA WORKSTREAM HW | 15557.76 |  | 15557.76 |  |  | 15649.7 | 113909 | -98259.3 | 2019-12-11 08:05 | 2022-10-28 | 2020-01-01
75088 | CY1900015 | CY190SW15 | CY190SW15 - IT-OT ANA WORKSTREAM SW | 201.35 |  | 201.35 |  |  | 201.35 | 10808 | -10606.65 | 2019-12-11 07:56 | 2022-10-28 | 2021-03-01
75088 | MRTP2021 | 400052004 | 400052004 - DEK - TB5800 TEST SETS | 3915.39 |  | 3915.39 |  |  | 3915.39 | 26866 | -22950.61 | 2021-09-17 10:42 | 2022-02-17 | 2021-12-01
|  |  |  | 69176587.266 | 67376749.315 | 1799837.951 | 2.602%

## 2022
Duke Energy Kentucky Natural Gas
Year 2022
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | EAMHPBU | 349472008 | 349472008 - EAM 2021 MAXIMO DURABLE TEAM | 23725.69 |  | 23725.69 |  |  | 64726.05 | 84630 | -19903.95 | 2021-01-22 15:11 | 2022-05-30 | 2021-02-01 | 2022-08-15
75086 | EAMHPBU | 349472009 | 349472009 - NEW EAM 2021 MOBILE DURABLE TEAM | 107.86 |  | 107.86 |  |  | 1842.41 | 39130 | -37287.59 | 2021-01-13 13:03 | 2022-05-30 | 2021-02-01 | 2022-08-15
75086 | EAMHPBU | 349472018 | 349472018 - EAM 2022 MAXIMO DURABLE TEAM | 10771.86 |  | 10771.86 |  |  | 10771.86 | 6760 | 4011.86 | 2022-01-04 15:44 | 2023-05-30 | 2022-01-01 | 2023-07-17
75086 | FMDT2020 | MDTGAS20 | MDTGAS20 - INSTALL WIN 7 PANASONIC TOUGHBOOKS | 38450.24 |  | 38450.24 |  |  | 534413.49 | 403995 | 130418.49 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01 | 2021-03-31
75086 | FPIT | 349472016 | 349472016 - AUTODESK SUBSCRIPTION AGREEMENT | -3.92 |  | -3.92 |  |  | 11781.69 | 11803 | -21.31 | 2021-10-29 14:51 | 2022-03-20 | 2021-11-01 | 2022-03-20
75086 | FPIT | 349472020 | 349472020 - SLATE - EAM WORK MGMT SCHEDULING TO | 12519.46 |  | 12519.46 |  |  | 12519.46 | 22340 | -9820.54 | 2022-03-18 16:15 | 2024-06-30 | 2022-03-01 | 2024-06-30
75086 | FPIT | 349472021 | 349472021 - FMA ENHANCEMENTS | 2994.1 |  | 2994.1 |  |  | 2994.1 | 4713 | -1718.9 | 2022-05-18 12:26 | 2026-03-31 | 2022-06-01
75086 | FPIT | 349472023 | 349472023 - SMALLWORLD ENHANCEMENTS | 907.54 |  | 907.54 |  |  | 907.54 | 15341 | -14433.46 | 2022-09-29 18:21 | 2025-03-30 | 2022-11-01 | 2024-03-31
75086 | FPIT | 349472024 | 349472024 - NEW PRIMAVERA OAM SERVERS | 37.4 |  | 37.4 |  |  | 37.4 | 173 | -135.6 | 2022-09-29 16:29 | 2023-08-08 | 2022-10-01 | 2023-08-08
75086 | FPIT | 349472S13 | 349472S13 - JUMP APPLICATION | 1015.08 |  | 1015.08 |  |  | 3447.89 | 2199.41 | 1248.48 | 2021-02-08 08:20 | 2022-07-30 | 2021-06-01 | 2022-10-01
75086 | FPIT | 349472S14 | 349472S14 - NEW ESRI INTEGRATIONS AND INFRA | 45130.72 |  | 45130.72 |  |  | 49889.78 | 532359 | -482469.22 | 2021-02-09 13:04 | 2023-11-30 | 2021-03-01 | 2024-03-06
75086 | FPIT | 349472SW6 | 349472SW6 - EAM-SC NEXT GEN MOBILE PLATFORM SW | 3600.98 |  | 3600.98 |  |  | 11867.3 | 12210 | -342.7 | 2020-12-15 21:01 | 2022-07-29 | 2021-01-01 | 2022-09-27
75086 | FPIT | 400055013 | 400055013 - NGBU COMMUNICATIONS PLATFORM ENHANC | 36259.95 |  | 36259.95 |  |  | 36259.95 | 62056 | -25796.05 | 2021-12-28 16:22 | 2023-09-29 | 2022-01-01 | 2023-07-31
75086 | FPIT | CC2000001 | CC2000001 - NGBU COMMUNICATIONS PLATFORM | 1143.03 |  | 1143.03 |  |  | 59569.69 | 1242489 | -1182919.31 | 2020-03-30 13:53 | 2022-03-31 | 2020-04-01 | 2022-03-31
75086 | FPIT | IT1900067 | IT1900067 - ARM TO MAXIMO INTEGRATION | -13.89 |  | -13.89 |  |  | 9.9476e-14 | 0 | 9.9476e-14 | 2020-10-12 17:08 | 2021-07-31 | 2020-10-01 | 2021-07-27
75086 | FPIT | IT1900069 | IT1900069 - TRG - WAM MEASUREMENT PROJECT | -215.29 |  | -215.29 |  |  | 8.8107e-13 | 65041 | -65041 | 2020-02-21 15:10 | 2021-12-31 | 2020-03-01
75086 | FPIT | IT2000091 | IT2000091 - GIM TOOL ENHANCEMENTS AND NOTIFICAT | 7523.78 |  | 7523.78 |  |  | 31323.76 | 37595 | -6271.24 | 2020-12-14 16:03 | 2022-03-31 | 2021-03-01 | 2022-06-25
75086 | FPIT | IT2000092 | IT2000092 - GTIS ENHANCEMENT AND ACOG | 105257.67 |  | 105257.67 |  |  | 198280.49 | 111184 | 87096.49 | 2020-12-22 10:20 | 2023-03-31 | 2021-01-01 | 2022-12-26
75086 | FPIT | IT2000093 | IT2000093 - NG SCADA TRAINING SIMULATOR | 51005.14 |  | 51005.14 |  |  | 53842.63 | 91646 | -37803.37 | 2020-12-29 14:47 | 2022-01-29 | 2021-02-01 | 2022-03-20
75086 | FPIT | IT2000095 | IT2000095 - TRACEABILITY PHASE 2 | 4262.75 |  | 4262.75 |  |  | 92319.29 | 275326 | -183006.71 | 2021-01-05 09:17 | 2022-03-31 | 2021-01-01 | 2022-03-31
75086 | FPIT | IT2000098 | IT2000098 - GAS SALES PLATFORM PHASE 2 | 16784 |  | 16784 |  |  | 241421 | 254148 | -12727 | 2021-01-21 10:30 | 2023-03-31 | 2021-01-01 | 2022-03-31
75086 | FPIT | IT2000111 | IT2000111 - KEY CONTROL SYSTEM | 4161.11 |  | 4161.11 |  |  | 35512.45 | 30928 | 4584.45 | 2021-01-13 16:01 | 2022-03-31 | 2021-02-01 | 2022-05-31
75086 | FPIT | IT2100084 | IT2100084 - DEVONWAY LICENSE RENEWAL | 5216.32 |  | 5216.32 |  |  | 12725.73 | 47034 | -34308.27 | 2021-08-13 09:22 | 2022-08-31 | 2021-08-01 | 2022-08-31
75086 | FPIT | IT2100095 | IT2100095 - MOBILE MAPPING CONSOLIDATION | 287.53 |  | 287.53 |  |  | 287.53 | 49072 | -48784.47 | 2022-02-16 09:08 | 2023-02-28 | 2022-02-01
75086 | FPIT | IT2100113 | IT2100113 - GAS SALES PLATFORM PHASE 3 | 62578.76 |  | 62578.76 |  |  | 62578.76 | 77035 | -14456.24 | 2022-01-07 10:50 | 2023-09-17 | 2022-01-01 | 2023-10-12
75086 | FPIT | IT2100114 | IT2100114 - TRACEABILITY PHASE 2 EXTENSION | 94130.95 |  | 94130.95 |  |  | 94130.95 | 132599 | -38468.05 | 2022-01-20 14:10 | 2023-03-31 | 2022-01-01 | 2023-03-31
75086 | FPIT | IT2100132 | IT2100132 - NGBU REPAIR PLAN EXPANSION | 90821.83 |  | 90821.83 |  |  | 90821.83 | 75912 | 14909.83 | 2022-01-27 17:05 | 2023-11-30 | 2022-02-01 | 2023-11-21
75086 | FPIT | IT2200081 | IT2200081 - ENERGY EFFICIENCY REBATE PROCESSING | 15326.09 |  | 15326.09 |  |  | 15326.09 | 11692 | 3634.09 | 2022-06-10 16:32 | 2023-02-28 | 2022-06-01 | 2023-01-31
75086 | FPIT | LTHGBLDPL | LTHGBLDPL - LIGHTHOUSE GAS BUILDER PORTAL | 59754.42 |  | 59754.42 |  |  | 59754.42 | 146642 | -86887.58 | 2022-04-25 15:46 | 2023-10-31 | 2022-05-01 | 2023-07-26
75086 | FPIT | LTHGCHTRS | LTHGCHTRS - LIGHTHOUSE: GAS OPS CHARTER | 30004.74 |  | 30004.74 |  |  | 89815.26 | 86372 | 3443.26 | 2021-03-17 12:28 | 2022-09-30 | 2021-04-01 | 2022-06-30
75086 | FPIT | MOBILEMP | MOBILEMP - MOBILE MAPPING CONSOLIDATION | 25570.41 |  | 25570.41 |  |  | 25570.41 | 0 | 25570.41 | 2021-08-16 14:44 | 2022-12-31 | 2021-08-01 | 2022-12-31
75086 | FPIT | TC2000057 | TC2000057 - PNG TELECOM - LNG AND COMPRESSOR ST | 26282.4 |  | 26282.4 |  |  | 80498.56 | 216847 | -136348.44 | 2020-12-22 09:43 | 2022-03-31 | 2021-01-01 | 2022-05-15
75086 | FUNCTOHKY | 107GASCK | 107GASCK - GAS CAPITAL OVERHEAD | 647274.495 |  | 647274.495 |  |  | 1668588.969 | 0 | 1668588.969 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G701660 | AW4645 | AW4645 - EMERGENT AM01 COVINGTON LEVEE PH 1 | 5267885.89 |  | 5267885.89 |  |  | 5324996.24 | 3601200 | 1723796.24 | 2021-10-01 08:50 | 2023-01-30 | 2021-10-01 | 2023-02-28
75086 | G701662 | AW4673 | AW4673 - EMERGENT - CASING 34 - TAYLOR MILL | 2717558.37 |  | 2717558.37 |  |  | 2719439.5 | 3207100 | -487660.5 | 2021-10-13 11:13 | 2023-02-28 | 2021-11-01 | 2023-01-07
75086 | G701662 | AW4878 | AW4878 - ROW - CASING 34 - TAYLOR MILL | 1151.89 |  | 1151.89 |  |  | 1151.89 | 71800 | -70648.11 | 2021-12-22 17:10 | 2023-02-28 | 2022-06-01 | 2023-01-07
75086 | G712237 | MX4669122 | MX4669122 - HEBRON LOOP PH 2 PRESSURE IMPROVEME | 20516.13 |  | 20516.13 |  |  | 52311.15 | 765.33 | 51545.82 | 2021-03-01 14:01 | 2027-03-04 | 2021-03-01
75086 | G74092 | MX3645041 | MX3645041 - CHARTER - BRISTOW RD. PRESSURE IMP | 32296.21 |  | 32296.21 |  |  | 32296.21 | 2365.83 | 29930.38 | 2022-10-13 10:01 | 2025-07-24 | 2022-12-01 | 2024-10-28
75086 | G74238 | 43848219 | 43848219 - LAND - CHARTER - PATTY LN | 3226.15 |  | 3226.15 |  |  | 3226.15 | 40000 | -36773.85 | 2022-05-06 12:13 | 2026-03-31 | 2022-07-01
75086 | G74381 | AW5096 | AW5096 - DRY RIDGE - EXPOSED MAIN | 46894.84 |  | 46894.84 |  |  | 46894.84 | 33500 | 13394.84 | 2022-02-17 08:25 | 2022-08-31 | 2022-03-01 | 2022-06-17
75086 | G74426 | AW4587 | AW4587 - CANCEL -GWUT DIGS ON AM07 (DUKE KY) | -182.47 |  | -182.47 |  |  | 0 | 491352 | -491352 | 2021-09-15 16:10 | 2022-03-31 | 2021-09-01
75086 | G74964 | MX5762350 | MX5762350 - CHARTER - ST RT 536 - INDEPENDANCE | 777968.25 |  | 777968.25 |  |  | 777968.25 | 842182.55 | -64214.3 | 2022-02-23 18:01 | 2024-01-31 | 2022-03-01 | 2023-02-01
75086 | G75449 | AW5471 | AW5471 - LN AM07 SCCDA DIGS | 722650.32 |  | 722650.32 |  |  | 722650.32 | 1642098.73 | -919448.41 | 2022-05-26 13:41 | 2022-12-31 | 2022-06-01 | 2022-11-27
75086 | G75498 | MX5370534 | MX5370534 - CHARTER-LP03 INSTALL PRESSURE IMPRO | 189688.03 |  | 189688.03 |  |  | 189688.03 | 765.33 | 188922.7 | 2022-07-08 14:01 | 2023-03-30 | 2022-10-01 | 2023-03-06
75086 | G75629 | AW5648 | AW5648 - LN AM07 ECDA DIGS | 1639865 |  | 1639865 |  |  | 1639865 | 1466970.34 | 172894.66 | 2022-07-01 09:23 | 2022-12-31 | 2022-07-01 | 2023-01-20
75086 | G75683 | MX4850228 | MX4850228 - TOEBBEN DR - FLORENCE - 12" PL & 8" | 415571.46 |  | 415571.46 |  |  | 415571.46 | 49862.08 | 365709.38 | 2022-07-14 14:01 | 2022-12-29 | 2022-07-01 | 2022-12-26
75086 | G75920 | AW5953 | AW5953 - LN AM07 STATION ECDA DIGS | 841191.56 |  | 841191.56 |  |  | 841191.56 | 734403.62 | 106787.94 | 2022-07-29 15:51 | 2022-12-31 | 2022-08-01 | 2023-01-20
75086 | G75924 | AW5965 | AW5965 - LN AM00B ECDA DIGS | 801998.79 |  | 801998.79 |  |  | 801998.79 | 1098620 | -296621.21 | 2022-08-03 13:21 | 2022-12-31 | 2022-08-01 | 2023-01-31
75086 | G75979 | MX4329859 | MX4329859 - CHARTER-KYTC 06-445.00 MINEOLA PK-E | 2377.44 |  | 2377.44 |  |  | 2377.44 | 697743.72 | -695366.28 | 2022-09-12 10:01 | 2024-03-28 | 2022-10-01 | 2023-12-06
75086 | G76300 | AW6368 | AW6368 - EMERGENT - AM07 EXPOSED MAIN (KY) | 90032 |  | 90032 |  |  | 90032 | 1348700 | -1258668 | 2022-11-16 13:54 | 2023-12-30 | 2022-11-01 | 2024-01-09
75086 | G76446 | MX1322454 | MX1322454 - CHARTER-KYTC-162.40-BRISTOW RD-STI- | 42422.39 |  | 42422.39 |  |  | 42422.39 | 786869.97 | -744447.58 | 2022-10-07 14:01 | 2025-10-29 | 2022-10-01 | 2025-03-07
75086 | G7AM00ACR | AW3397 | AW3397 - LINE AM00A CORROSION REMEDIATION | 60836.78 |  | 60836.78 |  |  | 193517.04 | 180372.32 | 13144.72 | 2021-01-20 10:04 | 2022-03-31 | 2021-12-01 | 2022-03-20
75086 | G7AM00BVL | V5471 | V5471 - AM00B & UL06 VALVE AUTOMATION | 257827.48 |  | 257827.48 |  |  | 257827.48 | 1830100 | -1572272.52 | 2021-11-22 12:33 | 2023-12-30 | 2022-04-01 | 2023-12-06
75086 | G7AM07IL2 | AW4685 | AW4685 - LINE AM07 PIPELINE REPLACEMENT PHAS | 569484.58 |  | 569484.58 |  |  | 609688.56 | 33015500 | -32405811.44 | 2021-10-18 16:29 | 2025-02-28 | 2021-11-01 | 2025-02-06
75086 | G7AM07IL2 | AW5957 | AW5957 - CANCEL_LINE AM07 PHASE 2 - STATION | 66.34 |  | 66.34 |  |  | 66.34 | 9656000 | -9655933.66 | 2022-08-01 15:12 | 2025-02-28 | 2022-10-01
75086 | G7AM07ILI | 0233100 | 0233100 - LINE AM07 PIPELINE REPLACEMENT PHAS | 1119078.14 |  | 1119078.14 |  |  | 1892074.73 | 37717000 | -35824925.27 | 2020-12-09 14:11 | 2023-12-31 | 2020-12-01 | 2024-03-18
75086 | G7AM07ILI | AW3074 | AW3074 - LINE AM07 PIPELINE REPLACE LAND | 1019260.69 |  | 1019260.69 |  |  | 1123597.22 | 6089500 | -4965902.78 | 2020-12-03 12:25 | 2023-12-31 | 2021-02-01 | 2024-03-18
75086 | G7AM07ILI | AW3138 | AW3138 - LINE AM07 PIPELINE REPLACEMENT-STN | 2049566.99 |  | 2049566.99 |  |  | 2062494.67 | 6278300 | -4215805.33 | 2020-12-18 13:08 | 2024-04-30 | 2021-05-01 | 2024-09-28
75086 | G7ASDD | MX5515912 | MX5515912 - AMAZON SOUTHWEST DELIVERY DIST. PRO | 270054.26 |  | 270054.26 |  |  | 327791.44 | 307485 | 20306.44 | 2020-04-16 18:01 | 2020-10-11 | 2020-05-01 | 2021-04-04
75086 | G7ASRP | CMSP70 | CMSP70 - ASRP CURB TO METER 3" OR LESS | 19294.88 |  | 19294.88 |  |  | 8899858.89 | 20388002 | -11488143.11 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | G7ASRP | MCSP70 | MCSP70 - ASRP MAIN TO CURB 3" OR LESS | 993991.82 |  | 993991.82 |  |  | 43018279.61 | 19954384 | 23063895.61 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | G7CORREM | AW5064 | AW5064 - KENTUCKY - CORROSION REMEDIATION | 124669.65 |  | 124669.65 |  |  | 124669.65 | 272000 | -147330.35 | 2022-02-10 15:46 | 2025-09-30 | 2022-08-01
75086 | G7ECOMPLX | V8967 | V8967 - ERLANGER MODULAR COMPLEX | -2366.65 |  | -2366.65 |  |  | 378579.32 | 244737.99 | 133841.33 | 2019-04-17 13:32 | 2020-10-30 | 2019-06-01 | 2022-01-30
75086 | G7EDGE | 39171904 | 39171904 - CANCEL-ROW- EDGEWOOD PRESSURE IMP | 29427.44 |  | 29427.44 |  |  | 29427.44 | 40000 | -10572.56 | 2022-06-07 07:26 | 2023-01-31 | 2022-08-01
75086 | G7EDGE | MX9171904 | MX9171904 - EDGEWOOD PRESSURE IMP | 413626.71 |  | 413626.71 |  |  | 413626.71 | 108825.77 | 304800.94 | 2022-09-22 14:01 | 2023-07-29 | 2022-09-01 | 2023-07-24
75086 | G7EM6131 | AW6193 | AW6193 - KLEERBAND REMED AND COAT KY | 4792.93 |  | 4792.93 |  |  | 4792.93 | 120000 | -115207.07 | 2022-10-03 12:32 | 2023-06-30 | 2022-12-01 | 2023-05-13
75086 | G7EMAM07 | AW5092 | AW5092 - EMERGENT - LINE AM07 - EXPOSED MAIN | 339761.63 |  | 339761.63 |  |  | 339761.63 | 1319200 | -979438.37 | 2022-02-15 14:54 | 2023-06-30 | 2022-04-01 | 2023-09-30
75086 | G7ENCC | AW3484 | AW3484 - ERLANGER CASINGS 2021 | 79.1 |  | 79.1 |  |  | 213821.2 | 181501.63 | 32319.57 | 2021-01-27 13:42 | 2022-03-31 | 2021-12-01 | 2022-04-13
75086 | G7ERGEMER | AW4046 | AW4046 - EMERGENCY ERLANGER GAS CUT OUT | -4338.26 |  | -4338.26 |  |  | 291787.6 | 95000 | 196787.6 | 2021-07-06 10:44 | 2021-10-30 | 2021-07-01 | 2021-11-06
75086 | G7ERLCP | AW1656 | AW1656 - ERLANGER MAG ANODES | 729326.55 |  | 729326.55 |  |  | 1594296.49 | 2442881.69 | -848585.2 | 2020-01-21 15:36 | 2026-12-31 | 2020-04-01
75086 | G7ESPEP | MX9171927 | MX9171927 - ELSMERE PRESSURE IMP | 1381513.66 |  | 1381513.66 |  |  | 1381513.66 | 327967.71 | 1053545.95 | 2022-04-25 14:01 | 2023-07-29 | 2022-05-01 | 2023-07-05
75086 | G7HARRPK | AW4778 | AW4778 - ROW - HARRIS PIKE UL45 EXT | 35509.06 |  | 35509.06 |  |  | 35509.06 | 926800 | -891290.94 | 2021-11-16 10:04 | 2026-11-30 | 2022-07-01
75086 | G7HARRPK | AW4796 | AW4796 - HARRIS PIKE UL45 EXT - PRESSURE IMP | 366895.25 |  | 366895.25 |  |  | 366895.25 | 7884400 | -7517504.75 | 2021-11-19 10:02 | 2026-11-30 | 2022-02-01
75086 | G7HICKSP | MX5739585 | MX5739585 - HICKS PIKE PRESSURE IMPROVEMENT PRO | 3800.25 |  | 3800.25 |  |  | 750987.56 | 254017.35 | 496970.21 | 2021-04-20 18:02 | 2022-02-24 | 2021-05-01 | 2022-02-02
75086 | G7HMISTAT | AW0938 | AW0938 - HMI WORK STATION ERLANGER | 4705.22 |  | 4705.22 |  |  | 97480.91 | 64259 | 33221.91 | 2019-08-09 13:08 | 2021-03-02 | 2019-10-01 | 2021-08-15
75086 | G7LGMR | MX6828172 | MX6828172 - TO BE CANCEL-REG420BELAIR&SPICEWOOD | -28971.38 |  | -28971.38 |  |  | 82.8 | 139842.24 | -139759.44 | 2018-04-04 10:01 | 2021-03-31 | 2019-01-01
75086 | G7LGMR | T4002 | T4002 - (CANCEL) STA 20933317 ERLANGER CP | -77.54 |  | -77.54 |  |  | -2407.97 | 31943.04 | -34351.01 | 2017-03-17 11:42 | 2018-12-30 | 2017-08-01
75086 | G7LGMR | T7778 | T7778 - CANCEL-SCAD 21153712 KY | -52.69 |  | -52.69 |  |  | -1058.63 | 165811.2 | -166869.83 | 2017-05-03 08:00 | 2018-06-29 | 2017-05-01
75086 | G7LUL02 | AW2880 | AW2880 - LINE UL02 - MAOP REPLACEMENT | 8794.16 |  | 8794.16 |  |  | 3242070.66 | 1717200 | 1524870.66 | 2020-10-07 12:58 | 2022-03-31 | 2020-10-01 | 2022-01-05
75086 | G7LUL02 | AW3546 | AW3546 - LINE UL 02 MAOP REPL LAND | 1646.67 |  | 1646.67 |  |  | 58176.59 | 50000 | 8176.59 | 2021-02-04 13:42 | 2022-03-31 | 2021-02-01 | 2022-01-05
75086 | G7MAINS | 42331188 | 42331188 - MEA, MASON ROAD FARM TAP-TAYLOW MIL | 135.36 |  | 135.36 |  |  | 135.36 | 40000 | -39864.64 | 2022-03-04 10:29 | 2022-08-27 | 2022-03-01 | 2022-08-04
75086 | G7MAINS | 42698978 | 42698978 - ROW E MT ZION RD; INDEPNDNCE | 2457.95 |  | 2457.95 |  |  | 2457.95 | 15000 | -12542.05 | 2022-02-28 16:11 | 2023-01-31 | 2022-06-01 | 2023-02-16
75086 | G7MAINS | AW6146 | AW6146 - CANCEL_ROW LAKELAND PARK DR; LIM | 3409.98 |  | 3409.98 |  |  | 3409.98 | 25000 | -21590.02 | 2022-09-20 13:09 | 2023-12-31 | 2022-10-01
75086 | G7MAINS | AW6147 | AW6147 - CANCEL-ROW MEA -STANBERY RIDGE | 410.29 |  | 410.29 |  |  | 410.29 | 25000 | -24589.71 | 2022-09-20 13:28 | 2023-09-09 | 2022-10-01
75086 | G7MAINS | MEAPJT70 | MEAPJT70 - JOINT TRENCH PLASITC MAIN EXTENSION | 1014175.97 |  | 1014175.97 |  |  | 5891338.01 | 10000000 | -4108661.99 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | G7MAINS | MX0245370 | MX0245370 - REDWOOD LIVING APARTMENTS - APPROAC | 120389.91 |  | 120389.91 |  |  | 131528.29 | 53405.95 | 78122.34 | 2021-09-07 10:02 | 2022-05-29 | 2021-09-01 | 2022-04-20
75086 | G7MAINS | MX0536654 | MX0536654 - CANCEL-NEWPORT CLIFTON SU - HOME | -35.46 |  | -35.46 |  |  | 0 | 765.33 | -765.33 | 2021-04-12 14:03 | 2024-08-13 | 2021-06-01
75086 | G7MAINS | MX0610527 | MX0610527 - JT-G-BALLYSHANNON SECTION 5 PHASE 9 | 43864.74 |  | 43864.74 |  |  | 43999.96 | 42242.95 | 1757.01 | 2021-11-30 14:02 | 2022-11-20 | 2021-12-01 | 2022-09-09
75086 | G7MAINS | MX0864994 | MX0864994 - MADONNA MANOR PH 2 MEA, VILLA HILLS | 98663.93 |  | 98663.93 |  |  | 113293.43 | 72524.38 | 40769.05 | 2021-09-24 14:02 | 2021-12-21 | 2021-10-01 | 2022-05-13
75086 | G7MAINS | MX0938445 | MX0938445 - JT-G-AUTUMN RIDGE PHASE 1 PART B | 21138.61 |  | 21138.61 |  |  | 29870.98 | 45429 | -15558.02 | 2021-11-16 14:01 | 2022-08-17 | 2021-12-01 | 2022-04-22
75086 | G7MAINS | MX0964990 | MX0964990 - 425' PLASTIC GAS MAIN EXTENSION. SA | 872.52 |  | 872.52 |  |  | 69847.02 | 26396.88 | 43450.14 | 2021-07-19 14:02 | 2024-12-24 | 2021-08-01 | 2022-02-02
75086 | G7MAINS | MX1062851 | MX1062851 - HOGREFE RD MEA-171 FT 4 INCH PL HP | 1237.18 |  | 1237.18 |  |  | 18309.67 | 18025.99 | 283.68 | 2021-07-26 14:02 | 2024-12-17 | 2021-08-01 | 2021-12-21
75086 | G7MAINS | MX1688384 | MX1688384 - NEW BUFFINGTON PH 2 EXTENSION; ELSE | 1003.01 |  | 1003.01 |  |  | 23000.83 | 25500.96 | -2500.13 | 2021-09-08 10:01 | 2024-04-23 | 2021-09-01 | 2022-02-03
75086 | G7MAINS | MX1811415 | MX1811415 - 137 PLAZA DR. FARM TAP,HIGHLAND HEI | 3227.13 |  | 3227.13 |  |  | 26079.49 | 34481.14 | -8401.65 | 2021-09-24 14:02 | 2022-03-03 | 2021-10-01 | 2022-02-08
75086 | G7MAINS | MX1921442 | MX1921442 - FARM TAP PROJECT REDSTONE RD - ALEX | 194.58 |  | 194.58 |  |  | 194911.56 | 74423.61 | 120487.95 | 2021-03-24 10:02 | 2024-10-07 | 2021-04-01 | 2021-11-30
75086 | G7MAINS | MX1957438 | MX1957438 - FARM TAP PROJ; GRANDVIEW RD | -25173.62 |  | -25173.62 |  |  | 494870.19 | 161978.74 | 332891.45 | 2020-09-29 10:01 | 2021-12-16 | 2020-09-01 | 2022-01-10
75086 | G7MAINS | MX1957677 | MX1957677 - FARM TAP PROJECT; UPPER LICK BRANCH | 22647.57 |  | 22647.57 |  |  | 154929.21 | 88637.51 | 66291.7 | 2021-10-12 14:01 | 2022-06-16 | 2021-10-01 | 2022-05-08
75086 | G7MAINS | MX2043872 | MX2043872 - FARM TAP PROJ; BARRS BRANCH RD | 23868.76 |  | 23868.76 |  |  | 158444.62 | 83717.7 | 74726.92 | 2021-08-20 10:02 | 2022-06-23 | 2021-08-01 | 2022-05-29
75086 | G7MAINS | MX2061333 | MX2061333 - STONEWATER PHASE B1 APPROACH MAIN | 159156.54 |  | 159156.54 |  |  | 159156.54 | 128082.79 | 31073.75 | 2022-02-10 10:02 | 2022-08-04 | 2022-02-01 | 2022-07-21
75086 | G7MAINS | MX2061362 | MX2061362 - JT-G-THE RESERVE AT BELLEVUE | 80636.81 |  | 80636.81 |  |  | 80636.81 | 46814.99 | 33821.82 | 2021-12-16 18:02 | 2023-03-01 | 2022-01-01 | 2022-12-14
75086 | G7MAINS | MX2331188 | MX2331188 - MEA, MASON ROAD FARM TAP-TAYLOW MIL | 256954.63 |  | 256954.63 |  |  | 608521.62 | 240393.36 | 368128.26 | 2021-09-15 18:02 | 2022-08-25 | 2021-10-01 | 2022-08-02
75086 | G7MAINS | MX2698978 | MX2698978 - E MT ZION RD; INDEPENDENCE; 6" PL; | 532304.78 |  | 532304.78 |  |  | 532304.78 | 161397.39 | 370907.39 | 2022-07-21 18:02 | 2023-02-26 | 2022-07-01 | 2023-02-21
75086 | G7MAINS | MX2700925 | MX2700925 - BRECKENRIDGE; ALEXANDRIA; 4" PL; MA | 126577.68 |  | 126577.68 |  |  | 126577.68 | 76342.51 | 50235.17 | 2022-05-18 18:01 | 2022-11-17 | 2022-05-01 | 2022-11-08
75086 | G7MAINS | MX3351619 | MX3351619 - HIGHLAND AVE AND WOODLAND PL MAE - | 29906.31 |  | 29906.31 |  |  | 33267.79 | 19811.35 | 13456.44 | 2021-12-10 14:02 | 2022-05-19 | 2021-12-01 | 2022-03-27
75086 | G7MAINS | MX3676138 | MX3676138 - JT-G-MEMORIAL POINTE PART 1 | 158.22 |  | 158.22 |  |  | 158.22 | 30148.66 | -29990.44 | 2022-09-14 14:01 | 2024-08-04 | 2022-10-01 | 2023-09-26
75086 | G7MAINS | MX3738158 | MX3738158 - JT-G-SAWGRASS PHASE D PART 2 | 158.22 |  | 158.22 |  |  | 158.22 | 36692.03 | -36533.81 | 2022-10-04 14:01 | 2024-04-22 | 2022-10-01 | 2023-10-23
75086 | G7MAINS | MX3880107 | MX3880107 - SERVICE RD; WALTON; 6" PL; MEA | 81614.89 |  | 81614.89 |  |  | 81614.89 | 54841.48 | 26773.41 | 2022-04-20 18:01 | 2022-09-15 | 2022-05-01 | 2022-09-05
75086 | G7MAINS | MX3955327 | MX3955327 - LOCK RD-BUTLER-1200 FT 4 INCH PL MA | 152492.34 |  | 152492.34 |  |  | 152492.34 | 66243.21 | 86249.13 | 2022-07-15 18:01 | 2022-12-29 | 2022-07-01 | 2022-12-20
75086 | G7MAINS | MX4296108 | MX4296108 - RICE PK; UNION; 4" PL; MEA | 107237.32 |  | 107237.32 |  |  | 107237.32 | 79193.21 | 28044.11 | 2022-06-07 14:01 | 2022-11-17 | 2022-06-01 | 2022-11-16
75086 | G7MAINS | MX4309183 | MX4309183 - JT-G-BALLYSHANNON SECTION 5 PHASE 1 | 23985.16 |  | 23985.16 |  |  | 23985.16 | 58459.77 | -34474.61 | 2022-04-07 10:01 | 2023-06-05 | 2022-04-01 | 2023-02-09
75086 | G7MAINS | MX4309894 | MX4309894 - HICKS PK; UNION; 4" PL; MEA | 31077.09 |  | 31077.09 |  |  | 31077.09 | 21184.14 | 9892.95 | 2022-04-20 18:01 | 2022-09-15 | 2022-05-01 | 2022-09-11
75086 | G7MAINS | MX4720432 | MX4720432 - 498 MASON RD FARM TAP EXTENSION | 22241.31 |  | 22241.31 |  |  | 22241.31 | 17882.37 | 4358.94 | 2022-08-25 10:01 | 2023-03-09 | 2022-08-01 | 2023-02-16
75086 | G7MAINS | MX4752800 | MX4752800 - MILITARY PKWY-FORT THOMAS-60 FT 2 I | 15797.66 |  | 15797.66 |  |  | 15797.66 | 389.02 | 15408.64 | 2022-06-15 10:01 | 2022-11-24 | 2022-06-01 | 2022-10-27
75086 | G7MAINS | MX5095081 | MX5095081 - EAST FROGTOWN RD; RICHWOOD; 6" PL; | 92834.96 |  | 92834.96 |  |  | 92834.96 | 71068.41 | 21766.55 | 2022-08-18 18:02 | 2023-03-30 | 2022-08-01 | 2023-02-20
75086 | G7MAINS | MX5190163 | MX5190163 - FROGTOWN CONNECTOR; RICHWOOD ; 4" P | 54977.55 |  | 54977.55 |  |  | 54977.55 | 2850.86 | 52126.69 | 2022-08-03 14:02 | 2023-01-12 | 2022-08-01 | 2023-01-01
75086 | G7MAINS | MX5652554 | MX5652554 - CANCEL-MASON-TAYLOR MILL-4IN PE 6IN | -23.46 |  | -23.46 |  |  | 3.5527e-14 | 237226.07 | -237226.07 | 2020-12-16 10:17 | 2021-09-24 | 2020-12-01
75086 | G7MAINS | MX5653109 | MX5653109 - FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 176791.78 |  | 176791.78 |  |  | 549751.77 | 194197.42 | 355554.35 | 2020-09-29 10:01 | 2023-07-13 | 2020-10-01 | 2023-11-15
75086 | G7MAINS | MX5709107 | MX5709107 - CANCEL-FARM TAP PROJ; BRANCH RD | -9.49 |  | -9.49 |  |  | 0 | 83287.78 | -83287.78 | 2021-02-25 18:02 | 2021-12-16 | 2021-02-01
75086 | G7MAINS | MX5751969 | MX5751969 - MEA - STANBERY RIDGE-FORT THOMAS-47 | 103579.55 |  | 103579.55 |  |  | 103579.55 | 24699.21 | 78880.34 | 2022-10-04 18:01 | 2023-03-23 | 2022-10-01 | 2023-03-21
75086 | G7MAINS | MX6108813 | MX6108813 - PARKVIEW ESTATES APP - UNION - 8" & | 168821.53 |  | 168821.53 |  |  | 168821.53 | 134092.12 | 34729.41 | 2022-10-26 10:01 | 2023-03-23 | 2022-11-01 | 2023-04-10
75086 | G7MAINS | MX6362268 | MX6362268 - SERVICE RD; WALTON; 6" PL; MEA | 13569.97 |  | 13569.97 |  |  | 13569.97 | 61477.74 | -47907.77 | 2022-11-10 16:16 | 2023-04-13 | 2022-11-01 | 2023-04-20
75086 | G7MAINS | MX6445818 | MX6445818 - CARBON WAY; RICHWOOD; 6" PL; MEA | 28343.81 |  | 28343.81 |  |  | 28343.81 | 100161.61 | -71817.8 | 2022-11-14 14:02 | 2023-06-08 | 2022-11-01 | 2023-05-30
75086 | G7MAINS | MX6891268 | MX6891268 - CANCEL AMAZON SOUTHWEST DELIVERY | -270054.26 |  | -270054.26 |  |  | 0 | 319190 | -319190 | 2020-05-22 14:01 | 2021-03-31 | 2020-05-01
75086 | G7MAINS | MX7488442 | MX7488442 - CANCEL-UARY VILLAGE PHASE 1 PART 3 | -40.85 |  | -40.85 |  |  | 0 | 44181.42 | -44181.42 | 2020-09-23 10:01 | 2023-03-22 | 2020-10-01
75086 | G7MAINS | MX8197104 | MX8197104 - JT-G-REDWOOD LIVING APARTMENTS | 25636.69 |  | 25636.69 |  |  | 25856.17 | 95065.91 | -69209.74 | 2021-03-26 18:02 | 2022-12-30 | 2021-04-01 | 2022-12-19
75086 | G7MAINS | MX9801147 | MX9801147 - ELIJAH CREEK LOOP; NEYER DEVELOPMEN | 155086.56 |  | 155086.56 |  |  | 158318.91 | 88032.99 | 70285.92 | 2021-11-30 14:02 | 2022-07-07 | 2021-12-01 | 2022-06-27
75086 | G7MAINS | MX9803235 | MX9803235 - MARY GRUBS HWY - WALTON - 4" PE - M | 5566.56 |  | 5566.56 |  |  | 39183.17 | 20070.03 | 19113.14 | 2021-05-10 10:02 | 2024-10-21 | 2021-06-01 | 2022-01-20
75086 | G7MREG118 | MX2217622 | MX2217622 - STATION 873 - 5TH & PHILADELPHIA | 152915.2 |  | 152915.2 |  |  | 178967.29 | 87907.04 | 91060.25 | 2017-09-22 14:01 | 2025-11-30 | 2017-10-01
75086 | G7PUBIMP | MX0073622 | MX0073622 - CANCEL - NEWPORT CLIFTON STI | -38.15 |  | -38.15 |  |  | 0 | 0 | 0 | 2021-03-04 10:02 | 2021-07-20 | 2021-05-01
75086 | G7PUBIMP | MX0129552 | MX0129552 - CHAPMAN LN. - ROAD RECONSTRUCTION - | 121065.3 |  | 121065.3 |  |  | 137360.64 | 73592.68 | 63767.96 | 2021-03-30 10:09 | 2025-02-17 | 2021-04-01 | 2022-06-29
75086 | G7PUBIMP | MX0503657 | MX0503657 - JOYCE AVE STI-NEWPORT KY - 300' OF | 12594.91 |  | 12594.91 |  |  | 141660.92 | 50388.91 | 91272.01 | 2021-06-22 18:02 | 2024-11-19 | 2021-06-01 | 2022-01-27
75086 | G7PUBIMP | MX1682120 | MX1682120 - CANCEL-*TEST HOLES* MADISON ST | -2948.97 |  | -2948.97 |  |  | 0 | 0 | 0 | 2021-08-18 14:03 | 2024-12-18 | 2021-09-01
75086 | G7PUBIMP | MX2442598 | MX2442598 - BROMLEY-CR. SPRINGS RD (KY 2373) | 152622.77 |  | 152622.77 |  |  | 249577.43 | 90736.42 | 158841.01 | 2021-08-02 14:02 | 2022-02-06 | 2021-08-01 | 2022-01-31
75086 | G7PUBIMP | MX2778391 | MX2778391 - STI JAQUELINE DR ERLANGER 80' 4" ST | -201.98 |  | -201.98 |  |  | 11633.31 | 20092.61 | -8459.3 | 2021-10-26 18:02 | 2022-05-22 | 2021-11-01 | 2022-03-06
75086 | G7PUBIMP | MX2781786 | MX2781786 - CANCEL_KYTC 19-9001 I-275 GRAVES RD | 13395.31 |  | 13395.31 |  |  | 104794.3 | 70082.56 | 34711.74 | 2020-12-09 10:02 | 2023-11-22 | 2021-06-01
75086 | G7PUBIMP | MX2911494 | MX2911494 - UL 35 STREET IMPROVEMENT PROJECT | -2000 |  | -2000 |  |  | 26756.85 | 51296.38 | -24539.53 | 2019-08-02 14:01 | 2020-01-09 | 2019-09-01 | 2020-09-15
75086 | G7PUBIMP | MX3359474 | MX3359474 - KYTC - RICHWOOD RD STI - BEAVERLICK | 291540.23 |  | 291540.23 |  |  | 320038.74 | 24088.21 | 295950.53 | 2021-12-13 14:02 | 2024-12-31 | 2021-12-01 | 2022-06-22
75086 | G7PUBIMP | MX4199889 | MX4199889 - US-25 WALTON - 4" PL - STI | 135622.56 |  | 135622.56 |  |  | 135622.56 | 38705.17 | 96917.39 | 2022-07-25 14:01 | 2023-03-30 | 2022-08-01 | 2023-02-16
75086 | G7PUBIMP | MX4966474 | MX4966474 - 7639 TURFWAY - FLORENCE - 8" PL - S | 85019.82 |  | 85019.82 |  |  | 85019.82 | 3293.8 | 81726.02 | 2022-06-27 18:01 | 2023-03-30 | 2022-07-01 | 2023-03-01
75086 | G7PUBIMP | MX5108455 | MX5108455 - KENTABOO DR - FLORENCE - 4" PL - ST | 62978.9 |  | 62978.9 |  |  | 62978.9 | 4544.42 | 58434.48 | 2022-06-21 14:01 | 2022-11-10 | 2022-06-01 | 2022-10-28
75086 | G7PUBIMP | MX6266002 | MX6266002 - US27/MARSHALL LN. TO JOHNS HILL RD. | 18712.77 |  | 18712.77 |  |  | 18712.77 | 31832.35 | -13119.58 | 2022-02-04 14:01 | 2023-01-12 | 2022-08-01 | 2022-12-25
75086 | G7PUBIMP | MX6798234 | MX6798234 - KYTC 06-8916 HOUSTON RD-ERLANGER-ST | 15602.1 |  | 15602.1 |  |  | 15602.1 | 142182.69 | -126580.59 | 2022-10-21 14:01 | 2024-01-11 | 2022-11-01 | 2024-03-19
75086 | G7PUBIMP | MX7832792 | MX7832792 - BROOKWOOD DR. SOUTH - EDGEWOOD - 4" | 23794.85 |  | 23794.85 |  |  | 132234 | 75946.23 | 56287.77 | 2020-09-09 10:01 | 2021-05-21 | 2021-03-01 | 2021-09-07
75086 | G7PUBIMP | MX8662697 | MX8662697 - CANCEL-PLEAST VALY PT 3 INSL STREET | -12.54 |  | -12.54 |  |  | 0 | 0 | 0 | 2020-11-04 18:02 | 2021-05-02 | 2021-06-01
75086 | G7PUBIMP | MX9244894 | MX9244894 - KYTC - MT.ZION RD KY536 STI | 722810.03 |  | 722810.03 |  |  | 1011173.41 | 1026778 | -15604.59 | 2019-11-08 10:01 | 2023-06-30 | 2020-01-01 | 2021-07-27
75086 | G7PUBIMP | MX9853572 | MX9853572 - GRAVES AND NORTHBEND ROUNDABOUT PRO | 33463.52 |  | 33463.52 |  |  | 269708.9 | 109422.27 | 160286.63 | 2021-02-16 18:02 | 2023-12-28 | 2021-02-01 | 2022-02-14
75086 | G7PUBIMP | MX9856643 | MX9856643 - CANCEL-KYTC - KY-536 DONALDSON RD | 39331.86 |  | 39331.86 |  |  | 39331.86 | 0 | 39331.86 | 2022-09-06 18:01 | 2024-12-31 | 2022-11-01
75086 | G7PUBIMP | MX9948553 | MX9948553 - WILBERS LN - FORT THOMAS - 2" PE - | 26004.32 |  | 26004.32 |  |  | 125983.92 | 75860.65 | 50123.27 | 2021-07-13 18:02 | 2024-12-16 | 2021-07-01 | 2023-02-21
75086 | G7PUINEW | INSREGREL | INSREGREL - INSTALL OR REMOVE REGULATOR/RELIEF | 86464.12 |  | 86464.12 |  |  | 1472475.63 | 800000 | 672475.63 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | MX8375093 | MX8375093 - M&R; 3087 TERMINAL DR; CVG AIRPORT | 7349.44 |  | 7349.44 |  |  | 58605.67 | 51696.38 | 6909.29 | 2021-05-04 18:02 | 2021-08-24 | 2021-06-01 | 2022-06-27
75086 | G7PUINEW | SETMETER | SETMETER - SET OR REMOVE METER | 2586675.13 |  | 2586675.13 |  |  | 12433826.74 | 2250000 | 10183826.74 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | T2904 | T2904 - CANCEL-MTR 11540114 1 CARBON WAY | -69.35 |  | -69.35 |  |  | -2125.29 | 29846.02 | -31971.31 | 2017-03-08 13:44 | 2018-12-31 | 2017-12-01
75086 | G7PUINMR | AGECHGLG | AGECHGLG - KENTUCKY AGE CHANGE LARGE METER | 155545.97 |  | 155545.97 |  |  | 759506.44 | 350000 | 409506.44 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | AGECHGSM - KENTUCKY AGE CHANGE SMALL METER | 725529.48 |  | 725529.48 |  |  | 7596975.66 | 14500000 | -6903024.34 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRLG | CHGMTRLG - CHANGE LARGE METER KENTUCKY | 3.02 |  | 3.02 |  |  | 165029.18 | 725000 | -559970.82 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | CHGMTRSM - CHANGE SMALL METER KENTUCKY | 143796.68 |  | 143796.68 |  |  | 3096858.32 | 1250000 | 1846858.32 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | CHGREGREL - CHANGE REGULATOR/RELIEF KENTUCKY | 1.21 |  | 1.21 |  |  | 168024.67 | 800000 | -631975.33 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7REG0026 | MX7281967 | MX7281967 - REG 0026 UPHIL AND HIGHWAY - REG SW | -6341.94 |  | -6341.94 |  |  | 2411.25 | 48953.52 | -46542.27 | 2020-07-07 10:01 | 2021-03-31 | 2020-08-01 | 2021-01-20
75086 | G7REG0031 | MX2737090 | MX2737090 - REG 0031 - NINTH AND YORK - ABANDON | -121.17 |  | -121.17 |  |  | 0 | 0 | 0 | 2021-11-02 14:02 | 2022-03-15 | 2021-12-01 | 2022-03-29
75086 | G7REG0089 | AW3224 | AW3224 - REG 0427 EMPIRE DR | 534450.88 |  | 534450.88 |  |  | 822438.94 | 732000 | 90438.94 | 2020-12-30 15:41 | 2025-10-30 | 2021-07-01
75086 | G7REG0089 | AW3246 | AW3246 - REG 0427 EMPIRE DR LAND | 14785.03 |  | 14785.03 |  |  | 63309.64 | 82500 | -19190.36 | 2021-01-02 13:48 | 2026-03-31 | 2021-04-01
75086 | G7REG010 | AW3280 | AW3280 - REG 0010 STEVENSON AND LEXINGTON RE | -16.08 |  | -16.08 |  |  | 27552.45 | 58000 | -30447.55 | 2021-01-06 11:52 | 2022-03-31 | 2021-06-01 | 2021-11-02
75086 | G7REG017 | AW3195 | AW3195 - REG 0017 FOOTE AND FAIRFIELD REPAIR | 5128.13 |  | 5128.13 |  |  | 28394.05 | 429700 | -401305.95 | 2020-12-29 08:23 | 2023-03-31 | 2021-09-01 | 2021-12-17
75086 | G7REG021 | AW3278 | AW3278 - REG 0021 GRAND AND S FT THOMAS REPA | 558.52 |  | 558.52 |  |  | 14410.4 | 56400 | -41989.6 | 2021-01-06 10:47 | 2022-03-31 | 2021-07-01 | 2021-10-23
75086 | G7REG026 | AW3184 | AW3184 - REG 0437 UPHILL & HIGHWAY | 1413967.66 |  | 1413967.66 |  |  | 1422563.29 | 507300 | 915263.29 | 2020-12-28 11:30 | 2023-03-31 | 2021-12-01 | 2023-02-08
75086 | G7REG026 | AW3355 | AW3355 - REG 0437 UPHILL & HIGHWAY - LAND | 8265.25 |  | 8265.25 |  |  | 8265.25 | 82500 | -74234.75 | 2021-01-13 10:41 | 2023-03-31 | 2022-03-01 | 2023-02-08
75086 | G7REG0359 | AW4715 | AW4715 - REG 0359 - TAYLOR MILL RD N - RS UP | 64751.09 |  | 64751.09 |  |  | 64751.09 | 37100 | 27651.09 | 2021-10-28 10:14 | 2023-03-30 | 2022-01-01 | 2023-02-18
75086 | G7REG045 | AW3228 | AW3228 - REG 0432 TENTH & BRIGHTON | 323759.84 |  | 323759.84 |  |  | 329411.77 | 660800 | -331388.23 | 2020-12-30 16:28 | 2021-03-31 | 2021-11-01 | 2023-07-11
75086 | G7REG045 | AW3356 | AW3356 - CANCEL- REG0432 TENTH-BRIGHTON LAND | 8486.63 |  | 8486.63 |  |  | 8503.25 | 82500 | -73996.75 | 2021-01-13 10:52 | 2023-03-31 | 2021-09-01
75086 | G7REG049 | AW3290 | AW3290 - REG 0049 PEARL AND TWENTIETH REPAIR | -737.56 |  | -737.56 |  |  | 24384.51 | 58000 | -33615.49 | 2021-01-06 14:56 | 2022-03-31 | 2021-06-01 | 2021-10-24
75086 | G7REG051 | AW3919 | AW3919 - REG 0051 WALNUT AND ELECTRIC REPAIR | -214.76 |  | -214.76 |  |  | 30833.21 | 175200 | -144366.79 | 2021-05-25 08:51 | 2022-03-31 | 2021-08-01 | 2021-11-23
75086 | G7REG055 | AW3288 | AW3288 - REG 0055 WRIGHT AND SPRING REPAIR | -1280 |  | -1280 |  |  | 11658.06 | 56400 | -44741.94 | 2021-01-06 14:20 | 2022-03-31 | 2021-07-01 | 2021-10-23
75086 | G7REG057 | AW3180 | AW3180 - REG 0431 SARATOGA & ELEVENTH | 461542.11 |  | 461542.11 |  |  | 470207.47 | 796400 | -326192.53 | 2020-12-28 10:43 | 2023-03-31 | 2021-11-01 | 2023-11-08
75086 | G7REG057 | AW3354 | AW3354 - CANCEL-REG431 SARATOGA-ELEVENTH ROW | 8091.69 |  | 8091.69 |  |  | 8102.63 | 82500 | -74397.37 | 2021-01-13 10:19 | 2023-03-31 | 2021-06-01
75086 | G7REG059 | AW3177 | AW3177 - REG 0059 HIGHLAND AND GRAND RS REPL | 2520149.93 |  | 2520149.93 |  |  | 2771496.74 | 746000 | 2025496.74 | 2020-12-28 10:15 | 2022-09-30 | 2021-06-01 | 2023-02-09
75086 | G7REG059 | AW3353 | AW3353 - REG 0059 HIGHLAND AND GRAND LAND | 81026.57 |  | 81026.57 |  |  | 87897.05 | 82500 | 5397.05 | 2021-01-13 10:02 | 2022-09-30 | 2021-04-01 | 2023-02-09
75086 | G7REG074 | AW4985 | AW4985 - REG 0074 - MCALPIN N OF HOPE - RELI | 808517.34 |  | 808517.34 |  |  | 808517.34 | 135940 | 672577.34 | 2022-03-01 12:43 | 2022-08-31 | 2022-05-01 | 2022-10-07
75086 | G7REG074 | MXA751466 | MXA751466 - CANCEL - REG 0074 - MCALPIN N - R | 13054.22 |  | 13054.22 |  |  | 13054.22 | 9701.94 | 3352.28 | 2022-06-21 14:01 | 2022-09-20 | 2022-06-01
75086 | G7REG093 | AW3284 | AW3284 - REG 0093 ALEXANDRIA AND BLOSSUM REP | -409.6 |  | -409.6 |  |  | 34892.01 | 61000 | -26107.99 | 2021-01-06 13:22 | 2022-03-31 | 2021-07-01 | 2021-11-20
75086 | G7REG095 | AW3283 | AW3283 - REG 0095 BAUM AND BURNET | -322.61 |  | -322.61 |  |  | 36270.07 | 402900 | -366629.93 | 2021-01-06 13:08 | 2022-03-31 | 2021-08-01 | 2021-11-20
75086 | G7REG684 | MX9167642 | MX9167642 - (CANCEL) REG0684-SHAW BLVD-REG UPG | -46.06 |  | -46.06 |  |  | 0 | 51953.52 | -51953.52 | 2021-01-08 14:01 | 2021-04-29 | 2021-02-01
75086 | G7REG74K | AW3285 | AW3285 - REG 0074 MCALPIN N OF HOPE LN REPAI | -1718.36 |  | -1718.36 |  |  | 38785.61 | 54100 | -15314.39 | 2021-01-06 13:36 | 2022-03-31 | 2021-07-01 | 2021-12-24
75086 | G7REPL | 28051 | 28051 - SMALL REPL KY | 274502.17 |  | 274502.17 |  |  | 1603730.05 | 0 | 1603730.05 | 2000-04-13 | 2050-12-31 | 1999-12-01
75086 | G7REPL | AW6197 | AW6197 - CANCEL- ROW SCHOOL RD - WALTON | 1959.01 |  | 1959.01 |  |  | 1959.01 | 25000 | -23040.99 | 2022-10-06 09:08 | 2023-06-17 | 2022-11-01
75086 | G7REPL | MX1379992 | MX1379992 - WEST 13TH ST RPL PROJECT, NEWPORT, | 325079.21 |  | 325079.21 |  |  | 338902.89 | 44018.51 | 294884.38 | 2021-09-13 10:02 | 2024-04-15 | 2021-09-01 | 2022-09-28
75086 | G7REPL | MX2163251 | MX2163251 - CANCEL HIGHLAND AVE WOODLAND PL | -7132.91 |  | -7132.91 |  |  | -5.03 | 24723.49 | -24728.52 | 2021-09-30 14:01 | 2022-05-12 | 2021-10-01
75086 | G7REPL | MX3269023 | MX3269023 - KYTC - HANDS PIKE - EDGEWOOD - 4" P | 281941.23 |  | 281941.23 |  |  | 281941.23 | 12423.85 | 269517.38 | 2022-06-27 18:01 | 2024-12-31 | 2022-07-01 | 2022-11-18
75086 | G7REPL | MX4962663 | MX4962663 - ALEXANDRIA PK - ALEXANDRIA- 8" SIZE | 155144.8 |  | 155144.8 |  |  | 155144.8 | 93664.48 | 61480.32 | 2022-08-10 14:02 | 2023-05-11 | 2022-08-01 | 2023-05-03
75086 | G7REPL | MX6343996 | MX6343996 - 182 MT ZION - FLORENCE - 8" PL - RP | 1024.68 |  | 1024.68 |  |  | 1024.68 | 6094.67 | -5069.99 | 2022-10-04 18:01 | 2022-10-25 | 2022-10-01 | 2022-10-27
75086 | G7REPL | MX9545566 | MX9545566 - RICHWOOD RD REPLACEMENT PROJ KY-338 | 871483.71 |  | 871483.71 |  |  | 1712526.76 | 1413710 | 298816.76 | 2019-11-12 10:01 | 2022-06-14 | 2020-01-01 | 2022-03-01
75086 | G7REPL | MX9817206 | MX9817206 - DUVENECK SQUARE RPL/MAE - COVINGTON | 33185.06 |  | 33185.06 |  |  | 416296.81 | 101691.72 | 314605.09 | 2021-04-08 10:02 | 2024-10-01 | 2021-05-01 | 2021-12-14
75086 | G7RGPI | MX9217475 | MX9217475 - GARVEY AVE. PRI, ELSMERE, 9400' 8" | 726984.45 |  | 726984.45 |  |  | 1475241.72 | 507691.08 | 967550.64 | 2021-08-16 18:02 | 2022-12-01 | 2021-09-01 | 2022-11-21
75086 | G7RRPI | MX9219249 | MX9219249 - RICHARDSON RD PRESSURE IMP 7300' OF | 32276.54 |  | 32276.54 |  |  | 32276.54 | 765.33 | 31511.21 | 2022-10-21 18:01 | 2026-03-12 | 2022-11-01
75086 | G7SERVMC | CMRP70 | CMRP70 - REPLACE C-M PLASTIC 2 INCH AND UNDE | 332943.36 |  | 332943.36 |  |  | 12980195.05 | 0 | 12980195.05 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | CMRS70 - 2" OR LESS STEEL C-M REPLACE | 1.6 |  | 1.6 |  |  | 10360.71 | 1000000 | -989639.29 | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVMC | LCMRP70 | LCMRP70 - GREATER THAN 2" C-M REPL PLASTIC | 34402.49 |  | 34402.49 |  |  | 75541.51 | 2500000 | -2424458.49 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | LMCRP70 - GREATER THAN 2" M-C REPL PLASTIC | 226090.88 |  | 226090.88 |  |  | 538283.3 | 2500000 | -1961716.7 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | LMCRS70 - GREATER THAN 2" M-C REPL STEEL | 6253.57 |  | 6253.57 |  |  | 16294.83 | 1000000 | -983705.17 | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | G7SERVMC | MCRP70 | MCRP70 - REPLACE (NON-AMRP) M-C PLASTIC 2 IN | 2668488.18 |  | 2668488.18 |  |  | 22032553.99 | 0 | 22032553.99 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | MCRS70 - REPLACE M-C STEEL 2 INCH AND UNDER | 40999.63 |  | 40999.63 |  |  | 591769.6 | 0 | 591769.6 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | CMNEWP70 | CMNEWP70 - NEW C-M PLASTIC 2 INCH AND UNDER KY | 252452.75 |  | 252452.75 |  |  | 8177009.4 | 1 | 8177008.4 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | LCMNEWP70 | LCMNEWP70 - GREATER THAN 2" C-M PLASTIC | 9679.73 |  | 9679.73 |  |  | 243812.88 | 2500000 | -2256187.12 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVNEW | LMCNEWP70 | LMCNEWP70 - GREATER THAN 2" M-C PLASTIC | 67130.76 |  | 67130.76 |  |  | 547641.85 | 2500000 | -1952358.15 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | LMCNEWS70 - GREATER THAN 2" M-C STEEL | 921.41 |  | 921.41 |  |  | 110137.85 | 2500000 | -2389862.15 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVNEW | MCNEWP70 | MCNEWP70 - NEW M-C PLASTIC 2 INCH AND UNDER KY | 2736164.62 |  | 2736164.62 |  |  | 20565243.37 | 1 | 20565242.37 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | MCNEWS70 - NEW M-C STEEL 2 INCH AND UNDER KY | 18026.77 |  | 18026.77 |  |  | 267930.23 | 1 | 267929.23 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SERVNEW | MX7824128 | MX7824128 - NEW COM; 7500 TURFWAY RD; TURFWAY P | 20611.11 |  | 20611.11 |  |  | 20611.11 | 70174.38 | -49563.27 | 2020-12-16 18:02 | 2022-06-30 | 2022-01-01 | 2022-05-29
75086 | G7STA011 | AW3227 | AW3227 - STA 0949 DAYTON VALVE HOUSE | 1046727.16 |  | 1046727.16 |  |  | 1080240.01 | 1062400 | 17840.01 | 2020-12-30 16:17 | 2025-10-30 | 2021-11-01
75086 | G7STA011 | AW3250 | AW3250 - STA 0949 DAYTON VALVE HOUSE LAND | 26088.92 |  | 26088.92 |  |  | 26108.32 | 82500 | -56391.68 | 2021-01-02 14:55 | 2025-11-29 | 2021-06-01
75086 | G7STA014 | AW3251 | AW3251 - CANCEL_STA 0014 EAST ALEXANDRIAPIKE | 69.91 |  | 69.91 |  |  | 76.77 | 82500 | -82423.23 | 2021-01-03 09:43 | 2023-03-31 | 2021-06-01
75086 | G7STA034 | AW3313 | AW3313 - STA 0034 WILDERS PLANT REPAIR | -1163.7 |  | -1163.7 |  |  | 40155.96 | 76500 | -36344.04 | 2021-01-07 12:19 | 2022-03-31 | 2021-07-01 | 2021-11-02
75086 | G7STA0375 | AW3193 | AW3193 - STA 0375 ELECTRIC AVE RS REPLACEMEN | 882935.31 |  | 882935.31 |  |  | 2263285.57 | 829000 | 1434285.57 | 2020-12-28 13:59 | 2022-04-22 | 2021-05-01 | 2022-05-09
75086 | G7STA0375 | AW3691 | AW3691 - STA 00375 LAND ELECTRIC | -1845.16 |  | -1845.16 |  |  | 232073.21 | 82500 | 149573.21 | 2021-02-27 09:31 | 2022-02-28 | 2021-04-01 | 2021-11-27
75086 | G7STA056 | AW3310 | AW3310 - STA 0056 BURLINGTON PIKE REPAIR | -1280 |  | -1280 |  |  | 26039.37 | 56400 | -30360.63 | 2021-01-07 11:42 | 2022-03-31 | 2021-08-01 | 2021-11-23
75086 | G7STA064 | AW3217 | AW3217 - STA 0940 GLECOE TB | 375631.9 |  | 375631.9 |  |  | 394949.37 | 510900 | -115950.63 | 2020-12-30 13:22 | 2021-03-31 | 2021-11-01 | 2023-09-27
75086 | G7STA064 | AW3268 | AW3268 - STA 0940 STA GLENCOE TB LAND | 7148.73 |  | 7148.73 |  |  | 7166.87 | 82500 | -75333.13 | 2021-01-05 14:36 | 2023-03-31 | 2021-08-01 | 2023-09-27
75086 | G7STA072 | AW3308 | AW3308 - STA 0072 TENTH AND BRIGHTON REPAIR | -886.5 |  | -886.5 |  |  | 20900.82 | 58000 | -37099.18 | 2021-01-07 11:18 | 2022-03-31 | 2021-06-01 | 2021-10-22
75086 | G7STA074 | AW3307 | AW3307 - STA 0074 LOUIS B NUNN REPAIR | -1296.08 |  | -1296.08 |  |  | 31027.3 | 59300 | -28272.7 | 2021-01-07 11:09 | 2022-03-31 | 2021-06-01 | 2021-11-21
75086 | G7STA0836 | AW3191 | AW3191 - STA 0838 ROSSFORD AVE RS REPLACEMEN | 1298420.8 |  | 1298420.8 |  |  | 2665887.23 | 539500 | 2126387.23 | 2020-12-28 13:11 | 2022-04-30 | 2021-05-01 | 2022-05-22
75086 | G7STA0836 | AW3686 | AW3686 - STA 0836 - LAND ROSSFORD AVE | 203.13 |  | 203.13 |  |  | 54384.34 | 82500 | -28115.66 | 2021-02-26 22:00 | 2022-02-28 | 2021-04-01 | 2021-11-27
75086 | G7STA100 | AW3306 | AW3306 - STA 0100 CHESAPEAKE AND KYLE REPAIR | -1280 |  | -1280 |  |  | 31647.64 | 106700 | -75052.36 | 2021-01-07 10:58 | 2022-03-31 | 2021-08-01 | 2022-01-13
75086 | G7STA117 | AW3305 | AW3305 - STA 0117 AMSTERDAM AND REDWOOD REPA | -1280 |  | -1280 |  |  | 22325.73 | 56400 | -34074.27 | 2021-01-07 10:45 | 2022-03-31 | 2021-07-01 | 2021-10-27
75086 | G7STA276 | AW3212 | AW3212 - STA 0276 MARY INGLES HWY RS ABANDON | 62339.66 |  | 62339.66 |  |  | 88128.21 | 553900 | -465771.79 | 2020-12-30 11:32 | 2021-03-31 | 2021-11-01 | 2022-11-18
75086 | G7STA276 | AW3689 | AW3689 - CANCEL-STA 0276 MARY IGLES HWY LAND | 1143.7 |  | 1143.7 |  |  | 3432.19 | 82500 | -79067.81 | 2021-02-26 23:34 | 2023-03-31 | 2021-06-01
75086 | G7STA280 | AW3213 | AW3213 - STA 0938 TAYLOR MILL & LONE OAK | 642139.29 |  | 642139.29 |  |  | 652476.55 | 562000 | 90476.55 | 2020-12-30 11:55 | 2023-09-30 | 2021-11-01 | 2023-09-08
75086 | G7STA280 | AW3272 | AW3272 - STA0938 TAYLOR MILL & LONE OAK LAND | 135157.21 |  | 135157.21 |  |  | 139786.78 | 82500 | 57286.78 | 2021-01-05 15:40 | 2023-03-31 | 2021-08-01 | 2023-09-08
75086 | G7STA286 | AW3216 | AW3216 - STA 0929 RILEY RD | 2024439.35 |  | 2024439.35 |  |  | 2092031.23 | 635200 | 1456831.23 | 2020-12-30 13:11 | 2021-03-31 | 2021-09-01 | 2023-06-28
75086 | G7STA286 | AW3271 | AW3271 - STA 0929 RILEY RD LAND | 81699.7 |  | 81699.7 |  |  | 81717.57 | 82500 | -782.43 | 2021-01-05 15:21 | 2023-03-31 | 2021-06-01 | 2023-06-28
75086 | G7STA338 | AW3192 | AW3192 - STA 0941 GUBSER MILL | 309820.8 |  | 309820.8 |  |  | 417598.43 | 538800 | -121201.57 | 2020-12-28 13:44 | 2025-12-30 | 2021-09-01
75086 | G7STA338 | AW3690 | AW3690 - STA 0941 GUBSER MILL LAND | 34438.09 |  | 34438.09 |  |  | 37601.48 | 82500 | -44898.52 | 2021-02-27 08:54 | 2025-10-25 | 2021-06-01
75086 | G7STA444 | AW3186 | AW3186 - STA 0948 THIRD & CRESCENT | 536803.16 |  | 536803.16 |  |  | 568877.9 | 948400 | -379522.1 | 2020-12-28 11:59 | 2025-11-27 | 2021-11-01
75086 | G7STA444 | AW3230 | AW3230 - STA 0948 THIRD & CRESCENT LAND | 18246.56 |  | 18246.56 |  |  | 18248.85 | 82500 | -64251.15 | 2020-12-31 08:30 | 2025-11-27 | 2021-08-01
75086 | G7STA535 | AW3299 | AW3299 - STA 0535 DRY RIDGE EAST REPAIR | 34778.73 |  | 34778.73 |  |  | 64527.58 | 56400 | 8127.58 | 2021-01-07 09:12 | 2022-08-31 | 2021-06-01 | 2022-12-02
75086 | G7STA750 | AW3296 | AW3296 - STA 0750 TURFWAY STATION REPAIR | 2110.55 |  | 2110.55 |  |  | 19759.92 | 112700 | -92940.08 | 2021-01-07 08:29 | 2022-03-31 | 2021-07-01 | 2021-11-19
75086 | G7STA793 | AW3188 | AW3188 - STA 0942 CAMP ERNST RD | 690170.94 |  | 690170.94 |  |  | 699709.1 | 887300 | -187590.9 | 2020-12-28 12:16 | 2023-09-30 | 2021-11-01 | 2024-01-18
75086 | G7STA793 | AW3767 | AW3767 - STA 0942 CAMP ERNST RD LAND | 64979.84 |  | 64979.84 |  |  | 66938.9 | 82500 | -15561.1 | 2021-03-16 18:53 | 2023-03-31 | 2021-06-01 | 2024-01-18
75086 | G7STA822 | AW3189 | AW3189 - STA 0822 COX RD RS REPAIR | 198466.71 |  | 198466.71 |  |  | 252980.55 | 541600 | -288619.45 | 2020-12-28 12:29 | 2022-12-31 | 2021-11-01 | 2022-11-18
75086 | G7STA822 | AW3685 | AW3685 - CANCEL 0822 - COX RD. RS REP - LAND | 2281.07 |  | 2281.07 |  |  | 4516.03 | 82500 | -77983.97 | 2021-02-26 18:47 | 2022-12-31 | 2021-06-01
75086 | G7STA876 | MX6800938 | MX6800938 - STA 876 WARSAW TOWN BORDER- STATION | 190594.09 |  | 190594.09 |  |  | 336829.81 | 252984 | 83845.81 | 2018-01-10 18:02 | 2022-09-30 | 2018-01-01 | 2023-09-29
75086 | G7TAM00B | AW2146 | AW2146 - LINE AM00B RETROFIT REPL | 13074131.76 |  | 13074131.76 |  |  | 14817784.27 | 6528636 | 8289148.27 | 2020-05-19 16:54 | 2022-10-15 | 2020-05-01 | 2022-09-17
75086 | G7TAM00B | AW3634 | AW3634 - LINE AM00B ILI RETROFIT-LAND | 365736.8 |  | 365736.8 |  |  | 402216.99 | 127500 | 274716.99 | 2021-02-17 09:27 | 2022-10-15 | 2021-10-01 | 2022-09-17
75086 | G7TOOLS | 28073 | 28073 - PURCHASE GAS TOOLS BLANKET | 239348.17 |  | 239348.17 |  |  | 1080778.35 | 0 | 1080778.35 | 2000-04-13 | 2015-12-31 | 1999-12-01
75086 | G7TOOLS | AW4691 | AW4691 - CGI UPGRADE KENTUCKY | 282563.9 |  | 282563.9 |  |  | 335694.13 | 120000 | 215694.13 | 2021-10-22 07:34 | 2022-06-30 | 2021-12-01
75086 | G7TUL06 | AW1592 | AW1592 - LINE UL06 - PIPELINE REPLACEMENTS | 98375.52 |  | 98375.52 |  |  | 9779331.08 | 10253358 | -474026.92 | 2020-01-05 02:41 | 2021-12-30 | 2020-02-01 | 2021-12-03
75086 | G7TUL06 | AW2021 | AW2021 - LINE UL06 - PIPELINE REPLACEMENTS L | 20320.5 |  | 20320.5 |  |  | 121670.17 | 115000 | 6670.17 | 2020-04-13 10:21 | 2021-12-31 | 2020-07-01 | 2021-12-03
75086 | G7UL02PH1 | V8191 | V8191 - UL60 PIPELINE PHASE 1 (PIPE) | 19280.84 |  | 19280.84 |  |  | 38635900.86 | 26326195 | 12309705.86 | 2019-01-23 15:21 | 2021-03-30 | 2019-01-01 | 2021-02-25
75086 | G7UL02PH2 | AW3877 | AW3877 - UL60 PIPELINE PHASE II - STATION | 4626921.51 |  | 4626921.51 |  |  | 4710665.8 | 1004152 | 3706513.8 | 2021-04-29 15:15 | 2022-03-30 | 2021-05-01 | 2021-11-18
75086 | G7UL02PH2 | V9444 | V9444 - UL60 PIPELINE PHASE II - PIPE | -4473543.44 |  | -4473543.44 |  |  | 20945431.22 | 22514005 | -1568573.78 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01 | 2021-11-18
75086 | G7UL02PH2 | V9445 | V9445 - UL60 PIPELINE PHASE II- LAND RIGHTS | 46060.22 |  | 46060.22 |  |  | 2552669.36 | 733000 | 1819669.36 | 2019-06-12 08:04 | 2022-02-02 | 2019-07-01 | 2021-11-18
75086 | G7UL57 | AW4824 | AW4824 - STA0917 UL61 CHAMBERS RD TO DIXIE | 473228.03 |  | 473228.03 |  |  | 473228.03 | 873000 | -399771.97 | 2021-12-09 11:26 | 2024-01-31 | 2022-02-01 | 2023-12-26
75086 | G7UL57 | AW4840 | AW4840 - UL61 CHAMBERS RD TO DIXIE HWY- LAND | 101413.96 |  | 101413.96 |  |  | 101413.96 | 82500 | 18913.96 | 2021-12-14 11:10 | 2023-01-31 | 2022-02-01 | 2023-12-26
75086 | G7WOODINT | AW3137 | AW3137 - DUKE WOODSDALE INTERCONNECT (KY) | -11723.27 |  | -11723.27 |  |  | 197098.24 | 2000000 | -1802901.76 | 2020-12-18 12:10 | 2021-12-31 | 2021-01-01 | 2022-01-31
75086 | MRTP2021 | 400052004 | 400052004 - DEK - TB5800 TEST SETS | 30018.07 |  | 30018.07 |  |  | 33933.46 | 26866 | 7067.46 | 2022-09-26 15:24 | 2022-02-17 | 2022-10-01 | 2022-04-30
75086 | SG000723F | SG723SW | SG723SW - DEE AMI OPERATIONS TOOL | 3705.99 |  | 3705.99 |  |  | 32523.56 | 26599 | 5924.56 | 2020-03-03 09:59 | 2022-07-30 | 2020-03-01 | 2022-07-31
75086 | SG000781F | SG781SW | SG781SW - SG DEE PPM PIMS PHASE 2 BUILD OUT | 267.58 |  | 267.58 |  |  | 78203.29 | 76873.76 | 1329.53 | 2018-07-12 09:17 | 2021-03-31 | 2018-07-01 | 2022-03-31
75086 | SG001117F | SG001117 | SG001117 - DEE LMR CONSOLES | 6364.26 |  | 6364.26 |  |  | 99093.23 | 124921 | -25827.77 | 2021-08-25 20:43 | 2023-03-31 | 2021-10-01 | 2022-11-30
75087 | CUSTCONN | 315986A | 315986A - CUSTOMER CONNECT - CORE | 1035806.651 |  | 1035806.651 |  |  | 4619692.461 | 2325960.3 | 2293732.161 | 2017-08-10 10:55 | 2022-12-05 | 2017-08-01 | 2022-07-06
75087 | CUSTCONN | 315986F | 315986F - CUSTOMER CONNECT- R6-8 SCOPE | 189686.16 |  | 189686.16 |  |  | 461854.53 | 53917 | 407937.53 | 2021-03-30 10:49 | 2022-06-30 | 2021-04-01 | 2022-07-06
75087 | CUSTCONN | 315986HW7 | 315986HW7 - CUSTOMER CONNECT - HARDWARE PROJ 5 | 8.04 |  | 8.04 |  |  | 28436.05 | 62454 | -34017.95 | 2021-04-21 14:12 | 2021-12-31 | 2021-04-01 | 2021-12-31
75087 | CUSTCONN | 315986HW8 | 315986HW8 - CUSTOMER CONNECT- HARDWARE PROJ 6 | 17400.72 |  | 17400.72 |  |  | 37341.41 | 67100 | -29758.59 | 2021-09-27 15:20 | 2022-06-30 | 2021-10-01 | 2022-09-15
75087 | CUSTCONN | 400109 | 400109 - CUST ENHANCEMENT AND OPTIMIZATION | 130568.41 |  | 130568.41 |  |  | 130568.41 | 480680 | -350111.59 | 2022-06-20 14:30 | 2024-01-19 | 2022-07-01 | 2024-01-26
75087 | FPIT | 307482002 | 307482002 - CUSTOMER MOBILE APP - PHASE 3 | -0.18 |  | -0.18 |  |  | 3105.67 | 26324 | -23218.33 | 2019-12-19 13:54 | 2022-03-15 | 2020-01-01 | 2022-03-31
75087 | FPIT | 307482003 | 307482003 - CUSTOMER MOBILE APP - PHASE 4 | 163856.16 |  | 163856.16 |  |  | 163856.16 | 24891 | 138965.16 | 2021-12-30 10:36 | 2023-03-31 | 2022-01-01 | 2023-03-31
75087 | FPIT | 307482SW2 | 307482SW2 - CUSTOMER MOBILE APP - PHASE 3 | 198.2 |  | 198.2 |  |  | 30440.03 | 30258 | 182.03 | 2020-04-13 09:32 | 2022-03-15 | 2020-04-01 | 2022-03-31
75087 | FPIT | 400055002 | 400055002 - CHATBOT CHANNELS | 5.31 |  | 5.31 |  |  | 17984.3 | 6219 | 11765.3 | 2020-12-08 09:37 | 2022-03-31 | 2021-01-01 | 2022-03-31
75087 | FPIT | 400055004 | 400055004 - INSPECTION PORTAL 2021 | 9470.8 |  | 9470.8 |  |  | 9470.8 | 10727 | -1256.2 | 2020-12-16 18:31 | 2023-07-03 | 2022-01-01 | 2023-07-31
75087 | FPIT | 400055005 | 400055005 - BUILDER PORTAL 2021 | 5608.8 |  | 5608.8 |  |  | 12305.64 | 17824 | -5518.36 | 2020-12-10 18:21 | 2023-09-30 | 2021-01-01 | 2023-09-30
75087 | FPIT | 400055008 | 400055008 - PNG - CRT | -901.5 |  | -901.5 |  |  | 0 | 11377 | -11377 | 2021-04-30 16:58 | 2022-02-28 | 2021-05-01 | 2022-03-31
75087 | FPIT | 400055009 | 400055009 - CALL CENTER ANALYTICS SW | 28416.34 |  | 28416.34 |  |  | 85596.83 | 5888 | 79708.83 | 2021-05-26 09:23 | 2022-09-30 | 2021-06-01 | 2022-09-30
75087 | FPIT | 400055010 | 400055010 - DIGITAL ASSISTANT PLATFORM PH 1 | 245.59 |  | 245.59 |  |  | 1691.36 | 6670 | -4978.64 | 2021-07-26 15:04 | 2022-03-15 | 2021-10-01 | 2022-03-31
75087 | FPIT | 400055015 | 400055015 - ATLANTIS (CUSTOMER ANALYTICS ENGINE | 12836.79 |  | 12836.79 |  |  | 12836.79 | 22832 | -9995.21 | 2021-12-29 10:35 | 2023-12-30 | 2022-01-01 | 2024-01-01
75087 | FPIT | 400055016 | 400055016 - TITAN (VOICE OF THE CUSTOMER ENGAGE | 12858.73 |  | 12858.73 |  |  | 12858.73 | 11104 | 1754.73 | 2021-12-20 13:25 | 2023-10-31 | 2022-01-01 | 2023-10-31
75087 | FPIT | 400055017 | 400055017 - DIGITAL ASSISTANT PLATFORM 2022 ENH | 22119.69 |  | 22119.69 |  |  | 22119.69 | 15150 | 6969.69 | 2021-12-20 10:25 | 2023-06-30 | 2022-01-01 | 2023-07-04
75087 | FPIT | 400055020 | 400055020 - SHORT URL MANAGEMENT APP | 15942.44 |  | 15942.44 |  |  | 15942.44 | 7433 | 8509.44 | 2022-03-08 08:51 | 2023-01-15 | 2022-03-01 | 2022-11-15
75087 | FPIT | 400055022 | 400055022 - BUSINESS OUTBOUND NOTIFICATION PLAT | 19.26 |  | 19.26 |  |  | 19.26 | 5949 | -5929.74 | 2022-05-19 11:29 | 2023-03-31 | 2022-10-01 | 2023-03-31
75087 | FPIT | CC1900001 | CC1900001 - CUSTOMER ANALYTICS ENGINE | 677.34 |  | 677.34 |  |  | 36105.62 | 26306 | 9799.62 | 2020-01-27 08:12 | 2022-03-31 | 2020-02-01 | 2022-03-31
75087 | FPIT | CC2000003 | CC2000003 - SITECORE JSS FRONT END MODERNIZATIO | 3912.43 |  | 3912.43 |  |  | 34322.77 | 28721 | 5601.77 | 2020-06-25 21:36 | 2022-05-30 | 2020-08-01 | 2022-05-31
75087 | FPIT | CO2200002 | CO2200002 - UTILITY ASSISTANCE MODERN ARCHITECT | 850.82 |  | 850.82 |  |  | 850.82 | 3296 | -2445.18 | 2022-06-30 10:34 | 2022-12-29 | 2022-07-01 | 2023-03-15
75087 | FPIT | CS1900001 | CS1900001 - VOICE OF THE CUSTOMER ENGAGEMENT PL | 35.01 |  | 35.01 |  |  | 31531.44 | 13742 | 17789.44 | 2020-01-29 16:09 | 2022-03-31 | 2020-02-01 | 2022-03-31
75087 | FPIT | CS2100008 | CS2100008 - NUANCE IVR ENHANCEMENTS | 730.81 |  | 730.81 |  |  | 3467.84 | 4174 | -706.16 | 2021-07-16 11:40 | 2022-08-31 | 2021-08-01 | 2022-08-31
75087 | FPIT | CS2100010 | CS2100010 - CONTACT CENTER WORK FROM HOME | 1139.59 |  | 1139.59 |  |  | 1139.59 | 4849 | -3709.41 | 2022-01-26 14:25 | 2022-11-28 | 2022-02-01 | 2023-01-06
75087 | FPIT | CS2200002 | CS2200002 - IVR ENHANCEMENTS 2022 | 3755.49 |  | 3755.49 |  |  | 3755.49 | 20162 | -16406.51 | 2022-05-05 13:03 | 2023-05-01 | 2022-05-01 | 2023-04-30
75087 | FPIT | CS2200005 | CS2200005 - UPLAND RIGHT ANSWER LICENSE PURCHAS | 12189.54 |  | 12189.54 |  |  | 12189.54 | 7962 | 4227.54 | 2022-08-03 15:29 | 2023-01-29 | 2022-12-01 | 2023-05-31
75087 | FPIT | CS2200006 | CS2200006 - VERINT UPGRADE | 54953.23 |  | 54953.23 |  |  | 54953.23 | 80257 | -25303.77 | 2022-11-04 16:13 | 2024-03-31 | 2022-11-01 | 2024-03-31
75087 | FPIT | CS2200007 | CS2200007 - FND LICENSES ADDITIONAL ENDPOINTS | 7827.53 |  | 7827.53 |  |  | 7827.53 | 7591 | 236.53 | 2022-11-01 10:57 | 2023-03-30 | 2022-12-01 | 2023-03-22
75087 | FPIT | CS2200008 | CS2200008 - AVAYA PLATFORM UPGRADE - SERVER | 14516.54 |  | 14516.54 |  |  | 14516.54 | 44473 | -29956.46 | 2022-11-14 12:16 | 2024-03-31 | 2022-11-01 | 2024-03-31
75087 | FPIT | CS220SW04 | CS220SW04 - OPENWAY ENDPOINT SOFTWARE LICENSES | 2016.14 |  | 2016.14 |  |  | 2016.14 | 2056 | -39.86 | 2022-09-07 09:51 | 2023-03-31 | 2022-10-01 | 2023-01-10
75087 | FPIT | LTHCESCS | LTHCESCS - WO OPTIMIZATION WORK INPUT/CALL-SW | 121.41 |  | 121.41 |  |  | 4910.55 | 13750 | -8839.45 | 2021-02-25 18:47 | 2022-03-31 | 2021-02-01 | 2021-03-31
75088 | CY1900015 | 349395006 | 349395006 - ITOT OT SIEM PHASE 2 HW WORKSTREAM | 2754.77 |  | 2754.77 |  |  | 54262.5 | 5497 | 48765.5 | 2020-04-13 16:35 | 2022-10-28 | 2020-05-01
75088 | CY1900015 | 349395SW6 | 349395SW6 - ITOT OT SIEM SW WORKSTREAM | 829.08 |  | 829.08 |  |  | 75187.42 | 6089 | 69098.42 | 2021-12-09 13:04 | 2022-10-28 | 2021-12-01
75088 | CY1900015 | CY190HW15 | CY190HW15 - IT-OT ANA WORKSTREAM HW | -15649.7 |  | -15649.7 |  |  | 0 | 113909 | -113909 | 2019-12-11 08:05 | 2022-10-28 | 2020-01-01
75088 | CY1900015 | CY190SW15 | CY190SW15 - IT-OT ANA WORKSTREAM SW | -201.35 |  | -201.35 |  |  | 0 | 10808 | -10808 | 2019-12-11 07:56 | 2022-10-28 | 2021-03-01
75088 | FPITKG | TC210HW57 | TC210HW57 - CIOPS NERC CIP CYBERARK HW | 285.75 |  | 285.75 |  |  | 285.75 | 304 | -18.25 | 2021-12-10 15:18 | 2024-09-30 | 2022-01-01
75088 | FPITKG | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | 1768.36 |  | 1768.36 |  |  | 1768.36 | 3357 | -1588.64 | 2021-12-10 14:08 | 2024-03-31 | 2022-02-01 | 2023-12-01
75088 | MRTP2021 | 400052004 | 400052004 - DEK - TB5800 TEST SETS | -3915.39 |  | -3915.39 |  |  | 0 | 26866 | -26866 | 2021-09-17 10:42 | 2022-02-17 | 2021-12-01
|  |  |  | 74578385.596 | 69331819.6465 | 5246565.9495 | 7.035%

## 2023
Duke Energy Kentucky Natural Gas
Year 2023
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | 4000156F | 04000156 | 04000156 - DEE EAM NEXTGEN GIS | 166841.84 |  | 166841.84 |  |  | 166841.84 | 599758 | -432916.16 | 2022-12-17 12:31 | 2026-12-31 | 2023-01-01
75086 | EAMHPBU | 349472018 | 349472018 - EAM 2022 MAXIMO DURABLE TEAM | 19867.69 |  | 19867.69 |  |  | 30639.55 | 6760 | 23879.55 | 2022-01-04 15:44 | 2023-05-30 | 2022-01-01 | 2023-07-17
75086 | EAMHPBU | 349472022 | 349472022 - NEW BOUD SERVERS | 490.2 |  | 490.2 |  |  | 490.2 | 83 | 407.2 | 2022-05-20 14:32 | 2023-03-31 | 2023-04-01 | 2022-10-30
75086 | FMDT2020 | MDTGAS20 | MDTGAS20 - INSTALL WIN 7 PANASONIC TOUGHBOOKS | 47122.26 |  | 47122.26 |  |  | 581535.75 | 403995 | 177540.75 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01 | 2021-03-31
75086 | FPIT | 349395006 | 349395006 - ITOT OT SIEM PHASE 2 HW WORKSTREAM | 46331.31 |  | 46331.31 |  |  | 100593.81 | 5497 | 95096.81 | 2023-03-27 14:03 | 2022-10-28 | 2023-03-01 | 2022-10-18
75086 | FPIT | 349395SW6 | 349395SW6 - ITOT OT SIEM SW WORKSTREAM | 74299.24 |  | 74299.24 |  |  | 149486.66 | 6089 | 143397.66 | 2023-03-27 14:47 | 2022-10-28 | 2023-03-01 | 2022-10-18
75086 | FPIT | 349472020 | 349472020 - SLATE - EAM WORK MGMT SCHEDULING TO | 33055.61 |  | 33055.61 |  |  | 45575.07 | 22340 | 23235.07 | 2022-03-18 16:15 | 2024-06-30 | 2022-03-01 | 2024-06-30
75086 | FPIT | 349472021 | 349472021 - FMA ENHANCEMENTS | 6385.43 |  | 6385.43 |  |  | 9379.53 | 4713 | 4666.53 | 2022-05-18 12:26 | 2026-03-31 | 2022-06-01
75086 | FPIT | 349472023 | 349472023 - SMALLWORLD ENHANCEMENTS | 21423.54 |  | 21423.54 |  |  | 22331.08 | 15341 | 6990.08 | 2022-09-29 18:21 | 2025-03-30 | 2022-11-01 | 2024-03-31
75086 | FPIT | 349472024 | 349472024 - NEW PRIMAVERA OAM SERVERS | 0.51 |  | 0.51 |  |  | 37.91 | 173 | -135.09 | 2022-09-29 16:29 | 2023-08-08 | 2022-10-01 | 2023-08-08
75086 | FPIT | 349472026 | 349472026 - HITACHI SERVICE SUITE 9-5 YEAR SUBS | 45230.73 |  | 45230.73 |  |  | 45230.73 | 45683 | -452.27 | 2023-01-26 13:33 | 2023-05-02 | 2023-02-01 | 2023-05-01
75086 | FPIT | 349472027 | 349472027 - NEW EAM SERVERS | 1.18 |  | 1.18 |  |  | 1.18 | 621 | -619.82 | 2023-02-03 21:53 | 2024-03-30 | 2023-09-01 | 2024-03-31
75086 | FPIT | 349472028 | 349472028 - NEW FMA ENHANCEMENTS | 11763.21 |  | 11763.21 |  |  | 11763.21 | 9670 | 2093.21 | 2023-04-14 17:52 | 2026-03-31 | 2023-04-01
75086 | FPIT | 349472029 | 349472029 - MAXIMO INTEGRATIONS AND OTHER ENHAN | 20415.44 |  | 20415.44 |  |  | 20415.44 | 19914 | 501.44 | 2023-04-06 12:33 | 2026-03-31 | 2023-04-01
75086 | FPIT | 349472030 | 349472030 - ESRI UPGRADE TO 10.9 | 22910.75 |  | 22910.75 |  |  | 22910.75 | 6738 | 16172.75 | 2023-04-21 13:07 | 2024-03-30 | 2023-04-01 | 2024-03-31
75086 | FPIT | 349472031 | 349472031 - MATERIAL ISSUE LIGHTING APPLICATION | 915.84 |  | 915.84 |  |  | 915.84 | 4516 | -3600.16 | 2023-10-20 11:44 | 2024-06-30 | 2023-10-01 | 2024-06-30
75086 | FPIT | 349472H14 | 349472H14 - NEW ESRI INTEGRATIONS AND INFRASTRU | 8.53 |  | 8.53 |  |  | 8.53 | 9725 | -9716.47 | 2021-02-09 13:54 | 2023-11-30 | 2023-06-01 | 2024-03-06
75086 | FPIT | 349472S14 | 349472S14 - NEW ESRI INTEGRATIONS AND INFRA | 10005.71 |  | 10005.71 |  |  | 59895.49 | 532359 | -472463.51 | 2021-02-09 13:04 | 2023-11-30 | 2021-03-01 | 2024-03-06
75086 | FPIT | 400055013 | 400055013 - NGBU COMMUNICATIONS PLATFORM ENHANC | 24375.35 |  | 24375.35 |  |  | 60635.3 | 62056 | -1420.7 | 2021-12-28 16:22 | 2023-09-29 | 2022-01-01 | 2023-07-31
75086 | FPIT | 400124010 | 400124010 - CISCO PARTNERSHIP AGREEMENT (SPA) | 21111.38 |  | 21111.38 |  |  | 21111.38 | 21158 | -46.62 | 2023-11-01 06:26 | 2024-03-30 | 2023-11-01 | 2024-03-19
75086 | FPIT | 400149HW2 | 400149HW2 - ESCA - ITOT CYBER CARBON BLACK HW | 675.78 |  | 675.78 |  |  | 675.78 | 2282 | -1606.22 | 2023-08-09 12:36 | 2026-03-31 | 2023-08-01
75086 | FPIT | IT2000092 | IT2000092 - GTIS ENHANCEMENT AND ACOG | 394.52 |  | 394.52 |  |  | 198675.01 | 111184 | 87491.01 | 2020-12-22 10:20 | 2023-03-31 | 2021-01-01 | 2022-12-26
75086 | FPIT | IT2100095 | IT2100095 - MOBILE MAPPING CONSOLIDATION | -287.53 |  | -287.53 |  |  | 0 | 49072 | -49072 | 2022-02-16 09:08 | 2023-02-28 | 2022-02-01
75086 | FPIT | IT2100113 | IT2100113 - GAS SALES PLATFORM PHASE 3 | 26822.96 |  | 26822.96 |  |  | 89401.72 | 77035 | 12366.72 | 2022-01-07 10:50 | 2023-09-17 | 2022-01-01 | 2023-10-12
75086 | FPIT | IT2100114 | IT2100114 - TRACEABILITY PHASE 2 EXTENSION | 1269.07 |  | 1269.07 |  |  | 95400.02 | 132599 | -37198.98 | 2022-01-20 14:10 | 2023-03-31 | 2022-01-01 | 2023-03-31
75086 | FPIT | IT2100132 | IT2100132 - NGBU REPAIR PLAN EXPANSION | 98572.68 |  | 98572.68 |  |  | 189394.51 | 75912 | 113482.51 | 2022-01-27 17:05 | 2023-11-30 | 2022-02-01 | 2023-11-21
75086 | FPIT | IT2200155 | IT2200155 - GAS SUPPLY - AUTOMATING CONFIRMATIO | 25169.49 |  | 25169.49 |  |  | 25169.49 | 67905 | -42735.51 | 2022-12-28 15:04 | 2024-06-30 | 2023-01-01 | 2023-10-31
75086 | FPIT | IT2200157 | IT2200157 - FUTURE STATE 811 5 STATE LOCATE | 69714.29 |  | 69714.29 |  |  | 69714.29 | 71696 | -1981.71 | 2022-12-05 13:37 | 2024-04-30 | 2022-12-01 | 2024-04-30
75086 | FPIT | IT2200160 | IT2200160 - NGBU-AI FRAMEWORK | 64084.19 |  | 64084.19 |  |  | 64084.19 | 185731.65 | -121647.46 | 2022-12-13 14:38 | 2027-03-30 | 2023-01-01
75086 | FPIT | IT2200165 | IT2200165 - NGBU TRACEABILITY PLATFORM | 45605.22 |  | 45605.22 |  |  | 45605.22 | 125985 | -80379.78 | 2022-12-01 16:03 | 2026-03-31 | 2023-01-01
75086 | FPIT | IT2200175 | IT2200175 - LOTO PROCEDURES DEVONWAY SOLUTIONS | 11370.88 |  | 11370.88 |  |  | 11370.88 | 23704 | -12333.12 | 2022-12-21 08:40 | 2024-08-31 | 2023-01-01 | 2024-08-31
75086 | FPIT | IT2300049 | IT2300049 - GTIS EDI SOLUTION | 26944.99 |  | 26944.99 |  |  | 26944.99 | 48240 | -21295.01 | 2023-08-17 15:16 | 2024-07-30 | 2023-08-01 | 2024-07-20
75086 | FPIT | LTHGBLDPL | LTHGBLDPL - LIGHTHOUSE GAS BUILDER PORTAL | 45863.29 |  | 45863.29 |  |  | 105617.71 | 146642 | -41024.29 | 2022-04-25 15:46 | 2023-10-31 | 2022-05-01 | 2023-07-26
75086 | FPIT | LTHGCHTRS | LTHGCHTRS - LIGHTHOUSE: GAS OPS CHARTER | -660.23 |  | -660.23 |  |  | 89155.03 | 86372 | 2783.03 | 2021-03-17 12:28 | 2022-09-30 | 2021-04-01 | 2022-06-30
75086 | FPIT | LTHGIRFS | LTHGIRFS - LIGHTHOUSE: GAS IRIS | 429016.18 |  | 429016.18 |  |  | 429016.18 | 218641 | 210375.18 | 2020-05-20 12:10 | 2025-03-01 | 2020-06-01 | 2025-04-16
75086 | FPIT | LTHGIROS | LTHGIROS - LIGHTHOUSE: GAS IRIS | 242278.6 |  | 242278.6 |  |  | 242278.6 | 99723 | 142555.6 | 2020-05-20 10:15 | 2024-03-01 | 2020-05-01 | 2024-03-31
75086 | FPIT | LTHGVISTO | LTHGVISTO - LIGHTHOUSE INITIATIVE - GAS VISTO | 59805.48 |  | 59805.48 |  |  | 59805.48 | 88003 | -28197.52 | 2023-05-25 08:00 | 2024-09-30 | 2023-06-01 | 2024-09-30
75086 | FPIT | MOBILEMP | MOBILEMP - MOBILE MAPPING CONSOLIDATION | 284.15 |  | 284.15 |  |  | 25854.56 | 0 | 25854.56 | 2021-08-16 14:44 | 2022-12-31 | 2021-08-01 | 2022-12-31
75086 | FPIT | PH2ASPAHW | PH2ASPAHW - ESCA-OT ASSET,PATCH & VULNERABILITY | 271.85 |  | 271.85 |  |  | 271.85 | 3196 | -2924.15 | 2023-09-01 09:44 | 2026-03-31 | 2023-10-01
75086 | FPIT | PH2ASPASW | PH2ASPASW - ESCA-OT ASSET,PATCH & VULNERABILITY | 25342.29 |  | 25342.29 |  |  | 25342.29 | 323116 | -297773.71 | 2023-09-01 03:52 | 2026-03-31 | 2023-09-01
75086 | FPIT | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | 3074.42 |  | 3074.42 |  |  | 4842.78 | 3357 | 1485.78 | 2023-03-27 18:41 | 2024-03-31 | 2023-03-01 | 2024-03-01
75086 | FUNCTOHKY | 107GASCK | 107GASCK - GAS CAPITAL OVERHEAD | 1006224.085 |  | 1006224.085 |  |  | 2674813.054 | 0 | 2674813.054 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G701660 | AW4645 | AW4645 - EMERGENT AM01 COVINGTON LEVEE PH 1 | 85129.09 |  | 85129.09 |  |  | 5410125.33 | 3601200 | 1808925.33 | 2021-10-01 08:50 | 2023-01-30 | 2021-10-01 | 2023-02-28
75086 | G701662 | AW4673 | AW4673 - EMERGENT - CASING 34 - TAYLOR MILL | 277238.91 |  | 277238.91 |  |  | 2996678.41 | 3207100 | -210421.59 | 2021-10-13 11:13 | 2023-02-28 | 2021-11-01 | 2023-01-07
75086 | G712237 | MX4669122 | MX4669122 - HEBRON LOOP PH 2 PRESSURE IMPROVEME | 56336.5 |  | 56336.5 |  |  | 108647.65 | 765.33 | 107882.32 | 2021-03-01 14:01 | 2027-03-04 | 2021-03-01
75086 | G74092 | MX3645041 | MX3645041 - CHARTER - BRISTOW RD. PRESSURE IMP | 128484.11 |  | 128484.11 |  |  | 160780.32 | 2365.83 | 158414.49 | 2022-10-13 10:01 | 2025-07-24 | 2022-12-01 | 2024-10-28
75086 | G74238 | 43848219 | 43848219 - LAND - CHARTER - PATTY LN | 76.31 |  | 76.31 |  |  | 3302.46 | 40000 | -36697.54 | 2022-05-06 12:13 | 2026-03-31 | 2022-07-01
75086 | G74964 | MX5762350 | MX5762350 - CHARTER - ST RT 536 - INDEPENDANCE | -312817.21 |  | -312817.21 |  |  | 465151.04 | 842182.55 | -377031.51 | 2022-02-23 18:01 | 2024-01-31 | 2022-03-01 | 2023-02-01
75086 | G75449 | AW5471 | AW5471 - LN AM07 SCCDA DIGS | 13897.23 |  | 13897.23 |  |  | 736547.55 | 1642098.73 | -905551.18 | 2022-05-26 13:41 | 2022-12-31 | 2022-06-01 | 2022-11-27
75086 | G75498 | MX0458440 | MX0458440 - CHARTER-AMSTERDAM RD- VILLA HILLS- | 57488.69 |  | 57488.69 |  |  | 57488.69 | 18170.8 | 39317.89 | 2023-09-15 14:01 | 2024-01-29 | 2023-09-01 | 2024-01-03
75086 | G75498 | MX5370534 | MX5370534 - CHARTER-LP03 INSTALL PRESSURE IMPRO | 30095.4 |  | 30095.4 |  |  | 219783.43 | 765.33 | 219018.1 | 2022-07-08 14:01 | 2023-03-30 | 2022-10-01 | 2023-03-06
75086 | G75498 | MX6650945 | MX6650945 - CHARTER-AMSTERDAM RD- VILLA HILLS-P | 74019.29 |  | 74019.29 |  |  | 74019.29 | 251700.17 | -177680.88 | 2022-12-20 14:01 | 2025-02-27 | 2023-02-01 | 2025-01-07
75086 | G75629 | AW5648 | AW5648 - LN AM07 ECDA DIGS | 382263.19 |  | 382263.19 |  |  | 2022128.19 | 1466970.34 | 555157.85 | 2022-07-01 09:23 | 2022-12-31 | 2022-07-01 | 2023-01-20
75086 | G75683 | MX4850228 | MX4850228 - TOEBBEN DR - FLORENCE - 12" PL & 8" | 4633.95 |  | 4633.95 |  |  | 420205.41 | 49862.08 | 370343.33 | 2022-07-14 14:01 | 2022-12-29 | 2022-07-01 | 2022-12-26
75086 | G75710 | MX6588521 | MX6588521 - CHARTER-BONNIE LN- SOUTHGATE- REPLA | 207149.55 |  | 207149.55 |  |  | 207149.55 | 127456.36 | 79693.19 | 2023-02-01 18:01 | 2023-07-30 | 2023-02-01 | 2023-07-24
75086 | G75723 | MX6588233 | MX6588233 - CANCEL-RICHARD KNOCK HWY-WALTON-MA | 25429.79 |  | 25429.79 |  |  | 25429.79 | 0 | 25429.79 | 2023-03-21 14:01 | 2025-08-30 | 2023-05-01
75086 | G75734 | AW6846 | AW6846 - KENTUCKY - CORROSION REMEDIATION | 57999.86 |  | 57999.86 |  |  | 57999.86 | 180000 | -122000.14 | 2023-03-24 11:42 | 2025-09-30 | 2023-07-01
75086 | G75920 | AW5953 | AW5953 - LN AM07 STATION ECDA DIGS | 112.21 |  | 112.21 |  |  | 841303.77 | 734403.62 | 106900.15 | 2022-07-29 15:51 | 2022-12-31 | 2022-08-01 | 2023-01-20
75086 | G75924 | AW5965 | AW5965 - LN AM00B ECDA DIGS | 88081.47 |  | 88081.47 |  |  | 890080.26 | 1098620 | -208539.74 | 2022-08-03 13:21 | 2022-12-31 | 2022-08-01 | 2023-01-31
75086 | G75979 | MX4329859 | MX4329859 - CHARTER-KYTC 06-445.00 MINEOLA PK-E | 1149221.95 |  | 1149221.95 |  |  | 1151599.39 | 697743.72 | 453855.67 | 2022-09-12 10:01 | 2024-03-28 | 2022-10-01 | 2023-12-06
75086 | G75995 | AW6478 | AW6478 - LINE AM07 - CASING 50 - HYDROTEST | 292829.52 |  | 292829.52 |  |  | 292829.52 | 2386600 | -2093770.48 | 2022-12-30 12:47 | 2024-10-01 | 2023-02-01 | 2024-09-10
75086 | G76300 | AW6368 | AW6368 - EMERGENT - AM07 EXPOSED MAIN (KY) | 1259049.41 |  | 1259049.41 |  |  | 1349081.41 | 1348700 | 381.41 | 2022-11-16 13:54 | 2023-12-30 | 2022-11-01 | 2024-01-09
75086 | G76444 | MX6909455 | MX6909455 - KYTC 06-444 DONALDSON-ERLANGER-STI | 1837364.84 |  | 1837364.84 |  |  | 1837364.84 | 1219782.34 | 617582.5 | 2023-04-05 18:01 | 2024-09-01 | 2023-04-01 | 2024-05-29
75086 | G76446 | MX1322454 | MX1322454 - CHARTER-KYTC-162.40-BRISTOW RD-STI- | 70949.33 |  | 70949.33 |  |  | 113371.72 | 786869.97 | -673498.25 | 2022-10-07 14:01 | 2025-10-29 | 2022-10-01 | 2025-03-07
75086 | G76451 | MX8051147 | MX8051147 - CHARTER-SPARTA PIKE-EXPOSED MAIN RE | 179807.77 |  | 179807.77 |  |  | 179807.77 | 9490.2 | 170317.57 | 2023-05-02 10:01 | 2025-03-31 | 2023-09-01 | 2024-02-09
75086 | G76569 | AW6597 | AW6597 - EMERGENT - 6-9025 KY MAIN RELOCATE | 559459.05 |  | 559459.05 |  |  | 559459.05 | 3971500 | -3412040.95 | 2023-02-02 08:37 | 2024-07-15 | 2023-02-01 | 2024-08-02
75086 | G77046 | MX9473869 | MX9473869 - CHARTER-EMERGENT - MADISON PIKE - E | 212785.97 |  | 212785.97 |  |  | 212785.97 | 267037 | -54251.03 | 2023-07-27 18:01 | 2024-01-13 | 2023-07-01 | 2023-12-21
75086 | G77138 | 500000144 | 500000144 - THREE MILE - VRG CONTROL VALVE REPL | 9957.44 |  | 9957.44 |  |  | 9957.44 | 22770 | -12812.56 | 2023-06-29 10:08 | 2024-01-31 | 2023-08-01 | 2024-04-27
75086 | G7AM00BVL | V5471 | V5471 - AM00B & UL06 VALVE AUTOMATION | 214473.83 |  | 214473.83 |  |  | 472301.31 | 1830100 | -1357798.69 | 2021-11-22 12:33 | 2023-12-30 | 2022-04-01 | 2023-12-06
75086 | G7AM07IL2 | AW4685 | AW4685 - LINE AM07 PIPELINE REPLACEMENT PHAS | 6805064.34 |  | 6805064.34 |  |  | 7414752.9 | 33015500 | -25600747.1 | 2021-10-18 16:29 | 2025-02-28 | 2021-11-01 | 2025-02-06
75086 | G7AM07IL2 | AW5957 | AW5957 - CANCEL_LINE AM07 PHASE 2 - STATION | 2432242.44 |  | 2432242.44 |  |  | 2432308.78 | 9656000 | -7223691.22 | 2022-08-01 15:12 | 2025-02-28 | 2022-10-01
75086 | G7AM07IL2 | AW7013 | AW7013 - ROW - PIPELINE REPLACEMENT - PH2 | 187157.5 |  | 187157.5 |  |  | 187157.5 | 4284600 | -4097442.5 | 2023-05-18 14:09 | 2025-04-18 | 2023-09-01 | 2025-02-06
75086 | G7AM07IL3 | AW6387 | AW6387 - LINE AM07 - PIPE REPLACEMENT - PH 3 | 856064.92 |  | 856064.92 |  |  | 856064.92 | 40828200 | -39972135.08 | 2022-11-23 12:26 | 2025-12-31 | 2023-01-01
75086 | G7AM07IL3 | AW6388 | AW6388 - LINE AM07 PHASE 3 - LAND | 93301.12 |  | 93301.12 |  |  | 93301.12 | 4060000 | -3966698.88 | 2022-11-28 09:37 | 2025-12-31 | 2023-09-01
75086 | G7AM07ILI | 0233100 | 0233100 - LINE AM07 PIPELINE REPLACEMENT PHAS | 24311135.62 |  | 24311135.62 |  |  | 26203210.35 | 37717000 | -11513789.65 | 2020-12-09 14:11 | 2023-12-31 | 2020-12-01 | 2024-03-18
75086 | G7AM07ILI | AW3074 | AW3074 - LINE AM07 PIPELINE REPLACE LAND | 4526459.35 |  | 4526459.35 |  |  | 5650056.57 | 6089500 | -439443.43 | 2020-12-03 12:25 | 2023-12-31 | 2021-02-01 | 2024-03-18
75086 | G7AM07ILI | AW3138 | AW3138 - LINE AM07 PIPELINE REPLACEMENT-STN | 7604544.006 |  | 7604544.006 |  |  | 9667038.676 | 6278300 | 3388738.676 | 2020-12-18 13:08 | 2024-04-30 | 2021-05-01 | 2024-09-28
75086 | G7ASRP | CMSP70 | CMSP70 - ASRP CURB TO METER 3" OR LESS | 48986.38 |  | 48986.38 |  |  | 8948845.27 | 20388002 | -11439156.73 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | G7ASRP | MCSP70 | MCSP70 - ASRP MAIN TO CURB 3" OR LESS | 946448.983 |  | 946448.983 |  |  | 43964728.593 | 19954384 | 24010344.593 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | G7CORREM | AW5064 | AW5064 - KENTUCKY - CORROSION REMEDIATION | 88867.23 |  | 88867.23 |  |  | 213536.88 | 272000 | -58463.12 | 2022-02-10 15:46 | 2025-09-30 | 2022-08-01
75086 | G7EDGE | 39171904 | 39171904 - CANCEL-ROW- EDGEWOOD PRESSURE IMP | 7096.14 |  | 7096.14 |  |  | 36523.58 | 40000 | -3476.42 | 2022-06-07 07:26 | 2023-01-31 | 2022-08-01
75086 | G7EDGE | MX9171904 | MX9171904 - EDGEWOOD PRESSURE IMP | 154557.32 |  | 154557.32 |  |  | 568184.03 | 108825.77 | 459358.26 | 2022-09-22 14:01 | 2023-07-29 | 2022-09-01 | 2023-07-24
75086 | G7EM6131 | AW6193 | AW6193 - KLEERBAND REMED AND COAT KY | 164225.85 |  | 164225.85 |  |  | 169018.78 | 120000 | 49018.78 | 2022-10-03 12:32 | 2023-06-30 | 2022-12-01 | 2023-05-13
75086 | G7EMAM07 | AW5092 | AW5092 - EMERGENT - LINE AM07 - EXPOSED MAIN | 2308306.71 |  | 2308306.71 |  |  | 2648068.34 | 1319200 | 1328868.34 | 2022-02-15 14:54 | 2023-06-30 | 2022-04-01 | 2023-09-30
75086 | G7ESPEP | MX9171927 | MX9171927 - ELSMERE PRESSURE IMP | 1098722.9 |  | 1098722.9 |  |  | 2480236.56 | 327967.71 | 2152268.85 | 2022-04-25 14:01 | 2023-07-29 | 2022-05-01 | 2023-07-05
75086 | G7HARRPK | AW4778 | AW4778 - ROW - HARRIS PIKE UL45 EXT | 102848.99 |  | 102848.99 |  |  | 138358.05 | 926800 | -788441.95 | 2021-11-16 10:04 | 2026-11-30 | 2022-07-01
75086 | G7HARRPK | AW4796 | AW4796 - HARRIS PIKE UL45 EXT - PRESSURE IMP | 305251.69 |  | 305251.69 |  |  | 672146.94 | 7884400 | -7212253.06 | 2021-11-19 10:02 | 2026-11-30 | 2022-02-01
75086 | G7HOPECH | MX1415972 | MX1415972 - HOPEFUL CHURCH RD. PRI, FLORENCE 13 | 21721.46 |  | 21721.46 |  |  | 21721.46 | 2073615.27 | -2051893.81 | 2022-12-21 18:01 | 2025-06-26 | 2023-02-01 | 2025-06-17
75086 | G7LGMR | MX6828172 | MX6828172 - TO BE CANCEL-REG420BELAIR&SPICEWOOD | -82.8 |  | -82.8 |  |  | -7.2475e-13 | 139842.24 | -139842.24 | 2018-04-04 10:01 | 2021-03-31 | 2019-01-01
75086 | G7MAINS | 42698978 | 42698978 - ROW E MT ZION RD; INDEPNDNCE | 521.3 |  | 521.3 |  |  | 2979.25 | 15000 | -12020.75 | 2022-02-28 16:11 | 2023-01-31 | 2022-06-01 | 2023-02-16
75086 | G7MAINS | AW6146 | AW6146 - CANCEL_ROW LAKELAND PARK DR; LIM | 841.94 |  | 841.94 |  |  | 4251.92 | 25000 | -20748.08 | 2022-09-20 13:09 | 2023-12-31 | 2022-10-01
75086 | G7MAINS | AW6147 | AW6147 - CANCEL-ROW MEA -STANBERY RIDGE | 7.67 |  | 7.67 |  |  | 417.96 | 25000 | -24582.04 | 2022-09-20 13:28 | 2023-09-09 | 2022-10-01
75086 | G7MAINS | AW6415 | AW6415 - CANCEL-TBC ROW MEA-DECLARATION DR | 6386.09 |  | 6386.09 |  |  | 6386.09 | 25000 | -18613.91 | 2022-12-05 12:55 | 2023-07-14 | 2023-01-01
75086 | G7MAINS | AW6482 | AW6482 - CANCEL_LIS RD; CONSTANCE; 6" PL | 4176.01 |  | 4176.01 |  |  | 4176.01 | 25000 | -20823.99 | 2023-01-06 11:45 | 2023-08-25 | 2023-02-01
75086 | G7MAINS | AW6483 | AW6483 - CANCEL_CRESTVW HL; VILLA MADONNA DR | 4227.19 |  | 4227.19 |  |  | 4227.19 | 25000 | -20772.81 | 2023-01-06 11:55 | 2023-04-28 | 2023-02-01
75086 | G7MAINS | AW6484 | AW6484 - CANCEL_OLD LEXINGTON PIKE_RICHWOOD | 674.56 |  | 674.56 |  |  | 674.56 | 25000 | -24325.44 | 2023-01-06 12:04 | 2023-10-13 | 2023-02-01
75086 | G7MAINS | AW6694 | AW6694 - CANCEL_ROW MEA - MANHATTAN BLVD- | 2769.92 |  | 2769.92 |  |  | 2769.92 | 25000 | -22230.08 | 2023-02-20 10:52 | 2023-06-09 | 2023-03-01
75086 | G7MAINS | MEAPJT70 | MEAPJT70 - JOINT TRENCH PLASITC MAIN EXTENSION | 1343599.95 |  | 1343599.95 |  |  | 7234937.96 | 10000000 | -2765062.04 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | G7MAINS | MX0742327 | MX0742327 - MEA - BEECHWOOD RD; FT MITCHEL; 4" | 11766.58 |  | 11766.58 |  |  | 11766.58 | 58680.03 | -46913.45 | 2023-11-29 14:01 | 2024-04-18 | 2023-12-01 | 2024-04-17
75086 | G7MAINS | MX0840009 | MX0840009 - JT-G- BALLYSHANNON SECTION 5 PHASE | 80.88 |  | 80.88 |  |  | 80.88 | 50460.65 | -50379.77 | 2023-11-07 10:01 | 2024-08-19 | 2023-12-01 | 2024-07-31
75086 | G7MAINS | MX2698978 | MX2698978 - E MT ZION RD; INDEPENDENCE; 6" PL; | -4603.02 |  | -4603.02 |  |  | 527701.76 | 161397.39 | 366304.37 | 2022-07-21 18:02 | 2023-02-26 | 2022-07-01 | 2023-02-21
75086 | G7MAINS | MX2700925 | MX2700925 - BRECKENRIDGE; ALEXANDRIA; 4" PL; MA | -9728.45 |  | -9728.45 |  |  | 116849.23 | 76342.51 | 40506.72 | 2022-05-18 18:01 | 2022-11-17 | 2022-05-01 | 2022-11-08
75086 | G7MAINS | MX3676138 | MX3676138 - JT-G-MEMORIAL POINTE PART 1 | 81810.55 |  | 81810.55 |  |  | 81968.77 | 30148.66 | 51820.11 | 2022-09-14 14:01 | 2024-08-04 | 2022-10-01 | 2023-09-26
75086 | G7MAINS | MX3738158 | MX3738158 - JT-G-SAWGRASS PHASE D PART 2 | 78368.46 |  | 78368.46 |  |  | 78526.68 | 36692.03 | 41834.65 | 2022-10-04 14:01 | 2024-04-22 | 2022-10-01 | 2023-10-23
75086 | G7MAINS | MX3955327 | MX3955327 - LOCK RD-BUTLER-1200 FT 4 INCH PL MA | 19981.46 |  | 19981.46 |  |  | 172473.8 | 66243.21 | 106230.59 | 2022-07-15 18:01 | 2022-12-29 | 2022-07-01 | 2022-12-20
75086 | G7MAINS | MX4309183 | MX4309183 - JT-G-BALLYSHANNON SECTION 5 PHASE 1 | 941.4 |  | 941.4 |  |  | 24926.56 | 58459.77 | -33533.21 | 2022-04-07 10:01 | 2023-06-05 | 2022-04-01 | 2023-02-09
75086 | G7MAINS | MX4720432 | MX4720432 - 498 MASON RD FARM TAP EXTENSION | -105.84 |  | -105.84 |  |  | 22135.47 | 17882.37 | 4253.1 | 2022-08-25 10:01 | 2023-03-09 | 2022-08-01 | 2023-02-16
75086 | G7MAINS | MX4735611 | MX4735611 - W 3RD ST & W 4TH ST-NEWPORT-2194 FT | 161512.31 |  | 161512.31 |  |  | 161512.31 | 268126.22 | -106613.91 | 2023-10-25 14:01 | 2024-05-09 | 2023-10-01 | 2024-05-21
75086 | G7MAINS | MX5095081 | MX5095081 - EAST FROGTOWN RD; RICHWOOD; 6" PL; | 75915.66 |  | 75915.66 |  |  | 168750.62 | 71068.41 | 97682.21 | 2022-08-18 18:02 | 2023-03-30 | 2022-08-01 | 2023-02-20
75086 | G7MAINS | MX5502940 | MX5502940 - JT-G-BALLYSHANNON SECTION 5 PHASE 2 | 171079.44 |  | 171079.44 |  |  | 171079.44 | 141473.31 | 29606.13 | 2023-04-03 18:01 | 2023-09-19 | 2023-04-01 | 2024-01-13
75086 | G7MAINS | MX5543296 | MX5543296 - OLD LEXINGTON PIKE; RICHWOOD ; 8" P | 2086483.76 |  | 2086483.76 |  |  | 2086483.76 | 465508.22 | 1620975.54 | 2022-12-15 18:01 | 2024-01-04 | 2023-02-01 | 2024-01-01
75086 | G7MAINS | MX5653109 | MX5653109 - FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 397252.66 |  | 397252.66 |  |  | 947004.43 | 194197.42 | 752807.01 | 2020-09-29 10:01 | 2023-07-13 | 2020-10-01 | 2023-11-15
75086 | G7MAINS | MX5709799 | MX5709799 - LAKELAND PARK DR; LIMABURG ; 6" PL; | 202279.52 |  | 202279.52 |  |  | 202279.52 | 28078.8 | 174200.72 | 2022-12-20 14:01 | 2023-05-18 | 2023-01-01 | 2023-05-18
75086 | G7MAINS | MX5751969 | MX5751969 - MEA - STANBERY RIDGE-FORT THOMAS-47 | 9394.37 |  | 9394.37 |  |  | 112973.92 | 24699.21 | 88274.71 | 2022-10-04 18:01 | 2023-03-23 | 2022-10-01 | 2023-03-21
75086 | G7MAINS | MX5777720 | MX5777720 - CANCEL - MEMORIAL- SOUTHGATE -8" | -0.01 |  | -0.01 |  |  | -0.01 | 156448.39 | -156448.4 | 2022-11-15 18:02 | 2023-10-16 | 2023-01-01
75086 | G7MAINS | MX6108586 | MX6108586 - JT-G-ENCLAVE SUBDIVISION | 58147.53 |  | 58147.53 |  |  | 58147.53 | 87608.95 | -29461.42 | 2023-01-19 18:01 | 2023-11-16 | 2023-02-01 | 2024-03-12
75086 | G7MAINS | MX6108813 | MX6108813 - PARKVIEW ESTATES APP - UNION - 8" & | 97062.44 |  | 97062.44 |  |  | 265883.97 | 134092.12 | 131791.85 | 2022-10-26 10:01 | 2023-03-23 | 2022-11-01 | 2023-04-10
75086 | G7MAINS | MX6119454 | MX6119454 - JT-G-TUSCANY SECTION 39 & 40 | 24253.88 |  | 24253.88 |  |  | 24253.88 | 20175.25 | 4078.63 | 2022-12-14 18:01 | 2023-11-19 | 2023-05-01 | 2023-10-31
75086 | G7MAINS | MX6212508 | MX6212508 - ELLIS RD; CONSTANCE; 6" PL; MEA | 91903.57 |  | 91903.57 |  |  | 91903.57 | 73565.15 | 18338.42 | 2023-06-14 18:01 | 2023-11-09 | 2023-06-01 | 2023-10-30
75086 | G7MAINS | MX6362268 | MX6362268 - SERVICE RD; WALTON; 6" PL; MEA | 100529.14 |  | 100529.14 |  |  | 114099.11 | 61477.74 | 52621.37 | 2022-11-10 16:16 | 2023-04-13 | 2022-11-01 | 2023-04-20
75086 | G7MAINS | MX6445818 | MX6445818 - CARBON WAY; RICHWOOD; 6" PL; MEA | 257254.69 |  | 257254.69 |  |  | 285598.5 | 100161.61 | 185436.89 | 2022-11-14 14:02 | 2023-06-08 | 2022-11-01 | 2023-05-30
75086 | G7MAINS | MX6591941 | MX6591941 - ST RT 42; UNION; 4" PL; MEA; UNION | 175960.94 |  | 175960.94 |  |  | 175960.94 | 16663.83 | 159297.11 | 2023-04-03 10:01 | 2023-09-07 | 2023-04-01 | 2023-09-13
75086 | G7MAINS | MX6678695 | MX6678695 - MEA-DECLARATION DR-INDEPENDENCE-4 I | 94687.23 |  | 94687.23 |  |  | 94687.23 | 32908.63 | 61778.6 | 2023-08-01 18:01 | 2023-12-28 | 2023-08-01 | 2023-12-25
75086 | G7MAINS | MX6735987 | MX6735987 - CRESTVW HL; VILLA MADONNA DR; 4" IP | 96134.72 |  | 96134.72 |  |  | 96134.72 | 60882.54 | 35252.18 | 2023-03-17 18:01 | 2023-08-17 | 2023-03-01 | 2023-09-19
75086 | G7MAINS | MX6877874 | MX6877874 - MEA - EDGEWOOD; SUTTER DR; 4IN PL | 13151.75 |  | 13151.75 |  |  | 13151.75 | 11203.51 | 1948.24 | 2023-02-14 10:01 | 2023-06-29 | 2023-02-01 | 2023-06-19
75086 | G7MAINS | MX7843275 | MX7843275 - MEA - MANHATTAN BLVD-DAYTON-250 FT | 22294.86 |  | 22294.86 |  |  | 22294.86 | 17848.21 | 4446.65 | 2023-06-05 18:01 | 2023-10-26 | 2023-06-01 | 2023-11-22
75086 | G7MAINS | MX8153338 | MX8153338 - MEA - BROMLEY; WOODHAVEN CT; 2" PL | 7451.78 |  | 7451.78 |  |  | 7451.78 | 596.7 | 6855.08 | 2023-06-08 10:01 | 2023-10-26 | 2023-06-01 | 2023-10-08
75086 | G7MAINS | MX8197104 | MX8197104 - JT-G-REDWOOD LIVING APARTMENTS | 46703.65 |  | 46703.65 |  |  | 72559.82 | 95065.91 | -22506.09 | 2021-03-26 18:02 | 2022-12-30 | 2021-04-01 | 2022-12-19
75086 | G7MAINS | MX8327384 | MX8327384 - MAE- MEMORIAL POINT APPROACH - SOUT | 218723.66 |  | 218723.66 |  |  | 218723.66 | 103571.49 | 115152.17 | 2023-03-21 14:01 | 2023-08-17 | 2023-03-01 | 2023-08-02
75086 | G7MREG118 | MX2217622 | MX2217622 - STATION 873 - 5TH & PHILADELPHIA | 238191.88 |  | 238191.88 |  |  | 417159.17 | 87907.04 | 329252.13 | 2017-09-22 14:01 | 2025-11-30 | 2017-10-01
75086 | G7PUBIMP | MX0722354 | MX0722354 - CANCEL -BARRS BRANCH BRIDGE PROJECT | 139.67 |  | 139.67 |  |  | 139.67 | 0 | 139.67 | 2023-09-07 10:01 | 2024-03-28 | 2023-10-01
75086 | G7PUBIMP | MX2781786 | MX2781786 - CANCEL_KYTC 19-9001 I-275 GRAVES RD | -104794.3 |  | -104794.3 |  |  | 0 | 70082.56 | -70082.56 | 2020-12-09 10:02 | 2023-11-22 | 2021-06-01
75086 | G7PUBIMP | MX3359474 | MX3359474 - KYTC - RICHWOOD RD STI - BEAVERLICK | 159258.39 |  | 159258.39 |  |  | 479297.13 | 24088.21 | 455208.92 | 2021-12-13 14:02 | 2024-12-31 | 2021-12-01 | 2022-06-22
75086 | G7PUBIMP | MX4199889 | MX4199889 - US-25 WALTON - 4" PL - STI | 13410.42 |  | 13410.42 |  |  | 149032.98 | 38705.17 | 110327.81 | 2022-07-25 14:01 | 2023-03-30 | 2022-08-01 | 2023-02-16
75086 | G7PUBIMP | MX4966474 | MX4966474 - 7639 TURFWAY - FLORENCE - 8" PL - S | -2009.33 |  | -2009.33 |  |  | 83010.49 | 3293.8 | 79716.69 | 2022-06-27 18:01 | 2023-03-30 | 2022-07-01 | 2023-03-01
75086 | G7PUBIMP | MX6266002 | MX6266002 - US27/MARSHALL LN. TO JOHNS HILL RD. | -789.03 |  | -789.03 |  |  | 17923.74 | 31832.35 | -13908.61 | 2022-02-04 14:01 | 2023-01-12 | 2022-08-01 | 2022-12-25
75086 | G7PUBIMP | MX6798234 | MX6798234 - KYTC 06-8916 HOUSTON RD-ERLANGER-ST | 387459.32 |  | 387459.32 |  |  | 403061.42 | 142182.69 | 260878.73 | 2022-10-21 14:01 | 2024-01-11 | 2022-11-01 | 2024-03-19
75086 | G7PUBIMP | MX8637896 | MX8637896 - CC STI -BLOSSOM LN- SOUTHGATE -8" P | 339834.6 |  | 339834.6 |  |  | 339834.6 | 128671.29 | 211163.31 | 2023-03-30 18:01 | 2023-09-04 | 2023-04-01 | 2023-09-04
75086 | G7PUBIMP | MX8840782 | MX8840782 - CANCEL INSTALL STREET IMPROVEMENT | -7.19 |  | -7.19 |  |  | -5.9508e-14 | 0 | -5.9508e-14 | 2020-02-06 18:01 | 2018-12-07 | 2020-02-01
75086 | G7PUBIMP | MX9077703 | MX9077703 - 0014.00 US-25 AT MT. ZION ROAD STI | 92925.49 |  | 92925.49 |  |  | 92925.49 | 32071.13 | 60854.36 | 2023-04-24 14:01 | 2023-06-09 | 2023-05-01 | 2023-08-09
75086 | G7PUBIMP | MX9121402 | MX9121402 - KYTC 06-423 FROGTOWN-UNION-STI | 36325.98 |  | 36325.98 |  |  | 36325.98 | 24602.7 | 11723.28 | 2023-07-13 10:01 | 2024-02-29 | 2023-07-01 | 2024-02-19
75086 | G7PUBIMP | MX9244894 | MX9244894 - KYTC - MT.ZION RD KY536 STI | 79198.21 |  | 79198.21 |  |  | 1090371.62 | 1026778 | 63593.62 | 2019-11-08 10:01 | 2023-06-30 | 2020-01-01 | 2021-07-27
75086 | G7PUBIMP | MX9568282 | MX9568282 - STI-TAYLOR MILL RD SIDEWALK-TAYLOR | 37496.5 |  | 37496.5 |  |  | 37496.5 | 38707.06 | -1210.56 | 2023-10-19 14:01 | 2024-04-30 | 2023-10-01 | 2024-03-11
75086 | G7PUBIMP | MX9853572 | MX9853572 - GRAVES AND NORTHBEND ROUNDABOUT PRO | -268599.65 |  | -268599.65 |  |  | 1109.25 | 109422.27 | -108313.02 | 2021-02-16 18:02 | 2023-12-28 | 2021-02-01 | 2022-02-14
75086 | G7PUBIMP | MX9856643 | MX9856643 - CANCEL-KYTC - KY-536 DONALDSON RD | -39331.86 |  | -39331.86 |  |  | 0 | 0 | 0 | 2022-09-06 18:01 | 2024-12-31 | 2022-11-01
75086 | G7PUBIMP | MX9948553 | MX9948553 - WILBERS LN - FORT THOMAS - 2" PE - | -32384.48 |  | -32384.48 |  |  | 93599.44 | 75860.65 | 17738.79 | 2021-07-13 18:02 | 2024-12-16 | 2021-07-01 | 2023-02-21
75086 | G7PUINEW | INSREGREL | INSREGREL - INSTALL OR REMOVE REGULATOR/RELIEF | 16889.19 |  | 16889.19 |  |  | 1489364.82 | 800000 | 689364.82 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | SETMETER | SETMETER - SET OR REMOVE METER | 1564512.18 |  | 1564512.18 |  |  | 13998338.92 | 2250000 | 11748338.92 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGLG | AGECHGLG - KENTUCKY AGE CHANGE LARGE METER | 262496.64 |  | 262496.64 |  |  | 1022003.08 | 350000 | 672003.08 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | AGECHGSM - KENTUCKY AGE CHANGE SMALL METER | 1138940.25 |  | 1138940.25 |  |  | 8735915.91 | 14500000 | -5764084.09 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRLG | CHGMTRLG - CHANGE LARGE METER KENTUCKY | -15.39 |  | -15.39 |  |  | 165013.79 | 725000 | -559986.21 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | CHGMTRSM - CHANGE SMALL METER KENTUCKY | 208546.53 |  | 208546.53 |  |  | 3305404.85 | 1250000 | 2055404.85 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | CHGREGREL - CHANGE REGULATOR/RELIEF KENTUCKY | 14553.33 |  | 14553.33 |  |  | 182578 | 800000 | -617422 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7REG0026 | MX7281967 | MX7281967 - REG 0026 UPHIL AND HIGHWAY - REG SW | 837.32 |  | 837.32 |  |  | 3248.57 | 48953.52 | -45704.95 | 2020-07-07 10:01 | 2021-03-31 | 2020-08-01 | 2021-01-20
75086 | G7REG0057 | MX7281845 | MX7281845 - CANCEL -REG 0057 SARATOGA 11TH - OR | -2699.91 |  | -2699.91 |  |  | -59.88 | 44953.52 | -45013.4 | 2020-07-07 10:01 | 2021-03-31 | 2020-07-01
75086 | G7REG0089 | AW3224 | AW3224 - REG 0427 EMPIRE DR | 66987.81 |  | 66987.81 |  |  | 889426.75 | 732000 | 157426.75 | 2020-12-30 15:41 | 2025-10-30 | 2021-07-01
75086 | G7REG0089 | AW3246 | AW3246 - REG 0427 EMPIRE DR LAND | 33947.65 |  | 33947.65 |  |  | 97257.29 | 82500 | 14757.29 | 2021-01-02 13:48 | 2026-03-31 | 2021-04-01
75086 | G7REG010 | AW3280 | AW3280 - REG 0010 STEVENSON AND LEXINGTON RE | -1377.62 |  | -1377.62 |  |  | 26174.83 | 58000 | -31825.17 | 2021-01-06 11:52 | 2022-03-31 | 2021-06-01 | 2021-11-02
75086 | G7REG013 | AW3273 | AW3273 - REG 0013 SIXTEENTH AND HOLMAN REPAI | 677.43 |  | 677.43 |  |  | 22853.06 | 39300 | -16446.94 | 2021-01-06 08:46 | 2022-03-31 | 2021-07-01 | 2021-11-24
75086 | G7REG021 | AW3278 | AW3278 - REG 0021 GRAND AND S FT THOMAS REPA | 1348.23 |  | 1348.23 |  |  | 15758.63 | 56400 | -40641.37 | 2021-01-06 10:47 | 2022-03-31 | 2021-07-01 | 2021-10-23
75086 | G7REG026 | AW3184 | AW3184 - REG 0437 UPHILL & HIGHWAY | 327140.23 |  | 327140.23 |  |  | 1749703.52 | 507300 | 1242403.52 | 2020-12-28 11:30 | 2023-03-31 | 2021-12-01 | 2023-02-08
75086 | G7REG0359 | AW4715 | AW4715 - REG 0359 - TAYLOR MILL RD N - RS UP | 4779.84 |  | 4779.84 |  |  | 69530.93 | 37100 | 32430.93 | 2021-10-28 10:14 | 2023-03-30 | 2022-01-01 | 2023-02-18
75086 | G7REG045 | AW3228 | AW3228 - REG 0432 TENTH & BRIGHTON | 1921779.56 |  | 1921779.56 |  |  | 2251191.33 | 660800 | 1590391.33 | 2020-12-30 16:28 | 2021-03-31 | 2021-11-01 | 2023-07-11
75086 | G7REG045 | AW3356 | AW3356 - CANCEL- REG0432 TENTH-BRIGHTON LAND | -9215.31 |  | -9215.31 |  |  | -712.06 | 82500 | -83212.06 | 2021-01-13 10:52 | 2023-03-31 | 2021-09-01
75086 | G7REG051 | AW3919 | AW3919 - REG 0051 WALNUT AND ELECTRIC REPAIR | 920.74 |  | 920.74 |  |  | 31753.95 | 175200 | -143446.05 | 2021-05-25 08:51 | 2022-03-31 | 2021-08-01 | 2021-11-23
75086 | G7REG053 | MX9751457 | MX9751457 - REG 0053 - OVERTON AND NINTH - REG | 2185.83 |  | 2185.83 |  |  | 65189.05 | 43953.52 | 21235.53 | 2021-02-08 18:02 | 2022-03-31 | 2021-06-01 | 2021-10-28
75086 | G7REG057 | AW3180 | AW3180 - REG 0431 SARATOGA & ELEVENTH | 2175190.37 |  | 2175190.37 |  |  | 2645397.84 | 796400 | 1848997.84 | 2020-12-28 10:43 | 2023-03-31 | 2021-11-01 | 2023-11-08
75086 | G7REG057 | AW3354 | AW3354 - CANCEL-REG431 SARATOGA-ELEVENTH ROW | -11300.35 |  | -11300.35 |  |  | -3197.72 | 82500 | -85697.72 | 2021-01-13 10:19 | 2023-03-31 | 2021-06-01
75086 | G7REG059 | AW3177 | AW3177 - REG 0059 HIGHLAND AND GRAND RS REPL | 515315.2 |  | 515315.2 |  |  | 3286811.94 | 746000 | 2540811.94 | 2020-12-28 10:15 | 2022-09-30 | 2021-06-01 | 2023-02-09
75086 | G7REG059 | AW3353 | AW3353 - REG 0059 HIGHLAND AND GRAND LAND | 2550.73 |  | 2550.73 |  |  | 90447.78 | 82500 | 7947.78 | 2021-01-13 10:02 | 2022-09-30 | 2021-04-01 | 2023-02-09
75086 | G7REG069 | AW3287 | AW3287 - REG 0069 JEFFERSON AND HAWTHORNE RE | -1100.42 |  | -1100.42 |  |  | 20990.74 | 56400 | -35409.26 | 2021-01-06 14:06 | 2022-03-31 | 2021-07-01 | 2021-11-14
75086 | G7REG073 | AW3286 | AW3286 - REG 0073 GRAVES AND HULBERT REPAIR | 819.93 |  | 819.93 |  |  | 44634.14 | 58000 | -13365.86 | 2021-01-06 13:49 | 2022-03-31 | 2021-06-01 | 2021-11-28
75086 | G7REG074 | AW4985 | AW4985 - REG 0074 - MCALPIN N OF HOPE - RELI | 100624.73 |  | 100624.73 |  |  | 909142.07 | 135940 | 773202.07 | 2022-03-01 12:43 | 2022-08-31 | 2022-05-01 | 2022-10-07
75086 | G7REG074 | MXA751466 | MXA751466 - CANCEL - REG 0074 - MCALPIN N - R | -13054.22 |  | -13054.22 |  |  | 0 | 9701.94 | -9701.94 | 2022-06-21 14:01 | 2022-09-20 | 2022-06-01
75086 | G7REG093 | AW3284 | AW3284 - REG 0093 ALEXANDRIA AND BLOSSUM REP | 3358.26 |  | 3358.26 |  |  | 38250.27 | 61000 | -22749.73 | 2021-01-06 13:22 | 2022-03-31 | 2021-07-01 | 2021-11-20
75086 | G7REG095 | AW3283 | AW3283 - REG 0095 BAUM AND BURNET | 202.01 |  | 202.01 |  |  | 36472.08 | 402900 | -366427.92 | 2021-01-06 13:08 | 2022-03-31 | 2021-08-01 | 2021-11-20
75086 | G7REG097 | AW3282 | AW3282 - REG 0097 HOME AND MAIN REPAIR | 1128.67 |  | 1128.67 |  |  | 39706.92 | 73500 | -33793.08 | 2021-01-06 12:55 | 2022-03-31 | 2021-07-01 | 2022-01-13
75086 | G7REG74K | AW3285 | AW3285 - REG 0074 MCALPIN N OF HOPE LN REPAI | 548.58 |  | 548.58 |  |  | 39334.19 | 54100 | -14765.81 | 2021-01-06 13:36 | 2022-03-31 | 2021-07-01 | 2021-12-24
75086 | G7REPL | 28051 | 28051 - SMALL REPL KY | 354339.29 |  | 354339.29 |  |  | 1958069.34 | 0 | 1958069.34 | 2000-04-13 | 2050-12-31 | 1999-12-01
75086 | G7REPL | AW6197 | AW6197 - CANCEL- ROW SCHOOL RD - WALTON | 2168.66 |  | 2168.66 |  |  | 4127.67 | 25000 | -20872.33 | 2022-10-06 09:08 | 2023-06-17 | 2022-11-01
75086 | G7REPL | MX0506978 | MX0506978 - KYTC MT ZION - INDEPENDENCE - 12" P | 92483.97 |  | 92483.97 |  |  | 92483.97 | 43338.35 | 49145.62 | 2023-10-12 14:01 | 2024-02-20 | 2023-10-01 | 2024-02-07
75086 | G7REPL | MX3269023 | MX3269023 - KYTC - HANDS PIKE - EDGEWOOD - 4" P | -23357.78 |  | -23357.78 |  |  | 258583.45 | 12423.85 | 246159.6 | 2022-06-27 18:01 | 2024-12-31 | 2022-07-01 | 2022-11-18
75086 | G7REPL | MX4962663 | MX4962663 - ALEXANDRIA PK - ALEXANDRIA- 8" SIZE | 232289.57 |  | 232289.57 |  |  | 387434.37 | 93664.48 | 293769.89 | 2022-08-10 14:02 | 2023-05-11 | 2022-08-01 | 2023-05-03
75086 | G7REPL | MX6589218 | MX6589218 - SCHOOL RD - WALTON - 4" PL - RPL | 152319.03 |  | 152319.03 |  |  | 152319.03 | 31266.98 | 121052.05 | 2023-03-17 18:01 | 2023-11-30 | 2023-03-01 | 2023-11-29
75086 | G7REPL | MX7352150 | MX7352150 - AVALON SQUARE - WEAVER RD - FLORENC | 72691.99 |  | 72691.99 |  |  | 72691.99 | 45572.01 | 27119.98 | 2023-05-03 18:01 | 2023-09-21 | 2023-05-01 | 2023-10-03
75086 | G7REPL | T9340 | T9340 - CANCEL RPL WATERWORKS RD. INLET | -53.87 |  | -53.87 |  |  | -2701.4 | 28102.56 | -30803.96 | 2017-07-14 10:10 | 2018-09-01 | 2018-04-01
75086 | G7REPL | T9341 | T9341 - CANCEL RPL WATERWORKS RD. OUTLET | -52.79 |  | -52.79 |  |  | -2988.77 | 28102.56 | -31091.33 | 2017-07-14 10:19 | 2018-09-01 | 2018-04-01
75086 | G7RGPI | MX9217475 | MX9217475 - GARVEY AVE. PRI, ELSMERE, 9400' 8" | 37403.52 |  | 37403.52 |  |  | 1512645.24 | 507691.08 | 1004954.16 | 2021-08-16 18:02 | 2022-12-01 | 2021-09-01 | 2022-11-21
75086 | G7RRPI | MX9219249 | MX9219249 - RICHARDSON RD PRESSURE IMP 7300' OF | 45141.83 |  | 45141.83 |  |  | 77418.37 | 765.33 | 76653.04 | 2022-10-21 18:01 | 2026-03-12 | 2022-11-01
75086 | G7SERVMC | 8MCR70 | 8MCR70 - CANCEL_REPLACE M-C 8" AND GREATER | -210.39 |  | -210.39 |  |  | -210.39 | 0 | -210.39 | 2010-05-05 | 2050-12-31 | 2013-03-01
75086 | G7SERVMC | AW6981 | AW6981 - SERVICE ABANDONMENTS - IAP | 12191.52 |  | 12191.52 |  |  | 12191.52 | 0 | 12191.52 | 2023-05-02 09:49 | 2050-12-31 | 2023-05-01
75086 | G7SERVMC | CMRP70 | CMRP70 - REPLACE C-M PLASTIC 2 INCH AND UNDE | 251035.39 |  | 251035.39 |  |  | 13231230.44 | 0 | 13231230.44 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | CMRS70 - 2" OR LESS STEEL C-M REPLACE | 1448.49 |  | 1448.49 |  |  | 11809.2 | 1000000 | -988190.8 | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVMC | LCMRP70 | LCMRP70 - GREATER THAN 2" C-M REPL PLASTIC | 14953.65 |  | 14953.65 |  |  | 90495.16 | 2500000 | -2409504.84 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRP70 | LMCRP70 - GREATER THAN 2" M-C REPL PLASTIC | 136183.5 |  | 136183.5 |  |  | 674466.8 | 2500000 | -1825533.2 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | LMCRS70 - GREATER THAN 2" M-C REPL STEEL | 232.64 |  | 232.64 |  |  | 16527.47 | 1000000 | -983472.53 | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | G7SERVMC | MCRP70 | MCRP70 - REPLACE (NON-AMRP) M-C PLASTIC 2 IN | 1589253.17 |  | 1589253.17 |  |  | 23621807.16 | 0 | 23621807.16 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | MCRS70 - REPLACE M-C STEEL 2 INCH AND UNDER | 33041.54 |  | 33041.54 |  |  | 624811.14 | 0 | 624811.14 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | CMNEWP70 | CMNEWP70 - NEW C-M PLASTIC 2 INCH AND UNDER KY | 509262.78 |  | 509262.78 |  |  | 8686272.18 | 1 | 8686271.18 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | CMNEWS70 - 2" OR LESS STEEL NEW C-M | 14935.28 |  | 14935.28 |  |  | 297438.99 | 5000000 | -4702561.01 | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVNEW | LCMNEWP70 | LCMNEWP70 - GREATER THAN 2" C-M PLASTIC | 27714.78 |  | 27714.78 |  |  | 271527.66 | 2500000 | -2228472.34 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVNEW | LCMNEWS70 | LCMNEWS70 - GREATER THAN 2" C-M STEEL | 17506.75 |  | 17506.75 |  |  | 17506.75 | 1000000 | -982493.25 | 2017-03-10 10:26 | 2050-12-31 | 2019-07-01
75086 | G7SERVNEW | LMCNEWP70 | LMCNEWP70 - GREATER THAN 2" M-C PLASTIC | 183192.88 |  | 183192.88 |  |  | 730834.73 | 2500000 | -1769165.27 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | LMCNEWS70 - GREATER THAN 2" M-C STEEL | 53394.11 |  | 53394.11 |  |  | 163531.96 | 2500000 | -2336468.04 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVNEW | MCNEWP70 | MCNEWP70 - NEW M-C PLASTIC 2 INCH AND UNDER KY | 2339381.35 |  | 2339381.35 |  |  | 22904624.72 | 1 | 22904623.72 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | MCNEWS70 - NEW M-C STEEL 2 INCH AND UNDER KY | 99085.29 |  | 99085.29 |  |  | 367015.52 | 1 | 367014.52 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SHOW2 | MX8547529 | MX8547529 - CHARTER - SHOWCASE CINEMAS RPL 1500 | 1431508.06 |  | 1431508.06 |  |  | 1431508.06 | 417336.96 | 1014171.1 | 2023-03-11 12:03 | 2023-07-21 | 2023-03-01 | 2023-10-20
75086 | G7STA011 | AW3227 | AW3227 - STA 0949 DAYTON VALVE HOUSE | 332436.28 |  | 332436.28 |  |  | 1412676.29 | 1062400 | 350276.29 | 2020-12-30 16:17 | 2025-10-30 | 2021-11-01
75086 | G7STA011 | AW3250 | AW3250 - STA 0949 DAYTON VALVE HOUSE LAND | 501.51 |  | 501.51 |  |  | 26609.83 | 82500 | -55890.17 | 2021-01-02 14:55 | 2025-11-29 | 2021-06-01
75086 | G7STA014 | AW3251 | AW3251 - CANCEL_STA 0014 EAST ALEXANDRIAPIKE | -57.29 |  | -57.29 |  |  | 19.48 | 82500 | -82480.52 | 2021-01-03 09:43 | 2023-03-31 | 2021-06-01
75086 | G7STA014 | MX5466775 | MX5466775 - CHARTER - EAST ALEXANDRIA PIKE | 352187.52 |  | 352187.52 |  |  | 352187.52 | 129995.81 | 222191.71 | 2022-11-22 10:02 | 2023-12-29 | 2023-03-01 | 2023-11-20
75086 | G7STA064 | AW3217 | AW3217 - STA 0940 GLECOE TB | 704166.04 |  | 704166.04 |  |  | 1099115.41 | 510900 | 588215.41 | 2020-12-30 13:22 | 2021-03-31 | 2021-11-01 | 2023-09-27
75086 | G7STA064 | AW3268 | AW3268 - STA 0940 STA GLENCOE TB LAND | 54157.69 |  | 54157.69 |  |  | 61324.56 | 82500 | -21175.44 | 2021-01-05 14:36 | 2023-03-31 | 2021-08-01 | 2023-09-27
75086 | G7STA276 | AW3212 | AW3212 - STA 0276 MARY INGLES HWY RS ABANDON | -1547.23 |  | -1547.23 |  |  | 86580.98 | 553900 | -467319.02 | 2020-12-30 11:32 | 2021-03-31 | 2021-11-01 | 2022-11-18
75086 | G7STA276 | AW3689 | AW3689 - CANCEL-STA 0276 MARY IGLES HWY LAND | -3090.98 |  | -3090.98 |  |  | 341.21 | 82500 | -82158.79 | 2021-02-26 23:34 | 2023-03-31 | 2021-06-01
75086 | G7STA280 | AW3213 | AW3213 - STA 0938 TAYLOR MILL & LONE OAK | 2062158.57 |  | 2062158.57 |  |  | 2714635.12 | 562000 | 2152635.12 | 2020-12-30 11:55 | 2023-09-30 | 2021-11-01 | 2023-09-08
75086 | G7STA280 | AW3272 | AW3272 - STA0938 TAYLOR MILL & LONE OAK LAND | 3596.12 |  | 3596.12 |  |  | 143382.9 | 82500 | 60882.9 | 2021-01-05 15:40 | 2023-03-31 | 2021-08-01 | 2023-09-08
75086 | G7STA286 | AW3216 | AW3216 - STA 0929 RILEY RD | 2007912.43 |  | 2007912.43 |  |  | 4099943.66 | 635200 | 3464743.66 | 2020-12-30 13:11 | 2021-03-31 | 2021-09-01 | 2023-06-28
75086 | G7STA286 | AW3271 | AW3271 - STA 0929 RILEY RD LAND | 5337.91 |  | 5337.91 |  |  | 87055.48 | 82500 | 4555.48 | 2021-01-05 15:21 | 2023-03-31 | 2021-06-01 | 2023-06-28
75086 | G7STA338 | AW3192 | AW3192 - STA 0941 GUBSER MILL | 184144.42 |  | 184144.42 |  |  | 601742.85 | 538800 | 62942.85 | 2020-12-28 13:44 | 2025-12-30 | 2021-09-01
75086 | G7STA338 | AW3690 | AW3690 - STA 0941 GUBSER MILL LAND | 10798.51 |  | 10798.51 |  |  | 48399.99 | 82500 | -34100.01 | 2021-02-27 08:54 | 2025-10-25 | 2021-06-01
75086 | G7STA444 | AW3186 | AW3186 - STA 0948 THIRD & CRESCENT | 69030.77 |  | 69030.77 |  |  | 637908.67 | 948400 | -310491.33 | 2020-12-28 11:59 | 2025-11-27 | 2021-11-01
75086 | G7STA444 | AW3230 | AW3230 - STA 0948 THIRD & CRESCENT LAND | 35410.61 |  | 35410.61 |  |  | 53659.46 | 82500 | -28840.54 | 2020-12-31 08:30 | 2025-11-27 | 2021-08-01
75086 | G7STA535 | AW3299 | AW3299 - STA 0535 DRY RIDGE EAST REPAIR | 6469.35 |  | 6469.35 |  |  | 70996.93 | 56400 | 14596.93 | 2021-01-07 09:12 | 2022-08-31 | 2021-06-01 | 2022-12-02
75086 | G7STA793 | AW3188 | AW3188 - STA 0942 CAMP ERNST RD | 2990403.21 |  | 2990403.21 |  |  | 3690112.31 | 887300 | 2802812.31 | 2020-12-28 12:16 | 2023-09-30 | 2021-11-01 | 2024-01-18
75086 | G7STA793 | AW3767 | AW3767 - STA 0942 CAMP ERNST RD LAND | 41976.41 |  | 41976.41 |  |  | 108915.31 | 82500 | 26415.31 | 2021-03-16 18:53 | 2023-03-31 | 2021-06-01 | 2024-01-18
75086 | G7STA822 | AW3189 | AW3189 - STA 0822 COX RD RS REPAIR | -64550.49 |  | -64550.49 |  |  | 188430.06 | 541600 | -353169.94 | 2020-12-28 12:29 | 2022-12-31 | 2021-11-01 | 2022-11-18
75086 | G7STA822 | AW3685 | AW3685 - CANCEL 0822 - COX RD. RS REP - LAND | -4516.03 |  | -4516.03 |  |  | 0 | 82500 | -82500 | 2021-02-26 18:47 | 2022-12-31 | 2021-06-01
75086 | G7STA876 | AW6684 | AW6684 - ROW WARSAW TB RS REPLACEMENT - LAND | 48325.46 |  | 48325.46 |  |  | 48325.46 | 15000 | 33325.46 | 2023-02-15 13:24 | 2023-11-30 | 2023-03-01 | 2023-09-29
75086 | G7STA876 | MX6800938 | MX6800938 - STA 876 WARSAW TOWN BORDER- STATION | 2010706.59 |  | 2010706.59 |  |  | 2347536.4 | 252984 | 2094552.4 | 2018-01-10 18:02 | 2022-09-30 | 2018-01-01 | 2023-09-29
75086 | G7TAM00B | AW2146 | AW2146 - LINE AM00B RETROFIT REPL | 5043.84 |  | 5043.84 |  |  | 14822828.11 | 6528636 | 8294192.11 | 2020-05-19 16:54 | 2022-10-15 | 2020-05-01 | 2022-09-17
75086 | G7TOOLS | 28073 | 28073 - PURCHASE GAS TOOLS BLANKET | 201289.07 |  | 201289.07 |  |  | 1282067.42 | 0 | 1282067.42 | 2000-04-13 | 2015-12-31 | 1999-12-01
75086 | G7TOOLS | AW4691 | AW4691 - CGI UPGRADE KENTUCKY | 10417.92 |  | 10417.92 |  |  | 346112.05 | 120000 | 226112.05 | 2021-10-22 07:34 | 2022-06-30 | 2021-12-01
75086 | G7UL02PH2 | V9444 | V9444 - UL60 PIPELINE PHASE II - PIPE | 53563.43 |  | 53563.43 |  |  | 20998994.65 | 22514005 | -1515010.35 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01 | 2021-11-18
75086 | G7UL57 | AW4824 | AW4824 - STA0917 UL61 CHAMBERS RD TO DIXIE | 3249465.97 |  | 3249465.97 |  |  | 3722694 | 873000 | 2849694 | 2021-12-09 11:26 | 2024-01-31 | 2022-02-01 | 2023-12-26
75086 | G7UL57 | AW4840 | AW4840 - UL61 CHAMBERS RD TO DIXIE HWY- LAND | 10440.37 |  | 10440.37 |  |  | 111854.33 | 82500 | 29354.33 | 2021-12-14 11:10 | 2023-01-31 | 2022-02-01 | 2023-12-26
75086 | G7UL57 | MX9221113 | MX9221113 - UL57 DIXIE HWY REG RPL MAE 9700' OF | 1037129.14 |  | 1037129.14 |  |  | 1037129.14 | 382586.71 | 654542.43 | 2022-12-06 10:02 | 2024-02-28 | 2023-01-01 | 2023-12-19
75086 | OM75086 | GCPBUDKY | GCPBUDKY - BUDGET ONLY - KENT GAS CAP | 6634.92 |  | 6634.92 |  |  | 6634.92 | 0 | 6634.92 | 2018-06-18 12:20 | 2050-12-31 | 2023-05-01
75086 | SG000723F | SG723SW | SG723SW - DEE AMI OPERATIONS TOOL | 65.74 |  | 65.74 |  |  | 32589.3 | 26599 | 5990.3 | 2020-03-03 09:59 | 2022-07-30 | 2020-03-01 | 2022-07-31
75086 | SG001117F | SG001117 | SG001117 - DEE LMR CONSOLES | -1630.9 |  | -1630.9 |  |  | 97462.33 | 124921 | -27458.67 | 2021-08-25 20:43 | 2023-03-31 | 2021-10-01 | 2022-11-30
75086 | SG001135F | CGRREPLA | CGRREPLA - CGR REPLACE DEK GAS | 31245.642 |  | 31245.642 |  |  | 31245.642 | 0 | 31245.642 | 2023-03-06 13:28 | 2050-12-31 | 2023-04-01
75087 | CUSTCONN | 315986F | 315986F - CUSTOMER CONNECT- R6-8 SCOPE | 22.49 |  | 22.49 |  |  | 461877.02 | 53917 | 407960.02 | 2021-03-30 10:49 | 2022-06-30 | 2021-04-01 | 2022-07-06
75087 | CUSTCONN | 315986HW8 | 315986HW8 - CUSTOMER CONNECT- HARDWARE PROJ 6 | -11.85 |  | -11.85 |  |  | 37329.56 | 67100 | -29770.44 | 2021-09-27 15:20 | 2022-06-30 | 2021-10-01 | 2022-09-15
75087 | CUSTCONN | 400109 | 400109 - CUST ENHANCEMENT AND OPTIMIZATION | 239515.17 |  | 239515.17 |  |  | 370083.58 | 480680 | -110596.42 | 2022-06-20 14:30 | 2024-01-19 | 2022-07-01 | 2024-01-26
75087 | CUSTCONN | 400109M | 400109M - MY ACCOUNT MODERNIZATION | 41873.36 |  | 41873.36 |  |  | 41873.36 | 135363 | -93489.64 | 2023-06-09 11:52 | 2025-03-31 | 2023-06-01 | 2025-01-16
75087 | FPIT | 307482003 | 307482003 - CUSTOMER MOBILE APP - PHASE 4 | 8146.34 |  | 8146.34 |  |  | 172002.5 | 24891 | 147111.5 | 2021-12-30 10:36 | 2023-03-31 | 2022-01-01 | 2023-03-31
75087 | FPIT | 400055004 | 400055004 - INSPECTION PORTAL 2021 | 2342.98 |  | 2342.98 |  |  | 11813.78 | 10727 | 1086.78 | 2020-12-16 18:31 | 2023-07-03 | 2022-01-01 | 2023-07-31
75087 | FPIT | 400055005 | 400055005 - BUILDER PORTAL 2021 | 3085.83 |  | 3085.83 |  |  | 15391.47 | 17824 | -2432.53 | 2020-12-10 18:21 | 2023-09-30 | 2021-01-01 | 2023-09-30
75087 | FPIT | 400055015 | 400055015 - ATLANTIS (CUSTOMER ANALYTICS ENGINE | 12443.92 |  | 12443.92 |  |  | 25280.71 | 22832 | 2448.71 | 2021-12-29 10:35 | 2023-12-30 | 2022-01-01 | 2024-01-01
75087 | FPIT | 400055016 | 400055016 - TITAN (VOICE OF THE CUSTOMER ENGAGE | 2186.68 |  | 2186.68 |  |  | 15045.41 | 11104 | 3941.41 | 2021-12-20 13:25 | 2023-10-31 | 2022-01-01 | 2023-10-31
75087 | FPIT | 400055017 | 400055017 - DIGITAL ASSISTANT PLATFORM 2022 ENH | 5248.29 |  | 5248.29 |  |  | 27367.98 | 15150 | 12217.98 | 2021-12-20 10:25 | 2023-06-30 | 2022-01-01 | 2023-07-04
75087 | FPIT | 400055022 | 400055022 - BUSINESS OUTBOUND NOTIFICATION PLAT | -19.26 |  | -19.26 |  |  | 0 | 5949 | -5949 | 2022-05-19 11:29 | 2023-03-31 | 2022-10-01 | 2023-03-31
75087 | FPIT | 400055023 | 400055023 - USAGE ALERTS PHASE 2 | 17190.36 |  | 17190.36 |  |  | 17190.36 | 23299 | -6108.64 | 2022-12-15 19:09 | 2024-06-29 | 2023-01-01 | 2024-06-30
75087 | FPIT | 400055024 | 400055024 - SERVICE NAVIGATOR | 15942.96 |  | 15942.96 |  |  | 15942.96 | 22425 | -6482.04 | 2022-12-20 19:47 | 2024-06-30 | 2023-01-01 | 2024-07-31
75087 | FPIT | 400055025 | 400055025 - DIGITAL CARE PLATFORM | 33315.25 |  | 33315.25 |  |  | 33315.25 | 25411 | 7904.25 | 2023-03-14 09:59 | 2024-03-31 | 2023-03-01 | 2024-03-31
75087 | FPIT | 400055026 | 400055026 - INSPECTOR PORTAL PHASE 3 | 3442.01 |  | 3442.01 |  |  | 3442.01 | 2491 | 951.01 | 2023-06-28 10:38 | 2024-03-29 | 2023-07-01 | 2024-03-31
75087 | FPIT | 400055029 | 400055029 - IVR VOICE AUTHENTICATION | 55106.98 |  | 55106.98 |  |  | 55106.98 | 77856 | -22749.02 | 2023-10-19 13:17 | 2025-06-29 | 2023-10-01 | 2025-01-31
75087 | FPIT | 400055030 | 400055030 - SAP & BUSINESS CUSTOMER WEB PORTAL | 24274.68 |  | 24274.68 |  |  | 24274.68 | 212277 | -188002.32 | 2023-11-01 02:36 | 2025-09-30 | 2023-11-01 | 2025-07-31
75087 | FPIT | 400055031 | 400055031 - D-E.COM/MY ACCOUNT WEB | 1592.93 |  | 1592.93 |  |  | 1592.93 | 22654 | -21061.07 | 2023-10-31 07:30 | 2025-06-29 | 2023-11-01 | 2025-07-15
75087 | FPIT | 400055032 | 400055032 - CUSTOMER - MOBILE APPLICATION | 7755.97 |  | 7755.97 |  |  | 7755.97 | 42720 | -34964.03 | 2023-10-31 04:40 | 2025-07-30 | 2023-11-01 | 2025-07-15
75087 | FPIT | CO2200002 | CO2200002 - UTILITY ASSISTANCE MODERN ARCHITECT | 1143.76 |  | 1143.76 |  |  | 1994.58 | 3296 | -1301.42 | 2022-06-30 10:34 | 2022-12-29 | 2022-07-01 | 2023-03-15
75087 | FPIT | CO2300002 | CO2300002 - GIFT CARD INVENTORY MODERN ARCHITEC | 1116.67 |  | 1116.67 |  |  | 1116.67 | 1823 | -706.33 | 2023-05-31 13:28 | 2024-10-30 | 2023-06-01 | 2025-01-30
75087 | FPIT | CS2100010 | CS2100010 - CONTACT CENTER WORK FROM HOME | 1178.33 |  | 1178.33 |  |  | 2317.92 | 4849 | -2531.08 | 2022-01-26 14:25 | 2022-11-28 | 2022-02-01 | 2023-01-06
75087 | FPIT | CS2200002 | CS2200002 - IVR ENHANCEMENTS 2022 | 287.48 |  | 287.48 |  |  | 4042.97 | 20162 | -16119.03 | 2022-05-05 13:03 | 2023-05-01 | 2022-05-01 | 2023-04-30
75087 | FPIT | CS2200005 | CS2200005 - UPLAND RIGHT ANSWER LICENSE PURCHAS | -4206.45 |  | -4206.45 |  |  | 7983.09 | 7962 | 21.09 | 2022-08-03 15:29 | 2023-01-29 | 2022-12-01 | 2023-05-31
75087 | FPIT | CS2200006 | CS2200006 - VERINT UPGRADE | 24239.45 |  | 24239.45 |  |  | 79192.68 | 80257 | -1064.32 | 2022-11-04 16:13 | 2024-03-31 | 2022-11-01 | 2024-03-31
75087 | FPIT | CS2200007 | CS2200007 - FND LICENSES ADDITIONAL ENDPOINTS | -5.01 |  | -5.01 |  |  | 7822.52 | 7591 | 231.52 | 2022-11-01 10:57 | 2023-03-30 | 2022-12-01 | 2023-03-22
75087 | FPIT | CS2200008 | CS2200008 - AVAYA PLATFORM UPGRADE - SERVER | 31152.92 |  | 31152.92 |  |  | 45669.46 | 44473 | 1196.46 | 2022-11-14 12:16 | 2024-03-31 | 2022-11-01 | 2024-03-31
75087 | FPIT | CS2300001 | CS2300001 - CCO REMOTE WORKSTATION EQUIPMENT | 7331.51 |  | 7331.51 |  |  | 7331.51 | 8282 | -950.49 | 2023-02-03 15:54 | 2024-01-31 | 2023-03-01 | 2024-01-31
75087 | FPIT | TC2300028 | TC2300028 - 3 YR NEWS GOTHIC FONT LICENSE | 2259.35 |  | 2259.35 |  |  | 2259.35 | 2277 | -17.65 | 2023-06-06 15:42 | 2023-09-24 | 2023-07-01 | 2023-09-26
75087 | FPIT | TC2300036 | TC2300036 - SAP CUSTOMER SYSTEM CHANGES AND ENH | 9337.14 |  | 9337.14 |  |  | 9337.14 | 23896 | -14558.86 | 2023-08-07 15:13 | 2024-08-29 | 2023-08-01 | 2024-08-31
75087 | FPIT | TC2300037 | TC2300037 - SAP ENABLE NOW APPLICATION | 5770.83 |  | 5770.83 |  |  | 5770.83 | 5061 | 709.83 | 2023-08-09 16:47 | 2024-03-30 | 2023-08-01 | 2024-03-31
75088 | CY1900015 | 349395006 | 349395006 - ITOT OT SIEM PHASE 2 HW WORKSTREAM | -54262.5 |  | -54262.5 |  |  | 0 | 5497 | -5497 | 2020-04-13 16:35 | 2022-10-28 | 2020-05-01
75088 | CY1900015 | 349395SW6 | 349395SW6 - ITOT OT SIEM SW WORKSTREAM | -75187.42 |  | -75187.42 |  |  | 0 | 6089 | -6089 | 2021-12-09 13:04 | 2022-10-28 | 2021-12-01
75088 | FPITKG | TC210HW57 | TC210HW57 - CIOPS NERC CIP CYBERARK HW | -285.75 |  | -285.75 |  |  | 0 | 304 | -304 | 2021-12-10 15:18 | 2024-09-30 | 2022-01-01
75088 | FPITKG | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | -1698.5 |  | -1698.5 |  |  | 69.86 | 3357 | -3287.14 | 2021-12-10 14:08 | 2024-03-31 | 2022-02-01 | 2023-12-01
|  |  |  | 100543300.476 | 71817091.3721 | 28726209.1039 | 28.57%

## 2024
Duke Energy Kentucky Natural Gas
Year 2024
Business Unit | Funding Project | Project No. | Project Title/Description | Annual Actual Cost | Annual Original Budget | Variance in Dollars | Variance as Percent | Percent of Budget | Total Actual Project Cost | Total Budget Project Cost | Variance in Dollars | Date Original Budget Start | Date Original Budget End | Date Actual Start | Date Actual End
75086 | 4000156F | 04000156 | 04000156 - DEE EAM NEXTGEN GIS | 414387.41 |  | 414387.41 |  |  | 581229.25 | 599758 | -18528.75 | 2022-12-17 12:31 | 2026-12-31 | 2023-01-01
75086 | 75086 | ARCOS24 | ARCOS24 - DEE ARCOS REPORTS AND ANALYTICS | 60039.85 |  | 60039.85 |  |  | 60039.85 | 60040 | -0.15 | 2024-05-14 12:34 | 2024-09-30 | 2024-05-01 | 2024-07-31
75086 | DVV2023 | 400154001 | 400154001 - MIDWEST GAS UPLIFT - KENTUCKY | 86573.78 |  | 86573.78 |  |  | 86573.78 | 97995 | -11421.22 | 2023-12-08 04:50 | 2025-12-29 | 2024-01-01
75086 | FMDT2020 | MDTGAS20 | MDTGAS20 - INSTALL WIN 7 PANASONIC TOUGHBOOKS | -58669.07 |  | -58669.07 |  |  | 522866.68 | 403995 | 118871.68 | 2019-10-10 14:30 | 2021-03-31 | 2019-12-01 | 2021-03-31
75086 | FP00ISENT | IT2400036 | IT2400036 - EMISSSIONS PHASE II | 75590.31 |  | 75590.31 |  |  | 75590.31 | 193878 | -118287.69 | 2024-11-13 02:56 | 2026-03-31 | 2024-11-01
75086 | FP00ISENT | IT2400064 | IT2400064 - NGBU DIGITAL MOBILE PORTFOLIO | 65877.41 |  | 65877.41 |  |  | 65877.41 | 155769 | -89891.59 | 2024-11-12 02:27 | 2026-03-31 | 2024-11-01
75086 | FPIT | 349472020 | 349472020 - SLATE - EAM WORK MGMT SCHEDULING TO | 7100.31 |  | 7100.31 |  |  | 52675.38 | 22340 | 30335.38 | 2022-03-18 16:15 | 2024-06-30 | 2022-03-01 | 2024-06-30
75086 | FPIT | 349472021 | 349472021 - FMA ENHANCEMENTS | 368.4 |  | 368.4 |  |  | 9747.93 | 4713 | 5034.93 | 2022-05-18 12:26 | 2026-03-31 | 2022-06-01
75086 | FPIT | 349472023 | 349472023 - SMALLWORLD ENHANCEMENTS | 4325.99 |  | 4325.99 |  |  | 26657.07 | 15341 | 11316.07 | 2022-09-29 18:21 | 2025-03-30 | 2022-11-01 | 2024-03-31
75086 | FPIT | 349472028 | 349472028 - NEW FMA ENHANCEMENTS | 10469.37 |  | 10469.37 |  |  | 22232.58 | 9670 | 12562.58 | 2023-04-14 17:52 | 2026-03-31 | 2023-04-01
75086 | FPIT | 349472029 | 349472029 - MAXIMO INTEGRATIONS AND OTHER ENHAN | 17054.39 |  | 17054.39 |  |  | 37469.83 | 19914 | 17555.83 | 2023-04-06 12:33 | 2026-03-31 | 2023-04-01
75086 | FPIT | 349472030 | 349472030 - ESRI UPGRADE TO 10.9 | 349.9 |  | 349.9 |  |  | 23260.65 | 6738 | 16522.65 | 2023-04-21 13:07 | 2024-03-30 | 2023-04-01 | 2024-03-31
75086 | FPIT | 349472031 | 349472031 - MATERIAL ISSUE LIGHTING APPLICATION | 630.76 |  | 630.76 |  |  | 1546.6 | 4516 | -2969.4 | 2023-10-20 11:44 | 2024-06-30 | 2023-10-01 | 2024-06-30
75086 | FPIT | 349472032 | 349472032 - EAM - ARGUS ENHANCEMENTS | 13731.4 |  | 13731.4 |  |  | 13731.4 | 8290 | 5441.4 | 2024-01-30 08:06 | 2026-03-31 | 2024-02-01
75086 | FPIT | 349472033 | 349472033 - EAM MOBILEMAX & LIGHTING SUPPORT | 18328.55 |  | 18328.55 |  |  | 18328.55 | 4834 | 13494.55 | 2023-12-22 09:28 | 2026-03-31 | 2024-01-01
75086 | FPIT | 349472034 | 349472034 - EAM DATA PRODUCTS MADE | 5110.68 |  | 5110.68 |  |  | 5110.68 | 31355 | -26244.32 | 2024-02-20 05:11 | 2026-03-31 | 2024-02-01
75086 | FPIT | 349472S14 | 349472S14 - NEW ESRI INTEGRATIONS AND INFRA | 76.32 |  | 76.32 |  |  | 59971.81 | 532359 | -472387.19 | 2021-02-09 13:04 | 2023-11-30 | 2021-03-01 | 2024-03-06
75086 | FPIT | 400149HW2 | 400149HW2 - ESCA - ITOT CYBER CARBON BLACK HW | 1500.87 |  | 1500.87 |  |  | 2176.65 | 2282 | -105.35 | 2023-08-09 12:36 | 2026-03-31 | 2023-08-01
75086 | FPIT | 400149SW2 | 400149SW2 - ESCA - ITOT CYBER CARBON BLACK SW | 2174.7 |  | 2174.7 |  |  | 2174.7 | 4067 | -1892.3 | 2023-08-08 10:18 | 2026-03-31 | 2024-01-01
75086 | FPIT | 400161002 | 400161002 - CISCO LICENSE SPA 2024 | 25766.38 |  | 25766.38 |  |  | 25766.38 | 28490 | -2723.62 | 2024-06-18 08:17 | 2025-01-30 | 2024-06-01 | 2024-10-01
75086 | FPIT | IT2200155 | IT2200155 - GAS SUPPLY - AUTOMATING CONFIRMATIO | 4219.97 |  | 4219.97 |  |  | 29389.46 | 67905 | -38515.54 | 2022-12-28 15:04 | 2024-06-30 | 2023-01-01 | 2023-10-31
75086 | FPIT | IT2200157 | IT2200157 - FUTURE STATE 811 5 STATE LOCATE | 2415.82 |  | 2415.82 |  |  | 72130.11 | 71696 | 434.11 | 2022-12-05 13:37 | 2024-04-30 | 2022-12-01 | 2024-04-30
75086 | FPIT | IT2200160 | IT2200160 - NGBU-AI FRAMEWORK | 113319.15 |  | 113319.15 |  |  | 177403.34 | 185731.65 | -8328.31 | 2022-12-13 14:38 | 2027-03-30 | 2023-01-01
75086 | FPIT | IT2200165 | IT2200165 - NGBU TRACEABILITY PLATFORM | 46423.27 |  | 46423.27 |  |  | 92028.49 | 125985 | -33956.51 | 2022-12-01 16:03 | 2026-03-31 | 2023-01-01
75086 | FPIT | IT2200175 | IT2200175 - LOTO PROCEDURES DEVONWAY SOLUTIONS | 1145.21 |  | 1145.21 |  |  | 12516.09 | 23704 | -11187.91 | 2022-12-21 08:40 | 2024-08-31 | 2023-01-01 | 2024-08-31
75086 | FPIT | IT2300049 | IT2300049 - GTIS EDI SOLUTION | 16512.04 |  | 16512.04 |  |  | 43457.03 | 48240 | -4782.97 | 2023-08-17 15:16 | 2024-07-30 | 2023-08-01 | 2024-07-20
75086 | FPIT | IT2300096 | IT2300096 - TIMP DATA INTEGRATION AND ALIGNMENT | 95328.69 |  | 95328.69 |  |  | 95328.69 | 75811 | 19517.69 | 2023-11-30 10:33 | 2026-06-29 | 2024-01-01
75086 | FPIT | IT2300097 | IT2300097 - TEMPORARY GAS ORDER ENTRY SYSTEM (T | 11832.42 |  | 11832.42 |  |  | 11832.42 | 15803 | -3970.58 | 2024-03-07 08:52 | 2025-03-31 | 2024-03-01 | 2024-12-31
75086 | FPIT | IT2300098 | IT2300098 - MAJOR PROJECTS DIGITAL INSPECTION | 34071.89 |  | 34071.89 |  |  | 34071.89 | 41810 | -7738.11 | 2024-01-03 10:17 | 2025-05-28 | 2024-01-01 | 2025-05-24
75086 | FPIT | IT2300102 | IT2300102 - GTIS 3-YEAR PLAN / EDI PLATFORM | 91048.29 |  | 91048.29 |  |  | 91048.29 | 336772 | -245723.71 | 2023-11-30 11:43 | 2026-06-29 | 2024-01-01
75086 | FPIT | IT2300103 | IT2300103 - NGBU DATA FABRICS BUILD | 34638.32 |  | 34638.32 |  |  | 34638.32 | 229894 | -195255.68 | 2024-02-06 23:28 | 2027-03-31 | 2024-02-01
75086 | FPIT | IT2400006 | IT2400006 - PCS INSPECTION TOOL REPLACEMENT | 20611.16 |  | 20611.16 |  |  | 20611.16 | 50039 | -29427.84 | 2024-02-18 23:38 | 2025-03-31 | 2024-02-01 | 2025-03-31
75086 | FPIT | IT2400017 | IT2400017 - MICROSOFT PRODUCTIVITY SUITE FIVE | 142932.49 |  | 142932.49 |  |  | 142932.49 | 115668 | 27264.49 | 2024-05-07 06:07 | 2024-08-28 | 2024-05-01 | 2024-08-30
75086 | FPIT | IT2400024 | IT2400024 - BEACON PLUME INVESTIGATION WORK | 26871.91 |  | 26871.91 |  |  | 26871.91 | 22730 | 4141.91 | 2024-06-05 06:22 | 2025-04-30 | 2024-06-01 | 2025-03-31
75086 | FPIT | IT2400042 | IT2400042 - BEACON MIDWEST COMPLIANCE WORK ORDE | 3429.93 |  | 3429.93 |  |  | 3429.93 | 90096 | -86666.07 | 2024-08-09 03:29 | 2025-06-29 | 2024-10-01 | 2024-12-31
75086 | FPIT | LTHGIRFS | LTHGIRFS - LIGHTHOUSE: GAS IRIS | 136944.5 |  | 136944.5 |  |  | 565960.68 | 218641 | 347319.68 | 2020-05-20 12:10 | 2025-03-01 | 2020-06-01 | 2025-04-16
75086 | FPIT | LTHGVISTO | LTHGVISTO - LIGHTHOUSE INITIATIVE - GAS VISTO | 61424.73 |  | 61424.73 |  |  | 121230.21 | 88003 | 33227.21 | 2023-05-25 08:00 | 2024-09-30 | 2023-06-01 | 2024-09-30
75086 | FPIT | LTHNGBUDP | LTHNGBUDP - LIGHTHOUSE INITIATIVE: NGBU | 93365.41 |  | 93365.41 |  |  | 93365.41 | 91438 | 1927.41 | 2023-12-05 04:17 | 2025-02-28 | 2024-01-01 | 2025-04-01
75086 | FPIT | PH2ASPAHW | PH2ASPAHW - ESCA-OT ASSET,PATCH & VULNERABILITY | 3255.54 |  | 3255.54 |  |  | 3527.39 | 3196 | 331.39 | 2023-09-01 09:44 | 2026-03-31 | 2023-10-01
75086 | FPIT | PH2ASPASW | PH2ASPASW - ESCA-OT ASSET,PATCH & VULNERABILITY | 50368.26 |  | 50368.26 |  |  | 75710.55 | 323116 | -247405.45 | 2023-09-01 03:52 | 2026-03-31 | 2023-09-01
75086 | FPIT | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | 164.27 |  | 164.27 |  |  | 3308.55 | 3357 | -48.45 | 2023-03-27 18:41 | 2024-03-31 | 2023-03-01 | 2024-03-01
75086 | FPIT | TC2400041 | TC2400041 - BROADCOM VMWARE CLOUD FOUNDATION SU | 581093.12 |  | 581093.12 |  |  | 581093.12 | 73156 | 507937.12 | 2024-12-19 08:50 | 2025-09-28 | 2024-12-01
75086 | FUNCTOHKY | 107GASCK | 107GASCK - GAS CAPITAL OVERHEAD | -2476523.31 |  | -2476523.31 |  |  | 198289.744 | 0 | 198289.744 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G701660 | AW4645 | AW4645 - EMERGENT AM01 COVINGTON LEVEE PH 1 | 39575.39 |  | 39575.39 |  |  | 5449700.72 | 3601200 | 1848500.72 | 2021-10-01 08:50 | 2023-01-30 | 2021-10-01 | 2023-02-28
75086 | G701662 | AW4673 | AW4673 - EMERGENT - CASING 34 - TAYLOR MILL | 15828.17 |  | 15828.17 |  |  | 3012506.58 | 3207100 | -194593.42 | 2021-10-13 11:13 | 2023-02-28 | 2021-11-01 | 2023-01-07
75086 | G712237 | MX4669122 | MX4669122 - HEBRON LOOP PH 2 PRESSURE IMPROVEME | 73334.81 |  | 73334.81 |  |  | 181982.46 | 765.33 | 181217.13 | 2021-03-01 14:01 | 2027-03-04 | 2021-03-01
75086 | G73MILES | T1437 | T1437 - STA 249: THREE MILE RD | 95433.11 |  | 95433.11 |  |  | 25538716.87 | 15406228 | 10132488.87 | 2017-01-05 11:19 | 2020-08-28 | 2017-01-01 | 2020-09-15
75086 | G74092 | MX3645041 | MX3645041 - CHARTER - BRISTOW RD. PRESSURE IMP | 1037685.33 |  | 1037685.33 |  |  | 1198465.65 | 2365.83 | 1196099.82 | 2022-10-13 10:01 | 2025-07-24 | 2022-12-01 | 2024-10-28
75086 | G74238 | MX3848219 | MX3848219 - CHARTER - PATTY LN-RPL-2" & 4"PL-87 | 95516.83 |  | 95516.83 |  |  | 95516.83 | 540783.33 | -445266.5 | 2023-12-22 14:01 | 2025-10-02 | 2024-05-01
75086 | G74381 | AW5096 | AW5096 - DRY RIDGE - EXPOSED MAIN | 466.69 |  | 466.69 |  |  | 47361.53 | 33500 | 13861.53 | 2022-02-17 08:25 | 2022-08-31 | 2022-03-01 | 2022-06-17
75086 | G74964 | MX5762350 | MX5762350 - CHARTER - ST RT 536 - INDEPENDANCE | 1073023.76 |  | 1073023.76 |  |  | 1538174.8 | 842182.55 | 695992.25 | 2022-02-23 18:01 | 2024-01-31 | 2022-03-01 | 2023-02-01
75086 | G75449 | AW5471 | AW5471 - LN AM07 SCCDA DIGS | 5382.74 |  | 5382.74 |  |  | 741930.29 | 1642098.73 | -900168.44 | 2022-05-26 13:41 | 2022-12-31 | 2022-06-01 | 2022-11-27
75086 | G75498 | MX0458440 | MX0458440 - CHARTER-AMSTERDAM RD- VILLA HILLS- | 11911.63 |  | 11911.63 |  |  | 69400.32 | 18170.8 | 51229.52 | 2023-09-15 14:01 | 2024-01-29 | 2023-09-01 | 2024-01-03
75086 | G75498 | MX5370534 | MX5370534 - CHARTER-LP03 INSTALL PRESSURE IMPRO | 1724.58 |  | 1724.58 |  |  | 221508.01 | 765.33 | 220742.68 | 2022-07-08 14:01 | 2023-03-30 | 2022-10-01 | 2023-03-06
75086 | G75498 | MX6650945 | MX6650945 - CHARTER-AMSTERDAM RD- VILLA HILLS-P | 1040409.4 |  | 1040409.4 |  |  | 1114428.69 | 251700.17 | 862728.52 | 2022-12-20 14:01 | 2025-02-27 | 2023-02-01 | 2025-01-07
75086 | G75629 | AW5648 | AW5648 - LN AM07 ECDA DIGS | 7307.47 |  | 7307.47 |  |  | 2029435.66 | 1466970.34 | 562465.32 | 2022-07-01 09:23 | 2022-12-31 | 2022-07-01 | 2023-01-20
75086 | G75683 | MX4850228 | MX4850228 - TOEBBEN DR - FLORENCE - 12" PL & 8" | 475.17 |  | 475.17 |  |  | 420680.58 | 49862.08 | 370818.5 | 2022-07-14 14:01 | 2022-12-29 | 2022-07-01 | 2022-12-26
75086 | G75723 | MX2532997 | MX2532997 - CHARTER-RICHARD KNOCK HWY-PIMP-8" P | 124844.69 |  | 124844.69 |  |  | 124844.69 | 143363.15 | -18518.46 | 2024-01-31 14:01 | 2025-06-26 | 2024-02-01 | 2025-05-14
75086 | G75723 | MX6588233 | MX6588233 - CANCEL-RICHARD KNOCK HWY-WALTON-MA | -25429.79 |  | -25429.79 |  |  | 0 | 0 | 0 | 2023-03-21 14:01 | 2025-08-30 | 2023-05-01
75086 | G75734 | AW6846 | AW6846 - KENTUCKY - CORROSION REMEDIATION | 344658.77 |  | 344658.77 |  |  | 402658.63 | 180000 | 222658.63 | 2023-03-24 11:42 | 2025-09-30 | 2023-07-01
75086 | G75920 | AW5953 | AW5953 - LN AM07 STATION ECDA DIGS | 4274.73 |  | 4274.73 |  |  | 845578.5 | 734403.62 | 111174.88 | 2022-07-29 15:51 | 2022-12-31 | 2022-08-01 | 2023-01-20
75086 | G75924 | AW5965 | AW5965 - LN AM00B ECDA DIGS | 4079.82 |  | 4079.82 |  |  | 894160.08 | 1098620 | -204459.92 | 2022-08-03 13:21 | 2022-12-31 | 2022-08-01 | 2023-01-31
75086 | G75979 | MX4329859 | MX4329859 - CHARTER-KYTC 06-445.00 MINEOLA PK-E | 25532.02 |  | 25532.02 |  |  | 1177131.41 | 697743.72 | 479387.69 | 2022-09-12 10:01 | 2024-03-28 | 2022-10-01 | 2023-12-06
75086 | G75995 | AW6478 | AW6478 - LINE AM07 - CASING 50 - HYDROTEST | 255492.11 |  | 255492.11 |  |  | 548321.63 | 2386600 | -1838278.37 | 2022-12-30 12:47 | 2024-10-01 | 2023-02-01 | 2024-09-10
75086 | G76300 | AW6368 | AW6368 - EMERGENT - AM07 EXPOSED MAIN (KY) | 55.16 |  | 55.16 |  |  | 1349136.57 | 1348700 | 436.57 | 2022-11-16 13:54 | 2023-12-30 | 2022-11-01 | 2024-01-09
75086 | G76444 | MX6909455 | MX6909455 - KYTC 06-444 DONALDSON-ERLANGER-STI | 479409.16 |  | 479409.16 |  |  | 2316774 | 1219782.34 | 1096991.66 | 2023-04-05 18:01 | 2024-09-01 | 2023-04-01 | 2024-05-29
75086 | G76446 | MX1322454 | MX1322454 - CHARTER-KYTC-162.40-BRISTOW RD-STI- | 1520404.48 |  | 1520404.48 |  |  | 1633776.2 | 786869.97 | 846906.23 | 2022-10-07 14:01 | 2025-10-29 | 2022-10-01 | 2025-03-07
75086 | G76451 | MX8051147 | MX8051147 - CHARTER-SPARTA PIKE-EXPOSED MAIN RE | 942.5 |  | 942.5 |  |  | 180750.27 | 9490.2 | 171260.07 | 2023-05-02 10:01 | 2025-03-31 | 2023-09-01 | 2024-02-09
75086 | G76569 | AW6597 | AW6597 - EMERGENT - 6-9025 KY MAIN RELOCATE | 3802315.89 |  | 3802315.89 |  |  | 4361774.94 | 3971500 | 390274.94 | 2023-02-02 08:37 | 2024-07-15 | 2023-02-01 | 2024-08-02
75086 | G77046 | MX9473869 | MX9473869 - CHARTER-EMERGENT - MADISON PIKE - E | 10104.44 |  | 10104.44 |  |  | 222890.41 | 267037 | -44146.59 | 2023-07-27 18:01 | 2024-01-13 | 2023-07-01 | 2023-12-21
75086 | G77138 | 500000144 | 500000144 - THREE MILE - VRG CONTROL VALVE REPL | 4329.83 |  | 4329.83 |  |  | 14287.27 | 22770 | -8482.73 | 2023-06-29 10:08 | 2024-01-31 | 2023-08-01 | 2024-04-27
75086 | G77762 | 500000547 | 500000547 - INTERNAL CORR COUPON INSTALL KY | 21905.96 |  | 21905.96 |  |  | 21905.96 | 13890.8 | 8015.16 | 2024-06-17 18:01 | 2025-03-24 | 2024-10-01 | 2025-03-06
75086 | G77799 | MX0356982 | MX0356982 - CHARTER-KYTC- 162.10 BRISTOW RD FRO | 166843.3 |  | 166843.3 |  |  | 166843.3 | 278044.58 | -111201.28 | 2024-01-18 14:01 | 2026-02-05 | 2024-02-01
75086 | G78143 | 500000493 | 500000493 - OC-TC ENERGY FOSTER INTERCONNECTSCA | 43475.27 |  | 43475.27 |  |  | 43475.27 | 74946.01 | -31470.74 | 2024-04-10 14:01 | 2024-07-30 | 2024-04-01 | 2024-09-07
75086 | G78373 | AW8410 | AW8410 - OC-REG 0149 - ERLANGER M&R 149 UPGR | 2138548.77 |  | 2138548.77 |  |  | 2138548.77 | 11169500 | -9030951.23 | 2024-06-25 09:46 | 2026-03-31 | 2024-07-01
75086 | G78478 | 500000576 | 500000576 - OC - MIDWEST - ERX INSTALL KY | 17550.53 |  | 17550.53 |  |  | 17550.53 | 36086.84 | -18536.31 | 2024-09-06 10:01 | 2025-01-31 | 2024-10-01 | 2025-03-12
75086 | G78502 | AW78502 | AW78502 - EMERGENCY CHARTER 24'' AMO7 CUT OUT | 161477.77 |  | 161477.77 |  |  | 161477.77 | 99000 | 62477.77 | 2024-08-06 14:07 | 2024-12-05 | 2024-08-01 | 2024-11-08
75086 | G7AM00ACR | AW3397 | AW3397 - LINE AM00A CORROSION REMEDIATION | 1557.85 |  | 1557.85 |  |  | 195074.89 | 180372.32 | 14702.57 | 2021-01-20 10:04 | 2022-03-31 | 2021-12-01 | 2022-03-20
75086 | G7AM00BVL | V5471 | V5471 - AM00B & UL06 VALVE AUTOMATION | 157560.79 |  | 157560.79 |  |  | 629862.1 | 1830100 | -1200237.9 | 2021-11-22 12:33 | 2023-12-30 | 2022-04-01 | 2023-12-06
75086 | G7AM07CUT | AW1330 | AW1330 - AM07 CUTOUT FIDELITY | 4812.76 |  | 4812.76 |  |  | 1612522.56 | 1236780 | 375742.56 | 2019-10-23 11:50 | 2019-12-30 | 2019-10-01 | 2020-02-02
75086 | G7AM07DIG | V8815 | V8815 - LINE AM07 INTEGRITY DIGS | 3525.11 |  | 3525.11 |  |  | 1310515.42 | 923350 | 387165.42 | 2019-04-02 12:33 | 2019-12-30 | 2019-06-01 | 2019-12-31
75086 | G7AM07IL2 | AW4685 | AW4685 - LINE AM07 PIPELINE REPLACEMENT PHAS | 40506360.37 |  | 40506360.37 |  |  | 47921113.27 | 33015500 | 14905613.27 | 2021-10-18 16:29 | 2025-02-28 | 2021-11-01 | 2025-02-06
75086 | G7AM07IL2 | AW5957 | AW5957 - CANCEL_LINE AM07 PHASE 2 - STATION | -2432308.78 |  | -2432308.78 |  |  | 0 | 9656000 | -9656000 | 2022-08-01 15:12 | 2025-02-28 | 2022-10-01
75086 | G7AM07IL2 | AW7013 | AW7013 - ROW - PIPELINE REPLACEMENT - PH2 | 158776.6 |  | 158776.6 |  |  | 345934.1 | 4284600 | -3938665.9 | 2023-05-18 14:09 | 2025-04-18 | 2023-09-01 | 2025-02-06
75086 | G7AM07IL3 | AW6387 | AW6387 - LINE AM07 - PIPE REPLACEMENT - PH 3 | 3179242.24 |  | 3179242.24 |  |  | 4035307.16 | 40828200 | -36792892.84 | 2022-11-23 12:26 | 2025-12-31 | 2023-01-01
75086 | G7AM07IL3 | AW6388 | AW6388 - LINE AM07 PHASE 3 - LAND | 2026490.57 |  | 2026490.57 |  |  | 2119791.69 | 4060000 | -1940208.31 | 2022-11-28 09:37 | 2025-12-31 | 2023-09-01
75086 | G7AM07IL3 | AW7772 | AW7772 - LINE AM07 PHASE 3 - STATION | 895028.38 |  | 895028.38 |  |  | 895028.38 | 4905200 | -4010171.62 | 2023-12-18 12:17 | 2025-12-31 | 2024-01-01
75086 | G7AM07IL4 | AW7866 | AW7866 - LINE AM07 PHASE 4 - PIPE | 1228269.08 |  | 1228269.08 |  |  | 1228269.08 | 60559700 | -59331430.92 | 2024-01-29 15:53 | 2027-03-30 | 2024-02-01
75086 | G7AM07IL4 | AW7883 | AW7883 - LINE AM07 PHASE 4 - LAND | 990.57 |  | 990.57 |  |  | 990.57 | 7551100 | -7550109.43 | 2024-01-31 01:46 | 2027-03-30 | 2024-11-01
75086 | G7AM07ILI | 0233100 | 0233100 - LINE AM07 PIPELINE REPLACEMENT PHAS | -963379.53 |  | -963379.53 |  |  | 25239830.82 | 37717000 | -12477169.18 | 2020-12-09 14:11 | 2023-12-31 | 2020-12-01 | 2024-03-18
75086 | G7AM07ILI | AW3074 | AW3074 - LINE AM07 PIPELINE REPLACE LAND | -71753.41 |  | -71753.41 |  |  | 5578303.16 | 6089500 | -511196.84 | 2020-12-03 12:25 | 2023-12-31 | 2021-02-01 | 2024-03-18
75086 | G7AM07ILI | AW3138 | AW3138 - LINE AM07 PIPELINE REPLACEMENT-STN | 9090245.23 |  | 9090245.23 |  |  | 18757283.906 | 6278300 | 12478983.906 | 2020-12-18 13:08 | 2024-04-30 | 2021-05-01 | 2024-09-28
75086 | G7ASRP | CMSP70 | CMSP70 - ASRP CURB TO METER 3" OR LESS | 268884.08 |  | 268884.08 |  |  | 9217729.35 | 20388002 | -11170272.65 | 2015-03-04 11:36 | 2019-12-31 | 2015-07-01
75086 | G7ASRP | MCSP70 | MCSP70 - ASRP MAIN TO CURB 3" OR LESS | 2606336.17 |  | 2606336.17 |  |  | 46571064.763 | 19954384 | 26616680.763 | 2015-03-04 11:18 | 2019-12-31 | 2015-07-01
75086 | G7CAS106 | V7737 | V7737 - CASING#106 AM07 & MARTHA LAYNE | 4765.3 |  | 4765.3 |  |  | 1994498.76 | 1749344 | 245154.76 | 2018-11-28 14:40 | 2019-12-30 | 2018-12-01 | 2020-01-23
75086 | G7CAS42 | V7739 | V7739 - CASING#42 ABANDON- AM07 & HULBERT | 9386.74 |  | 9386.74 |  |  | 1707520.45 | 1939294 | -231773.55 | 2018-11-28 14:52 | 2019-11-30 | 2018-12-01 | 2019-11-15
75086 | G7CAS49 | V7902 | V7902 - CASING #49 ABANDON - AM07 & I-75 | 18029.1 |  | 18029.1 |  |  | 7354093.39 | 6131715 | 1222378.39 | 2018-12-14 14:26 | 2020-02-28 | 2019-01-01 | 2020-02-23
75086 | G7CORREM | AW5064 | AW5064 - KENTUCKY - CORROSION REMEDIATION | 37718.03 |  | 37718.03 |  |  | 251254.91 | 272000 | -20745.09 | 2022-02-10 15:46 | 2025-09-30 | 2022-08-01
75086 | G7EDGE | 39171904 | 39171904 - CANCEL-ROW- EDGEWOOD PRESSURE IMP | -36523.58 |  | -36523.58 |  |  | 0 | 40000 | -40000 | 2022-06-07 07:26 | 2023-01-31 | 2022-08-01
75086 | G7EDGE | MX9171904 | MX9171904 - EDGEWOOD PRESSURE IMP | 83776.11 |  | 83776.11 |  |  | 651960.14 | 108825.77 | 543134.37 | 2022-09-22 14:01 | 2023-07-29 | 2022-09-01 | 2023-07-24
75086 | G7EMAM07 | AW5092 | AW5092 - EMERGENT - LINE AM07 - EXPOSED MAIN | 78724.53 |  | 78724.53 |  |  | 2726792.87 | 1319200 | 1407592.87 | 2022-02-15 14:54 | 2023-06-30 | 2022-04-01 | 2023-09-30
75086 | G7ENCC | AW3484 | AW3484 - ERLANGER CASINGS 2021 | 1533.71 |  | 1533.71 |  |  | 215354.91 | 181501.63 | 33853.28 | 2021-01-27 13:42 | 2022-03-31 | 2021-12-01 | 2022-04-13
75086 | G7ERGEMER | AW4046 | AW4046 - EMERGENCY ERLANGER GAS CUT OUT | 490.04 |  | 490.04 |  |  | 292277.64 | 95000 | 197277.64 | 2021-07-06 10:44 | 2021-10-30 | 2021-07-01 | 2021-11-06
75086 | G7ERLCP | AW1656 | AW1656 - ERLANGER MAG ANODES | 34484.1 |  | 34484.1 |  |  | 1628780.59 | 2442881.69 | -814101.1 | 2020-01-21 15:36 | 2026-12-31 | 2020-04-01
75086 | G7ERLCP19 | V9157 | V9157 - 2019 ERLANGER OPS MAG ANODES | 3175.95 |  | 3175.95 |  |  | 393520.36 | 350811.63 | 42708.73 | 2019-05-08 10:16 | 2020-07-30 | 2019-05-01 | 2020-09-08
75086 | G7ESPEP | MX9171927 | MX9171927 - ELSMERE PRESSURE IMP | 9672.46 |  | 9672.46 |  |  | 2489909.02 | 327967.71 | 2161941.31 | 2022-04-25 14:01 | 2023-07-29 | 2022-05-01 | 2023-07-05
75086 | G7EUL47 | V6391 | V6391 - LINE UL47 SCHEDULED DIGS | 915.68 |  | 915.68 |  |  | 990338.41 | 724400 | 265938.41 | 2018-10-10 08:17 | 2019-03-30 | 2018-10-01 | 2019-03-14
75086 | G7HARRPK | AW4778 | AW4778 - ROW - HARRIS PIKE UL45 EXT | 29073.07 |  | 29073.07 |  |  | 167431.12 | 926800 | -759368.88 | 2021-11-16 10:04 | 2026-11-30 | 2022-07-01
75086 | G7HARRPK | AW4796 | AW4796 - HARRIS PIKE UL45 EXT - PRESSURE IMP | 71963.85 |  | 71963.85 |  |  | 744110.79 | 7884400 | -7140289.21 | 2021-11-19 10:02 | 2026-11-30 | 2022-02-01
75086 | G7HICKSP | MX5739585 | MX5739585 - HICKS PIKE PRESSURE IMPROVEMENT PRO | 3597.48 |  | 3597.48 |  |  | 754585.04 | 254017.35 | 500567.69 | 2021-04-20 18:02 | 2022-02-24 | 2021-05-01 | 2022-02-02
75086 | G7HOPECH | MX1415972 | MX1415972 - HOPEFUL CHURCH RD. PRI, FLORENCE 13 | 3403375.03 |  | 3403375.03 |  |  | 3425096.49 | 2073615.27 | 1351481.22 | 2022-12-21 18:01 | 2025-06-26 | 2023-02-01 | 2025-06-17
75086 | G7IMPRPL | MX1996777 | MX1996777 - AM07 EXPOSURE-HORSEBRANCH RD. SEGME | 1692.68 |  | 1692.68 |  |  | 799207.7 | 436474.83 | 362732.87 | 2017-09-11 18:02 | 2019-07-31 | 2017-10-01 | 2019-09-10
75086 | G7IMPRPL | T1525 | T1525 - AM02 EXPOSED MAIN IN SOUTHGATE, KY | 4707.6 |  | 4707.6 |  |  | 4707.6 | 351129.6 | -346422 | 2017-01-12 09:24 | 2018-09-30 | 2017-01-01 | 2018-11-24
75086 | G7INTDIG | AW2017 | AW2017 - LINE UL06 INTEGRITY DIGS | 5117.61 |  | 5117.61 |  |  | 1331121.62 | 2024700 | -693578.38 | 2020-04-09 07:34 | 2021-01-30 | 2020-04-01 | 2021-01-05
75086 | G7INTDIG | AW2018 | AW2018 - LINE UL47 INTEGRITY DIGS | 2500.59 |  | 2500.59 |  |  | 814002.83 | 748000 | 66002.83 | 2020-04-09 07:40 | 2021-01-30 | 2020-04-01 | 2020-10-09
75086 | G7ISREF | KYWSREF24 | KYWSREF24 - KY WORKSTATION REFRESH 2024 | 1100723.94 |  | 1100723.94 |  |  | 1100723.94 | 200000 | 900723.94 | 2024-02-12 15:21 | 2026-02-28 | 2024-06-01
75086 | G7LGMR | C9571 | C9571 - CANCEL 2 STA 781-NUNN & UNV/CWA | 13268.2 |  | 13268.2 |  |  | 12979.98 | 0 | 12979.98 | 2007-04-10 | 2050-12-31 | 2007-04-01 | 2008-05-05
75086 | G7LGMR | MX0671045 | MX0671045 - REG 101 - COVERT RUN & TAYLOR | 898.92 |  | 898.92 |  |  | 168875 | 81442.56 | 87432.44 | 2018-12-06 10:01 | 2019-08-30 | 2019-03-01 | 2019-10-27
75086 | G7LGMR | MX2218039 | MX2218039 - INSTALL SCADA EQ-THREE MILE RD STA | 1426.81 |  | 1426.81 |  |  | 602589.45 | 411228.18 | 191361.27 | 2017-09-21 14:01 | 2020-07-10 | 2017-10-01 | 2020-09-15
75086 | G7LGMR | MX2335804 | MX2335804 - STA 872 - OAKLAND VALVE HOUSE | 51679.46 |  | 51679.46 |  |  | 13843276.58 | 4268942.55 | 9574334.03 | 2017-10-06 18:03 | 2019-08-15 | 2017-11-01 | 2019-09-19
75086 | G7LNUL57 | AW0832 | AW0832 - LINE UL57 MONOLITHIC INSULATORS | 4301.12 |  | 4301.12 |  |  | 1033031.92 | 564646 | 468385.92 | 2019-07-26 13:48 | 2020-12-25 | 2020-03-01 | 2020-12-03
75086 | G7LUL02 | AW2880 | AW2880 - LINE UL02 - MAOP REPLACEMENT | 20536.33 |  | 20536.33 |  |  | 3262606.99 | 1717200 | 1545406.99 | 2020-10-07 12:58 | 2022-03-31 | 2020-10-01 | 2022-01-05
75086 | G7MAINS | AW6146 | AW6146 - CANCEL_ROW LAKELAND PARK DR; LIM | -4251.92 |  | -4251.92 |  |  | 0 | 25000 | -25000 | 2022-09-20 13:09 | 2023-12-31 | 2022-10-01
75086 | G7MAINS | AW6147 | AW6147 - CANCEL-ROW MEA -STANBERY RIDGE | -417.96 |  | -417.96 |  |  | 0 | 25000 | -25000 | 2022-09-20 13:28 | 2023-09-09 | 2022-10-01
75086 | G7MAINS | AW6415 | AW6415 - CANCEL-TBC ROW MEA-DECLARATION DR | -2240.19 |  | -2240.19 |  |  | 4145.9 | 25000 | -20854.1 | 2022-12-05 12:55 | 2023-07-14 | 2023-01-01
75086 | G7MAINS | AW6482 | AW6482 - CANCEL_LIS RD; CONSTANCE; 6" PL | -4176.01 |  | -4176.01 |  |  | 0 | 25000 | -25000 | 2023-01-06 11:45 | 2023-08-25 | 2023-02-01
75086 | G7MAINS | AW6483 | AW6483 - CANCEL_CRESTVW HL; VILLA MADONNA DR | -4240.01 |  | -4240.01 |  |  | -12.82 | 25000 | -25012.82 | 2023-01-06 11:55 | 2023-04-28 | 2023-02-01
75086 | G7MAINS | AW6484 | AW6484 - CANCEL_OLD LEXINGTON PIKE_RICHWOOD | -674.56 |  | -674.56 |  |  | 0 | 25000 | -25000 | 2023-01-06 12:04 | 2023-10-13 | 2023-02-01
75086 | G7MAINS | AW6694 | AW6694 - CANCEL_ROW MEA - MANHATTAN BLVD- | -2778.35 |  | -2778.35 |  |  | -8.43 | 25000 | -25008.43 | 2023-02-20 10:52 | 2023-06-09 | 2023-03-01
75086 | G7MAINS | AW8571 | AW8571 - 526 JOHNS HILL RD - RENEW | 3151.45 |  | 3151.45 |  |  | 3151.45 | 25000 | -21848.55 | 2024-08-30 11:41 | 2025-06-09 | 2024-12-01
75086 | G7MAINS | AW8633 | AW8633 - 211 KY HIGHWAY W 36 - MAE | 3749 |  | 3749 |  |  | 3749 | 25000 | -21251 | 2024-09-26 05:09 | 2025-05-05 | 2024-12-01
75086 | G7MAINS | AW8689 | AW8689 - PETERSBURG RD - MAE - 8" PL - 3,300 | 3177.91 |  | 3177.91 |  |  | 3177.91 | 25000 | -21822.09 | 2024-10-04 03:52 | 2025-05-05 | 2024-12-01
75086 | G7MAINS | AW8766 | AW8766 - DISTRIBUTION DR - MAE - 4" PL - 730 | 1221.25 |  | 1221.25 |  |  | 1221.25 | 25000 | -23778.75 | 2024-11-05 08:43 | 2025-09-20 | 2024-12-01
75086 | G7MAINS | C9770 | C9770 - CANCEL 2 STA 781-INLET/CWA | 9934.97 |  | 9934.97 |  |  | 9826.56 | 0 | 9826.56 | 2007-05-06 | 2050-12-31 | 2007-05-01 | 2008-05-05
75086 | G7MAINS | D1230 | D1230 - CANCEL 2 844337/CHRIS AMPHER | 7033.81 |  | 7033.81 |  |  | 5408.65 | 0 | 5408.65 | 2007-07-23 | 2050-12-31 | 2007-09-01 | 2008-08-12
75086 | G7MAINS | G8058 | G8058 - CANCEL 2 JT EMAX 3298935 ARCADIA | 17910.28 |  | 17910.28 |  |  | 18248.87 | 49594.21 | -31345.34 | 2012-07-13 | 2014-11-30 | 2013-07-01 | 2014-02-26
75086 | G7MAINS | MEAPJT70 | MEAPJT70 - JOINT TRENCH PLASITC MAIN EXTENSION | 1443646.01 |  | 1443646.01 |  |  | 8678583.97 | 10000000 | -1321416.03 | 2016-01-13 11:02 | 2050-12-31 | 2016-02-01
75086 | G7MAINS | MX0245370 | MX0245370 - REDWOOD LIVING APARTMENTS - APPROAC | 1520.18 |  | 1520.18 |  |  | 133048.47 | 53405.95 | 79642.52 | 2021-09-07 10:02 | 2022-05-29 | 2021-09-01 | 2022-04-20
75086 | G7MAINS | MX0458305 | MX0458305 - CULL RD - MAE- 6" PL-650' | 332219.23 |  | 332219.23 |  |  | 332219.23 | 59163.8 | 273055.43 | 2024-02-29 18:01 | 2024-11-07 | 2024-03-01 | 2024-10-30
75086 | G7MAINS | MX0556249 | MX0556249 - FARM TAP PROJ; CALIFORNIA CROSSROAD | 2325.5 |  | 2325.5 |  |  | 273223.93 | 123394.12 | 149829.81 | 2019-01-14 10:01 | 2019-10-24 | 2019-05-01 | 2020-01-03
75086 | G7MAINS | MX0602140 | MX0602140 - FARM TAP PROJ; ENZWEILER RD | 797.23 |  | 797.23 |  |  | 200882.28 | 83366.18 | 117516.1 | 2020-09-01 18:01 | 2021-10-17 | 2020-09-01 | 2021-10-06
75086 | G7MAINS | MX0742327 | MX0742327 - MEA - BEECHWOOD RD; FT MITCHEL; 4" | 85908.64 |  | 85908.64 |  |  | 97675.22 | 58680.03 | 38995.19 | 2023-11-29 14:01 | 2024-04-18 | 2023-12-01 | 2024-04-17
75086 | G7MAINS | MX0840009 | MX0840009 - JT-G- BALLYSHANNON SECTION 5 PHASE | 46522.15 |  | 46522.15 |  |  | 46603.03 | 50460.65 | -3857.62 | 2023-11-07 10:01 | 2024-08-19 | 2023-12-01 | 2024-07-31
75086 | G7MAINS | MX0864994 | MX0864994 - MADONNA MANOR PH 2 MEA, VILLA HILLS | 1233.46 |  | 1233.46 |  |  | 114526.89 | 72524.38 | 42002.51 | 2021-09-24 14:02 | 2021-12-21 | 2021-10-01 | 2022-05-13
75086 | G7MAINS | MX0964990 | MX0964990 - 425' PLASTIC GAS MAIN EXTENSION. SA | 493.24 |  | 493.24 |  |  | 70340.26 | 26396.88 | 43943.38 | 2021-07-19 14:02 | 2024-12-24 | 2021-08-01 | 2022-02-02
75086 | G7MAINS | MX1356700 | MX1356700 - FARM TAP PROJ; WINTERS LN HIGHLAND | 1041.2 |  | 1041.2 |  |  | 255288.49 | 147466.28 | 107822.21 | 2019-06-27 10:02 | 2019-12-26 | 2019-07-01 | 2020-03-11
75086 | G7MAINS | MX1921442 | MX1921442 - FARM TAP PROJECT REDSTONE RD - ALEX | 889.49 |  | 889.49 |  |  | 195801.05 | 74423.61 | 121377.44 | 2021-03-24 10:02 | 2024-10-07 | 2021-04-01 | 2021-11-30
75086 | G7MAINS | MX1957438 | MX1957438 - FARM TAP PROJ; GRANDVIEW RD | 2710.48 |  | 2710.48 |  |  | 497580.67 | 161978.74 | 335601.93 | 2020-09-29 10:01 | 2021-12-16 | 2020-09-01 | 2022-01-10
75086 | G7MAINS | MX1957677 | MX1957677 - FARM TAP PROJECT; UPPER LICK BRANCH | 1518.62 |  | 1518.62 |  |  | 156447.83 | 88637.51 | 67810.32 | 2021-10-12 14:01 | 2022-06-16 | 2021-10-01 | 2022-05-08
75086 | G7MAINS | MX1958084 | MX1958084 - FARM TAP PROJ; FLAGG SPRINGS PIKE | 3335.55 |  | 3335.55 |  |  | 578321.41 | 541626 | 36695.41 | 2020-02-05 10:02 | 2020-05-22 | 2020-02-01 | 2020-10-30
75086 | G7MAINS | MX2043872 | MX2043872 - FARM TAP PROJ; BARRS BRANCH RD | 1059.2 |  | 1059.2 |  |  | 159503.82 | 83717.7 | 75786.12 | 2021-08-20 10:02 | 2022-06-23 | 2021-08-01 | 2022-05-29
75086 | G7MAINS | MX2061333 | MX2061333 - STONEWATER PHASE B1 APPROACH MAIN | 1238.62 |  | 1238.62 |  |  | 160395.16 | 128082.79 | 32312.37 | 2022-02-10 10:02 | 2022-08-04 | 2022-02-01 | 2022-07-21
75086 | G7MAINS | MX2061362 | MX2061362 - JT-G-THE RESERVE AT BELLEVUE | 531.2 |  | 531.2 |  |  | 81168.01 | 46814.99 | 34353.02 | 2021-12-16 18:02 | 2023-03-01 | 2022-01-01 | 2022-12-14
75086 | G7MAINS | MX2143681 | MX2143681 - MAINE AVE - MAE - 2IN PL - 238' | 39699.59 |  | 39699.59 |  |  | 39699.59 | 22070.6 | 17628.99 | 2024-03-07 10:01 | 2024-08-08 | 2024-03-01 | 2024-07-21
75086 | G7MAINS | MX2271880 | MX2271880 - MEA ~800 FT; 494 JONES RD | 1020.14 |  | 1020.14 |  |  | 243948.95 | 163070 | 80878.95 | 2019-07-30 10:01 | 2020-02-27 | 2019-08-01 | 2020-05-13
75086 | G7MAINS | MX2291390 | MX2291390 - MEA-PINNACLE OF FORTH MITCHELL APPR | 15171.97 |  | 15171.97 |  |  | 15171.97 | 10940.87 | 4231.1 | 2024-02-01 14:01 | 2024-07-07 | 2024-02-01 | 2024-05-30
75086 | G7MAINS | MX2291478 | MX2291478 - THE RESERVES OF EDGEWOOD - APP MAE | 20058.95 |  | 20058.95 |  |  | 20058.95 | 15290.78 | 4768.17 | 2024-05-20 18:01 | 2024-10-17 | 2024-05-01 | 2024-09-23
75086 | G7MAINS | MX2331188 | MX2331188 - MEA, MASON ROAD FARM TAP-TAYLOW MIL | 5436 |  | 5436 |  |  | 613957.62 | 240393.36 | 373564.26 | 2021-09-15 18:02 | 2022-08-25 | 2021-10-01 | 2022-08-02
75086 | G7MAINS | MX2698978 | MX2698978 - E MT ZION RD; INDEPENDENCE; 6" PL; | 3153.95 |  | 3153.95 |  |  | 530855.71 | 161397.39 | 369458.32 | 2022-07-21 18:02 | 2023-02-26 | 2022-07-01 | 2023-02-21
75086 | G7MAINS | MX2700925 | MX2700925 - BRECKENRIDGE; ALEXANDRIA; 4" PL; MA | 858.16 |  | 858.16 |  |  | 117707.39 | 76342.51 | 41364.88 | 2022-05-18 18:01 | 2022-11-17 | 2022-05-01 | 2022-11-08
75086 | G7MAINS | MX3119117 | MX3119117 - CARPENTER RD-MAE-2"PL-200' | 71768.64 |  | 71768.64 |  |  | 71768.64 | 33684.62 | 38084.02 | 2024-05-10 10:02 | 2025-02-20 | 2024-05-01 | 2025-02-18
75086 | G7MAINS | MX3164809 | MX3164809 - RICHARD KNOCK HWY-MAE-8" PL-578'-0 | 173119.58 |  | 173119.58 |  |  | 173119.58 | 68945.02 | 104174.56 | 2024-07-31 14:01 | 2025-05-29 | 2024-10-01 | 2025-05-14
75086 | G7MAINS | MX3277149 | MX3277149 - BILL WENTZ-MAE-2"PL-75' | 18854.59 |  | 18854.59 |  |  | 18854.59 | 14087.05 | 4767.54 | 2024-05-13 14:01 | 2024-09-26 | 2024-05-01 | 2024-09-12
75086 | G7MAINS | MX3351619 | MX3351619 - HIGHLAND AVE AND WOODLAND PL MAE - | -5.47 |  | -5.47 |  |  | 33262.32 | 19811.35 | 13450.97 | 2021-12-10 14:02 | 2022-05-19 | 2021-12-01 | 2022-03-27
75086 | G7MAINS | MX3471260 | MX3471260 - DOLWICK DR - MAE - 4" PL - 275' - 1 | 38814.59 |  | 38814.59 |  |  | 38814.59 | 23780.45 | 15034.14 | 2024-07-30 10:01 | 2025-01-13 | 2024-08-01 | 2024-12-23
75086 | G7MAINS | MX3880107 | MX3880107 - SERVICE RD; WALTON; 6" PL; MEA | 705.53 |  | 705.53 |  |  | 82320.42 | 54841.48 | 27478.94 | 2022-04-20 18:01 | 2022-09-15 | 2022-05-01 | 2022-09-05
75086 | G7MAINS | MX3955327 | MX3955327 - LOCK RD-BUTLER-1200 FT 4 INCH PL MA | 966.52 |  | 966.52 |  |  | 173440.32 | 66243.21 | 107197.11 | 2022-07-15 18:01 | 2022-12-29 | 2022-07-01 | 2022-12-20
75086 | G7MAINS | MX4018013 | MX4018013 - JOHNS HILL RD MEA | 964.14 |  | 964.14 |  |  | 210927.94 | 73344 | 137583.94 | 2019-11-13 10:01 | 2020-01-03 | 2019-11-01 | 2020-06-18
75086 | G7MAINS | MX4034314 | MX4034314 - MEA-KY 16 & KY 17-4 IN PL-1220 FT-6 | 44472.78 |  | 44472.78 |  |  | 44472.78 | 120008.83 | -75536.05 | 2024-11-06 14:01 | 2025-06-26 | 2024-11-01 | 2025-06-25
75086 | G7MAINS | MX4105546 | MX4105546 - MAN O WAR BLVD - MAE - 4" PL - 1100 | 140414.74 |  | 140414.74 |  |  | 140414.74 | 46333.3 | 94081.44 | 2024-09-10 18:01 | 2025-03-13 | 2024-09-01 | 2025-02-19
75086 | G7MAINS | MX4151648 | MX4151648 - JT-G-WILLOW GREEN | 34.16 |  | 34.16 |  |  | 34.16 | 60212.64 | -60178.48 | 2024-10-15 16:16 | 2025-09-18 | 2024-10-01
75086 | G7MAINS | MX4296108 | MX4296108 - RICE PK; UNION; 4" PL; MEA | 544.52 |  | 544.52 |  |  | 107781.84 | 79193.21 | 28588.63 | 2022-06-07 14:01 | 2022-11-17 | 2022-06-01 | 2022-11-16
75086 | G7MAINS | MX4318038 | MX4318038 - CITYVIEW APP MAIN - MAE - 6"PL - 80 | 60402.09 |  | 60402.09 |  |  | 60402.09 | 35364.6 | 25037.49 | 2024-09-11 10:01 | 2025-02-13 | 2024-09-01 | 2025-02-10
75086 | G7MAINS | MX4355391 | MX4355391 - ~1,600 FT MEA; 300 RICHARD KNOCK HW | 1659.98 |  | 1659.98 |  |  | 252925.92 | 225972 | 26953.92 | 2020-05-27 10:01 | 2020-08-25 | 2020-06-01 | 2020-11-30
75086 | G7MAINS | MX4735611 | MX4735611 - W 3RD ST & W 4TH ST-NEWPORT-2194 FT | 489694.71 |  | 489694.71 |  |  | 651207.02 | 268126.22 | 383080.8 | 2023-10-25 14:01 | 2024-05-09 | 2023-10-01 | 2024-05-21
75086 | G7MAINS | MX4875568 | MX4875568 - FARM TAP PROJECT; E ALEXANDRIA / CA | 7545.57 |  | 7545.57 |  |  | 1059966.43 | 1255100 | -195133.57 | 2020-03-03 10:01 | 2020-09-11 | 2020-03-01 | 2020-12-26
75086 | G7MAINS | MX5095081 | MX5095081 - EAST FROGTOWN RD; RICHWOOD; 6" PL; | 371.35 |  | 371.35 |  |  | 169121.97 | 71068.41 | 98053.56 | 2022-08-18 18:02 | 2023-03-30 | 2022-08-01 | 2023-02-20
75086 | G7MAINS | MX5112893 | MX5112893 - 211 KY HIGHWAY W 36 - MAE - 4" PL - | 3510.71 |  | 3510.71 |  |  | 3510.71 | 0 | 3510.71 | 2024-10-16 14:01 | 2026-01-01 | 2024-11-01
75086 | G7MAINS | MX5190163 | MX5190163 - FROGTOWN CONNECTOR; RICHWOOD ; 4" P | 547.61 |  | 547.61 |  |  | 55525.16 | 2850.86 | 52674.3 | 2022-08-03 14:02 | 2023-01-12 | 2022-08-01 | 2023-01-01
75086 | G7MAINS | MX5543296 | MX5543296 - OLD LEXINGTON PIKE; RICHWOOD ; 8" P | 674.56 |  | 674.56 |  |  | 2087158.32 | 465508.22 | 1621650.1 | 2022-12-15 18:01 | 2024-01-04 | 2023-02-01 | 2024-01-01
75086 | G7MAINS | MX5653109 | MX5653109 - FARM TAP PROJ; CROSBY PKWY/MAGELLAN | 4569.86 |  | 4569.86 |  |  | 951574.29 | 194197.42 | 757376.87 | 2020-09-29 10:01 | 2023-07-13 | 2020-10-01 | 2023-11-15
75086 | G7MAINS | MX5709799 | MX5709799 - LAKELAND PARK DR; LIMABURG ; 6" PL; | 4500.72 |  | 4500.72 |  |  | 206780.24 | 28078.8 | 178701.44 | 2022-12-20 14:01 | 2023-05-18 | 2023-01-01 | 2023-05-18
75086 | G7MAINS | MX5751969 | MX5751969 - MEA - STANBERY RIDGE-FORT THOMAS-47 | 1177.1 |  | 1177.1 |  |  | 114151.02 | 24699.21 | 89451.81 | 2022-10-04 18:01 | 2023-03-23 | 2022-10-01 | 2023-03-21
75086 | G7MAINS | MX6085790 | MX6085790 - INSTALL GAS ONLY APPROACH MAIN - NE | 20570.09 |  | 20570.09 |  |  | 20570.09 | 73074 | -52503.91 | 2024-12-03 10:01 | 2025-03-06 | 2024-12-01 | 2025-01-02
75086 | G7MAINS | MX6108586 | MX6108586 - JT-G-ENCLAVE SUBDIVISION | 93674.95 |  | 93674.95 |  |  | 151822.48 | 87608.95 | 64213.53 | 2023-01-19 18:01 | 2023-11-16 | 2023-02-01 | 2024-03-12
75086 | G7MAINS | MX6108813 | MX6108813 - PARKVIEW ESTATES APP - UNION - 8" & | 863.99 |  | 863.99 |  |  | 266747.96 | 134092.12 | 132655.84 | 2022-10-26 10:01 | 2023-03-23 | 2022-11-01 | 2023-04-10
75086 | G7MAINS | MX6212508 | MX6212508 - ELLIS RD; CONSTANCE; 6" PL; MEA | 4176.01 |  | 4176.01 |  |  | 96079.58 | 73565.15 | 22514.43 | 2023-06-14 18:01 | 2023-11-09 | 2023-06-01 | 2023-10-30
75086 | G7MAINS | MX6678695 | MX6678695 - MEA-DECLARATION DR-INDEPENDENCE-4 I | 12946.78 |  | 12946.78 |  |  | 107634.01 | 32908.63 | 74725.38 | 2023-08-01 18:01 | 2023-12-28 | 2023-08-01 | 2023-12-25
75086 | G7MAINS | MX6684040 | MX6684040 - ~1825 FTMEA; WRIGHT BLVD | 1327.98 |  | 1327.98 |  |  | 144757.53 | 117730.07 | 27027.46 | 2020-10-02 10:01 | 2020-12-18 | 2020-10-01 | 2021-03-08
75086 | G7MAINS | MX6735987 | MX6735987 - CRESTVW HL; VILLA MADONNA DR; 4" IP | 4240.01 |  | 4240.01 |  |  | 100374.73 | 60882.54 | 39492.19 | 2023-03-17 18:01 | 2023-08-17 | 2023-03-01 | 2023-09-19
75086 | G7MAINS | MX7231229 | MX7231229 - STONEWATER APPROACH MAIN | 5575.49 |  | 5575.49 |  |  | 583658.71 | 201665.76 | 381992.95 | 2020-12-15 10:01 | 2021-12-18 | 2020-12-01 | 2021-08-14
75086 | G7MAINS | MX7843275 | MX7843275 - MEA - MANHATTAN BLVD-DAYTON-250 FT | 2778.35 |  | 2778.35 |  |  | 25073.21 | 17848.21 | 7225 | 2023-06-05 18:01 | 2023-10-26 | 2023-06-01 | 2023-11-22
75086 | G7MAINS | MX8327384 | MX8327384 - MAE- MEMORIAL POINT APPROACH - SOUT | 3928.06 |  | 3928.06 |  |  | 222651.72 | 103571.49 | 119080.23 | 2023-03-21 14:01 | 2023-08-17 | 2023-03-01 | 2023-08-02
75086 | G7MAINS | MX8505395 | MX8505395 - ~350 FT MEA; 351 KENTON LANDS | 817.53 |  | 817.53 |  |  | 67182.64 | 32683.85 | 34498.79 | 2020-12-01 14:18 | 2021-02-28 | 2020-12-01 | 2021-06-28
75086 | G7MAINS | MX8745338 | MX8745338 - JT-G-THE PINNACLE OF FORT MITCHELL | 86559.98 |  | 86559.98 |  |  | 86559.98 | 48277.14 | 38282.84 | 2023-09-22 10:01 | 2024-08-21 | 2024-02-01 | 2024-08-19
75086 | G7MAINS | MX9801147 | MX9801147 - ELIJAH CREEK LOOP; NEYER DEVELOPMEN | 1330.81 |  | 1330.81 |  |  | 159649.72 | 88032.99 | 71616.73 | 2021-11-30 14:02 | 2022-07-07 | 2021-12-01 | 2022-06-27
75086 | G7MAINS | MXA201375 | MXA201375 - JT-G-THE MEADOWS AT GRAND GARDEN PH | 141229.23 |  | 141229.23 |  |  | 141229.23 | 47840.63 | 93388.6 | 2024-01-11 14:01 | 2024-08-15 | 2024-01-01 | 2024-08-28
75086 | G7MASOINT | AW3449 | AW3449 - DUKE MASON INTERCONNECT (KY) | 147718.15 |  | 147718.15 |  |  | 1039080.24 | 2000000 | -960919.76 | 2021-01-26 10:39 | 2021-12-30 | 2021-01-01 | 2022-03-05
75086 | G7MREG118 | MX2217622 | MX2217622 - STATION 873 - 5TH & PHILADELPHIA | 39603.88 |  | 39603.88 |  |  | 456763.05 | 87907.04 | 368856.01 | 2017-09-22 14:01 | 2025-11-30 | 2017-10-01
75086 | G7PRESIM | MX1640159 | MX1640159 - ELIJAH CREEK PRESSURE IMPROVEMENT P | 5182.7 |  | 5182.7 |  |  | 866787.44 | 760041.64 | 106745.8 | 2019-06-04 14:01 | 2020-02-26 | 2019-06-01 | 2020-01-15
75086 | G7PUBIMP | 2781786 | 2781786 - KYTC 19-9001 I-275 GRAVES RD | -539.77 |  | -539.77 |  |  | -539.77 | 70082.56 | -70622.33 | 2024-09-13 10:22 | 2023-11-22 | 2024-09-01 | 2024-12-14
75086 | G7PUBIMP | B1252 | B1252 - CANCEL- BULLITSVILLE RD CONN/CWA | -25.56 |  | -25.56 |  |  | -6971.14 | 0 | -6971.14 | 2002-06-28 | 2050-12-31 | 2002-07-01
75086 | G7PUBIMP | MX0129552 | MX0129552 - CHAPMAN LN. - ROAD RECONSTRUCTION - | 1237.6 |  | 1237.6 |  |  | 138598.24 | 73592.68 | 65005.56 | 2021-03-30 10:09 | 2025-02-17 | 2021-04-01 | 2022-06-29
75086 | G7PUBIMP | MX0503657 | MX0503657 - JOYCE AVE STI-NEWPORT KY - 300' OF | 735.82 |  | 735.82 |  |  | 142396.74 | 50388.91 | 92007.83 | 2021-06-22 18:02 | 2024-11-19 | 2021-06-01 | 2022-01-27
75086 | G7PUBIMP | MX0722354 | MX0722354 - CANCEL -BARRS BRANCH BRIDGE PROJECT | -139.67 |  | -139.67 |  |  | 0 | 0 | 0 | 2023-09-07 10:01 | 2024-03-28 | 2023-10-01
75086 | G7PUBIMP | MX0783884 | MX0783884 - PLEASANT VALLEY ROAD/CAMP ERNST ROA | 7509.53 |  | 7509.53 |  |  | 1986328.93 | 1689689.28 | 296639.65 | 2018-04-26 10:01 | 2018-08-25 | 2018-05-01 | 2019-01-22
75086 | G7PUBIMP | MX1844009 | MX1844009 - KYTC 06-445.00 MINEOLA PK (CHANNEL | 255181.14 |  | 255181.14 |  |  | 255181.14 | 34558.39 | 220622.75 | 2024-02-22 18:01 | 2024-08-01 | 2024-03-01 | 2024-07-29
75086 | G7PUBIMP | MX2334412 | MX2334412 - KYTC STI-SHORLAND RR XING-WALTON | 6944.09 |  | 6944.09 |  |  | 6944.09 | 0 | 6944.09 | 2024-01-17 18:01 | 2025-11-06 | 2024-03-01
75086 | G7PUBIMP | MX2338415 | MX2338415 - EAST 1ST-STI-2"PL-163' | 35294.9 |  | 35294.9 |  |  | 35294.9 | 21816.49 | 13478.41 | 2024-03-25 10:09 | 2024-08-29 | 2024-04-01 | 2024-08-19
75086 | G7PUBIMP | MX2442598 | MX2442598 - BROMLEY-CR. SPRINGS RD (KY 2373) | 2468.01 |  | 2468.01 |  |  | 252045.44 | 90736.42 | 161309.02 | 2021-08-02 14:02 | 2022-02-06 | 2021-08-01 | 2022-01-31
75086 | G7PUBIMP | MX2698762 | MX2698762 - DOH PENDELTON/CAMPBELL INSTALL STRE | 2097.29 |  | 2097.29 |  |  | 313268.53 | 99383.99 | 213884.54 | 2019-09-20 14:01 | 2020-04-03 | 2019-12-01 | 2020-07-09
75086 | G7PUBIMP | MX2719627 | MX2719627 - RPL - DIXIE HWY - FORT MITCHELL- 4" | 12172.95 |  | 12172.95 |  |  | 12172.95 | 85946.42 | -73773.47 | 2024-02-16 10:27 | 2024-09-12 | 2024-02-01 | 2024-10-07
75086 | G7PUBIMP | MX2781786 | MX2781786 - CANCEL_KYTC 19-9001 I-275 GRAVES RD | -1077.18 |  | -1077.18 |  |  | -1077.18 | 70082.56 | -71159.74 | 2020-12-09 10:02 | 2023-11-22 | 2021-06-01
75086 | G7PUBIMP | MX3198076 | MX3198076 - DAVIS LN-STI-4"PL-150' | 1146.85 |  | 1146.85 |  |  | 1146.85 | 14806.69 | -13659.84 | 2024-03-27 14:01 | 2024-07-18 | 2024-04-01 | 2024-07-15
75086 | G7PUBIMP | MX3359474 | MX3359474 - KYTC - RICHWOOD RD STI - BEAVERLICK | 3210.02 |  | 3210.02 |  |  | 482507.15 | 24088.21 | 458418.94 | 2021-12-13 14:02 | 2024-12-31 | 2021-12-01 | 2022-06-22
75086 | G7PUBIMP | MX3584545 | MX3584545 - NARROWS RD-STI-8"PL-2,145' | 525913.26 |  | 525913.26 |  |  | 525913.26 | 131448.69 | 394464.57 | 2024-06-13 18:01 | 2025-04-13 | 2024-06-01 | 2025-03-20
75086 | G7PUBIMP | MX4039676 | MX4039676 - ROSSFORD BRIDGE REPLACEMENT - STI - | 19161.72 |  | 19161.72 |  |  | 19161.72 | 22892.3 | -3730.58 | 2024-10-24 14:01 | 2025-02-27 | 2024-10-01 | 2025-02-11
75086 | G7PUBIMP | MX4199889 | MX4199889 - US-25 WALTON - 4" PL - STI | 1048.46 |  | 1048.46 |  |  | 150081.44 | 38705.17 | 111376.27 | 2022-07-25 14:01 | 2023-03-30 | 2022-08-01 | 2023-02-16
75086 | G7PUBIMP | MX4966474 | MX4966474 - 7639 TURFWAY - FLORENCE - 8" PL - S | 966.25 |  | 966.25 |  |  | 83976.74 | 3293.8 | 80682.94 | 2022-06-27 18:01 | 2023-03-30 | 2022-07-01 | 2023-03-01
75086 | G7PUBIMP | MX5108455 | MX5108455 - KENTABOO DR - FLORENCE - 4" PL - ST | 421.07 |  | 421.07 |  |  | 63399.97 | 4544.42 | 58855.55 | 2022-06-21 14:01 | 2022-11-10 | 2022-06-01 | 2022-10-28
75086 | G7PUBIMP | MX5793857 | MX5793857 - KYTC - DONALDSON & COX AVE - GO ARO | 12413.77 |  | 12413.77 |  |  | 12413.77 | 19660.9 | -7247.13 | 2024-11-06 14:01 | 2025-03-06 | 2024-11-01 | 2025-02-19
75086 | G7PUBIMP | MX6628393 | MX6628393 - PLEASANT VALLEY 2020 RELOCATION | 1521.53 |  | 1521.53 |  |  | 391214.24 | 399033 | -7818.76 | 2020-05-18 10:01 | 2020-10-29 | 2020-06-01 | 2020-11-17
75086 | G7PUBIMP | MX6798234 | MX6798234 - KYTC 06-8916 HOUSTON RD-ERLANGER-ST | 54715.71 |  | 54715.71 |  |  | 457777.13 | 142182.69 | 315594.44 | 2022-10-21 14:01 | 2024-01-11 | 2022-11-01 | 2024-03-19
75086 | G7PUBIMP | MX7599942 | MX7599942 - INSTALL STREET IMPROVEMENT PROJECT | 743.23 |  | 743.23 |  |  | 165799.8 | 99125.15 | 66674.65 | 2019-08-02 10:01 | 2020-02-27 | 2019-08-01 | 2020-02-29
75086 | G7PUBIMP | MX7832792 | MX7832792 - BROOKWOOD DR. SOUTH - EDGEWOOD - 4" | 889.95 |  | 889.95 |  |  | 133123.95 | 75946.23 | 57177.72 | 2020-09-09 10:01 | 2021-05-21 | 2021-03-01 | 2021-09-07
75086 | G7PUBIMP | MX8637896 | MX8637896 - CC STI -BLOSSOM LN- SOUTHGATE -8" P | -36745.82 |  | -36745.82 |  |  | 303088.78 | 128671.29 | 174417.49 | 2023-03-30 18:01 | 2023-09-04 | 2023-04-01 | 2023-09-04
75086 | G7PUBIMP | MX9121402 | MX9121402 - KYTC 06-423 FROGTOWN-UNION-STI | 252694.55 |  | 252694.55 |  |  | 289020.53 | 24602.7 | 264417.83 | 2023-07-13 10:01 | 2024-02-29 | 2023-07-01 | 2024-02-19
75086 | G7PUBIMP | MX9244894 | MX9244894 - KYTC - MT.ZION RD KY536 STI | 13631.07 |  | 13631.07 |  |  | 1104002.69 | 1026778 | 77224.69 | 2019-11-08 10:01 | 2023-06-30 | 2020-01-01 | 2021-07-27
75086 | G7PUBIMP | MX9568282 | MX9568282 - STI-TAYLOR MILL RD SIDEWALK-TAYLOR | 21374.45 |  | 21374.45 |  |  | 58870.95 | 38707.06 | 20163.89 | 2023-10-19 14:01 | 2024-04-30 | 2023-10-01 | 2024-03-11
75086 | G7PUBIMP | MX9853572 | MX9853572 - GRAVES AND NORTHBEND ROUNDABOUT PRO | 1503.67 |  | 1503.67 |  |  | 2612.92 | 109422.27 | -106809.35 | 2021-02-16 18:02 | 2023-12-28 | 2021-02-01 | 2022-02-14
75086 | G7PUBIMP | MX9948553 | MX9948553 - WILBERS LN - FORT THOMAS - 2" PE - | 923.66 |  | 923.66 |  |  | 94523.1 | 75860.65 | 18662.45 | 2021-07-13 18:02 | 2024-12-16 | 2021-07-01 | 2023-02-21
75086 | G7PUBIMP | S8867 | S8867 - STI 10873483 MT ZION RD | 11430.82 |  | 11430.82 |  |  | 2416414.73 | 447690.24 | 1968724.49 | 2016-07-26 13:07 | 2020-01-30 | 2017-01-01 | 2019-12-21
75086 | G7PUINEW | INSREGREL | INSREGREL - INSTALL OR REMOVE REGULATOR/RELIEF | 19289.05 |  | 19289.05 |  |  | 1508653.87 | 800000 | 708653.87 | 2015-03-03 17:08 | 2050-12-31 | 2015-04-01
75086 | G7PUINEW | SETMETER | SETMETER - SET OR REMOVE METER | 1579518.7 |  | 1579518.7 |  |  | 15577857.62 | 2250000 | 13327857.62 | 2015-03-03 16:32 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGLG | AGECHGLG - KENTUCKY AGE CHANGE LARGE METER | 530053.64 |  | 530053.64 |  |  | 1552056.72 | 350000 | 1202056.72 | 2015-03-03 16:46 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | AGECHGSM | AGECHGSM - KENTUCKY AGE CHANGE SMALL METER | 754855.73 |  | 754855.73 |  |  | 9490771.64 | 14500000 | -5009228.36 | 2015-03-03 16:42 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRLG | CHGMTRLG - CHANGE LARGE METER KENTUCKY | 19898.57 |  | 19898.57 |  |  | 184912.36 | 725000 | -540087.64 | 2015-03-03 16:53 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGMTRSM | CHGMTRSM - CHANGE SMALL METER KENTUCKY | 78989.69 |  | 78989.69 |  |  | 3384394.54 | 1250000 | 2134394.54 | 2015-03-03 16:57 | 2050-12-31 | 2015-04-01
75086 | G7PUINMR | CHGREGREL | CHGREGREL - CHANGE REGULATOR/RELIEF KENTUCKY | 39857.37 |  | 39857.37 |  |  | 222435.37 | 800000 | -577564.63 | 2015-03-03 17:12 | 2050-12-31 | 2015-04-01
75086 | G7REG0048 | MX7282035 | MX7282035 - REG 0048 FIFTH AND PHILADELPHIA - R | 161.75 |  | 161.75 |  |  | 12965.05 | 48953.52 | -35988.47 | 2020-07-14 10:02 | 2021-03-31 | 2020-08-01 | 2020-10-28
75086 | G7REG0089 | AW3224 | AW3224 - REG 0427 EMPIRE DR | 47684.21 |  | 47684.21 |  |  | 937110.96 | 732000 | 205110.96 | 2020-12-30 15:41 | 2025-10-30 | 2021-07-01
75086 | G7REG0089 | AW3246 | AW3246 - REG 0427 EMPIRE DR LAND | 6374.89 |  | 6374.89 |  |  | 103632.18 | 82500 | 21132.18 | 2021-01-02 13:48 | 2026-03-31 | 2021-04-01
75086 | G7REG026 | AW3184 | AW3184 - REG 0437 UPHILL & HIGHWAY | 9452.77 |  | 9452.77 |  |  | 1759156.29 | 507300 | 1251856.29 | 2020-12-28 11:30 | 2023-03-31 | 2021-12-01 | 2023-02-08
75086 | G7REG045 | AW3228 | AW3228 - REG 0432 TENTH & BRIGHTON | 490.23 |  | 490.23 |  |  | 2251681.56 | 660800 | 1590881.56 | 2020-12-30 16:28 | 2021-03-31 | 2021-11-01 | 2023-07-11
75086 | G7REG045 | AW3356 | AW3356 - CANCEL- REG0432 TENTH-BRIGHTON LAND | 712.06 |  | 712.06 |  |  | 0 | 82500 | -82500 | 2021-01-13 10:52 | 2023-03-31 | 2021-09-01
75086 | G7REG053 | MX9751457 | MX9751457 - REG 0053 - OVERTON AND NINTH - REG | -2185.83 |  | -2185.83 |  |  | 63003.22 | 43953.52 | 19049.7 | 2021-02-08 18:02 | 2022-03-31 | 2021-06-01 | 2021-10-28
75086 | G7REG057 | AW3180 | AW3180 - REG 0431 SARATOGA & ELEVENTH | 6613.29 |  | 6613.29 |  |  | 2652011.13 | 796400 | 1855611.13 | 2020-12-28 10:43 | 2023-03-31 | 2021-11-01 | 2023-11-08
75086 | G7REG057 | AW3354 | AW3354 - CANCEL-REG431 SARATOGA-ELEVENTH ROW | 3197.72 |  | 3197.72 |  |  | 0 | 82500 | -82500 | 2021-01-13 10:19 | 2023-03-31 | 2021-06-01
75086 | G7REG059 | AW3177 | AW3177 - REG 0059 HIGHLAND AND GRAND RS REPL | 19506.25 |  | 19506.25 |  |  | 3306318.19 | 746000 | 2560318.19 | 2020-12-28 10:15 | 2022-09-30 | 2021-06-01 | 2023-02-09
75086 | G7REG074 | AW4985 | AW4985 - REG 0074 - MCALPIN N OF HOPE - RELI | 5256.84 |  | 5256.84 |  |  | 914398.91 | 135940 | 778458.91 | 2022-03-01 12:43 | 2022-08-31 | 2022-05-01 | 2022-10-07
75086 | G7REPL | 28051 | 28051 - SMALL REPL KY | 547582.69 |  | 547582.69 |  |  | 2505652.03 | 0 | 2505652.03 | 2000-04-13 | 2050-12-31 | 1999-12-01
75086 | G7REPL | AW6197 | AW6197 - CANCEL- ROW SCHOOL RD - WALTON | -4127.67 |  | -4127.67 |  |  | 0 | 25000 | -25000 | 2022-10-06 09:08 | 2023-06-17 | 2022-11-01
75086 | G7REPL | MX0506978 | MX0506978 - KYTC MT ZION - INDEPENDENCE - 12" P | 59756.65 |  | 59756.65 |  |  | 152240.62 | 43338.35 | 108902.27 | 2023-10-12 14:01 | 2024-02-20 | 2023-10-01 | 2024-02-07
75086 | G7REPL | MX1379992 | MX1379992 - WEST 13TH ST RPL PROJECT, NEWPORT, | 2743.03 |  | 2743.03 |  |  | 341645.92 | 44018.51 | 297627.41 | 2021-09-13 10:02 | 2024-04-15 | 2021-09-01 | 2022-09-28
75086 | G7REPL | MX2163251 | MX2163251 - CANCEL HIGHLAND AVE WOODLAND PL | 5.29 |  | 5.29 |  |  | 0.26 | 24723.49 | -24723.23 | 2021-09-30 14:01 | 2022-05-12 | 2021-10-01
75086 | G7REPL | MX3269023 | MX3269023 - KYTC - HANDS PIKE - EDGEWOOD - 4" P | 1285.64 |  | 1285.64 |  |  | 259869.09 | 12423.85 | 247445.24 | 2022-06-27 18:01 | 2024-12-31 | 2022-07-01 | 2022-11-18
75086 | G7REPL | MX4342633 | MX4342633 - PLEASANT VALLEY STEEL REP (FOUNDERS | 2170.03 |  | 2170.03 |  |  | 388656.66 | 166756 | 221900.66 | 2019-10-18 10:01 | 2020-02-28 | 2019-10-01 | 2020-06-26
75086 | G7REPL | MX4962663 | MX4962663 - ALEXANDRIA PK - ALEXANDRIA- 8" SIZE | 601.27 |  | 601.27 |  |  | 388035.64 | 93664.48 | 294371.16 | 2022-08-10 14:02 | 2023-05-11 | 2022-08-01 | 2023-05-03
75086 | G7REPL | MX6589218 | MX6589218 - SCHOOL RD - WALTON - 4" PL - RPL | -1153.57 |  | -1153.57 |  |  | 151165.46 | 31266.98 | 119898.48 | 2023-03-17 18:01 | 2023-11-30 | 2023-03-01 | 2023-11-29
75086 | G7REPL | MX9545566 | MX9545566 - RICHWOOD RD REPLACEMENT PROJ KY-338 | 15339.12 |  | 15339.12 |  |  | 1727865.88 | 1413710 | 314155.88 | 2019-11-12 10:01 | 2022-06-14 | 2020-01-01 | 2022-03-01
75086 | G7REPL | MX9817206 | MX9817206 - DUVENECK SQUARE RPL/MAE - COVINGTON | -32321.5 |  | -32321.5 |  |  | 383975.31 | 101691.72 | 282283.59 | 2021-04-08 10:02 | 2024-10-01 | 2021-05-01 | 2021-12-14
75086 | G7RGPI | MX9217475 | MX9217475 - GARVEY AVE. PRI, ELSMERE, 9400' 8" | 10632.53 |  | 10632.53 |  |  | 1523277.77 | 507691.08 | 1015586.69 | 2021-08-16 18:02 | 2022-12-01 | 2021-09-01 | 2022-11-21
75086 | G7RRPI | MX9219249 | MX9219249 - RICHARDSON RD PRESSURE IMP 7300' OF | 22733.19 |  | 22733.19 |  |  | 100151.56 | 765.33 | 99386.23 | 2022-10-21 18:01 | 2026-03-12 | 2022-11-01
75086 | G7SERVMC | AW6981 | AW6981 - SERVICE ABANDONMENTS - IAP | 249297.66 |  | 249297.66 |  |  | 261489.18 | 0 | 261489.18 | 2023-05-02 09:49 | 2050-12-31 | 2023-05-01
75086 | G7SERVMC | C9839 | C9839 - CANCEL 2 PP896043/CWA | 9454.49 |  | 9454.49 |  |  | 9355.08 | 0 | 9355.08 | 2007-05-17 | 2050-12-31 | 2007-05-01 | 2007-09-22
75086 | G7SERVMC | CMRP70 | CMRP70 - REPLACE C-M PLASTIC 2 INCH AND UNDE | 785211.42 |  | 785211.42 |  |  | 14016441.86 | 0 | 14016441.86 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVMC | CMRS70 | CMRS70 - 2" OR LESS STEEL C-M REPLACE | 8691.88 |  | 8691.88 |  |  | 20501.08 | 1000000 | -979498.92 | 2016-01-13 11:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVMC | LCMRP70 | LCMRP70 - GREATER THAN 2" C-M REPL PLASTIC | 189595.66 |  | 189595.66 |  |  | 280090.82 | 2500000 | -2219909.18 | 2016-01-13 10:11 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LCMRS70 | LCMRS70 - GREATER THAN 2" C-M STEEL REPLACEME | 228.87 |  | 228.87 |  |  | 228.87 | 1000000 | -999771.13 | 2017-03-10 10:36 | 2050-12-31 | 2017-09-01
75086 | G7SERVMC | LMCRP70 | LMCRP70 - GREATER THAN 2" M-C REPL PLASTIC | 65111.95 |  | 65111.95 |  |  | 739578.75 | 2500000 | -1760421.25 | 2016-01-13 09:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVMC | LMCRS70 | LMCRS70 - GREATER THAN 2" M-C REPL STEEL | 37161.24 |  | 37161.24 |  |  | 53688.71 | 1000000 | -946311.29 | 2016-01-13 09:59 | 2050-12-31 | 2016-11-01
75086 | G7SERVMC | MCRP70 | MCRP70 - REPLACE (NON-AMRP) M-C PLASTIC 2 IN | 1137482.62 |  | 1137482.62 |  |  | 24759289.78 | 0 | 24759289.78 | 2008-07-01 | 2050-12-31 | 2008-07-01 | 2009-12-20
75086 | G7SERVMC | MCRS70 | MCRS70 - REPLACE M-C STEEL 2 INCH AND UNDER | 145726.57 |  | 145726.57 |  |  | 770537.71 | 0 | 770537.71 | 2008-07-01 | 2050-12-31 | 2008-07-01
75086 | G7SERVNEW | CMNEWP70 | CMNEWP70 - NEW C-M PLASTIC 2 INCH AND UNDER KY | 774221.77 |  | 774221.77 |  |  | 9460493.95 | 1 | 9460492.95 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | CMNEWS70 | CMNEWS70 - 2" OR LESS STEEL NEW C-M | 9019.92 |  | 9019.92 |  |  | 306458.91 | 5000000 | -4693541.09 | 2016-01-13 10:24 | 2050-12-31 | 2016-05-01
75086 | G7SERVNEW | LCMNEWP70 | LCMNEWP70 - GREATER THAN 2" C-M PLASTIC | 117859.36 |  | 117859.36 |  |  | 389387.02 | 2500000 | -2110612.98 | 2016-01-13 10:51 | 2050-12-31 | 2016-02-01
75086 | G7SERVNEW | LCMNEWS70 | LCMNEWS70 - GREATER THAN 2" C-M STEEL | 38090.89 |  | 38090.89 |  |  | 55597.64 | 1000000 | -944402.36 | 2017-03-10 10:26 | 2050-12-31 | 2019-07-01
75086 | G7SERVNEW | LMCNEWP70 | LMCNEWP70 - GREATER THAN 2" M-C PLASTIC | 78480.5 |  | 78480.5 |  |  | 809315.23 | 2500000 | -1690684.77 | 2016-01-13 10:34 | 2050-12-31 | 2016-03-01
75086 | G7SERVNEW | LMCNEWS70 | LMCNEWS70 - GREATER THAN 2" M-C STEEL | 124141.38 |  | 124141.38 |  |  | 287673.34 | 2500000 | -2212326.66 | 2016-01-13 10:42 | 2050-12-31 | 2016-04-01
75086 | G7SERVNEW | MCNEWP70 | MCNEWP70 - NEW M-C PLASTIC 2 INCH AND UNDER KY | 2128695.94 |  | 2128695.94 |  |  | 25033320.66 | 1 | 25033319.66 | 2010-12-31 | 2050-12-31 | 2011-01-01
75086 | G7SERVNEW | MCNEWS70 | MCNEWS70 - NEW M-C STEEL 2 INCH AND UNDER KY | 38334.55 |  | 38334.55 |  |  | 405350.07 | 1 | 405349.07 | 2010-12-31 | 2050-12-31 | 2011-04-01
75086 | G7SHOW2 | MX8547529 | MX8547529 - CHARTER - SHOWCASE CINEMAS RPL 1500 | -47513.39 |  | -47513.39 |  |  | 1383994.67 | 417336.96 | 966657.71 | 2023-03-11 12:03 | 2023-07-21 | 2023-03-01 | 2023-10-20
75086 | G7STA011 | AW3227 | AW3227 - STA 0949 DAYTON VALVE HOUSE | 182334.11 |  | 182334.11 |  |  | 1595010.4 | 1062400 | 532610.4 | 2020-12-30 16:17 | 2025-10-30 | 2021-11-01
75086 | G7STA014 | AW3251 | AW3251 - CANCEL_STA 0014 EAST ALEXANDRIAPIKE | -19.48 |  | -19.48 |  |  | 0 | 82500 | -82500 | 2021-01-03 09:43 | 2023-03-31 | 2021-06-01
75086 | G7STA014 | MX5466775 | MX5466775 - CHARTER - EAST ALEXANDRIA PIKE | 7879.11 |  | 7879.11 |  |  | 360066.63 | 129995.81 | 230070.82 | 2022-11-22 10:02 | 2023-12-29 | 2023-03-01 | 2023-11-20
75086 | G7STA0375 | AW3193 | AW3193 - STA 0375 ELECTRIC AVE RS REPLACEMEN | 20394.36 |  | 20394.36 |  |  | 2283679.93 | 829000 | 1454679.93 | 2020-12-28 13:59 | 2022-04-22 | 2021-05-01 | 2022-05-09
75086 | G7STA064 | AW3217 | AW3217 - STA 0940 GLECOE TB | 2415.12 |  | 2415.12 |  |  | 1101530.53 | 510900 | 590630.53 | 2020-12-30 13:22 | 2021-03-31 | 2021-11-01 | 2023-09-27
75086 | G7STA064 | AW3268 | AW3268 - STA 0940 STA GLENCOE TB LAND | 7680.23 |  | 7680.23 |  |  | 69004.79 | 82500 | -13495.21 | 2021-01-05 14:36 | 2023-03-31 | 2021-08-01 | 2023-09-27
75086 | G7STA0836 | AW3191 | AW3191 - STA 0838 ROSSFORD AVE RS REPLACEMEN | 21247.24 |  | 21247.24 |  |  | 2687134.47 | 539500 | 2147634.47 | 2020-12-28 13:11 | 2022-04-30 | 2021-05-01 | 2022-05-22
75086 | G7STA276 | AW3212 | AW3212 - STA 0276 MARY INGLES HWY RS ABANDON | -85455.33 |  | -85455.33 |  |  | 1125.65 | 553900 | -552774.35 | 2020-12-30 11:32 | 2021-03-31 | 2021-11-01 | 2022-11-18
75086 | G7STA276 | AW3689 | AW3689 - CANCEL-STA 0276 MARY IGLES HWY LAND | -341.21 |  | -341.21 |  |  | 0 | 82500 | -82500 | 2021-02-26 23:34 | 2023-03-31 | 2021-06-01
75086 | G7STA280 | AW3213 | AW3213 - STA 0938 TAYLOR MILL & LONE OAK | 442.42 |  | 442.42 |  |  | 2715077.54 | 562000 | 2153077.54 | 2020-12-30 11:55 | 2023-09-30 | 2021-11-01 | 2023-09-08
75086 | G7STA280 | AW3272 | AW3272 - STA0938 TAYLOR MILL & LONE OAK LAND | 67569.24 |  | 67569.24 |  |  | 210952.14 | 82500 | 128452.14 | 2021-01-05 15:40 | 2023-03-31 | 2021-08-01 | 2023-09-08
75086 | G7STA286 | AW3216 | AW3216 - STA 0929 RILEY RD | 10689.61 |  | 10689.61 |  |  | 4110633.27 | 635200 | 3475433.27 | 2020-12-30 13:11 | 2021-03-31 | 2021-09-01 | 2023-06-28
75086 | G7STA338 | AW3192 | AW3192 - STA 0941 GUBSER MILL | 3382.93 |  | 3382.93 |  |  | 605125.78 | 538800 | 66325.78 | 2020-12-28 13:44 | 2025-12-30 | 2021-09-01
75086 | G7STA338 | AW3690 | AW3690 - STA 0941 GUBSER MILL LAND | 2204.16 |  | 2204.16 |  |  | 50604.15 | 82500 | -31895.85 | 2021-02-27 08:54 | 2025-10-25 | 2021-06-01
75086 | G7STA444 | AW3186 | AW3186 - STA 0948 THIRD & CRESCENT | 2890.3 |  | 2890.3 |  |  | 640798.97 | 948400 | -307601.03 | 2020-12-28 11:59 | 2025-11-27 | 2021-11-01
75086 | G7STA444 | AW3230 | AW3230 - STA 0948 THIRD & CRESCENT LAND | 1291.92 |  | 1291.92 |  |  | 54951.38 | 82500 | -27548.62 | 2020-12-31 08:30 | 2025-11-27 | 2021-08-01
75086 | G7STA793 | AW3188 | AW3188 - STA 0942 CAMP ERNST RD | 298601.57 |  | 298601.57 |  |  | 3988713.88 | 887300 | 3101413.88 | 2020-12-28 12:16 | 2023-09-30 | 2021-11-01 | 2024-01-18
75086 | G7STA793 | AW3767 | AW3767 - STA 0942 CAMP ERNST RD LAND | 37911.52 |  | 37911.52 |  |  | 146826.83 | 82500 | 64326.83 | 2021-03-16 18:53 | 2023-03-31 | 2021-06-01 | 2024-01-18
75086 | G7STA822 | AW3189 | AW3189 - STA 0822 COX RD RS REPAIR | 1888.4 |  | 1888.4 |  |  | 190318.46 | 541600 | -351281.54 | 2020-12-28 12:29 | 2022-12-31 | 2021-11-01 | 2022-11-18
75086 | G7STA876 | MX6800938 | MX6800938 - STA 876 WARSAW TOWN BORDER- STATION | 84091.68 |  | 84091.68 |  |  | 2431628.08 | 252984 | 2178644.08 | 2018-01-10 18:02 | 2022-09-30 | 2018-01-01 | 2023-09-29
75086 | G7TAM00B | AW2146 | AW2146 - LINE AM00B RETROFIT REPL | 130261.8 |  | 130261.8 |  |  | 14953089.91 | 6528636 | 8424453.91 | 2020-05-19 16:54 | 2022-10-15 | 2020-05-01 | 2022-09-17
75086 | G7TAM00B | AW3634 | AW3634 - LINE AM00B ILI RETROFIT-LAND | 1948.04 |  | 1948.04 |  |  | 404165.03 | 127500 | 276665.03 | 2021-02-17 09:27 | 2022-10-15 | 2021-10-01 | 2022-09-17
75086 | G7TOOLS | 28073 | 28073 - PURCHASE GAS TOOLS BLANKET | 721241.56 |  | 721241.56 |  |  | 2003308.98 | 0 | 2003308.98 | 2000-04-13 | 2015-12-31 | 1999-12-01
75086 | G7TOOLS | AW4691 | AW4691 - CGI UPGRADE KENTUCKY | 3776.09 |  | 3776.09 |  |  | 349888.14 | 120000 | 229888.14 | 2021-10-22 07:34 | 2022-06-30 | 2021-12-01
75086 | G7TUL06 | AW1592 | AW1592 - LINE UL06 - PIPELINE REPLACEMENTS | 53028.94 |  | 53028.94 |  |  | 9832360.02 | 10253358 | -420997.98 | 2020-01-05 02:41 | 2021-12-30 | 2020-02-01 | 2021-12-03
75086 | G7TUL06 | AW2021 | AW2021 - LINE UL06 - PIPELINE REPLACEMENTS L | 449.18 |  | 449.18 |  |  | 122119.35 | 115000 | 7119.35 | 2020-04-13 10:21 | 2021-12-31 | 2020-07-01 | 2021-12-03
75086 | G7UL02PH1 | V8191 | V8191 - UL60 PIPELINE PHASE 1 (PIPE) | 167246.14 |  | 167246.14 |  |  | 38803147 | 26326195 | 12476952 | 2019-01-23 15:21 | 2021-03-30 | 2019-01-01 | 2021-02-25
75086 | G7UL02PH1 | V8352 | V8352 - UL60 PIPELINE P1 - LAND RIGHTS PROJ | 15636.98 |  | 15636.98 |  |  | 4912529.99 | 1941000 | 2971529.99 | 2019-02-11 09:32 | 2021-03-30 | 2019-03-01 | 2021-02-25
75086 | G7UL02PH2 | AW3877 | AW3877 - UL60 PIPELINE PHASE II - STATION | 53799.42 |  | 53799.42 |  |  | 4764465.22 | 1004152 | 3760313.22 | 2021-04-29 15:15 | 2022-03-30 | 2021-05-01 | 2021-11-18
75086 | G7UL02PH2 | V9444 | V9444 - UL60 PIPELINE PHASE II - PIPE | 73115.9 |  | 73115.9 |  |  | 21072110.55 | 22514005 | -1441894.45 | 2019-06-12 07:56 | 2022-03-30 | 2019-10-01 | 2021-11-18
75086 | G7UL02PH2 | V9445 | V9445 - UL60 PIPELINE PHASE II- LAND RIGHTS | 4614.44 |  | 4614.44 |  |  | 2557283.8 | 733000 | 1824283.8 | 2019-06-12 08:04 | 2022-02-02 | 2019-07-01 | 2021-11-18
75086 | G7UL57 | AW4824 | AW4824 - STA0917 UL61 CHAMBERS RD TO DIXIE | 161760.98 |  | 161760.98 |  |  | 3884454.98 | 873000 | 3011454.98 | 2021-12-09 11:26 | 2024-01-31 | 2022-02-01 | 2023-12-26
75086 | KYCIBS05 | D3212 | D3212 - CANCEL 2 KY CIBS MOD 341 CLOSE | 1808.16 |  | 1808.16 |  |  | 1808.16 | 0 | 1808.16 | 2008-04-01 | 2008-12-31 | 2008-03-01 | 2006-05-31
75086 | OM75086 | GCPBUDKY | GCPBUDKY - BUDGET ONLY - KENT GAS CAP | 10154.2 |  | 10154.2 |  |  | 16789.12 | 0 | 16789.12 | 2018-06-18 12:20 | 2050-12-31 | 2023-05-01
75086 | SG001135F | CGRREPLA | CGRREPLA - CGR REPLACE DEK GAS | 30212.371 |  | 30212.371 |  |  | 61458.013 | 0 | 61458.013 | 2023-03-06 13:28 | 2050-12-31 | 2023-04-01
75087 | CUSTCONN | 400109 | 400109 - CUST ENHANCEMENT AND OPTIMIZATION | -27.4 |  | -27.4 |  |  | 370056.18 | 480680 | -110623.82 | 2022-06-20 14:30 | 2024-01-19 | 2022-07-01 | 2024-01-26
75087 | CUSTCONN | 400109M | 400109M - MY ACCOUNT MODERNIZATION | 18843.57 |  | 18843.57 |  |  | 60716.93 | 135363 | -74646.07 | 2023-06-09 11:52 | 2025-03-31 | 2023-06-01 | 2025-01-16
75087 | FPIT | 400055015 | 400055015 - ATLANTIS (CUSTOMER ANALYTICS ENGINE | 151.71 |  | 151.71 |  |  | 25432.42 | 22832 | 2600.42 | 2021-12-29 10:35 | 2023-12-30 | 2022-01-01 | 2024-01-01
75087 | FPIT | 400055023 | 400055023 - USAGE ALERTS PHASE 2 | 4348.16 |  | 4348.16 |  |  | 21538.52 | 23299 | -1760.48 | 2022-12-15 19:09 | 2024-06-29 | 2023-01-01 | 2024-06-30
75087 | FPIT | 400055024 | 400055024 - SERVICE NAVIGATOR | 7316.83 |  | 7316.83 |  |  | 23259.79 | 22425 | 834.79 | 2022-12-20 19:47 | 2024-06-30 | 2023-01-01 | 2024-07-31
75087 | FPIT | 400055025 | 400055025 - DIGITAL CARE PLATFORM | 2606.1 |  | 2606.1 |  |  | 35921.35 | 25411 | 10510.35 | 2023-03-14 09:59 | 2024-03-31 | 2023-03-01 | 2024-03-31
75087 | FPIT | 400055026 | 400055026 - INSPECTOR PORTAL PHASE 3 | 23.4 |  | 23.4 |  |  | 3465.41 | 2491 | 974.41 | 2023-06-28 10:38 | 2024-03-29 | 2023-07-01 | 2024-03-31
75087 | FPIT | 400055029 | 400055029 - IVR VOICE AUTHENTICATION | 5030.51 |  | 5030.51 |  |  | 60137.49 | 77856 | -17718.51 | 2023-10-19 13:17 | 2025-06-29 | 2023-10-01 | 2025-01-31
75087 | FPIT | 400055030 | 400055030 - SAP & BUSINESS CUSTOMER WEB PORTAL | 157508.48 |  | 157508.48 |  |  | 181783.16 | 212277 | -30493.84 | 2023-11-01 02:36 | 2025-09-30 | 2023-11-01 | 2025-07-31
75087 | FPIT | 400055031 | 400055031 - D-E.COM/MY ACCOUNT WEB | 18794.39 |  | 18794.39 |  |  | 20387.32 | 22654 | -2266.68 | 2023-10-31 07:30 | 2025-06-29 | 2023-11-01 | 2025-07-15
75087 | FPIT | 400055032 | 400055032 - CUSTOMER - MOBILE APPLICATION | 60945.77 |  | 60945.77 |  |  | 68701.74 | 42720 | 25981.74 | 2023-10-31 04:40 | 2025-07-30 | 2023-11-01 | 2025-07-15
75087 | FPIT | 400055038 | 400055038 - CONTACT CENTER PLATFORM MODERNIZATI | 92866.74 |  | 92866.74 |  |  | 92866.74 | 573597 | -480730.26 | 2024-05-16 07:18 | 2026-03-31 | 2024-05-01
75087 | FPIT | 400055039 | 400055039 - NUANCE LICENSES | 21582.78 |  | 21582.78 |  |  | 21582.78 | 21907 | -324.22 | 2024-05-20 03:51 | 2024-09-29 | 2024-07-01 | 2024-10-01
75087 | FPIT | 400055040 | 400055040 - MODERN CUSTOMER AUTHENTICATION | 28434.69 |  | 28434.69 |  |  | 28434.69 | 49003 | -20568.31 | 2024-06-04 08:36 | 2026-03-31 | 2024-06-01
75087 | FPIT | 400055041 | 400055041 - NEW MYACCOUNT PLATFORM | 24362.2 |  | 24362.2 |  |  | 24362.2 | 109160 | -84797.8 | 2024-06-07 09:12 | 2026-03-31 | 2024-06-01
75087 | FPIT | 400055045 | 400055045 - EONS LICENSES | 7821.45 |  | 7821.45 |  |  | 7821.45 | 3641 | 4180.45 | 2024-12-09 07:27 | 2025-03-31 | 2024-12-01 | 2025-03-31
75087 | FPIT | CO2300002 | CO2300002 - GIFT CARD INVENTORY MODERN ARCHITEC | -1116.67 |  | -1116.67 |  |  | 0 | 1823 | -1823 | 2023-05-31 13:28 | 2024-10-30 | 2023-06-01 | 2025-01-30
75087 | FPIT | CS2200008 | CS2200008 - AVAYA PLATFORM UPGRADE - SERVER | -4329.17 |  | -4329.17 |  |  | 41340.29 | 44473 | -3132.71 | 2022-11-14 12:16 | 2024-03-31 | 2022-11-01 | 2024-03-31
75087 | FPIT | CS2300001 | CS2300001 - CCO REMOTE WORKSTATION EQUIPMENT | 44.29 |  | 44.29 |  |  | 7375.8 | 8282 | -906.2 | 2023-02-03 15:54 | 2024-01-31 | 2023-03-01 | 2024-01-31
75087 | FPIT | IT2400022 | IT2400022 - SAP CUSTOMER SYSTEM CHANGES | 23437.69 |  | 23437.69 |  |  | 23437.69 | 33919 | -10481.31 | 2024-05-08 09:23 | 2025-06-29 | 2024-05-01 | 2025-06-30
75087 | FPIT | TC2300036 | TC2300036 - SAP CUSTOMER SYSTEM CHANGES AND ENH | 8143.62 |  | 8143.62 |  |  | 17480.76 | 23896 | -6415.24 | 2023-08-07 15:13 | 2024-08-29 | 2023-08-01 | 2024-08-31
75087 | FPIT | TC2300037 | TC2300037 - SAP ENABLE NOW APPLICATION | 540.28 |  | 540.28 |  |  | 6311.11 | 5061 | 1250.11 | 2023-08-09 16:47 | 2024-03-30 | 2023-08-01 | 2024-03-31
75088 | FPITKG | TC210SW57 | TC210SW57 - CIOPS NERC CIP CYBERARK IMPLEMENTAT | -69.86 |  | -69.86 |  |  | 3074.42 | 3357 | -282.58 | 2021-12-10 14:08 | 2024-03-31 | 2022-02-01 | 2023-12-01
|  |  |  | 91160343.161 | 81572239.2007 | 9588103.9603 | 10.52%