## Sheet1
| Case No. 2021-00190 Estimates | Case No. 2025-00125 Estimates/Actuals | Reason for overrun/variation
| CPCN Filing Estimates | Actuals/Expected Costs
Phase 1 | 32300000 | 49900000 | Unforeseen increases in material, land, and construction along with project going into the following year due to system constraints - Actual Cost
Phase 2 | 49300000 | 51050000 | Project on target - Estimated $49.3 million in Case No. 2023-00210 CPCN Filing
Phase 3 | 48500000 | 51400000 | Project on target - Estimated $48.5 million in Case No. 2024-00189 CPCN Filing
Phase 4 | 43100000 | 43136000 | Expected cost in left column at time of filing based on Case No. 2025-00057.
Phase 5 | *30,388,000 | 32160000 | Expected cost as of 8/8/2025
*projected in Case No 2022-00084 testimony by Brian Weisker