## 5a Prior Yr Compl LTD CapEx
Project ID | Project Description | Kentucky Actual $ | Wheeling Actual $ | Total Actual $ | Total Estimated $ | Total Act $ minus Est $ | Reason (see tab "5 a and b for Key" for more detail)
000026265 | ML U2 Cooling Tower Reinforce | 3591935.22 | 25444548.59 | 29036483.81 | 43572173 | -14535689.19 | Availability
MLWVC1CL1 | Mitchell U1 SCR Catalyst L1 | 348377.7 | 2458121.93 | 2806499.63 | 2791109 | 15390.63 | Environmental
MLW1CGRPL | ML U1 Clinker Grinder Replace | 272265.07 | 1871629.16 | 2143894.23 | 1563904 | 579990.23 | Boiler Reliability
MLWEP1GNI | ML E U1 Generator Field Out In | 239074.67 | 1780646.87 | 2019721.54 | 1334249 | 685472.54 | Turbine/Generator Reliability
MLWEP1GGB | ML E U1 Gen Gas Baffle Purch | 173429.97 | 1264756.36 | 1438186.33 | 825810 | 612376.33 | Turbine/Generator Reliability
MLWSPBRNN | ML S Burner Nozzle Rplcmt | 121783.91 | 858534.68 | 980318.59 | 1307306 | -326987.41 | Boiler Reliability
MLWMPD10T | ML M Rebuild D10T Caught Fire | 105560.28 | 865555.42 | 971115.7 | 1162255 | -191139.3 | Fuel Delivery Reliability
MLWSPCCHN | ML S Collection Cnv Chain Repl | 109635.99 | 806525.72 | 916161.71 | 947904 | -31742.29 | Environmental
MLWVPOPIP | ML V Outage FGD Pipe Replace | 97399.87 | 699783.74 | 797183.61 | 541780 | 255403.61 | Environmental
MLWSPVALV | ML S Blr Brnr Steam Valve Repl | 88852.1 | 653185.92 | 742038.02 | 435775 | 306263.02 | Boiler Reliability
MLWES1BTI | ML1 E BFPT INSPECTION | 86684.89 | 650251.05 | 736935.94 | 485627 | 251308.94 | Turbine/Generator Reliability
MLWVPPUMP | ML V FGD CPS Pumps | 86633.63 | 625566.35 | 712199.98 | 963985 | -251785.02 | Environmental
MLWEPTFRM | ML E Transformers | 84248.84 | 563262.03 | 647510.87 | 727011 | -79500.13 | Turbine/Generator Reliability
MLWMPROTO | ML M Roto Booster Fan Replace | 78538.57 | 559289.45 | 637828.02 | 655222 | -17393.98 | Environmental
MLWSPPULV | ML S Pulverizer Rebuilds | 65169.45 | 500551.87 | 565721.32 | 726205 | -160483.68 | Fuel Delivery Reliability
MLWESCRTV | ML E Comb Reheat Turbine Valve | 59209.04 | 491243.93 | 550452.97 | 356477 | 193975.97 | Boiler Reliability
MLWVPFGDN | ML V FGD Other Non Outage PPB | 66116.47 | 452196.13 | 518312.6 | 456873 | 61439.6 | Environmental
MLWVPHBSH | ML V ID Fan Hub Shell Rplc | 56706.49 | 435661.03 | 492367.52 | 542734 | -50366.48 | Environmental
MLWEPDFPM | ML E Diesel Fire Pump Replace | 63059.36 | 398515.07 | 461574.43 | 341787 | 119787.43 | Safety/Employee
MLWMPCOMP | ML M CY Conv Component Repl | 53575.75 | 391864.32 | 445440.07 | 509757 | -64316.93 | Fuel Delivery Reliability
MLWVP21ID | MLP V REBUILD #21 ID FAN | 53936.48 | 382982.71 | 436919.19 | 369706 | 67213.19 | Environmental
MLWEPPUMP | ML E Pump Replacements | 50888.21 | 383651.9 | 434540.11 | 630759 | -196218.89 | Reliability
MLWSPSBSR | MLP STACK BREACH CASING REPL | 51166.2 | 376579.71 | 427745.91 | 372175 | 55570.91 | Reliability
MLWVP11ID | MLP V REBUILD #11 ID FAN | 45481.48 | 335887.22 | 381368.7 | 294364 | 87004.7 | Environmental
MLWEPTRMT | ML E Transmitter Replacements | 43049.61 | 323057.42 | 366107.03 | 389339 | -23231.97 | Reliability
MLWEPCTRL | ML E Control Upgds Rplcmts | 31995.72 | 231365.31 | 263361.03 | 275367 | -12005.97 | Reliability
MLWEPHVAC | MLP E HVAC Unit Replacements | 31301.97 | 221711.11 | 253013.08 | 249588 | 3425.08 | Buildings
MLWMPHSTF | ML M HS TUNNEL FIRE CAPITAL | 31649.36 | 220541.37 | 252190.73 | 295829 | -43638.27 | Fuel Delivery Reliability
MLWNPBLDG | ML N Capital Building Upgrades | 29665.63 | 219847.58 | 249513.21 | 377531 | -128017.79 | Buildings
MLWNPWINT | ML CAPITAL WINTERIZATION | 29937.03 | 206778.64 | 236715.67 | 250803 | -14087.33 | Reliability
MLWVPEJNT | ML V FGD CPS Expansion Joints | 27611.81 | 198696.56 | 226308.37 | 239238 | -12929.63 | Environmental
MLWEP2BAT | ML E U2 Station Battery Rep | 26136.87 | 188074.23 | 214211.1 | 253958 | -39746.9 | Reliability
MLWVPBLML | ML V Ball Mill Liner Replace | 26576.29 | 186172.56 | 212748.85 | 286924 | -74175.15 | Environmental
MLWEPTURB | ML E Trb Brg, Rtr, Shaft Rbld | 22337.81 | 165226.28 | 187564.09 | 227824 | -40259.91 | Turbine/Generator Reliability
MLWSPEJNT | ML S Expansion Joint Repl | 21404.38 | 163752.7 | 185157.08 | 213703 | -28545.92 | Reliability
MLWMPOTHR | ML M Other Non-Outage PPB | 21985.57 | 158830.36 | 180815.93 | 218360 | -37544.07 | Reliability
MLWVPVALV | ML V FGD CPS Valve Replace | 20936.02 | 153533.41 | 174469.43 | 198399 | -23929.57 | Environmental
MLWNPTOOL | ML N Capital Tool Purchases | 19778.16 | 145296.5 | 165074.66 | 202803 | -37728.34 | Safety/Employee
MLWMPBELT | ML M Conveyor Belt Rplcmts | 18665.7 | 142143.13 | 160808.83 | 191313 | -30504.17 | Fuel Delivery Reliability
MLWVIDFMR | ML VP OUT ID FAN MOTOR REPL | 17580.66 | 139057.2 | 156637.86 | 156809 | -171.14 | Fuel Delivery Reliability
MLWEPSWGR | ML E Switchgear Breaker Rplcmt | 15844.49 | 128048.36 | 143892.85 | 127737 | 16155.85 | Reliability
MLWVPIDHY | ML V ID Fan Hyd Cyl Rplc | 16476.04 | 122913.36 | 139389.4 | 142599 | -3209.6 | Environmental
MLWEPMOTR | ML E Motor Rewind/Rplc >10HP | 16761.91 | 115108.92 | 131870.83 | 256801 | -124930.17 | Reliability
MLWMPPUMP | ML M CY Pump Replace Cap >10HP | 12613.49 | 89975.09 | 102588.58 | 119736 | -17147.42 | Fuel Delivery Reliability
MLWMPFIRE | ML M Fire Protection Replace | 11155.71 | 88087.84 | 99243.55 | 110362 | -11118.45 | Fuel Delivery Reliability
MLWMPECRN | ML M ECrane Capital Work | 9484.08 | 79628.54 | 89112.62 | 130259 | -41146.38 | Environmental
MLWEPAIRD | ML E Air Dryer Install Replace | 10538.77 | 74371.14 | 84909.91 | 118856 | -33946.09 | Reliability
MLWMPMOTR | ML M Motor Rewind/Rplc >10HP | 10405.08 | 73014.45 | 83419.53 | 98584 | -15164.47 | Fuel Delivery Reliability
MLWEPLGHT | ML E Lighting Replacements | 8868.33 | 61677.87 | 70546.2 | 77296 | -6749.8 | Safety/Employee
000026231 | General Plant Cap Blkt - WPCo | 6829.04 | 47807.14 | 54636.18 | 124000 | -69363.82 | Safety/Employee
MLWMPCTRL | ML M Control Upgrades | 6490.9 | 40769.58 | 47260.48 | 59772 | -12511.52 | Reliability
MLWMPVALV | ML M CY Valve Replacements | 4585.36 | 35830.23 | 40415.59 | 20258 | 20157.59 | Fuel Delivery Reliability
MLWMPHEAT | ML M Heat Trace Instl/Rplc | 4695.43 | 32562.1 | 37257.53 | 48825 | -11567.47 | Reliability
MLWEPVALV | ML E Valve Replacements | 4110.38 | 29121.09 | 33231.47 | 33431 | -199.53 | Reliability
MLWVPTRMT | ML V FGD CPS Env Transmitters | 3776.09 | 27471.55 | 31247.64 | 47197 | -15949.36 | Environmental
MLWVPELGC | ML V ELG CAP COMPONENT REPL | 3855.25 | 26102.84 | 29958.09 | 39246 | -9287.91 | Environmental
MLWEPCABL | ML E Cable Replacements | 3432.76 | 25334.26 | 28767.02 | 34924 | -6156.98 | Reliability
MLWVPABEJ | ML V Absorber Exp Joints | 3280.33 | 21958.44 | 25238.77 | 30349 | -5110.23 | Environmental
MLWSPGRBX | ML S Gearbox Replacements | 2462.38 | 19078.06 | 21540.44 | 28029 | -6488.56 | CCR Handling
MLWSPDFAF | ML S Dry Fly Ash Fltr Sep Bags | 1751.21 | 14560.69 | 16311.9 | 23732 | -7420.1 | CCR Handling
MLWOPNONP | ML O Non-Process Outage PPB | 1382.25 | 9248.53 | 10630.78 | 12430 | -1799.22 | Reliability
MLWSPLIME | ML S Lime Injection Equipment | 1108.46 | 9267.16 | 10375.62 | 23744 | -13368.38 | Environmental
MLWSPASHL | ML S Ash Line Remove Replace | 1096.35 | 7869.39 | 8965.74 | 11008 | -2042.26 | CCR Handling
MLWVPTANK | ML V FGD CPS Tanks | 725.99 | 5290.62 | 6016.61 | 10934 | -4917.39 | Environmental
MLWOPFGDP | ML O FGD Process Outage PPB | 253.35 | 2122.97 | 2376.32 | 8289 | -5912.68 | Environmental
MLWPCT1PC | ML1 Cooling Tower Canopy PreCI | 213.6 | 1013.01 | 1226.61 | 1 | 1225.61 | Reliability
MLWSPCLGR | ML S Clinker Grinder Replace | -1896.14 | -19090.11 | -20986.25 | 72549 | -93535.25 | Boiler Reliability
Grand Total |  | 6630643.12 | 47484018.64 | 54114661.76 | 67753683 | -13639021.24
Methodology: Data represents actual costs incurred life to date, excluding AFUDC, through 12/31/2025 against account 1070001 for work orders which were placed in service during calendar year 2025. The estimates are based on property accounting estimates input at the time of work order creation with adjustments as needed for phased work orders.

## 5b Cur Yr Ctl >=$500k
Project Description | 2026, Total Estimated $ | Reason (see tab "5 a and b for Key" for more detail)
Total
Methodology: Data represents the 2026 Control budget, excluding AFUDC, for account 1070001 with expected adjustments incorporated. The numbers represent total operating dollars prior to allocating between the owners.

## 5 a and b Key
Reason | Reason Description
Availability | Projects to enhance the performance of the Plant.
Boiler Reliability | Projects performed to enhance reliability of the boiler.
Buildings | Required structure improvements.
CCR Handling | Projects for ash disposal.
Day to day reliability projects | Minor reliability improvement projects (less than $500k).
Environmental | Projects performed to maintain compliance with environmental laws.
Fuel Delivery Reliability | Projects related to coal handling and efficient delivery to the Units.
Reliability | General Plant improvements not related to a specific process.
Safety/Employee | Projects to ensure safe Plant environment for employees.
Turbine/Generator Reliability | Projects performed to enhance reliability of the turbine generator system.

## 5c Prior Yr CapEx Variances
Project Description | 2025 KY Act $ | 2025 KY Fore $ | 2025 KY Act minus Fore $ | 2025 WP Act $ | 2025 WP Fore $ | 2025 WP Act minus Fore $ | 2025 Total Act $ | 2025 Total Fore $ | 2025 Total minus Fore $
000026265 ML U2 Cooling Tower Reinforce | 1843894.29 | 1808914.421 | 34979.869 | 14257718.6 | 14426373.342 | -168654.742 | 16101612.89 | 16235287.763 | -133674.873
MLWVC1CL1 Mitchell U1 SCR Catalyst L1 | 257837.95 | 232329.065 | 25508.885 | 1858614.34 | 1819067.29 | 39547.05 | 2116452.29 | 2051396.355 | 65055.935
MLWEP1GNI ML E U1 Generator Field Out In | 239074.67 | 163408.158 | 75666.512 | 1780646.87 | 1291505.435 | 489141.435 | 2019721.54 | 1454913.593 | 564807.947
MLW1CGRPL ML U1 Clinker Grinder Replace | 173877.88 | 120089.6 | 53788.28 | 1291842.09 | 949464.167 | 342377.923 | 1465719.97 | 1069553.767 | 396166.203
MLWEPPUMP ML E Pump Replacements | 126279.19 | 36806.105 | 89473.085 | 1020910.67 | 291774.394 | 729136.276 | 1147189.86 | 328580.499 | 818609.361
MLWEPMOTR ML E Motor Rewind/Rplc >10HP | 116343.33 | 7361.222 | 108982.108 | 1006179.26 | 58354.877 | 947824.383 | 1122522.59 | 65716.099 | 1056806.491
MLWPC0ELG ML PCC U0 ELG/CCR Compliance | 338595.32 | 418794.603 | -80199.283 | 698406.51 | 424585.478 | 273821.032 | 1037001.83 | 843380.081 | 193621.749
MLWMPD10T ML M Rebuild D10T Caught Fire | 109772.41 | 80331.812 | 29440.598 | 901689.42 | 636377.626 | 265311.794 | 1011461.83 | 716709.438 | 294752.392
MLWEP1GGB ML E U1 Gen Gas Baffle Purch | 117996.02 | 0 | 117996.02 | 883360.11 | 0 | 883360.11 | 1001356.13 | 0 | 1001356.13
MLWEPCTRL ML E Control Upgds Rplcmts | 107061.81 | 103532.427 | 3529.383 | 857762.51 | 823749.143 | 34013.367 | 964824.32 | 927281.57 | 37542.75
MLWSPBRNN ML S Burner Nozzle Rplcmt | 102240.94 | 0 | 102240.94 | 803477.66 | 0 | 803477.66 | 905718.6 | 0 | 905718.6
MLWSPCCHN ML S Collection Cnv Chain Repl | 91558.76 | 387580.747 | -296021.987 | 719868.35 | 394258.405 | 325609.945 | 811427.11 | 781839.152 | 29587.958
MLWVPOPIP ML V Outage FGD Pipe Replace | 91272.05 | 0 | 91272.05 | 658376.86 | 0 | 658376.86 | 749648.91 | 0 | 749648.91
MLWNPBLDG ML N Capital Building Upgrades | 80021.6 | 22083.659 | 57937.941 | 657639.05 | 175064.637 | 482574.413 | 737660.65 | 197148.296 | 540512.354
MLWES1BTI ML1 E BFPT INSPECTION | 86684.89 | 33501.054 | 53183.836 | 650251.05 | 264742.891 | 385508.159 | 736935.94 | 298243.945 | 438691.995
MLWMPOTHR ML M Other Non-Outage PPB | 74432.5 | 49427.219 | 25005.281 | 588875.83 | 397218.565 | 191657.265 | 663308.33 | 446645.784 | 216662.546
MLWSPPULV ML S Pulverizer Rebuilds | 73026.91 | 113246.923 | -40220.013 | 582409.95 | 903358.126 | -320948.176 | 655436.86 | 1016605.049 | -361168.189
MLWVPPUMP ML V FGD CPS Pumps | 68212.02 | 1247.216 | 66964.804 | 543948.98 | 10142.861 | 533806.119 | 612161 | 11390.077 | 600770.923
MLWESCRTV ML E Comb Reheat Turbine Valve | 59209.04 | 0 | 59209.04 | 491243.93 | 0 | 491243.93 | 550452.97 | 0 | 550452.97
MLWVPEJNT ML V FGD CPS Expansion Joints | 60020.11 | 11777.958 | 48242.152 | 459160.24 | 93367.808 | 365792.432 | 519180.35 | 105145.766 | 414034.584
MLWSPVALV ML S Blr Brnr Steam Valve Repl | 56958.77 | 36580.877 | 20377.893 | 441531.98 | 297490.062 | 144041.918 | 498490.75 | 334070.939 | 164419.811
MLWVPHBSH ML V ID Fan Hub Shell Rplc | 56706.49 | 0 | 56706.49 | 435661.03 | 0 | 435661.03 | 492367.52 | 0 | 492367.52
MLWMPROTO ML M Roto Booster Fan Replace | 55476.49 | 20924.294 | 34552.196 | 432061.25 | 165596.24 | 266465.01 | 487537.74 | 186520.534 | 301017.206
MLWVP11ID MLP V REBUILD #11 ID FAN | 56567.63 | -24.421 | 56592.051 | 429437.21 | -193.163 | 429630.373 | 486004.84 | -217.584 | 486222.424
MLWEPTRMT ML E Transmitter Replacements | 54882.74 | 12160.172 | 42722.568 | 425271.8 | 96627.083 | 328644.717 | 480154.54 | 108787.255 | 371367.285
MLWVP21ID MLP V REBUILD #21 ID FAN | 53936.48 | 13853.157 | 40083.323 | 382982.71 | 113780.114 | 269202.596 | 436919.19 | 127633.271 | 309285.919
MLWSPSBSR MLP STACK BREACH CASING REPL | 50237.28 | 31419.656 | 18817.624 | 370190.51 | 248915.779 | 121274.731 | 420427.79 | 280335.435 | 140092.355
MLWSP2BLC ML2 S BLR CAMERA UPGRADE (OUT) | 40306.44 | 13132.205 | 27174.235 | 345771.01 | 101080.16 | 244690.85 | 386077.45 | 114212.365 | 271865.085
MLW2CGRPL ML U2 Clinker Grinder Replace | 46591.11 | 147500.93 | -100909.82 | 333546.04 | 1158101.083 | -824555.043 | 380137.15 | 1305602.013 | -925464.863
MLWNPFIRE ML N Fire Systems Capital Repl | 36005.68 | 21221.826 | 14783.854 | 302195.71 | 166978.255 | 135217.455 | 338201.39 | 188200.081 | 150001.309
MLWVP22ID MLP V REBUILD #22 ID FAN | 31485.3 | 36101.461 | -4616.161 | 259806.66 | 284859.38 | -25052.72 | 291291.96 | 320960.841 | -29668.881
MLWMPCOMP ML M CY Conv Component Repl | 31620.26 | 5214.206 | 26406.054 | 254959.28 | 41334.743 | 213624.537 | 286579.54 | 46548.949 | 240030.591
GENLOTOWP WPCo Generation Lockout Tagout | 22501.17 | 19386.309 | 3114.861 | 197666.87 | 159502.241 | 38164.629 | 220168.04 | 178888.55 | 41279.49
MLWVPFGDN ML V FGD Other Non Outage PPB | 25066.8 | 0 | 25066.8 | 184234.35 | 0 | 184234.35 | 209301.15 | 0 | 209301.15
MLWMPBELT ML M Conveyor Belt Rplcmts | 20907.26 | 42940.461 | -22033.201 | 167666.62 | 340403.494 | -172736.874 | 188573.88 | 383343.955 | -194770.075
MLWEPTURB ML E Trb Brg, Rtr, Shaft Rbld | 22337.81 | 0 | 22337.81 | 165226.28 | 0 | 165226.28 | 187564.09 | 0 | 187564.09
MLWEPHVAC MLP E HVAC Unit Replacements | 20137.55 | 9814.97 | 10322.58 | 153283.23 | 77806.543 | 75476.687 | 173420.78 | 87621.513 | 85799.267
MLWVIDFMR ML VP OUT ID FAN MOTOR REPL | 17580.66 | 19785.537 | -2204.877 | 139057.2 | 156527.835 | -17470.635 | 156637.86 | 176313.372 | -19675.512
MLWSPEJNT ML S Expansion Joint Repl | 17639.36 | 26762.492 | -9123.132 | 137848.52 | 212480.466 | -74631.946 | 155487.88 | 239242.958 | -83755.078
MLWSPNPPB ML S Other Non Outage PPB | 15175.92 | 0 | 15175.92 | 133316.4 | 0 | 133316.4 | 148492.32 | 0 | 148492.32
MLWMPHSTF ML M HS TUNNEL FIRE CAPITAL | 18059.79 | 0 | 18059.79 | 127042.12 | 0 | 127042.12 | 145101.91 | 0 | 145101.91
MLWEPSWGR ML E Switchgear Breaker Rplcmt | 15844.49 | 0 | 15844.49 | 128048.36 | 0 | 128048.36 | 143892.85 | 0 | 143892.85
MLWVPIDHY ML V ID Fan Hyd Cyl Rplc | 16476.04 | 0 | 16476.04 | 122913.36 | 0 | 122913.36 | 139389.4 | 0 | 139389.4
MLWEPDFPM ML E Diesel Fire Pump Replace | 16515.41 | 0 | 16515.41 | 120920.79 | 0 | 120920.79 | 137436.2 | 0 | 137436.2
MLWVPVALV ML V FGD CPS Valve Replace | 14900.46 | 14722.442 | 178.018 | 119033.66 | 116709.762 | 2323.898 | 133934.12 | 131432.204 | 2501.916
MLWEPAIRD ML E Air Dryer Install Replace | 13482.99 | 0 | 13482.99 | 106129.81 | 0 | 106129.81 | 119612.8 | 0 | 119612.8
MLWEPTFRM ML E Transformers | 13845.02 | 0 | 13845.02 | 102541.92 | 0 | 102541.92 | 116386.94 | 0 | 116386.94
MLWVPBLML ML V Ball Mill Liner Replace | 12204.89 | 0 | 12204.89 | 88967.13 | 0 | 88967.13 | 101172.02 | 0 | 101172.02
MLWMPFIRE ML M Fire Protection Replace | 11155.71 | 24118.195 | -12962.485 | 88087.84 | 189866.769 | -101778.929 | 99243.55 | 213984.964 | -114741.414
MLWMPECRN ML M ECrane Capital Work | 9484.08 | 0 | 9484.08 | 79628.54 | 0 | 79628.54 | 89112.62 | 0 | 89112.62
MLWMPMOTR ML M Motor Rewind/Rplc >10HP | 10405.08 | 6134.356 | 4270.724 | 73014.45 | 48629.102 | 24385.348 | 83419.53 | 54763.458 | 28656.072
000026231 General Plant Cap Blkt - WPCo | 9795.08 | 0 | 9795.08 | 72617.13 | 0 | 72617.13 | 82412.21 | 0 | 82412.21
MLWSPASHL ML S Ash Line Remove Replace | 7411.95 | 0 | 7411.95 | 63350.3 | 0 | 63350.3 | 70762.25 | 0 | 70762.25
MLWEPLGHT ML E Lighting Replacements | 8868.33 | 23555.901 | -14687.571 | 61677.87 | 186735.614 | -125057.744 | 70546.2 | 210291.515 | -139745.315
MLWEPCWPM ML E Circ Water Pump Reb (Cap) | 8288.62 | 17330.502 | -9041.882 | 61021.97 | 136517.463 | -75495.493 | 69310.59 | 153847.965 | -84537.375
MLWMPPUMP ML M CY Pump Replace Cap >10HP | 8237.2 | 5214.206 | 3022.994 | 59865.24 | 41334.743 | 18530.497 | 68102.44 | 46548.949 | 21553.491
MLWEPCABL ML E Cable Replacements | 7202.75 | 5888.979 | 1313.771 | 58452.63 | 46683.904 | 11768.726 | 65655.38 | 52572.883 | 13082.497
MLWEP2BAT ML E U2 Station Battery Rep | 6843.94 | 18083.934 | -11239.994 | 55334.65 | 143005.609 | -87670.959 | 62178.59 | 161089.543 | -98910.953
MLWNPWINT ML CAPITAL WINTERIZATION | 6829.43 | 0 | 6829.43 | 50178.04 | 0 | 50178.04 | 57007.47 | 0 | 57007.47
MLWVPTRMT ML V FGD CPS Env Transmitters | 5473.24 | 0 | 5473.24 | 46784.6 | 0 | 46784.6 | 52257.84 | 0 | 52257.84
MLWVPAIRC ML V FGD Air Compressor Rplc | 6164.24 | 0 | 6164.24 | 45749.47 | 0 | 45749.47 | 51913.71 | 0 | 51913.71
MLWNPTOOL ML N Capital Tool Purchases | 7266.57 | 17816.492 | -10549.922 | 43587.72 | 141237.319 | -97649.599 | 50854.29 | 159053.811 | -108199.521
MLWMPVALV ML M CY Valve Replacements | 4585.36 | 0 | 4585.36 | 35830.23 | 0 | 35830.23 | 40415.59 | 0 | 40415.59
MLWSPDFAF ML S Dry Fly Ash Fltr Sep Bags | 3313.98 | 13526.277 | -10212.297 | 27450.5 | 108229.891 | -80779.391 | 30764.48 | 121756.168 | -90991.688
MLWVPMONS ML V Monitoring Systems | 3488.12 | 6134.356 | -2646.236 | 27220.16 | 48629.102 | -21408.942 | 30708.28 | 54763.458 | -24055.178
MLWEPCATT ML E Cation Tank Rplc | 2888.95 | 0 | 2888.95 | 23748.24 | 0 | 23748.24 | 26637.19 | 0 | 26637.19
MLWSPGRBX ML S Gearbox Replacements | 2462.38 | 0 | 2462.38 | 19078.06 | 0 | 19078.06 | 21540.44 | 0 | 21540.44
MLWEPVALV ML E Valve Replacements | 1979.01 | -248990.087 | 250969.097 | 14882.16 | -1973828.472 | 1988710.632 | 16861.17 | -2222818.559 | 2239679.729
MLWHAULRD Mitchell Haul Road Relocate | 1825.57 | 0 | 1825.57 | 13125.88 | 0 | 13125.88 | 14951.45 | 0 | 14951.45
MLWMPHEAT ML M Heat Trace Instl/Rplc | 1687.16 | 0 | 1687.16 | 11864.44 | 0 | 11864.44 | 13551.6 | 0 | 13551.6
MLWVPTANK ML V FGD CPS Tanks | 1372.83 | 0 | 1372.83 | 9902.99 | 0 | 9902.99 | 11275.82 | 0 | 11275.82
MLWSPLIME ML S Lime Injection Equipment | 1108.46 | 0 | 1108.46 | 9267.16 | 0 | 9267.16 | 10375.62 | 0 | 10375.62
MLWEP2LA0 ML2 E LPA L0 Rotor Repr at CMS | 1217.6 | 0 | 1217.6 | 8523.19 | 0 | 8523.19 | 9740.79 | 0 | 9740.79
MLWEP2LB0 ML2 E LPB L0 Rotor Repr at CMS | 1217.6 | 0 | 1217.6 | 8523.19 | 0 | 8523.19 | 9740.79 | 0 | 9740.79
MLWEPBFPB ML E BFP Rebuild Removed (Cap) | 591.72 | 0 | 591.72 | 4141.67 | 0 | 4141.67 | 4733.39 | 0 | 4733.39
MLWEP2LA1 ML2 E LPA L1 Rotor Repr at CMS | 389.56 | 0 | 389.56 | 2726.91 | 0 | 2726.91 | 3116.47 | 0 | 3116.47
MLWEP2LB1 ML2 E LPB L1 Rotor Repr at CMS | 389.56 | 0 | 389.56 | 2726.91 | 0 | 2726.91 | 3116.47 | 0 | 3116.47
MLWOPNONP ML O Non-Process Outage PPB | 364.05 | 0 | 364.05 | 2587.12 | 0 | 2587.12 | 2951.17 | 0 | 2951.17
MLWVPABEJ ML V Absorber Exp Joints | 416.51 | 0 | 416.51 | 2254.72 | 0 | 2254.72 | 2671.23 | 0 | 2671.23
MLWOPFGDP ML O FGD Process Outage PPB | 253.35 | 0 | 253.35 | 2122.97 | 0 | 2122.97 | 2376.32 | 0 | 2376.32
ITCB413W0 KENTUCKY POWER - GEN | 102.9 | 0 | 102.9 | 746.8 | 0 | 746.8 | 849.7 | 0 | 849.7
MLWMPCTRL ML M Control Upgrades | 28.27 | 0 | 28.27 | 197.93 | 0 | 197.93 | 226.2 | 0 | 226.2
MLWNPROAD ML N Road Paving and Capital | 3.44 | 0 | 3.44 | 23.99 | 0 | 23.99 | 27.43 | 0 | 27.43
MLWPCT1PC ML1 Cooling Tower Canopy PreCI | 0.65 | 0 | 0.65 | 4.59 | 0 | 4.59 | 5.24 | 0 | 5.24
MLWEPCWPR ML E Circ Water Pump Replace | 0 | 51539.589 | -51539.589 | 0 | 409229.269 | -409229.269 | 0 | 460768.858 | -460768.858
MLWEP2HRR ML E U2 HP/1st RH Rotor Repair |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
X00000290 For Property Acctg Use Only | 0 | 179127.769 | -179127.769 | 0 | 1418069.95 | -1418069.95 | 0 | 1597197.719 | -1597197.719
MLWEPELVC ML E Elevator Controls Upgrade | 0 | 17176.172 | -17176.172 | 0 | 136161.307 | -136161.307 | 0 | 153337.479 | -153337.479
INCCAPINV Incremental Capital Investment | 0 | -540.549 | 540.549 | 0 | -4337.341 | 4337.341 | 0 | -4877.89 | 4877.89
000022392 ML LANDFILL EXPANSION - PH 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
EVRCS Cap Stnd - Environmental Repl | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWEPDVLV ML E Demineralizer Valve Rplc |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MLWEPCWPS ML E Circ Water Pump Cap Spare | 0 | 48542.077 | -48542.077 | 0 | 386615.648 | -386615.648 | 0 | 435157.725 | -435157.725
GWSCBU420 PPB UNREG PPA 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWSPSJNT ML S Burner Line Slip Jnt Repl | 0 | 32654.596 | -32654.596 | 0 | 260799.172 | -260799.172 | 0 | 293453.768 | -293453.768
AP24IRCM1 WPCo Gen 24 IRC ML U2 CT Shell | 0 | 0.012 | -0.012 | 0 | 0.027 | -0.027 | 0 | 0.039 | -0.039
MLWEP2LAR ML E U2 LPA Rotor Repr at CMS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MLWPC0LF3 ML PCC U0 Landfill Exp Ph 3 | 0 | 45072.163 | -45072.163 | 0 | 355881.659 | -355881.659 | 0 | 400953.822 | -400953.822
MLWMPBUBC ML M Barge Unldr Bckt Chn Repl | 0 | 142512.977 | -142512.977 | 0 | 1126924.206 | -1126924.206 | 0 | 1269437.183 | -1269437.183
TSCREDITC Tech Servics Cap Offset Credit | 0 | -13504.195 | 13504.195 | 0 | -105161.845 | 105161.845 | 0 | -118666.04 | 118666.04
MLWNPLABR ML N Capital Labor Budgeting | 0 | 45196.348 | -45196.348 | 0 | 358422.35 | -358422.35 | 0 | 403618.698 | -403618.698
000001075 Non Regulated Fuels Accounting |  |  |  | 0 | -136.56 | 136.56 | 0 | -136.56 | 136.56
MLWMPGRBX ML M Gearbox Rebuild PPB | 0 | 3680.607 | -3680.607 | 0 | 29177.428 | -29177.428 | 0 | 32858.035 | -32858.035
MLWSPOILL ML S Oil Lighter Replacements | 0 | 30767.415 | -30767.415 | 0 | 244922.902 | -244922.902 | 0 | 275690.317 | -275690.317
MLWSPPEXP ML S Pulv Exp Joint Repl | 0 | 34356.042 | -34356.042 | 0 | 272329.865 | -272329.865 | 0 | 306685.907 | -306685.907
MLWEPTBCU ML E TURBINE CONTROLS UPGRADE | 0 | 952.043 | -952.043 | 0 | 7742.384 | -7742.384 | 0 | 8694.427 | -8694.427
MLWSOBRNB ML S BURNER BARRIER REPLACEMNT | 0 | 32212.244 | -32212.244 | 0 | 255768.292 | -255768.292 | 0 | 287980.536 | -287980.536
MLWSPPDMP ML S PULV DAMPER REPL (OUT) | 0 | 75450.435 | -75450.435 | 0 | 598330.409 | -598330.409 | 0 | 673780.844 | -673780.844
MLWSP1BLC ML1 S BLR CAMERA UPGRADE (OUT) | 0 | 19668.838 | -19668.838 | 0 | 155230.582 | -155230.582 | 0 | 174899.42 | -174899.42
CFOCAPPRJ CFO CAPITAL PROJECTS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWEC2HSI ML E U2 HP&2RH Trb & Rtr Insp | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWSPSFVL ML S Safety Valves | 0 | 18403.048 | -18403.048 | 0 | 145887.196 | -145887.196 | 0 | 164290.244 | -164290.244
MLWSP2BSS ML2 S Boiler Sidewall Seals | 0 | 82007.322 | -82007.322 | 0 | 657780.907 | -657780.907 | 0 | 739788.229 | -739788.229
GWSCB Cap Blkt - Prod Plant Blnkt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWEPNPCS ML E Nash Pump Cap Spare | 0 | 38032.964 | -38032.964 | 0 | 301500.175 | -301500.175 | 0 | 339533.139 | -339533.139
MLWEPXPPT ML E Exciter PPT Xfrmr Repl | 0 | 10598.748 | -10598.748 | 0 | 83717.086 | -83717.086 | 0 | 94315.834 | -94315.834
MLWMPLGBX ML M Limestone GRBX Cap Spare | 0 | 9163.57 | -9163.57 | 0 | 72543.482 | -72543.482 | 0 | 81707.052 | -81707.052
MLWES2BTI ML2 E BFPT INSPECTION | 0 | 30513.582 | -30513.582 | 0 | 242791.645 | -242791.645 | 0 | 273305.227 | -273305.227
MLWMPPOND ML M N CY Pond Trtmnt Facility | 0 | 44167.321 | -44167.321 | 0 | 350129.278 | -350129.278 | 0 | 394296.599 | -394296.599
MLWVPBMIL ML V Ball Mill Inlt Liner Repl | 0 | 17090.051 | -17090.051 | 0 | 135378.76 | -135378.76 | 0 | 152468.811 | -152468.811
MLWSPBECK ML S Brnr Rgstr Sleeve Drv Rpl | 0 | 22083.666 | -22083.666 | 0 | 175064.64 | -175064.64 | 0 | 197148.306 | -197148.306
MLWEP2SRR ML E U2 2nd RH Rotor Insp Rpr |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MLWSPBLWR ML S Blowers & Fans Rplc | 0 | 7115.84 | -7115.84 | 0 | 56409.677 | -56409.677 | 0 | 63525.517 | -63525.517
MLWVPDSIN ML V DSI Non Outage PPB Rplcmt | 0 | 935.412 | -935.412 | 0 | 7607.144 | -7607.144 | 0 | 8542.556 | -8542.556
BUDOFFSET Budget Reductions/Offsets | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWMPCHUT ML M Chute Replacements | 0 | 38548.779 | -38548.779 | 0 | 304271.499 | -304271.499 | 0 | 342820.278 | -342820.278
MLWVPMEMB ML V RO Membrane Replacements | 0 | 6230.054 | -6230.054 | 0 | 49387.716 | -49387.716 | 0 | 55617.77 | -55617.77
MLWVPIDEJ ML V ID Fan Expansion Joints | 0 | 7714.857 | -7714.857 | 0 | 61153.292 | -61153.292 | 0 | 68868.149 | -68868.149
MLWEPBLWR ML E Blower Vent Fan Repl | 0 | 18812.191 | -18812.191 | 0 | 152988.128 | -152988.128 | 0 | 171800.319 | -171800.319
MLWEPCPLC ML E Critical PLC Replacements | 0 | 5786.142 | -5786.142 | 0 | 45864.967 | -45864.967 | 0 | 51651.109 | -51651.109
000001586 Capital Staff Project | 0 | 0 | 0 | 0 | 0.001 | -0.001 | 0 | 0.001 | -0.001
MLWSPBRNR ML S Coal Burner Replacements | 0 | 8262.814 | -8262.814 | 0 | 67196.443 | -67196.443 | 0 | 75459.257 | -75459.257
MLWVPOXAB ML V Oxidation Air Blowers | 0 | 3533.383 | -3533.383 | 0 | 28010.344 | -28010.344 | 0 | 31543.727 | -31543.727
MLWEPRESN ML E Resin Replacements |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
MLWVPSCRM ML V SCR GAS MNTR SYSTEM REPL | 0 | 33676.068 | -33676.068 | 0 | 268388.364 | -268388.364 | 0 | 302064.432 | -302064.432
MLWSPCCRC ML S CCR Critical Cap Replmnts | 0 | 72771.291 | -72771.291 | 0 | 74079.65 | -74079.65 | 0 | 146850.941 | -146850.941
MLWMPGGBX ML M Gypsum GRBX Cap Spare | 0 | 18403.048 | -18403.048 | 0 | 145887.196 | -145887.196 | 0 | 164290.244 | -164290.244
MLWEPROOF ML E Roof Replacements |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
TLSWEMERG TRANS Project Labor | 0 | 0 | 0 | 0 | 0.003 | -0.003 | 0 | 0.003 | -0.003
MLWEPSTRN ML E Strainer Replacements | 0 | 15761.884 | -15761.884 | 0 | 124578.869 | -124578.869 | 0 | 140340.753 | -140340.753
WSNANDA Generation ANDA |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
BUDTRKTBD Budget Adjustments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MLWMPHEVY ML M Heavy Equip Rebuild PPB | 0 | 79746.553 | -79746.553 | 0 | 632177.852 | -632177.852 | 0 | 711924.405 | -711924.405
MLWMPHSGB ML M HS Coal GRBX Cap Spare | 0 | 53260.506 | -53260.506 | 0 | 422245.081 | -422245.081 | 0 | 475505.587 | -475505.587
MLWVPELGC ML V ELG CAP COMPONENT REPL | -1316.51 | 0 | -1316.51 | -9390.1 | 148158.923 | -157549.023 | -10706.61 | 148158.923 | -158865.533
MLWSPCLGR ML S Clinker Grinder Replace | -1896.14 | 0 | -1896.14 | -19090.11 | 0 | -19090.11 | -20986.25 | 0 | -20986.25
Grand Total | 5210762.58 | 5338225.551 | -127462.971 | 38377514.14 | 36473614.188 | 1903899.952 | 43588276.72 | 41811839.739 | 1776436.981
Methodology: Data represents 2025 Actual costs compared to the Forecast measure, excluding AFUDC, for account 1070001. The Forecast measure is the working budget which gets updated throughout the calendar year during which the costs are incurred and against which teams are held accountable.

## 5c 10 Yr Cap Budg
Project Description | 2026 Total Control $ | 2027 Total Control $ | 2028 Total Control $ | 2029 Total Control $ | 2030 Total Control $ | 2031 Total Control $ | 2032 Total Control $ | 2033 Total Control $ | 2034 Total Control $ | 2035 Total Control $ | 2026-35 Total Control $
Methodology: Data represents the 2026-2035 Control budget, excluding AFUDC, for account 1070001 with expected adjustments incorporated. The numbers represent total operating dollars prior to allocating between the owners.