## Capital
|  | Actuals Spend thought April 2025 |  |  | Forecast Additional Spend through December 2025
Category | Project | Kentucky Power | Wheeling Power | Total Actual | Kentucky Power | Wheeling Power | Total Forecasted
Administration | 000001586 Capital Staff Project |  |  |  | -130904.6658 | -1062395.7562 | -1193300.422
| TSCREDITC Tech Servics Cap Offset Credit |  |  |  | -54850.0044 | -445150.0356 | -500000.04
Ash Handling Facilities | MLWMPPOND ML M N CY Pond Trtmnt Facility |  |  |  | 49428.4706 | 401150.1124 | 450578.583
Ash, Wastewater CCR | MLWSPCCHN ML S Collection Cnv Chain Repl | 57079.53 | 395087.37 | 452166.9 | 405154.4784 | 309344.7506 | 714499.229
Ash, Wastewater-Landfill | MLWPC0LF3 ML PCC U0 Landfill Exp Ph 3 |  |  |  | 44883.3203 | 364262.7167 | 409146.037
Ash, Wastewtr Systems Group | MLWSPASHL ML S Ash Line Remove Replace | 1507.43 | 9952.87 | 11460.3 | -983.5417 | -7982.1983 | -8965.74
BlrDrft/CombustnAir-FGD Assoc | MLWVPIDEJ ML V ID Fan Expansion Joints | 2927.33 | 14356.07 | 17283.4 | 8058.0089 | 65396.9491 | 73454.958
| MLWVPIDHY ML V ID Fan Hyd Cyl Rplc | 6312.82 | 46083.11 | 52395.93 | -5747.8335 | -46648.0965 | -52395.93
Boiler & Auxiliaries | MLWSPBRNE ML S Coal Burner Exp Joint Rpl | 366.21 | 1814.92 | 2181.13
| MLWSPBRNN ML S Burner Nozzle Rplcmt | 574067.28 | 3361057.62 | 3935124.9
| MLWSPSOOT ML S Sootblower Replace Remove | 153356.57 | 831255.39 | 984611.96
| MLWSPVALV ML S Blr Brnr Steam Valve Repl | 64671.26 | 427526.09 | 492197.35 | -16869.1142 | -136905.8558 | -153774.97
| MLWNPINSL ML N Insulation & Lagging Rplc | 99488.27 | 486591.94 | 586080.21
| MLWSPDUCT ML S Duct Lag Insul Replace | 23644.99 | 117779.16 | 141424.15
| MLWSPNPPB ML S Other Non Outage PPB | 51520.45 | 293866.73 | 345387.18
| MLWSPGRBX ML S Gearbox Replacements | 1774.32 | 12139.5 | 13913.82 | -1178.5345 | -9564.7155 | -10743.25
| MLW2CGRPL ML U2 Clinker Grinder Replace | 169146.62 | 1057307.9 | 1226454.52 | 145718.8134 | 1182620.4156 | 1328339.229
| MLW1CGRPL ML U1 Clinker Grinder Replace | 205765.08 | 1367675.06 | 1573440.14 | 19086.1091 | 154898.4769 | 173984.586
| MLWOPSOOT ML O Sootblower (Stm Outg) | 1519.65 | 9623.35 | 11143
| MLWSPBECK ML S Brnr Rgstr Sleeve Drv Rpl |  |  |  | 24714.2331 | 200575.0389 | 225289.272
| MLWSPSJNT ML S Burner Line Slip Jnt Repl |  |  |  | 24174.0273 | 196190.8527 | 220364.88
Boiler Draft/Combustn Air Grp | MLWSPFANS ML S Fans Blowers etc | 1032.5 | 5633.23 | 6665.73
Boiler Make-up Water Sup Syst | MLWEPRESN ML E Resin Replacements | 43246.29 | 232620.26 | 275866.55
Boiler/Boiler Components | MLWOPNONP ML O Non-Process Outage PPB | 315461.84 | 1708146.5 | 2023608.34 | -323.7433 | -2627.4267 | -2951.17
| MLWSC1AHB ML S U1 Air Heater Basket Rplc | 577060.31 | 3149896.39 | 3726956.7
| MLWSC2AHB ML S U2 Air Heater Basket Rplc | 649887.76 | 3194252.44 | 3844140.2
| MLWSP2LSO ML S U2 Lower Sidewl Weld Ovly | 235084.74 | 1149788.72 | 1384873.46
| MLWEPNPCS ML E Nash Pump Cap Spare |  |  |  | 42563.3991 | 345434.7699 | 387998.169
| MLWEPSTRN ML E Strainer Replacements |  |  |  | 15411.3051 | 125074.6119 | 140485.917
| MLWSOBRNB ML S BURNER BARRIER REPLACEMNT |  |  |  | 31604.2631 | 256492.9389 | 288097.202
| MLWSP1BLC ML1 S BLR CAMERA UPGRADE (OUT) |  |  |  | 21545.3614 | 174857.2036 | 196402.565
| MLWSP2BLC ML2 S BLR CAMERA UPGRADE (OUT) |  |  |  | 22769.2315 | 184789.8525 | 207559.084
| MLWSP2BSS ML2 S Boiler Sidewall Seals |  |  |  | 39884.2203 | 323691.1697 | 363575.39
| MLWSPSFVL ML S Safety Valves |  |  |  | 20595.1948 | 167145.8702 | 187741.065
Bottom Ash Disposal Sys CCR | MLWSPCCRC ML S CCR Critical Cap Replmnts |  |  |  | 84322.265 | 84322.265 | 168644.53
Building Facilities | MLWEPELVC ML E Elevator Controls Upgrade |  |  |  | 19222.1721 | 156002.7329 | 175224.905
Condenser & Auxiliaries | MLWEPVALV ML E Valve Replacements | 48998.38 | 282546.15 | 331544.53 | -279620.499 | -2269335.736 | -2548956.235
Cooling Twr, Misc Wtr, ChemGrp | MLWPC2CTC ML PCC U2 Cooling Tower Comp | 666383.03 | 3255657.45 | 3922040.48
| 000026265 ML U2 Cooling Tower Reinforce | 2455312.87 | 16311029.41 | 18766342.28 | 1739009.3922 | 14113400.7468 | 15852410.139
Cooling Water Facilities | MLWEPCWPM ML E Circ Water Pump Reb (Cap) | 161698.93 | 942705.03 | 1104403.96 | 15534.8877 | 126077.5803 | 141612.468
| MLWEPCWPR ML E Circ Water Pump Replace |  |  |  | 50566.821 | 410388.703 | 460955.524
| MLWEPCWPS ML E Circ Water Pump Cap Spare |  |  |  | 52768.4878 | 428256.9252 | 481025.413
CT/CC Group | MLWEC1CTF ML E U1 Cooling Tower Compnnts | 1336903.56 | 7352605.55 | 8689509.11
| MLWPCT1PC ML1 Cooling Tower Canopy PreCI | 213.6 | 1013.01 | 1226.61 | -0.57483 | -4.6652 | -5.24
| MLWPCT1BP ML U1 Cooling Tower Canopy RPL | 622366.72 | 3706128.12 | 4328494.84
Environmental | MLWNPROAD ML N Road Paving and Capital | 812.65 | 5068.92 | 5881.57 | -3.0091 | -24.4209 | -27.43
| MLWSPEJNT ML S Expansion Joint Repl | 425980.95 | 2323783.64 | 2749764.59 | 24346.0528 | 197586.9722 | 221933.025
| MLWDFALND ML DFA LAND ACQUISITION | 126333.59 | 690579.2 | 816912.79
| MLWMPDRNG ML M Drainage Projects (Cap) | 15734.78 | 89714.81 | 105449.59
| MLWVPMONS ML V Monitoring Systems | 906.76 | 5580.75 | 6487.51 | 6865.0708 | 55715.3372 | 62580.408
| MLWVPCNTM ML V Containment Systems | 731.85 | 4945.68 | 5677.53
| MLWEPCATT ML E Cation Tank Rplc | 17318.65 | 119390.15 | 136708.8 | -868.8898 | -7051.7102 | -7920.6
| MLWSPPEXP ML S Pulv Exp Joint Repl |  |  |  | 35884.1945 | 291227.8795 | 327112.074
| MLWVPMEMB ML V RO Membrane Replacements |  |  |  | 6972.1663 | 56584.4997 | 63556.666
Facilities | MLWSHSVB 2021 Gen Plt Cap Blkt - KYPC-G | 6101.47 | 29235.95 | 35337.42
| MLWSTORB Gen Plt Blkt KY-G WP | 696.95 | 3339.25 | 4036.2
| 000026231 General Plant Cap Blkt - WPCo | 7238.37 | 50677.47 | 57915.84 | -6353.3676 | -51562.4724 | -57915.84
FGD (Scrubber) Group | MLWMPECRN ML M ECrane Capital Work | 55151.06 | 284093.68 | 339244.74
| MLWOPFGDP ML O FGD Process Outage PPB | 266913.47 | 1513108.59 | 1780022.06
| MLWPC0LIM ML PCC U0 Lime Conversion | 1636278.6 | 8141749.13 | 9778027.73
| MLWVPAIRC ML V FGD Air Compressor Rplc | 10415.78 | 65632.61 | 76048.39
| MLWVPBATT ML V FGD CPS Batteries | 51806.64 | 251088.99 | 302895.63
| MLWVPFGDN ML V FGD Other Non Outage PPB | 292401.97 | 1637819.04 | 1930221.01 | -19056.7966 | -154660.5834 | -173717.38
| MLWVPHEAT ML V FGD CPS Heaters | 3195.83 | 16463.41 | 19659.24
| MLWVPPUMP ML V FGD CPS Pumps | 178353.49 | 1104119.67 | 1282473.16 | -22993.504 | -186609.996 | -209603.5
| MLWVPTRMT ML V FGD CPS Env Transmitters | 40738.01 | 246636.33 | 287374.34 | -3447.7536 | -27981.1764 | -31428.93
| MLWVPVALV ML V FGD CPS Valve Replace | 76210.64 | 403652.36 | 479863 | 18775.413 | 152376.939 | 171152.352
| MLWVPGRBX ML V Gearbox Replacements | 28004.56 | 155538.16 | 183542.72
| MLWVPOPIP ML V Outage FGD Pipe Replace | 303694.51 | 1834304.27 | 2137998.78 | -76476.3787 | -620664.7213 | -697141.1
| MLWVPPIPE ML V Non Outage FGD Pipe Repl | 200326.35 | 1116229.88 | 1316556.23
| MLWVPDSIN ML V DSI Non Outage PPB Rplcmt | 9228.93 | 52013.42 | 61242.35
| MLWVPTANK ML V FGD CPS Tanks | 3406.25 | 22503.46 | 25909.71 | -1236.9575 | -10038.8625 | -11275.82
| MLWVPEJNT ML V FGD CPS Expansion Joints | 35546.15 | 246322.13 | 281868.28 | -9243.0697 | -75014.6303 | -84257.7
| MLWVIDFMR ML VP OUT ID FAN MOTOR REPL | 45903.75 | 294914.18 | 340817.93 | 20011.3177 | 162407.2573 | 182418.575
| MLWVPELGC ML V ELG CAP COMPONENT REPL | 3855.25 | 26102.84 | 29958.09 | 1174.5151 | 178594.0699 | 179768.585
| MLWVPBLML ML V Ball Mill Liner Replace | 47692.69 | 330363.37 | 378056.06 | -10849.6876 | -88053.5724 | -98903.26
| MLWVPABEJ ML V Absorber Exp Joints | 3280.33 | 21958.44 | 25238.77 | -293.0339 | -2378.1961 | -2671.23
| MLWVP21ID MLP V REBUILD #21 ID FAN | 53738.72 | 381460.86 | 435199.58 | -52734.6916 | -427982.6434 | -480717.335
| MLWVP11ID MLP V REBUILD #11 ID FAN | 42757.89 | 315518.95 | 358276.84 | -39326.7254 | -319166.6696 | -358493.395
| MLWVPHBSH ML V ID Fan Hub Shell Rplc | 22294.12 | 161802.68 | 184096.8 | -20195.419 | -163901.381 | -184096.8
| MLWVP22ID MLP V REBUILD #22 ID FAN |  |  |  | 48905.3366 | 396904.4774 | 445809.814
| MLWVPBMIL ML V Ball Mill Inlt Liner Repl |  |  |  | 17825.7136 | 144669.3964 | 162495.11
| MLWVPOXAB ML V Oxidation Air Blowers |  |  |  | 3954.2778 | 32092.0102 | 36046.288
Financial |  |  |  |  | 174621.5331 | 1417188.2489 | 1591809.782
Fly Ash Disposal System | MLWSPDFAF ML S Dry Fly Ash Fltr Sep Bags | 5910.96 | 32084.61 | 37995.57 | 9666.0334 | 78447.3066 | 88113.34
| MLWSPBLWR ML S Blowers & Fans Rplc |  |  |  | 7963.4695 | 64629.6895 | 72593.159
Fly Ash Landfill | MLWHAULRD Mitchell Haul Road Relocate | 956108.65 | 6261566.8 | 7217675.45 | -1328.4538 | -10781.4262 | -12109.88
Fossil/Steam-OthDirectUnitCost | MLWEPHVAC MLP E HVAC Unit Replacements | 81612.68 | 443710.67 | 525323.35 | 8704.696 | 70645.313 | 79350.009
| MLWNPBLDG ML N Capital Building Upgrades | 271380.01 | 1585483.03 | 1856863.04 | 5348.4377 | 43406.6913 | 48755.129
| MLWNPTOOL ML N Capital Tool Purchases | 262462.79 | 1471812.68 | 1734275.47 | 8651.3745 | 70212.5685 | 78863.943
| MLWNPWINT ML CAPITAL WINTERIZATION | 53357.44 | 345123.15 | 398480.59
| MLWEP2BAT ML E U2 Station Battery Rep | 19381.79 | 133361.51 | 152743.3 | 17470.3307 | 141785.1903 | 159255.521
| MLWMPHSTF ML M HS TUNNEL FIRE CAPITAL | 31547.99 | 219776.35 | 251324.34 | -15822.6365 | -128412.8835 | -144235.52
| INCCAPINV Incremental Capital Investment |  |  |  | 62601.7671 | 508061.5609 | 570663.328
| MLWNPLABR ML N Capital Labor Budgeting |  |  |  | 50636.2548 | 410952.2122 | 461588.467
Fuel | MLWMPOCOM ML M Out Conv Component Repl | 36532.16 | 233085.77 | 269617.93
| MLWMPD10T ML M Rebuild D10T Caught Fire |  |  |  | 85501.2234 | 693908.2876 | 779409.511
Fuel Systems Group | MLWMPBELT ML M Conveyor Belt Rplcmts | 227949.77 | 1249790.99 | 1477740.76 | 43803.2995 | 355497.5165 | 399300.816
| MLWMPCHUT ML M Chute Replacements | 145792.35 | 743324.86 | 889117.21 | 37611.7005 | 305247.9215 | 342859.622
| MLWMPHEAT ML M Heat Trace Instl/Rplc | 33350.35 | 174762.59 | 208112.94 | -1486.6105 | -12064.9895 | -13551.6
| MLWMPPUMP ML M CY Pump Replace Cap >10HP | 43746.86 | 258123.8 | 301870.66 | -973.6768 | -7902.1372 | -8875.814
| MLWSPPULV ML S Pulverizer Rebuilds | 400754.34 | 2199513.96 | 2600268.3 | 76128.5399 | 617841.7421 | 693970.282
| MLWMPCTRL ML M Control Upgrades | 8565.14 | 54063.33 | 62628.47 | -24.8141 | -201.3859 | -226.2
| MLWMPVALV ML M CY Valve Replacements | 18170.93 | 100176.33 | 118347.26
| MLWMPOTHR ML M Other Non-Outage PPB | 25346.98 | 169260.91 | 194607.89 | -14180.8356 | -115088.4044 | -129269.24
| MLWMPHEVY ML M Heavy Equip Rebuild PPB | 4021.68 | 27189.36 | 31211.04 | 89245.8516 | 724298.8304 | 813544.682
| MLWMPGGBX ML M Gypsum GRBX Cap Spare |  |  |  | 20595.1948 | 167145.8702 | 187741.065
| MLWMPHSGB ML M HS Coal GRBX Cap Spare |  |  |  | 53944.8224 | 437803.7866 | 491748.609
| MLWMPLGBX ML M Limestone GRBX Cap Spare |  |  |  | 9553.8038 | 77536.4772 | 87090.281
| MLWSPOILL ML S Oil Lighter Replacements |  |  |  | 26860.0335 | 217989.8615 | 244849.895
| MLWSPPDMP ML S PULV DAMPER REPL (OUT) |  |  |  | 80412.8183 | 652611.9607 | 733024.779
Generator & Support Systems | MLWEP0DCS ML E U0 Ovation DCS Upgrade | 131688.78 | 634608.61 | 766297.39
| MLWEP1DCS ML E U1 Ovation DCS Upgrade | 115789.88 | 558172.61 | 673962.49
| MLWEP2DCS ML E U2 Ovation DCS Upgrade | 117579.01 | 566642.19 | 684221.2
| MLWEPCTRL ML E Control Upgds Rplcmts | 249953.7 | 1510451.66 | 1760405.36 | 80277.3327 | 651512.3913 | 731789.724
| MLWEPDGHR ML E Doghouse Rectifier | 29952.5 | 148194.63 | 178147.13
| MLWEPFTCL ML E Flash Tank Controls | 35928.48 | 216689.08 | 252617.56
| MLWEPMOTR ML E Motor Rewind/Rplc >10HP | 72313.31 | 445667.01 | 517980.32 | -1061.7451 | -8616.8789 | -9678.624
| MLWEPPUMP ML E Pump Replacements | 317225.78 | 1838777.67 | 2156003.45 | 22894.7128 | 185808.2302 | 208702.943
| MLWEPSERV ML E Server Replacements | 100960.84 | 501165.02 | 602125.86
| MLWEPSWGR ML E Switchgear Breaker Rplcmt | 118899.54 | 628220.15 | 747119.69
| MLWEPTRMT ML E Transmitter Replacements | 46009.79 | 299324.7 | 345334.49 | -9719.7879 | -78883.5661 | -88603.354
| MLWEPCABL ML E Cable Replacements | 15283.51 | 87146.59 | 102430.1 | 4610.0015 | 37413.7135 | 42023.715
| MLWMPCOMP ML M CY Conv Component Repl | 68541.51 | 443096.7 | 511638.21 | 6178.3123 | 50141.7637 | 56320.076
| ML1XTRPTP ML1 XTR PPT Fail 12-19-23 PPB | 1119.68 | 6513.91 | 7633.59
| MLWEPTFRM ML E Transformers | 82699.93 | 551566.82 | 634266.75 | -11314.7674 | -91828.0526 | -103142.82
| MLWMPMOTR ML M Motor Rewind/Rplc >10HP | 10767.32 | 75243.58 | 86010.9 | -2099.4937 | -17039.0083 | -19138.502
| MLWEPAIRD ML E Air Dryer Install Replace | 15615.64 | 108715.33 | 124330.97 | -5067.9612 | -41130.4088 | -46198.37
| MLWMPROTO ML M Roto Booster Fan Replace | 60073.02 | 418431.07 | 478504.09 | 12652.1451 | 102681.9029 | 115334.048
| MLWSPSBSR MLP STACK BREACH CASING REPL | 47095.69 | 345351.56 | 392447.25 | -9414.0415 | -76402.1985 | -85816.24
| MLWEPCPLC ML E Critical PLC Replacements |  |  |  | 6043.5071 | 49047.7149 | 55091.222
| MLWEPXPPT ML E Exciter PPT Xfrmr Repl |  |  |  | 10349.6879 | 83995.6891 | 94345.377
| MLWMPBUBC ML M Barge Unldr Bckt Chn Repl |  |  |  | 150271.3729 | 1219567.9421 | 1369839.315
| MLWMPGRBX ML M Gearbox Rebuild PPB |  |  |  | 4119.0451 | 33429.2239 | 37548.269
Industrial Safety | MLWEPDFPM ML E Diesel Fire Pump Replace | 125295.57 | 745675.22 | 870970.79
| MLWEPLGHT ML E Lighting Replacements | 68705.53 | 358151.33 | 426856.86 | 20273.3156 | 164533.5724 | 184806.888
| MLWMPFIRE ML M Fire Protection Replace |  |  |  | 29062.0892 | 235861.2398 | 264923.329
| MLWNPFIRE ML N Fire Systems Capital Repl |  |  |  | 25860.4461 | 209877.4399 | 235737.886
Main Generator System | MLWEP1GGB ML E U1 Gen Gas Baffle Purch | 124757.7 | 887180.03 | 1011937.73
| MLWEP1GNI ML E U1 Generator Field Out In | 110307.74 | 812795.34 | 923103.08 | 58261.1231 | 472833.8919 | 531095.015
Main Turbine System | MLWEP2LAI ML E U2 LPA Turb Insp | 266203.86 | 1303903.74 | 1570107.6
| MLWEP2LBI ML E U2 LPB Turb Insp | 218887.75 | 1070461.48 | 1289349.23
| MLWEPMTRL ML E Main Trb Redundnt LVDT | 31331.34 | 163467.54 | 194798.88
| MLWES1BTI ML1 E BFPT INSPECTION | 42015.17 | 304125.83 | 346141 | -3536.229 | -28699.222 | -32235.451
| MLWEC1VHL ML E U1 VHP/HP&LPA Turbn Insp | 582966.7 | 3273003.66 | 3855970.36
| MLWEP2LA1 ML2 E LPA L1 Rotor Repr at CMS | 86748.59 | 581104.79 | 667853.38 | -341.8768 | -2774.5932 | -3116.47
| MLWEP2LB0 ML2 E LPB L0 Rotor Repr at CMS | 271139.45 | 1816288.55 | 2087428 | -1068.5647 | -8672.2253 | -9740.79
| MLWEP2LA0 ML2 E LPA L0 Rotor Repr at CMS | 271139.45 | 1816288.55 | 2087428 | -1068.5647 | -8672.2253 | -9740.79
| MLWEP2LB1 ML2 E LPB L1 Rotor Repr at CMS | 86748.59 | 581104.79 | 667853.38 | -341.8768 | -2774.5932 | -3116.47
| MLWES2BTI ML2 E BFPT INSPECTION |  |  |  | 34920.5609 | 283407.2501 | 318327.811
Other |  |  |  |  | -14.9806 | -121.5794 | -136.56
Other/Overheads |  |  |  |  | -0.0009873 | -0.0080127 | -0.009
Precipitator | MLWEPPTPF ML E Precip Trnsfrmr Pwr Feed | 7617.97 | 38551.07 | 46169.04
| MLWPC2ESP ML PCC U2 ESP Upgrades | 558790.27 | 3682090.97 | 4240881.24
| MLWSPPHCH ML S Precip Hopr Case/Htr Rplc | 889.4 | 5812.99 | 6702.39
SCR | MLWPC1CL4 ML PCC U1 SCR Catalyst Layer 4 | 3.7022e-10 | 5.5024e-11 | 4.2525e-10
| MLWVC2CL4 ML V U2 Catalyst Layer 4 Rplc | 213011.96 | 1040464.52 | 1253476.48
| MLWVC1CL1 Mitchell U1 SCR Catalyst L1 | 322198.41 | 2257007.57 | 2579205.98 | 106153.6685 | 861518.7885 | 967672.457
| MLWVPSCRM ML V SCR GAS MNTR SYSTEM REPL |  |  |  | 32896.2534 | 266978.4356 | 299874.689
Security_Audit_Risk | MLWNPSECU ML N Security Projects (Cap) | 14823.01 | 81478.05 | 96301.06
Stm, Condensate, FeedwtrSysGrp | MLWEPBFPB ML E BFP Rebuild Removed (Cap) | 144181 | 418062.79 | 562243.79 | -519.2529 | -4214.1371 | -4733.39
| MLWEPBFPE ML E BFP Rotating Element Rplc | 10026.75 | 49087.55 | 59114.3
Telecommunications | ITCB413W0 KENTUCKY POWER - GEN | 31620.02 | 161845.92 | 193465.94 | -93.2121 | -756.4879 | -849.7
Turbine & Support Systems | MLWEPTURB ML E Trb Brg, Rtr, Shaft Rbld | 22337.81 | 165226.28 | 187564.09 | -20575.7807 | -166988.3093 | -187564.09
Grand Total |  | 20415084.17 | 118369219.76 | 138784303.93 | 3682259.8905 | 26474623.5745 | 30156883.465

## Removal
|  | Actuals Spend thought April 2025 |  |  | Forecast Additional Spend through December 2025
Category | Project | Kentucky Power | Wheeling Power | Total Actual | Kentucky Power | Wheeling Power | Total Forecasted
Ash Handling Facilities | MLWMPPOND ML M N CY Pond Trtmnt Facility |  |  |  | 70000.02 | 70000.02 | 140000.04
Ash, Wastewater CCR | MLWSPCCHN ML S Collection Cnv Chain Repl | 22839.7 | 22839.68 | 45679.38 | 98435.31 | 98435.31 | 196870.62
Ash, Wastewtr Systems Group | MLWSPASHL ML S Ash Line Remove Replace | 29293.94 | 29293.82 | 58587.76 | -1210.03 | -1210.03 | -2420.06
BlrDrft/CombustnAir-FGD Assoc | MLWVPIDEJ ML V ID Fan Expansion Joints | 1728.5 | 1728.49 | 3456.99 | 6000 | 6000 | 12000
| MLWVPIDHY ML V ID Fan Hyd Cyl Rplc | 24943.13 | 24943.1 | 49886.23 | -24943.115 | -24943.115 | -49886.23
Boiler & Auxiliaries | MLWSPBRNE ML S Coal Burner Exp Joint Rpl | 402.84 | 402.83 | 805.67
| MLWSPBRNN ML S Burner Nozzle Rplcmt | 367640.42 | 367639.77 | 735280.19 | -44122.755 | -44122.755 | -88245.51
| MLWSPSOOT ML S Sootblower Replace Remove | 107983.32 | 107982.79 | 215966.11 | -13825.045 | -13825.045 | -27650.09
| MLWSPVALV ML S Blr Brnr Steam Valve Repl | 18883.5 | 18883.03 | 37766.53 | -8607.785 | -8607.785 | -17215.57
| MLWNPINSL ML N Insulation & Lagging Rplc | 4843.22 | 4843.21 | 9686.43
| MLWSPSOTO ML S SOOTBLOWER REMOVAL | 178114.15 | 178113.97 | 356228.12
| MLWSPDUCT ML S Duct Lag Insul Replace | 6272.97 | 6272.95 | 12545.92
| MLWSPNPPB ML S Other Non Outage PPB | 59946.01 | 59945.68 | 119891.69
| MLW2CGRPL ML U2 Clinker Grinder Replace |  |  |  | 75000 | 75000 | 150000
| MLW1CGRPL ML U1 Clinker Grinder Replace | 256685.4 | 256685.26 | 513370.66 | -181685.33 | -181685.33 | -363370.66
| MLWOPSOOT ML O Sootblower (Stm Outg) | 1949.22 | 1949.22 | 3898.44
| MLWSPBECK ML S Brnr Rgstr Sleeve Drv Rpl |  |  |  | 9999.96 | 9999.96 | 19999.92
| MLWSPSJNT ML S Burner Line Slip Jnt Repl |  |  |  | 21000 | 21000 | 42000
Boiler Draft/Combustn Air Grp | MLWSPFANS ML S Fans Blowers etc | 4559.4 | 4559.33 | 9118.73
Boiler Make-up Water Sup Syst | MLWEPRESN ML E Resin Replacements | 17715.63 | 17715.52 | 35431.15
Boiler/Boiler Components | MLWOPNONP ML O Non-Process Outage PPB | 301474.65 | 301473.29 | 602947.94 | -1529.37 | -1529.37 | -3058.74
| MLWSC1AHB ML S U1 Air Heater Basket Rplc | 779380.93 | 779380.82 | 1558761.75
| MLWSC2AHB ML S U2 Air Heater Basket Rplc | 34616.25 | 34616.25 | 69232.5
| MLWEPSTRN ML E Strainer Replacements |  |  |  | 4999.995 | 4999.995 | 9999.99
| MLWSP1BLC ML1 S BLR CAMERA UPGRADE (OUT) |  |  |  | 15000 | 15000 | 30000
| MLWSP2BLC ML2 S BLR CAMERA UPGRADE (OUT) |  |  |  | 15000 | 15000 | 30000
Bottom Ash Disposal Sys CCR | MLWSPCCRC ML S CCR Critical Cap Replmnts |  |  |  | 7500 | 7500 | 15000
Building Facilities | MLWEPELVC ML E Elevator Controls Upgrade |  |  |  | 30000 | 30000 | 60000
Condenser & Auxiliaries | MLWEPVALV ML E Valve Replacements | 424170.24 | 424168.91 | 848339.15 | -84060.455 | -84060.455 | -168120.91
Cooling Twr, Misc Wtr, ChemGrp | MLWPC2CTC ML PCC U2 Cooling Tower Comp | 529832.89 | 529832.79 | 1059665.68
Cooling Water Facilities | MLWEPCWPM ML E Circ Water Pump Reb (Cap) | 94819.84 | 94819.31 | 189639.15 | -59227.99 | -59227.99 | -118455.98
CT/CC Group | MLWEC1CTF ML E U1 Cooling Tower Compnnts | 818544.9 | 818544.59 | 1637089.49
| MLWPCT1BP ML U1 Cooling Tower Canopy RPL | 76638.93 | 76638.92 | 153277.85
Environmental | MLWNPROAD ML N Road Paving and Capital |  | 0 | 0
| MLWSPEJNT ML S Expansion Joint Repl | 1099276.91 | 1099276.47 | 2198553.38 | 115200.9 | 115200.9 | 230401.8
| MLWMPDRNG ML M Drainage Projects (Cap) | 6807.9 | 6807.87 | 13615.77
| MLWVPMONS ML V Monitoring Systems | 430.99 | 430.96 | 861.95
| MLWVPCNTM ML V Containment Systems | 380.61 | 380.6 | 761.21
| MLWSPPEXP ML S Pulv Exp Joint Repl |  |  |  | 47547.995 | 47547.995 | 95095.99
| MLWVPMEMB ML V RO Membrane Replacements |  |  |  | 750 | 750 | 1500
FGD (Scrubber) Group | MLWMPECRN ML M ECrane Capital Work | -7735.79 | -7735.79 | -15471.58
| MLWOPFGDP ML O FGD Process Outage PPB | 376755.3 | 376754.62 | 753509.92
| MLWPC0LIM ML PCC U0 Lime Conversion | 348315.34 | 348315.12 | 696630.46
| MLWVPAIRC ML V FGD Air Compressor Rplc | 2140.59 | 2140.58 | 4281.17
| MLWVPBATT ML V FGD CPS Batteries | 26585.99 | 26585.67 | 53171.66
| MLWVPFGDN ML V FGD Other Non Outage PPB | 923279.74 | 923278.77 | 1846558.51 | -3090.92 | -3090.92 | -6181.84
| MLWVPHEAT ML V FGD CPS Heaters | -2094.11 | -2094.11 | -4188.22
| MLWVPPUMP ML V FGD CPS Pumps | 55317.14 | 55315.89 | 110633.03 | -29049.435 | -29049.435 | -58098.87
| MLWVPTRMT ML V FGD CPS Env Transmitters | 4916.57 | 4915.96 | 9832.53 | -1073.085 | -1073.085 | -2146.17
| MLWVPVALV ML V FGD CPS Valve Replace | 108512.93 | 108512.35 | 217025.28 | 14961.625 | 14961.625 | 29923.25
| MLWVPGRBX ML V Gearbox Replacements | 5754.74 | 5754.68 | 11509.42
| MLWSPLIME ML S Lime Injection Equipment | 50084.75 | 50084.68 | 100169.43 | -5203.54 | -5203.54 | -10407.08
| MLWVPOPIP ML V Outage FGD Pipe Replace | 365803 | 365802.75 | 731605.75 | -89766.49 | -89766.49 | -179532.98
| MLWVPPIPE ML V Non Outage FGD Pipe Repl | 277879.21 | 277878.85 | 555758.06
| MLWVPDSIN ML V DSI Non Outage PPB Rplcmt | 602.09 | 601.99 | 1204.08
| MLWVPTANK ML V FGD CPS Tanks | 6455.72 | 6455.67 | 12911.39 | -1557.365 | -1557.365 | -3114.73
| MLWVPEJNT ML V FGD CPS Expansion Joints | 45005.79 | 45005.71 | 90011.5 | -14581.485 | -14581.485 | -29162.97
| MLWVIDFMR ML VP OUT ID FAN MOTOR REPL | 34644.2 | 34644.08 | 69288.28 | 350000 | 350000 | 700000
| MLWVPELGC ML V ELG CAP COMPONENT REPL |  |  |  | 0 | 15000 | 15000
| MLWVPBLML ML V Ball Mill Liner Replace | 27795.84 | 27795.82 | 55591.66 | -27795.83 | -27795.83 | -55591.66
| MLWVP21ID MLP V REBUILD #21 ID FAN | 124602.33 | 124602.11 | 249204.44 | -125610.22 | -125610.22 | -251220.44
| MLWVP11ID MLP V REBUILD #11 ID FAN | 89036.48 | 89036.26 | 178072.74 | -89036.37 | -89036.37 | -178072.74
| MLWVP22ID MLP V REBUILD #22 ID FAN |  |  |  | 75000 | 75000 | 150000
| MLWVPBMIL ML V Ball Mill Inlt Liner Repl |  |  |  | 33999.99 | 33999.99 | 67999.98
| MLWVPOXAB ML V Oxidation Air Blowers |  |  |  | 5599.98 | 5599.98 | 11199.96
Fly Ash Disposal System | MLWSPDFAF ML S Dry Fly Ash Fltr Sep Bags | 2901.78 | 2901.51 | 5803.29 | 7200 | 7200 | 14400
| MLWSPBLWR ML S Blowers & Fans Rplc |  |  |  | 2500.02 | 2500.02 | 5000.04
Fossil/Steam-OthDirectUnitCost | MLWEPHVAC MLP E HVAC Unit Replacements | 42941.61 | 42941.48 | 85883.09 | 10000.02 | 10000.02 | 20000.04
| MLWNPBLDG ML N Capital Building Upgrades | -7147.46 | -7147.77 | -14295.23 | 4393.815 | 4393.815 | 8787.63
| MLWNPTOOL ML N Capital Tool Purchases | -85756.37 | -85756.49 | -171512.86 | -218.655 | -218.655 | -437.31
| MLWNPWINT ML CAPITAL WINTERIZATION | 6042.48 | 6042.41 | 12084.89 | -1246.57 | -1246.57 | -2493.14
| MLWEP2BAT ML E U2 Station Battery Rep |  |  |  | 35000 | 35000 | 70000
| MLWMPHSTF ML M HS TUNNEL FIRE CAPITAL | 16244.55 | 16244.52 | 32489.07 | -16244.535 | -16244.535 | -32489.07
| MLWEPBLWR ML E Blower Vent Fan Repl |  | 0 | 0
| INCCAPINV Incremental Capital Investment |  |  |  | 0 | 0 | 0
| MLWNPLABR ML N Capital Labor Budgeting |  |  |  | 164863.682 | 164863.682 | 329727.364
Fuel | MLWMPD10T ML M Rebuild D10T Caught Fire |  |  |  | 142500 | 142500 | 285000
Fuel Systems Group | MLWMPBELT ML M Conveyor Belt Rplcmts | 63392.23 | 63391.85 | 126784.08 | 10958.75 | 10958.75 | 21917.5
| MLWMPCHUT ML M Chute Replacements | 127317.26 | 127317.18 | 254634.44 | 30000 | 30000 | 60000
| MLWMPHEAT ML M Heat Trace Instl/Rplc | 2488.09 | 2488.1 | 4976.19 | -2085.425 | -2085.425 | -4170.85
| MLWMPPUMP ML M CY Pump Replace Cap >10HP | 8765.95 | 8765.57 | 17531.52 | 2842.085 | 2842.085 | 5684.17
| MLWSPPULV ML S Pulverizer Rebuilds | 252389.27 | 252388.38 | 504777.65 | 89333.435 | 89333.435 | 178666.87
| MLWMPCTRL ML M Control Upgrades | 9561.91 | 9561.79 | 19123.7 | -3370.54 | -3370.54 | -6741.08
| MLWMPVALV ML M CY Valve Replacements | 5094.59 | 5094.49 | 10189.08
| MLWMPREMV ML M Misc CY Removal Prj | 10686.92 | 10686.83 | 21373.75 | -1009.14 | -1009.14 | -2018.28
| MLWMPOTHR ML M Other Non-Outage PPB | 2542.01 | 2541.97 | 5083.98 | -1370.005 | -1370.005 | -2740.01
| MLWSPOILL ML S Oil Lighter Replacements |  |  |  | 24999.995 | 24999.995 | 49999.99
| MLWSPPDMP ML S PULV DAMPER REPL (OUT) |  |  |  | 100000.005 | 100000.005 | 200000.01
Generator & Support Systems | MLWEP0DCS ML E U0 Ovation DCS Upgrade | 727.6 | 727.59 | 1455.19
| MLWEPCTRL ML E Control Upgds Rplcmts | 53750.59 | 53749.54 | 107500.13 | 85962.25 | 85962.25 | 171924.5
| MLWEPDGHR ML E Doghouse Rectifier | 6628.64 | 6628.63 | 13257.27
| MLWEPFTCL ML E Flash Tank Controls | 4476.62 | 4476.53 | 8953.15
| MLWEPMOTR ML E Motor Rewind/Rplc >10HP | -20156.59 | -20158.08 | -40314.67 | 27697.16 | 27697.16 | 55394.32
| MLWEPPUMP ML E Pump Replacements | 114789.47 | 114788 | 229577.47 | -6805.935 | -6805.935 | -13611.87
| MLWEPSWGR ML E Switchgear Breaker Rplcmt | 27164.58 | 27164.34 | 54328.92
| MLWEPTRMT ML E Transmitter Replacements | 14473.87 | 14472.66 | 28946.53 | 1930.255 | 1930.255 | 3860.51
| MLWEPCABL ML E Cable Replacements | 5411.07 | 5411.06 | 10822.13 | 12000 | 12000 | 24000
| MLWMPCOMP ML M CY Conv Component Repl | 60685.54 | 60685.2 | 121370.74 | -15274.645 | -15274.645 | -30549.29
| ML1XTRPTP ML1 XTR PPT Fail 12-19-23 PPB | 433.93 | 433.86 | 867.79
| MLWEPTFRM ML E Transformers | 8844.98 | 8844.95 | 17689.93 | -8844.965 | -8844.965 | -17689.93
| MLWMPMOTR ML M Motor Rewind/Rplc >10HP | 8221.34 | 8221.32 | 16442.66
| MLWEPAIRD ML E Air Dryer Install Replace | 2602.35 | 2602.35 | 5204.7 | -2602.35 | -2602.35 | -5204.7
| MLWMPROTO ML M Roto Booster Fan Replace | 101101.04 | 101100.88 | 202201.92 | -14251.995 | -14251.995 | -28503.99
| MLWSPSBSR MLP STACK BREACH CASING REPL | 13217.24 | 13217.22 | 26434.46 | -717.22 | -717.22 | -1434.44
| MLWEPCPLC ML E Critical PLC Replacements |  |  |  | 2499.995 | 2499.995 | 4999.99
| MLWEPXPPT ML E Exciter PPT Xfrmr Repl |  |  |  | 10000.005 | 10000.005 | 20000.01
| MLWMPBUBC ML M Barge Unldr Bckt Chn Repl |  |  |  | 177500 | 177500 | 355000
| MLWMPGRBX ML M Gearbox Rebuild PPB |  |  |  | 5000 | 5000 | 10000
Industrial Safety | MLWEPDFPM ML E Diesel Fire Pump Replace | 42193.81 | 42193.23 | 84387.04 | -7546.315 | -7546.315 | -15092.63
| MLWEPLGHT ML E Lighting Replacements | 515.19 | 515.19 | 1030.38 | 5500.02 | 5500.02 | 11000.04
| MLWNPFIRE ML N Fire Systems Capital Repl |  |  |  | 37500 | 37500 | 75000
Main Generator System | MLWEP1GGB ML E U1 Gen Gas Baffle Purch | 25927.67 | 25927.64 | 51855.31 | -25927.655 | -25927.655 | -51855.31
| MLWEP1GNI ML E U1 Generator Field Out In | 356269.24 | 356268.81 | 712538.05 | -281269.025 | -281269.025 | -562538.05
Main Turbine System | MLWEP2LAI ML E U2 LPA Turb Insp | 254961.83 | 254961.39 | 509923.22
| MLWEP2LBI ML E U2 LPB Turb Insp | 326825.96 | 326825.26 | 653651.22
| MLWEPMTRL ML E Main Trb Redundnt LVDT | 2702.85 | 2702.62 | 5405.47
| MLWES1BTI ML1 E BFPT INSPECTION | 101380.72 | 101380.63 | 202761.35 | -45806.22 | -45806.22 | -91612.44
| MLWEC1VHL ML E U1 VHP/HP&LPA Turbn Insp | 773231.85 | 773230.98 | 1546462.83
| MLWES2BTI ML2 E BFPT INSPECTION |  |  |  | 50000 | 50000 | 100000
Precipitator | MLWEPPTPF ML E Precip Trnsfrmr Pwr Feed | 5790.04 | 5790.01 | 11580.05
| MLWPC2ESP ML PCC U2 ESP Upgrades | 593085.43 | 593085.34 | 1186170.77
| MLWSPPHCH ML S Precip Hopr Case/Htr Rplc | 1244.07 | 1244.07 | 2488.14
SCR | MLWPC1CL4 ML PCC U1 SCR Catalyst Layer 4 | 6136.8 | 6136.78 | 12273.58
| MLWVC2CL4 ML V U2 Catalyst Layer 4 Rplc | 12353.04 | 12353.01 | 24706.05
| MLWVC1CL1 Mitchell U1 SCR Catalyst L1 | 408580.56 | 408580.45 | 817161.01 | -82080.505 | -82080.505 | -164161.01
| MLWVPSCRM ML V SCR GAS MNTR SYSTEM REPL |  |  |  | 12500 | 12500 | 25000
Stm, Condensate, FeedwtrSysGrp | MLWEPBFPB ML E BFP Rebuild Removed (Cap) | -84037.04 | -84037.33 | -168074.37
| MLWEPBFPE ML E BFP Rotating Element Rplc | 13223.1 | 13222.96 | 26446.06
Turbine & Support Systems | MLWEPTURB ML E Trb Brg, Rtr, Shaft Rbld | 1760 | 1760 | 3520 | -1760 | -1760 | -3520
Grand Total |  | 11835816.45 | 11835790 | 23671606.45 | 724268.952 | 739268.952 | 1463537.904