## Cost Report
AM07 Phase 1
Actual Spend
Project Cost Breakdown
Revision: | 2025-09-23
|  | Capital Improvement and Retirement |  |  | Retirement
24'' Line AM07
PH 1 /25,153
WBS 1 | Description |  | Station | Pipelay 1 | Pipe Abandonment
NGENGNC | Engineering | 2282479 | 11751 | 2270728
NGLANDC | Land Acquisition & Support | 5226607 |  | 5226607
NGMATEC | Materials/Equipment | 7055920 | 4093283 | 2962637
NGCONPC | Construction Serv - Pipeline | 15600215 | 1229258 | 13797420 | 573537
NGCONFC | Construction Serv - Facility | 8147144 | 8147144
NGFITSC | Field Inspections | 2989439 | 1489603 | 1499836
NGMPGL | PNG Labor | 1285267 | 585780 | 699487
NGMOTH | Other Direct Costs | 17104 | 17104
Subtotal Direct Cost |  | 42604175 | 15573923 | 26456715 | 573537
Project Contingency
Project Escalation
Total Contingency & Escalation |  | 0 |  | 0 | 0
Total Direct Cost |  | 42604175 |  | 26456715 | 573537
NGMPGL | AFUDC Debt | 4569382 | 712041 | 3857341
NGMOVH | Overhead and Allocations | 2841019 | 2122392 | 718627
Total PNG Overhead Cost |  | 7410401 | 2834433 | 4575968 | 0
Project Total |  | 50014576 | 18408356 | 31032683 | 573537
Notes:

## Actuals by WBS - AM07 Phase 1
Exported from EcoSys on 09/24/2025 09:45:43
Actuals Summary
Project: G7AM07ILI Posted to CPR Line AM07 Pipeline Replacement Phase 1 Project Period: 202508
| Path ID | Name | PTD Production Cost
| G7AM07ILI | (Posted to CPR) Line AM07 - Pipeline Replacement - Phase 1 | 50014748.1
| G7AM07ILI.AW3074 | Line AM07 - Pipeline Replacement - Land | 5584894.26
| G7AM07ILI.AW3074.NGENGNC | 010 - ENGINEERING | 29403.61
| G7AM07ILI.AW3074.NGENGNC.G630 | G630 - Field Environmental Costs | 3167.82
| G7AM07ILI.AW3074.NGENGNC.G663 | G663 - Transmission – Temporary Land | 23490
| G7AM07ILI.AW3074.NGENGNC.G801 | G801 - Pre-Design Activities | 0
| G7AM07ILI.AW3074.NGENGNC.G802 | G802 - Route Development | 0
| G7AM07ILI.AW3074.NGENGNC.G803 | G803 - Project Management | 0
| G7AM07ILI.AW3074.NGENGNC.G804 | G804 - Records Research | 0
| G7AM07ILI.AW3074.NGENGNC.G805 | G805 - Estimate and Scoping | 0
| G7AM07ILI.AW3074.NGENGNC.G806 | G806 - Land Survey | 0
| G7AM07ILI.AW3074.NGENGNC.G807 | G807 - Land Acquisition Support (Engineering) | 0
| G7AM07ILI.AW3074.NGENGNC.G808 | G808 - Other Permitting | 0
| G7AM07ILI.AW3074.NGENGNC.G809 | G809 - Geotechnical Services | 0
| G7AM07ILI.AW3074.NGENGNC.G810 | G810 - Design - Pipeline | 0
| G7AM07ILI.AW3074.NGENGNC.G811 | G811 - Design - Facility | 0
| G7AM07ILI.AW3074.NGENGNC.G812 | G812 - Cathodic Protection | 0
| G7AM07ILI.AW3074.NGENGNC.G813 | G813 - Bid Package Development | 0
| G7AM07ILI.AW3074.NGENGNC.G814 | G814 - Construction Support (Engineering) | 1305.26
| G7AM07ILI.AW3074.NGENGNC.G815 | G815 - As-Built Survey | 0
| G7AM07ILI.AW3074.NGENGNC.G816 | G816 - Project Close-Out | 0
| G7AM07ILI.AW3074.NGENGNC.G900 | G900 - Engineering - White | 0
| G7AM07ILI.AW3074.NGENGNC.ENGNA | Not Assigned - Engineering | 0
| G7AM07ILI.AW3074.NGLANDC | 020 - LAND SERVICES | 5160410.88
| G7AM07ILI.AW3074.NGLANDC.G301 | G301 - Contract Labor - Legal | 392116.9
| G7AM07ILI.AW3074.NGLANDC.G656 | G656 - Construction Support - Land | 109792.12
| G7AM07ILI.AW3074.NGLANDC.G661 | G661 - Transmission - Land Purchase | -312076
| G7AM07ILI.AW3074.NGLANDC.G662 | G662 - Transmission - Land Rights | 115701
| G7AM07ILI.AW3074.NGLANDC.G901 | G901 - Land Services - White | 0
| G7AM07ILI.AW3074.NGLANDC.LANNA | Not Assigned - Land Services | 4800698
| G7AM07ILI.AW3074.NGCONPC | 030 - CONSTRUCTION SERVICES – PIPELINE | 0
| G7AM07ILI.AW3074.NGCONPC.G631 | G631 - Field Environmental and Erosion Control | 0
| G7AM07ILI.AW3074.NGCONPC.G820 | G820 - Mob/Demob | 0
| G7AM07ILI.AW3074.NGCONPC.G821 | G821 - Clearing and Grubbing | 0
| G7AM07ILI.AW3074.NGCONPC.G822 | G822 - Rock Excavation | 0
| G7AM07ILI.AW3074.NGCONPC.G825 | G825 - Conventional Bore - Dirt | 0
| G7AM07ILI.AW3074.NGCONPC.G826 | G826 - Conventional Bore - Rock | 0
| G7AM07ILI.AW3074.NGCONPC.G827 | G827 - Directional Drill – Dirt | 0
| G7AM07ILI.AW3074.NGCONPC.G828 | G828 - Directional Drill – Rock | 0
| G7AM07ILI.AW3074.NGCONPC.G829 | G829 - Conventional Upland Lay | 0
| G7AM07ILI.AW3074.NGCONPC.G830 | G830 - Conventional Wetland Lay | 0
| G7AM07ILI.AW3074.NGCONPC.G831 | G831 - High Water Table | 0
| G7AM07ILI.AW3074.NGCONPC.G832 | G832 - Civil or General Conditions | 0
| G7AM07ILI.AW3074.NGCONPC.G833 | G833 - Hydro Test and Caliper Tool Run | 0
| G7AM07ILI.AW3074.NGCONPC.G834 | G834 - Commissioning | 0
| G7AM07ILI.AW3074.NGCONPC.G835 | G835 - Clean-up | 0
| G7AM07ILI.AW3074.NGCONPC.G836 | G836 - Stand-By - Pipeline | 0
| G7AM07ILI.AW3074.NGCONPC.G837 | G837 - AC/CP | 0
| G7AM07ILI.AW3074.NGCONPC.G902 | G902 - CS Pipeline - White | 0
| G7AM07ILI.AW3074.NGCONPC.CONPNA | Not Assigned - Construction Services - Pipeline | 0
| G7AM07ILI.AW3074.NGCONFC | 040 - CONSTRUCTION SERVICES – FACILITY | 27444.65
| G7AM07ILI.AW3074.NGCONFC.G632 | G632 - Field Environmental and Erosion Control | 0
| G7AM07ILI.AW3074.NGCONFC.G850 | G850 - Mob/Demob | 27444.65
| G7AM07ILI.AW3074.NGCONFC.G851 | G851 - Site Preparation | 0
| G7AM07ILI.AW3074.NGCONFC.G852 | G852 - Concrete, Paving and Gravel | 0
| G7AM07ILI.AW3074.NGCONFC.G853 | G853 - Building Erection | 0
| G7AM07ILI.AW3074.NGCONFC.G854 | G854 - Fabrication | 0
| G7AM07ILI.AW3074.NGCONFC.G855 | G855 - Installation | 0
| G7AM07ILI.AW3074.NGCONFC.G856 | G856 - Security, Fire Alarm, Instrumentation and Controls | 0
| G7AM07ILI.AW3074.NGCONFC.G857 | G857 - Fencing | 0
| G7AM07ILI.AW3074.NGCONFC.G858 | G858 - Tie-In | 0
| G7AM07ILI.AW3074.NGCONFC.G859 | G859 - Hydro Test | 0
| G7AM07ILI.AW3074.NGCONFC.G860 | G860 - AC/CP | 0
| G7AM07ILI.AW3074.NGCONFC.G861 | G861 - Commissioning | 0
| G7AM07ILI.AW3074.NGCONFC.G862 | G862 - Stand-By - Facility | 0
| G7AM07ILI.AW3074.NGCONFC.G903 | G903 - CS Facility - White | 0
| G7AM07ILI.AW3074.NGCONFC.CONFNA | Not Assigned - Construction Services - Facility | 0
| G7AM07ILI.AW3074.NGREMPC | 050 - CONSTRUCTION RETIREMENT | 0
| G7AM07ILI.AW3074.NGREMPC.G823 | G823 - Abandon in Place Pipe | 0
| G7AM07ILI.AW3074.NGREMPC.G824 | G824 - Removal of Pipe | 0
| G7AM07ILI.AW3074.NGREMPC.G863 | G863 - Station Retirement | 0
| G7AM07ILI.AW3074.NGREMPC.G904 | G904 - Construction Retirement - White | 0
| G7AM07ILI.AW3074.NGREMPC.CONRNA | Not Assigned - Construction Retirement | 0
| G7AM07ILI.AW3074.NGILIPC | 060 - INLINE INSPECTION PROGRAM | 0
| G7AM07ILI.AW3074.NGILIPC.G870 | G870 - Row Clearing | 0
| G7AM07ILI.AW3074.NGILIPC.G871 | G871 - Validation Digs | 0
| G7AM07ILI.AW3074.NGILIPC.G872 | G872 - Retrofits | 0
| G7AM07ILI.AW3074.NGILIPC.G873 | G873 - Anomalies | 0
| G7AM07ILI.AW3074.NGILIPC.G906 | G906 - Inline Inspection Program - White | 0
| G7AM07ILI.AW3074.NGILIPC.ILINA | Not Assigned - Inline Inspection Program | 0
| G7AM07ILI.AW3074.NGFITSC | 070 - FIELD INSPECTION AND TESTING | 17663.51
| G7AM07ILI.AW3074.NGFITSC.G880 | G880 - Construction Inspection | 0
| G7AM07ILI.AW3074.NGFITSC.G881 | G881 - Non-Destructive Testing | 0
| G7AM07ILI.AW3074.NGFITSC.G882 | G882 - Safety | 0
| G7AM07ILI.AW3074.NGFITSC.G883 | G883 - Environmental | 14859.14
| G7AM07ILI.AW3074.NGFITSC.G905 | G905 - Field Inspection and Testing - White | 0
| G7AM07ILI.AW3074.NGFITSC.FITNA | Not Assigned - Field Inspection and Testing | 0
| G7AM07ILI.AW3074.NGMATEC | 080 - MATERIALS AND EQUIPMENT | 11028.79
| G7AM07ILI.AW3074.NGMATEC.G201 | G201 - Inventory – Materials | 0
| G7AM07ILI.AW3074.NGMATEC.G202 | G202 - Non-Inventory Parts / Materials | 0
| G7AM07ILI.AW3074.NGMATEC.G204 | G204 - Materials – Contractors | 0
| G7AM07ILI.AW3074.NGMATEC.G205 | G205 - Materials – MRC | 11028.79
| G7AM07ILI.AW3074.NGMATEC.G907 | G907 - Material & Inspection - White | 0
| G7AM07ILI.AW3074.NGMATEC.MAT001 | MAT001 - Material Allocations | 0
| G7AM07ILI.AW3074.NGMATEC.MAT002 | MAT002 - Stores Loading | 0
| G7AM07ILI.AW3074.NGMATEC.MATNA | Not Assigned - Materials and Equipment | 0
| G7AM07ILI.AW3074.NGMPGL | 090 - DUKE LABOR | 27403.11
| G7AM07ILI.AW3074.NGMPGL.DL001 | DL001 - Labor | 10533.22
| G7AM07ILI.AW3074.NGMPGL.DL002 | DL002 - Labor Loader | 0
| G7AM07ILI.AW3074.NGMPGL.DL003 | DL003 - Overtime | 0
| G7AM07ILI.AW3074.NGMPGL.DL004 | DL004 - Overhead Labor - Allocation | 12585.89
| G7AM07ILI.AW3074.NGMPGL.G101 | G101 - Project Support Labor | 4284
| G7AM07ILI.AW3074.NGMPGL.DLNA | Not Assigned - Internal Labor | 0
| G7AM07ILI.AW3074.NGMOTH | 100 - OTHER | 2257.5
| G7AM07ILI.AW3074.NGMOTH.OTHNA | Not Assigned - Other | 0
| G7AM07ILI.AW3074.NGMOTH.OTH001 | OTH001 - Other | 2257.5
| G7AM07ILI.AW3074.NGMOVH | 110 - OVERHEAD | 129663.89
| G7AM07ILI.AW3074.NGMOVH.OVHNA | Not Assigned - Overhead | 0
| G7AM07ILI.AW3074.NGMOVH.OVH001 | OVH001 - Overhead | 129663.89
| G7AM07ILI.AW3074.NGMAFD | 120 - AFUDC | 179506.29
| G7AM07ILI.AW3074.NGMAFD.ACCTG | ACCTG - AFUDC | 170618.96
| G7AM07ILI.AW3074.NGMAFD.AFUDCNA | Not Assigned - AFUDC | 0
| G7AM07ILI.AW3074.NGCONT | 130 - CONTINGENCY | 0
| G7AM07ILI.AW3074.NGCONT.CONT001 | CONT001 - Contingency | 0
| G7AM07ILI.AW3074.NGEXCEP | 140 - EXCEPTION | 0
| G7AM07ILI.AW3074.NGEXCEP.EXCEP001 | EXCEP001 - Exception | 0
| G7AM07ILI.0233100 | Line AM07 - Pipeline Replacement - Pipe | 26106514.25
| G7AM07ILI.0233100.NGENGNC | 010 - ENGINEERING | 2241323.95
| G7AM07ILI.0233100.NGENGNC.G630 | G630 - Field Environmental Costs | 111458.02
| G7AM07ILI.0233100.NGENGNC.G663 | G663 - Transmission – Temporary Land | 0
| G7AM07ILI.0233100.NGENGNC.G801 | G801 - Pre-Design Activities | 5070
| G7AM07ILI.0233100.NGENGNC.G802 | G802 - Route Development | -1864
| G7AM07ILI.0233100.NGENGNC.G803 | G803 - Project Management | 26606.98
| G7AM07ILI.0233100.NGENGNC.G804 | G804 - Records Research | 0
| G7AM07ILI.0233100.NGENGNC.G805 | G805 - Estimate and Scoping | 0
| G7AM07ILI.0233100.NGENGNC.G806 | G806 - Land Survey | 142752.1
| G7AM07ILI.0233100.NGENGNC.G807 | G807 - Land Acquisition Support (Engineering) | 7111
| G7AM07ILI.0233100.NGENGNC.G808 | G808 - Other Permitting | 50116.5
| G7AM07ILI.0233100.NGENGNC.G809 | G809 - Geotechnical Services | 69387
| G7AM07ILI.0233100.NGENGNC.G810 | G810 - Design - Pipeline | 304769
| G7AM07ILI.0233100.NGENGNC.G811 | G811 - Design - Facility | 182064
| G7AM07ILI.0233100.NGENGNC.G812 | G812 - Cathodic Protection | 13297
| G7AM07ILI.0233100.NGENGNC.G813 | G813 - Bid Package Development | 28816
| G7AM07ILI.0233100.NGENGNC.G814 | G814 - Construction Support (Engineering) | 426856.74
| G7AM07ILI.0233100.NGENGNC.G815 | G815 - As-Built Survey | 800798.36
| G7AM07ILI.0233100.NGENGNC.G816 | G816 - Project Close-Out | 7921.25
| G7AM07ILI.0233100.NGENGNC.G900 | G900 - Engineering - White | 0
| G7AM07ILI.0233100.NGENGNC.ENGNA | Not Assigned - Engineering | 0
| G7AM07ILI.0233100.NGLANDC | 020 - LAND SERVICES | 66196.46
| G7AM07ILI.0233100.NGLANDC.G301 | G301 - Contract Labor - Legal | 0
| G7AM07ILI.0233100.NGLANDC.G656 | G656 - Construction Support - Land | 66196.46
| G7AM07ILI.0233100.NGLANDC.G661 | G661 - Transmission - Land Purchase | 0
| G7AM07ILI.0233100.NGLANDC.G662 | G662 - Transmission - Land Rights | 0
| G7AM07ILI.0233100.NGLANDC.G901 | G901 - Land Services - White | 0
| G7AM07ILI.0233100.NGLANDC.LANNA | Not Assigned - Land Services | 0
| G7AM07ILI.0233100.NGCONPC | 030 - CONSTRUCTION SERVICES – PIPELINE | 13889244.1
| G7AM07ILI.0233100.NGCONPC.G631 | G631 - Field Environmental and Erosion Control | 351279.33
| G7AM07ILI.0233100.NGCONPC.G820 | G820 - Mob/Demob | 615675.97
| G7AM07ILI.0233100.NGCONPC.G821 | G821 - Clearing and Grubbing | 517060.4
| G7AM07ILI.0233100.NGCONPC.G822 | G822 - Rock Excavation | 27273.95
| G7AM07ILI.0233100.NGCONPC.G825 | G825 - Conventional Bore - Dirt | 842073.55
| G7AM07ILI.0233100.NGCONPC.G826 | G826 - Conventional Bore - Rock | 0
| G7AM07ILI.0233100.NGCONPC.G827 | G827 - Directional Drill – Dirt | 1332080.64
| G7AM07ILI.0233100.NGCONPC.G828 | G828 - Directional Drill – Rock | 0
| G7AM07ILI.0233100.NGCONPC.G829 | G829 - Conventional Upland Lay | 7241111.86
| G7AM07ILI.0233100.NGCONPC.G830 | G830 - Conventional Wetland Lay | 0
| G7AM07ILI.0233100.NGCONPC.G831 | G831 - High Water Table | 16926.42
| G7AM07ILI.0233100.NGCONPC.G832 | G832 - Civil or General Conditions | 1823171.71
| G7AM07ILI.0233100.NGCONPC.G833 | G833 - Hydro Test and Caliper Tool Run | 883044.76
| G7AM07ILI.0233100.NGCONPC.G834 | G834 - Commissioning | 226553.81
| G7AM07ILI.0233100.NGCONPC.G835 | G835 - Clean-up | 0
| G7AM07ILI.0233100.NGCONPC.G836 | G836 - Stand-By - Pipeline | 0
| G7AM07ILI.0233100.NGCONPC.G837 | G837 - AC/CP | 12991.7
| G7AM07ILI.0233100.NGCONPC.G902 | G902 - CS Pipeline - White | 0
| G7AM07ILI.0233100.NGCONPC.CONPNA | Not Assigned - Construction Services - Pipeline | 0
| G7AM07ILI.0233100.NGCONFC | 040 - CONSTRUCTION SERVICES – FACILITY | 57730
| G7AM07ILI.0233100.NGCONFC.G632 | G632 - Field Environmental and Erosion Control | 0
| G7AM07ILI.0233100.NGCONFC.G850 | G850 - Mob/Demob | 0
| G7AM07ILI.0233100.NGCONFC.G851 | G851 - Site Preparation | 57730
| G7AM07ILI.0233100.NGCONFC.G852 | G852 - Concrete, Paving and Gravel | 0
| G7AM07ILI.0233100.NGCONFC.G853 | G853 - Building Erection | 0
| G7AM07ILI.0233100.NGCONFC.G854 | G854 - Fabrication | 0
| G7AM07ILI.0233100.NGCONFC.G855 | G855 - Installation | 0
| G7AM07ILI.0233100.NGCONFC.G856 | G856 - Security, Fire Alarm, Instrumentation and Controls | 0
| G7AM07ILI.0233100.NGCONFC.G857 | G857 - Fencing | 0
| G7AM07ILI.0233100.NGCONFC.G858 | G858 - Tie-In | 0
| G7AM07ILI.0233100.NGCONFC.G859 | G859 - Hydro Test | 0
| G7AM07ILI.0233100.NGCONFC.G860 | G860 - AC/CP | 0
| G7AM07ILI.0233100.NGCONFC.G861 | G861 - Commissioning | 0
| G7AM07ILI.0233100.NGCONFC.G862 | G862 - Stand-By - Facility | 0
| G7AM07ILI.0233100.NGCONFC.G903 | G903 - CS Facility - White | 0
| G7AM07ILI.0233100.NGCONFC.CONFNA | Not Assigned - Construction Services - Facility | 0
| G7AM07ILI.0233100.NGREMPC | 050 - CONSTRUCTION RETIREMENT | 573537.15
| G7AM07ILI.0233100.NGREMPC.G823 | G823 - Abandon in Place Pipe | 57838.64
| G7AM07ILI.0233100.NGREMPC.G824 | G824 - Removal of Pipe | 39305.32
| G7AM07ILI.0233100.NGREMPC.G863 | G863 - Station Retirement | 0
| G7AM07ILI.0233100.NGREMPC.G904 | G904 - Construction Retirement - White | 0
| G7AM07ILI.0233100.NGREMPC.CONRNA | Not Assigned - Construction Retirement | 476393.19
| G7AM07ILI.0233100.NGILIPC | 060 - INLINE INSPECTION PROGRAM | 0
| G7AM07ILI.0233100.NGILIPC.G870 | G870 - Row Clearing | 0
| G7AM07ILI.0233100.NGILIPC.G871 | G871 - Validation Digs | 0
| G7AM07ILI.0233100.NGILIPC.G872 | G872 - Retrofits | 0
| G7AM07ILI.0233100.NGILIPC.G873 | G873 - Anomalies | 0
| G7AM07ILI.0233100.NGILIPC.G906 | G906 - Inline Inspection Program - White | 0
| G7AM07ILI.0233100.NGILIPC.ILINA | Not Assigned - Inline Inspection Program | 0
| G7AM07ILI.0233100.NGFITSC | 070 - FIELD INSPECTION AND TESTING | 1482172.36
| G7AM07ILI.0233100.NGFITSC.G880 | G880 - Construction Inspection | 1112434.12
| G7AM07ILI.0233100.NGFITSC.G881 | G881 - Non-Destructive Testing | 369738.24
| G7AM07ILI.0233100.NGFITSC.G882 | G882 - Safety | 0
| G7AM07ILI.0233100.NGFITSC.G883 | G883 - Environmental | 0
| G7AM07ILI.0233100.NGFITSC.G905 | G905 - Field Inspection and Testing - White | 0
| G7AM07ILI.0233100.NGFITSC.FITNA | Not Assigned - Field Inspection and Testing | 0
| G7AM07ILI.0233100.NGMATEC | 080 - MATERIALS AND EQUIPMENT | 2951607.93
| G7AM07ILI.0233100.NGMATEC.G201 | G201 - Inventory – Materials | 78606.57
| G7AM07ILI.0233100.NGMATEC.G202 | G202 - Non-Inventory Parts / Materials | 2828143.22
| G7AM07ILI.0233100.NGMATEC.G204 | G204 - Materials – Contractors | 0
| G7AM07ILI.0233100.NGMATEC.G205 | G205 - Materials – MRC | -75626.04
| G7AM07ILI.0233100.NGMATEC.G907 | G907 - Material & Inspection - White | 0
| G7AM07ILI.0233100.NGMATEC.MAT001 | MAT001 - Material Allocations | -330.48
| G7AM07ILI.0233100.NGMATEC.MAT002 | MAT002 - Stores Loading | 3457.11
| G7AM07ILI.0233100.NGMATEC.MATNA | Not Assigned - Materials and Equipment | 117357.55
| G7AM07ILI.0233100.NGMPGL | 090 - DUKE LABOR | 672083.86
| G7AM07ILI.0233100.NGMPGL.DL001 | DL001 - Labor | 70229.61
| G7AM07ILI.0233100.NGMPGL.DL002 | DL002 - Labor Loader | 0
| G7AM07ILI.0233100.NGMPGL.DL003 | DL003 - Overtime | 0
| G7AM07ILI.0233100.NGMPGL.DL004 | DL004 - Overhead Labor - Allocation | 346027.28
| G7AM07ILI.0233100.NGMPGL.G101 | G101 - Project Support Labor | 252187.37
| G7AM07ILI.0233100.NGMPGL.DLNA | Not Assigned - Internal Labor | 3639.6
| G7AM07ILI.0233100.NGMOTH | 100 - OTHER | -94193.86
| G7AM07ILI.0233100.NGMOTH.OTHNA | Not Assigned - Other | 0
| G7AM07ILI.0233100.NGMOTH.OTH001 | OTH001 - Other | -94193.86
| G7AM07ILI.0233100.NGMOVH | 110 - OVERHEAD | 3727691.1
| G7AM07ILI.0233100.NGMOVH.OVHNA | Not Assigned - Overhead | 0
| G7AM07ILI.0233100.NGMOVH.OVH001 | OVH001 - Overhead | 3727691.1
| G7AM07ILI.0233100.NGMAFD | 120 - AFUDC | 539121.2
| G7AM07ILI.0233100.NGMAFD.ACCTG | ACCTG - AFUDC | 539121.2
| G7AM07ILI.0233100.NGMAFD.AFUDCNA | Not Assigned - AFUDC | 0
| G7AM07ILI.0233100.NGCONT | 130 - CONTINGENCY | 0
| G7AM07ILI.0233100.NGCONT.CONT001 | CONT001 - Contingency | 0
| G7AM07ILI.0233100.NGEXCEP | 140 - EXCEPTION | 0
| G7AM07ILI.0233100.NGEXCEP.EXCEP001 | EXCEP001 - Exception | 0
| G7AM07ILI.AW3138 | Line AM07 - Pipeline Replacement - Station | 18323339.59
| G7AM07ILI.AW3138.NGENGNC | 010 - ENGINEERING | 11751.22
| G7AM07ILI.AW3138.NGENGNC.G630 | G630 - Field Environmental Costs | 1802.5
| G7AM07ILI.AW3138.NGENGNC.G663 | G663 - Transmission – Temporary Land | 0
| G7AM07ILI.AW3138.NGENGNC.G801 | G801 - Pre-Design Activities | 0
| G7AM07ILI.AW3138.NGENGNC.G802 | G802 - Route Development | 6597.25
| G7AM07ILI.AW3138.NGENGNC.G803 | G803 - Project Management | 0
| G7AM07ILI.AW3138.NGENGNC.G804 | G804 - Records Research | 0
| G7AM07ILI.AW3138.NGENGNC.G805 | G805 - Estimate and Scoping | 0
| G7AM07ILI.AW3138.NGENGNC.G806 | G806 - Land Survey | 0
| G7AM07ILI.AW3138.NGENGNC.G807 | G807 - Land Acquisition Support (Engineering) | 0
| G7AM07ILI.AW3138.NGENGNC.G808 | G808 - Other Permitting | 0
| G7AM07ILI.AW3138.NGENGNC.G809 | G809 - Geotechnical Services | 0
| G7AM07ILI.AW3138.NGENGNC.G810 | G810 - Design - Pipeline | 0
| G7AM07ILI.AW3138.NGENGNC.G811 | G811 - Design - Facility | 1405.47
| G7AM07ILI.AW3138.NGENGNC.G812 | G812 - Cathodic Protection | 0
| G7AM07ILI.AW3138.NGENGNC.G813 | G813 - Bid Package Development | 0
| G7AM07ILI.AW3138.NGENGNC.G814 | G814 - Construction Support (Engineering) | 0
| G7AM07ILI.AW3138.NGENGNC.G815 | G815 - As-Built Survey | 0
| G7AM07ILI.AW3138.NGENGNC.G816 | G816 - Project Close-Out | 1946
| G7AM07ILI.AW3138.NGENGNC.G900 | G900 - Engineering - White | 0
| G7AM07ILI.AW3138.NGENGNC.ENGNA | Not Assigned - Engineering | 0
| G7AM07ILI.AW3138.NGLANDC | 020 - LAND SERVICES | 0
| G7AM07ILI.AW3138.NGLANDC.G301 | G301 - Contract Labor - Legal | 0
| G7AM07ILI.AW3138.NGLANDC.G656 | G656 - Construction Support - Land | 0
| G7AM07ILI.AW3138.NGLANDC.G661 | G661 - Transmission - Land Purchase | 0
| G7AM07ILI.AW3138.NGLANDC.G662 | G662 - Transmission - Land Rights | 0
| G7AM07ILI.AW3138.NGLANDC.G901 | G901 - Land Services - White | 0
| G7AM07ILI.AW3138.NGLANDC.LANNA | Not Assigned - Land Services | 0
| G7AM07ILI.AW3138.NGCONPC | 030 - CONSTRUCTION SERVICES – PIPELINE | 1229257.95
| G7AM07ILI.AW3138.NGCONPC.G631 | G631 - Field Environmental and Erosion Control | 0
| G7AM07ILI.AW3138.NGCONPC.G820 | G820 - Mob/Demob | 0
| G7AM07ILI.AW3138.NGCONPC.G821 | G821 - Clearing and Grubbing | 0
| G7AM07ILI.AW3138.NGCONPC.G822 | G822 - Rock Excavation | 0
| G7AM07ILI.AW3138.NGCONPC.G825 | G825 - Conventional Bore - Dirt | 0
| G7AM07ILI.AW3138.NGCONPC.G826 | G826 - Conventional Bore - Rock | 0
| G7AM07ILI.AW3138.NGCONPC.G827 | G827 - Directional Drill – Dirt | 0
| G7AM07ILI.AW3138.NGCONPC.G828 | G828 - Directional Drill – Rock | 0
| G7AM07ILI.AW3138.NGCONPC.G829 | G829 - Conventional Upland Lay | 16579.93
| G7AM07ILI.AW3138.NGCONPC.G830 | G830 - Conventional Wetland Lay | 0
| G7AM07ILI.AW3138.NGCONPC.G831 | G831 - High Water Table | 0
| G7AM07ILI.AW3138.NGCONPC.G832 | G832 - Civil or General Conditions | 1212678.02
| G7AM07ILI.AW3138.NGCONPC.G833 | G833 - Hydro Test and Caliper Tool Run | 0
| G7AM07ILI.AW3138.NGCONPC.G834 | G834 - Commissioning | 0
| G7AM07ILI.AW3138.NGCONPC.G835 | G835 - Clean-up | 0
| G7AM07ILI.AW3138.NGCONPC.G836 | G836 - Stand-By - Pipeline | 0
| G7AM07ILI.AW3138.NGCONPC.G837 | G837 - AC/CP | 0
| G7AM07ILI.AW3138.NGCONPC.G902 | G902 - CS Pipeline - White | 0
| G7AM07ILI.AW3138.NGCONPC.CONPNA | Not Assigned - Construction Services - Pipeline | 0
| G7AM07ILI.AW3138.NGCONFC | 040 - CONSTRUCTION SERVICES – FACILITY | 8061968.73
| G7AM07ILI.AW3138.NGCONFC.G632 | G632 - Field Environmental and Erosion Control | 397818.87
| G7AM07ILI.AW3138.NGCONFC.G850 | G850 - Mob/Demob | 221313.63
| G7AM07ILI.AW3138.NGCONFC.G851 | G851 - Site Preparation | 274320.5
| G7AM07ILI.AW3138.NGCONFC.G852 | G852 - Concrete, Paving and Gravel | 315230.33
| G7AM07ILI.AW3138.NGCONFC.G853 | G853 - Building Erection | 0
| G7AM07ILI.AW3138.NGCONFC.G854 | G854 - Fabrication | 1048164.41
| G7AM07ILI.AW3138.NGCONFC.G855 | G855 - Installation | 4752194.29
| G7AM07ILI.AW3138.NGCONFC.G856 | G856 - Security, Fire Alarm, Instrumentation and Controls | 334010.96
| G7AM07ILI.AW3138.NGCONFC.G857 | G857 - Fencing | 159035
| G7AM07ILI.AW3138.NGCONFC.G858 | G858 - Tie-In | 53103.76
| G7AM07ILI.AW3138.NGCONFC.G859 | G859 - Hydro Test | 453673.23
| G7AM07ILI.AW3138.NGCONFC.G860 | G860 - AC/CP | 0
| G7AM07ILI.AW3138.NGCONFC.G861 | G861 - Commissioning | 53103.75
| G7AM07ILI.AW3138.NGCONFC.G862 | G862 - Stand-By - Facility | 0
| G7AM07ILI.AW3138.NGCONFC.G903 | G903 - CS Facility - White | 0
| G7AM07ILI.AW3138.NGCONFC.CONFNA | Not Assigned - Construction Services - Facility | 0
| G7AM07ILI.AW3138.NGREMPC | 050 - CONSTRUCTION RETIREMENT | 0
| G7AM07ILI.AW3138.NGREMPC.G823 | G823 - Abandon in Place Pipe | 0
| G7AM07ILI.AW3138.NGREMPC.G824 | G824 - Removal of Pipe | 232400.69
| G7AM07ILI.AW3138.NGREMPC.G863 | G863 - Station Retirement | 0
| G7AM07ILI.AW3138.NGREMPC.G904 | G904 - Construction Retirement - White | 0
| G7AM07ILI.AW3138.NGREMPC.CONRNA | Not Assigned - Construction Retirement | -232400.69
| G7AM07ILI.AW3138.NGILIPC | 060 - INLINE INSPECTION PROGRAM | 0
| G7AM07ILI.AW3138.NGILIPC.G870 | G870 - Row Clearing | 0
| G7AM07ILI.AW3138.NGILIPC.G871 | G871 - Validation Digs | 0
| G7AM07ILI.AW3138.NGILIPC.G872 | G872 - Retrofits | 0
| G7AM07ILI.AW3138.NGILIPC.G873 | G873 - Anomalies | 0
| G7AM07ILI.AW3138.NGILIPC.G906 | G906 - Inline Inspection Program - White | 0
| G7AM07ILI.AW3138.NGILIPC.ILINA | Not Assigned - Inline Inspection Program | 0
| G7AM07ILI.AW3138.NGFITSC | 070 - FIELD INSPECTION AND TESTING | 1489603.32
| G7AM07ILI.AW3138.NGFITSC.G880 | G880 - Construction Inspection | 1489603.32
| G7AM07ILI.AW3138.NGFITSC.G881 | G881 - Non-Destructive Testing | 0
| G7AM07ILI.AW3138.NGFITSC.G882 | G882 - Safety | 0
| G7AM07ILI.AW3138.NGFITSC.G883 | G883 - Environmental | 0
| G7AM07ILI.AW3138.NGFITSC.G905 | G905 - Field Inspection and Testing - White | 0
| G7AM07ILI.AW3138.NGFITSC.FITNA | Not Assigned - Field Inspection and Testing | 0
| G7AM07ILI.AW3138.NGMATEC | 080 - MATERIALS AND EQUIPMENT | 4093283.21
| G7AM07ILI.AW3138.NGMATEC.G201 | G201 - Inventory – Materials | 94005
| G7AM07ILI.AW3138.NGMATEC.G202 | G202 - Non-Inventory Parts / Materials | 1156328.95
| G7AM07ILI.AW3138.NGMATEC.G204 | G204 - Materials – Contractors | 0
| G7AM07ILI.AW3138.NGMATEC.G205 | G205 - Materials – MRC | -75757.03
| G7AM07ILI.AW3138.NGMATEC.G907 | G907 - Material & Inspection - White | 0
| G7AM07ILI.AW3138.NGMATEC.MAT001 | MAT001 - Material Allocations | -162.73
| G7AM07ILI.AW3138.NGMATEC.MAT002 | MAT002 - Stores Loading | 92926.42
| G7AM07ILI.AW3138.NGMATEC.MATNA | Not Assigned - Materials and Equipment | 2740724.6
| G7AM07ILI.AW3138.NGMPGL | 090 - DUKE LABOR | 585779.8
| G7AM07ILI.AW3138.NGMPGL.DL001 | DL001 - Labor | 233082.8
| G7AM07ILI.AW3138.NGMPGL.DL002 | DL002 - Labor Loader | 0
| G7AM07ILI.AW3138.NGMPGL.DL003 | DL003 - Overtime | 0
| G7AM07ILI.AW3138.NGMPGL.DL004 | DL004 - Overhead Labor - Allocation | 264702.61
| G7AM07ILI.AW3138.NGMPGL.G101 | G101 - Project Support Labor | 70923.74
| G7AM07ILI.AW3138.NGMPGL.DLNA | Not Assigned - Internal Labor | 16759.15
| G7AM07ILI.AW3138.NGMOTH | 100 - OTHER | 17104.01
| G7AM07ILI.AW3138.NGMOTH.OTHNA | Not Assigned - Other | 0
| G7AM07ILI.AW3138.NGMOTH.OTH001 | OTH001 - Other | 17104.01
| G7AM07ILI.AW3138.NGMOVH | 110 - OVERHEAD | 2122550.35
| G7AM07ILI.AW3138.NGMOVH.OVHNA | Not Assigned - Overhead | 0
| G7AM07ILI.AW3138.NGMOVH.OVH001 | OVH001 - Overhead | 2122550.35
| G7AM07ILI.AW3138.NGMAFD | 120 - AFUDC | 712041
| G7AM07ILI.AW3138.NGMAFD.ACCTG | ACCTG - AFUDC | 712041
| G7AM07ILI.AW3138.NGMAFD.AFUDCNA | Not Assigned - AFUDC | 0
| G7AM07ILI.AW3138.NGCONT | 130 - CONTINGENCY | 0
| G7AM07ILI.AW3138.NGCONT.CONT001 | CONT001 - Contingency | 0
| G7AM07ILI.AW3138.NGEXCEP | 140 - EXCEPTION | 0
| G7AM07ILI.AW3138.NGEXCEP.EXCEP001 | EXCEP001 - Exception | 0