## First Sheet
Object Path ID | Resource Type Path ID | Start Date | End Date | Curve ID | Cost | Currency | Transaction Date | External Key
N/A.CP1.NGCONFC |  | 2025-03-01 | 2028-01-29 | 2Y-NGCONFC | 0
N/A.CP1.NGCONPC |  | 2025-03-01 | 2028-01-29 | 2Y-NGCONPC | 12165700
N/A.CP1.NGCONT |  | 2025-03-01 | 2028-01-29 | 2Y-NGCONT | 3546300
N/A.CP1.NGENGNC |  | 2025-03-01 | 2028-01-29 | 2Y-NGENGNC | 1890800
N/A.CP1.NGEXCEP |  | 2025-03-01 | 2028-01-29 | 2Y-NGEXCEP | 0
N/A.CP1.NGFITSC |  | 2025-03-01 | 2028-01-29 | 2Y-NGFITSC | 1791400
N/A.CP1.NGILIPC |  | 2025-03-01 | 2028-01-29 | 2Y-NGILIPC | 0
N/A.CP1.NGLANDC |  | 2025-03-01 | 2028-01-29 | 2Y-NGLANDC | 3610800
N/A.CP1.NGMAFD |  | 2025-03-01 | 2028-01-29 | 2Y-NGMAFD | 719600
N/A.CP1.NGMATEC |  | 2025-03-01 | 2028-01-29 | 2Y-NGMATEC | 3336600
N/A.CP1.NGMOTH |  | 2025-03-01 | 2028-01-29 | 2Y-NGMOTH | 42000
N/A.CP1.NGMOVH |  | 2025-03-01 | 2028-01-29 | 2Y-NGMOVH | 3911100
N/A.CP1.NGMPGL |  | 2025-03-01 | 2028-01-29 | 2Y-NGMPGL | 997500
N/A.CP1.NGREMPC |  | 2025-03-01 | 2028-01-29 | 2Y-NGREMPC | 150500

## Master Tab
Input here will populate each tab with common information so that it does not need to be input on each tab.
Master Input Data
| Description | User Input | Notes
| Estimate Revision Number | D-Initiate | Change number on each draft to be sent out
| Ecosys Oppurtunity Number | N/A | Need to complete from Ecosys for Charter estimates.
| Project Name | Line AM07 Pipeline Replacement Phase 5
| Date: | 2025-01-16 | Update with each revision
| Length of Indicative Schedule in Years | 2 | This is required for Ecosys spend curves. Need to put 1, 2, or 3.
| Customer | Duke Energy/PNG
| City / County / Township | Erlanger, KY
| State | Kentucky
| Project manager | Kelsey Pace
| Modeler | System Planning
| Lead Estimator | R. Fredericks | Person who does the estimate
| Total Project Schedule | 35 | 1 Year Project - 17 months ¦ 2 Year Project - 35 months ¦ 3 Year Project - 46 months | **ADD +3 MONTHS IF RED STAKEHOLDER ENGAGEMENT
| Engineering Project Schedule | 15 | 1 Year Project - 5 months ¦ 2 Year Project - 15 months ¦ 3 Year Project - 16 months
| Construction Project Schedule | 9 | 1 Year Project - 4 months ¦ 2 Year Project - 9 months ¦ 3 Year Project - 10 months
| Estimate Requested By | Kelsey Pace
| Rate Requested |  | firm, interruptible, etc.
| Hourly Flow (MCFH) |  | change unit of measure as needed
Delivery Pressure (PSIG)
| Resource Center | Erlanger | Select from the Drop-down list
| Estimate Type | Class 4
| Length of Pipeline | 10,982 LF | Enter the overall pipe line footage. | *For Charters, use a 5% routing factor if proposed route appears to be thought out & follows property boundaries. Use 14% if straight line/does not follow property boundaries.
| Add Sales tax ( PNG Materials Only) | 7.75% | Input Percentage - Will automatically apply to materials
| Pipe Size | 24"
| Escalation (in Years) | 0 | Years until start date (not in-service date) (Put '0' if project is kicking off within 6 months)
| Escalation Rate (%) | 2.5% | Rate of Escalation (use '0' only for commit and build gates)
| Contingency (%) | 15% | Contingency %
| Start Date | 2025-03-01 | *Either start date from Ecosys or leave as 1/1/2022 for 2022 charters
| In-Service Date | 2027-08-30 | *This will auto-populate when total project schedule is completed | *For Charters, if the in-service date does not match this date then we need to let Renee's group know
| Close-Out Date | 2028-01-29 | *This will auto-populate when total project schedule is completed
| Ecosys In-Service Date | 2027-11-30 | *From Ecosys for Charters **IF HIGHLIGHTED RED THEN NOT FEASIBLE, CONTACT CHARTER GROUP** | *For Charters, if the in-service date does not match this date then we need to let Renee's group know
Estimate Steps
1 | Input information above - this transfers to headers on individual tabs
2 | Write Project description on the Review Format Tab (This can be updated as estimating progresses)
3 | Enter Pipe quantities on the Quantities Tab, enter quantities of HDD etc.
Select State
|  |  |  | North Carolina | 2500 | 2000
|  |  |  | South Carolina | 2000 | 1500
|  |  |  | Tennessee | 4100 | 3500
|  |  |  | Ohio | 4700 | 4000
|  |  | 4. Escalation was assumed at | Kentucky | 3500 | 3000
|  |  | per year with the project kicking off on | 2-State (LNG) | 5200 | 4500
.
[7 empty] | .CP1. | NGCONFC | Y-
NGCONPC
NGCONT
NGENGNC
NGEXCEP
NGFITSC
NGILIPC
NGLANDC
NGMAFD
NGMATEC
NGMOTH
NGMOVH
NGMPGL
NGREMPC
Formulas:
User Input = [User Input, row below]-(5*30.4)

## Estimate Uncertainty Tool
| PMCoE |  | Estimate Uncertainty
Cell requires user entry
[7 empty] | Identify | Class 5
| Project Name: |  | Line AM07 Pipeline Replacement Phase 5 |  | Date: | 2025-01-16 | Initiate | Class 4
[7 empty] | Commit | Class 3
| Next Stage Gate: |  | Initiate |  | Minimum Class: | Class 4 | Build | Class 3
PMCoE Estimate Uncertainty Tool
| Informed Range |  |  | Best Case (Optimistic: O) | Estimate Value (Most Likely: ML) | Worst Case (Pessimistic: P)
| - % | + % | Cost Description
OK | -30% | 50% | Engineering | 1323560 | 1890800 | 2836200
OK | -30% | 50% | Land | 2527560 | 3610800 | 5416200
OK | -30% | 50% | Materials/Equipment | 2335620 | 3336600 | 5004900
OK | -30% | 50% | Construction Services | 8380400 | 11972000 | 17958000
OK | -30% | 50% | Field Inspections & Testing | 1088430 | 1554900 | 2332350
OK | -30% | 50% | PNG Labor | 698250 | 997500 | 1496250
OK | -30% | 50% | Other | 29400 | 42000 | 63000
OK | -30% | 50% | AFUDC | 503720 | 719600 | 1079400
OK | -30% | 50% | Overhead & Allocations | 2737770 | 3911100 | 5866650
|  |  | Sub Total | 19624710 | 28035300 | 42052950 | O | 19624710
[7 empty] | ML*4 | 112141200
|  | 3.333% | A. Cummulative Risk EMV |  | 0 |  | P | 42052950
|  |  | B. Estimate Uncertainty PERT ((O+P+(ML*4))/6)-ML |  | 934510 |  | Total | 173818860
|  |  | C. Contingency (A+B) |  | 934510 |  | Divided by 6 | 28969810
|  |  |  | 19624710 | 28969810 | 42052950
|  |  |  | Best Case | Expected Case | Worst Case | ML | 28035300
|  |  | Project Informed Range | -32.26% |  | 45.16% | EU | 934510
|  |  | Certainty* | P10 | P50 | P90
|  | * P10 and P90 are representitive values, but not statistically proven by this methodology. These values do not include any Risk EMV and are shown to allow the project to assess if their Project Informed Range is aligned with the AACEI Class of Estimate expectations. | [5 empty] | 28969810
AACEI Estimate Class Reference:
|  | Class | Typical Methodology | Low Range | High Range
| Class 5 | 5 | Capacity Factored. Parametric Models. Judgement, or Analogy | -20% | 30%
| Class 5 |  |  | -50% | 100%
| Class 4 | 4 | Equipment Factored. Parametric Models. | -15% | 20%
| Class 4 |  |  | -30% | 50%
| Class 3 | 3 | Semi-Detailed Unit Costs with Assembly Level Line Items. | -10% | 10%
| Class 3 |  |  | -20% | 30%
| Class 2 | 2 | Detailed Unit Cost with Detailed Take-Off. | -5% | 5%
| Class 2 |  |  | -15% | 20%
| Class 1 | 1 | Detailed Unit Cost with Detailed Take-Off. | -3% | 3%
| Class 1 |  |  | -10% | 15%
Note on B12: PMCoE: The maximum allowable value in the -% Informed Range Column is 0%
Note on C12: PMCoE: The minimum allowable value in the +% Informed Range Column is 0%
Note on A13: PMCoE: Note that any items highlighted red require correction.
Note on A14: PMCoE: Note that any items highlighted red require correction.
Note on A15: PMCoE: Note that any items highlighted red require correction.
Note on A16: PMCoE: Note that any items highlighted red require correction.
Note on A17: PMCoE: Note that any items highlighted red require correction.
Note on A18: PMCoE: Note that any items highlighted red require correction.
Note on A19: PMCoE: Note that any items highlighted red require correction.
Note on A20: PMCoE: Note that any items highlighted red require correction.
Note on A21: PMCoE: Note that any items highlighted red require correction.
Note on F25: PMCoE: ML is subtracted from the PERT formula to show only the Estimate Uncertainty value.

## Finance Breakdown
Line AM07 Pipeline Replacement Phase 5
Funding Breakdown
2025-01-16
Description | Budget
Contract Labor | 16283400 | External Engineering, Construction Services, Field Inspection & Testing, Escalation
Material Purchased by PNG | 3336600 | Major Equipment and Testing
PNG Labor | 997500 | Internal Engineering and Construction Management
Land (Permanent Only) | 2836300 | Permanent Land purchases only
Other | 531500 | Land Rights (temporary land, land services, etc), Other Direct Costs - travel, meals, hotel, misc expenses
Sub-Total | 23985300
Contingency | 3546300 | Contingency
Sub-Total | 27531600
AFUDC | 0 | By Finance
Overheads | 0 | By Finance
Total | 27531600
Start Date | 2025-03-01 | By Project Manager
In-Service Date | 2027-08-30 | From Project Charter or Project Mgr.
Completion Date | 2027-11-30 | From Estimating
*ENSURE DISTRIBUTION COSTS HAVE BEEN REMOVED FROM ABOVE

## Assumptions
Line AM07 Pipeline Replacement Phase 5
Notes and Assumptions
2025-01-16
| Estimate Revision: | D-Initiate
1. 2023 Ecosys SOW: Phase 5 (of 5 Phases) includes the following: *Perform detailed engineering to support replacement of 23,710 feet (4.5 miles) of 24" pipe designed for a pressure of 1000 psig. *Install new 24" steel pipeline that starts where Phase 2 ends (dead end of Centre View Blvd [39° 1'19.33"N, 84°33'10.31"W]) and ends where Phase 3 starts (in the vicinity of coordinates [39° 1'33.74"N, 84°30'29.44"W]). *Abandon Line AM07 along this section. *Address remaining farm taps including elimination of UL26. *Preliminary proposed pipeline route that was field reviewed by Implemented
2023 Revised Scope per the Project Manager: *Perform detailed engineering to support replacement of 9,504 LF (1.8 Miles) of 24" Pipe designed for a pressure of 1000psig. *Install new 24" pipeline along the route proposed by the Map Exhibit below. *Abandon LineAM07 along this section. *Address remaining farm taps including elimination of UL26.
1. A routing Factor has been assumed for the pipeline route. Estimate revision assumes 10,835 LF of total Pipelay per the proposed High Level Routing with a 14% Routing Factor. Total Pipelay estimated is 10,835 LF.
2. Estimate assumes AC Mitigation is not required.
3. Estimate assumes basic environmental control design.
4. Estimate assumes SCADA is not required.
5. Estimate assumes that a laydown yard is required.
6. Estimate assumes that traffic control is required.
7. Estimate assumes 20% Rock Pipelay/0% Rock Bores per completed Phase Project AM07 Replacements.
8. Revision assumes no open cut Stream Crossings.
9. Revision assumes 1 Road Bore, Horsebranch Rd. (50LF).
10. Revision assumes existing Pipeline installed 2017. Retirement and Tie-ins does not require Coal Tar & Asbestos Remediation.
11. Revision assumes a MLV Installation is no longer required along the new Pipelay per Project Manager.
RevD-Initiate Estimate:
1. Pipelay estimate is 10,982 Linear Feet per B&McD Proposal.
2. Estimate assumes 1dirt bores, 1 rock HDD, and 1 RR crossing.
3. Estimate assumes AC Mitigation is not required.
4. Estimate assumes basic environmental control design.
5. Estimate assumes SCADA is not required.
6. Estimate assumes that a laydown yard is required.
7. Estimate assumes that traffic control is required.
8. Estimate assumes Engineering cost of $1,486,863 per B&McD Proposal.
9. Revision assumes no open cut Stream Crossings.
10. Estimate assumes existing pipeline built in 1956 per Project Charter. Retirement requires Coal Tar and Asbestos Remediation.
11. Estimate assumes 3 foot section removed of retired pipeline every 5,000 Linear Feet.

## Cost Change Log
This is to document the changes requested in the estimate from reviews.
Piedmont Natural Gas
Line AM07 Pipeline Replacement Phase 5
Estimate Change Log
[5 empty] | Revision: |  |  | D-Initiate
Item | Revision | Date | Description | Price Before Change | Price After Change | Change Amount | Change Directed By: | Estimate Changed By:
1 | A | XX/XX/XX | Starting Estimate | 0 | 0 | 0
2 | B | 2020-08-04 | Charter Estimate | 0 | 64609200 | 64609200 | Charter | K. Gillow
3 | C | 2023-11-30 | Revised Estimate-Class 5 Scope Change in Pipelay footage and Routing Change-Route is High Level and a 14% routing factor is included. 20,000 LF to 10,800 LF Reduction and no MLV Installation | 64609200 | 35497500 | -29111700 | Brad Seiter | Benton Jones
4 | D | 2025-01-16 | Initiate Estimate: Directional Drill Scope Reduced, Length of pipeline reduced. | 35497500 | 32162300 | -3335200 | Kelsey Pace | R. Fredericks
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## Cost Report
Line AM07 Pipeline Replacement Phase 5
Erlanger, KY
Project Cost Breakdown
Erlanger
2025-01-16
Revision: | D-Initiate | Capital Improvement and Retirement | Capital Improvement |  | Retirement
|  |  | Size / Name | 24" Steel Pipeline | 24" Steel
|  |  | Length / Qty | 16,036 LF | 23,710 LF
WBS 1 | Description |  | Total | Pipelay 1 | Pipe Abandon 1
NGENGNC | Engineering | 1890800 | 1878200 | 1878200 | 12600
NGLANDC | Land - Permanent | 2836300 | 2836300 | 2836300 | 0
NGLANDC | Land - Temporary | 489500 | 489500 | 489500 | 0
NGLANDC | Land - Support | 225000 | 225000 | 225000 | 0
NGLANDC | Land Legal | 60000 | 60000 | 60000 | 0
NGMATEC | Materials/Equipment | 3336600 | 3330400 | 3330400 | 6200
NGCONPC | Construction Serv - Pipeline | 11972000 | 11821500 | 11821500 | 150500
NGCONFC | Construction Serv - Facility | 0 | 0 | 0 | 0
NGFITSC | Field Inspections | 1554900 | 1536800 | 1536800 | 18100
NGFITSC | Field Testing | 236500 | 236500 | 236500 | 0
NGMPGL | Duke/PNG Labor | 997500 | 980000 | 980000 | 17500
NGMOTH | Other Direct Costs | 42000 | 38500 | 38500 | 3500
Subtotal Direct Cost |  | 23641100 | 23432700 | 23432700 | 208400
| Project Contingency | 3546300 | 3515000 | 3515000 | 31300
| Project Escalation | 344200 | 339900 | 339900 | 4300
Total Contingency & Escalation |  | 3890500 | 3854900 | 3854900 | 35600
Total Direct Cost |  | 27531600 | 27287600 | 27287600 | 244000
NGMAFD | AFUDC Debt | 719600 | 719600 | 719600 | 0 | AFUDC | 0.07
NGMOVH | Overhead and Allocations | 3911100 | 3865900 | 3865900 | 45200 | Overheads | 0.19
Total PNG Overhead Cost |  | 4630700 | 4585500 | 4585500 | 45200
Project Total |  | 32162300 | 31873100 | 31873100 | 289200
Notes:
1. Contingency is not included on escalation.
2. Overheads and Allocations calculated using 19% of Total Direct Cost less Land Purchase, Materials/Equipment and FERC cost.
3. AFUDC calculated using 7% of total Direct Cost. (No AFUDC on Retirement Cost.)
4. Escalation was assumed at 2.5% per year with the project kicking off on 03/01/25.
|  | OVERHEAD RATE | AFUDC RATE
| Erlanger | 0.19 | 0.07
| FBRG - Fort Bragg | 0.13 | 0.069
| GD10 - Ohio | 0.23 | 0.0568
| GD70 - Kentucky | 0.19 | 0.07
| GDKO | 0.23 | 0.0568
| Kellogg | 0.23 | 0.0568
| Monfort Heights | 0.23 | 0.0568
| PAOC - Anderson | 0.13 | 0.069
| PBLN - Bentonville LNG | 0.02 | 0.069
| PBOC - Burlington | 0.13 | 0.069
| PCLN - PNG Carolina LNG | 0.02 | 0.069
| PCOC - Charlotte | 0.13 | 0.069
| PEOC - Elizabeth City | 0.13 | 0.069
| PFOC - Fayetteville | 0.13 | 0.069
| PGDO - Goldsboro | 0.13 | 0.069
| PGOC - Greensboro | 0.13 | 0.069
| PGRO - Greenville | 0.13 | 0.069
| PHLN - Huntersville LNG | 0.02 | 0.069
| PHOC - Hickory | 0.13 | 0.069
| PHPC - High Point | 0.13 | 0.069
| PIOC - Indian Trail | 0.13 | 0.069
| PMOC - Mayland | 0.13 | 0.069
| PNOC - New Bern | 0.13 | 0.069
| PNOV - Nashville | 0.11 | 0.069
| PROC - Reidsville | 0.13 | 0.069
| PROO - Rockingham | 0.13 | 0.069
| PSOC - Salisbury | 0.13 | 0.069
| PSPO - Spartanburg | 0.13 | 0.069
| PTOC - Tarboro | 0.13 | 0.069
| PWIO - Wilmington | 0.13 | 0.069
| PWOC - Winston Salem | 0.13 | 0.069
| Todhunter | 0.23 | 0.0568
| PSOP - South Carolina | 0.13 | 0.069

## Pipeline 1
Line AM07 Pipeline Replacement Phase 5
2025-01-16 | 24" |  |  |  | Revision # | D-Initiate
Control Code | Component Description | Units | Unit of Measure | Unit Cost | Sub-totals | Totals
Internal Engineering & Construction Management
G101 | Duke/PNG Labor | 35 | Month | 28000 | 980000
OTH001 | Other Direct Cost | 35 | Month | 1100 | 38500
Sub-Total - Internal E&CM | [5 empty] | 1018500
External Engineering
G801 | Pre-Design Activities | 1 | Lump Sum | 3334 | 3334 |  | Per B&McD Proposal
G802 | Route Development | 1 | Lump Sum | 18225 | 18225 |  | Per B&McD Proposal
G803 | Project Managemenet | 1 | Lump Sum | 71580 | 71580 |  | Per B&McD Proposal
G804 | Records Research | 1 | Lump Sum | 1182 | 1182 |  | Per B&McD Proposal
G805 | Estimating & Scoping | 0 | Lump Sum | 0 | 0 |  | Per B&McD Proposal
G806 | Land Survey | 1 | Lump Sum | 85371 | 85371 |  | Per B&McD Proposal
G807 | Land Acquistion Support (Engineering) | 1 | Lump Sum | 29887 | 29887 |  | Per B&McD Proposal
G808 | Environmental Services & Permitting | 1 | Lump Sum | 82894 | 82894 |  | Per B&McD Proposal
G809 | Geotechnical Services | 1 | Lump Sum | 134586 | 134586 |  | Per B&McD Proposal
G810 | Design - Pipeline | 1 | Lump Sum | 246090 | 246090 |  | Per B&McD Proposal
G811 | Engineering Adders | 1 | Lump Sum | 400259 | 400259 |  | Per B&McD Proposal
G812 | Cathodic Protection | 1 | Lump Sum | 11036 | 11036 |  | Per B&McD Proposal
G813 | Bid Package Development | 1 | Lump Sum | 15644 | 15644 |  | Per B&McD Proposal
G814 | Construction Support | 1 | Lump Sum | 320109 | 320109 |  | Per B&McD Proposal
G815 | As-Built Survey | 1 | Lump Sum | 453937 | 453937 |  | Per B&McD Proposal
G815 | Project Close-out | 1 | Lump Sum | 452 | 452 |  | Per B&McD Proposal
G663 | MAOP Oversight | 1 | Lump Sum | 3600 | 3600 |  | *Per Farsnworth costs that Robin provided.
Sub-Total - External Engineering | [5 empty] | 1878200
Land Services
G661 | Transmission - Fee Purchase - Rural | 0 | Acre | 0 | 0
G661 | Transmission - Fee Purchase - Urban | 0 | Acre | 156250 | 0
G662 | Transmission - Permanent Easements - Rural | 0 | Acre | 0 | 0 |  |  |  | 458 | 1444 | 340 | 302 | 375 | 494 | 940 | 500 | 321 | 844 | 186 | 1210 | 773 | 561 | 218 | 264 | 880 | 1106 | 201 | 319 | 228 | 627 | 972 | 320 | 256
G662 | Transmission - Permanent Easements - Urban | 15.1267 | Acre | 187500 | 2836300
G662 | Transmission - Stations Easements - Rural | 0 | Acre | 0 | 0 |  |  |  | 119 | 106 | 137
G662 | Transmission - Stations Easements - Urban | 0 | Acre | 218750 | 0 |  |  |  | 80 | 80 | 80 | 80 | 80 | 80
G663 | Transmission - Temporary Easements - Rural | 0 | Acre | 0 | 0 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2
G663 | Transmission - Temporary Easements - Urban | 10.0845 | Acre | 39062.5 | 394000
G662 PA | Transmission - Access Roads | 2 | Each | 10000 | 20000
G663 | Transmission - Laydown Yard | 11 | Months | 4200 | 46200
G656 | Transmission - Damages | 9 | Per Parcel | 3250 | 29300
G656 | Transmission - Additional Damages | 0 | Acre | 0 | 0
G301 | Contract Labor - Land Services | 18 | Per Parcel | 12500 | 225000
G301 | Contract Labor - Legal | 2 | Per Parcel | 30000 | 60000
Sub-Total - Land Services | [5 empty] | 3610800
Construction Services - Pipeline |  | 10982 | Overall LF of Pipe installed
820 | Mob/Demob | 1 | Lump Sum | 1074681.7012 | 1074681.7012 |  | 10%
821 | Clearing and Grubbing | 11.708 | acre | 85000 | 995179.0634
821 | Tree Cutting Only/No Grubbing | 1.6781 | acre | 75000 | 125860.8815
829 | Conventional Upland Lay | 9994 | Linear Foot | 475 | 4747150
829 | Conventional Upland Lay (Residential) | 0 | Linear Foot | 0 | 0
830 | Conventional Wetland Lay | 0 | Linear Foot | 385 | 0
825 | Conventional Bore - Dirt ( 1 Bore) | 48 | Linear Foot | 2500 | 120000
826 | Conventional Bore - Rock | 0 | Linear Foot | 0 | 0
827 | Directional Drill – Dirt | 0 | Linear Foot | 0 | 0
828 | Directional Drill – Rock | 940 | Linear Foot | 1590 | 1494600
828 | ScarGuard Application | 943.6 | Linear Foot | 269 | 253828.4
822 | Rock Excavation – Blasting | 0 | Cubic Yard | 0 | 0
822 | Rock Excavation – Mechanical | 888.3556 | Cubic Yard | 300 | 266506.6667
829 | Anomoly Dig | 0 | Each | 0 | 0
829 | Retrofit Cost | 0 | Linear Foot | 0 | 0
829 | Material Verification | 0 | Each | 18000 | 0
829 | Bore/Drill Pits | 2 | Per Bore/Drill | 25000 | 50000
829 | Extra Depth Ditch | 0 | Per 1 ft depth / LF | 40 | 0
829 | Padding – Job Site | 1998.8 | Linear Foot | 25 | 49970
829 | Padding - Haul | 0 | Linear Foot | 0 | 0
829 | Sand Padding over Existing Lines | 0 | Cubic Yard | 0 | 0
822 | Rock Shield | 0 | Linear Foot | 0 | 0
831 | Saddle Bag Weight | 0 | Each | 0 | 0
831 | River Weight | 0 | Each | 0 | 0
831 | Concrete Coating | 0 | Linear Foot | 0 | 0
837 | Zinc Ribbon (AC Mitigation) | 0 | Linear Foot | 0 | 0
837 | Anode Bed | 0 | Each | 0 | 0
835 | Temporary Clean-up / Temporary Stabilization | 9994 | Linear Foot | 50 | 499700
833 | Hydro Test | 11922 | Lump Sum | 34 | 405348
833 | Hydro Water Testing | 0 | Lump Sum | 25000 | 0
834 | Commissioning | 10982 | Lump Sum | 4 | 43928
837 | Re-coating of Exposed Pipe (Hand Application) | 0 | Linear Foot | 0 | 0
837 | Re-coating of Exposed Pipe (Spray Application) | 0 | Linear Foot | 0 | 0
837 | Armor Plate | 0 | Linear Foot | 0 | 0
829 | Daylight Existing Utilities (Pot Holing) | 4 | Lump Sum | 1500 | 6000
829 | AirVac/Hydro Vac Excavation | 0 | Cubic Foot | 0 | 0
829 | Pipe Rack Construction (Dirt/Sand Berm) | 0 | Lump Sum | 0 | 0
829 | Transition Of Bevels | 0 | Each | 0 | 0
837 | Test Station Installation | 7 | Each | 1000 | 7000
829 | Temporary Stabilization | 0 | Linear Foot | 0 | 0
630 | Silt Fence (metal post & wire backing) | 19988 | Linear Foot | 25 | 499700
630 | Conventional Silt Fence | 0 | Linear Foot | 0 | 0
630 | Super Silt Fence (metal post & chainlink fence backing) | 0 | Linear Foot | 0 | 0
630 | Curlex Blanket with Staples (4 x 100) | 200 | Square Yard | 5 | 1000
630 | Curlex Double Net Blanket with Staples (4 x 100) | 0 | Square Yard | 0 | 0
630 | Curlex Triple Net Blanket with Staples (4 x 100) | 0 | Square Yard | 0 | 0
630 | Curlex Premier Coconut Blanket with Staples (4 x 100) | 0 | Square Yard | 0 | 0
630 | Curlex Premier Straw/Coconut Blanket with Staples (4 x 100) | 0 | Square Yard | 0 | 0
630 | Hydroseeding Temporary Stabilization | 0 | Square Yard | 0 | 0
630 | Hydroseeding Permanent Stabilization | 0 | Square Yard | 0 | 0
630 | Rip Rap Placement | 0 | Ton | 0 | 0
630 | Gravel Placement | 0 | Ton | 0 | 0
630 | Geo Textile Fabric | 0 | Square Yard | 0 | 0
630 | Safety Fence | 900 | linear ft | 8 | 7200
630 | Culvert Pipe (CMP) | 0 | Inch Dia per LF | 0 | 0
630 | Sack Breakers | 0 | Each | 0 | 0
630 | Sediment Basin (excludes rock) | 0 | Each | 0 | 0
630 | Trench Breaker (Plug) | 0 | Each | 0 | 0
630 | Foam Breakers | 0 | Each | 0 | 0
630 | Construction (Timber) Mats | 100 | Linear Foot (Width) | 125 | 12500
630 | Laminated (Truck) Mats | 0 | Linear Foot (Width) | 0 | 0
630 | Bentonite Trench Seals in Wetlands | 0 | Each | 0 | 0
630 | Permanent Seeding (seed straw, and tack) | 999400 | Square Foot | 0.15 | 149910
630 | Intermediate Seeding (seed straw, and tack) | 499700 | Square Foot | 0.1 | 49970
630 | Dry Crossing (Flume or Dam/Pump Method) | 0 | Each | 0 | 0
630 | Sod | 0 | SF | 0 | 0
630 | Straw Wattle 9'' x 10' | 0 | Each | 0 | 0
630 | Sediment Log 8'' | 0 | Each | 0 | 0
630 | Sediment Log 10'' | 0 | Each | 0 | 0
630 | Sediment Log 12'' | 0 | Each | 0 | 0
630 | Sediment Log 20'' | 0 | Each | 0 | 0
630 | Erosion Eel 10'' | 0 | Each | 0 | 0
630 | Erosion Eel 12'' | 0 | Each | 0 | 0
630 | Erosion Eel 14'' | 0 | Each | 0 | 0
630 | Erosion Eel 20'' | 0 | Each | 0 | 0
630 | Permanent Waterbar Installation | 0 | Each | 0 | 0
630 | Temporary Waterbar Installation | 0 | Each | 0 | 0
630 | Filtration Sediment Bags 10' x 15' | 0 | Each | 0 | 0
630 | Dewater Structure | 0 | Lump Sum | 0 | 0
630 | Clear Water Diversion Pit | 0 | Lump Sum | 0 | 0
630 | Stabilized Construction Entrance 20'W x 50'L x 6''D | 6 | Each | 4500 | 27000
831 | Well Points | 0 | Each | 0 | 0
832 | Air Bridges | 0 | Each | 0 | 0
832 | Chain Link Fence & Gates – New | 0 | Linear Foot | 0 | 0
832 | Chain Link Fence & Gates - Repair | 0 | Linear Foot | 0 | 0
832 | Temporary Pasture Fencing | 0 | Linear Foot | 0 | 0
832 | Permanent Access Roads | 0 | Linear Foot | 0 | 0
832 | Temporary Access Roads | 2000 | Linear Foot | 35 | 70000
832 | Top Soil | 0 | Ton | 0 | 0
832 | Asphalt Removal | 1384 | Square Foot | 17.5 | 24220
832 | Asphalt Restoration | 1384 | Square Foot | 17.5 | 24220
832 | Sheet Piling | 0 | Day | 0 | 0
832 | Ditch Shoring | 0 | Day | 5000 | 0
832 | Road Plates (10' Long) | 14 | Each | 750 | 10500
832 | Trench Boxes | 0 | Day | 0 | 0
832 | Traffic Control (Flaggers) | 40 | Day | 5000 | 200000
832 | Traffic Control (Signage) | 60 | Day | 100 | 6000
832 | Traffic Control (Barriers) | 60 | Day | 100 | 6000
832 | Flowable Fill | 0 | Cubic Yard | 0 | 0
832 | Noise Reduction Barriers | 0 | Day | 0 | 0
837 | Rectifier/Groundbed (CP) | 1 | Lump Sum | 9000 | 9000
837 | ACVG Testing (less than 10 miles) | 2 | Mile | 9000 | 18000
837 | ACVG Testing (greater than 10 miles) | 0 | Mile | 6000 | 0
| MLV Installation | 0 | Each | 0 | 0
| MLV Foundations | 0 | Each | 7500 | 0
| SCADA for MLV Sites | 0 | Each | 100000 | 0
| Electrical/Controls for MLV Sites | 0 | Each | 50000 | 0
| Security for MLV Sites | 0 | Each | 21000 | 0
| L/R Installation | 0 | Each | 0 | 0
| L/R Foundations | 0 | Each | 30000 | 0
| Painting & Waxing Flanges | 0 | Lump Sum | 25000 | 0
| Staging & Laydown Yard | 5 | Acre | 65000 | 325000
| Railway Crossings | 1 | Each | 20000 | 20000
| Civil or General Conditions | 0 | Lump Sum | 0 | 0
| Stopple Pit | 2 | Each | 25000 | 50000
| Contractor Tap Support 24" | 2 | Each | 21273 | 42546
| TDW - Hot Tap 24" | 2 | Each | 16500 | 33000
| TDW - Tap & Stop | 0 | Each | 0 | 0
| TDW - Bypass | 0 | Each | 0 | 0
| HDD Geo-analytical Design | 1 | Each | 60000 | 60000
| HDD Mudd Disposal | 940 | Linear Foot | 17 | 15980
| HDD Mudd Engineer | 1 | Lump Sum | 20000 | 20000
Sub-Total - Construction Services - Pipeline | [5 empty] | 11821500
Field Inspection & Testing
G880 | Construction Inspection | 1807.9941 | Per Man-Days | 850 | 1536795 |  | 13% | Inspection Rate
G881 | Non-Destructive Testing | 94.572 | Days | 2500 | 236430 |  | 2% | NDT Rate
Sub-Total - Field Inspection & Testing | [5 empty] | 1773300
Major Equipment & Materials
Pipe
G205 | 24" Standard Wall, X52, Coated, DRL | 10940 | Linear Foot | 200 | 2188000
G205 | 24" Standard Wall, X52, Powercrete | 60 | Linear Foot | 175 | 10500
G205 | XX" Standard Wall, X52, Bare | 0 | Linear Foot | 0 | 0
Fittings
G205 | 24" 3R - 45 deg ell - Segmentable | 18 | Each | 4242 | 76356
G205 | 24" 3R - 90 deg ell - Segmentable | 12 | Each | 6158 | 73896
Equipment
G204 | XX" TDW Stopple | 0 | Each | 0 | 0
G204 | 24" TDW Spherical Tee | 2 | Each | 58000 | 116000
G204 | XX" L/R Module | 0 | Each | 0 | 0
G204 | XX" MLV Module | 0 | Each | 0 | 0
Miscellaneous
| Anode Bed Material | 0 | Each | 20000 | 0
| Rectifier/Groundbed Material (CP) | 1 | Each | 9000 | 9000
| AC Mitigation Material | 0 | Each | 75000 | 0
G204 | ScarGuard | 943.6 | Linear Foot | 269 | 253828.4
G205 | Misc. Materials (10% of Total Major) | 1 | Calculated | 272758.04 | 272758.04
G205 | Taxes & Freight (11% of All Material) | 1 | Calculated | 330037.2284 | 330037.2284
Sub-Total - Materials | [5 empty] | 3330400
Sub-Total | [5 empty] | 23432700
Escalation |  | 0 | Year at | 2.5% |  | 339900
Contingency |  |  |  | 15% |  | 3515000
Pipeline Estimate Total | [5 empty] | 27287600
[5 empty] | Cost per foot | 2484.7569
[5 empty] | Cost per mile | 13119516.2994

## Demo 1
Line AM07 Pipeline Replacement Phase 5
2025-01-16 | Retirement |  |  |  | Revision # | D-Initiate
Control Code | Component Description | Units | Unit of Measure | Unit Cost | Sub-totals | Totals
Internal Engineering & Construction Management
G101 | Duke/PNG Labor | 35 | Month | 500 | 17500
OTH001 | Other Direct Cost | 35 | Month | 100 | 3500
Sub-Total - Internal E&CM | [5 empty] | 21000
External Engineering
G810 | Design - Pipeline | 100.288 | Hour | 125 | 12536
G811 | Design - Facility | 0 | Hour | 125 | 0
G663 | MAOP | 0 | Lump Sum | 0 | 0
Sub-Total - External Engineering | [5 empty] | 12600
Land Services
G-663 | Transmission - Temp Work Space - Rural | 0 | Acre | 45000 | 0
G-663 | Transmission - Temp Work Space - Urban | 0 | Acre | 5000 | 0
G-662 PA/G-663 TA | Transmission - Access Roads | 0 | Each | 10000 | 0
G-301 | Contract Labor - Land Services | 0 | Per Parcel | 10000 | 0
Sub-Total - Land Services | [5 empty] | 0
Construction Services - Pipeline |  | 23710 | Overall LF of Pipe to be Abandoned
850 | Mob/Demob | 1 | Lump Sum | 13676.275 | 13676.275 |  | 10%
| Demo Equipment | 3 | Days | 7500 | 22500
823 | Grouting of Abandoned Pipe | 0 | Cubic Yard | 0 | 0
824 | Removal of Existing Pipeline | 14.226 | Linear Foot | 2125 | 30230.25
| Tar Coated Steel Remediation & Removal | 4.742 | Per Dig/Site | 3750 | 17782.5
| Install & Remove Flare + Mob/Demob | 0 | Lump Sum | 50000 | 0
| Methane Recapture | 1 | Lump Sum | 25000 | 25000
G863 | Launcher/Receiver Removal | 0 | Each | 75000 | 0
G863 | Small Station Removal | 0 | Each | 35000 | 0
G863 | Medium Station Removal | 0 | Each | 50000 | 0
G863 | Large Station Removal | 0 | Each | 85000 | 0
| Haul Materials | 1 | Per Site | 10000 | 10000
| Nitrogen Clearing | 1 | Lump Sum | 25000 | 25000
| Line Locating | 0.5 | Week | 12500 | 6250
| Contractor Tap Support | 0 | Days | 0 | 0
| Seeding | 0 | SF | 0 | 0
| Clean up | 0 | LF | 0 | 0
| TDW Tap | 0 | Each | 0 | 0
150500
Field Inspection & Testing
G880 | Construction Inspection | 21.2471 | Man-Days | 850 | 18060
G881 | Non-Destructive Testing | 0 | Days | 2000 | 0
Sub-Total - Field Inspection & Testing | [5 empty] | 18100
Major Equipment & Materials
G205 | Purge Materials | 1 | Lump Sum | 5000 | 5000
G204 | Stopple | 0 | Each | 0 | 0
G204 | Stopple | 0 | Each | 0 | 0
G205 | Misc. Materials (10% of Total Major) | 1 | Calculated | 500 | 500
G205 | Taxes & Freight (11% of All Material) | 1 | Calculated | 605 | 605
Sub-Total - Materials | [5 empty] | 6200
Sub-Total | [5 empty] | 208400
Escalation |  | 0 | Year at | 2.5% |  | 4300
Contingency |  |  |  | 15% |  | 31300
Pipeline Estimate Total | [5 empty] | 244000

## Dropdown Values (hidden)
DropDown Values
Pipeline Length | Less than 2000 feet
< 1 mile
1-5 miles
> 5 miles
Retrofit Length | < 5 miles
5-10 miles
> 10 miles
Yes/No | Yes
No
Land | Urban
Rural
Suburban
Parcels | 0 parcels
< 20 parcels
20 - 50 parcels
> 50 parcels
Vegetation Management | 0-5%
6-33%
| 34%-66% | 6 | 6
67%-100%
Zoning Type | Farmlands
Existing Utility Right of Way
Electric Right of Way
Commercial/Industrial
Parks & Recreation
Residential
Nature Preserves
Mixed Use
4.2 Permit requirement | Open House
Public Notice
None of the above

## EJ Questionaire
Environmental Justice Assessment Trigger Questionnaire
Date: | 2025-01-16
Activity/Project Name: | Line AM07 Pipeline Replacement Phase 5
Business Unit: | NGBU
Project Staff: | Major Projects
Activity/Project Scope or Description: |  | 1. 2023 Ecosys SOW: Phase 5 (of 5 Phases) includes the following: *Perform detailed engineering to support replacement of 23,710 feet (4.5 miles) of 24" pipe designed for a pressure of 1000 psig. *Install new 24" steel pipeline that starts where Phase 2 ends (dead end of Centre View Blvd [39° 1'19.33"N, 84°33'10.31"W]) and ends where Phase 3 starts (in the vicinity of coordinates [39° 1'33.74"N, 84°30'29.44"W]). *Abandon Line AM07 along this section. *Address remaining farm taps including elimination of UL26. *Preliminary proposed pipeline route that was field reviewed by Implemented
The intent of this questionnaire is to identify Duke Energy projects /activities that might have significant environmental or community impacts or required regulatory approvals and/or that are located in or near communities of environmental justice (EJ) concern to further assess for potential EJ risks and planning.
Review activity/project and answer the following questions: |  |  | Answer (Yes, No, Unknown)
Does the activity/project anticipate a public regulatory approval that may trigger EJ Assessment requirements? (i.e. federal permitting, NRC licensing, state Public Utility Commission approval) Transmission only, Should only apply to Ohio (OPSB) & Kentucky (CPCN). |  |  | No
Does the activity/project anticipate creating significant new, modifying, or increasing discharge, emissions, or waste generation - either amount or type? Compressor Station, Permanent Flare, Heaters over 10 mmBTU/hr (not associated with Duke M&R), Station located near Paper Mill, Pellet, Concrete, Brick Plant, chemical (large emission or smell producing plants) |  |  | No
Does the activity/project anticipate significant land use modification, land acquisition, easement acquisition and/or modifications to community aesthetics? Large Stations immediately outside or in the middle of developments, neighborhoods. 20+ miles of pipeline |  |  | No
Does the activity/project trigger routing or site selection studies? OPSB, 20+ miles of pipeline, if charter states a routing/site selection study will be required |  |  | No
Is the activity/project in a community with known, previous and/or on-going EJ concerns? ACP corridor, Tribal Lands, Known Opposition |  |  | No
If the answer is “Yes” or “Unknown” to any of the questions above, consult with Environmental and External Engagement Staff (Nicole Kiser) to determine if an initial EJ Assessment is needed.

## PE Level of Risk Template
Nat Gas Project Public Engagement Level-of-Risk Assessment
Charter/Project Name: |  | Date: |  |  |  |  | 0-10 level | 0-10 level | Impact - Magnitude of stateholder opposition (Defined by cost, or reputation)
Risk | Public Engagement Questionaire | Response | Priority | Calculation Menu | Probability | Impact | Probability | Impact | Probabilty - External stakeholder opposition
1. Attributes
1.1 | New Natural Gas Pipeline Length (in new footprint) (miles) (system infrastructure growth)? | Less than 2000 feet |  |  | 0 | 0 | 0,1,3,5 | 0,1,3,5
1.2 | Replace or Retrofit Natural Gas Pipeline Length (miles)(Integrity project)? * | 1-5 miles |  |  | 1 | 1 | 0,1,2 | 0,1,1
1.3 | New Regulator Station(s)/Launcher/Receiver? | No |  |  | 0 | 0 | 0,3 | 0,2
1.4 | Expanding the footprint of existing Regulator Station? | No |  |  | 0 | 0 | 0,3 | 0,3
1.5 | New Compressor Station(s)? | No |  |  | 0 | 0 | 0,8 | 0,7 |  | Community Engagement Heat Map
1.6 | Expanding the footprint of existing Compressor Station? | No |  |  | 0 | 0 | 0,3 | 0,3 |  | Probability
1.7 | Requires flaring? | No |  |  | 0 | 0 | 0,2 | 0,5
2. Land
2.1 | Urban, Rural or Suburban? | Urban |  |  | 7 | 7 | urban = 7,suburban=6,rural=0 | urban = 7,suburban=5,rural=0 |  |  |  | X
2.2 | New Easement acquisition required? | Yes |  |  | 3 | 3 | 0,3 | 0,3
2.3 | New Land acquisition required (in fee)? | No |  |  | 0 | 0 | 0,4 | 0,4 |  |  | Impact
2.4 | Anticiapted number of parcels to be purchased? | < 20 parcels |  |  | 2 | 2 | 0,2,4,6 | 0,2,4,6
2.5 | Amount of new Right of Way tree clearing required | 6-33% |  |  | 2 | 2 | 0,2,4,6 | 0,2,4,6 |  | 1 | Notify Community Relations
3. Environment, Historic, Archeological | [9 empty] | 2 | Local Community Relations Engagenment at Project Initiation
3.1 | Crossing navigable waterways? | No |  |  | 0 | 0 | 0,2 | 0,4 |  | 3 | Enable Strike Team 24 months prior to Project Kickoff
3.2 | Larger environmentally sensitive areas? * | No |  |  | 0 | 0 | 0,3 | 0,7
3.4 | State/Local permits required? | Yes |  |  | 0 | 0
3.4 | Sensitive, Protected, Historical Sites, Cultural Areas? (Not environmental) | No |  |  | 0 | 0 | 0,3 | 0,5
3.5 | Zoning Type? * | Residential |  |  | 6 | 6 | See dropdown value sheet
4. Additional Factors
4.1 | Past opposition from affected land owners and communities? | No |  |  | 0 | 0 | 0,8 | 0,8
4.2 | Permiting process requires : | None of the above |  |  | 0 | 0 | Open House =7,Public Notice=4, NA=0 | Open House =10,Public Notice=6, NA=0
1 | Is Easement Acquisition Required for New Nat Gas Project Line? | YES | 2 | YES | 5 | 7
2 | New Nat Gas Project R/W Length (miles)? | <1 | 2 | NO | 1 | 1
3 | Nat Gas Project Line Rebuild Length (Miles)? | N/A | 7 | N/A | 0 | 0
4 | Is Nat Gas Project traverse Commercial, Residential, Rural, Multiple or All land types | Residential Only | 3 | 0-10 | 3 | 3
5 | Does Nat. Gas Proejct involve rebuild/replacement with larger size, pressure, controls, or systems? | NO | 3 | 11-20 | 0 | 0 |  |  |  |  | Impact
6 | What is the expected number range of parcels involved with this project? | NO | 8 | 21+ | 0 | 0 |  |  |  |  | #N/A
7 | What level of vegetation management is required? | N/A | 7 |  | 0 | 0 |  |  |  |  | Notify Community Relations
8 | Is this a line abandonment/relocation project that requires community engagement? | NO | 8 | N/A | 0 | 0 |  |  |  |  | Local Community Relations Engagenment at Project Initiation
9 | Is a regulatory or state filing required? (ie: LIST SPECIFIC REG BODIES) | NO | 5 | <1 | 0 | 0 |  |  |  |  | Enable Strike Team 24 months prior to Project Kickoff
10 | Does this project include addition of new regulator station, compressor station, flare tower, etc. seen by the public? | NO | 7 | 1-5 | 0 | 0 |  |  |  |  | #N/A
11 | Does this project expand exisiting regulator station, compressor station, flare tower, etc. seen by the public? | NO |  | >5 | 0 | 0 |  |  |  |  | #N/A
12 | Is land acquisition/easement required for expanding right of way, new ROW, laydown space or access? | YES | 4 |  | 3 | 5 |  |  |  |  | #N/A
13 | Are there Current/Historic Community Sensitivities? | YES | 4 |  | 5 | 5 |  |  |  |  | #N/A
14 | Is zoning/rezoning required? | NO | 5 | N/A | 0 | 0 |  |  |  |  | #N/A
15 | Federal Permitting Required? | NO | 5 | High | 0 | 0 |  |  |  |  | #N/A
16 | Special Use or Conditional Use Permit Required? | NO | 5 | Med | 0 | 0 |  |  |  |  | #N/A
17 | Does project involve Environmentally Sensitive Areas | NO | 7 | Low | 0 | 0
18 | Project involve Sensitive, Protected, Historical Sites, Cultural Areas? | NO | 7 |  | 0 | 0
19 | Estimated number of Property Owners Impacted? | 0-10 | 4 | N/A | 2 | 3
|  |  | Final Total | Commercial Only | 21 | 21
Residential Only
|  |  |  | Rural Only |  |  |  | Community Engagement Heat Map
|  |  |  | 2 of the Above |  |  |  | Probability
All
"Notify Community Relations
Near term stakeholder engagement striketeam
Lead In community engagement prior to project kickoff
*Do Not Remove Below
[13 empty] | X Marks the Spot | Heat Level
[13 empty] | $P$13 | 1
* Notes
1.2 Response should be reflective of actual footage of construction not mileage researched
3.2 May not know environment sensitivity initially
3.2 Environmentally Sensitive - Named Environmental areas (shows up on a map with a name)
3.5 If entire project is in Utility ROW and no known preexisiting opposition to construction in or near that ROW then the project can default to 'Yellow' or Green'
Note on C30: Johnson, Kevin S: The intent is to recognize that a significant portion of the line is in a residential area
Note on C33: Johnson, Kevin S: High = Full Clearing / Danger Tree Removal Med = Side Trimming Low = Bushhogging
Note on C34: Johnson, Kevin S: Consider if the r/w will be returned to the property owner or retained by DE as a response to this question
Note on C43: Johnson, Kevin S: Examples would include wetlands, swamps, endangered species, sensitive natural resources, etc.
Note on C44: Johnson, Kevin S: Examples of Sensitive Areas are National Forest, National / State / Local Park, Federal Land, Nature Preserve, etc.

## R&D Credit Potential
R&D Credit Potential Checklist
Date: | 2025-01-16
Activity/Project Name: | Line AM07 Pipeline Replacement Phase 5
Business Unit: | NGBU
Project Staff: | Major Projects
Activity/Project Scope or Description: |  | 1. 2023 Ecosys SOW: Phase 5 (of 5 Phases) includes the following: *Perform detailed engineering to support replacement of 23,710 feet (4.5 miles) of 24" pipe designed for a pressure of 1000 psig. *Install new 24" steel pipeline that starts where Phase 2 ends (dead end of Centre View Blvd [39° 1'19.33"N, 84°33'10.31"W]) and ends where Phase 3 starts (in the vicinity of coordinates [39° 1'33.74"N, 84°30'29.44"W]). *Abandon Line AM07 along this section. *Address remaining farm taps including elimination of UL26. *Preliminary proposed pipeline route that was field reviewed by Implemented
The intent of this questionnaire is to identify Duke Energy projects /activities that may qualify for the Duke R&D Credit Incentive Program.
Review activity/project and answer the following questions: |  |  | Answer (Yes, No, Unknown)
PERMITTED PURPOSE: Does the activity relate to a new/improved business component (Function, Performance, Reliability, Quality)? *A business component includes any product, process, computer software, technique, formula, or invention which is to be(A)held for sale, lease, or license, or (B)used by the taxpayer in a trade or business of the taxpayer.
TECHNOLOGICAL IN NATURE: Does the activity performed fundamentally rely on principles of Physical/Biological Science, Engineering, and Computer Science?
ELIMINATION OF UNCERTAINTY: Is the activity intended to discover information to eliminate uncertainty concerning the Capability, Method, and/or Design for developing/improving a business component?
PROCESS OF EXPERIMENTATION: Will the taxpayer engage in an evaluative process that is capable of identifying and evaluating one or more alternatives to achieve a result (this may include modeling, simulation, or systematic trial & error methodology)?

## AFUDC
| Projected | Cumulative | Cum. Charges | Monthly | Cumulative
Month | Charges | Charges | for AFUDC | AFUDC | AFUDC
2025-03-01 |  | 0 | 0 | 0 | 0 | 0% | 0% | 0%
2025-04-01 | 7029.81 | 7029.81 | 3514.905 | 20.5036 | 20.5036 | 3% | 0.03% | 0%
2025-05-01 | 9373.08 | 16402.89 | 11716.35 | 68.3454 | 88.849 | 4% | 0.04% | 0.01%
2025-06-01 | 11716.35 | 28119.24 | 22261.065 | 129.8562 | 218.7052 | 4.5% | 0.05% | 0.01%
2025-07-01 | 11716.35 | 39835.59 | 33977.415 | 198.2016 | 416.9068 | 3% | 0.05% | 0.01%
2025-08-01 | 11716.35 | 51551.94 | 45693.765 | 266.547 | 683.4538 | 3.75% | 0.05% | 0.02%
2025-09-01 | 119506.77 | 171058.71 | 111305.325 | 649.2811 | 1332.7348 | 4.25% | 0.51% | 0.02%
2025-10-01 | 276505.86 | 447564.57 | 309311.64 | 1804.3179 | 3137.0527 | 4% | 1.18% | 0.06%
2025-11-01 | 107790.42 | 555354.99 | 501459.78 | 2925.182 | 6062.2348 | 4.875% | 0.46% | 0.365%
2025-12-01 | 100760.61 | 656115.6 | 605735.295 | 3533.4559 | 9595.6907 | 15.25% | 0.43% | 0.275%
2026-01-01 | 156999.09 | 813114.69 | 734615.145 | 4285.255 | 13880.9457 | 18.5% | 0.67% | 0.61%
2026-02-01 | 86700.99 | 899815.68 | 856465.185 | 4996.0469 | 18876.9926 | 16% | 0.37% | 0.6%
2026-03-01 | 194491.41 | 1094307.09 | 997061.385 | 5816.1914 | 24693.184 | 10.5% | 0.83% | 3.5%
2026-04-01 | 126536.58 | 1220843.67 | 1157575.38 | 6752.523 | 31445.707 | 4.875% | 0.54% | 3.5%
2026-05-01 | 712354.08 | 1933197.75 | 1577020.71 | 9199.2875 | 40644.9945 | 1.5% | 3.04% | 2.5%
2026-06-01 | 639712.71 | 2572910.46 | 2253054.105 | 13142.8156 | 53787.8101 | 1.25% | 2.73% | 6.5%
2026-07-01 | 756876.21 | 3329786.67 | 2951348.565 | 17216.2 | 71004.0101 | 0.5% | 3.23% | 2%
2026-08-01 | 1054471.5 | 4384258.17 | 3857022.42 | 22499.2975 | 93503.3075 | 0.25% | 4.5% | 1%
2026-09-01 | 1241933.1 | 5626191.27 | 5005224.72 | 29197.1442 | 122700.4517 |  | 5.3% | 1.57%
2026-10-01 | 1089620.55 | 6715811.82 | 6171001.545 | 35997.509 | 158697.9607 |  | 4.65% | 0.35%
2026-11-01 | 1888675.62 | 8604487.44 | 7660149.63 | 44684.2062 | 203382.1669 |  | 8.06% | 0.54%
2026-12-01 | 2230793.04 | 10835280.48 | 9719883.96 | 56699.3231 | 260081.49 |  | 9.52% | 0.54%
2027-01-01 | 2354986.35 | 13190266.83 | 12012773.655 | 70074.513 | 330156.003 |  | 10.05% | 1.75%
2027-02-01 | 3025161.57 | 16215428.4 | 14702847.615 | 85766.6111 | 415922.6141 |  | 12.91% | 1.5%
2027-03-01 | 3299324.16 | 19514752.56 | 17865090.48 | 104213.0278 | 520135.6419 |  | 14.08% | 1.5%
2027-04-01 | 1996466.04 | 21511218.6 | 20512985.58 | 119659.0826 | 639794.7245 |  | 8.52% | 1.56%
2027-05-01 | 754532.94 | 22265751.54 | 21888485.07 | 127682.8296 | 767477.554 |  | 3.22% | 13%
2027-06-01 | 527235.75 | 22792987.29 | 22529369.415 | 131421.3216 | 898898.8756 |  | 2.25% | 13%
2027-07-01 | 323371.26 | 23116358.55 | 22954672.92 | 133902.2587 | 1032801.1343 |  | 1.38% | 10%
2027-08-01 | 53895.21 | 23170253.76 | 23143306.155 | 135002.6192 | 1167803.7536 |  | 0.23% | 8%
2027-09-01 | 28119.24 | 23198373 | 23184313.38 | 135241.8281 | 1303045.5816 |  | 0.12% | 8%
2027-10-01 | 234327 | 23432700 | 23315536.5 | 136007.2963 | 1439052.8779 |  | 1% | 6%
2027-11-01 | 0 | 23432700 | 23432700 | 136690.75 | 1575743.6279 |  |  | 7%
2027-12-01 | 0 | 23432700 | 23432700 | 136690.75 | 1712434.3779 |  |  | 2%
2028-01-01 | 0 | 23432700 | 23432700 | 136690.75 | 1849125.1279 |  |  | 1%
2028-02-01 | 0 | 23432700 | 23432700 | 136690.75 | 1985815.8779 |  |  | 0.5%
2028-03-01 | 0 | 23432700 | 23432700 | 136690.75 | 2122506.6279 |  |  | 0.05%
2028-04-01 | 0 | 23432700 | 23432700 | 136690.75 | 2259197.3779 |  |  | 0.05%
2028-05-01 | 0 | 23432700 | 23432700 | 136690.75 | 2395888.1279 |  |  | 0.03%
2028-06-01 | 0 | 23432700 | 23432700 | 136690.75 | 2532578.8779 |  |  | 0.03%
2028-07-01 | 0 | 23432700 | 23432700 | 136690.75 | 2669269.6279 |  |  | 0.01%
2028-08-01 | 0 | 23432700 | 23432700 | 136690.75 | 2805960.3779 |  |  | 0.01%
2028-09-01 | 0 | 23432700 | 23432700 | 136690.75 | 2942651.1279 |  |  | 0.01%
2028-10-01 | 0 | 23432700 | 23432700 | 136690.75 | 3079341.8779 |  |  | 0.01%
2028-11-01 | 0 | 23432700 | 23432700 | 136690.75 | 3216032.6279 |  |  | 0.01%
2028-12-01 | 0 | 23432700 | 23432700 | 136690.75 | 3352723.3779 |  |  | 1%
|  |  | 1 Year Proj AFUDC |  | 93503.3075
|  |  | 2 Year Proj AFUDC |  | 1439052.8779
|  |  | 3 Year Proj AFUDC |  | 3352723.3779
Formulas:
Month = DATE(YEAR([Month, row above]),MONTH([Month, row above])+1,DAY([Month, row above]))
Note on A6: Note: If this project has retirement components, omit all retirement related costs. AFUDC is applied only to capital (not capital retirement) projects.
Note on A22: For example, if this template will be used for an Advance, enter the date of the projected Planning Funding. If filling out template for a Fully Funded or last phase of phased project, leave blank.
Note on A23: A project number should be placed into closure when all of the assets (i.e. units of property) it covers are either “ready for service” or (more commonly) “placed in service”. The fact that a project number will accept charges for several additional months after it is placed into closure is irrelevant.
Note on D46: AFUDC compounding changes this month.