## First Sheet
Object Path ID | Resource Type Path ID | Start Date | End Date | Curve ID | Cost | Currency | Transaction Date | External Key
OPP-000XXX.CP1.NGCONFC |  | 2022-01-01 | 2025-05-31 | BEL | 0
OPP-000XXX.CP1.NGCONPC |  | 2022-01-01 | 2025-05-31 | BEL | 13313300
OPP-000XXX.CP1.NGCONT |  | 2022-01-01 | 2025-05-31 | BEL | 5456000
OPP-000XXX.CP1.NGENGNC |  | 2022-01-01 | 2025-05-31 | BEL | 1438400
OPP-000XXX.CP1.NGFITSC |  | 2022-01-01 | 2025-05-31 | BEL | 1492400
OPP-000XXX.CP1.NGLANDC |  | 2022-01-01 | 2025-05-31 | BEL | 4470000
OPP-000XXX.CP1.NGMAFD |  | 2022-01-01 | 2025-05-31 | BEL | 832500
OPP-000XXX.CP1.NGMATEC |  | 2022-01-01 | 2025-05-31 | BEL | 2160500
OPP-000XXX.CP1.NGMOTH |  | 2022-01-01 | 2025-05-31 | BEL | 60000
OPP-000XXX.CP1.NGMOVH |  | 2022-01-01 | 2025-05-31 | BEL | 2639900
OPP-000XXX.CP1.NGMPGL |  | 2022-01-01 | 2025-05-31 | BEL | 238000

## Check List
Estimate Document Checklist
Line AM07 PH 4
Class 5
2020-08-04 | Revision: |  | B
Document Type | Yes | No | Comment
Engineering
Design Basis Document
Input from System Planning
Was project Modeled by PNG
Were Engineering drawings provided
Project Location
Flow Rate
Pressure
In-service Date
Quantities
Land
Land price Estimate
Pricing
Current Equipment Pricing
Contractor Construction Quote
External Engineer's Estimate
Long Lead Material Analysis
Schedule
Project Schedule
Project Schedule Contingency
Long Lead Material Analysis
Other
Does the design route parallel existing facilities?
Does the design route parallel other ROW's
Are there Plant Safety Requirements
Military Base
OM
OM Estimate

## Typical%Check
Line AM07 PH 4 | [13 empty] | Indicative Percentages
2020-08-04 | [11 empty] | Revision: | B | Pipeline |  |  | Station |  |  | ILI Projects
Description | TOTAL PROJECT COST | Pipelay 1 | Pipelay 2 | Pipelay 3 | Station 1 | Station 2 | Station 3 | Station 4 | Station 5 | Demo 1 | Demo 2 | Demo 3 | Demo 4 | NC | TN | OH/KY | NC | TN | OH/KY | NC | TN | OH/KY
Engineering | 5.398% | 5.329% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 6.998% | #REF! | #REF! | #REF! | 6% | 5% | 7% | 13% | 10% | 7% | 13% | 10% | 7%
Land Purchase | 12.95% | 13.51% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF!
Land - Rights | 0.6755% | 0.705% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF!
Land - Support | 2.702% | 2.82% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF!
Land Legal | 0.4504% | 0.47% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF!
Land Services | 16.78% | 17.51% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | 12% | 15% | 7% | 8% | 8% | 8% | 8% | 8% | 8%
Materials/Equipment | 8.108% | 8.418% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0.9895% | #REF! | #REF! | #REF! | 13% | 6% | 6% | 29% | 24% | 19% | 29% | 24% | 19%
Construction Serv - Pipeline | 49.97% | 49.42% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 62.59% | #REF! | #REF! | #REF! | 48% | 54% | 55% | 0% | 0% | 0% | 0% | 0% | 0%
Construction Serv - Facility | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | 0% | 0% | 0% | 14% | 23% | 31% | 14% | 23% | 31%
Field Inspections | 5.601% | 5.436% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 9.391% | #REF! | #REF! | #REF! | 7% | 7% | 8% | 13% | 11% | 9% | 13% | 11% | 9%
PNG Labor | 0.8932% | 0.6815% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5.757% | #REF! | #REF! | #REF! | 2% | 2% | 1% | 4% | 4% | 4% | 4% | 4% | 4%
Other Direct Costs | 0.2252% | 0.1723% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1.439% | #REF! | #REF! | #REF! | 1% | 0% | 0% | 1% | 1% | 1% | 1% | 1% | 1%
AFUDC Debt | 3.124% | 3.26% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | #REF! | #REF! | #REF! | 4% | 4% | 5% | 6% | 5% | 4% | 6% | 5% | 4%
Overhead and Allocations | 9.908% | 9.78% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 12.84% | #REF! | #REF! | #REF! | 8% | 6% | 11% | 13% | 15% | 16% | 13% | 15% | 16%

## Master Tab
Input here will populate each tab with common information so that it does not need to be input on each tab.
Master Input Data
| Description | User Input | Notes
| Estimate Revision Number | B | Change number on each draft to be sent out
| Ecosys Oppurtunity Number | OPP-000XXX | Need to complete from Ecosys for Charter estimates.
| Project Name | Line AM07 PH 4
| Date: | 2020-08-04 | Update with each revision
| Customer | PNG
| Physical Location | Erlanger,Ky | City, State
| Project manager | PM
| Modeler | System Planning
| Lead Estimator | Kyle Gillow | Person who does the estimate
| Total Project Schedule | 40 | 1 Year Project - 17 months ¦ 2 Year Project - 31 months ¦ 3 Year Project - 40 months
| Engineering Project Schedule | 22 | 1 Year Project - 7 months ¦ 2 Year Project - 16 months ¦ 3 Year Project - 22 months
| Construction Project Schedule | 10 | 1 Year Project - 5 months ¦ 2 Year Project - 8 months ¦ 3 Year Project - 10 months
| Estimate Requested By | Requestor
| Rate Requested |  | firm, interruptible, etc.
| Hourly Flow (MCFH) |  | change unit of measure as needed
Delivery Pressure (PSIG)
| Resource Center | GD70
| Estimate Type | Class 5
| Length of Pipeline | 11690 | Enter the overall pipe line footage. | *For Charters, use a 5% routing factor if proposed route appears to be thought out & follows property boundaries. Use 14% if straight line/does not follow property boundaries.
| Add Sales tax ( PNG Materials Only) | 7.75% | Input Percentage - Will automatically apply to materials
| Pipe Size | 24
| Escalation (in Years) | 3 | Years until start date (not in-service date) (Put '0' if project is kicking off within 6 months)
| Escalation Rate (%) | 2.5% | Rate of Escalation (use '0' only for commit and build gates)
| Contingency (%) | 15% | Contingency %
| Start Date | 2022-01-01 | *Either start date from Ecosys or leave as 1/1/2022 for 2022 charters
| In-Service Date | 2025-05-01 | *This will auto-populate when total project schedule is completed | *For Charters, if the in-service date does not match this date then we need to let Renee's group know
| Completion Date | 2025-05-31 | *This will auto-populate when total project schedule is completed
| Ecosys In-Service Date | 2026-01-30 | *From Ecosys for Charters **IF HIGHLIGHTED RED THEN NOT FEASIBLE, CONTACT CHARTER GROUP** | *For Charters, if the in-service date does not match this date then we need to let Renee's group know
Estimate Steps
1 | Input information above - this transfers to headers on individual tabs
2 | Write Project description on the Review Format Tab (This can be updated as estimating progresses)
3 | Enter Pipe quantities on the Quantities Tab, enter quantities of HDD etc.
[5 empty] | .CP1. | NGCONFC
NGCONPC
NGCONT
NGENGNC
NGFITSC
NGLANDC
NGMAFD
NGMATEC
NGMOTH
NGMOVH
NGMPGL
Formulas:
User Input = [User Input, row above]+(30.4*C15)
User Input = [User Input, row above]+30

## Estimate Uncertainty Tool
| PMCoE |  | Estimate Uncertainty
Cell requires user entry
[7 empty] | Identify | Class 5
| Project Name: |  | Line AM07 PH 4 |  | Date: | 2020-08-04 | Initiate | Class 4
[7 empty] | Commit | Class 3
| Next Stage Gate: |  | Build |  | Minimum Class: | Class 3 | Build | Class 3
PMCoE Estimate Uncertainty Tool
| Informed Range |  |  | Best Case (Optimistic: O) | Estimate Value (Most Likely: ML) | Worst Case (Pessimistic: P)
| - % | + % | Cost Description
OK | -20% | 30% | Engineering | 1150720 | 1438400 | 1869920
OK | -20% | 30% | Land | 3576000 | 4470000 | 5811000
OK | -20% | 30% | Materials/Equipment | 1728400 | 2160500 | 2808650
OK | -20% | 30% | Construction Services | 10650640 | 13313300 | 17307290
OK | -20% | 30% | Field Inspections & Testing | 1193920 | 1492400 | 1940120
OK | -20% | 30% | PNG Labor | 190400 | 238000 | 309400
OK | -20% | 30% | Other | 48000 | 60000 | 78000
OK | -20% | 30% | AFUDC | 666000 | 832500 | 1082250
OK | -20% | 30% | Overhead & Allocations | 2111920 | 2639900 | 3431870
|  |  | Sub Total | 21316000 | 26645000 | 34638500 | O | 21316000
[7 empty] | ML*4 | 106580000
|  | 1.667% | A. Cummulative Risk EMV |  | 0 |  | P | 34638500
|  |  | B. Estimate Uncertainty PERT ((O+P+(ML*4))/6)-ML |  | 444083.3333 |  | Total | 162534500
|  |  | C. Contingency (A+B) |  | 444083.3333 |  | Divided by 6 | 27089083.3333
|  |  |  | 21316000 | 27089083.3333 | 34638500
|  |  |  | Best Case | Expected Case | Worst Case | ML | 26645000
|  |  | Project Informed Range | -21.31% |  | 27.87% | EU | 444083.3333
|  |  | Certainty* | P10 | P50 | P90
|  | * P10 and P90 are representitive values, but not statistically proven by this methodology. These values do not include any Risk EMV and are shown to allow the project to assess if their Project Informed Range is aligned with the AACEI Class of Estimate expectations. | [5 empty] | 27089083.3333
AACEI Estimate Class Reference:
|  | Class | Typical Methodology | Low Range | High Range
| Class 5 | 5 | Capacity Factored. Parametric Models. Judgement, or Analogy | -20% | 30%
| Class 5 |  |  | -50% | 100%
| Class 4 | 4 | Equipment Factored. Parametric Models. | -15% | 20%
| Class 4 |  |  | -30% | 50%
| Class 3 | 3 | Semi-Detailed Unit Costs with Assembly Level Line Items. | -10% | 10%
| Class 3 |  |  | -20% | 30%
| Class 2 | 2 | Detailed Unit Cost with Detailed Take-Off. | -5% | 5%
| Class 2 |  |  | -15% | 20%
| Class 1 | 1 | Detailed Unit Cost with Detailed Take-Off. | -3% | 3%
| Class 1 |  |  | -10% | 15%
Note on B12: PMCoE: The maximum allowable value in the -% Informed Range Column is 0%
Note on C12: PMCoE: The minimum allowable value in the +% Informed Range Column is 0%
Note on A13: PMCoE: Note that any items highlighted red require correction.
Note on A14: PMCoE: Note that any items highlighted red require correction.
Note on A15: PMCoE: Note that any items highlighted red require correction.
Note on A16: PMCoE: Note that any items highlighted red require correction.
Note on A17: PMCoE: Note that any items highlighted red require correction.
Note on A18: PMCoE: Note that any items highlighted red require correction.
Note on A19: PMCoE: Note that any items highlighted red require correction.
Note on A20: PMCoE: Note that any items highlighted red require correction.
Note on A21: PMCoE: Note that any items highlighted red require correction.
Note on F25: PMCoE: ML is subtracted from the PERT formula to show only the Estimate Uncertainty value.

## Finance Breakdown
Line AM07 PH 4
Funding Breakdown
2020-08-04
Description | Budget
Contract Labor | 19064100 | External Engineering, Construction Services, Field Inspection & Testing, Escalation
Material Purchased by PNG | 2160500 | Major Equipment and Testing
PNG Labor | 238000 | Internal Engineering and Construction Management
Land (Permanent Only) | 3450000 | Permanent Land purchases only
Other | 240000 | Land Rights (temporary land, land services, etc), Other Direct Costs - travel, meals, hotel, misc expenses
Sub-Total | 25152600
Contingency | 3476000 | Contingency
Sub-Total | 28628600
AFUDC | 0 | By Finance
Overheads | 0 | By Finance
Total | 28628600
Start Date | 2022-01-01 | By Project Manager
In-Service Date | 2025-05-01 | From Project Charter or Project Mgr.
Completion Date | 2026-01-30 | From Estimating
*ENSURE DISTRIBUTION COSTS HAVE BEEN REMOVED FROM ABOVE

## Assumptions
Line AM07 PH 4
Notes and Assumptions
2020-08-04
| Estimate Revision: | B
1.
2.
3.
4.
5.
6.
7.
8.
9.
10.

## Cost Change Log
This is to document the changes requested in the estimate from reviews.
Piedmont Natural Gas
Line AM07 PH 4
Estimate Change Log
[5 empty] | Revision: |  |  | B
Item | Revision | Date | Description | Price Before Change | Price After Change | Change Amount | Change Directed By: | Estimate Changed By:
1 | A | XX/XX/XX | Starting Estimate | 0 | 0 | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26

## Cost Report
Line AM07 PH 4
Erlanger,Ky
Project Cost Breakdown
Class 5
Revision: | B |  |  |  | 2020-08-04
|  | Capital Improvement and Retirement |  | Capital Improvement |  | Retirement
|  |  |  | Size / Name | 24''/Line AM07 | 24'' Line AM07
|  |  |  | Length / Qty | 14716LF | 13862
WBS 1 | Description |  |  | Total | Pipelay 1 | Pipe Abandonment
NGENGNC | Engineering | 1438400 |  | 1360600 | 1360600 | 77800
NGLANDC | Land Purchase | 3450000 |  | 3450000 | 3450000 | 0
NGLANDC | Land - Rights | 180000 |  | 180000 | 180000 | 0
NGLANDC | Land - Support | 720000 |  | 720000 | 720000 | 0
NGLANDC | Land Legal | 120000 |  | 120000 | 120000 | 0
NGMATEC | Materials/Equipment | 2160500 |  | 2149500 | 2149500 | 11000
NGCONPC | Construction Serv - Pipeline | 13313300 |  | 12617500 | 12617500 | 695800
NGCONFC | Construction Serv - Facility | 0 |  | 0 | 0 | 0
NGFITSC | Field Inspections | 1492400 |  | 1388000 | 1388000 | 104400
NGMPGL | PNG Labor | 238000 |  | 174000 | 174000 | 64000
NGMOTH | Other Direct Costs | 60000 |  | 44000 | 44000 | 16000
Subtotal Direct Cost |  | 23172600 |  | 22203600 | 22203600 | 969000
| Project Contingency | 3476000 |  | 3330600 | 3330600 | 145400
| Project Escalation | 1980000 |  | 1894700 | 1894700 | 85300
Total Contingency & Escalation |  | 5456000 |  | 5225300 | 5225300 | 230700
Total Direct Cost |  | 28628600 |  | 27428900 | 27428900 | 1199700
NGMPGL | AFUDC Debt | 832500 |  | 832500 | 832500 | 0 | AFUC | 0.0607
NGMOVH | Overhead and Allocations | 2639900 |  | 2497200 | 2497200 | 142700 | Overheads | 0.12
Total PNG Overhead Cost |  | 3472400 |  | 3329700 | 3329700 | 142700
Project Total |  | 32101000 |  | 30758600 | 30758600 | 1342400
Notes:
1. Contingency is not included on escalation.
2. Overheads and Allocations calculated using 12% of Total Direct Cost less Land Purchase, Materials/Equipment and FERC cost.
3. AFUDC calculated using 6.07% of total Direct Cost. (No AFUDC on Retirement Cost.)
4. Project Escalation is assumed for 3 Year at 2.5%.
| AFUDC | NC + Spartanburg | 7.51%
|  | SC - Spartanburg | 3.91%
|  | TN | 7.98%
|  | KY | 6.07%
|  | OH | 7.07%
|  | 3ST | 7.29%
|  | 2ST | 7.16%
| Overheads | NC | 9%
|  | SC | 10.33%
|  | TN | 6%
|  | OH/KY | 12%

## Pipeline 1
Line AM07 PH 4
2020-08-04 |  | 24 |  |  |  | Revision # | B
| Control Code | Component Description | Units | Unit of Measure | Unit Cost | Sub-totals | Totals | Instructions
| Internal Engineering & Construction Management | [6 empty] | Yellow tab w/ red font is a calculated value. No input required.
|  | PNG Labor | 40 | Month | 4350 | 174000 |  | *$4,350 for 1st Pipeline, $2,000 for each additional
|  | Other Direct Cost | 40 | Month | 1100 | 44000 |  | *$1,100 for 1st Pipeline, $500 for each additional
| Sub-Total - Internal E&CM | [5 empty] | 218000
External Engineering
|  | Design - Pipeline | 10772.72 | Hour | 125 | 1346590
|  | Design - Facility | 0 | Hour | 125 | 0
|  | MAOP | 1 | Lump Sum | 14000 | 14000 |  | *Per costs that Robin provided.
| Sub-Total - External Engineering | [5 empty] | 1360600
Land Services
|  | Transmission - Fee Simple Purchases | 11 | Acre | 150000 | 1650000
|  | Transmission - Permanent Easements (Rural) | 0 | Acre | 20000 | 0
|  | Transmission - Permanent Easements (Urban) | 36 | Acre | 50000 | 1800000
|  | Transmission - Stations Easements (Rural) | 0 | Acre | 30000 | 0
|  | Transmission - Stations Easements (Urban) | 0 | Acre | 30000 | 0
|  | Transmission - Temp Work Space (Rural) | 0 | Acre | 5000 | 0
|  | Transmission - Temp Work Space (Urban) | 0 | Acre | 12500 | 0
|  | Transmission - Access Roads | 0 | Each | 7500 | 0
|  | Transmission - Laydown Yard | 36 | Months | 5000 | 180000 |  | *Zero out if no laydown yard is required
|  | Land Services - Contractor | 60 | Per Parcel | 12000 | 720000
|  | Contract Labor - Legal | 6 | Per Parcel | 20000 | 120000 |  | *10% of parcels are assumed to go to condemnation
| Sub-Total - Land Services | [5 empty] | 4470000
| Construction Services - Pipeline |  | 11690 | Overall LF of Pipe installed
820 |  | Mob/Demob | 1 | Lump Sum | 1147045.3 | 1147045.3 |  | 10% | Use 5% to 10% for the construction services cost listed below. The larger the project, the lower the %; Always leave quantity as 1
821 | 821 | Clearing and Grubbing | 44 | acre | 37800 | 1663200 |  | *Only use for wooded or brush areas where trees are under 10'. Not needed for fields or already cleared land.
821 | 821 | Tree Cutting Only/No Grubbing | 0 | acre | 0 | 0 |  | *Only use for wooded/forested area where trees are over 10' high
829 | 829 | Conventional Upland Lay | 9910 | Linear Foot | 335 | 3319850
829 | 829 | Conventional Wetland Lay | 780 | Lump Sum | 385 | 300300
825 | 825 | Conventional Bore - Dirt | 0 | Linear Foot | 0 | 0
826 | 826 | Conventional Bore - Rock | 1000 | Linear Foot | 390 | 390000
827 | 827 | Directional Drill – Dirt | 0 | Linear Foot | 0 | 0 |  | *This is an adder to the conventional uplay cost and qty does not count toward overall pipe installed
828 | 828 | Directional Drill – Rock | 0 | Linear Foot | 0 | 0 |  | *This is an adder to the conventional uplay cost and qty does not count toward overall pipe installed
822 | 822 | Rock Excavation – Blasting | 0 | Cubic Yard | 0 | 0
822 | 822 | Rock Excavation – Mechanical | 6115 | Cubic Yard | 275 | 1681625
829 | 829 | Extra Depth Ditch | 0 | Per 1 ft depth/ LF | 0 | 0
829 | 829 | Padding – Job Site | 0 | Linear Foot | 0 | 0
829 | 829 | Padding - Haul | 0 | Linear Foot | 0 | 0
829 | 829 | Sand Padding over Existing Lines | 0 | Cubic Yard | 0 | 0
822 | 822 | Rock Shield | 0 | Linear Foot | 0 | 0
831 | 831 | Saddle Bag Weight | 0 | Each | 0 | 0 |  | * 2 per stream/creek open cut
831 | 831 | River Weight | 0 | Each | 0 | 0 |  | * At least 2 per river open cut
831 | 831 | Concrete Coating | 0 | Linear Foot | 0 | 0
837 | 837 | Zinc Ribbon | 11690 | Linear Foot | 16 | 187040
837 | 837 | Anode Bed | 1 | Each | 20400 | 20400
835 | 835 | Temporary Clean-up | 11690 | Linear Foot | 14 | 163660
833 | 833 | Hydro Test | 1 | Lump Sum | 300000 | 300000 |  | *Use LF cost but Minimum $15,000 for shop hydrotest / Minimum $25,000 for field hydrotest (labor/Water/pumps/water dispoal)
834 | 834 | Commissioning | 1 | Lump Sum | 75000 | 75000 |  | *Use LF cost but Minimum $6,000 (based upon a crew of 4, working 10 hours at ~100/hr + Nitrogen)
829 | 829 | Additional Hill Resources | 0 | Lump Sum | 0 | 0
828 | 828 | Scar Guard | 0 | Linear Foot | 0 | 0
630 | 630 | Silt Fence (metal post & wire backing) | 23380 | Linear Foot | 14 | 327320
630 | 630 | Conventional Silt Fence | 0 | Linear Foot | 0 | 0
630 | 630 | Curlex Blanket with Staples (4 x 100) | 0 | Square Yard | 0 | 0
630 | 630 | Hydroseeding Temporary Stabilization | 0 | SF | 0 | 0
630 | 630 | Hydroseeding Permanent Stabilization | 0 | SF | 0 | 0
630 | 630 | Rip Rap Placement | 0 | Ton | 0 | 0
630 | 630 | Gravel Placement | 300 | Ton | 67 | 20100
630 | 630 | Geo Textile Fabric | 0 | Square Yard | 0 | 0
630 | 630 | Safety Fence | 11690 | linear ft | 7 | 81830 |  | *Quote 60' per bore/drill pit and tie-in. Also include length to match MLV fence and L/R fence.
630 | 630 | Culvert Pipe (CMP) | 0 | Inch Diameter/LF | 0 | 0
630 | 630 | Sack Breakers | 0 | Each | 0 | 0
630 | 630 | Sediment Basin (excludes rock) | 0 | Each | 0 | 0
630 | 630 | Trench Breaker (Plug) | 0 | Each | 0 | 0
630 | 630 | Foam Breakers | 0 | Each | 0 | 0
630 | 630 | Construction (Timber) Mats (4'x18') | 215 | Each | 200 | 43000 |  | *Wetland Lay /4
630 | 630 | Laminated (Truck) Mats (8'x16') | 0 | Each | 0 | 0
630 | 630 | Bentonite Trench Seals in Wetlands | 0 | Each | 0 | 0
630 | 630 | Permanent Seeding (seed straw, and tack) | 1169000 | SF | 0.21 | 245490
630 | 630 | Intermediate Seeding (seed straw, and tack) | 1169000 | SF | 0.13 | 151970
630 | 630 | Dry Crossing (Flume or Dam/Pump Method) | 2 | Each | 38500 | 77000
630 | 630 | Sod | 0 | SF | 0 | 0
630 | 630 | 12" Sediment Log | 0 | Each | 0 | 0
630 | 630 | Erosion Eel | 0 | Each | 0 | 0
630 | 630 | Rock Filter Outlet | 0 | Each | 0 | 0
630 | 630 | Block and Gravel Basin Filter | 0 | Each | 0 | 0
630 | 630 | Permanent Wetland Seeding | 0 | SF | 0 | 0
831 | 831 | Well Points | 0 | Each | 0 | 0
832 | 832 | Air Bridges | 0 | Each | 0 | 0
832 | 832 | Chain Link Fence & Gates – New | 200 | Linear Foot | 64 | 12800
832 | 832 | Chain Link Fence & Gates - Repair | 0 | Linear Foot | 0 | 0
832 | 832 | Temporary Pasture Fencing | 0 | Linear Foot | 0 | 0
832 | 832 | Permanent Access Roads | 100 | Linear Foot | 150 | 15000
832 | 832 | Temporary Access Roads | 1200 | Linear Foot | 150 | 180000
832 | 832 | Top Soil | 0 | Ton | 0 | 0
832 | 832 | Asphalt Removal/Restoration | 52000 | Square Foot | 20 | 1040000
823 | 823 | Grouting of Abandoned Pipe | 0 | Cubic Yard | 0 | 0
824 | 824 | Removal of Existing Pipeline | 0 | Linear Foot | 0 | 0
832 | 832 | Farm Gate | 0 | Linear Foot | 0 | 0
|  | MLV Installation | 0 | Each | 0 | 0 |  | *One MLV is required per 8 miles (in congested Urban areas this will be 1 MLV every 5 miles)
|  | L/R Installation | 1 | Each | 225000 | 225000
|  | Staging & Laydown Yard | 12 | Acre | 65000 | 780000
|  | Civil or General Conditions | 0 | Lump Sum | 0 | 0
|  | HDD Mudd Disposal | 0 | Linear Foot | 0 | 0
|  | HDD Mudd Engineer | 0 | Per HDD | 20000 | 0 |  | *Note that this cost is per HDD. Long Rock Drills could increase this cost.
|  | Contractor Tap Support | 4 | Each | 31967 | 127868
|  | TDW Tap | 4 | Each | 10500 | 42000
|  | TDW Tap | 0 | Each | 0 | 0
12617500
Field Inspection & Testing
|  | Construction Inspection | 1201.6667 | Man-Days | 840 | 1009400
|  | Non-Destructive Testing | 189.2625 | Days | 2000 | 378525
| Sub-Total - Field Inspection & Testing | [5 empty] | 1388000
Major Equipment & Materials
Pipe
|  | 24 Standard Wall, X52, Coated, DRL | 11000 | Linear Foot | 109 | 1199000
|  | 24" Standard Wall, X52, Powercrete | 1000 | Linear Foot | 117 | 117000
|  | XX" Standard Wall, X52, Bare | 0 | Linear Foot | 0 | 0
Fittings
|  | 24" 3R - 45 deg ell - Segmentable | 15 | Each | 5000 | 75000
|  | 24" 3R - 90 deg ell - Segmentable | 16 | Each | 5575 | 89200
Equipment
|  | XX" TDW Stopple | 0 | Each | 0 | 0
|  | 24" TDW Spherical Tee | 4 | Each | 65000 | 260000
|  | 24" L/R Module | 1 | Each | 190444 | 190444
|  | XX" MLV Module | 0 | Each | 0 | 0
Miscellaneous
|  | Cathodic Protection Supplies | 11690 | Linear Foot | 2 | 23380
|  | Misc. Materials (10% of Total Major) | 1 | Calculated | 195402.4 | 195402.4
| Sub-Total - Materials | [5 empty] | 2149500
Sub-Total | [6 empty] | 22203600
Escalation |  |  | 3 | Year at | 2.5% |  | 1894700
Contingency |  |  |  |  | 15% |  | 3330600
Pipeline Estimate Total | [6 empty] | 27428900
[6 empty] | Cost per foot | 2346.3559
[6 empty] | Cost per mile | 12388758.9393

## Demo 1
Line AM07 PH 4
2020-08-04 |  | Retirement |  |  |  | Revision # | B
| Control Code | Component Description | Units | Unit of Measure | Unit Cost | Sub-totals | Totals | Instructions
| Internal Engineering & Construction Management | [6 empty] | Yellow tab w/ red font is a calculated value. No input required.
|  | PNG Labor | 40 | Month | 1600 | 64000
|  | Other Direct Cost | 40 | Month | 400 | 16000
| Sub-Total - Internal E&CM | [5 empty] | 80000
External Engineering
|  | Design - Pipeline | 621.984 | Hour | 125 | 77748
|  | Design - Facility | 0 | Hour | 125 | 0
|  | MAOP | 1 | Lump Sum | 0 | 0 |  | *Per costs that Robin provided.
| Sub-Total - External Engineering | [5 empty] | 77800
Land Services
|  | Transmission - Land Purchase | 0 | Acre | 50000 | 0
|  | Transmission - Pipeline Easements | 0 | Acre | 20000 | 0
|  | Transmission - Stations Easements | 0 | Acre | 30000 | 0
|  | Transmission - Temp Work Space | 0 | Acre | 5000 | 0
|  | Transmission - Access Roads | 0 | Each | 7500 | 0
|  | Transmission - Laydown Yard | 0 | Years | 60000 | 0
|  | Construction Support - Land | 0 | Per Parcel | 12000 | 0
|  | Contract Labor - Legal | 0 | Per Parcel | 20000 | 0
| Sub-Total - Land Services | [5 empty] | 0
| Construction Services - Pipeline |  | 0 | Overall LF of Pipe to be Abandoned
|  | Mob/Demob | 1 | Lump Sum | 63250 | 63250 |  | 10% | Use 5% to 10% for the construction services cost listed below. The larger the project, the lower the %; Always leave quantity as 1
|  | Demo Equipment | 5 | Days | 7500 | 37500
|  | Grouting | 0 | LF | 0 | 0
|  | Pipe Removal | 140 | LF | 2125 | 297500
|  | Dig Cut & Remove (Every 1000') | 14 | Each | 12500 | 175000
|  | Install & Remove Flare + Mob/Demob | 1 | Lump Sum | 50000 | 50000
|  | Launcher/Receiver Removal | 0 | Each | 75000 | 0
|  | Small Station Removal | 0 | Each | 35000 | 0
|  | Medium Station Removal | 0 | Each | 50000 | 0
|  | Large Station Removal | 0 | Each | 85000 | 0
|  | Haul Materials | 1 | Lump Sum | 10000 | 10000
|  | Nitrogen Clearing | 1 | Lump Sum | 50000 | 50000
|  | Line Locating | 1 | Week | 12500 | 12500
|  | Contractor Tap Support | 0 | Days | 0 | 0
|  | TDW Tap | 0 | Each | 0 | 0
695800
Field Inspection & Testing
|  | Construction Inspection | 124.25 | Man-Days | 840 | 104370
|  | Non-Destructive Testing | 0 | Days | 2000 | 0
| Sub-Total - Field Inspection & Testing | [5 empty] | 104400
Major Equipment & Materials
|  | Purge Materials | 1 | Lump Sum | 10000 | 10000
|  | Stopple | 0 | Each | 0 | 0
|  | Stopple | 0 | Each | 0 | 0
|  | Misc. Materials (10% of Total Major) | 1 | Calculated | 1000 | 1000
| Sub-Total - Materials | [5 empty] | 11000
Sub-Total | [6 empty] | 969000
Escalation |  |  | 3 | Year at | 2.5% |  | 85300
Contingency |  |  |  |  | 15% |  | 145400
Pipeline Estimate Total | [6 empty] | 1199700