## Test Year
Schedule D (Historical Test Year)
Kentucky Power Company
Case No. 2025-00257
Construction Projects for the Historical Test Year
June 2024 - May 2025
Definitions:
| (C)* | Represents the month project expenditures were initially recorded to CWIP (Account 107).
| (H)* | Represents Total Cost (G) per Schedule D.
| (J)* | 2023-03-31
| Blanket | Repetitive and predictable project charged and closed continuously throughout the calendar year.
| Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
| Other | Other amounts reflected in budget; do not directly relate to a project with actual spend during the period.
| Preliminary | Requires assessments and pre-engineering activities for developing detail scopes and estimates. Costs are transferred to new a project once enough data is available for project creation.
| n.m. | Not meaningful.
[5 empty] | 110 & 180 - Control | 110 & 180 - Forecast
Actual Accumulated Costs - June 2024 through May 2025
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time through May 31, 2025 (J)* | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures June 2024 through May 2025 | GLBU-Project
(A) | (B) | (C)* | (D) | (E) = ((J)- (C)) / ((D) -(C)) | (F) | (G) | (H)* | (I) = (G)/(H)
1 | GLBU 110 (Distribution)
2 | 000001818 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 9490496.376 | 5733590.512 | 5657283.69 | 101.3%
3 | 000002241 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 358718.925 | 341653.849 | 388301.99 | 87.99%
4 | 000004737 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 637377.78 | 472362.16 | 1111934.64 | 42.48%
5 | 000005234 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 3106479.94 | 0%
6 | 000007558 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 30633.778 | 26856.423 | 18490.42 | 145.2%
7 | 000007599 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 4901893.111 | 3560506.564 | 4076115.28 | 87.35%
8 | 000007615 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 191842.195 | 123109.092 | 76160.66 | 161.6%
9 | 000007818 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 3413956.792 | 3126035.608 | 3670045.3 | 85.18%
10 | 000008169 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 944462.324 | 911308.399 | 145051.75 | 628.3%
11 | 000008184 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 1211109.919 | 1138373.015 | 270712.95 | 420.5%
12 | 000016528 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 431178.264 | 402561.255 | 309599.03 | 130%
13 | 000025229 | 1/1/2018 | Blanket | Blanket | 112639.605 | 557689.973 | 780314.92 | 71.47%
14 | 110KYLSBO | 2022-06-01 | 2022-06-30 | 1045% | 0 | 0 | 43332.16 | 0%
15 | A15710085 | 7/1/2019 | 2021-09-17 | 169.2% | 0 | 26839.102 | 5623.59 | 477.3%
16 | A15710086 | 7/1/2019 | 2021-09-17 | 169.2% | 0 | 0 | 5825.85 | 0%
17 | A20045031 | 2020-05-01 | 2021-12-31 | 174.7% | 0 | 0 | 403.71 | 0%
18 | A20045075 | 2020-09-01 | 2021-12-31 | 193.6% | 0 | 0 | 276.74 | 0%
19 | A20045086 | 2020-11-01 | 2021-12-31 | 207.1% | 0 | 0 | 79.32 | 0%
20 | A20045087 | 2020-11-01 | 2021-12-31 | 207.1% | 0 | 0 | 308.86 | 0%
21 | A20077007 | 2021-01-01 | 2023-11-30 | 77.05% | 7612.735 | 6760.012 | 197.04 | 3431%
22 | A20077008 | 2020-12-01 | 2023-11-30 | 77.7% | 6144.784 | 5497.736 | 145.25 | 3785%
23 | A20077010 | 2020-09-01 | 2023-11-30 | 79.41% | 6578.789 | 6045.979 | 184.54 | 3276%
24 | A20077011 | 2021-06-01 | 2023-11-30 | 73.25% | 8835.533 | 7974.449 | 125.57 | 6351%
25 | A20077013 | 2021-01-01 | 2023-11-30 | 77.05% | 7407.916 | 6156.777 | 128.48 | 4792%
26 | A20077017 | 2020-09-01 | 2023-11-30 | 79.41% | 7659.123 | 7080.007 | 238.14 | 2973%
27 | A20077018 | 2021-01-01 | 2023-11-30 | 77.05% | 8685.395 | 7402.63 | 161.75 | 4577%
28 | A20077019 | 2020-09-01 | 2023-11-30 | 79.41% | 216.4 | 0 | 276.29 | 0%
29 | A20077022 | 2021-01-01 | 2023-11-30 | 77.05% | 795.12 | 0 | 144.2 | 0%
30 | A20705068 | 9/1/2019 | 2020-06-15 | 453.8% | 0 | 0 | -11590.7 | 0%
31 | A20705085 | 11/1/2019 | 2020-06-18 | 541.7% | 0 | 0 | 435.15 | 0%
32 | A20934001 | 2021-03-01 | 2021-09-01 | 413% | 28201.209 | 26785.15 | 703720.91 | 3.806%
33 | A21222009 | 2020-08-01 | 2022-10-30 | 118.5% | 0 | 0 | 23910.21 | 0%
34 | A21222015 | 2020-08-01 | 2022-10-30 | 118.5% | 0 | 0 | 3179.69 | 0%
35 | A21505006 | 2021-04-01 | 2021-12-31 | 266.1% | 0 | 0 | 510.04 | 0%
36 | A21505009 | 2021-08-01 | 2025-12-31 | 37.63% | 129 | 0 | 137.36 | 0%
37 | A23067001 | 2024-09-01 | 2025-06-30 | -172.2% | 0 | -97901.361 | 427139.5 | -22.92%
38 | A23088001 | 2023-12-01 | 2024-06-30 | -115.6% | 0 | 0 | -40449.29 | 0%
39 | A23750004 | 2024-03-01 | 2025-06-01 | -73.52% | 0 | 0 | 361347.35 | 0%
40 | A23928006 | 2025-04-01 | 2026-06-30 | -160.9% | 0 | 0 | 62845.14 | 0%
41 | A24022009 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 4867.22 | 0%
42 | A24038004 | 2025-05-01 | 2027-05-30 | -100.4% | 2432.95 | 2258.224 | 4282.06 | 52.74%
43 | A24083001 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 982.85 | 0%
44 | A24083003 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 468.01 | 0%
45 | A24083004 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 982.85 | 0%
46 | A24083006 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 280.82 | 0%
47 | A24112002 | 2021-08-01 | 2024-11-30 | 49.88% | 4577.457 | 3507.704 | -4219.65 | -83.13%
48 | A24112010 | 2021-06-01 | 2024-11-30 | 52.27% | 880.189 | -2855.779 | 25.94 | -11009%
49 | A24112012 | 2021-08-01 | 2024-11-30 | 49.88% | 1003.499 | -2855.779 | -3719.27 | 76.78%
50 | A25101001 | 2022-02-01 | 2025-11-30 | 30.26% | 286.79 | 0 | 128.28 | 0%
51 | A25101002 | 2022-03-01 | 2025-11-30 | 28.83% | 44 | 0 | 166.7 | 0%
52 | A25101003 | 2022-02-01 | 2025-11-30 | 30.26% | 48 | 0 | 50.94 | 0%
53 | A25101005 | 2022-02-01 | 2025-11-30 | 30.26% | 19 | 0 | 17.06 | 0%
54 | A25101006 | 2022-03-01 | 2025-11-30 | 28.83% | 44 | 0 | 41.26 | 0%
55 | A26112003 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 39.69 | 0%
56 | A26112006 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 39.69 | 0%
57 | B110KYPAC | 2024-07-01 | Blanket | Blanket | 0 | 0 | 83449.99 | 0%
58 | B110KYRMB | 2025-05-01 | Blanket | Blanket | 0 | 0 | 3727.82 | 0%
59 | B110KYSRR | 11/1/2016 | Blanket | Blanket | 444603.478 | 419334.144 | 1651316.81 | 25.39%
60 | B110KYTEL | 2024-03-01 | Blanket | Blanket | 8311.762 | 7840.205 | 97649.88 | 8.029%
61 | C24097002 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
62 | C24097004 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
63 | C24097005 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
64 | C24097006 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
65 | C24097007 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
66 | C24097008 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
67 | C24097009 | 2025-05-01 | 2026-12-01 | -131.6% | 0 | 0 | 120.72 | 0%
68 | DCTSUVLKY | Charges Began Prior to Jan 2015 | Blanket | Blanket | 8612.81 | 0 | 3316789.65 | 0%
69 | DMS24KK04 | 2024-04-01 | 2024-12-31 | -133.9% | 15.33 | 0 | -168131.04 | 0%
70 | DMS24KK05 | 2024-04-01 | 2024-12-31 | -133.9% | 0 | 0 | 2111.94 | 0%
71 | DMS24KK07 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | -16508.95 | 0%
72 | DMS24KK08 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | -94703.12 | 0%
73 | DMS24KK09 | 2024-06-01 | 2024-12-31 | -200.9% | 0 | 0 | 32805.95 | 0%
74 | DMS24KK10 | 2024-07-01 | 2024-12-31 | -250.3% | 0 | 0 | 16983.15 | 0%
75 | DMS24KK11 | 2024-08-01 | 2024-12-31 | -321.7% | 0 | 0 | 63033.93 | 0%
76 | DMS24KK12 | 2024-09-01 | 2024-12-31 | -429.8% | 6894.89 | 0 | 3267786.08 | 0%
77 | DMS24KK13 | 2024-12-01 | 2024-12-31 | -2037% | 0 | 0 | 140390.18 | 0%
78 | DMS24KK14 | 2025-01-01 | 2024-12-31 | 64200% | 0 | 0 | 48071.45 | 0%
79 | DMS25KK01 | 2025-01-01 | 2025-12-31 | -176.4% | 0 | 0 | 1919553.06 | 0%
80 | DMS25KK02 | 2025-02-01 | 2025-12-31 | -202.1% | 0 | 0 | 132243.97 | 0%
81 | DMS25KK03 | 2025-03-01 | 2025-12-31 | -229.8% | 0 | 0 | 2798195.24 | 0%
82 | DMS25KK05 | 2025-04-01 | 2025-12-31 | -267.2% | 0 | 0 | 311873.95 | 0%
83 | DMS25KK06 | 2025-05-01 | 2025-12-31 | -312.3% | 0 | 0 | 247294.45 | 0%
84 | DMS25KK07 | 2025-05-01 | 2025-12-31 | -312.3% | 0 | 0 | 69748.8 | 0%
85 | DMS25KK08 | 2025-05-01 | 2025-12-31 | -312.3% | 0 | 0 | 1421942.19 | 0%
86 | DMS25KK09 | 2025-05-01 | 2025-12-31 | -312.3% | 0 | 0 | 81190.22 | 0%
87 | DP16K03A0 | 2023-01-01 | 2024-06-30 | 16.3% | 2931.33 | 1713608.271 | 494356.72 | 346.6%
88 | DP16K03B0 | 10/1/2019 | 2021-01-06 | 275.8% | 0 | 0 | 344806.64 | 0%
89 | DR18K02A0 | 3/1/2019 | 2019-12-02 | 540.2% | 328.32 | 0 | 14159.75 | 0%
90 | DR19K05A0 | 5/1/2019 | 2020-10-12 | 269.8% | 960.9 | 0 | 52474.21 | 0%
91 | DR19K05B0 | 6/1/2019 | 2020-10-12 | 280.4% | 2254.63 | 0 | -48353.69 | 0%
92 | DR19K05B1 | 6/1/2019 | 2020-11-11 | 264.5% | 0 | 0 | -51562.59 | 0%
93 | DR19K05B2 | 6/1/2019 | 2020-05-28 | 386.5% | 0 | 0 | -211141.98 | 0%
94 | DX21K0002 | 2021-10-01 | 2022-11-01 | 137.9% | 0 | 0 | 130.01 | 0%
95 | DX21K0003 | 2021-10-01 | 2022-11-01 | 137.9% | 396.68 | 0 | 23218.82 | 0%
96 | DX23K01A0 | 2023-11-01 | Blanket | Blanket | 23.36 | 0 | 1614.78 | 0%
97 | EDN011333 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 728363.317 | 565966.192 | 448711.17 | 126.1%
98 | EDN012370 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 1020403.033 | 1206064.978 | 1190458.89 | 101.3%
99 | EDN014651 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 3932751.717 | 3819253.481 | 4186539.73 | 91.23%
100 | EDN014658 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 291282.337 | 284862.954 | 278245.44 | 102.4%
101 | EDN014680 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 3434478.876 | 5148462.843 | 2827964.4 | 182.1%
102 | EDN014687 | Charges Began Prior to Jan 2015 | Blanket | Blanket | -42476.026 | -40395.088 | 9270.48 | -435.7%
103 | EDN014694 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 919694.337 | 918660.897 | 555319.22 | 165.4%
104 | EDN014701 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 9182.82 | 0%
105 | EDN014720 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 4491302.261 | 3820945.872 | 3388534.3 | 112.8%
106 | EDN015042 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 447011.755 | 411905.334 | 48002.84 | 858.1%
107 | EDN100033 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 2220449.408 | 1993108.924 | 2191889.5 | 90.93%
108 | EDN100044 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 83598.051 | 66216.378 | 107970.83 | 61.33%
109 | EDN100577 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 760682.255 | 675582.675 | 202127.65 | 334.2%
110 | EDN103175 | Charges Began Prior to Jan 2015 | Blanket | Blanket | -1003967.783 | 0.025 | -9978.74 | -0.0002505%
111 | EON011326 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 3934356.236 | 3413885.265 | 6638812.82 | 51.42%
112 | ETN000110 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 0 | #DIV/0!
113 | IT1101723 | 2020-12-01 | Blanket | Blanket | 0 | 0 | -650.1 | 0%
114 | IT1101724 | 2020-12-01 | Blanket | Blanket | 0 | 0 | -56955.57 | 0%
115 | IT1101725 | 2020-11-01 | Blanket | Blanket | 0 | 0 | 165317.12 | 0%
116 | IT1102013 | 2023-08-01 | 2023-12-31 | -80.92% | 117.27 | 0 | 259369.48 | 0%
117 | IT1102049 | 2023-10-01 | 2028-07-01 | -10.61% | 0 | 0 | 1331.53 | 0%
118 | IT110ADMS | 2023-06-01 | 2026-03-31 | -5.996% | 4878.53 | 0 | 1206901.26 | 0%
119 | IT110CCIC | 2020-01-01 | 2030-12-31 | 29.5% | 0 | 0 | 597108.21 | 0%
120 | ITCB11000 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 238330.36 | 0%
121 | ITCF11000 | 2023-08-01 | 2023-12-31 | -80.92% | 110813.475 | 403986.429 | 360947.5 | 111.9%
122 | ITCT11004 | 2021-11-01 | Blanket | Blanket | -10015.196 | -9448.098 | 689448.46 | -1.37%
123 | ITCW11004 | 4/1/2017 | 2021-12-31 | 126.2% | -181040.72 | 2327559.003 | 1470416.27 | 158.3%
124 | ITPCLC110 | 2023-04-01 | 2025-12-31 | -0.0995% | 242047.01 | 189923.307 | 74147.53 | 256.1%
125 | KEPDS2201 | 2022-07-01 | 2022-12-31 | 149.2% | 835180.099 | -156479.756 | 510.99 | -30623%
126 | KEPDS2202 | 2023-01-01 | 2022-12-31 | -8900% | 0 | 0 | 146.67 | 0%
127 | KEPDS2501 | 2023-05-01 | 2025-12-31 | -3.179% | 0 | 0 | 65093.12 | 0%
128 | KEPDS2502 | 2025-04-01 | 2025-12-31 | -267.2% | 0 | 0 | 353697.49 | 0%
129 | KY5YCYCLE | 1/1/2019 | Blanket | Blanket | 3049379.953 | 1840508.233 | 1662849.2 | 110.7%
130 | KYCAPTOOL | 3/1/2019 | Blanket | Blanket | 15094.448 | 13262.484 | 373771.19 | 3.548%
131 | P14030009 | 11/1/2016 | 2024-12-20 | 78.8% | 25667.095 | 23850.367 | 157274.92 | 15.16%
132 | P17076002 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | -241341.03 | 0%
133 | P17076003 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | -101963.44 | 0%
134 | P17076011 | 4/1/2018 | 2020-12-01 | 187.2% | 0 | 0 | -7606.22 | 0%
135 | P17083016 | 3/1/2019 | 2024-11-15 | 71.48% | 1716864.118 | -245504.676 | 133544.16 | -183.8%
136 | P17083025 | 3/1/2019 | 2024-11-15 | 71.48% | 169230.139 | 144661.037 | 375670.08 | 38.51%
137 | P17083030 | 4/1/2019 | 2024-11-15 | 71.05% | 1220466.278 | 1074899.769 | 1201345.4 | 89.47%
138 | P17083033 | 2020-01-01 | 2024-11-15 | 66.57% | 2586.824 | 2393.466 | -2040.74 | -117.3%
139 | P17083040 | 2021-10-01 | 2024-11-15 | 47.85% | 541808.739 | -837952.2 | 4283702.97 | -19.56%
140 | P17084005 | 11/1/2017 | 2024-05-15 | 82.78% | 217655.634 | 183647.283 | 76563.55 | 239.9%
141 | P17084006 | 2021-07-01 | 2024-05-15 | 60.82% | 18179.96 | 0 | 5850.96 | 0%
142 | P17084025 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 7261.15 | 0%
143 | P17084055 | 2022-10-01 | 2028-07-25 | 8.522% | 433.14 | 0 | 59099.91 | 0%
144 | P18025001 | 3/1/2018 | 2019-12-09 | 286.4% | 7476.518 | 519242.095 | 193996.05 | 267.7%
145 | P18025002 | 3/1/2018 | 2019-12-09 | 286.4% | 0 | 0 | 6756.36 | 0%
146 | P18025018 | 2021-05-01 | 2022-11-18 | 123.5% | 0 | 0 | 125126.3 | 0%
147 | P18221011 | 5/1/2019 | 2022-11-04 | 111.5% | 0 | 0 | 2107.59 | 0%
148 | P19036002 | 2020-09-01 | 2022-11-11 | 117.5% | 0 | 0 | 16701.84 | 0%
149 | P19036005 | 2020-07-01 | 2022-11-11 | 116.2% | 0 | 0 | 294376.53 | 0%
150 | P19036012 | 2021-08-01 | 2022-11-11 | 130% | 0 | 0 | 166575.84 | 0%
151 | P19037003 | 2021-12-01 | 2024-11-01 | 45.5% | -348278.391 | -268257.201 | 67552.42 | -397.1%
152 | P19037008 | 2023-04-01 | 2027-11-01 | -0.0597% | -319331.931 | -307393.269 | 171386.3 | -179.4%
153 | P19037016 | 2021-10-01 | 2026-09-24 | 30.02% | -14714.577 | -25556.083 | 98570.21 | -25.93%
154 | P19037017 | 2022-02-01 | 2026-09-24 | 24.94% | -78380.422 | -24210.486 | 340261.26 | -7.115%
155 | P19037031 | 2024-07-01 | 2027-03-24 | -45.98% | 582.5 | 0 | 27477.58 | 0%
156 | P19037032 | 2024-08-01 | 2027-03-24 | -50.67% | 25 | 0 | 1950.45 | 0%
157 | P19092002 | 9/1/2019 | 2023-10-02 | 87.6% | 40916.469 | 83.822 | 38716.31 | 0.2165%
158 | P19092014 | 5/1/2019 | 2023-10-18 | 87.68% | 9336.01 | 0 | 23396.93 | 0%
159 | P19092016 | 5/1/2019 | 2023-10-18 | 87.68% | 93203.539 | 79075.102 | 30160.84 | 262.2%
160 | P19092022 | 2020-09-01 | 2023-10-18 | 82.4% | 5231.432 | 3063.291 | 4798.16 | 63.84%
161 | P19092023 | 2021-04-01 | 2023-10-18 | 78.39% | 220087.761 | 28005.544 | 221037.13 | 12.67%
162 | P19305013 | 2020-06-01 | 2025-05-22 | 56.88% | 544021.385 | -803654.76 | 1730807.42 | -46.43%
163 | P19305022 | 2020-08-01 | 2024-11-22 | 61.75% | 69725.376 | 22604.515 | 568848.09 | 3.974%
164 | P20035005 | 2020-12-01 | 2023-09-01 | 84.66% | 424.9 | 0 | 1560.26 | 0%
165 | P20035008 | 2020-05-01 | 2023-09-01 | 87.36% | -15981.588 | -15881.831 | 2804.27 | -566.3%
166 | P21043005 | 2023-02-01 | 2025-10-01 | 5.961% | -234515.959 | -225399.304 | 306332.69 | -73.58%
167 | P21043006 | 2021-04-01 | 2025-10-01 | 44.34% | 120790.232 | 183670.804 | 657359.52 | 27.94%
168 | P21720003 | 2022-07-01 | 2025-09-01 | 23.58% | 33990.775 | 29988.485 | 10222.85 | 293.3%
169 | P21720007 | 2023-03-01 | 2025-09-01 | 3.279% | 172345.923 | 190984.327 | 6383.18 | 2992%
170 | P21753003 | 2022-05-01 | 2025-06-01 | 29.64% | -94167.187 | -95531.386 | 15811.14 | -604.2%
171 | P22005001 | 2022-02-01 | 2025-11-06 | 30.79% | 212013.165 | 182840.067 | 551482.99 | 33.15%
172 | P22012001 | 2022-04-01 | 2028-06-01 | 16.16% | 943.15 | 0 | 1937.87 | 0%
173 | P22012002 | 2022-04-01 | 2028-06-01 | 16.16% | 2795.09 | 0 | 1626.79 | 0%
174 | P22113002 | 2023-07-01 | 2025-06-11 | -12.94% | 5085.251 | 4714.441 | 490895.28 | 0.9604%
175 | P24083002 | 2024-10-01 | 2031-05-01 | -22.89% | 6.64 | 0 | 6138.54 | 0%
176 | P24125002 | 2024-12-01 | 2029-11-01 | -34.02% | 0 | 0 | 8154 | 0%
177 | P24125003 | 2025-01-01 | 2029-11-01 | -36.37% | 0 | 0 | 15255.54 | 0%
178 | P24125004 | 2025-05-01 | 2029-11-01 | -46.32% | 0 | 0 | 1701.38 | 0%
179 | TP1403006 | 2022-10-01 | 2024-12-20 | 22.32% | 19520 | 9224.677 | 689121.44 | 1.339%
180 | TP1708310 | 2022-07-01 | 2023-12-22 | 50.65% | 243784.736 | 229872.882 | 11124.51 | 2066%
181 | TP1802510 | 2022-03-01 | 2019-06-01 | -39.34% | 0 | 395646.021 | 1089668.65 | 36.31%
182 | TP1822105 | 2022-02-01 | 2022-09-01 | 199.5% | 0 | 0 | 110421.04 | 0%
183 | TP1903604 | 2022-03-01 | 2022-11-11 | 154.9% | 0 | 0 | 244897.08 | 0%
184 | TP1930505 | 2024-04-01 | 2025-10-10 | -65.89% | 22024.03 | 0 | 1236458.54 | 0%
185 | TREEREL21 | 2021-01-01 | Blanket | Blanket | 3.072 | 3.049 | 664.4 | 0.4589%
186 | TREEREL23 | 2023-03-01 | Blanket | Blanket | 3573730.768 | 0 | -35421.61 | 0%
187 | TREEREL24 | 2024-01-01 | Blanket | Blanket | 5299.7 | 3051852.875 | 3529259.37 | 86.47%
188 | TREEREL25 | 2025-01-01 | Blanket | Blanket | 3079948.665 | 2876334.506 | 3709344.5 | 77.54%
189 | XHWCAP110 | 2024-02-01 | 2025-12-31 | -43.92% | 284.44 | 0 | 335243.16 | 0%
190 | Other Budgeted Projects | Other | Other | Other | 13509126.62 | 28077014.025 | 0 | Other
191 | Total GLBU 110 (Distribution) | 0 | 6514506 | 578.2082 | 72375874.11 | 79895687.907 | 89862169.9
192 | GLBU 117 (Generation) | 0
193 | 000005237 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 0 | 0 | 483424.81 | 0% | 117-000005237 | Used Control measure for Original and Forecast for Most Recent
194 | 000025231 | 3/1/2018 | (blank) | n.m. | 12.63 | 0 | 7349.91 | 0% | 117-000025231 | Budget Estimates only for referenced time period
195 | BSPPB0002 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 323809.04 | 308158.934 | 47574.89 | 647.7% | 117-BSPPB0002
196 | BSPPB0007 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 217.68 | 0 | 138165.45 | 0% | 117-BSPPB0007
197 | BSPPB0008 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 228.03 | 0 | 35028.35 | 0% | 117-BSPPB0008
198 | BSPPB0011 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 120.29 | 0 | 67287.39 | 0% | 117-BSPPB0011
199 | BSPPB0013 | Charges Began Prior to Jan 2015 | 2018-12-31 | n.m. | 336302.547 | 832845.96 | 1158052.85 | 71.92% | 117-BSPPB0013
200 | BSPPBENEW | Charges Began Prior to Jan 2015 | (blank) | n.m. | 246.25 | 0 | 247589.97 | 0% | 117-BSPPBENEW
201 | BSPPBOUT1 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 845917.808 | 956559.622 | 634689.19 | 150.7% | 117-BSPPBOUT1
202 | BSPPBS347 | 2018-11-01 | 2018-12-21 | 3222% | 565.12 | 183248.525 | 414957.95 | 44.16% | 117-BSPPBS347
203 | BSPPBS368 | 2023-08-01 | 2024-12-31 | -23.75% | 4265647.78 | 5810643.636 | 8135599.44 | 71.42% | 117-BSPPBS368
204 | BSPPBWGRN | 2025-05-01 | 2026-02-01 | -276.1% | 1170678.818 | 1148697.852 | 1278.32 | 89860% | 117-BSPPBWGRN
205 | IT117CCIC | 2020-01-01 | 2030-12-31 | 29.5% | 0 | 0 | 106531.99 | 0% | 117-IT117CCIC
206 | ITCB11700 | Charges Began Prior to Jan 2015 | 2022-12-31 | n.m. | 0 | 5237.414 | 4676.65 | 112% | 117-ITCB11700
207 | ITCBLBRTY | 2022-09-01 | 2022-12-31 | 174.4% | 0 | 0 | 1241.46 | 0% | 117-ITCBLBRTY
208 | ITPCLC117 | 2023-05-01 | 2025-12-31 | -3.179% | 13110.401 | 12494.993 | 4542.91 | 275% | 117-ITPCLC117
209 | ML1E25C02 | 2023-04-01 | 2023-11-27 | -0.4167% | 0 | 0 | 10847.36 | 0% | 117-ML1E25C02
210 | MLKP26265 | 2023-03-01 | 2026-12-31 | 2.141% | 2095605.829 | 1859019.84 | 2390343.87 | 77.77% | 117-MLKP26265
211 | MLKYELGFL | 2025-04-01 | 2025-06-30 | -813.3% | 0 | 0 | 117846.22 | 0% | 117-MLKYELGFL
212 | MLL1CGRPL | 2023-12-01 | 2024-05-31 | -134.6% | 209458.753 | 202987.471 | 180868.78 | 112.2% | 117-MLL1CGRPL
213 | MLL2CGRPL | 2023-12-01 | 2024-05-31 | -134.6% | 276.37 | 0 | 80075.8 | 0% | 117-MLL2CGRPL
214 | MLLEC1VHL | 2023-05-01 | 2023-11-30 | -14.55% | 0 | 0 | 9.25 | 0% | 117-MLLEC1VHL
215 | MLLEP2LA0 | 2024-09-01 | 2026-06-01 | -81.5% | 166.05 | 0 | 275693.84 | 0% | 117-MLLEP2LA0
216 | MLLEP2LA1 | 2024-09-01 | 2026-06-01 | -81.5% | 53.13 | 0 | 89424.99 | 0% | 117-MLLEP2LA1
217 | MLLEP2LB0 | 2024-09-01 | 2026-06-01 | -81.5% | 166.05 | 0 | 275693.84 | 0% | 117-MLLEP2LB0
218 | MLLEP2LB1 | 2024-09-01 | 2026-06-01 | -81.5% | 53.13 | 0 | 89424.99 | 0% | 117-MLLEP2LB1
219 | MLLHAULRD | 2023-12-01 | 2023-12-31 | -816.7% | 567186.399 | 645880.152 | 922405.75 | 70.02% | 117-MLLHAULRD
220 | MLLPC0ELG | 2022-09-01 | 2024-12-31 | 24.77% | 2906687.993 | 3414944.798 | 2295473.46 | 148.8% | 117-MLLPC0ELG
221 | MLLPC0LIM | 2022-09-01 | 2023-12-31 | 43.42% | 0 | 0 | 153.62 | 0% | 117-MLLPC0LIM
222 | MLLPC2ESP | 2022-09-01 | 2022-12-31 | 174.4% | 0 | 0 | -3500.45 | 0% | 117-MLLPC2ESP
223 | MLLPCT1BP | 2024-02-01 | 2024-06-10 | -236.2% | 0 | -69142.593 | -330841.72 | 20.9% | 117-MLLPCT1BP
224 | MLLPCT1PC | 2023-12-01 | 2025-11-30 | -33.56% | 0 | 0 | 167127.65 | 0% | 117-MLLPCT1PC
225 | MLLPPBSHD | 2022-09-01 | (blank) | n.m. | 1713510.134 | 2109996.758 | 2596663.83 | 81.26% | 117-MLLPPBSHD
226 | MLLSC1AHB | 2022-09-01 | 2023-12-31 | 43.42% | 0 | 0 | -44229.47 | 0% | 117-MLLSC1AHB
227 | MLLVC1CL1 | 2024-08-01 | 2025-05-31 | -161.4% | 274790.474 | 273686.078 | 332314.66 | 82.36% | 117-MLLVC1CL1
228 | XHWCAP117 | 2024-03-01 | 2025-12-31 | -50.15% | 156.5 | 0 | 118353.17 | 0% | 117-XHWCAP117
229 | Other | Other Budgeted Projects | Other | n.m. | 7707009.676 | 12244172.605 |  | n.m. | 117-Other | Main driver is Big Sandy Gen Core Restack project which incurred actuals in 2025 after May while budgeted in Q1
230 | Total GLBU 117 (Generation) | 0 | 1230407 | 6.8952 | 22431976.882 | 29939432.045 | 21052140.97
231 | GLBU 180 (Transmission) | 0
232 | 000005273 | Charges Began Prior to Jan 2015 | 2018-01-23 | n.m. | 0 | 0 | 1034881.56 | 0%
233 | 000025230 | 4/1/2018 | Blanket | Blanket | 50.92 | 0 | 18695.19 | 0%
234 | 180KYLSBO | 2022-06-01 | 2022-06-30 | 1045% | 0 | 0 | 37605.95 | 0%
235 | A14068001 | 6/1/2015 | 2021-12-20 | 119.5% | 205.379 | 275.769 | 11740.67 | 2.349%
236 | A14068006 | 2021-10-01 | 2022-06-30 | 200.7% | 44372.546 | 2486.71 | 52577.68 | 4.73%
237 | A15702006 | 4/1/2016 | 2025-12-31 | 71.75% | 6383.31 | 0 | 17934.6 | 0%
238 | A15702007 | 6/1/2017 | 2018-05-31 | 584.9% | 0 | 0 | -15873.91 | 0%
239 | A15702029 | 6/1/2017 | 2023-11-17 | 90.21% | 610070.506 | -2219972.878 | 2061379.59 | -107.7%
240 | A15702030 | 5/1/2017 | 2020-06-30 | 186.9% | 0 | 0 | 63230.2 | 0%
241 | A15702032 | 5/1/2017 | 2019-12-31 | 221.8% | 0 | 0 | 2226.16 | 0%
242 | A15702035 | 5/1/2017 | 2019-12-31 | 221.8% | 11020.13 | 0 | 5988.28 | 0%
243 | A15702036 | 5/1/2017 | 2019-12-31 | 221.8% | 0 | 0 | 2649.38 | 0%
244 | A15702041 | 6/1/2017 | 2019-12-31 | 225.8% | 0 | 0 | 21303.42 | 0%
245 | A15710071 | 7/1/2019 | 2021-09-17 | 169.2% | 905.48 | 0 | 2719.03 | 0%
246 | A18730001 | 8/1/2017 | 2019-12-31 | 234.5% | 957.06 | 0 | 459.48 | 0%
247 | A18730004 | 8/1/2017 | 2018-05-16 | 718.1% | 1033.25 | 0 | 496.05 | 0%
248 | A18730005 | 8/1/2017 | 2019-12-31 | 234.5% | 916.29 | 0 | 439.89 | 0%
249 | A19063004 | 2024-09-01 | 2026-05-30 | -81.76% | 72.78 | 228382.981 | 4752.32 | 4806%
250 | A19063005 | 2024-09-01 | 2026-05-30 | -81.76% | 70.65 | 0 | 4289.33 | 0%
251 | A19063006 | 2024-08-01 | 2026-05-30 | -73.31% | 4291.24 | 0 | 139272.54 | 0%
252 | A19750118 | 2022-07-01 | 2022-12-30 | 150% | 0 | 0 | -0.61 | 0%
253 | A20020001 | 2020-09-01 | 2022-07-01 | 140.9% | 0 | 0 | 355896.72 | 0%
254 | A20020002 | 2020-10-01 | 2022-07-01 | 142.8% | 0 | 0 | 15053 | 0%
255 | A20045015 | 2020-04-01 | 2026-06-01 | 48.58% | 6090.74 | 0 | 204672.93 | 0%
256 | A20045023 | 2020-06-01 | 2021-12-31 | 178.7% | 0 | 0 | 741.78 | 0%
257 | A20045046 | 2020-08-01 | 2021-12-31 | 188% | 0 | 0 | 851.66 | 0%
258 | A20045063 | 2020-07-01 | 2025-05-30 | 55.91% | 365943.782 | 1826444.379 | 977780.22 | 186.8%
259 | A20045085 | 2020-11-01 | 2021-12-31 | 207.1% | 0 | 0 | 104.73 | 0%
260 | A20077006 | 2021-01-01 | 2023-11-30 | 77.05% | 107.23 | 0 | 153.79 | 0%
261 | A20077009 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | 139.17 | 0%
262 | A20077012 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | 126.25 | 0%
263 | A20077026 | 2023-11-01 | 2028-04-14 | -13.22% | 1102569.979 | 1147165.257 | 27810.63 | 4125%
264 | A20077027 | 2024-02-01 | 2028-04-14 | -20.01% | 0 | 0 | 16869.37 | 0%
265 | A20077028 | 2023-11-01 | 2028-04-14 | -13.22% | 83477.584 | 142285.656 | 16847.01 | 844.6%
266 | A20077029 | 2023-11-01 | 2028-04-14 | -13.22% | 263684.995 | 429680.245 | 37644.75 | 1141%
267 | A20077030 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 17546.76 | 0%
268 | A20077031 | 2023-11-01 | 2028-04-14 | -13.22% | 321589.202 | 560072.757 | 8552.92 | 6548%
269 | A20077032 | 2023-11-01 | 2028-04-14 | -13.22% | 79367.199 | 135069.43 | 5212.35 | 2591%
270 | A20077033 | 2024-02-01 | 2028-04-14 | -20.01% | 95.06 | 0 | 152.25 | 0%
271 | A20077034 | 2023-11-01 | 2028-04-14 | -13.22% | 846882.285 | 1114228.33 | 29159.77 | 3821%
272 | A20077035 | 2023-11-01 | 2026-05-30 | -22.85% | 0 | 0 | 75.98 | 0%
273 | A20705028 | 7/1/2019 | 2028-06-01 | 42.02% | 1589.93 | 0 | 387.95 | 0%
274 | A20705035 | 9/1/2019 | 2019-12-31 | 1080% | 304 | 0 | 732.89 | 0%
275 | A20705036 | 9/1/2019 | 2019-12-31 | 1080% | 14519 | 0 | 85734.37 | 0%
276 | A20705037 | 8/1/2019 | 2030-11-01 | 32.55% | 0 | 0 | -24918.11 | 0%
277 | A20705052 | 9/1/2019 | 2020-01-31 | 859.9% | 0 | 0 | -28844.31 | 0%
278 | A20705057 | 9/1/2019 | 2020-01-31 | 859.9% | 0 | 0 | 814.19 | 0%
279 | A20705067 | 11/1/2019 | 2020-06-18 | 541.7% | 0 | 0 | 371.18 | 0%
280 | A20705077 | 2020-01-01 | 2020-06-14 | 718.2% | 0 | 0 | 486.32 | 0%
281 | A20705078 | 2020-01-01 | 2020-06-14 | 718.2% | 0 | 0 | 481.2 | 0%
282 | A20705079 | 11/1/2019 | 2020-06-10 | 561.3% | 0 | 0 | 59.49 | 0%
283 | A20705080 | 2020-01-01 | 2020-07-12 | 614% | 0 | 0 | 42.96 | 0%
284 | A20705081 | 2020-01-01 | 2020-06-15 | 713.9% | 0 | 0 | 42.96 | 0%
285 | A20705082 | 10/1/2019 | 2026-11-19 | 49% | 258257.146 | 360862.757 | 1639766.31 | 22.01%
286 | A20705083 | 10/1/2019 | 9/1/20205 | n.m. | 1678.52 | 0 | 1039.27 | 0%
287 | A21071001 | 2022-05-01 | 2024-12-31 | 34.26% | 537.632 | 32.06 | 2404.46 | 1.333%
288 | A21071002 | 2022-06-01 | 2024-12-31 | 32.1% | 655.02 | 0 | 314.46 | 0%
289 | A21071003 | 2022-05-01 | 2024-12-31 | 34.26% | 1291.317 | 40.111 | 6658.15 | 0.6024%
290 | A21071004 | 2022-06-01 | 2024-12-31 | 32.1% | 567.17 | 0 | 272.28 | 0%
291 | A21222008 | 2020-04-01 | 2024-10-30 | 65.39% | 301 | 0 | -5105.43 | 0%
292 | A21222017 | 2020-09-01 | 2022-10-30 | 119.3% | 0 | 0 | 72.93 | 0%
293 | A21222018 | 2025-03-01 | 2026-05-30 | -154.1% | 0 | 0 | 16106.03 | 0%
294 | A21505001 | 2022-06-01 | 2025-01-01 | 32.06% | 3782 | 0 | 4891.26 | 0%
295 | A21505003 | 2021-07-01 | 2021-12-31 | 348.6% | 0 | 0 | 1135.12 | 0%
296 | A21505004 | 2021-07-01 | 2021-12-31 | 348.6% | 0 | 0 | 5346.09 | 0%
297 | A21505005 | 2021-04-01 | 2021-12-31 | 266.1% | 0 | 0 | 385.66 | 0%
298 | A21505007 | 2021-07-01 | 2021-12-31 | 348.6% | 0 | 0 | 983.83 | 0%
299 | A21505008 | 2021-09-01 | 2021-12-31 | 476% | 0 | 0 | 2709.83 | 0%
300 | A21505011 | 2021-08-01 | 2025-12-31 | 37.63% | 0 | 0 | -24080.18 | 0%
301 | A21750002 | 2022-03-01 | 2022-12-30 | 129.9% | 0 | 0 | 2.58 | 0%
302 | A21750004 | 2022-04-01 | 2022-05-06 | 1040% | 0 | 0 | 41599.2 | 0%
303 | A21750007 | 2022-05-01 | 2022-11-18 | 166.2% | 90029.102 | 96588.343 | 46857.81 | 206.1%
304 | A21750008 | 2022-07-01 | 2022-12-31 | 149.2% | 432011.067 | 463486.058 | 35690.33 | 1299%
305 | A21750009 | 2024-11-01 | 2022-12-30 | 86.46% | 0 | 0 | 4600.9 | 0%
306 | A21750010 | 2022-07-01 | 2024-12-31 | 29.87% | 155222.6 | 166531.641 | 72878.85 | 228.5%
307 | A21750015 | 2023-11-01 | 2024-12-31 | -50.47% | 0 | 0 | 98175.93 | 0%
308 | A23750005 | 2024-09-01 | 2026-06-19 | -79.27% | 1053.07 | 0 | 101063.69 | 0%
309 | A23750007 | 2024-07-01 | 2025-09-30 | -100.4% | 967.27 | 0 | 568188.02 | 0%
310 | A23750008 | 2024-11-01 | 2026-01-31 | -127.4% | 0 | 0 | 782777.3 | 0%
311 | A23750009 | 2025-03-01 | 2026-01-31 | -208.6% | 0 | 0 | 5869.45 | 0%
312 | A23928003 | 2025-02-01 | 2026-06-01 | -138.8% | 0 | 0 | 51455.18 | 0%
313 | A23928005 | 2025-03-01 | 2026-06-01 | -153.4% | 0 | 0 | 120.6 | 0%
314 | A24005001 | 2024-10-01 | 2026-06-12 | -88.85% | 23935.224 | 33818.004 | 24397.98 | 138.6%
315 | A24006001 | 2024-11-01 | 2026-06-12 | -98.81% | 23935.224 | 33818.004 | 40589.96 | 83.32%
316 | A24022001 | 2024-07-01 | 2027-05-30 | -43.09% | 59413.858 | 82424.831 | 7679.82 | 1073%
317 | A24022004 | 2024-07-01 | 2027-05-30 | -43.09% | 208467.615 | 289868.972 | 13711.13 | 2114%
318 | A24022005 | 2024-08-01 | 2027-05-30 | -47.38% | 79528.029 | 114365.776 | 17169.45 | 666.1%
319 | A24025009 | 2024-06-01 | 2026-05-31 | -58.71% | 371060.707 | 938654.463 | 37705.65 | 2489%
320 | A24033001 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | 31248.02 | 0%
321 | A24033002 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | 169286.76 | 0%
322 | A24033003 | 2024-06-01 | 2025-06-30 | -108.6% | 0 | 0 | 787401.07 | 0%
323 | A24033004 | 2024-09-01 | 2025-06-30 | -172.2% | 0 | 0 | 1117.56 | 0%
324 | A24038001 | 2024-07-01 | 2027-05-30 | -43.09% | 69619.201 | 96504.398 | 4749.84 | 2032%
325 | A24038002 | 2024-07-01 | 2027-05-30 | -43.09% | 25359.75 | 34744.009 | 1030.77 | 3371%
326 | A24038003 | 2025-04-01 | 2027-05-30 | -92.78% | 7672.663 | 10850.182 | 2682.64 | 404.5%
327 | A24055001 | 2024-10-01 | 2025-06-30 | -202.2% | 0 | 0 | 903741.68 | 0%
328 | A24072002 | 2024-07-01 | 2025-06-30 | -125.8% | 0 | -237135.997 | 1066882.04 | -22.23%
329 | A24072003 | 2024-09-01 | 2025-06-30 | -172.2% | 0 | 0 | 1059021.82 | 0%
330 | A24072004 | 2024-07-01 | 2025-06-30 | -125.8% | 16818.27 | 0 | 548929.29 | 0%
331 | A24072005 | 2024-07-01 | 2025-06-30 | -125.8% | 16578.75 | 0 | 435986.58 | 0%
332 | A24072006 | 2024-07-01 | 2025-06-30 | -125.8% | 0 | 5975572.751 | 1239303.45 | 482.2%
333 | A24072007 | 2024-08-01 | 2025-06-30 | -146.8% | 12187.26 | 0 | 271315.56 | 0%
334 | A24072008 | 2024-08-01 | 2025-06-30 | -146.8% | 10102.27 | 0 | 238416.57 | 0%
335 | A24072009 | 2024-08-01 | 2025-06-30 | -146.8% | 15245.15 | 0 | 356203.01 | 0%
336 | A24072010 | 2024-07-01 | 2025-06-30 | -125.8% | 17765.37 | 0 | 570997.4 | 0%
337 | A24072011 | 2024-08-01 | 2025-06-30 | -146.8% | 0 | 0 | 188519.29 | 0%
338 | A24072012 | 2024-07-01 | 2025-06-30 | -125.8% | 18329.37 | 0 | 601715.13 | 0%
339 | A24072013 | 2024-08-01 | 2025-06-30 | -146.8% | 10855 | 0 | 350676.29 | 0%
340 | A24083007 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 206.53 | 0%
341 | A24093002 | 2025-03-01 | 2027-06-30 | -82.37% | 0 | 0 | 960746.42 | 0%
342 | A24093003 | 2025-03-01 | 2027-06-30 | -82.37% | 0 | 0 | 212289.02 | 0%
343 | A24112005 | 2021-08-01 | 2024-11-30 | 49.88% | 17695.383 | 18984.612 | 36.81 | 51575%
344 | A24112009 | 2021-06-01 | 2024-11-30 | 52.27% | 17695.383 | 18984.612 | -2402.88 | -790.1%
345 | A25101004 | 2022-03-01 | 2025-11-30 | 28.83% | 1921.39 | 2358.625 | 154.81 | 1524%
346 | A25101007 | 2022-03-01 | 2025-11-30 | 28.83% | 0 | 0 | 47.22 | 0%
347 | A25101008 | 2021-11-01 | 2025-11-30 | 34.56% | 0 | 0 | 90.63 | 0%
348 | A26112002 | 2025-05-01 | 2027-05-30 | -100.4% | 0 | 0 | 36.96 | 0%
349 | B180KYDEM | 2025-03-01 | Blanket | Blanket | 112.45 | 0 | 12189.82 | 0%
350 | B180KYLRC | 2/1/2017 | Blanket | Blanket | 8100220.148 | 4870590.886 | 8335011 | 58.44%
351 | B180KYLRR | 2022-02-01 | Blanket | Blanket | 2331876.231 | 82364.334 | 9646840.84 | 0.8538%
352 | B180KYPAC | 2024-10-01 | Blanket | Blanket | 23027.516 | 18613.847 | 128892.93 | 14.44%
353 | B180KYRMB | 7/1/2019 | Blanket | Blanket | 0 | 0 | 237924.16 | 0%
354 | B180KYSRR | 10/1/2016 | Blanket | Blanket | 556005.868 | 331396.221 | 318870.12 | 103.9%
355 | B180KYTEC | 2023-05-01 | Blanket | Blanket | 80428.944 | 65897.398 | 257048.92 | 25.64%
356 | DP16K03C0 | 11/1/2019 | 2021-01-06 | 288.4% | 0 | 0 | -52861.78 | 0%
357 | DP16K03C1 | 12/1/2019 | 2021-01-06 | 302.5% | 0 | 0 | -4580.25 | 0%
358 | DP16K03T0 | 2022-09-01 | 2021-01-06 | -34.99% | 0 | 0 | 2375.58 | 0%
359 | DR19K05C0 | 2022-02-01 | 2021-11-30 | -671.4% | 252.15 | 0 | 1828.22 | 0%
360 | DR19K05D0 | 6/1/2019 | 2020-11-11 | 264.5% | 0 | 0 | -58347.92 | 0%
361 | DTLM18001 | 2024-08-01 | 2030-06-01 | -22.96% | 0 | 0 | 349076.71 | 0%
362 | ETN000180 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 28.64 | 0 | -53699.858 | 0%
363 | ETN102802 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 277.26 | 0%
364 | IT180BILL | 7/1/2017 | Blanket | Blanket | 2260.43 | 0 | 199635.43 | 0%
365 | IT180CCIC | 2020-01-01 | Blanket | Blanket | 0 | 0 | 161048.69 | 0%
366 | ITCB18000 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 16341.586 | 15241.214 | 3899.34 | 390.9%
367 | KEPCS2202 | 2022-12-01 | 2022-12-31 | 400% | 64289.433 | -455250.681 | 1576102.13 | -28.88%
368 | KEPCS2401 | 2024-01-01 | 2024-12-31 | -75.62% | 55091.709 | 73413.52 | 35438.24 | 207.2%
369 | KEPCS2402 | 2024-04-01 | 2024-12-31 | -133.9% | 260053.203 | 346215.358 | 570568.23 | 60.68%
370 | KEPCS2404 | 2024-09-01 | 2024-12-31 | -429.8% | 123.29 | 0 | 265266.61 | 0%
371 | KEPCS2503 | 2025-04-01 | 2025-12-31 | -267.2% | 0 | 0 | 454508.89 | 0%
372 | P11063002 | Charges Began Prior to Jan 2015 | 2022-06-23 | n.m. | 0 | 0 | 926.91 | 0%
373 | P13064002 | 8/1/2016 | 2022-11-15 | 105.9% | 0 | 0 | 22510.44 | 0%
374 | P13064003 | 5/1/2016 | 2021-11-15 | 124.8% | 0 | 0 | 25231.05 | 0%
375 | P13064021 | 5/1/2016 | 2019-12-03 | 192.6% | 0 | 0 | 53742.34 | 0%
376 | P13064025 | 4/1/2017 | 2019-12-03 | 224.4% | 0 | 0 | 182.65 | 0%
377 | P13064029 | 8/1/2017 | 2020-12-03 | 169.5% | 0 | 0 | -1759.26 | 0%
378 | P13064030 | 9/1/2017 | 2022-11-15 | 107.2% | 0 | 0 | -35082.55 | 0%
379 | P13064031 | 12/1/2017 | 2021-11-15 | 134.7% | 0 | 0 | -1424.18 | 0%
380 | P14030002 | 3/1/2017 | 2024-12-20 | 77.9% | 304867.026 | 298128.074 | 170178.6 | 175.2%
381 | P14030008 | 6/1/2016 | 2023-11-17 | 91.52% | 23788.976 | 957.318 | 1781394.92 | 0.05374%
382 | P14030010 | 2020-06-01 | 2024-12-20 | 62.12% | 36496.999 | 46677.945 | 9507.08 | 491%
383 | P14030011 | 2020-06-01 | 2024-12-20 | 62.12% | 278071.446 | 266151.091 | 144486.87 | 184.2%
384 | P14030013 | 9/1/2016 | 2024-12-20 | 79.22% | 56313.195 | 42318.565 | 374166.58 | 11.31%
385 | P14030015 | 11/1/2016 | 2024-12-20 | 78.8% | 13.71 | 0 | 12.37 | 0%
386 | P14030016 | 11/1/2016 | 2024-12-20 | 78.8% | 751861.072 | 679767.799 | 717421.66 | 94.75%
387 | P14030101 | 3/1/2017 | 2024-12-20 | 77.9% | 73011.098 | 69020.139 | 46254.56 | 149.2%
388 | P14030102 | 12/1/2017 | 2024-12-20 | 75.54% | 3819781.871 | 1366105.256 | 13144444.03 | 10.39%
389 | P14030103 | 12/1/2017 | 2024-12-20 | 75.54% | 5204856.182 | 495876.459 | 10745777.52 | 4.615%
390 | P14030104 | 12/1/2017 | 2024-12-20 | 75.54% | 143270.595 | 109701.853 | 49694.3 | 220.8%
391 | P14030105 | 2023-03-01 | 2024-12-20 | 4.545% | 29623.441 | 27940.968 | 157052.7 | 17.79%
392 | P14030106 | 2023-01-01 | 2024-12-20 | 12.38% | 28527.51 | 26925.425 | 68864.28 | 39.1%
393 | P14030109 | 2024-12-01 | 2026-05-11 | -116.2% | 0 | 0 | 1498.34 | 0%
394 | P14030110 | 2024-12-01 | 2025-05-22 | -355.2% | 0 | 0 | 2083179.7 | 0%
395 | P16116003 | 11/1/2016 | 2027-11-15 | 58.07% | 573281.918 | 556250.343 | 664.83 | 83668%
396 | P16116005 | 7/1/2017 | 2027-11-15 | 55.4% | 24817.8 | 0 | 34949.2 | 0%
397 | P17076001 | 9/1/2017 | 2020-12-01 | 171.6% | 13.698 | 18.394 | -164157.56 | -0.01121%
398 | P17076005 | 9/1/2017 | 2020-12-01 | 171.6% | 3.94 | 0 | -24018.38 | 0%
399 | P17076006 | 10/1/2017 | 2020-12-01 | 173.5% | 0 | 0 | -228721.75 | 0%
400 | P17076008 | 2023-09-01 | 2021-07-01 | 19.44% | 13.698 | 18.394 | -862.79 | -2.132%
401 | P17076009 | 2020-06-01 | 2020-12-01 | 564.5% | 17.274 | 23.193 | -1266.9 | -1.831%
402 | P17076010 | 6/1/2018 | 2020-12-01 | 193% | 0 | 0 | -1011.48 | 0%
403 | P17083001 | 3/1/2019 | 2024-11-15 | 71.48% | 13346302.09 | 7865150.127 | 4103149.79 | 191.7%
404 | P17083002 | 2020-01-01 | 2024-11-15 | 66.57% | 1003144.871 | 909651.033 | 1264059.38 | 71.96%
405 | P17083003 | 3/1/2019 | 2024-11-15 | 71.48% | 4210.571 | 1252.023 | -51439.54 | -2.434%
406 | P17083005 | 4/1/2019 | 2024-11-15 | 71.05% | 55901.325 | 3254.215 | 17123.45 | 19%
407 | P17083006 | 3/1/2019 | 2024-11-15 | 71.48% | 8201837.411 | 4600653.1 | 930520.27 | 494.4%
408 | P17083007 | 2020-01-01 | 2024-11-15 | 66.57% | 24919.981 | -21870.206 | 884870.81 | -2.472%
409 | P17083008 | 3/1/2019 | 2024-11-15 | 71.48% | 2242055.839 | 2304798.256 | 1829625.3 | 126%
410 | P17083009 | 3/1/2019 | 2024-11-15 | 71.48% | 0 | 0 | -15873.54 | 0%
411 | P17083024 | 2020-09-01 | 2024-11-15 | 61.26% | 280.92 | 0 | -5716.17 | 0%
412 | P17083031 | 2020-01-01 | 2024-11-15 | 66.57% | 3912884.93 | 4623873.44 | 754391.11 | 612.9%
413 | P17083032 | 2022-07-01 | 2024-11-15 | 31.45% | 1676657.656 | 1722443.618 | 392597.85 | 438.7%
414 | P17083034 | 3/1/2019 | 2024-11-15 | 71.48% | 363340.215 | 589098.304 | 38818.62 | 1518%
415 | P17083037 | 2021-11-01 | 2024-11-15 | 46.4% | 45293.554 | 23793.069 | -19183.12 | -124%
416 | P17083038 | 2021-10-01 | 2024-11-15 | 47.85% | 140144.95 | 123758.072 | 205053.23 | 60.35%
417 | P17083041 | 2021-11-01 | 2024-11-15 | 46.4% | 2521463.633 | 2504411.917 | 3373445.89 | 74.24%
418 | P17083042 | 2023-11-01 | 2024-11-15 | -56.58% | 781726.847 | 887799.049 | 31207.92 | 2845%
419 | P17083043 | 2023-11-01 | 2025-06-02 | -37.13% | 68154.454 | 68099.145 | 18380.84 | 370.5%
420 | P17083044 | 2023-11-01 | 2025-06-02 | -37.13% | 167.11 | 0 | 16895.95 | 0%
421 | P17084007 | 10/1/2017 | 2020-12-01 | 173.5% | 162971.028 | 163515.095 | 274726.68 | 59.52%
422 | P17084008 | 2020-08-01 | 2020-12-01 | 796.7% | 28181.678 | 29251.904 | 33813.53 | 86.51%
423 | P17084017 | 9/1/2017 | 2020-12-01 | 171.6% | 302.71 | 0 | 4517.79 | 0%
424 | P17084018 | 9/1/2017 | 2020-12-01 | 171.6% | 282.88 | 0 | 3519.42 | 0%
425 | P17084019 | 9/1/2017 | 2020-12-01 | 171.6% | 784.78 | 0 | 5775.55 | 0%
426 | P17084020 | 9/1/2017 | 2020-12-01 | 171.6% | 223.46 | 0 | 44743.27 | 0%
427 | P17084041 | 2024-11-01 | 2030-08-01 | -27.68% | 0 | 0 | 2844.83 | 0%
428 | P17084042 | 2025-04-01 | 2031-08-13 | -31.48% | 0 | 0 | 631.9 | 0%
429 | P17084043 | 2024-11-01 | 2031-08-13 | -23.47% | 0 | 0 | 2470.92 | 0%
430 | P17084046 | 2024-11-01 | 2030-04-19 | -29.12% | 0 | 0 | 2304.12 | 0%
431 | P17084051 | 2024-11-01 | 2028-07-25 | -42.66% | 0 | 0 | 9999.84 | 0%
432 | P17084053 | 2024-11-01 | 2028-07-25 | -42.66% | 0 | 0 | 18158.2 | 0%
433 | P17084056 | 2024-09-01 | 2028-04-28 | -38.95% | 26.39 | 0 | 16303.29 | 0%
434 | P17084057 | 2024-09-01 | 2028-04-28 | -38.95% | 6.04 | 0 | 12024.94 | 0%
435 | P17225001 | 11/1/2017 | 2020-12-01 | 175.5% | 0 | 0 | -59583.09 | 0%
436 | P17225003 | 11/1/2017 | 2019-12-01 | 260% | 0 | 0 | -3774.33 | 0%
437 | P17225015 | 11/1/2017 | 2020-11-04 | 179.8% | 0 | 0 | 986.93 | 0%
438 | P18025005 | 3/1/2018 | 2019-12-09 | 286.4% | 3148139.065 | -2912326.911 | 2846391.2 | -102.3%
439 | P18025006 | 5/1/2018 | 2019-12-09 | 305.8% | 7642 | 0 | 20560.48 | 0%
440 | P18025007 | 5/1/2018 | 2019-12-09 | 305.8% | 2236849.774 | 416420.045 | 51934.14 | 801.8%
441 | P18025008 | 5/1/2018 | 2019-12-09 | 305.8% | 2236849.774 | 2450953.676 | 52253.09 | 4691%
442 | P18025009 | 5/1/2019 | 2019-12-09 | 644.1% | 0 | 0 | -2854.78 | 0%
443 | P18025010 | 5/1/2019 | 2019-12-09 | 644.1% | 0 | 0 | 90370 | 0%
444 | P18025012 | 9/1/2018 | 2019-12-09 | 360.3% | 3081.97 | 0 | 62391.1 | 0%
445 | P18025013 | 6/1/2018 | 2019-12-09 | 317.3% | 0 | 0 | -142.15 | 0%
446 | P18025014 | 2021-10-01 | 2019-11-12 | -79.25% | 0 | 0 | 133231.04 | 0%
447 | P18221002 | 5/1/2019 | 2022-11-04 | 111.5% | 2249478.774 | 2450953.676 | 118275.17 | 2072%
448 | P18221003 | 5/1/2019 | 2022-11-04 | 111.5% | 2236849.774 | 2450953.676 | 277950.06 | 881.8%
449 | P18221004 | 5/1/2019 | 2022-11-04 | 111.5% | 4213.774 | 4123.303 | 443223.76 | 0.9303%
450 | P18221005 | 5/1/2019 | 2022-11-04 | 111.5% | 25755.678 | 3771.912 | 138132.43 | 2.731%
451 | P18221007 | 2020-05-01 | 2022-11-04 | 116% | 0 | 0 | 1889.17 | 0%
452 | P18221008 | 2020-05-01 | 2022-11-04 | 116% | 0 | 0 | 4952.43 | 0%
453 | P18221010 | 5/1/2019 | 2022-11-04 | 111.5% | 1491233.182 | 1633969.119 | 2849.68 | 57339%
454 | P18221013 | 5/1/2019 | 2022-09-01 | 117.3% | 507.131 | 496.243 | 498.26 | 99.6%
455 | P18221014 | 10/1/2019 | 2022-11-04 | 113% | 259.877 | 254.4 | 21694.09 | 1.173%
456 | P18221017 | 8/1/2019 | 2022-09-01 | 118.7% | 5700 | 0 | -48948.34 | 0%
457 | P18221019 | 2021-02-01 | 2022-11-04 | 122.9% | 0 | 0 | 81885.49 | 0%
458 | P18221020 | 2021-04-01 | 2022-11-04 | 125.3% | 6.508 | 6.417 | 27789.59 | 0.02309%
459 | P18221021 | 2021-04-01 | 2022-11-04 | 125.3% | 224307.638 | 8383.756 | 297649.62 | 2.817%
460 | P19036003 | 2020-07-01 | 2022-11-11 | 116.2% | 57069.61 | 3002733.306 | 1371841.16 | 218.9%
461 | P19036004 | 2021-04-01 | 2022-11-11 | 123.8% | 2235 | 0 | 4651 | 0%
462 | P19036006 | 2020-07-01 | 2022-11-11 | 116.2% | 135565.666 | 147741.802 | 528263.64 | 27.97%
463 | P19036007 | 2021-03-01 | 2022-11-11 | 122.6% | 0 | 0 | 12981.44 | 0%
464 | P19036009 | 2022-09-01 | 2022-11-11 | 297.2% | 0 | 0 | 236340.41 | 0%
465 | P19037004 | 2021-07-01 | 2024-11-01 | 52.34% | 4529.996 | 1302.149 | 389707.58 | 0.3341%
466 | P19037005 | 2021-07-01 | 2027-11-01 | 27.57% | 3227.401 | 1349.966 | 237851.9 | 0.5676%
467 | P19037006 | 2021-11-01 | 2024-11-01 | 46.99% | 550.046 | 146.42 | 27333.52 | 0.5357%
468 | P19037007 | 2025-03-01 | 2025-05-01 | -1149% | 0 | 0 | 40807.47 | 0%
469 | P19037011 | 2021-10-01 | 2024-11-01 | 48.45% | 2833.62 | 235.802 | 204398.36 | 0.1154%
470 | P19037012 | 2021-10-01 | 2024-11-01 | 48.45% | 5483.133 | 3420.655 | 261004.3 | 1.311%
471 | P19037013 | 2021-11-01 | 2026-09-24 | 28.8% | 3634.408 | 577.912 | 89531.66 | 0.6455%
472 | P19037014 | 2021-07-01 | 2026-09-24 | 33.39% | 2592.327 | 512.014 | 50094.84 | 1.022%
473 | P19037023 | 2025-01-01 | 2027-03-24 | -79.06% | 1303.682 | 1236.178 | 1176.86 | 105%
474 | P19037025 | 2024-06-01 | 2027-03-24 | -41.72% | 1479.892 | 1236.178 | 8308.62 | 14.88%
475 | P19037027 | 2025-04-01 | 2027-03-24 | -101.4% | 24798.652 | -1898688.573 | 5448.55 | -34848%
476 | P19091011 | 2020-02-01 | 2020-11-03 | 418.1% | 0 | 0 | -8.44 | 0%
477 | P19092007 | 5/1/2019 | 2023-10-02 | 88.54% | 132.632 | 177.313 | 29954.99 | 0.5919%
478 | P19092008 | 11/1/2019 | 2023-10-18 | 86.11% | 1283.84 | 0 | 616.36 | 0%
479 | P19092011 | 7/1/2019 | 2023-10-18 | 87.2% | 237.572 | 307.542 | 46812.1 | 0.657%
480 | P19092012 | 5/1/2019 | 2023-10-18 | 87.68% | 3824.967 | 2175.771 | 2317.25 | 93.89%
481 | P19092013 | 5/1/2019 | 2023-10-18 | 87.68% | 2063.26 | 2324.866 | 85315.91 | 2.725%
482 | P19092017 | 11/1/2019 | 2023-10-18 | 86.11% | 1958.342 | 32.582 | 924.37 | 3.525%
483 | P19092019 | 11/1/2019 | 2023-10-18 | 86.11% | 106.021 | 142.356 | 17926.3 | 0.7941%
484 | P19104010 | 5/1/2019 | 2022-08-30 | 117.5% | 6513.708 | 838817.418 | -4280.85 | -19595%
485 | P19294011 | 2021-02-01 | 2022-11-18 | 120.3% | 0 | 0 | 3320.3 | 0%
486 | P19294012 | 2021-02-01 | 2022-11-18 | 120.3% | 0 | 0 | 3618.7 | 0%
487 | P19305001 | 2020-02-01 | 2025-05-30 | 59.33% | 3892536.444 | 5175046.551 | 2502905.46 | 206.8%
488 | P19305002 | 2020-03-01 | 2025-05-30 | 58.72% | 35354.391 | 23725.338 | 442679.44 | 5.359%
489 | P19305009 | 2020-02-01 | 2025-05-29 | 59.36% | 63053.645 | 78994.555 | 183978.04 | 42.94%
490 | P19305010 | 2020-02-01 | 2025-05-30 | 59.33% | 41971.653 | 11317.616 | 433463.68 | 2.611%
491 | P19305016 | 2020-02-01 | 2025-05-30 | 59.33% | 1353936.471 | -1149161.805 | 3708192.55 | -30.99%
492 | P19305017 | 2020-03-01 | 2025-10-10 | 54.9% | 604939.366 | 661572.797 | 745693.03 | 88.72%
493 | P19305018 | 2020-02-01 | 2025-05-30 | 59.33% | 67719.32 | 55295.709 | 258929.65 | 21.36%
494 | P19305019 | 2020-06-01 | 2025-05-30 | 56.63% | 5209.327 | 3629.254 | 9092.03 | 39.92%
495 | P19305021 | 2022-04-01 | 2025-10-10 | 28.26% | 10029.431 | 10997.027 | 5144.84 | 213.7%
496 | P19305023 | 2025-04-01 | 2024-04-20 | 211.6% | 18498.145 | 13497.246 | 541.81 | 2491%
497 | P20035004 | 2020-05-01 | 2023-09-01 | 87.36% | 3955.7 | 0 | 24480.48 | 0%
498 | P20035007 | 2024-09-01 | 2024-03-01 | 282.6% | 0 | 0 | 48.29 | 0%
499 | P21027001 | 2022-02-01 | 2024-05-15 | 50.72% | 0 | 0 | 14991.49 | 0%
500 | P21027002 | 2022-04-01 | 2023-12-01 | 59.77% | 3589.029 | 3583.98 | -156832.83 | -2.285%
501 | P21027003 | 2022-02-01 | 2023-12-01 | 63.32% | 0 | 0 | 1219.12 | 0%
502 | P21043001 | 2021-04-01 | 2025-10-01 | 44.34% | 45058.334 | 9629.644 | 429034.75 | 2.244%
503 | P21043002 | 2021-06-01 | 2025-10-01 | 42.2% | 483429.386 | 638291.874 | 366039.41 | 174.4%
504 | P21043003 | 2024-10-01 | 2026-04-01 | -100.5% | 3617.47 | 4948.463 | 3987.75 | 124.1%
505 | P21043004 | 2021-07-01 | 2025-10-01 | 41.08% | 105268.307 | 103428.12 | 37594.32 | 275.1%
506 | P21043008 | 2021-04-01 | 2025-10-01 | 44.34% | 299047.049 | 580953.064 | 280028.15 | 207.5%
507 | P21043009 | 2021-06-01 | 2025-10-01 | 42.2% | 79945.779 | 89472.293 | 549643.5 | 16.28%
508 | P21043015 | 2022-07-01 | 2025-10-01 | 22.98% | 356713.841 | 447532.045 | 325599.7 | 137.4%
509 | P21205003 | 2022-05-01 | 2025-05-30 | 29.69% | 27142.475 | 28208.244 | 668750.89 | 4.218%
510 | P21720001 | 2022-01-01 | 2025-09-01 | 33.91% | 25765.627 | 4021.381 | 488875.25 | 0.8226%
511 | P21720008 | 2022-06-01 | 2025-09-01 | 25.51% | 995.598 | 1.578 | 19554.95 | 0.00807%
512 | P21720011 | 2023-12-01 | 2027-03-01 | -20.66% | 24978.874 | 31851.508 | 43064.69 | 73.96%
513 | P21720012 | 2024-08-01 | 2027-03-01 | -51.91% | 91588.034 | 125652.246 | 411316.83 | 30.55%
514 | P21720013 | 2025-01-01 | 2027-05-19 | -73.96% | 0 | 0 | 7134.79 | 0%
515 | P21753001 | 2022-02-01 | 2025-06-01 | 34.79% | 230789.106 | 237749.72 | 365788.64 | 65%
516 | P21753002 | 2022-02-01 | 2025-06-01 | 34.79% | 74808.787 | 2133532.079 | 543634.58 | 392.5%
517 | P21753004 | 2022-04-01 | 2025-06-01 | 31.46% | 28597.983 | 20632.681 | 505400.38 | 4.082%
518 | P22005002 | 2022-04-01 | 2025-11-06 | 27.68% | 112967.742 | 168111.477 | 59397.2 | 283%
519 | P22012033 | 2022-08-01 | 2028-06-01 | 11.36% | 308.64 | 0 | 73.76 | 0%
520 | P22012039 | 2024-09-01 | 2028-12-01 | -33.51% | 1.54 | 0 | 50.4 | 0%
521 | P22012047 | 2022-07-01 | 2028-06-01 | 12.63% | 686 | 0 | 147.86 | 0%
522 | P22012049 | 2022-06-01 | 2028-06-01 | 13.82% | 913.764 | 15.806 | 1050.58 | 1.505%
523 | P22012051 | 2022-09-01 | 2028-06-01 | 10.05% | 63069.489 | 101809.859 | 98.88 | 102963%
524 | P22012052 | 2022-06-01 | 2028-06-01 | 13.82% | 2637.7 | 0 | 2649.43 | 0%
525 | P22043001 | 2025-05-01 | 2027-04-23 | -105.5% | 0 | 0 | 956.1 | 0%
526 | P22043002 | 2025-05-01 | 2027-04-23 | -105.5% | 0 | 0 | 87.01 | 0%
527 | P22043005 | 2025-05-01 | 2027-04-23 | -105.5% | 0 | 0 | 727.99 | 0%
528 | P22113001 | 2022-07-01 | 2024-04-01 | 42.66% | 0 | 0 | -14266.99 | 0%
529 | P22113005 | 2023-02-01 | 2023-11-01 | 21.25% | 0 | 0 | 6638.52 | 0%
530 | P22113006 | 2024-01-01 | 2025-06-01 | -53.38% | 0 | 0 | 613686.01 | 0%
531 | P22745001 | 2022-11-01 | 2023-12-31 | 35.29% | 110289.246 | 128121.739 | 426043.8 | 30.07%
532 | P22745003 | 2023-01-01 | 2025-09-26 | 8.909% | 122712.135 | 163350.627 | 139994.15 | 116.7%
533 | P22745004 | 2023-04-01 | 2025-09-26 | -0.11% | 8215.41 | 9478.073 | 118054.38 | 8.029%
534 | P22745005 | 2023-04-01 | 2025-09-26 | -0.11% | 169304.655 | 947352.772 | 212128.38 | 446.6%
535 | P23042017 | 2023-07-01 | 2028-11-01 | -4.718% | 84.92 | 0 | 134.17 | 0%
536 | P23325001 | 2023-08-01 | 2026-02-13 | -13.27% | 18958.88 | 13595.923 | 256331.47 | 5.304%
537 | P24051001 | 2024-08-01 | 2027-07-01 | -45.96% | 2833143.914 | 5830343.816 | 9882140.76 | 59%
538 | P24083001 | 2024-11-01 | 2031-05-01 | -24.49% | 0 | 0 | 42007.81 | 0%
539 | P24083003 | 2024-11-01 | 2031-05-01 | -24.49% | 0 | 0 | 6378.59 | 0%
540 | P24083004 | 2024-12-01 | 2031-05-01 | -26.09% | 0 | 0 | 109.28 | 0%
541 | P24083005 | 2025-03-01 | 2031-05-01 | -31.13% | 0 | 0 | 0 | #DIV/0!
542 | P24083006 | 2025-03-01 | 2031-05-01 | -31.13% | 0 | 0 | 0 | #DIV/0!
543 | P24083007 | 2024-10-01 | 2031-05-01 | -22.89% | 39.91 | 0 | 46954.62 | 0%
544 | P24083008 | 2024-12-01 | 2031-05-01 | -26.09% | 0 | 0 | 37985.13 | 0%
545 | P24125001 | 2025-04-01 | 2029-11-01 | -43.7% | 0 | 0 | 13496.94 | 0%
546 | P24125005 | 2025-04-01 | 2029-11-01 | -43.7% | 0 | 0 | 3490.12 | 0%
547 | P24125006 | 2024-12-01 | 2029-11-01 | -34.02% | 0 | 0 | 58115.98 | 0%
548 | P24125007 | 2025-02-01 | 2029-11-01 | -38.81% | 0 | 0 | 913.73 | 0%
549 | P24125009 | 2025-05-01 | 2029-11-01 | -46.32% | 0 | 0 | 1220.37 | 0%
550 | TTKY180NN | 2021-06-01 | Blanket | Blanket | 2409987.448 | 2901965.48 | 5539516.07 | 52.39%
551 | TTKY180NR | 2022-01-01 | Blanket | Blanket | 782776.815 | 702812.947 | 82745.2 | 849.4%
552 | XHWCAP180 | 2023-09-01 | 2025-12-31 | -18.08% | 667.42 | 0 | 499556.7 | 0%
553 | Other Budgeted Projects | Other | Other | Other | 12971591.082 | 47764800.078 | 60736391.16 | Other
554 | Total GLBU 180 (Transmission) |  | 13889992 | 246.2541 | 104876312.654 | 124290671.096 | 184793170.392
555 | Total Kentucky Power CWIP Additions |  | 21634905 | 831.3575 | 199684163.646 | 234125791.048 | 295707481.262
556
557 | X00000288 | For Property Acctg Use Only - GLBU 117 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -38341855.52 | Property Acctg
558 | X00000306 | For Property Acctg Use Only - GLBU 180 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -113742832.65 | Property Acctg
559 | X00000317 | For Property Acctg Use Only - GLBU 110 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -94767517.89 | Property Acctg
560 | Total Kentucky Power Transfers to 101/106 |  |  | 0 | 0 | 0 | -246852206.06
561
562 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year June 2024 - May 2025 |  | 21634905 | 831.3575 | 199684163.646 | 234125791.048 | 48855275.202
Formulas:
Estimated Project Completion Date = VLOOKUP([Project No.],'Gen Lookups'!A:K,3,FALSE)

## 12 Mos. Preceding Test Year
Schedule D (12 Months Preceding the Historical Test Year)
Kentucky Power Company
Case No. 2025-00257
Construction Projects for the 12 Months Preceding the Historical Test Year
June 2023 - May 2024
Definitions:
| (C)* | Represents the month project expenditures were initially recorded to CWIP (Account 107).
| (H)* | Represents Total Cost (G) per Schedule D.
| (J)* | 2023-03-31
| Blanket | Repetitive and predictable project charged and closed continuously throughout the calendar year.
| Property Acctg | Property Accounting perpetual administrative projects used to transfer plant in service or hold temporary charges later cleared to other work orders, e.g., construction overheads, suspense, labor accrual, etc.
| Other | Other amounts reflected in budget; do not directly relate to a project with actual spend during the period.
| Preliminary | Requires assessments and pre-engineering activities for developing detail scopes and estimates. Costs are transferred to new a project once enough data is available for project creation.
| n.m. | Not meaningful.
[5 empty] | 110 & 180 - Control | 110 & 180 - Forecast
Actual Accumulated Costs - June 2023 through May 2024
Line No. | Project No. | Date Construction Work Began | Estimated Project Completion Date | Percent of Elapsed Time through May 31, 2024 (J)* | Original Budget Estimate | Most Recent Budget Estimate | Total Project Expenditures | Percent of Total Expenditures June 2023 through May 2024 | GLBU-Project
(A) | (B) | (C)* | (D) | (E) = ((J)- (C)) / ((D) -(C)) | (F) | (G) | (H)* | (I) = (G)/(H)
1 | GLBU 110 (Distribution)
2 | 000001818 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 3932015.163 | 5241246.798 | 5681516.08 | 92.25%
3 | 000002241 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 111292.835 | 234439.649 | 440591.43 | 53.21%
4 | 000004464 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 9.2015e-12 | 0%
5 | 000004737 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 100404.456 | 2106742.521 | 1530230.79 | 137.7%
6 | 000005234 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 777 | 688765.009 | 2929871.45 | 23.51%
7 | 000007558 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 15491.244 | 33901.26 | 684.11 | 4956%
8 | 000007599 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 2471521.529 | 3631261.554 | 4192864.41 | 86.61%
9 | 000007615 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 120987.861 | 263637.9 | 253469.96 | 104%
10 | 000007818 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 1573386.893 | 6197138.549 | 7021813.38 | 88.26%
11 | 000016528 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 206247.657 | 242604.657 | 526811.69 | 46.05%
12 | 000025229 | 1/1/2018 | Blanket | Blanket | 60691.998 | 201842.587 | 1505510.65 | 13.41%
13 | 110KYLSBO | 2022-06-01 | 2022-06-30 | 1045% | 0 | 0 | 757447.04 | 0%
14 | A15710080 | 6/1/2019 | 2021-06-01 | 191.4% | 0 | 0 | -7218.17 | 0%
15 | A15710085 | 7/1/2019 | 2021-09-17 | 169.2% | 0 | -126.855 | 3635.6 | -3.489%
16 | A15710086 | 7/1/2019 | 2021-09-17 | 169.2% | 0 | -9026.079 | 27397.54 | -32.94%
17 | A20045031 | 2020-05-01 | 2021-12-31 | 174.7% | 0 | 0 | 392.52 | 0%
18 | A20045075 | 2020-09-01 | 2021-12-31 | 193.6% | 0 | 0 | 269.05 | 0%
19 | A20045086 | 2020-11-01 | 2021-12-31 | 207.1% | 0 | 0 | 77.12 | 0%
20 | A20045087 | 2020-11-01 | 2021-12-31 | 207.1% | 0 | 0 | 300.31 | 0%
21 | A20077007 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | 191.59 | 0%
22 | A20077008 | 2020-12-01 | 2023-11-30 | 77.7% | 0 | 0 | 141.21 | 0%
23 | A20077010 | 2020-09-01 | 2023-11-30 | 79.41% | 0 | 0 | 179.45 | 0%
24 | A20077011 | 2021-06-01 | 2023-11-30 | 73.25% | 0 | 0 | 122.09 | 0%
25 | A20077013 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | 124.93 | 0%
26 | A20077017 | 2020-09-01 | 2023-11-30 | 79.41% | 0 | 0 | 153.45 | 0%
27 | A20077018 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | 157.27 | 0%
28 | A20077019 | 2020-09-01 | 2023-11-30 | 79.41% | 0 | 0 | 268.66 | 0%
29 | A20077022 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | 140.2 | 0%
30 | A20077023 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | 0 | -3292.05 | 0%
31 | A20705033 | 7/1/2019 | 2028-06-01 | 42.02% | 0 | 0 | 0.74 | 0%
32 | A20705068 | 9/1/2019 | 2020-06-15 | 453.8% | 0 | 0 | 1226.87 | 0%
33 | A20705085 | 11/1/2019 | 2020-06-18 | 541.7% | 0 | 0 | 423.11 | 0%
34 | A20934001 | 2021-03-01 | 2021-09-01 | 413% | 0 | 0 | 17430.51 | 0%
35 | A21050054 | 2022-02-01 | 2022-12-30 | 127.4% | 0 | 0 | 7263.24 | 0%
36 | A21222009 | 2020-08-01 | 2022-10-30 | 118.5% | 0 | 0 | 282654.8 | 0%
37 | A21222015 | 2020-08-01 | 2022-10-30 | 118.5% | 0 | -201.883 | 10425.82 | -1.936%
38 | A21505006 | 2021-04-01 | 2021-12-31 | 266.1% | 0 | 0 | 495.9 | 0%
39 | A21505009 | 2021-08-01 | 2025-12-31 | 37.63% | 93 | 0 | 133.56 | 0%
40 | A23088001 | 2023-12-01 | 2024-06-30 | -115.6% | 0 | 0 | 475954.92 | 0%
41 | A23750004 | 2024-03-01 | 2025-06-01 | -73.52% | 0 | 0 | 1194334.52 | 0%
42 | A24112002 | 2021-08-01 | 2024-11-30 | 49.88% | -3632.01 | -3640.07 | 118.17 | -3080%
43 | A24112010 | 2021-06-01 | 2024-11-30 | 52.27% | 1061.825 | 1099.172 | 59.66 | 1842%
44 | A24112012 | 2021-08-01 | 2024-11-30 | 49.88% | 1110.825 | 1099.172 | 338.09 | 325.1%
45 | A25101001 | 2022-02-01 | 2025-11-30 | 30.26% | 60 | 0 | 86.13 | 0%
46 | A25101002 | 2022-03-01 | 2025-11-30 | 28.83% | 30 | 0 | 46.3 | 0%
47 | A25101003 | 2022-02-01 | 2025-11-30 | 30.26% | 36 | 0 | 49.51 | 0%
48 | A25101005 | 2022-02-01 | 2025-11-30 | 30.26% | 15 | 0 | 16.58 | 0%
49 | A25101006 | 2022-03-01 | 2025-11-30 | 28.83% | 30 | 0 | 46.42 | 0%
50 | B110KYSRR | 11/1/2016 | Blanket | Blanket | 0 | -358537.11 | 658829.08 | -54.42%
51 | B110KYTEL | 2024-03-01 | Blanket | Blanket | 0 | 0 | 13233.49 | 0%
52 | DCTSUVLKY | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | -346679.58 | 0%
53 | DMS22KK14 | 2022-07-01 | 2022-12-31 | 149.2% | 0 | 0 | -32121.48 | 0%
54 | DMS23KK01 | 2023-02-01 | 2023-12-31 | 17.42% | 0 | 0 | 155088.73 | 0%
55 | DMS23KK02 | 2023-03-01 | 2023-12-31 | 9.836% | 0 | 0 | -670843.45 | 0%
56 | DMS23KK03 | 2023-03-01 | 2023-12-31 | 9.836% | 0 | 0 | 160068.98 | 0%
57 | DMS23KK04 | 2023-04-01 | 2023-12-31 | -0.365% | 0 | 0 | -468418.95 | 0%
58 | DMS23KK05 | 2023-04-01 | 2023-12-31 | -0.365% | 0 | 0 | -118573.4 | 0%
59 | DMS23KK06 | 2023-07-01 | 2023-12-31 | -50.27% | 0 | 0 | 43054.44 | 0%
60 | DMS23KK07 | 2023-07-01 | 2023-12-31 | -50.27% | 0 | 0 | 75502.99 | 0%
61 | DMS23KK08 | 2023-07-01 | 2023-12-31 | -50.27% | 0 | 0 | 79764.27 | 0%
62 | DMS23KK09 | 2023-08-01 | 2023-12-31 | -80.92% | 0 | 0 | 89647.78 | 0%
63 | DMS24KK01 | 2024-01-01 | 2024-12-31 | -75.62% | 0 | 0 | 80049.88 | 0%
64 | DMS24KK02 | 2024-01-01 | 2024-12-31 | -75.62% | 0 | 0 | 252296.39 | 0%
65 | DMS24KK03 | 2024-02-01 | 2024-12-31 | -91.92% | 0 | 0 | 149273.71 | 0%
66 | DMS24KK04 | 2024-04-01 | 2024-12-31 | -133.9% | 0 | 0 | 1144020.98 | 0%
67 | DMS24KK05 | 2024-04-01 | 2024-12-31 | -133.9% | 0 | 0 | 9027.96 | 0%
68 | DMS24KK07 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | 167566.24 | 0%
69 | DMS24KK08 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | 1533122.35 | 0%
70 | DP14K02A0 | 2020-05-01 | 2020-12-01 | 497.2% | 0 | -7.639 | -32549.72 | 0.02347%
71 | DP14K02B0 | 3/1/2018 | 2020-12-01 | 184.5% | 0 | 0 | 829.04 | 0%
72 | DP16K03A0 | 2023-01-01 | 2024-06-30 | 16.3% | 1077 | 1468153.917 | 2674217.81 | 54.9%
73 | DP16K03B0 | 10/1/2019 | 2021-01-06 | 275.8% | 0 | 3112853.158 | 6857393.35 | 45.39%
74 | DR18K02A0 | 3/1/2019 | 2019-12-02 | 540.2% | 0 | -2190.102 | 16694.23 | -13.12%
75 | DR19K05A0 | 5/1/2019 | 2020-10-12 | 269.8% | -1 | -29852.065 | 57256.6 | -52.14%
76 | DR19K05B0 | 6/1/2019 | 2020-10-12 | 280.4% | 51 | 157680.065 | 119024.53 | 132.5%
77 | DR19K05B2 | 6/1/2019 | 2020-05-28 | 386.5% | 0 | 0 | -46.82 | 0%
78 | DR20K02B2 | 2020-04-01 | 2020-10-06 | 581.9% | 0 | 0 | -11677.21 | 0%
79 | DX16K02A0 | 2017-02-01 | 2017-09-01 | 1061% | 0 | 0 | 92.25 | 0%
80 | DX21K0002 | 2021-10-01 | 2022-11-01 | 137.9% | 0 | 0 | 379.22 | 0%
81 | DX21K0003 | 2021-10-01 | 2022-11-01 | 137.9% | 0 | 0 | 811114.22 | 0%
82 | DX23K01A0 | 2023-11-01 | Blanket | Blanket | 0 | 0 | 10240.61 | 0%
83 | EDN011333 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 406855.497 | 892667.696 | 359329.62 | 248.4%
84 | EDN012370 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 459487.746 | 964271.601 | 1160111.28 | 83.12%
85 | EDN014651 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 1839490.115 | 3970840.235 | 4915128.1 | 80.79%
86 | EDN014658 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 139835.453 | 298817.278 | 237645.52 | 125.7%
87 | EDN014680 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 807266.008 | 1476921.367 | 1480037.95 | 99.79%
88 | EDN014687 | Charges Began Prior to Jan 2015 | Blanket | Blanket | -10118.781 | 2210254.226 | -45388.57 | -4870%
89 | EDN014694 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 317712.535 | 689588.443 | 1529277.45 | 45.09%
90 | EDN014701 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 8745.34 | 0%
91 | EDN014720 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 521428.567 | 1284646.482 | 2057754.04 | 62.43%
92 | EDN015042 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 329383.774 | 736018.498 | 101166.76 | 727.5%
93 | EDN100033 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 1067748.865 | 3956362.025 | 2069757.71 | 191.2%
94 | EDN100044 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 52885.889 | 115606.317 | 129671.57 | 89.15%
95 | EDN100577 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 289595.656 | 633298.922 | 316610.49 | 200%
96 | EDN103175 | Charges Began Prior to Jan 2015 | Blanket | Blanket | -717224.989 | 0.014 | -10179.32 | -0.0001375%
97 | EON011326 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 1449595.436 | 4133307.758 | 4842578.1 | 85.35%
98 | ETN000110 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 0 | #DIV/0!
99 | IT1101722 | 2020-12-01 | Blanket | Blanket | 0 | 0 | 269333.78 | 0%
100 | IT1101723 | 2020-12-01 | Blanket | Blanket | 0 | 0 | -8.44 | 0%
101 | IT1101724 | 2020-12-01 | Blanket | Blanket | 0 | 0 | 8409.77 | 0%
102 | IT1101725 | 2020-11-01 | Blanket | Blanket | 0 | 0 | 619506.28 | 0%
103 | IT1102013 | 2023-08-01 | 2023-12-31 | -80.92% | 0 | 0 | 60737.98 | 0%
104 | IT1102049 | 2023-10-01 | 2028-07-01 | -10.61% | 0 | 0 | 5504.85 | 0%
105 | IT110ADMS | 2023-06-01 | 2026-03-31 | -5.996% | 0 | 0 | 1716845.57 | 0%
106 | IT110CCIC | 2020-01-01 | 2030-12-31 | 29.5% | 0 | 0 | 513160.34 | 0%
107 | ITCB11000 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 448587.87 | 928346.6 | 48.32%
108 | ITCF11000 | 2023-08-01 | 2023-12-31 | -80.92% | 0 | 0 | 147982.34 | 0%
109 | ITCT11004 | 2021-11-01 | Blanket | Blanket | 0 | 372644.145 | 453062.03 | 82.25%
110 | ITCW11004 | 4/1/2017 | 2021-12-31 | 126.2% | 0 | 152321.635 | 359665.68 | 42.35%
111 | ITCW11006 | 2021-12-01 | 2022-06-30 | 229.9% | 0 | 372644.145 | 146631.17 | 254.1%
112 | ITPCLC110 | 2023-04-01 | 2025-12-31 | -0.0995% | 114281.122 | 257032.024 | 154626.13 | 166.2%
113 | KEPDS2201 | 2022-07-01 | 2022-12-31 | 149.2% | 623141.581 | -49737.682 | 17058.36 | -291.6%
114 | KEPDS2202 | 2023-01-01 | 2022-12-31 | -8900% | 0 | 0 | -1088.77 | 0%
115 | KY5YCYCLE | 1/1/2019 | Blanket | Blanket | 1540841.903 | 3430698.448 | 1599747.78 | 214.5%
116 | KYCAPTOOL | 3/1/2019 | Blanket | Blanket | 10202.065 | 22364.013 | 179748.13 | 12.44%
117 | P13064028 | 2019-11-01 | 2020-08-01 | 454.7% | 0 | 0 | 11640.92 | 0%
118 | P14030009 | 11/1/2016 | 2024-12-20 | 78.8% | 90872.589 | 90485.868 | 80801.75 | 112%
119 | P17076002 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 3930.79 | 0%
120 | P17076003 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 1368.94 | 0%
121 | P17076011 | 4/1/2018 | 2020-12-01 | 187.2% | 0 | -126.855 | 1097.68 | -11.56%
122 | P17083016 | 3/1/2019 | 2024-11-15 | 71.48% | 1050888.199 | -121130.632 | 488495.4 | -24.8%
123 | P17083025 | 3/1/2019 | 2024-11-15 | 71.48% | 615270.796 | 606118.116 | 1250797.69 | 48.46%
124 | P17083030 | 4/1/2019 | 2024-11-15 | 71.05% | 283357.685 | 277887.777 | 417036.44 | 66.63%
125 | P17083033 | 2020-01-01 | 2024-11-15 | 66.57% | 1982.427 | 1954.465 | 3063.18 | 63.81%
126 | P17083040 | 2021-10-01 | 2024-11-15 | 47.85% | 403347.549 | 367049.784 | 1243586.19 | 29.52%
127 | P17084005 | 11/1/2017 | 2024-05-15 | 82.78% | 0 | 0 | 24455.05 | 0%
128 | P17084006 | 2021-07-01 | 2024-05-15 | 60.82% | 14533 | 0 | 7389.23 | 0%
129 | P17084025 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | -40720.49 | 0%
130 | P17084055 | 2022-10-01 | 2028-07-25 | 8.522% | 0 | 0 | 911.49 | 0%
131 | P17225006 | 12/1/2017 | 2020-04-01 | 228.4% | 0 | 0 | -3751.69 | 0%
132 | P18025001 | 3/1/2018 | 2019-12-09 | 286.4% | 1196747.931 | -307262.775 | 444731.6 | -69.09%
133 | P18025002 | 3/1/2018 | 2019-12-09 | 286.4% | 0 | 0 | 6817.96 | 0%
134 | P18025018 | 2021-05-01 | 2022-11-18 | 123.5% | 0 | 0 | 257071.64 | 0%
135 | P18221011 | 5/1/2019 | 2022-11-04 | 111.5% | -6879.102 | -70093.57 | 11883.2 | -589.9%
136 | P19036002 | 2020-09-01 | 2022-11-11 | 117.5% | 0 | 0 | 5238.86 | 0%
137 | P19036005 | 2020-07-01 | 2022-11-11 | 116.2% | 370084.05 | -193107.158 | 509530.34 | -37.9%
138 | P19036011 | 2020-08-01 | 2022-11-11 | 116.8% | 0 | 0 | 9243.69 | 0%
139 | P19036012 | 2021-08-01 | 2022-11-11 | 130% | 0 | 0 | 26697.01 | 0%
140 | P19037003 | 2021-12-01 | 2024-11-01 | 45.5% | -129157.146 | -127481.539 | 24160.37 | -527.6%
141 | P19037008 | 2023-04-01 | 2027-11-01 | -0.0597% | -141566.377 | -137422.41 | 65639.11 | -209.4%
142 | P19037016 | 2021-10-01 | 2026-09-24 | 30.02% | -55314.15 | -54968.966 | 62313.24 | -88.21%
143 | P19037017 | 2022-02-01 | 2026-09-24 | 24.94% | -106031.127 | -102401.264 | 37327 | -274.3%
144 | P19092002 | 9/1/2019 | 2023-10-02 | 87.6% | 296888.073 | -525234.356 | 83464.83 | -629.3%
145 | P19092014 | 5/1/2019 | 2023-10-18 | 87.68% | 533.482 | -70630.535 | 76500.23 | -92.33%
146 | P19092016 | 5/1/2019 | 2023-10-18 | 87.68% | 6747.273 | -119070.457 | 118846.18 | -100.2%
147 | P19092022 | 2020-09-01 | 2023-10-18 | 82.4% | 5766 | -100022.319 | 8224.47 | -1216%
148 | P19092023 | 2021-04-01 | 2023-10-18 | 78.39% | -858396.451 | 2522458.988 | 1499256 | 168.2%
149 | P19305013 | 2020-06-01 | 2025-05-22 | 56.88% | 1061243.645 | -361758.17 | 837291.2 | -43.21%
150 | P19305020 | 2021-05-01 | 2024-11-22 | 53.73% | 17203.325 | 996.322 | 6449.06 | 15.45%
151 | P19305022 | 2020-08-01 | 2024-11-22 | 61.75% | 98419.015 | 24180.948 | 245010.8 | 9.869%
152 | P20035005 | 2020-12-01 | 2023-09-01 | 84.66% | 0 | -2610.544 | 692.25 | -377.1%
153 | P20035008 | 2020-05-01 | 2023-09-01 | 87.36% | -6855.996 | -33252.508 | 1575.02 | -2111%
154 | P21043005 | 2023-02-01 | 2025-10-01 | 5.961% | -106626.87 | -130652.584 | 19978.9 | -654%
155 | P21043006 | 2021-04-01 | 2025-10-01 | 44.34% | 2141 | 0 | 10041.47 | 0%
156 | P21720003 | 2022-07-01 | 2025-09-01 | 23.58% | 251 | -10399.428 | 9629.95 | -108%
157 | P21720007 | 2023-03-01 | 2025-09-01 | 3.279% | 654 | -17421.075 | 9551.1 | -182.4%
158 | P21753003 | 2022-05-01 | 2025-06-01 | 29.64% | -55888.973 | -57974.412 | 4165.35 | -1392%
159 | P22005001 | 2022-02-01 | 2025-11-06 | 30.79% | 4860.619 | 1008.193 | 42444.58 | 2.375%
160 | P22012001 | 2022-04-01 | 2028-06-01 | 16.16% | 360 | 0 | 1272.45 | 0%
161 | P22012002 | 2022-04-01 | 2028-06-01 | 16.16% | 1094 | 0 | 1944.12 | 0%
162 | P22113002 | 2023-07-01 | 2025-06-11 | -12.94% | 17773.86 | 14896.04 | 150908.87 | 9.871%
163 | TP1403006 | 2022-10-01 | 2024-12-20 | 22.32% | 15138 | -216943.146 | 1778398.69 | -12.2%
164 | TP1708310 | 2022-07-01 | 2023-12-22 | 50.65% | 0 | -192746.454 | 3020741.86 | -6.381%
165 | TP1802510 | 2022-03-01 | 2019-06-01 | -39.34% | 0 | 320496.459 | 198542.95 | 161.4%
166 | TP1822105 | 2022-02-01 | 2022-09-01 | 199.5% | 0 | 0 | 90623.77 | 0%
167 | TP1903604 | 2022-03-01 | 2022-11-11 | 154.9% | 0 | 5787.686 | 70029.8 | 8.265%
168 | TP1930505 | 2024-04-01 | 2025-10-10 | -65.89% | 0 | 0 | 446372.31 | 0%
169 | TREEREL21 | 2021-01-01 | Blanket | Blanket | 2.246 | 5.082 | -24711.15 | -0.02057%
170 | TREEREL23 | 2023-03-01 | Blanket | Blanket | 2639598.195 | 4697274.052 | 3860779.31 | 121.7%
171 | TREEREL24 | 2024-01-01 | Blanket | Blanket | 0 | 2198758.604 | 1114048.98 | 197.4%
172 | XHWCAP110 | 2024-02-01 | 2025-12-31 | -43.92% | 0 | 0 | 34656.25 | 0%
173 | Other Budgeted Projects | Other | Other | Other | 418092.464 | 25849947.449 | 26268039.913 | Other
174 | Total GLBU 110 (Distribution) |  | 5833761 | 48.4094 | 24982290.949 | 83574634.301 | 111598876.853
175 | GLBU 117 (Generation)
176 | 000005237 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 53733.945 | 53733.945 | 593628.23 | 9.052% | 117-000005237 | Used Forecast measure for original and most recent due to Control budget data appearing inaccurate
177 | 000025231 | 3/1/2018 | (blank) | n.m. | 0 | 0 | 5907.45 | 0% | 117-000025231 | Budget Estimates only for referenced time period
178 | BSPPB0002 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 27286.031 | 27286.031 | 12265.83 | 222.5% | 117-BSPPB0002
179 | BSPPB0007 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 0 | 0 | 24036.03 | 0% | 117-BSPPB0007
180 | BSPPB0008 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 276067.299 | 276067.299 | 69184.39 | 399% | 117-BSPPB0008
181 | BSPPB0009 | 2020-03-01 | (blank) | n.m. | 0 | 0 | -261710.84 | 0% | 117-BSPPB0009
182 | BSPPB0013 | Charges Began Prior to Jan 2015 | 2018-12-31 | n.m. | 28637.422 | 28637.422 | -1302602.41 | -2.198% | 117-BSPPB0013
183 | BSPPB0016 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 0 | 0 | -24776.63 | 0% | 117-BSPPB0016
184 | BSPPBOUT1 | Charges Began Prior to Jan 2015 | (blank) | n.m. | 423526.055 | 423526.055 | 40287.57 | 1051% | 117-BSPPBOUT1
185 | BSPPBS339 | 11/1/2018 | 2022-06-30 | 120.5% | 0 | 0 | 370710.46 | 0% | 117-BSPPBS339
186 | BSPPBS340 | 11/1/2018 | 2022-06-30 | 120.5% | 0 | 0 | 376901.55 | 0% | 117-BSPPBS340
187 | BSPPBS368 | 2023-08-01 | 2024-12-31 | -23.75% | 1530189.504 | 1530189.504 | 1030440.02 | 148.5% | 117-BSPPBS368
188 | IT117CCIC | 2020-01-01 | 2030-12-31 | 29.5% | 0 | 0 | 146093.5 | 0% | 117-IT117CCIC
189 | ITCB11700 | Charges Began Prior to Jan 2015 | 2022-12-31 | n.m. | 0 | 0 | 38173.03 | 0% | 117-ITCB11700
190 | ITCBLBRTY | 2022-09-01 | 2022-12-31 | 174.4% | 0 | 0 | 11977.2 | 0% | 117-ITCBLBRTY
191 | ITPCLC117 | 2023-05-01 | 2025-12-31 | -3.179% | 11266.991 | 11266.991 | 1531.77 | 735.6% | 117-ITPCLC117
192 | ML1E25C02 | 2023-04-01 | 2023-11-27 | -0.4167% | 176022.417 | 176022.417 | 1338067.75 | 13.15% | 117-ML1E25C02
193 | MLKP26265 | 2023-03-01 | 2026-12-31 | 2.141% | 1096610.033 | 1096610.033 | 185122.93 | 592.4% | 117-MLKP26265
194 | MLL1CGRPL | 2023-12-01 | 2024-05-31 | -134.6% | 43997.027 | 43997.027 | 88526.56 | 49.7% | 117-MLL1CGRPL
195 | MLL2CGRPL | 2023-12-01 | 2024-05-31 | -134.6% | 133452.945 | 133452.945 | 99308.04 | 134.4% | 117-MLL2CGRPL
196 | MLLEC1VHL | 2023-05-01 | 2023-11-30 | -14.55% | 298295.199 | 298295.199 | 589446.77 | 50.61% | 117-MLLEC1VHL
197 | MLLEP2LBI | 2022-09-01 | 2022-12-31 | 174.4% | 0 | 0 | -683.25 | 0% | 117-MLLEP2LBI
198 | MLLHAULRD | 2023-12-01 | 2023-12-31 | -816.7% | 257240.84 | 257240.84 | 38130.27 | 674.6% | 117-MLLHAULRD
199 | MLLPC0ELG | 2022-09-01 | 2024-12-31 | 24.77% | 6526563.823 | 6526563.823 | 5316591.99 | 122.8% | 117-MLLPC0ELG
200 | MLLPC0LIM | 2022-09-01 | 2023-12-31 | 43.42% | -33291.033 | -33291.033 | 86736.6 | -38.38% | 117-MLLPC0LIM
201 | MLLPC2CTC | 2022-09-01 | 2022-12-31 | 174.4% | -174.942 | -174.942 | 7597.29 | -2.303% | 117-MLLPC2CTC
202 | MLLPC2ESP | 2022-09-01 | 2022-12-31 | 174.4% | -50470.045 | -50470.045 | 46506.43 | -108.5% | 117-MLLPC2ESP
203 | MLLPCT1BP | 2024-02-01 | 2024-06-10 | -236.2% | 682955.453 | 682955.453 | 960485.58 | 71.11% | 117-MLLPCT1BP
204 | MLLPCT1PC | 2023-12-01 | 2025-11-30 | -33.56% | 299894.262 | 299894.262 | -166914.05 | -179.7% | 117-MLLPCT1PC
205 | MLLPPBSHD | 2022-09-01 | (blank) | n.m. | 2030564.039 | 2030564.039 | 2910154.09 | 69.78% | 117-MLLPPBSHD
206 | MLLSC1AHB | 2022-09-01 | 2023-12-31 | 43.42% | 463303.058 | 463303.058 | 550116.59 | 84.22% | 117-MLLSC1AHB
207 | MLLSC2AHB | 2022-09-01 | 2022-12-31 | 174.4% | 524.83 | 524.83 | 1500.41 | 34.98% | 117-MLLSC2AHB
208 | MLLVC2CL4 | 2022-09-01 | 2022-12-31 | 174.4% | 349.885 | 349.885 | 50.72 | 689.8% | 117-MLLVC2CL4
209 | XHWCAP117 | 2024-03-01 | 2025-12-31 | -50.15% | 0 | 0 | 18884.8 | 0% | 117-XHWCAP117
210 | Other | Other Budgeted Projects | Other | n.m. | 464919.201 | 464919.201 |  | n.m. | 117-Other
211 | Total GLBU 117 (Generation) |  | 1133744 | -0.17152 | 14741464.239 | 14741464.239 | 13201676.67
212 | GLBU 180 (Transmission)
213 | 000005273 | Charges Began Prior to Jan 2015 | 2018-01-23 | n.m. | 52 | 49825.313 | 1001538.9 | 4.975%
214 | 000025230 | 4/1/2018 | Blanket | Blanket | 0 | 49167.172 | 85908.08 | 57.23%
215 | 180KYLSBO | 2022-06-01 | 2022-06-30 | 1045% | 0 | 0 | 247580.34 | 0%
216 | A14068001 | 6/1/2015 | 2021-12-20 | 119.5% | 0 | 0 | 51713 | 0%
217 | A14068006 | 2021-10-01 | 2022-06-30 | 200.7% | 15922 | 0 | 48209.62 | 0%
218 | A15702006 | 4/1/2016 | 2025-12-31 | 71.75% | 4442 | 0 | 24111.25 | 0%
219 | A15702007 | 6/1/2017 | 2018-05-31 | 584.9% | 0 | 0 | 1264.92 | 0%
220 | A15702029 | 6/1/2017 | 2023-11-17 | 90.21% | 316054.192 | -3955886.484 | 4023938.41 | -98.31%
221 | A15702030 | 5/1/2017 | 2020-06-30 | 186.9% | 0 | 0 | -14534.94 | 0%
222 | A15702032 | 5/1/2017 | 2019-12-31 | 221.8% | 0 | 0 | 2021.77 | 0%
223 | A15702035 | 5/1/2017 | 2019-12-31 | 221.8% | 8785 | 0 | 5438.43 | 0%
224 | A15702036 | 5/1/2017 | 2019-12-31 | 221.8% | 0 | 0 | 2406.12 | 0%
225 | A15702041 | 6/1/2017 | 2019-12-31 | 225.8% | 0 | 266174.768 | 5107247.42 | 5.212%
226 | A15702053 | 5/1/2017 | 2017-12-31 | 885.2% | 0 | 0 | -2509.43 | 0%
227 | A15702054 | 2017-06-01 | 2017-12-31 | 999.5% | 0 | 0 | -219471.52 | 0%
228 | A15710034 | 8/1/2018 | 2017-12-31 | -799.5% | 0 | 0 | -4039.82 | 0%
229 | A15710071 | 7/1/2019 | 2021-09-17 | 169.2% | 0 | 0 | 1853.95 | 0%
230 | A18730001 | 8/1/2017 | 2019-12-31 | 234.5% | 764 | 0 | 439.55 | 0%
231 | A18730004 | 8/1/2017 | 2018-05-16 | 718.1% | 825 | 0 | 474.54 | 0%
232 | A18730005 | 8/1/2017 | 2019-12-31 | 234.5% | 731 | 0 | 420.81 | 0%
233 | A18730013 | 4/1/2018 | 2018-05-25 | 3380% | 0 | 0 | 10119.25 | 0%
234 | A19750108 | 2020-07-01 | 2022-04-20 | 152.4% | 0 | 0 | 311.77 | 0%
235 | A19750113 | 2021-03-01 | 2021-10-12 | 337.8% | 0 | 0 | 1266.03 | 0%
236 | A19750114 | 2021-04-01 | 2021-05-31 | 1215% | 0 | 0 | -963.4 | 0%
237 | A19750118 | 2022-07-01 | 2022-12-30 | 150% | 0 | 0 | -98223.08 | 0%
238 | A20020001 | 2020-09-01 | 2022-07-01 | 140.9% | 0 | -389747.554 | 698137.94 | -55.83%
239 | A20020002 | 2020-10-01 | 2022-07-01 | 142.8% | 0 | -25114.766 | 7216.05 | -348%
240 | A20045015 | 2020-04-01 | 2026-06-01 | 48.58% | 0 | 0 | 3965.1 | 0%
241 | A20045023 | 2020-06-01 | 2021-12-31 | 178.7% | 0 | 0 | 676.95 | 0%
242 | A20045046 | 2020-08-01 | 2021-12-31 | 188% | 0 | 0 | 777.25 | 0%
243 | A20045063 | 2020-07-01 | 2025-05-30 | 55.91% | 109462.487 | 459996.721 | 342847.5 | 134.2%
244 | A20045085 | 2020-11-01 | 2021-12-31 | 207.1% | 0 | 0 | 95.56 | 0%
245 | A20077006 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | -13030.697 | 140.36 | -9284%
246 | A20077009 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | -2103.632 | 127.03 | -1656%
247 | A20077012 | 2021-01-01 | 2023-11-30 | 77.05% | 0 | -2103.632 | 131.17 | -1604%
248 | A20077026 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 4914.41 | 0%
249 | A20077027 | 2024-02-01 | 2028-04-14 | -20.01% | 0 | 0 | 1934.14 | 0%
250 | A20077028 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 2757.14 | 0%
251 | A20077029 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 3657.14 | 0%
252 | A20077030 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 1408.08 | 0%
253 | A20077031 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 3395.15 | 0%
254 | A20077032 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 165.64 | 0%
255 | A20077033 | 2024-02-01 | 2028-04-14 | -20.01% | 0 | 0 | 2967.36 | 0%
256 | A20077034 | 2023-11-01 | 2028-04-14 | -13.22% | 0 | 0 | 20119.51 | 0%
257 | A20077035 | 2023-11-01 | 2026-05-30 | -22.85% | 0 | 0 | 4993.65 | 0%
258 | A20705028 | 7/1/2019 | 2028-06-01 | 42.02% | 632 | 0 | 352.33 | 0%
259 | A20705029 | 7/1/2019 | 2028-06-01 | 42.02% | 0 | 0 | 838.42 | 0%
260 | A20705035 | 9/1/2019 | 2019-12-31 | 1080% | 218 | 0 | 414.23 | 0%
261 | A20705036 | 9/1/2019 | 2019-12-31 | 1080% | 10445 | 0 | 26776.84 | 0%
262 | A20705037 | 8/1/2019 | 2030-11-01 | 32.55% | 0 | 0 | 1039.75 | 0%
263 | A20705052 | 9/1/2019 | 2020-01-31 | 859.9% | 0 | 0 | 1203.5 | 0%
264 | A20705057 | 9/1/2019 | 2020-01-31 | 859.9% | 0 | 0 | 743.07 | 0%
265 | A20705067 | 11/1/2019 | 2020-06-18 | 541.7% | 0 | 0 | 530.54 | 0%
266 | A20705077 | 2020-01-01 | 2020-06-14 | 718.2% | 0 | 0 | 443.84 | 0%
267 | A20705078 | 2020-01-01 | 2020-06-14 | 718.2% | 0 | 0 | 439.17 | 0%
268 | A20705079 | 11/1/2019 | 2020-06-10 | 561.3% | 0 | 0 | 54.27 | 0%
269 | A20705080 | 2020-01-01 | 2020-07-12 | 614% | 0 | 0 | 39.21 | 0%
270 | A20705081 | 2020-01-01 | 2020-06-15 | 713.9% | 0 | 0 | 39.21 | 0%
271 | A20705082 | 10/1/2019 | 2026-11-19 | 49% | 11178.53 | -34693.94 | 125053.66 | -27.74%
272 | A20705083 | 10/1/2019 | 9/1/20205 | n.m. | 946.65 | 260.536 | 948.5 | 27.47%
273 | A21071001 | 2022-05-01 | 2024-12-31 | 34.26% | 0 | 0 | 3539.26 | 0%
274 | A21071002 | 2022-06-01 | 2024-12-31 | 32.1% | 0 | 0 | 1344.45 | 0%
275 | A21071003 | 2022-05-01 | 2024-12-31 | 34.26% | 0 | 0 | 22883.39 | 0%
276 | A21071004 | 2022-06-01 | 2024-12-31 | 32.1% | 0 | 0 | 2804.65 | 0%
277 | A21222008 | 2020-04-01 | 2024-10-30 | 65.39% | 336 | -1465.598 | 309.26 | -473.9%
278 | A21222017 | 2020-09-01 | 2022-10-30 | 119.3% | 0 | 0 | 35.16 | 0%
279 | A21505001 | 2022-06-01 | 2025-01-01 | 32.06% | 2933 | 0 | 4463.99 | 0%
280 | A21505003 | 2021-07-01 | 2021-12-31 | 348.6% | 0 | 0 | 1035.98 | 0%
281 | A21505004 | 2021-07-01 | 2021-12-31 | 348.6% | 0 | 0 | 2789.12 | 0%
282 | A21505005 | 2021-04-01 | 2021-12-31 | 266.1% | 0 | 0 | 351.99 | 0%
283 | A21505007 | 2021-07-01 | 2021-12-31 | 348.6% | 0 | 0 | 897.9 | 0%
284 | A21505008 | 2021-09-01 | 2021-12-31 | 476% | 0 | 0 | 2473.14 | 0%
285 | A21505011 | 2021-08-01 | 2025-12-31 | 37.63% | 0 | 0 | 1686.92 | 0%
286 | A21750001 | 2021-11-01 | 2022-09-30 | 154.7% | 0 | 0 | 181.46 | 0%
287 | A21750002 | 2022-03-01 | 2022-12-30 | 129.9% | 0 | 0 | 1243810.88 | 0%
288 | A21750004 | 2022-04-01 | 2022-05-06 | 1040% | 0 | 0 | 3726.13 | 0%
289 | A21750006 | 2022-08-01 | 2023-03-23 | 103.4% | 62981.34 | 63323.332 | 37610.37 | 168.4%
290 | A21750007 | 2022-05-01 | 2022-11-18 | 166.2% | 67249.754 | -119732.254 | 829962.62 | -14.43%
291 | A21750008 | 2022-07-01 | 2022-12-31 | 149.2% | 322702.754 | 139968.122 | 15124.77 | 925.4%
292 | A21750010 | 2022-07-01 | 2022-12-30 | 150% | 115947.866 | 116577.47 | 27304.02 | 427%
293 | A21750012 | 2022-08-01 | 2022-08-31 | 806.7% | 0 | 0 | 2714.73 | 0%
294 | A21750013 | 2022-08-01 | 2022-09-16 | 526.1% | 0 | 0 | -801.42 | 0%
295 | A21750015 | 2023-11-01 | 2024-12-31 | -50.47% | 0 | 0 | 1491930.18 | 0%
296 | A24033001 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | 5556.07 | 0%
297 | A24033002 | 2024-05-01 | 2024-12-31 | -162.7% | 0 | 0 | 721.12 | 0%
298 | A24112005 | 2021-08-01 | 2024-11-30 | 49.88% | 13218.065 | 13289.836 | 62.04 | 21421%
299 | A24112009 | 2021-06-01 | 2024-11-30 | 52.27% | 13218.065 | 13289.836 | 69.11 | 19230%
300 | A25101004 | 2022-03-01 | 2025-11-30 | 28.83% | 20 | 0 | 2397.17 | 0%
301 | A25101007 | 2022-03-01 | 2025-11-30 | 28.83% | 20 | 0 | 43.1 | 0%
302 | A25101008 | 2021-11-01 | 2025-11-30 | 34.56% | 39 | 0 | 82.7 | 0%
303 | B180KYLRC | 2/1/2017 | Blanket | Blanket | 2280470.813 | 2116084.388 | 3301302.39 | 64.1%
304 | B180KYLRR | 2022-02-01 | Blanket | Blanket | 0 | 0 | 3073551.88 | 0%
305 | B180KYRMB | 7/1/2019 | Blanket | Blanket | 0 | 0 | 311829.73 | 0%
306 | B180KYSRR | 10/1/2016 | Blanket | Blanket | 0 | -193467.096 | 539806.56 | -35.84%
307 | B180KYTEC | 2023-05-01 | Blanket | Blanket | 0 | 0 | 25207.64 | 0%
308 | B180KYTRE | 3/1/2017 | Blanket | Blanket | 0 | 0 | 449893.27 | 0%
309 | DP16K03C0 | 11/1/2019 | 2021-01-06 | 288.4% | 0 | -78653.797 | 476636.74 | -16.5%
310 | DP16K03C1 | 12/1/2019 | 2021-01-06 | 302.5% | 0 | -65229.434 | 520896.74 | -12.52%
311 | DP16K03T0 | 2022-09-01 | 2021-01-06 | -34.99% | 0 | 0 | 549.59 | 0%
312 | DR19K05C0 | 2022-02-01 | 2021-11-30 | -671.4% | 0 | -5299.768 | 929 | -570.5%
313 | ETN000180 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 64315.44 | 0%
314 | ETN102802 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 0 | 0 | 1500 | 0%
315 | IT180BILL | 7/1/2017 | Blanket | Blanket | 0 | 0 | 309492.84 | 0%
316 | IT180CCIC | 2020-01-01 | Blanket | Blanket | 0 | 0 | 136000.89 | 0%
317 | ITCB18000 | Charges Began Prior to Jan 2015 | Blanket | Blanket | 8537.958 | -8034.713 | 27279.48 | -29.45%
318 | ITPCLC180 | 2023-05-01 | 2025-12-31 | -3.179% | 0 | 1031.013 | 3503.66 | 29.43%
319 | KEPCS2101 | 2021-02-01 | 2021-12-31 | 236.6% | 0 | 872122.038 | 261890.56 | 333%
320 | KEPCS2201 | 2022-02-01 | 2022-12-31 | 127% | 0 | 0 | -835.56 | 0%
321 | KEPCS2202 | 2022-12-01 | 2022-12-31 | 400% | 200 | 0 | 136615.2 | 0%
322 | KEPCS2301 | 2023-03-01 | 2023-12-21 | 10.17% | 0 | 0 | 9045.38 | 0%
323 | KEPCS2302 | 2017-07-01 | 2023-12-21 | 88.79% | 0 | 0 | -102.34 | 0%
324 | KEPCS2401 | 2024-01-01 | 2024-12-31 | -75.62% | 0 | 0 | 149670.29 | 0%
325 | KEPCS2402 | 2024-04-01 | 2024-12-31 | -133.9% | 0 | 0 | 726261.03 | 0%
326 | P10115014 | 2017-07-01 | 2020-07-01 | 191.5% | 0 | 0 | 46169.81 | 0%
327 | P10115015 | 2017-07-01 | 2019-05-09 | 310% | 0 | 0 | -9899.21 | 0%
328 | P11063002 | Charges Began Prior to Jan 2015 | 2022-06-23 | n.m. | 67.585 | -818.874 | 308064.16 | -0.2658%
329 | P11161010 | 7/1/2015 | 2018-12-31 | 221.3% | 0 | 0 | -13886.53 | 0%
330 | P11161023 | 8/1/2017 | 2018-12-31 | 400% | 0 | 0 | -3391.4 | 0%
331 | P13064002 | 8/1/2016 | 2022-11-15 | 105.9% | 0 | 0 | 1190706.1 | 0%
332 | P13064003 | 5/1/2016 | 2021-11-15 | 124.8% | 0 | 0 | 25503.92 | 0%
333 | P13064021 | 5/1/2016 | 2019-12-03 | 192.6% | 0 | 0 | 714.92 | 0%
334 | P13064025 | 4/1/2017 | 2019-12-03 | 224.4% | 0 | 0 | 9936.68 | 0%
335 | P13064029 | 8/1/2017 | 2020-12-03 | 169.5% | 0 | 0 | 62743.46 | 0%
336 | P13064030 | 9/1/2017 | 2022-11-15 | 107.2% | 0 | 0 | 361464.92 | 0%
337 | P13064031 | 12/1/2017 | 2021-11-15 | 134.7% | 0 | 0 | -5185.8 | 0%
338 | P14030002 | 3/1/2017 | 2024-12-20 | 77.9% | 75891.681 | 71593.642 | 80587.81 | 88.84%
339 | P14030008 | 6/1/2016 | 2023-11-17 | 91.52% | 60570.301 | -97592.737 | 419032.08 | -23.29%
340 | P14030010 | 2020-06-01 | 2024-12-20 | 62.12% | 8179.822 | 3505.614 | 117290.88 | 2.989%
341 | P14030011 | 2020-06-01 | 2024-12-20 | 62.12% | 30311.971 | -131791.02 | 621191.16 | -21.22%
342 | P14030013 | 9/1/2016 | 2024-12-20 | 79.22% | 72571.9 | 56627.763 | 680355.61 | 8.323%
343 | P14030015 | 11/1/2016 | 2024-12-20 | 78.8% | 5 | 0 | 11.34 | 0%
344 | P14030016 | 11/1/2016 | 2024-12-20 | 78.8% | 14716.373 | 1709.973 | 193569.58 | 0.8834%
345 | P14030101 | 3/1/2017 | 2024-12-20 | 77.9% | 63637.415 | 57397.118 | 26990.89 | 212.7%
346 | P14030102 | 12/1/2017 | 2024-12-20 | 75.54% | 1222021.275 | 1125281.489 | 4506717.61 | 24.97%
347 | P14030103 | 12/1/2017 | 2024-12-20 | 75.54% | 1353333.92 | 668572.841 | 1392290.21 | 48.02%
348 | P14030104 | 12/1/2017 | 2024-12-20 | 75.54% | 2195119.427 | -542477.836 | 837107.19 | -64.8%
349 | P14030105 | 2023-03-01 | 2024-12-20 | 4.545% | 11208.599 | 10987.398 | 4003.8 | 274.4%
350 | P14030106 | 2023-01-01 | 2024-12-20 | 12.38% | 10554.432 | 10333.654 | 1725.7 | 598.8%
351 | P16116003 | 11/1/2016 | 2027-11-15 | 58.07% | 1225 | -5720.536 | 635.99 | -899.5%
352 | P16116005 | 7/1/2017 | 2027-11-15 | 55.4% | 9647 | 0 | 14682.05 | 0%
353 | P17076001 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 3221.29 | 0%
354 | P17076005 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 500.43 | 0%
355 | P17076006 | 10/1/2017 | 2020-12-01 | 173.5% | 0 | 0 | 18132.46 | 0%
356 | P17076008 | 2023-09-01 | 2021-07-01 | 19.44% | 0 | 0 | 862.79 | 0%
357 | P17076009 | 2020-06-01 | 2020-12-01 | 564.5% | 0 | 0 | 1034.06 | 0%
358 | P17076010 | 6/1/2018 | 2020-12-01 | 193% | 0 | 0 | 15.83 | 0%
359 | P17083001 | 3/1/2019 | 2024-11-15 | 71.48% | 1209256.116 | -2521188.675 | 6801267.25 | -37.07%
360 | P17083002 | 2020-01-01 | 2024-11-15 | 66.57% | 682666.719 | -510391.205 | 1496383.41 | -34.11%
361 | P17083003 | 3/1/2019 | 2024-11-15 | 71.48% | 1399.068 | 0.069 | 4353.09 | 0.001585%
362 | P17083005 | 4/1/2019 | 2024-11-15 | 71.05% | 93587.188 | 86342.152 | 150440.58 | 57.39%
363 | P17083006 | 3/1/2019 | 2024-11-15 | 71.48% | 1992132.82 | 285748.91 | 2234995.4 | 12.79%
364 | P17083007 | 2020-01-01 | 2024-11-15 | 66.57% | 317095.816 | 221062.384 | 119523.63 | 185%
365 | P17083008 | 3/1/2019 | 2024-11-15 | 71.48% | 757985.071 | 744303.212 | 72113.7 | 1032%
366 | P17083009 | 3/1/2019 | 2024-11-15 | 71.48% | 0 | 0 | 231.04 | 0%
367 | P17083024 | 2020-09-01 | 2024-11-15 | 61.26% | 141 | 0 | 795.99 | 0%
368 | P17083031 | 2020-01-01 | 2024-11-15 | 66.57% | 2287859.395 | 2265205.963 | 2571783.17 | 88.08%
369 | P17083032 | 2022-07-01 | 2024-11-15 | 31.45% | 423554.265 | 646322.839 | -3275.12 | -19734%
370 | P17083034 | 3/1/2019 | 2024-11-15 | 71.48% | 837900.43 | 814327.499 | 235325.5 | 346%
371 | P17083037 | 2021-11-01 | 2024-11-15 | 46.4% | 33445.882 | 3639.04 | 31660.76 | 11.49%
372 | P17083038 | 2021-10-01 | 2024-11-15 | 47.85% | 55692.493 | 38944.494 | 464244.53 | 8.389%
373 | P17083041 | 2021-11-01 | 2024-11-15 | 46.4% | 1566578.213 | 525322.884 | 1363030.15 | 38.54%
374 | P17083042 | 2023-11-01 | 2024-11-15 | -56.58% | 191671.729 | -12210.17 | 462.46 | -2640%
375 | P17083043 | 2023-11-01 | 2025-06-02 | -37.13% | 48869.211 | 47290.583 | 1974.61 | 2395%
376 | P17083044 | 2023-11-01 | 2025-06-02 | -37.13% | 0 | 0 | 2118.53 | 0%
377 | P17084007 | 10/1/2017 | 2020-12-01 | 173.5% | 15395 | 0 | 69469.68 | 0%
378 | P17084008 | 2020-08-01 | 2020-12-01 | 796.7% | 2293 | -17424.144 | 37391.85 | -46.6%
379 | P17084017 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 390.36 | 0%
380 | P17084018 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 364.39 | 0%
381 | P17084019 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 1021.43 | 0%
382 | P17084020 | 9/1/2017 | 2020-12-01 | 171.6% | 0 | 0 | 286.59 | 0%
383 | P17225001 | 11/1/2017 | 2020-12-01 | 175.5% | 0 | 0 | -143090.25 | 0%
384 | P17225003 | 11/1/2017 | 2019-12-01 | 260% | 0 | 0 | -51854.02 | 0%
385 | P17225013 | 11/1/2017 | 2020-11-04 | 179.8% | 0 | 0 | -5279.24 | 0%
386 | P17225014 | 2017-12-01 | 2020-11-05 | 181.9% | 0 | 0 | 1262.45 | 0%
387 | P17225015 | 11/1/2017 | 2020-11-04 | 179.8% | 0 | 0 | -1065.25 | 0%
388 | P17225017 | 12/1/2017 | 2020-11-04 | 182% | 0 | 0 | -71.1 | 0%
389 | P17225025 | 2020-07-01 | 2020-06-30 | -100300% | 0 | 0 | -2198.85 | 0%
390 | P18025005 | 3/1/2018 | 2019-12-09 | 286.4% | 1603622.213 | -376130.377 | 2841340.05 | -13.24%
391 | P18025006 | 5/1/2018 | 2019-12-09 | 305.8% | 77848 | -83596.575 | 106644.6 | -78.39%
392 | P18025007 | 5/1/2018 | 2019-12-09 | 305.8% | 1050541.821 | -375689.722 | 30519.28 | -1231%
393 | P18025008 | 5/1/2018 | 2019-12-09 | 305.8% | 1050541.821 | 1052594.201 | 15399.67 | 6835%
394 | P18025009 | 5/1/2019 | 2019-12-09 | 644.1% | 1757.193 | -3260.242 | 27826.66 | -11.72%
395 | P18025010 | 5/1/2019 | 2019-12-09 | 644.1% | 0 | -1313.719 | 25997.37 | -5.053%
396 | P18025012 | 9/1/2018 | 2019-12-09 | 360.3% | 17430.511 | -3722.433 | 66824.5 | -5.57%
397 | P18025013 | 6/1/2018 | 2019-12-09 | 317.3% | 0 | -62880.725 | 3466.29 | -1814%
398 | P18025014 | 2021-10-01 | 2019-11-12 | -79.25% | 0 | -12012.553 | 63387.63 | -18.95%
399 | P18221002 | 5/1/2019 | 2022-11-04 | 111.5% | 1073459.497 | 1011432.259 | 627899.43 | 161.1%
400 | P18221003 | 5/1/2019 | 2022-11-04 | 111.5% | 1083607.17 | 1180344.91 | 532147.73 | 221.8%
401 | P18221004 | 5/1/2019 | 2022-11-04 | 111.5% | 49898.198 | -132419.834 | 697547.92 | -18.98%
402 | P18221005 | 5/1/2019 | 2022-11-04 | 111.5% | 32473.672 | -82637.909 | 802428.21 | -10.3%
403 | P18221007 | 2020-05-01 | 2022-11-04 | 116% | 287.59 | -1046.259 | 4379.86 | -23.89%
404 | P18221008 | 2020-05-01 | 2022-11-04 | 116% | 347.596 | -1752.089 | 3217.78 | -54.45%
405 | P18221010 | 5/1/2019 | 2022-11-04 | 111.5% | 700724.858 | 696664.202 | 14195.16 | 4908%
406 | P18221013 | 5/1/2019 | 2022-09-01 | 117.3% | 739.887 | -81066.392 | 13254.59 | -611.6%
407 | P18221014 | 10/1/2019 | 2022-11-04 | 113% | 2687.6 | -37678.749 | 130802.82 | -28.81%
408 | P18221017 | 8/1/2019 | 2022-09-01 | 118.7% | 19298 | -30977.501 | 17025.27 | -182%
409 | P18221019 | 2021-02-01 | 2022-11-04 | 122.9% | 139098 | -252163.977 | 394964.58 | -63.84%
410 | P18221020 | 2021-04-01 | 2022-11-04 | 125.3% | 67918.736 | -142745.576 | 142197.37 | -100.4%
411 | P18221021 | 2021-04-01 | 2022-11-04 | 125.3% | -380767.303 | 489510.054 | 559541.05 | 87.48%
412 | P19036003 | 2020-07-01 | 2022-11-11 | 116.2% | 655595.08 | 1631403.531 | 3506632.18 | 46.52%
413 | P19036004 | 2021-04-01 | 2022-11-11 | 123.8% | 7567 | -22.586 | 3976.06 | -0.568%
414 | P19036006 | 2020-07-01 | 2022-11-11 | 116.2% | 93680 | 444764.637 | 574187.14 | 77.46%
415 | P19036007 | 2021-03-01 | 2022-11-11 | 122.6% | 0 | -952.194 | 6206.72 | -15.34%
416 | P19036009 | 2022-09-01 | 2022-11-11 | 297.2% | 0 | 0 | 51227.84 | 0%
417 | P19037004 | 2021-07-01 | 2024-11-01 | 52.34% | 2523 | 0 | 98504.53 | 0%
418 | P19037005 | 2021-07-01 | 2027-11-01 | 27.57% | 2904.95 | 1342.24 | 86545.4 | 1.551%
419 | P19037006 | 2021-11-01 | 2024-11-01 | 46.99% | 317 | 0 | 11757.57 | 0%
420 | P19037011 | 2021-10-01 | 2024-11-01 | 48.45% | 1912 | -40329.961 | 8738.58 | -461.5%
421 | P19037012 | 2021-10-01 | 2024-11-01 | 48.45% | 4629.863 | -23580.751 | 13203.08 | -178.6%
422 | P19037013 | 2021-11-01 | 2026-09-24 | 28.8% | 2306 | 0 | 48098.06 | 0%
423 | P19037014 | 2021-07-01 | 2026-09-24 | 33.39% | 1592 | 0 | 40073.83 | 0%
424 | P19091004 | 12/1/2019 | 2020-11-03 | 359.8% | 0 | 0 | 0 | #DIV/0!
425 | P19091011 | 2020-02-01 | 2020-11-03 | 418.1% | 674728.81 | -330840.264 | -597.62 | 55360%
426 | P19092007 | 5/1/2019 | 2023-10-02 | 88.54% | 14769.269 | -6968.329 | 44113.06 | -15.8%
427 | P19092008 | 11/1/2019 | 2023-10-18 | 86.11% | 0 | -2714.377 | 777.47 | -349.1%
428 | P19092011 | 7/1/2019 | 2023-10-18 | 87.2% | 18594.101 | -98794.048 | 39210.03 | -252%
429 | P19092012 | 5/1/2019 | 2023-10-18 | 87.68% | 2050.641 | -12564.55 | 1347.54 | -932.4%
430 | P19092013 | 5/1/2019 | 2023-10-18 | 87.68% | -656597.429 | 282490.728 | 103725.66 | 272.3%
431 | P19092017 | 11/1/2019 | 2023-10-18 | 86.11% | 2331.643 | -6617.352 | 1166.01 | -567.5%
432 | P19092019 | 11/1/2019 | 2023-10-18 | 86.11% | 0 | -5159.904 | 16034.64 | -32.18%
433 | P19104010 | 5/1/2019 | 2022-08-30 | 117.5% | 0 | 577803.953 | 156201.09 | 369.9%
434 | P19104012 | 7/1/2019 | 2022-08-30 | 118.4% | 0 | 0 | 0 | #DIV/0!
435 | P19104016 | 2022-03-01 | 2022-02-25 | -9875% | 0 | -6887.214 | 5269.54 | -130.7%
436 | P19215005 | 12/1/2019 | 2021-11-22 | 168.4% | 0 | 0 | -8701.75 | 0%
437 | P19215014 | 2021-12-01 | 2021-11-22 | -5389% | 0 | 0 | -5641.51 | 0%
438 | P19294011 | 2021-02-01 | 2022-11-18 | 120.3% | 0 | 0 | -8721.03 | 0%
439 | P19294012 | 2021-02-01 | 2022-11-18 | 120.3% | 0 | 0 | 6633.52 | 0%
440 | P19305001 | 2020-02-01 | 2025-05-30 | 59.33% | 538226.292 | 306660.864 | 523044.59 | 58.63%
441 | P19305002 | 2020-03-01 | 2025-05-30 | 58.72% | 137.494 | -80740.771 | 218422.61 | -36.97%
442 | P19305009 | 2020-02-01 | 2025-05-29 | 59.36% | 6284.868 | -30995.424 | 139087.57 | -22.28%
443 | P19305010 | 2020-02-01 | 2025-05-30 | 59.33% | 12154.601 | -128924.266 | 148263.6 | -86.96%
444 | P19305016 | 2020-02-01 | 2025-05-30 | 59.33% | 14931.211 | -368233.194 | 302993.43 | -121.5%
445 | P19305017 | 2020-03-01 | 2025-10-10 | 54.9% | 9968 | -32.022 | 234943.67 | -0.01363%
446 | P19305018 | 2020-02-01 | 2025-05-30 | 59.33% | 54186.078 | 25571.871 | 49547.54 | 51.61%
447 | P19305019 | 2020-06-01 | 2025-05-30 | 56.63% | 33.408 | -122.649 | 20817.39 | -0.5892%
448 | P19305021 | 2022-04-01 | 2025-10-10 | 28.26% | 8 | -36188.612 | 12.82 | -282282%
449 | P20035004 | 2020-05-01 | 2023-09-01 | 87.36% | 1559 | -5550.651 | 808.84 | -686.2%
450 | P21027001 | 2022-02-01 | 2024-05-15 | 50.72% | 3036 | -74994.951 | 153404.5 | -48.89%
451 | P21027002 | 2022-04-01 | 2023-12-01 | 59.77% | -115 | 0 | 176747.52 | 0%
452 | P21027003 | 2022-02-01 | 2023-12-01 | 63.32% | 2289 | 0 | -62560.93 | 0%
453 | P21043001 | 2021-04-01 | 2025-10-01 | 44.34% | 93374.501 | 85245.646 | 125897.26 | 67.71%
454 | P21043002 | 2021-06-01 | 2025-10-01 | 42.2% | 1187 | -57205.263 | 11604.43 | -493%
455 | P21043004 | 2021-07-01 | 2025-10-01 | 41.08% | 1032 | 0 | 14779.49 | 0%
456 | P21043008 | 2021-04-01 | 2025-10-01 | 44.34% | 118751.028 | 265368.579 | 36928.94 | 718.6%
457 | P21043009 | 2021-06-01 | 2025-10-01 | 42.2% | 1157 | -28602.614 | 9170.66 | -311.9%
458 | P21043015 | 2022-07-01 | 2025-10-01 | 22.98% | 0 | 0 | 33922.25 | 0%
459 | P21205003 | 2022-05-01 | 2025-05-30 | 29.69% | 4958.302 | -247787.408 | 69622.1 | -355.9%
460 | P21605001 | 2021-10-01 | 2022-04-01 | 300% | -1028 | 0 | 36212.67 | 0%
461 | P21605002 | 2021-11-01 | 2022-04-01 | 341.1% | 80 | 0 | -26181.26 | 0%
462 | P21605003 | 2024-04-01 | 2022-10-01 | 66.97% | 80 | 0 | 0 | #DIV/0!
463 | P21605004 | 2022-08-01 | 2022-04-01 | -198.4% | 197 | 0 | -6904.43 | 0%
464 | P21720001 | 2022-01-01 | 2025-09-01 | 33.91% | 10371.739 | -36242.448 | 122260.03 | -29.64%
465 | P21720008 | 2022-06-01 | 2025-09-01 | 25.51% | 114 | 0 | 7080.58 | 0%
466 | P21720011 | 2023-12-01 | 2027-03-01 | -20.66% | 0 | 0 | 6486.64 | 0%
467 | P21753001 | 2022-02-01 | 2025-06-01 | 34.79% | 19569.505 | -16073.078 | 56130.36 | -28.64%
468 | P21753002 | 2022-02-01 | 2025-06-01 | 34.79% | 15339.824 | 836067.762 | 50881.47 | 1643%
469 | P21753004 | 2022-04-01 | 2025-06-01 | 31.46% | 543 | -8040.404 | 19610.47 | -41%
470 | P22005002 | 2022-04-01 | 2025-11-06 | 27.68% | 4574.702 | -42036.947 | 24996.41 | -168.2%
471 | P22012033 | 2022-08-01 | 2028-06-01 | 11.36% | 110 | 0 | 925.52 | 0%
472 | P22012047 | 2022-07-01 | 2028-06-01 | 12.63% | 272 | 0 | 141.45 | 0%
473 | P22012049 | 2022-06-01 | 2028-06-01 | 13.82% | 342 | 0 | 1654.84 | 0%
474 | P22012051 | 2022-09-01 | 2028-06-01 | 10.05% | 182 | 0 | 94.59 | 0%
475 | P22012052 | 2022-06-01 | 2028-06-01 | 13.82% | 1038 | 0 | 3201.52 | 0%
476 | P22113001 | 2022-07-01 | 2024-04-01 | 42.66% | 87068.019 | 1042898.718 | -29196.08 | -3572%
477 | P22113004 | 2022-07-01 | 2023-11-01 | 55.94% | 118.154 | -189516.594 | -20107.75 | 942.5%
478 | P22113005 | 2023-02-01 | 2023-11-01 | 21.25% | 0 | 0 | -18681.47 | 0%
479 | P22113006 | 2024-01-01 | 2025-06-01 | -53.38% | 0 | 0 | 3491.9 | 0%
480 | P22745001 | 2022-11-01 | 2023-12-31 | 35.29% | 0 | 0 | 99867.04 | 0%
481 | P22745003 | 2023-01-01 | 2025-09-26 | 8.909% | 0 | 0 | 91305.68 | 0%
482 | P22745004 | 2023-04-01 | 2025-09-26 | -0.11% | 0 | 0 | 26900 | 0%
483 | P22745005 | 2023-04-01 | 2025-09-26 | -0.11% | 0 | 303496.61 | 114384.22 | 265.3%
484 | P23042017 | 2023-07-01 | 2028-11-01 | -4.718% | 28 | 0 | 1426.18 | 0%
485 | P23325001 | 2023-08-01 | 2026-02-13 | -13.27% | 0 | 0 | 131407.37 | 0%
486 | TTKY180NN | 2021-06-01 | Blanket | Blanket | 334798.571 | -99900.32 | 1315328.83 | -7.595%
487 | TTKY180NR | 2022-01-01 | Blanket | Blanket | 90775.839 | -586.937 | 288631.17 | -0.2034%
488 | XHWCAP180 | 2023-09-01 | 2025-12-31 | -18.08% | 0 | 571812.21 | 156805.92 | 364.7%
489 | Other Budgeted Projects | Other | Other | Other | 4287190.157 | 47494007.804 |  | Other
490 | Total GLBU 180 (Transmission) |  | 11772014 | -724.0175 | 32150259.872 | 57742631.568 | 68699760.43
491 | Total Kentucky Power CWIP Additions |  | 18739519 | -675.7797 | 71874015.06 | 156058730.108 | 193500313.953
492
493 | X00000317 | For Property Acctg Use Only - GLBU 110 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -79826328.91 | Property Acctg
494 | X00000288 | For Property Acctg Use Only - GLBU 117 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -9490335.35 | Property Acctg
495 | X00000306 | For Property Acctg Use Only - GLBU 180 | Property Acctg | Property Acctg | Property Acctg | Property Acctg | -54394338.75 | Property Acctg
496 | Total Kentucky Power Transfers to 101/106 |  |  | 0 | 0 | 0 | -143711003.01
497
498 | Total Kentucky Power CWIP Activity 12 Months Preceding the Historical Test Year June 2023 - May 2024 |  | 18739519 | -675.7797 | 71874015.06 | 156058730.108 | 49789310.943
Formulas:
Estimated Project Completion Date = VLOOKUP([Project No.],'Gen Lookups'!A:K,3,FALSE)

## Gen Lookups
|  |  | Year-ending May | Values
|  |  | 2024 | 2024 | 2024 | 2025 | 2025 | 2025
Prj | Project to Use for Budg | Est ISD, Prj to Use | Sum of Ctrl $ | Sum of Fore $ | Sum of Act $ | Sum of Ctrl $ | Sum of Fore $ | Sum of Act $ | Chk Test Year | Chk Prior
000001585 | 000001585 O&M / Fuel Staff Project | (blank) | 0 | 1.4921e-13 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000001586 | 000001586 Capital Staff Project | (blank) | -1.0914e-11 | 0.005 | 0 | 0.021 | 0.012 | 0 | 117-Other | 117-Other
000005237 | 000005237 KyPCo-G Capital Software Dev | (blank) | 0 | 53733.945 | 593628.23 | 0 | 0 | 483424.81 | 117-000005237 | 117-000005237
000005706 | 000005706 Ds IM Mich-Anda | 1902-01-01 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
000005707 | 000005707 Ds AP WVirg-Anda | 1902-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000005708 | 000005708 Ds SEP La-Anda | 1902-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000007652 | 000007652 OOC Capital Projects | 2028-12-31 | 5137.385 | 8585.13 | 0 | 10456.725 | 9958.401 | 0 | 117-Other | 117-Other
000012736 | 000012736 ISO Certification | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000014351 | 000014351 Budget Earnings Adjustments | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000018412 | 000018412 FEL IT Projects | (blank) | 2853.819 | 5266.622 | 0 | 5954.159 | 5675.422 | 0 | 117-Other | 117-Other
MLLPC0ELG | MLLPC0ELG ML PCC U0 ELG/CCR Comply - 117 | 2024-12-31 | 183468 | 4744329.453 | 0 | 236575 | 0 | 0 | 117-MLLPC0ELG | 117-MLLPC0ELG | Updated Project ID | 000020310 ML U0 ELG / CCR Compliance
000022309 | 000022309 ML U2 ESP Upgrades | 2022-05-27 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
000022392 | 000022392 ML LANDFILL EXPANSION - PH 3 | 2019-12-31 |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
000025231 | 000025231 2018 Gen Plt Cap Blkt - KYPC-G | (blank) | 0 | 0 | 5907.45 | 12.63 | 0 | 7349.91 | 117-000025231 | 117-000025231
MLLHAULRD | MLLHAULRD Mitchell Haul Road Relocate | 2023-12-31 | 158478.918 | -545872.715 | 0 | 567186.399 | 513395.505 | 0 | 117-MLLHAULRD | 117-MLLHAULRD | Updated Project ID | 000025624 Mitchell Haul Road Relocate
000026753 | 000026753 189MW PSO Solar Pixley | 2025-04-30 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000026765 | 000026765 598MW SWEPCo Wagon Wheel | 2025-12-15 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000026956 | 000026956 135MW Wind Flat Ridge IV | 2025-05-30 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
000026957 | 000026957 153MW Wind Flat Ridge V | 2025-07-30 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
ACCTTAX | ACCTTAX Accounting and Tax BPO | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
AEPLEADER | AEPLEADER AEP Leadership Devel Programs | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
AESAVINGS | AESAVINGS AE Savings | (blank) | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
AP24IRCM1 | AP24IRCM1 WPCo Gen 24 IRC ML U2 CT Shell | 2025-12-31 |  |  |  | 0 | 0.005 | 0 | 117-Other | 117-Other
BDLABSPRD | BDLABSPRD Budget Labor Spread | (blank) | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
BLDCS | BLDCS Building Projects Cap Std | 2026-12-31 | 11254.021 | 17769.939 | 0 | 22426.491 | 19383.491 | 0 | 117-Other | 117-Other
BSPGENREW | BSPGENREW BS1 Gen Core Restack & Rewind | 2027-12-31 |  |  |  | 7039553.244 | 6952681.422 | 0 | 117-Other | 117-Other
BSPPB0002 | BSPPB0002 Boiler & Auxiliaries PPB<100k | (blank) | 0 | 27286.031 | 12265.83 | 323809.04 | 308158.934 | 47574.89 | 117-BSPPB0002 | 117-BSPPB0002
BSPPB0003 | BSPPB0003 Boiler MU Water Supply PPB<100 | (blank) | 0 | 25580.642 | 0 | 317943.852 | 304733.442 | 0 | 117-Other | 117-Other
BSPPB0007 | BSPPB0007 Condenser & Aux. PPB<100k | (blank) | 0 | 0 | 24036.03 | 217.68 | 0 | 138165.45 | 117-BSPPB0007 | 117-BSPPB0007
BSPPB0008 | BSPPB0008 Clg Water Facilities PPB<100k | (blank) | 0 | 276067.299 | 69184.39 | 228.03 | 0 | 35028.35 | 117-BSPPB0008 | 117-BSPPB0008
BSPPB0009 | BSPPB0009 Effluent WW Treating PPB<100k | (blank) | 0 | 0 | -261710.84 |  |  |  | 117-Other | 117-BSPPB0009
BSPPB0011 | BSPPB0011 Generator & Support PPB<100k | (blank) |  |  |  | 120.29 | 0 | 67287.39 | 117-BSPPB0011 | 117-Other
BSPPB0013 | BSPPB0013 Other Costs PPB<$100k | 2018-12-31 | 0 | 28637.422 | -1302602.41 | 336302.547 | 832845.96 | 1158052.85 | 117-BSPPB0013 | 117-BSPPB0013
BSPPB0016 | BSPPB0016 Turb & Support Sys PPB<100k | (blank) | 0 | 0 | -24776.63 |  |  |  | 117-Other | 117-BSPPB0016
BSPPBENEW | BSPPBENEW BSP PPB Envr. New | (blank) |  |  |  | 246.25 | 0 | 247589.97 | 117-BSPPBENEW | 117-Other
BSPPBENVR | BSPPBENVR Other Environ Repl <100k | (blank) | 12197.682 | 25243.096 | 0 | 42371.912 | 37401.379 | 0 | 117-Other | 117-Other
BSPPBOUT1 | BSPPBOUT1 Unit 1PPB Outage<100k | (blank) | 58952.96 | 423526.055 | 40287.57 | 845917.808 | 956559.622 | 634689.19 | 117-BSPPBOUT1 | 117-BSPPBOUT1
BSPPBPOND | BSPPBPOND Install Reflective Balls | 2026-04-01 |  |  |  | 223696.747 | 219464.851 | 0 | 117-Other | 117-Other
BSPPBRVSC | BSPPBRVSC River Screen - Upgrade | 2026-12-01 |  |  |  | 372401.498 | 365422.777 | 0 | 117-Other | 117-Other
BSPPBS339 | BSPPBS339 REPLACE 15 BREAKERS "A" BUS | 2022-06-30 | 0 | 0 | 370710.46 |  |  |  | 117-Other | 117-BSPPBS339
BSPPBS340 | BSPPBS340 REPLACE 15 BREAKERS "B" BUS | 2022-06-30 | 0 | 0 | 376901.55 |  |  |  | 117-Other | 117-BSPPBS340
BSPPBS347 | BSPPBS347 REP U1 BFPT Rotor with Spare | 2018-12-21 |  |  |  | 565.12 | 183248.525 | 414957.95 | 117-BSPPBS347 | 117-Other
BSPPBS358 | BSPPBS358 BS1 REPL BLR COMBUSTION COILS | 2029-12-31 | 0 | -7186.182 | 0 | 7237.187 | 0 | 0 | 117-Other | 117-Other
BSPPBS359 | BSPPBS359 BS1 HEAT RATE INSTRUMENTATION | 2029-12-31 |  |  |  | 2894.676 | 0 | 0 | 117-Other | 117-Other
BSPPBS365 | BSPPBS365 BSP UPGRADE U1 FREIGHT ELEVATO | 2024-12-31 | 40691.755 | 0 | 0 | 11056.374 | 146.278 | 0 | 117-Other | 117-Other
BSPPBS368 | BSPPBS368 Big1 Boiler Exit Gas Duct Repl | 2024-12-31 | 1643002.666 | 1530189.504 | 1030440.02 | 4265647.78 | 5810643.636 | 8135599.44 | 117-BSPPBS368 | 117-BSPPBS368
BSPPBS370 | BSPPBS370 Rep U1 BFPT Rotor with Spare | 2028-10-20 |  |  |  | 372401.498 | 614835.375 | 0 | 117-Other | 117-Other
BSPPBS371 | BSPPBS371 REP BFP rotor with spare | 2024-10-25 |  |  |  | 250768.948 | 245090.33 | 0 | 117-Other | 117-Other
BSPPBS372 | BSPPBS372 Rep Heater Bay Roof | 2026-12-18 |  |  |  | 78292.652 | 77060.393 | 0 | 117-Other | 117-Other
BSPPBSKYC | BSPPBSKYC Stack Sky Climber Replacement | 2026-12-30 |  |  |  | 208780.393 | 205494.38 | 0 | 117-Other | 117-Other
BSPPBWGRN | BSPPBWGRN Ovation Evergreen Upgrade | 2026-02-01 |  |  |  | 1170678.818 | 1148697.852 | 1278.32 | 117-BSPPBWGRN | 117-Other
BUDOFFSET | BUDOFFSET Budget Reductions/Offsets | 2019-12-31 | -16 | 0 | 0 | 6001.005 | 6602.85 | 0 | 117-Other | 117-Other
BUDTRKTBD | BUDTRKTBD Budget Adjustments | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
CDNANDA | CDNANDA Corp Dev Anda | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
CFOCAPPRJ | CFOCAPPRJ CFO CAPITAL PROJECTS | 2018-12-31 | 3366.659 | 105620.148 | 0 | 4514.488 | -149434.678 | 0 | 117-Other | 117-Other
CHNANDA | CHNANDA Chairman Anda | (blank) | 0 | 1.35e-13 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
CORPR117G | CORPR117G Corporate Reserve - KYPCO Gen | 2018-12-31 | -2128750 | 0 | 0 | -2980250 | 0 | 0 | 117-Other | 117-Other
CRPTARGET | CRPTARGET CORP CALIBRATION PROJECT | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
DIGITAHUB | DIGITAHUB Digital Hub Project | 2018-12-31 | 0 | -1102.846 | 0 |  |  |  | 117-Other | 117-Other
DISTARGET | DISTARGET Dist Budget Calibration | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
ECNANDA | ECNANDA Telecommunications Anda | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
EDN103172 | EDN103172 Ds Ap Virg-Anda | 1902-01-01 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
EDN103175 | EDN103175 Ds Kp Anda | 1902-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
EDN103177 | EDN103177 Ds Op Anda | 1902-01-01 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
EDN103178 | EDN103178 Ds Pso Anda | 1902-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
EDN103180 | EDN103180 Ds Im Ind-Anda | 1902-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
EDNANDA | EDNANDA Distribution Anda Project | 1902-01-01 | 0 | -7.816e-14 | 0 | 2.7711e-13 | -3.6238e-13 | 0 | 117-Other | 117-Other
EON011324 | EON011324 Line Transformer/Op | 1902-01-01 | 29.857 | 647.696 | 0 | 60.565 | 58.101 | 0 | 117-Other | 117-Other
ETNANDA | ETNANDA Transmission Anda | 1902-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
EVNCBA215 | EVNCBA215 Environmental Cap Blkt APCO | (blank) | 0 | 0 | 0 | -3.64 | 0 | 0 | 117-Other | 117-Other
EVNCBK117 | EVNCBK117 Environmental Cap Blkt KYPCO | (blank) | 0 | 0 | 0 | -261.53 | 0 | 0 | 117-Other | 117-Other
EVNCBW413 | EVNCBW413 Environmental Cap Blkt WPCO | (blank) | -215 | 0 | 0 | -177.33 | 0 | 0 | 117-Other | 117-Other
EVRCB | EVRCB Cap Blkt - Environmental Repl | (blank) | 0 | 0 | 0 | -10.39 | 0 | 0 | 117-Other | 117-Other
EVRCS | EVRCS Cap Stnd - Environmental Repl | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
FANANDA | FANANDA Activity NOT assoc with a PROJ | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
FHGCAPCUT | FHGCAPCUT FHG Capital Cuts | (blank) | -124466.654 | -8067.154 | 0 | -176330.54 | -29026.92 | 0 | 117-Other | 117-Other
FLTADJIRC | FLTADJIRC Fleet Adjustment IRC | (blank) | 0 | -0.002 | 0 | 0 | -0.002 | 0 | 117-Other | 117-Other
GLNANDA | GLNANDA General Ledger Expense | (blank) | 0 | -0.007 | 0 | -3.8725e-13 | -3.9311e-12 | 0 | 117-Other | 117-Other
GWSCB | GWSCB Cap Blkt - Prod Plant Blnkt | 2018-12-31 | 0 | 0 | 0 | -313.68 | 0 | 0 | 117-Other | 117-Other
GWSCBA215 | GWSCBA215 PPB for APCO - Budget Only | (blank) | 1 | 0 | 0 | -204.13 | 0 | 0 | 117-Other | 117-Other
GWSCBI132 | GWSCBI132 PPB I&M - Budget Only | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
GWSCBK117 | GWSCBK117 PPB KPCO - Budget Only | (blank) | 0 | 0 | 0 | 1664.87 | 0 | 0 | 117-Other | 117-Other
GWSCBU420 | GWSCBU420 PPB UNREG PPA 420 | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
GWSCBW413 | GWSCBW413 PPB WPCO - Budget Only | (blank) | 237 | 0 | 0 | 4095.99 | 0 | 0 | 117-Other | 117-Other
GWSCS | GWSCS Cap Stnd - Prod Plant Stnd | 2018-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
INCCAPINV | INCCAPINV Incremental Capital Investment | 2024-12-31 | 0 | -1345871.205 | 0 | 130648.716 | 1325056.392 | 0 | 117-Other | 117-Other
IT117CCIC | IT117CCIC Cloud Computing Imp Cost-KyP G | 2030-12-31 | 0 | 0 | 146093.5 | 0 | 0 | 106531.99 | 117-IT117CCIC | 117-IT117CCIC
ITCAPPROJ | ITCAPPROJ It Capital Projects | 2018-12-31 | -80519.698 | -184418.621 | 0 | 273108.332 | 87917.454 | 0 | 117-Other | 117-Other
ITCB10300 | ITCB10300 AEP Service Corp - Telecom | 2017-12-31 | 0 | -8568.124 | 0 |  |  |  | 117-Other | 117-Other
ITCB11700 | ITCB11700 KENTUCKY POWER - GEN | 2022-12-31 | 0 | 0 | 38173.03 | 0 | 5237.414 | 4676.65 | 117-ITCB11700 | 117-ITCB11700
ITCBLBRTY | ITCBLBRTY KENTUCKY POWER LIBERTY | 2022-12-31 | 0 | 0 | 11977.2 | 0 | 0 | 1241.46 | 117-ITCBLBRTY | 117-ITCBLBRTY
ITCHR0001 | ITCHR0001 IT Chairman Blanket | 2018-12-31 | 2584.176 | 4352.293 | 0 | 5166.03 | 4915.445 | 0 | 117-Other | 117-Other
ITCOP0001 | ITCOP0001 IT Commercial Ops Blanket | 2006-11-01 | 20240.409 | 31686.538 | 0 | 37711.705 | 34134.638 | 0 | 117-Other | 117-Other
ITCT10304 | ITCT10304 Fiber Asset Management Tool | 2025-05-15 | 0 | 3661.195 | 0 | 0 | 24019.696 | 0 | 117-Other | 117-Other
ITCUS1957 | ITCUS1957 Texas SET 5 | 2024-12-31 | 1054.299 | 2263.864 | 0 | 1292.024 | 1209.851 | 0 | 117-Other | 117-Other
ITDIS1952 | ITDIS1952 DIST Interconnect Standardize | 2026-02-27 | 0 | 1374.4 | 0 |  |  |  | 117-Other | 117-Other
ITDIS1987 | ITDIS1987 DIST Hosting Capacity Analysis | 2025-06-30 | 0 | 439.176 | 0 |  |  |  | 117-Other | 117-Other
ITDIS1988 | ITDIS1988 DER Data Repository | 2025-03-31 | 0 | 513.622 | 0 |  |  |  | 117-Other | 117-Other
ITDIS2004 | ITDIS2004 ESRI ELA Extension 2023-2024 | 2023-01-31 | 0 | 2.463 | 0 |  |  |  | 117-Other | 117-Other
ITGEN0004 | ITGEN0004 IT Generation Blanket | 2029-12-31 | 44416.414 | 54606.514 | 0 | 62253.346 | 59672.818 | 0 | 117-Other | 117-Other
ITGEN2000 | ITGEN2000 eSOMS Impl at Rest Fossil Hyd | 2024-12-31 | 0 | 32215.751 | 0 | 28.173 | 11867.46 | 0 | 117-Other | 117-Other
ITGEN2001 | ITGEN2001 Maximo WAM for Generation | 2024-04-30 | 3632.088 | 6367.688 | 0 | -1403.312 | 291.667 | 0 | 117-Other | 117-Other
ITPCLC103 | ITPCLC103 PC Lifecycle CI - 103 | 2025-12-31 | 0 | 1663.377 | 0 |  |  |  | 117-Other | 117-Other
ITPCLC117 | ITPCLC117 PC Lifecycle CI - 117 | 2025-12-31 | 6338.351 | 11266.991 | 1531.77 | 13110.401 | 12494.993 | 4542.91 | 117-ITPCLC117 | 117-ITPCLC117
ITPFP0002 | ITPFP0002 IT Pol Fin & Strat Pln Blanket | 2018-12-31 | 3618.245 | 6093.203 | 0 | 7229.032 | 11142.471 | 0 | 117-Other | 117-Other
ITPFP1742 | ITPFP1742 PeopleSoft Finance 9.2 Upgrade | 2022-05-01 | 0 | 215.813 | 0 |  |  |  | 117-Other | 117-Other
ITPFP1924 | ITPFP1924 ACCT PowerTax Utilization | 2023-05-31 | 0 | 1348.646 | 0 |  |  |  | 117-Other | 117-Other
ITPFP1978 | ITPFP1978 PowerPlan Module Upgrade | 2024-05-31 | 5234.532 | 12070.402 | 0 | 6413.182 | 6004.356 | 0 | 117-Other | 117-Other
ITPFP1986 | ITPFP1986 PeopleSoft 9.2 Rel 2 | 2023-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
ITPFP2007 | ITPFP2007 UI Planner Mod Update | 2024-03-31 | 2034.154 | 7833.456 | 0 | 4617.674 | 4948.138 | 0 | 117-Other | 117-Other
ITPFP2089 | ITPFP2089 PeopleSoft Platform Update | 2025-10-10 |  |  |  | 25191.581 | 62568.416 | 0 | 117-Other | 117-Other
ITSEC1436 | ITSEC1436 Security Blanket | 2018-12-31 | 38407.071 | 56755.796 | 0 | 56421.357 | -2918.179 | 0 | 117-Other | 117-Other
ITSEC1819 | ITSEC1819 Cyber-IronNet | 2025-12-31 | 1532.635 | 2402.506 | 0 | 1875.667 | 1719.712 | 0 | 117-Other | 117-Other
ITSEC1934 | ITSEC1934 Splunk | 2022-12-31 | 0 | 1022.313 | 0 |  |  |  | 117-Other | 117-Other
ITSEC1971 | ITSEC1971 Cyber - Hadoop | 2023-06-30 | 0 | 220.388 | 0 |  |  |  | 117-Other | 117-Other
ITSEC1972 | ITSEC1972 Cyber-Dashbrdng5newDomains | 2023-05-31 | 0 | 272.325 | 0 |  |  |  | 117-Other | 117-Other
ITSEC1974 | ITSEC1974 Cyber-DataPrivcyCompliance | 2023-01-31 | 113.878 | 249.395 | 0 | 139.287 | 131.172 | 0 | 117-Other | 117-Other
ITSEC2037 | ITSEC2037 Cyber-Tulsa IDS Upgrade | 2024-04-30 | 64.424 | 1957.083 | 0 | 78.801 | 74.209 | 0 | 117-Other | 117-Other
ITSEC2077 | ITSEC2077 Cybr-Trellix/McAfee SLA Ren 25 | 2028-10-31 |  |  |  | 10064.541 | 9852.19 | 0 | 117-Other | 117-Other
ITSEC2079 | ITSEC2079 Content Management Upgrade | 2025-12-31 |  |  |  | 4286.32 | 4195.891 | 0 | 117-Other | 117-Other
ITSEC2081 | ITSEC2081 MyAccess Solution Replacement | 2026-06-30 |  |  |  | 8404.237 | 8226.931 | 0 | 117-Other | 117-Other
ITSEC2082 | ITSEC2082 Cyber-Full Packet Capture Soln | 2025-12-31 |  |  |  | 3972.123 | 3888.315 | 0 | 117-Other | 117-Other
ITSEC2091 | ITSEC2091 Cyber Axonius Sec Asst Mgmt | 2025-10-31 |  |  |  | 151.348 | 6693.161 | 0 | 117-Other | 117-Other
ITSEC2106 | ITSEC2106 CyberArk Licensing | 2027-12-31 |  |  |  | 0 | 1648.033 | 0 | 117-Other | 117-Other
ITSEC2115 | ITSEC2115 CyberArk 2025 Expansion-Cpcty | 2025-12-31 |  |  |  | 0 | 1394.661 | 0 | 117-Other | 117-Other
ITSEC2125 | ITSEC2125 Cyber CIRC Logging Alerting | 2025-04-01 |  |  |  | 0 | 1290.147 | 0 | 117-Other | 117-Other
ITSSV0003 | ITSSV0003 IT Shared Services Blanket | (blank) | 269174.681 | 468830.236 | 0 | 382582.716 | 565170.884 | 0 | 117-Other | 117-Other
ITSSV1652 | ITSSV1652 IT SAS Centralized Server | 2022-12-30 | 0 | 297.391 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1750 | ITSSV1750 IT INFR Windows 2012 | 2020-01-01 | 0 | 1100.752 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1781 | ITSSV1781 IT Infrastructure Ent PKI Cert | 2023-12-31 | 0 | 1380.643 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1830 | ITSSV1830 Enterprise Contract Admin | 2022-10-31 | 0 | 83.878 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1834 | ITSSV1834 IT Microsoft Office 365 | 2023-10-31 | 31669.756 | 27583.721 | 0 | 40547.15 | 38041.658 | 0 | 117-Other | 117-Other
ITSSV1903 | ITSSV1903 GDC Network Upgrade | 2024-12-31 | 0 | 11409.919 | 0 | 4.97 | 4495.098 | 0 | 117-Other | 117-Other
ITSSV1912 | ITSSV1912 IT EggPlant Test App | 2023-04-01 | 0 | 388.048 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1915 | ITSSV1915 SCPFO Fleet Virtul Svc Wtr | 2022-05-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1916 | ITSSV1916 DERMS Event Hub | 2024-11-01 | 1250.517 | 2603.403 | 0 | 1533.272 | 1435.874 | 0 | 117-Other | 117-Other
ITSSV1963 | ITSSV1963 HR HCM Modernization | 2025-06-01 | 15850.496 | 28851.882 | 0 | 23668.404 | 37111.476 | 0 | 117-Other | 117-Other
ITSSV1970 | ITSSV1970 Synopsys Code Scanning | 2024-12-31 | 0 | 170.51 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1980 | ITSSV1980 IDAA Appliance Lifecycle | 2022-12-31 | 0 | 13.358 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1998 | ITSSV1998 1RP Comm Closet Upgrade | 2022-11-30 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
ITSSV1999 | ITSSV1999 Cook Business LAN Lifecycle | 2023-12-31 | 0 | 2235.431 | 0 |  |  |  | 117-Other | 117-Other
ITSSV2013 | ITSSV2013 Field Mobility iPAD CI | 2023-12-31 | 0 | 39.033 | 0 |  |  |  | 117-Other | 117-Other
ITSSV2036 | ITSSV2036 Fortress VRM Renewal 2023 | 2023-06-30 | 0 | 13338.462 | 0 |  |  |  | 117-Other | 117-Other
ITSSV2039 | ITSSV2039 ServiceNow Renewal 2023 | 2023-08-31 | 0 | 14680.745 | 0 |  |  |  | 117-Other | 117-Other
ITSSV2043 | ITSSV2043 ARCOS Product Renewal 2024 | 2024-01-01 | 0 | 9128.818 | 0 | 11 | 9934.353 | 0 | 117-Other | 117-Other
ITSSV2063 | ITSSV2063 WAM RBS and Assessment | 2025-12-31 |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
ITSSV2069 | ITSSV2069 IBM Enterprise License Agrmt | 2024-12-31 |  |  |  | 13.87 | 12519.16 | 0 | 117-Other | 117-Other
ITSSV2076 | ITSSV2076 IOS Dell EMC TLA Renewal-2025 | 2025-01-31 |  |  |  | 14472.498 | 20463.343 | 0 | 117-Other | 117-Other
ITSSV2078 | ITSSV2078 IOS Dynatrace Renewal - 2025 - | 2024-12-31 |  |  |  | 68.81 | 17813.772 | 0 | 117-Other | 117-Other
ITSSV2080 | ITSSV2080 IOS Splunk Renewal - 2025-2027 | 2024-12-31 |  |  |  | 50.49 | 13073.988 | 0 | 117-Other | 117-Other
ITSSV2086 | ITSSV2086 ESRI Platform Upgrade 11.3 | 2026-07-30 |  |  |  | 2011.299 | 2242.533 | 0 | 117-Other | 117-Other
ITSSV2087 | ITSSV2087 Esri ELA 2025-2029 | 2025-01-31 |  |  |  | 164.46 | 42579.511 | 0 | 117-Other | 117-Other
ITSSV2092 | ITSSV2092 IOS OpenShift LC - Purch | 2025-01-31 |  |  |  | 36.42 | 18638.918 | 0 | 117-Other | 117-Other
ITSSV2093 | ITSSV2093 IBM Maximo App Suite Agreement | 2029-10-31 |  |  |  | 26.49 | 10205.496 | 0 | 117-Other | 117-Other
ITSSV2096 | ITSSV2096 ServiceNow Contract REN 2024 | 2024-12-31 |  |  |  | 39.79 | 10302.488 | 0 | 117-Other | 117-Other
ITSSV2098 | ITSSV2098 SYNOPSYS SOFTWARE 2025 | 2025-05-01 |  |  |  | 0 | 1220.366 | 0 | 117-Other | 117-Other
ITSSV2100 | ITSSV2100 Process Intelligence | 2025-12-31 |  |  |  | 0 | 13576.09 | 0 | 117-Other | 117-Other
ITSSV2122 | ITSSV2122 IOS OCPU Subscription | 2025-06-30 |  |  |  | 0 | 3320.797 | 0 | 117-Other | 117-Other
ITSSV2128 | ITSSV2128 VMWare ELA | 2025-07-31 |  |  |  | 0 | 10323.116 | 0 | 117-Other | 117-Other
ITTRN1272 | ITTRN1272 Transmission IT Projects Blank | (blank) | 0 | -37151.481 | 0 | -7.54 | -6807.676 | 0 | 117-Other | 117-Other
ITTRN1729 | ITTRN1729 T-Nexus RTO Integration | 2024-01-31 | 0 | 1390.606 | 0 |  |  |  | 117-Other | 117-Other
ITTRN1829 | ITTRN1829 Trans Outage Mgmt (T-Nexus) | 2023-08-30 | 0 | 2220.519 | 0 |  |  |  | 117-Other | 117-Other
ITTRN1844 | ITTRN1844 Trans Field Inspection | 2023-06-30 | 0 | 3211.183 | 0 |  |  |  | 117-Other | 117-Other
ITTRN1848 | ITTRN1848 T-Nexus Master Project | 2024-12-31 | 1694.528 | 3539.852 | 0 | 3686.806 | 3523.23 | 0 | 117-Other | 117-Other
ITTRN1909 | ITTRN1909 Short Circuit Modeling | 2024-12-31 | 0 | 9694.959 | 0 |  |  |  | 117-Other | 117-Other
ITTRN1921 | ITTRN1921 TPS Consolidated 2022 (T-Nexus | 2023-12-31 | 0 | 1086.775 | 0 |  |  |  | 117-Other | 117-Other
ITUOP1404 | ITUOP1404 WebEOC Implementation | 2016-12-31 | 266.729 | 453.759 | 0 | 544.55 | 520.566 | 0 | 117-Other | 117-Other
ITUOP2029 | ITUOP2029 TCOM and DIST Int Dsgn Constr | 2025-12-31 | 397.981 | 1480.463 | 0 | 486.799 | 458.438 | 0 | 117-Other | 117-Other
LGN100315 | LGN100315 Dgc Gen & Adm (Regulated) | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
LGN101644 | LGN101644 Property Sales | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
LGN101704 | LGN101704 Litigation - General | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
LGN102539 | LGN102539 Ext, Media & Policy Comm | (blank) | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
LGN102653 | LGN102653 Video Web Design | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
LGNANDA | LGNANDA Legal/Policy/Cc Anda | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
ML020SP01 | ML020SP01 ML MITCHELL DSI PROJECT | 2023-04-30 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
ML1E25C02 | ML1E25C02 ML1 E COOLING TOWER REPLACMENT | 2023-11-27 | 1636 | 176022.417 | 1338067.75 | 0 | 0 | 10847.36 | 117-ML1E25C02 | 117-ML1E25C02
MLKP26265 | MLKP26265 ML U2 Cooling Tower Reinforce | 2026-12-31 | 309835.968 | 1096610.033 | 185122.93 | 2095605.829 | 1859019.84 | 2390343.87 | 117-MLKP26265 | 117-MLKP26265
MLKYELGFL | MLKYELGFL MLP KY ELG CPCN Filing 2025 | 2025-06-30 |  |  |  | 0 | 0 | 117846.22 | 117-MLKYELGFL | 117-Other
MLL1CGRPL | MLL1CGRPL ML U1 Clinker Grinder Rpl - KY | 2024-05-31 | 46002.795 | 43997.027 | 88526.56 | 209458.753 | 202987.471 | 180868.78 | 117-MLL1CGRPL | 117-MLL1CGRPL
MLL2CGRPL | MLL2CGRPL ML U2 Clinker Grinder Rpl - KY | 2024-05-31 | 0 | 133452.945 | 99308.04 | 276.37 | 0 | 80075.8 | 117-MLL2CGRPL | 117-MLL2CGRPL
MLLEC1VHL | MLLEC1VHL ML E U1 VHP/HP&LPA Turbn Insp | 2023-11-30 | -51 | 298295.199 | 589446.77 | 0 | 0 | 9.25 | 117-MLLEC1VHL | 117-MLLEC1VHL
MLLEP2LA0 | MLLEP2LA0 ML2 LPA L0 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  |  | 166.05 | 0 | 275693.84 | 117-MLLEP2LA0 | 117-Other
MLLEP2LA1 | MLLEP2LA1 ML2 LPA L1 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  |  | 53.13 | 0 | 89424.99 | 117-MLLEP2LA1 | 117-Other
MLLEP2LB0 | MLLEP2LB0 ML2 LPB L0 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  |  | 166.05 | 0 | 275693.84 | 117-MLLEP2LB0 | 117-Other
MLLEP2LB1 | MLLEP2LB1 ML2 LPB L1 Rtr Rpr at CMS KPCo | 2026-06-01 |  |  |  | 53.13 | 0 | 89424.99 | 117-MLLEP2LB1 | 117-Other
MLLEP2LBI | MLLEP2LBI ML E U2 LPB Turb Insp Liberty | 2022-12-31 | 0 | 0 | -683.25 |  |  |  | 117-Other | 117-MLLEP2LBI
MLLHAULRD | MLLHAULRD Mitchell Haul Road Relocate | 2024-11-30 | 0 | 803113.555 | 38130.27 | 0 | 132484.647 | 922405.75 | 117-MLLHAULRD | 117-MLLHAULRD
MLLPC0ELG | MLLPC0ELG ML PCC U0 ELG/CCR Comply - 117 | 2024-12-31 | 1592280.603 | 1782234.37 | 5316591.99 | 2670112.993 | 3414944.798 | 2295473.46 | 117-MLLPC0ELG | 117-MLLPC0ELG
MLLPC0LIM | MLLPC0LIM ML PCC U0 Lime Conversion 117 | 2023-12-31 | 0 | -33291.033 | 86736.6 | 0 | 0 | 153.62 | 117-MLLPC0LIM | 117-MLLPC0LIM
MLLPC2CTC | MLLPC2CTC ML PCC U2 Cooling Twr Cmp 117 | 2022-12-31 | 0 | -174.942 | 7597.29 |  |  |  | 117-Other | 117-MLLPC2CTC
MLLPC2ESP | MLLPC2ESP ML PCC U2 ESP Upgrades 117 | 2022-12-31 | 0 | -50470.045 | 46506.43 | 0 | 0 | -3500.45 | 117-MLLPC2ESP | 117-MLLPC2ESP
MLLPCT1BP | MLLPCT1BP ML U1 Cooling Tower Canopy KYP | 2024-06-10 | 0 | 682955.453 | 960485.58 | 0 | -69142.593 | -330841.72 | 117-MLLPCT1BP | 117-MLLPCT1BP
MLLPCT1PC | MLLPCT1PC ML1 Cool Twr Canopy PreCI KPCo | 2025-11-30 | 0 | 299894.262 | -166914.05 | 0 | 0 | 167127.65 | 117-MLLPCT1PC | 117-MLLPCT1PC
MLLPPBSHD | MLLPPBSHD ML Minor PPB Liberty Shadow | (blank) | 325979.409 | 2030564.039 | 2910154.09 | 1713510.134 | 2109996.758 | 2596663.83 | 117-MLLPPBSHD | 117-MLLPPBSHD
MLLSC1AHB | MLLSC1AHB ML S U1 Air Htr Bskt Rplc Lbty | 2023-12-31 | 233 | 463303.058 | 550116.59 | 0 | 0 | -44229.47 | 117-MLLSC1AHB | 117-MLLSC1AHB
MLLSC2AHB | MLLSC2AHB ML S U2 Air Htr Bskt Rplc Lbty | 2022-12-31 | 0 | 524.83 | 1500.41 | 0 | 0 | 0 | 117-Other | 117-MLLSC2AHB
MLLVC1CL1 | MLLVC1CL1 Mitchell U1 SCR Catalyst L1 | 2025-05-31 |  |  |  | 274790.474 | 273686.078 | 332314.66 | 117-MLLVC1CL1 | 117-Other
MLLVC2CL4 | MLLVC2CL4 ML V U2 Cat Layer 4 Rplc Lbty | 2022-12-31 | 0 | 349.885 | 50.72 |  |  |  | 117-Other | 117-MLLVC2CL4
MLWEC2HSI | MLWEC2HSI ML E U2 HP&2RH Trb & Rtr Insp | 2026-05-25 |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
MLWEP1LAR | MLWEP1LAR ML E U1 LPA Turbn Rotor Rep | 2023-11-30 | 0 | 210608.906 | 0 |  |  |  | 117-Other | 117-Other
MLWEP1RHR | MLWEP1RHR ML E U1 HP 1stRH Rem Rtr Rpr | (blank) | 0 | 38493.146 | 0 |  |  |  | 117-Other | 117-Other
MLWEP2LAR | MLWEP2LAR ML E U2 LPA Rotor Repr at CMS | 2026-06-01 | 187881.195 | 183034.248 | 0 | 219276.128 | 204069.984 | 0 | 117-Other | 117-Other
MLWEP2LBR | MLWEP2LBR ML E U2 LPB Rotor Repr at CMS | 2026-12-31 | 187881.195 | 183034.248 | 0 | 219276.128 | 204069.984 | 0 | 117-Other | 117-Other
MLWEPCPLC | MLWEPCPLC ML E Critical PLC Replacements | (blank) |  |  |  | 3035.621 | 3024.912 | 0 | 117-Other | 117-Other
MLWEPCWPS | MLWEPCWPS ML E Circ Water Pump Cap Spare | (blank) |  |  |  | 10483.822 | 10345.06 | 0 | 117-Other | 117-Other
MLWEPELVC | MLWEPELVC ML E Elevator Controls Upgrade | (blank) |  |  |  | 8024.159 | 7906.805 | 0 | 117-Other | 117-Other
MLWEPNPCS | MLWEPNPCS ML E Nash Pump Cap Spare | (blank) |  |  |  | 17767.83 | 17507.945 | 0 | 117-Other | 117-Other
MLWEPRVOS | MLWEPRVOS ML E Reverse Osmosis Rpl | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
MLWEPSTRN | MLWEPSTRN ML E Strainer Replacements | (blank) |  |  |  | 15749.16 | 15748.557 | 0 | 117-Other | 117-Other
MLWEPXPPT | MLWEPXPPT ML E Exciter PPT Xfrmr Repl | (blank) |  |  |  | 10631.007 | 10584.059 | 0 | 117-Other | 117-Other
MLWES2BTI | MLWES2BTI ML2 E BFPT INSPECTION | (blank) |  |  |  | 0 | 0 | 0 | 117-Other | 117-Other
MLWMPGGBX | MLWMPGGBX ML M Gypsum GRBX Cap Spare | (blank) |  |  |  | 8597.343 | 8471.586 | 0 | 117-Other | 117-Other
MLWMPGRBX | MLWMPGRBX ML M Gearbox Rebuild PPB | (blank) |  |  |  | 1719.456 | 1694.313 | 0 | 117-Other | 117-Other
MLWMPHSGB | MLWMPHSGB ML M HS Coal GRBX Cap Spare | (blank) |  |  |  | 26537.194 | 26185.934 | 0 | 117-Other | 117-Other
MLWMPLGBX | MLWMPLGBX ML M Limestone GRBX Cap Spare | (blank) |  |  |  | 8845.735 | 8728.645 | 0 | 117-Other | 117-Other
MLWMPPOND | MLWMPPOND ML M N CY Pond Trtmnt Facility | (blank) |  |  |  | 20633.592 | 20331.811 | 0 | 117-Other | 117-Other
MLWNPLABR | MLWNPLABR ML N Capital Labor Budgeting | (blank) | 25806.1 | 59511.376 | 0 | 56173.321 | 50323.844 | 0 | 117-Other | 117-Other
MLWSP1LSO | MLWSP1LSO ML S U1 Lower Sidewl Weld Ovly | 2023-11-30 | 12 | 309647.491 | 0 |  |  |  | 117-Other | 117-Other
MLWSPBECK | MLWSPBECK ML S Brnr Rgstr Sleeve Drv Rpl | (blank) |  |  |  | 10316.808 | 10165.902 | 0 | 117-Other | 117-Other
MLWSPBLWR | MLWSPBLWR ML S Blowers & Fans Rplc | (blank) | 3847.003 | 14285.993 | 0 | 8697.619 | 8140.575 | 0 | 117-Other | 117-Other
MLWSPOILL | MLWSPOILL ML S Oil Lighter Replacements | (blank) |  |  |  | 13491.6 | 13444.057 | 0 | 117-Other | 117-Other
MLWSPPDMP | MLWSPPDMP ML S PULV DAMPER REPL (OUT) | (blank) |  |  |  | 20237.399 | 20166.087 | 0 | 117-Other | 117-Other
MLWSPPEXP | MLWSPPEXP ML S Pulv Exp Joint Repl | (blank) |  |  |  | 18024.375 | 17960.855 | 0 | 117-Other | 117-Other
MLWSPPLVY | MLWSPPLVY ML S Pulverizer Yoke Rplc | (blank) | 11 | 9144.881 | 0 |  |  |  | 117-Other | 117-Other
MLWSPSJNT | MLWSPSJNT ML S Burner Line Slip Jnt Repl | (blank) |  |  |  | 12142.442 | 12099.65 | 0 | 117-Other | 117-Other
MLWVC2CL1 | MLWVC2CL1 ML V U2 SCR Catalyst Layer 1 | 2033-08-10 | 2053 | 0.151 | 0 | 2854 | 0 | 0 | 117-Other | 117-Other
MLWVPBMIL | MLWVPBMIL ML V Ball Mill Inlt Liner Repl | (blank) |  |  |  | 8989.509 | 8985.878 | 0 | 117-Other | 117-Other
MLWVPOXAB | MLWVPOXAB ML V Oxidation Air Blowers | (blank) |  |  |  | 1650.689 | 1626.545 | 0 | 117-Other | 117-Other
P17CC1007 | P17CC1007 APCo - Virginia D Projects | 2022-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
P17CC1031 | P17CC1031 OHPCo - D Projects | 2022-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
SSGSNANDA | SSGSNANDA Shared Services-Accumulate Gen | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
SSHRNANDA | SSHRNANDA Accumulate Gen & Admin HR Exp | (blank) | 0 | 0 | 0 | -2.1205e-14 | 0 | 0 | 117-Other | 117-Other
SSITNANDA | SSITNANDA Accumulate Gen _ Admin IT Exp | (blank) | 0 | 0 | 0 | 0 | 1.3856e-13 | 0 | 117-Other | 117-Other
SSNANDA | SSNANDA Shared Services Anda | (blank) | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
TDOANDA | TDOANDA T And D Other Anda | (blank) | 0 | 0 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
TLSWEMERG | TLSWEMERG TRANS Project Labor | 1902-01-01 | 0 | -1.1369e-13 | 0 | 0 | 0 | 0 | 117-Other | 117-Other
TSCREDITC | TSCREDITC Tech Servics Cap Offset Credit | 2024-12-31 | -28827.335 | -74637.504 | 0 | -64273.554 | 4874.996 | 0 | 117-Other | 117-Other
WSNANDA | WSNANDA Generation ANDA | (blank) | 0 | 8.5265e-13 | 0 | 0 | 2.558e-13 | 0 | 117-Other | 117-Other
WSX114322 | WSX114322 Eng'r Svc. Capital Staff Budge | 2013-05-12 | 2.6645e-14 | 0 | 0 | -8.8995e-13 | 1.7408e-13 | 0 | 117-Other | 117-Other
WSXRENEWC | WSXRENEWC Renewable Capital Staff Budget | (blank) | 0 | 0 | 0 | 0 | 9.0949e-12 | 0 | 117-Other | 117-Other
X00000288 | X00000288 For Property Acctg Use Only | (blank) | 0 | 0 | -247320.04 | 120.39 | 0 | 37645.26 | 117-Other | 117-Other
X00000290 | X00000290 For Property Acctg Use Only | (blank) | 30619.835 | 100646.056 | 0 | 115393.43 | 172058.788 | 0 | 117-Other | 117-Other
X00116261 | X00116261 Pro Serv Capital All Reg Gener | (blank) | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP103 | XHWCAP103 HW CAP CI - 103 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP114 | XHWCAP114 HW CAP CI - 114 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP117 | XHWCAP117 HW CAP CI - 117 | 2025-12-31 | 0 | 0 | 18884.8 | 156.5 | 0 | 118353.17 | 117-XHWCAP117 | 117-XHWCAP117
XHWCAP120 | XHWCAP120 HW CAP CI - 120 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP150 | XHWCAP150 HW CAP CI - 150 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP160 | XHWCAP160 HW CAP CI - 160 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP169 | XHWCAP169 HW CAP CI - 169 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP180 | XHWCAP180 HW CAP CI - 180 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP190 | XHWCAP190 HW CAP CI - 190 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP192 | XHWCAP192 HW CAP CI - 192 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP194 | XHWCAP194 HW CAP CI - 194 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP200 | XHWCAP200 HW CAP CI - 200 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP250 | XHWCAP250 HW CAP CI - 250 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP380 | XHWCAP380 HW CAP CI - 380 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
XHWCAP385 | XHWCAP385 HW CAP CI - 385 | 2025-12-31 | 0 | 0 | 0 |  |  |  | 117-Other | 117-Other
| Grand Total |  | 2920480.502 | 14741464.239 | 12954356.63 | 22431976.882 | 29939432.045 | 21089786.23